**CO MEXICO**

**MONITORING, EVALUATION AND RESEARCH PLAN 2014-2019**

**UPDATED: 8 October 2018**

| **Activity**  | **Partners and stakeholders**  | **Planned Dates (Month and year of start and end)** | **Budget** |
| --- | --- | --- | --- |
| Source | Amount |
| **MONITORING** |
| Periodic monitoring of core and non-core projects (programmatic activities & delivery) | Internal exercise | Monthly basis | Core | Covered by CO Human Resources |
| CO Quarterly progress report  | RMS based exercise | April/ June/ September/ December of each year | Core | Covered by CO Human Resources |
| CO Annual Progress Report | RMS based exercise | Annual basis- November-December of each year | Core | Covered by CO Human Resources |
| Annual UNDAF Logframe Monitoring System | RC Office, UNCT, Ministry of Foreign Affairs through AMEXCID | April- May each year (reporting past year) | RC Office |  |
| Strategic Note Mid-Term Review | HQs Programmatic Division and LAC-Centre / Internal exercise | July-November 2017 | Core | US$ 6000 |
| **RESEARCH** |
| Analyses (qualitative and quantitative) on the participation of women in decision making positions in the legislative bodies at federal level. Systematization of the lessons learnt, the political model and the political, legislative and judicial tools to ensure the political and electoral right of women:* “Iniciativa SUMA: Democracia es Igualdad. Una ruta mexicana de aprendizaje compartido” (SUMA Initiative: Democracy is Equality. The Mexican path to shared policy learning)
* “Iniciativa SUMA, democracia es igualdad. Modelo para la Participación Política y el Empoderamiento Económico de las Mujeres” (SUMA Initiative: Democracy is Equality. Model for the Political Participation and the Economic Empowerment of Women)
* “Los Derechos Políticos de las Mujeres y Cómo Defenderlos” (Women’s Political Rights and How to Defend Those Rights)
 | SUMA, INMUJERES | Project implemented 2013- 2015 (finalized) | Cost-Sharing INMUJERES& core  | US$ 25,000  |
| Mapping exercise on the state of implementation of CEDAW General Recommendation 26 * “Legislación Mexicana y Derechos de las Trabajadoras Migrantes: un análisis del cumplimiento de la Convención sobre la Eliminación de todas las formas de Discriminación Contra la Mujer (CEDAW) y su Recomendación General no. 26 sobre trabajadoras migrantes en la legislación” (Mexican Legislation and Women Migrant Workers’ Rights: an Analysis of the implementation of the CEDAW and its General Recommendation no. 26 on women migrant workers in legislation)
* “Guía para desarrollar legislación migratoria con perspectiva de género en México” (Guide to Developing Migratory Legislation with a Gender Perspective in Mexico)
* “Compromisos de México con los derechos humanos de las trabajadoras migrantes” (Mexico´s commitment to the Human Rights of Women Migrant Workers))
 | Ministries of Interior, Foreign Affairs and Labor, Legislative Commission on Migration Affairs, INMUJERES, UNHCR, IOM, CSOs, COLMEX, COLEF (Norte y Sur), IMUMI(Instituto para las Mujeres en la Migración, A.C. IMUMI), INSP (Instituto Nacional de Salud Pública) | Activity initiated in 2013Launching and dissemination: January 2014EU financed multi-country Project 2014-2017 | Non-core, core | US$ 6,000  |
| Diagnosis on the situation of migrant women* “Derechos de las trabajadoras migrantes Mexico plan 2013-2018” (Women Migrant Workers’ Human Rights: Mexico Plan 2013-2018)
* “Las trabajadoras migrantes centroamericanas en Chiapas. Recomendaciones de política pública para garantizar el ejercicio de sus derechos” (Central American Women Migrant Workers in Chiapas: Public policy Recommendations to guarantee the exercise of their rights)
* “Las trabajadoras migrantes en la frontera sur de México. Hacia una agenda de investigación” (Women Migrant Workers at Mexico’s Southern Border: Towards a Research Agenda)
* “Serie Transformar Nuestro Mundo: Derechos humanos de las trabajadoras migrantes” (“Transforming Our World: Human Rights of Women Migrant Workers”)
* “[Situación de las mujeres trabajadoras migrantes. Síntesis analítica del Encuentro Internacional sobre la Situación de las Mujeres Trabajadoras Migrantes”.](http://mexico.unwomen.org/es/digiteca/publicaciones/2017/08/mujeres-trabajadoras-migrantes) (Situational análisis of women migrant workers’ in Mexico)
* “Análisis sobre las percepciones populares y estereotipos en torno a las trabajadoras migrantes centroamericanas en Chiapas” (Analyse on popular perceptions and stereotypes concerning women migrant workers in Mexico)
* “Las mujeres trabajadoras migrantes, el envío de remesas y la generación de cadenas en el corredor Chiapas-Centroamérica” (Women Migrant Workers, Remittances and the Creation of Global Care Chains in the Chiapas-Central American Corridor)
* Infografía: “Mujeres migrantes centroamericanas en la frontera sur de México” (Infographic: Central American Women Migrant Workers on Mexico´s southern border)
* Buenas prácticas del proyecto “Promoción y protección de los derechos de las trabajadoras migrantes” (Promotion and protection of the women migrant workers rights)
 | Ministries of Interior, Foreign Affairs and Labor, Legislative Commission on Migration Affairs, INMUJERES, UNHCR, IOM, CSOs, COLMEX, COLEF (Norte y Sur), IMUMI(Instituto para las Mujeres en la Migración, A.C. IMUMI), INSP (Instituto Nacional de Salud Pública) | 2013-2017Launching and dissemination: January 2014EU financed multi-country Project 2014-2107 | Non-core | US$ 27,054  |
| Evidence based knowledge products on women's time use and unpaid work* “Por un sistema social y económico para la vida. Agenda pública para hacer realidad el derecho al cuidado” (2016)
* “Trabajo doméstico y de Cuidados no remunerado” (2016) (Domestic and unpaid care work)
* “El trabajo de cuidados: una cuestión de derechos humanos y políticas públicas” (2018) (Care work: a human rights and public policy issue)
 | COLMEX, INEGI, INMUJERES, OECD, ILO and the Division for Gender Affairs ECLAC | 2015-2018 | Core  | $23,617.02 |
| Development of “Women’s Economic Atlas” with Key indicators on Women’s Economic Empowerment in Mexico. | INMUJERES, INEGI | 2017 | Core | US$ 8,606 |
| Knowledge products to promote women’s economic empowerment in their operations (IFAD project/State of Oaxaca).* Voces del terreno: 30 historias de mujeres emprendedoras. (Voices from the field: 30 stories of women entrepreneurs)
* Tool kit (“Caja de herramientas”) clau
 | TBD with Guatemalan CO | Guatemalan CO | IFAD | TBC |
| Research on violence against women HR defenders/advocates:* Metodología de revisión de mecanismos de protección para las defensoras 2017. (Methodology for reviewing protection mechanisms for women defenders 2017)
* Application of methodology in 2018.
 | UNHCHR, Just Associates, Women’s Human Rights Defenders  | 2016-2018 | Core funding | US$ 13,000 |
| Research studies to detect strengths and weaknesses on violence against women’s administrative records and suggestions for improvements in targeted states* Violencia contra las mujeres: propuestas de mejora en la atención y en la medición para el fortalecimiento de políticas públicas (análisis de los derechos humanos de las mujeres que se violan o vulneran en los códigos civiles, penales y de procedimientos vigentes en las 32 entidades federativas y en el nivel federal
 | INMUJERES, Parliamentarian feminicide Commission, INEGI and stakeholders at State level | 2015-2016 | Cost-Sharing INMUJERES(Hard Pipeline) | Approximately US$ 2,331.10-6000.00 |
| Research studies on feminicide violence at national level and 32 state fascicules | IP: COLMEX, Red de Investigadoras por la vida y la libertad de las mujeres; Strategic partners:INMUJERES, Parliamentarian feminicide Commission, INEGI and stakeholders at State level, CIMAC  | 2014-2019(the research studies are updated bi-annually) | CORE | US$ 16,661.03 |
| Monitoring of changes in legislation regarding crimes committed against women in accordance with international standards thru the revision of laws, civil and penal codes and protocols of each Mexican State.* “[Hacia un sistema integrado de información estadística sobre impartición de justicia con perspectiva de género y Derechos Humanos](http://mexico.unwomen.org/es/digiteca/publicaciones/2017/07/justicia-con-perpectiva-de-genero-y-derechos-humanos)” (Towards an integrated statistical information system on gender justice and human rights)
* [Armonización legislativa para la no discriminación y la protección de los Derechos Humanos de las mujeres en el estado de Coahuila de Zaragoza](http://mexico.unwomen.org/es/digiteca/publicaciones/2016/01/armonizacion-legislativa-coahuila). (Legislative harmonization for non-discrimination and protection of the human rights of women in the state of Coahuila de Zaragoza)
 | TBD accordingly with the project work plan | 2014-2016 | EU | US$ 47,827.24(35,000€) |
| Systematization of major gaps to incorporate CEDAW and CTM in the federal and state legal and policy frameworks (in the frame of country periodic reporting)  | UNS (Gender Thematic Group) | 2017-2018 | Gender Thematic GroupCore funds | US$ 5,000 |
| Legislative diagnosis in targeted states and Municipalities on GRB and elaboration of tools for the incorporation of a gender equality perspective in public budgets:* Hacia una metodología de Marco Lógico con Perspectiva de Género (Towards a logical framework methodology with a gender perspective)
* Perspectiva de género en la legislación y normatividad estatales. Síntesis de Entidades Federativas. (Gender perspective in state legislation and norms. Summary of federal entities)
* “Experiencias internacionales en la elaboración de presupuestos públicos con perspectiva de género” (International Experiences in the Elaboration of Public Budgets with a Gender Perspective)
* “Referentes conceptuales de los presupuestos con perspectiva de género” (Conceptual References for Budget with a Gender Perspective)
* “Presupuestos con perspectiva de género en el nivel federal y estatal en México” (Budgets with a Gender Perspective at Federal and State Level in Mexico)
* Inclusión transversal de la Perspectiva de Género en el “Diplomado de Presupuesto basado en Resultados (PbR)” (Mainstreaming of a Gender Perspective in the “Course on Results Based Budgets”)
* Inclusión transversal de la Perspectiva de Género en el “Diplomado de Presupuesto basado en Resultados (PbR)”: Módulo específico de género para el Diplomado Presupuesto basado en Resultados (PbR) (Tranversal Inclusion of the Gender Perspective in the “Course on Results Based Budgets”: Specific Module on Gender for the “Course on Results Based Budgets”)
* “La igualdad entre mujeres y hombres en la información presupuestaria: Diagnóstico de la información presupuestaria a nivel estatal” (Equality between Women and Men in Budgetary Information: Diagnosis of budgetary information at state level)
* “Presupuestación con Enfoque de Género en México” (Budgeting with a Gender Focus in Mexico)
 | IP. EQUIDAD Y GENERO, ILSB, FLACSO, Strategic Partners: INMUJERES, State Governments, State Parliaments, Local Women’s machineries.CIDE, UNAM | 2014-2015(Number and dates of diagnosis depending on targeted states for each year) | Cost-sharingINMUJERES | US$ 68,000 |
| Incorporating gender and intercultural perspectives into justice administration at federal level, elaboration of position papers, systematization of experiences etc. * [Mujeres Indígenas, Derechos Humanos y Acceso a la Justicia](http://mexico.unwomen.org/es/digiteca/publicaciones/2016/01/mujeres-indigenas-dh-acceso-justicia)
 | IFIW, Interinstitutional Committee on Gender Equity of the Federal Justice Power | Last quarter of 2015/2016  | Core /Non Core | $2,741.28 |
| Flagship programme “Safe Cities and Public Spaces for Women and Girls”* Fact Sheet del Programa Insignia "Ciudades Seguras México" (completed)
* Buenas prácticas para prevenir y eliminar la violencia sexual contra las mujeres y las niñas en los espacios públicos (completed)
* Buenas prácticas y lecciones aprendidas del Programa Safe Cities (ongoing- January 2019)
* Manual técnico operativo con PEG (ongoing-December 2018)
* Fact Sheet del Programa Insignia "Ciudad Segura TORREÓN" (completed)
* Programa Ciudades y Espacios públicos seguros para mujeres y niñas en la ciudad de Torreón (completed)
* Diagnóstico sobre la violencia contra las mujeres y las niñas en los espacios públicos de Torreón, Coahuila (completed)
* Programas y acciones desarrolladas por la Secretaría de las Mujeres en apoyo a la transversalización de la perspectiva de género en el Estado de Coahuila (2014-2016) (completed).
* Brochure"Programa Ciudades y Espacios Públicos seguros para mujeres y niñas en el municipio de Torreón, Coahuila (completed)
* Fact Sheet del Programa Insignia "Ciudad Segura PUEBLA" (ongoing-November 2018)
* Programa para la prevención y atención del acoso y otras formas de violencia sexual contra las mujeres y las niñas en los espacios públicos de la ciudad de Puebla (completed)
* Diagnóstico y Documento de programa con diagnóstico de Puebla (completed)
* Fact Sheet del Programa Insignia "Ciudad Segura CDMX"
* Diagnóstico sobre la violencia contra las mujeres y las niñas en el transporte público de la Ciudad de México (ongoing- November 2018)
* Encuesta sobre la Violencia Sexual en el transporte y otros espacios públicos en la Ciudad de México (ongoing)
* Fact Sheet del Programa Insignia "Ciudad Segura GUADALAJARA" (ongoing- November 2018)
* Diagnóstico sobre la violencia contra las mujeres y las niñas en el transporte público en Guadalajara (completed)
* Fact Sheet del Programa Insignia "Ciudad Segura MONTERREY" (ongoing- November 2018)
* Diagnóstico sobre la violencia contra las mujeres y las niñas en el transporte público en Monterrey (ongoing- December 2018)
 | Estudios y Estrategias para el Desarrollo y la Equidad, A.C. (EPADEQ); INMUJERES CDMX; Instituto Municipal de la Mujer de Torreón; El Colegio de México; Instituto Municipal de la Mujer Monterrey, Municipalidad de Guadalajara, Municipalidad de Puebla. | Last quarter of 2018 | Non-core  | 311,128.25 |
| Overview of the progress in gender statistics in the region, brochures in Spanish and English on: 1) statistics regarding women’s time use and unpaid work, 2) the UNW strategy in gender statistics for public policy use; 3) strategic alliance between INEGI, INMUJERES Mexico, UN Women and ECLAC in LAC.Serie transformar nuestro mundo (2016): “Matrimonio y uniones tempranas de niñas”; [La Democracia Paritaria. Un acelerador de la igualdad sustantiva y del desarrollo sostenible en México](http://mexico.unwomen.org/es/digiteca/publicaciones/2017/03/democracia-paritaria); [La hora de la igualdad sustantiva. Participación política de las mujeres en América Latina y el Caribe Hispano](http://mexico.unwomen.org/es/digiteca/publicaciones/2015/10/la-hora-de-la-igualdad). | INEGI, NSOs, INMUJERES, and the Division for Gender Affairs ECLAC | Completed | Core funds | ApproximateUS$ 15,000-20,000 |
| Assessment of governance for gender equality in Mexico. Two main products will be developed:-Six communicational products about the governance for gender equality.-Systematization and analysis of strategies to incorporate the National Programme of Equity and non-discrimination against women 2013-2018 (PROIGUALDAD) in the institutional and regulatory structure of Mexican institutions. | INMUJERES and UN Women | Last quarter of 2018  | Non-core funds | US$ 26,546 |
| In the framework of the Project “Alliance UN Women – Danone to promote equal opportunities for women and men and women´s economic empowerment”:* Baseline study
 | UN Women | Third quarter of 2018 (ongoing) | Non-core funds | US$ 15,000 ($276,544 mxn)  |
| Development of qualitative and quantitative products in the framework of the Project “UN Women Second Chance Education and Vocational Learning Programme”:* Baseline Study (TBD)
* Country Needs Assessment
 | UN Women | Last quarter of 2018 and first quarter of 2019 | Non-core funds | US$ 35,000 |
| Systematization and analysis of judicial decisions on women’s political electoral rights and political VAW. | UN Women in coordination with Federal Electoral Court and other key stakeholders. | 2019 | Non-core funds | US$ 191,387 |
| Follow-up on elected women through specialized study focusing on exercise of political rights and capacity assessment of women on the local level | UN Women | 2019 | Core Fund | US$ 3,000 |

**Evaluation Plan 2014-2019**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Evaluation name** | **Mandatory?****(Y/N)** | **UNDAF Outcome/ UN Women SP Goal, Outcome** | **Country/ MCO/ RO AWP Output** | **Office in charge** | **Region/ country** | **Joint activity****(Y/ N, indicate partners)** | **Key Stakeholders** | **Planned Dates****(start-end)** | **Budget (US$) / Sources of Funding** | **Status (pending/ initiated/ ongoing/ completed)** | **Remarks** |
| **Evaluations managed by the office** |  |
| INMUJERES-UN WOMEN Projects 2013-2018 | Y | UNDAF V priority area/SP 1.1, 3.1 and 5.1 | Mexico AWP-DRF Output 1.1.1, 1.1.2, 3.1.2 and 4.1.2. | Mexico CO | Mexico and targeted states | YINMUJERES | INMUJERES, SUMA-Initiative, federal state electoral institutions, electoral justice tribunals, political parties, state governments  | 2018  |  | Cancelled | This evaluation was changed to knowledge products about governance for gender equality in See page 6.  |
| Final evaluation of #NoEsdeHombres Campaign | N | UNDAF Direct Effect 9DRF Goal 3Outcome 3.2 | Mexico AWP-DRF Output 3.2.2  | Mexico CO | Mexico | N | Inmujeres Mexico City | 2017 | $48,652 | Completed |  |
| Evaluation of EVAW Campaign (16 days of activism, 2018) | N | SP Output 11 | Mexico AWP DRF Output 3.3.1 & OEEF Output cluster 4.3 | Mexico CO | Mexico  | N | EmbassiesPrivate SectorMedia influencersUNCT | November- December 2018 | $15,200 | Pending- will initiate in November 2018 | LTA process |
| Final Evaluation of Mexico Strategic Note 2014-2019 | Y | OEEF Output cluster 2 | Mexico AWP OEEF Output Cluster 2 | Mexico CO | Mexico |  | Government parties | 2019 | US$ 8,000Core/Non-core $20,000-30,000 |  |  |
| **Evaluations in which the office participates** |  |
| Final evaluation of the SUMA FGE-project: “*Strengthening Women's Political Participation and Promoting an**Economic Empowerment Agenda”* | Y | UNDAF V priority area/SP 1.1  DRFGoal 1Outcome 1.1 | Mexico AWP Output1.1.1 | HQ | Mexico (federal and 14 States) | Y (FGE) | Implementing partners (CSOs), NWMs, Federal Electoral Institute, Federal Electoral Justice Tribunal, Political Parties, State Governments, State Parliaments, among others | 2014 | FGE $10,000 | Completed |  |
| Final evaluation UNTF grantee:“Contributing to the Effective Implementation of the General Law onWomen’s Access to a Life Free from Violence in Mexico and theRecommendations by the Inter-American Court of Human Rights in the “Campo Algodonero” Case | Y | SP Impact 3 | Mexico AWP Output3.2.1 | HQUNTF-EVAW | Mexico | N | Católicas por el Derecho a Decidir- Mexico, National Citizen Observatory on Feminicide | December 2014 | UNTFUS$ 18,575 | Completed |  |
| Regional Evaluation on Access to Justice as a Prevention Mechanism to End Violence against Women | N | SP Impact 3 | México AWP Outcome 3 | HQ | 4 Countries: México Case Study | N | Implementing partners (CSOs), NWMs, Federal Electoral Institute, Federal Electoral Justice Tribunal, Political Parties, CSO | 2015-2016 | Regional Office | Completed |  |
| Corporate Evaluation of UN-Women’s Contribution to UN-system Coordination on Gender Equality and the Empowerment of Women | N | SP Impact 1 | México AWP Outcome 1 | HQ | Multi-Country: México Case Study | N | CO México, Implementing Partners | 2015-2016 | HQ | Completed |  |
| UNDAF Mid-Term Review | Y | UNDAF Paragraph 6. MonitoringEvaluation and Communications | México AWPOEEF Output 2.2. | RC Office | México | Y/ UNS | RC Office, UNCT, Ministry of Foreign Affairs through AMEXCID |  September 2017  | TBD by RC Office | Completed |  |
| Corporate Evaluation of UN Women Strategic Partnerships for Gender Equality and Women’s Empowerment | N | UNDAF V Priority area/ SP 12.1 |  | HQ | 30 countries | N | Awaiting information from HQs | 2016 | HQ | Completed |  |
| Final evaluation of theEuropean Union project: Strengthening institutional capacities in the justice sector to protect women’s right to a life free of violence | Y | UNDAF IV Priority area/SP 3.1 | Mexico AWP Output 3.1.2 | HQ | Albania,Mexico and Timor Leste | Awaiting information from HQs | Awaiting information from HQs | Last quarter of 2016, to be defined by the UE | EU$54,849.63 (for the 3 countries) | Completed |  |
| Final evaluation of theEuropean Union project: Thematic Programme of Cooperation with Third Countries in the Areas of Migration and Asylum | Y | UNDAF IV Priority area/SP 2.1 | Mexico AWP Output 2.1.1 | HQ | Mexico, Moldova and Philippines  | Awaiting information from HQ | Awaiting information from HQ | Last Quarter of 2016, to be defined by the UE | EU | Completed |  |
| Final Evaluation of UNDAF 2014-2019 | Y | UNDAF Paragraph 6. Monitoring Evaluation and Communications | México AWPOEEF Output 2.2. | RC office | Mexico | YUNS | RC Office, UNCT, Ministry of Foreign Affairs through AMEXCID | 2019  | TBD by RC Office | Planned |  |
| Final evaluation of the IFAD project: Broadening Economic Opportunities for Rural Women Entrepreneurs In Lac Region (BeO) | Y | UNDAF II priority area/SP2.2 | Mexico AWP Output 2.1.4 | Guatemala Office | Mexico, Guatemala and Nicaragua | N | IFAD, rural women entrepreneurs  |  | TBDby the Guatemala CO | Completed  |  |
| Corporate evaluation in leadership and political participation | N | UNDAF V Priority area | Mexico AWP Outputs 1.1.2 & 1.1.3 | HQ | Global with national case studies  | N |  | April 2017 | HQ budget | Ongoing  |  |
| Corporate Evaluation of the Contribution of UN Women to Governance and National Planning (GNP) | N |  | Mexico AWP Outputs 1.2.1  | HQ | Global |  |  | June 2018 | HQ budget | Ongoing |  |
| Final Evaluation of the Fund for Gender Equality Project "Influence and empowerment for an agenda of social responsibility in care work" | Y | SP Output 4 | Mexico AWP DRF Output 2.1.1 | FGE-HQ/Mexico CO | Mexico | ILSB | ILSB | May-June 2019 | $10,077  | Evaluation will initiate in May 2019 |  |