**ROAP’s MONITORING, EVALUATION AND RESEARCH PLAN 2016-2017[[1]](#footnote-1)**

**Monitoring and Research Plan**

| **Activity** | **Partners and stakeholders** | **Planned Dates (Month and year of start and end)** | **Budget** | |
| --- | --- | --- | --- | --- |
| Source | Amount |
| **MONITORING** | | | | |
| **DRF 1:** **Women lead and participate in decision making at all levels** | | | | |
|  |  |  |  |  |
| **DRF 2: Gender Equality in capability and resources: Women, especially the poorest and most excluded, are economically empowered and benefit from development** | | | | |
| Project monitoring of Preventing exploitation of women migrant workers | ROAP, Laos project office, Cambodia CO and Viet Nam CO | Throughout 2015 | AusAID |  |
| **DRF 3:** **Women and girls live a life free from violence** | | | | |
| Project monitoring of AusAid funded project |  |  |  |  |
| Project monitoring of Australia-funded project: quarterly field visits to implementing partners by each project officer; at least 1 monitoring meeting per year from regional focal point | UN Women COs/POs in Lao PDR, Indonesia, Viet Nam and Timor-Leste and their government and NGO partners | Q1 2014-Q4 2015 | Australia (Project ID 86405) | 40,000 |
|  |  |  |  |  |
|  |  |  |  |  |
| **DRF 4: Peace and security and humanitarian action are shaped by women leadership and participation** | | | | |
|  |  |  |  |  |
| **DRF 5: Governance and national planning fully reflect accountability for gender equality commitments and priorities** | | | | |
|  |  |  |  |  |
| **DRF 6: A comprehensive and dynamic set of global norms, policies and standards on gender equality and women’s empowerment is in place and is applied through action by Governments and other stakeholders at all levels** | | | | |
| CEDAW SEAP[[2]](#footnote-2): 4 Field visits per programme officer/year to meet implementing partners |  | Q1-Q4/per year  (2014-2017) |  | 40,000 |
| CEDAW SEAP: 2 Monitoring meetings/year |  | Q1-Q4/twice per year (2014-2017) |  | 18,000 |
| **Cross-cutting** | | | | |
| Baseline data collection for SN and AWP indicators, monitoring of the indicators, establish a review process | RO, MCO’s, COs | 2014-2017 | Core | Staff cost |
| Annual review of SN | RO | November every year | Core | 2000 |
| Mid-term review of SN (2015) | RO, MCOs, COs, Partners | Q1-Q2 of 2015 Any activity in 2016-2017? | Core | tbc |
| Fund for Gender Equality (FGE) Programmes. Ongoing monitoring support and technical assistance in the implementation of FGE Programmes implemented in ROAP[[3]](#footnote-3). | FGE Grantees (NGO’s & Government partners) & UN Women RO/MCO/CO/PO relevant staff (Focal Points, Finance, Evaluation, etc). | 2015 | Non-Core | 70,000US$[[4]](#footnote-4) |
| Mid-term review of SN and adjustment of SN/AWP | RO | Q2-3 2015 Any activity in 2016-2017? | Core | 10,000 |
| **RESEARCH** | | | | |
| **DRF 1:** **Women lead and participate in decision making at all levels** | | | | |
|  |  |  |  |  |
|  |  |  |  |  |
| **DRF 2: Gender Equality in capability and resources: Women, especially the poorest and most excluded, are economically empowered and benefit from development** | | | | |
| A body of knowledge relating to gender and macroeconomics | TBC | 2016 | Core | 100,000 |
|  |  |  |  |  |
| **DRF 3:** **Women and girls live a life free from violence** | | | | |
| Multi-country study on VAW costing of services undertaken in three countries within the scope of the Australia-funded programme, and M&E of implementation undertaken in two countries | National University of Galway, ICRW, government and NGO partners in Indonesia, Lao PDR, and Timor-Leste | Q3-Q4 | Core |  |
| Mapping and distillation of key results achieved under UNiTE in the AP region | TBD | Q3 2015 | TBD | TBD |
| Regional research (desk review and knowledge-sharing meeting) on VAW in the context of women’s mobility and security | TBD | Q1-Q2 2015 | Core | 75000 |
| Other context-specific studies on EVAW (linked to disability, statelessness, etc) | TBD | 2016-2017 (one per year) | Core | TBD |
|  |  |  |  |  |
| **DRF 4: Peace and security and humanitarian action are shaped by women leadership and participation** | | | | |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
| **DRF 5: Governance and national planning fully reflect accountability for gender equality commitments and priorities** | | | | |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
| **DRF 6: A comprehensive and dynamic set of global norms, policies and standards on gender equality and women’s empowerment is in place and is applied through action by Governments and other stakeholders at all levels** | | | | |
| Study/Review of Barangay Justice System and Women’s Access to Justice in piloted city (Quezon) | LGU and Research NGO | ? |  | 5,000 |
| Conduct sectoral studies (1 a year) of the select outcomes of the Beijing Platform for Action +20 | UN Women | 2014-2017 |  | 300,000 |

**Evaluation Plan 2016-2017**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Evaluation name** | **Mandatory?**  **(Y/N)** | **UNDAF Outcome/ UN Women SP Goal, Outcome** | **Country/ MCO/ RO AWP Output** | **Office in charge** | **Region/ country** | **Joint activity**  **(Y/ N, indicate partners)** | **Key Stakeholders** | **Planned Dates**  **(start-end)** | **Budget (US$) / Sources of Funding** | **Status (pending/ initiated/ ongoing/ completed)** | **Remarks** |
| **Evaluations managed by the office** | | | | | | | | | | |  |
| **DRF 1:** **Women lead and participate in decision making at all levels** | | | | | | | | | | | |
| **DRF 2: Gender Equality in capability and resources: Women, especially the poorest and most excluded, are economically empowered and benefit from development** | | | | | | | | | | | |
| Final evaluation of Prevention of exploitation of women migrant workers | Y | DRF2 | Multi-country (ASEAN countries) | RO | ASEAN countries | N | Migrant workers, Governments, Donors (AusAID) | Q4 2015 | USD 37,500 | Pending |  |
| **DRF 3:** **Women and girls live a life free from violence** | | | | | | | | | | | |
| Evaluation of Australia-funded project on EVAW in South East Asia(2015) | Y | DRF 3: Women and girls live a life free from violence | Output 3.1.1. Governments, CSOs and UN entities have access to and utilize new regional evidence, tools and knowledge to inform the development and implementation of laws, policies, strategies and programmes to EVAW | RO | AP | No | UN Women COs/POs in Lao PDR, Indonesia, Viet Nam, Timor-Leste and their partners | 4th Quarter, 2015 - 2016 | 49,619.55(Australia, Project ID 86405) | On-going | Q4/2015 Final evaulation of the project |
|  |  |  |  |  |  |  |  |  |  |  |  |
| **DRF 4: Peace and security and humanitarian action are shaped by women leadership and participation** | | | | | | | | | | | |
|  |  |  |  |  |  |  |  |  |  |  |  |
| **DRF 5: Governance and national planning fully reflect accountability for gender equality commitments and priorities** | | | | | | | | | | | |
|  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |
| **DRF 6: A comprehensive and dynamic set of global norms, policies and standards on gender equality and women’s empowerment is in place and is applied through action by Governments and other stakeholders at all levels** | | | | | | | | | | | |
| Final Evaluation of Regional Programme on Improving Women’s Human Rights in South East Asia – CEDAW SEAP | Y | DRF6 | RO | Regional Office for Asia and the Pacific | Regional Office for Asia and the Pacific |  | Principle stakeholders at national and regional levels; government, women’s groups, CSOs and relevant UN agencies | 2015/ 2016 | 150,000 |  |  |
| **Evaluations in which the office participates** | | | | | | | | | | |  |
| **DRF 1: Women lead and participate in decision making at all levels** | | | | | | | | | | | |
| Final Evaluation of FGE programme “strengthening the voice of young women as gender equality advocates in SEA” IWRAW | N | DRF 6 |  | Regional Office – FGE Focal Point and FGE M&R | Regional | N | IWRAW | 3 months before programme end in June 2015 | Funds are part of the grantees budget. | Not started | Co-Managed by FGE M&R specialist in Bangkok |
|  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |
| **DRF 2: Gender Equality in capability and resources: Women, especially the poorest and most excluded, are economically empowered and benefit from development** | | | | | | | | | | | |
| P4P Mid-Term (2015) | N | DRF 3: Women and girls live a life free from violence | Output 3.1.1. Governments, CSOs and UN entities have access to and utilize new regional evidence, tools and knowledge to inform the development and implementation of laws, policies, strategies and programmes to EVAW | RO | AP | Y – UNDP, UNFPA, UNV | UN Women COs/POs; UNCTs in P4P countries, national working groups and partners | Q3 2015 | TBC | Pending |  |
| *EVAW Trust Fund (2014 – 2017)*  1. Beijing Cultural Development Center for Rural Women  2. RIFKA ANNISA  3. The Victims Support Section of the Extraordinary Chambers in the Courts of Cambodia (ECCC)  4. International Rescue Committee (IRC)  Mid-term Evaluation  Final Evaluation  5. Action Aid  Midterm-Evaluation  Final Evaluation  6. Two programmes awarded in 2014 under cycle 18th grant making  (Contract to be signed in Nov 2014)  6.1 Mongolia Women’s Fund  6.2 Rainbow Sky Association of Thailand | *Y*  *Y*  *Y*  *Y*  *Final Evaluation*  *Y* | *DRF 3.1.2* | *RO*  *RO*  *RO*  *Action Aid*  *RO*  *RO* | *RO*  *RO and PO Indonesia*  *RO and CO Cambodia*  *RO*  *Action Aid* | *China*  *Indonesia*  *Cambodia*  *Thailand*  *Myanmar*  *Mongolia*  *Thailand* | *Final Evaluation by external evaluator*  *Final Evaluation by external evaluator*  *Final Evaluation by external evaluator*  *Final Evaluation by external evaluator*  *Final Evaluation by external evaluator* | *TOR to engage evaluator need clearance from UNTF Secretariat* | *Q1 2014*  *Q2 2015*  *Q4 2014*  *Q3 2014*  *Q4 2015*  *Q4 2014*  *Q4 2015*  *Q4 2016*  *Q4 2017* | *5,000*  *43,529*  *50,000*  *5,000*  *15,000*  *2,000*  *8,000*  *TBD*  *TBD* | *Done*  *Pending*  *In progress*  *Cancelled*  *In progress*  *In progress*  *Pending* |  |
| **Cross-cutting** | | | | | | | | | | | |
| **2015** | | | | | | | | | | | |
| Bangladesh UNDAF | Y | UNDAF | Bangladesh CO and RO | Bangladesh CO and RO | Bangladesh | Y | Government, UN Agencies | 2015 | ? | On-going |  |
| Iran and Mongolia UNDAF | Y | UNDAF | ? | ? | ? | Y | Government, UN Agencies | 2015 | ? | On-going |  |
| Thailand UNDAF | Y | UNDAF | Thailand Project Office and RO | Thailand Project Office and RO | Thailand | Y | Government, UN Agencies | 2015 | ? | Pending |  |
| Laos UNDAF | Y | UNDAF | Laos | Laos | Laos | Y | Government, UN Agencies | 2015 | ? | On-going |  |
| Viet Nam One UN evaluation | Y | UNDAF | Viet Nam CO and RO | Viet Nam CO and RO | Viet Nam | Y | Government, UN Agencies | 2015 | ? | On-going |  |
| 2016 | | | | | | | | | | | |
| Regional meta-evaluation | N | All countries in AP | All countries in AP conducted evaluation in the last 5 years | RO | RO | N | Governments, NGO partners | 2016 | USD 50,000 |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |

**China Project Office**

**MONITORING, EVALUATION AND RESEARCH PLAN 2014-2017**

**Monitoring and Research Plan 2014-2017**

| **Activity** | **Partners and stakeholders** | **Planned Dates (Month and year of start and end)** | **Budget** | |
| --- | --- | --- | --- | --- |
| *Source* | *Amount* |
| **MONITORING** | | | | |
| Monitoring CGF 6th and 7th batch projects | Government and NGO partners | Jan 2014-Dec 2016 | Non-Core | $35,000 |
| *Monitoring the 2nd Phase EVAW Programme* | *ACWF* | *Oct. 2013 – Oct. 2016* | *Non-Core* | *$12,000* |
| *Monitoring of Women’s Political Participation Programme in China* | *ACWF* | *October 2013-Decemeber 2016* | *Non-Core* | *$ 8,700* |
| **RESEARCH** | | | | |
| *Example: Common Country Assessment* |  | *6/16-12/16* | *Core* | *$15,000* |

**Evaluation Plan 2014-2017[[5]](#footnote-5)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Evaluation name** | **Mandatory?**  **(Y/N)** | **UNDAF Outcome/ UN Women SP Goal, Outcome** | **Country/ MCO/ RO AWP Output** | **Office in charge** | **Region/ country** | **Joint activity**  **(Y/ N, indicate partners)** | **Key Stakeholders** | **Planned Dates**  **(start-end)** | **Budget (US$) / Sources of Funding** | **Status (pending/ initiated/ ongoing/ completed)** | **Remarks** |
| ***Evaluations managed by the office*** | | | | | | | | | | |  |
| ***Evaluation 1: Mid-Term External Evaluation of the CGF*** | *Y* | *UN Women SP DRF Goal 1,2,3 and 5*  *UNDAF Outcome 1.5,2.1,2.2,2.3 and 2.4*  *( To focus on 6th batches projects and cover partial 5 batches)* | *RO AWP Output 1.2.2, 2.1.1. 2.2.1,2.2.2,3.1.1 and 3.1.2* | *China Office* | *China* | *Donors, TAC members and grantees* | *Donors, TAC members and grantees* | *Oct-Dec 2015* | *US$50,000, non-core funds* | *Pending* |  |

1. The MERP for Regional Office for Asia and the Pacific (ROAP) includes Laos, the Philippines and Thailand Project Offices. China and Indonesia Project Offices followed the ROPA MERP as they have stand-alone projects. [↑](#footnote-ref-1)
2. Monitoring will be carried out according to the Programme Monitoring Framework (PMF): 4 layers – 1) monitoring will be conducted by the implementing partners as per agreed indicator 2) monitoring will be conducted by the Cos 3) monitoring will be conducted by the RO Management Team 4) monitoring of Mid-Term Review by UNW and CIDA [↑](#footnote-ref-2)
3. Please note that there are currently 15 FGE programmes being implemented in the Asia Pacific Region as a whole (RO+MCO+CO+PO). 5 programmes are part of the ROAP (2 regional and 3 national, including China FGE programme). In addition there are 4 programmes in India MCO, 2 programmes in Pakistan CO, 1 programme in Bangladesh CO, Afghanistan CO, Cambodia CO, and Vietnam CO. [↑](#footnote-ref-3)
4. 3.5% of total grant amounts for programme duration. [↑](#footnote-ref-4)
5. Please fill out a separate row for each evaluation. [↑](#footnote-ref-5)