UN WOMEN GEORGIA

UN WOMEN GEORGIA

Final Evaluation of the project “Good Governance for Gender Equality in Georgia (GG4GEG)”

Final evaluation report submitted on May 12 2023

Marina Gurbo, Team Leader

Rusudan Konjaria, National Consultant

Gocha Sirbiladze, National Consultant

Marina Gurbo, Team Leader

Rusudan Konjaria, National Consultant

Gocha Sirbiladze, National Consultant

Table of Contents

Acronyms and Abbreviations	3

Executive Summary	4

1.	Introduction	9

1.1.	The project description	9

1.2.	The political and socioeconomic context of the project	12

1.3.	The progress of the country towards achievement of international GEWE commitments and SDGs	13

2.	The purpose, objectives and scope of evaluation	18

2.1.	The purpose of evaluation	18

2.2.	Evaluation objectives	18

2.3.	The scope of evaluation	19

3.	Evaluation methodology	19

3.1.	Theoretical Framework	19

3.2.	Evaluation standards, criteria and evaluation questions	19

3.3.	Data collection and analysis	21

3.4.	Limitations	23

3.5.	Evaluation management	25

3.6.	Ethical issues	25

4.	Findings	27

4.1.	Relevance	27

4.2.	Coherence	33

4.3.	Effectiveness	36

4.4.	Efficiency	46

4.5.	Sustainability	49

4.6.	Partnerships for GEWE and SDGs	52

4.7.	Innovativeness	54

5.	Conclusions	57

6.	Lessons learned	59

7.	Recommendations	60

8.	Annexes	65

Annex 1 Reconstructed ToC 	66

Annex 2 Evaluation Matrix	67

Annex 3 Stakeholders’ analysis	74

Annex 4 Data collection instruments	81

Annex 5 List of respondents	91

Annex 6 List of documents reviewed	96

Annex 7 Composition of the Evaluation Reference Group	104

Annex 8 Summary of the SWOT findings	105

Annex 9 GG4GEG Result and Resources Framework	107

Annex 10 Terms of Reference	116

# Acronyms and Abbreviations

BpfA                                  Beijing Declaration and Platform for Action (BpfA

BTU                                   Business and Technology University

CEDAW                        Convention on the Elimination of All Forms of Discrimination against Women

CSB                                    Civil Service Bureau

CSO                                    Civil Society Organization

FAO                                    Food and Agriculture Organization of the United Nations

GEC                                    Gender Equality Council at the Parliament of Georgia

GEWE                                Gender Equality and Women’s Empowerment

GFA 	Georgian Farmers’ Association

GCCI	Georgian Chamber of Commerce and Industry

GGA                                   Gender Gap Analysis

GIA                                     Gender Impact Assessment

GITA	Georgian Innovation and Technology Agency

GRB                                    Gender Responsive Budgeting

HRPA                                  Human Resources Professionals Association in Georgia

IT	 Information Technology

JAWE	 A Joint Action for Women’s Economic Empowerment in Georgia

LELP	 Legal Entity of Public Law

MoFA                                  Academy of Ministry of Finance

NALAG                                National Association of Local Authorities

NGO	 Non-Governmental Organization

NARP                                   National Agency of Public Registry

PGA	  Participatory Gender Audit

PDO	  Public Defender’s Office

SDG                                      Sustainable Development Goals

SHG	  Self-Help Group

TASO	  TASO Foundation

TIGE                                     Technology and Innovation for Gender Equality Action

UNCT                                   United Nations Country Team

UNDP                                   United Nations Development Programme

UNFPA                                 United Nations Population Fund

UN GTG                               United Nations Gender Theme Group

UNSDCF                               United Nations Sustainable Development Cooperation Framework

UN-SWAP                            UN System-wide Action Plan on Gender Equality and the Empowerment of   Women

UN Women	 United Nations Entity for Gender Equality and the Empowerment of Women

VNR                                     Voluntary National Review

WEE                                     Women’s Economic Empowerment

WEPs   		                Women’s Empowerment Principles: Equality Means Business

# Executive Summary

Description of the project

The project Good Governance for Gender Equality in Georgia has been implemented by the United Nations Entity for Gender Equality and the Empowerment of Women (UN Women) with generous support of the Norwegian Government from 1 September 2019 with until 31 May 2023.  A new component on women’s economic empowerment (further - WEE) was added starting from 1 June 2021. The final budget of the project amounts to USD 4,224,915, with USD 2,000,000 allocated for the WEE component. The overarching goal (impact level) of the GG4GEG project is to ensure that governance systems, programmes, and policies along with private sector partners are gender sensitive and enable women’s economic empowerment and broader gender equality in Georgia.

The project’s two Outcomes are:

- Outcome 1- Governance systems are gender-sensitive and enable gender equality in Georgia;

- Outcome 2- Women in rural areas benefit from increased income-generation opportunities in the agrotourism and ICT sectors and fully realize their economic rights with the support of a gender-responsive private sector.

Under the first component (Good Governance or Outcome 1), the project aimed to ensure that governance systems are gender sensitive and enable gender equality in Georgia. The target groups of this component are governance institutions and public servants responsible for planning and budgeting at the national level, as well as local governments of all 64 municipalities and five self-governing cities. By equipping them with knowledge of gender mainstreaming methodologies such as Gender Responsive Budgeting (GRB), Gender Impact Assessment (GIA) and Participatory Gender Audit (PGA), it is expected, in the long run, that women and men are going to equality benefit from more transparent and coherent planning and budgeting processes and from better informed civil servants who will be able to address more effectively diverse needs of women, men, boys and girls. The objective of the second component (WEE or Outcome 2) was to ensure that women in rural areas benefit from increased income-generation opportunities in the agrotourism and ICT sectors and fully realize their economic rights with the support of a gender-responsive private sector.  The project worked with three key target groups:  private businesses - over 170 companies’ signatories of UN Women Women’s Empowerment Principles: Equality Means Business; government bodies and public entities responsible for an enabling environment for businesses development, especially, in agrotourism and ICT.

Interventions developed in the framework of the project had nation-wide coverage and, in case, of the WEE component, more emphasis was set on more economically disadvantaged and conflict affected regions of Western Georgia (Imereti, Guria, Ratcha-Lechkhumi, Samegrelo and Shida Qartli).  The project design targeted gender mainstreaming across a broad scope of reforms, such as decentralization, public service reform and public finance management reform, economic diversification (entrepreneurship), tourism (agritourism), financing, vocational education and training (work-based training), startups development, ICT industry, trade (value chain) and other. Due to that fact, the project implementation benefited from strategic partnerships developed with a large number of representatives from the Government, public administration institutions, non-governmental sector – CSOs and professional associations, and private enterprises. Selection of partners was informed by their position in national planning and decision-making mechanisms including the power to influence gender equality mainstreaming at the national and local level, as well as promote gender mainstreaming across sectors and reforms in the scope of the project interventions.  In this connection, UN Women has broadened its cooperation with the national gender machinery - the Gender Equality Council of the Parliament and relevant legislative committees; the Inter-Agency Commission on Gender Equality, Violence against Women and Domestic Violence in the Prime Minister’s Office, and Public Defender’s Office (PDO).  Other key partners include the National Statistics Office of Georgia (GEOSTAT), the National Association of Local Authorities of Georgia (NALAG), Civil Service Bureau and Ministry of Finance (and its academy - MoFA); Georgian Chamber of Commerce and Industry (GCCI), Enterprise Georgia, National Statistics Office of Georgia (GEOSTAT);  non-governmental organizations such as Taso Foundation, Georgian Farmers' Association (GFA); as well, National Agency of Public Registry (NAPR) of the Ministry of Justice of Georgia, Georgia's National Tourism Administration (GNTA), Human Resources Professionals Association in Georgia (HRPA), the Ministry of Education and Science (MoES), and representatives of academia i.e., Business and Technology University (BTU), and private companies- WEPs signees.

The purpose and objectives of evaluation and methodology

The main purpose of this final mandatory evaluation was to assess the achievement of the project results and performance and identify lessons learned, best practices and challenges in order to promote accountability, learning and decision-making at UN Women Georgia. The evaluation was conducted based on the standard criteria of relevance, coherence, effectiveness, efficiency, sustainability and two additional criteria of partnerships for GEWE and SDGs and innovativeness. The evaluation followed a theory-based design and its methodology that included both qualitative and quantitate methods integrated participatory and human rights and gender equality responsive approaches in order to give voice to all partners and beneficiaries of the project including those in most vulnerable situations.

A variety of data collection methods and validation techniques allowed collecting rich information and input from 224 participants ( 96% female) including 4 representatives of the national gender machinery (GEC and PDO), 32 – of the Government administration, ministries and LELPs; 42 representatives of Gender Focal Points in local governance; 77 women organized in self-help groups and 13 women-entrepreneurs benefited from the project interventions; and 14 private companies – signatories of WEPs. In addition, the evaluation team interviewed representatives of media, gender experts, data users and CSOs that were involved in different components of the project.

Overall, the evaluation report includes 23 findings, five lessons learned and ten conclusions. Main evaluation users include UN Women Country Office in Georgia, as well as the Government of Norway (the project donor). It is expected that the findings from this evaluation will contribute to building of the evidence base on effective strategies for enhancement of gender equality and women’s empowerment in Georgia and will facilitate UN Women’s strategic reflection and learning for programming in these areas. Furthermore, national stakeholders – civil society partners, Parliamentary counterparts and targeted state and non-state agencies are expected to benefit from this evaluation.  Recommendations from the evaluation also seek creation of new partnerships and enhancement of synergies with stakeholders from all sectors in order to accelerate achievement of Good Governance for Gender Equality and Women’s Economic empowerment and, consequently, related SDG targets.

Key findings

The evaluation found the project highly relevant to the aspirations of the country to achieve the national priorities, ensure compliance with international gender equality frameworks e.g., CEDAW, Bejing Platform for Action and meet nationalized SDG targets. Based on the quality analysis, the project intervention targeted solution of root causes of gender-based inequalities such as access to land and financial resources, stereotypes and perceptions entrenched in the systems, gender blind policies and institutions and other. Moreover, the project largely invested into addressing lack of disaggregated data and research to inform decision making in the number of areas i.e., extent of gender mainstreaming in governance, sexual harassment in public institutions, inequal balance of unpaid work in the family, access of women to ICT and career in technology, barriers to women’s entrepreneurship and other.

The project design represents a coherent approach to addressing gender-based inequalities in relation to women’s participation in decision making and women’s economic empowerment. Focusing on the key reforms such as in the Public Administration Reform (PAR), public budget management, land ownership and other, UN Women used its comparatives advantages and ownership of gender tools as Participatory Gender Audits, Gender Impact Assessment, Gender Responsive Budgeting, sexual harassment prevention mechanisms to ensure institutionalization of these tools and reinforce their mainstreaming at the level of public and private institutions.

In relation to achievement of targets and of the overall goal, the project was very effective and the key achievements include institutionalization of gender impact assessments and gender-responsive budgeting and a breakthrough in terms of promotion of WEPs and institutionalization of gender sensitive practices at the private sector. Project interventions reached 1,327 public servants by gender mainstreaming capacity development interventions; and 444 representatives from the WEPs companies increased their awareness of gender equality at the workplace.

The project strategies have been effective in increasing women’s opportunities to build sustainable business due to quality of capacity building provided by UN Women and partners and commitment of the private companies-signees of WEPs. Voluntarily contribution (pro-bono activities) also added to the efficiency of the project which allowed reaching larger numbers of women-beneficiaries that had been initially planned. In total, 101 women in rural areas received grants for economic activities, 202 women improved skills in business and leadership-related topics; and 994 women and girls acquired new IT skills under the 500 Women in Tech project.

The project has been effective in generation of the national ownership of the project results. Adoption of high-level policy documents and NAPs that integrate gender analysis creates an enabling environment for continuation of reforms initiated by the project.  Institutionalization of gender mainstreaming tools and mechanisms at the partners and stakeholders’ institutions that have key positions in influencing achievement of gender equality in the targeted by the project areas should ensure sustainability of developed capacities and further dissemination of good practices introduced by the project. Sustainability of the project results have also been enhanced by strategic partnerships nurtured by UN Women through participation in the working groups under the GEC of the Parliament, Human Rights Council, Women Economic Empowerment Working Group and other and establishing new formats of cooperation such as a working group with IFIs and WEPs Advisory Council.

Finally, project has been catalytic in development and piloting of new methodologies and promotion of innovative gender equality mainstreaming tools into the polices and institutions. Several methodologies such as data user satisfaction survey with the focus on gender data products, Time Use Survey and Gender Responsive Public Financial Management (GRPFM) assessment have been first implemented in Georgia, and some in the region. Integration of results generated by use of these tools and methodologies is under way and will require further support from UN Women during the next phase of the project.

Some innovative initiatives as a Ring the Bell for Gender Equality event and a UN Women flagship initiative -500 Women in Tech project, launched in private-public partnership with BTU, have enjoyed increasing involvement from the private sector companies, governance institutions and representatives of media which allows to raise awareness of the pivotal role of the private sector in promotion of economic empowerment of women, also break gender stereotypes in relation to the choice of professions. As most relevant to sustainability of these initiatives, opportunities for broader dissemination and their integration at the partners’ institutions and outside the project have been given sufficient attention in the project exit strategy.

Conclusions and lessons learned

Overall, the project being well aligned with the UN Women Global Strategic Plan 2022-2025 has made a significant contribution to its implementation, in particular in the Impact Area 1: Governance and Participation in Public Life (Outcome 1 Global normative frameworks and gender responsive laws, policies and institutions and Impact) . Under the Good Governance Component, UN Women successfully leveraged its technical expertise in gender impact assessments, gender-responsive budgeting and gender disaggregated data to achieve the ultimate goal of increasing participation of women in decision making (SDG 5.5.1). Integration of gender responsive budgeting into public financing was another success that should promote achievement of SDG Indicator 5.c.1.

Under the WEE component aligned to Impact Area 2: Women’s Economic Empowerment (Outcome 4), UN Women built up on the success of the first phase of the JAWE project and continued raising gender-sensitivity of the private sectors through WEPs. In parallel, using available gender tools (GIA, PGA) the project addressed structural barriers to greater economic empowerment of women as access to land (SDG indicator 5.a.1)  and gender -sensitivity of financial instruments. Furthermore, UN Women used the comparative advantages being a leading agency at the Generation Equality Action Coalitions (joined by Georgia in 2021) to strengthen coherence and cooperation between interventions of private and public institutions in order to accelerate increase of women and girls in STEM and ICT. UN Women launched 500 Women in Tech project and supported the country to develop a Technology and Innovation for Gender Equality (TIGE) action plan.

The project presents a good value for money and its success may be attributed to effective strategies including needs based, tailored approaches employed by UN Women to bring on board governmental and non- governmental institutions, associations, CSOs and private companies.  At the same time, focusing on a large number of nation priorities and needs has exhausted resources (human) available at UN Women and pointed at the need to prioritize future interventions in the target areas. In this connection, CSOs (and right holders) capacities developed under the project could have used more proactively to address the gaps in capacities of local governance institutions the latest still have to ensure meaningful and effective utilization of gender mainstreaming tools.

The success of future interventions of UN Women in the areas of good governance and women’s economic participation depends on effectiveness of the design and implementation strategies in tackling some barriers to more systemic changes in systems and institutions. These barriers include lack of high level commitment to integrate gender equality into the initiated reforms; lack of human resources and problems of their retention (affecting institutional memory and consistency in implementation); insufficient financial resources; unclear accountability mechanisms for gender mainstreaming (at local governance); and building effective cooperation with civil society.

Key Recommendations

The evaluation team proposed six major recommendations and 21 specific actions that are addressed at UN, Gender Equality Council at the Parliament, implementing partners and the WEPs Advisory Council. The main of them include the following:

- Continue with mainstreaming of GEWE into existing broad-scale reforms such as Public Administration Reform, systemic land registration process, also lawmaking around agrotourism and agriculture i.e., farmers’ status to accelerate achievement of all GEWE targets and SDG 5;

- Continue building capacities of public servants to ensure effective application of gender equality mainstreaming tools and to use gender disaggregated data for decision making;

- Disseminate further the results of the Time Use Survey and advocate for amendments in relevant legislation and institutional practices to accelerate achievement of work and life balance for women;

- Continue building evidence base of benefits from integration of gender equality mainstreaming tools in the public and the private sector, such as from integration of sexual harassments prevention mechanisms, GRB, GIA etc.;

- Increase involvement of CSOs and women from Self-Help Groups, through the grant schemes and targeted funding, in dissemination of gender mainstreaming tools and capacities to use these tools at the local governance level;

- Expand further successful cooperation with stakeholders representing different sectors and IFIs and, in particular, to support sustainable development of women’s enterprises in rural areas;

- Use the WEPs Council as a platform to expand public-private partnerships and engage the WEPs Council, thematic groups and CSOs to work together and provide input to governmental institutions in relation to desirable changes in sectoral strategies and relevant legislation;

- Continue advocating for recognition of the private sector’s contribution to gender equality and women’s economic empowerment and SDGs i.e., through procurement processes, allocation of targeted grants etc.

- Continue integration of innovative methodologies into relevant strategies and action plans at the national and institutional levels and ensure that innovative initiatives such as the “500 Women in Tech project” and other become sustainable and more accessible for rural women.

# Introduction

## The project description

The project Good Governance for Gender Equality in Georgia was launched by the United Nations Entity for Gender Equality and the Empowerment of Women (UN Women) on 1 September 2019 with the initial duration of 36 month. In 2021, Due to the new agreement with the donor – the Norwegian Ministry of Foreign Affairs, it received the extension until 31 May 2023 with a new added component on women’s economic empowerment (further - WEE) starting from 1 June 2021.  The final budget of the project amounts to USD 4,224,915 with USD 2,000,000 allocated for the WEE component. The overarching goal (impact level) of the GG4GEG project is to ensure that governance systems, programmes, and policies along with private sector partners are gender sensitive and enable women’s economic empowerment and broader gender equality in Georgia.

The project is aligned to the UN Women Global Strategic Plan 2022-2025, Impact Area 1: Governance and Participation in Public Life; and Impact Area 2: Women’s Economic Empowerment.  Its implementation should contribute to the result areas under  the UN Women Georgia Strategic Note 2021-2025, Outcome 1 (synchronized with Outcome 1 of the UNSDCF for Georgia 2021-2025): By 2025, all people in Georgia enjoy improved good governance, more open, resilient and accountable institutions, rule of law, equal access to justice, human rights and increased representation and participation of women in decision-making; and Outcome 2 (synchronized with UNSDCF Outcome 3): By 2025, all people without discrimination benefit from a sustainable, inclusive and resilient economy in Georgia. The benefits generated by the project should contribute to achievement SDG 5, 16, 17 and 8 (as main goals) with spillover effect on targets under SDG 1 and 10.

The project’s two Outcomes are:

- Outcome 1- Governance systems are gender-sensitive and enable gender equality in Georgia;

- Outcome 2- Women in rural areas benefit from increased income-generation opportunities in the agrotourism and ICT sectors and fully realize their economic rights with the support of a gender-responsive private sector.

Each of Outcomes has been implemented by a dedicated UN Women project team with their own work plans and monitoring systems in place. It is noteworthy though that several result areas, for example, work on sexual harassment mechanisms, integration of Participatory Gender Audits (PGAs) and Gender Impact Assessment (GIA) methodologies was overtaken from the previous JAWE project. Integration of these gender mainstreaming tools had been integrated under Outcome 1 from the start, therefore, there was no overlapping observed in terms of deliverables. Each of Outcomes had own strategic partners, while both components worked closely with the national gender equality mainstreaming mechanisms and GEOSTAT – the key stakeholder in monitoring SDGs and the main producer of disaggregated gender sensitive statistical reports.  Figure 1 presents the project Outputs and underlying theories of change.

Figure 1 The Project Design and Theories of Change

| Theory of change | Hierarchy of results |  | Theory of change |
| --- | --- | --- | --- |
| Overall Goal/Impact: Governance systems, programmes, and policies along with private sector partners are gender sensitive and enable women’s economic empowerment and broader gender equality in Georgia |  |  |  |
| Then governance systems will be strengthened for gender equality; because institutional mechanisms and policymaking processes and patterns will become gender-sensitive and gender-aware. | Outcome 1 Governance systems are gender-sensitive and enable gender equality in Georgia | Outcome 2 Women in rural areas benefit from increased income-generation opportunities in the agrotourism and ICT sectors and fully realize their economic rights with the support of a gender-responsive private sector. | Then women in rural areas benefit from increased income generation opportunities in the agrotourism and ICT sectors in Georgia, because the private, public and civil society sectors take actions to create an enabling environment for rural women’s economic empowerment. |
| If gender equality and gender mainstreaming are institutionalized at national and local levels; and | Output 1.1 Gender equality and gender mainstreaming are institutionalized at the national and local levels | Output 2.1: Businesses have an increased understanding of the Women’s Empowerment Principles (WEPs) and have the skills to implement measures that benefit women, specifically in rural areas | If Businesses have increased understanding of Women’s Empowerment Principles (WEPs) and skills to implement measures that benefit women, specifically in rural areas; |
| If gender mainstreaming capacity is developed and sustained at national and local levels; and | Output 1.2: Gender mainstreaming capacities are developed and sustained at the national and local levels | Output 2.2: Policymakers and public agencies have increased capacities to identify and address challenges faced by women entrepreneurs in agrotourism and ICT | If Policymakers and public agencies have increased capacities to identify and address challenges faced by women entrepreneurs in agrotourism and ICT; |
| If more and better-quality data and analysis are available to promote and track the progress of gender equality and women’s empowerment | Output 1.3: More and better-quality data and analysis are available to promote and track the progress of gender equality and women’s empowerment | Output 2.3: Women have increased confidence, skills and resources to utilize income-generation opportunities in the agrotourism and ICT sectors and related value chains | If Women have increased confidence, skills and resources to utilize income generation and opportunities in the agrotourism and ICT sectors; |

Under the first component (Good Governance or Outcome 1), the project aim was to ensure that governance systems are gender sensitive and enable gender equality in Georgia. The primary target group of this component was comprised of government institutions and public servants, especially those responsible for planning and budgeting at the national level, as well as local governments of all 64 municipalities and 5 self-governing cities. The key benefits of the project interventions for the primary target group included increased knowledge human resources and capacities of institutions in gender equality mainstreaming. For secondary target group such as gender advocates, experts, academia, and civil society organizations the project interventions sought deepening their knowledge and expertise in the selected gender mainstreaming tools and methodologies, such as Gender Responsive Budgeting (GRB), Gender Impact Assessment (GIA) and Participatory Gender Audit (PGA). In the long run, it has been expected that women and men will equally benefit from more transparent and coherent planning and budgeting processes, as well as from better informed civil servants equipped with more sensitive gender approaches to address diverse needs of women, men, boys and girls. The key state partners for Outcome 1 included: the Gender Equality Council of the Parliament and relevant legislative committees; the Inter-Agency Commission for Gender Equality in the Prime Minister’s Office, Public Defender’s Office (PDO), the National Statistics Office of Georgia (GEOSTAT), the National Association of Local Authorities of Georgia (NALAG), the Civil Service Bureau and the Ministry of Finance (and its academy - MoFA).

Under the second component (WEE or Outcome 2), the project aimed to ensure that women in rural areas benefit from increased income-generation opportunities in the agrotourism and ICT sectors and fully realize their economic rights with the support of a gender-responsive private sector.  The project worked with three key target groups:  private businesses - over 170 companies’ signatories of UN Women Women’s Empowerment Principles: Equality Means Business;  government bodies and public entities responsible for creation of an enabling environment for businesses development  such as the Ministry of Economy and Sustainable Development and its entities (Enterprise Georgia, Georgia’s Innovation and Technology Agency, etc.); and women in Georgia, especially those residing in rural areas, whose skills the project built to enable them to access decent work and/or grow their agrotourism-related businesses. The project interventions were implemented in partnership with established partners from public institutions i.e., Georgian Chamber of Commerce and Industry (GCCI), Enterprise Georgia, GEOSTAT and non-governmental organizations such as TASO Foundation, Georgian Farmers' Association (GFA), the latest ones supported improving women’s job skills and their access to legal, financial and economic services. New partnerships were developed with several entities under the public law - National Agency of Public Registry (NAPR) of the Ministry of Justice of Georgia, Georgia's National Tourism Administration (GNTA), Human Resources Professionals Association in Georgia (HRPA) and the Ministry of Education and Science (MoES), representatives of academia i.e., Business and Technology University (BTU), and private companies.

The project results under both Outcomes and Outputs lie across several areas and, respectively SDG goals, such as decentralization, public administration reform, judiciary reform, economic diversification (entrepreneurship), sustainable agriculture, tourism (agrotourism), infrastructure, vocational education and training (work-based training), SME development including high tech (ICT industry, trade (value chain) and other, which informed development of strategic partnerships mentioned above in order to mainstream gender equality and women’s economic empowerment in several thematic areas and economic sectors. Interventions developed in the framework of the project had nation-wide coverage and, in case of the WEE component, support to rural women was provided in more disadvantaged and conflict affected regions of Western Georgia (Imereti, Guria, Ratcha-Lechkhumi, Samegrelo and Shida Qartli).

## The political and socioeconomic context of the project

Prior to the launch of the project, in 2019, the context of the country was characterized by a robust and resilient economic growth and multifaceted reforms implemented in all public spheres.  Between 2010 and 2019, Georgia’s GDP per capita grew at an average annual rate of 4.8 percent. In 2018, Georgia has moved up from a lower-middle income country to an upper-middle income one based on the World Bank GNI per capita classification. Nevertheless, inclusive growth remains a major challenge for the Georgian economy. While the GINI score was 35.90 in 2019 for Georgia and it is higher than the long -term of objective of 27.5, which is commendable, it has been stagnating. The Government has prioritized knowledge based and innovation driven economic development and actively supports increase of innovative activities of the micro, small, and medium-sized enterprises, including startups and individuals and their participation in the digital economy.

During 2020-2021, the project operating environment was affected by multiply crises: the COVID-19 pandemic, the protracted political crisis related to the outcomes of parliamentary elections in October 2020 and the change of the government in March 2021, and the launch of the Russian Federation’s military offensive in Ukraine, which all undermined political stability, resulted in economic slowdown and had substantial security and political implications for the region.

According to the UN Women report, the impact of the COVID-19 pandemic was higher on women due to increased household burden (in particular for large families with children), domestic violence and deterioration in mental health.  Traditionally women dominated trade and tourism including hospitality sectors have been hit very hard. The same may be said about agriculture that employs 54 % women due to closure of markets and lock down measures.  Oil and food prices increased sharply since the beginning of the war in Ukraine due to uncertainty and disrupted supplies from Russia and Ukraine; there were observed reductions in trade, tourism and remittances, as well as elevated commodity prices. Nevertheless, the swift post-pandemic rebound and the recovery from the initial impact of Russia’s invasion of Ukraine and related sanctions demonstrated growing economic resilience of the country, supported by sound macroeconomic management. Still, profound uncertainty remains due to the war in Ukraine and tightening of financial conditions globally.

To a greater extent, the project implementation was affected by the political crisis such as the elections of 2020 and changes in the Government in March 2021 which have put on hold important for the project policy development processes and capacity building interventions. It was noted in the project annual reports to the donor that high-level political commitment to implement tangible reforms for gender equality and women’s empowerment had been declining amid competing priorities and frequent turnover of leadership within the women’s national machinery. In 2021, the title of the position of Advisor to the Prime Minister on Human Rights and Gender Equality was amended removing “Gender Equality” from the title altogether. Many strategies and action plans promoting gender equality and women’s empowerment expired in 2020 and their renewal had undertaken longer than expected.

In 2022, the overall operating environment improved, mainly, due to stabilization after the economic recess.  In June 2022, the European Commission recommended to the EU Council that Georgia should be given the perspective to become a member of the European Union once the set of made recommendations is addressed. Among the recommendations, it was stressed to notably consolidate efforts to enhance gender equality and fight violence against women.  At the end of 2022, with the contribution of the project, several important framework documents were endorsed by the Government, namely: the Parliament approved the new State Concept on Gender Equality; 2022-2024 National Action Plan for combating domestic violence and violence against women and ensuring the protection of survivors; 2022 – 2024 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions 1325 on Women, Peace and Security.  Georgian State Budget for 2023 adopted in 2022 references gender 42 times, an increase from 16 references in the previous year. In November 2022, the Government adopted “the Vision 2030 – National Development Strategy”. The document mentions gender on three occasions: 1) in terms of collecting gender-disaggregated statistical data on enterprises; 2) in terms of provision of gender-balanced job placement services; 3) in terms of preventing work place violence. While these developments took place at the end of the project, they had significant positive impact on sustainability of the results and UN Women interventions under upcoming projects, among those the second phase of the GG4GEG project.

In March 2023, following the mass protests, Georgia's parliament voted to officially drop the draft law that would have forced media outlets and NGOs that receive 20% of their funding from abroad to register as "foreign agents". Nevertheless, concerns remain that the Government may impose other measures  that would have a chilling effect on democracy and impede work of media and, in particular, civil society of delivering essential services to the most vulnerable and helping protect their human rights.

## The progress of the country towards achievement of international GEWE commitments and SDGs

Figure 2. SDG report for Georgia (2022)

Figure 2. SDG report for Georgia (2022)

In 2019, Georgia adopted a national document on Sustainable Goals with 17 goals and 93 nationalized targets and indicators.In 2020, the country presented the second Voluntary National Review (VNR) of Sustainable Development Goals implementation at the virtual United Nations High-Level Political Forum (HLPF) on Sustainable Development. Despite the fact that, during the period of 2020-2022, the country moved some points up in overall performance  (see Figure 2), significant challenges remain to achieve SDG 5. In terms of budget allocation, programmes for SDG 5 Gender Equality, together with the “Planet” goals (6, 12, 13, 14 and 15) accounted for only 3% of the total budget for SDGs. Georgia has made significant progress to refine the legislative framework and institutional mechanisms for achieving greater gender equality, however, timely reporting on the adopted international obligations, such as the Beijing Declaration and Platform for Action (BpfA) and the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) remains to be improved.

There is a recognition in the Government that ensuring equal opportunities for women (SDG 5.5, 5.a) offers huge potential economic gains, especially, if the burden of unpaid care (5.4) could be addressed. As most relevant to the economic component of the project, in September 2021, Georgia joined the Equal Pay International Coalition (EPIC). In 2021, the Government of Georgia joined the Generation Equality Forum and undertook new commitments under the following two Action Coalitions: Gender-Based Violence, and Technology and Innovation for Gender Equality.  The Georgian Government has committed to SDG target 5.1 to undertake reforms giving women equal rights to economic resources, as well as access to ownership and control over land and other forms of property, financial services, inheritance and natural resources.

These commitments are regarded by UN Women in Georgia as an opportunity to accelerate progress in relation to several targets requiring closer attention, according to the VNP 2020. These targets include elimination of violence against women and violence against children from daily life (5.2, 5.3, 16.2); the full inclusion of persons with disabilities (10.2) and greater tolerance and appreciation of diversity, whether in terms of ethnic background, religious affiliation or sexual orientation.

Institutional mechanisms for mainstreaming gender equality and women’s empowerment

With regards to the national gender equality mainstreaming machinery , the special PDO report  found that Inter-Agency Commission for Gender Equality in the Prime Minister’s Office lacked effectiveness because of its somewhat ambiguous mandate, weak role in defining the government’s vision/strategy, lack of human and financial resources, etc.  As to the Gender Equality Council, the PDO noted the critical need for more human and financial resources as the persons working for the Council had to combine their responsibilities with additional tasks and the GEC financially depended on donors, contrary to the CEDAW’s recommendations. In general, the role of institutional mechanisms for gender equality is largely administrative support and advisory functions and fails to influence policy-making and improve the rights of women. The lack of a state vision on gender mainstreaming, including a lack of readiness and coordination, remains a challenge - gender mainstreaming tools are chaotic and unsystematic.  Similar challenges are observed at the level of the ministries, law enforcement institutions and other, which are explained by the lack of dedicated staff and institutional level gender equality strategies to mainstream gender in specific areas of work.

The regular independent monitoring of the implementation of three frameworks – the National Action Plan on Women, Peace and Security, the National Action Plan on Ending Violence against Women and Domestic Violence and the gender equality chapter of the broader National Action Plan for Human Rights – is conducted by the Public Defender’s Office and by women’s NGOs. These monitoring processes have revealed several shortcomings that hinder successful implementation, namely: (a) low sensitivity, awareness and capacity among public servants of gender equality and gender mainstreaming issues affecting the quality of implementation and reporting; (b) lack of clarity about resources allocated for the implementation of the various activities in the plans (as none of the gender-relevant national plans have been costed and budgeted); (c) lack of coordination both within and among the state institutions responsible for the implementation; and (d) lack of the action plans’ localization, resulting in low levels of informed citizen participation in both the development and the implementation of the plans.

Furthermore, monitoring processes are impeded by the lack gender-relevant statistics, available to the public. As per CEDAW requests, it is essential to urge improvement in the quality of data and analysis informing gender equality and women’s empowerment for the benefit of policymaking processes. Monitoring of budget allocation to gender equality and women’s empowerment should have benefited from introduction of Gender-Responsive Budgeting (GRB) as a tool in the public finance reform of Georgia.

Participation of women in governance and decision making

Increasing women’s political (15%) and economic (56%) participation would be an important step towards achieving 50/50 world in 2030.  The progress under SDG 16 has been moderately improving, while remaining insufficient to attain the goal by 2030.  The instrumental role of SDG 16 and, in particular, building strong and inclusive institutions at all levels to address existing inequalities was acknowledged at the national level which promoted public administration and governance reforms.

To mainstream gender equality and women’s empowerment at the local governance level, most of 64 municipalities have created gender equality councils and the gender advisors have been appointed by all mayors in Georgia. The 2021 report on the local governance reform noted that the majority of chairpersons of gender equality councils at the municipality level are men (46 men versus 19 women), while more women are staff members responsible for gender equality issues at the city halls of municipalities and cities (65 women versus 9 men). It was also acknowledged that existing methods of citizen participation do not guarantee engagement of a wide spectrum of local society in decision making, in particular in remote rural areas. The comprehensive Gender Equality profile (updated in 2021) highlighted the criticality of development of new tools and mechanisms to increase responsibilities of local administration for gender equality issues.

Participation of women in decision making is essential for achievement of gender equality and other SDGs.  Nevertheless, women continue to be underrepresented in decision-making at national and at local levels. As per the electoral reforms in 2020, one quarter of candidates on the party lists used in the proportional vote are required to be representatives of the opposite sex. As a result of the October 2020 elections, 31 women were elected to Parliament (21% of mandates), but only 16 entered (17% of Members of Parliament as of March 2021). Out of 12 ministers, only four are women. The 2020 electoral reforms also introduced gender quotas for local elections, but women are even more underrepresented at local level than on the national. Only 1 of the 64 mayors in the country is a woman. The barriers reported in 6th periodic report submitted by Georgia under article 18 to the CEDAW Committee include absence of sexual harassment prevention mechanisms, the burden of domestic work, stereotypical attitudes, inaccessibility of municipality buildings for disabled women and the language barrier in case of women from ethnic minorities.

Women’s access to resources and economic participation

There is a gender gap in the property ownership in Georgia, which is most evident in the ownership of agricultural land (SDG indicator 5.a.1). A 12%-point gender gap is observed for reported ownership and an 18%- point gender gap for documented ownership of agricultural land. A new Agriculture and Rural Development Strategy for the period 2021–2027 identified women’s limited access to information, technologies and agricultural resources, as well as women’s limited access to agricultural lands, finances and other assets, as weaknesses that have to be addressed. Nevertheless, the Action plan (2021-2023) for the Strategy with activities and indicators does not correspond to the gender gaps, and women’s empowerment and inclusion components are not incorporated into the document. Gender mainstreaming is missing from other related normative documents and laws including the Law on Agricultural Cooperatives.

In 2019, the Parliament of Georgia’s Thematic Inquiry on Women’s Participation in State Economic Programmes identified that women are less likely to benefit from these programmes. The inquiry provides specific recommendations for relevant agencies on improving women’s involvement in the economic programmes. In 2018, women represented 45.1 % of the beneficiaries of Enterprise Georgia, while in agriculture programmes, such as the Preferential Agrocredit Programme, the share of women beneficiaries was only 7.6 % in the 2014–2019 period.

According to the GEOSTAT, Women and Men in Georgia 2021, the number of men founding businesses is almost twice as high as the number of women in the same category. A relatively small number of women- business owners are found in the mining industry, construction, transport and warehousing, and agriculture. On the other hand, the number of female owners is much higher than the number of male owners in areas of activity such as education, health and social services and other services.  It is important to mention that the gender gap in labour-force participation is higher in the rural population. The economic inactivity rate for urban women and men was 54.6 per cent and 35.5 per cent respectively while for rural women and men, the economic inactivity rate was 66.5 per cent and 40.9 per cent respectively (a difference of 25.5 points).

The Government of Georgia developed a new 2021–2025 SME Development Strategy of Georgia which recognizes the gender gap in small and medium-sized enterprises (SMEs) in terms of equal rights, knowledge and perspectives, as well as business opportunities, including unequal access to finances for women and men. Under the previous strategy, participation of women in entrepreneurship has not significantly increased. In 2018, women’s share among the newly established enterprise owners was 29.1 per cent in 2018, 29.2 per cent in 2019 and 29.7 per cent in 2020. In addition to owning fewer assets compared to men, responsibilities related to unpaid domestic and care work, as well as prevalent gender stereotypes, create additional barriers for women to start their own business. In the National Assessment of Women’s Entrepreneurship Development Report 2022 (WED), most women- entrepreneurs (61%) named access to financing as the biggest challenge to start-up their businesses and 74% of them see high interest rates as the most significant problem in obtaining loans from financial institutions.

As per CEDAW recommendations, Georgia was urged to facilitate the reconciliation of professional and private life for women and men including by expanding the number of childcare facilities and encouraging men to equally participate in family responsibilities, and to ratify the Maternity Protection Convention 2000 (No. 183) of the International Labour Organization, which has not been adopted yet.  In addition, the Committee stressed out the importance of effectives measures to prevent and combat sexual harassment of women to be established in the workplace.

As mentioned previously, in March 2021, the Government of Georgia joined the Generation Equality Forum and undertook new commitments in the area of Technology and Innovation for Gender Equality.  The information and communications technology (ICT) sector remains male dominated, with 86% of students in bachelor’s programmes being male in the 2021/22 academic year. In the case of engineering, production and construction, the number of female students  constitutes only 8%. In terms of economic participation, female employees in Georgia are also underrepresented in the ICT sector. The significant wage gap between the genders, including in the ICT sector, is a major issue in the country, with female employees earning 20 per cent less than male employees in 2020.

# The purpose, objectives and scope of evaluation

## The purpose of evaluation

This is a mandatory external final evaluation which is conducted by UN Women in the last year of the project (for both components) in the line with the UN Women Evaluation Policy.  The main purpose was to assess the achievement of the project results, its performance and identify lessons learned, best practices and challenges in order to promote accountability, learning and decision-making at UN Women Georgia.

The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for women’s empowerment in Georgia and to facilitate UN Women’s strategic reflection and learning for programming in the areas of good governance and women’s economic empowerment.  Main evaluation users include UN Women Country Office in Georgia, as well as the Government of Norway (the project donor). It is expected that the findings from this evaluation will contribute to building of the evidence base on effective strategies for enhancement of gender equality and women’s empowerment in Georgia and will facilitate UN Women’s strategic reflection and learning for programming in these areas. Furthermore, national stakeholders – civil society partners, Parliamentary counterparts and targeted state and non-state agencies are also expected to benefit from this evaluation.  Recommendations from the evaluation also seek creation of new partnerships and enhancement of synergies with stakeholders from all sectors in order to accelerate achievement of Good Governance for Gender Equality and Women’s Economic empowerment and, consequently, related SDG targets.

## Evaluation objectives

The specific evaluation objectives are as follows:

- Analyze the relevance of the implementation strategy and approaches of the “Good Governance for Gender Equality in Georgia” project;

- Assess effectiveness and organizational efficiency in progressing towards the achievement of the project’s results as defined in the interventions;

- Validate the project results in terms of achievements and/or lack of progress toward the outcome and outputs;

- Determine the impact of the intervention with respect to gender equality and women’s empowerment;

- Assess the sustainability of the results achieved by the project;

- Document lessons learned, best practices, success stories and challenges to inform future work of UN Women and the Norwegian Ministry of Foreign Affairs in the areas of governance and participation in public life and economic empowerment of women;

- Identify strategies for replication and upscaling of the project’s best practices;

- Provide actionable recommendations for future programmatic developments and maximize ownership by partners in the country covered by the project;

- Assess how the project and its results relate and contribute to commitments and achievement of Sustainable Development Goals (SDGs) in Georgia.

## The scope of evaluation

The final evaluation considered all aspects of the project and covered almost the full project implementation during the period starting from September 2019 until the end of March 2023. The evaluation was conducted online and in Georgia. Both components (Outcomes) of the project with their respective outputs were evaluated separately. Where relevant, the results from Outputs under both Outcomes were evaluated in their interconnectedness in order to draw conclusions on their mutual complementarity to contribute to the project Outcomes and, consequently, to the developmental goal.

The evaluation had both national and regional scope. At the national level, the evaluation team focused on the work that was done by the project to increase gender sensitivity of systems and institutions by integrating gender equality mainstreaming tools (mainly, under Outcome 1) and improving access to disaggregated data in the country. To that end, decision makers at the central level and gender focal points from local municipalities were engaged in the evaluation process to provide their insights about progress that the project made towards realization of the overall project goal.

In relation to the women’s economic empowerment, the results from the WEE component were compared with baselines established under the previous phase (the UN Women JAWE project).  As for the   grass root mobilization work in the regions of Guria, Imereti, Racha-Lechkhumi and Samegrelo-Zemo Svaneti, which was the part of the JAWE project, the focus of evaluation was on new Self-Help Groups (SHGs) developed under the WEE component (Outcome 2) and a new cohort of social workers (14 women) who provided leadership and guidance to local women to increase their participation in social mobilization and economic activities.

# Evaluation methodology

## Theoretical Framework

Following the initial desk review, the evaluation team reconstructed an overarching Theory of Change (see Annex 1) for the whole project with synergies or interlinkages between separate outputs. The synergies were identified through the consultations with the Project Team and validated with project partners. The overaching ToC and theories of change under each Outcome served as a theoretical framework (hypothesis) for this evaluation to answer the main question – to what extent the results brought by the project interventions matched the desirable results as formulated in the ToC at the level of the Outcomes and Outputs.  Furthermore, the ToC was used to validate the list of critical assumptions (in RRF, see Annex 9) and to inform lessons learned and recommendations. The presentation of findings in this evaluation report considers as much as possible interlinkages and synergies between both components (Outcomes) and outputs that were established during the inception phase.

## Evaluation standards, criteria and evaluation questions

This final evaluation was conducted according to the UNEG Norms and Standards for evaluation (2016) and the UNEG Code of Conduct for Evaluations in the UN System (2008). The consultants ensured that the evaluation process and the final report were in compliance with the GERAAS quality standards. Considering that all the evaluations at UN Women are annually assessed against the UN-SWAP Evaluation Performance Indicator and a related scorecard, the evaluation team followed the UNEG Guidance on Integrating Human Rights and Gender Equality to ensure that issues of human rights and gender equality were systematically addressed during the process of evaluation and reporting of the results. To answer the requirements for accountability at the inter-agency level against the performance indicators  in the UN Disability Inclusion Strategy (UNDIS),  the consultants  reviewed the extent of mainstreaming of rights of people with disabilities across the project interventions.

The evaluation was conducted based on the standard criteria of relevance, coherence, effectiveness, efficiency, sustainability. During the initial desk review and consultations with the project team, the team of consultants proposed two additional criteria of Partnerships for GEWE and SDGs and Innovativeness.

The key questions to be answered by the evaluation were the following:

- Relevance: A) How does the project reflect and align with gender equality national strategic plans and normative frameworks as well as Georgia’s international obligations and commitments? B) Is the project design based on quality analysis, including gender and human rights-based analysis, risk assessments, socio-cultural and political analysis? C) Were the programmatic strategies appropriate to address the identified needs of beneficiaries?

- Coherence: A) To what extent the project adheres to corporate strategic priorities of UN Women and the UN Women CO Strategic Note? B) Is the project achieving synergies between the larger UN Women’s portfolios and the work of the UN Country Team? C) Is the project achieving synergies between UN Women and key national stakeholders including national governments and CSOs? D) How does the project design match with the complexity of national structures, systems and decision-making processes?

- Effectiveness: A) What has been the progress made towards achievement of the expected results?  B) What are the reasons for the achievement or non-achievement of the project results? C) Does the project have effective monitoring mechanisms in place to measure progress towards results? D) What is the influence of the specific country context and circumstances on the achievement of results and operational effectiveness? F) How adaptable and rapidly does the project react to changing situations? G) Has the project achieved any unforeseen results, either positive or negative? For whom? H) What are the good practices and the obstacles or shortcomings encountered? How were they overcome? I) To what extent have capacities of relevant duty-bearers and rights-holders been strengthened?

- Efficiency: A) Have resources (financial, human, technical support, etc.) been allocated strategically to achieve the project outcomes? B) Have the outputs been delivered in a timely manner? C) To what extent were relevant stakeholders and actors included in the project planning and implementation? D)To what extent did the allocation of resources prioritize the need of most vulnerable women and girls?

- Sustainability:  A) To what extent has the project identified strategic partners that could pick up on supporting continued government, private sector and non-governmental action when the project comes to an end? B) How effectively has the project been able to contribute to the generation of national ownership of the project outputs? C) What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time after the project phase out?  D)To what extent has the project’s exit strategy been well planned and successful? E) To what extent has UN Women been able to promote replication of project successes?

- Partnerships for GEWE and SDGs: A) To what extent has UN Women been able to promote private and public partnerships to achieve GEWE and SDGs? B) What is the likelihood that these partnerships are going to be maintained to continue dissemination of the project results and successes?  C) What strategies were used by UN Women to strengthen leadership, commitment and technical capacity of institutions from various sectors to contribute to achievement of GEWE targets and SDGs?

- Innovativeness: A) What -if any- types of innovative good practices have been introduced in the project for the achievement of Good Governance and WEE results?

Additional sub-questions and specific indicators (standards) to guide data collection and analysis were developed under each of the criteria and are included in the Annex 2 Evaluation Matrix.

## Data collection and analysis

The evaluation methodology deployed mixed, quantitative and qualitative data.  Quantitative data coming from surveys and databases at the project partners’ and UN Women was collected and analyzed to answer the evaluation questions. Qualitative data collection methods included desk review, individual and focus group discussions, SWOT workshops and observations that were conducted remotely (online) and face to face. The data collection instruments are included into Annex 4. To ensure triangulation of data, the evaluation team employed several data collection methods with same categories of respondents i.e., local governance institutions, WEPs private companies, women from Self-Help Groups. The reasons for selection of methods are explained further:

- individual interviews were conducted with partners and stakeholders from the Government due their unique position and experience in relation to specific deliverables or products developed by the project;

- in case of WEPs signatory private companies, administration of a real time survey and following that discussion of findings during the meeting of WEPS advisory Council pursued the objective of validation of preliminary findings from analysis of surveys conducted by UN Women and individual interviews with selected WEPs companies (based on their size and economic sector);

- in order to reach as many as possible representatives of gender focal points from municipalities, individual interviews with Gender Advisors were followed by two online focus group discussions during which a real time survey method was used to engage participants into discussion and validation of findings from different data sources (individual interviews, desk review);

- individual and small group interviews with women-entrepreneurs (grantees of GFA) were conducted to collect stories and insights about relevance and effectiveness of strategies applied by the project;

- group interviews were conducted with rural women mobilized into SHGs to provide them with opportunities to share their views about the project and changes that it promoted in their lives; two of these interviews were conducted during site visits to two municipalities (Gori and Kareli); and two were held online to reach women located in remote regions;

- in parallel, to increase participation of women at grass root level in evaluation, 12 community workers facilitated SWOT workshops with them based on the guidelines developed by the international consultant; prior to that, capacity development was provided to 14 social workers in participatory methods of evaluation and SWOT techniques by the international and national consultants.

In addition to above, gender-responsive methods that facilitate participation and inclusion such as appreciative inquiry to identify results and positive changes in capacity development, Most Significant Change techniques, identification of success stories (impact on women’s lives, communities) were used with beneficiaries from SHGs and women-grantees of the project.  Integration of Human Rights and Gender Equality into data collection employed the methods such as adjusting interview questions to age, gender, ethnic, cultural and gender identification, level of education, vulnerability status of participants; and comparing data obtained from different sources (triangulation).

Selection of participants (sampling) in this evaluation was informed by the stakeholder analysis conducted during the inception phase (see Annex 3) and followed the criteria for inclusion such as the position of stakeholders to the project Outputs and deliverables, priorities  for their inclusions ( High, Medium, Low) based on criticality of their engagement for sustainability of results, and their role in the evaluation. In selection of respondents for interviews and focus groups discussion, the evaluation team applied purposive, non- random sampling methods. Mainly, inclusion of representatives of duty bearers was informed by their position (power) and ability to influence decision making and  contribute to sustainability of interventions and deliverables of the project. Sampling of beneciaries of the project – rural women from SHGs groups and women-entrepreneurs considered their availability and location. As mentioned under the scope of evaluation, the project worked in four regions. Beneficiaries from all regions were included into the evaluation sample. Two regions – Shida Kartli and Kvemo Kartli – were selected for site visits due to population characteristics such as large numbers of IDPs ( among them women) and compact living of ethnic minorities.

In the result, 224 participants from 8 regions of Georgia contributed to the evaluation findings (about 96% women) . Out of them,  77 participants represent rural women from most vulnerable groups in five regions of Georgia. Figure 3 provides a detailed overview of  participation of stakeholders and beneficiaries in this evaluation. The full list of respondents is included in Annex 5. The evaluation team revised about 120 documents that have relevance to this evalution. The list of documents is found in Annex 6.

Figure 3 Representation of participants in evaluation

Mainly, the evaluation team used qualitative data analysis methods such as coding of interviews according to the evaluation criteria and indicators in Evaluation Matrix and identification of common themes and similarities and differences in responses. To ensure mainstreaming of human rights and gender equality into data analysis, the evaluation team collected and used disaggregated data available at UN Women and partners. Furthermore, qualitative data obtained during interviews and focus groups discussions was compared with existing data on HR and GE available in monitoring and assessment reports and baseline studies. Data analysis also integrated identification of common and different responses and themes between groups of stakeholders (duty bearers and rights holders). As well, individual stories and case studies i.e., success stories were analysed in the context of general information found in the studies and reports prepared by the project and other research. Quantitative methods included calculation of frequencies and other simple statistics for data that came from surveys and databases owned by UN Women and partners.

## Limitations

During the inception phase, the evaluation team identified potential limitations that may affect validity and reliability of findings. These limitations are related to participation of beneficiaries, especially from remote areas (mountainous regions) and from vulnerable groups; conclusions about UN Women’s project results attribution to changes in gender sensitivity of systems and institutions and progress in women’s economic empowerment, and issues of subjectivity in interpretation of qualitative data from interviews and focus group discussions. Table 1 presents these issues together with risks and mitigation strategies.

Table 1 Limitation mitigation strategies

| Limitations | Risks | Mitigation strategies |
| --- | --- | --- |
| - Participation of beneficiaries from remote areas (mountainous regions) and from vulnerable groups i.e., rural women from mountainous villages or with poor infrastructure, women with many children, disable women or women who take care of disable family members and other. | Findings do not capture progress or lack of that for most vulnerable women (LNOB) | - The evaluation employed of a variety of data collection methods, such as individual interviews (phone), focus group discussions, SWOT workshops; - The evaluation team raised the capacity of 14 local community workers in SWOT to conduct SWOT workshops in distant villages |
| - Participation of beneficiaries of NALAG – local municipalities (64 municipalities) | The evaluation team did not have time and means to reach all 64 municipalities. Moreover, the project mainly worked on the central level. Nevertheless, the findings related to the local governance component (NALAG as the main partner) would have been limited without reaching the majority of municipalities that differ by their context (location, population, uneven socioeconomic) and status of their gender focal points (Gender Advisors) | - Individual interviews with selected representatives of municipalities in all regions targeted by the project were followed by online focus group discussions; - During focus group discussions, a real-time survey was administered using Slido to validate results of individual interviews and desk review of project documents and to |
| - Attribution versus contribution of the project results to progress in gender sensitivity of systems and institutions and women’s economic empowerment | During the inception phase, multiply actors have been identified such as other UN agencies, World Bank, USAID, EU, GIZ and non-governmental organizations that have been working towards similar results (Outcome and Output level) which may affect conclusions about actual project contributions | - To avoid the bias, the evaluation focused on the project contribution through the lenses of comparative advantages of UN Women Georgia such as ownership of gender mainstreaming methodologies and tools such as GIA, GRB and WEE; - The evaluation team conducted desk review and interviews with some of actors on the topic of synergies and/or overlapping. |
| - Subjectivity related to qualitative data collection and analysis | Subjectivity such as differences in interpretation of qualitative data and making connection to evaluation questions may affect reliability of findings | - the international consultant developed a coding system and the consultants were trained in using it. - In addition, the peer review was applied continuously to ensure that there was consistency in coding the data. |

## Evaluation management

The evaluation was coordinated with the Evaluation Management Group established at UN Women. The UN Women Georgia Monitoring and Evaluation Focal Point (GG4GEG Project Coordinator) was responsible for day-to-day management of the evaluation and ensured that the evaluation was conducted in accordance with Evaluation Policies, United Nations Evaluation Group Ethical Guidelines and Code of Conduct for Evaluation in the United Nations system and other key relevant guidance documents. Furthermore, participants in the Evaluation Reference Group (see Annex 7) were consulted by the evaluation team on different aspects of evaluation and were engaged throughout the process. The ERG group participated in validation of the preliminary findings, reviewed the draft evaluation report and provided substantive feedback into that to ensure quality and completeness of the final report.  The evaluation process was supported by the UN Women Europe and Central Asia Regional Evaluation Specialist.

## Ethical issues

The evaluation was conducted in accordance with the principles outlined in the UNEG Ethical Guidelines for Evaluation (2020). The evaluation team upheld to the following the principles during the evaluation:

Respect: the evaluation process and communication of results was conducted in the way that clearly respected the stakeholders’ dignity and self-worth;

Empowerment: use of participatory and empowerment approaches methods was emphasized by the evaluators to ensure that all participants realize benefits from their participation in this evaluation and how it was related to realization of human rights, gender equality and achievement of the SDGs;

Informed consent: every participant was informed on the objectives of this evaluation and their participation is on a voluntarily basis, meaning that, at any time, all participants are given the rights to choose whether or not to participate and/or withdraw from the evaluation;

Inclusion and Non-Discrimination:  equitable participation and treatment of all participants was ensured through the evaluation methodology; differences in culture, local customs, religious beliefs and practices, personal interaction and gender roles, age and ethnicity were mindfully weighted and considered when planning, carrying out evaluation and reporting on the results;

Do no harm:  the evaluation team ensured that no harm happened to the participants of the evaluation; all meetings were held in safe places and no recording were made; notes from interviews did not contain full names and were not shared with anyone, as well data presentation and discussion in the report does not allow for their potential identification;

Fair representation: the selection of participants was done in relation to the aims of the evaluation, not simply because of their availability; the power imbalances were purposefully addressed by ensuring that data collection methods allowed for participation of most vulnerable women from remote locations.

# Findings

## Relevance

Main findings: Finding 1. The project is directly aligned with national strategies, UNSDCF and nationalized SDGs; its implementation directly supported the country in meeting international commitments, in particular by addressing the majority of recommendations from CEDAW, European Commission and other related to strengthening gender equality mainstreaming through relevant legislation and systematic application of gender equality mechanisms and tools at the institutional level; Finding 2. The project strategies were informed by the quality analysis of human rights and gender equality based on assessment of international organizations and UN Women analytical input such as a comprehensive Country Gender Equality Profile. The project largely contributed to availability of data and research on the situation of human rights and gender equality in the number of areas i.e., access of women to ICT and career in technology, barriers to women’s entrepreneurship, sexual harassment in public administration and other. In relation to the rights of women with disabilities, the project contributed with the situation analysis and informed development of relevant legislation. Finding 3. Mainstreaming of the LNOB principle was evident in the design which presents an attempt to address holistically gender-based inequalities at the national and local governance level; criteria for inclusion were consistently applied by the project partners and interventions directly addressed the needs of most vulnerable women i.e., rural women, IDPs, ethnic minorities in most disadvantaged regions of Georgia in order to increase their income generation opportunities.

Full description of findings

Finding 1. The project is directly aligned with national strategies, the UNSDCF 2021-2025 and nationalized SDGs; its implementation directly supported the country in meeting international commitments, in particular by addressing the majority of recommendations from CEDAW, European Commission and other related to strengthening gender equality mainstreaming through relevant legislation and systematic application of gender equality mechanisms and tools at the institutional level.

As it was stressed out in the VNR 2020, further legal amendments are needed to bring the country in full

compliance with the international obligations, notably those of the Beijing Declaration and Platform for

Action (BpfA) and the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW). Applying gender lenses to ongoing and upcoming reforms would enable Georgia to fill many gender equality gaps and help the full realization of Agenda 2030, especially in relation of some forms of violence against women (VAW) and gender-based violence (GBV) that women and girls face in Georgia, women’s underrepresentation at all levels of governance, and women’s lack of access to resources and assets.

To that end, the project directly addressed the concerns of the CEDAW Committee expressed at lack of strategic vision for gender equality in Georgia and the need to ensure systemic approach to integration of gender mainstreaming tools. Most noteworthy contributions of the project component on Good Governance include  the State Concept of Gender Equality adopted by the Parliament of Georgia in December 2022; the legislative proposal on institutionalizing Gender Impact Assessments (GIAs) as a part of the law-making cycle adopted by the Parliament of Georgia in 2022; the Gender Mainstreaming Toolkit for the Government of Georgia, endorsed by the GEC in 2021; and integration of gender-responsive budgeting into public finance management systems (the Public Finance Management Strategy to be adopted in the first of quarter of 2023). The latest is of particular importance for improving accountability and financing for gender equality and SDG 5 since it is to embed the system of gender tags in the budget management system, which “will enable analysis of influence of gender aspects on gender budgeting process; gender analysis of impact of service provision type programs; supervision of gender aspects by representative bodies.”

Being in alignment with the UNSDCF 2021- 2025 (respective Outcomes 1 on Good Governance and 3 on Inclusive Economic Growth), the project promoted achievement of 17 targets (directly or indirectly) in the Result Framework, mainly under SDG 5, 16, and 8.  In relation to the UNSDCF target 1.1.3 Number of policies/procedures adopted by the Government of Georgia that aim at improvement of institutionalization of gender equality and gender mainstreaming (NSDG 5.1.1./SDG 5.1), due to efforts UN Women and partners, 11 policy documents, guidelines and procedures were developed and approved that institutionalize gender equality and its mainstreaming in the national policy planning processes and budgeting at the level of the Government and public administration institutions.

Finding 2. The project strategies were informed by the quality analysis of human rights and gender equality based on assessment of international organizations and UN Women analytical input such as a comprehensive Gender Equality Country Profile. The project largely contributed to availability of data and research on the situation of human rights and gender equality in the number of areas i.e., access of women to ICT and career in technology, barriers to women’s entrepreneurship, sexual harassment in public administration and other. In relation to the rights of women with disabilities, the project contributed with the situation analysis and informed development of relevant legislation.

The project design and strategies were informed by several background studies and assessments including the UN Common Country Analysis, VNR 2020 and others.  Among those, a most compressive Country Gender Equality Profile (developed in 2020 and updated under the project in 2021) described and analyzed situation in Georgia based on the SDG indicators and, at the same time, considering the BPfA and CEDAW frameworks. The CGEP revised all 12 critical areas of the BPfA  , identified barriers and risks and provided with recommendations. On following these recommendations, the project promoted solutions in eight areas out of 12 and integrated strategies that directly targeted fulfilment of women’s human rights such as freedom from discrimination and violence, access to education, ownership over agricultural land and the right to participate in public life and decision-making.

On following the recommendations from CGEP the project addressed in a systematic and holistic way roots causes of gender-based inequalities as in relation to women’s participation in decision making and women’s economic empowerment. A good example of that would be an approach undertaken towards gender mainstreaming in the Public Administration Reform (PAR). While supporting development of the Public Administration Reform Strategy and its Action Plan, UN Women ensured that gender mainstreaming has been integrated into the institutional strategies of key stakeholders such as Civil Service Bureau, NALAG, and others, and human resources capacities of public administration have been increased to ensure gender-sensitivity of internal policies and provision of services. This makes direct relevance to the project objective of having better informed civil servants who can make decisions and provide services to women with respect to their specific needs and women’s human rights. Furthermore, the project addressed poor enforcement of some legislation such as on prohibiting sexual harassment in the workplace   and violence, in particular in public service. Twelve entities (including ministries and LELPs) adopted internal sexual harassment complaint mechanisms with the support of the project and 775 public servants were trained on sexual harassment. The ultimate target of this systemic approach was of removing of some structural barriers for women to pursue career development in public administration and to increase the number of women in decision making positions.

The WEE component further promoted gender sensitivity and women’s economic empowerment at the private sector through the WEPs platform and by addressing women’s human rights such as access to land.  Conducted under the WEE component, Gender Impact Assessment (GIA) of the legal framework about the matrimonial property as joint ownership of the spouses provided policy recommendations for enhancement of equal rights of women and men for land and other assets essential for their economic empowerment. By partnering with National Agency of Public Registry and promoting gender mainstreaming at the level of this entity, UN Women attempted to create a more favourable environment for reinforcement of the relevant legislation and its effective monitoring. Furthermore, the project made an attempt to mainstream issues of diversity, equality and inclusion (DEI) into human resources management at the WEPs companies by producing the first of such kind manual for WEPs signatory companies.

The efforts of the project to address lack of data and research on the situation with human rights and gender equality are most commendable and in line with the international recommendations and national priorities to ensure that policy planning and decision making are based on evidence and disaggregated data. Seven studies have been produced under the project (four of them by the Public Defender’s Office) that address data gaps in relation to gender specific inequalities such as on needs of women and girls with disabilities  ,  access of women to ICT  and women’s entrepreneurship   and other (see Annex 6). In relation to the rights of women and girls with disabilities, the project contributed with the situation analysis to implementation of  the UN joint program “Transforming Social Protection for Persons with Disabilities in Georgia” supported by the Norwegian Ministry of Foreign Affairs and the Joint SDG Fund and involved one of non-governmental organizations (Partnership for Human Rights) that promotes participation of women with disabilities in decision making to contribute to development of the shadow report to the CEDAW Committee.

First time in Georgia, the Time Use Survey was conducted by the National Statistics Office of Georgia (GEOSTAT) providing with the national data for the SDG indicator 5.4.1.  The proportion of time spent in a day on unpaid domestic and care work by men and women. Due to the project capacity development interventions, GEOSTAT developed the Strategy for Gender Statistics 2021-2023, which presents a comprehensive policy document on improvement of gender statistics and disaggregated data in the country, also in relation to most vulnerable population as women and girls with disabilities, rural women.

Finding 3. Mainstreaming of the LNOB principle was evident in the design which presents an attempt to address holistically gender-based inequalities at the national and local governance level; criteria for inclusion were consistently applied by the project partners and interventions directly addressed the needs of most vulnerable women i.e., rural women, IDPs, ethnic minorities in most disadvantaged regions of Georgia in order to increase their income generation opportunities.

While the major focus on the Good Governance component was on the national level gender mainstreaming capacity development and, in line with that, on raising capacity of duty bearers’ institutions to promote gender equality in their areas of work, the selection of key partners and areas of impact informs of prioritizing the needs of most vulnerable women i.e., IDPs and victims of domestic and gender-based violence.  For example, with the project support, two important national documents - National Action Plan on Combating Violence against Women and Domestic Violence and Measures to be Implemented for the Protection of Victims and National Action Plan on the Implementation of UN Security Council Resolution 1325 were developed and approved integrating gender disaggregated data and analysis. The strong emphasis was put on combating of workplace sexual harassment  and protection from domestic violence including in the public service, which may increase awareness and reporting on these offences remaining largely unreported according to the CEDAW Committee concluding observations  and accelerate achievement of DV and GBV targets due to increased gender -sensitivity of public administration and services provisions.

The evidence from the SWOT analysis conducted with rural women – members of self-help groups (beneficiaries of the WEE component) provides additional justification of relevance of the project strategies and interventions (see Figure 4). For example, during one of the meetings of the evaluation team with women in SHGs in the conflict affected region of Georgia, women who have children with disabilities (among them adopted) commented on the relevance of the project to provide them with opportunities to increase knowledge and skills and to improve necessary infrastructure and support for children in the village, which allows them also to pursue their economic activities and establish financial independence.

The relevance of interventions designed by the project has been also confirmed by the findings from the Time Use Survey 2020-2021, as well as other studies, in particular on women’s entrepreneurship. The financing rate of the self-employment support grant programme is lower in the regions compared to Tbilisi (in the case of both genders), and the difference is more significant in the case of females.  Increasing access for women to the state funded support programmes i.e., Enterprise Georgia and those of the financial institutions had a strong relevance to the beneficiaries of Taso Foundation (social mobilization component) and Georgian Farmers Association (GFA).  In this connection, the emphasis of the project on cooperation with the financial sector as with financial institutions -WEPs signees and with IFIs (through an established working group) is most commendable since it had the ultimate target to increase opportunities for entrepreneurship for vulnerable women in the rural areas.

Women, beneficiaries of the social mobilization component included rural women, among them those who are subjected to a variety of vulnerabilities such as women-IDPs, women who married early, ethnic minorities, single household women, women with many children, women with disabilities and taking care of family members of disabilities. Taso Foundation, a long-term partner of UN Women under the WEE component (Outcome 2), developed a methodology for social mobilization which specifically addressed issues of inclusion. As Figure 5 shows, out of 241 women organized into self-help groups, 65 women or 27 % included women who are regarded as most vulnerable. It is noteworthy that 100% of these women participated in trainings provided by Taso Foundation and partners from WEPs companies. While the percentage of the women who received the grants to start the business varies across the regions, in average it constitutes 35%; in addition, some women were able upon completion of trainings to apply and secure finding from other sources including the state funded programmes e.g., at Enterprise Georgia. Although the project was not able to report at this stage on increase in the number of women with disabilities to economic opportunities, according to Partnership for Human Rights, at this moment the emphasis is on social mobilization of women with disabilities, also by increasing their representation in the boards of CSOs. The organization has created a platform to consolidate  the efforts of all CSOs representing women with disabilities to advocate, at national and local level, also with involvement of media outlets, political and economic participation of women with disabilities.  Increasing participation of women with disabilities in economy is seen as the next step.

## Coherence

Main findings: Finding 4. The project was well aligned with the UN Women global and national strategic documents and its implementation demonstrated the effective use of UN Women Georgia comparative advantages in the areas of good governances and women’s economic empowerment; Finding 5. UN Women ensured synergies between the project and the larger UN Women’s portfolio and with the work of the UN Country Team without overlapping and duplication. At the same time, better communication and coordination would be desirable in relation to gender mainstreaming at the local governance. Coordination with national institutions, CSOs, private sector and non-UN stakeholders was enhanced through various formats including ones established during the project. Finding 6. The project design and implementation strategies make clear references to the national structures and decision-making processes and makes maximum use of existing in the system opportunities; the project team did an excellent job in securing participation and ownerships of results of key institutions that have decision making power and capacities influence positive changes in relation to challenges addressed by the project.

Full description of findings

Finding 4. The project was well aligned with the UN Women global and SN 2016-2020 and 2021-2025, consequently, and its implementation demonstrated the effective use of UN Women Georgia comparative advantages in the areas of good governances and women’s economic empowerment.

The project is well aligned with the UN Women Global Strategic Plan 2022-2025 and it made a significant contribution to a number of indicators under the Impact Area 1: Governance and Participation in Public Life (Outcome 1 Global normative frameworks and gender responsive laws, policies and institutions and Impact) . Among traditional actors in this field in Georgia as UNDP, EU, GIZ and other, UN Women successfully leveraged its technical expertise in gender impact assessments, gender-responsive budgeting and gender disaggregated data. Under Good Governance component, UN Women made a serious claim of being one of the leaders in mainstreaming gender into the Public Administration Reform (PAR) by integrating participatory gender audits, sexual harassment preventing mechanisms, raising capacities of public servants and supporting institutionalization of gender equality plans, all with the ultimate goal to increase participation of women in decision making (SDG 5.5.1).

By supporting the country to conduct its first Time Use Survey, the project has not only addressed the gaps in data for SDG 5.4.1: Proportion of time spent on unpaid domestic and care work, by sex, age and location, but facilitated policy dialogue and decisions making that would also benefit results related to women’s economic empowerment. Integration of gender responsive budgeting into public financing was another success that should promote achievement of SDG Indicator 5.c.1: Proportion of countries with systems to track and make public allocations for gender equality and women’s empowerment and facilitate tracking and, hence, accountability of public budget allocation to gender equality and women’s empowerment.

Under the WEE component aligned to Impact Area 2: Women’s Economic Empowerment UN Women (Outcome 4), UN Women built up on the success of the first phase of the JAWE project and continued raising gender-sensitivity of the private sector through WEPs. Ownership of WEPs and increased expertise of UN Women has been broadly recognized and sought by private companies and partners, also promoting cooperation of UN Women in the private sector with non-UN actors such as USAID, EBRD in ensuring coherence in mainstreaming gender equality and women’s empowerment into interventions. During the interviews with the evaluation team, representatives of USAID and EBRD shared how they ensured coherence to the work of the project by integrating requirements or motivating private companies – applicants to join WEPs and implement interventions that benefit women in particular.

As most relevant, UN Women used available gender tools (GIA, PGA) to address structural barriers to greater economic empowerment of women. For example, pursuing access to land (SDG indicator 5.a.1)  has been in cooperation with financial institutions -signees of WEPs and key public institutions i.e., Enterprise Georgia and GITA. Furthermore, UN Women used the comparative advantages being a leading agency at the Generation Equality Action Coalitions (joined by Georgia in 2021) to strengthen coherence and cooperation between interventions of private and public institutions to accelerate the increase of women and girls in STEM and ICT by launching 500 Women in Tech project and supported the country to develop a Technology and Innovation Action Plan.

Finding 5. UN Women ensured synergies between the project and the larger UN Women’s portfolio and with the work of the UN Country Team without overlapping and duplication. At the same time, better communication and coordination would be desirable in relation to gender mainstreaming at the local governance. Coordination with national institutions, CSOs, private sector and non-UN stakeholders was enhanced through various formats including ones established during the project.

There is good evidence found by this evaluation of synergies between the project and the larger UN Women’s portfolio. For example, in connection to the commitment made by Georgia to eliminate the gender pay gap that equals to 36 per cent (GEOSTAT, 2019) , UN Women has been participating in the reform of the Labour Code and has developed a mechanism and methodology for enforcing this principle. These actions provided complementarity to the efforts of the GG4GEG project component to reduce stereotypes as related to women’s or men’s professions and increase opportunities for career advancement and better income for women in the private sector. Furthermore, the Good Governance component of the project represents the largest project in the UN Women portfolio in Georgia in the area of governance and by promoting gender sensitivity of legislation, national policies and institutions the project creates more favourable operating environment for other projects.

Overall coordination has been effective and UN Women used its participation in the national gender mainstreaming mechanism such Parliamentary Gender Equality Council, Inter-Agency Commission, UNSDCF Result Groups, UNSDCF Gender Theme Group and other thematic groups and networks to ensure that there is no duplication across different stakeholders’ intervention. For example, under the Good Governance component, development of a legislative proposal on institutionalizing gender impact assessments (GIA) as a part of the law-making cycle was a highly consultative process in close cooperation with development partners (especially UNDP and the NDI) and representatives of the legislative and executive branches of the Government. Similar, the Rapid Gender Assessment (RGA) of the COVID-19 situation in Georgia (second wave) has been conducted by UN Women in partnership with UNDP and UNFPA. The findings and recommendations of the second RGA were further incorporated into a broader COVID-19 impact analysis coordinated by the Administration of the Government with the support of the UNCT and USAID.

One more example would be gender mainstreaming into the Public Administration Reform which was pursed in synergies with Parliamentary Gender Equality Council, NALAG, PDO (independent monitoring), other actors as UNDP, GIZ, EU and civil society organizations. This work also highlighted the need for UN Women to improve communication among donors and actors supporting decentralization and public administration reforms.  As shared by representatives of 24 municipalities during the focus group discussions, lack of communication between mentioned actors and CSOs working on local governance issues   results in misunderstanding and inconsistency in use of gender mainstreaming tools i.e., GRB, gender equality plans by local governance institutions.

Finding 6. The project design and implementation strategies make clear references to the national structures and decision-making processes and makes maximum use of existing in the system opportunities; the project team did an excellent job in securing participation and ownerships of results of key institutions that have decision making power and capacities influence positive changes in relation to challenges addressed by the project.

Box 1: How do you see the role of WEPs Council in 3-4 years?

- WEPs Council has role of a mediator between businesses, government and the society;

- Outreach and engagement with businesses, governments, and civil society organizations to promote awareness and understanding of the importance of gender equality and women's empowerment in the workplace and beyond,

- Engage those sectors that are not involved right now. Georgia has still a lot of work to do in terms of Gender equality and WEPs is one important tool for this.

- WEPs Council could work more actively with the Government to advance gender equality on the national level;

- WEPs Council is an independent agency / entity (mainstreaming the women’s empowerment and diversity (not only gender, but age, ethnic, disabilities, LGBTQ etc.)

Source: Quotes from the real -time survey conducted during the meeting of the evaluation team with the WEPs Council on March 24th in Tbilisi

Box 1: How do you see the role of WEPs Council in 3-4 years?

- WEPs Council has role of a mediator between businesses, government and the society;

- Outreach and engagement with businesses, governments, and civil society organizations to promote awareness and understanding of the importance of gender equality and women's empowerment in the workplace and beyond,

- Engage those sectors that are not involved right now. Georgia has still a lot of work to do in terms of Gender equality and WEPs is one important tool for this.

- WEPs Council could work more actively with the Government to advance gender equality on the national level;

- WEPs Council is an independent agency / entity (mainstreaming the women’s empowerment and diversity (not only gender, but age, ethnic, disabilities, LGBTQ etc.)

Source: Quotes from the real -time survey conducted during the meeting of the evaluation team with the WEPs Council on March 24th in Tbilisi

UN Women should be complimented on the quality of stakeholders’ analysis and partnership building for this project. The key structures, such as the Parliamentary Gender Equality Council, four thematic task forces under the Inter-Agency Commission and other institutions with power to affect decision making have been effectively used to ensure mainstreaming of gender equality and women’s empowerment in the legislative and executive branches of power. This may have contributed to a high rate of legal acts, strategic documents and action plans developed with support of the project. In parallel, partnerships with key institutions Ministry of Finance, CSB, PDO, NAPR etc., as well as innovative partnerships established with associations (NALAG, HRPA) allowed attracting available national capacity to ensure broader impact on systems (governance) and institutions within the overall project goal to achieve their greater gender sensitivity for gender equality and women’s empowerment in Georgia.

Under the WEE component, UN Women continued cooperation with key partners that are in position to promote gender mainstreaming in the private sector, but also , following recommendations from the final evaluation of the JAWE project, supported establishment of the WEPs Council – a new structure comprised of active WEPs-signees that has lots of potential, according to its members (see Box 1), to promote WEPs into other companies and sectors that are not currently engaged and advocate together with civil society at the Government decision making that should accelerate achievement of gender equality and women’s economic empowerment i.e., on maternity protection, equal share of responsibilities in the family of men and women etc.

Active engagement with the Parliamentary Gender Equality Council and PDO has resulted in development of several comprehensive assessment studies that have broader implications for ongoing structural reforms (PAR, decentralization) critical for achievement of gender equality. To add to the list, UN Women consolidated engagement of 29 NGOs and CSOs using the CEDAW reporting mechanism, to work on the shadow report that provides with independent opinion of women’s organizations and human rights and gender equality advocated on the progress that the country made since the previous reporting period.

## Effectiveness

Main findings: Finding 7: In terms of UN Women contribution to achievement of the overall goal and, respectively to SDGs, institutionalization of gender impact assessments and gender-responsive budgeting is a critical achievement to mainstream gender equality into national policy processes and implementations supported by quality gender-disaggregated data to inform decision making. Some milestones were achieved to promote more gender sensitive public administration institutions and increase gender sensitivity in several sectors in order to accelerate achievement of the international commitments and nationalized SDG targets. Finding 8: The project achieved a breakthrough in terms of promotion of WEPs and institutionalization of gender sensitive practices at the private sector. Relevant and tailored for the needs of stakeholders’ project strategies contributed to maturity of WEPs companies and increased their ownerships of WEPs and SDGs. The new institutional structures – the WEPs Council and thematic groups - gained trust and recognition, which provides assurance that greater engagement of private companies in discussion and solution of key problems in relation to GEWE may be increased in future. Finding 9: Achievement of the project results for rights holders – vulnerable women from rural areas reconfirmed comparative advantages of UN Women in this area of work such as effectiveness of social mobilization methodology and established strategic partnership and quality expertise provided by UN Women and the project partners to increase women’s opportunities to build sustainable business and increase income. Finding 10: The project ToC was sound; major assumptions and risks to overall project performance (crisis in the Government, post-COVID19 recovery) are well defined and risk strategies have been effective. The project rapidly reacted to the changing situation in the country which was affected by multiply crises during the project implementation. Needs based, tailored approaches in working with the Government and stakeholders from ministries and LELPs, as well as with private companies allowed UN Women to achieve more under this project than it was anticipated. Finding 11: Monitoring systems at UN Women and partners allowed collecting rich information on activities and immediate products. At the same time, reporting on LNOB and lessons learned has been uneven among partners, which affected the quality of UN Women reports to the donor. Finding 12: The project made significant investment into building capacities of duty bearers at the national level and, to some extent, at the local level to mainstream gender equality structures and tools. The capacities of CSOs have been increased to ensure monitoring and evaluation of international GEWE commitments and to provide capacity development in GIA and GRB. Building capacities of the partners involved into the WEE component targete increased commitment of the individual private companies to WEPs.

Full description of findings

Finding 7: In terms of UN Women contribution to achievement of the overall goal and, respectively to SDGs, institutionalization of gender impact assessments and gender-responsive budgeting is a critical achievement to mainstream gender equality into national policy processes and implementations supported by quality gender-disaggregated data to inform decision making.  Some milestones were achieved to promote more gender sensitive public administration institutions and increase gender sensitivity in several sectors in order to accelerate achievement of the international commitments and nationalized SDG targets.

Figure 6: Key milestones under Good Governance component

- 11 policy and procedure documents developed and endorsed by the Government;

- 4 independent monitoring reports produced by Public Defender’s Office;

- 53 CSO representatives (48 Women and 5 men) strengthened their capacity on international monitoring and reporting mechanisms on gender equality; 18 representatives of CSOs (16 women, 2 men) were trained in Gender Impact Assessment (GIA);

- 1,327 public servants were reached by gender mainstreaming capacity development interventions;

- 44 municipalities developed gender equality plans;

- 12 Ministries and LELPs established sexual harassment prevention mechanisms;

- 176 producers (e.g., GEOSTAT) and users strengthened their capacities in the collection, analysis and use of gender statistics.

Figure 6: Key milestones under Good Governance component

- 11 policy and procedure documents developed and endorsed by the Government;

- 4 independent monitoring reports produced by Public Defender’s Office;

- 53 CSO representatives (48 Women and 5 men) strengthened their capacity on international monitoring and reporting mechanisms on gender equality; 18 representatives of CSOs (16 women, 2 men) were trained in Gender Impact Assessment (GIA);

- 1,327 public servants were reached by gender mainstreaming capacity development interventions;

- 44 municipalities developed gender equality plans;

- 12 Ministries and LELPs established sexual harassment prevention mechanisms;

- 176 producers (e.g., GEOSTAT) and users strengthened their capacities in the collection, analysis and use of gender statistics.

Under Outcome 1 (Good Governance) important milestones have been achieved by the project that are going to have a long term, positive effect on gender equality and empowerment of women in Georgia. In relation to gender sensitivity of systems, due to the project efforts to promote gender -responsive budgeting at the national level, the Ministry of Finance conducted a Gender-Responsive Public Finance Management (GRPFM) assessment and,  in alignment with the GRPFM report findings, has integrated gender equality in the draft Public Finance Management Strategy to be adopted by the Government of Georgia in the first quarter of 2023. This is going to have a profound impact on monitoring of funding allocation to gender equality and women’s empowerment at the public institutions and, therefore, track funding on gender related SDG targets and, consequently, SDG 5, which until now remained a challenge.

To improve access to gender-disaggregated data and support evidence-based decision making, the project strengthened capacities of partners in key positions to influence progress in this area. Visibility and capacity of two main gender equality mainstreaming structures as the Parliamentary Gender Equality Council and Public Defender’s Office have been enhanced due to elaboration of high-quality studies and assessment reports. Identification of problems of gender mainstreaming in public administration at the national and local level contributed to elaboration through gender lens of the Public Administration Reform Strategy and Action Plan (adopted in 2022).

The evaluation looked at the current level of mainstreaming of gender equality and women’s economic empowerment in some national level plans and sectoral strategies that were developed within the framework of this project and beyond with support of UN Women.  The purpose was to identify to what extent the documents promoting participation of women in decision making and women’s economic empowerment integrate specific objectives related to mainstreaming of gender analysis and collection of gender disaggregated data – two tools actively advocated by the project through institutionalization of gender impact assessments (GIA) and building national statistical capacities. As findings in the Figure 7 suggest, using gender analysis has been mentioned as an objective in the majority of the documents, except for the National Strategy for Human Rights Protection 2022-2030. Also, most of the documents integrated tasks to improve collection and use of gender disaggregated data. This suggest that UN Women efforts, in particular of Good Governance component, to mainstream gender equality tools into national policy processes and institutional have been quite effective and the need for UN Women’s expertise is likely to remain high on the national policy agenda. The most demand for UN Women’s expertise, according to the interview with GEOSTAT, is going to be in the use of gender disaggregated data for decision making, which may be explained with the fact that implementation of many new strategies and action plans will be launched in 2023.

Figure 7. Mainstreaming of gender sensitivity

in key national and institutional strategies and action plans

Finding 8: The project achieved a breakthrough in terms of promotion of WEPs and institutionalization of gender sensitive practices at the private sector.  Relevant and tailored for the needs of stakeholder’s project strategies contributed to maturity of WEPs companies and increased their ownerships of WEPs and SDGs. The new institutional structures – the WEPs Council and thematic groups- gained trust and recognition, which provides assurance that greater engagement of private companies in discussion and solution of key problems in relation to GEWE may be increased in future.

Following the recommendations from the evaluation of the first phase of the JAWE project, the WEE component continued promoting WEPs in the private sector in Georgia, creating more enabling legislative and institutional environment to promote women’s economic empowerment and expanding cooperation between public, private and civil society sectors to address the needs of most vulnerable women residing in rural areas. Figure 8 presents the key results achieved under this component.

Figure 8: Key milestones under WEE component

- 175 companies signed the WEPs by January 2023;

- 444 representatives from the WEPs companies increased their awareness of gender equality at the workplace;

- WEPs Advisory Council and seven thematic groups have been established

- 50 policymakers and public servants were provided with capacity development in GEWE;

- 202 women increased skills in business and leadership-related topics;

- 101 women in rural areas were supported for economic activities;

- 29 new SHGs uniting 329 women have been formed;

- 591 women and girls acquired new IT skills

Figure 8: Key milestones under WEE component

- 175 companies signed the WEPs by January 2023;

- 444 representatives from the WEPs companies increased their awareness of gender equality at the workplace;

- WEPs Advisory Council and seven thematic groups have been established

- 50 policymakers and public servants were provided with capacity development in GEWE;

- 202 women increased skills in business and leadership-related topics;

- 101 women in rural areas were supported for economic activities;

- 29 new SHGs uniting 329 women have been formed;

- 591 women and girls acquired new IT skills

Flexible and tailored to the needs of private companies approach undertaken by UN Women and partners i.e., Georgian Chamber of Commerce and Industry has been highly appreciated by participants of interviews and meetings during the evaluation mission. About 60% companies went through WEPs training and were supported in use of Gender Gap Analysis tool (GGA) and development of action plans. About 30% of companies integrated sexual harassment prevention mechanisms into their human resources management (Figure 9).

As the results of the UN Women baseline study (2021)  suggest, top three reasons for motivation of the private companies to join WEPs were: 1) a stronger corporate reputation (68%); 2) contributing to women's empowerment will also help the economy (73%); and 3) company’s female employees are motivated and more productive. In terms of achievement of expected benefits, three areas that emerge include a stronger corporate reputation, an increase in interested investors who have substantial confidence in the company; and an increase in loyal customers. At the same, representatives of the companies shared their concerns with the evaluation team that benefits for a company are not easy to measure and few companies have frameworks and tools to track progress in gender equality and women’s empowerment, although human resources seem to become tasked more and more on providing such data to the companies’ leadership and middle management. Nevertheless, the impact study of 2021, identified that the share of female employees in leadership roles (i.e., in the position of director and above) has increased by 40 per cent in the micro-sized companies and has almost tripled in the large-sized companies since joining WEPs.

In addition to integration of gender sensitive internal mechanisms and practices, the signatory companies that gained knowledge and guidance from the implementation of WEPs work have been encouraged to empower women through pro-bono activities, including training women outside of their companies, promoting and branding products produced by female entrepreneurs, providing services (mainly consultancy services) for free to women entrepreneurs, and providing external mentoring ( 13 % of companies out of 40) and coaching to women in the communities, among other types of activities. In 2018-2020, the indicative time spent by the respondent companies was 2,451 hours which is equal in value to between GEL 122,550 and GEL 208,335. Among unexpected results was the extent of commitment of private companies to implementation of WEPs. For example, as compared with 2,451 hours in 2018-2020, only in 2022 this number almost doubled and constituted 4,542 hours spent on gender equality mainstreaming activities. As well, in 2022, 41 companies supported 11,814 women within and outside their organizations. The same number in 2018-2020 was 7000.

From the meeting of the evlaution team  with the WEPs Council on March 24th 2023:

“Women’s economic empowerment is not a charity. It is important to understand that the Government should be asked and tasked to ensure equality, it is the Government’s job to do it. It is their responsibility to ensure balance”

“We cannot do anything without Government. The triangle that works and makes changes is: the Government, the Private Sector and NGOs”

“We need the Government not in terms of finances, but in terms of creating enabling environment”

From the meeting of the evlaution team  with the WEPs Council on March 24th 2023:

“Women’s economic empowerment is not a charity. It is important to understand that the Government should be asked and tasked to ensure equality, it is the Government’s job to do it. It is their responsibility to ensure balance”

“We cannot do anything without Government. The triangle that works and makes changes is: the Government, the Private Sector and NGOs”

“We need the Government not in terms of finances, but in terms of creating enabling environment”

Declaration of commitment of the WEPs companies to gender equality and SDGs is also supported by the evidence of increased allocation of funding to their activities under the WEPs framework. According to the same online survey conducted in 2021, 10 WEPs signatory companies fundraised more than US$900,000 for advancing the gender equality agenda from various international financial institutions, local banks and donors. In 2022, the total amount (GEL) spent on the WEPs work internally in the company since joining WEPs included 514,218 GEL in 2022 and on the WEPs work outside of your company (community organizations, grants for communities) 646,738 GEL in 2022.   Raising visibility of individual contribution of WEPs companies to SDGs and, especially, to empowerment of women at the grass root level was one of the issues raised by companies interviewed for this evaluation.  In this regard, future plans shared by Un Women and Taso Foundation of rebranding of the social mobilization component into Women’s Community Academy may providing opportunities to consolidating and tracking individual contributions and making then more visible for the companies and for the public.

One of the project key milestones was the establishment of the WEPs Advisory Council, with three permanent members and six members on a rotating basis elected from the active WEPs companies. The main goal of the Advisory Council is to articulate the needs of the private sector, offer expertise and connections, provide guidance, share new insights and advise on how to meaningfully engage companies in the WEPs community.  Seven thematic groups are supposed to discuss their sector-specific challenges regarding gender equality and women’s empowerment. The structure is quite innovative, however, during the meeting with the evaluation team the participants shared their satisfaction with ongoing work.  Their vision of the future of the WEPs Advisory Council would be not limiting the role of the Council in advocating GEWE issues in the private sector but extending the private sector influence on decision making at the Government regarding solution of common problems i.e., lack of maternity protection, labour security issues, gender stereotypes in relation to professions etc.

Finding 9: Achievement of the project results for rights holders – vulnerable women from rural areas reconfirmed comparative advantages of UN Women in this area of work such as effectiveness of social mobilization methodology and established strategic partnership and quality expertise provided by UN Women and the project partners to increase women’s opportunities to build sustainable business and increase income.

Tailored support was provided to women-entrepreneurs and women from SHGs including targeted trainings in business skills and financing, consultancies, visits to farms, raising awareness of innovative technologies in the field of their work, existing standards and other was provided by the project partners - Taso Foundation, GFA, BTU and WEPs companies. About 88% of women-entrepreneurs participated in various training activities, while it was 100% for the beneficiaries of Taso Foundation and GFA. In total, 101 women in rural areas were supported financially for economic activities, of which 36 women were supported to expand their businesses and 65 women received grants to start business activities.

In relation to achievement of the WEE component objectives, 78% companies (out of 95 surveyed by GFA) increased their income, 30% of them doubled their annual turnover. 67% of respondents increased the number of employees (not including family members) during the course of the project; 25% of them with more than 3 employees, 42% with only 1 employee, and only 10% of them mention seasonal increase of employees. It is noteworthy that 60% of respondents integrated business risk management strategies by diversifying their business (added additional services).

Figure 10. Impact on women- beneficiaries of Taso Foundation and GFA

|  | Total - 241 beneficiaries: 75 women participated in training of Enterprise Georgia 14 women participated in"how to start a business" training (BDO) 47 women applied for grants at Enterprise Georgia 7 women received grants from Enterprise Georgia |
| --- | --- |
|  | Total- 95 beneficiaries 85% of respondents' businesses are registered (baseline- 40%) 60% of respondents diversified their business during the project (added additional services) 67% of respondents increased the number of employees 78% of respondents noted an increase in income |

In addition to creating opportunities for women to increase their income and ensure employability, it is important that the partners motivated women to register their businesses (see Figure 10), thus, moving them out of the shadow economy. During the individual and group interviews, beneficiaries of GFA expressed their satisfaction with services they have received describing the support from GFA and other partners most timely and relevant. This allowed them to become more self-confident and independent (including financially) and set further goals to build a more sustainable business. It seems that greater economic empowerment has affected how women see their specific problems in relation to the local and regional development.  Many of them see the need to expand their knowledge of the local communities and the regions and their resources including the natural advantages. In their opinion, this work should be done by municipalities when developing economic suppot programmes, also for women-entrepreneurs, so that the regions can develop based on assessment of natural, human and other resources.

“I was 17 years old when I got married and had to fight for my education. It was my dream to get higher education in public administration, and I am currently studying. “

“I never thought of participating, but Taso (Foundation) gave me motivation to become a community worker, and now I have an (own) organization.”

From interviews with Taso Foundation beneficiaries

“I was 17 years old when I got married and had to fight for my education. It was my dream to get higher education in public administration, and I am currently studying. “

“I never thought of participating, but Taso (Foundation) gave me motivation to become a community worker, and now I have an (own) organization.”

From interviews with Taso Foundation beneficiaries

The social mobilization component that involved work with most vulnerable women in rural areas have again proved effectiveness of the methodology developed and implemented by Taso Foundation. Being the first step in women’s economic empowerment, social mobilization united 241 in 28 self-help groups (SHGs) in five regions of Georgia. As the results of the SWOT analysis conducted with 77 women suggest, the benefits of participation in SHGs are regarded by the participants beyond strictly economic opportunities provided by the project (see Annex 7). For many women, participation in the project was a life changing experience which boosted their self-confidence to make own decision including to relation to their economic independence, provided access to vital for economic empowerment knowledge, skills and information about opportunities.  As most relevant to the overall goal of the project, social mobilization empowered women to get involved more actively into decision making at local municipalities and community development activities and projects.

Despite the improved increase for women in access to the state grant programmes  implemented by the legal entity Enterprise Georgia, women who participated in interviews and SWOT workshops noted major barriers that prevent women from enjoying economic opportunities. These include, in addition to the lack of time, limited access to financial support and programmes, as well as poor basic economic and social infrastructure, which also affects outmigration of young people out of the villages and labour migration of women (for example, to Turkey). In this connection, the efforts of UN Women to encourage state and private financial institutions to adopt a gender lens for financial services designed specifically for women are commendable. In 2022 and 2023, Un Women in cooperation with the Georgian Stock Exchange organized two “Ring the Bell” events that hosted the representatives of IFIs on the panel. The focus of discussions was on integrating women’s specific needs into business models and customer value propositions.

Finding 10. The project ToC was sound; major assumptions and risks to overall project performance (crisis in the Government, post-COVID19 recovery) are well defined and risk strategies have been effective. The project rapidly reacted to the changing situation in the country which was affected by multiply crises during the project implementation. Needs based, tailored approaches in working with the Government and stakeholders from ministries and LELPs, as well as with private companies allowed UN Women to achieve more under this project than it was anticipated.

The reconstruction of the Theory of Change (ToC) during the inception phase confirmed the validity imbedded into the project theories related to women’s participation in decisions making and women’s economic empowerment. Although the project design missed on clear articulation of some critical assumptions related to sufficient capacities of right holders to claim for gender sensitive services at governance institutions and on the pivotal role of CSOs in building these capacities while holding duty bearers’ institutions accountable, these issues still have been considered during the implementation stage. For example, several interventions targeted raising capacities of CSOs in gender mainstreaming tools and building a constructive dialogue between CSOs and representatives of duty bearers at the local governance. Nevertheless, some risks to mainstreaming of gender equality tools and their sustainability at public administration institutions such as actual demand for relevant capacities of public servants i.e., competencies, performance indicators, etc. could have been better explored.

Overall, the project was effective in mitigating the risks related to the crises in the Government and the COVID19 pandemic and following recovery.  The project adapted its strategies and invested more time and efforts into building close relationship with institutions representing national gender equality machinery including new leadership in the Gender Equality Country and contributed to post COVID19 recovery measures of the Government with studies and assessments targeting increased participation of women in economy.  Development of Rapid Gender Assessments brought addition value to the national recovery strategies and increased recognition of UN Women being a valuable partner in the large spectrum of reforms. UN Women effectively grasped the opportunities related to fulfilment of the EU recommendations and provided targeted support to the Government in their implementation.   These and other strategies have been effective in the long run and allowed UN to achieve more than anticipated in relation to the set of quantitative targets. Some unexpected results, which in addition to ones described under Finding 8, include institutionalization and adoption of several critical for promotion of gender equality key documents. More than that, UN Women and the project partners noted the unexpected level of interest and motivation from public administration institutions to participate in capacity development provided by the project in relation to the Public Administration Reform for example in establishment of institutional sexual harassment mechanisms. The same observation was also made by the evaluation team during interviews with the respondents from the Government and public administration institutions.

Finding 11:  Monitoring systems at UN Women and partners allowed collecting rich information on activities and immediate products. At the same time, reporting on LNOB and lessons learned has been uneven among partners, which affected the quality of UN Women reports to the donor.

Monitoring of the project included quarterly and annual reporting based on the activity plans and indicators and targets for Outputs. Established at UN Women and at the partners, monitoring systems allowed collecting rich information on activities and immediate products and deliverables, though it would be important to capture higher level changes in capacities of both duty bearers and right holders, as well as evidence of use of increased by the project capacities. In this regard, the set of indicators for Good Governance could be better defined in terms of HR and GE meaning keeping balance between indicators for duty bearers and rights holders i.e., evidence of increased capacities of CSOs, right holders in claiming their rights etc.

While some partners, for example Taso foundation, collect disaggregated to maximum extent data that inform on vulnerabilities related to sex, age, family status, children in the family etc., reporting on LNOB in general remains an issue. Finally, the crosscutting role of SDG 17 was most evident in achievement of the results, however, due to the lack of a relevant indicator, achievements of the project in building partnerships to achieve SDGs in a number of areas have remained underreported.

Finding 12: The project made significant investment into building capacities of duty bearers at the national level and, to some extent, at the local level to mainstream gender equality into structures and tools. The capacities of CSOs have been increased to ensure monitoring and evaluation of international GEWE commitments and to provide capacity development in GIA and GRB. Building capacities at the partners involved into the WEE component targeted increased commitment of the individual companies to WEPs.

Overall, the project made significant contribution to achievement of the national SDG target 16.6.2.1 (Global target 16.6) “The capacity and professionalism of male and female public servants at local and national levels strengthened to better serve their constituency”.  Under the Good Governance component more than 1,300 public servants were reached by gender mainstreaming capacity development interventions designed by UN Women in cooperation with the project partners. Ninety -eight local government representatives were trained on gender mainstreaming in local governance, and 775 public servants were trained on sexual harassment. An additional 381 public servants were trained on GRB. Strengthened by the project capacities should promote implementation of the institutional gender equality strategies (developed by six entities during the project) and reinforce implementation of sexual harassment legislation in the public service (12 ministries and LELPs). Furthermore, enhanced capacities of duty bearers in GRB should ensure implementation of the relevant law and facilitate mainstreaming of gender into the public budget at the national and local level.  To support implementation of the institutionalized GIAs into all sectors and policies, 54 public servants were trained in Gender Impact Assessment (GIA). As most relevant to the project objectives of data informed decision making, 176 producers and users strengthened their capacities in the collection, analysis and use of gender statistics.

In this connection, it is important that also representatives of CSOs were trained in Gender Impact Assessment (GIA) and GRB, which creates opportunities for cooperation between the public administration and civil society on these issues, in particular at the local level.  While majority of beneficiaries highly evaluate both relevance and quality of capacity building interventions, key partners as Ministry of Finance, MoFA and NALAG, as well beneficiaries from gender focal points at local governance, pointed out at low basic capacities in programme planning and budgeting, which is likely to affect the extent of implementation of the gender responsible budgeting.

In addition to targeted trainings in future, as highlighted by the PDO representative in the interview, it would be important to create more opportunities for CSOs, also by allocating more investment, so that the latest support governance institutors in fulfilling women’s rights in alignment with the international obligations and call duty bearers’ institutions for accountability for gender equality mainstreaming and women’s economic empowerment. As the results of focus group interviews with gender focal points suggest, existence of strong regional and local CSOs and their involvement in GRB and strengthening of local Gender Equality Councils at legislative branch of the governance, is very appreciated by municipalities and may explain the differences in performance across 64 municipalities in gender equality mainstreaming. The need to enhance synergies between project interventions under the WEE and those under the Good Governance has become most evident during the SWOT workshops with representatives of SHG groups (see SWOT results in Annex 7). As Figure 11 presents, increased engagement of socially mobilized women and their grass root organizations in the local governance structures and decision-making process provides with additional capacity to improve gender sensitivity of local programmes and their budgeting.

Figure 11 Selected findings from real time surveys with GF points and women-leaders of SHGs

Under the WEE component, additional 632 representatives (842 altogether) from the WEPs companies increased their awareness of relevance of gender equality in their work. Enterprise Georgia employees and partner organizations were trained in the mechanisms and tools to ensure gender inclusiveness in the project implementation process. It deems important to mention here that 2022 was the first year when the percentage of women grant recipients in Enterprise Georgia increased to 50%, which may be also attributed to the quality of services provided to female applicants.

Capacity development activities have been delivered to over 50 policymakers and public servants.  In addition, Participatory Gender Audits (PGAs) have been conducted in three entities:  the Ministry of Education and Science of Georgia (MoES), the National Agency of Public Registry (NAPR) and the Georgian National Tourism Administration (GNTA). The above-mentioned Institutions examined their activities from a gender perspective and identified strengths and weaknesses in promoting gender equality. Following one of the PGA recommendations, NAPR benefited from UN Women's technical assistance to establish sexual harassment mechanism within the organization.

During interviews with the evaluation team, respondents from the public and private sector were able to identify some impact that gender mainstreaming already had on their institutions and services provision. For example, the Prosecutor’s Office commented on improved capacity to investigate gender - based crimes i.e., femicide, which was one of the recommendations from the CEDAW. The National Agency of Public Registry (NAPR), the key partner in improvement access to land for women, reported on their activities to increase the number of women- land surveyors, which was until now a male dominated profession.  Most relevant, promoting women to this profession was supported by training in digital tools that is aligned with the project targets related to women in technology and engineering.

## Efficiency

Main findings: Finding 13: The project presents a good value for money considering the scope of interventions and the numbers of deliverables and beneficiaries. Overachieving of targets suggests that there is a high demand for UN Women expertise and services, however, there are some concerns about availability of human resources at UN Women to ensure in future support to initiated large-scale reforms and upscaling of interventions. Finding 14: UN Women attracted high level expertise and resources available at the partners including individual WEPs companies. In addition, coordination with partners ensured that the project products and capacity development activities were of high relevance and timely delivered. Building strategic partnerships resulted in increase of cost-effectiveness of the project due to voluntarily contributions of WEPs companies and co-funding. Finding 15: The policy and governance work under the Good Governance component has directly targeted the root causes of vulnerabilities for women and groups of women. Allocation of resources prioritized the needs of most vulnerable girls and women, also due to increased engagement of WEPs companies in the social mobilization component and with women-entrepreneurs.

Full description of findings

Finding 13: The project presents a good value for money considering the scope of interventions and the numbers of deliverables and beneficiaries. Overachieving of targets suggests that there is a high demand for UN Women expertise and services, however, there are some concerns about availability of human resources at UN Women to ensure in future support to initiated large-scale reforms and upscaling of interventions.

The numbers of delivered products is impressive including studies, legislative and policy documents, manuals and learning tools. The same may be said about the numbers of beneficiaries that were reached with services and other interventions (for example in IT and other sectors). While achievement of quantitative targets for indicators is commendable, their overachievement may suggest that the need for UN Women expertise and services was higher than expected, which informs of high relevance of the project in terms of addressing the gaps that include lack of comprehensive and systematic approach to mainstreaming of gender equality tools and mechanisms in the governance sector e.g., GRB, GIA, sexual harassment and insufficient awareness of the private sector to how to integrate WEPs in practice.

While the latest informs of comparative advantages of UN Women, this also raises the question about availability of resources at UN Women, first of all human resources as acknowledged in the reports for the donor. Two components after merging contained the same allocation of human resources in each project, the decision that may be justified in terms of the scale of each project and to meet the increased demand from beneficiaries.  Nevertheless, overstretching of human resources has been noticeable for the evaluation team and partners, which raises concerns how UN Women will ensure in future support to initiated large-scale reforms for example during implementation phase of initiated reforms (PAR, GRB). At the same time, considering how many critical for GEWE national level documents (national strategies and NAPs) have been approved by the end of the project, sufficient resources are required for further advocacy and support during implementation of these project. Already in this project, UN Women had to allocate additional human resources at the national gender mainstreaming institutions such as GEC and PDO.

Finding 14: UN Women attracted high level expertise and resources available at the partners including individual WEPs companies. In addition, coordination with partners ensured that the project products and capacity development activities were of high relevance and timely delivered. Building strategic partnerships resulted in increase of cost-effectiveness of the project due to voluntarily contributions of WEPs companies and co-funding.

Quality and timewise, expertise and support of the UN Women project staff, their partners and attracted experts were highly praised by all participants of the project who participated in this evaluation. One of most frequently mentioned positive feedback was in relation of relevance of training and other activities to the needs of participants, the local context and good timing, which was very important for women who are involved into seasonal businesses.

Some partners shared also their own experience in upgrading their operations and services provision with the purpose of increasing both efficiency and effectiveness in their field.  For example, GFA started the process of digitalization which has been used in the project – e-commerce, online provision of information, locating of agrotourism beneficiaries on the maps and other. Learning from the exprience from the first phase of providing grants for women- entrepreneurs, GFA instroduced matching grants (10/90) and descreased their amont (to 10,000 GEL)) to ensure that women can successfully manage recieved funds.  One more example, Enterprise Georgia considers to optimize their operations in the situation of increase of applications from women to ensure effiency  and quality of feedback that would enable women to improve their applications in future. Building strategic partnership, in particular with IFis and the financial sector, has also contributed to the project efficiency (See Figure 12).

Figure 12. Co-funding of interventions under the WEE component

| Activities | Co-funding agency | Amount of contribution |
| --- | --- | --- |
| 1.Publication “Culinary journey with women- entrepreneurs” | Tera Bank | 5,000 USD |
| 2. Ring the Bell for Gender Equality event 2023 | IFC | 810 USD |
| 3. Social mobilization component (Taso Foundation) | Various private sector companies | 18,200 USD |
| 4. Campaign “Women who do not exist” | Bodyshop Toyota | 20,000 USD 5,000 USD |
| 5. 500 Women in Tech | BTU | 113,480 USD |
| 6. Women’s Entrepreneurship Expo | EBRD TBC Bank | 30,000 EUR 10, 000 USD |
| 7. WED Assessment | ILO | 19,600 USD |
| 8. ICT study | PwC | the half amount of market value – 38,000 USD |
| 9. DataFest | Regional Office Europe and Central Asia | 20,000 USD |

Finding 15: The policy and governance work under the Good Governance component has directly targeted the root causes of vulnerabilities for women and groups of women.  Allocation of resources prioritized the needs of most vulnerable girls and women, also due to increased engagement of WEPs companies in the social mobilization component and with women-entrepreneurs.

Figure 13. GG4GEG budget distribution

Figure 13. GG4GEG budget distribution

While in case of the Good Governance component, allocation of resources directly to LNOB groups have not been foreseen, the policy and governance work has directly targeted the root causes of vulnerabilities that all women and groups of women e.g., women and girls with disabilities face to be able to benefits from equal opportunities and inclusive economic growth. Allocation of resources to capacity development of duty bearers’ institutions considered their involvement with most vulnerable women, for example the regional outreach implemented by PDO in communities populated by ethnic minorities (Azeri, Armenian) and IDPs. The same consideration applies to integration of victim-orientated internal investigation of sexual harassment cases at public administration institutions and private companies or, as in the case of Prosecutor’s Office, effective investigation of crimes committed on grounds of gender intolerance.

Another good example would be the Civil Service Bureau domestic violence policy that stipulates obligations of the Bureau management for protection of employed persons from domestic violence both at the place of employment and beyond.

Investments into production of disaggregated data and integration of gender analysis into policies and public budgeting is going to contribute, in a long term, to their effectiveness and cost-effectiveness which is one more argument for efficiency of the project in terms of expected benefits for vulnerable groups.

Almost a quarter (24%) of the budget was used to address the needs of right holders from most vulnerable groups under the WEE components (Output 2.3, see Figure 13). In addition, the social mobilization component attracted financing from WEPs companies (18,200 USD). Co-funded activities addressed important for women’s economic empowerment areas such as participation of girls and women in STEM and undertaking professions in the technology sector.

## Sustainability

Main findings: Finding 16: The project has been effective in generation of the national ownerships of the project results. Adoption of high-level policy documents and NAPs that integrate gender analysis creates an enabling environment for dissemination of gender mainstreaming tools further. Finding 17: Sustainability at the private sector companies was pursued through a variety of approaches and strategies. Support to creation of action plans for gender equality targeted integration of WEPs into the corporate strategic directions. This work was complemented by revision of project partners’ gender equality strategies and action plans. Finding 18: Developed by the project capacity is likely to sustain in majority of institutions; there is sufficient evidence at partners’ institutions of having intentions to utilize developed capacities to promote gender equality in their work. Nevertheless, sufficiency of implementation capacities to mainstream gender equality into broad scale reforms such as PAR and public programmes budgeting has been questioned by partners and stakeholders. Finding 19: The evaluation identified several factors that are likely to affect negatively capacities of national and local level governance institutions such as commitment to integrate gender equality into the initiated reforms, lack of human resources and problems of their retention (affecting institutional memory and consistency in implementation), insufficient financial resources and unclear accountability mechanisms.

Full description of findings

Finding 16: The project has been effective in generation of the national ownerships of the project results. Adoption of high-level policy documents and NAPs that integrate gender analysis creates an enabling environment for dissemination of gender mainstreaming tools further.

Sustainability has been ensured through institutionalization of gender mainstreaming tools at the national level and through implementation of gender equality strategies in target agencies, i.e., GEOSTAT, Prosecutor’s Office, and others. Adoption of high-level policy documents and NAPs that integrate gender analysis creates an enabling environment for dissemination of gender mainstreaming tools.

High level participatory monitoring mechanisms, like the one established for TIGE ,  should ensure commitment and coherence of stakeholders’ actions and donors’ interventions.  Implementation of the state Concept of Women’s Economic Empowerment (developed in 2023) should allow to consolidate results and upscale them for both components and ensure that gender analysis, disaggregated data, gender- sensitive public budgeting will be mainstreamed on a larger scale into the economic sector.

As mentioned previously, selection of strategic partners and key stakeholders has largely affected all aspects of the project including its sustainability. The position of each of the partners in relation to sustainability of the results has been considered during the stakeholder’s analysis ensuring opportunities for further dissemination and upscale. For example, involvement of the key partner in the local governance component (NALAG) into networking and experience exchange under the European Charter for Equality of Women and Men in Local Life has resulted in 14 municipalities having acceded to the Charter , which creates assurance that implementation of gender equality strategies in these municipalities is going to be taken to the next level.

The awareness of gender has increased, and, in every activity, we always start to consider the gender aspect.

From the interview with “Enterprise Georgia”

The awareness of gender has increased, and, in every activity, we always start to consider the gender aspect.

From the interview with “Enterprise Georgia”

Sustainability of the project deliverables has been promoted through institutionalization of gender mainstreaming tools, such as GIA, GRB and development of guidelines and manuals e.g.  Gender Mainstreaming Toolkit for the Government of Georgia, the manual on gender equality mainstreaming at the local governance and other. There is evidence of UN Women planning to use these tools, for example, for the commitments under Generation Equality Forum by integrating into the TIGE plan tasks to carry out GIAs for laws and policies from the relevant fields.  Still, further support from UN Women and other partners would be needed to ensure that these tools and related capacities are appropriately and effectively utilized. Overall, implementation of the Concept on the Gender Equality and the chapter on gender equality in the National Human Right Plan should add to sustainability of developed by the project capacities.

Finding 17: Sustainability at the private sector companies was pursued through a variety of approaches and strategies. Support to creation of action plans for gender equality targeted integration of WEPs into the corporate strategic directions. This work was complemented by revision of project partners’ gender equality strategies and action plans.

Sustainability of mainstreaming of WEPs at the private companies has been pursued through development of action plans with a major emphasis on outlying activities directed to increase business performance and gain competitive advantages through gender-responsive business practices, This task was done was done with the support of the Georgian Chamber of Commerce and Industry (GCCI) and  two main directions include: (1) integration of the WEPs into the companies’ corporate policies and culture i.e.  HR policy documents, (2) pro-bono activities to promote women’s economic empowerment outside the companies. It is noteworthy that the project partners continued implementation of their action plans developed after gender gaps assessments (GGA) under the first phase of the WEE component. For example, addition two additional scoring points for women - entrepreneurs at Enterprise Georgia allowed for increasing numbers of applications. Also, GITA, the main national agency in promotion of innovations and technology Women have increased quota for women in the ICT Training for Georgian Citizens programme. Moreover, women’s startups will get additional 2 points in state grants programme for innovation managed by GITA, which should give competitive advantage to women’s startups to get funding and all support envisioned under the programme.

Still, further support from UN Women and other partners would be needed to ensure that gender, tools and related capacities are appropriately and effectively utilized.  The intentions of UN Women to integrate commitments under TIGE into the National Human Rights Action Plan are most notable and relevant to be pursued under the next project phase. This and similar activities should enhance synergies between Good Governance and WEE and increase national ownership over capacities developed with the support of the project.

Finding 18: Developed by the project capacity is likely to sustain in majority of institutions; there is sufficient evidence at partners’ institutions of having intentions to utilize developed capacities to promote gender equality in their work.  Nevertheless, sufficiency of implementation capacities to mainstream gender equality into broad scale reforms such as PAR and public programmes budgeting has been questioned by partners and stakeholders.

Revision of institutional gender equality strategies in ministries and LELPs and other structures that have been shared with the evaluation team i.e., GEOSTAT, Prosecutor’s Office, Ministry of Finance and other etc. suggests that developed capacities is likely to sustain in stakeholders’ institutions. As most relevant to the sustainability of interventions in the public administration, Civil Service Bureau, its gender equality action plan for 2022-2024 outlines activities to integrate evidence and collection of data to strengthen gender equality in public service, to create work environment free of discrimination and to promote equal opportunities for women and men in public service; and to strengthen family-friendly employment policy in public service. Adoption of the Public Finance Management Reform Strategy 2023-2026 that foresees integrate gender aspects by embedding the system of gender tags in the budget management system will enable the Ministry of Finance to promote gender responsive budgeting into all state funded programmes.

Some concerns remain in relation of availability of sustainable finances to pursue gender equality mainstreaming. For example, implementation of institutional gender equality plans still rely on external funding from donors and IFIs.  In addition, human capacity to ensure dissemination of knowledge and skills in some institutions may be not sufficient, for example 3 trainers in MoFA may be not enough to address the needs of public intuitions when mainstreaming GRB.  The same may be said also about capacities to support gender mainstreaming into the Public Administration Reform.

It has been acknowledged in UN Women and other reports, meeting undertaken obligations and recommendations (EU membership) seems to be a defining factor that affected adoption of several important for Human Rights and GEWE promotion documents including the Concept on Gender Equality in 2022-beginning of 2023.  Implementation of these documents was a challenge in the past, according to the CEDAW Committee and other monitoring instruments. As shared by several participants of this evaluation, building evidence of benefits from implementation of these framework documents for sustainable development of the country and to share interim progress and results of gender equality mainstreaming in the targeted policy areas would help advocacy efforts to increase national ownership of the gender equality agenda.

Finding 19: The evaluation identified several factors that are likely to affect negatively capacities of national and local level governance institutions such as commitment to integrate gender equality into the initiated reforms, lack of human resources and problems of their retention (affecting institutional memory and consistency in implementation), insufficient financial resources and unclear accountability mechanisms.

As it was shared by representatives of public institutions, lack of human resources and problems with their retention affects gender mainstreaming capacities. Changes in leadership due to national elections may put on hold or reverse the progress towards GEWE, as it was observed during the timeline of the project. High level commitment to integration of the reforms remains the defining factor for Georgia. Changes in staff result in reduced capacity and loss of institutional memory.

In addition, accountability mechanisms in some cases are not clear, for example in the situation of gender equality plans at local governance institutions. While the work of PDO and the GEC at the Parliament in this regard is commendable e.g., to studies and outreach to local governance institutions, the current mechanisms to provide oversight and feedback are not sufficient to help local governance institutions with identification of gaps and strategic directions. According to the PDO representative, ongoing policy dialogue on revising existing gender mainstreaming structures in order to strengthen the position of Gender Focal Points and GECs at the legislative branch, provides opportunities to increase ownership and capacities at local governance institutions to integrate gender equality mainstreaming tools.

Capacity of the National Human Rights Instrument (PDO) has been largely enhanced with UN Women support which is evident in numbers of studies and beneficiaries who received services through the regional outreach. Nevertheless, there are concerns whether a change in leadership might affect structural changes and, in particular, existence of Gender Equality Department, and retention of the regional staff.

The importance of involvement of high-level management (CEO etc.) in the project interventions on raising awareness on WEPs have been shared by the representatives of the private sector. The WEPs and gender equality still is not one of the main strategic priorities for businesses. Despite of events organized under the project such as a workshop for CEOs from the WEPs signatory companies  and video shooting with CEOs about the WEPs (with support of GCCI), focal gender points at the private companies interviewed in the scope of this evaluation think that there is often lack of understanding by CEOs of benefits of mainstreaming of gender equality for the company and, consequently, lack of interest and motivation to provide leadership in this area.

## Partnerships for GEWE and SDGs

Main findings: Finding 20: The project was effective largely due to success of partnerships established by UN Women with the key Government agencies, public institutions, private companies and civil society organizations. By building partnerships around the results, the project also emphasized the need for a holistic and coherent approach to mainstreaming gender equality across sectors and thematic areas. Finding 21: UN Women built partnerships with consideration of interests/stakes of stakeholders in the thematic areas of the project and their comparative advantages. The position of the partners in relation to decisions making and/or implementation of key reforms that were the target of gender mainstreaming interventions of the project creates confidence in sustainability of partnerships.

Full description of findings

Finding 20: The project was effective largely due to success of partnerships established by UN Women with the key Government agencies, public institutions, private companies and civil society organizations. By building partnerships around the results, the project also emphasized the need for a holistic and coherent approach to mainstreaming gender equality across sectors and thematic areas.

The project has been effective in terms of achievement and overachievement of target largely due to success of partnerships established by UN Women with public institutions, private companies and civil society organizations and other entities and agencies (UN, IFIs, development agencies). Mainstreaming of SDG 17 (Target 17.17)  has been consistently applied as a crosscutting principle across all areas of results with good evidence of bringing up also financial benefits resulting from these partnerships. Support provided by UN Women to building capacity at the GEOSTAT and other data producers and users made direct contribution to 17. 18  which is instrumental to GEWE mainstreaming in all policy areas.

Key partnerships were built around thematic areas such as integration of sexual harassment prevention mechanism, building capacities of public administration, integration of GRB into state programmes budgeting and other. At the same time, the project also emphasized the need for systemic approach by integrating gender equality mainstreaming tools in the public, private in non-governmental sectors. It deems important to mention that all partners went through the PGA process and elaborated their gender equality action plans. Majority of partners established sexual harassment prevention mechanisms. Moreover, desk review of the partners’ gender equality strategies or action plans revealed that most of them are collecting or planning to collect data disaggregated by sex. The latest has utmost important in the situation of scarcity or discrepancy of data some areas at the GEOSTAT i.e., women’s ownership of enterprises. In this way, partners act a role model to their beneficiaries – public and private institutions.

Finding 21: UN Women built partnerships with consideration of interests/stakes of stakeholders in the thematic areas of the project and their comparative advantages. The position of the partners in relation to decisions making and/or implementation of key reforms that were the target of gender mainstreaming interventions of the project creates confidence in sustainability of partnerships.

As mentioned previously, selection of partners for the project reflected current mechanisms and patterns of decision making and specific interests or stakes that each partner had in relation to solution of challenges addressed by the project.  In addition, building partnerships considered comparative advantages of each partner to ensure not only integration of gender equality and women’s economic empowerment mechanisms in their areas of work, but also opportunities to promote dissemination and upscale. For example, regional outreach that some partners have (i.e., NALAG, GFA, GCCI) or planning to improve it (i.e., Enterprise Georgia) provides such opportunities and, most important, seeks to transfer knowledge and expertise to vulnerable regions and groups of women. While it would be not possible for this report to list all initiatives implemented by the project partners and beneficiaries, some innovative practices stand out due to their criticality to addressing roots causes of gender inequality. For example, to increase land registration by women, who also constitute the largest groups of migrants, NARP, with support from IFIs, initiated integration of best global practices such as use of AI, blockchain to improve access of women to land registration, and encouraged them to buy land.

Furthermore, many of the partners have extensive networking at the national, regional or global level that they may use as a leverage to establish new partnerships for beneficiaries of the project and increase access for women and girls to finances. For example, participation of NALAG in EU gender equality framework projects has already resulted in development of partnerships at the local governance level and increase in gender-sensitivity of institutions, which was recognized through the competition held by NALAG in 2022.

Finally, UN Women effectively used existing platforms and formats to enhance partnerships and ensure coherence among stakeholders such as participation in the working groups under the GEC of the Parliament, Women Economic Empowerment Working Group and other. Cooperation with IFIs received a boost during the project by establishment of a new working group with them, which contributed to both effectiveness and efficiency of the project.

Creation of the WEPs Advisory Council and thematic working groups extended opportunities for building sustainable partnerships with the private sector.  Rebranding of the social mobilization component as a Women’s Community Academy may raise visibility of effective cooperation between state institutions, private sector, non-governmental and, lately, with IFIs to increase access to finance for women entrepreneurs and women-owned. For example, representative of WEPs companies shared in the interviews with evaluation consultants that it is important for private companies to have recognition of individual input of each company to keep their high motivation to commit to WEPs.

## Innovativeness

Main findings: Finding 22: The project was catalytic in piloting new methodologies and promotion of innovative gender equality mainstreaming tools into polices and institutions. Integration of these tools and methodologies is under way and will require further support from UN Women during the next phase of the project. Finding 23: Visibility and dissemination of innovative methodologies and platforms was supported by communication strategies employed by UN Women which were of a good variety and reached out significant numbers of people in Georgia. Opportunities for broader dissemination and their integration in the partners’ institutions were well explored and captured in the sustainability plans of the latest.

Full description of findings

Finding 22: The project was catalytic in piloting new methodologies and promotion of innovative gender equality mainstreaming tools into polices and institutions. Integration of these tools and methodologies is under way and will require further support from UN Women during the next phase of the project.

Under the Good Governance component, to raise capacities of governance institutions and national level decision makers and data producers, the project supported piloting of new methodologies that have not been implemented in Georgia before. For example, first in country and the region user satisfaction assessment was conducted by GEOSTAT focusing on gender data products. The assessment identified high demand on gender disaggregated data and informed developed of the National Gender Statistics Strategy. Similar, Time Use Survey was conducted first time in Georgia and as the first full scale survey in the region. Piloting these methodologies has resulted not only in the increase of evidence and data to inform decision making, but gave a boost to building national statistical capacities of data producers and users.   Gender Responsive Public Financial Management (GRPFM) assessment, conducted for the first time in Georgia, is the key product of the project to promote GRB and, on a large scale, improve financing for SDGs, in particular for gender related targets (SDG 5 and other).

Under the WEE component, development of “Diversity, Equity and Inclusion (DEI)” manual and the certification programme for human resources on DEI implemented in partnership with HRPA stands out as the first attempt to introduce issues of diversity and inclusion in the country. The DEI allows for broader interventions in terms of addressing different target groups of women and other i.e., disabilities, ethnic minorities, etc. In the situation of scarcity of qualified human resources in Georgia, integrating issues of diversity and inclusion is critical both for the public and private sectors.

The “500 Women in Tech” project is a UN Women flagship private-public partnership with BTU and with the involvement of the private sector companies that involves free training for 500 women across the country in popular professions of the information and communications technology sector, after which the project offers them an internship and employment. The relevance of this important initiative for the existing gender imbalance in technology was acknowledged at the high-level event “Joint Efforts to Empower Women in Technology”, which took place online on 7 March 2023 within the framework of the 67th session of the Commission on the Status of Women. It is noteworthy that the initiative has been is shortlisted for Emerging Europe Award as the best Future- Proof Education.

Overall, the project was effective in creation of more enabling environment for mainstreaming gender equality and women’s economic empowerment tools and promotion mechanisms at the national level. Nevertheless, while basic capacities and partnerships to promote integration of innovate gender equality tools have been built, the further support from UN Women to their meaningful and effective implementation will be required. Not least important, according to the respondents of the interviews, is to achieve broader recognition of benefits resulting from these initiatives and acknowledgement of impact that gender sensitivity of systems and institutions may have on achievement of national priorities.

Finding 23: Visibility and dissemination of innovative products and tools was supported by communication strategies employed by UN Women and partners which were of a good variety and reached out significant numbers of people in Georgia.

UN Women and partners used a variety of media and communication channels to raise visibility of the innovative products and work done by the project. For example, results from the Time Use Survey were disseminated through public presentations, publications, briefs and Facebook cards capturing the key findings. The survey generated substantial public attention and was covered by 45 media outlets (national and regional) within the first four days since its launch.

To increase participation of women in ICT (500 Women in Tech), UN Women launched a communication campaign to remind the population of Georgia of gender stereotypes in the division of professions into "women's" and "men's" job and to raise attention to the importance of having a free choice of profession for women, as well as men. The campaign reached almost 1.8 people and collected 672,901 unique views.

A “Ring the Bell for Gender Equality” event that stock exchanges around the world host to raise awareness of the pivotal role the private sector has led to establishment of the UN Women- IFIs working group that  focused on promotion of financial products and services tailored for women. It is noteworthy that the project received support from some private companies -Toyota, Bodyshop, Tera Bank who provided co-funding for communication campaigns.

UN Women partners from the public institutions and non-governmental organizations also used their own resources and communication channels to share information about innovative products and methodologies. As shared by some partners e.g., BTU, HRPA, increase of interest in new initiatives and products was most evident in the numbers of received application. At the same time, some partners acknowledged the lack of communication specialists with skills in delivering gender- sensitive communication, e.g., NAPR, and stressed importance of having UN Women’s support in this area.

# Conclusions

Conclusion 1. The project implementation supported the country in meeting human rights and gender equality international commitments by strengthening gender equality mainstreaming through relevant legislation and systematic application of gender equality mechanisms and tools at the institutional level. Informed by the human rights analysis that was evident in baseline and assessment studies produced by the project, interventions of UN and partners directly addressed the root causes of gender inequalities such as access to land and financial resources, stereotypes and perceptions entrenched in the systems, gender blind policies and institutions and lack of gender-disaggregated statistics.

Conclusion 2. The project was implemented in coherence with UN Women global and national strategic documents and international commitments undertaken by the Government of Georgia. At the same time, through participation in high level working groups and thematic groups at UNCT, UN Women ensured complementarity, harmonization and co-ordination with others actors in the fields without duplication of effort. The project was instrumental in achievement of UN Women Georgia Strategic Note and the country portfolio. The added value of the project was addressing gender sensitivity of systems and institutions in a holistic way. In the regard, policy documents, guidelines and procedures that were developed and approved by the Government and other stakeholders ensured institutionalization of gender equality mainstreaming tools such as Gender Impact Assessment, Gender Responsive Budgeting that should broaden impact on gender sensitivity of systems and institutions and create enabling environment for pursuing objectives of interventions of UN Women and other UN agencies.

Conclusion 3. The efforts of the project to address lack of gender disaggregated data are most commendable. The project commissioned 11 studies that provided evidence for decision making in several areas and, in particular, on the situation with human rights and gender equality for women and girls with disabilities, access of women to ICT and entrepreneurship, unequal distribution of domestic and care between men and women and other. By broad dissemination of findings from these studies and building capacities of data users, especially of duty bearers from the Government and public administration institutions, the project contributed to achievement of the UNSDCF objective of improved policy development and decision making that is based on   evidence and gender disaggregated data.

Conclusion 4: UN Women Georgia leveraged effectively the comparative advantages such as ownership of gender equality and women’s economic empowerment tools (PGA, GIA, GRB, WEPs) and unique expertise in mainstreaming of these and other tools into policies, action plans and institutions. By building strategic partnerships with the national gender equality machinery and duty bearers’ institutions, UN Women used effectively   national structures and decision-making process to promote adoption of several important for GEWE legislative acts, strategic documents and action plans.

Conclusion 5: The project design targeted gender mainstreaming across a broad scope of reforms, such as decentralization, public administration reform, judiciary reform, economic diversification (entrepreneurship), tourism (agritourism), infrastructure, vocational education and training (work-based training), SME development including high tech, ICT industry, trade (value chain) and other. The project effectiveness and efficiency have been achieved largely due established partnerships with key duty bearers’ institutions, associations, NGOs/CSOs and the private sector. Despite the success in achievement and even overachievement of targets, implementation of the project at such a large scale informed UN Women of having its resources overstretched and pointed at the need to prioritize the work during the next stage of the project.

Conclusion 6. The project contributed to increased commitment of the private sectors to WEPs. Cooperation with the private WEPs companies and consolidation of interventions under the WEPs framework received the boost by establishment of the WEPs Advisory Council – a new structure comprised of active WEPs-signees. While benefits from using this platform for promoting WEPs into other companies and sectors are to be seen, active members of this new structure have motivation and ambitions to extend its work and engage in advocacy together with civil society to influence decision making at the Government that should accelerate achievement of gender equality and women’s economic empowerment.

Conclusion 7:  Significant investments into building capacities of duty bearers at the national level and at the local level should ensure mainstreaming of tools and mechanisms in the areas targeted by the project. While the project increased capacities of CSOs to ensure monitoring and evaluation of international GEWE commitments and to provide capacity development in GIA and GRB, use of these capacities was not sufficient to increase cooperation between CSOs and governance institutions at the local level and enhance accountability of the latest for implementation of the national GEWE commitments.

Conclusion 8: The project was effective in generation of national ownership of the project results. The project exit strategies ensured integration of products and tools developed by the project at partners’ institutions. In addition, adoption of high-level policy documents and NAPs that integrate gender analysis creates an enabling environment for further dissemination of gender mainstreaming tools. However, implementation capacities to mainstream gender equality into broad scale reforms such as PAR and public programmes budgeting may be not sufficient to ensure that gender tools and related capacities are appropriately and effectively utilized.

Conclusion 9: The project effectively leveraged strategic partnerships with key Government agencies, public institutions, associations, private companies and civil society organizations to increase its effectiveness and promote sustainability of the achievements. UN Women effectively used existing platforms and formats to enhance partnerships and ensure coherence among stakeholders’ interventions. Engagement with WEPs companies and IFIs increased efficiency and cost -effectiveness of the project. At the same time, lack of recognition by the Government of contribution of partners, especially from WEPs companies, to achievement of the GEWE targets and SDGs may create an impediment to keeping high motivation of partners from the private sector and their commitment to WEPs.

Conclusion 10: The project gave a boost to development and integration of innovative gender equality mainstreaming tools, methodologies and platforms e.g., “500 Women in Tech”. Raising visibility of these innovation have been actively pursued by elaborate communication strategies employed by UN Women and partners.  Ownership of these tools and methodologies has been established, and the project ensured their broader dissemination and upscale by their integration into relevant national framework documents. Nevertheless, additional support (human resources, financing) is likely to be required to ensure meaningful integration and usage of some tools and methodologies e.g., GIA, GRB etc.

# Lessons learned

This section present lessons learned that were formulated by UN Women and the project partners during the project implementation and, in addition, the ones that were identified by the evaluation team jointly with participants of interviews and validation workshops. Mainly, the lesson learned point out at the criticality of systematic integration of gender mainstreaming tools at the policy and institutional level and relevant capacity building; the need for high level support and leadership in GEWE; and for building effective cooperation with civil society and women-leaders at grass root level to promote local gender mainstreaming.  The key lessons learned include the following:

Lesson learned 1: Implementation of the GG4GEG project has proved that possession of GEWE tools, mechanisms, platforms and expertise how to use them enables UN Women to achieve impact regardless of the thematic area. However, systematic integration of these tools in some broad-scale reforms, such as public administration and public financing reforms, and monitoring of impact of integration are likely to accelerate achievement of several GEWE and SDG targets.

Lesson learned 2: High level support and leadership involving ministers and/or their deputies, heads of municipalities, high level management, CEOs is needed at the public institutions, local governance and private sector to ensure that developed capacities are used and integrated into daily activities and performance reporting; therefore, raising awareness of high level leadership on benefits stemming gender equality mainstreaming in their areas and designing for them relevant capacity development is critical for meaningful integration of gender equality tools and mechanisms.

Lesson learned 3: In municipalities and villages where strong cooperation between self-governance and women’s CSOs and self-help groups has been established, results from mainstreaming of gender equality are more evident for beneficiaries.  CSOs and mobilized women who have knowledge of gender mainstreaming tools, such as GRB, GIA, needs assessment, bring additional capacities that contribute to effective implementation of gender equality interventions at local governance.

Lesson learned 4: In addition to insufficient local budgets, low status and diversity of parallel positions of Gender Advisers at the municipalities (different workloads etc.) are other limiting factors that may affect the extent of local gender mainstreaming.

Lesson learned 5:  The WEPs and gender equality are still not the main strategic priority for businesses; it is hard for them to allocate much time or human capital for implementing the WEPs. Therefore, it is important for UN Women and the project partners who have good experiences working with companies to devote sufficient time to get them fully on board and apply needs based and tailored approaches considering the character of a business mind, models of doing business and communication channels.

# Recommendations

The evaluation team developed six major recommendations that are supported by more specific action points for how to operationalize each recommendation. The recommendations were developed in consultations with the project partners and stakeholders and representatives of beneficiaries who had opportunities to provide with their opinion and feedback during the data collection process and the validation workshops. The recommendations are based on the findings from this evaluation and make references to the corresponding conclusions and lessons learned. The majority of recommendations are addressed to UN Women and project partners with some recommendations addressed to Gender Equality Council at the Parliament of Georgia.

| Reference | Recommendation | Target | Priority |
| --- | --- | --- | --- |
| Mainstreaming GEWE into national policies and strengthening gender mainstreaming structures |  |  |  |
| Lesson learned 1 Conclusion 2 Conclusion 4 | - Continue with mainstreaming of GEWE into existing broad-scale reforms such as Public Administration Reform, systemic land registration process, also lawmaking around agrotourism and agriculture i.e., farmers’ status to accelerate achievement of all GEWE targets and SDG 5 | UN Women, GEC | High |
| Conclusion 8 | - Continue building national capacities to ensure effective utilization of gender equality mainstreaming tools such as GIA, GRB, prevention of sexual harassment and to use gender disaggregated data for decision making | UN Women (lead) CSOs HRPA | High |
| Conclusion 3 | - Continue building the evidence base of benefits of integration of gender equality mainstreaming tools in the public and the private sector such as sexual harassments prevention mechanisms, GRB, GIA etc. | UN Women (lead) PDO, GEOSTAT and other partners with relevance to the topic | High |
| Conclusion 3 | - Disseminate further the results of the Time Use Survey and advocate for amendments in relevant legislation and institutional practices to accelerate achievement for women work and life balance | GEC/ UN Women (lead) WEPs companies | Medium |
| Lesson learned 4 | - Use opportunities of participating in the ongoing dialogue on the status of gender advisors and Gender Equality Councils to strengthen capacities of these structures to promote GEWE | GEC/UN Women (lead) | High |
| Mainstreaming GEWE at the local governance level |  |  |  |
| Conclusion 7 Lesson learned 3 | - Increase involvement of CSOs and women from SHGs, through the grant schemes and targeted funding, in promoting of gender mainstreaming tools and capacities to use these tools at the local governance level; | UN Women, NALAG | High |
| Conclusion 7 | - integrate into the grant schemes for CSOs activities to develop capacity of duty bearers at the local governance level in GIA, GRB and use of gender disaggregated data for policy planning; | TASO Foundation WIC Other CSOs trained under the project in GIA, GRB | High |
| Finding 9 | - To enable women at the grassroot level to address the barriers to their economic empowerment, provide them with communication and advocacy skills to influence decision making at local governance | Taso Foundation | High |
| Lesson learned 4 | - Increase accountability of local governance for implementation of gender equality plans by involving local CSOs into their monitoring | NALAG (lead) UN Women Municipal GECs | High |
| Enhancing Partnerships for GEWE and SDGs |  |  |  |
| Conclusions 6 and 9 | - Expand further successful cooperation with stakeholders representing different sectors and IFIs | UN Women and other UN agencies | High |
| Lesson learned 2 | - Enhance participation of high-level management, CEOs, heads of municipalities in UN Women and partners’ advocacy and capacity building activities | UN Women (lead) | Medium |
| Conclusion 9 | - Continue liaison with IFIs, UN agencies and other actors/ donors to ensure sustainability of support for women -entrepreneurs and to upgrade their businesses | GFA, BDO and UN Women (lead) | High |
| Conclusion 6 | - Use the WEPs Council as a platform to expand public-private partnerships and dialogue and engage WEPs Council /thematic groups and CSOs to work together and provide input in relation to desirable changes in sectoral strategies and relevant legislation and inform where GIA would be most relevant. | UN Women (lead) GEC WEPs Advisory Council Thematic groups | High |
| Conclusion 6 | - Support joint advocacy initiatives of WEPs companies and CSOs with relevant duty-bearers (national and local governments) to address the challenges that prevent women from equal participation in the economy such as lack of childcare facilities, social care infrastructure, in particular in rural areas, etc. | UN Women (lead) WEPs Advisory Council | High |
| Lesson learned 5 Conclusion 9 | - Continue advocating for recognition of the private sector’s contribution to gender equality and women’s economic empowerment and SDGs i.e., awarding additional points in procurement processes, through allocation of targeted grants etc. | UN Women WEPs Council (lead) GCCI (co-lead) Enterprise Georgia | High |
| Finding 20, Conclusion 9 | - During the stakeholder analysis, consider mapping of stakeholders and partners around the project results (Outputs and Targets) indicating towards which nationalized and/or global SDG targets these partnerships will be contributing (e.g., SDGs 5.4) | UN Women | Medium |
| Finding 20, Conclusion 9 | - Increase visibility of partnerships for GEWE and SDGs in online reporting and communication campaigns by adding hashtags next to information on partners/ partnerships under the project e.g., #SDG 5.4 | UN Women | Medium |
| Strengthening RBM and reporting of results on LNOB |  |  |  |
| Finding 10 | - Strengthen RBM capacity of UN Women project staff and partners and promote consistency of partners’ reporting towards the project results and indicators including on informing on the progress in achievement of HR and GEWE | UN Women | High |
| Finding 10 | - Provide a training for the project team (and partners) in RBM and Theory of Change and in mainstreaming of HR and GE into the project design and implementation | Un Women | High |
| Finding 10 | - Developing simple reporting templates for each of indicators and providing guidelines for reporting on LNOB e.g., disaggregation of data. | UN Women (lead) Taso Foundation FAO | High |
| Finding 10 | - Revise ToC (annually) and make the revision of make ToC a participatory exercise, for example as a part of Steering Committee meeting or partners’ extended meeting, and involve in that exercise key partners and stakeholders to reviews results (indicators) and validate/ revise the assumptions. | UN Women (lead) Partners in Steering Committee | Medium |
| Efficient use of human resources at UN Women |  |  |  |
| Conclusion 5 | - To avoid overstretching of human resources of UN Women, keep a manageable scale of interventions during the next phase of the Good Governance project | UN Women | High |
| Conclusion 5 | - Prioritize interventions to pilot new tools e.g., GIA, GRB in order to demonstrate their relevance and effectiveness in the areas targeted by the project (e.g., PAR, agrotourism and agriculture, unpaid work) | UN Women | High |
| Conclusion 5 | - Integrate in the design use of capacities developed during this project such as of ToTs in GRB and GIA, CSOs in monitoring of international HR and GE obligations etc. | UN Women | High |
| Sustainability and dissemination of innovations |  |  |  |
| Conclusion 10 | - Emphasize under the next phase maximum use of results from application of innovative methodologies, products and initiatives | UN Women (lead) Partners | High |
| Conclusion 10 | - Continue integration of innovative methodologies into relevant strategies and action plans at the national policy level | UN Women (lead) GITA | High |
| Conclusion 10 | - Integrate innovative products and concepts and models developed under both components of the project through (1) own interventions and (2) at partners’ institutions, for example through gender equality strategies and action plans | UN Women (lead) BTU | High |

# Annexes

## Annex 1 Reconstructed ToC

Critical assumptions:

A1 (Output 1.2  Output 1.3): there is actual demand for capacities at governance institutions e.g., integrated into daily activities, job description (competencies), performance assessment etc.

A2 (Output 1.3  Output 2.2):  data is sufficiently disaggregated to inform on sector specific problems for target groups of women

A3 (Outputs 2.3  Output 2.2):  there is a constructive dialogue between policy makers and the private companies on solution of challenges to GE and WEE

A4: (Outputs 2.3 + Output 2.2  Output 2.1): women have access to sustainable financing and support

A5 (Output 1.1 Outcome 1):  there is effective high-level oversight (GEC, PDO etc.) and independent monitoring conducted by CSOs

A6 (Output 2.3.  Outcome 2):  barriers to women's economic participation are addressed e.g., unpaid work, stereotypes, access to land

A7 (Outcome 1  Outcome 2): rural women actively claim for their rights at the governance institutions

A8 (Outcome 1  Outcome 2): local governance institutions have capacities to implement sustainable gender equality measures

A9 (Outcome 1 Impact): political will and commitment to sustainability of reforms and international obligations

Critical assumptions:

A1 (Output 1.2  Output 1.3): there is actual demand for capacities at governance institutions e.g., integrated into daily activities, job description (competencies), performance assessment etc.

A2 (Output 1.3  Output 2.2):  data is sufficiently disaggregated to inform on sector specific problems for target groups of women

A3 (Outputs 2.3  Output 2.2):  there is a constructive dialogue between policy makers and the private companies on solution of challenges to GE and WEE

A4: (Outputs 2.3 + Output 2.2  Output 2.1): women have access to sustainable financing and support

A5 (Output 1.1 Outcome 1):  there is effective high-level oversight (GEC, PDO etc.) and independent monitoring conducted by CSOs

A6 (Output 2.3.  Outcome 2):  barriers to women's economic participation are addressed e.g., unpaid work, stereotypes, access to land

A7 (Outcome 1  Outcome 2): rural women actively claim for their rights at the governance institutions

A8 (Outcome 1  Outcome 2): local governance institutions have capacities to implement sustainable gender equality measures

A9 (Outcome 1 Impact): political will and commitment to sustainability of reforms and international obligations

## Annex 2 Evaluation Matrix

| Relevant evaluation criteria | Key Questions | Specific Sub- Questions | Data collection methods and sources of information/data | Indicators / Standards | Methods for Data Analysis |
| --- | --- | --- | --- | --- | --- |
| Relevance: Extent to which the objectives of a development intervention are consistent with beneficiaries’ requirements, country needs, global priorities and partners’ and donors’ policies. | A) How does the project reflect and align with gender equality national strategic plans and normative frameworks as well as Georgia’s international obligations and commitments? B) Is the project design based on quality analysis, including gender and human rights-based analysis, risk assessments, socio-cultural and political analysis? C) Were the programmatic strategies appropriate to address the identified needs of beneficiaries? | A.1) Has the theory of change of the project and results framework of the intervention integrated HR & GE? B.1) To what extent does the project design integrate the LNOB principle and target achievement of SDGs for the most marginalized women and girls? | A) Desk review: legal and policy documents, report to CEDAW; UN Women AWP, ProDoc, project reports; Interviews: with Gender Advisors at UN Women and partners’ organizations; project management and project partners in particular in position to accelerate gender mainstreaming in national legislation and policies, and the national reform agenda, such as B) Desk review: baseline studies, RGA, Gender Profile Georgia, CCA etc. Interviews: partners; selected WEPs companies (private sector) ToC validation workshop: project staff and key partners C) Focus group discussions: beneficiaries of the project representing right holders (members the SHGs, women-owners of business) and duty bearers (representatives of municipalities, CSOs as secondary duty bearers; | A) extent of alignment between the project design and national strategies, policies; N of targets (SDGs, UN Woman Global Plan) incorporated into project design A.1) extent of alignment of the design with HR &GE plans and the country’s internationally undertaken obligations B) evidence of use of baseline studies, another research in the project; % of project beneficiaries (right holders from vulnerable groups) B.1) evidence of use disaggregated data in project (partners, UN Women): evidence of integration of disability issues C) extent of satisfaction of beneficiaries with the project results; N of beneficiaries (by group) | - Qualitative (coding in NVIVO i.e., legal and policy planning documents; project documents; interviews’ data -Quantitative (frequencies, cross-tabulations etc.) |
| Coherence: The compatibility of the intervention with other interventions in a country, sector or institution. | A) To what extent the project adheres to corporate strategic priorities of UN Women and the UN Women CO Strategic Note? B) Is the project achieving synergies between the larger UN Women’s portfolios and the work of the UN Country Team? C) Is the project achieving synergies between UN Women and key national stakeholders including national governments and CSOs? D) How does the project design match with the complexity of national structures, systems and decision-making processes? | A.1) To what extent was UN Women able to use current comparative advantages in the areas of GG and WEE as compared with other UN entities and key partners in Georgia? C.1) To what extent was the project implementation well- coordinated to ensure synergies and avoid duplications? | A-A.1) Desk review: project documents, UN Women SN, AWPs; interviews with CO Head and Deputy Head; B-C) Desk review: notes of UNSDCF GTG; UNCT annual reports Interviews: UN Resident Coordinator, selected UN agencies D) Desk review: Stakeholders’ analysis Interviews: key partners in the Government | A) extent of alignment with UN Women SN and Global Plan A.1) use of UN Women comparative advantages; UN Women-led forums, platforms, partnerships B) evidence of synergies with other UN Women projects; evidence of synergies with other projects of UN agencies ; evidence of synergies with other actors -WB, USAID/ N of joint actions including co-funding C) evidence of complementarity between actions of stakeholders; strategies to avoid duplication C.1) established mechanisms for project coordination D) participation of UN Women in national GEWE mainstreaming mechanisms ; quality of selection of stakeholders | Qualitative: analysis of documents and interviews against predefined criteria (coding in NVIVO) Quantitative: descriptive statistics |
| Effectiveness: Extent to which the development intervention’s objectives were achieved, or are expected to be achieved, taking into account their relative importance. Effectiveness assesses the outcome level, intended as an uptake or result of an output. | A) What has been the progress made towards achievement of the expected outcomes and expected results? What are the results achieved? B) What are the reasons for the achievement or non-achievement of the project results? C) Does the project have effective monitoring mechanisms in place to measure progress towards results? D) What is the influence of the specific country context and circumstances on the achievement of results and operational effectiveness? E) How adaptable and rapidly does the project react to changing situations? F) Has the project achieved any unforeseen results, either positive or negative? For whom? G) What are the good practices how the obstacles or shortcomings encountered? How were they overcome? What strategies were used to mitigate risks to the project effectiveness, arising also from the pandemic, environmental issues/climate change, violence against women and girls, other? H) To what extent have capacities of relevant duty-bearers and rights-holders been strengthened? | A.1) To what extent has the project contributed to nationalized SDG targets and improved the situation for most marginalized women and girls B.1) Was the ToC of the project sound? Were the assumptions/risks formulated in the project ToC valid and sufficient? C.1) Was monitoring data collected and disaggregated according to relevant criteria (sex, age, ethnicity, location, income etc.) in accordance to HR and GEWE principles? | A-A.1, B, D, F) Desk review of project annual reports to the donors, quarterly reports in the system, project databases; plans and reports of the project partners, beneficiaries’ databases Interviews and focus groups discussions with the project beneficiaries and partners from public and private sectors: representatives of CSOs, right holders- beneficiaries of the project (women and girls in rural areas) B- B.1) Validation workshop on the reconstructed ToC with the project staff and key partners; C-C.1): Desk review RRF, project reports, beneficiaries’ databases; G), H) Focus group discussion/SWOT workshops/ real time survey: rural women- beneficiaries of the project and representatives of local administration Desk review: publications including on social media, video materials, success stories etc. | A) achievement of targets; perceptions of results by target groups A.1) extent of satisfaction of beneficiaries from most vulnerable groups with the project results B) perception of factors affecting the project by target groups and beneficiaries B.1) quality of lessons learned C) evidence of monitoring against targets; quality of indicators (set) C1) evidence of use disaggregated data in project (partners, UN Women) D) evidence of ongoing risk analysis done by UN Women /context analysis and decision making and /or adaptability E) evidence of flexibility of strategies F) perceptions of results by target groups G) evidence of risk management strategies H) evidence of strengthened capacities of duty bearers; evidence of strengthened capacities rights- holders; relevance of capacity building to the needs of duty-bearers and rights- holders | Quantitative: analysis of databases of partners), results of surveys (descriptive statistics, frequencies, crosstabulation) Qualitative: analysis of documents and interviews against predefined criteria (coding in NVIVO) |
| Efficiency: Measure of how economically resources/inputs (funds, expertise, time, etc.) are converted to results. It is most commonly applied to the input-output link in the causal chain of an intervention. | A) Have resources (financial, human, technical support, etc.) been allocated strategically to achieve the project outcomes? B) Have the outputs been delivered in a timely manner? C) To what extent were relevant stakeholders and actors included in the project planning and implementation? D)To what extent did the allocation of resources prioritize the need of most vulnerable women and girls? | A.1) How did the project ensure that deliverables were of high quality and were relevant to the needs of various targets groups and beneficiaries? | A- A.1) Desk review of budget records, interim/ status/ annual reports, partners’ and experts’ contribution, financial reports, etc.); Interviews with partners and beneficiaries (users of the project deliverables i.e., studies, guidelines, GIA, PGA, capacity development, etc.) B) Desk review: progress reports (quarterly), reports to the donor C) Interviews: the project team and partners D) Desk review: Allocation of budget per deliverables, beneficiaries’ databases (access to grants, support etc.) | A) % of expenditure on project management/coordination/technical expertise/capacity building; quality of attracted expertise A.1) evidence of satisfaction of users of products B) actual versus planned expenditure by project output; actual delivery versus planned timeline of delivery of outputs C) participation of stakeholders in the Steering Committee and other coordination structures ; evidence of cost -efficiency due partnerships (use of human resources capacity, expertise and resources, coordination, etc.), monetary value in relation to the project budget D) % of resources allocation to prioritize most vulnerable | Quantitative (budget calculation, descriptive statistics) Qualitative analysis of documents and interviews against predefined criteria (coding in NVIVO) |
| Sustainability: Continuation of benefits from a development intervention after major development assistance has been completed. The probability of continued long-term benefits | A) To what extent has the project identified strategic partners that could pick up on supporting continued government, private sector and non-governmental action when the project comes to an end? B) How effectively has the project been able to contribute to the generation of national ownership of the project outputs? C) What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time after the project phase out? D)To what extent have the project’s exit strategy been well planned and successful? E) To what extent has UN Women been able to promote replication of project successes? | E1) What kind of scale-up strategies were used? | A) Desk review: project documents, stakeholders ‘analysis, partners’ sustainability plans (if any) Interviews: project management partners, key stakeholders from the Government, CSOs, private sector; B-C) Desk review: surveys of beneficiaries of projects, minutes of working groups established during the project; Interviews and focus group discussions/SWOT workshops/ real time survey: project management, public administration institutions, local governance, WEPs enterprises; CSOs and women-beneficiaries of the project D, E.-E.1) Desk review: project annual and quarterly reports, budget allocation for communication, advocacy, dissemination of products, knowledge management/ SN AWPs Interviews: project team, communication specialists (UN Women and partners) | A) quality of selection of stakeholders B) willingness and capacity of project partners to integrate project interventions/services into their own programs; C) evidence of favourable changes in enabling environment i.e., laws/policy planning; evidence of strengthened capacities rights- holders from target groups to continue benefiting from the project interventions and results; evidence of strengthened capacities of duty bearers to promote GG /WEE D) evidence of targeted dissemination, advocacy, replication of results and products E) evidence of replication of results and products E.1) allocation of the project budget/ use of partners’ resources to disseminate information/ use of regional, global platforms | Quantitative (allocation of budget to sustain actions) Qualitative (of documents and interviews against predefined criteria (coding in NVIVO) |
| Partnerships to achieve GEWE and SDGs | A) To what extent has UN Women been able to promote private and public partnerships to achieve GEWE and SDGs? B) What is the likelihood that these partnerships are going to be sustainable to continue of the project results and successes? C) What strategies were used by UN Women to strengthen leadership, commitment and technical capacity of institutions from various sectors to contribute to achievement of GEWE targets and SDGs? |  | Desk review: project reports, communication materials, Face to face and online interviews: with stakeholders from all sectors involved into the project and UN Women staff | A) No of public-private partnerships established during the project (in case of WEE -new partnerships) B) No of working groups, advisory councils, platforms and other formats established to sustain partnerships; evidence of sustainability of partnerships/mechanisms established such as MoU and similar agreements C) documentation of effective strategies/ lessons learned | Qualitative (of documents and interviews against predefined criteria (coding in NVIVO) |
| Innovativeness | A) What -if any- types of innovative good practices have been introduced in the project for the achievement of GG and WEE results? | A.1) To what extent were the project management and partners able to ensure sustainability of these innovative good practices and their broader dissemination i.e., nationally, regionally, globally? How was it done? | Desk review of project reports; -interviews with project management, project partners | A) evidence of recording/documenting innovative good practices; evidence of initiatives to promote innovative approaches A.1) evidence of communication/dissemination of innovative good practices | Qualitative (Analysis of project documentation, communication materials, publications, social media) |

## Annex 3 Stakeholders’ analysis

| Stakeholders | Category | Purpose of involvement in evaluation | Priority | Stage of the evaluation to engage them | Capacities in which stakeholders participate |
| --- | --- | --- | --- | --- | --- |
| Outcome 1 |  |  |  |  |  |
| National institutional mechanisms to promote gender equality i.e., Gender Equality Council of the Parliament, Inter-Agency Commission on Gender Equality, Violence against Women and Domestic Violence Issues | Duty bearers with the authority to make decision related to the intervention | Consult: evidence of impact of project on gender- sensitive of legislation and policy making | High (Due to influence on new legislation as well as oversight on implementation | Data collection and analysis Report preparation | Informant / member of Steering Committee |
| Structures in Government -oversight over HR and GEWE (Human Rights Secretariat, Advisor to the Prime Minister of Georgia on human rights issues) | Duty bearers with the authority to make decision related to the intervention | Consult: evidence of impact of project on gender- sensitive of legislation and policy making | High (Due to influence on new legislation as well as oversight on implementation | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| National Association of Local Authorities of Georgia (NALAG) | Duty bearers with the authority to make decision related to the intervention | Consults on local governance issues /Collaborate (Incorporate advice and concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (Due influence on sustainability of gender mainstreaming at a local level) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| Civil Service Bureau (CSB) | Duty bearers with the authority to make decision related to the intervention | Collaborate (Incorporate advice and concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (due influence on sustainability of gender mainstreaming through Public Administration Reform ) | Data collection and analysis Report preparation | Informant |
| Governmental structures adopting internal sexual harassment complaint mechanisms (MRDI, MEPA, LEPL Sakpatenti , the Prosecutor’s Office, Civil Service Bureau (CSB), Ministry of Education and Science (MoES), Office of Resource Officers of Educational Institutions under MoES) and/or conducting PGAs (Prosecutor’s Office, NAPR) | Duty bearers with the authority to make decision related to the intervention | Collaborate (Incorporate advice and concerns to the greatest degree possible) | Medium to high (influence on sustainability of mechanisms for the protection of women under Labour Code in the public sphere and gender mainstreaming in public sphere) | Data collection and analysis Report preparation | Informant |
| Ministry of Finance of Georgia (MoF) | Duty bearers with the authority to make decision related to the intervention | Consult on gender-responsive budgeting, integrate their feedback | High (influence on budgeting processes, mainstreaming of gender into budgeting) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| Local governance (64 units) | Beneficiaries/ Duty bearers with the authority to make decision related to the intervention | Collaborate (Incorporate advice and concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (due to influence on sustainability of gender mainstreaming at the local governance level) | Data collection and analysis Report preparation | Informant |
| CSOs | Secondary duty bearers with responsibility to ensure independent monitoring of GEWE commitments /beneficiaries | Consult (Incorporate advice and concerns to the greatest degree possible) | High (due to their role in the national gender equality mechanisms) | Data collection and analysis Report preparation | Informant |
| Ilia State University’s Gender Research Center | Secondary duty bearers involved into interventions | Consult, integrate their feedback | Medium ( have certain influence on gender mainstreaming from scholarly gender research perspective) | Data collection and analysis | Contributor to country’s first gender profiling |
| Outcome 2 |  |  |  |  |  |
| Parliament of Georgia (Agrarian Committee) | Duty bearers with the authority to make decision related to the intervention | Consult: context analysis, economic impact | High (due to influence on new legislation to promote the economic participation of rural women) | Data collection and analysis Report preparation | Informant |
| Gender Equality Council of the Parliament | Duty bearers with the authority to make decision related to the intervention | Collaborate (Incorporate advice and concerns to the greatest degree possible) | Medium to high (influence on sustainability of gender mainstreaming in legislation and policy processes ) | Data collection and analysis Report preparation | Informant |
| Georgian Chamber of Commerce and Industry (GCCI), | Duty bearers who have direct responsibility for intervention | Collaborate (incorporate advice and concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (due influence on sustainability of support to WEPs companies and dissemination of best practices) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| Enterprise Georgia | Duty bearer with direct responsibility for intervention | Collaborate (incorporate advice and concerns to the greatest degree possible) | High (decision-maker in terms of supporting gender economic empowerment) | Data collection and analysis Report preparation | Informant |
| Ministry of Education and Science (MoES) | Duty bearers who have direct responsibility for intervention | Collaborate (incorporate advice and concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (due influence on sustainability of gender mainstreaming) | Data collection and analysis Report preparation | Informant |
| Georgian National Tourism Administration (GNTA) | Duty bearer with direct responsibility for intervention | Consult (incorporate advice and concerns to the greatest degree possible) | High (decision-maker and implementer of gender sensitive policies and actions, influencer in contributing and sustaining women empowerment actions) | Data collection and analysis Report preparation | Informant |
| TASO Foundation (NGO) | Secondary duty bearers who have direct responsibility for intervention at the grass root level | Collaborate (incorporate advice and concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (influence on dissemination of social mobilization of women) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| Georgian Farmers’ Association (GFA) | Secondary duty bearers who have direct responsibility for intervention | Collaborate (incorporate advice, concerns) | High (influence on sustainability of support to women involved in agro-business, women in rural areas) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| The WEPs Advisory Council /thematic working groups | Secondary duty bearers who have direct responsibility for intervention | Collaborate (incorporate advice and concerns to the greatest degree possible) | High (Influencer/decision maker on effective implementation of WEPs) | Data collection and analysis Report preparation | Informant |
| WEPs companies sample includes TBC, Liberty Bank, Tegeta Motoros, Tera Bank, Geostqb, PwC (medium), GAU (medium), GPI (large), Crystal (medium) | Secondary duty bearers from private sector (WEPs companies) with direct responsibility for intervention | Collaborate and consult (incorporate advice and concerns to the greatest degree possible, incorporate feedback) | High (Influencers in creating preconditions for women engagement and economic empowerment) | Data collection and analysis Report preparation | Informant |
| Human Resources Professionals Association in Georgia (HRPA) | Duty bearers who have direct responsibility for intervention | Collaborate (incorporate advice and concerns to the greatest degree possible) | Medium (Contributor to women skill building and empowerment) | Data collection and analysis Report preparation | Informant |
| CRRC Georgia | Secondary duty bearers who have direct responsibility for intervention | Consult, context analysis, incorporate advise | Medium (analysis, women skill building and empowerment) | Data collection and analysis Report preparation | Informant |
| NARP | Secondary duty bearer | Consult (incorporate advice and concerns to the greatest degree possible) | Medium | Data collection and analysis Report preparation | Informant |
| BDO | Secondary duty bearer with direct responsibility for intervention | Consult (incorporate advice and concerns to the greatest degree possible) | Medium (Contributor to women skill building and empowerment) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| Representatives of women-led enterprises | Secondary duty bearers involved into interventions | Collaborate to the greatest degree Provide opportunities for meaningful involvement Provide feedback, how their input was incorporated | High (evidence on results/relevance and sustainability of WEPs action plans) | Data collection and analysis Report preparation | Informant |
| Georgia Innovations and Technology Agency (GITA) | Duty bearer with direct responsibility for intervention | Collaborate (incorporate advice and concerns to the greatest degree possible) | High (decision-maker, play a role in supporting women’s economic opportunities) | Data collection and analysis Report preparation | Informant |
| Business and Technology University (BTU) and ICT representatives | Secondary duty bearers directly involved into intervention | Consult, integrate their feedback | Medium (accountability &empowerment women, education and training) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| Self-help groups (SHGs) 29 new SHGs uniting 329 women | Right holders, beneficiaries of the project | Collaborate to the greatest degree Provide opportunities for meaningful involvement Provide feedback, how their input was incorporated | High (evidence on relevance and promotion of HR&GEWE, sustainability of women’s mobilization | Data collection and analysis Report preparation | Informant; partner, support to data collection |
| Outcome 1 and 2 |  |  |  |  |  |
| Public Defender’s Office | National Human Rights Instrument; Secondary bearers with the authority to make decision related to the intervention | Collaborate (incorporate advice and concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (influence on sustainability of some milestones i.e. sexual harassment prevention mechanism, online courses) | Data collection and analysis Report preparation | Informant /member of Steering Committee Informant ; support in data collection |
| GEOSTAT | Partner/ beneficiary Duty bearers with the authority to make decision related to the intervention | Collaborate (incorporate advice and concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (responsible for SDG targets monitoring, provider of data for informed decision-making) | Data collection and analysis | Informant /member of Steering Committee |
| Ministry of Finance Training Academy (MoFA) | Secondary duty bearers directly involved into intervention | Consult, integrate their feedback | Medium (empowerment of women, education and training) | Data collection and analysis Report preparation | Informant |
| Ministry of Economy and Sustainable Development (MoESD) and its Legal Persons of Public Law (LEPLs) | Duty bearers with the authority to make decision related to the intervention | Consult, integrate their feedback | Medium (sustainability of initiatives) | Data collection and analysis Report preparation | Informant |
| UNDP, ILO, FAO UNFPA/ members of UN Gender Equality Group | UN system | Consult, integrate their input in the evaluation report | Medium to High (coordinate, ensure synergies) | Data collection and analysis Report preparation | Informant |
| EU, USAID | International organizations/donors | Consult, integrate their input in the evaluation report | Medium to high | Data collection and analysis | Informant |

## Annex 4 Data collection instruments

#### 4.1. Interview protocol with the Project Management Team, UN Women Director and Deputy Director

Context

- Can you describe the significance of this project and its place in relation to formerly and currently implemented projects in the areas of good governance and WEE; UN Women Strategic Note; UNSDCF?

- What would be your overall opinion of the external environment in which the project was implemented (political, economic, and cultural)? In what way was it favourable for the project and in what way not?

Relevance

- What was done to ensure that the project outputs are /remain relevant to the needs to stakeholders and beneficiaries, national policy and international commitments i.e., Istanbul Convention, CEDAW?

- What mechanisms were put in place to monitor the relevance?

Coherence

- How did UN Women's use its comparative advantages under this project vis a vis of other partners?

- What was done to ensure the synergy with other projects and programmes that target gender equality and women’s economic empowerment of women (other UN Women projects, other UN agencies, etc.)? How did it work? How does this project fit into implementation of the Outcome 1 and Outcome 3 under UNSDCF?

Effectiveness

- How would you define the main achievements of the project, in relation to achieving greater gender equality in Georgia? What were unexpected achievements?

- What factors contributed to achievement or non-achievement (if it was the case) of the project results? What were the risks that you did not anticipate and what strategies were used to mitigate risks to the project effectiveness? Were they effective?

- How were the issues of equity and disability addressed by the project?

- What monitoring tools were used to observe the project performance (including at the partner’s institutions), achievement of the results, test the assumptions and diagnose the risks?

Efficiency

- What measures did you take during planning and implementation to ensure that resources are used most efficiently?

- Were the main milestones achieved on time? If not, what were the reasons for delay and what effect had it on other milestones/components of the project?

- To what extent, if any, did addition of the second component (Outcome 2- WEE) have impact on project efficiency and cost-efficiency?

Sustainability

- What has been done to ensure that result of the project (products/services/capacity) will be used after the project completion? Please comment by Outcome and Output.

- What may affect the sustainability of the benefits produced by the project? Please comment by Output?

- What upscale strategies were used to promote a wider impact on beneficiaries and promotion of Good Governance/WEE on the national level?

- Has participation in this project affected in any way the level of cooperation between partners and stakeholders? If Yes, what has changed? What contributed to that, in your opinion? What do you think of sustainability of some (which) partnerships?

Innovativeness

- What innovative ideas, approaches and methods have been introduced in the project for the achievement of Good Governance/WEE results? How can they be disseminated or have they been disseminated as good practices to promote empowerment of women? What platforms, forums, or UN Women global resources and networks have been used (if any) to ensure broader dissemination of innovation? Do you think joining ODA by Georgia in 2021 may have a positive effect on integration of innovative practices on the national level and/or regional level? What may be of the role of UN Women in that?

#### 4.2. SWOT Analysis Tool for Self-help groups (SHGs)

Objectives         To assess the strengths and weaknesses of women’s mobilization in local SHGs and complement this with an analysis of opportunities and constraints in the context of Georgia (participation of women in decision making at the local governance level/ development of economic opportunities for women at the regional/ national level)

.

Participants 		Women- representatives of SHGs, community workers, women who were employed by other women, women who started their own business through the support of the project, women participating in local Gender Advisory Councils (GACs)

Method A framework of four elements guides the systematisation such as: Strength – Weakness – Opportunities – Constraints.

Material 	Flipcharts, markers (preferably two distinct colours), SWOT guidelines (in handout)

Procedure:  Step 1 will be done through focus group discussions facilitated by national consultants and local community workers with small groups of women. Participants analyse the strengths and weaknesses of women’s engagement. The following questions will be asked to the participants to reflect upon:

- What do you think about participation of women in SHGs? What are the advantages/ strengths of women’s mobilization that you can see or feel? Any weaknesses?

- What can you say about cooperation of the SHGs with local self-governments? What goes well and what may be improved? Do you see any changes in how women present their needs and advocate them at the local self-government? In relation to women’s economic empowerment, do you see any changes during the last two year? Do you see more support a) from the local government, b) private companies to provide women with more opportunities to start business or get involved into economic activities? If yes, why do you think it is happening?

- Did you notice any change of attitudes in the communities towards SHGs and mobilization of women? Is there a difference in attitudes in case women participate in economic activities or they mobilize to influence decision making at the local governance?

Then participants will identify contextual opportunities and constraints.

- Do you think that women can do more to influence decision making and promote economic development in the communities? What opportunities do you see for women involved in SHGs to increase their participation in local governance/ having more influence on development of local plans including gender equality plans? What can women do to promote economic participation of women in their communities? What do women need to be able to use these opportunities – knowledge, skills, resources, organization, changes in legislation etc.?

- What do you see as barriers to mobilization of women at the community level and their more active participation in local governance, social and economic activities in their communities?

Table 1: The performance of SHGs

| Strong points | Weak points | ##### Opportunities | Constraints/ Barriers |
| --- | --- | --- | --- |

Step 2 will involve discussion of the results of SWOT among community workers. They will be invited to validate the results of discussion using a real time survey tool during the focus group discussion in Zoom. Prior to that the evaluation team will analyse the results of SWOT and turn them into a set of statements with which participants will be invited to agree or disagree and provide argument for or against and include recommendations how mobilization of women (SHGs) and their capacities may be strengthened to be able to influence decisions making at the local governance, which will also have positive effect on WEE.

#### 4.3. Interviews with local governance representatives and gender advisors at the municipalities

Relevance

- How useful was for you participation in the project activities?

- In what way did the project assist your institution in implementation of your assigned responsibilities, the national reform agenda, national plans and ongoing local projects or programmes related to gender equality and women’s economic empowerment?

- Were you able to share your needs, concerns and recommendation with anyone in the project? With who? Was your opinion considered?

Effectiveness

- What do you see as the main results of this project for your institutions? for your municipality and community in general?

- How can you evaluate the capacity building provided to you by UN Women, NALAG and other partners? Were able to notice changes in the capacity of your institution, your staff, something that goes better/easier/ better satisfaction with your services?

- In case if you implement projects also with other UN entities in the same area of work (gender equality, GRB) , how do you see the advantages of being supported by UN Women?

- What did not go or is not going that well? Which factors, in your opinion affected/affect  that (political, social, economic, cultural or other)?

Efficiency

- How would you evaluate the quality of expertise (trainings, guidelines etc.) provided by the project?

Sustainability

- Would be able to continue working independently on the gender equality agenda (Gender Equality Plans, Gender-Responsive Budgeting) without external support? If Yes, which activities will you for sure continue after the project is closed?

- For which activities would you still need additional support and capacity development? What kind of support is needed, from whom?

#### 4.4. Interview protocols with project partners

For the evaluation team: please adapt the questions in relation to specific Outputs

- National Gender Equality Machinery, PDO

Relevance

- To what extent did this project help the country move forwards with the national agenda (strategies and plans) related to human rights and gender equality and meet undertaken international commitments such to CEDAW and others? What about nationalized SDG targets?

- In what way did the project answer the needs of your organization, such as related to your position and capacity development in order to fulfil your mandate to promote GEWE?

Coherence

- How did this project complement/ was coherent to other projects (and other actors) in the areas of GE and/or WEE that your organization was part of?

Effectiveness

- How would you define the main results/achievements of the project (in your area of work, your responsibilities)?

- What went very well and what did not go that well? Which factors, in your opinion, affected the extent of achievement of results (internal – project strategies, cooperation between partners; external- political, social, economic, cultural or other?

- Were there any unintended/ unexpected results? What happened?

Efficiency

- Were there any delays that affected activities and achievement of the results in the area of your work?

- How would you evaluate the management and coordination in this project?

- Are you satisfied with the level of expertise provided by the project?

Sustainability

- How would you evaluate the current state of gender sensitivity of legislation, policies and governance systems?

- Which results of the project are most likely to have a sustainable effect on decision making processes and implementation mechanisms as more gender sensitive and with HR and Women’s Empowerment in mind?

- Which areas of work under this project require addition support to ensure their sustainability?

Partnerships for GEWE and SDGs

- Has participation in this project affected in any way the level of cooperation between partners and stakeholders from different sectors (public, private, CSOs, academia)? If Yes, what has changed? What do you think of sustainability of some (which) partnerships?

Innovativeness

- Did the project promote any kind of innovative practices in the area of your work? How can they be disseminated or have they been disseminated (also with your support) as good practices to promote Good Governance and WEE?

- Non- governmental and associations, academic institutions:  TASO Foundation, GFA, NALAG, etc.

Relevance

- To what extent did this project make relevance to the mandate and goals of your organization, and your daily activities?

- How do you see the place of the component/project activities (in which your participated) in a broader picture of achieving good governance for gender equality/ women’s economic empowerment in Georgia?

Effectiveness

- What do you see as the main results of this project for your institutions? for your beneficiaries? for communities where you work?

- Were you able to notice any changes in the capacity of your institution and/or your beneficiaries? What are these changes?

- Were there any unintended/unexpected results that you would like to talk about? What happened?

- What did not go or is not going that well in the component of your work? Which factors, in your opinion affected/affect that (political, social, economic, cultural or other)?

- How did you monitor activities and results of your component of work? Did you do assessment of risks and other factors that may affect the results that your organization was working for under this project? Did you have to change strategies or approaches, why and how?

Efficiency

- How would you evaluate the management and coordination among partners under this project?

- Was the project, in your opinion, cost- efficient, provided good value for money? If Yes or NO, please elaborate why you believe that, what evidence you have.

Sustainability

- What do you think about sustainability of the project results (as you define them)? Which activities or benefits will be sustainable without additional/external support after the project phase out?

- Which activities will you for sure continue on your own? For which activities would you still need additional support and capacity development? What kind of support is needed, from whom?

Partnerships for GEWE and SDGs

- Has participation in this project affected in any way the level of your cooperation with partners and/or stakeholders from different sectors (public, private, CSOs, academia)? If Yes, what has changed? What do you think of sustainability of some (which) partnerships?

For BTU (Business and Technology University), please add a question on 500 Women in Tech:

4.1. To what extent was the project effective in promoting participation of women in technology studies and employment of this sector?

10.1. What do you think of the sustainability of the Women in Tech component and how such initiatives may be expanded to achieve a broad impact ion girls and women, especially in rural areas?

- Ministries and LEPLs, GEOSTAT

Relevance

1.In what way did the project support your institution in implementation of your mandate, your plans and national reforms that affect your institution?

Effectiveness

2. What do you see as the main benefits from this project for your organization? for the sector you are in? for promoting achievement of the national reform agenda, nationalized SDG targets?

3. How has gender mainstreaming processes supported by the project affected your capacity, your processes and daily routine so far? What has changed?

4. What did not go or does not go that well under the project? Which factors, in your opinion affected/affect that (political, social, economic, cultural or other)? What could have been done better or differently?

Efficiency

5.How would you evaluate the quality of expertise (trainings, consultancy, etc.) provided to you?

6.Are you satisfied with the way how products/benefits (studies, guidelines, training tools) developed under this project were made visible and disseminated? Please, elaborate.

Sustainability

7.Which activities or benefits will be sustainable without additional/external support after the project phase out? Which activities will you for sure continue on your own?

8.For which activities would you still need additional support and capacity development? What kind of support is needed, from whom?

Partnerships for GEWE and SDGs

9. Has participation in this project affected in any way the level of your cooperation with partners and/or stakeholders from different sectors (public, private, CSOs, academia)? If Yes, what has changed? What do you think of sustainability of some (which) partnerships?

#### 4.5. Interviews with WEPs companies

Contextual questions: When did you join the WEPs network?

In case the company joined recently (after 2021) - What was your motivation to participate in the project as a beneficiary – to integrate WEPs in your organization?

In case the company continued cooperation with UN Women under this project – what was your involvement with the UN Women in 2021-2022 under the WEE component?

Effectiveness

- Do you see any benefits/positive changes in your organization since you started integration of the WEPs?

- What kind of initiatives that promote GEWE have you launched as a part of the WEPs? What kind of results have you seen so far?

- Did you face any difficulties (or still face) with integration of a particular gender-equality policy /WEP principle? What would you have done differently if you had to start again?

- Do the current oil and prices crises, instability in the regions affect in any way motivation of the companies to invest into the women’s empowerment?

Sustainability

- Do you think that companies will continue implementing their action plans on integration of WEPs after the project is over? Which activities will you for sure continue doing (like mentoring, coaching, providing free training for women -led businesses, women who seek employment or other)?

- How would you evaluate communication done by the project staff from UN Women to get companies on board/ secure their participation?

- What do you think should be done to attract more private businesses to integrate WEPs? Who should be involved into the process from government, business associations, international organizations and other?

Partnerships for GEWE and SDGs

- What do you think of the institutional structures, such as WEPs Advisory Council and thematic working groups developed under the project?

- What do you see as benefits of these structures for promoting GEWE? Any drawbacks, challenges? What may be improved in future?

- To what extent was the project able to promote new, public and private partnerships? Are you a part of such a partnership? Please tell about that. What do you think about sustainability of these partnerships after the project phases out?

Innovativeness

11. Did the project promote any innovations (for your company or with support of you company) that directly target gender equality and women’s empowerment mainstreaming? If Yes, please name them.

4.6. Focus group discussion with women -entrepreneurs, recipients of grants (GFA)

Relevance

- To what extent has your participation in this project met your needs, expectations? What may have been done differently, in your opinion?

- Which project activities did you find the most useful/relevant for you?

Effectiveness

- What positive changes happened (for you, for your business, for other women in your community) because of your participation in the project? Please tell us about most significant change in your opinion.

- Do you feel yourself empowered by the project so that you can help other women to achieve economic independence? Are you doing that or going to do that? If Yes, In what way?

- Do you think that in the result of this project women became more capable to make decisions related to their economic participation? If Yes, please provide an example.

- What is the attitude in the community/communities where you established your business to women as entrepreneurs? Have you noticed any changes in

Sustainability

- Which activities do you think should continue after the project phases out? What other activities may you recommend to promote access of women to employment and economic activities?

- How are you going to use what you have learned under this project in future: for your company? Or to help other women?

Partnerships for GEWE and SDGs

- What do you think of cooperation with partners in this project (GFA, Taso Foundation, MoFA) ? Are there any institutions or organizations (at national, local level) that should be also involved to help women become more successful entrepreneurs? If Yes, please name them. Why would it be important that they join the project?

- How do you evaluate the current involvement and/or support from the local administration to promote economic opportunities for women, their access to markets, value chains and other?

## Annex 5 List of respondents

| Stakeholder’s Group | Name and position | Data collection method | Location |
| --- | --- | --- | --- |
| UN agencies |  |  |  |
| UN Women | Kaori Ishikava, Country Representatives | Online and face to face interviews | Tbilisi |
|  | Tamar Sabedashvili, Gender Adviser | Online and face to face interviews | Tbilisi |
|  | Ana Pashalishvili, WEE Component, Project Manager | Online and face to face interviews | Homebased and Tbilisi |
|  | Tamar Vashakidze, GG component, Program Analyst | Online and face to face interviews | Tbilisi |
|  | Marika Jobava, Program Analyst | Online and face to face interviews | Tbilisi |
|  | Elene Gabelaia, WEE Component, Project Analyst | Online and face to face interviews | Tbilisi |
|  | Lili Dopidze, WEE Component, Project Manager, Analyst | Online and face to face interviews | Tbilisi |
|  | Gvantsa Asatiani, Communications and Outreach Specialist | Face to face interview | Tbilisi |
|  | Nino Natroshvili communications team member, journalist | Face to face interview | Tbilisi |
| Partners |  |  |  |
| National Statistics Office of Georgia (GEOSTAT) | Paata Shavishvili, Deputy Director | Online interview | Tbilisi |
|  | Vasil Tsakadze, Head of Social statistics department | Online interview | Tbilisi |
|  | Aleko Arabuli, Head of Business Analytics Department | Online interview | Tbilisi |
| NALAG | Natya Gvinashvili, Deputy Head | Online interview | Tbilisi |
| Public Defender’s Office | Sopio Rusetski, Head of Gender Equality Department | Face to face interview | Tbilisi |
|  | Ekaterine Skhiladze, Deputy Head of Public Defender | Online interview | Tbilisi |
| Academy of Ministry of Finance Academy | Tariel Chulukadze, Director | Face to face interview | Tbilisi |
|  | Natia Gulua, Head of Budgetary Department | Face to face interview | Tbilisi |
|  | Ana Margiani, Head of International Relations Department | Face to face interview | Tbilisi |
|  | Ekaterine Gogelashvili, Head of Program Management Department | Face to face interview | Tbilisi |
| GFA | Natia Ninikelashvili, Project Manager | online interview | Tbilisi |
| Georgia Chamber of Commerce and Industry | Giorgi Vekua, Director of Business & Regional Development Department | online interview | Tbilisi |
|  | Nazi Burduladze, trainer | online interview |  |
| BDO | Ela Manukyan, Senior Trainings Consultant | online interview | Tbilisi |
|  | Maia Khachidze, Partner, Head of Corporate Finance | online interview | Tbilisi |
| TASO Foundation | Ketevan Zhordania, Director | online interview | Tbilisi |
| BTU | Nata Kizivadze, Head of Marketing Department | online interview | Tbilisi |
|  | Nino Enukidze, Rector | Face to face interview (job forum) | Tbilisi |
|  | Mariam Shashiashvili, project manager | online interview | Tbilisi |
|  | Ana Cheishvili, Head of International Relations & Development Office | online interview | Tbilisi |
| Human Resources Professionals Association in Georgia (HRPA) | Sergo Nozadze, Director | Face to face interview | Tbilisi |
|  | Salome Ghachava, CEO | Face to face interview | Tbilisi |
| PwC | Nino Cholokashvili, Project Manager | online interview | Tbilisi |
| Government/Public institutions (primary duty bearers) |  |  |  |
| GEC at the Parliament | Nino Tsilosani, MP, GEC Chair | Online interview | Tbilisi |
| Human Rights Secretariat of GoG Administration | Maka Peradze, Head | Face to face interview | Tbilisi |
| Ministry of Finances | Natia Gulua, Head of Budgetary Department | Face to face interview | Tbilisi |
| National Agency of Public Registry (NAPR) | Eliso Gelashvili, Deputy Chairmen | Online interview | Tbilisi |
|  | Elene Grigolia, Project Manager | Online interview | Tbilisi |
| Enterprise Georgia | Meri Gulua, Gender Consultant | online interview | Tbilisi |
|  | Irakli Gabriadze, Deputy Director | online interview | Tbilisi |
| Georgia's Innovation and Technology Agency | Annie Vashakmadze, Head of Donor Relations and International Relations Department | online interview | Tbilisi |
| Civil Service Bureau (CSB) | Maia Dvalishvili, Deputy Head | Face to face interview | Tbilisi |
| Civil Service Bureau (CSB) | Irina Aghapishvili, Head of Strategic Planning Department | Face to face interview | Tbilisi |
| Policy, Planning and Government Coordination Department of the Government of Georgia | Ketevan Tsanava, Head of Public Administration Unit | Online interview | Tbilisi |
| Prosecutor's Office | Salome Shengelia, Head of the Human Rights Department | Online interview | Tbilisi |
| Ministry of Education and Science of Georgia | Kakha Khandolishvili, Head of Strategic Planning and International Relations Department | Face to face interview | Tbilisi |
|  | Mariam Dzidziguri, Head of HR Department | Face to face interview | Tbilisi |
|  | Tatia Naneishvili, Head Of Analytical Division of Internal Audit Department | Face to face interview | Tbilisi |
| Local municipalities (Gender focal points) |  |  |  |
| 5 selected municipalities (Keda, Poti, Bagdati, Tetritskaro, Gardabani) | 8 Gender focal points and GEC representatives | Online group interview | Tbilisi |
| Imereti municipalities | 19 Gender focal points and GEC representatives (actually, live survey counted up to 21 persons) | Online focus group interview | Tbilisi |
| Guria, Shida Kartli, Racha-Lechkhumi municipalities | 14 Gender focal points and GEC representatives | Online focus group interview | Tbilisi |
| CSOs |  |  |  |
| WIC |  |  |  |
| Partnership for Human Rights | Ana Arganashvili, Executive Director | Online interview | Tbilisi |
| Beneficiaries (rights’ holders) |  |  |  |
| Self-Help Groups’ (SHGs) members | 14 participants | On-line SWOT workshop | Tbilsi |
|  | 11 participants | On-line SWOT results validation | Tbilsi |
|  | 12 participants | face-to-face focus group interview | Zguderi, Shida Kartli |
|  | 15 participants | face-to-face focus group interview | Shindisi, Shida Kartli |
|  | 8 beneficiaries from SHGs, Ozugeti | Online focus group interview | Tbilsi |
|  | 12 beneficiaries from SHGs, Chokhatauri | Online focus group interview | Tbilsi |
| Women entrepreneurs – small farmers (beneficiaries of GFA) | 10 participants | Online focus group interview | Tbilisi |
| TASO grantees | 19 participants | Online focus group interview | Tbilisi |
| Beneficiary | Kety Tsilosani, Youth Portal (and Café), Guria | online interview | Tbilisi |
| Beneficiary | Lia Kotrikadze, Lotos, Guria | online interview | Tbilisi |
| Beneficiary | Ana Abuladze, Samegrelo | online interview | Tbilisi |
| HRPA | 5 participants/ Human Resources Professionals Association in Georgia (HRPA) training | face-to-face direct observation | Tbilisi |
| WEPs signees |  |  |  |
| Tegeta | Nino Chelchelashvili, CSR | online interview | Tbilisi |
|  | Mariam Pharnishvili, HR | online interview | Tbilisi |
| GPI Holding | Tinatin Stambolishvili, Director of Communications | online interview | Tbilisi |
| Crystal | Maia Kobalia, Head Environmental and Social Division | online interview | Tbilisi |
| TBC | Maka Bochorishvili, Head of CSR | online interview & WEP Council Meeting | Tbilisi |
|  | Natha Tkhilava, consultant | online interview | Tbilisi |
| Geostqb | Natia Sirbiladze, General Director | online interview & WEP Council Meeting | Tbilisi |
| TERA Bank | Iza Kandelaki, Head of Training Center | online interview | Tbilisi |
| Liberty Bank | Nino Chikhladze, Head of HR | online interview & WEP Council Meeting | Tbilisi |
| BoG | NA | WEP Council Meeting | Tbilisi |
| WEP Council and working group meeting | 11 participants | face-to-face FGD | Tbilisi |
| Gender data experts |  |  |  |
| On.Ge, Queer.Ge | Khatia Ghoghoberidze, journalist | Online interview | Tbilisi |
| Supreme Court of Georgia | Lia Mchedlishvili, Head of Statistics Sector, Analytical Department | Online interview | Tbilisi |
| Tbilisi State University / Women’s Association | Khatuna Chugoshvili, Head, Library of the central reading- hall | Online interview | Tbilisi |
| Gender equality experts/PGA Experts |  |  |  |
| Tamar Bagratia | PGA consultant | online interview | Tbilisi |
| Nino Liluashvili | PGA consultant | online interview | Tbilisi |
| IFIs/Donors |  |  |  |
| USAID/USAID Skills Building Programme | Nelly Revazishvili, ProgrammeManager | online interview | Tbilisi |
| EBRD |  |  |  |

## Annex 6 List of documents reviewed

GG4GEG project documents:

- GG4GEG Prodoc

- GG4GEG Project Theory of Change

- GG4GEG Project Indicative Activity Plan

- GG4GEG Results’ and Resources Frameworks

- GG4GEG budget revised until end of May 2023

- GG4GEG Project Activity Plan

- GG4GEG Project Risk Management Plan

- Donor agreement amendment signed on July 2021

- GG4GEG justification note for extension

- GG4GEG 1st annual progress Report

- GG4GEG 2nd annual progress Report

- GG4GEG 3rd annual progress Report

- GG4GEG Project Quarterly Monitoring Reports 2022

- GG4GEG Project presentation

- GG4GEG Mission Report -  GIA training of CSOs (April 2022)

- GG4GEG Mission Report -  GIA training of Public Servants (October 2022)

- 8 MoFA Quarterly Reports to UN Women (2021-2022)

- 12 PDO Quarterly Reports to UN WOmen (2020-2022)

- 11 NALAG Quarterly Reports to UN Women (2020-2022)

- UN Women - NALAG Contract

- UN Women concept note - Ring the Bell for Gender Equality 2023

- GFA Quarterly reports (4 reports) to UN Women (2021-2022)

- BDO reports ( 3 reports) to UN Women (2021-2022)

- HRPA reports ( 3 reports) and Deliverable 1 package to UN Women (2021-2022)

- GCCI reports and deliverable packages to UN Women (2021-2022)

- BTU reports (2 reports) to UN Women (2021-2022)

- Memorandum of Understandings (MoU) with: TBC Bank, USAID Skills programme, NAPR

- ToR on Thematic Working Group on Promoting Gender Equality in Decision-Making Positions in the Financial Sector of Georgia

- ToR on the creation of the WEPs Council

- ToR on Thematic Working Group on Promoting Gender Equality in Decision-Making Positions in the Financial Sector of Georgia

- GFA grants manual

- GFA databases

- Taso databases

- Enterprise Georgia Action Plan Implementation Report

- Enterprise Georgia statistics report

Country reports, UN Women strategic documents, other related publications:

- UN Women Georgia Annual Work Plan Report 2020

- UN Women Georgia Annual Work Plan Report 2021

- UN Women Strategic Note 2016-2020

- UN Women Strategic Note 2021

- UN Women Strategic Note 2022-2023

- Sixth Periodic Report of Georgia on The Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) 2020 - https://myrights.gov.ge/uploads/files/docs/4944CEDAW_Report_Georgia_ENG.pdf

- Joint Shadow Report on the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) 2021 - http://www.ginsc.net/uploads/docs/b5ffb1814504598223a8849b022013fa.pdf

- Country Gender Equality Profile of Georgia 2021, UN Women - https://georgia.unwomen.org/sites/default/files/2022-04/Country%20Gender%20Equality%20ENG%20%20UPDATED.pdf

National Policy Documents developed with UN Women support under the GG4GEG project:

- State Concept on Gender Equality Concept of Georgia (2022) - https://matsne.gov.ge/ka/document/view/5664358?publication=0

- Gender Equality Strategy and Action Plan for the Civil Service Bureau (2022) - http://csb.gov.ge/media/3368/7896546.pdf

- Gender Equality Strategy of the Prosecutor’s Office of Georgia 2022-2027 - https://pog.gov.ge/uploads/e17e8dd3-genderuli-Tanasworobis-strategia-GEWE-Strategy-2022-2027.pdf

- Gender Equality Action Plan of the Prosecutor’s Office of Georgia 2022-2024 - https://pog.gov.ge/uploads/b6ee7bb1-PO-GE-Action-Plan-2022-2024-1-7.pdf

- Permanent Parliamentary GEC Thematic Inquiry Report: Mainstreaming Gender Equality Issues into Government Policy (2022) (unpublished version)

- CSB. Protection of Victims of Domestic Violence at a Work Place in Public Service (pre-final, unpublished version)

- Gender Equality Council’s Action Plan 2023, Abasha Municipality

- Gender Equality Plan 2022-2023, Gardabani Municipality

- Gender Equality Council’s Action Plan 2023-2025, Kutaisi

- Gender Equality Council’s Action Plan 2022-2024, Samtredia Municipality

- Gender Equality Council’s Strategy 2021-2023, Poti Municipality

- Report on Gender Equality Council’s Action Plan Implementation 2021-2022, Poti Municipality

- MoF, Draft Public Finance Reform Management Strategy 2023-2026 (unpublished version)

- Generation Equality Forum: Technology and Innovation for Gender Equality (TIGE) Action Plan for Georgia 2022-2025

- Georgia for Gender Equality  georgia.unwomen.org/en/digital-library/publications/2021/06/georgia-for-gender-equality

Studies and Assessments developed with UN Women’s support under GG4GEG:

- National Statistics Office of Georgia. Time Use Survey in Georgia 2020-2021 - https://georgia.unwomen.org/sites/default/files/2022-12/GTUS%20Report%20ENG%20WEB%20%281%29.pdf

- National Statistics Office of Georgia. GTUS presentation Concept note and Agenda

- UN Women. Time Use Survey media coverage monitoring report (2021)

- Civil Service Bureau PGA report (2020)

- State Inspector’s Service PGA report (2020)

- Prosecutor’s Office of Georgia PGA report (2020)

- Gender Responsive Public Financial Management (GRPFM) Assessment Report (2022) - https://www.pefa.org/sites/pefa/files/2022-12/GE-Oct22-GRPFM-Public%20with%20PEFA%20Check.pdf

- UN Women. Workplace Sexual Harassment in the Civil Service in Georgia (2021) - https://georgia.unwomen.org/sites/default/files/Field%20Office%20Georgia/Attachments/Publications/2021/Workplace%20Sexual%20Harassment%20in%20the%20Civil%20Service%20in%20Georgia%20ENG%20renewed.pdf

- UN Women. Investigating Workplace Sexual Harassment Cases with a Victim-centered Approach (2022) - https://georgia.unwomen.org/sites/default/files/2022-12/Manual%20-%20Investigating%20Workplace%20SH%20Cases%20with%20a%20Victim-centered%20Approach.pdf

- Gender Impact Assessments of the Law of Georgia on Public Service (unpublished version)

- Public Defender’s Office of Georgia. Evaluation of Gender Equality Policies of Municipalities 2022 (unpiblished version)

- Public Defender’s Office of Georgia. Assessment of Gender Policy of Local Self-government Bodies (2020) - https://ombudsman.ge/res/docs/2020061711084244176.pdf

- Public Defender of Georgia. Assessment of Effectiveness of Gender Equality Institutional Mechanism in Georgia (2021) - https://www.ombudsman.ge/res/docs/2022032913195236233.pdf

- Public Defender of Georgia. Review of Georgiaʼs Gender Mainstreaming Obligations and their Fulfilment Status (2021) - https://www.ombudsman.ge/res/docs/2021031012092124287.pdf

- Baseline Study on the Impact of the Women's Empowerment Principles (WEPs) on Business in Georgia (ENG, GEO) https://georgia.unwomen.org/en/digital-library/publications/2021/12/baseline-study-on-the-impact-of-the-womens-empowerment-principles

- WEP Brochure https://www.weps.org/sites/default/files/2021-03/WEPs_BROCHURE.pdf

- Stories of Success from the WEPs Companies (ENG, GEO) https://georgia.unwomen.org/en/digital-library/publications/2021/02/womens-empowerment-principles-in-georgia

- WEP Survey 2022

- Participatory Gender Audit - National Agency or Public Registry (NAPR)

- Participatory Gender Audit - Georgian National Tourism Administration (GNTA)

- Participatory Gender Audit - Ministry of Education and Science of Georgia (MoES)

- NAPR GIA Report - Gender Impact Assessment of the Legal Framework regarding Matrimonial Property as Being under the Joint Ownership of Spouses

- Women's Entrepreneurship Development (WED) report

- Research on Women's Participation in Technology Report

- WEPs Council Concept Note

- Research on Women’s Participation in Technilogy in Georgia

- Survey on Women Entrepreneurs in Georgia. Prepared by CRRC Georgia and Geostat with GG4GEG project support

- National Assessment of Women’s Enterprneurship Developemnt (WED) Georgia. november 2022, Prepared by CRRC with GG4GEG project support

- Classification of agrotourismstructures, AgrotourismStandard of Georgia, GFA

Laws (amendments) and Regulations developed with UN Women support under the GG4GEG:

- Parliament of Georgia. Gender Impact Assessment - the State Paper for Undertaking GIA in Political Spheres (2020) - https://pbo.parliament.ge/media/k2/attachments/GIA_guideline-10.2020.pdf

- Amendments to the Organic Law of Georgia on Normative Acts institutionalizing Gender Impact Assessment (2020) - https://parliament.ge/legislation/24782 and https://matsne.gov.ge/ka/document/view/90052?publication=37

- GoG’s Decree #629 on Monitoring and Evaluation of Policy Documents (2019) - https://matsne.gov.ge/ka/document/download/4747283/0/ge/pdf

- GoG’s Municipality Development Planning Guide (2022)

- Meeting Notes – Gender Theme Group (GTG) (1 April 2022)

- Meeting Notes – Gender Theme Group (GTG)  (4 October 2022)

- Meeting Notes – Gender Theme Group (GTG) (16 February 2022)

Manuals, guidelines and training courses developed under the GG4GEG project:

- National Statistics Office of Georgia. Agenda and participation lists of Time Use Survey training

- UN Women. Agenda and participation lists Sexual Harassment Trainings for various State bodies (2021-2021)

- NALAG Gender Equality Strategy & Action Plan 2021-2025 - https://gender.nala.ge/%E1%83%A9%E1%83%95%E1%83%94%E1%83%9C%E1%83%A1-%E1%83%A8%E1%83%94%E1%83%A1%E1%83%90%E1%83%AE%E1%83%94%E1%83%91/3

- UN Women. Gender Mainstreaming Toolkit for the Government of Georgia (unpublished version)

- MoFA. Gender Responsive Budgeting Training Module (2022)

- MoFA. GRB training syllabus (2022)

- MoFA. GRB training schedule, agenda, participation list (2022)

- UN Women. Investigating Workplace Sexual Harassment Cases with a Victim-centered Approach (2022)- https://georgia.unwomen.org/sites/default/files/2022-12/Manual%20-%20Investigating%20Workplace%20SH%20Cases%20with%20a%20Victim-centered%20Approach.pdf

- Training module on How to Start and Develop Your Business

- Communications Strategy of Women’s Community Academy

- Branding Guidelines of Women’s Community Academy

- Diversity, Equity and Inclusion (DEI) manual for HR Professionals

- Training module on How to Start and Develop Your Business

- Training module on Diversity, Equity and Inclusion (DEI) for HR Professionals

- Ready-made templates of gender-sensitive HR policies and procedures including: HR Policy, Code of Conduct, Contract Template, Guidelines for gender mainstreaming through HR process, Sexual harassment prevention mechanisms implementation proecdures

Evaluation reference materials:

- Committee on the Elimination of Discrimination against Women. Concluding observations on the sixth periodic report of Georgia 2 March 2023 - https://tbinternet.ohchr.org/_layouts/15/treatybodyexternal/Download.aspx?symbolno=CEDAW%2FC%2FGEO%2FCO%2F6&Lang=en

- United Nations Evaluation Group (2016). Norms and Standards for Evaluation. New York: UNEG.

- The UN Women Evaluation Policy (2012) - http://undocs.org/en/UNW/2012/12

- UN Women Evaluation Strategy to Transform Women’s and Girls’ Lives, 2018-2021

- UNEG Code of Conduct for Evaluations - http://www.unevaluation.org/document/detail/100;

- UNEG Ethical Guidelines - http://www.unevaluation.org/document/detail/102;

- UNEG Guidance Integrating Human Rights and Gender in the UN System - http://www.uneval.org/document/detail/1616;

- UN Women Evaluation Handbook - http://genderevaluation.unwomen.org/en/evaluation-handbook

- UN SWAP Evaluation Performance Indicator and related Scorecard - http://www.uneval.org/document/detail/145

- GoG. Public Administration Reform Strategy 2023-2026 of Georgia (unpublished version)

- GoG. Public Administration Reform Action Plan 2023-2024 of Georgia (unpublished version)

- GoG. Municipality Development Planning Guide (2022)

- Organic Law of Georgia on Local Self-Governance - https://matsne.gov.ge/ka/document/view/2244429?publication=66

- State Social Rehabilitration Program 2023 https://www.matsne.gov.ge/ka/document/download/5727062/0/ge/pdf

- Temporary Rules for Authorization of Organizations Providing Early Upbringing and Education and/or Pre-School Upbringing Services, as well as for Suspension and Termination of such Authorization -  https://matsne.gov.ge/ka/document/view/5727272?publication=0

- Akhali Ganatleba. Authorization of Kindergartens - When it Would Start and What Stages Pre-School Organizations would have to Pass - https://akhaliganatleba.ge/%E1%83%91%E1%83%90%E1%83%A6%E1%83%94%E1%83%91%E1%83%98%E1%83%A1-%E1%83%90%E1%83%95%E1%83%A2%E1%83%9D%E1%83%A0%E1%83%98%E1%83%96%E1%83%90%E1%83%AA%E1%83%98%E1%83%90

- Law of Georgia on Early Upbrining and Pre-School Education - https://matsne.gov.ge/ka/document/view/3310237?publication=13

- EU4GenderEquality Reform HelpDesk. Gender Equality in Georgia in GAP III Priority Areas: Country Review (2021) - https://www.eeas.europa.eu/sites/default/files/documents/Georgia%20Country%20Gender%20Review_0.pdf

- European Charter for Equality of Women and Men in Local Life (2022 update) - https://charter-equality.eu/the-charter/lobservatoire-europeen-en.html

- EU Gender Action Plan III – 2021-2025 - Country Level Implementation Plan – CLIP for Georgia - https://www.eeas.europa.eu/sites/default/files/clip_georgia_2021_2025_0.pdf

- Congress of Local and Regional Authorities of the Council of Europe. Human Rights at Local Level in Georgia. Assessment Report (2021) - https://rm.coe.int/assessment-report-human-rights-at-local-level-in-georgia-eng/1680a524e0

- Office of the State Minister of Georgia for Reconciliation and Civic Equality. State Strategy on Civic Equality and Integration 2021-2030. https://smr.gov.ge/ge/page/31/samoqalaqo-tanasworobisa-da-integraciis-saxelmwifo-strategia-da-samoqmedo-gegma#collapse0

- Office of the State Minister of Georgia for Reconciliation and Civic Equality. Draft Action Plan 2023-2024 for the State Strategy on Civic Equality and Integration 2021-2030 - https://smr.gov.ge/uploads/Files/_%E1%83%98%E1%83%9C%E1%83%A2%E1%83%94%E1%83%92%E1%83%A0%E1%83%90%E1%83%AA%E1%83%98%E1%83%90/samoqalaqo_tanasworobisa_da_integraciis_samoqmedo_gegmis_proeqti_(2023-2024)_ww_(1).xlsx

- Office of the State Minister of Georgia for Reconciliation and Civic Equality. State Strategy on Civic Equality and Integration 2021-2030 - Annual Report on Fulfillment of 2021 Action Plan - https://smr.gov.ge/uploads/Files/_%E1%83%98%E1%83%9C%E1%83%A2%E1%83%94%E1%83%92%E1%83%A0%E1%83%90%E1%83%AA%E1%83%98%E1%83%90/wliuri-angarishi-2021.pdf

- GoG. National Action Plan of Georgia 2022-2024 for the Implementation of UN Security Council’s Resolutions on Women, Peace and Security - https://matsne.gov.ge/ka/document/view/5598617?publication=0

- GoG. the Vision 2030 – National Development Strategy (2022) - https://matsne.gov.ge/ka/document/view/5604706?publication=0

- GoG. National Strategy of Georgia on Protection of Human Rights 2022-2030 - https://info.parliament.ge/file/1/BillReviewContent/304602

- GoG. State Youth Strategy 2023-2026 and the Action Plan 2023 - https://www.matsne.gov.ge/ka/document/view/5675992?publication=0

- GoG. State Strategy on Science and Education 2022-2030 and the Action Plan 2022-2024 - https://www.matsne.gov.ge/ka/document/view/5557675?publication=0

- GoG. State Healthcare Strategy 2022-2030 - https://www.matsne.gov.ge/ka/document/view/5453716?publication=0

- Euractiv.  How the EU can push for its priorities in Georgia (2022) - https://www.euractiv.com/section/all/opinion/how-the-eu-can-push-for-its-priorities-in-georgia/

- GoG. Mental Health Strategy 2022-2030 - https://matsne.gov.ge/ka/document/view/5357283?publication=0

- GoG.  Fourth Report to the Council of Europe on Protection of National Minorities - https://rm.coe.int/4th-sr-georgia-en/1680a78b0c

- GoG. National action plan for combating domestic violence and violence against women and ensuring the protection of survivors 2022-2024 - https://matsne.gov.ge/ka/document/view/5597108?publication=0

- Georgian State Budget for 2023 - https://matsne.gov.ge/ka/document/view/5652523?publication=0

- GoG. Public Service Development Strategy for 2022-2025 - https://www.matsne.gov.ge/ka/document/view/5436909?publication=0

- EECMD/EPRC. Challenges to Gender Budgeting in Georgia on Municipal Level. Policy Paper (2020) - https://eecmd.org/wp-content/uploads/2021/02/Policy-Paper_Gender-Budgeting-1.pdf

## Annex 7 Composition of the Evaluation Reference Group

| UN Women | Tamar Vashakidze, Good Governance component, Programme Analyst |
| --- | --- |
| UN Women | Ana Pashalishvili, Women’s Economic Empowerment Component, Project Analyst |
| GEC at the Parliament | Nino Tsilosani, MP, GEC Chair |
| Public Defender’s Office | Sopio Rusetski, Head of Gender Equality Department |
| NALAG | Natya Gvinashvili, Deputy Head |
| GFA | Natia Ninikelashvili, Project Manager |
| TASO Foundation | Ketevan Zhordania, Director |
| Enterprise Georgia | Irakli Gabriadze, Deputy Director |

## Annex 8 Summary of the SWOT findings

| Strengths of participation of women in SHGs - women’s sense of self-worth; - understanding self-worth, increased self-confidence and courage; more rich life, having purpose in life; mutual respect; increased motivation e.g., active participation in training; abilities to generate ideas and see them through; changes in attitudes to women and their empowerment in the communities; - women’s right to have and to determine choices; - increased access to knowledge and increased awareness of women’s rights; better understanding of needs; having own space (women’s rooms, technology, library) and time for growth and reflection - changes in attitudes and opinions about what women can do; - modeling for other women how to determine choices; - expanded choices (though skills trainings and mobilization, networking with other SHGs; - women’s right to have access to opportunities and resources; - improved access to information on choices and opportunities (such as grants, education resources etc.); - having the agency (SHG) to participate in projects available to groups; - women’s right to have power to control their own lives - increased financial independence - improved access to employment; - managing a group budget - women’s ability to influence the direction of social change - increased communication with decision makers; - more active participation in community life, such as village meetings, etc. - initiating community life improvement projects creation of initiative groups | Weaknesses - women’s sense of self-worth - passiveness of women/ overreliance on the social workers; reluctance to take responsibility; lack of education and skills; disappointment because of not obtaining grants - women’s right to have and to determine choices - lack of information, education and experience to exercise choices; - lack of own space for sharing ideas and learning (3) women’s right to have access to opportunities and resources; - low awareness of legal rights (knowledge of relevant legislation); - women’s right to have power to control their own lives - stereotypes within women; - lack of skills (accountancy) to manage the budget; - women’s ability to influence the direction of social change - lack of advocacy and conflict resolution skills when having differences of opinion in the community; - communication with local governance authorities is not a common practice; - indifference among women to problems in the community, lack of volunteering culture;. |
| --- | --- |
| Opportunities Arising from more gender -sensitive systems and institutions: - support and opportunities from governmental and non-governmental organizations, donors (USAID, etc.) that work on women’s empowerment e.g., access to training, raising awareness, business consultancy, grants etc. - implementation of local gender equality agenda though cooperation with local self-government; - local programs implemented in the villages; - positive attitude to self-help group resulting with better facilities for women for meeting and work; more regular and frequent meeting of women Arising from social mobilization/empowerment of women - better opportunities to voice the needs of women through representation of groups in different meetings and fora; - knowledge and skill for participation in competitions; - ICT and language skills to access information for learning and decision making; - establishment of women’s organizations; expansion of SHGs - more regular and frequent meeting of women resulting in strengthening of women’s organizations | Threats (barriers, challenges) Gender inequalities embedded in the systems: o lack of time due overload at home; o negative attitude or pressure from the society; o resistance / lack of support from family members; Gender- blind institutions: o no space (physical or mental) for women; o neglection of women’s need or problems within local self-governance; o lack of communication from the local self-governance about opportunities available for women; o low awareness in the society about women’s rights and empowerment; o passive attitude to community problems from local people; o prevalence of stereotypes in the society; hostile attitude to active women; physical security, bullying from locals; Inequal regional and local development: o lack of/ low-quality internet; o lack of human resources in the villages due to migration; o poor economic conditions; o location such as lack of roads, transport; o low budget at the local self-governance; |

## Annex 9 GG4GEG Result and Resources Framework

| Project Title: Good Governance for Gender Equality in Georgia (GG4GEG) Duration: 45 months Project Development Goal / Impact: Governance systems, programmes, and policies along with private sector partners are gender sensitive and enable women’s economic empowerment and broader gender equality in Georgia Indicator A: Systems in place to track and make public allocations for gender equality and women’s empowerment (SDG indicator 5.c.1) Target: Yes by 2023 Baseline: No (2020) Source: Report of the Secretary-General Progress towards the Sustainable Development Goals, Statistical Annex, Global Database and Monitoring reports on Georgia’s Nationalized SDGs Indicator B: Georgia’s ranking by World Economic Forum Global Gender Gap Index Target: 64 by 2022 Baseline: 74 (2020) Source: The Global Gender Gap Report, World Economic Forum Indicator C: Number of policies/procedures adopted by the Government of Georgia that aim at improvement of institutionalization of gender equality and gender mainstreaming (NSDG 5.1.1. (GT 5.1) Target: 3 new by 2023 Baseline: 6 by 2020 Source: Legislative Herald of Georgia; Project donor reports Indicator D: % of the female labor force participation in Armenia, Azerbaijan and Georgia Target: 45.1% (increase with 2%) by 2023 Baseline: 43.1% (2019) Source: Labour Force Survey, GEOSTAT Indicator E: Proportion of women in managerial positions NSDG 5.5.2 (GT 5.5) Target: 40 by 2023 Baseline: 36% (2018) Source: Labour Force Survey, GEOSTAT Indicator F: Number of interventions to enhance day care facilities and re-skilling of women to enhance their Labour Force Participation Rate NSDG: 8.5.2 (GT 8.5) Target: 2 by 2023 Baseline: 0 (2020) Source: Project donor reports Indicator G: Proportion of women with a positive perception on their influence on business and economic-related decision-making Target: TBD by 2023 Baseline: TBD (2021) Source: TBD ient and accountableual access to justices, human rights and increased representation of women in decision-making.” and Outcome 3: “By 2025, all people without discrimination benefit from sustainable, inclusive and resilient economy in Georgia.” |  |
| --- | --- |
| UN Women SP Outcome 2: Women lead, participate in, and benefit equally from governance systems; UN Women SP Outcome 3: Women have income security, decent work, and economic autonomy |  |
| Project Outcome 1: Governance systems are gender sensitive and enable gender equality in Georgia |  |
| Outcome 1 indicators: 1.A. Ministry of Finance integrates gender-responsive budgeting in public finance management systems Target: Yes by 2023 Baseline: No (2018) Source: Project progress reports; Relevant circular of the Ministry of Finance. 1.B. Number of government’s sectorial policies and programmes that integrate gender data and analysis through the Gender equality institutional mechanisms (Inter Agency Commission and Parliamentary Gender Equality Council) Target: 3 by 2023 Baseline: 0 (2018) Source: Monitoring Report of gender equality and gender mainstreaming policymaking and implementation by Public Defender of Georgia | Outcome 1 assumptions/risks: - COVID-19 pandemic mitigation measures enable successful implementation of the project - Project activities are not affected by any major crisis (economic, political, natural disaster) - All project partners and beneficiaries are interested and express the will to participate in the project - Gender mainstreaming requirements and standards promoted by the project are sustainable after its phase out - The tools and strategies promoted by the project are of high quality and well adapted to Georgia’s context - Sex disaggregated data and gender analysis informs effective policies and legislation to accurately reflect the needs of women, particularly of the poor and socially excluded |
| Both Output 1.1 and Output 2.2 of the project and their corresponding indicators fall under UN Women Georgia CO SN/AWP Output 1.1.1 Civil servants’ capacities as well as processes for gender mainstreaming in policies and budgets developed and sustained at the national and local levels |  |
| Output 1.1: Gender equality and gender mainstreaming are institutionalized at the national and local levels | Output 1.1 assumptions/risks: - UN Women successfully advocates with the government to put gender equality high on its political agenda - Roles, responsibilities and mandates of different structures engaged in gender equality institutional mechanisms at national and local levels are clearly defined and articulated in relevant normative frameworks - The assumption that the “default” allocation of resources is gender-neutral is overcome / gender responsive budgeting is fully understood as a tool to mainstream gender in national policies, plans and programmes |
| Output 1.1 indicators/target/baseline/source: Indicator 1.1.a: Number of internal policies/procedures submitted for adoption/endorcement to the government of Georgia that aim at improvement of institutionalization of gender equality and gender mainstreaming Target: 4 by 2023 Baseline: 0 (2018) Source: Project progress reports Indicator 1.1.b: Independent monitoring of institutionalization of gender equality and gender mainstreaming obligations by government at all levels Target: Yes by 2023 Baseline: No (2018) Source: Monitoring Report of gender equality and gender mainstreaming policymaking and implementation by Public Defender of Georgia and CSOs monitoring reports |  |
| ACTIVITIES |  |
| Activity 1.1.1. To provide technical support to the government of Georgia (represented by the Ministry of Foreign Affairs and the Inter-Agency Commission for Gender Equality, Violence against Women and Domestic Violence in the Prime Minister’s Office) in Beijing Platform for Action +25 (BPfA +25) review process and in acting upon CEDAW’s gender mainstreaming recommendations |  |
| Activity 1.1.2. To obtain political support and provide technical support to the Inter-Agency Commission in the development of the government’s internal roadmap for gender equality and gender mainstreaming |  |
| Activity 1.1.3. To provide technical support to the Inter-Agency Commission and Gender Equality Council of the Parliament in establishing clear division of roles, responsibilities and lines of accountability of key governmental and oversight bodies at national and local levels in implementing gender equality and gender mainstreaming initiatives |  |
| Activity 1.1.4. To advocate in partnership with civil society for bolstering the capacities and resources of Inter-Agency Commission for Gender Equality, Violence against Women and Domestic Violence at the Prime Minister’s Office |  |
| Activity 1.1.5. To support in strengthening vertical and horizontal coordination and accountability mechanisms across governmental bodies and levels that involve relevant non-governmental stakeholders to ensure synergies and effective implementation of gender equality initiatives |  |
| Activity 1.1.6. To provide technical support to gender equality institutional mechanisms at the level of local governments to better undertake gender equality and mainstreaming obligations (including but not limited to promotion of healthy competition among the municipalities) |  |
| Activity 1.1.7. To facilitate coordinated action of development, civil society and government partners towards institutionalization of gender responsive budgeting (GRB) |  |
| Activity 1.1.8. To provide technical support to the Ministry of Finance to institutionalize GRB on central as well as local levels |  |
| Activity 1.1.9. To provide technical support to the Public Defender’s Office of Georgia to ensure consistent and thorough monitoring of institutionalization of gender equality and gender mainstreaming by the government at all levels |  |
| Output 1.2: Gender mainstreaming capacities are developed and sustained at the national and local levels | Output 1.2 assumptions/risks: - Capacity development interventions of the project reach out to all concerned staff/institutions - Capacity development interventions of the project reach out to managers and senior officials - Capacity development interventions and tools anchored as much as possible into continuous on-the-job training of relevant public servants - Gender mainstreaming tools and assessments do not become “tick box” exercise - Training materials and tools developed are not too complex to be used by a wide range of relevant actors |
| Output 1.2 indicators/target/baseline/source: Indicator 2.a: Number of public servants outreached by gender mainstreaming capacity development interventions of the project Target: 500 by 2023 Baseline: 0 (2012) Source: Training participants list and training evaluations documented through project progress reports Indicator 1.2.b: Number of educational tools on gender mainstreaming produced with technical support of the project Target: 3 by 2023 Baseline: 0 (2018) Source: Project progress reports Indicator 1.2.c: Share of PGA recommendations implemented by the audited entities Target: 40% by 2023 Baseline: 0 (2018) Source: Project progress reports |  |
| Activity 1.2.1. To provide technical support to the Prime Minister’s Office, Inter-Agency Commission and Civil Service Bureau in mainstreaming gender into policies aimed at capacity development of public servants in Georgia |  |
| Activity 1.2.2. To create a pool of local experts in Gender Impact Assessment (GIA) that will be affiliated with the Inter-Agency Commission under the Prime Minister’s Office |  |
| Activity 1.2.3. To develop an instruction for public servants on Gender Impact Assessment (GIA) to be endorsed by the Inter-Agency Commission for Gender Equality, Violence against Women and Domestic Violence at the Prime Minister’s Office |  |
| Activity 1.2.4. To provide trainings to selected policy-makers in GIA on the basis of the instruction |  |
| Activity 1.2.5. To create a pool of local experts in Gender Responsive Budgeting (GRB) |  |
| Activity 1.2.6. To conduct series of trainings (from introductory to hands on) in GRB for central and local level public finance officials |  |
| Activity 1.2.7. To culminate the face-to-face training in the development of an on-line course on GRB for public servants (replicating best examples of similar work from UN Women offices in the region) to be endorsed by the Ministry of Finance |  |
| Activity 1.2.8. To expand the pool of local Participatory Gender Audit (PGA) facilitators |  |
| Activity 1.2.9. To conduct PGA of at least three ministries identified in consultation with the Inter-Agency Commission for Gender Equality, Violence against Women and Domestic Violence at the Prime Minister’s Office |  |
| Activity 1.2.10. To follow up to the PGA recommendations in close partnership with the audited three ministries |  |
| Output 1.3 of the project and its corresponding indicators fall under UN Women Georgia CO SN/AWP Output 1.1.2 More and better-quality data and analysis are available to promote and track the progress of gender equality and women’s empowerment |  |
| Output 1.3: More and better-quality data and analysis are available to promote and track the progress of gender equality and women’s empowerment | Output 1.3 assumptions/risks: - Sex-disaggregated and gender-sensitive data are not “women only“ focused - Political will is secured to conduct time use survey and use its findings for policymaking - Sex-disaggregated and gender-sensitive data are obtained and processes in consultation with civil society organizations - There is centralised system (GEOSTAT) where relevant gender-sensitive data are collected, stored and accessible |
| Output 1.3 indicators/target/baseline/source: Indicator 1.3 a: Number of data producers and users with strengthened capacities in the collection, analysis, dissemination and use of gender statistics, including in improving Tier II and Tier III SDGs indicators Target: 100 by 2023 Baseline: 0 Source: Project progress reports Indicator 1.3 b: Time use survey carried out Target: Yes by 2023 Baseline: No (2018) Source: Final report of time use survey by GEOSTAT |  |
| Activity 1.3.1. To support GEOSTAT to facilitate process of development of National Strategy for Gender Statistics to support achievement of the goals in the upcoming National Statistics Development Strategy through gender-mainstreaming across the national statistical system |  |
| Activity 1.3.2. To support GEOSTAT and Inter-Agency Commission for Gender Equality, Violence against Women and Domestic Violence at the Prime Minister’s Office to develop a national set of gender indicators, including those used for reporting on national and international commitments to gender, such as the SDGs, the Istanbul Convention, CEDAW and the Beijing Platform for Action |  |
| Activity 1.3.3. To carry out advocacy work to boost investment in analysis within GEOSTAT and other data producing agencies so that statistical products go beyond presenting sex disaggregated indicators to explain, interpret and contextualize the information |  |
| Activity 1.3.4. To support GEOSTAT in assessing user satisfaction with existing gender statistics products, including the soon to be released Gender Statistics Portal, to gauge how well they are meeting user needs, how they can be enhanced and what other products are likely to be most useful |  |
| Activity 1.3.5. To provide support to GEOSTAT to improve its gender statistics products (Women and Men and Gender Portal) on the basis of user satisfaction assessment |  |
| Activity 1.3.6. To provide technical support to GEOSTAT and other relevant partners from the government and academia towards the development of Georgia country gender profile |  |
| Activity 1.3.7. To support GEOSTAT to conduct a time use survey and to support gender analysis and dissemination of the findings. |  |

| Project Outcome 2: Women in rural areas benefit from increased income-generation opportunities in the agrotourismand ICT sectors and fully realize their economic rights with the support of a gender-responsive private sector |  |
| --- | --- |
| Outcome 2 indicators: 2.A. Number of beneficiary women with increased income in agrotourismand related fields through project intervention Target: 100 new (altogether 150) by 2023 Baseline: 50 by 2020 Source: Project progress reports 2.B. Number of beneficiary women with increased income in ICT and related fields through project intervention Target: 100 new (altogether 209) by 2023 Baseline: 109 by 2020 Source: Project progress reports | Outcome 2 assumptions/risks: - COVID-19 pandemic mitigation measures enable successful implementation of the project - Private sector partners demonstrate resilience to COVID-19 induced crisis and find strengths to cooperate with the project - Project activities are not affected by any major crisis (economic, political, natural disaster) - All project partners and beneficiaries are interested and express the will to participate in the project - Cultural and gender norms do not prevent women from participating and benefiting from all activities - The most vulnerable groups of women are identified, outreached and interested and able to participate in the project |
| Both Output 2.1 and Output 2.2 of the project and their corresponding indicators fall under UN Women Georgia CO SN/AWP Output 2.1.2 The capacities of the representatives of government, public institutions and private companies strengthened to develop and deliver legislation, policies, services and programs for women’s economic empowerment |  |
| Output 2.1: Businesses have an increased understanding of the Women’s Empowerment Principles (WEPs) and have the skills to implement measures that benefit women, specifically in rural areas | Output 2.1 assumptions/risks: - Private companies understand their responsibilities and roles in relation to promoting the SDGs and gender equality and women’s empowerment - Private companies are interested in working together with other stakeholders including the UN, the Government and women business enterprises and associations - Trainings on gender equality and non-discrimination in the workplace successfully create a non-hostile and enabling environment for increased representation of women at all levels and changes in internal and external policies - Financial situation in WEPs companies allows them to invest in women’s economic empowerment |

| Output 2.1 indicators/target/baseline/source: Indicator 2.1.a: Number of private enterprises that signed the UNW/UN Global Compact Women’s Empowerment Principles with a focus on implementing gender-responsive corporate policies/practices Target: 50 new (altogether 130) by 2023 Baseline: 80 (2020) Source: Global roster of WEPs signatories: https://www.weps.org/companies Indicator 2.1.b: Number of companies’ employees with increased knowledge of WEPs Target: 300 new (altogether 510) by 2023 Baseline: 210 (2020) Source: Project progress report |  |
| --- | --- |
| ACTIVITIES |  |
| Activity 2.1.1. To conduct meetings and trainings for company representatives on gender equality, women’s empowerment, and WEPs (including WEPs certification) |  |
| Activity 2.1.2. To implement a leadership training programme to empower women managers to advocate for change within and outside their companies |  |
| Activity 2.1.3. To facilitate exchange of company experiences and lessons learned through conferences, publications, meetings, and international and local study visits |  |
| Activity 2.1.4. To provide technical advisory support to companies in assessing current corporate practices and developing new policies and initiatives in compliance with WEPs |  |
| Activity 2.1.5. To gather and disseminate evidence on the benefits of integrating WEPs in companies |  |
| Activity 2.1.6. To develop and disseminate guidance, tools and sample policies/practices for companies (including online tools) |  |
| Activity 2.1.7. To showcase WEPs success stories for encouraging new companies to join the WEPs and conduct communications campaign |  |
| Activity 2.1.8. To develop technical capacity on WEPs’ in business associations to foster national ownership and sustainability of WEPs |  |
| Activity 2.1.9. To raise awareness of journalists/media outlets and advertising agencies on WEPs and women’s economic empowerment issues |  |
| Output 2.2: Policymakers and public agencies have increased capacities to identify and address challenges faced by women entrepreneurs in agrotourismand ICT | Output 2.2 assumptions/risks: - Government is open and willing to receive suggestions on how to reform their policies and programmes to better advance women’s economic empowerment - Government is willing to strengthen partnerships with the private sector to achieve development and gender equality goals - State agencies concerned are prioritizing work on women’s economic empowerment |
| Output 2.2 indicators/target/baseline/source: Indicator 2.2.a: Number of new studies/analyses made available on women’s opportunities and challenges in entrepreneurship, agrotourismand/or ICT sectors developed by the project Target: 3 by 2023 Baseline: 0 (2020) Source: Study reports; Project progress reports Indicator 2.2.b: Evidence of policymakers’ utilizing data and evidence generated by the project while designing and/or implementing relevant policies/programmes aimed at women’s economic empowerment Target: at least three policies/programmes by 2023 Baseline: 0 (2020) Source: Study reports; Project progress reports Indicator 2.2.c: Number of policymakers and public servant with increased capacities in the area of women’s economic empowerment Target: 50 by 2023 Baseline: 0 (2020) Source: Training participants list and training evaluations documented through project progress reports |  |
| Activity 2.2.1. To generate and disseminate data and knowledge on women’s opportunities and challenges in entrepreneurship, agrotourismand/or ICT sectors to support evidence-based decision-making |  |
| Activity 2.2.2. To support evidence-based legislative and policy level work on development of gender sensitive agrotourismand ICT sectors |  |
| Activity 2.2.3. To promote public-private dialogue and partnerships for improving women’s access to technologies and markets |  |
| Activity 2.2.4. To support government bodies working in tourism and ICT sectors (Georgian National Tourism Administration (GNTA) and Open Net (and/or Communications Commission) to conduct Participatory Gender Audits and follow-up to its findings |  |
| Activity 2.2.5. Explore opportunities for conducting Gender Impact Assessment/s of selected state programmes relevant for ICT (for example, National Innovations Ecosystem Program of GITA) and/or agrotourismsectors |  |
| Activity 2.2.6. To support relevant government entities (Georgian Innovations and Technology Agency and Enterprise Georgia, among others) to design and implement action plans / policy measures and projects to address the identified gender gaps |  |
| Activity 2.2.7. To strengthen capacity of policymakers and public servants of targeted institutions (GNTA; GITA; Enterprise Georgia; Open Net/Communications Commission) in the area of women’s economic empowerment |  |
| Output 2.3 of the project and its corresponding indicators fall under UN Women Georgia CO SN/AWP Output 2.1.1. Women, particularly poor and socially excluded, use skills, economic opportunities, and relevant information to be (self-)employed and/or start/develop their businesses |  |
| Output 2.3: Women have increased confidence, skills and resources to utilize income-generation opportunities in the agrotourismand ICT sectors and related value chains | Output 2.3 assumptions/risks: - Vulnerable groups of women who are awarded job and educational opportunities can pursue these opportunities without obstacles due to discriminatory gender norms and expectations - There is sufficient interest among private sector to increase women business enterprises in their supply chains - Women beneficiaries of small grants equally benefit from the business management and skills training to ensure that their business growth is sustainable |
| Output 2.3 indicators/target/baseline/source: Indicator 2. 3 a: Number of women entrepreneurs receiving technical assistance from UN Women with increased skills in business and leadership-related topics because of the project Target: 200 new (altogether 601) by 2023 Baseline: 401 (2020) Source: Project progress reports Indicator 2.3 b: Number of women with access to new grants, investment, or other productive resources for entrepreneurial activities as a result of the project Target: 100 new (altogether 281) by 2023 Baseline: 181 (2020) Source: Project progress reports; Human stories Indicator 2.3 c: Number of self- help groups (SHGs) formed for vulnerable groups of women to increase their access to decent work and sustainable livelihoods Target: 20 new (altogether 72) by 2023 uniting to at least 160 new women (altogether 584) Baseline: 52 uniting 424 women Source: Project progress reports |  |
| Activity 2.3.1. To provide technical, business skills, management and leadership trainings to current and aspiring women entrepreneurs in ICT and agrotourismsectors |  |
| Activity 2.3.2. To upgrade women entrepreneurs’ agrotourismproduct packages, brands, and marketing strategies |  |
| Activity 2.3.3. To use social mobilization to form self-help groups for vulnerable groups of women to faciliate their access to engagement in agrotourismor ICT sectors or related value chains |  |
| Activity 2.3.4. To increase women-owned agrotourismbusinesses’ access to, knowledge of and presence in digitals platforms |  |
| Activity 2.3.5. To provide funding to women entrepreneurs for expanding their businesses and improving their market presence, social and environmental impact |  |
| Activity 2.3.6. To support peer-to-peer learning and empowerment through expanding women’s support networks, linking women in mentoring relationships and implementing exchange visits |  |
| Activity 2.3.7. To raise public awareness among rural women on agrotourismand ICT sector opportunities |  |
| Activity 2.3.8. To provide scholarships, internships and other specialized skill building opportunities to women for engaging in agrotourismand ICT |  |
| Activity 2.3.9. To advise women entrepreneurs in the identification and management of business risks and contingency planning |  |
| Activity 2.3.10. To support women’s engagement in advocacy initiatives on opportunities in the agrotourismand ICT sectors |  |
| Activity 2.3.11. To explore the opportunity of developing an e-commerce platform for women entrepreneurs |  |

## Annex 10 Terms of Reference

International Consultant / National Evaluator for the Final Evaluation of the UN Women Project “Good Governance for Gender Equality in Georgi (GG4GEG)”

Terms of Reference

Background

UN Women, grounded in the vision of equality enshrined in the Charter of the United Nations, works for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security.

UN Women supports UN Member States as they set global standards for achieving gender equality and works with governments and civil society to design laws, policies, programmes and services needed to implement these standards. It stands behind women’s equal participation in all aspects of life, focusing on five priority areas: increasing women’s leadership and participation; ending violence against women; engaging women in all aspects of peace and security processes; enhancing women’s economic empowerment; and making gender equality central to national development planning and budgeting. UN Women also coordinates and promotes the UN system’s work in advancing gender equality.

Although many positive results have been achieved since Georgia began actively working on accelerating gender equality laws and policies in 1994 (CEDAW ratification year), significant challenges remain in formal as well as informal policies, practices and procedures across state institutions as well as public sector that hinder the achievement of substantive gender equality. To enhance good governance and democratic development of Georgia and to strengthen the private sector’s role in women’s economic empowerment, UN Women Georgia Country Office launched a project Good Governance for Gender Equality in Georgia (GG4GEG) with the support of the Norwegian Ministry of Foreign Affairs. The project started in 1st of September 2019 and runs for 45 months with an end date in 31st of May, 2023. The total budget of the project is USD 4,224,915.

The overarching goal/impact of the GG4GEG project is to ensure that Governance systems, programmes, and policies along with private sector partners are gender sensitive and enable women’s economic empowerment and broader gender equality in Georgia. The project consists of two components linked to two outcomes of the project. Under the first component, the project aims to ensure that Governance systems are gender sensitive and enable gender equality in Georgia (Outcome 1) and delivers on the following three key outputs: 1. Gender equality and gender mainstreaming are institutionalized at the national and local levels; 2. Gender mainstreaming capacities are developed and sustained at the national and local levels; and 3. More and better-quality data and analysis are available to promote and track the progress of gender equality and women’s empowerment. The proposed theory of change for the first outcome is as follows: if (1) gender equality and gender mainstreaming are institutionalized at national and local levels; and (2) gender mainstreaming capacity is developed and sustained at national and local levels; and (3) more and better-quality data and analysis are available to promote and track the progress of gender equality and women’s empowerment; then (4) governance systems will be strengthened for gender equality; because (5) institutional mechanisms and policymaking processes and patterns will become gender-sensitive and gender-aware. This component of the project started in 1st of September 2019 and runs for 45 months with an end date in 31st of May 2023.

Under its second component, the project aims to to ensure that women in rural areas benefit from increased income-generation opportunities in the agritourism and ICT sectors and fully realize their economic rights with the support of a gender-responsive private sector (Outcome 2). Under this Outcome, the project delivers on the following three outputs: 1. Businesses have an increased understanding of the Women’s Empowerment Principles (WEPs) and have the skills to implement measures that benefit women, specifically in rural areas; 2. Policymakers and public agencies have increased capacities to identify and address challenges faced by women entrepreneurs in agritourism and ICT; and 3. Women have increased confidence, skills and resources to utilize income-generation opportunities in the agritourism and ICT sectors and related value chains. The Theory of Change for the second outcome of the GG4GEG project is: If (1) Businesses have increased understanding of Women’s Empowerment Principles (WEPs) and skills to implement measures that benefit women, specifically in rural areas; and if

(2) Policymakers and public agencies have increased capacities to identify and address challenges faced by women entrepreneurs in agritourism and ICT; and if (3) Women have increased confidence, skills and resources to utilize income generation opportunities in the agritourism and ICT sectors, then (4) women in rural areas benefit from increased income generation opportunities in the agritourism and ICT sectors in Georgia, because (5) the private, public and civil society sectors take actions to create an enabling environment for rural women’s economic empowerment. This Women’s Economic Empowerment (WEE) component of the project started in 1st of June 2021 and ends in 31st of May 2023 (as a result of the Donor Agreement Amendment #1).

Under the first outcome, the key state partners of the project in Georgia are: the Gender Equality Council of the Parliament and relevant legislative committees; the newly created Inter-Agency Commission for Gender Equality in the Prime Minister’s Office, Public Defender’s Office and GEOSTAT; The target groups of the project are the public servants, especially those responsible for planning and budgeting on the national level – more specifically, those within the Prime Minister’s Office, the Civic Service Bureau, the Ministry of Finance and all other ministries through their affiliation in the Inter-Agency Commission, as well as the local governments of all 64 municipalities and 5 self-governing cities. The key benefits of the action for the primary target group include increased knowledge and individual and institutional capacities in gender equality and gender mainstreaming (using GRB, GIA and PGA methodologies) to carry out decentralization, civil service and public finance reforms in line with Georgia’s international and national commitments in the field of women’s rights and gender equality. The intervention also targets gender advocates, experts, academia and civil society organizations (as secondary target groups) by deepening their knowledge and expertise in the selected gender mainstreaming tools and methodologies, such as Gender Responsive Budgeting (GRB), Gender Impact Assessment (GIA) and Participatory Gender Audit (PGA).The ultimate beneficiaries of the project are socially excluded groups of women and men who, in the long run, will benefit from more transparent and coherent planning and budgeting processes, as well as from better informed civil servants equipped with more sensitive gender approaches to the diverse needs of women, men, boys and girls.

Under the second Outcome the project works with three key target groups: 1. Private businesses interested in increasing their contributions to the SDGs, their accountability and women’s economic empowerment by promoting gender equality in the workplace, marketplace and community (over 150 companies’ signatories of UN Women Women’s Empowerment Principles: Equality Means Business (WEPs) as of October 2022). 2. Government bodies / public entities responsible for an enabling environment for businesses development, especially agrotourism and ICT sectors’ growth and equal opportunities therein such as the Ministry of Economy and Sustainable Development and its entities (Enterprise Georgia, Georgia’s Innovation and Technology Agency, etc.). 3.Women in Georgia, especially those residing in rural areas, supporting their skills building to access decent work and/or grow their agritourism-related businesses.

Purpose and the Use of Evaluation

Upon the project completion , as established in the Project Document, a mandatory external final evaluation is to be conducted by UN Women for accountability and learning purposes. This final evaluation will take place towards the end of the implementation of the intervention (December 2022 – April 2023) and its main purpose is assessing the achievement of project results and performance of the above- described interventions. Findings of the final external evaluation will inform UN Women Georgia’s future work in the areas of governance and participation in public life and women’s economic empowerment. The external evaluation will further identify lessons learned, best practices and challenges of the GG4GEG project and will greatly inform the development of the follow-up programmatic interventions.

The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for women’s empowerment in Georgia and to facilitate UN Women’s strategic reflection and learning for programming in the area.

The information generated by the evaluation will be used by different stakeholders to:

- Contribute to building of the evidence base on effective strategies for gender sensitive governance system and economic empowerment of women

- Facilitate strategic reflection, learning and further planning for programming in the areas of governance and participation in public life and economic empowerment of women

- Strengthen national stakeholders and structures with the aim to increase sustainability of the results beyond the project

Main evaluation users include UN Women Country Office in Georgia as well as Government of Norway (project donor). Furthermore, national stakeholders – civil society partners, Parliamentary counterparts and targeted state and non-state agencies will be also closely involved in the evaluation process to increase ownership of findings, draw lessons learned and make and greater use of this final evaluation results.

Evaluation Objectives, Criteria and Questions

The specific evaluation objectives are as follows:

- Analyze the relevance of the implementation strategy and approaches of the “Good Governance for Gender Equality in Georgia” project;

- Assess effectiveness and organizational efficiency in progressing towards the achievement of the project’s results as defined in the interventions;

- Validate the project results in terms of achievements and/or weaknesses toward the outcome and outputs;

- Determine the impact of the intervention with respect to gender equality and women’s empowerment;

- Assess the sustainability of the results achieved by the project;

- Document lessons learned, best practices, success stories and challenges to inform future work of UN Women and the Norwegian Ministry of Foreign Affairs in the areas of governance and participation in public life and economic empowerment of women;

- Identify strategies for replication and up-scaling of the project’s best practices;

- Provide actionable recommendations for future programmatic developments and maximize ownership by partners in the country covered by the project;

- To assess how the project and its results relate and contribute to commitments and achievement of Sustainable Development Goals (SDGs) in Georgia.

The evaluation will address the criteria of Project Relevance, Effectiveness, Efficiency, and Sustainability. More specifically, the evaluation will address the key evaluation questions:

- Relevance: A) How does the project reflect and align with gender equality national strategic plans and normative frameworks as well as Georgia’s international obligations and commitments? B) Is the project design based on quality analysis, including gender and human rights-based analysis, risk assessments, socio-cultural and political analysis? C) Were the programmatic strategies appropriate to address the identified needs of beneficiaries?

- Coherence: A) To what extent the project adheres to corporate strategic priorities of UN Women and the UN Women CO Strategic Note? B) Is the project achieving synergies between the larger UN Women’s portfolios and the work of the UN Country Team? C) Is the project achieving synergies between UN Women and key national stakeholders including national governments and CSOs? D) How does the project design match with the complexity of national structures, systems and decision- making processes?

- Effectiveness: A) What has been the progress made towards achievement of the expected outcomes and expected results? What are the results achieved? B) What are the reasons for the achievement or non-achievement of the project results? C) Does the project have effective monitoring mechanisms in place to measure progress towards results? D) What is the influence of the specific country context and circumstances on the achievement of results and operational effectiveness? F) How adaptable and rapidly does the project react to changing situations? G) Has the project achieved any unforeseen results, either positive or negative? For whom? H) What are the good practices and the obstacles or shortcomings encountered? How were they overcome? I) To what extent have capacities of relevant duty-bearers and rights-holders been strengthened? J) What -if any- types of innovative good practices have been introduced in the project for the achievement of WEE results?

- Efficiency: A) Have resources (financial, human, technical support, etc.) been allocated strategically to achieve the project outcomes? B) Have the outputs been delivered in a timely manner? C) To what extend were relevant stakeholders and actors included in the project planning and implementation?

- Sustainability A) How effectively has the project been able to contribute to the generation of national ownership of the project outputs? B) What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time after the project phase out? C) To what extend has the project identified strategic partners that could pick up on supporting continued government and non-governmental action when the project comes to an end? D) Do national/local institutions demonstrate leadership commitment and technical capacity to continue to replicate some project activities? E) To what extend have the project’s exit strategy been well planned and successful? F) To what extend has UN Women been able to promote replication of project successes?

The questions outlined above are preliminary and are expected to be revised and refined by the evaluation team during the inception phase of the evaluation.

Scope of the Evaluation

The final evaluation of the project is to be conducted externally by an international external consultant/evaluator in a team with two national consultants/assistant evaluators. It is planned to be completed in 40 working days in the period of 28 December 2022 – 5 May 2023.

The final evaluation will include all aspects of the project and will cover almost the full project implementation period starting from September 1, 2019 till the end of March 2023.

Evaluation Design, Process and Methods

The evaluation methodology will be mixed (quantitative and qualitative research methods and analytical approaches) to account for complexity of gender relations and to ensure participatory and inclusive processes that are culturally appropriate. A theory of change approach will be followed, and the consultants is expected to reconstruct, validate, and identify the gaps in the project’s theories of change (for each of the Outcomes). The reconstructed theories of change should elaborate on following how GG4GEG project has contributed to creating an enabling legislative, policy, institutional and economically enabling environment in line with internationally binding standards on gender-sensitive governance systems and women’s economic empowerment in Georgia. Assumptions should be tested and explain both the connections between early, intermediate, and long-term project outcomes and the expectations about how and why the project has brought them about. By reconstructing the Theories of Change evaluators are also expected to identify challenges and gaps in the implementation of the project for future improvement. Hence an eventual next phase of the project will benefit from a refined and tested Theories of Change.

Interviews and focus group discussions with all key stakeholders involved in the project implementation, including but not limited to GG4GEG project team, government partners, NGO partners, beneficiaries, etc. shall also take place.

The evaluation team should develop a sampling frame (area and population represented, rationale for selection, mechanism of selection, limitations of the sample) and specify how it will address the diversity of stakeholders in the intervention. The evaluation team should take measures to ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights; for example, the limitations of the sample (representativeness) should be stated clearly and the data should be triangulated (cross-checked against other sources) to help ensure robust results. The evaluation process is divided in four phases: 1) Preparation, mainly devoted to structuring the evaluation approach, establishing reference group, preparing the TOR, compiling project documentation, and recruitment of the evaluation team; 2) Conduct, which involves reconstruction of theory of change, organizing inception meetings, drafting inception report and finalization of evaluation methodology, data collection and analysis, including desk research and preparation of interviews and focus groups, preparation of field missions and visits to project sites (data collection in the field will be implemented by national consultants based on the clear and specific guidelines from the international consultant); 3) Reporting, focusing on presentation of preliminary findings, developing draft and final reports; and 4) Use and follow-up, which will entail the development of management response by UN Women team and follow-up to the implementation of the management response.

The consultant will be responsible only for Conduct and Reporting phases.

  - Conduct phase: at the beginning of the consultancy, the consultant will be provided with key sources of information for an initial desk review. The online inception meetings will be conducted with GG4GEG team. In this phase an inception report that will include the refined evaluation methodology including data collection plan and instruments will be delivered. The inception report will be validated and approved by UN Women. Based on the inception phase, the consultant will carry out further in- depth desk review. Data collection will be carried out jointly by the international and national consultants. Online or face-to-face interviews and focus group discussions with key stakeholders, as relevant, will take place. Field missions will be conducted by international and national consultants jointly in line with data collection plan and instruments developed by the international consultant, while international consultant can also interview major English-speaking project partners online.

  - National consultants will provide summaries of interviews in English to the consultant in line with the pre-agreed format and the international consultant will carry out further analysis.

  - Reporting phase: The collected information will be analyzed and final evaluation report will be delivered. A validation meeting will be organized where the consultant will validate the final report with UN Women and Evaluation Reference Group (ERG) and submit for approval by UN Women.

UN Women’s Independent Evaluation Service (IES) has developed the GERAAS, which has adapted UNEG Standards for Evaluation in the UN System to guide evaluation managers and evaluators on what constitutes a ‘good quality’ report at UN Women. All evaluations in UN Women are annually assessed against the framework adopted in GERAAS and hence the consultant should be familiar with GERAAS quality standards.

In addition, UN Women is an UN-SWAP reporting entity and the consultant will take into consideration that all the evaluation in UN Women are annually assessed against the UN-SWAP Evaluation Performance Indicator and its related scorecard. The evaluation will be conducted in accordance with UN Women evaluation guidelines and UNEG Norms and Standards for evaluation and the UNEG Code of Conduct for Evaluations in the UN System.

Stakeholders Participation and Evaluation Management Structure

The evaluation will be a consultative, inclusive and participatory process and will ensure the participation of stakeholders engaged in the implementation of the project.

The evaluation will be Human Rights and Gender responsible and an Evaluation Reference Group (ERG) will be established.

The Evaluation Reference Group is an integral part of the evaluation management structure and is constituted to facilitate the participation of relevant stakeholders in the design and scope of the evaluation, raising awareness of the different information needs, quality assurance throughout the process and in disseminating the evaluation results. The Evaluation Reference Group will be engaged throughout the process and will be composed of relevant representatives of state and non-state stakeholders. The ERG group will review the draft evaluation report and provide substantive feedback to ensure quality and completeness of the report and will participate in the inception and validation meeting of the final evaluation report.

The UN Women Georgia Monitoring and Evaluation Focal Point will serve as the Evaluation Task Manager, who will be responsible for day-to-day management of the evaluation and ensure that the evaluation is conducted in accordance with the sister entities Evaluation Policies, United Nations Evaluation Group Ethical Guidelines and Code of Conduct for Evaluation in the United Nations system and other key relevant guidance documents. The evaluation process will be supported by the UN Women Europe and Central Asia Regional Evaluation Specialist.

Coordination in the field including logistical support will be the responsibility of UN Women.

Within six weeks upon completion of the evaluation, UN Women has the responsibility to prepare a management response that addresses the findings and recommendations to ensure future learning and inform implementation of relevant projects.

This is a consultative/participatory final project evaluation with a strong learning component. The management of the evaluation will ensure that key stakeholders are consulted.

The international consultant will lead the evaluation in close coordination with two (2) national consultants.

Description of Responsibilities

- To conduct inception meetings/interviews with GG4GEG staff and elaborate and submit the detailed inception report which contains evaluation objectives and scope, desk review, description of evaluation methodology / methodological approach, data collection tools, data analysis methods, key informants/agencies, evaluation questions, performance criteria, issues to be studied, work plan and reporting requirements. It should include a clear evaluation matrix linking all these aspects;

- To elaborate and finalize the data collection plan (outlining the roles of international and national consultants) and data collection tools (e.g. guides and questionnaires) individually designed for each respondent/group of respondents to be used during the interviews and focus-groups with the key informants/interviewees;

- To conduct individual interviews and focus groups discussions with the relevant stakeholders online and face-to-face with the support and together with national consultants;

- To analyze the data and reconstruct, validate, and identify the gaps in the project’s theory of change based on the research findings;

- To prepare a Power Point Presentation and an outline on preliminary findings and present to ERG and reflect the feedback shared at this presentation in the final report;

- To produce and submit the draft and final evaluation reports in English. Format of the final evaluation report shall include the following chapters: Executive Summary, Project description, Evaluation purpose, Evaluation methodology, Findings, Lessons learned, Recommendations and Annexes (including interview list - without identifying names for confidentiality, data collection instruments, key documents consulted, Terms of Reference).

Deliverables:

- Detailed Inception Report, which contains evaluation objectives and scope, findings from inception meetings with all relevant stakeholders, initial desk review, description of evaluation methodology/methodological approach, data collection plan and tools, data analysis methods, key informants/agencies, evaluation questions, performance criteria, issues to be studied, work plan and reporting requirements. It should include a clear evaluation matrix linking all these aspects - by 30 January 2023 (10 working days, home-based)

- Data collected through interviews and focus group discussions - by March 10, 2023 (10 working days in Georgia –fieldwork will be carried out by international consultant and national consultants jointly in line with the agreed guidelines)

- Data analyzed and Power Point Presentation on preliminary findings conducted to highlight key evaluation findings and conclusions, lessons learnt and recommendations - by March 27, 2023 (5 working days home-based)

- Draft Evaluation report that reflects key findings, conclusions and recommendations and deployed methodology (indicative samples will be provided by UN Women) in English taking into consideration comments and feedback collected from the presentation of preliminary findings. The report shall include the following chapters: Executive Summary, Introduction and Background, Evaluation approach and methodology, Findings, Conclusions, Lessons learnt, Recommendations and relevant Annexes - by April 28, 2023 (14 working days, home based).

- The evaluation team has to submit the initial draft of the evaluation report to Evaluation Reference Group after 10 working days – by April 17, 2023 and use the additional 4 days to address ERG comments/feedback and resubmit the final version to the Evaluation Task Manager) – by April 28,2023.

- Evaluation brief that reflects key findings, conclusions and recommendations and deployed methodology (indicative samples will be provided by UN Women) – by May 10, 2023 (1 working day).

The WEE component builds on the implementation of the 37-month project “A Joint Action for Women’s Economic Empowerment in Georgia” (JAWE) in 2017-2020 with the generous support of the Norwegian Ministry of Foreign Affairs (total budget of USD 3,114,823.10). The project focused on the grassroots social mobilization work and support to women’s employment and entrepreneurship through integration of Women’s Empowerment Principles (WEPs) at the private sector in order to increase the responsibility of private enterprises for achievement of gender equality and women’ economic empowerment in the country.

SDG 5.1.1: Whether or not legal frameworks are in place to promote, enforce and monitor equality and non-discrimination on the basis of sex.

Proportion of countries with systems to track and make public allocations for gender equality and women’s empowerment and facilitate tracking and, hence, accountability of public budget allocation to gender equality and women’s empowerment.

(a) Proportion of total agricultural population with ownership or secure rights over agricultural land, by sex

The WEE component builds on the implementation of the 37-month project “A Joint Action for Women’s Economic Empowerment in Georgia” (JAWE) in 2017-2020 with the generous support of the Norwegian Ministry of Foreign Affairs (total budget of USD 3,114,823.10). The project focused on the grass root social mobilization work and support to women’s employment and entrepreneurship through integration of Women’s Empowerment Principles (WEPs) at the private sector in order to increase the responsibility of private enterprises for achievement of gender equality and women’ economic empowerment in the country.

The complexity and significance of partnerships is reflected in more detail in Annex 3 Stakeholder Analysis

Rapid Gender Assessment of COVID-19 Situation in Georgia - 2 wave, at https://georgia.unwomen.org/en/digital-library/publications/2021/03/rapid-gender-assessment-of-covid-19-situation-in-georgia-2-wave

UN Women Georgia, GG4GEG project annual report to donor, 2021

European Commission, Opinion on the EU membership application by Georgia, memo, 17 June 2022

Statement of the United Nations in Georgia on the draft Law on Transparency of Foreign Influence, made on February 26 2023, retrieved on April 27 2023 from https://www.undp.org/georgia/news/un-statement-on-draft-law-on-transparency-of-foreign-influence#:~:text=February%2026%2C%202023&text=The%20United%20Nations%20in%20Georgia%20expresses%20profound%20concern%20that%20the,they%20make%20to%20Georgian%20democracy

Voluntarily National Review, Georgia (2020) , retrieved on February 26  2023 from https://hlpf.un.org/sites/default/files/vnrs/2021/26390VNR_2020_Georgia_Report.pdf

In 2020, with overall score of 71.88 (out of 100), Georgia ranked 58 out of 193 countries

Some key results: the 2010 Law on Gender Equality (2010) established the first national gender equality machinery at the parliamentary level;  the 2014 Law on the Elimination of All Forms of Discrimination (Anti-Discrimination Law) mandated the Public Defender’s Office (PDO) with its implementation authority (through judiciary);  the following state strategies and respective action plans have laid an important ground work for women’s empowerment: the 2014-2020 Human Rights Strategy and subsequent action plans, including the 2018-2020 National Action Plan (NHRSAP) which also introduced the chapter on equality policy and combating discrimination; NAP on Combating Violence against Women and Domestic Violence and Measures to be implemented for the Protection of Victims (Survivors) (VAWG/DV NAP) and the NAP for the Implementation of the UN Security Council Resolutions on Women, Peace and Security (WPS NAP); in 2019, Georgia passed the amendments to the Labour Code and Administrative Violations Code making sexual harassment legally punishable at workplace and in public spaces.

Voluntarily National Review, Georgia, 2020, retrieved on February 26 from https://hlpf.un.org/sites/default/files/vnrs/2021/26390VNR_2020_Georgia_Report.pdf

Written Submission for 84th session of the Committee on the Elimination of Discrimination against Women (CEDAW) by the Public Defender of Georgia, submitted on January 9, 2023, retrieved on February 26 2023 from https://www.ombudsman.ge/eng/190821112029siakhleebi/sakhalkho-damtsvelma-gaeros-kalta-mimart-diskriminatsiis-aghmofkhvris-komitets-alternatiuli-angarishi-tsarudgina

United Nations (July 24 2014). CEDAW Concluding observations on the combined fourth and fifth periodic reports of Georgia Adopted by the Committee at its fifty-eighth session (30 June-18 July 2014), retrieved on February 26 2023 from https://digitallibrary.un.org/record/779007?ln=en

Voluntarily National Review, Georgia, 2020, retrieved on February 26 2023 from https://hlpf.un.org/sites/default/files/vnrs/2021/26390VNR_2020_Georgia_Report.pdf

Sustainable Development Report 2022, retrieved on February 26 2023 from https://dashboards.sdgindex.org/profiles/georgia

National Association of Local Authorities of Georgia (March 2021). Decentralization and local public administration reform in Georgia (a report), retrieved on February 15 2023 from https://platforma-dev.eu/wp-content/uploads/2021/10/Status-Report-Decentralisation-and-Local-Public-Administration-Reform-in-Georgia.pdf

UN Women (2021).  The Georgia Country Gender Equality Profile (CGEP), retrieved on February 26 from https://georgia.unwomen.org/en/digital-library/publications/2021/11/country-gender-equality-profile-of-georgia_georgia

In 2020, the Parliament approved amendments to the Election Code of Georgia requiring political parties to include one member of the opposite sex for every four members in the election lists that are submitted to the Central Election Commission.

6th periodic report submitted by Georgia under article 18 of the Convention, due in 2018 (2021), §18-19, Convention on the Elimination of All Forms of Discrimination against Women, retrieved on May 6 2023 from https://digitallibrary.un.org/record/3927020?ln=en

Agriculture represents an important sector of the Georgian economy employing 50.89 % of the active population, 54.13 % of which are women, however, the only data responding to the indicator are reported in the GEOSTAT publication Women and Men in Georgia 2018, according to which in 2015, 37.7 % of landowners were women and 62.3 % were men.

FAO (Food and Agriculture Organization of the United Nations). 2018. “Gender, Agriculture and Rural

Development in Georgia.” Country Gender Assessment Series. Retrieved in February 26 2023 from http://www.fao.org/documents/card/en/c/CA0577EN/.

Parliament of Georgia (2019). Thematic Inquiry on Women’s Participation in State Economic Programmes, available in Georgian, retrieved on May 5 2023 from https://web-api.parliament.ge/storage/files/shares/tematuri-mokvleva/genderuli/mainstreaming/angarishi-meinstrimingi.pdf

National Statistics Office of Georgia, Women and Men in Georgia (Statistical Publication), Tbilisi, 2021, retrieved on February 26 2023 from https://www.geostat.ge/media/41855/WOMEN-AND-MEN-IN-GEORGIAN_-2021.pdf

UN Women (2021).  The Georgia Country Gender Equality Profile (CGEP), retrieved on February 26 2023 from https://georgia.unwomen.org/en/digital-library/publications/2021/11/country-gender-equality-profile-of-georgia_georgia

The same as above

United Nations (July 24 2014). CEDAW Concluding observations on the combined fourth and fifth periodic reports of Georgia Adopted by the Committee at its fifty-eighth session (30 June-18 July 2014), retrieved on February 26 2023 from https://digitallibrary.un.org/record/779007?ln=en

The same as above

United Nations (2020). United Nations Disability Inclusion Strategy, retrieved on March 15 2023 from https://www.un.org/en/content/disabilitystrategy/assets/documentation/UN_Disability_Inclusion_Strategy_english.pdf

Voluntarily National Review, Georgia (2020) , retrieved on January 30 2023 from https://sustainabledevelopment.un.org/content/documents/26390VNR_2020_Georgia_Report.pdf

Draft Public Finance Management Reform Strategy 2023-2026

UN Women (2020). Country Gender Equality Profile, retrieved on February 26 2023 from https://georgia.unwomen.org/sites/default/files/Field%20Office%20Georgia/Attachments/Publications/2020/Country%20Gender%20Equality%20Profile%20of%20Georgia.pdf

There 12 areas include the following: women and poverty; the education and training of women; women and health; violence against women; women and armed conflict; women and the economy; women in power and decision-making; women and the media; women in agriculture and the environment; and the girl child. The eleventh and twelfth areas - institutional mechanisms and the human rights of women - are considered cross-cutting for all ten areas.

The summary of findings from assessment of each area of BPfA may be found in briefs prepared under the project: Brief on Women in Decision-Making, Brief on Women, Peace and Security, Brief on Institutional Mechanisms for the Advancement of Women in Georgia, Brief on Violence against women in Georgia, Brief of Women with Disabilities in Georgia, Brief on Women in the Rural Economy in Georgia, Brief on Employment and Gender in Georgia, Brief on Unpaid Care Work in Georgia, Brief on Women and Poverty in Georgia, Brief on Women and Social Protection in Georgia, Brief on Women’s Economic Inactivity in Georgia.

CEDAW Committee, Concluding Observations on the Combined Fourth and Fifth Periodic Reports of Georgia, 2014, para. 28.

Embedding Diversity, Equity and Inclusion into the Women’s Empowerment Principles: A Manual for Signatory Companies. Tbilisi, Georgia, December 2022

Public Defender’s Office (2022). Assessment of the Needs of Women and Girls with Disabilities and the State of Protection of their Rights in Georgia, a special report. Retrieved on February 27 2023 from https://www.ombudsman.ge/eng/190306081201spetsialuri-angarishebi/shezghuduli-shesadzleblobis-mkone-kalebisa-da-gogoebis-sachiroebebisa-da-mati-uflebebis-datsvis-mdgomareobis-shefaseba-sakartveloshi ; UN Women

CRRC, GEOSTAT (November 2022). National Assessment of Women’s Entrepreneurship Development (WED) (in design)

UN Women (January 2023). Research on Women’s Participation in Technology in Georgia. Tbilisi, Georgia (in design)

UN Women (2021). Workplace Sexual Harassment in the Civil Service in Georgia, retrieved on April 5 2023 from https://georgia.unwomen.org/sites/default/files/Field%20Office%20Georgia/Attachments/Publications/2021/Workplace%20Sexual%20Harassment%20in%20the%20Civil%20Service%20in%20Georgia%20ENG%20renewed.pdf ;and

UN Women (2022).  Investigating Workplace Sexual Harassment Cases with a Victim-centered Approach, retrieved on April 5 2023 from  https://georgia.unwomen.org/sites/default/files/2022-12/Manual%20-%20Investigating%20Workplace%20SH%20Cases%20with%20a%20Victim-centered%20Approach.pdf

United Nations (July 24 2014). CEDAW Concluding observations on the combined fourth and fifth periodic reports of Georgia Adopted by the Committee at its fifty-eighth session (30 June-18 July 2014), retrieved on February 26 2023 from https://digitallibrary.un.org/record/779007?ln=en

UN Women, ISET-PI (2022). Gender Impact Assessment of the Vocational Education Support Programme for IDPs and Ecomigrants and the Self-Employment Support Grant Programme, retrieved on April 5 2023 from https://georgia.unwomen.org/en/digital-library/publications/2022/12/gender-impact-assessment-of-vocational-education-support-and-self-employment-support-grant-programmes

SDG 5.1.1: Whether or not legal frameworks are in place to promote, enforce and monitor equality and non-discrimination on the basis of sex.

a) Proportion of total agricultural population with ownership or secure rights over agricultural land, by sex) and gender -sensitivity of financial instruments to increase participation of women in startups and other entrepreneurship activities

Georgia joined the Equal Pay International Coalition (EPIC) in 2021

Joint Shadow Report on the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW). To be presented to the UN Committee on the Elimination of Discrimination against Women. Prepared by 29 civil society organizations working on gender equality and women’s empowerment in Georgia. Tbilisi, 2021, Georgia

See Annex 6

The list of documents includes PAR Strategy 2026 and PAR Action Plan 2023-2024; Gender Equality Strategy for the Civil Service Bureau; Draft Public Finance Management Reform Strategy 2023-2026; National Action Plan on Combating Violence against Women and Domestic Violence and Measures to be Implemented for the Protection of Victims; National Action Plan on the Implementation of UN Security Council Resolution 1325; National Strategy for Human Rights Protection for the years 2022-2030

UN Women, PwC (2021). Baseline Study on the Impact of the Women’s Empowerment Principles (WEPs) on Businesses in Georgia.  Tbilisi, Georgia

UN Women, PwC (2021). Baseline Study on the Impact of the Women’s Empowerment Principles (WEPs) on Businesses in Georgia.  Tbilisi, Georgia.

WEPs companies’ survey conducted by UN Women project in 2022

In addition, The WEPs Secretariat was set up and is led by the WEPs Coordinator (UN Women), who is responsible for the coordination of the WEPs community and is in charge of facilitating membership, partnerships and initiatives, administrative arrangements, knowledge collation and dissemination, coordination and reporting.

According to the information provided by Enterprise Georgia, in micro grants programmes 50% of participants are women; at the same time in the loan scheme, there are only 30%-35% of women

Gender Equality Action Plan of the Prosecutor's Office of Georgia 2022 - 2024

Monitoring Group around Generation Equality that is co-led by the GEC and CGE and unites Ambassadors of Norway, Sweden, European Union and France along with UN Resident Coordinator, and UN agencies

The number of municipalities in Georgia that have acceded to the Charter increased from 4 in 2018 to 21 in 2022 constituting 33 % of the total of 64 municipalities.

On 22 and 23 September 2022, CEOs from the WEPs signatory companies gathered on the workshop to discuss the challenges related to the gender equality within their companies and communities. The session was held in Men Talking to Men format, which implies that the session is only attended by the male participants. As a result of the workshop, the participants, in total 18 male CEOs and Deputy CEOs, committed for proactive and consistent integration of gender equality in all aspects of their corporate work.

# Target 17.17: encourage and promote effective public, public- private, and civil society partnerships, building on the experience and resourcing strategies of partnerships

##### By 2020, enhance capacity-building support to developing countries, including for least developed countries and small island developing States, to increase significantly the availability of high-quality, timely and reliable data disaggregated by income, gender, age, race, ethnicity, migratory status, disability, geographic location and other characteristics relevant in national contexts

See more at https://emerging-europe.com/future-of-ee-awards/shortlist/

The information about the action is available at www.unstereotype.ge

Reconstructed ToC incorporates assumptions that support validity of pathways (Output Output and Output Outcome level)

Measures the proportion of a country’s female working-age population (15-64) that engages actively in the labor market, either by working or looking for work. Labor force data does not consider workers employed abroad.

GEOSTAT, Gender Statistics Portal, 2019 data, UN Women calculations  http://gender.geostat.ge/gender/index.php?action=Employment%20and%20Unemployment

Note: Georgia has changed the calculation of labour participation methodology and updated LFS. The change has reduced both female and male economic participation rates.

UN Women conducted Comprehensive Gender Assessment of National Statistical System in 2018 that found that the fact that there has never been carried out a time-use survey in Georgia resulted in a lack of data on time spent on unpaid and paid work (needed for evidence-based policymaking and as an input to SDG indicator 5.4.1).

UN Women SN/AWP indicator 2.1.2.A

This activity will cover women in Tbilisi Administered Territories of Georgia as well as women residing in Abkhazia, Georgia. UN Women Georgia Country Office has established its presence in Sukhumi back in 2017 and has full capacity to administer and implement project activities across whole Abkhazia.