Final Evaluation of THE “WOMEN AND GIRLS ACCESS TO JUSTICE THROUGH EFFECTIVE, ACCOUNTABLE AND GENDER-RESPONSIVE INSTITUTIONS” (ACCESS TO JUSTICE) PROJECT

UN Women Photo Gallery: Launch of the one of the Knowledge tools; The Multi sectoral Training Manual 2021

March 2023

By Paul Bukuluki and Sydey Etima Ojara

# ACRONYMS

A2J       	Access to Justice

ADA		Austrian Development Agency

AJP		Administration of Justice Programme

CEDAW	Convention on the Elimination of Discrimination Against Women

CSO 		Civil Society Organisation

DGAL		Directorate of Government Analytical Laboratory

DVA		Domestic Violence Act

EU		European Union

FGM		Female Gentile Mutilation

FPI		Flagship Programming Initiative

GBV		Gender Based Violence

GERAAS	Global Evaluation Reports Assessment and Analysis System

GSP		Governance and Security Programme

ICGLR 		International Conference of the Great Lakes Region

ICPD		International Conference on Population and Development

JLOS 		Justice Law and Order Sector/Services

JTI		Judicial Training Institute

LC		Local Council

MoGLSD	Ministry of Gender Labour and Social Development

MoH 		Ministry of Health

MoJCA 	Ministry of Justice and Constitutional Affairs

MoLG		Ministry of Local Government

NDP		National Development Plan

NGBVP 	National Gender Based Violence Policy

ODPP 		Office of the Director of Public Prosecutions

SDG 		Sustainable Development Goals

SDP 		Strategic Development Plan

SGBV		Sexual and Gender Based Violence

SRHR		Sexual Reproductive Health Rights

ToC		Theory of Change

UBOS 		Uganda Bureau of Statistics

UDHS		Uganda Demographic and Health Survey

UN		United Nations

UNCST		Uganda National Council for Science and Technology

UNDAF		United Nations Development Assistance Framework

UNEG		United Nations Evaluation Group

UNHCR	United Nations High Commissioner for Refugees

UNICEF	United Nations Children’s Fund

UNSDCF	United Nations Sustainable Development Cooperation Framework

UPF 		Uganda Police Force

VAC		Violence Against Children

VAW 		Violence Against Women

VAWG 		Violence Against Women and Girls

Contents

ACRONYMS	ii

LIST OF TABLES	iv

LIST OF FIGURES	iv

EXECUTIVE SUMMARY	v

1.	INTRODUCTION AND BACKGROUND	1

1.1.	Introduction	1

1.2.	Access to Justice and GBV Frameworks in Uganda	1

1.3 The A2J Project	3

1.3. Partnership and Collaboration	4

1.4. Operating context	4

1.5. Theory of Change	6

1.6. Purpose, Objectives, and Scope of the Final Evaluation	7

2.	METHODOLOGY	8

2.1.	Evaluation approach	8

2.2.	Study sites, participants and sample size	8

2.3.	Data management and analysis	9

2.4.	Ethical Procedures	9

2.5.	Limitations	9

3.	FINDINGS	10

3.1.	Relevance of A2J project and its approach in line with local, national, and international priorities	10

3.1.1.	Alignment to national and international policies/frameworks/laws, needs and priorities for GBV survivors in Uganda.	10

3.1.2.	Contribution to addressing priorities and needs for survivors of GBV	11

3.1.3.	Relevance of strategies adopted and choice of partners in addressing needs of beneficiaries and stakeholders.	12

3.2.	Effectiveness of the A2J project	13

3.2.1.	Progress toward outcomes and outputs	13

3.2.2.	Main enabling and hindering factors to achieving planned project outcomes	22

3.3.	Impact of the Project	23

3.4.	Efficiency and coherence of the A2J project for achievement of results	24

3.4.1.	Availability of funds to implementing partners	24

3.4.2.	UN Women Programme management structure and approach and efficiency for the A2J project’s implementation	25

3.4.3.	Partnerships and coordination	27

3.5.	Sustainability of the A2J project and its approach	28

3.5.1.	Working within the existing policies, frameworks and systems	29

3.5.2.	Partnerships and collaborations	30

3.5.3.	Capacity building	30

3.5.4.	Ability of A2J partners to finance similar interventions	31

3.6.	Integration of human rights approach and gender equality principles in the design and implementation of the project	32

3.7.	Lessons learned and promising practices and innovations.	34

4.	CONCLUSION AND RECOMMENDATIONS	36

4.1.	Conclusion	36

4.2.	Recommendations	37

REFERENCES	42

ANNEX I: EVALUATION MATRIX	43

ANNEX II: TERMS OF REFERENCE	45

TERMS OF REFERENCE	45

ANNEX III: ACTIVITIES IMPLEMENTED BY IMPLEMENTING PARTNERS	58

ANNEX IV: SCORING CRITERIA	61

ANNEX V: DATA COLLECTION TOOLS	63

ANNEX VI: LIST OF RESPONDENTS INTERVIEWED	77

# LIST OF TABLES

Table 1: A2J Project Evaluation Scores	vi

Table 2: Progress on outcome one.	14

Table 3: GBV Cases reported and forwarded to court by Police (Source: UPF Crime reports 2020/21/22)	16

Table 4: Progress made on Outcome 2	16

Table 5: Progress on Output 3	20

# LIST OF FIGURES

Figure 1: A2J Project Expected Outcomes and Outputs	6

# EXECUTIVE SUMMARY

Introduction

This Report presents findings of an Independent End Evaluation of the “Women and Girls Access to Justice (A2J) Through Effective, Accountable and Gender Responsive Institutions (A2J Project)” commissioned by the United Nations Entity for Gender Equality and the Empowerment of Women (UN Women – [UNW]) with support from the Austrian Development Agency (ADA). UN Women, grounded in the vision of equality enshrined in the Charter of the United Nations, works for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action, peace and security.

The evaluation set out to assess the project’s achievements against set objectives, to identify and document lessons learnt (including design issues and best practices that can be scaled up or replicated). It examined how the project contributed to harnessing the capacities of women towards the goals of providing access to justice to victims of Gender Based Violence (GBV). The evaluation was gender-responsive and human rights based in nature.

The evaluation specifically, assessed the relevance of the project and its approach in line with local, national, and international priorities on A2J. The effectiveness and efficiency in achieving results, as defined in the logical framework, including the Theory of Change (TOC) were also assessed. It similarly analyzed how the human rights approach and gender equality principles were integrated in the design and implementation of the project. Lessons learned including understanding why particular development interventions worked out or not, promising practices and innovations of work supported by A2J Project within the context of the aid effectiveness agenda were also identified. Annex I to this report provides the Evaluation Matrix used. Actionable recommendations with respect to the overall approach to implementation of the project are proposed.

The final evaluation was conducted at the national, district and community levels. At district and community level, the evaluation was conducted in five out of the 11 focus districts/centers of excellence. A cross-sectional mixed methods design involving qualitative and quantitative methods of data collection was adopted. The methods used followed the UNW Evaluation Policy, Austria Development Agency (ADA) donor Guidelines for Programme and Project Evaluations and the Organization of Economic Cooperation and Development’s (OECD) evaluation criteria for assessing relevance, effectiveness, efficiency, sustainability and impact of the A2J project. Qualitative data approaches included; 32 Key Informant Interviews (KIIs) at national and sub-national levels (district and community), 6 In-depth interviews (IDIs), and 12 focus group discussions (FGDs) at community level with a total of 78 participants (42 female and 36 male). In total 116 respondents were reached (68 female and 48 male). A desk review of the project documents including the A2J proposal, results framework/matrix, implementing partners (IP) agreements and annual progress reports was undertaken. Thematic content analysis was used for the qualitative data while descriptive statistical analysis was performed for quantitative data. The key baseline and end-term indicator values were compared in assessing performance.

Findings

Overall, the project achieved its set objectives, outputs and outcomes despite the delays in commencement occasioned by the significant shift in the operating context outlined in section 1.4. of this report. The A2J project scores per the evaluation criteria are summarized below;

Table 1: A2J Project Evaluation Scores

| Evaluation Criteria | Score |
| --- | --- |
| Relevance | A |
| Effectiveness | B |
| Efficiency and coherence | B |
| Impact | B |
| Sustainability | A |
| Gender and Human Rights | A |

Relevance of the A2J Project

The project focus was on tandem with the key international, regional and national policy, legal instruments and guidelines that underscore the human rights-based approach (HRBA) and gender equality including the Convention on the Elimination of Discrimination Against Women (CEDAW), the Cooperation Framework theory of change (UNSDCF 2021-2025), Principles of Leave No One Behind (LNOB), Gender Equity and Empowerment of Women, Sustainability and Accountability.

At the national policy level, the Project was aligned to policies and laws on GBV, including the national policy on elimination of GBV, the Gender Policy, the Domestic Violence Act (DVA), the Succession Act as amended, the Penal Code Act, the Administration of Justice Programme (AJP) and Governance and Security Programme (GSP)/Access to Justice sub-Programme in adapting to the transition in programming introduced under the Third National Development Plan.

The project invested in and responded to key contextual A2J needs for GBV survivors of; limited legal awareness, technological and technical (GBV specific) capacity both in terms of skills enhancement and acquisition of equipment, aggregated data on GBV cases to inform targeted interventions and service delivery standards.

Effectiveness of the A2J Project

The project achieved most of its targets, outputs and outcomes. The project contributed to capacity building of the key justice institutions and set a strong foundation for improving access to justice for GBV survivors. It succeeded in building trust and establishing strong relationships particularly with the judiciary as well as the ODPP and UPF. Key strategic documents such as a costed strategy/options paper for institutionalisation of a specialised justice system for effective management of GBV cases and draft service delivery standards are in place. Although there was a delay in developing these strategic documents, the fundamentals have been established and any follow on project is likely to be highly effective.

Efficiency and coherence of the A2J Project

Resources allocated were substantial and contributed to the achievement of the relevant outputs. UNW has a robust financial management and accountability system that maintained the integrity of the project and ensured value for money. Stronger relationships and partnerships have been built with the respective justice institutions that create opportunities for more effective and efficient implementation of the A2J project activities. There is evidence that UNW’s approach to implementation of A2J project activities have built on the foundation and lessons learnt from European Union (EU) Spotlight Initiative/Spotlight and United Nations Joint Programme on GBV (UNJPGBV/UN Joint Programme). This reflects synergy and collaboration between A2J and sister projects with a stake in improving access to justice for GBV survivors. However, there were reported delays in implementation of some key activities, and this affected the timely realization of some of the outputs. This is more so in relation to delays in finalization of the options paper/strategy and the service delivery standards. The COVID-19 pandemic and the complex operational environment of the key justice institutions also caused delays in getting key partners like the judiciary on board.

Sustainability of the A2J Project

The key sustainability strategies adopted by the A2J project included working within; a) the existing policy and strategy frameworks; b) structures and systems strengthening in the key justice institutions and with the District Local Government (DLG) especially the Community Based Services Department (CBSD) and the District Director of Health Services Offices; and c) multi-sectoral capacity building through technological (through equipment) and technical (GBV specific) advancements at the national, subnational (with focus on police, prosecutors and judicial officers) as well as community levels (para-legals and para social workers) through existing institutes and academies such JTI and UPF academies. The A2J project succeeded in building on and leveraging efforts of Government efforts and ongoing projects such as the European Union (EU) Spotlight Initiative, UN Joint Programme) among others. The project among others set out to institute a Special Service Delivery and Accountability System/GBV special court whose implementation was delayed, and feasibility reevaluated. Consequently, a strategy for institutionalizing a specialized justice system for effective management of GBV cases and draft service delivery standards were developed, whose gains last beyond the project.

Gender and Human Rights

Overall, the A2J Project was anchored on promotion of human rights and gender equality right from its conceptualization, the ToC, goal, outcomes and outputs. The goals and priority actions in the options paper and its costed action plan as well as overall activity implementation have at their core addressed the human rights of women and girls affected by GBV and ensured that mechanisms to promote their access to justice are institutionalized. This speaks directly to the notions of human rights and gender equality.

Key Project Enablers and Impeding Factors

- Working within existing GBV legal, policy and strategy frameworks as well as structures and systems facilitated conformity, prompt start-up and implementation of the project.

- The idea of introducing 11 centers of excellence as the focus for the project implementation aided focused interventions and monitoring.

- The GBV court case census was great in assisting to appreciate the gravity of the GBV problem in the judiciary.

- Court Open Days and barazas facilitated enhanced community reach and awareness creation.

- Key encumbrances impacting achievement of planned outcomes included; variance in the approved Public Service Duty Facilitation for Government Officials and UNW rates.

- In some instances, there was an unpredictable release of funds from UNW hence impacting on implementation of activities. Relatedly, some activities were outsourced that project implementing partners felt could have been implemented in-house.

- Delayed on-boarding of the project coordinating entity and effects of the COVID-19 pandemic and its lockdowns were an impediment in service delivery with the delayed commencement of certain activities and curtailed physical contact that led to increased backlog of cases across the justice chain.

Good practices

- Maximizing the value-added of partnerships, working relationships and connections at all levels especially at the local government and community level was instrumental directing the project’s ability to leverage limited resources for larger results within diverse and complex regions including Karamoja and northern Uganda.

- Adaptation to the context of the changes in the operating environment and the COVID-19 pandemic enabled reprogramming some planned activities. Despite the delays and additional costs that came with the impact of COVID-19, the project innovated feasible ways to continue implementing some of the key project interventions.

- Infrastructural investments through provision of audio-visual Institutionalized equipment and rooms that facilitate privacy and confidentiality as well as support to victims as they provide testimonies in courts have contributed towards realization of the survivor centred approach to access to justice. A survivor-centered approach seeks to empower the survivor by prioritizing their rights, needs, and wishes. This includes ensuring that survivors have access to appropriate, accessible, and quality services. Through infrastructural investments the project facilitated the creation of a supportive environment in which survivor’s rights are respected and in which a survivor is treated with dignity and respect.

- The UNW Country Office has cultivated and demonstrated long-term consistency and dependability through teamwork, mutual respect and being approachable in its strategic partnerships with the key Ministries Departments and Agencies especially the MoGLSD, UPF and ODPP. It has applied the same approach to the Judiciary that has seen building relationships that have culminated into leadership commitment from the top management and leadership of the Judiciary to A2J priority activities.

- Multi-sectoral training/capacity building of justice agencies, especially on international mechanisms and standards, reporting and recognizing gender, GBV and human rights violations and abuses was identified by stakeholders as highly important and impactful in promoting shared learning, communication, cooperation and coordination.

Lessons Learned

- Building on successes, achievements and lessons from previous and ongoing programmes is important for fast tracking achievements of project deliverables, capacity building and sustainability. A2J did well by building on and leveraging efforts of the ongoing projects such as the EU Spotlight Initiative, UNJGBV among others. However, there is need to be intentional in identification of other ongoing initiatives in the judiciary, UPF and ODPP as well as MGLSD to leverage and draw lessons to inform programming.

- Survivor centred, trauma informed, gender sensitive and human rights-based approaches are crucial in responding to risk and vulnerability and the unique needs of the GBV survivors to enable them to be confident and have the self-esteem needed to pursue justice throughout the justice chain. A2J has started several innovations ranging from trainings, survivor support, installing audio-visual equipment and rooms to offer confidentiality. These are good practices that should be institutionalised and continued throughout the justice chain.

- Finding a delicate balance between strengthening both GBV response and prevention is crucial given that both strands are essential in improving access and the quality of justice. The focus particularly on social and gender norms change at the institutional and community level is imperative.

Conclusion

- Overall, the project was relevant to the national and sub-national context of GBV and access to justice. It made major inroads in multi-sectoral capacity building initiatives and strengthening of justice institutions laying the foundation for further work crucial to promoting and institutionalizing access to justice. This was possible through building of strong relations with the Judiciary, Uganda Police Force (UPF) and the Office of the Directorate of Public Prosecutions (ODPP).

- Project partners mutually agreed to and owned a strategy/options paper for institutionalizing a specialised justice system for effective management of GBV cases as well as the drafting of service delivery standards (near finalization). There were significant delays in the completion of some activities. This led to several no-cost extensions that were required to ensure that a strong foundation is laid for the follow-on project activities.

- Working through existing structures at all levels coupled with building on achievements and lessons learnt from ongoing projects especially the Spotlight initiative and UN Joint Programme on GBV set a strong foundation for sustainability.

Recommendations

- There is need for key stakeholders to further consolidate, strengthen partnership and collaboration between the Judiciary, ODPP and UPF as well as the relevant DLG departments in all project processes including design, implementation, monitoring and evaluation.

- Given the level of complexity and bureaucracy involved in working with the key justice institutions and that some of these institutions like the judiciary were recently onboarded, UNW Country Office and its implementing partners should engage with donors to advocate for long term funding to enable adequate time for project inception, implementation and improvement to the quality of outputs and deliverables as a means of realising greater impact.

- With the strategy for institutionalisation of a specialised justice system for effective management of GBV cases against women and girls – ‘options paper’ and the draft service delivery standards in place, UNW Country Office and the project implementing partners should review the A2J project ToC, work plan and approach to align to the strategy/options paper and service delivery standards. This means that donors should consider a second phase of the A2J project aligned to the strategy/options paper and the service delivery standards.

- Need to fast track the review and finalisation of detailed and concrete Service Delivery Standards and Procedures covering all the steps towards delivering Quality Integrated Justice Services. This is crucial for improving coordination and harmonisation of the delivery of justice to the GBV survivors and for promoting the good practice of justice being understood and operationalised as a chain. It will also facilitate monitoring of the quality as well as in holding the relevant duty bearers accountable.

- UNW and its partners should agree to and consider different approaches implementingcapacity building in financial management and accountability. This will facilitate building competencies of IPs in timely reporting for funds received to address the delays in accountability and implementation of project activities.

- Given the importance of investing in both prevention and response, there is need for UNW and partners to consider investment in social norm change at the institutional and community level to complement the access to justice components of the project. This is because social norms may deter reporting of cases and may continue to justify violence against women and girls.

- There is need to strengthen the M&E sytem to collect baseline information and populate the all indicators in the results framework to faciliate tracking impact.

# INTRODUCTION AND BACKGROUND

## Introduction

This report is prepared in accordance with the Terms of Reference (ToR) herewith attached (see Annex II). It provides an Executive Summary of the evaluation, the A2J project description, evaluation purpose and primary objectives. The evaluation methodology, key findings, cross-project analysis and cross-cutting issues are embedded. Lessons learned, promising practices, innovations, conclusions and recommendations are also included. The report comprises of a list of literature reviewed, interviews conducted both at national and district level, data collection tools, and analysis. It is informed by an extensive desk review of GBV and A2J policies, strategies as well as project documents including thematic and progress reports. The report has been further enriched by consultations with the formal justice, GBV and informal actors, development partners and civil society both at national and sub-national levels including project beneficiaries, the Project team and Evaluation Reference Group.

## Access to Justice and GBV Frameworks in Uganda

Access to justice is essential and an empowering aspect of a survivor’s healing process. The justice sector therefore has a vital role to play in a coordinated response to ending VAWGs; by using the authority of the government, or of the community, to enforce laws and other rules of behaviour that can protect women and girls from violence and punish perpetrators. Access to justice for women and girls, especially those who have experienced GBV, is upheld in several legal frameworks and numerous statutory structures and institutions that are involved in ensuring justice for survivors of GBV at all levels of governance are provided for.  The roles of these actors are well articulated in several legal and statutory frameworks.

The A2J sub program of the GSP brings together 17 former JLOS institutions responsible for administering justice, maintaining law and order and promoting the observance of human rights. Uganda’s progressive legal framework promotes access to and utilisation of services and protects women and girls from GBV and harmful practices. Rights such as equality and freedom from discrimination; protection of right to life; respect for human dignity and protection from inhuman treatment; right to a fair hearing; rights of women; and rights of children are enshrined in the Constitution of the Republic of Uganda, 1995. At the international and regional levels, Uganda has ratified and adopted instruments on the elimination of discrimination and violence against women and girls. Several of these Conventions have been domesticated at the national level.

Human Rights and Gender Equality in Uganda

Ensuring a culture of human rights observance in Uganda is the central focus for implementation of Uganda’s Bill of Rights comprised in Chapter Four of the 1995 Constitution. Objective XIV of the Constitution of the Republic of Uganda (National Objectives and Directive Principles of State Policy) mandates the State to fulfill the fundamental rights of all Ugandans to social justice and economic development and to ensure that all development efforts are directed at guaranteeing maximum social and cultural well-being of the people. The Constitution further enjoins Government to formulate policies and enact laws to protect all citizens against human rights abuse. In recognition of the fact that GBV affects women and girls more than men and boys, Government has the obligation to protect their rights, taking into consideration their unique status and maternal functions in society as provided for under Article 33(3) of the Constitution. Sectoral and institutional Gender and Equity Mainstreaming Strategies are in place hinged on promoting equal access to justice for boys and girls, women and men and the most vulnerable members of the Ugandan Society.

Violence against women and girls in Uganda

Despite the existence of a progressive legal regime, implementation remains weak for multiple reasons, including limited technical and financial resource allocation by the Government. VAWG is a major public health concern and a human rights violation. It severely undermines the nation’s economic and social development. Estimates published by the World Health Organisation (WHO) indicate that globally about 1 in 3 (30%) of women worldwide have been subjected to either physical and/or sexual violence in their lifetime. The occurrence of GBV in Uganda is widespread and is worsening. GBV offences, particularly defilement, top the list of most recurring crimes every year for the last ten years. The number of GBV cases in Uganda increased consistently by 9.8 percent in 2020. Majority of survivors are girl children, and most perpetrators were male adults. During the COVID 19 lockdown, Uganda registered the highest GBV levels in the East Africa region. This was attributed to the total lockdown of the country to stop the spread of the COVID-19 pandemic, disputes over family property, failure to provide for the family, drug and alcohol abuse, and cases of infidelity.

Almost all women (95%) had experienced physical or sexual violence, or both, by partners or non-partners, since the age of 15 years. In most regions the perpetrators were mainly family members (22%) and about half of the women in Uganda (47%) face economic violence. About nine in every ten women in Uganda (86%) had ever experienced an act of violence at the workplace. The prevalence of childhood sexual abuse in Uganda stood at 59%. In most settings, women who had ever experienced physical or sexual partner violence, or both, were significantly more likely to report symptoms of ill health and higher levels of emotional distress than women who had never experienced partner violence. About half of the women (49%) reported to have ever been involved in online harassment. Four in ten (43%) of the women who had been physically abused by their partner had never sought help from formal services or individuals in a position of authority (e.g. village leaders).

According to available data, 16% of Ugandans have disabilities – the largest percentage being from Northern Uganda due to injuries sustained during the Lord’s Resistance Army war. Women with disabilities are particularly at risk of GBV because of social exclusion, limited mobility, lack of support structures, communication barriers, and social perceptions that they are weak, stupid, or asexual. Discriminatory attitudes remain a major barrier to accessing justice and the full inclusion of women with disabilities into society. Displaced communities and those that host large numbers of refugees face high risks of violence, including sexual exploitation and abuse. According to UNHCR, 81% of Uganda’s 1.4 million refugees are women and children, who are at high risk GBV, including sexual exploitation and abuse, rape, forced and child marriage, and intimate partner violence. In crisis settings GBV threats soar. Armed conflict, natural disasters and humanitarian emergencies can significantly weaken a society’s ability to protect women and girls from GBV.

GBV is rooted in gender inequality, the abuse of power and harmful norms, therefore gender and equity responsive planning and budgeting, strengthening implementation of Uganda’s legislative and policy framework, institutionalizing special GBV court sessions, legal aid service provision, awareness creation, accountability and capacity development are vital in eliminating all forms of VAWGs.

## 1.3 The A2J Project

The A2J Project commenced on 1st November 2019 and ended on 30th March 2023. The project was aligned to and contributes to UN Women’s FPIs, the Sustainable Development Goals Specifically Goal 5 on Gender Equality and Goal 16, which seeks to promote peaceful and inclusive societies for sustainable peace and development by providing A2J to all and to build effective, accountable, and inclusive institutions at the national and sub national levels. The project has contributed to UN Women’s Global Strategic Plan; impact area three on Ending Violence against Women and Girls and the United Nations Sustainable Development Cooperation Framework (UNSDCF) 2021 – 2025, specifically Outcome 1.1. The project was aligned to Uganda’s National Policy and Action Plan on Elimination of GBV (2016), the Third National Development Plan (NDP III) (2020/21-2024/25), Uganda’s commitment to implement obligations under the Kampala Declaration, the Administration of Justice, and Governance and Security Programmes.

The A2J project set out to strengthen integrated service delivery and accountability systems for managing GBV cases across JLOS from entry to exit and to upgrade eleven selected High Court Circuits and Chief Magisterial areas into Regional Centres of Excellence. The A2J project was designed to complement the EU-UN Spotlight Initiative and the UN Joint Programme on GBV currently implemented in 20 districts and UNICEF’s installation of Audio Video Links and Child Friendly Rooms in seven districts.

The A2J project sought to directly benefit approximately 30,000 women, children, older persons, refugees, and persons with disabilities and people vulnerable to violence annually by improving the quality of justice services. The project anticipated directly targeting approximately 1,000 justice actors i.e., 51 Judges, 200 Chief Magistrates (CMs), Prosecutors and Resident State Attorneys, and 500 Criminal Investigation Officers and Child and Family Protection Officers, 100 Health workers and 150 Administration and frontline staff by improving their knowledge and skills in providing specialised justice and referral services for GBV cases through the special court system. Secondary beneficiaries included duty bearers from institutions mandated under the National GBV Policy to handle GBV cases such as Lawyers, Heath workers, Local Council leaders, and traditional justice actors. Ultimately, 38,823,100 Ugandans were expected to indirectly benefit from the Special Service Delivery and Accountability System/Special Court for GBV.

## 1.3. Partnership and Collaboration

The A2J was developed in partnership with key stakeholders at various levels including the Government of Uganda, development partners and representatives from the District Local Governments (DLGs) and Civil Society Organizations (CSOs).  As such, meaningful partnerships were established at national, sub-national and community levels. At the national level, the key partners included; the Judiciary/Administration of Justice Programme, Judicial Training Institute, Governance and Security Programme (GSP) Secretariat, Ministry of Gender, Labour and Social Development (MoGLSD); Ministry of Justice and Constitutional Affairs (MoJCA), Uganda Police Force (UPF), Office of the Director of Public Prosecutions (ODPP), Directorate of Government Analytical Laboratory (DGAL); CSOs (Justice Centres Uganda [JCU], Legal Aid Project of Uganda Law Society [ULS/LAP] and Centre for Domestic Violence Prevention [CEDOVIP]; Academia, Faith Based Organizations (FBOs), Media, Private sector and Cultural Institutions. At the subnational level, the Project collaborated with the key stakeholders including; the DLGs, CSOs, Religious and Cultural Institutions. At the community level, the Project engaged with the leadership structures including the political, culture and religious leaders, para legals, para social workers, village health teams, local councils among others. See attached Annex III with details of activities implemented by partners under the A2J project.

## 1.4. Operating context

The A2J project was conceptualized as part of Government of Uganda’s (GoU) efforts under the Second National Development Plan (NDPII) covering the period 2015/16 – 2019/20, the Fourth Justice, Law and Order Sector (JLOS) Strategic Development Plan (SDPIV), and Government’s plan to reduce case backlog in the justice system and to enhance access to JLOS services particularly for vulnerable persons. The project’s implementation cascaded to the NDPIII (2020/21-2024/25) period characterized by a transition from the sector-wide approach to programmatic planning, budgeting, implementation, and reporting. The NDPIII that introduced a new programme based approach commenced at a time when Uganda, like the rest of the world, was confronted with the COVID-19 pandemic. The Plan reconstituted 17 former sectors into 20 Programs, five-year Program Implementation Action Plans (PIAPs) now replace Sector/Strategic Development Plans as frameworks for the realization of NDPIII.

The emergence of the global COVID-19 Pandemic in 2020 and its lockdowns accelerated the need for digital transformation in service delivery especially with regards to citizen engagement and empowerment across the justice chain. The pandemic led to restricted access to courts, despite such access being a fundamental human right provided for in Article 28(1) of the 1995 Constitution of the Republic of Uganda. In a bid to enable access to courts during the COVID-19 pandemic, the Judiciary took measures such as online hearings and electronic delivery of judgments. However, access to courts remained a challenge due to a host of factors. The pandemic hampered access to justice while impacting on livelihoods, it exposed gaps in the implementation of laws and the need for more investment in crime response. An increase in violence against women and girls was attributed to the effect of the COVID-19 pandemic.

The COVID-19 lockdowns worsened pre-existing challenges regarding childcare and learning, as nearly 15 million learners were locked out of school. It also elevated child protection concerns, and compounded risks of poor child health. The lack of funding was the main reason for leaving school for both boys (43%) and girls (41%) followed by school not being affordable or being expensive reported by 24% for boys and 22% for girls that had left school. Pregnancy among girls accounted for 8 percent of the females that left school in the age bracket of 6 years to 24 years. The lockdowns and other restrictions led to the depletion of household incomes and erosion of livelihoods. The plight of the working poor deepened, with a disproportionate impact on children. More than ever, the pandemic demonstrated the necessity of child sensitive social protection to reduce poverty and vulnerabilities caused by job loss, depletion of household savings and assets, and restrictions in movement and trading activities as witnessed during the lockdowns.

The A2J project adapted to the shift in the operating context that impacted on overall implementation;

- Programming and coordination arrangements: Contracting a project implementing partner was inordinately delayed and impacted upon by the national change in Programming introduced under NDPIII from the sector wide approach to the Programme based budgeting.

Initially the former JLOS Secretariat was identified to lead overall coordination and management of the project for which a capacity assessment was successfully completed. There were changes in the overall project coordination to the Judiciary. This necessitated lengthy on boarding – including undertaking a capacity assessment and endorsing a Letter of Agreement (LoA) with the Judiciary with whom UN Women had no running agreement.

Relatedly, the A2J project embodied developing a strategy for special courts for SGBV cases by UNFPA whose finalization was delayed and inhibited the project’s commencement. It was later agreed that UN Women spearheads the strategy development.

- The COVID 19 Pandemic, its accompanying lockdown measures and the associated scale down on personnel and scope of work hampered A2J across the justice chain including; the Judiciary, police and ODPP for most of 2021. This impacted on timely delivery of planned project activities.

- Other processes like adjudication of election petitions arising from the 2021 general elections that the Judiciary should have addressed in early 2021 also delayed and took place in September – October 2021. This meant that judicial officers were unable to engage in any other activity whilst handling electoral petitions. This was followed by the SGBV sessions which commenced on 25th October 2021 and ended on 17th December 2021. With majority of the judicial officers involved in the election petitions and SGBV sessions planned capacity building trainings for judicial officers were rescheduled to take place in 2022.

Expected impact

Survivors/victims of GBV access quality integrated essential justice services through effective, accountable and gender-responsive justice institutions. The project’s expected outcomes and outputs are represented in figure 1 below.

Figure 1: A2J Project Expected Outcomes and Outputs

Human Resources: Three staff members (United Nations Volunteer and an EVAWG Programme Specialist) were onboarded to support with fast-tracking project delivery. A project taskforce comprising of representatives from – Judicial Training Institute (JTI), Under Secretary Judiciary, Economic and Policy Analysts, and an M&E unit was set-up.

Financial Resources: The total approved budget for the action was $2,232,982.86 disbursed in two instalments of $1,207,962.61 and $569,767.44 totaling $1,777,730.05 with initial funds disbursed in April 2021.

## 1.5. Theory of Change

The ToC underpinning the A2J project was elaborated around the preconditions and change pathways of;

- If legislation, policies and budgets are gender-responsive; and if special courts for GBV are institutionalized; and, If Justice institutions improve performance standards, procedures and accountability mechanisms and are integrated; then, survivors of GBV will access fair justice mechanisms and redress based on relevant gender equality standards; because systems and capacities will be in place to address gender discrimination and other barriers to women’s access to justice at all levels and stages of the justice delivery chain.

- If capacities of duty bearers are enhanced, their attitudes towards women conform to gender equality standards, and if mechanisms are in place to monitor the delivery and quality of justice services to women; then the performance and accountability of justice institutions to women will improve; because investing in duty bearers is critical to improving the quality of justice services for women.

- If women know their rights as potential users of the justice system and are accepted as actors of the justice system; then women will be able to claim their rights; because evidence shows that rights awareness and the active participation of females in the justice sector increases quality, access and fair justice outcomes for women.

## 1.6. Purpose, Objectives, and Scope of the Final Evaluation

The purpose of the final evaluation was to assess the A2J project’s achievements against the set objectives, identify and document lessons learnt (including design issues, lessons and best practices that can be up scaled or replicated), and assess how the project contributed to harnessing the capacities of women towards the goals of providing access to justice to victims of GBV.

The primary purpose of this evaluation is to provide:

- Learning and improved decision-making to support better implementation of future A2J projects;

- Provide accountability for the development effectiveness of the Programme to the donor, beneficiaries and other key stakeholders;

- Provide lessons learned, including an understanding why particular development interventions have worked out or not; and

- Recommendations to provide clear direction for UN Women’s further A2J work as well as inform future resource mobilisation efforts.

The evaluation specifically:

- Assessed the relevance of the project and its approach in line with local, national, and international priorities on A2J;

- Assessed the effectiveness and efficiency of the Programme approach for achievement of results, as defined in the logical framework, including the Programme ToC;

- Analysed how the human rights approach and gender equality principles were integrated in the design and implementation of the project;

- Identified and validated lessons learned including understanding why particular development interventions have worked out or not, promising practices and innovations of work supported by A2J Programme within the context of the aid effectiveness agenda; and

- Provided actionable recommendations with respect to the overall approach to implementation of the A2J project.

# METHODOLOGY

## Evaluation approach

The evaluation employed an exploratory and multipronged approach. In line with the United Nations Evaluation Group (UNEG) norms and UN Women and Global Evaluation Reports Assessment and Analysis System (GERAAS) standards, a gender equity and human rights-based approach was applied throughout the evaluation process. The evaluation followed a collaborative and participatory approach ensuring close engagement with Programme beneficiaries, implementing partners, ministries, departments, agencies and local governments and other key stakeholders at the different stages of the evaluation process.

FGD Female Beneficiaries Moroto

The evaluation utilized a mixed-method approach to gather and integrate data from multiple data sources and methods. Standard qualitative methodologies were used and data was derived from KIIs and FGDs. Quantitative data was derived from project documents, monitoring and progress reports highlighting the project approach, various activities, expenditure, and quantitative results of the A2J project. The evaluation adopted the OECD/DAC evaluation criteria. The A2J project was assessed following the six OECD-DAC domains of relevance, effectiveness, efficiency, coherence, impact, sustainability and on the Human Rights and Gender Equality criterion. (See Annex I: Evaluation matrix). In addition, a scoring of the project across the six domains was done to measure the performance (see Annex IV to this report for further details of the scoring criteria).

## Study sites, participants and sample size

Data collection was conducted both at national and district levels. At district level, data was collected in five districts of Kasese, Tororo, Moroto, Gulu and Kampala. These study sites were agreed on with UN Women considering the prevalence of VAW/G in those localities, the substantial project investment in terms of capacity enhancement (training and provision of equipment) and identification of champions within partner institutions. The existence of other justice actors (UPF and ODPP) as well as districts were UN Spotlight and the UNJGBV interventions were implemented were also considered in selecting the sites. The data collection tools are attached to this report see Annex V. The evaluation participants included: government officials, development partners, CSOs and community members beneficiaries. In total 116 respondents were interviewed (68 female and 48 male) during the evaluation. Of the total number of respondents interviewed, 32 KIIs were conducted at national and sub-national levels (district and community) and 6 In-depth interviews (IDIs) with GBV survivors. Twelve FGDs were conducted at community level; mixed, with females only and males separately. In total 78 participants (42 female and 36 male) participated in the FGDs. See Annex VI to this report for a list of respondents interviewed.

## Data management and analysis

Different data was used and produced during this evaluation:  numeric (databases, spreadsheets), textual (documents), and audio. Existing numeric data (from monitoring reports, available statistics) have been re-used by the evaluation team throughout this exercise. Data validity and quality was cross checked through the UN Women M&E and Project officers to explain any discrepancies. Data sources were also triangulated to further assess data quality.

Several activities were undertaken in the course of analyzing and processing primary data collected through interviews. First, research assistants for the respective study sites transcribed all audio-recorded data and simultaneously translated it from local languages to English. Data was coded manually in excel. A coding matrix was developed following the evaluation objectives, matrix and project objectives. This was followed by coding/creation of quotations and discussion under each theme/family. Some verbatim quotations have been inserted directly into the report to demonstrate the accuracy of interpretation, deepen understanding, and enhance readability and the voice of community members.

## Ethical Procedures

The Evaluation Team respected protection and confidentiality of data as recommended by UNEG and the related code of conduct for evaluation in the UN system. The following ethical guidelines were strictly adhered to by the evaluation team members: independence and impartiality; credibility; honesty and integrity; accountability; confidentiality; respect for dignity and diversity; avoidance of harm; accuracy, completeness and reliability; transparency. The ethical principles; of “do no harm”, respect for cultural norms, commitment to an inclusive approach ensuring access to/participation of women and men as well as minority groups, confidentiality and anonymity of interviewees were considered.

Before conducting the interviews, informed consent was sought from all respondents. Consent was obtained after explaining to them all issues pertaining to the evaluation in the language, they understand including risks, benefits, and other ethical issues. Consent was sought throughout the evaluation. All data collection was conducted in private locations and privacy was ensured as much as possible. The FGDs were conducted in locations of participants’ choice and such a venue(s) ensured that privacy was maintained. In addition, all research team members were carefully selected, with training of research teams not only on the subject matter and methodology but also ethical issues informing the evaluation. Design of research tools was sensitive to the special needs of vulnerable groups including women, and persons with disabilities. During the interviews with survivors, careful attention was given to the ethical and safety issues associated with the evaluation. Survivors were interviewed from places they selected and perceived to be comfortable and secure. They were made aware of services available for referral in case this was needed. They were also made aware that they could stop the interview if they felt uncomfortable and answer only those questions, they felt comfortable to answer. This was largely guided by guidelines developed by WHO for researching violence against women.

## Limitations

The overall approach used was qualitative with quantitative data generated from secondary sources. A quantitative survey was not conducted, and this may affect some aspects related to generalisation of the results to the entire population targeted. However, the evaluation team minimised these limitations by engaging in triangulation of data from various sources (secondary from the review of relevant documents including reports from UPF, Judiciary and ODPP, M&E reports and primary data sources, and by use of several methods of data collection (IDIs, KIIs, FGDs) that complement each other. The results were also validated with key stakeholders to provide their inputs.

# FINDINGS

## Relevance of A2J project and its approach in line with local, national, and international priorities

| Relevance Score | A – Very Good |
| --- | --- |
| Scoring: | The evaluation found that the A2J project interventions adequately addressed the needs and priorities of women, girls, partners and stakeholders. The project interventions were aligned with Government, SDGs, and International frameworks such as CEDAW, UNW priorities, policies and strategies. The needs and priorities of GBV survivors’ and some of the root causes of GBV were addressed as discussed in Finding 2 and section 3.1.2 to this report. . |

## Alignment to national and international policies/frameworks/laws, needs and priorities for GBV survivors in Uganda.

Finding 1. The A2J Project was aligned to international gender equality human rights norms and national policies. The project was aligned to Uganda’s policy and legal frameworks as well as to legal and policy frameworks at international and regional levels that promote gender equality, access to justice, equitable access and utilisation of services while protecting women and girls from GBV and harmful norms and practices. Despite this, there is need for enhanced implementation of existing frameworks through allocation of more resources and strengthening the institutional frameworks and systems for delivery of access to justice services. In adapting to the transition in Programming, the A2J project was aligned with the AJP and GSP/Access to Justice sub-Programme. The Project partnered with key justice institutions who contribute to both the AJP (judiciary) and GSP in the case of (UPF and ODPP). The findings related to the A2J Project integration of the Human Rights Approach and Gender Equality Principles are exhaustively discussed in Section 3.5 of this report.

Finding 2. The A2J Project responded to underlying causes of gender inequality. Gender inequalities limit the ability of women and girls to fully participate in, and benefit from development programmes in Uganda. Formal and informal institutions as well as social, gender norms and harmful cultural practices play a major role in perpetuating gender inequalities in Uganda. The project invested in and responded to key contextual A2J needs for GBV survivors including limited legal awareness, technological and technical (GBV specific) capacity both in terms of skills enhancement and acquisition of equipment, aggregated data on GBV cases to inform targeted interventions and service delivery standards. Implementing institutions acknowledged the enhancement of their capacity gaps. The UPF for instance, acknowledged the improved quality of evidential material that reaches the forensic laboratory as a quick win in addressing GBV cases through the provision of consumables to process cases/forensic examination and the acquisition of scene of crime processing kits. In handling backlog and prioritizing SGBV cases DGAL has now reduced the turn-around time to a month from 120 days (four months) from the time of submission evidential material.

In addressing limited awareness on women rights the A2J project supported community outreach activities such as Court Open Days, radio programmes and barazas in facilitating enhanced community reach and legal awareness creation. In one of the FDGs conducted, beneficiaries noted that;

“Through on-going sensitization campaigns more women now understand their role, and they know where to go when they encounter challenges. At the community level they approach a Local Council (LC)1, LC2, Justice Centers  or the Division...” (FGD with male beneficiaries, Tororo District).

## Contribution to addressing priorities and needs for survivors of GBV

Finding 3. The project contributed to addressing priorities and need for survivors of GBV by strengthening the capacity of institutions to provide A2J services. Specialized multi-sectoral GBV trainings were conducted for judicial officers (Magistrates), administrative staff, police and ODPP using the reference resources (GBV Manuals developed). Specialized equipment to support adjudication of SGBV offences (audio visual and transcription equipment) were acquired to facilitate conduct of and recording court proceedings as well as timely access to court records. There was improvement of data availability (aggregation of GBV data through the case census).

On profiling the nature of the most prevalent GBV cases in Uganda, the Annual Crime Report specifies domestic violence (DV), murder as a result of DV and sex-related crimes of defilement, rape and others (indecent assault, incest, unnatural offences) by region/district, division and relations to prevalence. According to the National Survey on Violence in Uganda almost all women (95%) had experienced physical or sexual violence, or both, by partners or non-partners, since the age of 15 years. The lifetime prevalence of physical or sexual violence, or both, by an intimate partner was 56% with physical violence at 45% and sexual violence at 36%. Electoral violence, stalking and cyber harassment were also profiled as forms of violence requiring targeted interventions.

Trained judicial officers and administrative staff attested to the trainings being the first specialized GBV training they had benefitted from even after having served for more than five years. The A2J project addressed enhanced technical capacity through increased knowledge and skills in handing GBV cases” (KII UN Women). The trainees acknowledged the Manuals as useful reference resources for their day-to-day operations.

“Multi-sectoral trainings ensured that all categories of actors are targeted (judiciary, police, prosecutors, medical personnel, probation and social welfare officials). There is enhanced appreciation of prosecutor-led investigations which has contributed to reducing the time between investigations and handover of cases to the ODPP from two months to a minimum of four days. This is because investigations now focus on relevant evidence needed by prosecution. The trainings have also enhanced legal awareness for some police officers on the Penal Code Act that has assisted to provide guidance on charges to preferred against accused persons” (KII with UN Women and ODDP).

The ODPP reported an overall increased reporting of GBV cases and 80% conviction rate. “In addressing the A2J sub-Programme priority of case backlog reduction, the increase in SGBV case disposal/conviction rates registered is worth applauding. Similarly, impact assessments in GBV cases have contributed to strengthening case outcomes and facilitated judicial officers to make informed sentences, hence improving the quality of justice delivered (KII with GSP Secretariat and ODPP).”

Trainings conducted under the Project have contributed to disaggregation of GBV records/cases as trainees (court administrative staff) attested to improvements in filing out the GBV case registers. “Previously, GBV case registers were not being utilized, instead GBV/SGBV cases were being recorded as criminal cases” (KII with JTI).

The victim centred approach is taking root and has improved victim participation in the criminal justice system that is majorly focused on the accused. The project also contributed to expansion of the geographical reach of A2J services for GBV survivors through the 11 centers of excellence targeted.

The evaluation observed the need for an agreed working definition of GBV for project implementation. The term GBV evolved from the Violence Against Women (VAW). The UN Declaration on Elimination of Violence against Women (1993) defines VAW as “any act of GBV which results in or is likely to result in physical, sexual or psychological harm or suffering to women, including threats of such acts, coercion or are arbitrarily deprivation of liberty, whether occurring in public or private life.” UN Women defines GBV as “harmful acts directed at an individual or a group of individuals based on their gender. It is rooted in gender inequality, the abuse of power and harmful norms. The term is primarily used to underscore the fact that structural, gender-based power differentials place women and girls at risk of multiple forms of violence. While women and girls suffer disproportionately from GBV, men and boys can also be targeted.

Violence against women and girls (VAW/G) is defined as any act of GBV that results in, or is likely to result in, physical, sexual or mental harm or suffering to women and girls, including threats of such acts, coercion or arbitrary deprivation of liberty, whether occurring in public or in private life. VAWG therefore encompasses, but is not limited to, physical, sexual and psychological violence occurring in the family or within the general community and perpetrated or condoned by the State.” The DVA  defines GBV to include; physical, sexual, emotional, verbal, psychological and economic abuse while the Penal Code Act also lays out a broad range of GBV related offences. The terms Sexual Violence, GBV, VAW/G, and SGBV are frequently used interchangeably. Over time GBV has become an umbrella term for any harm that is perpetuated against a person’s will based on unequal relations between women and men as well as through abuse of power. However, it is important to note that all terms relate to a violation of fundamental human rights that perpetuate sex–stereotyped roles which deny human dignity and the self–determination of an individual and hamper human development.

## Relevance of strategies adopted and choice of partners in addressing needs of beneficiaries and stakeholders.

Finding 4. The project adopted relevant strategies and partnered with key justice actors in addressing the needs of beneficiaries and stakeholders. The project adopted a three-pronged approach in enhancing access to fair justice mechanisms and redress based on relevant gender equality standards through strengthened systems and capacities to address gender discrimination and other barriers to women’s access to justice at all levels and stages of the justice delivery chain. The Judiciary was the lead implementing institution with the Registrar JTI-administrative head planning, coordination and implementation of training activities in the Judiciary as the lead focal point person. The Judiciary, UPF and ODPP-frontline justice institutions and the Directorate of Government analytical Laboratories were targeted. These institutions complement each other in the justice chain and specifically in addressing GBV against women and girls. The project’s implementation was focused on a gender sensitive, victim centered and trauma informed approach.

“In a UNW monitoring mission to Kasese we noted that the provision of the audio-visual linkages has greatly improved on the status of the court in terms of being in sync with developments regarding exposure of GBV survivors to secondary trauma. The use of audio-visual linkage and victims’ friendly rooms allowed survivors of GBV to provide evidence outside open court linked to the accused/perpetrator via screens. The technological advancement is a whole new environment and experience for court users that allows for a progressive court proceeding. The victim friendly rooms are conducive, allowing for a survivor to comfortably give their evidence without going through secondary trauma”, (KII with UN women).

Employing complementary civil society support through legal aid service providers such as JCU, FIDA, and ULS/LAP played a crucial role in creating awareness about the specialist justice system for effective management of GBV and VAC cases as well as training the informal justice actors.

## Effectiveness of the A2J project

| Effectiveness Score | B - Satisfactory |
| --- | --- |
| Scoring: | Scoring: The A2J interventions met its objectives, outcomes, outputs and targets as defined in the results framework, and aligned to the Project ToC. But some changes are necessary particularly to ensure that the activities that lay the foundation for the other activities are implemented in time such as the costed strategy or options paper and the service standards. |

The A2J project was designed to complement the EU-UN Spotlight Initiative and the UN Joint Programme on GBV currently implemented in 20 districts and UNICEF’s installation of Audio Video Links and Child Friendly Rooms in seven districts.  Therefore, the project sought to ensure survivors/victims of GBV access quality integrated essential justice services through effective, accountable and gender-responsive Justice Institutions. The planned outcomes included; a) Special service delivery and accountability systems/special courts for GBV institutionalized, integrated, and perpetrators are held accountable in accordance with the law and human rights, and b) Increased use of available, accessible, and quality essential justice services by women and girls who experience violence. The planned outputs were; a) systems, procedures and standards strengthened, integrated and implemented to guarantee quality justice for survivors of GBV and vulnerable women and girls; b) capacities of formal justice institutions to deliver quality, coordinated essential services and fast track cases of GBV and other forms of discrimination is strengthened; and c) Women and girls at risk of violence are empowered on their rights, have knowledge of and can access and use quality justice services.

## Progress toward outcomes and outputs

Outcome 1: Special service delivery systems and special courts for GBV institutionalized and perpetrators are held accountable in accordance with the law and human rights.

Outcome one of the A2J project sought to ensure that special service delivery systems and special courts for GBV are institutionalized and perpetrators are held accountable in accordance with the law and human rights.

Finding 5. Most of the indicators under this outcome were not implemented and therefore noted monitored (see table 2 below). Discussions with project implementers reveal that under indicator 1, an informed target could not be set because the assumption was that it would be based on the functioning of the special service delivery system and special court which was to be set up before UN Women’s project (A2J) commenced. Similarly, indicator 2 was not activated because it was included with the expectation that the special service delivery system and special court would be in place. However, the system has not been established to date. Nonetheless, the project achieved indicator 3.  Discussions with stakeholders show that there has been improved capacity of JLOS actors (Police, Prosecutors and Judicial Officers) to manage GBV cases as a result of UN Women’s support.

Finding 6. The project has supported the development of a costed strategy for institutionalisation of a specialised justice system for effective management of GBV cases against women and girls and a baseline survey for benchmarking the impact of the Special Service Delivery and Accountability System has been completed. This was then followed by the development and presentation to the top leadership of the Judiciary, ODPP and UPF the Options Paper for Institutionalisation of Special Courts for effective management of GBV cases. The time-sharing option was selected which will entail a minimum of one court room designated per Court to handle GBV criminal matters.  Cases would be heard on designated days. The location of the designated court room is within a High Court circuit (one court room for the Judge and one courtroom for Magistrates in a High Court Circuit). An implementation plan for the time sharing model has been developed and approved for the three high court circuits of Mbarara, Masaka and Jinja. The project supported the development of tools in terms of guidelines and standards covering all the steps towards delivering quality integrated justice services throughout the special service delivery and accountability systems/ special court.  Standard operating procedures (SoPs) for GBV and VAWG for delivery of quality integrated justice services under the A2J project. The SoPs were developed to facilitate multi- sectoral referral mechanisms for women, and girls at risk. They describe clear procedures, roles, and responsibilities for all justice actors, who agree to the same procedures, guiding principles and working together to ensure justice to victims of GBV and vulnerable women and girl. The standards of practice and guiding principles are in line with globally acceptable standards and applies to all justice actors involved GBV cases in Uganda.

The project supported the development of a Navigation Guide for use by victims of SGBV and other persons reporting SGBV. It aims to provide practical guidance for victims and persons acting on their behalf from the moment an incident occurs until the case is disposed of. The Guide therefore adopts a step-by-step approach and explains criminal justice processes and procedures at each stage. It details the rights of victims, duties of criminal justice actors and highlights what a victim might expect at each stage.

Table 2: Progress on Outcome one.

| Indicators | Baseline | Achievements |  |  | Target |
| --- | --- | --- | --- | --- | --- |
|  |  | 2020 | 2021 | 2022 |  |
| - Reduced lead times for processing GBV cases – | 2190 days (6 years) | NA | NA | NA | 18 months |
| - Level of public satisfaction with the special service delivery system and special court | NA | NA | NA | NA | NA |
| - JLOS systems and procedures strengthened with UN Women support |  |  | Yes (Partially) |  | Yes |

The costed strategy for institutionalisation of a specialised justice system/mechanism for effective management of GBV cases entailed a detailed review of systems, procedures and tools to address the root causes of delays, poor investigation, prosecution and adjudication. This has contributed to improvement in handling of GBV case as well as strengthening JLOS systems and procedures on handling SGBV cases.  Centres of excellence were established and a GBV case census was commissioned in four high court circuits of Fort Portal, Gulu, Soroti and Kampala and three magisterial areas of Kasese, Moroto and Tororo. From this exercise, a total of 2,890 GBV criminal case files and 328 GBV civil case files were isolated and profiled to establish caseload and identify those that needed to be prioritized. It also led to a deeper understanding and appreciation of the GBV problem in the judiciary. This exercise contributed a reduction lead times for processing GBV cases. According to the 2021 Annual A2J Review Report, the GBV case census has shortened the time taken for cause listing from 3 to 1.5 days. This is because the cases had already been identified unlike in the past where efforts and time was spent in finding GBV cases.

The Costed Strategy’s implementation plan proposes an inception phase that will focus on conducting desk-based baseline assessment and refinement of the intervention logic and the performance monitoring framework. Clearance will be obtained from government through a guidance circular and signing of a memorandum of understanding between the participating JLOS institutions to designate infrastructure, human and financial resources as a pre-condition to initiate the establishment of the Special Service Delivery Special Court system (SSDS) and special court for GBV. The launch of the SSDS special court for GBV cases will then follow.

Finding 7. Stakeholders revealed that the GBV case census has potential to contribute to detailed data records on GBV cases in increasing the institutional capacity of the Judiciary to generate evidence on GBV cases to guide policy, strategy, decision making and operations regarding coordinated, efficient, and effective delivery of justice for GBV survivors. In addition, sensitization on the plea bargain has been done among inmates. Although there are some demerits to plea bargain such as; the assumption that it provides soft justice for the guilty, eliminates the chance to appeal, enforcement of plea bargain agreements is weak and it still creates a criminal record, it has contributed to lessening the time for processing some of the GBV cases and weeding out of cases that do not warrant being before courts of law as a means of addressing backlog.

The project supported revisions to the criminal offences and civil suit registers for the judiciary with input from stakeholders through review meetings. Trainings were also conducted for court clerks, office attendants, judicial officers (Registrars and Magistrates), office supervisors, systems administrators and data entry clerks on the GBV case census tool. The tool embodies case type and category to ease disaggregation of GBV cases. The idea of introducing 11 centres of excellence for the project implementation aided focused interventions and monitoring. The GBV court case census was great in assisting to appreciate the gravity of the GBV problem in the judiciary”, (KII with a Judicial Officer, Kampala).

“It does not take long because when a judge handles a file in a week, time is committed to writing the judgement. Often when a case is handled, the judge takes one week to write the judgement then it is delivered at once. Files of convicts and those who are to be released are handled concurrently. Those whose cases were concocted especially those for land issues and false defilement cases are released without conviction”, (KII with a Judicial Officer, Gulu)

“Sometimes we all have court at the prisons in Mubuku. There is what we call a "plea bargain." You accept your crime before you even go to testify; you accept and agree that yes, I beat this woman, I want the court to forgive me, and I will not do it again. It was my first time. I'll never do it again, and the court can say that you go and do community service or any other appropriate sentence. This has helped a lot because somebody will finish their sentence early and your absence will not be good for your family.” (KII with JCU, Kasese District)

In addition, JLOS systems and procedures were strengthened. A GBV training manual for judicial officers was developed by JTI in partnership with CEDOVIP and UN Women. Discussions with stakeholders also show that data generation and handling of GBV cases has been enhanced through the provision of equipment’s such as computer desktops to the 11 centres of excellence as well as sets of court recordings were at two courts. Discussions with stakeholders show that this has contributed to speeding up the turnaround time for judgements as well as improvement on transcription. Despite the considerable efforts to institutionalize and the availability of special courts sessions, some stakeholders revealed that there are still challenges with case backlog and infrastructural challenges especially electricity/power to run equipment.

“With the institution of several specialized courts/divisions; International Crimes, family, criminal, civil, commercial, Standard Utilities and Wildlife, and Anti-Corruption courts, special focus is placed on these cases however there is still the growing concern of case backlog and need for prioritization”, (KII with European Union Delegation).

“A few courts are connected to prisons and remand homes, majorly in urban settings hence technology enhancement has its own drawbacks of; limited capacity to operate and maintain equipment, intermittent power/electricity supply, fuel, literacy levels and confidentiality. With the current enhancement in the judiciary’s budget in the medium-term, interventions can be sustained including technological advancements”, (KII with a Judicial Officer).

Similarly, a review of the Judiciary Annual Report reflects that case backlog is still a daunting challenge. The UPF Annual Crime reports for the period 2020/2021/2022 further shows that very low GBV cases are processed. For instance, in 2022, out of the 557 cases taken to court, only 3 cases secured a conviction. In relation to defilement, out of the 4,725 cases taken to court, only 205 secured a conviction (see table 3 below). Most of the cases are still pending investigations.

Table 3: GBV Cases reported and forwarded to court by Police (Source: UPF Crime reports 2020/21/22)

|  | Rape | Defilement | DV |
| --- | --- | --- | --- |
| Cases Reported |  |  |  |
| 2020 | 1,519 | 14,134 | 17,664 |
| 2021 | 1,486 | 14,436 | 17,533 |
| 2022 | 1,623 | 12,580 | 17,698 |
| Cases taken to court |  |  |  |
| 2020 | 612 | 5,745 | 1,359 |
| 2021 | 667 | 6,191 | 1,640 |
| 2022 | 557 | 4,725 | 1,357 |
| Cases that secured Conviction |  |  |  |
| 2020 | 16 | 794 | 400 |
| 2021 | 25 | 939 | 464 |
| 2022 | 3 | 205 | 207 |

Outcome 2: Increased use of available accessible and quality essential justice services by women and girls who experience violence

Under this outcome, the project sought to ensure increased use of available, accessible, and quality essential justice services by women and girls who experience violence. The main output was to capacitate formal justice institutions to deliver quality, coordinated essential services and fast track cases of GBV and other forms of discrimination is strengthened.

Finding 8. Under some indicator’s targets have been achieved and where targets have not been achieved, progress made is about 80%. Table 4 below provides progress on the indicators set out under this outcome.

Table 4: Progress made on Outcome 2

| Indicators | Baseline | 2020 | 2021 | 2022 | Target | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| - No. of SGBV cases disposed off | 1000 p.a |  | 619 | 682 | 900 p.a |  |
| - % of trained JLOS staff applying specialised skills and tools for managing GBV cases | 0 |  |  | 75% | 50% |  |
| - No. of JLOS actors with strengthened capacity to provide quality essential services and to fast track cases of GBV and other forms of discrimination | 0 | 105 | 278 | 402 | 1021 | 80% Achievement |
| - No. of JLOS institutions with strengthened capacity to provide quality essential services and to fast track cases of GBV and other forms of discrimination | 0 | 2 (JTI, ODPP) | 2 (Police, ODPP) |  | 3 | Fully Achieved |

Capacity strengthening of JLOS

Police Group Photo SGBV Training in Kotido from 20th – 23rd April 2022

Finding 9. JLOS actors received technical training on SGBV management under the A2J project. The training targeted several aspects including on collection, preservation of forensic evidence and management, handling of GBV cases and survivor centered services. The trainings were provided varying from actor to actor. For instance, police activity reports show that in 2022, four trainings were conducted by police across the country. The training focused on collection, preservation of forensic evidence and management. Through these training, about 349 police officers received specialized skills in collection, preservation of forensic evidence and management. In addition, scenes of crime officers (SOCO), crime investigators, child and family protection unit (CFPU), prosecutors and medical officers received training management of forensic evidence ranging from evidence collection, packaging, labeling, preservation, storage and transportation. This has improved on the quality and integrity of forensic evidence submitted for analysis. Discussions with police officers noted that trainings have equipped officers with skills on collecting biological evidence in a manner that prevents contamination and degradation and ensures integrity during all phases of the investigation and litigation. It was noted that there is improvement in storage of biological evidence in controlled environments that allow adjustments of temperature and humidity and using appropriate packaging material.

The trainings are multi sectoral in nature targeting police officers, prosecutors, judicial officers, medical personnel, and probation and social welfare officers. Police officers now appreciate prosecutor led investigations, in terms of facilitating sanctioning file. The period for sanctioning files has reduced from two months to a minimum of 4 days because now time is wasted in collecting irrelevant evidence since prosecutors guide police on what is needed”, (KII with UNW).

“We built on ongoing support from the Spotlight Programme, Initial trainings were being done under Spotlight and UNJPGBV. Strengthening synergies is clearly demonstrated by the fact that the manual for training judicial officers and police was initially developed with funding from Spotlight and UNJP GBV but rolled out with support of A2J”, (KII with UNW)

“JCU together with UN Women have trained professional lawyers but cases have been over whelming. We have trained para-social workers but the challenge is that some come and go, that is why recruitment and training is continuous”, (ODPP, Kasese).

In addition, ODPP also conducted training to strengthen the capacity of staff in handling of SGBV cases. Trainings focused on collecting, handling, preservation and presentation of forensic evidence in SGBV cases as well as handling SGBV cases under the plea bargain mechanism.  Similar trainings were also conducted for the UPF. Plea bargain trainings were also conducted and were intended to impart skills to effectively negotiate plea bargain sentences to ensure that justice is not only done but seen to be done. Similarly, review of documents show that the judiciary organized two trainings targeting court clerks and front desk officers.  These acquired knowledge and skills on customer care, institutional strengthening, their mandate in ensuring justice for all, GBV, provision of survivor centered services and security and risk management. A two-day training on customer care, survivor centered support and management of victims and cases of GBV was subsequently conducted. Discussions with participants revealed that the trainings have played a significant role in strengthening the JLOS in the processing of SGBV cases. Training for front desk contributed to enhancing customer care services that will ultimately improve trust and confidence in the Judiciary and ultimately the Justice System. It was also noted that trainings have strengthened collaboration between police and ODPP when managing SGBV cases.

“They trained us on how to handle systems like registration and recordings. Sometimes we have juvenile victims/survivors whom were accommodate in the children’s room. Using cameras, the two (judicial officer and shall communicate in a manner that makes the child comfortable”, (KII with Judicial Officer, Gulu)

“Trainings were conducted for desk officers, secretaries and clerks on interpretation skills, transcription and sign language. GBV training was conducted for 30 Chief Magistrates”, (KII with Judicial Officers, Kampala).

Findings from study districts indicate that there is no provision for special needs for Persons with Disabilities (PWDs) at community level. Many caretakers for PWDs give up seeking justice for people with special needs because of the absence of special needs services at community level such as sign language interpretation. Findings also revealed that services provided at community level are non-inclusive excluding people with special needs to obtain justice.

“There is a disconnect between the formal sign language and that which is used to communicate in the communities. Most families that have hard of hearing family members learn to communicate with them on their own without any education intervention. As such, when they come to court, it is the family members who understand what the victims are saying, which many times is differently communicated by the formal sign language.”

“GBV sessions have contributed to sustained litigation or disposal of related cases. On the down side they might be counterproductive in delaying justice or hearing of other cases, like the resource requirement for conducting criminal sessions is quite high. This could be detrimental to hearing of GBV cases that require timely investigation and adjudication. Focus on GBV case could negatively impacts on timely disposal of other cases”, (KII with European Union Delegation).

“We were trained on how to handle those cases of GBV. If the person comes in with those cases, you first need to sit the person down, you get the details, and you talk to the person. Secondly is the customer care. You know people who go to court are already people who are disadvantaged and have lost hope in life because of certain things that they have experienced out there, and they need justice. We underscore the need to maintain confidentiality. When you talk to a victim, you assure the person that whatsoever he/she will tell you shall remain confidential and what you will tell him/her will also remain confidential”, (KII with Judicial Officer, Gulu).

Survivor centered and availability of victim support services

JLOS staff received training on survivor centered services. It was noted that such training enabled them to reflect on the kind of support and services, they offer to GBV victims seeking for justice at courts because of the violence and abuse they experience. This compelled judicial institutions to ensure that survivor centred services are provided to GBV survivors/victims. Discussions show that some of courts of law have established child friendly/Safe spaces for victims.

Findings 10. The victim support, victim friendly procedures and processes have contributed to this high conviction rate. These are victim friendly interviewing skills in conducive rooms, creating rapport with the victim by de-robing and dropping the titles such as State. However, more work needs to be done in improving the attitudes of judicial officers towards victims with disabilities.

“Training on sign language emanating from challenges in leading evidence of some witnesses. There is increased use of child-friendly rooms and audio-visual facilities. Witnesses, victims and survivors, freely provide evidence when they are not in proximity with the accused/perpetrator”, (KII with JTI).

“In addressing trauma on judicial officers handling GBV cases, the judiciary is planning to recruit counsellors. Those trained are on board and are often empathetic in handling related cases. The ideal situation is to facilitate all the justice chain actors collectively the judiciary, police, ODPP, DGAL and Gender. If the judiciary is resourced and the ODPP does not have funds to summon witnesses, DGAL has not produced a forensic report and/or Judicial Officers are deployed in courts without DPP staff, then cases cannot be heard hence backlog and delayed justice”, (KII with a Judicial Officer, Kampala).

In addition, the project has also supported survivors with victim support services such soap, pampers for mother who are witnesses and came to court with babies, sanitary wear (towels, panties, cotton wool), slippers, and a change of clothes to young girls/survivors to reduce on the stigma. For instance, the 2021 Annual Project Report shows that about 140 survivors of GBV and mothers who were witnesses were supported with victim support services. It was noted that these items made the witnesses comfortable and helped with boosting their confidence during the sessions.

Use of scientific evidence

Findings 11. The A2J project also strengthened the JLOS with provision of logistics and equipment for managing and processing SGBV cases. For instance, the UPF under the Directorate of Forensics Services was supported with assortment of equipment and consumables to enhance management of SGBV, and Violence Against Women and Children (VAWC). The equipment comprised of 18 SOCO kits, 18 crime cameras and DNA consumables. This equipment has played a significant role in enhancing crime scene investigations through proper processing of crime, timely collection and transportation of evidence/exhibits from different stations to the Forensic laboratory for analysis and timely reporting of the findings to the line departments.

Utilization of cameras and SOCCO kits and DNA consumables

It was noted that cameras have aided in documentation of crime scenes leveraging on the photographic, video graphic and acoustic elements of high resolution and good quality. This has enabled the officers to collect, analyze and present electronic evidence with authenticity. Most of these have been presented to court awaiting convictions.  Similarly, DNA Consumables including DNA extraction, Quantification, Polymerase Chain Reaction and separation and detection kits and SOCO kits were acquired. SOCO kits have supported in collection, labeling, packaging of exhibits at the crime scenes and general processing of crime, mitigating the risk of contamination of the crime scene as well as preserving the officers’ physical health elements in the process of Crime Scene Management.

“The substantial investment of the A2J project targeted system strengthening, hence leveraging sustainability of actions by Government while addressing business process challenges. With the recurring requirement for consumables, SOCO kits, once the value of DNA evidence in handling cases is demonstrated, cases are processed faster, current backlog being 294 GBV cases, and justice seekers can see benefits and improved service delivery then budget allocation can be increased. Currently the Directorate requires UGX6Bn to operate at optimum but only received UGX800M. On the quarterly basis the Directorate requires UGX450M. Hence, the recurring need for consumables and training including in other specialized areas such as cybercrime”, (KII with UPF).

However, despite progress made, review of police A2J activity report for 2022 shows that there are still challenges/gaps in forensic evidence collection and management. It was noted that there is limited awareness among the police on the available equipment and role of the Forensics Directorate in managing cases of SGBV, VAWC increases number of cases handled to completion. This is coupled with the inadequate consumables to enhance timely and proper collection, packaging, storage and analysis of evidence as well as limited capacity of officers on collection, packaging, labeling, storage and transportation of Forensic evidence. This has impacted on a number of cases being defeated due to mismanagement of crime scenes or forensic evidence.

Empowerment of Women and girls at risk of violence on their rights, access to and use of quality justice services.

Under this output the project sought to support CSOs to conduct civic education and awareness on the special court system, survivor rights, legal implications of GBV, available justice services and how to access them to enhance public trust in the justice system and increase reporting of GBV cases. The project also pursuing improving community participation and feedback on the justice system through open court days, Baraza’s, and toll-free hotlines. Training of non-formal justice actors, including elders, religious, cultural leaders, and LCs, in the target districts focused on strengthening their knowledge on what constitutes GBV cases, their jurisdiction and their role in referral. The project targeted to reach 800 women and girls at risk of GBV per year with information about their rights and able to claim them. Annual project report for ULS 2022 shows that in 2021 a total of 957 (F=647, M=310) community members and 5,183 (F=4307 M=876) in 2022 were reached with information and legal aid and referral services for VAWG through the non-formal justice (see table 5 below).

Table 57: Progress on Output 3

| Indicators | Baseline | Achievements 2021 | Achievements 2022 | Target | Comment |
| --- | --- | --- | --- | --- | --- |
| No. of women and girls at risk of GBV aware of their rights and can claim them | 0 | 957 (F=647, M=310) | 5,183 (F=4307 M=876) | 800 p. a | Achieved #Reported by ULS 2022. Women accessing legal aid and referral services for VAWG through the non-formal justice systems. |

Community participation and feedback on the justice system through open court days and Baraza’s

Finding 12. The A2J project supported enhanced community outreach and awareness creation through open court days, Baraza’s, and operate toll-free hotlines. Through open court days and barazas community members received information on where and how to seek justice for GBV cases, aired their grievances with the justice system, discussed challenges with accessing justice and remedies. Open court days and barazas were held in Tororo, Mororo Fortportal, Kasese and Gulu. Through the open court days, Barazas, the Judiciary committed to organizing quarterly peer review and feedback meetings with the ODPP and Police to discuss challenges and solutions to emerging issues and hold each other accountable. It was noted that the barazas also provided an opportunity for the justice actors to come up with key actions to improve access to justice for GBV survivors. For instance, some of recommendations that came up included the need for District Committee Coordination (DCC) meetings to be organised regularly to address some of the challenges highlighted during the barazas and the need to strengthen stakeholder engagement between the implementing partners and DLG on GBV response.

“UN Women support to Court Open Days and Barazas facilitated enhanced community reach and awareness creation”, (KII with Judicial Officials, Kampala).

“We conducted one Baraza and often times use Open Court Day sessions to raise community awareness on rights issues and court processes. Open courts are conducted where community members are free to attend including parents of the victims and of the accused. Those who participate in open court days inform other community members of the information shared and the legal consequences of actions”, (KII with Judicial Officer, Gulu).

“Actually, to me we should advocate for continuous Baraza’s and funds permitting, set-up JCU offices at every parish like police posts to address justice needs. With the current presence of police posts people are afraid to break the laws.” (KII with LC Official, Kasese).

“During open court sessions and community barazas, we call upon all JLOS stakeholders including; the police, Chief Magistrate, prisons, and other legal aid providers. Justice issues in the community are discussed with input from all actors. The justice actors talk about the nature of the work they do in their offices. If anybody asks a question about prisons, the prisons officer stands up and explains and answers the question. Therefore, it is social accountability to the people. Even those who have complaints get responses there and then. And we even register cases from there.” (KII with JCU, Kasese)

In addition, it was noted that in 2020 barazas and open court sessions were halted due to COVID-19 and the lockdown restrictions and in compliance with the directive issued by the Chief Justice. However, other alternatives like use of media avenues e.g., radio transmission were used to ensure implementation of these activities. Discussions revealed that barazas and open court sessions have contributed to increase in reporting cases of GBV. This has attributed to the confidence the public has gained in the system as well as initiatives by police such as community policing and the popularisation of the GBV toll free call centre.

“The level of reporting is increasing because the sensitization that we have been making in the community has improved their knowledge and changed attitudes. Even when the cases exist, the members seem to have better capacity to address them”, (FGD with Paralegals, Gulu).

“There are some cases that cannot be handled at a local court for instance when one seriously beats a spouse, we refer the matter to police and it is later handled in court. We also refer cases such rape or defilement to the police. For example, I got a case during the Christmas period on 24th, I was from the market in my happy mood I had bought my meat, when I received a phone call. I know the law, I was trained JCU. I had to leave my food to the scene checking the girl, she too young and I called the police.” (KII with Community Based Volunteer (CBV), Kasese)

GBV toll free Call Centre

Implementing partners including ULS, JCU and police have been supported in running of GBV toll free Call Centre. Discussions show that these call centers have supported quick access to and response to GBV case. For instance, the UPF A2J report 2022 shows that 175 cases were reported through the call center.  All the 175 cases reported through the call center were forwarded to the relevant police stations for further investigations. However, further deliberations with police officers revealed that follow-up on the cases reported is still a challenge. The respondents recommended that logistics such as airtime for police officers to make follow-up is provided considering that human resources are still limited. Nonetheless, there are efforts by police to address the challenges by upgrading the system that was developed so that real time actions can be remotely accessed by the system administrators. This will support in facilitating accountability of the cases reported as well as aid reporting of accurate information to all stakeholders.

Capacity building for non-formal justice actors, including elders, religious and cultural leaders

There are other informal justice actors that play a vital role in prevention and responding to GBV. These actors include; elders, religious leaders, cultural leaders and community structures such as para legal/Para social workers. The A2J project supported the training of informal justice actors through implementing partners (ULS and JCU) to embrace and refer cases of a criminal nature to the formal justice system.

Finding 13. Non formal justice actors play a critical role in identifying, reporting, mediation and referring of GBV cases. Participants observed that the rate of GBV is reducing and this is attributed to the high level of sensitization and awareness in the fight against GBV as well as the involvement of non-traditional actors such as elders and religious leaders.

“The project was directly targeting the paralegals and community structures for the training and not the police. It is necessary for the police to also be involved in the capacity building activities”, (KII with Police, Gulu).

“When those cases are reported we process them and those that are supposed to be referred to our mother station are immediately worked on. Cases referring the LCs intervention are referred for their action. Some of them rush with somel cases without passing through the local leaders and when we assess that the case needs to be handled by the L.C I, we refer them back to him”, (KII with Police, Gulu).

“Most people begin with the LC, after failing with the LC, they approach the police. When we receive a complaint, we always inquire if they the complainant approached their LC chairperson. Have you ever explained this case to your LC chairperson? Is he/she aware? We do this because when summons are dispatched, we send it to the chairperson, and the chairperson is the one who will hand it over to the perpetrator, the husband or wife”, (KII with Police, Tororo).

However, it was further noted that despite receiving training, several challenges related to limited logistics including; transportation, stationary and social cultural norms continue to affect the operations of the non-traditional justice actors.

## Main enabling and hindering factors to achieving planned project outcomes

Findings 14. The idea of introducing 11 centers of excellence as the focus for the project implementation aided focused interventions and monitoring. The GBV court case census was great in assisting to appreciate the gravity of the GBV problem in the judiciary. Court Open Days and barazas facilitated enhanced community reach and awareness creation.

Encumbrances impacting achievement of planned outcomes included; variance in the approved Public Service Duty Facilitation for Government Officials and UN Women rates. Compensation for judicial officers (judges) for instance requires planning for three people [the Judge and two support staff-driver and bodyguard]. Once allowances are set for Government officials (approved Public Service rates), officials are entitled to the attendant pay. This meant top-up of close to ¾ of the funds for trainings judges which funds in some cases were not available/planned for. Target judicial officers had to be adjusted accordingly to Magistrates instead of Judges whose compensation does not entail support staff. Despite this adjustment, project funds provided were limited and only a total of thirty Chief Magistrates were trained.

In some instances, there was an unpredictable release of funds from UN Women hence impacting on implementation of activities. Relatedly, some activities were outsourced that project implementing partners felt could have been implemented in-house. Consultations with stakeholders indicated that this related particularly to the training of judicial officers and the court administration staff. It was done to ensure that planned activities are implemented. It was also undertaken due to delays in submission of accountabilities by the Judiciary.

Lack of joint Programming at the onset of the Project meant different entities were involved in planning of similar interventions separately. As a mitigation a taskforce was put in place and additional personnel were on-boarded as focal point to coordinate and for oversight.

The COVID-19 pandemic and its lockdowns were an impediment in service delivery with the curtailed physical contact that led to increased backlog of cases across the justice chain.

## Impact of the Project

| Impact Score | B – Satisfactory |
| --- | --- |
| Scoring: | A2J interventions project interventions are showing signs of generating positive effects but some changes are necessary especially continued strengthening of the JLOS system to deliver services effectively through implementing the strategic activities in the options paper and the service delivery standards as well strengthening efforts aimed at social norm change at the community and institutional levels. |

The project sought to ensure that survivors/victims of GBV access quality essential justice services through effective, accountable and gender-responsive justice institutions.

Findings 15. Findings show that the project implementation mainly focused at the output and outcome level. Key activities that could contributed to impact of the project were delayed. For instance, there were significant delays in development and implementation of the costed Strategy for a specialised mechanism to handle GBV cases and detailed service delivery standards for delivering quality integrated justice services. This has affected the realization of the project impact that would arise from translation of these key strategies into practice. However, given a second phase of the project, the project is on course to realize its impact.

However, this notwithstanding, there is significant progress made towards achieving the project impact. For example, discussions with stakeholders show an increase in conviction rate for SGBV cases to about 73% compared to 60.1% in 2019/20 and 50.5% in 2016. This is attributed to special emphasis of development partners on addressing GBV through technical and logistical support as well as capacity strengthening of JLOS institutions in management and handling of GBV cases. In 2022, the Judiciary organized 14 criminal sessions in selected districts that included the project’s target districts of Kampala (Criminal Division), and High Court circuits sitting at; Tororo, Gulu, Moroto, Kasese and sessions at Tororo CM among others. Overall, a total of 682 SGBV cases were disposed.

“To ensure a high conviction rate ODPP deployed trained prosecutors to participate in the SGBV sessions and provided victim friendly services. A total of 140 girls from the Centers of Excellence in Tororo, Kasese, Kampala and Moroto benefitted from victim support services that included sanitary items to reduce on the stigma. All these items ensured that witnesses were comfortable while in court and helped with boosting their confidence during the sessions”, (KII with UN Women)

“Investments in enhancing the capacity of the Forensics Directorate have led to 70% success rates/conviction in cases requiring DNA related evidence. With the enhanced efficiency there is a reduction in the turn-around time for processing cases as good quality evidence is collected and received in the laboratory”, (KII with UPF).

“The DPP is in a critical position per its mandate in the criminal justice system therefore it cannot work alone but in collaboration with other key justice players particularly judiciary, police and prisons. The multi sectoral approach in handling cases involving the police and court as well as working with MoGLSD and civil society facilitated enhanced implementation. The supportive institutional management eased implementation of the project, increasing the conviction rate of 80%.  The UN Women project management team was very supportive throughout implementation of the project in providing technical support and facilitating reporting”, (KII with ODPP).

In addition, the A2J annual report 2021 notes that 1,750 GBV cases were reported in the 20 project districts including the 11 centres of excellence in 2021. Of the cases reported, 209 were successfully investigated, and of the files taken to court, 615 cases were resolved at police stations while 926 are still being investigated. However, despite improvement in conviction rates, at police there were several challenges reported which have affected the effectiveness of the project. Some of these challenges relate to limited human resources. For instance, the UPF 2021 crime report notes that CID still faces a very high detective case ratio of 1:255. This has affected effective investigation and quick processing of cases to courts of law. Similarly, limited logistics especially transport for police officers continue to affect for quick response, investigations, movement of victims and witness.

## Efficiency and coherence of the A2J project for achievement of results

| Efficiency and Coherence Score | B – Satisfactory |
| --- | --- |
| Scoring: | The project delivered maximum results for the resources and inputs used and the implementation approach adds value—avoiding duplication of efforts, leverages partnerships and took corrective actions to minimize project implementation delays. But some changes are necessary to build capacity of partners in financial reporting, timely accountability and to increase efforts towards joint planning and coordination in implementation of project activities. |

Findings 16. The resources allocated were substantial and contributed to the achievement of the relevant outputs. UN Women has a robust financial accountability system with checks and balances that align Programmatic deliverables and financial disbursements and reporting. Stronger relationships and partnerships have been built with the respective justice institutions that create opportunities for more effective and efficient implementation of the A2J project activities. This more so with the judiciary which was on-boarded and was motivated to actively engage in coordination, leadership and implementation of A2J activities. There is evidence that UN Women’s approach to implementation of A2J project activities has built on the foundation and lessons learnt from Spotlight and UNJPGBV. This reflects synergy and collaboration between A2J and sister projects with a stake in improving access to justice for GBV survivors.

However, the evaluation found out that COVID-19 and delay in procurement impacted on timely implementation of project activities. Although some partners noted that there, were delayed disbursements, UN Women undertakes several interventions to minimize delays in disbursements. Some project outputs such as the strategy and options paper were delayed yet they were crucial to laying the foundation for strategic decisions of the project interventions.

## Availability of funds to implementing partners

The A2J project made commendable efforts to ensure that funds for implementation of project activities are available to implementing partners. The project management lead by UN Women allocated substantial resources to Programmatic activities that contributed to the achievement of the relevant outputs of the project. The analysis of allocation of project funds to the various key interventions implemented by implementing partners demonstrate that resources were adequately allocated based on the scope of work of the partner institutions. Among the key partner institutions, the bulk of the funds were allocated to the prime activities undertaken by the Judiciary in comparison to ODPP and UPF. This decision was taken by management based on the reality that UPF and ODPP were receiving additional funding from A2J sister projects (the Spotlight Initiative and UNJPGBV). Interactions with key stakeholders in the judiciary, UPF and ODPP indicate that project interventions were in line with their needs, aspirations, and expectations especially in relation to capacity building, improvements in infrastructure and procuring of the requisite equipment to support functioning of the various MDAs involved in the project. The support was perceived by stakeholders to have contributed to institutional strengthening and human resource capacity building required to improve access and quality of the justice services for GBV survivors. Based on these considerations, the evaluation confirms that there was value for money.

The total estimated budget for A2J project activities in Uganda stood at 2 million Euros. According to interviews with the project management officials at UN Women and IPs, nearly all total funds received by UN Women and the partners were spent and obligated for the project activities in line with the approved budgets by ADA.

## UN Women Programme management structure and approach and efficiency for the A2J project’s implementation

Finding 17. Long inception period characterised by delays in onboarding implementing partners especially the judiciary caused project delays although it laid a strong foundation for effective project implementation. The coordination and management of the project evolved during the inception phase of the project and this led to a long inception period. Initially, A2J was planned to be coordinated by the JLOS Secretariat given their broader mandate and already established working relationship with UN Women. A Harmonized Approach to Cash Transfer (HACT) framework assessment was consequently undertaken for the Secretariat. However, stakeholder consultations revealed that this was not the best option for coordination and funding of the project activities for the key justice institutions. A decision was taken to directly work with or operate through each institution; Judiciary, ODPP and UPF. This meant that the Judiciary had to undergo a HACT assessment as per the SoPs of UN Women and other UN agencies. UPF and ODPP were already UN Women partners. It took a while to get this done particularly for the Judiciary.

Interviews with relevant officials indicated that by the time of COVID 19 and its control measures were instituted, no agreement had been signed with the judiciary. The agreement with the Judiciary was only concluded in March 2021.There was therefore need to request for a no-cost extension [NCE] (from March 2021 to December 2022) to enable the work, particularly with the Judiciary to be undertaken and expedited. Due to the late start, activities were not completed in time, and this necessitated another NCE to 30th March 2023. The good news is that all these procedural and bureaucratic processes are done, and the necessary structures and systems are now in place build upon to accelerate implementation of A2J project related interventions. There are now much more stronger relationships with the key justice institutions with the mandate to implement access to justice interventions.

“Progressive legal framework affording redress to victims/survivors of GBV. Response institutions in place but operate at below capacity (are not adequately financed and skilled and tooled). There is therefore need to reinforce these institutions”, (KII with GSP Secretariat and European Union Delegation)

Some critical activities that had to lay the foundation of the forthcoming project activities took longer than planned due to the changes in operating context and in actors accountable for these deliverables. For example, the evaluation established that there was a delay in completion of the options paper/Strategy that was to lay the strategic direction for the A2J interventions. Initially, this was supposed to be led by UNFPA but was later taken up by UN Women. One of the reasons for taking it up was to fast track its development and bring on board the judiciary. Stronger relationships established with the judiciary were among the factors that facilitated completion of the strategy and options paper. These have now been completed and have laid a strong foundation to build upon to increase access to justice and improve quality of justice services provided to GBV survivors.

“There was a delay in developing the strategy. We did not have a chance in this case to base the interventions on the strategy as planned right from the start. This was a disconnect in the design of the Programme…but now it is available and we can base all our strategic Programmatic decisions on it”, (KII UNW).

Finding 18. Reported delay in disbursements of funds affected the implementation of project activities.

UN Women has robust system for ensuring checks and balances, and to ensure that there is accountability for deliverables in a timely manner.  The evaluation team established that there is a strong and consistent system to review quarterly work plans, financial and Programme reports and provide required feedback mainly on completeness, quality of reporting and to assess the utilisation rates of the funds. The project managers at UN Women have a system in place to ensure that regular audits are conducted in line with the standard norms of financial management practices. It was noted from interviews that delays in fund disbursement were observed by partners and this contributes to delays in implementing project activities. However, this must be understood and accurately interpreted in its context. UN Women has robust internal financial control systems that are essential for ensuring accountability and value for money. Following these procedures is crucial to remain credible before donors, government and other stakeholders. For new institutions onboarded, there are procedures to follow and it may take a while for their financial systems and practices to adapt to these financial procedures and accountability procedures and practices. The evaluation noted that although UN Women undertakes several interventions to minimize delays in disbursements, there are circumstances under which delays are caused by late accountability and reporting from some of the implementing partners. Due to delays in submitting accountability from some of the partners, UN Women/A2J management took a pragmatic decision to procure some of the equipment and supplies directly and deliver them to the respective institutions.

“Our finance officers organised training sessions with the IPs including those from the Judiciary focusing on the kind of accountability that is required and how to fill in the various forms in the financial reports. This has helped to improve the quality and completeness of the financial reports…” (KII with UNW).

“To secure additional resources for activities, the institution concerned must first account for the funds already disbursed programmatically then submit correct and accurate financial accountability. This may lead to delays in release of funds, but it is necessary as part of our accountability procedures. Accountability has been slow for some partners. They implement activities but have a challenge with timely accountability for funds. We had in some cases to start paying suppliers directly.  Instead of Police procuring items (consumables for SOCO), police preferred that UN Women pays the suppliers and that equipment fit for purpose is secured, (KII with UNW).

Finding 19. There were challenges related to differences in rates offered by A2J and those offered to judicial officers by the government of Uganda. The rates set by the Government of Uganda are higher than the UN Women rates for allowances. This was perceived as a disincentive for the judicial officers actively engaged in implementing activities supported by the A2J project.

“Variance in the rate of allowances paid between Uganda/Judiciary approved Public Service Duty Facilitation for Judicial Officers and UN Women rates as well as the unpredictable release of project funds affected project implementation”, (KII with Judicial Officers, Kampala).

Leadership of the A2J project engaged in reprogramming of project activities to accelerate implementation of project activities in a timely manner to adapt to the impact of COVID-19 and its control measures. COVID-19 and its control measures changed the operating environment of several projects including A2J. UN Women and its IPs had to weigh various options and adopt those that are least costly to continue to implement the project activities. For example, during COVID-19, the management team of the project at UN Women and the implementing partners engaged in a “reprogramming” exercise to ensure continuity of delivery of project activities through use of Information, Communication Technology (ICT) including working virtually and reducing the number of participants to engage at any one time in in-person project activities such as trainings and community dialogue meetings. Partners such as ULS and JCU for example modified and adapted meetings and community dialogue meetings to reduce the time for meetings to take less time and to take place in relatively more open places where people can easily socially distance to follow the SoPs for COVID-19.

“Different entities were involved in planning interventions concurrently. A taskforce was instituted to mitigate this with JTI as the focal point. The COVID-19 pandemic was a big setback in the justice chain. Embracing change and the resistance that may come with it for instance with the on-going shift from manual recording of evidence or conduct of business to automated or digitalized impacted on timely delivery of planned activities”, (KII with Judicial Officers, Kampala).

“Sometimes we need to communicate but lack the means to make this be in a timely manner. The first issue is the lack of finances and the second is the bad weather that restricts our movements to go and resolve any issues or even the long distance to be covered”, (FGD with paralegals, Gulu).

Provision of a good results framework and support team for tracking progress of A2J project interventions. The M&E function for the UN Women and implementing partners has provided a guiding framework for tracking progress with implementation of planned activities for the quarter/work plans and budgets. This has provided a platform for continuous assessment adherence of work plans, budgets allocated vs. expenditure and the expected outputs. According to the UN Women and the IPs, the adaptive management style helped the team to engage in reprogramming in pragmatic ways to align the project implementation strategies to the challenges posed by COVID-19 as well as the challenges that arose with the delays in onboarding the Judiciary as a key partner.

Finding 20. There were some delays in fully populating the results framework with the baseline and endline values for some of the indicators. The explanation provided was that some indicators had to wait for the judiciary to come on board and for the GBV Special Service Delivery and Accountability Systems to be developed before they could be accurately populated.

## Partnerships and coordination

Finding 21. Partnership strategy, implementation arrangements and joint programming reduced duplication of efforts and promoted efficient use of resources. As stated in the ToC, access to justice involves a multi-sectoral and multi-disciplinary approach requiring collaboration from various institutions in the justice, health and protection sectors. The A2J project particularly scored highly in terms of galvanizing efforts of the key justice institutions and streamlining the concept of the justice chain or justice being conceptualized as a chain and a holistic process with the Police being the entry point, and then over to the ODPP and the judiciary. A2J has also established links with the Community Based Services Department (CBSD) through its work with the probation and social welfare officers at the local government level particularly through the work of JCU and ULS. It has also reached out the grassroots structures particularly the para-legals and para social workers as well as community activists against GBV. All this has been helpful in improving the justice chain link at the various levels to facilitate access to justice for survivors of GBV.

Based on comparative advantage, each implementing partner was responsible for executing project activities, and in partnership with local government based on experience and qualification. During implementation, other partners such as the JTI and CEDOVIP have been able to update Manuals and these are being used to train the relevant judicial officials, clerks and administrators. Infrastructural investments through provision of audio-visual equipment and rooms that facilitate privacy and confidentiality as well as support to victims as they provide testimonies in courts have contributed towards realization of the survivor centered approach to access to justice. Special sessions on GBV are helping to address the backlog of cases and processes to institutionalise these arrangements will go a long way in sustaining access to justice. Efforts towards development of SoPs for the various institutions including the judiciary represent steps in the right strategic direction.

However, there are sentiments expressed about balancing support by A2J project to the institutions involved. Currently, support and funding is skewed more towards the judiciary and some stakeholders feel that there is need to balance this support in the ODPP and the UPF in order to maintain the required traction for holistic delivery of justice services for survivors of GBV.

UN Women has been proactive in partnering not only with the direct implementation partners but also with other agencies to enhance coordination, consultation, joint planning, and implementation of the A2J project. There is evidence that UN Women’s approach to implementation of A2J project activities has built on the foundation and lessons learnt from Spotlight and UNJPGBV. This reflects synergy and collaboration between A2J and sister projects with a stake in improving access to justice for GBV survivors.  Reflections with the project team and some partners pointed to the notion that joint Programmes contributed to reduced duplication of efforts and enhancement of efficiency. It was noted that for example, A2J interventions have built on efforts by Spotlight Initiative and UNJPGBV to develop and operationalize Manuals for building capacity of duty bearers including police, the judicial officers and prosecutors in GBV prevention and response.

“The A2J project also contributed supporting both the demand and supply side. This was done by strengthening the supply side to be able to meet the needs on the demand side in terms of access to justice. This is also as seen in the priority areas supported by the project through training officers on SGBV and provision of the equipment”, (KII with UNW).

“Sufficient information sharing, clarity of interventions and partnerships from the onset of the project are vital in facilitating and/or feeding in to on-going efforts, joint monitoring and reporting. The Secretariat did not have direct contact with ADC on the project but met UN Women at the onset of the project and later participated in a number of the A2J project interventions”, (KII with GSP Secretariat).

“UN women is viewed as a valuable partner on the A2J Development Partners Group (DPG). They are very supportive often taking on the lead in assessment/performance reviews on gender issues because of their thematic areas of expertise Addressing GBV requires a collaborative approach as it cuts across several sectors; education, health and justice among others”, (KII with European Union Delegation)

Partnerships with the Districts were also reported to have increased ownership of the project interventions by the DLGs especially in relation to the GBV prevention and response interventions including referrals that required cultivating relationships with Police, the Judiciary, and the CDSD of the various DLGs. These partnerships are contributing to institutional strengthening, system wide change and harmonization of approaches and efforts towards response to GBV and access to justice particularly for women and girls.

## Sustainability of the A2J project and its approach

| Sustainability Score | A – Very Good |
| --- | --- |
| Scoring: | The A2J project activities and achievements are likely to continue after the completion of the A2J project—built local ownership, capacity of partners and established accountability and oversight systems. And no changes are required. |

Finding 23. Key sustainability strategies adopted by the A2J project included; (a) working within the existing national frameworks, structures and systems in the Uganda Police, Judiciary and ODPP as well as the DLG especially the Community Based Services Department (CBSD) and the District Director of Health Services Offices; (b) partnerships and collaborations with sister Programmes especially the EU-UN Spotlight Initiative and the UN Joint Programme on GBV (building on their foundation and ongoing activities that have intersections with capacity strengthening for delivery of integrated GBV prevention and response services with specific focus on access to justice; and (c) capacity building at the national, subnational (focus on police, prosecutors and judicial officers) and community levels (para-legals and para social workers). The project set out to institute a Specialist Service Delivery and Accountability System/GBV special court whose implementation was delayed, and feasibility reevaluated. Consequently, a strategy for institutionalizing a specialized justice system for effective management of GBV cases and draft service delivery standards were developed, whose gains last beyond the project.

## Working within the existing policies, frameworks and systems

Finding 24: The evaluation noted that the A2J project operated within the existing policies, frameworks and systems to contribute to improving access to justice of all especially women and girls who are survivors of GBV in the target districts. A review of the documents showed that the Programme functioned within the existing international, regional and national strategic frameworks, policies, systems and structures at national, district and community levels. The Programme heavily leveraged on the existing structures in the judiciary, police and ODPP to strengthen the capacity of these institutions and systems to deliver its mandate. This is particularly important for securing sustainability of the Programme outcomes and laying the foundation for ownership of these initiatives at the national and local government as well as community levels.

At the National level, the Programme supported the development of the strategy and options paper and standards/guidelines for promoting access to quality GBV justice services led by the key justice institutions (UPF, judiciary and ODPP). The Costed Plan and Strategy to provide strategic direction for implementing and coordination of access to justice services for GBV including Special Court sessions for GBV is owned by the key institutions with this mandate. The capacity building using manuals that had initially been developed by sister Programmes including the UNJPGBV and EU-Spotlight Initiative Programme in collaboration with the ODPP and UPF and Judiciary is a positive step for integration of these trainings in the continuous professional development initiatives.

“Developing SoPs that are specific to the justice sector for GBV survivors; setting minimum standards to help stakeholders hold duty bearers accountable to address issues of impunity has been made possible through the A2J and it is likely to have a lasting impact on access to justice. The strategy that the judiciary is committed to implement with dedicated days to GBV cases, rooms to prepare people (survivors and witnesses), audio-visual equipment in the various court circuits. This is key in laying a foundation to improve access to justice.” (KII, UNW, Uganda)

“Training and capacity building initiatives targeted senior officers of ODPP, trainers supporting mentorship and coaching as a strategy for continuing/sustaining project outcomes. With the planned recruitment in the ODPP there is need for on-going training and coaching on the necessary skills required before deployment to the field or regions. Trainings also need to correspond to the trends and changing context”, (KII with ODPP).

“In fact, UN Women has helped because they have involved the local leaders in the community. Before the sessions are held, there is sensitization in the radio stations. We always go to Radio Rupiny where people are sensitized before the sessions. We use either Radio Mega or Ruping where we take the lawyers and the judicial officer and people are encouraged to call and ask questions”, (KII with Judicial Officer, Gulu).

At the subnational level, the Programme worked with several district structures including the District Health Offices (DHOs), Community Development Offices (CDOs), Police, CSOs such as ULS and JCU to coordinate response and implementation of GBV interventions at the DLG and community level. In an effort to foster ownership and sustainability, the Programme collaborated with the relevant district structures. For example, the project worked with the para legals and para social workers as well as LCs to strengthen referral pathways, mobilisation and community dialogue sessions through the barazas.

The consensus among respondents at the national and subnational level was that there was adequate involvement of the technical staff in the Programmatic design, implementation and monitoring of the various GBV interventions. More importantly, the training institutions such as the JTI and UPF have adopted the training Manuals and are likely to continue using them to train the officials as part of continuous professional development. The leadership of the judiciary, UPF and ODPP have demonstrated commitment to support continuity of these interventions although they need further support to consolidate and scale up these achievements. Modules from the training manual for police have been included in the police curriculum and professional courses for police officers which will take place at the police training schools.  SOCO trainings funded by GoU now have a module on management on SGBV cases unlike previously when they focused on general crime scene management.

Finding 25: In contrast, some respondents were concerned about the continuity of some of the directly funded Programme activities such as the trainings, procurement of various items to support operation and maintenance of the infrastructure established in courts, audio visual materials, continuing to funds to support procurement of supplies for forensics and transport means to continue improving timely mobility to collect evidence at the scenes of crime. Despite these concerns there is evidence that the support has been crucial and there is commitment to continue lobbying for resources to support these initiatives.

“Our work must continue whether the project continues or not because this is about rendering services to ourselves and we cannot stop it. We should continue to carryout work. Even when the office is closed, we shall continue with our work because we already have the knowledge. A problem shall arise when we have to travel long distances without the means. That shall make it impossible for us”, (FGD with Paralegals, Gulu).

“We have structures the CBVs, police and others, if they can continue with their work of sensitization, not sure whether those who fund the CBVs and local leader still support them. This is because they do a lot of work”, (FGD with Female Beneficiaries, Kasese).

## Partnerships and collaborations

Finding 24: Throughout the implementation process, the Programme fostered partner coordination through facilitating periodic coordination meetings at national and sub-national level and facilitating joint supervision, mentorship and monitoring of GBV through the key justice institutions especially the judiciary, ODPP and UPF. Planning and review meetings involving all partners were held. These have been helpful in reinforcing the concept of justice as a chain from entry to exit and demonstrated the complementarity between the justice institutions and other sectors.

“Creating partnerships and building lasting trusting relationships has been our prime strategy in A2J…Creating a strong partnership with the judiciary has now firmed up…we see leadership commitment among the top leadership of the judiciary.” (KII with UNW).

“We have structures in place and the institution should be able to help. As local government, we have the community development department that deals directly with these social issues and we have the technical personnel who are deployed there to support but we also have the judicial institutions in place. A cordial work relationship needs to be fostered between JCU and the main stream structures so that our main stream structures are well placed to handle these issues even without JCU”, (KII with District official, Tororo).

## Capacity building

Finding 26: The Programme adopted a system and institutional strengthening approach to enhance the structural, infrastructural and technical capacity of the institutions to plan, coordinate and deliver an integrated response to GBV and promotion access to justice. This is an appropriate and relevant strategy and is likely to contribute to sustainability of the project outcomes. The approach of working through established training institutions such as the JTI and UPF Academies was considered by stakeholders interviewed as a viable sustainability strategy. The multi-sectoral trainings across the chain of dispensing justice were perceived to have potential to improve quality and contribute to fast tracking conviction rates.

“Manuals of the judiciary, how to handle SGBV from a judicial perspective, and then a multi-sectorial manual for all the key players like the DPP, police and others were developed. This body of knowledge has not just been developed, but it has been institutionalized and is currently being operationalized for sustainability and that is key”, (KII with UN women).

“I can say that the activities might continue because sometimes JLOS also helps us. They also give us money. There are also other NGO’s that come in always to help us. The judiciary also have their own budget for that”, (KII with Judicial Officer, Gulu).

“For us who use the traditional justice systems we have resolved more cases and we have also empowered part of the traditional and religious leaders in monitoring cases. We have what we call case management record books that we use for monitoring situations of upcoming crimes within areas before sensitization can be done or intervention”, (Traditional justice Actor, Moroto).

“Our role shall continue, we who have been trained are not being paid salary but we have been trained to help the community. As a religious leader who is engaged with the church and my community is experiencing violence while these NGOs are no longer there, I cannot simply watch. Even with the LCs and cultural leaders who are already trained, we are supposed to continue working with the community”, (KII with Religious leader, Gulu).

Finding 27: However, there was a feeling among stakeholders that project did not adequately invest in community social norms change interventions to complement its investments in justice institutions that are at the helm of promoting access to justice.

Overall, the project approach of working with the three major justice institutions (ODPP, UPF and Judiciary) as well as DLG and community level structures and its focus on institutional strengthening was perceived by stakeholders as having potential for sustainability. However, there are concerns that without sufficient funding, the potential of sustainability for some directly supported interventions remains weak. Although there are indications of commitment to mobilise government to increase investments in these interventions and to institutionalise them, the existing domestic funding may be incapable of supporting long term sustainability of the human resources and infrastructure capacity at court circuits, districts and communities.

“A2J for women and vulnerable persons is a critical issue that remains relevant for the unforeseeable future. Building partnerships with institutions on the ground to attract resources or sustained advocacy of those directly involved. Interventions are majorly projectized, with a definite duration, dedicated resources and geographical focus usually determined making funding aspects difficult to outlive the project. There is therefore need for government financing in the national budget to address GBV”, (KII with EUD).

“Project resources complement funding for budgeted but unfunded priority. This therefore requires consulting the Programme or subProgramme budgets to identify such areas for support. Understanding budgeting for GBV cases as criminal investigation of GBV cases is costly both at institutional and Programme levels is critical”, (KII with GSP Secretariat).

## Ability of A2J partners to finance similar interventions

Finding 28: The current enhancement in the judiciary’s budget in the medium-term interventions can be sustained including technological advancements. The are concerns that the Judiciary and other actors (police) may not be able to maintain the technological high-tech equipment. The project has potential to generate impact if the UN Women support is fully integrated into institutions. Joint cause listing during GBV sessions has facilitated weeding out cases with DPP withdrawing in “non-starter cases”, those pending evidence, and following gender victim assessment (KII with ODPP).

## Integration of human rights approach and gender equality principles in the design and implementation of the project

| Intergration of the Human Rights Approach and Gender Equality Principles | Score: A – Very Good |
| --- | --- |
| Scoring: | The A2J project activities were adequately designed, implemented and monitored to promote the meaningful participation of both rights holders and duty bearers and to minimize negative effects of social exclusion. No changes were required. However, there are emerging issues such as the need for a stronger focus on social and gender norms and the needs of PWDs that should be prioritised in future programming to facilitate access to justice. |

Finding 29: Overall, the A2J Programme centered around promotion of human rights and gender equality right from its conceptualization, the ToC, goal, outcomes and outputs. The goals and priority actions in the options paper and its costed action plan have at their core addressed the human rights of women and girls affected by GBV and ensured that mechanisms to promote their access to justice are institutionalized. This speaks directly to the notions of human rights and gender equality. The key target beneficiaries for the project that include the disadvantaged categories of the population especially women and girls who experience GBV or are at risk of GBV in the catchment areas of the High Court Circuits reflect the focus on gender equality and human rights. The Programme design was well targeted to vulnerable populations, particularly with respect to the protection and promotion of gender, human rights and disability inclusion. The project targeted districts with poor human rights indicators in various regions in Uganda including Karamoja and northern Uganda as well as South Western Uganda (particularly Kasese district).

“Some victims do not know their rights, somebody can be assaulted, their land can be grabbed, if this person had the knowledge they would be helped. The victims have a right to shelter they have a right to food they have a right to legal services and they also have a right to medical examination all these are mandated to the victims,” (FGD with the Para Social Workers in Moroto).

Finding 30: The project focus is also in tandem with the key international and national policy, legal instruments and guidelines that underscore the human rights-based approach and gender equality including the CEDAW, the Cooperation Framework theory of change (UNSDCF 2021-2025), Principles of Leave No One Behind (LNOB), HRBA, Gender Equity and Empowerment of Women, Sustainability and Accountability. At the national policy level, the Project was aligned to policies and laws on GBV, including the national policy on elimination of GBV, the Gender Policy, the DVA, the amended Succession Act, and the Penal Code Act, among others.

Finding 31: The focus on building capacity of the key duty bearers in the Judiciary, ODPP and UPF in mainstreaming human rights and gender equality in the course of their work; the investments in efforts to create a conducive environment for victims or survivors of GBV and the witnesses to be able to boost their confidence to testify and to offer them confidentiality are all steps in the right direction to institutionalise and build capacity to facilitate access to justice for survivors of GBV through promoting a survivor centered approach and the HRBA to social justice for the those most affected by GBV.

“Witnesses are protected because while in the court. We have court orderly that protect them. When they come, and are done with their testimonies, immediately we pay them transport, food and if they sleep here, we pay them for accommodation. Sometimes we do not disclose the witnesses to the public. The only persons who will be knowing the witnesses are the court processors and the court”, (KII with Judicial Officer, Gulu).

Similarly, the A2J project also had a strong focus on engagement and involvement of community structures in promoting gender equality, human rights and GBV response at the community level through engagement of community structures such as the non-formal justice actors, paralegals and parasocial workers by providing them trainings, materials and support to follow up GBV cases, referrals and working with them to conduct community dialogue meetings or barazas. Reports from stakeholders reveal that this has helped to increase awareness on human rights and pathways for access to justice for survivors of GBV prevention. Similarly, the strategy of increasing access to justice for survivors of GBV through legal aid and mobile court sessions was directly responding to promoting gender equality and access to the justice.

“It has helped us because the backlog has now gone down. When they give us money, we conduct a session and this reduces on the backlog. The community out there also learnt that for such cases, you are bound for conviction”, (KII with Judicial Officer, Gulu).

“I learnt from the JCU. I am not a person of the law but I go for workshops with them, they always train us and communities. We now have some basic knowledge and we have been empowered on where to go and/or refer people in need of justice services. We know what to do when there’s a problem, you have to report immediately and then you follow it. l have learnt a lot from JCU”, (KII with Traditional/cultural Leader, Tororo).

Finding 32: However, the evaluation team noted that the project has not invested adequately in the social norms and gender norms change for both the duty bearers, survivors and the community members yet this is very imperative in strengthening the prevention of GBV and for promoting human rights and gender equality. There is therefore need to innovate strategies to strengthen the balance between GBV response and GBV prevention particularly through investment in social and gender norms change strategies.

It was also noted by the evaluation team that the project has not explored the concept of intersectionality and how this affects the ability of women and girls to navigate the barriers and make use of the enabling factors to exercise the individual and collective agency to access justice. This points the need to review the ToC to add aspects of facilitating survivors to exercise their individual and collective agency to overcome barriers related to social norms, gender norms and other structural barriers to access to justice in the context of GBV. This may also extend to understanding how institutional norms in the UPF, Judiciary, ODPP and lower-level justice structures such as LCs and the non-formal justice actors influence their decisions and actions of promoting justice for survivors. Strategies can be explored on how to increase agency of actors in the formal justice institutions to translate the laws and policies for GBV prevention and response into action including committing resources and time to facilitate access to justice following the gender equality and human rights-based approach.

“People are aware of Police Form 3 for cases of assault or sexual offences that is required to be filled as the first process. Without that form your case is not listened to. Community knowledge about their rights has increased following our community sensitization sessions. They approach us, LCs or the police whenever their rights have been violated”, (FGD with Paralegals, Gulu).

Finding 33: In specific regard to the integration of LNOB principles, the evaluation observed that the project followed the SDGs, UN Women and donor commitment on LNOB and Human rights approach. However, the evaluation found there have been weaknesses observed in systematically integrating focus on people with disabilities and their unique needs in respect to access to justice in a more holistic manner. We note that there was some attention to sign language and training of interpreters but this was perceived by stakeholders to be critical but only one of the many structural barriers for access to justice services for people with disabilities. Therefore, although there are a few examples highlighting that needs of women, girls, boys and men with disabilities were considered in the project design the project lacked a holistic inclusiveness strategy and a vulnerable and marginalized group plan to ensure better inclusiveness of particularly PWDs.

## Lessons learned and promising practices and innovations.

A number of good practices were identified within the A2J project and have the potential for replication. Several lessons learned also emerged that can guide future programming.

Finding 34 Good Practices:

- The strong technical capacity of the Country Office and staff gave legitimacy to UN Women. The reputation of UN Women staff for technical competence instilled confidence among key national justice institutions (the Judiciary, UPF and ODPP) as well as the CSO partners to engage and participate in the project activities in line with their mandates. This provided space for constructive engagement with duty bearers to contribute to the various project outputs and outcomes.

- The UN Women Country Office has cultivated and demonstrated long-term consistency and dependability through teamwork, mutual respect and being approachable in its strategic partnerships with the key Ministries Departments and Agencies especially the MoGLSD, UPF and ODPP. It has applied the same approach to the Judiciary that has seen building relationships that have culminated into leadership commitment from the top management and leadership of the Judiciary to A2J priority activities including those identified in the costed Strategy for a specialised mechanism to handle GBV cases among others.

- Maximizing the value-added of partnerships, working relationships and connections at all levels especially at the local government and community level through working with existing structures such as paralegals, parasocial workers, community activists, non-formal justice actors has proven itself as a defining factor in the A2J project’s ability to leverage limited resources for larger results within diverse and complex regions including Karamoja and northern Uganda.

- Survivor centred approaches are crucial in responding to risk and vulnerability and the unique needs of the GBV survivors to enable them to be confident and have the self-esteem needed to pursue justice throughout the justice chain. A2J has started several innovations ranging from trainings, survivor support, installing audio-visual equipment and rooms to offer confidentiality. These are good practices that should be institutionalised and continued throughout the justice chain.

- Emphasis on evidence collection and prosecution led investigations and approaching justice from a justice chain and multisectoral approach was identified by stakeholders as a promising practice. A2J has laid the foundation for strengthening the multi-sectoral and justice chain approach that should be further strengthened and sustained.

Findings 35: Lessons Learned:

- Undertaking technical and advisory roles and responsibilities within the relevant MDAs takes quite a long duration given the bureaucratic and institutional frameworks and mandates as well as the sensitivity of issues related to access to justice for GBV. It is therefore important to take the complexity of working with justice institutions in mind while making decisions on the duration of the projects.

- Training/capacity building of justice agencies, especially on international mechanisms and standards, reporting and recognizing gender, GBV and human rights violations and abuses was identified by stakeholders as highly important and impactful. With staff turnover and staff transfers however, the impact of capacity building could be a challenge to sustain. The UN Women Country Office and partners will need to continue to expand and innovate the training approaches and engage with the UPF, ODPP and Judiciary to find other measures to mitigate these challenges.

- A strong and adequately staffed and funded Monitoring, Evaluation and Learning (MEL) function is crucial to effective design, review and tracking of the alignment of the project to the ToC, timely populating of the baseline values and targets as well continuous learning and adaptation of project strategies to align with changes in the context. At present, the team noted that there were gaps in populating some of the indicators and targets in the results framework. This is also complicated by the fact that there is no central data base that collates and synthesises data from the justice institutions. This context needs to be considered while designing, staffing and budgeting for the MEL to support the project.

- Finding a delicate balance between strengthening both GBV response and Prevention is crucial given that both strands are crucial in improving access and the quality of justice. The focus particularly on social and gender norms change at the institutional and community level is imperative.

- Building on successes, achievements and lessons from previous and ongoing programmes is important for fast tracking achievements of project deliverables, capacity building and sustainability. A2J did well by building on and leveraging efforts of the ongoing projects such as the EU Spotlight Initiative, UNJGBV among others. However, there is need to be intentional in identification of other ongoing initiatives in the judiciary, UPF and ODPP as well as MGLSD to leverage and draw lessons to inform programming.

- While developing service delivery standards particularly for the justice institutions, there is need to pay attention to the mandates, unique organisational culture and operating environments, the complexity and feasibility of enforcement of the standards as well as the resource implications. The balance between being very specific and prescriptive and remaining broad enough to allow room for innovation and navigating the complexity of the operational environments of each institution in the justice chain at various levels in important to maximise effectiveness, efficiency and contextualisation to the sensitivities of each institution.

# CONCLUSION AND RECOMMENDATIONS

## Conclusion

Relevance (Score A):

Strengths: Overall, the project is relevant to the access to justice priority issues in Uganda in the context of GBV. The project also adapted to emerging changes in the context due to challenges like the COVID-19 pandemic. It is also aligned to the SDGs, the international instruments such as CEDAW as well as to the NDP III and the legal and regulatory framework policy frameworks on GBV and access to justice in general. (See findings 1, 2, 3, 4)

Weakness: The emerging evidence shows the need for the A2J project to pay stronger attention and focus on the root causes of GBV/VAW including the harmful social and gender norms and other structural factors that are context specific at the community and institutional levels.

Effectiveness (Score B):

Strengths: The project achieved most of its targets and its outputs and outcomes. The project contributed to capacity building of the key justice institutions and set a strong foundation for improving access to justice for GBV survivors. It succeeded in building trust and establishing strong relationships particularly with the judiciary as well as the ODPP and UPF.  With the strong relationships established and the costed strategy/options paper in place, the A2J project is at a stage where if there is a second phase, there is a very high likelihood that effectiveness and efficiency as well as impact will score very highly because the fundamentals have been established (see findings 8, 9.10, 11, 12, 13).

Weaknesses: However, there were significant delays in development and implementation of some of the key strategies such as the costed Strategy for a specialised mechanism to handle GBV cases and detailed service delivery standards for delivering quality integrated justice services. These along with the COVID-19 pandemic affected the pace of implementation of the A2J project activities (see findings 5, 6, 7).

Efficiency (Score B)

Strengths: The project delivered maximum results for the resources and inputs used and the implementation approach adds value—avoiding duplication of efforts, leverages partnerships and took corrective actions to minimize project implementation delays. UNW has a robust financial and accountability system and procedures that contribute to efficiency (see findings 15, 16).

Weaknesses: However, some changes are necessary to build capacity of partners in financial reporting, timely accountability and to increase efforts towards joint planning and coordination in implementation of project activities. In addition, key activities that lay the foundation of the project such as the options paper and the service deliver standards were completed late/delayed. Weaknesses in the M&E especially ensuring that all baseline values for indicators and targets are populated is critical (Findings 15, 16, 17, 18, 19).

Sustainability (Score A)

Strengths: The project worked with and through established structures at the national, regional, district and community level in its work on capacity building, awareness and demand creation, developing the strategy/options paper for handling GBV cases as well as developing the draft detailed service delivery standards for delivering quality integrated justice services. There is clear expression of capacity enhancement, ownership and stakeholder engagement at all levels. This implies a strong foundation for sustainability of the project achievements. (See findings 24, 25)

Weakness: More investments are definitely required to enable translation of the costed strategy and the service delivery standards into practice. These activities were developed but rather late and their operationalization is not yet realized. This will be impactful in improving the access and quality of justice services from entry to exit or the justice chain (Finding 28).

Additionally, the evaluation team notes that the major focus for the current A2J project learned more on institutional strengthening and capacity building (supply side) although there were also commendable efforts aimed at community engagement through the community dialogue or barazas and building capacity of non-formal justice actors and para-legals/para social workers to facilitate awareness and dialogue on GBV response as well as prevention at the community level and with the GBV survivors. The focus on comprehensive prevention particularly through social and gender norm change strategies did not receive adequate attention both at institutional and the community level. Any follow-on projects should prioritise this to balance the focus on both prevention and response to GBV given that they are both important in promoting access to justice. (See finding 27)

Integration of the Human Rights Approach and Gender Equality Principles (Score A)

Strengths: Overall, the A2J project activities were designed, implemented and monitored to promote the meaningful participation of both rights holders (especially GBV survivors and their families) and duty bearers (Major Justice Institutions especially UPF, ODPP and Judiciary) and to minimize negative effects of social exclusion (See findings 29, 31).

Weakness: However, there are emerging issues such as the need for a stronger focus on of concern that need to be addressed in future programming highlight the need to address social and gender norms human rights and gender equality nexus as well as the needs of PWDs that should be prioritised in future programming (see findings 32, 33).

## Recommendations

Some of the recommendations highlighted below were suggested by; a) key stakeholders (the development partners, implementing partners, beneficiaries, survivors), b) the evaluation team in reviewing available literature and stakeholder consultations. The recommendations were validated by ERG and stakeholders during a presentation and review of preliminary findings hosted by UNW Uganda office.

| Recommendation 1: There is need for key stakeholders to further consolidate, strengthen partnership and collaboration between the Judiciary, ODPP and UPF as well as the relevant DLG departments especially with the District Health Office and the Community Based Services Depatment at all levels in all project processes including design, implementation and monitoring and evaluation. These are crucial for delivery of a holistic approach through the chain of justice from entry to exit and for effective coordination, institutional/systems strengthening and sustainability. |  |  |
| --- | --- | --- |
| How to do |  | Stakeholder engagement workshop of all stakeholders to plan and discuss the implementation of project activities. |
| Responsible actor(s) |  | UN Women, Judiciary, UPF, ODPP, DLG, ULS, CEDOVIP and JCU |
| Urgency |  | Immediate |
| Impact |  | High |
| Difficulty |  | Low |
| Link to conclusions |  | Aligned to RELEVANCE , EFFECTIVENESS, SUSTAINABILITY (Finding 1,4, 10,11, 24, 25) |
| Recommendation 2: Given the level of complexity and bureaucracy involved in working with the key justice institutions and that some of these institutions like the judiciary have just come on board recently, UN Women Country Office and its implementing partners should engage with donors to advocate for long term funding or longer duration of funding for projects to enable adequate time for project inception, implementation and to improve the quality of outputs and deliverables and to realise greater impact. |  |  |
| How to do | Lobbying donors and development partners for increased long-term funding of project activities. |  |
| Responsible actor(s) | UN Women, GoU led by the Judiciary, UPF, ODPP and MoGLSD |  |
| What if it is not done | Long-term deliverables may not be achieved |  |
| Urgency | Immediate |  |
| Impact | High |  |
| Difficulty | Low |  |
| Link to conclusions | Aligned to EFFICIENCY and Finding 15, 16, 17, 18, 19 |  |
| Recommendation 3: Now that a costed Strategy/options paper for a specialised mechanism to handle GBV cases and service delivery standards are ready for roll out, UN Women Country Office and the project implementing partners should review the A2J project ToC, work plan and approach to align it to the strategy and delivery standard with a workplan developed to fast track rollout. This implies that donors and national justice institutions should consider a second phase of the A2J project aligned to the costed strategy/, service delivery standardsoptions paper. |  |  |
| How to do |  | Through workshops and engagement |
| Responsible actor(s) |  | UN Women, donors and all implementing partners |
| What if it is not done |  | There will be a delay in the implementation of project and the strategy/options paper may not be translated into action |
| Urgency |  | Immediate |
| Impact |  | High |
| Difficulty |  | Low |
| Link to conclusions |  | Aligned to EFFICIENCY, EFFECTIVENESS and SUSTAINABILITY and Finding 5, 6, 7, 15, 16, 17, 18, 19 |
| Recommendation 4: UN Women and its partners should develop and implement capacity building in financial management and accountability to build competencies of IPs in timely accountability for funds received to address the delays in accountability and therefore implementation of project activities. |  |  |
| How to do | Organise a workshop targeting financial officers/acounts personnel for the IPs |  |
| Responsible actor(s) | UN Women and all Implementing partners |  |
| What if it is not done | There is risk of delays in disbursements and accountability for funds affecting timely implementation of activities. |  |
| Urgency | Immediate |  |
| Impact | High |  |
| Difficulty | Low |  |
| Link to conclusions | Aligned to EFFICIENCY AND EFFECTIVENESS and Finding 15, 16, 17, 18, 19x |  |
| Recommendation 5: Given the diversity of needs in each sector, UN Women and its partners should review and identify the cross cutting needs common in the three sub-sectors (judiciary, ODPP and UPF) as well as the needs specific to each partner and develop and implement a capacity building plans relevant to each institution and across the institutions. Implementing partners should be supported to track and document use of knowledge and skills imparted through training interventions. |  |  |
| How to do | Organise Project review workshop for each partner to set key priorities and to identify cross cutting priorities that benefit all partners to improve the effectiveness and efficiency of the justice chain from entry to exit. |  |
| Responsible actor(s) | UN Women and all Implementing partners |  |
| What if it is not done | There is risk of not addressing key priorities specific to sectors or institutions |  |
| Urgency | Mid-term |  |
| Impact | High |  |
| Difficulty | Low |  |
| Link to conclusions | Aligned to RELEVANCE, EFFICIENCY AND EFFECTIVENESS and Finding 1,2, 4, 10,11, 24, 25 |  |
| Recommendation 6: Based on the lessons learnt and the good practices especially related to survivor centered approaches, improvements in evidence collection and use as well as advantages of joint capacity building, UN Women and its partners should advocate for sharing the lessons and scale up of the good practices to other regions. Policy and programming briefs should be written to facilitate sharing lessons and promising practices. |  |  |
| How to do | Organise Project review workshop for each partner to set key priorities and to identify cross cutting priorities that benefit all partners to improve the effectiveness and efficiency of the justice chain from entry to exit. |  |
| Responsible actor(s) | UN Women and all Implementing partners |  |
| What if it is not done | There is risk of not scaling up lessons and good practices |  |
| Urgency | Mid-term |  |
| Impact | High |  |
| Difficulty | Low |  |
| Link to conclusions | Aligned to conclusions on EFFECTIVENESS and SUSTAINABILITY and Finding on lessons learnt (35) and good practices (34) |  |
| Recommendation 7: There is need to be intentional in being more equitable in terms of investments in capacity building and institutional strengthening across the justice institutions to realise justice from entry to exit. |  |  |
| How to do | Review gaps and set priorities for each institution/programmes and sub programmes |  |
| Responsible actor(s) | UN Women, Implementing partners and Secretariats (AJP and GSP) |  |
| What if it is not done | There is risk of being skewed in investments rather than equitable. This can be a disincentive and can affect efficiency. |  |
| Urgency | Mid-term |  |
| Impact | High |  |
| Difficulty | Low |  |
| Link to conclusions | Aligned to EFFECTIVENESS and EFFICIENCY and Finding 8, 9, 10, 12, 34 and 35) |  |
| Recommendation 8: Given the imprtance of investing in both prevention and response, there is need for UN Women and partners to consider investment in social norm change to complement the access to justice components of the project. This is because social norms may deter reporting of cases and may continue to justify violece against women and girls. Also social and gender norms have an effect on the decisions and actions taken by officials in UPF, ODPP and the Judiciary as well as the legislature and cabinet. Therefore social norm change should not focus only at the family and community level but also on changing harmful institutional norms and organisational culture that may be rooted in harmful partriarchal widely accepted beliefs and VAWG |  |  |
| How to do | Identify strategic actions to contribute to social norm change and create pathways between prevention and response |  |
| Responsible actor(s) | UN Women and all Implementing partners (state and non-state actors) |  |
| What if it is not done | There is risk of not balancing GBV response and prevention |  |
| Urgency | Immediate |  |
| Impact | High |  |
| Difficulty | Low |  |
| Link to conclusions | Aligned to RELEVANCE,and SUSTAINABILITY and Finding 1,3,4, 27, 32, 33 |  |
| Recommendation 9: Need to strengthen the M&E sytem to collect baseline information and populate all indicators in the results framework, set realistic targets as well as to be able to track impact. For example, the M&E should go beyond reporting numbers and report on the quality of outcomes of cases of GBV across the spectrum as well as the impact on GBV survivors accessing justice. |  |  |
| How to do | Organise Project review workshop for each partner to set key priorities and to identify cross cutting priorities and indicators, targets that benefit all partners to improve the effectiveness and efficiency of the justice chain from entry to exit. |  |
| Responsible actor(s) | UN Women and all Implementing partners |  |
| What if it is not done | There is risk of not scaling up lessons and good practices |  |
| Urgency | Mid-term |  |
| Impact | High |  |
| Difficulty | Low |  |
| Link to conclusions | Aligned to EFFECTIVENESS and EFFICIENCY and Finding 6, 7, 20 |  |
| Recommendation 10: Need to fast track the review and finalisation of detailed and concrete Service Delivery Standards and Procedures covering all the steps towards delivering Quality Integrated Justice Services. This is crucial for improving coordination and harmonisation of the delivery of justice to the GBV survivors and for promoting the good practice of justice being understood and operationalised as a chain. It will also facilitate monitoring of the quality as well as in holding the relevant duty bearers accountable. |  |  |
| How to do | Organise Project review workshop with representatives from each partner to review the draft service delivery standards and procedures and align them to their mandates and operational/instutional frameworks. This may call for organising a residential workshop with all partners in the room to review, refine and adopt the standards. These can then be further validated in the regions for ownership and adaptation. |  |
| Responsible actor(s) | UN Women and all Implementing partners |  |
| What if it is not done | There is risk of not following standardised procedures/service standards as well as not being able to hold stakeholders accountable to specific standards. |  |
| Urgency | Immediate |  |
| Impact | High |  |
| Difficulty | Low |  |
| Link to conclusions | Aligned to EFFECTIVENESS, EFFICIENCY and SUSTAINABILITY and Finding 4, 7, 15, 35, 35 |  |

# REFERENCES

- A Baseline Survey for Benchmarking the Impact of the GBV Special Service Delivery and Accountability System/Institutionalised Specialist Justice System and Structure for Management Cases of GBV Against Women and Girls

- Access to Justice Project Budget

- Access to Justice sub program strategic plan 2020/21-2024/25

- ADA Second Progress report 1st November 2019 – December 2020

- Annual SDG progress report 2021/2022 with focus on SDG 5 and 16

- Final Proposal for Institutionalizing Special Courts for GBV in Uganda

- Gender snapshot report 2022

- Governance and Security Program Implementation Action Plan, 2020/21-2024/25

- Governance and Security Programme Secretariat Report of Training on the JLOS Gender and Equity Mainstreaming Strategy, 19-21 January 2022

- JLOS Annual Performance Report 2019/20

- JLOS Gender and Equity Mainstreaming Strategy, July 2019

- Judiciary Court Open Days to Fort Portal and Kasese Courts (Access to Justice Project Centres of Excellence), Mort, 1

- National Policy and Action Plan for Elimination of Gender Based Violence, MoGLSD, August 2016

- Progress Report Austria Development Agency Annual Report 2021 Final

- Project Results Framework and Project Indicator Performance Tracking Table Revised

- Revised Project indicator definitions

- Third National Development Plan 2020/21-2024/25

- Uganda Police Force, Annual Crime Report, 2020 and 2021

- UN Women Handbook on Gender Responsive Evaluation

# ANNEX I: EVALUATION MATRIX

| Evaluation Criteria | Main Evaluation Questions | Indicators data | Data collection methods | Data source |
| --- | --- | --- | --- | --- |
| Relevance The extent to which A2J Project Objectives are responsive to the needs and priorities of women, girls, partners and stakeholders and are aligned with government and UN priorities, policies and strategies. | - Was A2J project aligned with international gender equality human rights norms? - Was the project aligned with national policies, Programmes, or priorities? - Were the Programmatic methodologies/strategies appropriate to address the identified needs of beneficiaries and stakeholders? - Was the choice of partners most relevant in addressing the Programme needs? Were the choice of interventions most relevant to the situation in the target thematic areas? Was the technical design of the project including the ToC relevant? - Did the intervention target the underlying causes of gender inequality? - To what extent have lessons learned been shared to inform country office Programming? | - Evidence of alignment with national policies, frameworks and plans on EVAW, UNSCR1325, National Policy on Elimination of GBV the UNDAF and other key instruments on GEWE - Respondent perceptions, - ToC design | - Desk Review and analysis of various documents and Reports including annual reports. - In depth Interviews with key stakeholders implementing partners at national and sub national - Focus group discussions (FDGs) with para-legals, cultural and religious leaders (informal justice actors), women and men in the communities who have been benefited from A2J interventions and services | - A2J Project M&E Reports - A2J Programme staff - Officials from the involved MDA - National and international strategies and plans, - UNDCF - Websites of UN agencies, local media, Ministries and partners - Communication materials - Project beneficiaries |
| Effectiveness The extent to which the A2J project’s objectives were achieved and the interventions’ success in producing the expected outputs and achieving milestones were met. | - To what extent have planned outputs been achieved on time? - Did the interventions contribute to the expected outcomes? - What unexpected outcomes (positive and negative) have been achieved? - What has UN Women’s contribution been to the progress of the achievement of outcomes? - Did the Programme implementation partners have access to the necessary skills, knowledge and capacities needed to deliver the project? - What were the main enabling and hindering factors to achieving planned outcomes? - To what extent has A2J project interventions been mainstreamed in UN joint Programming such as UNSDCF? | - Evidence of achievements against outputs indicators and Testimonies of interviewees on delivered outputs, outcomes and their quality. | - Analysis of results and baseline - Interviews with officials from involved MDAs and NGOS - Focus group discussions (FDGs) with para-legals, cultural and religious leaders (informal justice actors), women and men in the communities who have been benefited from A2J interventions and services - Analysis of training report - Analysis of activity, monitoring and missions’ reports - Analysis of other relevant data | - UN Women in Uganda - A2J Programme staff - Officials from the involved Ministries (ODPP, UPF, JTI, Judicial Officers, MGLSD, MoJCA, DLGs) - Local Media, CSOs, NGOs (e.g., Justice Centres, Uganda Law Society) - All relevant stakeholders Various training reports and materials available - Monitoring and progress reports - M&E plans - Reports from implementing partners. - Beneficiaries |
| Efficiency/Coherence The extent to which the SN and its interventions delivered maximum results for the resources and inputs used (funds, expertise, time, etc.). The Coherence is looking at the compatibility of the intervention with other interventions in a country, sector or institution | - Were the outputs delivered appropriate to resources used? - To what extent did the UN Women Programme management structure support efficiency for the project’s implementation? - What is UN Women’s comparative advantage in implementing this type of Programme compared with other UN entities, other stakeholders in A2J Programming and key partners? - To what extent did the project’s implementation approach add value while avoiding duplication of efforts? - How well were resources and risks managed to ensure results for the Programme? - Did the project management team manage Programme implementation delays efficiently and what corrective actions were undertaken? - Was a Results Based Management system established and implemented for the Programme? | - Risk assessments including effect of COVID-19 and mitigation strategies. - Level / degree of involvement of stakeholders in coordination mechanisms - The extent to which resources / inputs were allocated in a timely manner and used to achieve project’s outcomes and objectives. - The extent to which synergies available were efficiently used by the Programme management. - Level of cost effectiveness and timeliness of the Programme execution | - We will review the budgets and expenditure on the different project activities as well as the feedback from stakeholders about the implementation modalities/strategies and how cost effective they are perceived to be in relation to similar projects. - Analysis of means of verification (MoVs) - Programme work plans and budget revisions - Review and analysis of monitoring & progress reports - Coordination reports -Interviews with officials from ministries, UN staff, partners, stakeholders and donors | - UN agencies - Financial reports - Monitoring and coordination reports - M&E reports - Reports from implementing partners. - Work Plan and Budget Documents - Stakeholders and beneficiaries - Reports to donors |
| Sustainability The likelihood of a continuation of the results after the completion of the A2J project | - Is there local ownership and are there local and national champions for the intervention? - To what extent was capacity of partners developed to ensure sustainability of efforts and benefits? - What local accountability and oversight systems have been established to support the continuation of activities? - What are the recommendations for similar support in future? (What are the priority future interventions based on the current evaluation findings). | - Existing or updated legal frameworks in place. - Accountability framework - Evidence of sustainability focused capacitating processes to the benefit of the implementing partners. | - Documentary analysis - Monitoring and progress reports; - Analysis of any studies or reviews generated by UN women, donor and stakeholders | - Reports from implementing partners. - Beneficiaries - All stakeholders - Homepages of partners |
| Impact The extent to which the intervention has generated or is expected to generate significant positive or negative, intended or unintended, higher-level effects. | - To what extent has the Programme interventions generated or is expected to generate significant positive or negative, intended or unintended, higher-level (capture the significance, the scope, and the transformative nature of the effects) effects? | - Evidence of significance and potentially transformative effects of the intervention. - Evidence of long term social, changes achieved by the A2J project implementation. | - Analysis of the results achieved by capacity building and development & skills development of those involved. - Existing legal and institutional frameworks of A2J related interventions and issues. | - Beneficiaries - All stakeholders - Strategic Plans of partners |
| Gender and Human Rights The extent to which the A2J project activities were designed, implemented and monitored to promote the meaningful participation of both rights holders and duty bearers and to minimize negative effects of social exclusion | - To what extent is theA2J project changing the dynamics of power in relationships between different groups? - Has the A2J project been implemented according to human rights and development effectiveness principles: Participation/empowerment; Inclusion/non-discrimination; National accountability/transparency; anti-corruption; and climate and environment | - Degree / Level to which GE&HR principles were taken into consideration in all the Programme phases (Design, Planning, Implementing, M&E and Reporting) - Evidence of active involvement of marginalized groups during the Programme intervention | - Review & analysis of relevant documents - In-depth interviews and FDGs with beneficiaries and grassroots implementers such as para legals, cultural and religious leaders involved in the project. | - Programme Staff - Monitoring and coordination reports - Reports from relevant stakeholders and beneficiaries - Reports on implementation and reform of legal and institutional frameworks and National/ district plans |

# ANNEX II: TERMS OF REFERENCE

# TERMS OF REFERENCE

END OF PROJECT Evaluation

Project name:  Women and Girls Access to Justice Through Effective, Accountable and Gender-Responsive Institutions

Location: 	Uganda

Application Deadline:	December 3rd 2022

Type of Contract:	Special Service Agreement (SSA)

Post Level:	2 National Consultants

Languages Required:	English

Starting Date:	December 14th, 2022

Typology of the consultancy:	Individual

Duration of Contract:	30 working days

# UN Women Organizational Context

The United Nations Entity for Gender Equality and the Empowerment of Women (UN Women), grounded in the vision of equality enshrined in the Charter of the United Nations, works for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security. UN Women provides support to Member States’ efforts and priorities in meeting their gender equality goals and for building effective partnerships with civil society and other relevant actors.

UN Women operationalizes this through Flagship Programming Initiatives (FPIs) developed to achieve transformative results for gender equality and women empowerment. The Flagship Programme on Women’s Access to Justice addresses bias and gender discrimination in justice delivery. Eliminating gender discrimination across the justice chain is critical for protecting women’s economic assets, bodily integrity, voice and agency.

The Uganda Access to Justice project contributes to the flagship Programme. The project’s implementation began in November 2019 and is set to end on 31st December 2022. The project is aligned and contributes to the Sustainable Development Goals (SDG) -specifically Goal 5 on Gender Equality and Goal 16, which seeks to promote peaceful and inclusive societies for sustainable peace and development by providing access to justice to all and to build effective, accountable, and inclusive institutions at the national and county level. The project also contributes to UN Women’s global Strategic Plan impact area three on Ending Violence against Women and Girls and the United Nations Sustainable Development Cooperation Framework (UNSDCF) 2021 – 2025, specifically Outcome 1.1. The project is aligned to Uganda’s National Policy and Action Plan on Elimination of GBV (2016) and Uganda’s commitment to implement obligations under the Kampala Declaration, which was signed by the President of Uganda, His Excellency Yoweri Kaguta Museveni.

# Program Overview / Results

The Second National Development Plan (2015/16 – 2019/2020) underpinned gender equality as a basis for Uganda’s development, and links ending violence against women and girls (VAWG) to the realization of women´s rights in Uganda. The Access to Justice (A2J) project aimed to increase access to quality justice services for women and girls who experience gender-based violence (GBV). This was to be realized when: i) Special Courts for GBV are institutionalized, and systems, procedures and accountability mechanisms integrated and strengthened to offer specialized, quality essential justice services for survivors of GBV and when ii) women and girls who experience violence use these services and perpetrators are held accountable under the law. These interventions would improve the capacity of justice institutions to provide quality services, fast track cases of GBV, and empower women and girls at risk of violence on their rights and capacity to use justice ser-vices.

The A2J project was designed to complement the EU-UN Spotlight Initiative and the UN Joint Programme on GBV currently implemented in 20 districts and UNICEF’s installation of Audio Video Links and Child Friendly Rooms in seven districts. This project set out to strengthen integrated Service Delivery and Accountability Systems for managing GBV cases across the Justice Law and Order Sector (JLOS) from entry to exit and upgrade five selected High Court Circuits and Chief Magisterial areas in to Regional Centres of Excellence. The project aimed to directly benefit approximately 30,000 women and children annually, as well as build the capacity of approximately 1,000 justice sector actors.

The A2J project sought to directly benefit approximately 30,000 women, children, older persons, refugees, and persons with disabilities and people vulnerable to violence by improving the quality of justice services. The project also directly targeted 51 Judges, 200 Chief Magistrates, Prosecutors and Resident State Attorneys, and 500 Criminal Investigation Officers and Child and Family Protection Officers, 100 Health workers and 150 Administration and frontline staff by improving their knowledge and skills in providing specialised justice and referral services for GBV cases through the special court system. Secondary beneficiaries include duty bearers from institutions mandated under the National GBV Policy to handle GBV cases such as Lawyers, Heath workers, Local Council leaders, and traditional justice actors. Ultimately, 38,823,100 Ugandans were expected to indirectly benefit from the Special Service Delivery and Accountability System/ Special Court for GBV.

Programme Expected Impact: Survivors/victims of Gender Based Violence (GBV) access quality integrated essential justice services through effective, accountable and gender-responsive Justice Institutions.

Programme Expected Outcome 1: Special Service Delivery and Accountability Systems/Special Courts for Gender Based Violence institutionalized, integrated, and perpetrators are held accountable in accordance with the law and human rights.

Programme Expected Outcome 2: Increased use of available, accessible, and quality essential justice services by women and girls who experience violence.

Programme Expected Output 1: Systems, procedures and standards strengthened, integrated and implemented to guarantee quality justice for survivors of GBV and vulnerable women and girls.

Programme Expected Output 2: Capacities of formal justice institutions to deliver quality, coordinated essential services and fast track cases of GBV and other forms of discrimination is strengthened.

Programme Expected Output 3: Women and girls at risk of violence are empowered on their rights, have knowledge of and can access and use quality justice services.

This program was designed based on a well thought through theory of change stated as below:

If legislation, policies and budgets are gender-responsive; and if special courts for GBV are institutionalized; and, If Justice institutions improve performance standards, procedures and accountability mechanisms and are integrated; then, survivors of GBV will access fair justice mechanisms and redress based on relevant gender equality standards; because systems and capacities will be in place to address gender discrimination and other barriers to women’s access to justice at all levels and stages of the justice delivery chain.

If capacities of duty bearers are enhanced, their attitudes towards women conform to gender equality standards, and if mechanisms are in place to monitor the delivery and quality of justice services to women; then the performance and accountability of justice institutions to women will improve; because investing in duty bearers is critical to improving the quality of justice services for women.

If women know their rights as potential users of the justice system and are accepted as actors of the justice system; then women will be able to claim their rights; because evidence shows that rights awareness and the active participation of females in the justice sector increases quality, access and fair justice outcomes for women.

# Purpose of the Evaluation

The UN Women Evaluation Policy and the UN Women Evaluation Strategic Plan 2014-2017 and Austria Development Agency (ADA) donor Guidelines for Programme and Project Evaluations are the main guiding documents that set forth the principles and organizational framework for evaluation planning, conduct and follow-up in UN Women. These principles are aligned with the United Nations Evaluation Group (UNEG) Norms and Standards for Evaluation in the UN System and the Global Evaluation Reports Assessment and Analysis System (GERAAS) guidelines. The key principles for gender-responsive evaluation at UN Women are: 1) National ownership and leadership; 2) UN system coordination and coherence with regard to gender equality and the empowerment of women; 3) Innovation; 4) Fair power relations and empowerment; 5) Participation and inclusion; 6) Independence and impartiality; 7) Transparency; 8) Quality and credibility; 9) Intentionality and use of evaluation; and 10) Ethics.

In line with the program requirements and the UN Women evaluation policy, an end of Programme evaluation is to be conducted at the end of a Programme/project to assess the performance of the Programme. The purpose of this independent end term evaluation is to assess the project’s achievements against the set objectives, identify and document lessons learnt (including design issues, lessons and best practices that can be up-scaled or replicated), and assess how the program contributed to harnessing the capacities of women towards the goals of providing access to justice to victims of GBV. It is a priority for UN Women that this end line program evaluation will be gender-responsive and human rights based in nature.

The primary intended users of this evaluation are:

- Relevant staff in target ministries, local government and targeted government institutions, and CSOs

- Target beneficiary communities/groups

- Relevant staff in participating UN agencies.

- Staff of implementing partners

UN Agencies technical working groups

- Development partners

Primary intended uses of this evaluation will be:

- Learning and improved decision-making to support better implementation of future A2J projects.

- Provide accountability for the development effectiveness of the program to the donor, beneficiaries and other key stakeholders.

- Provide lessons learned, including an understanding why particular development interventions have worked out or not.

- and recommendations to provide clear direction for UN Women’s further A2J work as well as inform future resource mobilisation efforts.

# Evaluation objectives (evaluation criteria and key questions)

This evaluation will specifically:

- Assess the relevance of the project and its approach in line with local, national, and international priorities on A2J

- Assess the effectiveness and efficiency of the program approach for achievement of results, as defined in the logical framework, including the Program Theory of Change

- Analyse how the human rights approach and gender equality principles were integrated in the design and implementation of the project.

- Identify and validate lessons learned including understanding why particular development interventions have worked out or not, promising practices and innovations of work supported by A2J Program within the context of the aid effectiveness agenda

- Provide actionable recommendations with respect to the overall approach to implementation of the A2J project

The evaluation will apply 6 OECD/DAC evaluation criteria which are in alignment with similar UN Evaluation Group (UNEG) evaluation criteria (relevance, effectiveness, efficiency, coherence, impact and sustainability) and Human Rights and Gender Equality as an additional criterion. The evaluation will seek to answer the following key evaluation questions and sub-questions:

The evaluation will seek to answer amongst others the following key evaluation questions and sub-questions:

| Criterion | Questions |
| --- | --- |
| Relevance | Was the project aligned with international and regional gender equality and human rights norms? |
|  | Was the project aligned with national policies, programmes, or priorities addressing A2J? |
|  | Were the programmatic methodologies/strategies appropriate to address the identified needs of beneficiaries and stakeholders? |
|  | Was the choice of partners most relevant in addressing the program needs? |
|  | Were the choice of interventions most relevant to the situation in the target thematic areas? |
|  | Was the technical design of the project including the ToC relevant? |
|  | Did project interventions target the underlying causes of gender inequality? Including A2J? |
| Effectiveness | To what extent have planned outputs been achieved on time? |
|  | Did the interventions contribute to the expected outcomes? |
|  | What unexpected outcomes (positive and negative) have been achieved? |
|  | What has UN Women’s contribution been to the progress of the achievement of outcomes? |
|  | Did the programme implementation partners have access to the necessary skills, knowledge and capacities needed to deliver the project? |
|  | What were the main enabling and hindering factors to achieving planned outcomes? |
|  | To what extent has A2J project interventions been mainstreamed in UN joint programming such as UNSDCF? |
| Efficiency and Coherence | Were the outputs delivered appropriate to resources used? |
|  | To what extent did the UN Women programme management structure support efficiency for the project’s implementation? |
|  | What is UN Women’s comparative advantage in implementing this type of project compared with other UN entities, other stakeholders in A2J programming and key partners? |
|  | How well were resources and risks managed to ensure results for the project? |
|  | Did the project management team manage program implementation delays efficiently? and what corrective actions were undertaken? |
|  | Was a Results Based Management system established and implemented for the project? |
| Sustainability | Is there local ownership and are there local and national champions for the intervention? |
|  | To what extent was capacity of partners developed (at the individual and organizational) to ensure sustainability of project outcomes and benefits? What are the key factors that will require attention in order to improve prospects of sustainability of outcomes and the potential for replication of the approaches? |
|  | What local accountability and oversight systems have been established to support the continuation of activities? What are the recommendations for similar support in future? (NB: The recommendations should provide comprehensive proposals for future interventions based on the current evaluation findings). |
| Human Rights and Gender Equality | To what extent is the project changing the dynamics of power in relationships between different groups? Has the project been implemented according to human rights and development effectiveness principles: Participation/empowerment; Disability inclusion and or non-discrimination; National accountability/transparency; anti-corruption; and climate and environment |
| Impact | To what extent have program interventions generated or have the potential to generate significant positive or negative, intended or unintended, higher-level (capture the significance, the scope, and the transformative nature of the effects) effects? |

# Scope of the evaluation

The evaluation is an end of project evaluation and will cover all project activities implemented since March 2021 to 31st December 2022. Lessons learned and documented from this process will inform other ongoing implementation of A2J programme and how the Country Office will design future A2J programmes.

The evaluator will undertake an initial assessment of the availability of secondary data necessary for the evaluation. In circumstances where constraints are faced such as limited travel or accessibility to project sites, these limitations should be understood and generalizing findings should be avoided where a strong sample has not been used. In addition, cultural aspects that could impact the collection of data should be analysed and integrated into data collection methods and tools. The evaluator is expected to include adequate time for testing data collection tools.

The evaluation team is expected to undertake a rapid evaluability assessment in the Inception. This should include the following:

- An assessment of the relevance, appropriateness and coherence of the implicit or explicit theory of change, strengthening or reconstructing it where necessary through a stakeholder workshop;

- An assessment of the quality of performance indicators in the program, and the accessibility and adequacy of relevant documents and secondary data;

- A review of the conduciveness of the context for the evaluation;

- Recommendations for improvements/changes in the indicators, as per the ToC

- Ensuring familiarity with accountability and management structures for the evaluation.

# Evaluation Approach and methodology

The evaluation will be an external, independent and participatory exercise, which should be completed within a timeframe of 30 days spread over a period of 2 months beginning in December 2022.  The final evaluation methodology will document and analyze the distinct achievements of each programme outcome.

The evaluation shall provide evidence-based information that is credible, reliable and useful and will be based on gender and human rights principles, as defined in the UN Women Evaluation Policy and adhere to the United Nations norms and standards for evaluation.

The evaluation will employ mixed methods including desk-based review of relevant documents backed by consultation with key project stakeholders and field-based primary data collection from direct project beneficiaries. An initial desk review and brief discussions with key stakeholders will support the refinement and finalization of the methodology and analytical framework.

The evaluation is expected to follow a collaborative and participatory approach ensuring close engagement with Programme beneficiaries, implementing partners, ministries, departments, agencies and local governments and other key stakeholders as will be informed by the stakeholder mapping process.  The analysis of the application of human rights and gender equality principles in A2J interventions will be an integral part of the evaluation. Integration of human rights and gender equality issues into the evaluation requires adherence to three main principles – inclusion, participation, and fair power relations. Consequently, a case study approach will also be employed to illustrate the results in the lives of beneficiaries and key stakeholders in each of the project areas. The case studies will consider innovative approaches for engaging these actors in the documentation of Programme results, through at least one case study in each area, using tools like participatory video; significant change stories; photo exhibition; collaborative outcome reporting; and other participatory methods that prioritize the voices of beneficiaries and stakeholders.

The main recommended phases of the evaluation methodology are:

- Inception Phase:

- Conduct an initial desk review of available documents, gather and analyse programme data, conceptualize the evaluation approach, consult internally on the approach, develop data collection tools, stakeholder mapping, engage reference group.

- Conduct brief interviews with key stakeholders to refine the evaluation scope and methodology.

- Draft an Inception Report that will be reviewed by the Evaluation Reference Group.

- Refine the evaluation methodology/question matrix based on Evaluation Reference Group’s feedback and integrate proposed changes (as appropriate) into the final evaluation report.

- Intensive field-based Phase: Data collection Phase

- A more in-depth review of documents.

- Review existing baseline data (primarily from individual IP-based research studies) to determine available data (or could be reframed) against which to measure progress.

- Collect data from beneficiaries and selected stakeholders

- Conduct in-depth interviews with national UN Women staff, partner organizations, donor representatives, and others as necessary.

- Deliver PowerPoint presentation of preliminary field key findings.

- Analysis and Report Writing Phase:

- Review and analyse all available data including staff, partner and stakeholder survey(s) and interpret findings.

- Prepare first draft of the synthesis evaluation report and submit to Evaluation Reference Group for comments and possible endorsement.

- Revise report based on the feedback from Evaluation Management Group and debriefing session (as appropriate).

- Submit final report

- Develop communications materials (popularized version of the final report)

# MANAGEMENT OF THE EVALUATION

The evaluation and quality assurance will be managed by UN Women Uganda Country Office, with technical support of the lead national consultant. The lead national consultant will lead in the execution of activities and take responsibility for meeting all deliverables.

The lead national consultant will be accountable to the Evaluation Manager at UN Women. The evaluation will be conducted in accordance with UN Women and UNEG norms and standards and ADA evaluation guidelines. Upon completion of the evaluation, UN Women has the responsibility to prepare a management response that addresses the findings and recommendations to ensure future learning and inform implementation of their relevant programmes.

The evaluation management structure will comprise of one coordinating entity and two consultative bodies: The Evaluation Management Group and the Evaluation Reference Group. The Planning, Monitoring and Evaluation Specialist is the Evaluation Manager and will manage the day-to-day aspects of the evaluation.

The Evaluation Management Group will be responsible for management of the evaluation. It will coordinate the selection and recruitment of the evaluation team, manage contractual agreements, budget and personnel involved in the evaluation, support the reference groups, provide all necessary data to the evaluation team, facilitate communication between the evaluation team and the reference group. The Management Group will include M&E Specialist; Team Leader - EVAWG & Regional Evaluation Specialist.

The Evaluation Reference Group will provide direct oversight, safeguard independence, and give technical input over the course of the evaluation. It will provide guidance on evaluation team selection and key deliverables (Inception Report and Evaluation Report) submitted by the lead evaluation consultant. It will also support dissemination of the findings and recommendations. The Evaluation Reference Group will include: UN Women programme staff, National government partners, Development partners/donors, Civil Society partners, Regional Evaluation Specialist.

# Time frame and Deliverables

The evaluation will be conducted between December 9th 2022 to January 31st, 2023

The primary evaluation deliverables are:

| Deliverable | Required Timeframe | Payment % |
| --- | --- | --- |
| - Consultants on-boarded | 2nd January | - |
| - Inception Report: this report will include a detailed evaluation methodology, revised evaluation question matrix, proposed data collection tools and analysis approach, and final evaluation work plan (with corresponding timeline) | 12th January 2023 | 40% |
| - Complete consultations | 30th January 2023 |  |
| - First Draft of Evaluation Report – Shared with Evaluation Reference Group | 10th February 2023 |  |
| - Second Draft of Evaluation Report. (Clean copy and dirty copy with tracked response to comments). The draft evaluation report should include all annexes summarizing the data analysis and incorporate feedback from the Evaluation Reference Group | 20th February 2023 | 50% |
| - Validation of Evaluation Report – Workshop | 24th February 2023 |  |
| - Final Evaluation products incorporating feedback from validation workshop. The products should include the following components: - Executive summary (not more than 10 pages) - Standalone Eval report (Not more than 30 pages) - Comprehensive Eval report (with all annexes) - Evaluation comments log/audit trail - Annexes (Separately) | 28th February 2023 | 10% |

# Qualifications, skills, and experiences

With this Terms of Reference, UN Women is seeking to recruit 2 national consultants under SSA contract for a period of 30 days spread between two months. This will include a lead national consultant and an associate consultant.

The National Consultant is expected is expected to have the following expertise:

- At least a master’s degree; PhD preferred, in any social science, preferably Gender or Law, including, evaluation or social research;

- A minimum of 12 years of working experience applying qualitative and quantitative evaluation methods, particularly at the outcome level of a final evaluation;

- A strong record in conducting gender-responsive evaluations including understanding of A2J programming in Uganda is desirable;

- Knowledge of international normative standards on women’s rights and gender mainstreaming processes

- Extensive knowledge and experience in using ICT for research, including electronic/digital data collection, analysis, and reporting.

- Strong ability to communicate with stakeholders and clear understanding of the local/national stakeholders’ landscape;

- Experience in evaluating relevant programmes to the Access to Justice programme in Uganda

- Knowledge of the role of UN Women and its programming in Uganda is desirable

- English language proficiency

The Associate consultant is expected to have the following expertise

Education

- A Master’s degree related to any of the social sciences including Laws, political science, international relations, economics, gender studies and evaluation, but preferably Laws (LLB)

Work Experience

- A minimum of 8 years of working experience in the justice, law and order sector in Uganda

- Experience working on gender, women and other vulnerable persons in the access to justice sphere

- Good working knowledge on human rights of key populations in Uganda.

- Experience in designing and conducting evaluations in the access to justice sector

- Flexibility and Ability to work with teams in multicultural settings

- Demonstrable ability to work under pressure to meet challenging deadlines

- Excellent communication, organisational, facilitation, writing and analytical skills with fluency in both written and spoken in the English language.

# Ethical code of conduct

UN Women has developed the UN Women Evaluation Consultants Agreement Form for evaluators that must be signed as part of the contracting process, which is based on the UNEG Ethical Guidelines and Code of Conduct. The signed Agreement will be annexed to the consultants’ contract. The UNEG Guidelines note the importance of ethical conduct for the following reasons:

- Responsible use of power: All those engaged in evaluation processes are responsible for upholding the proper conduct of the evaluation.

- Ensuring credibility: With a fair, impartial, and complete assessment, stake- holders are more likely to have faith in the results of an evaluation and to take note of the recommendations.

- Responsible use of resources: Ethical conduct in evaluation increases the chances of acceptance by the parties to the evaluation and therefore the likelihood that the investment in the evaluation will result in improved outcomes.

The evaluator is expected to provide a detailed plan on how the following principles will be ensured throughout the evaluation (see UNEG Ethical Guidance for descriptions): 1) Respect for dignity and diversity; 2) Right to self-determination; 3) Fair representation; 4) Compliance with codes for vulnerable groups (e.g., ethics of research involving young children or vulnerable groups); 5) Redress; 6) Confidentiality; and 7) Avoidance of harm.

Specific safeguards must be put in place to protect the safety (both physical and psychological) of both respondents and those collecting the data. These should include:

- A plan to protect the rights of the respondent, including privacy and confidentiality

- The interviewer or data collector is trained in collecting sensitive information, and if the topic of the evaluation is focused on violence against women, they should have previous experience in this area

- Data collection tools are designed in a way that are culturally appropriate and do not create distress for respondents

- Data collection visits are organized at the appropriate time and place to minimize risk to respondents

- The interviewer or data collector is able to provide information on how individuals in situations of risk can seek support

As with the other stages of the evaluation, involvement of stakeholders should not interfere with the impartiality of the evaluation.

The evaluator has the final judgment on the findings, conclusions and recommendations of the evaluation report, and the evaluator must be protected from pressures to change information in the report.

Additionally, if the evaluator identifies issues of wrongdoing, fraud or other unethical conduct, UN Women procedures must be followed, and confidentiality be maintained. The UN Women Legal Framework for Addressing Non-Compliance with UN Standards of Conduct, and accompanying policies protecting against retaliation and prohibiting harassment and abuse of authority, provide a cohesive framework aimed at creating and maintaining a harmonious working environment, ensuring that staff members do not engage in any wrongdoing and that all allegations of wrongdoing are reported promptly, investigated, and appropriate action taken to achieve accountability. The UN Women Legal Framework for Addressing Non-Compliance with UN Standards of Conduct defines misconduct and the mechanisms within UN Women for reporting and investigating. More information can be provided by UN Women if required.

# Application Procedure

Interested qualified individual consultants must apply online latest by December 9th, 2022. Candidates should submit one PDF File attachment containing:

- A letter of interest,

- A personal CV and

- UN Women P11 dully filled form with at least three (3) professional references (UN Women Personal History Form (P11), can be downloaded at: http://www.unwomen.org/about-us/employment;

- Technical and financial proposal.

ANNEX 1: Evaluation Team Selection Criteria

The selection of the Consultants will be based on the fulfilment of the specification established in the TOR. The submitted proposals will be assessed on three main categories: the expertise and competencies of the consultant, as reflected in their CVs, the technical proposal for the specific evaluation; and financial proposal. Weights will be assigned as below.

- Qualifications, Skills & Experience (35%)

The consultant’s experience and qualifications meet the criteria indicated in the TOR.

- Technical Proposal (35%)

  - Evaluation matrix: The matrix clearly addresses the TOR, relating evaluation Questions with evaluation Criteria, with Indicators and with Means of verification.

  - Evaluation approach and methodology: The proposal presents a specific approach and a variety of techniques for gathering and analysing qualitative and quantitative data that are feasible and applicable in the timeframe and context of the evaluation and incorporates human rights and gender equality perspectives.

  - Work plan: The timeframe and resources indicated in the financial proposal are realistic and useful for the needs of the evaluation.

  - Motivation and ethics: The evaluator reflects clear professional commitment with the subject of the assignment and follow UNEG ethical code of conduct.

- Budget (30%)

The budget proposed is sufficient for applying the data gathering techniques and for obtaining reliable data for the evaluation in the timeframe indicated.

ANNEX 2: Outline – Final Evaluation Report Format

The evaluation team can refine the final evaluation report format as necessary, to be done in consultation with the Evaluation Reference Group. Overall, the evaluation report should have the following structure, taking into consideration details provided in section VIII:

- Executive Summary (maximum 5 pages)

- Programme Description

- Evaluation Purpose and Primary Objectives

- Evaluation Methodology, including the final analytical framework

- Main Findings

- National

- Program Level (include specific findings and cross-programme analysis)

- Cross-cutting

- Lessons Learnt and Promising Practices

- Conclusions

- Recommendations

- Annexes

- Documents reviewed

- Interviews conducted

- Data collection tools/analysis approach

- Evaluation Terms of Reference

- Communication piece (not more than 12 power point presentation slides, a participatory video, significant change stories & photo exhibition)

# ANNEX III: ACTIVITIES IMPLEMENTED BY IMPLEMENTING PARTNERS

| Outcome | Output | Activities | Implementing Partner(s) |
| --- | --- | --- | --- |
| Outcome 1: Special Service Delivery and Accountability Systems/Special Courts for Gender Based Violence (GBV) institutionalized, integrated, and perpetrators are held accountable in accordance with the law and human rights. | Output 1: Systems, procedures and standards strengthened, integrated and implemented to guarantee quality justice for survivors of GBV and vulnerable women and girls. | Major activities implemented through consultancies contracted by UN Women. |  |
|  |  | Development of a costed strategy for institutionalisation of a specialist justice system for effective management of GBV cases against women and girls. | Center for Justice Studies and Innovations |
|  |  | Develop detailed and concrete service delivery standards and procedures covering all the steps towards delivering quality integrated justice services throughout the Special Service Delivery and Accountability Systems/ Special court. | Prof. Emmanuel Kasimbazi |
|  |  | Local consultant to conduct a baseline survey for benchmarking the impact of the Special Service Delivery and Accountability System. | Ms. Lillian Keene Mugerwa |
|  |  | Local Consultant to develop Gender Monitoring Guidelines for District Chain Linked Committees. | Dr Consolata Kabonesa and Ms. Theodora Webaale |
|  |  | Support implementation of the Justice, Law and Order Services (JLOS) sector Gender Strategy - Dissemination of the JLOS Gender Strategy. - Training of gender focal persons (both at national and regional level, for example, gender desk officers in Uganda Police Force [UPF]), planning officers, working group members, GSP Secretariat. | Ms. Lucy Ladira, Governance and Security Programme (GSP) Secretariat Ms. Dora Kanabahita – Facilitator |
|  |  | Support the Directorate of Governmental Analytical Laboratories (DGAL) to print and disseminate guidelines for handling and submission of forensic exhibits in SGBV cases. | Department of Government Analytical Laboratory - Director DGAL Kepher Kuchana Kateu |
|  |  | Consultant to develop, translate and disseminate GBV survivors guide to the criminal justice system. | Dr. Josephine Ndagiire |
| Outcome 2: Increased use of available, accessible, and quality essential justice services by women and girls who experience violence. | Output 2: Capacities of formal justice institutions to deliver quality, coordinated essential services and fast track cases of GBV and other forms of discrimination is strengthened. | Training of all Judicial Officers in the 11 Centres of Excellence on survivor centered support and management of victims in handling GBV Cases by Judicial Training Institute (JTI). | JTI |
|  |  | Health workers and multi-sectoral trainings. | Office of the Director of Public Prosecutions |
|  |  | Training of police officers on effective investigation of GBV cases. | UPF |
|  |  | Short term training course of all court clerks and court interpreters in sign language and court interpretation services and GBV terminologies | JTI and Kyambogo University |
|  |  | Learning visit to South Africa criminal justice system on effective management of GBV cases | UN Women |
|  |  | Procurement of equipment – desktops, e-boards, audio visual equipment, court recording equipment | Judiciary and UN Women |
|  |  | Procurement of equipment – consumables, scene of crime cameras and scene of crime kits. | UPF and UN Women |
|  | Output 3: Women and girls at risk of violence are empowered on their rights, have knowledge of and can access and use quality justice services. | Provide hands on mentorship and supervision for administrative and frontline staff to ensure functionality and accountability of the special court system. | Activities dependent on the operationalization of the specialized GBV justice service delivery system which was not in place by end of the project and hence were not implemented. |
|  |  | Support the Inspectorate of Courts to develop a checklist for assessing quality standards and holding actors accountable to make it gender and equity. |  |
|  |  | Pretest the updated check list in the 11 centers of excellence on a quarterly basis. |  |
|  |  | Organize debriefing and support sessions for Judges within the special system to address stress and vicarious trauma associated with consistent exposure to GBV cases. | Judiciary. This activity did not take off inspite of the Chief Registrar’s commitment. |
|  |  | Training of non-formal justice actors in Magisterial areas in target districts on the specialised GBV justice service delivery system. | ULS. However, the training focused on GBV and their jurisdiction since the specialized GBV justice service delivery system was yet to be finalized. |
|  |  | Regional Chain Linked Committees and District Chain Linked Committees to improve community participation and feedback on the justice system through open court days, Barraza’s, and toll-free hotlines. | Judiciary |

Despite the significant shift in the operating context the following key achievements were registered;

  - A costed strategy for institutionalized specialist justice system and structure for management cases of GBV against women and girls was developed.

  - The capacity of two justice institutions of three was strengthened to provide quality essential services and to fast track GBV cases and other forms of discrimination.

  - A training Manual for Judicial Officers on GBV, Cross-Sectoral Handbook on Victim Centred Investigation, Prosecution and Adjudication of GBV cases, and the accompanying Multi–Sectoral Training Manual were developed.

  - The capacity of 349 (124F) justice actors to provide quality essential services and to fast track GBV cases was strengthened.

  - A GBV case census was successfully completed in 5 out of 11 selected high circuits and magisterial areas.

  - A total of 203 justice actors (78F:125M) [police, resident state attorney, Scene of Crime Officers and justice actors], were trained on victim-centred investigation and prosecution of Sexual Gender Based Violence (SGBV) cases.

  - Thirty-nine (15M:24M) court clerks, administrative staff and front desk officers acquired knowledge and skills on customer care, institutional strengthening, their mandate in ensuring justice for all, provision of survivor centred services when receiving and registering GBV cases and security and risk management.

  - Eighty five (42F:43M) court clerks, office attendants, judicial officers (Registrars and Magistrates), office supervisors, systems administrators, data entry clerks benefitted from the training on the GBV case census tool.

  - Two hundred fifty GBV related cases were cause listed from the following courts for the 2021 SGBV sessions.

  - Data generation on GBV cases has been enhanced through the provision of 30 computer desktops to the 11 centres of excellence.

  - Two sets of court recording equipment were purchased to facilitate quick turnaround time for judgements and improve transcription.

  - Victim support services were provided to 140 survivors of GBV and mothers/carers who were witnesses and came to court with babies during the 2021 SGBV sessions.

  - Through open court days 545 community members (277F:268M) received information on where and how to seek justice for GBV cases, aired their grievances with the justice system, discussed challenges with accessing justice and remedies.

# ANNEX IV: SCORING CRITERIA

| Evaluation criteria | Score |
| --- | --- |
| Relevance The extent to which A2J Project Objectives are responsive to the needs and priorities of women, girls, partners and stakeholders and are aligned with government and UN priorities, policies and strategies. | - A - Very good (if A2J interventions adequately addressed the needs and priorities of women, girls, partners and stakeholders and interventions were aligned with government and UN priorities, policies and strategies And no changes are required). - B - Satisfactory (if A2J interventions addressed the needs and priorities of women, girls, partners and stakeholders and interventions were aligned with government and UN priorities, policies and strategies But some changes are necessary). - C- No Satisfactory (if A2J interventions did not adequately address the needs and priorities of women, girls, partners and stakeholders and interventions were not aligned with government and UN priorities, policies and strategies And significant changes are necessary). |
| Effectiveness The extent to which the A2J project’s objectives were achieved and the interventions’ success in producing the expected outputs and achieving milestones were met. | - A - Very good (if A2J interventions adequately met its objectives, outcomes, outputs and targets as defined in the results framework, and aligned to the Project Theory of Change. And no changes are required). - B - Satisfactory (if A2J interventions met its objectives, outcomes, outputs and targets as defined in the results framework, and aligned to the Project Theory of Change. But some changes are necessary). - C- No Satisfactory (if A2J interventions did not adequately meet its objectives, outcomes, outputs and targets as defined in the results framework, and not well aligned to the Project Theory of Change Theory of Change. And significant changes are necessary). |
| Efficiency/Coherence The extent to which the A2J delivered maximum results for the resources and inputs used (funds, expertise, time, etc.). The Coherence is looking at the compatibility of the intervention with other interventions in a country, sector or institution | - A - Very good (if the project adequately delivered maximum results for the resources and inputs used and the implementation approach adds value—avoiding duplication of efforts, leverages partnerships and took corrective actions to minimize project implementation delays. And no changes are required). - B - Satisfactory (if the project delivered maximum results for the resources and inputs used and the implementation approach adds value—avoiding duplication of efforts, leverages partnerships and took corrective actions to minimize project implementation delays. But some changes are necessary). - C- No Satisfactory (if the project did not adequately achieve maximum results in relation to the resources and inputs used and there are indications of duplication and lack of partnerships and coordination with existing programs and structures. And significant changes are necessary). |
| Sustainability The likelihood of a continuation of the results after the completion of the A2J project | - A - Very good (if A2J project activities and achievements are likely to continue after the completion of the A2J project—built local ownership, capacity of partners and established accountability and oversight systems. And no changes are required). - B - Satisfactory (if A2J project activities and achievements are likely to continue and some considerable efforts were done to build local ownership, capacity of partners and established accountability and oversight systems. But some changes are necessary). - C- No Satisfactory (if A2J project activities and achievements likely to continue but limited effort was done to build local ownership, capacity of partners and established accountability and oversight systems. And significant changes are necessary). |
| Impact The extent to which the intervention has generated or is expected to generate significant positive or negative, intended or unintended, higher-level effects. | - A - Very good (if A2J interventions project interventions generated or is expected to generate significant positive or negative, intended, or unintended, higher-level (capture the significance, the scope, and the transformative nature of the effects) effects. And no changes are required). - B - Satisfactory (if A2J interventions project interventions are showing signs of generating positive or negative, intended, or unintended, higher-level (capture the significance, the scope, and the transformative nature of the effects) effects But some changes are necessary). - C- No Satisfactory (if A2J interventions do not adequately show signs of generating positive or negative, intended, or unintended, higher-level (capture the significance, the scope, and the transformative nature of the effects) effects And significant changes are necessary). |
| Gender and Human Rights The extent to which the A2J project activities were designed, implemented and monitored to promote the meaningful participation of both rights holders and duty bearers and to minimize negative effects of social exclusion | - A - Very good (if A2J project activities were adequately designed, implemented and monitored to promote the meaningful participation of both rights holders and duty bearers and to minimize negative effects of social exclusion. And no changes are required). - B - Satisfactory (if A2J project activities were designed, implemented and monitored to promote the meaningful participation of both rights holders and duty bearers and to minimize negative effects of social exclusion. But some changes are necessary). - C- No Satisfactory (if A2J project activities were not adequately designed, implemented and monitored to promote the meaningful participation of both rights holders and duty bearers and to minimize negative effects of social exclusion. And significant changes are necessary). |

# ANNEX V: DATA COLLECTION TOOLS

Key Informant Interview (KII) Guide - UN Women

Greetings!

I ____________________________, have been contracted on behalf of UN Women Uganda as a short term Consultant to undertake an end evaluation of the “Women and girls Access to Justice (A2J) through effective, accountable and gender-responsive institutions” A2J Project. You have been purposively selected to participate in this study and we therefore seek to get some information from you regarding the subject above. This interview is voluntary and all the information you provide us will be treated with confidentially with the sole purpose of facilitating similar future support.

Consent Statement

At this time, do you have any questions?

Are you willing to participate in this study?                  Yes☐                    No☐

Guiding Question(s)

Relevance

- What are the key needs and priorities of women, girls in relation to access to justice for GBV survivors?

- How has the A2J project contributed in addressing key A2J priorities and needs for women and girls (survivors of GBV)?

- To what extent were the A2J project activities aligned to international and regional human rights norms, national policies, programs or priorities?

- To what extent have the A2J project activities been implemented according to human rights and development effectiveness principles? [Probe for

- Participation/empowerment of beneficiaries and stakeholders

- Safe environment for handling GBV cases (availability of victim friendly spaces)]

- What strategies/approaches were adopted in addressing identified needs of beneficiaries and stakeholders? [Probe for: systems strengthening- [institutionalizing special GBV courts], legislative reforms, legal empowerment/awareness creation of women and girls, data collection, analysis and use, capacity enhancement of key justice/A2J actors]

- Was the choice of partners most relevant in addressing the project needs? And why? [judiciary, police, ODPP, civil society (joint training, legal aid service].

Effectiveness

- What changes, if any, have occurred due to the implementation of the A2J project? [Ask the participants why they attribute the change to the project and not other factors. Remember to probe of other contributing factors]

- Strengthening of systems, procedures and standards to guarantee quality justice for survivors of GBV and vulnerable women and girls.

- Strengthening capacities of formal justice institutions to deliver quality, coordinated essential services and fast track cases of GBV and other forms of discrimination.

- Empowerment of Women and girls at risk of violence to access and use quality justice services.]

- What lessons can we draw from the efforts of the A2J project activities in promoting access to quality essential services and handling cases of GBV and other forms of discrimination?

- In your view, what are the main enabling and hindering factors to achieving planned project outcomes?

- To what extent have the A2J project interventions been mainstreamed in UN joint programming? (UN Women)

Efficiency and Coherence

- What is UN Women’s comparative advantage in implementing this type of project compared with other UN entities, other stakeholders in A2J programming and key partners?

- How well were resources and risks managed to ensure results for the project?

- How did the project management team manage program implementation delays efficiently? and what corrective actions were undertaken?

- In terms of monitoring, was a Results Based Management system established and implemented for the project?

- How did the project ensure complementarity, collaboration and harmonization with other stakeholders during project implementation? [Probe for:

- What are the barriers and/or enablers to complementarity, collaboration and harmonization with other stakeholders during project implementation?

- To what extent were the activities of the project complementary to the work of other stakeholders, i.e. prevented duplication and contributed to the larger response activities in areas of operation?

- How did the collaboration/coordination between UN women and the relevant stake holders including judiciary, DPP and police contribute to the interventions with a positive effect on targeted beneficiaries and other stakeholders?]

- How did UN women/JTI utilize opportunities for collaboration to effectively implement the activities and how did they contribute to the effectiveness of the project?

Sustainability

- Is there local ownership and are there local and national champions for the intervention?

- To what extent was capacity of partners developed (at individual and institutional levels) to ensure sustainability of project outcomes and benefits?

- What mechanisms (local accountability and oversight system) are in place to ensure sustainability of project interventions [what are the potentials for replication of the approaches? including financing of similar interventions]

- What could have been done differently by UN women, and other partners to effectively maximize the benefits of the project?

- What are your suggestions to effectively enhance access to quality essential services and handling cases of GBV and other forms of discrimination?

Impact

- To what extent have program interventions generated or have the potential to generate significant positive or negative, intended or unintended, higher-level effects? [Capture the significance, the scope, and the transformative nature of the effects]

- What are the key lessons learned? Any success stories to share of the project?

Thank you very much for your time!

KII Guide – Austria Development Cooperation (ADC)

Greetings!

I ____________________________, have been contracted on behalf of UN Women Uganda as a short term Consultant to undertake an end evaluation of the “Women and girls Access to Justice (A2J) through effective, accountable and gender-responsive institutions” A2J Project. You have been purposively selected to participate in this study and we therefore seek to get some information from you regarding the subject above. This interview is voluntary and all the information you provide us will be treated with confidentially with the sole purpose of facilitating similar future support.

Consent Statement

At this time, do you have any questions?

Are you willing to participate in this study?                  Yes☐                    No☐

Guiding Question(s)

Relevance

- What are the key A2J needs and priorities for GBV survivors in Uganda?

- How has the A2J project contributed in addressing key A2J priorities and needs for women and girls (survivors of GBV)?

- What strategies/approaches were adopted in addressing identified needs of beneficiaries and stakeholders? [Probe for: systems strengthening- [institutionalizing special GBV courts], legislative reforms, legal empowerment/awareness creation of women and girls, data collection, analysis and use, capacity enhancement of key justice/A2J actors]

- Was the choice of partners most relevant in addressing the project needs? And why? [judiciary, police, ODPP, civil society (joint training, legal aid service].

Effectiveness

- What lessons/success stories can we draw from the A2J project? In your opinion what has worked well and what has not worked well?

- In your view, what are the main enabling and hindering factors to achieving planned project outcomes?

Efficiency and Coherence

- How well were resources and risks managed to ensure results for the project?

- How did the project ensure complementarity, collaboration and harmonization with other stakeholders during project implementation? [Probe for:

- What are the barriers and/or enablers to complementarity, collaboration and harmonization with other stakeholders during project implementation?

- To what extent were the activities of the project complementary to the work of other stakeholders, i.e. prevented duplication and contributed to the larger response activities in areas of operation?

Sustainability

- Is there local ownership?  what mechanisms are in place to ensure sustainability of project interventions [what are the potentials for replication of the approaches? including financing of similar interventions]

- What could have been done differently to effectively maximize the benefits of the project?

- What are your suggestions to effectively enhance access to quality essential A2J services and handling cases of GBV and other forms of discrimination?

Thank you very much for your time!

KII - UN agencies (UNFPA), EUD and GSP Secretariat

Greetings!

I ____________________________, have been contracted on behalf of UN Women Uganda as a short term Consultant to undertake an end evaluation of the “Women and girls Access to Justice (A2J) through effective, accountable and gender-responsive institutions” A2J Project for the period covering 1st November 2019 to 30th March 2023. The project aimed at strengthening integrated service delivery and accountability systems for managing Gender Based Violence (GBV) cases across Justice, Law and Order institutions from entry to exit. Its interventions focused on; 1) systems strengthening through the chain of justice to efficiently resolve GBV cases; 2) capacity building for duty bearers to monitor and deliver quality services to GBV survivors; and 3) enhanced awareness on rights of potential justice service users to enable them to claim their rights. The project implementing partners were; Judiciary, Judicial Studies Institute, Uganda Police Force, Office of the Director of Public Prosecutions and Centre for Domestic Violence Prevention.

You have been purposively selected to participate in this study and we therefore seek to get some information from you regarding the subject above. This interview is voluntary and all the information you provide us will be treated with confidentially with the sole purpose of facilitating similar future support.

Consent Statement

At this time, do you have any questions?

Are you willing to participate in this study?                  Yes☐                    No☐

Guiding Question(s)

Relevance

- What are the key A2J needs and priorities for GBV survivors in Uganda?

- What strategies/approaches need to be adopted in addressing identified needs of beneficiaries and stakeholders?

Effectiveness

- What lessons/success stories can we draw from the efforts to promote access to quality essential services and handling cases of GBV and other forms of discrimination?

- In your view, what could be the main enabling and hindering factors to achieving planned A2J outcomes for women and girls?

Efficiency and Coherence

- In what ways have you ensured complementarity, collaboration and harmonization with other stakeholders implementing access to justice interventions for women and girls?

Sustainability

- In your view what mechanisms can ensure sustainability of interventions geared towards enhancing access to justice for GBV survivors [what are the potentials for replication of the approaches? including financing of similar interventions]

- What are your suggestions to effectively enhance access to quality essential services and handling cases of GBV and other forms of discrimination?

Thank you very much for your time!

KII - Judicial Training Institute (JTI)

Principal Judge-Judiciary and Registrar/JTI/Project Focal Person

Greetings!

I ____________________________, have been contracted on behalf of UN Women Uganda as a short term Consultant to undertake an end evaluation of the “Women and girls Access to Justice (A2J) through effective, accountable and gender-responsive institutions” A2J Project. You have been purposively selected to participate in this study and we therefore seek to get some information from you regarding the subject above. This interview is voluntary and all the information you provide us will be treated with confidentially with the sole purpose of facilitating similar future support.

Consent Statement

At this time, do you have any questions?

Are you willing to participate in this study?                  Yes☐                    No☐

Guiding Question(s)

Relevance

- What is your opinion what are the key A2Jpriorities and needs for women and girls affected by GBV in Uganda? [PJ & JTI/Project Focal Person]

As it relates to judicial officers, there is need for psycho-social support as some official are traumaised and withdrawn from adjudicating SGBV cases.

- How has the UN Women A2J project contributed to addressing key priorities for women and girls? [PJ & JTI/Project Focal Person]

Effectiveness

- What activities where you engaged in the A2J project? [JTI/Project Focal Person] [Probe for;

- Capacity building and strengthening of judicial officers

- Women empowerment to access and use quality justice services

- System strengthening to guarantee quality justice for survivors of GBV and vulnerable women and girls]

- In your opinion, what changes, if any, have occurred due to the implementation of the project activities//similar A2J interventions for survivors of GBV? [PJ & JTI/Project Focal Person] [Probe for changes related to;

- Strengthening of systems, procedures and standards to guarantee quality justice for survivors of GBV and vulnerable women and girls.

- Strengthening capacities of formal justice institutions to deliver quality, coordinated essential services and fast track cases of GBV and other forms of discrimination.

- Empowerment of Women and girls at risk of violence to access and use quality justice services.]

- What strategies were used/can be used to achieve the outputs of the project/similar A2J interventions for survivors of GBV? [PJ & JTI/Project Focal Person] [Probe for;

- Establishment of court infrastructure (recording and transcription system for GBV cases, Audio-Visual links equipment, File Cabinets to store the GBV Case Registers, Procurement of computers, E-boards)

- Development of policies, strategies and materials including GBV case registers

- Training of court clerks and interpreters in sign language services and GBV terminologies

- Establishment of victim friendly rooms

- Bench marking visit to a country implementing an institutionalized specialist justice system and structure for management cases of GBV

- Conducting of file census to capture the GBV Cases

- Conducting of Open day Court sessions and barazas]

- How did the various strategies enable the target population to access to quality essential services in handling cases of GBV and other forms of discrimination? [JTI/Project Focal Person]

- What lessons/success stories can we draw from the efforts of the A2J project activities in promoting access to quality essential services and handling cases of GBV and other forms of discrimination? [PJ & JTI/Project Focal Person]

- In your view, what are the main enabling and hindering factors to achieving planned project outcomes? [PJ & JTI/Project Focal Person]

Efficiency/Coherence

- How did the project ensure/how can similar project ensure complementarity, collaboration and harmonization with other stakeholders during implementation? [PJ & JTI/Project Focal Person] [Probe for:

- What are the barriers and/or enablers to complementarity, collaboration and harmonization other stakeholders during project implementation?

- To what extent were the activities of the project complementary to the work of other stakeholders, i.e. prevented duplication and contributed to the larger response activities in areas of operation?

- How did the collaboration/coordination between UN women and the relevant stake holders including judiciary, DPP and police contribute to the interventions with a positive effect on targeted beneficiaries and other stakeholders?]

Sustainability

- What mechanisms are in place to ensure sustainability of A2J project interventions? [PJ & JTI/Project Focal Person] [Probe for:

- To what extent are the benefits of the project likely to be sustained after the completion of this project? [Including financing of future similar interventions]

- What local and national capacities have been established and enhanced to ensure sustainability of efforts and benefits?]

- What could have been done differently by UN women, and other partners to effectively maximize the benefits of the project? [PJ & JTI/Project Focal Person]

- What are your suggestions to effectively enhance access to quality essential services and handling cases of GBV and other forms of discrimination? [PJ & JTI/Project Focal Person]

Impact

- To what extent have program interventions generated or have the potential to generate significant positive or negative, intended or unintended, higher-level effects? [Capture the significance, the scope, and the transformative nature of the effects] [PJ & JTI/Project Focal Person]

Thank you very much for your time

KII Guide - Uganda Police Force, ODPP and DGAL

Greetings!

I ____________________________, have been contracted on behalf of UN Women Uganda as a short term Consultant to undertake an end evaluation of the “Women and girls Access to Justice (A2J) through effective, accountable and gender-responsive institutions” A2J Project. You have been purposively selected to participate in this study and we therefore seek to get some information from you regarding the subject above. This interview is voluntary and all the information you provide us will be treated with confidentially with the sole purpose of facilitating similar future support.

Consent Statement

At this time, do you have any questions?

Are you willing to participate in this study?                  Yes☐                    No☐

Guiding Question(s)

Relevance

- What is your opinion what are the key A2Jpriorities and needs for women and girls affected by GBV in Uganda?

- How has the UN Women A2J project contributed to addressing key priorities for women and girls?

Effectiveness

- What activities where you engaged in the A2J project? [Probe for;

- Capacity building and strengthening of police/DPP officers

- Women empowerment to access and use quality justice services

- System strengthening to guarantee quality justice for survivors of GBV and vulnerable women and girls]

- In your view, what changes, if any, have occurred due to the implementation of the project activities? [Probe for changes related to;

- Strengthening of systems, procedures and standards to guarantee quality justice for survivors of GBV and vulnerable women and girls.

- Strengthening capacities of formal justice institutions to deliver quality, coordinated essential services and fast track cases of GBV and other forms of discrimination.

- Empowerment of Women and girls at risk of violence to access and use quality justice services.]

- What strategies were used to achieve the outputs of the project? [Probe for;

- Capacity strengthening of police/DPP on gender sensitive, victim centered and trauma informed investigation and prosecution of GBV cases, collecting, handling, preservation and presentation of forensic evidence in SGBV cases

- Development of policies, strategies and materials including GBV case registers

- Establishment of victim friendly rooms]

- How did the various strategies enable target population to access to quality essential services and handling cases of GBV and other forms of discrimination?

- What lessons/success stories can we draw from the efforts of the A2J project activities in promoting access to quality essential services and handling cases of GBV and other forms of discrimination?

- In your view, what are the main enabling and hindering factors to achieving planned project outcomes?

Efficiency/Coherence

- How did the project ensure complementarity, collaboration and harmonization with other stakeholders during project implementation? [Probe for:

- What are the barriers and/or enablers to complementarity, collaboration and harmonization other stakeholders during project implementation?

- To what extent were the activities of the project complementary to the work of other stakeholders, i.e. prevented duplication and contributed to the larger response activities in areas of operation?

- How did the collaboration/coordination between UN women and the relevant stake holders including judiciary, DPP and police contribute to the interventions with a positive effect on targeted beneficiaries and other stakeholders?]

Sustainability

- What mechanisms are in place to ensure sustainability of A2J project interventions? [Probe for:

- To what extent are the benefits of the project likely to be sustained after the completion of this project? [Including financing future similar interventions]

- What local and national capacities have been established and enhanced to ensure sustainability of efforts and benefits?]

- What could have been done differently by UN women, and other partners to effectively maximize the benefits of the project?

- What are your suggestions to effectively enhance to access to quality essential services and handling cases of GBV and other forms of discrimination?

Impact

- To what extent have program interventions generated or have the potential to generate significant positive or negative, intended or unintended, higher-level effects? [Capture the significance, the scope, and the transformative nature of the effects]

Thank you very much for your time!

KII Guide - civil society partners (CEDOVIP, JCU and ULS)

[Training of judicial officers, administrative staff in collaboration with JTI and informal A2J actors]

Greetings!

I ____________________________, have been contracted on behalf of UN Women Uganda as a short term Consultant to undertake an end evaluation of the “Women and girls Access to Justice (A2J) through effective, accountable and gender-responsive institutions” A2J Project. You have been purposively selected to participate in this study and we therefore seek to get some information from you regarding the subject above. This interview is voluntary and all the information you provide us will be treated with confidentially with the sole purpose of facilitating similar future support.

Consent Statement

At this time, do you have any questions?

Are you willing to participate in this study?                  Yes☐                    No☐

Guiding Question(s)

Relevance

- What is your opinion what are the key A2J priorities and needs for women and girls affected by GBV in Uganda?

- How has the UN Women A2J project contributed to addressing key priorities for women and girls?

Effectiveness

- What activities where you engaged in the A2J project? [Probe for

- Capacity strengthening of judiciary/police/DPP on gender sensitive, victim centered and trauma informed investigation and prosecution of GBV cases, collecting, handling, preservation and presentation of forensic evidence in SGBV cases.]

- How did capacity strengthening of judiciary/police/DPP promote access to quality essential services and handling cases of GBV and other forms of discrimination?

- In your view, what changes, if any, have occurred due to the implementation of the project activities? [Probe for changes related to

- Strengthening of systems, procedures and standards to guarantee quality justice for survivors of GBV and vulnerable women and girls.

- Strengthening capacities of formal justice institutions to deliver quality, coordinated essential services and fast track cases of GBV and other forms of discrimination.

- Empowerment of Women and girls at risk of violence to access and use quality justice services.]

- What lessons/success stories can we draw from the efforts of the A2J project activities in promoting access to quality essential services and handling cases of GBV and other forms of discrimination?

- In your view, what are the main enabling and hindering factors to achieving planned project outcomes?

Efficiency/Coherence

- How did the project ensure complementarity, collaboration and harmonization with other stakeholders during project implementation? [Probe for:

- What are the barriers and/or enablers to complementarity, collaboration and harmonization other stakeholders during project implementation?

- To what extent were the activities of the project complementary to the work of other stakeholders, i.e. prevented duplication and contributed to the larger response activities in areas of operation?]

- How did UN women utilize opportunities for collaboration to effectively implement the activities and how did they contribute to the effectiveness of the project?

- How did the collaboration/coordination between UN women and the relevant stake holders including judiciary, DPP and police contribute to the interventions with a positive effect on targeted beneficiaries and other stakeholders?]

Sustainability

- What mechanisms are in place to ensure sustainability of A2J project interventions? Including financing of future similar interventions [Probe for:

- To what extent are the benefits of the project likely to be sustained after the completion of this project?

- What local and national capacities have been established and enhanced to ensure sustainability of efforts and benefits?]

- What could have been done differently by UN women, and other partners to effectively maximize the benefits of the project?

- What are your suggestions to effectively enhance to access to quality essential services and handling cases of GBV and other forms of discrimination?

Impact

- To what extent have program interventions generated or have the potential to generate significant positive or negative, intended or unintended, higher-level effects? [Capture the significance, the scope, and the transformative nature of the effects]

Thank you very much for your time!

District Level KII Guide and community level interviews

District KII Guide

Target

- Judiciary (judicial officers, administrative staff [court clerks, secretaries])

- Community Development Services Department

- UPF-CFPU/CID/ Scene of Crime Officers (SOCOs)/Forensics

- ODPP (Resident State Attorneys [RSAs] and administrative staff)

Questions

Relevance

- What are the underlying causes of gender inequality in your community? What are the needs and priorities of women, girls in relation to access to justice for GBV survivors? [Probe for

- How did the JCU/ULS activities address the underlying causes of gender inequality?

- How did the JCU/ULS activities address the needs and priorities of women, girls in relation to access to justice for GBV survivors?]

- What key strategies can be used to address the identified needs of beneficiaries? [Probe for how appropriate were the strategies used in addressing the identified needs of beneficiaries? Which of the above strategies or combination of strategies were more effective in increasing access to quality essential services and handling cases of GBV and other forms of discrimination?]

For police officers, probe for

- Training on effective investigation of GBV cases, interviewing, statement recording, crime scene management, exhibits management and processing

- Training on collecting, handling, preservation and presentation of forensic evidence in SGBV cases.

- Capacity building of non-formal justice actors, including elders, religious, cultural leaders, and Local Councilors, in the target districts on the new /special GBV service delivery system

- Availability victim support services

For Judicial/ ODPP officers’ probe for

- Participation in training on Customer care, institutional strengthening, their mandate in ensuring justice for all, Gender Based Violence, provision of survivor centred services and security and risk management

- Training on handling, preservation and presentation of forensic evidence in SGBV cases.

- Training on generating data on GBV cases and type

- Availability victim support services such as soap, pampers for mother who were witnesses and came to court with babies, sanitary towels, panties, cotton wool, slippers, and a change of clothes to young girls to reduce on the stigma.

- Conducting of open court sessions and community barazas

- Capacity building of non-formal justice actors, including elders, religious, cultural leaders, and Local Councillors, in the target districts on the new /special GBV service delivery system

Effectiveness

- In your view, what changes, if any, have occurred due to the implementation of the JCU/ULS activities? [Ask the participants why they attribute the change to the project and not other factors. Remember to probe of other contributing factors]

- In your view, how did the project contribute to quality essential services and handling cases of GBV and other forms of discrimination? [Probe for;

- Short time for processing GBV cases

- Conviction of perpetuators

- Positive attitudes of service providers handling GBV cases

- Availability of witness protection and victim support services such as emergency shelter, hygiene kits and transport]

- How have the activities of JCU/ULS been implemented taking into account the following?

- Participation/empowerment of beneficiaries and stakeholders

- Safe environment for handling GBV cases (availability of child friendly spaces, safe spaces for survivors of GBV)]

- What lessons can we draw from the efforts of the JCU/ULS activities in trying to improve the access to quality essential services and handling cases of GBV and other forms of discrimination in this district or community?

- In your view, what do you see as the main enabling and hindering factors to achieving planned outcomes?

Efficiency/Coherence

- How did the project ensure complementarity, collaboration and harmonization with other stakeholders during project implementation? [Probe for:

- To what extent were the activities of the project complementary to the work of other stakeholders, i.e. prevented duplication and contributed to the larger response activities in areas of operation?

- What are the barriers and/or enablers to complementarity, collaboration and harmonization other stakeholders during project implementation?

- How did JCU/ULS utilize opportunities for collaboration to effectively implement the activities and how did they contribute to the effectiveness of the project?

- How did the collaboration / coordination between JCU/ULS and the relevant stake holders including District office, Local government authorities, and community-based structures contribute, to the interventions with a positive effect on targeted beneficiaries and other stakeholders?]

Sustainability

- What mechanisms are in place to ensure sustainability of JCU/ULS interventions? [Probe for:

- To what extent are the benefits of the project likely to be sustained after the completion of this project? (including financing future similar interventions)

- What local capacities have been established and enhanced to ensure sustainability of efforts and benefits?]

- What lessons can be drawn from the successes and challenges in the implementation of the JCU/ULS activities?

- What could have been done differently by JCU/ULS, and other partners to effectively maximize the benefits?

- If one were to remodel the project, what advice would you give to make it more effective in increasing access to access to quality essential services and handling cases of GBV and other forms of discrimination in this district or community?

Impact

- To what extent have program interventions generated or have the potential to generate significant positive or negative, intended or unintended, higher-level effects? [Capture the significance, the scope, and the transformative nature of the effects]

- What are the key lessons learned? Any success stories to share of the project?

Thank you very much for your time!

KII Guide community level

Target group

- Local Council Authorities

- Traditional and cultural leaders

- Religious Leaders

Guiding discussion Questions

Relevance

- What’s your role in relation to addressing of gender inequality in your community? Probe for role in addressing GBV and harmful practices in the community?

- What are the underlying causes of gender inequality in your community? What are the needs and priorities of women, girls in relation to access to justice for GBV survivors? Probe for

- How did the JCU/ULS activities address the underlying causes of gender inequality?

- How did the JCU/ULS activities address the needs and priorities of women, girls in relation to access to justice for GBV survivors?

- What strategies were used by JCU/ULS to address the identified needs of beneficiaries?  Probe for

- Participation in training on their mandate in ensuring justice for all, Gender Based Violence, provision of survivor centered services and security and risk management

- Availability victim support services such as soap, pampers for mother who were witnesses and came to court with babies, sanitary towels, panties, cotton wool, slippers, and a change of clothes to young girls to reduce on the stigma.

- Conducting of open court sessions and community barazas

- How appropriate were the strategies used in addressing the identified needs of beneficiaries?

Effectiveness

- In your view, what changes, if any, have occurred due to the implementation of this project in this community/district/ subcounty/village? [Ask the participants why they attribute the change to the project and not other factors. Remember to probe of other contributing factors]

- Effectiveness in collection, preservation and presenting forensic evidence in the courts of law for GBV cases

- Filling the Police Form 3

- Knowledge on the rights and role of victims

- Knowledge on impact of power dynamics and the pressures that would lead a victim to “agree” to forgive

- Availability of safe spaces, child-friendly spaces

- In your view, how did the project contribute to quality of essential services and handling cases of GBV and other forms of discrimination? [Probe for;

- Reporting of GBV cases

- Short time for processing GBV cases

- Conviction of perpetuators

- Positive attitudes of service providers handling GBV cases

- Availability of witness protection and victim support services such as emergency shelter, hygiene kits and transport]

- What lessons can we draw from the efforts of JCU/ULS in trying to improve the access to quality essential services and handling cases of GBV and other forms of discrimination in this district or community?

- In your view, what do you see as the main enabling and hindering factors to achieving planned outcomes?

Sustainability

- What mechanisms are in place to ensure sustainability of project interventions? [Probe for:

- To what extent are the benefits of the project likely to be sustained after the completion of this project?

- What local capacities have been established and enhanced to ensure sustainability of efforts and benefits?]

- What could have been done differently by JCU/ULS, and partners to effectively maximize the benefits?

- If one were to remodel the project, what advice would you give to make it more effective in increasing access to quality essential services and handling cases of GBV and other forms of discrimination in this district or community?

Impact

- To what extent have the JCU/ULS activities generated or have the potential to generate significant positive or negative, intended or unintended, higher-level effects? What has worked well and what can be improved?

- What are the key lessons learned? Any success stories to share of the project?

Thank you very much for your time!

FGD Guide: Community Structures/ Paralegals

Guiding discussion Questions

Relevance

- What’s your role in relation to addressing of gender inequality in your community? Probe for role in addressing GBV and harmful practices in the community?

- What are the underlying causes of gender inequality in your community? What are the needs and priorities of women, girls in relation to access to justice for GBV survivors? Probe for

- How did the JCU/ULS activities address the underlying causes of gender inequality?

- How did the JCU/ULS activities address the needs and priorities of women, girls in relation to access to justice for GBV survivors?

- What strategies were used by JCU/ULS to address the identified needs of beneficiaries? Probe for

- Participation in training on their mandate in ensuring justice for all, Gender Based Violence, provision of survivor centred services and security and risk management

- Availability victim support services such as soap, pampers for mother who were witnesses and came to court with babies, sanitary towels, panties, cotton wool, slippers, and a change of clothes to young girls to reduce on the stigma.

- Conducting of open court sessions and community barazas

- How appropriate were the strategies used in addressing the identified needs of beneficiaries?

Effectiveness

- In your view, what changes, if any, have occurred due to the implementation of JCU and ULS activities in this community district/ subcounty/village? Ask the participants why they attribute the change to the project and not other factors. Remember to probe of other contributing factors]

- In your view, how did the project contribute to quality essential services and handling cases of GBV and other forms of discrimination? Probe for;

- Reporting of GBV cases

- Short time for processing GBV cases

- Conviction of perpetuators

- Positive attitudes of service providers handling GBV cases

- Availability of child friendly services

- Availability of witness protection and victim support services such as emergency shelter, hygiene kits and transport

- How would you rate the performance of the project/activities of JCU/ULS?  Probe for

- Effectiveness in collection, preservation and presenting forensic evidence in the courts of law for GBV cases

- Filling the Police Form 3

- Knowledge on the rights and role of victims

- Knowledge on effects of relationship between men and women and the pressures that would lead a victim to “agree” to forgive

- Availability of safe spaces, child-friendly spaces

- What lessons can we draw from the efforts of the project in trying to improve the access to quality essential services and handling cases of GBV and other forms of discrimination in this district or community?

- In your view, what do you see as the main enabling and hindering factors to achieving planned outcomes?

Sustainability

- What mechanisms are in place to ensure sustainability of project interventions? Probe for:

- To what extent are the benefits of the project likely to be sustained after the completion of this project?

- What local capacities have been established and enhanced to ensure sustainability of efforts and benefits?

- What could have been done differently by JCU/ULS, and partners to effectively maximize the benefits?

- If one were to remodel the project, what advice would you give to make it more effective in increasing access to access to quality essential services and handling cases of GBV and other forms of discrimination in this district or community?

Impact

- To what extent have the JCU/ULS activities generated or have the potential to generate significant positive or negative, intended or unintended, higher-level effects? What has worked well and what can be improved?

- What are the key lessons learned? Any success stories to share of the project?

Thank you very much for your time

FGD Guide: Community members (Male and Female)

Guiding discussion Questions

Relevance

- What are the underlying causes of gender inequality in your community?

- What are the needs and priorities of women, girls in relation to access to justice for GBV survivors?

- What are some of existing programs targeting women or girls at risk of violence? [Probe for

- JCU/ULS activities targeting women or girls at risk of violence?

- How does the JCU/ULS activities address the underlying causes of gender inequality and the needs and priorities of women, girls in relation to access to justice for GBV survivors in your community?]

Effectiveness

- In your view, what changes, if any, have occurred due to the implementation of JCU/ULS activities in this community district/ subcounty/village?

- In your view, how did the JCU/ULS activities contribute to quality essential services and handling cases of GBV and other forms of discrimination? [Probe for;

- Reporting of GBV cases

- Short time for processing GBV cases

- Conviction of perpetuators

- Positive attitudes of service providers handling GBV cases

- Availability of witness protection and victim support services such as emergency shelter, hygiene kits and transport]

- How would you rate the performance of the project/activities of JCU/ULS? Probe for

- Effectiveness in collection, preservation and presenting forensic evidence in the courts of law for GBV cases

- Filling the Police Form 3

- Knowledge on the rights and role of victims

- Knowledge on effects of relationship between men and women and the pressures that would lead a victim to “agree” to forgive

- Availability of safe spaces, child-friendly spaces

- What are the challenges to accessing quality essential services and handling cases of GBV and other forms of discrimination?

- In your view, what do you see as the main enabling and hindering factors to ensure access to quality essential services and handling cases of GBV and other forms of discrimination?

Sustainability

- What mechanisms are in place to ensure sustainability of project interventions? [Probe for:

- To what extent are the benefits of the project likely to be sustained after the completion of this project?

- What local capacities have been established and enhanced to ensure sustainability of efforts and benefits?]

- What lessons can be drawn from the successes and challenges in the implementation of the JCU/ULS activities?

- What could have been done differently by JCU/ULS, and partners to effectively maximize the benefits?

- If one were to remodel the project, what advice would you give to make it more effective in increasing access to access to quality essential services and handling cases of GBV and other forms of discrimination in this district or community?

Impact

- To what extent have the JCU/ULS activities generated or have the potential to generate significant positive or negative, intended or unintended effects? What has worked well and what can be improved?

- What are the key lessons learned? Any success stories to share of the project?

Thank you very much for your time!

IDI Guide (Survivors/Victims of GBV)

Discussion guidance questions

- What are the common concerns among men and women in your community? [Probe for cases of GBV in households and their causes]

- What is your experience with GBV? [Probe for;

- When did it happen?

- What support was given? Please describes the support received and the process of accessing justice]

- Was any organisation/ agency involved with your situation?  If yes, which organisation?

- What was the role of the organisation?

- Were you satisfied with the support that you received? Why or why not?

- What general challenges did you experience in access services? How were they overcome?

- What should be done to effectively address GBV and violence against children in this community?

- Any other comment

Thank you very much for your time!

# ANNEX VI: LIST OF RESPONDENTS INTERVIEWED

| # | Person met | Sex (F/M) | Institution/District | Designation |
| --- | --- | --- | --- | --- |
|  | National Level Consultations (Key Informant Interviews [KIIs]) |  |  |  |
|  | Hon. Justice Dr. Flavian Zeija | M | Judiciary of Uganda, Kampala | Principal Judge |
|  | Dr. Katja Kerschbaummer | F | Austria Development Agency (ADA), Kampala | Governance Advisor |
|  | Ms. Ruth Kitamirike | F | ADA, Kampala | Governance Trainee |
|  | Ms. Evelyne Letiyo | F | UN Women Country Office, Kampala | Ending Violence Against Women (EVAW) Team Lead and Program Specialist |
|  | Ms. Beatrice Ngonzi Mulindwa | F | UNW Country Office, Kampala | Access to Justice Specialist |
|  | Ms. Nina Asiimwe Byarugaba | F | UNW Country Office, Kampala |  |
|  | Ms. Rachel Odoi-Musoke | F | Governance and Security Program (GSP) Secretariat, Kampala | Senior Technical Advisor |
|  | Ms. Lucy Ladira | F | GSP Secretariat, Kampala | Criminal Justice Advisor/Gender Focal Point |
|  | Mr. Paul Otim-Okello | M | European Union Delegation (EUD), Kampala | Governance Advisor |
|  | Mr. Thomas Kamusiime | M | EUD, Kampala | Governance Advisor/Focal Point EU Spotlight Initiative |
|  | Ms. Robina Kirinya | F | Directorate of Government Analytical Laboratories, Kampala | Assistant Commissioner/Regional Forensic Laboratories |
|  | Her Worship Mary Kisakye | F | Judicial Studies Institute, Kampala | Registrar/Project Focal Person-Judiciary |
|  | Ms. Samali Lutswala | F | Office of the Director of Public Prosecutions (ODPP), Kampala | Asst. DPP/Head Gender, Children and Sexual Offences Department |
|  | Assistant Commissioner of Police Andrew Mubiru | M | Uganda Police Force (UPF), Kampala | Director Forensics Directorate |
|  | Superintendent of Police Lilian Mutesi | F | UPF, Kampala | Forensics Directorate |
|  | Ms. Hawa Kagoya | F | Centre for Domestic Violence Prevention (CEDOVIP), Kampala | Executive Director |
|  | Ms. Rachel Apondi Ogolla | F | United Nations Population Fund, Kampala | Programme Analyst- Sexual Reproductive Health/HIV |
|  | Subtotal national level KIIs | 17 (13F, 4M) |  |  |
|  | District Level KIIs |  |  |  |
|  | HW Abala Robert Robby | M | Gulu | Deputy Registrar |
|  | Sarah Amony | F | Gulu | State Attorney |
|  | Patrick Okanyang | M | Gulu | Officer in Charge (OC) Bungatira Police Post |
|  | Welsey Achan | F | Gulu | Reverend Church of Uganda, Bungatira sub County |
|  | Opira John Bosco | M | Gulu | Local Council (LC) 1, Loyo boo Anyanya Sub county |
|  | Betty Chieria Andera | F | Tororo | District speaker |
|  | Mrs Susan Alamai | F | Tororo | Probation officer |
|  | Mrs Asinde Kevin | F | Tororo | Cultural leader, Ass. Minister Tieng Adhola |
|  | Afande Okwange | M | Tororo | Police CID |
|  | Faizo kilaghilaghila | M | Kasese | DPP |
|  | Cosimotos Elisha | F | Kasese | Probation officer |
|  | Biira Cinderella Maureen, | F | Kasese | Legal Officer Justice Centers Uganda |
|  | Biira stella | F | Kasese | Traditional Leader, Obusinga |
|  | Ayebale Magrate | F | Kasese | Child and Family Protection Unit (CFPU), Police |
|  | Kalhyabyuma Isaac | M | Kasese | LC 2 |
|  | Subtotal District Level KIIs | 15 (9F, 6M) |  |  |
|  | Indepth Interviews (IDIs) with survivors |  |  |  |
|  | A | M | Gulu | GBV Survivor |
|  | B | F | Gulu | GBV Survivor |
|  | C | F | Tororo | GBV survivor Tororo |
|  | D | F | Tororo | GBV survivor Tororo |
|  | E | M | Kasese | GBV Survivor |
|  | F | F | Kasese | GBV Survivor |
|  | Subtotal IDIs with survivors | 6 (4F, 2M) |  |  |
|  | Focus Group Discussion (FDGs) |  |  |  |
|  | FGD para social workers mixed group | M and F | Gulu | 3 Males and 3 Females |
|  | FGD Paralegals mixed group | M and F | Gulu | 3 Males and 3 Females |
|  | FGD beneficiaries | F | Gulu | 6 Females |
|  | FGD beneficiaries | M | Gulu | 6 Males |
|  | FGD with beneficiaries (Osukuru Sub county) | F | Tororo | 11 Females |
|  | FGD with parasocial workers (Osukuru Sub county) | F and M | Tororo | 3 Males and 4 Females |
|  | FGD with Beneficiaries Western Division | M | Tororo | 6 Males |
|  | FGD with para-social workers (Western Division) | F and M | Tororo | 3 Females and 3 Males |
|  | FGD with Beneficiaries | F | Kasese | 6 Participants |
|  | FGD with beneficiaries | M | Kasese | 6 Participants |
|  | FGD with community Volunteers | F | Kasese | 6 Participants |
|  | FGD with community volunteers | M | Kasese | 6 Participants |
|  | Subtotal FDGs conducted | 12 |  |  |
|  | FDG Participants | 78 (42F 36M) |  |  |
|  | Overall Total # of respondents 118 (68F 48M) |  |  |  |

UN Women Flagship Programme Brief, updated December 2015, also available at https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2016/FPI-Brief-Access-to-Justice.pdf accessed in January 2023.

MoGLSD, Ministry of Health (MoH), Ministry of Internal Affairs, Judiciary, ODPP, UPF, and Civil Society Organizations (CSOs) at national level among others. At sub national level, LGs, the police, health care providers, community-based services department, ODPP, courts of judicature, LCCs, Institutions of Traditional or Cultural Leaders, community legal volunteers/paralegals, Local Councils, institutions of learning, households and communities among others play a vital role in addressing VAWGs.

Access to Justice sub program strategic plan 2020/21-2024-25, p. 4

Universal Declaration of Human Rights (UDHR), the Sustainable Development Goals (SDGs), the Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW), Convention on the Rights of the Child (CRC) 1990, the Declaration on Elimination of Violence against Women (DEVAM), 1993, the International Conference on Population and Development (ICPD) 1994, the Beijing Platform for Action (BPfA) 1995, the United Nations Security Council Resolutions on Women, Peace and Security (UNSCRs 1325, 1820, 1888, 1889, 1860, 2106 and 2122), the ILO gender equality conventions, the  SDG targets and indicators, the  Protocol to the African Charter on Human and People’s Rights on the Rights of Women in Africa (Maputo Protocol), the Solemn Declaration on Gender Equality in Africa, the Maputo Declaration on Gender Mainstreaming (2003), and  the International Conference of the Great Leaks Region (ICGLR) Protocol (2006) on Prevention and Suppression of Sexual Violence against Women and Children.

Domestic Violence Act (DVA) 2010 and its Regulations 2011; the Prohibition of Female Genital Mutilation Act 2010 and Regulations; The Prevention of Trafficking in Persons Act 2009; The Penal Code Act, Cap 120; The Divorce Act Cap 249; The Children Act Cap 59 as amended; and the International Criminal Court Act 2010 among others.

Access to Justice Sub Program/JLOS Annual Report 2021/22, October 2022, p.89

National Policy and Action Plan on Elimination of Gender Based Violence, MoGLSD revised edition, August 2016

JLOS Gender and Equity Mainstreaming Strategy, July 2019; Judiciary Gender Policy and Strategy; The Gender Bench Book: Women’s access to justice in Uganda and Uganda Police Force Gender Policy, interalia.

Violence against women, key facts-WHO 9 March 2021, also available at: https://www.who.int/news-room/fact-sheets/detail/violence-against-women

GBV and harmful practices in Uganda, UNFPA 2021 Factsheet available at https://uganda.unfpa.org/sites/default/files/pub-pdf/gbv_factsheet._final.pdf

Strategic Options Report: Consultancy to develop a costed strategy for Institutionalised Specialist Justice System and Structure for Case Management of GBV against women and girls, UN Women June 2022, p. 10

UPF Annual Crime Report 2020, p. 27

National survey on violence in Uganda, Module 1: VAWGs, UBOS, November 2021, p.15-18

Uganda Census Report, 2016

Human Rights Watch, 2010

Preventing and responding to GBV and keeping children safe in Uganda’s refugee hosting communities, World Bank, October 2020 available at: https://www.worldbank.org/en/country/uganda/publication/preventing-and-responding-to-gender-based-violence-and-keeping-children-safe-in-ugandas-refugee-hosting-districts

GBV in emergencies, UNICEF available at: https://www.unicef.org/protection/gender-based-violence-in-emergencies

UN Women provides support to Member States’ efforts and priorities in meeting their gender equality goals and for building effective partnerships with civil society and other relevant actors. UN Women operationalizes this through FPIs developed to achieve transformative results for gender equality and women empowerment.

Signed 15th December 2011 - Resolution 8 of Kampala Declaration (2011), ICGLR PROTOCOL HoS Decision.

High court circuits of Fort Portal, Gulu, Soroti and Kampala. Chief Magistrate courts of Fort Portal, Kasese, Buganda Road, Tororo, Moroto, Gulu and Soroti, UN Women First Progress Report January to December 2020, p.7.

14 Districts under the JPGBV (Abim, Amuria, Kaabong, Kaberamaido, Kiryandongo, Kotido, Napak, Nakapiripirit, Pader, Yumbe, Moroto, Gulu, Bundibugyo and Kampala) and 7 EU-UN Spotlight Initiative districts (Tororo, Kasese, Amudat, Kitgum, Kyegegwa and Arua).

Since 2016 UNICEF has supported installation of audio video links and Child Friendly rooms in 7 high court circuits- Kampala- Makindye, Mbarara, Kabarole, Jinja, Gulu, Arua.

With the transition in programming introduced under NDPIII, the Access to Justice sub program of the Governance and Security Program maintains reference to the JLOS substituting “Sector” for “Services”.

PIAPs are the basis for the development of sub-program and institutional strategic plans.

JLOS Annual Performance Report 2019/20, pp 16

UNICEF update on the socioeconomic impact of covid-19 on children, Issue 1, August 2021, also available at: https://www.unicef.org/uganda/reports/unicef-update-socioeconomic-impact-covid-19-children

The Judiciary registered 160 petitions at the Parliamentary and local Council levels across the country following the 2021 General Elections.

UNEG Code of Conduct for Evaluation in the UN System also available at http://www.uneval.org/document/detail/100

WHO Guidelines for researching VAW

AJP Implementation Action Plan (PIAP)

GSP PIAP and A2J sub-Programme strategic plan

UPF Annual Crime Report 2022 available at https://www.upf.go.ug/download/the-2022-annual-crime-report/

National Survey on Violence in Uganda, Module 1: Violence Against Women and Girls, Uganda Bureau of Statistics, November 2021, p. 15-16 also available at https://www.ubos.org/wp-content/uploads/publications/02_2022UBOS_VAWG_Report_-_Quantitative_report.pdf accessed on 27th March 2023.

A training Manual for Judicial Officers on GBV, Cross-Sectoral Handbook on Victim Centred Investigation, Prosecution and Adjudication of GBV cases, and the accompanying Multi–Sectoral Training Manual were developed and/or used for the conduct of training. These resources have been infused in institutional curricula.

A2J is acknowledged as having contributed to this increase along with other interventions happening in the country. Therefore, the increase is not entirely attributed to the A2J project.

National GBV policy in Uganda, MoGLSD 2016

UN Women, Frequently asked questions: Types of violence against women and girls, available at https://www.unwomen.org/en/what-we-do/ending-violence-against-women/faqs/types-of-violence accessed on 3rd April 2023.

Domestic Violence Act 3 of 2010, section 2

14 Districts under the JPGBV (Abim, Amuria, Kaabong, Kaberamaido, Kiryandongo, Kotido, Napak, Nakapiripirit, Pader, Yumbe, Moroto, Gulu, Bun-dibugyo and Kampala) and 7 EU-UN Spotlight Initiative districts (Tororo, Kasese, Amudat, Kitgum, Kyegegwa and Arua).

Since 2016 UNICEF has supported installation of audio video links and Child Friendly rooms in 7 high court circuits- Kampala- Makindye, Mbarara, Kabarole, Jinja, Gulu, Arua.

Standard operating procedures (SoPs) for GBV and VAWG for delivery of quality integrated justice services, UN Women supported consultancy under the A2J Project, February 2023.

A Navigation Guide for Victims/Survivors of SGBV: What Happens in the Criminal Justice System? UN Women supported consultancy under the A2J project.

An informed target could not be set because the assumption was that it would be based on the functioning of the special service delivery system and special court which was to be set up by UNFPA before UN Women’s project commenced.  Unfortunately, they have not yet been established to date. This indicator was therefore never activated.

Indicator was included in expectation that the special service delivery system would be in place. However, the system has not been established to date. This indicator was therefore never activated.

Systems, procedures and standards strengthening here refer to training aid (human capacity development) and the development and implementation of service delivery standards and guidelines for survivors.

Yes, means a JLOS system has been strengthened in at least one or more of the areas.

A2J annual Report 2021

Plea bargaining is a negotiated agreement between the prosecution and an accused person who is represented by a Lawyer. The accused person then comes before the Hon. Judge to plead guilty to the charges against him/her in exchange for a lesser sentence without going through a full trial.

Judiciary Annual Report 2021 available at http://www.judiciary.go.ug/files/downloads/ANNUAL_JUDICIARY_PERFORMANCE_REPORT%202020_2021.pdf

Judicial Annual Report 2022 Available at https://judiciary.go.ug/files/downloads/STATEMENT%20OF%20THE%20CHIEF%20JUSTICE%20AT%20THE%20LAUNCH%20OF%20THE%20ANNUAL%20PERFOMANCE%20REPORT%202021.2022%20LAST.pdf

UPF A2J project annual report 2022

A2J Annual Report 2021

51 judicial officers/judges, 500 police officers, 200 Prosecutors, Chief Magistrates and Resident State Attorneys, 120 health workers, 150 administrative and frontline staff of the special court system

Judiciary, October to December 2021 A2J Project Progress Report.

A Baseline Survey for benchmarking the impact of the GBV SSDA system/ institutionalised specialist justice system and structure for management of GBV cases against women and girls, UN Women January 2023.

Mission Report, Judiciary Court Open Days held in Fort Portal and Kasese Courts i.e., A2J project Centres of Excellence.

About 70 females attending open court days in each of the 11 centres

ADC-A2J Annual Report 2021 and 2019/20-JLOS Annual Performance Report

2022/2022-JLOS Annual Report

Although this achievement can not be entirely attributed to A2J, stakeholders acknowledge the contribution of A2J to this improvement in conviction.

UPF 2021 crime report. Available at https://www.upf.go.ug/annual-crime-report-2021/

https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2016/FPI-Brief-Access-to-Justice.pdf

Signed 15th December 2011 - Resolution 8 of Kampala Declaration (2011), ICGLR PROTOCOL HoS Decision 8

14 Districts under the JPGBV (Abim, Amuria, Kaabong, Kaberamaido, Kiryandongo, Kotido, Napak, Nakapiripirit, Pader, Yumbe, Moroto, Gulu, Bun-dibugyo and Kampala) and 7 EU-UN Spotlight Initiative districts (Tororo, Kasese, Amudat, Kitgum, Kyegegwa and Arua).

Since 2016 UNICEF has supported installation of audio video links and Child Friendly rooms in 7 high court circuits- Kampala- Makindye, Mbarara, Kabarole, Jinja, Gulu, Arua

See link to the adapted criteria http://www.oecd.org/dac/evaluation/revised-evaluation-criteria-dec-2019.pdf

It looks at the extent to which an intervention is compatible with other interventions in a country, sector or institution

A2J project progress reports, UN Women, 2021 and 2022

High Court Criminal Division, Iganga Chief Magistrate (CM) Court, Fort Portal High Court, Apac CM Court, Gulu High Court, Gulu CM Court, Moroto CM Court, Kasese CM Court, Tororo CM Court, Soroti High Court and Soroti CM Court

These included items such as soap, pampers, sanitary towels, panties, cotton wool, slippers and a change of clothes to young girls to reduce on the stigma.