Evaluation Report

Evaluation of the Project

Implementation of the Women, Peace and Security Agenda in Sri Lanka (the G7 Women, Peace and Security Partnerships Initiative)

January 2020 - December 2022

Melissa Andrade Costa                           Nadhiya Najab		           	International Consultant                        National Consultant

April 2023

Index

LIST OF ABBREVIATIONS	4

Acknowledgements	5

Evaluation background	6

Object of the Evaluation	6

Evaluation Purpose and Scope	6

Conclusions	7

Lessons Learned	8

Recommendations	8

1.	Evaluation background	9

2.	Object of the evaluation	11

3.	Evaluation Purpose, Objectives and Scope	17

4.	Evaluation Methodology	20

4.1.	Overall methodological approach and design	20

4.2.	Data Collection	22

4.3.	Sampling	23

4.4.	Methods of Analysis	29

4.5.	Limitations, Risks Involved and Mitigation Strategies	29

5.	Ethics of the Evaluation	30

5.1 Ethical Protocols Associated with Data Collection	31

6.	Quality Assurance and Evaluation Management	31

7.	Evaluation Findings	33

7.1.	Evaluation Criteria: Relevance	33

7.2.	Evaluation Criteria: Coherence	38

7.3.	Evaluation Criteria: Effectiveness	41

7.4.	Evaluation Criteria: Efficiency	54

7.5.	Evaluation Criteria: Sustainability	56

7.6.	Evaluation Criteria: Gender Equality and Human Rights	57

Lessons Learned	60

Conclusions	62

Recommendations	65

Appendix A. Rapid Assessment	71

Appendix C. Project Documents Reviewed and Consulted	82

Appendix D. Evaluation Instruments	86

Appendix E. Stakeholder Analysis	105

Appendix F. Updated Results Framework	109

Appendix G - Term of Reference	117

Appendix H – Evaluators Bio Data	117

Table 1. Results Chain of the Project	10

Table 2. Evaluation Questions	15

Table 3. Gender Results Effectiveness Scale	18

Table 4. Categories of Stakeholders  Interviewed 	23

Table 5. Risks Involved and Mitigation Strategies	27

Table 6. Status of the assumptions identified in the reconstructed Theory of Change	48

Table 7. Evaluation Matrix	72

Table 8. Stakeholders consulted as part of this evaluation and their roles	104

# LIST OF ABBREVIATIONS

| CSO | Civil Society Organization |
| --- | --- |
| CBO | Community Based Organisations |
| DAC | Development Assistance Committee |
| DSD | Divisional Secretary Divisions |
| FGD | Focus Group Discussion |
| FHH | Female Heads of Households |
| GoSL | Government of Sri Lanka |
| GRES | Gender Results Effectiveness Scale |
| LTTE | Liberation Tigers of Tamil Eelam |
| MWCASE | Ministry of Women, Child Affairs, and Social Empowerment |
| MPD | Multi Party Dialogue |
| NAP | National Action Plan |
| OECD | Organization for Economic Cooperation and Development |
| PVE | Prevention of Violent Extremism |
| TR | Term of Reference |
| UNSCR | United Nations Security Council Resolution |
| UN Women | United Nations Entity for Gender Equality and the Empowerment of Women |
| WPS | Women, Peace and Security |

# Acknowledgements

This evaluation would not have been possible without the valuable contributions of the following individuals:

- Ms. Ashika Gunasena, Chief Executive Officer, Chrysalis

- Ms. Champa Upasena, Director of the Women’s Bureau of Sri Lanka, Government of Sri Lanka

- Mr. Kumarathasan Vinopavan, Programme Manager, Chrysalis

- Ms. Pradeepa Kulasekera, Project Officer, UN Women Sri Lanka

- Ms. Prashani Dias, Officer-in-charge, UN Women Sri Lanka

- Ms. Ramaaya Salgado, Programme Analyst/Country Focal Point, UN Women Sri Lanka

- Ms. Sabrina Evangelista- Evaluation Specialist of UN Women Regional Office for Asia and the Pacific

- Mr Iman Adnan, Tamil language field consultant for the evaluation team

We also wish to express our gratitude to all individuals who have kindly given their time to be interviewed and participated in the data collection for this evaluation, specially those women who benefited from the project at a local level and who have taken part in the focus group discussions.

It is our wish that this exercise can be useful to generate learning and feed into interventions which foster the empowerment of both women and men who can live up to their potential as human beings able to dream and thrive.

Melissa Andrade Costa

Nadhiya Najab

Evaluation Team

Executive Summary

## Evaluation background

Sri Lanka has experienced nearly three-decades of armed conflict between the armed forces of the Government of Sri Lanka (GoSL) and the Liberation Tigers of Tamil Eelam (LTTE) which officially came to an end in May 2009. There were nearly 90,000 Female Headed Households (FHH) (UN, 2015) estimated to be widowed at the end of the armed conflict. Despite the passing of nearly 13 years since the end of the armed conflict in Sri Lanka, which corresponded with a time period of relative peace, the root causes of conflict and the other forms of structural imbalances that led to violence and discrimination have remained largely unaddressed. It is in such a context that the importance of gender-sensitive policies are emphasised, in order to adequately rebuild the relationships among affected communities, and contribute to the changing landscape of peace and security in Sri Lanka through the inclusion of women and girls who have and continue to be excluded.

## Object of the Evaluation

The project ´Implementation of the Women, Peace and Security Agenda in Sri Lanka´ is an initiative funded by the Government of Japan and implemented by UN Women in Sri Lanka in partnership with the Ministry of Women, Child Affairs and Social Empowerment. It is a follow-up of a previous project where the Government of Japan started to support the Women, Peace and Security (WPS) agenda in the country. The project aimed at having women contribute to sustainable peace in Sri Lanka through: 1) Women, including those in vulnerable situations, will be empowered to strengthen the peacebuilding process and social cohesion in Sri Lanka including through implementation of the NAP WPS; 2) Advocacy space is created and capacities of government is strengthened to validate and implement gender responsive policies related to women, peace and security and 3) Coordination and knowledge exchange at local, national and regional level is fostered including by acting as the national secretariat for the G7 WPS initiative.

The project started in January 2020 and due to COVID-19 restrictions and implementation delays, it was granted a no-cost extension until 31 December 2022 and a reprogramming of the activities with a total budget of US$1,995,058. The project covers most provinces of the country (North Central, Uva, Sabaragamuwa, Western, Eastern, and Northern). Chrysalis was responsible for the project in relation to the capacity building component for women at the community level while Hashtag Generation is a service provider responsible for capacity building in the area of digital literacy among identified participants from the Northern, Eastern and Western provinces.

## Evaluation Purpose and Scope

The evaluation purpose was to provide useful learning to support evidence-based decision making, demonstrate accountability to donors and stakeholders. The evaluation covered the whole period of project implementation, from 01 January 2020 to 31 Dec 2022 and looked at the implementation from a national and local perspective. The evaluation took palce between Dec 2022 and May 2023.

Evaluation Methodology

The methodology responded to the indicators proposed for each evaluation question using the criteria of Relevance, Coherence, Efficiency, Effectiveness, Impact, Sustainability, Gender Equality and Human Rights. A mixed method approach was used (with desk review, remote and in person semi-structured interviews, 2 online surveys and focus groud discussions). The evaluation design was a) Theory Based using a systemic approach and b) attributed value to the project through the Gender Results Effectiveness Scale. A stakeholder analysis was conducted to help identify key stakeholders. In total, 213 people were consulted (179 females and 34 males).

## Conclusions

Conclusion 1: The project´s approach and strategies were relevant to the agenda of women´s overall empowerment and Women, Peace and Security with a good and well tested combination of policy design and consultation, capacity building at different levels and grassroots work. The project team was able to adapt project design to the demands of the government and the needs identified of the various stakeholders. However, the project had challenges in delivering some of the demands brought by the government, such as refurbishment and IT projects due to poor internal communication challenges within the government and the lack of an existing procedure to ensure utility once delivered at a ground level. In fact, UN Women is not experienced with running initiatives in areas such as refurbishment as identified by other evaluation exercises in other countries. In addition, although the design of the project was relevant to stakeholders, this is more true to women on the ground. There is still much resistance at the national level of fully taking in the agenda of women´s empowerment and Women, Peace and Security in face of the still present feelings of grievance and resistance towards improving women’s participation in political participation, while conversations about peacebuilding and post-war recovery in the country continue to be considered a sensitive topic.

Conclusion 2: The project was able to mobilize different stakeholders in an ample discussion on Women, Peace and Security, however collaboration was limited to consultation. There were no major overlaps between the work of the project and other stakeholders, but limited collaboration. In face of so many crises in the country, it was difficult to have key partners convene high level meetings among stakeholders. In fact, continuous communication with a wider range of stakeholders and partnership building were identified as challenges of the project, further challenged due to the ownership status of the NAP related documents by the government entities. Engagement with the government was also more limited to those parties directly engaged with Women´s empowerment agenda which tend to have less power and agency. In this context, gaps were identified in the strategic positioning of women as a relevant partner in the agenda of Women, Peace and Security.

Conclusion 3: The project was successful in developing capacities of government officers at a national and regional level and of women on the ground, specially in entrepreneurial skills. Women participants are now more confident and more aware of their rights and possibilities. A more favourable policy scenario was also created with the approval of the National Action Plan on Women, Peace and Security and enhanced dialogue among government officers and women on the ground. A further step is now needed to help capacities built turn into actual and sustainable engagement of women in peacebuilding and disseminate the knowledge products generated within the project.

Conclusion 4: The project suffered delays and implementation challenges in face of the context of multiple crises in the country (COVID-19, economic and political crisis), but it was nevertheless able to deliver high quality outputs. The major implementation challenges were with the refurbishment component which were not fully delivered at the end of the project´s timeline and were taken up by UN Women´s management to run with their own resources. One additional implementation challenge identified was the reporting burden which was significant for the implementing partner. Overall, the relationship between UN Women and partners worked well. In terms of learning, the project would have benefited from conducting reflection exercises with front line government officers to obtain feedback on interventions implemented as part of the project. In addition, the Monitoring and Evaluation Framework was clear and monitoring efforts were in place, but there is no evidence of monitoring work feeding into project learning cycle for the most part, and this is attributed to a bulk of the interventions occurring towards the end of the project period.

Conclusion 5: Capacity was developed in stakeholders and the National Action Plan on Women, Peace and Security was approved which indicates a good foundation was built for sustainability. However, the use of the new skills by stakeholders, specially in the agenda of WPS and the implementation of NAP is still to be seen. The most sustainable efforts are with the entrepreneurial women and the development of their own business. The agenda of social cohesion and WPS will need further efforts and support to be sustained overtime. Within the local government context, the lack of an existing channel of communication between grassroots organizations, frontline officers, and decision makers at the local government will limit the sustainability of opportunities created through this project for local government officers to share the identified needs with officers with the necessary authority for decision making.

Conclusion 6: The project had a strong human rights framework, helping to develop capacity in duty bearers and rights holders and strengthen institutions. It had a gender transformative approach by helping to change norms (approve legislation) and change power relations at the household level with the contribution of women´s economic empowerment. It was very inclusive in its consultation process for the National Action Plan. It was only not fully successful in engaging people with disabilities despite of efforts in this direction.

## Lessons Learned

- Continuous adaptation of policy narrative and support is needed to keep partners engaged and maintain political momentum;

- Frequent and substantive communication with partners throughout project implementation is key for political support;

- Preliminary analysis and benchmarking needs to be in place at planning stage of complex and not usual types of project operations;

- When instability is the norm, crises are foreseen and need to be considered in timelines and budget contigencies in project design and throughout project implementation, bringing the donor close to make decisions according to the context. The context of continuous crisis have to be considered during project negotiation stage;

- Convening high level political dialogue is risky, requires special dedication and results are mostly unpredictable;

- Communication is strategic for increasing results and framing institutional positioning;

- Long term and continuous support bring long standing and more sustainable results;

- The combination of high-level policy work with grassroots work continues to be strategic and help foster cultural change.

## Recommendations

- Develop a communication strategy on a narrative for WPS which helps to set the policy scenario to further dialogue in the country and position UN Women as a key actor working in this agenda;

- Engage partners in future project design, consult HQ and Regional Office before engaging in refurbishment and IT projects and  explore alternative ways of delivering refurbishment and IT projects when needed (e.g. partnership with other agencies and consultations with beneficiaries to determine utility);

- Explore lessons learned and challenges in the attempts to engage people with disabilities in this project;

- Appropriately plan for contingency resources and flexible modes of delivery adapted to contexts of crisis and the work with partners;

- Increase dialogue with other government agencies beyond those related to women´s related policies;

- Include staff time in political processes whenever high level policy dialogue is involved;

- Disseminate knowledge products of the project, create a communication strategy for future projects and ensure continuous communication with partners in project implementation;

- Include continuous learning as part of the M&E framework.

# Evaluation background

Sri Lanka has experienced nearly three-decades of armed conflict between the armed forces of the Government of Sri Lanka (GoSL) and the Liberation Tigers of Tamil Eelam (LTTE) which officially came to an end in May 2009; a period characterised by waves of conflict, militarisation, and displacement (International Crisis Group, 2011).  While the root causes of the protracted war are multiple and complex, the post-independence politics of a majority-led leadership and the local and global political economic situation laid the foundations for violent social and political dissent. Sri Lanka’s history of conflict is not limited to the civil war, with the country experiencing violent insurrections led by Sinhala youth particularly in 1987 across the south, central, and western regions of the country. The proliferation of militant groups in the north and east of Sri Lanka culminated into fully- fledged war in the early 1980s, with the LTTE emerging as a protagonist in the drawn-out conflict with the state.

The period of armed conflict is attributed to the death and casualty of thousands of civilians, armed forces, and LTTE combatants, as well as multiple displacements, cases of physical and mental disabilities, and the destruction of homes and public property (Jayasundere & Weerackody, 2013). With nearly 90,000 Female Headed Households (FHH) (UN, 2015) estimated to be widowed at the end of the armed conflict, and FHHs accounting for approximately 23.5% of the total number of households in the country, the burden of responsibility on women to support their households is significant. FHHs include widows of soldiers, LTTE cadres, and other militant cadres and widows of civilians. This category also includes women whose spouses are disabled or have divorced or abandoned them.

The decades of armed ethnic conflict in Sri Lanka were visibly gendered. While men were the main casualties of war, women were left to cope with the loss of family members due to death and disappearances of income earners. FHHs were thus propelled into additional responsibilities of income generation while continuing to engage in carework.

Sri Lanka’s history is contextualised by militarization, a protracted armed conflict and the condoning of political violence which has contributed towards a culture of violence and impunity in the country since the 1980s, with a significant impact on violence against women. Despite the guarantee of fundamental rights and non-discrimination towards women in Sri Lanka since the 1978 Constitution, the Women’s Rights Bill is yet to be approved; and women’s rights, ensured in international instruments— such as the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW)—although ratified, have not yet been incorporated into national legislation. Furthermore, gender-based discrimination still exists in instances of inheritance rights, in settlements, and in religious personal laws. Although Sri Lanka has measures in place to protect women against sexual and gender-based violence, a study by Jayasundera (2009) highlights that women in Sri Lanka still encounter issues due to the lack of enforcement of these laws.

While women across the country were affected by the conflict, their experiences differed based on their ethnicity, class and socio-economic status. The change in roles and responsibilities for women within a deeply patriarchal society comes with its own challenges in terms of navigating the multiple burdens and exploitative conditions.

Despite the passing of nearly 13 years since the end of the armed conflict in Sri Lanka, which corresponded with a time period of relative peace, the root causes of conflict and the other forms of structural imbalances that led to violence and discrimination have remained largely unaddressed. To this end, the country experienced a revival in nationalist sentiments couched in ethno-religious terms resulting in riots and destruction of property in June 2014  and March 2018 propagated by extremist Buddhist groups, which resulted in inciting ethno-religious hate speech and violence targeting minority communities. The Easter Sunday terror attacks in April 2019, further intensified the tensions among ethnic communities, contributing to a general increase in communal mistrust, religious intolerance, hate speech and discrimination.

It is in such a context that the importance of gender-sensitive policies are emphasised, in order to adequately rebuild the relationships among affected communities, and contribute to the changing landscape of peace and security in Sri Lanka through the inclusion of women and girls who have and continue to be excluded. Policies and initiatives presented in response to the attacks aimed at prevention of further violence must critically consider how women are involved in violence – not only as perpetrators and victims, but also as preventers. Research has confirmed the important role women play in promoting social cohesion and preventing violent extremism. Across the region, women’s individual and collective roles in promoting peacebuilding are found to extend beyond their familial roles to civil society and religious settings where they can shape the decisions of community members to refrain from violent activities. Researchers have recommended scaling up support and increasing financing for their activities to enhance their impact on peacebuilding, social cohesion, and preventing extremist and terrorist-related violence.

The global Women Peace and Security (WPS) agenda is influenced by the United Nations Security Council Resolution (UNSCR) 1325 issued in October 2000 aimed at achieved equitable peace through a gendered lens. The project implemented by UN Women and funded by the Government of Japan is guided by the four pillars of the UNSCR 1325, with the intention of contributing towards ensuring women are ‘active agents’, provided with the necessary skills and knowledge to be able to participate actively towards social cohesion, reconciliation, conflict prevention, and conflict resolution is intended to bridge the identified gap, and subsequently contribute towards peacebuilding in Sri Lanka.

# Object of the evaluation

The project ´Implementation of the Women, Peace and Security Agenda in Sri Lanka´ is an initiative funded by the Government of Japan and implemented by UN Women in Sri Lanka in partnership with the Ministry of Women, Child Affairs and Social Empowerment. It is a follow-up of a previous project where the Government of Japan started to support the Women, Peace and Security (WPS) agenda in the country. The project aims to strengthen the peacebuilding process and social cohesion in the country through the empowerment of women in the context of UN Security Council Resolution 1325 and subsequent resolutions which call for governments to ensure the participation and leadership of women in conflict related and post conflict contexts. The project also looks at assisting with the implementation of the National Action Plan on Women, Peace and Security (NAP WPS).

Figure 1. Map of Sri Lanka

The project started in January 2020 and due to COVID-19 restrictions and implementation delays, it was granted a no-cost extension until 31 December 2022 and a reprogramming of the activities with a total budget of US$1,995,058. The project covers most provinces of the country (North Central, Uva, Sabaragamuwa, Western, Eastern, and Northern) and covers different levels of work – from national policy (through support to the government and CSOs) to community (capacity building, infrastructure and resources) and knowledge sharing (coordination meetings and networking within the NAP WPS). Chrysalis acts as responsible party of the project on the ground in the area of capacity building for women at the community level. Hashtag Generation is the service provider responsible for capacity building in the area of digital literacy among the identified participants from the Northern, Eastern and Western provinces.

The project is linked to UN Women Strategic Plan (2018-2022) Impact 4: Outcome 5 – Women and girls contribute and have greater influence in building sustainable peace and resilience and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action. The results chain of the project is presented in the Table 1 next.

Table 1. Results Chain of the Project

| Result level | Results statement |
| --- | --- |
| Goal | Women contribute to sustainable peace in Sri Lanka |
| Outcome | Women, including those in vulnerable situations, will be empowered to strengthen the peacebuilding process and social cohesion in Sri Lanka including through implementation of the NAP WPS |
| Output 1 | Advocacy space is created and capacities of government is strengthened to validate and implement gender responsive policies related to women, peace and security. |
| Output 2 | Women and women´s groups, including grassroots women and the most marginalized, have capacity, resources and skills to promote peace and social cohesion at the community level. |
| Output 3 | Coordination and knowledge exchange at local, national and regional level is fostered including by acting as the national secretariat for the G7 WPS initiative. |

Considering its support to the NAP WPS, the project was stated to work with various government counterparts of the Ministry of Women, Child Affairs and Social Empowerment (MWCASE) and national level officers as well as local government authorities and administrative structures and community leaders, marginalized groups of women, youth, men and development partners. 1,240 people were expected to be direct beneficiaries of the initiative. As per the project documents the project beneficiaries are disaggregated as follows:

- Output 1.2 would target 60 government officials

- Output 1.3 would target 150 beneficiaries encompassing government and CSO networks

- Output 2.1 would target 180 beneficiaries encompassing representatives of grassroot organisations, religious and community groups

- Output 2.2 would provide entrepreneurial capacity development training for 700 women belonging to vulnerable groups, of which 370 beneficiaries are targeted to receive in-kind assistance

- Output 2.3 would target 90 young women leaders to strethen capacities on informed digital engagement for peacebuilding

- Output 3.3 would target knowledge exchange between 60 government and civil society actors on women, peace and security

Under Output 1 the project helped to 1) promote multiple consultations within the government, Civil Society Organizations (CSOs), donors/development partners and UN Agencies as part of the process to validate the  National Action Plan (NAP) on WPS; 2) promote capacity building for government officers for implementation of policies on WPS which included a needs assessment, trainings for these professionals and provision of technical equipment (laptops) in selected locations to carry out the work on WPS and 3) Multi-party dialogues between the government and CSO networks for the promotion of joint work on WPS.

Under Output 2, the project built on previous work from UN Women in the area of economic empowerment and the work of its partner Chrysalis. , In this area it promoted the following activities: 1) Social cohesion dialogues and trainings to sensitize the participants and build skills for the promotion of social cohesion and conflict prevention; 2)  Entreprenurial skills development training     provided for women with an existing entrepreneurship profile based on a needs assessment and contextual value chain study; 3) Provision of in-kind assistance for selected women entrepreneurs in addition to mentorship and and market linkages.

Additionally, the project also focused on refurbishing and expanding local government training centres, marketplaces and service centres that provide counselling support for women – directly implemented by UN Women through its Contractor, Wemara Construction, and overseen by a Consultant Engineer to UN Women. Trainings for young women leaders on prevention of violent extremism through digital engagement, including social media was implemented through Hashtag Generation. Output 2 was the major focus of the project (45% of total budget as per revised framework in face of COVID-19).

Output 3 was about knowledge sharing and political support. It involved the following activities: 1) Promotion of meetings among G7 countries (Embassies in Sri Lanka) to help gather support for WPS agenda in Sri Lanka; 2) Production of studies on the agenda of WPS in the country and 3) Promotion of inter-district workshops aimed at knowledge exchange meetings and activities to help foster the agenda of WPS among various actors.

Developments within the Project Duration:

In addition to these activities which were planned from the beginning of the project, UN Women was requested by the GoSL to support on two other activities, namely: 1) Refurbishment of women shelters and counselling offices (under Output 2.2) and 2) Promotion of a national communication campaign in the context of COVID-19, to promote health and prevent violence against women (under Output 3.2). Additionally, the request from the GoSL also included to expand the geographical reach of the entrepreneurial skill development training and provision of in-kind assistance (Output 2.2) to include the district of Colombo- the capital district that was most significantly affected from COVID-19 related curfew and movement restrictions in 2020.

In July 2022, both the President and Prime Minister of the Government of Sri Lanka resigned in the context of a major economic crisis with a decrease of foreign reserves in the country which led to a lack of funds for purchasing essential imported goods. The country has been experiencing problems with shortage of fuel, power cuts and shortage of food, medical and other supplies required by the project. Inflation was at almost70% per year on September 2022 towards the end of the project (data from Central Bank of Sri Lanka). This context gives the background for the project which was assessed.

The following page shows the reconstructed Theory of Change by the evaluation team and validated by key stakeholders during inception phase. A series of assumptions were made in the causal chain between activities, outputs, outcome and impact and they were tested during data collection to see whether all the conditions were in place to achieve outputs and promote outcome leading to impact. See evaluation approach for further details on how the Theory of Change helped guide the evaluation exercise.

Assumptions tested were:

- Stakeholders engage in consultations and WPS agenda providing quality and useful feedback;

- Training methodologies adapted are effective for civil servants;

- Joint WPS work plans are implemented;

- Capacity developed stays in the organizations despite government changes;

- Draft NAP on WPS is approved;

- Government is able to maintain equipment;

- Equipment provided by the project is used for WPS related activities;

- Women are effectively included in NAP validation consultations;

- Needs assessments and value chain analyses are well produced and feed into training;

- Women are well identified for training activities;

- Trainings are well delivered – they are relevant and engaging;

- Women use the in-kind assistance provided effectively;

- Government facilities for women are used;

- Benefited women change attitude in face of trainings and assistance received;

- Study on prevention of violent extremism within the digital sphere feeds into training;

- G7 Countries are engaged in WPS process;

- Knowledge dissemination workshop engages relevant actors;

- National communication campaign has wide reach, high quality and relevance;

- Stakeholders engaged take concrete steps to include women in Peacebuilding;

- Studies/findings have high quality and are well disseminated;

- Targeted/identified women have the motivation to engage in peacebuilding activities.

These assumptions were explored in the course of the evaluation in different degrees, according to the data collected and made available through various means. The evaluation looked to which extent the project was able to empower women, including those in vulnerable situations, to strengthen the peacebuilding process and social cohesion in Sri Lanka including through implementation of the NAP WPS (outcome), thus being able to contribute to sustainable peace in Sri Lanka (impact). In order to do so, the evaluation explored to which extent the project was able to contribute to create an enabling and inclusive policy environment (mobilization of key actors and capacity building activities to national and local governments and strengthening of facilities and office infrastructure) and build capacity at a local level for women, especially for those in vulnerable situations.

Figure 1. Reconstructed Theory  of Change

# Evaluation Purpose, Objectives and Scope

According to the Term of Reference (ToR), the evaluation purpose is to provide useful learning to support evidence-based decision making, demonstrate accountability to donors and stakeholders, and inform and guide future peacebuilding programming at UN Women Sri Lanka and the UN Women Regional Office for Asia and the Pacific. It also aims at informing programming of other UN agencies such as UNDP, and government institutions like the Ministry of Women, Child Affairs and Social Empowerment focused on women’s engagement in the context of peacebuilding.

As stated in the TOR, the objectives of the final evaluation are:

  - to assess the project’s progress towards the expected outputs and outcomes set forth in the project results framework along the OECD-DAC criteria: relevance, coherence, effectiveness, efficiency, sustainability, and gender equality and human rights;

  - to assess to what extent the project has engaged with women, men, decision makers at the national and local authority level on matters related to women, peace and security;

  - to assess the level of cooperation/networking and coordination amongst key stakeholders of the project: implementing partner, Ministry  of Women, Child Affairs and Social Empowerment, Sri Lanka Womens’ Bureau, District Secretariats (Moneragala, Ampara, Batticaloa, Vavuniya and Jaffna), project direct beneficiaries, consultants involved in the project, and contractors involved in the project;

  - to assess the benefits of engaging women in peacebuilding as a means to promote gender equality, women’s empowerment, diffusing triggers of violence, as proposed by the project;

  - to identify and validate lessons learnt, good practices, and examples of interventions that support the implementation of the WPS agenda; and

  - to provide a set of clear, forward-looking, actionable recommendations for UN Women interventions, and generate knowledge to inform replicable, scaled-up interventions and guide future peacebuilding programming;

The evaluation covered the whole period of project implementation, from 01 January 2020 to 31 December 2022. From a geographical perspective the project looked at the implementation from a national and local perspective. It covered the districts of Anuradhapura, Polonnaruwa (North Central Province), Badulla, Moneragala (Uva Province), Ratnapura, Kegalle, (Sabaragamuwa Province), Colombo, Gampaha, Kalutara (Western Province), Ampara, Batticaloa (Eastern Province), Jaffna, Vavuniya, Mannar (Northern Province). A sub-set of project locations was more directly engaged as part of the data collection process, namely: the districts of Mannar, Vavuniya, Batticaloa, Ampara, Moneragala and Anuradhapura.

The final evaluation answered the following questions outlined in the Evaluation Criteria provided in the next table. The evaluation was conducted in accordance with the United Nations Evaluation Group Norms and Standards as well as the UN Women Evaluation Policy and Handbook (please see item on Ethics of the Evaluation), and guided by the Global Evaluation Reports Assessment and Analysis System (GERAAS). It is important to note that these questions were taken from the ToR with suggestions from UN Women´s team and they are detailed in the Evaluation Matrix in Appendix B.

Table 2. Evaluation Questions

| Criteria | Evaluation Questions (EQ) |
| --- | --- |
| Relevance: the extent to which the project has contributed to addressing the needs identified in its design | Evaluation question 1: To what extent were the project’s strategies relevant to local and national contexts and aligned with national priorities? Evaluation question 2: How has the project adapted to contextual changes, including the COVID-19 pandemic and the economic crisis, in order to remain relevant? Evaluation question 3: To what extent did the project align with and address the needs and priorities of the intended beneficiaries and the principle of “leaving no one behind”? |
| Coherence: the extent to which the project addresses synergies and interlinkages with UN Women’s overall programming on WPS (internal coherence) and complements other actors’ interventions on WPS in Sri Lanka (external coherence). | Evaluation question 4: To what extent is the project coherent internally? Is the project aligned with UN Women’s strategic planning? Evaluation question 5: To what extent is the project coherent with the overall WPS Agenda? To which extent does the project have a holistic/systemic approach in connection to the SDG agenda? Evaluation question 6: What is the comparative advantage of UN Women in the implementation of the WPS Agenda, compared with other UN entities and key partners in Sri Lanka? To what extent has the project capitalized on its comparative advantage? Evaluation question 7: To what extent is the project coherent externally with the interventions of other development actors in Sri Lanka (particularly within the UN system)? |
| Effectiveness: the extent to which the project has contributed towards its delivering outputs to achieve the outcomes targeting the beneficiaries to reach output and outcome-level results | Evaluation question 8: To what extent did the project deliver planned outputs? Evaluation question 9: To what extent did the output level interventions translate into progress towards outcomes? Evaluation question 10: To what extent has the project contributed to promoting women’s meaningful engagement in conflict prevention and social cohesion at the community level? Evaluation question 11: To what extent have capacities of duty-bearers and rightsholders been strengthened as a result of the project? Evaluation question 12: Were there any unexpected results (either positive or negative) as a result of project related interventions? Evaluation question 13: How did the project minimize the unintended negative consequences (dividers) and built on the positive consequences (connectors)? Evaluation question 14: What were the reasons for the achievement or nonachievement of planned results? Evaluation question 15: To what extent did the project make timely adjustments to its strategy to maintain its relevance and effectiveness? Evaluation question 16: How have stakeholders’ engagement on WPS changed as a result of this project? Which stakeholders have been newly engaged as a result of the project? Evaluation question 17: What measurable changes in gender equality and women’s empowerment have occurred as a result of the project? |
| Efficiency: the extent to which the project was efficiently managed, implemented and has delivered quality outputs, against what was planned (including official amendments) | Evaluation question 18: Have financial and human resources been allocated sufficiently and strategically to achieve project outcomes? Evaluation question 19: Have the outputs been delivered in a timely manner? Evaluation question 20: Have UN Women’s organizational structures, systems and mechanisms effectively supported delivery of the project? Evaluation question 21: Are the changes/results observed worth the resources spent? Evaluation question 22: How efficient was the project coordination between UN Women and Implementing Partner, including clarity of roles and accountabilities, monitoring and reporting, and potential added value? Evaluation question 23: Where there a clear Results Framework and a process of continuous monitoring of the project´s progress? |
| Sustainability: the extent to which the project has potential for sustainability | Evaluation question 24: To what extent has the project developed the capacity of government stakeholders, community leaders and other beneficiaries to ensure sustainability of efforts and benefits beyond the project? Evaluation question 25: Are national partners committed to continuing the project or elements of the project? Evaluation question 26: Are there any mechanisms developed and/or interventions linked with existing mechanisms at local and national levels to ensure continuation of contribution towards the WPS agenda? |
| Gender Equality and Human Rights: the extent to which the project has integrated gender, human rights and disability inclusion into the program design and implementation | Evaluation question 27: To what extent have gender equality, disability inclusion and human rights considerations been integrated into the project design and implementation? How to better incorporate them? Evaluation question 28: To what extent did the project address and respond to existing power dynamics and gender relations? |

Gender quality and human rights was used as a cross-cutting theme to be considered throughout the whole evaluation process – from its design to its implementation and sharing of results.

# Evaluation Methodology

### Overall methodological approach and design

The methodology responded to the indicators proposed for each evaluation question (See Appendix B for the evaluation matrix). A mixed method approach was used, and triangulation was key in order to contrast different sources and reach a common ground which is based on evidence. Triangulation took place using a variety of information sources: official project documents, UN Women representatives, informants from the government, a representative from the Government of Japan, donors from G7 countries, Civil Society Organizations and women beneficiaries. Triangulation allowed us to check different sources and views in order to identify a broader understanding of what has actually taken place as part of the project.

The evaluation design was a) Theory Based systemic approach and b) attributed value to the project through the Gender Results Effectiveness Scale. The Theory based systemic approach was  developed through the following steps: 1) Reconstruction of the theory of change by project team; 2) Validation of Theory of Change by project team during inception phase; 3) Design of methodology (evaluation matrix) and data collection instruments using the assumptions identified in the reconstructed Theory of Change; 4) Data collection probing for assumptions, results expected, intervening factors, unexpected results and broader contextual influential factors;  5) Data analysis and design of evaluation report in dialogue with the initial Theory of Change drafted; 6) Presentation of a reviewed Theory of Change based on actual data collected and analysis made in order to help mature future interventions of UN Women´s office, the Government of Sri Lanka and the Government of Japan in the field of WPS.

In its approach to a systemic intervention, the evaluation used the concept of ´transformational change´ as proposed by Uitto (2022)  as change toward a more sustainable, inclusive, resilient, and environmentally sound state. Transformational change refers to the goal of having a more systemic and deep-rooted type of change. In the context of this project, this will be considered as a change in 1) Mentality; 2) Social Structure which is more inclusive; 3) Economic progress; 4) Sound and respectful relationship with natural resources. The Theory of Change which was revised during data collection included an analysis on these four aspects to see whether the project was transformational, indicating what worked and what did not work in the path towards the promotion of a more systemic change, as often, interventions are found to be overly ambitious or rather consider change from a very limited perspective.

In terms of the Gender Results Effectiveness Scale (GRES), the evaluation team used this tool inspired by the document UN Women’s Good Practices in Gender Responsive Evaluation document (2020). This document shows a scale created in the context of the evaluation of the United Nations Development Programme (UNDP) contribution to Gender Equality and Women's Empowerment (GEWE). This scale is described below:

Table 3. Gender Results Effectiveness Scale

| Gender negative | Result had a negative outcome aggravated or reinforced existing gender inequalities and norms |
| --- | --- |
| Gender blind | Result had no attention to gender, failed to acknowledge the different needs of men, women, girls and boys, or marginalized populations |
| Gender targeted | Result focused on the number of equity (50/50) of women, men or marginalized populations that were targeted. |
| Gender responsive | Result addressed differential needs of men or women and addressed equitable distribution of benefits, resources, status and rights but did not address root causes of inequalities in their lives |
| Gender transformative | Result contributed to changes in norms, cultural values, power structures and the roots of inequalities and discriminations |

The GRES assessed the results at a project level. It was built on an analysis of results at an output level which led to an overall analysis of the project.

### Data Collection

The methodology of the evaluation includes:

- Desk review of relevant documents: The desk review has considered all the key documents involved in the design and management of the project (project document, results framework, Annual Project Progress Reports, knowledge products, report from main implementing partner etc). For the full list of documents, please refer to Appendix C.

- Remote and in person semi-structured interviews: These included project staff and stakeholders from the Government, UN Women, a representative of the Government of Japan, G7 donors, Chrysalis, Hashtag Generation and others in order to determine the nature of the interventions implemented, the objectives and outcomes. National, District and divisional level government officials, local-level coordinators of Chrysalis and individuals responsible for the implementation of project interventions, as well as state service providers targeted through this project who were identified as users of government buildings refurbished as part of this project in the relevant districts of project implementation were interviewed. (See Stakeholder Analysis in Appendix F for full list of individuals consulted).

- On-line surveys: Two surveys were carried out for this evaluation; the first, for the parties consulted for the NAP validation consultations, which included government officials who were capacitated on the concepts of gender and women peace and security,  and participants of the multi-party dialogues. The second survey was shared among the youth who participated in the digital training on prevention of violent extremism (PVE) . These stakeholders were selected for online responses as they have access to online resources and were expected to be able to answer the surveys. The two surveys were available in all three language and recorded responses of 56 and 32 persons for those who participated in the NAP validation consultations,  and Multiparty dialogues, and digital trainings on PVE respectively.

| NAP Consultation and MPD Participants Summary Survey Results |  |  |
| --- | --- | --- |
| Sex disaggregation of survey respondents | 38 females (70.3%); 16 males (29.6%); Total 54 |  |
| Age distribution | Between 20-29 | 3.7% (2) |
|  | Between 30-39 | 16.67% (9) |
|  | Between 40-50 | 22.22% (12) |
|  | Over 50 | 57.4% (31) |
| Type of stakeholder | National government | 29.63% (16) |
|  | Civil society organisation | 29.63% (16) |
|  | Local government | 27.78% (15) |
|  | Legal Aid Commission | 1.85% (1) |
|  | UN Agency representative | 1.85% (1) |
|  | INGO | 1.85% (1) |
|  | Private sector | 1.85% (1) |
|  | Youth Parliament | 1.85% (1) |

| Digital Training Participants’ Survey Results |  |  |
| --- | --- | --- |
| Sex disaggregation of survey respondents | Total 32 31 participants identified as female; 1 chose not to say |  |
| Age distribution | Between 20-29 | 100% |
| Geographial distribution | Eastern Province | 6.25% (2) |
|  | Western Province | 43.75% (14) |
|  | Northern Province | 40.63% (13) |
|  | Other | 9.38% (3) |
| How they connected to this training | Through colleagues/teacher/ Other people | 43.75% (14) |
|  | Online/ social media | 50% (16) |
|  | Webpage | 6.25% (2) |

- Focus Group Discussions (FGD): A major part of the stakeholders were consulted via focus group discussions. The following groups were consulted via FGDs: a) participants engaged in the NAP validation consultations and multiparty dialogues; b) CBO members who participated in social cohesion dialogues and trainings ; c) Participants in  Business Skills Development Training  and beneficiaries of in-kind support; d) Government staff at  local level who benefited  WPS capacity building trainings and knowledge exchange workshops. In the case of focus group at a local level, these discussions were carried out in the predominant local language of either Sinhala and/or Tamil to allow the identified participants/beneficiaries to voice their opinion about the activities of the project. In person Focus Group Discussions took place in the districts of Vavuniya, Ampara and Moneragala, while virtual interviews were conducted in the districts of Mannar, Ampara, Moneragala and Anuradhapura to ensure inclusiveness of participants who were located across the district.

### Sampling

During the inception process, a stakeholder analysis was carried out, considering who the major actors were and their role in the project to identify the list of people to take part in the semi-structured interviews. In addition, as part of the evaluation. in the semi-structured interviews, actors were asked to refer to other relevant stakeholders who should be considered in the process (snowball sampling).

As for the locations for the Focus Group Discussions, a set of districts was chosen as a proxy to understand what happened in the different geographical locations involved in the project, as well as to account for different perspectives based on ethno-religious diversity  and other intersectional factors including conflict affectedness in order to record diverse experiences of respondents. The districts selected for in-depth review were the districts of Batticaloa, Ampara, Moneragala, Anuradhapura, Vavuniya, and Mannar.

The districts were selected based on the predominant number of implementation activities that occurred in these locations. Where project related implementation activities took place with community level beneficiaries/rights holders, the evaluation team conducted interviews in the relevant Divisional Secretariat (DS) Division in an attempt to capture diversity of experiences as well as to capture contextual variations based on geographical location.

| District | Reason for selection |
| --- | --- |
| Vavuniya | Is located in the Northern province and characterised by structural factors and societal circumstances compounded by post war realities it is characterized by a higher number of FHHs, recognized as one of the most vulnerable groups in the country (Viluthu, 2022). Project implementation activities included: - Social cohesion dialogues and trainings - Business skill development trainings - Refurbishment/renovation of infrastructure - Emergency relief distribution - Participants from the training on PVE |
| Mannar | A district representing the Northern province and characterised by structural factors and societal circumstances compounded by post war realities. Has a higher representation of ethnic minority communities. Project implementation activities included: - WPS capacity building trainings - Participants from the training on PVE |
| Batticaloa | A district representing the Eastern province with a multi-ethnic population composition (majority of Muslim and Tamil), recognised as having a relatively higher predominance of incidence of hate speech, particularly in the aftermath of the Easter Attacks in April 2019 Project implementation activities included: - Refurbishment/renovation of infrastructure - Participants from the training on PVE |
| Ampara | A district representing the Eastern province with a higher representation of majority of Muslim, recognised as experiencing a relatively higher predominance of incidence of hate speech, particularly in the aftermath of the Easter Attacks in April 2019. Project implementation included - Social cohesion dialogues and trainings - WPS capacity building trainings - Business skill development trainings - Refurbishment/renovation of infrastructure - Emergency relief distribution - Participants from the training on PVE |
| Moneragala | The district of Moneragala has a higher representation of ethnic majority population and is characterised by a scarcity of resources and being relatively under-developed compared to other districts. Project implementation activities included: - Multiparty dialogues - Social cohesion dialogues and trainings - Business skill development trainings - Refurbishment/renovation of infrastructure - Emergency relief distribution |
| Anuradhapura | The Anuradhapura district is located in the North Central province and has a population that predominantly represents the ethnic majority of the country. It is also an important geographic location on account of it bordering the northern province which bore the brunt of the civil war. Anuradhapura district also has the second highest numbers of military widows in the country (following Kurunegala district).[1] Project implementation activities included: - WPS capacity building trainings - Multiparty dialogues - Recipients of laptops for implementation of WPS activities |

[1] https://cejsrilanka.org/wp-content/uploads/Sexual-Bribery-Of-Military-Widows-English.pdf

Where interviews with rights holders were conducted, respondents from different DS divisions were interviewed to obtain diverse and unique perspectives based on distinct geographic and ethnic characteristics. To this end, in the district of Vavuniya, interviews were conducted with respondents located in the DS Divisions of Nedunkerny and Vengalachcheddikulam; in the district of Moneragala, interviews were conducted in the DS Divisions of Siyambalanduwa and Madulla; while in the district of Ampara, interviews were conducted in the DS Division of Karaithivu.

. Data about project implementation activities in other districts came from the semi-structured interviews with national government counterparts, project staff and also Chrysalis as the main implementation partner, in addition to the two surveys deployed.

The table below presents a list of interviewees by type.

Table 4. Categories of Stakeholders  Interviewed

| Category | Number of Stakeholders | Data collection methodology |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Total | Female |  | Male | Type |
| Rightsholders* |  |  |  |  |  |
| - Representatives of Community based organisations who received capacity development on social cohesion (3 districts: Ampara, Vavuniya and Moneragala) | 24 |  | 24 | 0 | FGDs |
| - Direct beneficiaries of WEE support (3 districts: Vavuniya, Ampara, Moneragala) | 34 | 34 |  | 0 | FGDs |
| - Participant of the Multiparty Dialogues (4 districts: Moneragala/ Badulla, Anuradhapura/ Polonnaruwa) | 18 | 13 |  | 5 | FGDs and Survey |
| - Participants of digital training component | 32 | 32 |  | 0 | Survey |
| * There were overlap in certain districts of the participants where multiple interventions were implemented |  |  |  |  |  |
| Local Government staff |  |  |  |  |  |
| - WDOs, District Secretary, EDOs (4 districts Ampara, Batticaloa, Vavuniya, Moneragala) | 23 |  | 16 | 7 | KIIs /FGDs |
| - MPD participants (4 districts: Moneragala/ Badulla, Anuradhapura/Polonnaruwa | 4 | 4 |  | 0 | FGDs |
| - Participants of capacity building programmes (3 districts: Ampara, Mannar, Anuradhapura) | 14 | 10 |  | 4 | FGDs |
| - Beneficiaties of refurbishment of govt facilities (2 Districts covering 3 DS divisions in Batticaloa and Moneragala) | 3 | 3 |  | 0 | KIIs |
| - NAP consultation survey respondents | 15 | 13 |  | 2 | Survey |
| Implementing CSOs and private partners |  |  |  |  |  |
| - Chrysalis | 4 |  | 1 | 3 | KII |
| - Hashtag Generation | 4 | 1 |  | 3 | KII |
| - Training facilitators and consultants | 4 | 2 |  | 2 | KII |
| Representatives of UN Agencies** |  |  |  |  |  |
| - UN Women as implementing agency | 6 |  | 6 | 0 | KIIs |
| - Other UN women stakeholders including ERG and Regional colleagues | 2 | 2 |  | 0 | FGDs |
| **It was not possible to conduct interviews with previously identified representatives of other UN Agencies |  |  |  |  |  |
| National Government Officials - Ministry of Women, Child Affairs and Social Empowerment (MWCASE) | 1 |  | 0 | 1 | KIIs |
| - National Committee on Women (NCW) | 1 | 1 |  | 0 | KIIs |
| - Women’s Bureau of Sri Lanka | 1 | 1 |  | 0 | KIIs |
| - Survey respondents | 16 | 10 |  | 6 | Survey |
| Donor Agency (Japan) | 1 |  | 1 | 0 | KII |
| Development Partners representatives (members of the G7 + working group) | 6 | 5 |  | 1 | KII |
| Total | 213 |  | 179 | 34 |  |

### Methods of Analysis

The evaluation combined a number of methods of analysis: 1) Identification of key themes, challenges and contents in the desk review through individual notes by both consultants which helped facilitate dialogue with project staff; 2) Review of quantitative data in the project documents and analysis of survey data using descriptive statistics, 3) Systematization of qualitative data through key themes and quotes according to evaluation questions and indicators presented in the report.

The international consultant carried out the interviews in English with the assistance of the national consultant. The data collection in Sinhala was carried out by the National Consultant and the data collection in Tamil was carried out by a research assistant.

It is important to emphasise that the evaluation team was very careful about not identifying the participants of the evaluation and any particular situation which may link the quote with the respondent.

### Limitations, Risks Involved and Mitigation Strategies

During the inception phase, 4 risks were identified and are described in the next table along with their mitigation strategies. Overall, the major risk is in the process of data collection – difficulties in being able to interview key stakeholders due to government changes and the context in the country - proved relevant. Not all the stakeholders which the evaluation planned to consult were consulted, mainly government partners from other ministries. There was also limited engagement in the survey for government stakeholders at a local level. The evaluation team reached out to former staff from UN Women and also a wider group of project consultants to help fill in the data gaps. Another risk identified was in conducting the field work due to the fuel crisis in the country, but this did not prove to be a challenge afterall.

The evaluation team also had some difficulties in being able to interview other UN Agencies in the country, staff was not available to take part in the interviews in the evaluation timeframe or the relevant people had left the organization.

Table 5. Risks Involved and Mitigation Strategies

| Risk | Likelihood | Mitigation strategy |
| --- | --- | --- |
| Lack of response from key government actors due to government change and political instability in the country | Medium | Reaching out for former government staff and also other relevant actors who remain in power |
| Change in key stakeholders who are no longer accessible | High | Consulting other stakeholders who may now be the decision makers to probe for the future of the WPS agenda in the country |
| Difficulties in engaging women beneficiaries in Focus Group Discussions | Medium | Reaching out to women who may be more engaged with the project. |
| Lack of engagement from ministries and local government representatives in responding to request for Focus Group Discussions | High | Reaching out to other government departments apart from the Ministries consulted during the project. |

# Ethics of the Evaluation

The evaluation was based in the principles set by the United Nations Evaluation Group in the document ´Norms and Standards for Evaluation´ which has served as a landmark document for the United Nations and beyond. The UNEG guidelines for Integrating Human Rights and Gender Equality in Evaluations will also be used in the process. All the participants were briefed about the confidentiality and anonymity of the information. The consultants are fully independent from any organization that have been involved in designing, executing or advising any aspect of the UN Women Sri Lanka project that is the subject of this evaluation.

Moreover, the evaluation considered the principle of ´Do No Harm´, which consists of a careful and deep respect towards beneficiaries and special caution about not increasing conflict.

The UNEG principles used for this evaluation are detailed below to ensure they are truly incorporated in the evaluation process from the beginning to the end. They are as follows:

- Utility: the evaluation served the different stakeholders involved with the purpose of helping with decision making and answering the questions posed by the comissioning organizations.

- Necessity: the evaluation was conducted bearing in mind that it is needed for the Project team to enhance learning and accountability. It was not arbitrary and respected time and resources devoted to it.

- Independence: the evaluation was free of bias. The evaluation team exercised its Independence, attributing value to the Project based on evidence and not only on any personal interest of any kind.

- Impartiality: every initiative has its own merit and setbacks. The evaluation aimed to be balanced in terms of showing both sides of what has taken place in the course of Project implementation considering the context within which it was operating.

- Credibility: the evaluation was based on rigor design, data collection, observation and analysis so that it is credible and of high quality.

- Conflicts of Interest: the evaluation team has no conflict of interest in the evaluation.

- Honesty and Integrity: the evaluation team has openly pointed at the limitations of the evaluation in the report.

- Accountability: the evaluation team was committed to completing the evaluation within the timeframe and budget agreed as per signed in the contract.

- Information protection: this evaluation informed everyone about data management and protect the confidentialy of the Information provided by stakeholders and other actors involved in the evaluation.

- Respect for Dignity and Diversity: the evaluation tem took into account and respect the diferences in culture, local customs, religious beliefes and practices, disability, age and ethnicity, respecting all the individuals who were part of the evaluation process.

- Respect for individual will and sensitivity towards vulnerability: individuals were respected in their right to participate or not in the evaluation. The evaluation seeked to hear the ones who are more vulnerable and ensure their inputs were included in the evaluation report.

- Confidentiality: participants were briefed about their right to provide Information in confidence. Information in the report was disclosed in a way not to reveal the identity of informants.

- Avoidance of Harm: the evaluation seeked to minimize risks and burdens on the participants of the evaluation through scheduling interviews and focus group discussions in the most appropriate location and taking into consideration convenience of timing for identified stakeholders.

- Accuracy, Completeness and Reliability: the evaluation team seeked to present the most accurante, complete and reliable report it is able to, according to its capacity and in its best will and faith.

- Transparency: the evaluation made the commissioners of the evaluation informed of all the evaluation procedures and steps in the course of the evaluation.

- Reporting: the evaluation team made the evaluation report available for the comissioning organizations and encourage them to share with the other stakeholders.

### 5.1 Ethical Protocols Associated with Data Collection

The evaluation team took measures to ensure data collection and physical interaction with identified respondents adhered to the most recent WHO guidelines as well as national protocols in place to minimise any harmful impact on either the evaluation team or the identified respondents. When conducting data collection interviews, respondents’ participation were based on verbal informed consent – which was clearly communicated to them prior to commencement of the interview or focus group discussion. The evaluation team (including the research assistant) engaged in conducting the interviews made efforts to adhere to the principles of ‘do no harm’ and ethical guidelines elaborated above with regard to gathering information which fed into the evaluation report.

Lastly, it is important to note that the data from this evaluation was stored in the evaluators Personal Computers and this raw data will not be shared to any parties outside the commissioning organizations and was deleted upon completion of the report. Data in the report was anonymized.

# Quality Assurance and Evaluation Management

UN Women has developed a Global Evaluation Reports Assessment and Analysis System (GERAAS). The purpose of GERAAS is to give guidance and an Evaluation Quality Assessment to review evaluations carried out by the institution. It is guided by UNEG norms and standards. The evaluation team consulted the GERAAS matrix and is aware of the expectations for this evaluation process and delivery of final evaluation product.

According to the Term of Reference for this evaluation an Evaluation Management Group (EMG) and Evaluation Reference Group (ERG) was established to oversee and facilitate the evaluation process. The EMG was composed by the UN Women programme focal points (project officer and programme implementation consultant) and the UN Women Regional Evaluation Specialist. It provided quality assurance to the entire evaluation process and approve all deliverables. The EMG was under the supervision of the UN Women Sri Lanka Country focal point.

The ERG was established including the key stakeholders (from the Government and Chysalis, as the key implementing partner), and was consulted throughout the evaluation process. They were invited to participate in the inception phase and provided feedback and were also invited to the presentation of the preliminary evaluation findings.

# Evaluation Findings

## Evaluation Criteria: Relevance

Finding 1. The project was very participatory and promoted a wide consultation on the needs of women in the process of drafting the National Action Plan and promoted relevant training for government officials and women on the ground on gender equality and WPS. It further provided needed assistance for improving infrastructure of women´s related services and adapted to demands of the national government.

Finding 2. The project aligned with the national government´s aspirations in the agenda of Women´s Economic Empowerment and supported sustainable livelihoods and small scale businesses in the context of the economic crisis. However, the agenda of Women, Peace and Security was not a priority to the national government specially in the context of continuous change of government officials and serious economic and political crisis in the country at the time as the project implementation timeframe.

Finding 3. The project was able to adapt to the COVID-19 pandemic and provided relevant relief packages for women. The economic crisis in the country posed a lot of challenges especially with the great fluctuation in prices which made contracts outdated.

Finding 4. The project targeted vulnerable women from different ethnicities and incorporated their view in the policy consultations with the perspective of leaving no one behind. It was less successful in incorporating women with disabilities as per the data made available to the project team.

Alignment with National Policies and the Women, Peace and Security Agenda

- The drafting of the NAP on WPS has considered previous policies in the country and the voices of a myriad of women in Sri Lanka through consultations. The draft of the NAP was carefully designed and approved as part of the project, considering previous drafts, existing policies, national and political sensitivities. It incorporated findings from consultations with relevant government ministries, state officials who work closely with communities (such as Grama Seva Niladharees, Women Development Officers, police officers, representatives of the Human Rights Commission of Sri Lanka, doctors working on women’s issues, officers working on land and housing matters and disaster management), UN Agencies, Civil Society Organizations and women leaders at grassroots levels, as well as women from different parts of the country who have been affected by conflict and are vulnerable in diverse ways. Women consulted included, representatives of minority ethnic and religious communities, female ex-combatants, persons with disabilities, families of the surrendered, women from the plantation communities and women involved in de-mining operations (to name a few). This made the draft NAP submitted to the cabinet of Sri Lanka comprehensive and a reflection of needs on the ground in a context where few policies undergo such a wide consultation. This was a key achievement of the project and involved a very participatory process.

- The discussion of conflict and the aftermath of the war is recognised to be a sensitive subject in the country and the intersection of women and security cannot be framed purely from a post conflict context. Rather the project adapted and built a narrative on the participation of “women in crisis”, building on the experiences of women during the pandemic as a less sensitive subject area. Furthermore, the implementation of the UNSCR 1325 and its agenda still seems foreign to a broader Sri Lankan context, although there was recognised value in understanding the content, particularly among groups unfamiliar with the UNSCR 1325 prior to the project. There were many changes in the government and national policy framework during the discussion and preparation of the NAP due to political instability and continuous changes in the government, contributing to  various government officers having different views about the content of the NAP, which made alignment of the NAP with the government a continuous task.  Furthermore, the context in which the NAP was being finalised was characterised by a global pandemic, followed by the political and economic crisis which resulted in a shift in priorities from policy discourse to immediate relief efforts. The National Action Plan on WPS corresponds with content included within the draft “National Policy on Gender Equality and Women’s Empowerment” which has since been presented to the Parliament of Sri Lanka and was approved in February 2023. This policy intends to provide the mechanisms and guidelines for ensuring the empowerment of women and girls and the enjoyment of freedoms guarantees under the constitution, national legislation and obligations undertaken by the state.

Alignment of the project with the needs on the ground

- Needs assessments were carried out as part of the project implementation prior to the implementation of trainings for government officials and prior to the business trainings for women on the ground. This helped tailor capacity building initiatives. ​The data collected from the frontline government officers attached to the Women’s Bureau of Sri Lanka, working in the Ampara, Anuradhapura and Mannar districts and the officers of the State Ministry of Women and Child Development, Pre-Schools & Primary Education, School Infrastructure & Education Services (Capacity Assessment Report, May 2022) helped to design capacity building courses for the government. This data collected helped design courses which were reported by government officials to be relevant to their work. In addition, there was a needs assessments prior to the trainings along with a Value Chain Study to explore possible context specific economic opportunities for women were also carried out. This happened in this project and the women consulted via focus group discussions referred to the contents of the business development trainings led by Chrysalis as relevant and responsive to their needs.

Capacity of the project to adapt to changing circumstances

- The project was flexible to respond to the demand of the national government in incorporating the renovation of women´s shelters, economic support centres and counselling spaces as part of the project although it had difficulties in meeting the building targets within the project timeline and to tailor the refurbishment to specific local needs although extensive consultations were made. There were internal communication challenges within the government to appropriately present the refurbishment demands to UN Women. As part of the project, UN Women was asked to include support in the form of infrastructure development to women´s support venues at a local level (shelters, counselling rooms, offices, and economic support centres) as well as mobile sales carts. These changes were incorporated at the new project design right at the beginning of the implementation phase. Although some relevant structures were built to help better welcome women and meet their needs, not all the refurbishment spaces were deemed to be fully reflective of the needs of the local officers providing the services (i.e. counselling officer) or the intended recipients. For example, in the Vavuniya district, the justification for selecting the candle making factory for renovation was not known by the frontline government officers consulted as part of the evaluation, as they were not part of the consultation or decision making process related to site selection, despite the formal request being communicated to UN Women through the Women's Bureau.  The actual use/utility of the candle making factory once completed is called into doubt as there appears to be a lack of communication within the relevant DS Division or among women entrepreneurs as possible beneficiaries.  Comparatively, the renovation of the WESVA local economic development centre was positively welcomed, particularly due to the greater number of community members it was able to serve and its utility even while renovation was being completed at the point of data collection as part of this evaluation. It was recognised that it was a very difficult process to reach an agreement on the specificities of the refurbishment needed once implementation began due to challenges associated with travel restrictions which limited the ability to verify the materials and area to be renovated by a specialist prior to implementation. It is further recognised that where feasible, the needs of the local service providers were incorporated, such as in increasing the length of a partition in the space or adding privacy glass instead as an alternative to clear glass. UN Women made an effort to accommodate as many change requests as possible, keeping a contingency of 10% of contract value for this purpose. It was stated by the UN Women team, that the decision on infrastructure development projects to be renovated or constructed was at the discretion of the Women’s Bureau with UN Women team having no opportunity to determine feasibility prior to commencement. It is recommended that in future infrastructure related interventions, a needs assessment is carried out following the request from the State body to ensure highest level of utility of the final output.

- The project was also flexible enough to respond to the requests by the national government to expand the scope of the project to include women from the Colombo district to the economic and livelihood support component. This allowed women entrepreneurs negatively impacted by COVID-19 and the economic crisis – who predominantly represented female headed households (FHHs) to be included within the project interventions. This cohort is usually not identified as vulnerable due to their proximity to the country capital and market linkages.

- The price fluctuations in the country due to inflation were so high that it put at risk many project contracts which became obsolete overnight. This also affected the sourcing of materials and equipment for recipients of in-kind assistance which was a component of the business skill development training output . This led to difficulties in adaptation. The economic crisis in the country made prices of building materials double or triple overnight and stocks were limited due to import restrictions imposed. For the service delivery related to IT systems components for example, the depreciation of the rupee proved to be a challenge. This brought many difficulties to the project and the need to amend contracts. As delivery of hard infrastructure and IT systems was a new area of work for UN Women, it was faced with demands it did not have experience in managing, although expert consultants were hired to help in this process.

Inclusion of minorities, women with disabilities and protection in times of crisis

- There were attempts to include women with disabilities in the project but these were not fully successful. The project was not able to fully include women with disabilities within the economic support component of the interventions. The primary focus on the selection criteria was to identify the businesses that had a potential for growth and expansion, and livelihoods which were sustainable enough to move to next level. There were occasions in which women with disabilities were identified by the relevant DS Division officers but they did not attend the activities due to health and safety concerns in the backdrop of COVID-19 or because they had already benefited from support provided by previous project interventions. On the other hand, Women with disabilities were included during the NAP validation consultations and the multi party dialogues which were project interventions related to validating and implementing policies on WPS (Output 1). However, there are many challenges in including women with disabilities.  Their limited inclusion in the economic component of the project may also be linked to  a result of the attitude of women themselves which is an item to be considered for future interventions.

- The project included different ethnicities and minority groups. There were always trainings and benefits for both Tamil and Sinhalese women represented by the geographic spread of the project. For the business skills development training component, the project identified vulnerable women based on a selection criterion determined by the implementation partner (Chrysalis) in consultation with UN Women and District and Divisional Government Stakeholders. For the digital training on PVE component, the applicants were selected based on a scoring system developed by the service provider (Hashtag Generation) in consultation with UN Women with a higher number of participants selected from the Northern and Eastern provinces of the country due to limited opportunities for engagement in the past. The project also promoted Multi-party dialogues involving women from different ethnic backgrounds, as well the diversity market fairs where women entrepreneurs who participated in the business skills development trainings travelled outside of their districts to present their products and businesses. All activities from the project were implemented in local languages of Tamil and Sinhalese to ensure the inclusion and where necessary simultaneous interpretation services were made available.

- The relief package provided to recipients of in-kind support was positively welcomed in a backdrop of continued economic challenges and high cost associated with acquiring daily household goods. The cost savings accrued to the project as a result of the depreciation of the Sri Lankan currency, was used to provide a relief package consisting of household and personal care items such as dry rations, spices, personal hygiene products. While the delivery of this output was not part of the original project design, it is recognised to have supported the recipients by reducing the burden of sourcing basic needs as well as supporting entreprenuers to continue to develop their burgeoning business with minimal detraction towards meeting their basic consumption needs in the backdrop of inflation.

## Evaluation Criteria: Coherence

Finding 5. The project´s approach and design is coherent and aligned with its previous initiative (Empowered women, peaceful communities: promoting peace and preventing intolerance in Sri Lanka - Japan 1) and the practice of the office in linking WPS and economic empowerment. It is aligned with UN Women´s strategic plan under Outcome 5. The project is also coherent with the overall global WPS agenda and the process of developing NAPs in the region although there are challenges in fully fitting the work on WPS and NAP within the policy context of the country,

given the shifting priorities of the national government in a context of crisis and the limits of the priority of gender equality within the government.

Finding 6. The project taps into economic and political empowerment of women, and aims at change at a policy and grass roots level which gives to it a broad understanding of women´s empowerment and social change. It does not actively reach out to the complementarity of other SDGs, but this is not deemed by the evaluation as a failure of the project. Its coherence is rather in being restricted to mobilize the women related institutions in the country which are (already) rather weak and unstable.

Finding 7. UN Women´s comparative advantage lies in its focus on women in the view of partners, but its contribution in the domain of WPS is not acknowledged by other key development actors in the country. Complementarity was identified with other UN actors in the process of NAP´s consultation, but this dialogue with other UN Agencies not follow through the end of the project.

Coherence of the project within UN Women, the debate on WPS in the country and complementarity with other SDGs

- UN Women’s work in Sri Lanka is supportive to the Women, Peace and Security Agenda and this support translates well and coherently to the project. The project was designed to promote a key policy contribution in the agenda of WPS through the design of the National Action Plan. The National Action Plan is the primary policy document to help translate WPS in any country and the project tackles that. Sri Lanka is a country yet experiencing a toll from the aftermath of a three decades long armed conflict which is still to be overcome and UN Women Sri Lanka has been engaged in timely interventions to implement this agenda within the country. As in previous projects (see evaluation of UN Women’s Multi-Party Dialogues (MPDs) of the Project “Participation of Youth and Women in Peacebuilding Process”; and  Addressing Sexual Bribery Experienced by Female Heads of Households, including Military Widows and War Widows in Sri Lanka to Enable Resilience and Sustained Peace), UN Women Sri Lanka brings in a valid combination of high-level policy dialogue and consultation, grass roots work in political dialogue and awareness and implementation of well tested programmes for economic empowerment (based on the expertise of Chrysalis as a constant implementing partner). It is aligned with other current and past interventions within the office which tackle peacebuilding and women´s economic and political empowerment in the country. In addition, the project is aligned with UN Women Strategic Plan (2018-2022) Outcome 5 which is “Women and girls contribute and have greater influence in building sustainable peace and resilience and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action”.

- The WPS debate in the country is still in its infant stages which poses challenges and opportunities for projects in this area. The rationale of helping promote the role of women as peacebuilders in their communities has not been fully accepted in the national context. This is illustrated by the difficult and long-drawn out process of obtaining approval for the NAP and by feedback received through Focus Group Discussions with CSO members and KIIs with government officers where WPS was not seen as a priority).. It is important to acknowledge that during project implementation, the country was faced with multiple crisis (COVID-19, economic and political challenges) which resulted in the  political debate being captured by these urgent priorities. The agenda of women´s empowerment is not deemed very relevant in the country and the agenda of Women, Peace and Security (WPS), even less so. This speaks for the challenges the project faced in disseminating its main advocacy message, but also shows that this agenda is still largely unexplored which suggests the need of identifying new ways of approaching it (finding new stakeholders and project implementation designs). Through the Key Informant Interviews and Focus Group Discussions with government officers and CSOs, respondents recognised that there is yet much to be done in the area of recognising WPS as priority in the backdrop of COVID-19 and the ongoing economic crisis, even with the National Action Plan being approved by the cabinet. To this end it is recognised that further work in this area will be necessary, such as conducting awareness programmes for the general public on the topic of WPS.

- The project gave significant, substantial and high quality participatory inputs to the NAP development process in the country. The NAP process involved consultation of women from different sectors, government agencies, UN Agencies, G7 members and CSOs and it was able to produce a substantive  policy document which was adjusted according to government´s context. The draft document produced represents the aspirations of many sectors and women in the country. This document involved a participatory policy of consultation of stakeholders at multiple levels which is not common in the Sri Lankan context. The inclusive nature of the consultations were well recognised and appreciated as captured during a field level KII, “They asked for suggestions from us. We pointed out that women’s views should be taken in this plan. It would be better to include women instead of creating laws for women by men” (Frontline government officer_Ampara district_FGD).￼

Linkages of the project with other partners, including the UN

- The project had limited outreach to partners beyond NAP´s consultation on validation given the context in the country and the ownership of the NAP by the relevant ministry. The project had an ample outreach during the process of NAP´s consultation but collaboration and partnerships did not go beyond this consultation process. The project had a sectoral approach and focused on developing its activities, with limited collaboration with other partners such as government ministries from other sectors and even the G7 countries. There was limited intersectoral collaboration which also includes UN Agencies.

The UN Agencies were involved only during the consultation process around the NAP validation and were not sufficientlyinformed of other project activities and the dialogue around NAP´s approval, so little synergy was promoted among the various UN Agencies and G7 countries. Partnership building requires time and effort and there was not enough staff time to allocate to the more political/partnership building type of work. The value added of UN Women on WPS is not clear to all partners, except for UN Women´s work on gender. Partners were engaged during NAP and in specific meetings, but there was not an effective communication with partners during project implementation. When the NAP went to Cabinet for approval, UN partners were consulted but were not aware of the status of the project and new negotiations and engagement had to take place. As staff from one UN agency reported in the evaluation survey: ´They need to communicate to UN partners much better as most do not know what they have done.´ This could have been avoided if UN partners had been provided with more updates and engagement opportunities both during and throughout project implementation. However, it is important to acknowledge that the context of multiple crisis – COVID-19, economic and political challenges brought obstacles for convening the G7 members and the Working Group on WPS. In 2022, for example, the Ministry was functioning without senior leadership and the political crisis was severe in the country. Challenges to dissemination of the validated NAP is attributed by the UN Women team to the lack of permission to disseminate the document until approval by the cabinet, as it was owned by the government and its distribution and dissemination was controlled by the relevant ministry (MWCASE).

## Evaluation Criteria: Effectiveness

Finding 8. The project was able to successfully design and approve the National Action Plan on Women, Peace and Security which was at the heart of its ambitions.

Finding 9. The project was able to deliver its planned activities which have led to progress in Output 1 (creation of advocacy space and strengthening of government´s capacities) and Output 2 (increasing of women´s capacities to promote peace and social cohesion) where 6 out of the 7 targets were achieved and less so for output 3 (coordination and knowledge exchange). The project was able to contribute to the overall outcome which was ´Women, including those in vulnerable situations, will be empowered to strengthen the peacebuilding process and social cohesion in Sri Lanka including through implementation of the NAP WPS´, even though there is limited evidence that the overall goal of the project has been achieved given the timeframe of the project - Women contribute to sustainable peace in Sri Lanka, although important results have been mapped in terms of knowledge gained being used.

Finding 10. The project contributed to strengthen the capacities of duty-bearers and rightsholders to be more gender sensitive. It was successful in increasing capacities of women to run their own businesses, and this has helped to balance gender relations within the households. It further helped to increase dialogue among government officials at different levels.

Finding 11. The project produced high quality materials on the agenda of WPS which were appreciated and used by government officials and had limited wider use. The mass media communication outputs produced by the project on the approval of NAP and WPS had high quality.

NAP´s approval and process

“I hope the National Action Plan will become a reality in the country in the future.  Compared to other countries in South Asia, the women of Sri Lanka face many different economic, social and cultural problems which are more at the rural level as their (community members’) minds have not changed yet.  Legal frameworks like this are needed to stand up for them (women) and training like this is needed.  …When men treat women as second, the patriarchal society is further strengthened. These (inequalities) can be reduced, if these proposals become reality” (Frontline government officer_Moneragala district_FGD ).

The NAP was approved despite numerous government changes and the economic crisis as a culmination of a long process of consultation and work undertaken by the project. The NAP was approved on February 27 2023 and ceremoniously launched on Women´s day on March 8, 2023. This was the major target of the project which was achieved shortly after the official end date of the initiative in December 2022. This approval was the result of a continued effort by the project which involved the consultation of Government Ministries, CSOs, women community leaders, international donor organizations and G7 Countries and just recently a continuous process of advocacy, clarification and follow up with the government. After its approval, UN Women helped to communicate the new NAP with clear and visual explanation via its social media channels.  Now there is the next step which needs to follow which is its effective implementation. Graph 1 shows how a sample of stakeholders consulted during the NAP validation consultation assess as very high or high quality of the consultation process (58%).

Graph 1. Quality of the consultation process assessed by stakeholders

Source: Evaluation Survey.

Delivery of Outputs and contribution to Outcomes

- The project was able to deliver most of its planned outputs, mobilizing some of its own resources to honour refurbishment deliverables despite the difficult contextual changes. The project delivered fully on Output 1 through the completion of multiple consultations and capacity building programmes with government and civil society networks as part of the NAP validation consultations, WPS capacity building trainings, and Multi-party dialogues. Technical equipment in the form of laptops were also provided through the Ministry to Women’s Development offices in selected districts (Ampara, Anuradhapura and Colombo) as part of this output. Under output 2, the project was able to reach and exceed its targets related to entrepreneurial skill development trainings, reaching a total of 735 women (Indicator 2.3), the provision of assets in the form of in-kind assistance to 445 women (Indicator 2.4), and capacity building of 90 young women to promote peace and social cohesion through digital trainings on prevention of violent extremism (Indicator 2.5). However, the project faced challenges in completing activities of output 2 which encompassed 45% of the total budget due to major contextual challenges and had to adapt, mainly as a consequence of COVID-19 and the economic and political crisis of 2022. To this end, the work on refurbishment, was outstanding by the end of the project cycle in December 2022 and was carried on in 2023 to be delivered with UN Women´s own resources; the capacity building component for women from grassroots organisations through the social cohesion dialogues and trainings to promote  peace and reconciliation was not able to reach its target but was able to complete 91%. Under output 3, the project was able to complete the activities envisioned in the updated results framework in terms of facilitation of knowledge exchanges among identified stakeholders, and prepare media outputs, however, despite high circulation figures recorded, the actual reach of the knowledge products available online and circulated via national media is not known as respondents from the FGDs did not recall any of the media campaigns during field level consultations. There were also important personnel changes within the Ministry of Women, which is the key government partner for this project and this brought challenges to project implementation in the form of continuous/repeated introduction of the project its objectives and securing by-in for implementation. The project design and implementation was negotiated with a team at the MWCASE and later implemented by another one which demanded further adaptation and clarification from the part of the project team.

- Project outputs contributed to the overall outcome of the project and there is  evidence of its contribution to the overall goal of the project although to a limited extent. Outputs were mostly delivered and led to increase in capacity and collaboration by government officers, Civil Society Organizations and women entrepreneurs. They are now more aware of women´s rights and policies. These capacities developed have contributed to the development of provincial and district work plans, but to which extent these will be implemented and followed through is still to be seen.. The project was able to contribute to its outcome which was ‘Women, including those in vulnerable situations, will be empowered to strengthen the peacebuilding process and social cohesion in Sri Lanka including through implementation of the NAP WPS’, but these women are not necessarily engaged in contributing to sustainable peace in the country (overall goal). This is part of a political process which has not been fully ignited yet. While participants of the workshops and capacity building programmes/trainings have been capacitated in their knowledge of issues related to gender equality, conflict resolution, economic empowerment and the overall WPS agenda, the opportunities to apply the knowledge gained is recognised as a roadblock to achieving the stated project outcome, particularly in an environment where they engage and interact with a wider group of stakeholder who lack similar knowledge or understanding. Graph 2 shows how 75% of stakeholders who answered the survey on NAP validation consultation believe the project has helped to create a favourable environment for the participation of Sri Lankan women in Peacebuilding activities just to a certain degree which is rather expected given the ambition of creating an advocacy space in the country.

Graph 2. Support of the project in creating a favorable environment to the

participation of Sri Lanka women in peacebuilding activities

Source: Evaluation Survey.

Results in capacity building

- The trainings conducted for government officers on the implementation of WPS Policies in Sri Lanka were relevant and useful for the selected participants to increase their knowledge which in turn improves their ability to deliver services to their constituents. Participants invited for this training programme included Women Development Officers (WDOs), Counselling Officers, Early Childhood Development Officers (ECDOs), Child Rights Promoting Officers (CRPOs), Child Protection Officers (CPOs), and Development Officers (DOs). The respondents from the Focus Group Discussions indicated that the knowledge gained through the programmes they participated in allowed them the opportunity to conduct awareness programmes themselves to among the community members they serve which contributed towards increasing the awareness of location specific issues faced by women, solutions to the identified challenges.  The respondents stated that when people come to them with problems they now have the knowledge to empower them and provide them with solutions that are in keeping with the legal frameworks and rights they are entitled to, that they were not aware of previously. Learning of examples from an international perspective were also stated to have been useful to be able to understand different contexts backgrounds and unique experiences.  As recorded in the training report (Activity Completion report - Training for Government officers on Implementation on of WPS Policies in Sri Lanka) and stated during the FGDs, participants knowledge on concepts of gender, WPS or UNSCR 1325 prior to the training were limited to non-existent. Trainings conducted for frontline government officers related to support on women's economic empowerment, gender equality, mentoring and monitoring, were found relevant by participants; however, the ability to transfer knowledge gained through the programme to improved service delivery was found to be dependent on the officers’ own interests/willingness as well as the willingness of their superiors to incorporate changes to the existing operational procedures based on the knowledge gained through the project interventions. The trainings conducted were introductory in nature, and were more likely to be adopted among officers who already had a preliminary understanding of the concepts discussed. Transfer of officers to other DS Divisions during the project period were recognised to result in loss of knowledge within the project implementation locations.

- Part of the training activities of the project moved to an online mode and equipment and internet service was provided for women to help them participate in the activities. This proved to be partially successful. The project was able to adapt part of its trainings and capacity building programmes to an online modality. The participants of the digital engagement trainings were provided with internet data packs and sessions were recorded in the event that participants were unable to participate in the full duration due to electricity shortages. This was necessary to deliver project activities amidst the contextual challenges experienced by the project but there was a loss in the engagement of participants in this process as reported in the survey for youth participants in the Digital Engagement Course. The trainings on Business Skills Development  were conducted entirely in-person as it was identified by the implementing partner that they would have difficulty in taking part in online activities due to limited digital literacy, devices and poor internet connectivity. This resulted in implementation delays while waiting for an opportune time to conduct the training programmes in-person leaving little time for follow up with the training participants.

“We shared many things we learnt from the training with others. This attracts many people and they approach us (for advice). For example, when we talk about prevention of domestic violence act, women realise that they have rights… People who seek counselling services have increased. It is because awareness has increased. … Since the training we have also seen a change in the co-worker… they better understand the work we are doing for helping women” (Frontline government officer_ Ampara district_FGD).

The content of the trainings provided to local government staff were valued in terms of providing initial knowledge and awareness on the concepts of gender equity, sensitivity and is deemed relevant as it corresponds in improving the delivery of services, particularly to women identified as vulnerable. However, as the content was relatively new to a majority of the participants, it was suggested that the selection of participants be expanded beyond the officers responsible for women and children related issues (i.e. WDOs and Counselling Officers) in order to expand knowledge among more state service providers and to secure buy-in/approval from superior officers when attempts are made to expand the scope of service delivery based on knowledge gained through the project.

´The knowledge gained from this training was very important, especially on how to implement the knowledge from the training in a practical setting.  It is a very valuable program…  For example, when a woman is subjected to domestic violence in a family, it is very important that we empower that woman to be able to respond to the situation (how it is best for her). In places like Anuradhapura people have no knowledge about what institutions can help or how to care for the (vulnerable) women. We got the knowledge of what is our role as officers and how we should send this message to the rural society” (Frontline government officer_Anuradhapura district_FGD).

UN Women reported that capacities of 124 Women Development Officers, Counselling Officers, Early Childhood Development Officers, Child Rights Promoting Officers, Child Protection Officers and Development Officers were strengthened as a result of the project for the work on Women, Peace and Security policies (Activity completion report Training for Government officers on Implementation on of WPS Policies in Sri Lanka). WDOs consulted during Focus Group Discussions reported the relevance of the trainings received, in the form of being better able to recognise and address issues of vulnerable women, and how they benefited from engaging with the project related interventions. They also gave relevant feedback as for the successful implementation of NAP. These included the need to enhance capacity of officers to work with Information Computer Technology (ICT) in order to increase productivity, include more men in awareness-raising and capacity-building  programs, implementing mass communications strategy at the grassroots level, communicate the progress of NAP, establish guidelines for the monitoring and evaluation, identify women  affected/ 
at-risk  of gender based violence and incidents of gender inequity ￼with information of resources available to meet their needs, and establishing a focal point at each ministry to work with affected women and create sustainable national-level and district-level coordination mechanisms for women's affairs.

- The Women’s Economic Empowerment (WEE) component of the project aimed at improving existing entrepreneurial ventures was well received by the women  who participated in the business skills development trainings. Support to existing business ventures in the form of knowledge transfers are recognised to have provided women entreprenuers with the skills necessary to improve their businesses, particularly with regard to formalising ventures from hobbies to businesses through business registration and financial management knowledge. Respondents from  Focus Group Discussions indicated they were capacitated to distinguish between revenue and profits associated with their business venture, which allowed them to cost their products. Furthermore, knowledge and the importance of labelling and obtaining business registrations were appreciated by the participants. The respondents also indicated that participating in the business skills development trainings provided them with the knowledge to develop business plans which many had not prepared previously. The development of business plans was stated to have provided the participants with the confidence to be able to secure finances from a bank if necessary to expand their business venture, particularly appreciated by respondents who had not received in-kind assistance.  The training is also recognised to have assisted some of the participants with networking opportunities which in turn provided them with opportunities to better withstand the impact of the economic crisis experienced.

- Training content related to improving existing businesses have enabled women to be able to respond to opportunities to further expand their businesses and diversify as necessary. The entrepreneurs were linked with mentors and other project beneficiaries from outside of their districts as part of this intervention who provided them with the insights and personal experiences of engaging in entrepreneurial ventures. One respondent from the FGD indicated that since completion of the training she is more responsive to changing demands, to this end, she indicated that she had expanded her portfolio of products to include school bags as the new school term was beginning soon.  Another respondent from the FGDs indicated that in response to the demand in the market, she had since pivoted her business to sewing maternity clothes and selling it at the weekly fair hosted outside the DS office. While still another respondent who was had received in-kind assistance in the form of a dehydrating machine, had expanded from dehydrating unsold mushrooms to also dehydrating fruits and moringa leaves to sell in her shop. The establishment of a storefront to sell her products in a more formal setting has further encouraged this same respondent to expand the scope of her business to include items based on demand from her ever expanding customer base. For a respondent involved in tailoring, the fuel crisis and the subsequent inflationary pressure resulted in a rise in the cost of sourcing materials; through her networks built through this group and participating in the diversity market fairs, she was provided with information to be able to source material from alterantive sources.

- Quality trainings were delivered for young women on digital media engagement, who are now capacitated to counter hate speech and present their own content promoting messages of peace and reconciliation, however, use of knowledge gained can be further enhanced. According to the survey responses from participants of digital training on prevention of violent extremism, most (86%) of them found the training was engaging and relevant, and assessed this item as high or very high. However, fewer of the participants (60.6%) assessed as very high or high the use of knowledge gained in the trainings to counter disinformation or hate speech and the increase in engagement in social media platforms as can be seen in the next graph (62.1% noted as very high or high). Their competence has increased, as well as their motivation to engage in online activities, however, there is still more room to increase their use of knowledge and engagement in social media. It was noted by the service provider (Hashtag Generation) that some of the training participants had engaged with other programmes organised by them showing interest in further knowledge development and engagement in this subject area – with a particular interest in countering false narratives (aka fake news).

Graph 3. Assessment of Digital Training from Participants

Source: Evaluation Survey.

Unexpected results

- The project helped promote the dialogue among WDOs across the country and increase collaboration among them as an unintended result. There is no cooperation protocol or practice established among WDOs of different regions/ DS divisions to share information and promote collaboration. The interaction promoted by the project among WDOs with the representatives of the Planning Divisions at the national level consultation in Colombo in December 2022 provided an opportunity to share information and create more networking among them and subsequently incorporate the action plans developed within the divisional budgets. This was not expected as an output of the project and was positively reported by WDOs during the data collection component of the evaluation in the districts of Mannar and Gampaha. It has also created opportunities for networking among the WDO within the district of those who participated in the same localised WPS capacity building trainings.

- Capacity built among women entreprenuers in Vavuniya presented them with the opportunity to supply their products to a local supermarket chain. As the entrepreneurs had obtained business registration for their products, were familiar with the requirements of consistent labelling and packaging, and had experience facing an interview panel, they were able to make use of an opportunity to expand their production and supply to a wider audience. The women were informed of this opportunity through the officers at the DS division. As some of the women already employed other women in their business venture, expansion of supply has the potential to provide additional employment opportunities for other women in the community. In addition, the 101 business women supported with in-kind assistance in Monaragala were facilitated to obtain business registration within a short time period from a Business Service Center established with the support of another project of Chrysalis. This resulted in all businesses assisted through the skills development training being officially registered.

- Networks created and sustained among the women entrepreneurs through Whatsapp groups provide a platform for women interested in further developing their business venture. The networks built and maintained since participating in the economic development training are utilised as a self-support system for the women to support or assist each other to develop their businesses. One instance shared during the FGD data collection was that when the fuel shortage made transportation of raw materials from Colombo unaffordable, women shared information about alternative sources of materials. Furthermore, the self-improvement observed among themselves has resulted in selected beneficiaries increased willingness to pursue other avenues for capacity building, in the interest of further developing their businesses. In another instance, a respondent from a FGD indicated that the Whatsapp groups are useful to them particularly when the local frontline officers are also included as they are then informed of further development opportunities made available through the DS office.

Local action on peacebuilding

Work Plans were drafted as a result of collaboration among different stakeholders from the government and civil society through the Multi Party Dialogues. This contributes towards the NAP already being implemented at a grassroots level, although to a limited extent. NAP was approved

“They conducted training for us and emphasised that we are Sri Lankans despite ethnicity, race, language and religion. We had Muslim- Tamil conflicts before but now we live as a fraternity” (CBO representative_Ampara district_FGD).

only in February 2023, but it started bearing fruits previously with the promotion of Multi Party dialogues where stakeholders from different sectors came together to draft WPS plans at a local level during the third phase of interaction as part of the project. There is limited, but important evidence that these multiparty dialogues helped stir collaboration at a local level towards the agenda of peacebuilding in the country. While the level of engagement for the online-based interactions were appreciated and efforts by the facilitators to keep participants engaged were also appreciated, participants who had opportunities to meet in person expressed further benefits from being able to interact independent of the planned agenda.

- Peace Action Plans developed as a component of the social cohesion dialogues and trainings reflected the aspirations of grassroots organizations subsequent to the trainings provided on prevention of conflict which were found useful by participants. The dialogues conducted among the female CBOs at the grassroots levels led to the design of small community based activities aimed at improving engagement and opportunities to spread knowledge about conflict resolution methods amongst community members who may not have organically interacted although living in the same geographical space. Events/activities organised as part of the Peace Action Plans included, planting of saplings in public spaces, street dramas on the topic of preventing domestic violence and conflict, shramadana (community clean-up) at the village schools or communal spaces, as well as sports events. There is evidence that some of the activities implemented created opportunities for inter-ethnic engagement among community members in locations with multi-ethnic populations such as in the Ampara district, where community members came together to undertake a shramadana at a local pre-school attended by children of all ethnicities. There is also evidence from a FGD that the capacity building component on social cohesion provided community members from diverse backgrounds the opportunity to interact in a space free of prejudice which was valued in spaces of existing sensitivities due to ethnic or religious distinctions as well as power imbalances within the communities and across CBOs themselves in mono-ethnic communities. However it is important to ensure measures are taken to provide comprehensive information to the wider community members - outside of those CBO members who attended the social cohesion dialogues and training modules – of the purpose of the activities implemented as part of the peace action plans developed to minimise instances of disgruntlement outside the project timeline. Therefore, it is necessary to ensure closer review of the projects designed and selected for implementation.

- The timeliness of the interventions for capacitating grassroots organisations in the area of social cohesion dialogues and trainings affected the effectiveness of the programme. Although this component of the project intervention was started at the beginning of the project, due to contextual challenges these activities were suspended. When resumed again, the business skills development training component superseded this intervention due to limited time available resulting in little time left for the CBOs to reflect on the knowledge gained and planned activities or to conduct follow up activities aimed at promoting reconciliation independent of the project. As a result, some of the activities implemented (such as an awareness programme on waste segregation at a pre-school) appear to have limited connection with the overall objective of promoting social cohesion.

- Grassroots organizations and community leaders were trained on the role of women in prevention of conflict and peacebuilding and developed local pilot projects, but there is limited evidence that this knowledge was actually used or internalised by the participants outside of the project environment. An overlap in the selection of participants, with members of grassroot organisations also being selected for economic empowerment component of this project, resulted in difficulties in recollection for some participants of content related to conflict prevention as the knowledge transfer as part of the economic empowerment is observed to have had a greater resonance.

The contribution of in-kind support provided to women

- The support to women´s businesses through in kind assistance was well targeted and helped them grow their business, although there was not enough clarity among the targetted beneficiaries on the criteria to choose beneficiaries. Beneficiaries were chosen based on their entrepreneurial profile and the trainings were effective on developing skills of women to be more successful in their business (through budget planning, packaging, public speaking skills) and with the in-kind assistance received. However, there were also problems in implementation as beneficiaries underwent a long training and not all of them received in kind assistance. The criteria for the distribution of in-kind assistance was not clear to beneficiaries as a whole, particularly among those who did not receive in-kind support. In-kind support was awarded for a subset of women entrepreneurs who had completed an initial round of business development training and were successful during a pitching interview where they had to show commitment to development of their existing business venture. Although the implementing partner had criteria for selection of recipients, during the FGDs respondents communicated that there was confusion among participants, particularly among beneficiaries not selected for in-kind assistance on reasons for non-selection. Better communication throughout the project implementation with both frontline officers and participants could have minimised any ill will.

Networking and information exchange

- Meetings were convened among G7 members around the NAP but with limited advocacy and collaboration impact in face of the difficult scenario of crises in the country. They were rather of an informative nature and more focused at the beginning of the project. The conveners of the G7 members were the Goverrnment of Sri Lanka and the Government of Japan and UN Women played the role of facilitator. In the context of the economic crisis, all the efforts of the government went towards crisis management and the WPS agenda lost traction. Few G7 meetings actually took place in the last year of the project and did not involve substantive engagement and discussion.

- Quality knowledge products were produced on WPS in the country and used by government officers. G7 members and other key actors were not continuously informed by project´s activities. Various knowledge products were produced during the project implementation and were disseminated to participants of G7 and NAP validation consultations. However, they were not disseminated to a wider public and there is no evidence that the national media campaigns  have actually contributed to the development of debate in the country and policy making in the area of WPS discourse.

Reflections on the Theory of Change

- Most of the assumptions identified in the reconstruction of the Theory of Change proved true or partially true (85%) which shows the project rationale was mostly coherent. However, there were key assumptions which were identified as not holding true in project implementation: 1) G7 Countries are engaged in WPS process; 2) Communication campaign has wide reach, quality and relevance; 3) Stakeholders engaged take concrete steps to include women in Peacebuilding. In the first case, there was a challenge in the national context due to the political and economic crisis, in the second case, the communication efforts had limited impact and there is limited information for further analysis and in the third case, there is limited evidence on concrete engagement of women in relevant continuous peacebuilding activities as a consequence of the project. The next table shows the status of the assumption as per data collected in the evaluation process.

Table 6. Status of the assumptions identified in the reconstructed Theory of Change

| Assumptions | Status of the assumption | Quality of data available |
| --- | --- | --- |
| - Stakeholders engage in consultations and WPS agenda providing quality and useful feedback | True | Strong evidence, data was triangulated |
| - Training methodologies adapted are effective for civil servants | True | Medium level evidence, trainings were useful, but methodologies were not explored |
| - Joint WPS work plans are implemented | Partially true | There is evidence, although imited that some of the WPS work plans were implemented |
| - Capacity developed stays in the organizations despite government changes | No evidence available | This was not fully explored during data collection |
| - Draft NAP proposal is approved | True | It was officially published |
| - Government is able to maintain equipment | No evidence available | It is yet too early to determine if the infrastructure provided as part of the refurbishment component will be maintained due to limited funds available by the government. |
| - Equipment provided by the project is used for WPS related activities | Partially true | There is evidence that selected government officers provided with equipment are using them, although there is no assurance that they are being used for furthering WPS related objectives. |
| - Women are effectively included in NAP dialogue | True | There was wide engagement during NAP validation consultation |
| - Needs assessments and value chain analyses are well produced and feed into training | True | This is part of WEE methodology and was identified to work well in this project as in other projects run by UN Women |
| - Women are well identified for training activities | True | Targeted women showed engagement and the relevance of their participation |
| - Trainings are well delivered – they are relevant and engaging | True | Participants reported quality of training received |
| - Women use the in-kind assistance provided effectively | True | Beneficiaries provided information that in-kind assistance was useful and well used |
| - Government facilities for women are used | True | There is evidence that the facilities completed and handed over are being used |
| - Benefited women change attitude in face of trainings and assistance received | Partially true | There is evidence of change in attitude for the WEE component of the project |
| - Study on digital engagement feeds into training | True | This was reported during the interviews |
| - G7 Countries are engaged in WPS process | Partially true | They were engaged only in NAP consultation and specific meetings |
| - Knowledge dissemination workshop engages relevant actors | Partially true | There were limited convening opportunities for partners |
| - National media campaign has wide reach, high quality and relevance | Not true | There is no recall by FGD participants of the national media campaign, even though the data on the reach was high, it refers only to the potential viewers of the campaign |
| - Stakeholders engaged take concrete steps to include women in Peacebuilding | Partially true | District/provisional work plans developed by MPD participants had activities to involve women in peacebuilding and NAP consultation was very inclusive, however, there is limited evidence of actual and sustained engagement in peacebuilding from women. |
| - Studies/findings have high quality and are well disseminated | Partially true | The studies were well produced and there is evidence of their use by government officers but not by a wider audience |
| - Targeted/identified women have the motivation to engage in peacebuilding activities | Partially true | Beneficiaries appreciated the trainings but did not demonstrate high engagement in peacebuilding activities. |

Extent of the change promoted

- The project was relevant and effective in promoting Outputs 1 and 2, but promoted limited transformational change. The results were analysed against the concept of transformational change by Uitto (2022) as change toward a more sustainable, inclusive, resilient, and environmentally sound state. The project was analysed in terms of the promotion of change in 1) Mentality; 2) Social Structure which is more inclusive; 3) Economic progress and; 4) Sound and respectful relationship with natural resources. The change in mentality was promoted through the advocacy process and consultation and approval of NAP, the trainings to government officials, CSOs and entrepreneurs. Previous analysis (see paragraphs 21 and 25) show that the project was effective in promoting a mentality towards women´s empowerment although this still needs to be fostered and deepened to ignite a change in policy and attitude towards women in the country. In terms of social structure which is more inclusive, the major achievement of the project is in the approval of NAP and the promotion of more balanced relationships within the households of women entrepreneurs as identified in the Focus Group Discussions. As women increase their earnings they are in a better position to make their own decisions. As far as Economic Progress, this was promoted through the training and promotion of businesses of entrepreneurial women. Although this has been effective in enhancing small businesses, this has not reached higher level results in terms of impact in value chains and economic policy. In fact, given the timeframe of the project and the timing of the evaluation, it is difficult to identify higher level type of results. Its impact was more at an individual, household level, not reaching a more systemic level. In terms of a sound and respectful relationship with natural resources, this was not directly tackled by the project. Overall the project contributed to further promoting a change in mentality, followed by contribution towards a social structure which is more inclusive and less so on economic progress and respectful relationship with natural resources. The next figure illustrates the intensity of change analysed in each aspect, the closer to the centre, the higher the impact assessed to promote transformational change.

Figure 2. Status of the project as per transformational change status

Source: own elaboration.

## Evaluation Criteria: Efficiency

Finding 12. There were project delays and a no cost extension was signed in the context of COVID-19, a general election and economic and political crisis, but the project was able to deliver most of its outputs (with the exception of the work on refurbishment which was continued by UN Women after the end of the project).

Finding 13. There was staff turnover during the implementation of the project, but this did not impact project delivery. UN´s organizational structure was efficient for the overall implementation of the project with the exception of the high reporting demands on the implementing partner.

Finding 14. The coordination between UN Women and its implementing partner worked well and although some monitoring instruments were used during implementation (training surveys/report from activities), there is limited evidence that the data was used during implementation to feed into the project´s learning curve. The learning of the project was important in terms of the context analysis where interventions were designed based on previous needs assessments and other types of research.

Project´s delivery in relation to timeline, capacity to adapt to the context of crisis and deliver outputs planned

- There were delays in project implementation in the context of COVID-19, general election in 2020 and the high turnover of senior personnel from the government offices in addition to the economic and political crisis in 2022. However, the project adapted and was able to deliver by the end of 2022. There was a no cost extension of one year to the project in face of the contextual challenges. The project had to adapt and deliver online trainings. While there were savings, the budget allocated for personnel increased due to the project extension. Finally, the project was able to deliver most of its planned activities with some challenges for output 3 which involved the convening role of other stakeholders which were beyond the control of the project.

- UN Women´s structures and systems were effective in delivery most of the outputs with the exception with the work on refurbishment and IT. The project had a high delivery rate despite the external circumstances. The major challenges were on delivery in areas where UN Women had limited experience – refurbishment and also IT for which there were no adequate procedures/know how in place. In fact, this is a challenge also flagged in other UN Women Contexts. The project team hired external assistance/consultants to help facilitate delivery on refurbishment and IT, but there were still challenges in the communication between consultants and the line ministry and the fine tuning of demands and actual delivery. The IT system was delivered, but up to end of the project, there was no clarity to where the system would be hosted and if the system would be actually used, and this was attributed to limited resources available due to the financial limitations within the government. In terms of the refurbishment, demands were not clear, there were sketches and lists of materials which had to be reworked on a number of occasions and the speed of work did not meet the timeline which subsequently coincided with the debt crisis in the country and resultant import restrictions which led to a shortage and high prices of construction material in the country. As a matter of fact, constructions/refurbishments are dynamic and it is natural that the lists of materials change and more materials are needed, the challenge is to be able to plan for this type of work with realistic timelines. Even through, there was a contingency fund of 10% for managing changes, there were new requests by local officers/divisions coming in, despite earlier discussions at both national and local level. This made the management of refurbishment work particularly challenging.

Coordination and the work on Monitoring and Evaluation

- There was a good coordination between UN Women and the implementing partner and the roles were clear. However, there was a heavy burden on reporting taken by the implementing partner. Chrysalis is an old partner of UN Women used to its procedures and also of other international organizations and donors. Coordination between UN Women and Chrysalis worked well. The only concern identified by the evaluation was the heavy reporting demand which fell into the implementing partner. This high demand on reporting and the documentation required for compliance consumed a significant amount of time from implementing partners which had to subsequently direct more time to reporting than to technical issues and the reporting burden took much time than initially planned for.

- The Monitoring and Evaluation Framework of the project was clear and objective, but no evidence was found of the monitoring process feeding into a learning cycle. This is attributed to the timeline of the project implementation, with a bulk of the implementation taking place towards the end of the project duration due to external circumstances beyond the control of the project team. Post-training surveys are recorded for trainings conducted as part of output 1 for government and civil society stakeholders capacitated on the concepts of Women Peace and Security.

- The project was particularly successful on outputs 1 and 2 due to the quality of its partners and consultants mobilized and had challenges in delivering refurbishment services due to its inexperience in the area. The project responded to the needs posed by the government, but the government was not able to pose its demands in a structured way which led to many implementation challenges in the area of IT and refurbishment as already mentioned.

## Evaluation Criteria: Sustainability

Finding 15. There is mixed evidence for the motivation of national partners to continue the results of the project. Capacity was created at government structures and grassroots level, but there are still challenges in the continuation of the WPS agenda/implementation of NAP in the country now that it has been approved.

Finding 16. The most solid evidence of sustainability comes from the work with entrepreneurial women as they are taking their businesses forward. Mobilization has taken place at a grassroots level, but this initial work may require further support  from the government to continue overtime and bear fruits such as policies and activites at a local level.

Level of capacity built in the country

- There is ample evidence of government stakeholders benefiting from trainings as well as community leaders, CSOs and women entrepreneurs. However, there is only tangible evidence from continuing efforts by women entrepreneurs as they are fully engaged in their own livelihoods promotion. It is still early to verify to which extent capacities developed will ensure continuation of projects activities. Many of the trainings were completed towards the end of the project and the evaluation was not able to identify follow-up activities and actual results deriving from the capacity built. The more solid evidence found was in relation to the women entrepreneurs as they have been capacitated to work on their own businesses and continue what was in place, but this does not apply to the promotion of peacebuilding in the country. It is however also noted by the frontline government officials consulted during the evaluation that in the case of livelihood interventions, fledgeling businesses were hardest hit by the economic crisis due to the rising cost of materials which affected the demand for non-essential products.

The challenges around the implementation of NAP

- The NAP was approved, but there are serious questions about the extent to which the NAP will be actually implemented. A major achievement of the project was the approval of the NAP. The approval of NAP shows that the national government is concerned with the issue of WPS and placing women in the political agenda. However, although NAP has been approved, no budget was attached to it and there is no clear sign of continuation of this agenda in concrete terms yet. As the approval is very recent (March 8th 2023 for the official ceremony), to which extent this will be implemented by the government is still to be seen. Furthermore, in the backdrop of the ongoing economic crisis in the country, government spending has been reduced with local government service providers indicating that implementation of existing tasks and responsibilities is already proving to be challenging. Therefore, allocation of new funding for the implementation of the NAP within the year is unlikely from Government budgets, indicating a possible need for official development assistance from development partners.

The challenges and possibilities of sustainability at a local level

- Action Plans were developed and may pose a way for sustainability at a local level. The project worked at a national political level, but also at a grassroots level with trainings for CBOs and local government officials, through multi party dialogues, WPS capacity building trainings and development of small project initiatives as part of the social cohesion dialogues and trainings. The work plans developed as a result of multi-party dialogues have the highest level of engagement as a culture of incorporating feedback from diverse stakeholders has been established. FGDs with selected participants revealed that they remain in contact with other participants, with connections strengthened since meeting participants in person. The sustainability of the engagement and the successful implementation of the action plans are dependent on the opportunities available to the local government officers to present identified needs to officers with authority such as the Director Planning. There needs to be a better channel of communication established between grassroots organizations, frontline officers, and decision makers at the local government.

- The routine transfer of frontline officers resulted in a loss of knowledge of the project and subsequently a loss of buy-in with regard to the sustainability of the project related interventions beyond the project period. The transfer of frontline officers to other DS Divisions within the project period resulted in a loss of content knowledge on service delivery to vulnerable members of the community. It also resulted in a vacuum with regard to awareness of the project purpose, selection criteria and more importantly buy-in from the officers themselves to ensure regular follow up on the progress of business ventures of participants of the economic empowerment component.

## Evaluation Criteria: Gender Equality and Human Rights

Finding 17. Gender sensitive policy was approved and gender sensitive trainings materials were produced and delivered. However, there is limited evidence to the reaching of higher level outcomes as far as increased women´s continuous engagement with the agenda of Women, Peace and Security.

- The project was very efficient in having a design geared towards inclusion of women and the promotion of human rights with the spirit of leaving no one behind. The project involved women from diverse ethnic backgrounds and at different positions – from public officers to CSOs, leaders and entrepreneurs. It promoted trainings, research and other activities, the international frameworks for the protection of Women such as the UN Security Council Resolution 1325, other internationally agreed frameworks on the rights of women and national frameworks mirroring and expanding women´s protection domestically. It called the attention of duty bearers to their obligations and sensitized rights holders on their entitlements. The project was very much based on a human rights perspective in this respect.

- The project addressed and responded to existing power dynamics and gender relations at a national policy and at a household level as part of an ignite process which is ongoing and medium to long term. The project built on a policy process of increasing women´s rights in Sri Lanka. The approval of NAP was an important step forward. However, there is still much resistance within the government and limited awareness on the role of women as peacebuilders at a national policy level. The same applies to the work at a local level. Women participants are now better prepared to take up their businesses and their husbands are more supportive towards their capacity development and their new and improved livelihoods, however, this still applies to a limited  number of women and households. Change is on the way, but it is part of a long-term process.

- There is evidence that women participants are more outspoken and have more motivation and confidence to take up new challenges. The Focus Group Discussions have showed how women who were trained feel now more confident about their capacity to be entrepreneurs and run their own businesses. Economic empowerment is an important component of women being independent and for balancing gender relations within the household and the project contributed to that by helping to promote women with more agency in their lives and relationships both within and outside their homes.

- Although limited, the evaluation found evidence of women more motivated to take up leadership positions due to the project´s initiatives.  There is evidence that some of the women participants felt more economically and politically empowered thus contributing to higher level goals of the project. Two women who participated in two separate FGDs in the Northern and Eastern provinces felt capacitated enough from the training and have decided to run for the upcoming local government elections. In addition, understanding the profit of a business and how much income is coming in the household as a result of the business, has given the women confidence and agency in the area of decision making related to household-based expenses etc. A few of the women stated that they now feel more confident to expand their livelihood activity as more than a hobby and to see it as a business. One woman also said that she is now more confident to get a loan from a bank using the businesss plan.

- Based on the Gender Results Effectiveness Scale, the project can be considered gender transformative for its work at a policy level, on capacity building of duty bearers and rightsholders and for its promotion of women´s economic empowerment. A gender transformative project means its results contributes to changes in norms, cultural values, power structures and the roots of inequalities and discriminations. The project contributed to the approval of a new legislation geared towards the agenda of Women, Peace and Security in the country based on a wide consultation of women from diverse backgrounds, it brought sensitization and training to government officers at a national, regional and local level, CBOs and community leaders and helped promote women´s businesses with trainings and in-kind support. This combination of high level policy and consultation, capacity building economic empowerment helps to change norms and social structures, although much still needs to take place for this process of women´s empowerment to be fully implemented and sustained overtime at the national policy scenario in the country.

# Lessons Learned

- Continuous adaptation of policy narrative and support is needed to keep partners engaged and maintain political momentum

The project was able to draft a NAP policy document and adapt it along the way to have it approved at the end of the project cycle. It also adapted the communication narrative to a discourse that was more aligned with Sri Lankan political culture. And yet, more adaptation needs to take place to have the agenda of WPS more appropriated by national partners. Advocacy is a process of dialogue that needs to be flexible and take into account the voices of various partners to be effective. The UN is in a privileged position through UN Women and other agencies to deliver this type of dialogue and policy convergence on the subject of Women Peace and Security.

- Frequent and substantive communication with partners throughout project implementation is key for political support

The project lacked continuous communication after the process of NAP validation consultation. The communication with partners was in specific events, but not continuous. This absence of continuous communication was felt when NAP was discussed at the cabinet level at the end of the project cycle. There was limited communication with UN Agencies and G7 countries throughout the implementation of the project. Political support needs to be sustained through continuous communication and networking on the relevant matters to be matured. While it is recognised that the ownership of the NAP remains with the government and its counterparts, in future projects, it is necessary to reiterate the need for continuous communication efforts throughout the project to ensure adequate buy-in upon approval.

- Preliminary analysis and benchmarking needs to be in place at planning stage of complex and not usual types of project operations

The project design incorporated complex operational and thematic issues: IT, hard infrastructure (refurbishment) and the combination of economic empowerment and conflict resolution with the WPS agenda. There are many details on project operations that need to be taken into account in the design phase, so that the projects targets and timelines are more realistic. How to manage refurbishment? What needs to be considered when designing a new IT system (which is always a complex decision)? How can the work of economic empowerment dialogue with peacebuilding? These are key questions that need to be thought of upfront or at the early stages of negotiation with the government. Although UN Women policy for partnership does not allow for calling in specific experts and hiring them prior to a public call, consultations can be made within the UN System and  previous partners to better inform project design.

- When instability is the norm, crises are foreseen and need to be considered in timelines and budget contigencies in project design and throughout project implementation, bringing the donor close to make decisions according to the context. The context of continuous crisis have to be considered during project negotiation stage.

UN Women often operates in unstable political scenarios where crises are frequent and Sri Lanka is not an exception to this context. Capacity to adapt and make budget allocations and rules more flexible should be considered during project design and negotiation with the donor. Projects need to be designed with this adaptation in mind, with timelines that can be met. budget contingencies and flexible management proceduresfor crises scenarios.

- Convening high level political dialogue is risky, requires special dedication and results are mostly unpredictable.

The project was designed taking into account that the Government of Sri Lanka and the Government of Japan would convene high level political dialogues with G7 member countries around the WPS agenda. This was beyond the control of UN Women and did not take place as envisoned. Political dialogue and management is a work on its own and this needs to be considered up front to allocate the necessary staff resources and involve high level officials within the organization.

- Communication is strategic for increasing results and framing institutional positioning

The project had limited communication efforts to help convene its message to partners and the role of UN Women and the Government of Japan in helping promote WPS in the agenda. This is a complex task that requires dedicated efforts to be effective and adequate buy-in from the project partners.

- Long term and continuous support bring long standing and more sustainable results

This project built on a previous project of UN Women supported by the Government of Japan – with a project duration of 1.5 years, which evolved for 3 more years in the current project cycle and it was right after the second project ended that the NAP was approved. Advocacy projects and other types of development projects take long to mature and bear fruit. Continued and long-term engagement is needed to promote consistent results.

- The combination of high-level policy work with grassroots work continues to be strategic and help foster cultural change

This project worked on a UN Women formula that keeps working: engagement with policy at a national level, capacity building for the government and capacity building at a grass roots level. This combination helps to promote systemic and cultural change, where one level feeds the other. What is still to be better explored is the high level type of development result which involves sustained political dialogue and participation of women overtime. While capacities of participants at lower levels are improved, there also needs to be a similar improvement in capacity of the mid level government officials to allow/facilitate changes to be adopted with understanding and the necessary buy-in.

# Conclusions

Conclusion 1

The project´s approach and strategies were relevant to the agenda of women´s overall empowerment and Women, Peace and Security with a good and well tested combination of policy design and consultation, capacity building at different levels and grassroots work. The project team was able to adapt project design to the demands of the government and the needs identified of the various stakeholders. However, the project had challenges in delivering some of the demands brought by the government, such as refurbishment and IT projects due to poor poor internal communication challenges within the government and the lack of an existing procedure to ensure utility once delivered at a ground level. In fact, UN Women is not experienced with running initiatives in areas such as refurbishment as identified by other evaluation exercises in other countries. In addition, although the design of the project was relevant to stakeholders, this is more true to women on the ground. There is still much resistance at the national level of fully taking in the agenda of women´s empowerment and Women, Peace and Security in face of the still present feelings of grievance and resistance towards improving  women’s participation in political participation, while conversations about peacebuilding and post-war recovery in the country continue to be considered a sensitive topic.

Based on Findings 1-5

Conclusion 2

The project was able to mobilize different stakeholders in an ample discussion on Women, Peace and Security, however collaboration was limited to consultation. There were no major overlaps between the work of the project and other stakeholders, but limited collaboration. In face of so many crises in the country, it was difficult to have key partners convene high level meetings among stakeholders. In fact, continuous communication with a wider range of stakeholders and partnership building were identified as challenges of the project, further challenged due to the ownership status of the NAP related documents by the government entities. Engagement with the government was also more limited to those parties directly engaged with Women´s empowerment agenda which tend to have less power and agency. In this context, gaps were identified in the strategic positioning of women as a relevant partner in the agenda of Women, Peace and Security.

Based on Findings 6 and 7

Conclusion 3

The project was successful in developing capacities of government officers at a national and regional level and of women on the ground, specially in entrepreneurial skills. Women participants are now more confident and more aware of their rights and possibilities. A more favourable policy scenario was also created with the approval of the National Action Plan on Women, Peace and Security and enhanced dialogue among government officers and women on the ground. A further step is now needed to help capacities built turn into actual and sustainable engagement of women in peacebuilding and disseminate the knowledge products generated within the project.

Based on Findings 8-11

Conclusion 4

The project suffered delays and implementation challenges in face of the context of multiple crises in the country (COVID-19, economic and political crisis), but it was nevertheless able to deliver high quality outputs. The major implementation challenges were with the refurbishment component which were not fully delivered at the end of the project´s timeline and were taken up by UN Women´s management to run with their own resources. One additional implementation challenge identified was the reporting burden which was significant for the implementing partner. Overall, the relationship between UN Women and partners worked well. In terms of learning, the project would have benefited from conducting reflection exercises with front line government officers to obtain feedback on interventions implemented as part of the project. In addition, the Monitoring and Evaluation Framework was clear and monitoring efforts were in place, but there is no evidence of monitoring work feeding into project learning cycle for the most part, and this is attributed to a bulk of the interventions occurring towards the end of the project period.

Based on Findings 12-14

Conclusion 5

Capacity was developed in stakeholders and the National Action Plan on Women, Peace and Security was approved which indicates a good foundation was built for sustainability. However, the use of the new skills by stakeholders, specially in the agenda of WPS and the implementation of NAP is still to be seen. The most sustainable efforts are with the entrepreneurial women and the development of their own business. The agenda of social cohesion and WPS will need further efforts and support to be sustained overtime. Within the local government context, the lack of an existing channel of communication between grassroots organizations, frontline officers, and decision makers at the local government will limit the sustainability of opportunities created through this project for local government officers to share the identified needs with officers with the necessary authority for decision making.

Based on Findings 41, 43 and 44

Conclusion 6

The project had a strong human rights framework, helping to develop capacity in duty bearers and rights holders and strengthen institutions. It had a gender transformative approach by helping to change norms (approve legislation) and change power relations at the household level with the contribution of women´s economic empowerment. It was very inclusive in its consultation process for the National Action Plan. It was only not fully successful in engaging people with disabilities despite of efforts in this direction.

Based on Finding 17

# Recommendations

The recommendations were developed based on the interaction with the Evaluation Reference Group and the Evaluation Management Group through the presentation of preliminary findings and the revision of report. In addition, it took into account the suggestions made by various stakeholders during data collection and the experience of the evaluation team with past evaluations for UN Women. They were crafted taking into account their relevance, possible impact and feasibility.

| N. | Type/Source | Recommendation | Recipient | Action points | Rationale | Suggested timeframe |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Strategic and Operational Based on Conclusion 3 and 5 | Continue engagement in the implementation of NAP | UN Women | - Renew agreement with the Government of Japan to design a new project which can help with the implementation of NAP. - Continue engagement with government officers at a local level, keeping the same stakeholders to the same possible extent to deepen dialogue, capacity built and engagement. - Help support collaboration mechanisms among Women Development Officers at different levels with well established communication channels and regular regional and national meetings. - Continue capacity building activities for government officers at a local, regional and national level. - Raise awareness/Promote advocacy and communication campaigns on how women can be promoters of social cohesion and social transformation (UN Women´s value added). - Include a module on business and sustainability in future trainings so that environmental sustainability is clearly contemplated by the project. - Institute follow-up mechanisms in future project to see whether the new knowledge and skills are being used by participants (e.g. follow-up calls) and new community projects are being implemented. - Increase the linkages between economic empowerment and peacebuilding during trainings, helping women become more aware of their responsibility as agents of change by partnering with CSOs which have extensive know-how in this area and which can deliver specific modules in this topic. - Identify women and CSOs which already have relevant and continuous work in conflict prevention and engage them in training as opposed to women who have no experience n this area. - Consider include capacity building for women as mediators in local conflicts where they can be activelly included in preventing the escalation of conflicts. - Review training curriculum for women on social cohesion based on a benchmark of Successful Regional Experiences to help women develop practical skills for their use in daily life and in settling down conflict. - Consider public speaking as part of the training curriculum for women as a way of helping them voice their opinions and feel more confident. | This project built on a previous support given by UN Women and the government of Japan. The agenda of NAP has not been fully taken by the country and there are no resources allocated for that. Continuing support is needed and an implementation plan already exists. | May onwards |
| 2 | Strategic and operational Based on Conclusions 1 and 2 | Develop a communication strategy on a narrative for WPS which helps to set the policy scenario to further dialogue in the country and position UN Women as a key actor working in this agenda | UN Women | - Identify entry points for deepening the WPS agenda in the country given the new government and scenario (not directly addressing the word security/peacebuilding, but rather dialogue, cohesion, social harmony). - Engage with the Regional Office to further allocate resources (staff/financial resources) to a context specific communication strategy for the office in Sri Lanka. | Communication was a gap of the project and the need to adapt the narrative on WPS was identified as a lesson learned | May-Sept |
| 3 | Operational Based on Conclusions 1 and 4 | Engage partners in future project design whenever possible, consult HQ and Regional Office before engaging in refurbishment and IT projects as per the recommendation in Internal Audit of Liberia Country Office (IEAS/IAS/2019/13) referring to infrastructure and explore alternative ways of delivering refurbishment and IT projects when needed (e.g. partnership with other agencies and consultations with beneficiaries to determine utility). | UN Women HQ | - Call partners for inputs in the new project design. - Involve technical experts when designing reprograming of the project. - Publish guidelines for UN Women to deliver on IT and refurbishment based on lessons learned in implementation in these areas globally. - Conduct a needs assessment to determine utility of final outputs prior to implementation. | Complex delivery that UN Women does not have experience require outside expertise for better delivery. This was a lesson learned of the project and a challenge identified. | May-Sept |
| 4 | Operational Based on Conclusion 6 | Explore lessons learned and challenges in the attempts to engage people with disabilities in this project | UN Women | - Produce a document and discuss lessons learned on best practices and challenges to involve people with disabilities in this project. - Benchmark inclusion of people with disabilities in peacebuilding projects in initiatives implemented by other UN Agencies in the Region. | The evaluation team did not have evidence of significant engagement of people with disabilities in the project and this is an UN System requirement | May-Sept |
| 5 | Operational Based on Conclusion 4 | Appropriately plan for contingency resources and flexible modes of delivery adapted to contexts of crisis and the work with partners | UN Women | - Include in future project design a chapter on ´possible adaptations in a context of crisis´ where upfront strategising and thinking can be included on how to deal with possible crisis (contingency funds, more flexible delivery modes etc). This should be negotiated with the donor based on previous experience. Review reporting requirements for partners as a way of keeping up with control and at the same time facilitating accountability measures to ease the burden on implementing partners. | Sri Lanka has an unstable political and economic scenario which has to be properly taken into account. | Whenever necessary |
| 6 | Strategic Based on Conclusion 2 | Increase dialogue with other government agencies beyond those related to women´s related policies | UN Women | - Include other government agencies in future project design (Ministry of Finance and others) as to sensitize more key agencies on the importance of policies aimed at empowering women. | This project was very restricted to women related agencies which do not have significant decision-making power in the country | In future project design |
| 7 | Strategic Based on Conclusion 2 | Include staff time in political processes whenever high-level policy dialogue is involved | UN Women | - Consider staff time in project budget directed to policy dialogue. - Engage senior UN Women Officials whenever high-level policy dialogue is involved. | The project lacked more senior envolvement in helping to mobilize high level political actors in the country | In future project design |
| 8 | Operational Based on Conclusion 3 | Disseminate knowledge products of the project, create a communication strategy for future projects and ensure continuous communication with partners in project implementation | UN Women | - Publish knowledge products in UN Women´s website. - Send knowledge products to UN Women partners beyond this project´s scope. - Disseminate knowledge products to the press and other UN Agencies - Create opportunities for networking with partners beyond the project´s activitiies (e.g. UN events, Embassys´ functions etc). - Invest in a dedicated campaign with a clear message and specific spots produced and disseminated via social media, radio, TV and other means with the agenda of WPS. - Include a communication strategy with partners in future project design (within and outside the UN) – with dedicated budget allocated. | There were quality products developed as part of this project which have not been used and shared and they can be useful for increasing knowledge on WPS in the country and region. | May-Sept |
| 9 | Operational Based on Conclusion 4 | Include continuous learning as part of the M&E framework | UN Women (Sri Lanka and Regional Office) | - Include learning activities in project implementation (such as quarter meetings to reflect on what happened, present monitoring data, discuss corrective actions etc). | There was limited promotion of learning within project implementatin being fed by monitoring activities | In future project design |

# Appendix A. Rapid Assessment

Project: Implementation of the Women, Peace and Security Agenda in Sri Lanka (the G7 Women, Peace and Security Partnerships Initiative)

Period: January 2020-December 2022

Methodology: Desk review of secondary data (documents related to project) and consultation with UN Women Sri Lanka.

Issues of concern: Consultation with the ERG during inception phase to ensure their engagement and approval prior to data collection. The feedback from the Government of Sri Lanka and the Government of Japan are especially important to fine tune the demand.

Overview of data available: - Project documents and later revised results framework - Needs assessments - Project Annual reports (2020 and 2021, 2022 is pending) - Reports from activities and outputs delivered (NAP reviewed document, some of the studies and policy briefs produced, Chrysalis reports, pictures, media links, communication materials, TOR for G7 meetings, minutes) - Value chain analysis - Financial reports - Evaluation guidelines (GERASS Independent Evaluation and Audit Services, UN Women Global Evaluation Quality, Assessment and Rating matrix, Global Evaluation Report Assessment and Analysis System (GERAAS) Guiding Note - Ethical guidance (UNEG) The documents were sufficient for the inception phase.

Issues of concern: Further documentation is needed for knowledge products delivered.

Monitoring and Evaluation Framework: Consistency of data available: The project has clear reports with data on indicators for the years 2020 and 2021, however, there is still not data available for the indicators for the year 2022. The project framework is clear with its results chain.There is baseline data available in the results framework, but with no clear indication of source. The current project is a continuation of a previous initiative. The data presented is not disagregated by gender or other criteria, however, the project initiatives have fully targeted women as rightsholders and both women and men as government and other institutional stakeholders. Project indicators: all the indicators proposed are clear and objective. However, there is missing data for 2022 as many project activities were implemented only in 2022 due to the delays due to COVID-19.

Refinement of evaluation demand: It is important for the evaluation team to hear feedback from other key stakeholders (Government of Japan and Ministry of Women, Child´s Affairs and Social Empowerment) in order to produce an evaluation which is relevant.

Issues of concern: Receive final data from delivery of 2022 activities, including finance which is meant to be arriving during inception phase.

Initial findings in each area to be investigated by the project: Relevance: The project intervention area is aligned with the country´s context, UN Women´s agenda and the dialogue which was in place between the Sri Lankan and Japanese government. However, with the recent crisis (July 2022), there is a question as to whether this area of intervention remains relevant to the government. There is an indication of the mantainance of the gender equality agenda due to the International Monetary Fund´s demands to the country in this area. This is to be further investigated. Coherence: There is an early indication of an internal coherence of the project within UN Women´s Sri Lanka portfolio. It builds on previous projects on peacebuilding and Women´s Economic Empowerment. However, there is still no data to verify whether there is coherence within the UN System and within the larger international community in the country. This is to be verified through the interviews and focus group discussions. Effectiveness: The project delivered the review of the NAP document, consultation with stakeholders on the NAP, promotion of multi-party dialogues and work plans and refurbishment of government facilities for women in the districts in addition to the provision of laptops for government officials (Output 1). It also delivered on trainings for women on economic empowerment, peacebuilding and digital peacebuilding, in addition to in-kind support for women´s small businesses (Output 2). The project also produced knowledge products touching upon domestic and regional policies on WPS. However, there is still limited evidence under this work which was on knowledge exchange and G7 support to WPS in Sri Lanka (Outpu 3). Although most activities were delivered and some of them with high quality (NAP reviewed document, Chrysalis´ needs assessments and value chain study for example), there is still not enough data to understand to each extent this work has helped to embed the WPS agenda in the country in a sustainable way with clear results as far as women´s empowerment at a policy and grassroots level. Efficiency: There were many delays in the project due to the context of COVID-19 where most activities had to be reprogrammed and the project which was meant to end in Dec 2021 was extended to Dec 2022. However, up to now there is still not enough information to verify to which extent human resources were enough, contractual procedures worked, relationship between UN Women and Chrysalis was synergetic. This will be verified during the semi-structured interviews and focus group discussions. Sustainability: Considering the number of capacity building activities which were carried out, the knowledge products which were produced and the quality document which was produced for NAP, there is a slight indication that the project will leave an important legacy behind. However, given the current context in the country, nothing can be acertained at this point. Sustainability will have to be carefully looked at during and after data collection. Gender Equality and Human Rights: The project was geared towards women´s empowerment with a clear design to promote changes at a policy and grassroots level for women. However, how much of that has been achieved will be better known after focus groups are carried out with women. An assumption was made in the process of reconstructing the Theory of Change: women are willing to engage in peacebuilding. To which extent women were empowered and are willing to engage will have to be verified. The project seems to have a clear design for ´Leaving no one behind´, but this will have to be looked at more closely along with the inclusion of women with disabilities.

Overall issues of concern: There are still many data gaps which will have to be filled in during data collection, however, one of the risks identified is the lack of response from key stakeholders during data collection. The evaluation team might need an important assistance from UN Women office to help mobilize key stakeholders to answer the demand for participating in interviews and focus group discussions.

Table 7. Evaluation Matrix

| Evaluation criteria | Key question(s) | Indicator(s) data | Collection method(s) | Data source | Method for Data Analysis |
| --- | --- | --- | --- | --- | --- |
| Relevance | Evaluation question 1: To what extent were the project’s strategies relevant to local and national contexts and aligned with national priorities? Evaluation question 2: How has the project adapted to contextual changes, including the COVID-19 pandemic and the economic crisis, in order to remain relevant? Evaluation question 3: To what extent did the project align with and address the needs and priorities of the intended beneficiaries and the principle of “leaving no one behind”? | - Evidence of alignment with national policies on gender equality - Evidence of alignment with demands of rightsholders at a local level - Existence of needs assessment - Adequacy of project reprogramming strategy to demands of government stakeholders and rightsholders - Inclusion of women with disabilities in the group of beneficiaries - Proportion of minority groups in the group of rightsholders benefited by the project - Accessibiliy of the project to minority groups | Desk Review Focus Group Discussions Key Informant Interviews Desk Review Focus Group Discussions Key Informant Interviews Desk Review Focus Group Discussions Key Informant Interviews | Key national documents on gender equality Rightsholders benefited by the project Key government counterparts Needs assessments carried out by the project Reports of activities reprogrammed Rightsholders benefited by the project Key government counterparts Final Report of the project Rightsholders benefited by the project | Content analysis in all items |
| Coherence | Evaluation question 4: To what extent is the project coherent internally? Is the project aligned with UN Women’s strategic planning? Evaluation question 5: To what extent is the project coherent with the overall WPS Agenda? To which extent does the project have a holistic/systemic approach in connection to the SDG agenda? Evaluation question 6: What is the comparative advantage of UN Women in the implementation of the WPS Agenda, compared with other UN entities and key partners in Sri Lanka? To what extent has the project capitalized on its comparative advantage? Evaluation question 7: To what extent is the project coherent externally with the interventions of other development actors in Sri Lanka (particularly within the UN system)? | - Evidence of alignment of the project with UN Women´s global plan - Evidence of alignment of the project with the overall UN Women´s portfolio In Sri Lanka - Evidence of alignment of the project with the strategy of the Regional Office - Alignment of project Interventions with existing WPS debate in the country - Contribution given by the project to the discussion on NAP - Evidence of project design and ramifications linked to other Interventions and areas - Evidence of contribution of UN Women to the WPS agenda as assessed by key stakeholders - Evidence of collaboration of the project with other UN and donor Initiatives. | Desk Review Key Informant Interviews Key Informant Interviews Focus Group Discussions Key Informant Interviews Focus Group Discussions Key Informant Interviews Focus Group Discussions | UN Women´s global plan Portfolio of UN Women in Sri Lanka UN Women staff in Sri Lanka UN Women staff in the Regional Office Donor and donor community of G7 countries UN stakeholders engaged in NAP debate Government stakeholders engaged in NAP Civil Society stakeholders engaged in NAP Resident Coordinator UNFPA UNDP and other UN Agencies engaged in the NAP and WPS debate Donor and donor community of G7 countries Resident Coordinator UNFPA UNDP and other UN Agencies engaged in the NAP and WPS debate | Content analysis in all items |
| Effectiveness | Evaluation question 8: To what extent did the project deliver planned outputs? Evaluation question 9: To what extent did the output level interventions translate into progress towards outcomes? Evaluation question 10: To what extent has the project contributed to promoting women’s meaningful engagement in conflict prevention and social cohesion at the community level? Evaluation question 11: To what extent have capacities of duty-bearers and rightsholders been strengthened as a result of the project? Evaluation question 12: Were there any unexpected results (either positive or negative)? Evaluation question 13: How did the project minimize the unintended negative consequences (dividers) and built on the positive consequences (connectors)? Evaluation question 14: What were the reasons for the achievement or nonachievement of planned results? Evaluation question 15: To what extent did the project make timely adjustments to its strategy to maintain its relevance and effectiveness? Evaluation question 16: How have stakeholders’ engagement on WPS changed as a result of this project? Which stakeholders have been newly engaged as a result of the project? Evaluation question 17: What measurable changes in gender equality and women’s empowerment have occurred as a result of the project? | - Percentage of output targets delivered by the project as planned. - Evidence of advocacy/policy support activities leading to the empowerment of women to strengthen the peacebuilding process - Evidence of training activities leading to empowerment of women to strengthen the peacebuilding process - Evidence of peacebuilding dialogues leading to empowerment of women to strengthen the peacebuilding process - Evidence of policy dialogue leading to empowerment of women to strengthen the peacebuilding process - Evidence of meaningful engagement of women and concrete results in conflict prevention at the community level. • Evidence of knowledge, skills and attitudes enhanced in duty-bearers as a result of the project. - Evidence of unexpected results linked to the project (both positive and negative). - Evidence of project capacity to minimize unintended consequences and take the opportunity of creating synergy with the context. - Evidence of key obstacles faced by the project and key enabling factors for success. - Evidence of capacity of project to adapt to changing circumstances overtime. - Evidence of enhanced engagement of traditional stakeholders In WPS in the country. - Evidence of new stakeholders engaged in WPS In the country. - Evidence of change in political participation of women due to the project. - Evidence of change in women´s economic empowerment due to the project. - Evidence of change of women´s overall agency due to the project. | Desk Review Semi Structured Interviews Desk Review Semi Structured Interviews Focus Group Discussions Focus Group Discussions Semi Structured interviews Focus Group Discussions Semi Structured interviews Key Informant Interviews Focus Group Discussions Key Informant Interviews Focus Group Discussions Key Informant Interviews Focus Group Discussions Key Informant Interviews Focus Group Discussions Desk Review Key Informant Interviews Focus Group Discussions Desk Review Key Informant Interviews Focus Group Discussions Desk Review Key Informant Interviews Focus Group Discussions Key Informant Interviews Focus Group Discussions Key Informant Interviews Focus Group Discussions Key Informant Interviews Focus Group Discussions | Project reports UN Women Staff Crysalis Government of Japan Stakeholders involved in NAP Rightsholders benefited by training activities and peacebuilding dialogues Governement of Japan Donors from G7 countries Rightsholders Crysalis UN Women Staff Rightsholders Government staff engaged in activities carried out by the project Crysalis UN Women Staff Rightsholders Government at a national and local level Crysalis UN Women Staff Rightsholders Government at a national and local level Crysalis UN Women Staff Rightsholders Government at a national and local level Crysalis UN Women Staff Government at a national and local level Crysalis UN Women Staff Crysalis UN Women Staff Crysalis Crysalis UN Women Staff Chrysalis UN Women Donor Project reports Chrysalis UN Women Stakeholders engaged in NAP process, peacebuilding dialogues and exchange of Information. Project reports Chrysalis UN Women Donor UN Agencies - UNDP + UNFPA + RC Project reports Chrysalis UN Women Rightsholders Government representatives | Content analysis in all items |
| Efficiency | Evaluation question 18: Have financial and human resources been allocated sufficiently and strategically to achieve project outcomes? Evaluation question 19: Have the outputs been delivered in a timely manner? Evaluation question 20: Have UN Women’s organizational structures, systems and mechanisms effectively supported delivery of the project? Evaluation question 21: Are the changes/results observed worth the resources spent? Evaluation question 22: How efficient was the project coordination between UN Women and Implementing Partner, including clarity of roles and accountabilities, monitoring and reporting, and potential added value? Evaluation question 23: Where there a clear Results Framework and a process of continuous monitoring of the project´s progress? | - Final expenditure rate of project - Evidence of adequacy of human resources in relation to project´s needs. - Evidence of activities implemented according to timeline - Evidence of adequacy of UN Women´s structures and systems to support project´s implementation. - Results of the project in face of other projects of the same amount supported/implemented by the Government of Japan and UN Women. - Capacity of implementing partner to respond to project´s monitoring and reporting demands - Clarity of roles between UN Women and implementing partner - Adequacy of governance structure - Clarity of results framework - Evidence of monitoring work during project implementation feeding into a learning process. | Desk review Key Informant Interviews Desk review Key Informant Interviews Desk review Key Informant Interviews Desk review Key Informant Interviews Key Informant Interviews Desk Review Key Informant Interviews | Project Report Crysalis UN Women Staff Donor Project reports Government at a national and local level Crysalis UN Women Staff Project reports Crysalis UN Women Staff Similar project reports UN Women Staff Donor Project reports Chrysalis UN Women Staff Chrysalis UN Women Staff Donor Chrysalis | Desciptive statistics Content analysis in all items |
| Sustainability | Evaluation question 24: To what extent has the project developed the capacity of government stakeholders, community leaders and other beneficiaries to ensure sustainability of efforts and benefits beyond the project? Evaluation question 25: Are national partners committed to continuing the project or elements of the project? Evaluation question 26: Are there any mechanisms developed and/or interventions linked with existing mechanisms at local and national levels to ensure continuation? | - Evidence of use of capacities developed by stakeholders to promote peacebuilding In the country. - Evidence of steps taken by the national partners to continue the initiatives triggered by the project. • Evidence of legislation approved, committees created and other institutional measures approved to ensure continuity of the project. | Key Informant Interviews Focus Group Discussions Desk review Key Informant Interviews Focus Group Discussions Desk review Key Informant Interviews | Government counterparts Civil Society Organizations Rightholders Government counterparts Civil Society Organizations Rightholders Project Report Government counterparts Civil Society Organizations Rightholders | Content analysis in all items |
| Gender Equality and Human Rights | Evaluation question 27: To what extent have gender equality, disability inclusion and human rights considerations been integrated into the project design and implementation? How to better incorporate them? Evaluation question 28: To what extent did the project address and respond to existing power dynamics and gender relations? | - Evidence of principles of gender equality, disability Inclusion and human rights incorporated in training materials of the project - Evidence of principles of gender equality, disability Inclusion and human rights incorporated in peacebuilding dialogues and NAP validation consultations. - Evidence of Inclusion of people with disabilities in project activities. - Evidence of women taking up leadership positions due to the project´s initiatives. - Evidence of women taking up new roles and responsibilities due to the project´s initiatives. - Evidence of increased income of women due to project activities. | Desk review Key Informant Interviews Focus Group Discussions Key Informant Interviews Focus Group Discussions | Project document Project report Chrysalis Rightsholders UN Women Chrysalis Rightsholders Donors UN Agencies UN Women Staff | Content analysis in all items |

# Appendix C. Project Documents Reviewed and Consulted

| N | Name |
| --- | --- |
|  | Original Project document |
|  | Project plan- August 2020 |
|  | Approved budget |
|  | Revised budget planning paper |
|  | Revised project workplan |
|  | Revised results framework – 15 July 2021 |
|  | Progress Update Report- Project for Implementation of the WPS Agenda in Sri Lanka |
|  | Documents related to no-cost extension (2021) |
|  | Reprogramming document as at August 2020 |
|  | Activity reports related to Acivity 1.1 - Cabinet memo - Draft NAP WPS - Draft NAP before validations |
|  | Knowledge materials informing the project - CEDAW - Domestic Framework on Women Peace and Security - International Framework on Women Peace and Security - UNSCR 1325 - Women, peace and security in Sri Lanka: Policy Review - WPS Policy review: Why do we need a national action plan for women, peace and security in Sri Lanka? - Discussion brief to inform the implementation of the Women Peace and Security agenda in Sri Lanka: Mapping key lessons learnt from other countries in the Asia region - Crisis impact briefs: Women, Peace and Security in Crisis: Impacts on women heads of households - NAP implementation guide (Sinhala) - PVE study related material (not circulated) - Inception report: The role of women in promoting peace and social cohesion through informed digital engagement - Presentation: The role of women in prmoting peace and social cohesion through informed digital engagement - In-depth literature review: The role of women in promoting peace and social cohesion through informed digital engagement - Final study findings: The role of women in promoting peace and social cohesion through informed digital engagement - Project brochure – Empowered women, peaceful communities |
|  | NAP Validation report discussions. Documented feedback from: - Government - CSOs - G7 members - Development Agencies |
|  | NAP validation workshops related documents. Consultations and participant lists: - CSOs - G7 members - Government - UN and Development partners |
|  | Concept note: Building capacities of government officials on WPS policy implementation |
|  | Capacity assessment report and questionnaire |
|  | Capacity building related agendas and participant lists - Training completion report - In person trainings - Online training - Pre-post evaluation - Training modules |
|  | Implementation of the Women, Peace, and Security Agenda in Sri Lanka – Inception Report |
|  | WPS policy review of WPS (in Sinhala) |
|  | Letter confirming the delivery and receipt of Laptops and other equipment |
|  | Inception report of Multi Party Dialogues |
|  | Needs assessment questionnaire and data collated |
|  | MPD reports - Colombo district - Gampaha district - Kalutara district - North Central province - Sabaragamuwa province - Uva province |
|  | Capacity building workbooks |
|  | Feedback on capacity building video recordings by consultants |
|  | MPD workplans - Anuradhapura - Moneragala - Ratnapura - Colombo - Gampaha - Kalutara |
|  | Workplan development workshop |
|  | Value chain analysis |
|  | Inception report related to the Delivery of Capacity building training on social cohesion for CSOs and women’s economic empowerment programme in Sri Lanka |
|  | Training module on Social Cohesion and Peace Building for CSOs, Grassroot Organizations and Women Leaders (Sinhala) |
|  | Women’s Economic Empowerment Programme - Delivery of capacity-building training on social cohesion for CSOs and women’s economic empowerment programme |
|  | Needs Assessment of women led livelihood and SME initiatives and value chain analysis |
|  | Final report – Value chain analysis of FHHs in project operating districts of Ampara, Colombo, Moneragala and Vavuniya |
|  | Power point - partner agreement with chrysalis- rp of the project “Implementation of the women, peace and security agenda in Sri Lanka |
|  | Training modules - Product development training - Product development training module adopted for both physical and online - Product development handout (Sinhala) - Marketing management module (Sinhala) - Financial literacy and Business plan development customised to women entreprenuers (Sinhala) - Social cohesion module (Sinhala) - Video modules for WEE (Sinhala) |
|  | Beneficiary details - project beneficiary lists (Moneragala, Colombo, Vavuniya, Ampara - In kind assistance reciepients |
|  | Relief distribution lists |
|  | Progress reports of government buildings to be refurbished. |
|  | Capacity Assessment: Gender, Tech and Peace Fellowship related to the Capacity building of young women for positive digital engagement to promote social cohesion and Peacebuilding |
|  | Final Report: Gender, Tech and Peace Fellowship |
|  | Inception report: Capacity building of young women for positive digital engagement to promote social cohesion and peacebuilding |
|  | UN Women briefing document on the role of women in promoting peace and social cohesion through informed digital engagement |
|  | G7 meeting brief and agenda (March 2021) Presentation Advocacy strategy |
|  | G7 meeting brief and agenda (October 2021) |
|  | Study on the role of women in promoting peace and social cohesion through informed digital engagement (draft) - Power point presentation highlighting background and key areas of interest |
|  | Inception report on: The Role of Women in Promoting Peace and Social Cohesion Through Informed Digital Engagement |
|  | In-depth literature report: The Role of Women in Promoting Peace and Social Cohesion Through Informed Digital Engagement |
|  | Donor reports - 1 January 2020 – 31 December 2020 - January - December 2021 WPS Sri Lanka narrative report - Interim Financial Donor Report for Period ended 31 December 2021 |
|  | Budget related documents |
|  | Partner documents - Funding authorisation and certificate of expenditure – chrysalis - Q1 2021 – Q3 2022 - Narratives - Quarterly progress reports Q1 2021, Q2 2021, Q4 2021, Q1 2022, Q2, 2022 |
|  | Japan 1- Empowered Women, Peaceful Communities Project - EWPC project documents - EWPC Provincial consultation reports - Policy review - WEE reports |
|  | Project communication outputs - Impact stories - Multi party dialogues - Peace building social cohesion - Women’s economic empowerment - WPS training - Videos - Key achievements - WPS NAP outreach video - Media coverage (2021, 2022) - Photos |
|  | National media campaign - Segment briefing notes and preparation notes - Invitation to Ms Upasena to speak at SLBC - Invitation to Ms Jayamanne to speak at SLBC - Circulation and viewership numbers |
|  | Project communications - Impact stories - WPS trainings – case studies - Peacebuilding and social cohesion – videos, article and photos - Women’s economic empowerment – videos, article and photos - Multiparty dialogies on WPS – stories from participants - Videos (2019-2020; 2022) - Media coverage (2021, 2022) - Photos |

# Appendix D. Evaluation Instruments

Guide for Semi-structured Interviews

Thank you for meeting with us today. I/we have been commissioned by UN Women to conduct an evaluation of this project, “Implementation of the Women, Peace and Security Agenda in Sri Lanka (the G7 Women, Peace and Security Partnerships Initiative)”.

Based on your involvement and role within the project, we would like to use this opportunity to interview you, in order to capture your views, perceptions and feedback on the interventions implemented as part of the project. It is intended that your views shared will be used for learning and improving future project designs. We are interested in your understanding of the WPS agenda with regard to increasing capacity and knowledge to promote engagement of women in governance and peacebuilding processes.

Please note that there is no right or wrong answer, and any responses shared as part of this interview will not be used to identify you by name, maintaining confidentiality. The findings from interviews with yourself and other identified stakeholders will be tabulated and presented in a report to UN Women and the Government of Japan as the key funder of this project.

The interview is expected to last approximately 40 minutes to an hour. If you choose to, you may terminate your participation at any point of the interview. Before we begin, do you have any questions or need any further clarifications?

CONTROL INFORMATION:

| Name |  |
| --- | --- |
| Organization/ Institution |  |
| Designation |  |
| Date of interview |  |
| Contact information |  |

| Relevance | UN Women Staff | Government partners | Donor | UN Resident Coordinator | Implementing partner | Influencers/Consultants |
| --- | --- | --- | --- | --- | --- | --- |
| - What was your role/association with the project? - To what extent do you find the project was relevant to: - National policies on gender equality - Your needs - Overall WPS agenda in the country 2.1. Did the project carry out a needs assessment? - How has the project adapted to contextual changes, including the COVID-19 pandemic and the economic crisis? - How relevant do you find were the new programmed activities? - To what extent did the project include: - women with disabilities - minority groups - Was the project appropriately designed to benefit groups often excluded? - Has the project taken into account environmental concerns in its design and implementation? - Has the project developed a more holistic approach in its design and implementation connecting social, economic and environmental interventions? | X X X X X X X | X X X X X X X | X X X X X X X | X X X X X X X | X X X X X X X | X X X X X X X |
| Coherence | UN Women Staff | Government partners | Donor | UN Resident Coordinator | Implementing partner | Influencers/Consultants |
| - To what extent is the project coherent in relation to: - Portfolio of UN Women in Sri Lanka - UN Women´s strategic planning globally and regionally Please, give specific/concrete examples of alignment or non-alignment. - The overall WPS agenda/debate in the country - What is the comparative advantage of UN Women in the implementation of the WPS Agenda, compared with other UN entities and key partners in Sri Lanka? - To what extent has the project capitalized on its comparative advantage? - What was the contribution given by the project for the discussion on NAP? - To what extent is the project coherent externally with the interventions of other development actors in Sri Lanka (particularly within the UN system)? Please, mention specific collaborations of the project with other UN and donor initiatives | X X | X X | X X | X X | X X | X X |
| Effectiveness | UN Women Staff | Government partners | Donor | UN Resident Coordinator | Implementing partner | Influencers/Consultants |
| - To what extent did the project deliver planned outputs on: - Institutional Strengthening (Trainings for government officers, NAP Consultation, Equipment, refurbishment) Please, probe for quality of consultations and feedback received, quality of trainings, likelihood of NAP being approved and capacity of government to maintain equipment and if they are being used appropriately. - Capacity building for women (Entrepreneurial trainings, mobile sales carts, multiparty dialogues, digital training) Please, probe for the quality of the trainings and methodologies adopted, implementation of multiparty dialogues, adequacy of selection method of beneficiaries, use of inkind contributions by women, reach of women with disabilities, reach of communication campaign) - Policy Dialogue (G7 meetings, studies produced, information exchange meetings) Please, probe for quality and usefulness of studies produced and increase in political commitment from stakeholders. - To what extent has the project contributed to promoting women’s meaningful engagement in conflict prevention and social cohesion at the community level? - To what extent have capacities of partners and women been strengthened as a result of the project? Please, consider knowledge, skills and attitudes enhanced in both groups. - What were the reasons for the achievement or nonachievement of planned results? - Were there any unexpected results (either positive or negative)? - How did the project minimize the unintended negative consequences and take advantage of the positive consequences and opportunities? - To what extent did the project make timely adjustments to its strategy to maintain its relevance and effectiveness? - How have stakeholders’ engagement on WPS changed as a result of this project? Which stakeholders have been newly engaged as a result of the project? Please, provide us with concrete examples. - What measurable/actual changes in gender equality and women’s empowerment have occurred as a result of the project? Please, consider change in: - Political participation - Women´s economic empowerment - Overall agency of women Please consider to which extent the advocacy/policy support, peacebuilding dialogue, training activities, policy dialogue have helped to empower women to strengthen the peacebuilding process. Please, provide examples of meaningful engagement of women and concrete results in conflict prevention at the community level if any. | X X X X X X X X X X X X X X | X X X X X X X X X X X X X X | X X X X X X X X X X X X X X | X X | X X X X X X X X X X X X X X | X X X X X X X X X X X X X X |
| Efficiency | UN Women Staff | Government partners | Donor | UN Resident Coordinator | Implementing partner | Influencers/Consultants |
| - Did the project fully utilize its resources? - Were human resources adequate in relation to project´s needs? - Were activities implemented according to timeline? Why so and why not? - Were UN Women´s structures and systems adequate to support project´s implementation? - How would you assess this project in relation to other projects supported/implemented by the Government of Japan and UN Women (resources x results)? - Was they capacity in place from Chrysalis to respond to project´s monitoring and reporting demands? - Do you find the roles between UN Women and implementing partner were clear? - Was the governance structure of the project adequate? 26. How do you assess the quality of the results framework? How was its monitored? | X X X X X X X X X | X X X X | X X X X X | X | X X X X X X X X | 8X |
| Sustainability | UN Women Staff | Government partners | Donor | UN Resident Coordinator | Implementing partner | Influencers/Consultants |
| - To what extent are stakeholders more capable now to promote peacebuilding In the country and ensure continuity of the WPS agenda? - Is there evidence of national partners committed to continuing the project or elements of the project beyond its lifetime? Please, consider: - What resources have been allocated to ensure continuation of the project agenda beyond its lifetime? Likelihood of project activities to continue being run by the government or other partners. - Level of incorporation of WPS agenda within government at a national and local level - To what extent will the capacity developed stay within the local government organizations despite changes in government? - To what extent has there been or planned continued local government engagement with identified beneficiary groups beyond the project duration? - What factors can be considered to attribute to increased capacity of local community level CSO partners/beneficiaries? - Are local government representatives likely to replicate project operational methodologies, particularly with regard to WEE components? - Are there any mechanisms developed through this project and/or interventions linked with existing mechanisms at local and national levels to ensure continuation? Please, consider: - Capacity developed in stakeholders (government, CSOs, women, other stakeholders) that will help foster the WPS agenda in the country - Number of legislation/regulations approved which the project helped to influence - Shift in mindset of stakeholders to help foster the WPS agenda in the long run in the country | X X | X X | X X | X X | X X | X X |
| Gender equality and Human Rights | UN Women Staff | Government partners | Donor | UN Resident Coordinator | Implementing partner | Influencers/Consultants |
| - To what extent have gender equality, disability inclusion and human rights considerations been integrated into the project design and implementation (course materials, peacebuidling dialogue etc)? How to better incorporate them? Please, consider: - Comparing the initial stages of the project with the end, has there been any observed changes in mindset among beneficiary communities with regard to inclusion of beneficiaries with multiple levels of vulnerability in project design and implementation. - Can you provide any examples of the extent to which the project was able to or was not able to address and respond to existing gendered power dynamics, cultural norms and political dynamics? (e.g. through promoting leaderhip in women, women being able to take up new roles and responsibilities and increase their income) - Has there been adequate consideration for women with multiple levels of vulnerability in NAP on WPS? - Has there been adequate consideration for persons with disabilities in the NAP on WPS? - To what extent has the project been able to reach the most vulnerable, including persons with disabilities as beneficiaries? Do you have any additional comments you would like to share? | X | X | X | X | X | X |

Guides for Focus Group Discussions

Stakeholders engaged in NAP or Multiparty Dialogues

Number of participants: Minimum 4 and maximum 8

Sequence of events:

- Introduction of the evaluation and purpose of the Focus Group Discussion, mention of confidentiality and next steps for the evaluation process.

As a participant of the Multi Party Dialogues and the Capacity building trainings conducted as part of this project, you have been selected to participate in this focus group discussion in order to understand your views and experiences of being a part of the capacity building activities conducted. As you will notice, not all members of the original group are here today; as it is not possible to capture feedback from all participants, however, this discussion will be replicated acrossselected districts where the MPDs took place. By participating in this discussion, you will not receive any direct benefits; however, the views expressed will be beneficial in informing any projects which will be designed and implemented in the future.

This tool is designed to capture your thoughts and opinions. There is no correct or incorrect response. The opinions you provide will be anonymous, and no one will be identified individually. Only collective information will be used to identify common perceptions towards the delivery of the MPDs. Once completed, the results will be tabulated and presented in a report to UN Women and the Government of Japan as the key funder of this project.

You may choose not to engage in this activity, and there will be no adverse consequences. Additionally, if you do participate, but at any point, if you feel that you would rather not give your views on the matters, you have the freedom to stop answering the questions.

- Round of introductions for each participant (name and organization) where they report how they have been engaged in the project during the NAP consultation process or multiparty dialogues.

- Reiterate that this information will not be used to identify respondents individually.

| Name |  |
| --- | --- |
| Sex (male/female/other) |  |
| Age category (only answer if comfortable) | - Under 20 years - 20-29 years old - 30-39 years old - 40-50 years old - Over 50 years old |
| District and DS (or national level) |  |
| Organisation/department /CBO |  |
| Designation/position |  |
| Do you have a disability (only answer if comfortable) |  |

- Questions:

Warm up

- When was your first engagement with the MPDs?

  - Since then, have you attended any subsequent trainings/capacity building activities organised by UN Women?

- These dialogues brought together elected representatives, CBOs and CSOs and people from the district secretary offices all together for a discussion. What do you think of that?

- In your opinion: What were some of the challenges faced by women who seek leadership positions or seek to voice their opinion?

  - Probe for differences in opinion based on the sex of the respondent.

- How do you assess the relevance of the consultation process and the discussion promoted? What were the key results of this process?

- What skills/knowledge did you gain from attending the MPDs that were most useful for carrying out your duties?

- have you had an opportunity to share the knowledge gained with others in your community/organisation?

- Since the consultations, have more stakeholders participated in the process or felt motivated to engage?

- What is your experience with regard to the the process of engagement in this project on the topic of WPS within the NAP?

- What are the chances of NAP being really implemented in face of the current context?

- What are some of the factors contributing to facilitating and/or hindering the implementation of WPS agenda withing the NAP?

- Have there been any measurable changes or do you forsee any changes in women’s engagement within the WPS agenda in Sri Lanka as a result of participation in this intervention?

- Have there been any measurable changes or do you forsee any changes in inter-ethinc engagement as a result of participation in this intervention?

  - Please provide examples from your own experiences or observations

- Have there been any measurable changes or do you forsee any changes in gendered power dynamics within the local government or community level engagement as a result of participation in this intervention?

- What would you suggest for future UN Women interventions in the area of Women, Peace and Security? What could have been done differently to increase results around the NAP document, its approval and guidance for implementation?

- In terms of improvement of delivery: probe for duration, location, modality (online/in-person), language,

- Finalization of Focus Group with last comments from participants and thank you remarks given by facilitator followed by clarification that the report will be publically available in UN Women website.

Focus Group Discussion for Donors of G7 Countries

Number of participants: mininum 4 and maximum 8

Sequence of events:

- Introduction of the evaluation and purpose of the Focus Group Discussion, mention of confidentiality and next steps for the evaluation process.

As a participant/member of the G7+ working group on WPS convened as part of this project, you have been selected to participate in this focus group discussion in order to understand your views and experiences of being a part of this project. Your views and feedback expressed here will be beneficial in informing any projects which will be designed and implemented in the future.

This tool is designed to capture your thoughts and opinions. There is no correct or incorrect response. The opinions you provide will be anonymous, and no one will be identified individually. Only collective information will be used to identify common perceptions. Once completed, the results will be tabulated and presented in a report to UN Women and the Government of Japan as the key funder of this project.

You may choose not to engage in this activity, and there will be no adverse consequences. Additionally, if you do participate, but at any point, if you feel that you would rather not give your views on the matters, you have the freedom to stop answering the questions.

- Round of introductions for each participant (name and organization) where they report how they have been engaged in the project with a special focus on Output 3 – G7 Meetings and policy dialogue.

| Name |  |
| --- | --- |
| Sex |  |
| Organisation and designation |  |

- Questions:

- How do you assess the relevance of this project? What were the key results?

- What are the chances of NAP being approved and implemented in face of the current context? How do you see the future of the agenda of WPS in the country and your participation in it?

- What would you suggest for future UN Women and the Government of Japan interventions in the area of Women, Peace and Security in Sri Lanka? What could have been done differently to increase results around the NAP document, its approval, the dialogue among G7 countries and the exchange of experiences? To what extent are regional lessons learnt applicable in the local context?

- Finalization of Focus Group with last comments from participants and thank you remarks given by facilitator followed by clarification that the report will be publically available in UN Women website.

Focus Group Discussion for UN Agencies

Number of participants: mininum 4 and maximum 8

Sequence of events:

- Introduction of the evaluation and purpose of the Focus Group Discussion, mention of confidentiality and next steps for the evaluation process.

You have been selected to participate in this focus group discussion in order to understand your views and experiences based on your involvement with this project. Your views and feedback expressed here will be beneficial in informing any projects which will be designed and implemented in the future.

This tool is designed to capture your thoughts and opinions. There is no correct or incorrect response. The opinions you provide will be anonymous, and no one will be identified individually. Only collective information will be used to identify common perceptions. Once completed, the results will be tabulated and presented in a report to UN Women and the Government of Japan as the key funder of this project.

You may choose not to engage in this activity, and there will be no adverse consequences. Additionally, if you do participate, but at any point, if you feel that you would rather not give your views on the matters, you have the freedom to stop answering the questions.

- Round of introductions for each participant (name and organization) where they report how they have been engaged in the project with a special focus on NAP dialogue, value added of UN Women in WPS and the coherence of the UN System within this agenda.

| Name |  |
| --- | --- |
| Sex |  |
| Organisation and designation |  |

- Questions:

- How do you assess the relevance of this project? What were the key results? How does the project align with the national and local level policies and contextual changes?

- Are there any identified gaps between identified needs and implementation activities? How have these been addressed?

- How do you see the role of UN Women in the agenda of WPS? What is their unique contribution? Do you see coherence among the different UN Agencies in the area of WPS? Did the project design taken into consideration the heterogeneity of the participants based on their unique and intersectional characteristics To what extent were geographical and contextual differences taken into consideration? To what extent were the needs of persons with disabilities taken into consideration? To what extent was there consideration for environmental sustainability in relation to the implementation of the WPS agenda?

- In your view, have the Project interventions contributed towards conditions conducive to increased capacity among selected local and national level participants (women and men) to promote WPS NAP?

- To what extent has the project contributed to promoting meaningful engagement in conflict prevention and social cohesion at a community level? Can you provide examples and reasons for achievement or non-achievement? Have there been any unexpected results as a consequence of this project (either positive or negative)?

- What would you suggest for future UN Women interventions in the area of Women, Peace and Security in Sri Lanka? What could have been done differently in this project?

- Finalization of Focus Group with last comments from participants and thank you remarks given by facilitator followed by clarification that the report will be publically available in UN Women website.

Focus Group Discussion for Participants of Capacity Building Activities and Beneficiaries of equipment and refurbished facilities

Number of participants: mininum 4 and maximum 8

Sequence of events:

- Introduction of the evaluation and purpose of the Focus Group Discussion, mention of confidentiality and next steps for the evaluation process.

You have been selected to participate in this focus group discussion in order to understand your views and experiences based on your involvement with this project. Your views and feedback expressed here will be beneficial in informing any projects which will be designed and implemented in the future.

This tool is designed to capture your thoughts and opinions. There is no correct or incorrect response. The opinions you provide will be anonymous, and no one will be identified individually. Only collective information will be used to identify common perceptions. Once completed, the results will be tabulated and presented in a report to UN Women and the Government of Japan as the key funder of this project.

You may choose not to engage in this activity, and there will be no adverse consequences. Additionally, if you do participate, but at any point, if you feel that you would rather not give your views on the matters, you have the freedom to stop answering the questions.

- Round of introductions for each participant (name and organization) where they report which training activity they took part in and what other engagement they have had in the project (e.g. received laptop, participated in multiparty dialogues etc).

| Name |  |
| --- | --- |
| Sex (male/female/other) |  |
| Age category (if comfortable answering only) | - Under 20 years - 20-29 years old - 30-39 years old - 40-50 years old - Over 50 years old |
| District and DS (or national level) |  |
| Organisation/department |  |
| Designation |  |
| Do you have a disability (only answer if comfortable) |  |

- Questions:

Warm up questions:

- Can everyone please introduce yourselves?

- When did you first participate in any activities initiated from by this project?

- How did you learn about the programme?

- How many times have you participated in an activity arranged as part of this project?

- How do you assess the relevance of the training/equipment/structure received? What were the key takeaways for you? Have you used any of the contents/equipment of the training in your context? What was its impact in your life? How has it contributed to carrying out your duties? Do you feel motivated to foster work in WPS in your community/area of work?

  - For women recipeints of training and in-kind assistance (Distinguish between those who received in kind assistance, and those who did not): have you observed a change in your engagement with entrepreneurial activities since participation in the project related activities? Has there been a change in interaction with other community members? What factors have contributed to this change? If there has been no change, what has been the reason for this? (probe for impact of economic crisis). Has participating in the trainings given you the skills/knowledge to meet challenges you might experience in your everyday life? à please provide examples..

- How do you see the implementation of NAP in the future and the agenda of WPS in the country/your community? Has this training/project/structure helped engage more people in this agenda? Is there a difference between national and local level commitment towards implementation of the project agenda? Can you provide examples?

- Have you had an opportunity to engage with others who participated in similar trainings/capacity building activities outside of the project organised interactions? In what contexts did the engagements happen? If engagement did not happen, what factors can be attributed for this?

- To what extent do you see the shift in external context (COVID19, economic crisis, political uncertainty) affecting the implementation of the NAP on WPS or the provision of required equipment/services? How has it affected individuals identified as vulnerable or at risk specifically? Were there any mitigation measures adopted?

- Do you feel like you have experienced a transformation in how you view yourself or in how others may view you or in how you view your constitutents and their unique vulnerabilities, since participating in these activities? To what extent were persons with disabilities reached through this project interventions?

- What would you suggest for future UN Women interventions/trainings/support in the area of Women, Peace and Security in Sri Lanka? What could have been done differently in this project to empower/support women to strengthen the peacebuilding process?

- Finalization of Focus Group with last comments from participants and thank you remarks given by facilitator followed by clarification that the report will be publically available in UN Women website.

Survey for participants of NAP consultation process

- What is your gender?

- Female

- Male

- Prefer not to say

- What is your age bracket?

- Under 20 years

- 20-29 years old

- 30-39 years old

- 40-50 years old

- Over 50 years old

- Which district do you live in?

- Ampara

- Anuradhapura

- Badulla

- Batticaloa

- Colombo

- Galle

- Gampaha

- Hambantota

- Jaffna

- Kalutara

- Kandy

- Kegalle

- Killinochchi

- Kurunegala

- Mannar

- Matara

- Matale

- Moneragala

- Mullaitivu

- Nuwara Eliya

- Polonnaruwa

- Puttalam

- Ratnapura

- Trincomalee

- Vavuniya

- What is your ethnicity?

  - Sinhala

  - Sri Lankan Tamil

  - Sri Lanka Moor

  - Up-country Tamil

  - Other (specify)

- Which stakeholder group do you belong to?

- National Government

- Local Government

- Private Sector

- Civil Society Organization

- Individual Women

- Donors

- UN Agencies

- Other (please specify)

- Did you take part in the consultation process carried out for validation of the National Action Plan on Women, Peace and Security?

- Yes.

- No, but I am familiar with it.

- No and I am not familiar with it.

- How do you assess the quality of the consultation process carried out for validation of the National Action Plan on Women, Peace and Security?

- Very High

- High

- Neither high or low - Average

- Low

- Very Low

- Not applicable

- How do you assess the likelihood of approval of the NAP in the following months?

- Very likely

- Likely

- Not likely

- Very unlikely

- I don´t know/Not applicable

- Has the support of UN Women and the Government of Japan helped to create an environment more conducive to the participation of Sri Lanka women in peacebuilding activities?

- It has helped significantly

- It has helped to a certain degree

- It has neither helped or disturbed

- It has disturbed to a certain degree

- It has disturbed significantly

- I don´t know/Not applicable

- Do you have any suggestions for enhancing the work of UN Women and the Government of Japan in the area of Women, Peace and Security in this project or beyond? (please specify)

Survey for participants of digital training

- What is your gender?

- Female

- Male

- Prefer not to say

- What is your age bracket?

- Under 20 years old

- 20-29 years old

- 30-39 years old

- 40-50 years old

- Over 50 years old

- Which district do you live in?

- Ampara

- Anuradhapura

- Badulla

- Batticaloa

- Colombo

- Galle

- Gampaha

- Hambantota

- Jaffna

- Kalutara

- Kandy

- Kegalle

- Killinochchi

- Kurunegala

- Mannar

- Matara

- Matale

- Moneragala

- Mullaitivu

- Nuwara Eliya

- Polonnaruwa

- Puttalam

- Ratnapura

- Trincomalee

- Vavuniya

- What is your ethnicity?

  - Sinhala

  - Sri Lankan Tamil

  - Sri Lanka Moor

  - Up-country Tamil

  - Other (specify)

- How did you hear about the training on ´Capacity building of young women for positive digital engagement to promote social cohesion and Peacebuilding´?

- Colleagues/Teacher/Other people

- Online media post

- Webpage

- Other (specify)

- Was the training relevant for you? (Use the scale 1-5; where 1 is the lowest and 5 is highest)

- 2  3  4  5

- Was the training engaging? (Use the scale 1-5; where 1 is the lowest and 5 is highest )

- 2  3  4  5

- Since participating in this training how much have you increased your competence/knowledge in ´countering disinformation´? (Use the scale 1-5; where 1 is the lowest and 5 is highest)

- 2  3  4  5

- Since participating in this training, have you used the knowledge shared during the training to ´countering disinformation´ or hate speech? (Use the scale 1-5 where 1 is not at all and 5 is used frequently/often)

- 2  3  4  5

- How motivated do you feel to engage in online peacebuilding activities? (Use the scale 1-5; where 1 is the lowest and 5 is highest)

1  2  3  4  5

- Have you already started to promote online peacebuilding and social cohesion activities through content creation based on what you have learnt?

- Yes

- No

- Not applicable

- Since participating in this training, has your level of engagement on social media platforms changed with regard to conflict sensitive content?  (Use the scale 1-5; where 1 is the lowest and 5 is highest)

- 2  3  4  5

- Since participating in this training, have you shared the knowledge gained with others who engage with social media?

- Yes

- No

- Not applicable

- Do you have any suggestions for enhancing the work of UN Women and the Government of Japan in the area of Women, Peace and Security in this project or beyond? (please specify)

-------------------------------------------------------------------------------------------------------------------

# Appendix E. Stakeholder Analysis

For the purpose of this evaluation, stakeholders are defined as those individuals, groups, or entities which are directly involved in carrying out the work of the project.

A stakeholder analysis includes a mapping of all the relevant actors and their level of involvement in the initiative to make sure that all the key actors are considered. The stakeholders identified will be classified according to their level of involvement in the initiative:

- Implementing UN organization: UN Women is the lead agency in this case.

- Development partner/donor: it refers to all the development partners involved in the initiative who could be in advisory roles, carrying out joined projects or as donors at a central level.

- Implementing government partner: this includes all the implementing partners at a central level or on the ground who are part of the government.

- Implementing Civil Society Organization partner: this refers to Chrysalis which was the major partner of the project and Hashtag Generation who was responsible for the capacity building related to digital engagement

- Rights holders: this refers directly to the end-beneficiaries, in this case, beneficiary women.

- Consultant/Influencer: this includes individuals who may have given direct contribution to the project or some degree of influence over the project.

- Implementing private partners: this includes private organizations which may be engaged in the project (e.g. in multi-party dialogues).

The next table details the stakeholders and their roles in the project. All of the stakeholders mentioned will be considered during the evaluation process in one degree or another.

Table 8. Stakeholders consulted as part of this evaluation and their roles

| N | Position/ Organization |  | Role | Contribution |
| --- | --- | --- | --- | --- |
|  | Second Secretary Political/Economic & Development Cooperation, Protocol Sections Embassy of Japan | Development partner | Overall project supervision |  |
|  | Programme Analyst/Country Focal Point, UN Women Sri Lanka | Implementing UN Agency | Major head of project |  |
|  | Project Manager, UN Women Sri Lanka | Implementing UN Agency | Overall coordination of project |  |
|  | Consultant, UN Women Sri Lanka | Implementing UN Agency | Principal project consultant |  |
|  | Gender Coordination Officer, UN Women Sri Lanka | Implementing UN Agency | Member of UN Women team |  |
|  | UNW Communications Officer, UN Women Sri Lanka | Implementing UN Agency | Lead for the National Media Campaign |  |
|  | Former Project Officer, UN Women Sri Lanka | Implementing UN Agency | Project consultant |  |
|  | Chrysalis | Implementing Partner (women’s training programmes) | Implementer on the ground |  |
|  | Chrysalis – field-based programme officer, training facilitators | Implementing Partner (women’s training programmes) | Implementer on the ground |  |
|  | CEO of Chrysalis | Implementing Partner (women’s training programmes) | Implementer on the ground |  |
|  | Chrysalis – former field-based programme officer, training facilitator – Moneragala district | Implementing Partner (women’s training programmes) | Implementer on the ground |  |
|  | Director, Women's Bureau of Sri Lanka | Implementing government partner organisation at a central administrative level | Major government partner |  |
|  | Director Development, Ministry of Women, Child Affairs and Social Empowerment (MWCASE) And Chairperson of the National Committee on Women | Implementing government partner organisation at a central administrative level | Major government partner |  |
|  | Director General Planning, Ministry of Women, Child Affairs and Social Empowerment (MWCASE) | Implementing government partner organisation at a central administrative level | Major government partner |  |
|  | Embassy of Germany | Development partner | Participation in G7 working group on WPS |  |
|  | GIZ, Dutch Development Cooperation | Development partner | Participation in G7 working group on WPS |  |
|  | GIZ, Dutch Development Cooperation | Development partner | Participation in G7 working group on WPS |  |
|  | Deputy Programme Manager, British High Commission | Development partner | Participation in G7 working group on WPS |  |
|  | Gender Adviser – Conflict, Stability and Security Fund, Joint Funds Unit, British High Commission | Development partner | Participation in G7 working group on WPS |  |
|  | Development Officer, High Commission of Canada | Development partner | Participation in G7 working group on WPS |  |
|  | Consultant | Consultant | Consultant for NAP and other studies and policy briefs |  |
|  | Consultant, Training facilitator | Consultant | Trainer and consultant for WPS training and MPDs |  |
|  | Consultant Engineer- Refurbishment | Consultant | Consultant for oversight and implementation of the refurbishment component |  |
|  | Consultant, IT | Consultant | IT Consultant responsible for the development and deployment of the online reporting system |  |
|  | Programme coordinator, Hashtag Generation | Implementing private partner | Implemention partner of Digital training component |  |
|  | Consultant, Hashtag Generation | Implementing private partner | Resource person for the Tamil and English cohorts of the Digital training component |  |
|  | Project associate, Hashtag Generation | Implementing private partner | Consultant and overall co-lead for the Digital training component, lead the english cohort of the project intervention |  |
|  | Project associate, Hashtag Generation | Implementing private partner | Lead for the sinhala cohort for the Digital training component |  |
|  | Local Government officer, Wellawaya DS division, Moneragala district | Government beneficiary | Local government officer working in facilities which have been refurbished |  |
|  | Local Government officer, Medagama DS division, Moneragala district | Government beneficiary | Local government officer working in facilities which have been refurbished |  |
|  | District Secretariat Batticaloa | Government beneficiary | Participant of the District NAP validation consultations and beneficiary of shelter facilities which have been refurbished |  |
|  | Women Development officers, Development Officers, Economic Development officers, Small enterprise development officers, NEDA officers District Women’s Development Officers |  | Beneficiaries of capacity building on peacebuilding and gender equality. Officers with responsibility for oversight of the women beneficiaries of economic empowerment, in-kind assistance and capacity builing on peacebuilding for CBOs |  |
|  | CSO member representatives | Beneficiary | Engaged in NAP validation consultations |  |
|  |  | Beneficiary | Beneficiary of economic empowerment capacity building activities |  |
|  |  | Beneficiary | Beneficiary of in-kind assistance as part of the economic empowerment capacity building activities |  |
|  |  | Beneficiary | Beneficiary of capacity building on peacebuilding |  |
|  |  | Beneficiary | Beneficiary of digital training for WPS agenda |  |
|  |  | Beneficiary | Participants of multiparty dialogues |  |

# Appendix F. Updated Results Framework

Results Framework, Empowered Women Peaceful Communities, Sri Lanka, January 2020 – December 2022

| Goal: Women contribute to sustainable peace in Sri Lanka |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome: Women, including those in vulnerable situations, will be empowered to strengthen the peacebuilding process and social cohesion in Sri Lanka including through implementation of the NAP WPS Indicator 1: Number of gender-responsive policies or strategies developed that strengthen the peacebuilding process, promote social cohesion and contribute towards lasting peace in Sri Lanka Target: 1 NAP WPS is approved Baseline: No NAP on WPS Status: Achieved Finalised draft NAP WPS is handed over to the Ministry of Women, Child Affairs and Social Empowerment during the project period to initiate the Cabinet process. Cabinet approval was received in February 2023 and the NAP WPS was adopted. Data source: Gender sensitive strategies and policies Indicator 2: Number of districts with communities engaged in dialogues on Women Peace and Security and social cohesion Target: 9 districts (4 provinces) Baseline: 0 Status: Achieved, 9 districts (Anuradhapura, Polonnaruwa, Kegalle, Ratnapura, Moneragala, Badulla, Colombo, Kalutara and Gampaha) in 4 provinces (North Central, Uva, Sabaragamuwa and Western) Data source: Partners reports, dialogues reports |  |  | Alignment with UN Women Sri Lanka Strategic Note: Outcome 5: Women and girls contribute and have greater influence in building sustainable peace and resilience and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action. |  |  |  |  |
| Outputs | Lead organization | Indicative activities for each output |  |  | Resource allocation and indicative time frame (USD) |  |  |
|  |  |  | Y1 | Y2 |  | Y3 | Total |
| Output 1: Advocacy space is created, and capacities of government is strengthened to develop and implement gender responsive policies related to WPS. Indicator 1.1: Number of government institutions that received support for implementation of women, peace and security related policies. Target: 5 Baseline: 3 Status: Target achieved 52 government institutions, including the District Secretariat and 19 Divisional Secretariats in Ampara district, District Secretariat and 22 Divisional Secretariats in Anuradhapura district, District Secretariat and 5 Divisional Secretariats in Mannar district, Development Division and Planning Division of the Ministry of Women, Child Affairs and Social Empowerment, National Committee on Women, Women’s Bureau of Sri Lanka received support for implementation of Women, Peace and Security related policies. Data source: Report of support provided (including technical as well as assets and equipment) | UN Women | 1.1: Support the Ministry of Women and Child Affairs and other key ministries on the validation of policies on women, peace and security (WPS), including a National Action Plan on WPS | 110,000 | 100,000 |  | 145,000 | 355,000 |
| Indicator 1.2: Number of government officials that have increased their capacity on implementation of Women Peace and Security commitments Target: 60 Baseline: 0 Status: Target achieved 124 government officials representing 52 government institutions including the District Secretariat and 19 Divisional Secretariats in Ampara district, District Secretariat and 22 Divisional Secretariats in Anuradhapura district, District Secretariat and 5 Divisional Secretariats in Mannar district, Development Division and Planning Division of the Ministry of Women, Child Affairs and Social Empowerment, National Committee on Women, Women’s Bureau of Sri Lanka received support for implementation of Women, Peace and Security related policies. Data source: Workshop reports |  | 1.2: Strengthen the capacity of relevant government entities, including local and provincial government members and the Ministry of Women and Child Affairs, for the implementation of policies on women, peace and security (WPS), including a National Action Plan on WPS* |  |  |  |  |  |
| Indicator 1.3: Number of government and CSO stakeholders engaged in dialogues on Women Peace and Security Target: 150 Baseline: 0 Status: Target achieved 174 including local-level government officials, elected local councilors, CSO members, religious entities, media representatives, women and youth leaders were engaged in dialogues and capacity building activities to advocate for gender-responsive policies on WPS. Data source: Partners and dialogue reports |  | 1.3. Promote dialogue between the government and CSOs networks to advocate for gender responsive policies and strategies on WPS, including the NAP WPS |  |  |  |  |  |
| Output 2: Women and women’s groups, including grassroots women and the most marginalized, have capacity, resources and skills to promote peace and social cohesion at the community level Indicator 2.1: Number of individuals – disaggregated by sex – from grassroot organizations, religious and community leaders and women’s groups who have increased their expertise on the role women play in prevention of conflict and peacebuilding, gender responsive approaches to promote peace and security at the community level Target: 180 Baseline: 0 Status: Significant progress towards the target. 164 women community leaders were trained as social cohesion and peacebuilding implementors. They underwent ToTs in addition to engaging in workshops and dialogues during the training process. Data source: Partners reports Indicator 2.2: Number of individuals who have increased their understanding of the role women play in prevention of conflict, peacebuilding, gender responsive approaches through initiatives conducted by the trained grassroot organizations, religious and community leaders and women’s groups to promote peace and security at the community level Target: 5,400 Baseline: 0 Status: Target achieved 5,406. In addition to the 164 women peacebuilders who were trained, 5,242 secondary participants were involved as community volunteers to promote peace. Data source: Partners reports | UN Women | 2.1. Strengthen capacities of grassroot organizations, religious and community leaders and women’s groups to discuss the role women play in prevention of conflict and peacebuilding, as well as inform gender responsive approaches to promote peace and security at the community level 2.2. Promote social cohesion and women’s economic empowerment including through the transfer of assets with particular attention to vulnerable groups from different ethnic and faith groups including female headed households * | 480,000 | 100,000 |  | 336,328.11 | 916,328.11 |
| Indicator 2.3: Number of women who benefit from entrepreneurship activities linked to social cohesion Target:700 Baseline: 0 Status: Target achieved 735 participants were engaged with entrepreneurial skill development trainings. Data source: Partners reports Indicator 2.4: Number of women from those who have already received entrepreneurship skills who have received assets to start or expand their business e.g. equipment to vocational training centers, sewing machines, cows Target: 370 Baseline: 50 Status: Target achieved 445 (62+383) Beneficiaries have been granted in-kind assistance Data source: Partners reports |  |  |  |  |  |  |  |
| Indicator 2.5: Number of young women leaders who have increased their capacity on how to contribute to peace through informed digital engagement Target: 90 Baseline: 0 Status: Target achieved 90 young women leaders received capacity building and in-kind support to promote peace and social cohesion through digital engagement. Data source: Partners reports Social media inputs |  | 2.3. Build the capacities of young women leaders to contribute to peace through informed digital engagement, including social media* |  |  |  |  |  |
| Output 3: Coordination and knowledge exchange at local, national and regional level is fostered including by acting as the national secretariat for the G7 WPS initiative Indicator 3.1: Number of key documents developed and agreed by the G7 WPS Initiative Baseline: 1 draft action plan, 1 draft ToRs of the working group Target: 4 validated documents including validated action plan, validated ToRs for the working group and high-level group, G7 WPS initiative statements, outcome documents Status: Target achieved - Approved ToR for the G7+ Working Group - Approved Implementation Strategy - Press release on” G7 partners in Sri Lanka commit to support gender equality and women’s empowerment for COVID-19 recovery” - NAP on WPS Validated by the G7+ Working Group Data source: Validated documents as stated above | UN Women | 3.1. Support coordination and complementarity between development actors, including by acting as the Secretariat for the G7 WPS initiative in Sri Lanka | 115,000 | 100,000 |  | 130,000 | 345,000 |
| Indicator 3.2: Number of knowledge products on WPS in Sri Lanka Target: 4 Baseline: 0 Status: Target achieved - Three policy briefing papers (on international frameworks, regional frameworks and domestic frameworks) related WPS policies - NAP Implementation Guidelines - Study the role of women in promoting peace and social cohesion through informed digital engagement - Digitised training modules on WEE - Briefing papers on the impact of the economic crisis on different groups of women in Sri Lanka Data source: UN Women webpage Indicator 3.3: Number of individuals accessing knowledge products published online Target: 2,000 Status: Target achieved Knowledge products published online have received 200 views. Baseline: 0 Data source: UN Women webpage |  | 3.2. Develop and disseminate knowledge products, including research on WPS in Sri Lanka, using the platform of the G7 WPS initiative in Sri Lanka as possible and as appropriate |  |  |  |  |  |
| Indicator 3.4: Number of individuals accessing the mainstream media campaign on WPS Target: 50,000 Baseline: 0 Status: The campaign reached over 1.4million people through local TV, Radio and Newspapers Data source: Reports from the media channels Indicator 3.5: Number of participants who are learning from exchange of experience and knowledge on women peace and security Target: 60 Baseline: 0 Status: Target achieved 63 (55 government officials, 8 CSOs) Data source: To be added |  | 3.3. Promote global, regional and south-south knowledge exchanges on the implementation of the women, peace and security agenda |  |  |  |  |  |
| Sub-total |  |  |  |  |  |  | 1,616,328.11 |
| M&E (5%) |  |  |  |  |  |  | 70,316 |
| Communication (5%) |  |  |  |  |  |  | 80,316 |
| Operational Costs (5%) |  |  |  |  |  |  | 80,316 |
| Total programmable costs |  |  |  |  |  |  | 1,847,276.11 |
| Support Costs (8%) |  |  |  |  |  |  | 147,782 |
| Total (USD) |  |  |  |  |  |  | 1,995,058.11 |

# Appendix G - Term of Reference

# Appendix H – Evaluators Bio Data

Melissa Andrade Costa is a senior evaluator consultant with over 20 years of experience in carrying out evaluations for various UN and related Agencies (UN Women, UNAIDS, ICAO, UNOPS, UNPD, UNFPA, UNICEF, UNV, IOM, FAO) at a global, regional and national level in various themes (from women´s empowerment to HIV, civil aviation, security, economic inclusion, volunteerism, sexual and reproductive health, migration, inclusion of small farmers among others). She has worked mostly in Latin America, Sub-Saharan Africa and Southeast Asia. She has published a book on Evaluation Practices of International Cooperation in Brazil and is continously engaged in the debate on evaluation in various fora. She is part of the consultative board of the Brazilian Network of Monitoring and Evaluation.

Nadhiya Najab has worked in the development field for over 10 years with experience in conducting research and evaluations. These projects have looked at post-war resettlement experiences and assistance programmes, access to services, labour migration, and livelihood opportunities for marginalized and vulnerable groups with a strong gender focus. She is experienced in conducting monitoring and evaluation activities using the MEAL framework, as well as developing policy recommendations which are evidence-based and unbiased.

Both evaluators have been involved in a number of project evaluations on behalf of UN Women Sri Lanka  which have provided the necessary experience and expertise to carry out this end-of-project evaluation successfully, particularly during a pandemic and similar challenging contextual circumstances. The evaluations were guided by and were in compliance with standards set in the UNDP Evaluation Policy, UN Women Evaluation Policy, UN Women Evaluation Handbook and the Global Evaluation Report Assessment and Analysis System (GERAAS).

United Nations. (2015). Mapping of Socio-Economic Support Services to Female Headed Households in the Northern Province of Sri Lanka. Colombo: United Nations, Sri Lanka. http://lk.one.un.org/wp-content/uploads/2016/05/Mapping-of-Socio-Economic-Support-Services-to-Female-Headed-Households-in-the-Northern-Province-of-Sri-Lanka.pdf

International Crisis Group. (2011). Sri Lanka: Women's insecurity in the North and East. Colombo/Brussels: Crisis Group. Asia Report No.217 https://www.ecoi.net/en/file/local/1055886/2016_1324563161_217-sri-lanka-womens-insecurity-in-the-north-and-east-ko.pdf

Jayasundere, R. & Weerackody, C. (2013). Gendered implications of economic development in the post conflict Northern and Eastern Regions of Sri Lanka. Sri Lanka: Care International Sri Lanka.

United Nations. (2015). Mapping of Socio-Economic Support Services to Female Headed Households in the Northern Province of Sri Lanka. Colombo: United Nations, Sri Lanka. http://lk.one.un.org/wp-content/uploads/2016/05/Mapping-of-Socio-Economic-Support-Services-to-Female-Headed-Households-in-the-Northern-Province-of-Sri-Lanka.pdf

Asian Development Bank, Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH. (2015). Country Gender Assessment Sri Lanka Update.

ibid

Jayasundere, R. & Weerackody, C. (2013). Gendered implications of economic development in the post conflict Northern and Eastern Regions of Sri Lanka. Sri Lanka: Care International Sri Lanka.

https://reliefweb.int/report/sri-lanka/sri-lanka-s-anti-muslim-riots-signal-deeper-malaise

https://www.bbc.com/news/world-asia-27864716

https://www.theguardian.com/world/2018/mar/07/sri-lanka-blocks-social-media-as-deadly-violence-continues-buddhist-temple-anti-muslim-riots-kandy

Professor Jacqui True and Sri Eddyono, Monash University, “Preventing Violent Extremism: Gender Perspectives and Women’s Roles”, August 2017.

Uitto, Juha (2022). Transformational Change for People and the Planet: Evaluating Environment and Development – Introduction In book: Transformational Change for People and the Planet (pp.1-13). Available at: https://www.researchgate.net/publication/357797288

https://www.unwomen.org/-/media/headquarters/attachments/sections/library/publications/2020/good-practices-in-gender-responsive-evaluations-en.pdf?la=en&vs=2431

Policy Framework and National Plan of Action to Address Sexual and Gender-Based Violence in Sri Lanka 2016 – 2020; National Action Plan for the Protection and Promotion of Human Rights 2017 – 2021; National Action Plan on Women Headed Households 2017 – 2019; National Policy on Durable Solutions for Conflict-Affected Displacement; National Plan of Action for Children in Sri Lanka 2016 – 2020; Open Government Partnership: Sri Lanka’s 2nd National Action Plan 2019 – 2021; National Policy on Disability for Sri Lanka 2003; National Action Plan for Combatting Bribery and Corruption in Sri Lanka 2019 – 2023; National Labour Migration Policy for Sri Lanka 2008.

The Convention on the Elimination of All Forms of Discrimination Against Women, (“CEDAW”); international Covenant on Civil and Political Rights, (“ICCPR”); International Covenant on Economic, Social and Cultural Rights, (ECOSOC); Vienna Declaration on the Elimination of Violence against Women 1993; Sustainable Development Goals adopted by the United Nations in 2015; and other international Conventions, Treaties, Agreements relating to the rights and obligations of women and other applicable international instruments.

See Evaluation Unit Details : Multi-Country Office for India, Bhutan, Maldives, and Sri Lanka (MCO)-Global Accountability and Tracking of Evaluation Use - GATE System (unwomen.org)

See Paragraph 24 on interaction among government officers.

See UN-Women-audit-report-2022-004-Multi-Country-Office-in-Fiji-en.pdf (unwomen.org). In the case of the Audit in Fiji, there was a comment on  a recommendation coming from  tthe Internal Audit of Liberia Country Office (IEAS/IAS/2019/13) for the CO to ´perform cost–benefit analysis and risk assessment, and to consult with headquarters in timely manner and diligently monitor implementation of construction, if it is not possible to outsource this to other specialized agencies.” The audit report from Fiji issued a recommendation to Headquarters on the same issue: ´The Directors, PPID and DMA to develop a policy and process outlining if, when and how to conduct infrastructure work at UN Women´.According to the same document ´ there is a lack of corporate policy, procedure and guidance (PPG) on conducting infrastructure projects and associated implementation modalities`. Overall, challenges with the implementation on infrastruture projects and actions are recurrent in UN Women.

´For any future projects with infrastructure components, IAS encourages the CO to perform a cost–benefit analysis and risk assessment, and to consult with headquarters in timely manner and diligently monitor implementation of construction, if it is not possible to outsource this to other specialized agencies` - Internal Audit of Liberia Country Office (IEAS/IAS/2019/13) mentioned in Internal Audit Report UN Women Multicountry Office in Fiji (EAS/IAS/2022/004).