\

September 2023

End of Program Evaluation                                    Women’s Leadership, Empowerment, Access, and Protection (LEAP 2)                                  Somalia Activities                                            Muktar Abdi Hussein                                     National Consultant Somalia

Contents

List of Acronyms and Abbreviations	4

Executive Summary	5

1.	Background, Programme Description and Context	12

1.1.	Background and Context	12

1.2.	Programme Description	15

1.3.	Evaluation Purpose, Objectives and Scope	17

1.3.1.	Purpose	17

1.3.2.	Objective	17

1.3.3.	Scope	18

1.4.	Evaluation Criteria and Key Questions	19

1.5.	Theory of Change	19

2.	Evaluation Methodology and Limitations	20

2.1.	Evaluation Methodology	20

2.2.	Data Collection and Analysis Methods	20

2.2.1.	Data collection tools	20

2.2.2.	Data analysis	22

2.3.	Limitations	22

2.4.	Quality Assurance, Ethical Considerations, Gender and Human Rights in the Evaluation Process	22

3.	Findings of the Evaluation	23

3.1.	Relevance	23

3.1.1.	Relevance to the Needs of Beneficiaries	23

3.1.2.	Relevance of the Partnerships and Coordination	25

3.1.3.	Relevance of the Project Design	28

3.2.	Coherence	31

3.3.	Effectiveness	31

3.3.1.	Achievement of Objectives	31

3.3.2.	Achievement of Outcomes and Outputs	33

3.3.3.	Enabling and Hindering Factors to Results	39

3.3.4.	Effectiveness in Partnerships	42

3.4.	Efficiency	43

3.4.1.	Fund Utilization	43

3.4.2.	Financial Management	44

3.4.3.	Project Management and M&E process	45

3.5.	Sustainability	46

3.5.1.	Substantiality of the Results	46

3.5.2.	Gender Equality and Human Rights	47

4.	Lessons Learned and Good Practices	48

5.	Conclusions	49

6.	Recommendations	51

7.	Annexes	54

7.1.	Documents Reviewed	54

7.2.	Data Collection Instruments (questionnaires and interview guides)	54

7.3.	Evaluation Matrix	54

7.4.	List of Agencies and Partners Interviewed	54

7.5.	Evaluation ToR	57

7.6.	Evaluator Profile	57

Table of Figures

Figure 1: Women with Dignity Kits	24

Figure 2: Relevance of project activities	24

Figure 3: perception of improved protection, leadership and empowerment.	32

Figure 4: Perception on leadership skills	36

Figure 5: Twitter messaging on vaccine	39

Figure 6: Project inclusivity	40

Figure 7: How far LEAP project addressed gender inequalities?	41

Figure 8: Perception on women leadership	46

Figure 9: Perception on sustainability	46

List of Tables

Table 1 Project key stakeholders:	16

Table 2: Evaluation Key Questions	19

Table 3: Partners and their activities	26

Table 4: achievement of indicators	33

Table 5: Perception on different thematic areas	38

Table 6: Project's expenditure	43

Table 7: Perception on human rights and gender equalities	47

# List of Acronyms and Abbreviations

CEFM             Child, Early and Forced Marriage

CFM		Complaint and Feedback Mechanism

CSO		Civil Society Organization

ESARO		Eastern and Southern Africa Regional Office

FDG		Focus Group Discussion

FGM		Female Genital Mutilation

GBV		Gender based Violence.

HDP		Humanitarian, Development and Peace (nexus)

HRP		Humanitarian Relief Plan

IDP		Internally Displaced Person

IASC                  Inter-Agency Standing Committee

IPs                Implementing Partners

IPV                     Intimate Partner Violence

KII	              Key Informant Interview

LEAP	             Women‘s Leadership, Empowerment, Access and Protection

OCHA		United Nations Office for the Coordination of Humanitarian Affairs

PWD		Persons with Disabilities

SDG		Sustainable Development Goal

SGBV		Sexual and Gender based Violence.

ToC		Theory of Change

ToR		Terms of Reference

ToT		Training of Trainers

UN		United Nations

UNCT		United Nations Country Team

UNEG		United Nations Evaluation Group

UNSCF		United Nations Sustainable Development Framework

UN Women	United Nations Entity for Gender Equality and the Empowerment of Women

USD		United Stations Dollar(s)

VAWG            Violence Against Women and Girls

WLO                  Women-led Organization

# Executive Summary

Background - In Somalia, protracted conflicts and insecurities, violence, cyclical climatic shocks (drought and floods), locust invasion, political instability, socio-economic vulnerability, and the prevailing COVID-19 continue to fuel the humanitarian crisis and negatively impact livelihoods and gender equalities, particularly for women and girls. As of January 2023, GBV Information Management System (IMS) data reported a surge in GBV during COVID-19. Millions of people's lives, dignity, and futures are in jeopardy due to the severe and pervasive drought catastrophe in Somalia, which is now in its sixth season without rain. The effects on women and girls have been quite negative. Gender-based violence has become more severe as a result of ongoing hostilities, a spiralling economic crisis, migration, and historically rare food and basic shortages.

Programme Description - To tackle the complex multiple interlinked and complex crises mentioned above, UN Women implemented the LEAP project (women’s leadership, empowerment, access, and protection) in Somalia, from March 2022-March 2023 in four locations (Mogadishu, Baidoa, Kismayo and Garowe). The LEAP project sought to promote COVID-19 prevention and mitigation measures, targeting women and girls in IDP and refugee camps and was expected to enhance the leadership skills of IDP women and girls, develop their capacities for promoting gender-responsive COVID-19 prevention and recovery support among crisis-affected women in Mogadishu, Baidoa, Kismayo and Garowe. This project was directed to reach over 9,400 beneficiaries (IDPs women and girls) and benefit an additional 10,000 indirectly.

In Somalia, the project reached Somalia more than 10,000 vulnerable women, men, and youth to lead and participate in COVID-19 prevention, response and recovery interventions through awareness raising and education on COVID-19 prevention and mitigation for women in the IDP settings in Mogadishu, Kismayo, Baidoa and Garowe, distribution of COVID-19 prevention and mitigation tools. The awareness sessions ensured PCR testing and vaccination sites in refugee and IDP camps are safe, and women and girls are protected from sexual violence through awareness raising, effective monitoring and timely support by government and other stakeholders.

Besides, the project  improved the leadership of 600 women and girls in COVID-19 prevention, response and recovery interventions in Somalia by strengthening the capacity of 300 women in Mogadishu, Kismayo, Baidoa and Garowe on participation, decision-making in COVID-19 preparedness planning, response and recovery, conducting 2 training of trainers (ToT) workshops on GBV prevention and response using Inter-Agency Standing Committee (IASC) GBV in emergency guidelines for 300 women and girls from key stakeholders involved in COVID-19 response in target locations, partnering with community-based radios, women and youth organizations, religious and community leaders to create awareness, share information on the prevention and management of COVID-19 to men and women and assessing COVID-19 preparedness and response plans to identify how gender is being mainstreamed, gaps and opportunities to strengthen the integration of gender in these key frameworks to ensure effective prevention of COVID-19

Purpose and Scope of the Evaluation - This evaluation is an end-of-project evaluation that covered all project activities implemented from March 2022 – March 2023 by the different Implementing partners (IPs). The evaluation interviewed project beneficiaries in Baidoa (Southwest State), Garowe (Puntland), Mogadishu, and Kismayo (Jubaland) in Somalia. The evaluation team undertook the data collection that covered the following areas as per the ToR: The purpose of the independent endline evaluation is to assess the project’s achievements against the set objectives, identify and document lessons learnt (including design issues, lessons and best practices that can be up-scaled or replicated), and assess how the program contributed to promote COVID-19 prevention and mitigation measures, enhance leadership skills of IDP women and girls, develop their capacities for promoting gender responsive COVID-19 prevention and recovery support among crisis affected women in Mogadishu, Baidoa, Kismayo and Garowe.

The other objectives of the endline evaluation are to ensure accountability and communicate results achieved to the project stakeholders. It has done so by gauging the progress made by the project in achieving its agreed objectives through its planned activities and ensuring that resources were properly utilized to generate results and achieve the LEAP 2 project objectives. The evaluation applied the standard UN Evaluation Group (UNEG) evaluation criteria; namely: relevance, effectiveness-including normative, and coordination mandates of UN Women-, efficiency, coherence and sustainability.

Evaluation Audience and Intended Use - The end cycle evaluation will be used by the different stakeholders in their programming as the report is expected to inform learning and improved decision-making to support the scale up of the programme, provide feedback, participation and accountability to affected communities and act as capacity development and mobilization of national stakeholders to advance gender equality and the empowerment of women.

The primary audience of the report consists of relevant staff in target ministries/local government/government institutions, and participating CSOs; target beneficiary communities/groups; members of community leadership structures; relevant staff in participating UN agencies; staff of implementing partners; sector leads in the participating UN-agencies and refugee response coordination; UN Agencies technical working groups; development partners.

Evaluation Methodology & Related Limitations - The evaluation employed mixed methods of desk review and qualitative means of data collection, analysis, interpretation, and presentation. It applied a participatory approach, where substantive consultations were made with all project stakeholders to get insights from the project. Techniques used included a desk review, qualitative data collection through key informant interviews (KIIs), and focus group discussions (FGDs). The interviews and review of the project documents helped assess whether the LEAP 2 project adequately addressed gender considerations and supported GEWE throughout its implementation. Content analysis was used to analyze the data collected for this evaluation. In this regard, data were transcribed and coded to identify recurrent themes from opinions and experiences expressed during the 17 KIIs and 8 FDGs conducted. Data analysis entailed making notes of the transcripts, categorizing contents, and linking categories to summarize findings into themes. This information was used and interpreted in view of the evaluation objectives to make a conclusion about whether the intervention achieved its intended results, documented lessons learned, best practices, and made recommendations.

Prior to the data collection phase in the field, a certain number of risks and limitations had been identified as potentially hindering a smooth evaluation process. In a nutshell, these comprised insecurity or a spike of the COVID-19 pandemic, difficulties in reaching out to targeted IDPs or respondent information bias, or difficulties in accessing baseline reporting data. Thereafter, however, some unforeseen internal delays cropped up in the organization of the field trips for data collection and mobilization of FGD participants that slightly lagged the timeline for the submission of all the deliverables. Finally, the field visits took place as of June without major restrictions in terms of the quantity and quality of interviews carried out in the field.

Chiefly to be mentioned among the limiting factors is the absence of baseline data for objective and outcome 3 indicators which could have been used as a benchmark to compare with the endline data. Such comparison could have helped evaluate the results the project may have triggered in the target communities.

Quality Assurance, Ethical Considerations, Gender, and Human Rights in the Evaluation Process - Quality assurance measures included systematic cross-checking and triangulation of data. Gender and human rights concerns were covered by a specific sub-set of questions specifically geared towards these dimensions. Moreover, the vast majority of informants were female, especially at the field level. LNOB concerns were not only covered through related questions as part of the aforementioned module of specific questions, but related concerns were also reflected in the selection of the informants. The evaluation adhered to a specific set of ethical obligations and rules of conduct during interviews and FGD facilitation, and the interaction with beneficiaries throughout data collection, data management, storage and usage.

Strategies deployed to protect the informants included the following:  i. Participation was based on informed consent; ii. During the preparatory phase, data collection tools were tested on a group of participants who were informed about the purpose of the process and had the choice to opt-out or voluntarily participate; iii. During actual data collection, the participants were assured of the confidentiality of all data collected from them and further that the data would be used exclusively for the research process; iv. Interactions between the interviewers and the participants as well as among the participants themselves were governed by mutual respect and trust; v. Safeguards to ensure confidentiality during data processing and reporting included refraining from attributing specific statements to particular participants.

EVALUATION FINDINGS

Relevance - The LEAP 2 project responded to the needs and priorities of beneficiaries who were the most vulnerable category of people in the targeted IDP setting as the pandemic hard-hit them. It created massive awareness within the community on sanitation, especially proper handwashing, and empowered women on their rights. Harmful cultural practices and referral pathways for victims were the areas covered under some of the product activities.

Based on their participation in the pandemic response at the local level, the implementing partners were chosen rightly. The frontline responders in the humanitarian crisis are civil society organizations (CSOs), particularly women-led organizations (WLOs), who are in charge of coordinating efforts to provide vital and life-saving assistance to crisis-affected women and girls. In response to the COVID-19 epidemic, the initiative teamed up with two capable CSOs, the Somali Women's Development Centre (SWDC) and Nomadic Assistance for Peace and Development (NAPAD). These two groups are well renowned for supporting women's leadership and development.

The project worked with the ministries of Health as well as Women and Human Right Development (at Federal and State levels) by creating a partnership with these relevant stakeholders that facilitated the proper implementation of the project. The close collaboration with the government at the regional and federal levels improved ownership. The IPs consulted the two ministries when designing the project through daily field visits.

The project conception and design were appropriate and relevant to UN Women’s mandate to contribute to women’s engagement in humanitarian, peace, and security efforts in target locations in alignment with international commitments and standards as well as national policies, strategies and frameworks for humanitarian response and gender equality.

The LEAP 2022 project contributes to the UN Women Somalia Strategic Note which supports Women's Leadership, Empowerment, Access & Protection in Crisis Response (LEAP) program approaches to address multiple humanitarian crisis due to recurrent droughts, armed conflicts, floods, and COVID-19 on women’s livelihoods. This project leveraged implementation and continuity of the LEAP 1 pilot project in Somalia contributing to SDG 5; ‘Achieve gender equality and empower all women and girls’ and SDG 8; ‘Promote sustained, inclusive and sustainable economic growth, full productive employment and decent work for all.

The project supports the 2020 Humanitarian Response Plan, whose priorities include protection, recovery, and resilience (septically corresponding to Women and girls lead and participate in COVID-19 response planning and decision-making), as well as the Recovery and Resilience Framework (RRF), and is closely aligned with UN Women's Strategic Plan for 2022-2025, The Humanitarian Strategy for 2022-2025, and the UNW's 10 Gender Equality Accelerators.

The project is also aligned to WHO strategic preparedness and response plan (SPRP) designed to guide countries in the transition from COVID-19 pandemic emergence phase to sustainable comprehensive management of the pandemic. The strategic has five components: collaborative surveillance, community protection, safe and scalable care, access to countermeasures and emergency coordination.

Effectiveness - The project’s indicator targets were all achieved with some of them exceeding the target. The experience of IPs and their necessary skills, knowledge and capacities needed to deliver the project was the main contributing factors to successful project implementation through inclusive approaches which benefited the target community. Coordination at the different levels and the regular follow-up by UN Women was successful contributing factor. The main factors hindering the achievement of project results relate to the limited project timeframe, the presence or recurrent nature of drought and the patriarchal nature of the country.

Efficiency - Overall, the LEAP budget allocated a total of 29% for project management costs including staff costs and M&E (reporting and reporting and the final evaluation). This relatively high percentage can be explained by the high cost of doing business in the context of high insecurity in the country. the other expenses were as follows: Gender assessment: 3%, Rapid PCR test kits and aprons: 27%, community mobilization and inception meetings: 5%, COVID IPC-vaccination promotion and GBV prevention messages: 10%, door-to-door community hygiene promotion with a focus on COVID-19 Vaccine and PCR testing uptake: 2%, Protective equipment including gloves and face masks, sanitisers, and soaps for hygiene promoters: 3%, a monthly stipend for hygiene promoters: 8%, project monitoring by partners and government: 2%, Strengthen the capacity of 300 women on participation, decision making in COVID-19 preparedness planning, response and recovery: 2%, training of trainers (ToT) workshops on GBV prevention and response: 1%, Community conversations / dialogues: 1%, Development & printing of GBV pocket guidelines: 1%, Provision of material assistance (dignity kits): 1%, trainings for women leaders to enhance leadership, equal representation of women in decision-making and how-to refer cases to formal justice system in all target project areas: 1% and community-based radios, women and youth organizations, religious and community leaders to create awareness, share information on the prevention and management of COVID-19 with 2% of the total budget. The analysis of the fund utilization shows that 80% of the overall LEAP budget of USD $559,826 had been spent.

The overall budget was deemed sufficient for the general scope of work foreseen by the Prodoc and the set targets as per its results framework. However, the IPs described delays in the reimbursements of the budget from UN Women which delayed further implementation of planned activities. According to them, the delays caused hurried activities implementation and not the end results or the targets. The budget allocated or the IPs were transferred in tranches upon their request and after the finalization of the preceding tranche activities.  Additionally, partner selection and recruitment of the staff took some time and actual implementation started April 2023, however partners received their funds in October 23.

Sustainability - The evaluation findings show that the community awareness-raising sessions, provision of the dignity kits and PPEs, the training as well as other outreach activities had a positive impact on the lives of the target population, thus ensuring the sustainability of the results. According to them, the project was owned by the community and even now as the project ended the groups are still working on promoting women’s rights through regular meetings, however, they need more support such as training and income to sustain the project and achieve greater results.

Lessons Learned – The selection of hygiene promoters from the neighbourhoods who are known by the community established enabled trust of the target communities with the project. The engagement resulted the hygiene promoters to interact with the community all the time even after work. As a way to empower women and improve justice for displaced women, pocket GBV books were distributed to literate women which acts a guide to refer to all the time. The project partnered with a women-led organization with a presence in the field who are working in gender issues as well as prevention of the spread of COVID-19 which resulted in the successful implementation of the project. Targeting IDPs, returnees and the host community (who are always living in the same settlement) in project activities facilitated the social integration of IDPs and host community. By targeting beneficiaries with a different “displacement status”, the project facilitated the establishment of cross-cutting networks across different population groups among the inhabitants. This contributed to creating a cohesive network and promoted social cohesion including sharing insights and learning from one another. The practice of community door-to-door awareness-raising sessions potentially qualifies as a best practice. Further proof is needed, though, to ascertain whether these sessions helped communities to no longer commit harmful traditional practices (FGM, childhood marriages etc.) are more than a reflection of peer pressure during these public events, and the pledge actually translates into discontinuing and thus, abstaining from further adhering to said practices.

The project symbolized the importance of engaging communities in GBV and COVID-19 prevention response efforts during the project implementation. The project found that involving community members in project activities helped build trust and improve access to services.

Employing women: The LEAP project employed women to implement the project's activities while receiving a monthly incentive; in turn, this empowered vulnerable women, girls, and youth affected by COVID-19 in the IDPs in Somalia and decreased their families’ food insecurity and unemployment rate.

Targeted IDPs commonly lacked resources such as food, water, and healthcare, which made it difficult to prioritize prevention measures for COVID-19 and GBV. The level of poverty and the overcrowding of the IDP camps may prove sanitation and hygiene promotions ineffective though all the community members who interacted confirmed that the project has helped them acquire the required knowledge of the pandemic and its prevention measures.

Influence of culture: The norms and culture dictated that women’s place is in the kitchen and thus cultural and social beliefs prevented IDPs from seeking support or reporting incidents of GBV. For instance, some communities viewed GBV as a private matter that should be resolved within the family. This made it challenging to raise awareness about GBV and encourage reporting. For instance, religious leaders in Baidoa advocated the radio to stop broadcasting GBV and how to report them.

Recommendations – The evaluation presents the following recommendations:

Expanding Scope: In order to reach as many people as possible, the respondents with whom the evaluator interacted suggested that such a project in the future engage universities to highlight harmful cultural habits through theatre/drama and plays that are broadcast on television. Both an IDP situation and an out-of-camp one might benefit from this. In order to understand how the play and drama will be received by the community, it is crucial to conduct a survey. Arday (Student), a recent TV show on education in Somalia, went viral but was denounced by religious authorities while being seen by the public as an educational film that even discussed GBV issues including early and forced marriage in parts of the episodes.

Life skills: All the informants agreed on the importance to incorporate a life skills program. The coronavirus disease 2019 (COVID-19) pandemic has had a huge effect on adolescents' health and learning. Health promotion strategies should be valued, and life skill education is a potential approach in this direction. As the pandemic has thrown life into disarray, being responsible, valuing money, and bonding with loved ones are a few important life skills you can help the community learn in these uncertain times.

Livelihood Support: the pandemic has left indelible haunting moments on the IDPs as its effects (lockdown etc) hampered their livelihood like small-scale businesses. Most of the IDPs work as labourers in the main cities and this was minimized or even absent. It is recommended that such a project include some livelihood support to the supported communities in the form of income-generating activities or business start-up kits for women.

Continuity of the project: All of the informants contacted highly complimented the LEAP 2 project, which was created to develop awareness-raising sessions, for its applicability and timeliness as well as the outcomes it generated. Having said that, the implementation phase was quite brief, and a continuance should be taken into account. By enlisting more contributors or collaborating with other efforts with similar goals, it may be possible to continue supporting the beneficiaries while bringing in new funding to secure the project's viability.

Improve the capacity of partners on Results-based reporting: a two-day training on results-based monitoring and reporting was conducted for the IPs towards the end of the project implementation period. Though the training was relevant and applicable, it would have been planned in the inception phase of the project so that partners’ capacity on reporting is improved and skills and knowledge utilized throughout the project’s life span.

# Background, Programme Description and Context

## Background and Context

Since it first emerged at the start of 2020 as a global health crisis, COVID-19 has spread to nearly every country in the world. Defined as the greatest challenge the world has faced in decades, the pandemic has disrupted entire nations’ social, economic and political lives.

Over the past two decades, Somalia has experienced a raging civil war, a rise in violent extremism, and a devastating humanitarian crisis, which led to the collapse of institutional and bureaucratic infrastructure and has greatly damaged social cohesion and unity. Growing at an average of 2.5 percent per year from 2012 until 2019, the country’s economy has been exposed to, and suffered from, multiple shocks during the past two decades.

Natural disasters and catastrophes that struck the country included recurrent floods and droughts and, in recent years, also locust infestations. These plights were exacerbated by insufficient infrastructure and equipment, limited skills and capacities of public services and institutions to provide solutions in preventing, mitigating, and responding to crises, and weaknesses or outright gaps in the public financial management system.

Since the spring of 2020, the country’s fragility has been further compounded by the COVID-19 pandemic, which has claimed a large death toll and, other than that, also heavily impacted negatively on economic growth, food security, employment, remittances and fiscal revenue.

By 2019, it was estimated that more than 5.2 million people in Somalia, mostly pastoralists and agro pastoralists, were in urgent need of humanitarian assistance given the multiple shocks they had been exposed to over recent years if not decades and which had been steadily eroding their resilience and coping mechanisms (livestock and other assets). These numbers have further increased to about 6m over the last couple of years. By 2021, over 60% of the more than 5.9 million people in need of humanitarian assistance in Somalia, were experiencing food insecurity. In 2020, humanitarian agencies projected that the number of people in need would likely rise to 7.7 million in 2022 which means that during the LEAP implementation period, country-wide trends were still moving upwards due to sequent failed rainy reasons.

To curb the spread of the pandemic, the government put in place prevention measures including the establishment of COVID-19 response committees and an incident management system; border closures; suspension of local and international flights; movement restrictions; and suspensions of services including education. It also restricted mass gatherings and advised social distancing and curfews, which were eased for the holy month of Ramadan. The Ministry of Health and Human Services’ ‘National Preparedness and Response Plan for Corona Virus Disease, March-August 2020’ appealed to international support. The plan had 10 pillars, none of which focused on, or included, risk mitigation of the gendered impacts of the pandemic or ensured women’s and girls’ rights. Only two pillars made a reference to gender-related or women- and girl-specific needs, namely lifesaving maternal and neonatal services in the health pillar and gender-based violence (GBV) referral mechanisms in the Psychosocial Care pillar.

In a country in which only half of the population is economically active, the socio-economic impact of COVID-19 also plays an important role: a decline in remittances and in livestock export; increased food prices; and a decline in employment and other income-earning opportunities for the urban poor and internally displaced persons (IDPs). Despite representing 36.6 per cent of the economically active population, women make up to 70 percent of the informal sector and have been particularly affected by this situation. Most of them sell tea and khat and deal with currency exchange and fuel trade – activities that have been negatively impacted by restrictions and lockdowns.

Patriarchal social norms shape all areas and levels of Somali society: the dominance of men in decision-making and the discrimination against women and girls (and the right of men to preserve their dominance through violence) in the home; male dominance within wider formal and informal decision-making structures and institutions (including security and justice systems); and the differentiated impact of conflict and fragility on men and women (including income inequality). These norms legitimise and foster inequality, exclusion and violence against women and girls (VAWG), young people, marginalised communities and IDPs.

As they are expected to be first responders, women and girls bear the brunt of this pandemic by maintaining communities’ safety, distributing food for people in isolation, taking care of the sick and distributing protective equipment, as well as additional caring responsibilities when family members fall sick and caring for extended family. In addition, global evidence shows that women are disproportionately affected by economic shocks and crises and find difficulties in fulfilling their expected roles in terms of contribution to the food security and nutrition of their family.

In Somalia, at least 20 per cent of households are headed by women who bring in on average 70 per cent of all households’ incomes, the majority of which comes from activities in the informal sector. COVID-19 has seriously impacted women’s livelihood activities due to mobility restrictions and lockdowns. For example, measures to contain COVID-19 have imposed restrictions on international flights, affecting imports such as candies and clothes, most of which are sold by women in Somalia. Curfews have also impacted negatively on women sellers, such as tea sellers who cannot sell at night which is the peak time. As a result, many women have seen their income activities drastically reduced, which has negatively impacted them, their families and their communities. In addition, reduction in remittances and in aid programs that focus on strengthening women’s economic initiatives, have left women and their families in a precarious situation without the safety nets they usually rely on.

Somali women, young women and girls have long been marginalised from political participation due to gender norms in cultural, religious and clan related traditions that designate the public sphere as male territory. This has been reinforced by the protracted conflict. Despite the dedicated efforts of many Somali women activists and organisations, women continue to be significantly underrepresented in decision-making bodies at all levels, particularly in official institutions but also at the community and household levels. Girls continue to have little to no say in the face of decisions around traditions and practices that affect them directly, such as Female Genital Mutilation (FGM).

According to the Gender-Based Violence/Female Genital Mutilation Area of Responsibility (AoR) survey, 38 percent of survey respondents indicated an increase in GBV incidents compared to the period before the COVID-19 pandemic. Most reported cases are of physical violence, both in and outside the house (34 percent), sexual abuse and harassment (20 percent), intimate partner violence (18 percent), rape (18 percent) and Child, Early and Forced Marriage (CEFM) (nine percent). Thirty-one percent of respondents reported an increase in FGM during the COVID-19 period. Other sources have also reported an increase in FGM, with circumcisers going door-to-door offering to cut girls stuck at home during the pandemic, thereby undermining efforts to eradicate the practice in Somalia. The increase in FGM has been linked to: schools being closed and girls being at home, which practitioners see as an opportunity to increase their practice; the economic crisis which may drive families to increase income; and awareness-raising programs with communities on the dangers of FGM being stopped. This in essence presented a huge challenge to the elimination of FGM in Somalia, thus making the attainment of the SDG 5 indicators and targets difficult.

As a country where half of the population is in need of humanitarian aid, has been facing a triple threat: conflict, climate change and COVID. While the country now grapples with a severe food insecurity crisis, it also struggled to respond to the COVID-19 outbreak. A lack of resources, the spread of false or incomplete information about COVID-19, and unequal distributions of COVID-19 vaccines have been determining factors in the low vaccination rates persisting in Somalia.

The number of confirmed COVID-19 cases and deaths are underestimated due to the limited geographic coverage of testing for COVID-19 and low vaccine uptake as well as poor community awareness about prevention and mitigating the virus, especially among IDPs. The government is ill equipped to upscale COVID -19 prevention and mitigation measures. Thus, spread of COVID-19 is expected to continue impacting the livelihoods of vulnerable groups especially women who comprise 49% of the population estimated at 12, 316, 895. Even before the pandemic, Somalia women and girls were among the most vulnerable, in a country whose Gross Domestic Product (GDP) is ranked the second lowest globally. Like in many disaster settings, women’s health, livelihoods and bodily integrity are particularly at risk as evidenced during the COVID-19 pandemic. The pandemic is deepening pre-existing inequalities, exposing vulnerabilities in social, political and economic systems. There are reports of increased domestic violence, sexual violence, femicide, harmful practices, sex trafficking including sexual harassment in work/public places thus risking their economic opportunities and heath. These impacts are further amplified in contexts of fragility, conflict, and emergencies where social cohesion is already undermined and institutional capacity and services are limited. Within the constraints imposed by COVID-19 containment measures, women and girls are facing the brunt of sexual and gender-based violence exacerbated by the fact that over 90% women have undergone female genital cutting, one of the greatest risks to their sexual and reproductive wellbeing.

## Programme Description

UN Women, grounded in the vision of equality enshrined in the Charter of the United Nations, works for the elimination of discrimination against women and girls; the economic empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security. Placing women's rights at the centre of all its efforts, UN Women leads and coordinates United Nations system efforts to ensure that commitments on gender equality and gender mainstreaming translate into action throughout the world. It provides strong and coherent leadership in support of Member States' priorities and efforts, building effective partnerships with civil society and other relevant actors.

In Somalia, the LEAP project funded by the Government of Japan provided an opportunity for the internally displaced persons (IDPs) to strengthen the protection, leadership and empowerment of vulnerable women, men and youth affected by COVID- 19. The aim of the project is to prevent the spread of COVID-19 infections among women and girls displaced into IDP and refugee camps and help them mitigate their exposure to gender-based violence and improve their decision-making capacities. The project was implemented in four locations (Mogadishu (Banadir Regional Administration), Garowe (Puntland State), Kismayo (Jubaland State) and Baidoa (Southwest State) while leveraging on ongoing initiatives by other development partners. The project’s timeframe was from March 2022 to March 2023 with a total budget of $559,826. This project was directly to reach over 9,400 beneficiaries (IDPs women and girls) and benefit an additional 10,000 indirectly through outreach activities (awareness-raising, Radios, etc).

In Somalia, the project was meant to reach 9,400 vulnerable women and youth to lead and participate in COVID-19 prevention, response and recovery interventions through awareness raising and education on COVID-19 prevention and mitigation for women in the IDP settings in Mogadishu, Kismayo, Baidoa and Garowe, distribution of COVID-19 prevention and mitigation tools and ensure that PCR testing and vaccination sites in refugee and IDP camps are safe and women and girls are protected from sexual violence through awareness raising, effective monitoring and timely support by government and other stakeholders.

Besides, the project  improved leadership of 600 women and girls in COVID-19 prevention, response and recovery interventions in Somalia by strengthening the capacity of 300 women in Mogadishu, Kismayo, Baidoa and Garowe on participation, decision making in COVID-19 preparedness planning, response and recovery and conducting 2 training of trainers (ToT) workshops on GBV prevention and response using IASC GBV in emergency guidelines for 300 women and girls from key stakeholders involved in COVID-19 response in target locations.

The project also partnered with community-based radios, women and youth organizations, religious and community leaders to create awareness, share information on the prevention and management of COVID-19 to men and women and assessing COVID-19 preparedness and response plans to identify how gender is being mainstreamed, gaps and opportunities to strengthen the integration of gender in these key frameworks to ensure effective prevention of COVID-19.

UN Women partnered with two implementing partners (NAPAD and SWDC) in the implementation of the project. As detailed in table 1, each partner had a role to play to ensure the effective implementation and achievement of the project objectives. The close coordination (also discussed in section: Relevance of the Partnerships and Coordination) was one of the key factors that led to the success close out of the project’s implementation.

Table 1 Project key stakeholders:

| Partner | Role played in the project |
| --- | --- |
| NAPAD | Conduct community mobilization and inception meetings in Kismayo, Garowe, Baidoa and Mogadishu. |
|  | In partnership with the Ministry of Health, develop COVID IPC-vaccination promotion and GBV prevention messages that will be disseminated to educate and empower at-risk persons, surrounding businesses and localities through the printing of 700 pamphlets and 50 posters, through 37 social media promotions and 1 radio spots. |
|  | Facilitate 60 community hygiene promoters to conduct door-to-door community hygiene promotion with a focus on COVID-19 Vaccine and PCR testing uptake, COVID-19 prevention information and community led prevention and identification of, and response to SGBV in households. |
|  | Conduct project monitoring in partnership with relevant stakeholders, document change stories. |
| SWDC | Strengthen the capacity of 300 women in Mogadishu, Kismayo, Baidoa, and Garowe on participation, decision making in COVID-19 preparedness planning, response and recovery. |
|  | Conduct training of trainers (ToT) workshops on GBV prevention and response using IASC GBV in emergency guidelines for 300 women and girls from key stakeholders involved in COVID-19 response in target locations. |
|  | Partner with community-based radios, women and youth organizations, religious and community leaders to create awareness, share information on the prevention and management of COVID-19 to 10,000 men and women. |
|  | Community conversations / dialogues led by community opinion leaders. |
|  | Development & printing of GBV pocket guidelines for key community stakeholders. |
|  | Provision of material assistance (dignity kits) |
|  | Conduct trainings for women leaders to enhance leadership, equal representation of women in decision-making and how-to refer cases to formal justice system in all target project areas. |
| Ministry of Women and Human Right Development and Ministry of Health | Monitoring and oversight role. |
| UN Women | Recruited two consultants (one international and one national) to conduct study to assess, monitor and map out Gender mainstreaming gaps and opportunities in COVID-19 Preparedness and Response Plans in Mogadishu, Jubaland, Southwest and Puntland states in Somalia. |
|  | Distributed PPEs to 200 women. |

## Evaluation Purpose, Objectives and Scope

### Purpose

The end cycle evaluation will be used by the different stakeholders in their programming as the report is expected to inform learning and improved decision-making to support the scale up of the programme, provide feedback, participation and accountability to affected communities and act as capacity development and mobilization of national stakeholders to advance gender equality and the empowerment of women.

### Objective

The objective of the independent endline evaluation is to assess the project’s achievements against the set objectives, identify and document lessons learnt (including design issues, lessons and best practices that can be up-scaled or replicated), and assess how the program contributed to promote COVID-19 prevention and mitigation measures, enhance leadership skills of IDP women and girls, develop their capacities for promoting gender responsive COVID-19 prevention and recovery support among crisis affected women in Mogadishu, Baidoa, Kismayo and Garowe.

The specific objectives of the evaluation are:

- To assess the relevance of LEAP intervention in addressing the needs of COVID-19 prevention and mitigation measures

- To assess the effectiveness and efficiency of UN Women’s approach for achievement of results, as defined in the logical framework, including the Program Theory of Change

- To analyse how the human rights approach and gender equality principles were integrated in LEAP and humanitarian action programming in the South Sudanese response.

- To identify and validate lessons learned, promising practices and innovations of work supported by LEAP Program within the context of the aid effectiveness agenda.

- To assess the added value of the LEAP strategy and related interventions to UN Women’s mandate and to the overall UN System presence in project locations.

- To assess the inter-connectedness and sustainability of UN Women’s initiatives on increasing leadership, protection and economic opportunities for refugee women and analyse possible weaknesses in order to improve next steps for scale-up programming.

- To provide actionable recommendations with respect to the strategy, and overall approach to UN Women’s programming in humanitarian settings.

Regarding the audience and the intended utility of the evaluation, the primary audience of the report could be:

- UN Women

- Other UN Agencies

- Development Partners

- Relevant staff in target ministries/local government/government institutions, and participating CSOs

- Members of community leadership structures

- Staff of implementing partners

- Target beneficiary communities/groups

### Scope

This evaluation is an end of project evaluation and that covered all project activities implemented since March 2022 – March 2023 by the different Implementing partners (IPs). The evaluation interviewed project beneficiaries in Baidoa, (Southwest State), Mogadishu, Garowe (Puntland) and Kismayo (Jubaland) in Somalia as well UN Women Staff and IPs.

The evaluation team undertook the data collection that covered the following areas as per the ToR:

- An assessment of the relevance, appropriateness and coherence of the implicit or explicit theory of change, strengthening or reconstructing it where necessary

- An assessment of the quality of performance indicators in the program, and the accessibility and adequacy of relevant documents and secondary data

## Evaluation Criteria and Key Questions

The evaluation will apply the standard UN Evaluation Group (UNEG) evaluation criteria; namely: relevance, effectiveness-including normative, and coordination mandates of UN Women-, efficiency, coherence and sustainability. The evaluation sought to answer the following key evaluation questions:

Table 2: Evaluation Key Questions

| Evaluation Criteria | Key Question |
| --- | --- |
| Relevance | To what extent was the programme in line with the needs of the target population? Did the programme identify the right target population for the programme? To what extent did the programme ensure alignment with national? goals on gender equality and women’s empowerment? |
| Effectiveness | To what extent did the programme achieve its objectives and its results, including any differential results across groups? Were there any unintended results of the programme? How did UNWOMEN contribute towards the achievement of the results? |
| Efficiency | To what extent did the programme deliver the achieved results in an economic and timely way? |
| Inter-connectedness/Coherence | How well did the programme fit? |
| Sustainability | To what extent can the achieved results be sustained beyond the lifespan of the programme |
| Integration of human rights approach and gender equality principles | How were human rights approaches integrated in the programme? How was gender equity principle integrated in the programme? How was inclusion principle integrated into the programme? How was participation principle integrated into the programme? |
| Integration of Lesson Learned and M&E | Were there mechanisms in place to facilitate documentation and application of lessons learned? |

## Theory of Change

According to the project documents, the project had no Theory of Change (ToC) that could illustrate the change pathways. However, based on the activities and their results, the evaluator proposes the following ToC:

IF there is increased capacity of the community by awareness raising sessions at community level and women are educated on their rights and harmful cultural practices addressed through advocacy and access to services THEN there would be a reduction in gender-based violence leading to better living conditions for women and girls and Women and girls will show exemplary leadership in the promotion of positive gender norms and in managing the COVID-19 response BECAUSE their leadership positions will amplify the challenges faced by women and girls and equality will prevail.

# Evaluation Methodology and Limitations

## Evaluation Methodology

This evaluation used non-experimental design due to Its flexible during the evaluation process. The evaluation targeted all the beneficiary groups that participated in the different activities regardless of the gender (though the project targeted mainly female). The data collection took place from 15th May to 11th June 2023 in all the target locations. The evaluation interviewed 91 persons (89% female and 11% male). Females were higher as they were the majority targeted by the project.

The evaluation employed mixed methods of desk review and qualitative means of data collection, analysis, interpretation, and presentation. The evaluators deemed this approach as the best for achieving the evaluation purpose of determining the extent to which the LEAP project achieved its stated results, documented lessons learned and best practices and helped draw recommendations that would help improve similar programs in the future. The evaluation took a participatory approach, where substantive consultations `were made with all project stakeholders to get insights from the project.

## Data Collection and Analysis Methods

### Data collection tools

to conduct this evaluation, the evaluation employed desk review as well as qualitative data collection through key informant interviews (KIIs) and focus group discussions (FGDs). The evaluation took a participatory approach to collect the required data where the government, partners, staff from UN Women and the donor were interviewed for triangulation of information.

The respondents represented all beneficiaries that were engaged in the project including vulnerable groups (including Persons with Disabilities) and the data collection took place in the four target locations.

The interviews and review of the project documents helped assess whether the LEAP project adequately addressed gender considerations and supported GEWE throughout its implementation.

Desk review: The evaluators reviewed project documents and UN Women evaluation guidelines. The documents reviewed are annexed in the report. Some of the documents reviewed include:

- Project Document

- Project budget and expenditure tracking

- Project proposal

- Partner reports

- Monitoring report

- Project progress report to Donor

- Project workplan

- UNEG Norms and Standards for Evaluation

- UN Women Global Evaluation Reports Assessment and Analysis System (GERAAS)

- UN Women Evaluation Handbook: How to manage gender-responsive evaluation.

- UN Women Pocket Tool for Managing Evaluation during the COVID-19 Pandemic

Key Informant Interviews: The evaluation team conducted key informant interviews (KIIs) with key stakeholders, including community members of the LEAP project in Southwest, Puntland, Banadir and Jubaland, implementation partners (NAPAD and SWDC), UN Women staff Somalia office, ministries of women and Ministries of Health (Federal and State Level). A total of 17 KIIs were conducted (10 male and 7 female).  Informants were knowledgeable about this project and were purposively sampled by the project implementing partners.

| KII Sample |  |
| --- | --- |
| Informant Type | Number |
| UN Women staff (Somalia) | 1 |
| NAPAD Project staff | 4 |
| SWDC Project staff | 4 |
| Government Officials | 3 |
| Community Members targeted in awareness raising sessions | 5 |
| Total | 17 |

Focus Group Discussions: FGDs were conducted with key project stakeholders at community level. These FGDs explored the impact of the project and achievement of project activities based on key project outputs, as well as gather feedback on the project’s approach and activities to inform key lessons learned. Each FGD comprised of 8 participants sampled purposively to ensure a variety of participants according to their gender, age groups and activities in which they participated. A total of 8 FGDs were conducted and each FGD consisted of 8 participants (64 females in total).

| FGD Sample |  |  |
| --- | --- | --- |
| Participant Type |  | Number of FGDs |
| Women leaders trained to enhance leadership, equal representation of women in decision-making and how-to refer cases to formal justice system in all target project areas |  | 2 |
| Women Provided with material assistance (dignity kits) |  | 2 |
| Participants on Community conversations / dialogues led by community opinion leaders |  | 2 |
| Trainees on training of trainers (ToT) workshops on GBV prevention and response using IASC GBV in emergency guidelines |  | 2 |
| Total |  | 8 |

### Data analysis

Content analysis was used to analyse data collected for this evaluation. In this regard, data was recorded, transcribed and coded to identify recurrent themes from opinions and experiences expressed during the KIIs and FDGs. Data analysis entailed making notes of the transcripts, categorizing contents and linking categories to summarize findings into themes. This information was used and interpreted in view of the evaluation objectives to make a conclusion about whether the intervention achieved its intended results, documented lessons learned, best practices and made recommendations.

## Limitations

Prior to the data collection phase in the field, a certain number of risks and limitations had been identified as potentially hindering a smooth evaluation process. In a nutshell, these comprised insecurity or a spike of the Covid-19 pandemic, difficulties in reaching out to targeted IDPs or respondent information bias, or difficulties in accessing baseline reporting data. Thereafter, however, some unforeseen internal delays cropped up in the organization of the field trips for data collection and mobilization of FGD participants that slightly lagged the timeline for the submission of all the deliverables. Finally, the field visits took place as of June without major restrictions in terms of the quantity and quality of interviews carried out in the field.

Chiefly to be mentioned among the limiting factors is the absence of baseline data for objective and outcome 3 indicators which could have been used as benchmark to compare with the endline data. Such comparison could have helped evaluate the results the project may have triggered in the target communities.

## Quality Assurance, Ethical Considerations, Gender and Human Rights in the Evaluation Process

Quality assurance measures included systematic cross-checking and triangulation of data. Gender and human rights concerns were covered by a specific sub-set of questions specifically geared towards these dimensions. Moreover, the vast majority of informants were female, especially at the field level. LNOB concerns were not only covered through related questions as part of the aforementioned module of specific questions, but related concerns were also reflected in the selection of the informants.

In general, the evaluation adhered to a specific set of ethical obligations and rules of conduct during interviews and FGD facilitation, and the interaction with beneficiaries throughout data collection, data management, storage and usage. Strategies deployed to protect the informants included the following:

- Participation was based on informed consent which entailed providing the participants with information about the evaluation and its approach and their (anonymous) role in the assessment.

- During the preparatory phase, data collection tools were tested on a group of participants who were informed about the purpose of the process, asked whether they would be willing to voluntarily participate and given the possibility to opt out, prior to the actual testing.

- During actual data collection, the participants were assured of the confidentiality of all data collected from them and further that the data would be used exclusively for the research process. The principle of anonymity was also clearly stated in the introductory section of all tools and was clearly read to the participants prior to interviews and/or FGDs.

- The interactions between the interviewers and the participants as well as among the participants themselves were governed by mutual respect and trust.

- Safeguards to ensure confidentiality during data processing and reporting included refraining from attributing specific statements to particular participants. Special care was taken so as to prevent that any specific information gathered from KIIs or FGDs could be traced back to specific individuals.

# Findings of the Evaluation

## Relevance

### Relevance to the Needs of Beneficiaries

Finding 1: Hygiene promoters from the community increased ownership of the project

The LEAP project was crucial for those who had been displaced by conflict and drought in urban areas, particularly in Baidoa, Kismayo, Banadir, and Garowe. It was also timely because some residents had forgotten about COVID-19's effects on women and other communities who were most at risk and the lack of prevention efforts, while others thought COVID-19 was over and didn't exist anymore. Therefore, it is necessary to consistently address the detrimental effects of COVID-19 on the Somali community through community discourse, awareness-raising, and capacity development.

The initiative addressed the needs of communities at risk from COVID-19 and gender-based crimes including rape and FGM, which have escalated as a result of the epidemic, according to informants and FGD participants. Additionally, the initiative supported the target communities to understand good sanitation practices that help prevent the spread of the pandemic. It was observed that Internally Displaced Persons have not received such important awareness-raising sessions before and according to them, the COVID-19 awareness-raising sessions were concentrated in the urban/town centres and major hospitals.

The project was also carried out by involving the community in focus group discussions, community dialogue sessions, and community-based training. As a result, the community shared with us some of the key issues, such as domestic problems that made it simpler for them to get to the key locations for health services in the community and unrestricted access to justice at all times, without any doubt or hesitation.

Yes, it was appropriate, because the communities are at risk of COVID-19 and gender-related violations like rape and FGM. And the women face difficulties in access to legal services. This project addressed existing needs but wasn’t enough to achieve more impact due to the short period. Community member from Baidoa

The Ministries of Health and Women and the displaced people were among the project's stakeholders who benefited from LEAP project. The two ministries were informed about the project and were engaged throughout the project’s life cycle. The most susceptible communities—those affected by GBV and COVID-19—were involved and made aware of the project before it began.

Community hygiene promoters were also chosen from the villages where the initiative was executed, and Village Relief Committees (VRCs), community leaders, and the Ministry of Health (MOH) were also consulted throughout.

All project activities, such as awareness campaigns, community discussions, and training sessions on women's empowerment and COVID-19, benefitted IDP women. As a consequence, this effort addressed the needs of female IDPs in the villages of Baidoa, Banadir, Kismayo, and Garowe in relation to their degree of knowledge of hazardous cultural practices and the impending pandemic.

Figure 1: Women with Dignity Kits

Besides, the project helped the communities' mostly female residents assert their rights to justice and pandemic prevention measures, such as sanitation, and enabled them to play crucial roles in the existing community structure after capacity building and awareness sessions on COVID-19 and women's empowerment. In the FGD participants, 70 percent of the respondents confirmed that the project activities were relevant to their needs. See figure 2.

Finding 2: Communities have increased awareness on COVID-19

Figure 2: Relevance of project activities

People have always dreaded the COVID-19 vaccination because it is odd, and IDPs and newly displaced people are less aware of how the pandemic has affected their social, economic, cultural, and other societal phenomena including the family economics, women's empowerment, and cultural norms in Somalia.

Through education, public awareness, community dialogue, and the supply of PPE tools, the initiative gave women's ability to deal with the detrimental effects of COVID-19. Indirect beneficiaries received sessions on pandemic awareness and hazardous cultural habits. The community members were educated to reject harmful cultural practices after training and awareness-raising. Aside from that, the initiative hired and trained female community mobilizers.

The COVID-19 epidemic has made it more difficult for women to assert and use their rights. However, because the capacity-building program was only meant to help women, it would have been important to include men as well in order to safeguard women's rights as men and people of all genders need to stand in solidarity with women to create a bold, visible and united force for gender equality. The dignity kits provided to women is a significant example of respecting their rights.

Additionally, those activities helped the target communities comprehend the importance of hygiene and sanitation while referral systems were also in place to support the most vulnerable individuals to victims of harmful cultural practices including GBV. However, the IDPs live in crowded settlements and are unable to adhere to COVID-19 protocols like distancing.

In terms of the relevance of the project to addressing gender inequalities, interview data showed that the beneficiaries as well as institutional stakeholders were of the opinion that the project has contributed to gender equality. Empowering women through leadership training and increased level of awareness on the harmful cultural practices is expected to help them acquire the capacity to advocate for women’s rights.

“Most of the interventions in the project were of vital social support in tackling COVID-19 pandemic in the society. In absence of LEAP project, more vulnerable communities could have been impacted by the pandemic particularly women and children be at higher risk with the increased gaps of inequalities from the loss of livelihoods. Therefore, the project helped the society develop empathy, caring skills, communication and more other attributes necessary to build a strong community” Community Member in Mogadishu

The effort pushed individuals to get COVID-19 vaccines, and people started to take them readily. They also started to avoid going into crowded locations while keeping social distances. According to the community, they were in the midst of COVID-19. People at the local level began to practice better cleanliness, and community mobilization and awareness efforts were effective at both the local and federal levels.

### Relevance of the Partnerships and Coordination

Finding 3: Community engagement/consultation was strong.

The choice of the implementing partners was based on the presence at grassroot level in responding to the pandemic. Civil Society Organizations (CSOs), and especially Women-led organizations (WLOs) are the frontline responders in the humanitarian crisis, leading efforts to deliver essential and lifesaving support to crisis-affected women and girls. The project partnered with two capable CSOs; Somali Women's Development Centre (SWDC), and Nomadic Assistance for Peace and Development (NAPAD) in response to COVID-19 pandemic. These two organizations are known for promoting women's empowerment and leadership.

NAPAD as a partner was responsible for the implementation of Output 1.2 (Women and girls at risk of COVID-19, access and benefit from relevant prevention and mitigation measures) while SWDC implemented Outcome 3 (Improved leadership of women and girls in COVID-19 interventions). Both partners bring distinct advantage in being able to reach marginalized and vulnerable women and girls living in IDP camps and host communities. It was observed that, WLOs have better understanding of streamlining gender sensitive and responsive approaches.

The project worked with the ministries of Health as well as Women and Human Right Development (at Federal and State levels) by creating a partnership with these relevant stakeholders that facilitated the proper implementation of the project. The close collaboration with the government at the regional and federal levels improved ownership. The IPs consulted the two ministries when designing the project through daily field visits.

The strong community engagement/consultations facilitated the improvement of the collaboration between the communities and the organization and effective coordination and information sharing. The other key contribution of the community as a stakeholder included promoting the inclusion of often marginalized populations, such as women, youth, persons with disabilities, the elderly, and religious or ethnic minorities, decision-makers because they are truly aware of local needs and have local support.

Having made an inception meeting with the government, CSOs, and community partners created reflection and a forum for learning and feedback. Partnering with IPs and community engagement also increased generating local solutions to the project (COVID-19 and GBV prevention).

As a public health issue requiring a multisectoral strategy and sustained involvement, GBV and the pandemic are ideally positioned to be addressed by grassroots women's groups and other CSOs. In order to promote transformational social change, they have the contextual understanding of their communities and, with the proper competence, can link humanitarian aid with development activities. However, these groups still struggle with structural issues that restrict their ability to play a full part in society. Localizing GBV solutions will foster the agency and ownership of these solutions that are sorely lacking and provide accountability for them in the communities where they were born. Additionally, it will guarantee the type of dependable income that will allow women-led groups the adaptability to respond to necessities and customize solutions that support more extensive social change.

In order to guarantee that the project's engagement was efficiently organized and managed at all levels, all project stakeholders—including communities impacted by displacement, federal and state authorities, LEAP implementing partners, UN-women, and SWDC—worked together.  Despite a few roadblocks that prevented the project from being well-coordinated and coherent for example, Puntland's state-level coordinator was replaced after the project's engagement, necessitating a resumption of the engagement process with the newly appointed coordinator, the project was finished as planned. Additionally, the IDPs live in crowded settlements and are unable to adhere to COVID-19 protocols like distance and there were inadequate referral channels and IDPs were instructed to travel to MADINA hospital.

Table 3: Partners and their activities

| Partner | Activities participated | Status of completion |
| --- | --- | --- |
| NAPAD | Conduct community mobilization and inception meetings in Kismayo, Garowe, Baidoa and Mogadishu | Completed |
|  | In partnership with the Ministry of Health, develop COVID IPC-vaccination promotion and GBV prevention messages that will be disseminated to educate and empower at-risk persons, surrounding businesses and localities through the printing of 700 pamphlets and 50 posters, through 37 social media promotions and 1 radio spots | Completed |
|  | Facilitate 60 community hygiene promoters to conduct door-to-door community hygiene promotion with a focus on COVID-19 Vaccine and PCR testing uptake, COVID prevention information and community led prevention and identification of, and response to SGBV in households. | Completed |
|  | Conduct project monitoring in partnership with relevant stakeholders, document change stories | Completed |
| SWDC | Strengthen the capacity of 300 women in Mogadishu, Kismayo, Baidoa, and Garowe on participation, decision making in COVID-19 preparedness planning, response and recovery. | Completed |
|  | Conduct training of trainers (ToT) workshops on GBV prevention and response using IASC GBV in emergency guidelines for 300 women and girls from key stakeholders involved in COVID-19 response in target locations. | Completed |
|  | Partner with community-based radios, women and youth organizations, religious and community leaders to create awareness, share information on the prevention and management of COVID-19 to 10,000 men and women. | Completed |
|  | Community conversations / dialogues led by community opinion leaders. | Completed |
|  | Development & printing of GBV pocket guidelines for key community stakeholders | Completed |
|  | Provision of material assistance (dignity kits) | Completed |
|  | Conduct trainings for women leaders to enhance leadership, equal representation of women in decision-making and how-to refer cases to formal justice system in all target project areas | Completed |
| Ministry of Women and Human Right Development and Ministry of Health | Monitoring and oversight role | N/A |
| UN Women | Recruited two consultants (one international and one national) to conduct study to assess, monitor and map out Gender mainstreaming gaps and opportunities in COVID-19 Preparedness and Response Plans in Mogadishu, Jubaland, Southwest and Puntland states in Somalia. Distributed PPEs to 200 women | Completed |

### Relevance of the Project Design

Finding 4: No health treatments connected to COVID-19 were offered to the community.

The project conception and design were appropriate and relevant to UN Women’s mandate to contribute to women’s engagement in humanitarian, peace, and security efforts in target locations in alignment with international commitments and standards as well as national policies, strategies and frameworks for humanitarian response and gender equality.

The LEAP 2022 project contributes to the UN Women Somalia Strategic Note which supports Women's Leadership, Empowerment, Access & Protection in Crisis Response (LEAP) program approaches to address multiple humanitarian crisis due to recurrent droughts, armed conflicts, floods, and COVID-19 on women’s livelihoods. This project leveraged implementation and continuity of the LEAP 1 pilot project in Somalia contributing to SDG 5; ‘Achieve gender equality and empower all women and girls’ and SDG 8; ‘Promote sustained, inclusive and sustainable economic growth, full productive employment and decent work for all.

Additionally, LEAP Project is explicitly aligned to the UN Women’s Response plan to mitigate the impact of the COVID-19 crisis on women and girls and to ensure that the long-term recovery benefits them, focused on five priorities:

- Gender-based violence, including domestic violence, is mitigated and reduced.

- Social protection and economic stimulus packages serve women and girls.

- People support and practise equal sharing of care work.

- Women and girls lead and participate in COVID-19 response planning and decision-making.

- Data and coordination mechanisms include gender perspectives.

The project is also aligned to WHO strategic preparedness and response plan (SPRP) designed to guide countries in the transition from COVID-19 pandemic emergence phase to sustainable comprehensive management of the pandemic. The strategic plan has five components: collaborative surveillance, community protection, safe and scalable care, access to countermeasures and emergency coordination.

The project is closely aligned with the Somalia National Development Plan 9, 2020-2024 (NDP); the 2030 Agenda for Sustainable Development, UN Sustainable Development Cooperation Framework 2021- 2025 (UNSCF), which represent the commitment of the Federal Government of Somalia and the United Nations to partner in achieving peace, stability, and prosperity for all Somalis The UNSCF four overarching strategic priorities are: 1) Inclusive Politics and Reconciliation, 2) Security and Rule of Law, 3) Economic Development, and 4) Social Development. It also supports institutionalization of the triple nexus (humanitarian, development, and peace) interlinkages through which it will integrate its inclusive peacebuilding, development, and resilience ambitions to help address the chronic vulnerability and structural impediments to sustainable development in Somalia. Lastly, it supports the 2020 Humanitarian Response Plan whose priorities include protection, recovery and resilience and the Recovery and Resilience Framework (RRF)

The project is aligned with TICAD7 priorities -Japan’s contributions for Africa in particular, the Pillars on Society (Achieving Human Security and the SDGs) and Peace and Stability (with focus on addressing the needs and priorities of IDPs and refugees). It is also aligned with the concept of Human Security that advances the nation and community building though skills acquisition for human capital development and protection of individuals. By investing in this project, Japan and UN Women ensured that women and girls in these countries will live in dignity and free from fear due to social problems during the pandemic and its aftermath.

The relevance of the project can be viewed from the perspective of who (from the community) should be engaged. Therefore, the project involved youth, worked with men and boys and adopted community mobilization as a strategy to engage the target community in all the four locations. It is assumed that Violence Against Women/Girls goes reported in IDP settings and part of the project was to create awareness-raising sessions against harmful cultural practices including FGM, and early marriage that increased during the COVID-19 pandemic.

Lastly, the project is aligned with the Ministry of Women’s specific policies related to the eradication of GBV and the promotion of women’s economic and political empowerment as well as those of Ministry of Health to prevent and respond to the pandemic.

Women are not only the hardest hit by this pandemic, they are also the backbone of recovery in communities. Putting women and girls at the centre of economies will fundamentally drive better and more sustainable development outcomes for all, support a more rapid recovery, and place the world back on a footing to achieve the Sustainable Development Goals.

The situation of displaced women and girls in Somalia is made worse by the rise in gender-based violence. The COVID-19 epidemic made the situation worse. In the last quarter of 2022, 73% of GBV incidences were reported by displaced people; 19% of survivors came from the host populations; and 3% came from refugees, mostly from Ethiopia.

The COVID-19 pandemic-related limitations enforced by the Federal Government of Somalia, together with ongoing intercommunal and violent conflicts and natural calamities including droughts and floods, made things worse for the IDPs. An increase in sexual assault, intimate partner violence, and female genital mutilation among children, teenage girls, and women is linked to isolation, loss of livelihoods owing to business closures, interruptions in school calendars, and restrictions on transportation. These factors all affected the situation for women and girls and made it more difficult for them to get assistance.

The coronavirus pandemic poses a significant risk to public health and security, and its effects on gender equality are clear. A greater burden of unpaid care work, a higher risk of GBV/Intimate Partner Violence (IPV), restrictions on access to justice and legal systems, and severely diminished livelihoods and gross economic vulnerability are all issues that affect women, girls, and other marginalized groups like IDP communities.

Key informants and FGD participants testified that no health treatments for COVID-19 were offered to communities except than educating people about the use of masks, gloves, good handwashing methods, and social distancing. According to women IDPs, the living conditions in this IDP community prevent the implementation of these protocols. Instead, if someone is suspected of having the coronavirus, they are treated with traditional medicines like black seeds, ginger, and lemon with warm water and honey.

The evaluation's findings show that COVID-19 awareness raising was widespread; all informants and FGD participants reported having heard of the virus, and the majority had heard about it on the radio, in community awareness events, or over the phone from telecommunications companies.

All of the community people who were questioned also spoke about how the crisis has affected their livelihoods, and when asked if COVID-19 carriers experience stigma, they all said yes. The majority of respondents claimed that because of obligations to their families, their jobs, and their towns' lack of health resources, women with COVID-19 would not be able to isolate themselves.

All the duty bearers (Government officials and IPs) who addressed protection and GBV emphasized the unique needs and vulnerabilities of IDP groups, as well as women and girls in particular. Due to poor living circumstances, a lack of security in the IDP camps, and insufficient clan protection, officials who were questioned stated that IDPs are particularly vulnerable to GBV and sexual exploitation.

Finding 5: IDPs are at risk with GBV that exacerbated by lack of basic services.

IDPs and families in host communities continue to lack sources of support and income-generating activities, and poor housing puts women and girls at greater danger. In addition, the absence of police, poor illumination, and a rise in homes with only women make IDP settlements a breeding ground for gender-based violence. The prevalence of gender-based violence, including rape, physical assault, violence against women, sexual exploitation, and abuse, is frighteningly high, particularly among internally displaced people. This happens in a setting where women are severely underrepresented in traditional judicial systems and lack access to formal justice systems. Numerous governmental and INGOs organizations have planned community awareness campaigns and staff training on these topics. Local NGOs also employed religious authorities as role models and carried out initiatives aimed at modifying societal norms. These initiatives ought to be developed further.

Innovative strategies must be used in order to lessen the effect that COVID-19 limitations have on the survivors. In order to increase community protection, GBV service provision has to be given top priority in terms of finance and protective gear provision.

## Coherence

Finding 6: Provision of water and construction of latrines (by other agencies) helped compliment the awareness raising sessions at the community level.

LEAP 2 project is coherent with other humanitarian and government interventions to curb the spread of COVID-19 in the country. This project was purely on awareness raising and other agencies helped provide complimentary activities like the construction of latrines and provision of water. Besides, SWDC with support from Equal Access to Justice (EAJ) supported victims of GBV by providing legal services (freely) and this has synergised with LEAP project as SWDC was an implementing partner with UN Women on LEAP 2 project.

Additionally, the project is coherent with the Ministry of Women’s specific policies related to the eradication of GBV and the promotion of women’s economic and political empowerment as well as those of Ministry of Health to prevent and respond to the pandemic. This alignment ensured that the project addresses the synergies and interlinkages between the intervention and other interventions carried out by other institution or the government, as well as the consistency of the intervention with the relevant international norms and standards.

Moreso, the coherence in the project considered the consistency of the intervention with other actors in the same field and in the same context for complementarity, harmonisation and coordination purposes with others, and ensure the project is adding value while avoiding duplication of efforts.

## Effectiveness

### Achievement of Objectives

The LEAP project’s overall goal was to strengthen the protection, leadership and empowerment of over 15,760 vulnerable women, men and youth affected by COVID-19 in IDP camps of Somalia.

Objective indicators:

- Number of community members (vulnerable women, men and youth affected by COVID-19 and forcibly displaced into IDP and refugee camps) participating in project’s protection, leadership and empowerment activities (Target: 9,400)

- Proportion of community members (vulnerable women, men and youth affected by COVID-19 and forcibly displaced into IDP and refugee camps) reporting improved perception of protection, leadership and empowerment.

In assessing the performance of the project in Somalia, according to the progress report, a total of 14,055 direct beneficiaries were reached which means the project attained 150% of the end project target. However, the project indirectly reached many community members through social media and radio programs. Besides, a total of 951, 862 community members (475,931 Twitter, Facebook/Instagram 475,931) were reached through social media while 10,000 were reached through awareness-raising sessions. This signifies that in Somalia, the goal of the project has been overachieved and women and girls have gained lasting leadership capacities, and are able to participate in decision-making, and; communities have changed behaviour regarding COVID-19 prevention; and vulnerable women and girls have been protected from sexual and gender-based violence as per project’s contribution efforts.

Finding 7: Complimentary activities of awareness raising, and the availability of justice system improved the perception of the community.

According to 76 percent of the beneficiaries of that participated in project activities, the project has improved their perception, leadership and empowerment in relation to the pandemic. The participants were drawn from participants in the following activities:

- Women leaders trained to enhance leadership, equal representation of women in decision-making and how-to refer cases to formal justice system in all target project areas.

- Women Provided with material assistance (dignity kits)

- Participants on Community conversations / dialogues led by community opinion leaders.

Figure 3: perception of improved protection, leadership and empowerment.

Trainees on training of trainers (ToT) workshops on GBV prevention and response using IASC GBV in emergency guidelines.

When probed to give examples of how the project contributed to improve women’s leadership, protection and empowerment, they mentioned that the initiative promoted social inclusion for women and made it possible for them to take part in events like community gatherings, mediation procedures, and meetings for resolving disputes. According to them, women are no longer referred to as the kitchen object, but rather as whole beings with dignity. They are seen as significant individuals rather than as sex objects. Because community elders, government representatives, and NGOs are in a position to hear women's cries and provide them with the necessary support, the project encouraged women to speak up and be heard.

The project's activities, according to FGD participants, made it simpler for people to get to community health care hubs and seek justice without reservation or reluctance at all times. More importantly, following the engagement, the community members who were targeted began encouraging other community members to become involved and start spreading health awareness messages. After realizing the significance of the health messages, everyone in the community worked together to eradicate the terrible illnesses COVID-19 via cleanliness. All female leaders took part completely and equitably in the health awareness campaign, and they were all well-versed in the skills required at the local level.

The initiative was crucial in influencing the community's attitudes and behaviours regarding COVID-19 and its protocol, which helped the community comprehend the issues brought on by COVID-19 and how they might be avoided.

### Achievement of Outcomes and Outputs

The informants have not mentioned any unintended outcomes, whether positive or negative. According to documents reviewed and the responses from the interviews, all project outputs and outcomes were achieved with UN Women contribution, however, there were no baseline values for outcome 3 indicator which could be used for comparison purpose. Progress made per each indicator is shown below.

Table 4: achievement of indicators

| Result level | Indicator | Baseline | End of Project Target | Actual Performance to date | % of End of Project Target achieved | Reasons for deviation +/-10% of the expected Performance |
| --- | --- | --- | --- | --- | --- | --- |
| Goal: To strengthen the protection, leadership and empowerment of over 15,760 vulnerable women, men and youth affected by COVID- 19 in IDP and refugee camp of Uganda and Somalia. | Proportion of community members reporting improved perception of protection, leadership and empowerment | Not collected | Not established | 76% | 76% | N/A |
|  | Number of community members (vulnerable women, men and youth affected by COVID-19 and forcibly displaced into IDP and refugee camps) participating in project’s protection, leadership and empowerment activities | 0 | 9400 | 14,055 (Female=7,575 Male=6,480) | 150% | There being new influx into the IDP setting due to the recurring drought and the fight with Alshabab, the project reached more than expected. |
| Outcome 1: Vulnerable women, men and youth lead and participate in COVID-19 prevention, response and recovery interventions in Uganda and Somalia | Number of vulnerable women, men and youth leading and participating in COVID-19 prevention, response and recovery interventions | 0 | 8,800 | 13,480 (Female=7000 Male=6480) | 153% | The community hygiene promoters used to work six days a week, the reason for the extensive outreach is that the IDPs targeted were densely populated and overcrowded, each hygiene promoter was required to reach at least 20 households each day. |
| Output 1.2: Women and girls at risk of COVID-19, access and benefit from relevant prevention and mitigation measures targeting 8,800 women and girls in Somalia | Number of women reached through awareness raising and education on COVID-19 prevention and mitigation in the IDP settings in Mogadishu, Kismayo, Baidoa and Garowe. | 400 | 6,000 | 6,560 | 110% |  |
|  | Number of women benefiting from COVID-19 mitigation and prevention tools | 400 | 2,800 | 2,800 | 100% |  |
| OUTCOME 3: Improved leadership of 600 women and girls in COVID-19 prevention, response and recovery interventions in Somalia | Proportion women and girls in COVID-19 prevention, response and recovery interventions in Somalia reporting adequate leadership skills in COVID-19 response | Not collected | Not established | 70% | 70% | N/A |
| Output 3.1: Women and girls at risk of COVID -19 infection in target locations have improved access to information, capacities and knowledge to lead and participate in decision making and coordination mechanisms | Number women and girls provided with leadership skills in COVID-19 prevention, response and recovery interventions in Somalia | 0 | 600 | 575 | 96% |  |
|  | Number of men, women and girls reached indirectly with COVID-19 information | 0 | 10,000 | 10,000 (Female=6,500 Male=3,500) | 100% |  |
|  | Number of women whose capacity on participation, and decision making in COVID-19 preparedness planning, response and recovery has been strengthened in Mogadishu, Kismayo, Baidoa and Garowe. | 0 | 300 | 358 | 119% | Capacity-building on participation and decision-making in COVID-19 preparedness, planning, response and recovery was 300 females, 75 in each location. However, due to added funds to activity derived from Sept salaries, the total number of participants increased from 300 to 358. In Kismayo and Mogadishu, 75 individuals participated in each region. In Baidoa and Garowe, 104 women and girls participated |
|  | Number women and girls trained as trainers (ToT) on GBV prevention and response using IASC GBV in emergency guidelines (women and girls drawn from key stakeholders involved in COVID-19 response in target locations) | 0 | 300 | 300 | 100% |  |

Under Outcome 1, the LEAP 2 initiative exceeded its end-of-project target by 53% by reaching 13,480 women and girls who were able to access and benefit from pandemic preventive and mitigation measures. The greater success may have been caused by the fact that the community hygiene promoters worked six days a week and conducted considerable outreach in the targeted IDP communities, which were packed and densely inhabited. Each hygiene promoter was obliged to contact at least 20 houses each day, which may have contributed to the higher achievement.

Kismayo, CHPs using posters in schools to raise GBV awareness.

According to the last progress report, as of the project's conclusion, 6,560 women have been reached through awareness-raising and educational efforts, or 110% of the target, and develop COVID IPC vaccination promotion and GBV prevention messages in collaboration with the Ministry of Health. These messages were then disseminated to inform and empower at-risk individuals, nearby businesses, and communities through the printing of 700 pamphlets and 50 posters, through 37 social media promotions in each location, and through one radio spots per location.

According to UN Women, in an effort to provide COVID-19 preventive and mitigation strategies for women IDPs in Mogadishu, Kismayo, Baidoa, and Garowe, the organization delivered 2,800 Rapid PCR test kits and 2,000 aprons.

Partners confirmed that in all the target locations, the initiative organized community mobilization and initiation sessions where women activists, civil society groups, and government line ministries from the federal and state levels were present. All of the prospective stockholders agreed to work together to promote mitigation strategies for COVID-19, support implementing partners in gaining access to the target community and assist communities in understanding the risks and preventative measures associated with the disease.

As articulated by the partners, the LEAP initiative hired 60 [33 Female, 27 Male] community-based hygiene promoters on COVID-19 and GBV prevention and response to guarantee that PCR testing and vaccination sites in refugee and IDP camps are secure, and that women and girls are safeguarded from sexual assault. The promoters were chosen from Mogadishu (20), Kismayo (15), Baidoa (15), and Garowe (10), and they underwent a three-day training on COVID-19 prevention approaches and GBV prevention promotion. They were also given protective gear, such as gloves and face masks, sanitizers, and soaps, to help them with their community outreach efforts.

In accordance with outcome 3, the LEAP project enhanced the leadership skills of 96% of the targeted women and girls to lead and participate in COVID-19 prevention, response, and recovery interventions in Somalia. This means that they now have better access to information and the skills necessary to lead and take part in decision-making and coordination mechanisms. These women took part in community conversation sessions, leadership training, and training to improve capacity.

According to 70 percent of the FGD participants, the project helped them acquire adequate leadership skills in the responsive against COVID-19 pandemic. Women in Somalia are agents of change and usually bear the brunt of the adverse effects of the pandemic.

Additionally, the target community members now have more knowledge about and the capacity to participate in COVID-19 preparation planning, recovery, and reaction thanks to the strengthening of 358 women and girls' capacity for participation and decision-making in the target areas.

Figure 4: Perception on leadership skills

300 women and girls from important stakeholders engaged in the COVID-19 response in the target locations attended two training of trainers (ToT) workshops on GBV prevention and response using IASC GBV in emergency guidelines. The event gave the women present the chance to engage in frank discussion about the many types of GBV, the challenges faced by women and girls living in IDP communities, and the assistance available for survivors. These ladies subsequently fulfilled their obligation to inform others in their communities about these concerns.

Concerning COVID-19's effects in Somalia, several participants noted that as a result of less work and income-generating options, women and girls are now more likely to be subjected to GBV, such as early and forced marriage and female genital mutilation (FGM). Therefore, CSOs, women activists, and WLOs continue to remain at the forefront of COVID-19 and other emergencies while continuing to campaign for and work towards gender equality, despite the detrimental and severe repercussions of COVID-19 on women and girls.

Women in Mogadishu reading the GBV pocket guide.

Additionally, SWDC confirmed that the project created a GBV pocket guideline to better enlighten about GBV and its forms. This guideline was printed and given to 556 beneficiaries (139 in each project location). Women and girls who work in the fields, reside in safe houses, go to hospitals, and attend school are among those who benefit. Numerous stakeholders will get samples of these pocket guides, giving many more women who visit or attend those locations the chance to read them.

In order to educate 10,000 men and women about COVID-19 prevention and management, the initiative teamed with community-based radios, women's and youth groups, religious and community leaders. The combined messaging and awareness-raising sessions helped:

- Promote awareness raising on good prevention practices against COVID-19, disseminating knowledge on the prevention and management of COVID-19

- Production of 10,000 Somali-translated IEC materials, including stickers with safe messages on the prevention of COVID-19 guidelines/prevention, referral pathways, and available services. In addition to weekly door-to-door outreach efforts and peer-to-peer sessions, the IEC materials were delivered to community-based field workers to support awareness-raising sessions in schools, health care facilities, community centres, women's and girls' spaces, and spaces for children and families.

In order to ensure successful COVID-19 prevention, the project evaluated COVID-19 readiness and response plans to determine how gender is being mainstreamed, gaps, and possibilities to increase the integration of gender. In order to address the effects of COVID-19, GBV problems, and boosting community involvement, the initiative hosted sessions/conversations/dialogues with community opinion leaders, camp leaders, religious leaders, women activists, youth representatives, and women's rights groups.

To promote women and girls' psychosocial, and physical well-being, promoting mobility and safety of vulnerable and marginalized women and girls in IDP camps, a total of 335 females (Mogadishu: 150; Baidoa: 85; Kismayo: 50; Garowe: 50) received a dignity kit consisting of 2 dirac (Somali women dress), 1 veil or Hijab, 2 turbans, 2 underwear, 2 pants and 1 bag of soap. The beneficiaries attended courses to raise awareness of COVID-19 and the associated mitigation and preventative strategies.

A different group of community women got training in improving their capacities and improved knowledge of the importance of creating a system that includes equitable representation of women in decision-making processes as well as how to submit instances to formal legal systems with reference to the epidemic. These ladies provided guidance on how to lead oneself, which is more vital than guiding others in building a decent society.

Door-door awareness in Kismayo IDPs

According to the people interviewed, the project has conducted extensive community awareness-raising sessions in all the project locations. Part of community sessions included staff members paying visits to households and community members, to create awareness of how they can protect themselves against COVID-19. When the vaccine was first introduced, many Somalis refused to get vaccinated as many feared its potential harm due to false information circulating in their private circles.  Many in the community were afraid of the side effects of the vaccine, however, LEAP project assured target communities that vaccines are safe. By communicating with people and providing reliable resources on COVID-19, its risks, and prevention, those in the community became more open and willing to protect themselves.

Finding 8: Behavioural Change was reported (Washing hands regularly, have become an integral part of people’s daily routines).

As a result of the community awareness sessions, people in target communities have made use of a variety of means to prevent infection. Preventative hygiene measures, such as washing hands regularly, have become an integral part of people’s daily routines. A sense of awareness has reached most Somalis in a way that has enabled them to proactively protect themselves against the infection and support each other in doing so, as a community.

Radio, flyers, and door-to-door awareness campaigns were used to spread COVID-19 awareness among the project's target beneficiaries. Women's empowerment was accomplished through community conversation facilitation, awareness campaigns, and capacity-building training. Following the project's conclusion, the communities continued their COVID-19 and GBV volunteer awareness programs and saw an increase in the number of GBV cases being referred. Female project recipients were given the opportunity to assert and exercise their rights.

The initiative was crucial to some degree of behavioural change with regard to GBV and COVID-19, as evidenced by the communities affected by displacement's continuing knowledge of COVID-19 and gender equality after the project's conclusion. Today, some of the most vulnerable populations may assert and use their rights. Additionally, there are more referral cases now.

Some social norms and attitudes-related impediments have been addressed by the initiative. For instance, it is not considered culturally acceptable to discuss openly gender-related issues or COVID-19-related gender violence. The public finally embraced information about COVID-19 and women's empowerment after additional education. Furthermore, the community initially had no prior knowledge of Covid19 and FGM, but after receiving thorough workshops and trainings on the prevention of Covid19, they became aware of the dangerous and deadly diseases. As a result, the community changed its way of life and addressed the diseases by being given face masks, hand sanitizer, and advice to keep away from one another while maintaining social distance.

Table 5: Perception on different thematic areas

| Perception Area | Strongly agree | Agree | Neutral | Disagree | Strongly disagree | Total |
| --- | --- | --- | --- | --- | --- | --- |
| The assistance I received improved my well-being | 36% | 54% | 0% | 8% | 2% | 100% |
| As a result of the project activities women have the capacity to participate in decision-making platforms in the society | 25% | 36% | 3% | 16% | 20% | 100% |
| I have a clear knowledge of the prevention of COVID-19 | 44% | 45% | 8% | 2% | 2% | 100% |
| The project helped me know how to report GBV cases | 34% | 53% | 3% | 9% | 0% | 100% |

Finding 9: Women participate in community committees and decision-making platforms.

In terms of decision-making, 61 percent of the FGD participants confirmed that as a result of the project activities women have the capacity to participate in decision-making platforms in the society while 99 percent showed that they have a clear knowledge of the prevention of COVID-19. Besides, 87 percent of the women confirmed that the project helped them know how to report GBV cases whereas 90 percent said that the assistance improved their well-being.

In addition to meeting community members at the IDP centres where they gather and talk about the current issues with GBV and COVID-19, partners were present at the settlement, made field visits every morning, and distributed Hotline numbers to the target groups.

This project was very short, and its duration was only four months; such a short time can contribute less according to long term, such as recovery. If long-term contribution is needed, the project duration should be extended.

Community Member (Mogadishu)

According to Deeqa from SWDC, the project was able to deliver the targeted results thanks to door-to-door community awareness campaigns, radio awareness campaigns, community dialogues, the creation and distribution of the GBV bucket guidebook, and capacity building for the communities affected by the relocation. For instance, after awareness campaigns and capacity building, the number of GBV cases recorded rose. Following the awareness and capacity building, the communities bravely reported additional incidents. And the number of vaccinations received has grown, and some neighbourhood attitudes have improved.

Improvements in attitude were observed both before and after the initiative; IDP began receiving vaccinations on a voluntary basis, and women are now able to take part in meetings for making decisions and asserting their rights.

One indication that the project had a major influence on GBV and COVID-19 behaviour modification is the fact that the people impacted by displacement continued to be aware of COVID-19 and gender equality after the initiative had concluded. Some of the most at-risk populations can now assert and exercise their rights.

### Enabling and Hindering Factors to Results

Figure 5: Twitter messaging on vaccine

The experience of IPs and their necessary skills, knowledge and capacities needed to deliver the project was the main contributing factor to successful project implementation. The two implementing partners engaged are women-led and CSO organization that have grassroot presence and have implemented similar projects. Therefore, the choice of partners played a role in the successful implementation of the project. Another enabling factor were the deployment of inclusive approaches which benefited the whole community including women, girls, men, boys, elders, religious leaders, youth and marginalized members of the community (for example PwDs) as well as both IDPs, returned and host community.

Finding 10: Concerted efforts are needed to eradicate cultural harmful practices in the community.

Gender-based violence is a multidimensional problem that finds root in gender inequality, harmful cultural norms, and the abuse of power. Women, however, are not only victims or passive recipients of assistance. Today women across the world are becoming a leading force in disaster risk reduction and emergency response, including health services. Though underrepresented in leadership positions, women make up more than 40 percent of the humanitarian workforce. Their ability to take humanitarian action therefore enables participation by and accountability to crisis affected populations.

When FGD participants were asked how inclusive the LEAP project activities were, 59 percent confirmed that it was either much inclusive while 23 percent said that the project was partially inclusive and targeted majorly women. In a nutshell, the project was inclusive and targeted all the community members.

Figure 6: Project inclusivity

It needed time, flexibility, and adoption for the intervention to result in efficient, well-resourced operations due to widespread adverse effects of the pandemic and the prevalence of violence against women and girls in Somalia. The respondents believe that it will take a few more years for damaging cultural behaviours to dwindle. According to the respondents' opinions, the project did identify the community's problems and requirements, including developing women's leadership skills, gender equality capacity building, and controlling and containing pandemics and illnesses as a group. However, the project's lifetime was too short to have a widely felt impact on the community, yet despite this, the program made a significant contribution and greatly enlightened the community throughout its brief existence. The main purpose of the project was not only to contain and suppress COVID-19 but also to integrate with action against gender inequality which was aimed to enhance the level of awareness of the community on gender equality.

Finding 11: Culture hampers the eradication of harmful cultural practices from the community.

The project was severely hampered by the traditional culture and social customs of Baidoa, Kismayo, Banadir, and Garowe. For instance, Baidoa Radio ceased broadcasting awareness after a religious official had concerns about the COVID-19 and women's emancipation themes and asked the station to stop broadcasting them in his congregation during a Friday prayer. According to the religious leader, this is irrelevant to faith and culture. The awareness is then stopped by Baidoa Radio for fear of repercussions.

Additionally, some of the target audience for the project think gender equality is a Western concept unrelated to Islam. Through community engagement, community-building training, and public awareness campaigns, the project's obstacles were overcome. Traditional and religious leaders, for instance, have been used to address concerns of culture and tradition and to persuade bigger crowds.

Another difficulty was the referral channel, GBV victims and COVID-19 Follow-up cases. Due to security and cultural reasons, the victim is unable to pursue the GBV lawsuit. However, the project helped them safety in the pursuit of their rights.

The GBV pocket guideline was only meant for the literate people, however all the community members regardless of their educational background were reached through awareness raising sessions door to door, radio and trainings.

When the FGD participants were asked how far the project addressed gender equalities, 56 percent said that it has partially addressed while 39 percent confirmed that the project has addressed gender equalities much. This symbolizes that LEAP project made contributions to the efforts meant to address gender equalities in Somalia.

Figure 7: How far LEAP project addressed gender inequalities?

According to the informants, the project helped them acquire how to practise handwashing. Notably, the congestion of the IDP camps and the lack of latrines may further limit the impact of the awareness raising sessions on sanitation and hygiene.

Finding 12: It is important to consider contextual situations that may affect the implementation of the project.

In Somalia, the project experienced start-up delays due to dispute over delayed elections that resulted in political unrest and clashes between government and opposition groups. These conflicts affected the government's activities, hindered field missions to complete partner capacity assessment and selection processes. In addition to COVID-19, there has also been severe drought conditions for women and girls at the IDP camps. Somalia has been experiencing a historic drought following four consecutive failed rainy seasons that are leading to mass displacement, widespread death of livestock and a devastating food crisis that has led to the displacement of many people. The drought was intensified as Somalia faced the risk of a fifth consecutive failed rainy season from October to December 2022 exactly when the LEAP project implementation almost started.

In addition, persistent conflict mostly the ongoing campaign of the clan militias backed by the federal and state government forces, unresolved political tensions, and global supply and price shocks further exacerbated the water and food crises. Most people have settled in major Somali cities and towns which the project targets included as they seek humanitarian assistance. Displaced populations live in congested settlements, where they face poor sanitation and hygiene conditions and are often at risk of eviction by landowners. These factors slowed the project’s implementation. However, there is a need for more support in terms of livelihood and educating the new IDPs on GBV and other harmful cultural practices that are common in their areas of origin.

“The covid-19 project created a platform where women can discuss their own issues and problems including the GBV case, the project improved women’s access to social services, and information on covid19 which improved their health status. More women have adopted good hygiene practices as a result of the information shared about GBV. The project training on human rights has increased women’s access to protection services and developed their ability to seek assistance in order to recover from the shocks resulting from prejudices and violence” FGD participant.

Millions of people's lives, dignity, and futures are in jeopardy due to the severe and pervasive drought catastrophe in Somalia, which is now in its sixth season without rain. The effects on women and girls have been quite negative. Gender-based violence has become more severe as a result of ongoing hostilities, a spiralling economic crisis, migration, and historically rare food and basic shortages. Between January and March, 6.3 million people (IPC Phase 3 and above) were predicted to experience crisis-level or worse food insecurity outcomes, including 322,000 who were predicted to experience catastrophic hunger (IPC Phase 5); meanwhile, 1.2 million women and girls were predicted to suffer from a lack of access to safe housing and sufficient specialized services for GBV.

288,000 individuals were displaced within Somalia in January, the majority of them were due to either violence (79%) or drought (20%). According to data from the Gender-based Violence Information Management System (GBVIMS), there were 5% more recorded rape incidents in February than there were in January 2023. According to the data, there were 6% more recorded occurrences of intimate partner violence in February than there were in January 2023, which was 4%. The most marginalized individuals in Somalia at the moment are women and teenage girls, women from minority clans, women who head homes, and women who have impairments.

### Effectiveness in Partnerships

Findings 13: The project engaged the government that enhanced ownership.

The LEAP project contributed to encouraging stakeholders to collaborate and collectively leverage each other’s expertise for the benefit of women and girls in the target locations. The implementing partners worked closely with the Ministries Women and Human Right Development and Ministry of Health in their outreach activities as the project required a partnership between entities that have experience in the areas of development, recovery, resilience and humanitarian support.

Engagement and coordination with the government was effective throughout the project’s life cycle and according to the officials interviewed, they ensured a role during oversight as well as an in implementation ensuring an appropriate selection of beneficiaries to maximise the reach of the project in catering to the needs of the most vulnerable and underserved members of the community. However, officials from the ministry of women in Jubaland mentioned that coordination with and between the NGOs could be enhanced.

According to an official from MoH, the ministry had a great influence on the implementation of the LEAP project and overall give a great support in designing and developing IEC on posters with key messages in IPC. According to him, the project was working within the national framework and shared with them any implementations that they need to carry out within the selected areas of interventions and gave updates on weekly and monthly basis. Thus, LEAP project made a contribution to other continuing COVID-19 and women's empowerment initiatives, such as education-related programs.

## Efficiency

### Fund Utilization

Finding 14: The fund was utilized efficiently to produce results.

Overall, the LEAP budget allotted a total of 22% for project management costs including staff costs and M&E (Monitoring and reporting and the final evaluation) and visibility/communication. This relatively high percentage can be explained by the high cost of doing business in the context of high insecurity in Somalia. About 71% of the project’s budget went to direct implementation costs. For budget details under each activity, see table 6.

Table 6: Project's expenditure

| Activity Description | Budget USD | % | Actual | % |
| --- | --- | --- | --- | --- |
| National Project Specialist | 54,408.00 | 10% | TBC | TBC |
| M % E and Reporting Specialist | 50,148.00 | 9% | TBC | TBC |
| Monitoring, Evaluation & Travel (3 percent - 5000, 7600) | 12,600.00 | 2% | TBC | TBC |
| Communication & visibility (2 percent) | 8,400.00 | 2% | TBC | TBC |
| 1.2.1: Awareness raising and education on COVID-19 prevention and mitigation for 6,000 women in the IDP settings in Mogadishu, Kismayo, Baidoa and Garowe | 135,000.00 | 24% | 135,000.00 | 24% |
| 1.2.3: Ensure PCR testing and vaccination sites in refugee and IDP camps are safe, and women and girls are protected from sexual violence through awareness raising, effective monitoring and timely support by the government and other stakeholders. | 40,000.00 | 7% | 40,000.00 | 7% |
| Distribution of COVID-19 prevention and mitigation tools; 2,800 Rapid PCR test kits and 2,000 aprons for women IDPs in Mogadishu, Kismayo, Baidoa and Garowe | 120,000.00 | 21% | 120,000.00 | 21% |
| 3.1.1: Strengthen the capacity of 300 women in Mogadishu, Kismayo, Baidoa and Garowe on participation, decision making in COVID-19 preparedness planning, response and recovery | 40,000.00 | 7% | 40,000.00 | 7% |
| 3.1.2: Conduct 2 training of trainers (ToT) workshops on GBV prevention and response using IASC GBV in emergency guidelines for 300 women and girls from key stakeholders involved in COVID-19 response in target locations | 25,000.00 | 4% | 25,000.00 | 4% |
| 3.1.3: Partner with community-based radios, women and youth organizations, religious and community leaders to create awareness, share information on the prevention and management of COVID-19 to 10,000 men and women | 25,000.00 | 4% | 25,000.00 | 4% |
| 3.1.4: Assess COVID-19 preparedness and response plans to identify how gender is being mainstreamed, gaps and opportunities to strengthen the integration of gender in these key frameworks to ensure effective prevention of COVID 19. | 15,000.00 | 3% | 15,000.00 | 3% |
| Indirect support cost | 34,270.00 | 6% | TBC |  |
|  | 559,826.00 | 100% |  | 71% |

For the project staff and the other related costs directly handled by UN Women, the actual spending rate could not be established by the final evaluation due to unfinalized Payrolls, Travel Authorization expenses, and Open Purchase Orders as well as pending Back-Up Management Costs. All these payments are waiting to be processed so as to establish the actual expenditure rate for the project visa-vis the total budget.

### Financial Management

Finding 15: Delays in fund imbursement to partners were reported

The overall budget was deemed sufficient for the general scope of work foreseen by the Prodoc and the set targets as per its results framework. However, the IPs described delays in reimbursements of the budget from UN Women which delayed further implementation of planned activities. According to them, the delays caused hurried activities implementation and not the end results or the targets. The budget allocated or the IPs were transferred in tranches upon their request and after the finalization of the preceding tranche activities.

The partners received payments for the planned activities in tranches. Based on the agreed work plan and the activities, the IPs requested for payments in certain tranche. However, due to the shift of new financial system by UN Women, delays in fund imbursement were reported. This led to lack of enough time for requested funds to cover the payment for quite a number of activities which meant that IPs had to prefinance considerable portions of their operational budget under the project to then submit the paperwork for reimbursement which induced an additional layer of work during the compressed timeframe reserved for implementation.

The project's resource allocation was enough to deliver the anticipated results, although the Implementing Partners identified a number of areas that require further improvement. Firstly, a hasty proposal draft made the project's operations unclear; nevertheless, the IPs claim that regular discussions with UN Women allayed their worries. Secondly, PPEs were distributed when the project was practically finished, and informants claim that this affected the timely distribution of the items through it has not impacted the achievement of the objectives. Thirdly, when the project was about to come to a close, partners received training in results-based monitoring and reporting. Though the IPs acquired the necessary abilities and subject-specific knowledge, it was necessary to conduct the training earlier so that the acquired skills and knowledge could be applied and internalized during the project’s life cycle. The Results-based Monitoring and Reporting consultant had regular meetings and follow-up with the IPs to ensure monitoring and reporting is done properly.

### Project Management and M&E process

The overall LEAP design was crafted in line with the existing offer and the existing demand at the community in general, due to the unawareness level. The dynamics also included preferences, expectations, and longer-term interests of the primary donor (Japan), the Federal Government of Somalia in the form of key ministries (Women, Health) and State level governments and UN Women Somalia.

The overall project (both Uganda and Somalia) was managed by the regional office with Country level management and the CO led by dedicated country program manager and program specialist with 100% level of effort to support the implementation, monitoring, and reporting.

Finding 16: The results-based training was not timely.

At the country office, the project recruited a Monitoring and Reporting consultancy to provide technical support who developed a strong gender-sensitive monitoring and reporting mechanism as well as strengthened the capacity of partners in reporting and M&E of the project.  Additionally, UN Women dispatched its staff a number of times for on-site visits and spot-checking. The partners had complaint and Feedback Mechanism, including a contact centre with a toll-free number. A two-day training on results-based monitoring and reporting was conducted for the IPs Furthermore, the IPs had M&E staff whose role was to conduct daily monitoring of the activities as well as to capture success stories. However, the training was conducted when the project was about to end (3 months close to the project).

Besides, the project developed a coordination platform with other UN agencies and contributed to United Nations Country Team (UNCT) work plan and reporting and information-sharing on the COVID-19 pandemic at the country level.

The project utilized the funds as per the implementation work plan to ensure the funds are utilized efficiently and effectively. UNW ensured utilizing the funds through Cost-Effectiveness and efficiency manner. The project responded to the deadliest pandemic in the country by increasing communities’ knowledge, attitudes, and practices (KAP) toward COVID-19 for controlling and preventing the infectious disease pandemic. The project built the leadership of women to participate in, lead and have a voice in COVID-19 prevention and response efforts.

As UN Women’s entity dedicated to gender equality and the empowerment of women, UNW envisaged Gender responsive COVID-19 intervention and worked with Women led CSOs that are the frontline responders in the humanitarian crisis, leading efforts to deliver essential and lifesaving support to crisis-affected communities in hard-to-reach areas.

There were internal challenges as the UN Women Quantum system delayed fund disbursement to the partners and there was untimely procurement of the PPE due to unavailability of the PPEs in the country.  Additionally, partner selection and recruitment of the staff took some time and actual implementation started in April 2023, however, partners received their funds in October 23.

## Sustainability

### Substantiality of the Results

The LEAP 2 project was built on a sustainability model where the capacities of local women and district local governments institutions are further strengthened to participate in gender responsive COVID-19 prevention, response and service provision for IDPs, refugees and vulnerable women. UN Women employed key strategies that have previously generated tangible results, as well as those recommended through stakeholder consultations to improve sustainability including capacity development of women and women led organizations, government and humanitarian stakeholders, building a supportive system for women leaders, refugees, and host communities, utilizing existing coordination structures such as camp management committees and strengthening male engagement for gender equality and addressing negative social norms

It was successful to spread information on COVID-19 and harmful cultural norms through sources that the target communities were familiar with by selecting hygiene promoters from the displaced communities to conduct door-to-door sessions. The LEAP initiative also used the already-existing IDP committees as the greatest forum for community communication. The voluntary COVID-19 and women's empowerment awareness initiatives continued as a consequence of community ownership and leadership.

Finding 17: The project contributed to change in perception.

Figure 8: Perception on women leadership

The communities that benefited from the project first believed COVID-19 was finished and that no more safety precautions were needed. Communities were aware that COVID-19 prevention measures are necessary at all times as a result of door-to-door education campaigns, community involvement, and capacity-building training. Female presenters dominated COVID-19 and women's independence awareness-raising events. Every committee that was already in place had a female member, and a few of them even had a female chairperson. Since women made up the bulk of those who promoted good hygiene, they were able to support their families financially and empower women. This suggests that by upholding appropriate sanitary standards, the initiative had a favourable influence on the neighbourhood. To assess the likelihood of women being part of the society leadership structure, 61 percent of the FGD participants revealed that women would be likely to be included in the societal leadership structure. However, due to the parochial and patriarchal nature of the Somali society regarding women and leadership role, the full realization of women leadership would take time. The informants reiterated the need to intensify project's support activities in order to reach a considerable number of women; the bulk of project activities, with the exception of providing sanitation supplies, were awareness-raising activities, but for impact, more tangible assistance is needed.

Figure 9: Perception on sustainability

Informants from interviews and the FGD participants confirmed that community awareness-raising sessions, provision of the dignity kits and PPEs, the training as well as other outreach activities had a positive impact on the lives of the target population, thus ensuring the sustainability of the results. According to them, the project was owned by the community and even now as the project ended the groups are still working on promoting women’s rights through regular meetings, however, they need more support such as training and income to sustain the project and achieve greater results.

The LEAP project design included gender-responsive programming components which benefitted the IPs’ capacity to ensure the gender mainstreaming of future projects and programs they will be involved in. Finally, there is evidence that women’s capacity to participate in decision-making and access to protection mechanisms have all been improved. According to 84 percent of the beneficiaries interviewed, changes made by the project will be sustained after the project ends, and they also believe that the community has taken ownership after realizing the importance of taking the vaccine and coming to understand the hazards of GBV. However, the new influxes from recurring droughts and the fight between the government and Alshabab need to be relayed to the same message.

### Gender Equality and Human Rights

Finding 15: The outreach campaigns educated the community members on gender issues like human rights, FGM and GBV

By strengthening women's capacity in the fight against the prevention of the pandemic and harmful cultural practices including GBV and educating victims on the referral pathways, the LEAP project was created with the goal of contributing to gender responsive stabilization and recovery of conflict affected displaced women and men in target locations.

According to sources, the project's conception and execution substantially included gender and human rights concepts. The goal of the initiative was to promote women's participation, leadership, and protection rights while addressing discriminatory gender stereotypes in the target localities. This was consistent with the numerous normative frameworks on GEWE and human rights, such as the Beijing Platform for Action, CEDAW, and UNSCR 1,325.

The overwhelming majority of informants were of the opinion that the project has successfully contributed to addressing gender inequalities in the community; and that empowering woman paves the way for addressing the gaps while the outreach campaigns educated the community members on gender issues like human rights, FGM and GBV. Besides, the LEAP project is seen to have contributed to the capacity of the society to overcome gender inequalities.

Table 7: Perception on human rights and gender equalities

|  | Strongly agree | Agree | Neutral | Disagree | Strongly disagree | Total |
| --- | --- | --- | --- | --- | --- | --- |
| The community awareness-raising sessions helped me understand the harmful cultural practices like FGM, early marriage, and other GBV issues | 47% | 41% | 5% | 3% | 5% | 100% |
| The assistance I received improved the capacity of society to overcome gender inequalities | 6% | 45% | 20% | 16% | 13% | 100% |

The FGD participants confirmed that the project helped them improve their knowledge on human rights specifically FGM, early marriage, and other GBV issues. 88 percent of the participants said that the project activities helped them understand harmful cultural practices. On the other hand, 51 percent of the FGD participants mentioned that the project improved the community’s capacity to overcome gender inequalities. These demands more support to the community to galvanize the results achieved under the project.

# Lessons Learned and Good Practices

This project was built on successes and lessons learnt from the implementation of the LEAP 1 (2021-2022) project in Somalia and Uganda’. The overall goal of LEAP 1 project was to ensure that 7,440 women and girl refugees, IDPs are directly empowered to mitigate the impact of multiple crises on their livelihoods, protect themselves from exposure to GBV, and participate in decision-making processes within their communities. The evaluation report presents the following lessons learned and best practices based on the interviews and interactions with key stakeholders of the LEAP project:

Lessons 1: The use of local Hygiene promoters: By choosing hygiene promoters from the neighbourhoods who are known by the community established enabled trust of the target communities with the project. The engagement resulted the hygiene promoters to interact with the community all the times even after work.

Pocket GBV books: As a way to empower women and improve justice for displaced women, pocket GBV books were distributed to literate women which acts a guide to refer to all the time.

Partnering with Women-led Organizations: The project partnered with women-led organization with presence in the field who are working in gender issues as well as prevention of the spread of COVID.

-19 which resulted in the successful implementation of the project.

Social integration: Targeting IDPs, returnees and the host community (who are always living in the same settlement) in project activities facilitated the social integration of IDPs and host community. By targeting beneficiaries with a different “displacement status”, the project facilitated the establishment of cross-cutting networks across different population groups among the inhabitants. This contributed to creating a cohesive network and promoted social cohesion including sharing insights and learning from one another.

Hampering factors of gender equality: Giving opportunities to women contributes to addressing gender inequalities as lack of resources and capacity aggravates and widens existing gaps. According to informants, lack of business skills and knowledge are commonplace among, and afflict many businesses run by women; therefore, the entrepreneurship trainings would help them to acquire necessary relevant skills in terms of leadership and management, conflict resolution, tolerance in business, how to assess business opportunities and reintegration.

New influx: Somalia’s urban areas (specially Mogadishu) witnessed new influx displaced by the recurring drought as well as clashes between Alshabab and the government forces. The new displacement stretched the meagre resources available in the IDP camps that were already congested.

Sensitization activities: The practice of community door to door awareness raising sessions potentially qualifies as a best practice. Further proof is needed, though, to ascertain whether these sessions helped communities to no longer commit harmful traditional practices (FGM, childhood marriages etc.) are more than a reflection of peer pressure during these public events, and the pledge actually translates into discontinuing and thus, abstaining from further adhering to said practices.

Importance of community engagement: The project symbolized the importance of engaging communities in GBV and COVID-19 prevention response efforts during the project implementation. The project found that involving community members in project activities helped build trust and improve access to services.

Improved Coordination and Collaboration with stakeholders: The project's success was due in large part to collaboration and coordination between different sectors, including government line ministries, camp leaders, community members, women groups, women activists, and other stakeholders. These partnerships helped ensure a coordinated response to the project implementation.

Employing women: The LEAP project employed women to implement the project's activities while receiving a monthly incentive; in turn, this empowered vulnerable women, girls, and youth affected by COVID-19 in the IDPs in Somalia and decreased their families’ food insecurity and unemployment rate.

Insufficient resources in the camps: Targeted IDPs commonly lacked resources such as food, water, and healthcare, which made it difficult to prioritize prevention measures for COVID-19 and GBV. The level of poverty and the overcrowding of the IDP camps may prove sanitation and hygiene promotions ineffective though all the community members interacted confirmed that the project has helped them acquire the required knowledge of the pandemic and its prevention measures.

Influence of culture: The norms and culture dictated that women’s place is in the kitchen and thus cultural and social beliefs prevented IDPs from seeking support or reporting incidents of GBV. For instance, some communities viewed GBV as a private matter that should be resolved within the family. This made it challenging to raise awareness about GBV and encourage reporting. For instance, religious leaders in Baidoa advocated the radio to stop broadcasting GBV and how to report them.

Lack proper tracking of cases: Lack of GBV referral pathways and improper case tracking within the IDPs setup made it difficult for victims to receive the necessary assistance required. According to UNFPA, there has been widespread GBV cases during the pandemic and most of the cases may go unreported.

# Conclusions

Based on the detailed analysis, the LEAP 2 project activities were successful since the Implementing Partners coordinated with the line ministries and other stakeholders and largely produced the expected results. Within the given context constraints, the target communities have displayed an understanding of the pandemic as well as the harmful cultural practices that women and girls undergo in the patriarchal society.

The LEAP project was crucial for displaced communities in urban areas like Baidoa, Kismayo, Banadir, and Garowe, who were at risk from COVID-19 and gender-based crimes. The initiative supported target communities in understanding good sanitation practices to prevent the spread of the pandemic. The project involved community discussions, dialogue sessions, and training sessions, resulting in better access to health services and justice.

The Ministries of Health and Women and displaced people were among the stakeholders who benefited from the LEAP project. The most susceptible communities, affected by GBV and COVID-19, were involved and made aware of the project before it began. Community hygiene promoters, village relief committees, community leaders, and the Ministry of Health were also consulted.

All project activities, such as awareness campaigns, community discussions, and training sessions on women's empowerment and COVID-19, benefitted IDP women. The initiative helped female residents assert their rights to justice and pandemic prevention measures, such as sanitation.

The project contributed to gender equality by empowering women through leadership training and increased awareness on harmful cultural practices. The effort pushed individuals to get COVID-19 vaccines and started to practice better cleanliness. The project worked with the ministries of Health and Women and Human Right Development at federal and state levels, facilitating the proper implementation of the project. The strong community engagement/consultations facilitated the improvement of collaboration between communities and the organization, effective coordination, and information sharing. The community as a stakeholder also promoted the inclusion of marginalized populations, such as women, youth, persons with disabilities, the elderly, and religious or ethnic minorities, as decision-makers.

76 percent of the beneficiaries reported improved perception, leadership, and empowerment in relation to the pandemic. The project promoted social inclusion for women, made it easier for them to participate in events like community gatherings, mediation procedures, and meetings for resolving disputes. The project also encouraged women to speak up and be heard, as community elders, government representatives, and NGOs can hear women's cries and provide the necessary support.

The project's activities made it easier for people to access community health care hubs and seek justice without reservation or reluctance. The initiative was crucial in influencing the community's attitudes and behaviours regarding COVID-19 and its protocol, helping them comprehend the issues brought on by COVID-19 and how they might be avoided.

The LEAP project aimed to ensure successful COVID-19 prevention by evaluating readiness and response plans, addressing gender mainstreaming, gaps, and opportunities for gender integration. The project involved community opinion leaders, camp leaders, religious leaders, women activists, youth representatives, and women's rights groups. The project provided 335 females with a dignity kit, attended courses to raise awareness of COVID-19 and its mitigation and preventative strategies, and trained community women in improving their capacities and knowledge of gender representation in decision-making processes.

Community awareness sessions were conducted, and women's empowerment was achieved through community conversation facilitation, awareness campaigns, and capacity-building training. The project also led to increased referrals of GBV cases and the ability of vulnerable populations to assert and exercise their rights. Social norms and attitudes-related impediments were addressed, and the public embraced information about COVID-19 and women's empowerment after additional education.

The project's success was attributed to door-to-door community awareness campaigns, radio awareness campaigns, community dialogues, the creation and distribution of the GBV bucket guidebook, and capacity building for the affected communities. The number of GBV cases recorded rose, and the number of vaccinations received has grown, and some neighbourhood attitudes have improved.

The project had a significant influence on GBV and COVID-19 behaviour modification, as people impacted by displacement continued to be aware of COVID-19 and gender equality after the initiative had concluded. The experience of IPs and their necessary skills, knowledge, and capacities were the main contributing factors to successful project implementation.

Gender-based violence is a multidimensional problem rooted in gender inequality, harmful cultural norms, and power abuse. Women are now a leading force in disaster risk reduction and emergency response, including health services. The LEAP project was partially inclusive, with 59% of participants confirming it was much inclusive, while 23% said it was partially inclusive, targeting mostly women.

In conclusion, the LEAP project played a crucial role in addressing the challenges faced by displaced communities in urban areas. By partnering with civil society organizations and implementing effective strategies, the project aimed to improve the lives of women and girls affected by COVID-19 and other related issues.

# Recommendations

The evaluation report presents a number of recommendations which are useful for future programming. In view of maximizing the evaluation findings’ utility, the following grid lists elements that can be used for UN Women’s official management response to the recommendations and related corporate follow-up:

| Evaluation Title/year | LEAP 2 in Somalia /2023 |  |  |
| --- | --- | --- | --- |
| Summary of evaluation | LEAP 2 -Project interventions were successful – the fieldwork by the Implementing Partners in coordination with the line ministries largely produced the expected results. |  |  |
| Evaluation recommendation 1: Expanding Scope: In order to reach as many people as possible, the respondents with whom the evaluator interacted suggested that such a project in the future engage universities to highlight harmful cultural habits through theatre/drama and plays that are broadcast on television. Both an IDP situation and an out-of-camp one might benefit from this. In order to understand how the play and drama will be received by the community, it is crucial to conduct a survey. Arday (Student), a recent TV show on education in Somalia, went viral but was denounced by religious authorities while being seen by the public as an educational film that even discussed GBV issues including early and forced marriage in parts of the episodes. |  |  |  |
| Key action | Timeframe | Responsible entity | Priority |
| Explore the possibility of engaging TVs to showcase harmful cultural practices | Immediate continuation of existing LEAP 2 activities | UN Women Somalia, Funding Partners and IPs | High |
| Evaluation recommendation 2: Life skills: All the informants agreed on the importance to incorporate a life skills program. The coronavirus disease 2019 (COVID-19) pandemic has had a huge effect on adolescents' health and learning. Health promotion strategies should be valued, and life skill education is a potential approach in this direction. As the pandemic has thrown life into disarray, being responsible, valuing money, and bonding with loved ones are a few important life skills you can help the community learn in these uncertain times. |  |  |  |
| Key action | Timeframe | Responsible entity | Priority |
| Include life skills sessions/training in such interventions | To be introduced as a feature of a new, further upgraded project design | UN Women Somalia and ESARO, IPs, local partners | Medium |
| Evaluation recommendation 3: Livelihood Support: the pandemic has left indelible haunting moments on the IDPs as its effects (lockdown etc) hampered their livelihood like small-scale businesses. Most of the IDPs work as labourers in the main cities and this was minimized or even absent. It is recommended that such a project to include some livelihood support to the supported communities in form of income-generating activities or business start-up kits for women. |  |  |  |
| Key action | Timeframe | Responsible entity | Priority |
| Share LEAP project’s evaluation lessons learned, best practices, conclusions and recommendations with wider community to attract donors to mobilize more resources | August-December 2023 | UN Women Somalia and ESARO | High |
| Evaluation recommendation 4: Continuity of the project: All of the informants contacted highly complimented the LEAP 2 project, which was created to develop awareness-raising sessions, for its applicability and timeliness as well as the outcomes it generated. Having said that, the implementation phase was quite brief, and a continuance should be taken into account. By enlisting more contributors or collaborating with other efforts with similar goals, it may be possible to continue supporting the beneficiaries while bringing in new funding to secure the project's viability. |  |  |  |
| Key action | Timeframe | Responsible entity | Priority |
| Continue field operation in pilot areas | Once this phase ends | UN Women Somalia and ESARO/HQ | High |
| Evaluation recommendation 5: Improve the capacity of partners on Results-based reporting: a two-day training on results-based monitoring and reporting was conducted for the IPs towards the end of the project implementation period. Though the training was relevant and applicable, it would have been more effective if planned in the inception phase of the project so that partners’ capacity on reporting is improved and skills and knowledge utilized throughout the project’s life span. |  |  |  |
| Key action | Timeframe | Responsible entity | Priority |
| Assess the capacity of IPs before project implementation to ensure their capacity gaps are filled. Train IP project staff on reporting | To be started with new project cycle | UN Women | High |
| Evaluation recommendation 6: Improve Coordination with the Government: According to informants from the government, there was no close coordination at the State level, so UN Women needs to ensure effective coordination among the partners and with the government to ensure accountability. |  |  |  |
| Key action | Timeframe | Responsible entity | Priority |
| Engage with the government at both Federal and State levels | Before project, during and phase out. | UN Women, IP, | High |

# Annexes

## Documents Reviewed

- Project Document

- Project budget and expenditure tracking

- Project proposal

- Partner reports

- Monitoring report

- Project progress report to Donor

- Project workplan

- UNEG Norms and Standards for Evaluation

- UN Women Global Evaluation Reports Assessment and Analysis System (GERAAS)

- UN Women Evaluation Handbook: How to manage gender-responsive evaluation

- UN Women Pocket Tool for Managing Evaluation during the COVID-19 Pandemic

## Data Collection Instruments (questionnaires and interview guides)

## Evaluation Matrix

## List of Agencies and Partners Interviewed

| # | Name |  | Displacement Status | Village | Activity Participated |
| --- | --- | --- | --- | --- | --- |
| FGD Women Leaders Trained to Enhance Leadership, Equal Representation of Women In Decision-Making And How-To Refer Cases To Formal Justice System In All Target Project Areas |  |  |  |  |  |
|  | Munira Iman Mohamed |  | Host Community | Wadajir | Leadership Training |
|  | Suada Abdiaziz Dahir |  | Host Community | Hodan | Leadership Training |
|  | Mulki Ali Ibraahim |  | Host Community | Zope | Leadership Training |
|  | Kaha Abdi Alasow |  | Host Community | Wadajir | Leadership Training |
|  | Ayan Ahmed Osman |  | Host Community | Wadajir | Leadership Training |
|  | Zahra Cilmi Garad |  | Host Community | Wadajir | Leadership Training |
|  | Sabiriin Jacfar |  | Host Community | Hodan | Leadership Training |
|  | Kaltomo Nasir Abdi |  | Host Community | Wadajir | Leadership Training |
|  | Naima Mohamed Hassan |  | Host Community | Dharkenley | Leadership Training |
|  | Riyaq Abdullahi Hassan |  | Host Community | Wadajir | Leadership Training |
|  | Faduma Yussuf Osman |  | Host Community | Wadajir | Leadership Training |
|  | Ismahan Isse Mahamed |  | Host Community | Hamar Jajab | Leadership Training |
|  | Raqiya Abdullahi |  | Host Community | Kahda | Leadership Training |
|  | Muniro Osman Mahamoud |  | Host Community | Hilawa | Leadership Training |
|  | Ayan Ahmed Osman |  | Host Community | Wadajir | Leadership Training |
|  | Safiyo Barbe Ali |  | Host Community | Shibis | Leadership Training |
| Women Provided With Material Assistance (Dignity Kits) |  |  |  |  |  |
|  | Habibo Abu Mohamed |  | IDPS | Al Cadaala | Dignity Kits |
|  | Khadijo Hussein Borow |  | IDPS | Al Cadaala | Dignity Kits |
|  | Fardowsa Ali Mohamed |  | IDPS | Al Cadaala | Dignity Kits |
|  | Fadumo Hussein Hassan |  | IDPS | Al Cadaala | Dignity Kits |
|  | Sacido Elyas |  | IDPS | Al Cadaala | Dignity Kits |
|  | Khadijo Mohamed Ali |  | IDPS | Al Cadaala | Dignity Kits |
|  | Amino Abdikadir Hussein |  | IDPS | Al Cadaala | Dignity Kits |
|  | Khadijo Osman |  | IDPS | Al Cadaala | Dignity Kits |
|  | Fadumo Adon Gedow |  | IDPS | Al Cadaala | Dignity Kits |
|  | Sacdio Adon Ahmed |  | IDPS | Al Cadaala | Dignity Kits |
|  | Fadumo Jeilan Hodman |  | IDPS | Al Cadaala | Dignity Kits |
|  | Nacimo Ibrahim |  | IDPS | Al Cadaala | Dignity Kits |
|  | Asha Osman Omar |  | IDPS | Al Cadaala | Dignity Kits |
|  | Fadumo Aliyow Ahmed |  | IDPS | Al Cadaala | Dignity Kits |
|  | Nacimo Mohamed Odowa |  | IDPS | Al Cadaala | Dignity Kits |
|  | Madino mohamed siidow |  | IDP | Al Cadaala | Dignity Kits |
| Participants On Community Conversations / Dialogues Led By Community Opinion Leaders |  |  |  |  |  |
|  | Maleko Abdi Ali |  | IDP | Baidoa | Community Dialogues |
|  | Habbo Moalim Ibrahim |  | IDP | Baidoa | Community Dialogues |
|  | Maryan Ibrahim Okash |  | IDP | Baidoa | Community Dialogues |
|  | Sonto Ali Ronow |  | IDP | Baidoa | Community Dialogues |
|  | Isho Abukar Abdi |  | IDP | Baidoa | Community Dialogues |
|  | Nasro Jimale |  | IDP | Baidoa | Community Dialogues |
|  | Fartun Mohanmed Hussein |  | IDP | Baidoa | Community Dialogues |
|  | Hawo Ali Omar |  | IDP | Baidoa | Community Dialogues |
|  | Sahro Haji Ahmed |  | IDP | Baidoa | Community Dialogues |
|  | Kadijo Mohamed Ali |  | IDP | Baidoa | Community Dialogues |
|  | Hawo Aden Sheq |  | IDP | Baidoa | Community Dialogues |
|  | Sokorey Ahed Hassan |  | IDP | Baidoa | Community Dialogues |
|  | Nasteho Abdi Wehliye |  | IDP | Baidoa | Community Dialogues |
|  | Nasteho Abdi Wehliye |  | IDP | Baidoa | Community Dialogues |
|  | Barey Hassan Ibrahim |  | IDP | Baidoa | Community Dialogues |
|  | Maryan Aden Abas |  | IDP | Baidoa | Community Dialogues |
| Trainees On Training Of Trainers (Tot) Workshops On GBV Prevention And Response Using IASC GBV In Emergency Guidelines |  |  |  |  |  |
|  | Hamdi Hassan |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Aisha Olow |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Fardowsa Mohamed |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Fadumo Mudey Shire |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Raho Hassan Mohamed |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Amal Adan Muse |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Ismahan Mohamed Ali |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Rukia Dufle Mohamed |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Iman Mohamed Hassan |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Safi Ahmed Ali |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Fartun Ali Yussuf |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Yasmin Khalif Warsame |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Maryan Yusuf Hassan |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Hamdi Abdinasir Ahmed |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Asha Abdikarim Hassan |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
|  | Fartun Mohamed Warsame |  | Host Community | Kismayo | Tot) Workshops On GBV Prevention |
| Key Informant Interviews |  |  |  |  |  |  |
| No |  | Name | Title |  |  |  |
| Government Officials |  |  |  |  |  |  |
|  |  | Mohamud Dubad Mohamed | Deputy Health Promotion Ministry of Health Mogadishu |  |  |  |
|  |  | Issack Dahir Abdi | Deputy Health Promotion Ministry of Health Kismayo |  |  |  |
|  |  | Mohamed Abdiqadir Salat | MOH-District Social Mobilization Coordinator Baidoa |  |  |  |
| Community Members |  |  |  |  |  |  |
|  |  | Abdiaziz Hussein Salat | Hygiene Promoter |  |  |  |
|  |  | Zamzam Mohamed Aden | Hygiene Promoter |  |  |  |
|  |  | Mohamed Ibrahim Hassan | Hygiene Promoter |  |  |  |
|  |  | Mulki Abdi Ibrahim | Community Member |  |  |  |
|  |  | Aden Dahir | Community Member |  |  |  |
| UN Women |  |  |  |  |  |  |
|  |  | Omar Abdikadir | Program Specialist |  |  |  |
| SWDC |  |  |  |  |  |  |
|  |  | Decka Odawa | Project Coordinator |  |  |  |
|  |  | Idil Abdi Ahmed | Project Officer |  |  |  |
|  |  | Zamzam Ahmed Adow | Caseworker |  |  |  |
|  |  | Abdullahi Dahir Ahmed | Program Manager |  |  |  |
| NAPAD |  |  |  |  |  |  |
|  |  | Abdirahin Aden Abdullahi | Area Manager |  |  |  |
|  |  | Maria Abdi | Public Health Officer-Baidoa/Garowe |  |  |  |
|  |  | Sadia Abdullahi Mohamed | Project Focal Point |  |  |  |
|  |  | Mohamed Mohamud Garane | Project Focal Point Kismayo |  |  |  |

## Evaluation ToR

## Evaluator Profile

Muktar Abdi Hussein is a Monitoring Evaluation, Learning and Accountability expert who has conducted several evaluations and assessments related to WPS, gender, education, agriculture, stabilization, early recovery and other humanitarian and development themes.

World Bank, 2019. “Somalia Economic Update: Building Education to Boost Human Capital”, August, Edition No.4.

Federal Republic of Somalia. 2018. Somalia Recovery and Resilience Framework

RAAGSAN. May 2020. “Socioeconomic implication of COVID-19 on micro, small and medium women-owned enterprises: A case of Mogadishu”.

Ministry of Health and Human Services, Federal Government of Somalia (2020) ‘National Preparedness and Response Plan for Corona Virus Disease 2019 (COVID-19)’

FSNAU-FEWS NET (2020) ‘Post Gu Technical Release - Up to 2.1 million people in Somalia face acute food insecurity Crisis (IPC Phase 3) or worse outcomes in late 2020’, September FSNAU-FEWS NET (2020) ‘Post Gu Technical Release’, September 30th; and Mogadishu/Washington and Africa Renewal (2020) ‘Using innovation to deliver in Somalia despite COVID-19’, June (https://www.un.org/africarenewal/news/coronavirus/using-innovation-deliver-somalia-despite-covid-19)

International Labour Organization (2020) ‘Sectoral Assessment of Women’s Entrepreneurship Development in the Agriculture and Renewable Energy Sectors in Somalia’, June (https://www.ilo.org/ empent/areas/womens-entrepreneurship-development-wed/facet/WCMS_757371/lang--en/index.htm)

IDLO (2020) ‘COVID-19: pre-existing gender discrimination provides fertile ground for increased inequality, to the detriment of food security and nutrition’, June (https://www.idlo.int/news/commentary/ covid-19-pre-existing-gender-discrimination-provides-fertile-ground-increased)

Ibid.

DNS (n/d) ‘Population composition and Demographic Characteristics of the Somali People. Volume 2’ (https://www.nbs.gov.so/volume-2-population-composition-and-demographic-characteristics-of-the-somalipeople/

Rift Valley Institute (2020) ‘Khat and COVID-19: Somalia’s cross-border economy in the time of coronavirus’, May (https://riftvalley.net/publication/khat-and-covid-19-somalias-cross-border-economytime-coronavirus)

OCHA (2020) ‘Somalia Humanitarian Bulletin, 1 May - 2 June 2020’, June (https://reliefweb.int/report/somalia/somalia-humanitarian-bulletin-1-may-2-june-2020)

GBV AoR Somalia (2020) ‘GBV/FGM Rapid Assessment Report: In the Context of COVID-19 Pandemic’, July

The Guardian (2020) ‘Huge FGM rise recorded in Somalia during coronavirus lockdown’, May (https://www.theguardian.com/world/2020/may/18/fgm-risk-in-somalia-heightened-by-coronavirus-crisis)

Policy Brief: The impact of COVID-19 on Women, United Nations, April 2020

Policy Brief: The impact of COVID-19 on Women, United Nations, April 2020

http://www.unevaluation.org/document/detail/1914

See, https://somalia.un.org/en/96542-un-sustainable-development-cooperation-framework-somalia-2021-2025

See, http://mop.gov.so/wp-content/uploads/2018/07/Somalia-RRF-Summary-Report_final_layout6July2018-2.pdf

Polish Humanitarian Agency (PAH), Save the Children International, ACTED, etc

Progress Report

UN Women, “Frequently Asked Questions: Types of Violence against Women and Girls,” https://www.unwomen.org/en/what-we-do/ending-violence-against-women/faqs/ types-of-violence (accessed March 9, 2023).

UNOCHA, “On Tenth Anniversary of World Humanitarian Day, the UN Pays Special Tribute to Women Humanitarians,” press release, August 19, 2019, https://reliefweb .int/report/world/tenth-anniversary-world-humanitarian-day-un-pays-special-tribute -women-humanitarians.

https://somalia.unfpa.org/en/publications/unfpa-somalia-gbv-quarterly-advocacy-brief-january-march-2023

https://somalia.unfpa.org/en/publications/unfpa-somalia-gbv-quarterly-advocacy-brief-january-march-2023

http://www.unevaluation.org/document/detail/1914

https://www.unwomen.org/ /media/headquarters/attachments/sections/about%20us/evaluation/evaluation-geraas-guidance-en.pdf?la=en&vs=408

http://genderevaluation.unwomen.org/en/evaluation-handbook

https://www.unwomen.org/en/digital-library/publications/2020/05/pocket-tool-for-managing-evaluation-during-the-covid-19-pandemic