# UN Women-WHO Global Joint Programme on Violence against Women Data

# End Term Evaluation

13 October 2023

Submitted by

Shelah S. Bloom

# ACRONYMS

AiW		Arab Institute for Women

APHRC		African Population and Health Research Center

CEDAW	Convention on the Elimination of All Forms of Discrimination against Women

CO		Country Office

CSO		Civil-society organization

DHS		Demographic and Health Surveys

ESCWA		United Nations Economic and Social Commission for Western Asia

EGIE		European Institute for Gender Equality

EGM		Expert group meeting

EVAW		Ending violence against women

FCDO		Foreign, Commonwealth, and Development Office, United Kingdom of Great Britain and

Northern Ireland

FRA		EU Agency for Fundamental Rights

GWI		Global Women’s Institute

KII		Key informant interview

LAU		Lebanese American University

M&E		Monitoring and evaluation

MCO		Multi-country office

MoH		Ministry of health

MTR		Midterm reflection exercise

NGO		Non-government organization

NSO		National statistics office

PAHO		Pan American Health Organization

RO		Regional Office

SDG		Sustainable Development Goal

SVRI		Sexual Violence Research Initiative

TAG		Technical advisory group

UNEG		United Nations Evaluation Group

UN Women	United Nations Entity for Gender Equality and the Empowerment of Women

UNFPA		United Nations Fund for Population Activities

UNICEF		United Nations Children’s Fund

UNODC	United Nations Office on Drugs and Crime

UNSD		United Nations Statistical Division

UNSC		United Nations Statistical Commission

VAW		Violence against women

VAWG		Violence against women and girls

WHO		World Health Organization

# Acknowledgements

This report, and the overall evaluation process, was informed and enriched by the participation of about 40 stakeholders, personnel, and partners – many of whom actively contributed to the evaluation by serving as key informants, attending focus group discussions, or completing comprehensive surveys. Without the support and active participation of these individuals, this report would not have been possible.

The evaluation was conducted by Shelah S. Bloom, International Consultant.

The evaluation also benefitted from the active involvement of the Internal Reference Group members, composed of the UN Women Ending Violence Against Women and Girls Section, UN Women’s Independent Evaluation Office and the World Health Organization Department of Sexual and Reproductive Health and Research, whom we thank for their thoughtful comments and insights and for investing significant time and effort to ensure that the evaluation would be of maximum value and use.

Finally, we would like to thank all those who engaged or participated in this evaluation, be it through responding to a survey; making themselves available for interviews; or participating in the consultation process. We are grateful for your contributions, which have without doubt enriched this report.

Evaluation consultant: Shelah S. Bloom

Evaluation management:

UN Women, Ending Violence against Women Section

Kalliopi Mingeirou, Chief

Juncal Plazaola Castaño, Policy Specialist, Violence against Women Data

Raphaëlle Rafin, Programme Specialist, Violence against Women Data

UN Women Independent Evaluation Office

Florencia Tateossian, Evaluation Specialist

WHO Addressing the Needs of Populations in Vulnerable Situations Unit, Department of Sexual and Reproductive Health and Research

Claudia Garcia-Moreno, Unit Head

LynnMarie Sardinha, Technical Officer Violence against Women Data and Research

# Table of Contents

ACRONYMS	1

Acknowledgements	2

Table of Contents	3

Executive Summary	5

The UN Women-WHO Joint Programme on Violence against Women data advanced the global agenda on Ending Violence against Women and Girls	5

1  Increased VAW data availability and accessibility started a momentum of VAW data collection, production and use that will continue into the future and enable monitoring of SDG indicator 5.2.1	5

2  Spearheading the development and harmonization of methods and measures for new VAW data collection has effected a transformative shift in the VAW data field	5

3  Building capacity for collecting, producing and using quality VAW prevalence data has triggered a growing demand for these skills in regions and countries	6

4  Designing and implementing strategies that fostered the cycle of VAW data demand and use	6

5  A powerful leader as a coordinating body and a model of collaboration in the VAW data space	6

6  Demonstrating resilience and creativity in the face of unexpected change	7

‬7 Planning sustainability into activity design in all three areas of work	7

8 Key recommendations for a second phase	7

Context of the Evaluation	8

1 Background	10

1.1 Context	10

1.2  The Joint Programme	10

The goal and outcomes of the Joint Programme are: 	10

Area 1:  Strengthening methodologies and measurement of violence against women to enable the collection, production, dissemination, and use of sound prevalence and administrative data on violence against women.	11

Area 2: Capacities strengthened on the collection, analysis and use of VAW data by countries and sub-nationally, in line with international methodological, ethical and safety standards.	11

Area 3:  Building VAW data demand and supporting its use for advocacy and evidence-based decision-making	11

2  Evaluation Approach and Methods	13

2.1 Evaluation Process	13

2.2 Evaluation Objectives	13

2.3 Evaluation Research Questions	13

Effectiveness of the Programme	13

Programme Impact	14

Relevance of the programme design	14

Programme Coherence	14

Efficiency of programme approach and management	14

Sustainability of the programme	14

2.4 Data used for the Evaluation	14

Key Informant Interviews	14

Online Survey	15

2.5 Analyses	15

2.6 Management arrangements for the evaluation	15

3 Evaluation Findings	16

3.1 Effectiveness of the Programme	16

Finding 1: Joint Programme strategies and activities dramatically increased the availability and accessibility of VAW data and ensured it will continue to be collected, produced and used for years into the future	16

Finding 2:  By spearheading the development and harmonization of methods and measures for new data collection and use, the Joint Programme has effected a transformative shift in the VAW data field	18

Finding 3: The Joint Programme advanced country capacity for collecting, producing and using  VAW prevalence data in line with globally agreed-on standards, triggering a momentum for ongoing demand for these skills.	20

Finding 4: Joint Programme strategies pushed demand for VAW data at global, regional and country levels and facilitated its use to effect policy and programmatic change	22

‬	23

3.2 Programme Impact	23

Finding 5: Joint Programme work has influenced global and national policies and programmes to better prevent and respond to VAW	23

3.3 Programme Coherence	24

Finding 6: The Joint Programme demonstrated remarkable leadership as a coordinating body and model of collaboration in the VAW data space	24

3.4 Relevance of the programme design	26

Finding 7: Activities were designed to address current and emerging priorities—the response to unexpected developments demonstrated resilience and creativity	26

3.5 Efficiency of programme approach and management	28

Finding 8:  The Joint Programme maximized impact on a small budget	28

3.6 Sustainability of the programme	29

‬Finding 9:  Sustainability was planned into activity design in all three areas of the Joint Programme, with the strongest success in methodological development (Area 1)	29

4 Conclusions	31

5 Recommendations	33

‬	37

‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬Documents Reviewed‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬	38‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬

Annex 1: Interview Participants	43

Annex 2: Joint Programme Technical and Operational Results	45

Table A2.1: Joint Programme Technical Achievements	45

Table A2.2: Joint Programme Operational Achievements	55

Annex 3: Expert Survey Report	59

Methods	59

Results	60

Survey response	60

Experts reported positive experiences in Joint Programme working collaborations	60

Experts felt that a diverse range of stakeholders were convened	60

Participants expressed that the Joint Programme was important and unique:	61

Challenges identified	61

Suggestions for Join Programme Work in a second phase	61

Conclusions	62

Annex 4: Publications produced by the Joint Programme at a glance	63

# Executive Summary

Data is the new oil…framing the problem of violence against women as a data problem is essential for resource mobilization and … political will and action.

-External consultant-

## The UN Women-WHO Global Joint Programme on Violence against Women Data advanced the global agenda on Ending Violence against Women and Girls

In bringing together the distinct and complementary experience, expertise, and global presence of UN Women and WHO, the Joint Programme on violence against women (VAW) data was a unique initiative in both the VAW data space as well as the wider EVAW ecosystem. The two agencies joined forces to design and implement a combination of effective strategies and activities that successfully increased the availability of and accessibility to quality VAW data. By developing and promoting new, agreed-on methods and measures, the Joint Programme expanded the scope of current and future VAW data collection in both surveys and administrative systems. The Joint Programme’s focus on regional and country capacity to collect, interpret and use VAW data resulted in increased understanding and skills that has translated into a demand for more and better VAW data collection. Through implementing activities in countries to leverage collected VAW data for advocacy efforts, the Joint Programme directly contributed to policy and programmatic change that will better prevent and respond to violence against women.

These accomplishments have sparked a momentum of demand for new and better quality VAW data at the global, regional and country levels. Its extensive collaboration with sister UN agencies and over 100 leading VAW data experts and key stakeholders that underpinned all technical activities was pivotal to its success. In sum, the findings of this evaluation demonstrate that the Joint Programme is a key initiative for expanding the collection, production and use of quality VAW data—elements critical to ending violence against women and girls.

### 1  Increased VAW data availability and accessibility started a momentum of VAW data collection, production and use that will continue into the future, and enable monitoring of the SDG indicators on violence against women

Joint Programme work resulted in directly and indirectly increasing the availability and accessibility of quality VAW data for global monitoring, including for SDG indicators 5.2.1 on the prevalence of intimate partner violence against ever-partnered women aged 15 years and older and 5.2.2 on the prevalence of non-partner sexual violence against women aged 15 years and older. New global, regional, and national estimates for the prevalence of intimate partner violence, and regional and global estimates for the prevalence of non-partner sexual violence were produced and are easily accessed in user-friendly online platforms; the national estimates for intimate partner violence were accepted as the baseline for measuring progress made in countries against SDG indicator 5.2.1.  The guidance on the collection and use of VAW administrative data is being used in countries to develop and or strengthen VAW administrative data collection, which will lead to the production of quality data on VAW services.

- The agreed-on methodologies, measures, and guidance that were collaboratively developed are already helping countries to produce new VAW prevalence data and will continue to do so—there are existing commitments to using these measures in current and future efforts, and they will continue to be promoted in such exercises by the groups of experts involved in their development.

- Several countries are developing or strengthening VAW administrative data and the systems which will result in the availability of quality service-related data.

- A total of 27 countries have collected VAW data, including nationally representative surveys and those focused on specific areas, with the support of the Joint Programme.

### 2  Spearheading the development and harmonization of methods and measures for new VAW data collection has effected a transformative shift in the VAW data field

New methods  for measuring areas of VAW were developed collaboratively with experts in the field which will result in quality data to better our understanding of VAW. The Joint Programme revised existing and developed new global guidance on safety and ethical standards for collecting VAW prevalence data to keep pace with the current state of the field.

- In response to the felt need to evaluate how remote data collection could be safely obtained during the COVID-19 pandemic, the Joint Programme produced user-friendly guidance that adhered to globally agreed-on principles and standards.

- The first ever global guidance on the collection and production of administrative VAW data was published by the Joint Programme along with a package of user-friendly tools, and backed by technical support to countries and regions to promote better understanding of the purpose and use of administrative data and how to produce it.

- The range of the harmonized methods and measures developed and introduced—from the measurement recommendations and a survey module on violence against older women, recommendations for strengthening measures of violence against women with disabilities and psychological intimate partner violence, to a standard definition for measuring femicide and exploring newly emerging areas such as online and technologically facilitated violence—has expanded the field of VAW data collection that will increase our understanding of the many forms and contexts in which VAW takes place.

### 3  Building capacity for collecting, producing and using quality VAW prevalence data has triggered a growing demand for these skills in regions and countries

Regional, institutionalized courses aimed at providing skills for a broad range of country stakeholders—such as National Statistics Offices (NSOs), women’s machineries, Civil Society Organizations (CSOs), and others—to collect, produce and use VAW prevalence data in line with global standards has provided a strong foundation for increasing regional capacity with a focus in the Arab States and East and Southern Africa regions. VAW data-related dialogue with and technical support provided to individual countries has increased understanding and experience on a global level.

- Consortia in the Arab States and East and Southern Africa regions developed and launched dedicated regional courses on VAW data; in the Arab States this was the first-ever course on VAW data in the region.

- Capacity for understanding the meaning and importance of collecting good quality data on intimate partner prevalence was raised worldwide through the WHO country consultation process involved with publishing the national estimates for intimate partner violence.

- Extensive technical support to 27 individual countries and selected regions has been instrumental in increasing the capacity to collect, interpret and use VAW data.

- While there was technical support provided for developing administrative data systems to use the new guidance, country stakeholders still need the basic M&E skills that are fundamental to a functional system that shares and uses data within and across sectors.

4  Designing and implementing strategies that fostered the cycle of VAW data demand and use at global, regional and country levels, effecting policy and programmatic change

‬Joint Programme activities have influenced the demand for VAW data and facilitated its use in countries.

- The dialogues with all Member States on the newly produced intimate partner violence prevalence estimates created country ownership for these data along with a global awareness around the importance and potential impact of these data.

- Capacity building through workshops, institutionalized courses in regions, and technical support to countries on collecting, producing and using VAW survey and administrative data have created a demand for these data.

- Previous to Joint Programme work, countries needed to be encouraged to collect VAW data; while after the joint programme work, National Statistics Offices (NSOs) are asking for support to conduct national VAW surveys.

- The Joint Programme facilitated VAW data use for evidence-based decision making at both the global and national levels. The several examples of national policies and programmes that were changed or newly developed in response to advocacy efforts leveraging newly produced VAW data with the help of the Joint Programme is a remarkable accomplishment within a four and a half year programme implementation.

### 5  A powerful leader as a coordinating body and a model of collaboration in the VAW data space

The unique collaboration between UN Women and WHO was widely remarked on by numerous stakeholders.

- The collaborative nature of Joint Programme work formed the foundation for its success.

- Activities and strategies were backed by the technical input and support of a broad range of leading VAW data experts and key stakeholders both internal and external to the UN system.

- These collaborations took place by engaging stakeholders in consultative processes that were inclusive, transparent, and productive.

- This type of collaborative engagement ensured that the work was technically sound and sustainable through the long term, as those involved in the work will continue to promote it.

### 6  Demonstrating resilience and creativity in the face of unexpected change

Activities were designed using proven and reliable methods tailored for specific context like many programmes. The strength of a programme can be observed in its response to unexpected developments. These types of changes can have devastating effects on programmes, but the Joint Programme was able to pivot and to turn them into opportunities.

- The COVID-19 pandemic started 18 months into Joint Programme implementation. Activities were revised or newly developed to accommodate the conditions imposed by the emergency.

- Canceled in-person activities led to the unexpected availability of funds and activities were reprogrammed for other areas that would support the three outcomes, like the work on administrative data.

- In the same way, the Joint Programme responded to emerging priorities, such as the work on online and technology-facilitated violence.

‬7 Planning sustainability into activity design in all three areas of work

The collaborative strategy for producing new methods and methodologies ensured their continued use, as demonstrated by the results of similar ventures. Capacity building in and of itself is sustainable, as the skills needed in the work are imparted and strengthened by those who use them.

- The capacity to apply the skills acquired through technical support was observed in regions and countries.

- Institutionalizing training courses for a new area takes years of planning and support—both technically and financially—until institutional independence can be attained. The Joint Programme built a strong foundation in the two regions of focus for the continuation of these courses. Further work is required in this area for the courses to thrive.

### 8 Key recommendations for a second phase

- Continue to advance the development of agreed-on methodologies and measures for the prevalence of different forms of VAW and in areas to address data gaps, including among marginalized groups to further expand the contribution on Leaving No One Behind. The Joint Programme should continue its successful work in developing new methods and measures, and ensuring that the VAW prevalence estimates continue to be produced and updated. In moving forward, evaluate which types of collaborations, or which parts, can be accomplished either through online or hybrid activity, based on the experiences during the pandemic. Further, develop a feedback mechanism to ensure that everyone engaged understands next steps.

- Expand the work on administrative VAW data in select countries with a focus on including CSOs, and support this work by strengthening M&E capacity for administrative data in countries. VAW administrative data is sorely needed in countries to monitor and evaluate survivor response. Due to the complexity of a comprehensive response to survivors that involves multiple service sectors, coordination mechanisms are needed for the collection and sharing of data within and across sectors. Protocols are needed to guide how this will take place as well as the technology to produce and report these data both within and across sectors.  Given the years required to develop and sustain administrative systems, the Joint Programme should consider where best they can strengthen these systems, and they must be back by increased and sustained capacity in M&E.

- Provide support to the regional training partnerships to address current funding gaps and develop an exit strategy to ensure the sustainability of the VAW prevalence data course, and add a similar, dedicated course for the production and use of administrative VAW data for M&E in each region. The regional capacity training partnerships need extended support to become independent, both technically and financially. The Joint Programme should plan for the long term with both partnerships, including a feasible exit strategy, to ensure sustainability.

- Intensify efforts to support women’s machineries, CSOs, and other key country partners to leverage VAW prevalence and administrative data to advocate for policy and programmatic changes to better prevent and respond to violence against women and girls.  Some of the most impactful results from Joint Programme work were seen in this area, and work to support data use activities should continue. There are many existing tools for data use in both the VAW field as well as in other areas (e.g., health) that can be adapted and used to further this work that may engender more independence in countries. These changes depend on a political readiness in countries and the ability of country partners to effectively use these data to inform ongoing programmes or for advocacy work with policy makers, and the Joint Programme should tailor activities to match the level of commitment in various contexts.

- The distinct identity of the Joint Programme within the gender statistics arena should be preserved.  the Women Count flagship programme. However, given the specific requirements for VAW data, apart from general gender statistics, it is critical that the Joint Programme retain its distinction as a EVAW initiative.  Changing the name to The UN Women-WHO VAW Data Initiative, for example, may help facilitate this distinct identity, especially outside the UN system.

- Resource mobilization for a second phase should be based on a knowledge management (including branding) and communications strategies that will create a distinct identity for the Joint Programme.  A strong knowledge management strategy using consistent branding for products produced with a plan for disseminating results will strengthen resource mobilization. These actions will highlight the powerful results attained in its first phase and will help reinforce its distinct identity. The animation videos on VAW prevalence data and administrative data is an excellent example of the type of product that will attract donor attention.

- The Joint Programme should develop an M&E plan to better capture its results and impact, and build capacity for M&E basics in countries and regions. A results framework—the tables found at the end of annual reports—are good for capturing results based on indicators.  But a comprehensive M&E plan will cover everything from how programme goals and objectives are expected to be accomplished to the specific measures that will track progress and demonstrate results.

## Context of the Evaluation

The Joint Programme was implemented from June 2018-December 2022. This evaluation was commissioned by UN Women and WHO in line with the Joint Programme’s monitoring and evaluation plan. This evaluation was planned as both an assessment of what has been achieved and a forward-looking exercise in anticipation of a second phase, pending funding. The evaluation was conducted over the spring of 2023 and included a wide range of programme stakeholders within UN Women and WHO, other UN agencies, and external experts who worked with the Joint Programme. The objectives of the evaluation were to:

- Assess Joint Programme approaches and strategies in its three outcome areas.

- Gauge the results of the Joint Programme relative to the resources invested in it.

- Describe the performance of the UN Women and WHO collaboration in facilitating the achievement of programme outcomes, including programme design, implementation, and the combined effectiveness of the partnership including operational performance.

- Make concrete recommendations for how UN Women and WHO can build on the programme’s first phase, identifying successful strategies to scale-up and others to either modify or drop, based on lessons learned.

The evaluation used and triangulated three sources of data that provide evidence for the nine key findings: 1) a review of documents and publications; 2) Qualitative data collected through in-depth interviews with 39 different stakeholders (33 women, 6 men) working in a variety of contexts (23 UN personnel, 2 EU, 1 bi-lateral, 9 Researchers, 3 independent consultants); and 3) An online survey of 26/92 (28%) external experts.

- All external experts who worked with the Joint Programme were invited to participate in the evaluation, either in a key informant interview or in the survey.

The evaluation process adhered to the four UNEG guiding ethical principles of integrity, accountability, respect, beneficence and the guidance on Integrating Human Rights and Gender Equality in Evaluations.  The evaluation was conducted in a transparent and inclusive manner that promoted trust and meaningful engagement. The evaluation was a collaborative exercise between the Joint Programme internal reference group and the evaluator. The overarching research questions were based on the evaluation criteria of effectiveness, impact, relevance, coherence, efficiency, and sustainability.

# 1 Background

## 1.1 Context

In response to calls for the enhancement of the collection and use of data on violence against women, the United Nations Entity for Gender Equality and the Empowerment of Women (UN Women) and the World Health Organization (WHO) joined forces to implement and deliver the Joint Programme on Strengthening Methodologies and Measurement and Building National Capacities for Violence Against Women Data (the Joint Programme). The Joint Programme brought together the distinct and complementary experience and expertise of these two agencies to provide support and technical assistance to Member States and key stakeholders for the production, dissemination and use of VAW data based on global standards and human rights principles. UN Women and WHO, both resolute in their commitment to eliminating violence against women, strategically work to enhance the availability and use of quality, comparable VAW data as an instrumental component in their efforts to eradicate such violence. The Joint Programme was implemented for 54 months (June 2018 – December 2022) in close collaboration and coordination with other actors contributing to this field, particularly UNFPA, UNICEF,  UNODC, UNSD, and with the engagement of other stakeholders, and was funded by the Foreign, Commonwealth, and Development Office (FCDO) of the United Kingdom of Great Britain and Northern Ireland.

This evaluation was commissioned by UN Women and WHO in line with the Joint Programme’s monitoring and evaluation (M&E) plan as both a summative and formative exercise.  The mid-term reflection exercise (MTR) presented evidence to demonstrate that the Joint Programme had already made a powerful contribution to the field of data on violence against women, made recommendations for the remaining implementation period based on the findings, and described the potential impact that could be realized if the initiative were funded for a second phase. Data is considered a core component of work in the current UN Women Strategic Plan 2022-2025, and the current 13th WHO General Programme of Work 2019-2023 (and the upcoming 14th General Programme of Work), making the forward-looking part of the evaluation especially pertinent to the long-term priorities of both agencies. The evaluation aims were to:

- Assess the contribution of the Joint Programme to its goal of increasing the quality, comparability, availability and use of data on violence against women by documenting results achieved and their effects;

- Provide recommendations on how UN Women and WHO can further their work and contributions in a second phase (pending the availability of future funding).

## 1.2  The Joint Programme

### The goal and outcomes of the Joint Programme are:

Goal: To ensure that quality, comparable data on different forms of VAW are available and collected over time to address national data gaps and meet policy and reporting commitments including under the Sustainable Development Goals (SDGs), the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) and the Beijing Platform of Action.

Expected Outcomes:

- Measurement and methodologies for VAW data collection and use are strengthened and disseminated, including for national, regional and global monitoring and reporting requirements for SDG target 5.2 indicators.

- Capacity of countries to collect data on violence against women in line with globally agreed standards is increased.

- Demand for national VAW data and use of such data for advocacy, policy and programming to end violence against women and girls is increased.

Joint Programme strategies and activities were organized in three areas corresponding to these outcomes:

### Area 1:  Strengthening methodologies and measurement of violence against women to enable the collection, production, dissemination, and use of sound prevalence and administrative data on violence against women.

Under this area of work, new global, regional and national prevalence estimates on intimate partner violence and global and regional estimates on non-partner sexual violence were produced and disseminated as were new harmonized methods and measures for different types of VAW, capturing the experience of VAW in groups typically missed by existing population-based surveys, and guidance on developing and strengthening administrative VAW data. These new measures and methodologies will enable us to better understand and more accurately estimate the true prevalence, magnitude, and patterns of different forms of VAW across contexts/countries and regions and among diverse groups of women and adolescent girls. The improvement of VAW administrative data will increase our knowledge about VAW survivor service use and provision in countries.

### Area 2: Capacities strengthened on the collection, analysis and use of VAW data by countries and sub-nationally, in line with international methodological, ethical and safety standards.

This included establishing and institutionalizing two regional training programmes to cover these areas in the Arab States and in East and Southern Africa.  Capacity in countries was also strengthened through extensive technical support provided to regional and national partners for the design and implementation of VAW survey and through the WHO country consultation process for the prevalence estimates.

### Area 3:  Building VAW data demand and supporting its use for advocacy and evidence-based decision-making

The Joint Programme worked with global, regional and country partners in a range of activities that influenced the demand for VAW prevalence and administrative data, and promoted its use to advocate for policy and programmatic change.  User-friendly, accessible information products were produced and used to guide the formulation of policies and programmes to end violence against women (EVAW), and included contributing to high-level political commitments to EVAW, such as the Secretary General Political Engagement Strategy and the Action Coalition on Gender-Based Violence.

- These three areas constitute the three components identified as critical to both driving and sustaining the cycle of data demand-collection-availability-use that fosters evidence-based decision-making for the monitoring of programmes and policies to improve outcomes.

Figure 1 depicts the relationship between the Joint Programme’s three areas of work (dark blue circles), the cycle of VAW data demand and use (light blue circles), and the resulting development of evidenced-based programmes and policies that contribute to preventing and responding to violence against women: Methodology standards were developed by facilitating agreement among global experts, major players in the VAW data field, and country partners who promote them.  User-friendly guidance and tools based on these developed methods were produced and disseminated through capacity strengthening in regions and countries.  Supported advocacy efforts with key stakeholders at the global, regional and country levels enabled partners to leverage VAW data evidence for action to influence policy and programmatic change, that will eventually contribute to the global, regional, and country response to and prevention of violence against women.

Figure 1.  The pathway of influence between Joint Programme strategies (dark blue circles), the cycle of VAW data demand and use, and the prevention of and response to violence against women (adapted from MEASURE Evaluation’s conceptual framework for data demand and use to improve health systems).

# 2  Evaluation Approach and Methods

## 2.1 Evaluation Process

The evaluation design and process were guided by the UN Women Evaluation policy,  the United Nations Evaluation Group (UNEG) Norms and Standards for Evaluation, the UNEG Ethical Guidelines for Evaluation, and the UNEG Guidance on integrating gender equality and human rights in evaluations.  The evaluation was planned as an impartial, transparent, participatory and learning process that involved relevant UN Women and WHO staff, stakeholders, and partners at the global, regional, sub-regional and country levels. The evaluation process adhered to the four UNEG guiding ethical principles of integrity, accountability, respect, beneficence and was conducted in a transparent and inclusive manner that promoted trust and meaningful engagement.

The evaluation drew on the results of the end-term evaluation of the Women Count programme and recent evaluations conducted by the UN Women Independent Evaluation Service (IEAS), including the Corporate Evaluation of UN Women’s UN System Coordination and Broader Convening Role In Ending Violence Against Women, Evidence and lessons on types of UN Women support - A Meta-Synthesis of UN Women evaluations, and the Corporate evaluation of UN Women’s Flagship Programme Initiatives (FPIs) and the Thematic Priorities (TPs) of the Strategic Plan (SP) 2018–2021.

## 2.2 Evaluation Objectives

- Assess Joint Programme approaches and strategies in its three outcome areas.

- Gauge the results of the Joint Programme relative to the resources invested in it.

- Describe the performance of the UN Women and WHO collaboration in facilitating the achievement of programme outcomes, including programme design, implementation, and the combined effectiveness of the partnership including operational performance.

- Make concrete recommendations for how UN Women and WHO can build on the programme’s first phase, identifying successful strategies to scale-up and others to either modify or drop, based on lessons learned.

## 2.3 Evaluation Research Questions

The research questions were guided by the evaluation criteria of relevance, coherence, effectiveness, efficiency, impact and sustainability:

### Effectiveness of the Programme

To what extent did the Joint Programme contribute to the increased availability, accessibility and use of VAW data by implementing the strategies and activities in its three areas of work?

### Programme Impact

How did the results of the Joint Programme contribute to inform and influence national, regional, and global efforts to accelerate the achievement of EVAW-related global commitments?

### Relevance of the programme design

To what extent were programme activities appropriately designed to address identified priorities, including responding to changes due to circumstances that could not be anticipated?

### Programme Coherence

How well did Joint Programme strategies create synergies and interlinkages at the global, regional and country levels with other interventions on EVAW broadly and on VAW data in particular?

### Efficiency of programme approach and management

How did Joint Programme management systems, human and financial resources, and processes including ongoing financial monitoring and budget reallocations inform and contribute to or hinder the achievement of programme objectives?

### Sustainability of the programme

To what extent were the Joint Programme’s strategies to support the production, analysis and use of VAW data designed to last into the medium and long term?

## 2.4 Data used for the Evaluation

The evaluation was based on three sources of data that covered the full period of programme implementation:

- A review of 64 documents and publications, 27 of these were internal to the Joint Programme.

- Qualitative data collected through individual and group key informant interviews who were selected by UN Women and WHO.  Interviews covered how stakeholders worked with the Joint Programme, their views on what this work accomplished,, lessons learned, and their ideas of what activities should be included in a second phase.

- An online survey of external experts who worked with the Joint Programme as a participant in one or more of 11 of the 12 consultative processes, covering information similar to the interviews.

- All external experts who worked with the Joint Programme were invited to participate in the evaluation, either in a key informant interview or in the survey.

### Key Informant Interviews

Of the 48 Joint Programme stakeholders selected by UN Women and WHO for individual or group interview, nine were unavailable during the allotted time for data collection, leaving a total of 39 interview participants (33 women, 6 men) who are listed in Annex 1.  Participants were from UN Women and WHO HQ, UN Women Regional Offices (ROs), UN Women Country Offices (COs), all four institutions involved in the regional training consortia, UNFPA, UNODC, ESCWA, two EU-affiliated agencies (FRA and EIGE), FCDO, consultants, and participating experts in technical advisory groups and expert group convened by the Joint Programme.  Individual interviews were conducted with 25 participants and the remaining 14 were interviewed in groups of 2-4 people.  Interviews elicited information on Joint Programme work and contributions from the perspective of each participant’s role with the Joint Programme.  The content of the interviews reflected activity implementation from all years of programme implementation.  The interviews provided a rich context for programmatic results and detailed examples that demonstrated their effects.

### Online Survey

The survey was sent to all external experts (minus the 12 selected for interview) who participated in one or more of 11 of the 12 Joint Programme consultative processes, for a total of 93 potential participants.  A total of 26 people responded to the survey (28%).  The sample included at least one respondent from each of the consultative processes that were the basis of the survey questions.

## 2.5 Analyses

The three sources of data were triangulated and analyzed together to answer the evaluation research questions. Each data source offered information that was complementary to the others. The document review was used to understand programme background, design, strategies, planning, and to capture activity results.  The qualitative analyses used the perspectives offered by this diverse sample of Joint Programme stakeholders for insight into the context of these results. The data were coded based on deductive and inductive methods and analyzed to identify broader themes, using Atlas.ti v.9 software.  The online survey data were used to understand individual experiences as participants in the consultative processes.  The survey was developed and data were analyzed using Qualtrics software.  Survey results were integrated into the report where appropriate, and a more complete survey report appears in Annex 3.   Findings from programme achievements and lessons learned formed the basis for a set of recommendations for how the Joint Programme can best expand its work and deepen its impact during a second phase.

## 2.6 Management arrangements for the evaluation

The evaluation was managed by the Policy Specialist on Violence against Women Data and Programme Specialist on VAW Data and Research in UN Women HQ with guidance of the Independent evaluation Services (IES) and guidance and supervision from the UN Women Chief, EVAW Section. An internal Evaluation Reference Group (ERG) consisting of UN Women-WHO Joint Programme in HQ and the UN Women IES participated in the evaluation process to provide quality inputs and assurance, and contribute to the development of the final report, including development of the management responses.  The ERG provided substantial technical inputs, facilitated access to documents and served as key informants when needed, and ensured the high quality of the evaluation report.

# 3 Evaluation Findings

An exhaustive compilation of the Joint Programme’s technical and operational achievements resulting from the strategies and activities implemented over its four and a half year duration appears in the two tables in Annex 2.  Table A2.1 presents the technical results within the Joint Programme logic framework to show the specific accomplishments that contributed to the programme goal, three outcomes, and seven outputs. Table A2.2 is the compilation of operational results under the four themes: the unique contribution of the Joint Programme, collaborative partnerships and coordination, programme resilience (the ability to respond to change) and the Joint Programme response to the recommendations made at midterm. The results presented in these two tables are the basis and evidence for the findings presented in this section to answer the evaluation questions.

## 3.1 Effectiveness of the Programme

To what extent did Joint Programme strategies and activities under its three areas of work contribute to achieving its objectives?

## Finding 1: Joint Programme strategies and activities dramatically increased the availability and accessibility of VAW data and ensured it will continue to be collected, produced and used for years into the future

By implementing activities in in its three areas of work—developing methodologies, capacity strengthening, and data demand and use—Joint Programme work has both directly and indirectly increased the availability and accessibility of quality VAW data.  Newly derived and comparable global, regional, and national estimates of the prevalence of intimate partner violence, and regional and global estimates of the prevalence of non-partner sexual violence were produced and made available in user-friendly online platforms.  The agreed-on methodologies and measures that were collaboratively developed are already producing new VAW prevalence and administrative data and will continue to do so through existing commitments to using these measures in current and future efforts.  Capacity for the collection and production of VAW survey and administrative data has been strengthened in regions and countries.  The newly available data, along with increased capacity to collect, present, and use it, has fostered a growing demand for both survey and administrative VAW data in countries.

#### Key Results supporting this finding

- ‬In 2021, the Joint Programme produced and disseminated agreed-on, comparable prevalence estimates of intimate partner violence and at the national, regional, and global levels, and global and regional estimates of non-partner sexual violence (for the 2000-2018 period) in collaboration with the United Nations Inter-Agency Working Group on Violence against Women Estimation and Data, and with input and review of an independent technical advisory group.  The estimates were computed using robust statistical modeling methods from a range of existing survey data sources from 161 countries and areas, covering 90% of the world’s population of women and girls aged 15 and older. The estimates were disseminated through a series of global and regional events, publications including peer-reviewed papers in top journals (e.g., The Lancet), and user-friendly communications products, such as factsheets for the global, regional and country levels and infographics (3)).

  - The estimates are available in a WHO Global Database designed to accommodate updates and in a user-friendly, interactive data visualization platform launched in June 2021.  These house the estimates, the underlying survey data used to calculate them, and promote wide accessibility to these statistics by enabling users to generate maps, charts and tables (3,7).

  - Monitoring the 2030 Agenda for Sustainable Development:  These were the first VAW prevalence estimates within the SDG era (2015-2030) and the ones for intimate partner violence were accepted as a baseline for indicator 5.2.1  under SDG target 5.2 (7).

  - Evidence from some interviews suggested that the estimates were the most notable result of the programme and they were launched in strategic, high-profile ways that generated headlines on why VAW is priority in 2021: at a press conference at WHO and in an online presentation at the 65th Commission on the Status of Women. Other global and regional events based on the estimates followed (7).

- A total of 27 countries have collected VAW data with technical support from the Joint Programme, including nationally representative, dedicated VAW surveys (14 countries) and focused studies on particular forms of VAW, such as study of online violence in 12 countries in the Central Asia and Western Balkans region, and among groups missed in national surveys, such as The first-ever national-level survey on violence based on sexual orientation and gender identity in Nepal, and violence experienced by migrant women in Niger (7,8,9).

  - Newly developed/revised agreed-on methodologies and measures are currently producing new VAW data, and will continue to do so, expanding our understanding of VAW: Work in this area included exploring how to measure areas of VAW for which standardized measures had not yet been developed.  The Joint Programme conducted systematic and extensive reviews of existing information, in-depth data analyses and convened expert groups to provide technical guidance on methodological approaches and measures of different areas of VAW. These measures and methods are being used in data collection activities in countries and regions and are part of planning for future activities.

  - Countries conducted the Demographic and Health Surveys (DHS-8) and 15 countries using the revised versions of the WHO Multi-country study survey instrument will include and report on the newly developed, agreed-on measure of psychological violence. The work on these measures is ongoing  with the aim of strengthening the measures as well as their international comparability including for monitoring purposes (7).

  - Four countries will include the set of questions on violence against older women in their coming national VAW prevalence surveys.

  - The domestic violence module of the Demographic and Health Surveys (DHS) 8th version was revised to include never married women who had never lived with an intimate partner in both lifetime and recent (past 12 months) prevalence of intimate partner violence based on recommendations from Joint Programme work during the formal DHS consultation process (7).

  - The first-ever statistical framework for measuring the gender-related killing of women and girls (femicide/feminicide) developed in collaboration with UNODC  was endorsed by the United Nations Statistical Commission (UNSC) at its 53rd Session in March 2022, describing the agreed-on definition of femicide, which will be included in the second version of the International Classification of Crime for Statistical Purposes.  This framework, developed together with UN Women’s Center of Excellence on Gender Statistics in Mexico, provides a set of variables to allow measuring and reporting of femicide cases that occur in the public sphere by perpetrators beyond an intimate partner or other family member. Georgia is working with Geostat, the National Statistics Office (NSO) there, to align methodology on collecting femicide data with the Framework.

  - The Global Technical Guidance on VAW administrative data is being used in regions and countries working on VAW administrative data systems: Europe and Central Asia RO is promoting the guidance as an entry point to working on administrative data in the region; Georgia is using the guidance to develop a national concept of VAW administrative data in a participatory process including a broad range of stakeholders engaged in prevention and response; the Asia Pacific RO is using the guidance in the region in a large administrative data initiative, in particular to help bring in women’s machineries. The CARICOM countries are using the guidance to strengthen multi-sectoral VAW administrative data systems there. (3, 7) Uganda made significant progress in the justice sector (7); the Solomon Islands and Kiribati along with other countries in the region are developing cross-sector systems.

## Finding 2:  By spearheading the development and harmonization of methods and measures for new data collection and use, the Joint Programme has effected a transformative shift in the VAW data field

New methods  for measuring areas of VAW were developed collaboratively with experts in the field which will result in quality data to better our understanding of VAW. The Joint Programme revised existing and developed new global guidance on safety and ethical standards for collecting VAW prevalence data to keep pace with the current state of the field.

#### Key Results supporting this finding

- Global guidance on agreed-on ethical and safety standards for collecting VAW data in different contexts were developed and updated to respond to both the conditions imposed by the COVID-19 pandemic and the current state of the field. The Global Guidance Brief for VAW data collection within the context of COVID-19  was produced and disseminated along with The Decision Tree, a user-friendly tool depicting a simple pathway for deciding whether or not data collection to measure VAW prevalence should take place within the context of the COVID-19 epidemic. This tool, available in 15 languages, was produced by Joint Programme and UNFPA (3) and was remarked on as extremely useful to countries.  The 2001 and 2007 WHO recommendations on ethical and safety standards for the collection and use of VAW data was updated, including addressing the recent demand for remote data collection  during and following the COVID-19 pandemic (7).

- New standard methods, definitions and measures for specific types of VAW were developed to address existing gaps that will expand our understanding of VAW and enable cross-country comparisons of patterns and trends of psychological intimate partner violence, femicide, and technology-facilitated VAW and non-partner sexual violence.

  - A WHO checklist for planning surveys on the prevalence of intimate partner violence against women to ensure quality standards.  Challenges pertaining to data collection, analyses, and reporting practices of national and other surveys measuring VAW were identified during the VAW prevalence estimation process.  The Checklist was developed to help national statistical offices, other national research and data institutions, and research teams to think through the steps needed to produce quality survey data on intimate partner violence from survey planning to analysis, report write-up and dissemination of accurately interpreted findings.

  - A more precise method for measuring psychological intimate partner violence. Work in this area is ongoing and should lead to recommendations for how best to report psychological intimate partner violence in a way that is globally comparable for monitoring SDG 5.2.1.   The work was advanced by the Joint Programme through a review of instruments used to measure psychological intimate partner violence and thresholds for reporting globally, backed by extensive analyses of survey datasets from both high- and low- and middle-income countries. In addition to the two peer-reviewed publications, a Briefing note on Psychological intimate partner violence: data availability, methodological issues and recommendations for good practice is being finalized as part of the methodological resource package. This package, meant for researchers, national statistics offices and others involved in collecting data on violence against women, contributes to strengthening the quality and availability of violence against women data.

  - Development of a globally agreed definition of online and technology facilitated violence against women and girls began with a scoping review of existing proposed definitions and conceptual frameworks, and discussions on terminologies.  The results provided the background for an expert group meeting to inform quantitative and qualitative measurement tools to use in studies of online and technology facilitated violence against women and girls (7).  Many stakeholders (both those involved with the activity as well as others who knew about it) expressed that this work is both critical and timely, given the growing role of these technologies in the world today. An extensive state of the evidence scoping review was later produced in collaboration with the Ladysmith Collective and published in April 2023 to advance the understanding of the current status in the field of measurement of technology-facilitated VAW with the aim to inform subsequent consultations on methodologies for measurement.

  - An expert group meeting on strengthening the survey measurement of non-partner sexual violence in a standard way across countries was convened and resulted in updates to the WHO Multi Country Study questionnaire and a methodological briefing note on challenges and recommendations for good practice for measuring non-partner sexual violence is being finalized as part of a data and measurement package (7).

- Filling the gap on Leaving No One Behind in VAW data collection:  As per its strategy for developing new, agreed-on methodologies, the Joint Programme conducted extensive reviews of existing information on and convened experts specializing in VAW among groups not captured by ordinary surveys, as well as technically supporting surveys in regions where data is limited compared with others.

  - Measuring violence against women who are 60 years and older involved the development and cognitive testing of a survey module and interviewer guide to strengthen the measurement of violence experienced by older women.  The module was piloted in Ghana and will be cognitively- and pilot-tested in other  countries that have expressed interest. Additionally, a methodological Briefing Note on Measuring violence against older women: data availability, methodological issues and recommendations for good practice was developed.

  - Capturing violence faced by women living with disability: A scoping review and expert meeting led to recommendations on strengthening measurement of violence against women with disabilities, the inclusion of women with disabilities in violence against women research and ethical considerations for this (7). A Checklist to ensure inclusion of women with disability, and the topic of disability, in research on violence against women is being produced.  A methodological Briefing Note Measuring violence against women with disabilities: data availability, methodological issues and recommendations for good practice is also being produced as part of the data and measurement package.

  - Violence against LGBTIQ+ people: The Joint Programme collaborated with the Ladysmith Collective to conduct a scoping paper on violence based on sexual orientations, gender identities or expressions and sexual characteristics, that will provide the foundation for advocacy and further developments of specific methods and measures to be used in focused studies (7).

  - Facilitating dialogue on VAW prevalence data in the Arab States The Joint programme provided technical support for piloting the WHO Multi-country study questionnaire in Palestine, Morocco, and Egypt.  A meeting was organized to socialize the tool and tailor ethical guidelines for the region, where VAW data work is limited compared to other places.  Joint programme work in this area is opening up the dialogue on issues such as the barriers to asking about sexual violence (2, 3, 7).  In collaboration with ESCWA, the Joint Programme supported the English back-translation of ESCWA Violence Against Women Survey Implementation Toolkit, which is a complete questionnaire for a stand-alone survey based on the WHO Multi-Country survey that was adapted for the region. The back-translation is an example of how the survey was adapted to that specific context, which may be useful to those planning surveys in other contexts.

- Methodologies for collecting and using VAW administrative data has laid a strong foundation for increasing our understanding of VAW service use and response in regions and countries by providing agreed-on technical guidance based on international ethical and safety standards and technical support for establishing mechanisms and systems to collect, produce and use these data (7).

  - A Global Technical Guidance for VAW administrative data collection and use was produced in 2022 as the result of a comprehensive process that included a background synthesis, convening a dedicated technical advisory group as well as an expert group meeting to guide the work and come to agreement on definitions, methods, and approach, and consultations with several countries working on administrative systems to learn from successes and challenges (2,7).  It was an intensive learning process for all stakeholders involved.

  - The Joint Programme advanced the work on VAW administrative data by mobilizing momentum and interest from key stakeholders. Through the country consultations and participation in several high-level events during the development of the guidance, the Joint Programme was further positioned as the go-to global resource for VAW administrative data (7).

## Finding 3: The Joint Programme advanced country capacity for collecting, producing and using VAW prevalence data in line with globally agreed-on standards, triggering a momentum for ongoing demand for these skills.

Regional, institutionalized courses aimed at providing skills for a broad range of country stakeholders—such as National Statistics Offices (NSOs), women’s machineries, Civil Society Organizations (CSOs), and others—to collect, produce and use VAW prevalence data in line with global standards has provided a strong foundation for increasing regional capacity in the Arab States and East and Southern Africa regions. VAW data-related dialogue with and technical support provided to individual countries has increased understanding and experience on a global level.

#### Key Results supporting this finding

- The success of the regional training courses in the Arab States and East and Southern Africa Regions sparked continuing demand for capacity strengthening on VAW data.  The Joint Programme regional training consortia for the Arab States and East and Southern Africa regions are institutionalizing training courses for country stakeholders in academic centers.  The courses were preceded by workshops held in 2018-2019 that brought together NSOs, women’s machineries, CSOs and other country stakeholders that created initial momentum for further demand (1). The two consortia planned a 2-week workshop to pilot their respective curricula, identified and recruited participants from both regions, and conducted the workshops (7). Both workshops were very successful.

  - The high demand for this training was both stressed by the two regional consortia and demonstrated by the high number of applicants to each workshop and the continuing queries about future trainings since the end of them.

  - Using existing tools and based on agreed-on standards, the two curricula were developed to cover VAW survey design, data collection, analysis and use and were tailored for each regional context (7).

  - In Africa, participants worked in teams of two to develop a study protocol that included survey design and planning for data dissemination and use.  The success of this strategy was demonstrated when two of the participant groups presented their work at the Africa Joint AfDB-COMESA-PARIS21- UNECA -UN Women Regional Workshop on Gender Statistics.

  - The Arab States curriculum was piloted in the first ever course on VAW data in the region.  Relative to other regions, this region is characterized by a dearth of quality and comparable VAW data. The course was posted in English and in Arabic on Lebanese American University’s digital platform, the Blackboard platform, ready to be used or adapted in the future.  Interview respondents familiar with the region described the particular challenges to the collection and use of VAW data there, stating that work on VAW in general is challenging. Within this context, the course was described as an enormous success:

The mere fact that we could create the course with examples from the region…to choose people from different entities and train them, to have instructors from the region, to include a lot of people from statistical organizations and CSOs—it was an incredible win (for our region)

-Arab States regional partner

  - A network of regional experts was established in both regions through establishing mechanisms (WhatsApp groups), monitored by workshop facilitators, for workshop attendees to share knowledge and ideas. To date, forum participants have continued to identify and share resources and opportunities related to VAW data. The plan in both regions is to continue these networks by adding future workshop attendees to this first alumni cohort and establish peer-to-peer support, owned and maintained by the participants (7).

  - Both regional consortia worked on sustainability plans, but they are predicated on further funding.  In the Arab States, partners listed the possibilities that could take place with the course that is now on the Blackboard classroom platform including pitching it to a donor, using it as part of the minor in gender studies, and applying for a further grant as a consortia. In Africa, similar possibilities were mentioned including offering the course as part of its Virtual Academy, and offering the course as part of the ongoing degree programmes in both institutions.  Both consortia also stressed that institutionalizing a new programme involves a long enough term commitment from a donor.

‬

- Technical support provided by the Joint Programme at HQ to regions and countries has built capacity for VAW data collection.  As part of its capacity strengthening strategy, the HQ Technical Officers engaged with regions and countries in response to specific requests for advice on a range of VAW data collection activities. ROs and COs described this support as invaluable to facilitating their work. Some highlights of this work were:

  - The WHO country consultations on the estimates contributed to building country capacity for understanding and using VAW data on a global level by engaging in a dialogue over the estimates production and challenges of the underlying data.  WHO colleagues familiar with the process stated that it was worth the effort as the process resulted in building country level awareness, capacity and ownership of VAW data.  For example, discussions on the need for population-based survey data to measure prevalence versus the role of administrative/service data highlighted the need for conducting national surveys to understand the extent and magnitude of VAW in their countries, and discussions on the contribution of well-trained enumerators to data quality raised awareness about the importance of training enumerators in the future.

  - Technical support to the Europe and Central Asia Regional Statistical Officer over the years has enabled her to provide support and leadership for the multi-country study on online violence in the region. She described the advice from HQ as critical despite her expertise as a statistician because of the special requirements for the VAW data field.

  - Many Individual countries requested support from HQ for different VAW data activities, such as: a survey on violence and gender identity in Nepal, where the CO described the support as “generous and extensive”; administrative data work and a dedicated VAW survey that included cyber violence in Tanzania;  supporting the 2019 VAW survey in Morocco by providing expert insights on the survey tools..

- The regional training courses were designed to cover VAW prevalence data only; there is a need for a similar dedicated course on the M&E of administrative data  The East and Southern Africa partnership noted that there is a pressing need for building country capacity in the collection, production and use of administrative VAW data. The objectives for both regional training courses pertained solely to prevalence data collected in surveys, but given the time frame and financial limitations, it would not have been feasible to expand this to administrative data in a meaningful way.  Curricula for the M&E of administrative data in other areas such as HIV, which also address the coordination between multiple sectors were developed for two weeks workshops.

‬

‬

‬

## Finding 4: Joint Programme strategies pushed demand for VAW data at global, regional and country levels and facilitated its use to effect policy and programmatic change

An understanding of the value of data and how it can be utilized, along with the availability of sound data, are the fundamental elements needed to drive data demand.  Strengthening stakeholder capacity for data collection, analysis, interpretation, and use is what builds this understanding.  Capacity strengthening combined with access to quality data leads to sustained data demand in countries.  This is why the Joint Programme’s triple-arm strategy of developing globally agreed-on standards and methodologies to produce quality data, building capacity in regions and countries, and supporting data use has led to a sustained momentum for VAW data demand at the global, regional and country levels.

#### Key Results supporting this finding

- By facilitating country ownership of VAW data, the Joint Programme laid the foundation for global data demand:  The production of the new estimates for intimate partner violence and non-partner sexual violence has led to widespread availability and accessibility of quality VAW data.  The WHO’s mandated country consultation process with the 194 Member States to obtain their endorsement for the new estimates enabled an understanding of the meaning and importance of measuring intimate partner violence and non-partner sexual violence. This engagement inspired and motivated countries to collect more VAW data: many stated their desire to conduct a dedicated VAW survey. The cumulative effect of these engagements with so many countries has increased understanding of the need for and purpose of VAW data, creating a global momentum around the ongoing need for data on violence against women and girls.

- Creating political will for VAW data in countries by building consensus around how data can be leveraged to influence policy making and legislation. ‬ The Joint Programme’s engagement with countries led to an increased demand for VAW data collection, evidenced by a growing number of country NSOs expressing a desire to conduct VAW surveys.  In response, the Women Count initiative prioritized VAW data as part of its Phase II.  The NSO in Georgia‬ (Geostat) was described as “a champion for gender statistics” after years of VAW data technical support.

- The Joint Programme has laid the foundation for sustained VAW data demand by strengthening capacity in regions and countries by convening regional workshops, institutionalizing regional training courses, and providing extensive technical support on request to regions and countries.  This increased understanding, along with an awareness that the Joint Programme is a go-to for quality technical support, has further fueled the demand for VAW data and ensured that it will be sustained.

- Inspiring demand for VAW data in contexts where it has been limited:  Through the regional workshop, the institutionalization of the regional course on VAW data collection, analysis and use, and the discussions during the VAW estimates country consultations, countries in the Arab States region are demonstrating a new demand for VAW data.

- The Rapid Gender Assessments on the impact of COVID-19 on VAW were conducted in 13 countries in six regions by the Women Count Programme with technical support from the Joint Programme.

## ‬

## 3.2 Programme Impact

How did the results of the Joint Programme contribute to inform and influence national, regional, and global efforts to accelerate the achievement of EVAW-related global commitments?

## Finding 5: Joint Programme work has influenced global and national policies and programmes to better prevent and respond to VAW

Data are often produced, collected, analyzed, and described in a report that ends up sitting on a shelf.  There are many potential barriers to using data to push policy and programmes, as the process is complex and involves a range of stakeholders and technical skills.  Collected data have to be analyzed, interpreted and then transformed into easy to understand information, and that information must then be effectively delivered to key policy-makers and programme managers in countries.  Even when data are used well, it can take years to see legislative and policy changes, particularly at the global and national levels.  This is why the data use success stories documented here are notable for a four and a half year initiative.

#### Key Results supporting this finding

- Leveraging VAW data to inform global strategies: Throughout its programming period, the Joint Programme played a unique role in coordinating global partners for decision-making.  After the new prevalence estimates were produced and disseminated, the six UN co-custodians for SDG indicator 5.2.1. agreed that the national estimates for intimate partner violence would be used as a baseline for the UN Secretary General’s report starting in 2021 as they were the first such estimates to be produced during the SDG timeframe (3). This was remarked on as one of the Joint Programme’s most powerful contributions.

- The UN Secretary-General’s political engagement strategy to mobilize commitments and actions to end VAW during COVID-19 were informed by the global gender response tracker and the results from the Rapid Gender Assessments conducted to assess how the  pandemic impacted service-provision to survivors of violence that took place in nationally representative surveys in 13 countries spanning six regions with technical input from the Joint Programme.  Global advocacy using these data moved Member States to prioritize emergency responses during the pandemic to strengthen services. (3,7)

- Leveraging VAW data to effect national policy and programmatic change UN Women’s support for and close partnership with women’s machineries, CSOs, and other country actors has enabled country stakeholders to use their VAW survey data to successfully influence policy and programmatic change.(1,2,7,8).

  - Georgia: Results from a 2017 VAW survey that measured sexual harassment were used in lobbying efforts that culminated in passing a first-time bill on sexual harassment in 2019

  - Morocco: The 2019 VAW survey led to the revision of the National VAW strategy, adopted in 2021, and to draft the National Intersectoral Programme on Women’s Empowerment. (2,8)

  - Jamaica : VAW survey data were used to support the development of the National Strategic Action Plan against Gender-Based Violence 2017-2027. (1,8)

  - Albania:  Advocacy efforts using VAW survey data led to the establishment of the first rape crisis centre, and an amendment to the criminal code covering psychological violence. (2,8)

# 3.3 Programme Coherence

How well did Joint Programme strategies create synergies and interlinkages at the global, regional and country levels with other interventions on EVAW broadly and on VAW data in particular?

## Finding 6: The Joint Programme demonstrated remarkable leadership as a coordinating body and model of collaboration in the VAW data space

The Joint Programme forged numerous and varied partnerships at every level of its work.  Joint Programme activities were always conducted in collaboration with sister UN agencies and external partners to advance the elimination of violence against women.  UN agencies and other partners were convened around SDGs reporting, the estimation methods, methodological work on prevalence and administrative data, and capacity building on VAW data collection, interpretation and use.  In engaging experts in the field, ensuring strong diversity, and broad representation at the 12 convened consultative processes, the Joint Programme demonstrated the full potential of meaningful stakeholder engagement (7).

#### Key Results supporting this finding

- Two UN agencies working as one—a “showcase of genuine co-leadership:” The strength of the UN Women and WHO partnership that brought together the distinct and complementary expertise of both agencies to successfully speak with one voice was remarked on by numerous individuals who had worked with the Joint Programme.  Joint Programme HQ officers talked of recognizing each other’s strengths and having willingness trust, and open discussions.

The Joint Programme brought together the expertise and competencies of two organizations in a unique way to help create the demand for new data.

-External expert.

- Connections within both agencies were strengthened by Joint Programme work in the technical support provided by HQ ‬to regional and country offices on VAW survey data collection, understanding existing VAW data, using data as part of programme policy and design, and work on administrative data based on the Global Guidance (1,2,3,7).  This support was described as very helpful.

- Coordinating inter-agency collaboration and decision-making on VAW data:‬ The Joint Programme convened and coordinated the VAW Inter-Agency Working Group that brought together all the co-custodians for SDG target 5.2 indicators. This working group also supported the VAW estimates work. (1,2).

- Providing space for collaborative technical input on VAW data with over 100 leading experts: The Joint Programme engaged numerous technical experts through convening 12 different consultative processes to provide guidance and come to agreement on specific methodologies and areas of VAW.  ‬The consultative processes engaged people in a thoughtful way, promoting needed cross-fertilization (1,2,3,7).  Interview and survey participants both described the consultative processes as inclusive, transparent, and involving a broad, diverse group of experts and organizations who were leading the VAW data work in their respective area. The only negative comments were related to feedback after the meeting—some stakeholders expressed that they were not kept informed of next steps.  Examples of participants included in these mechanisms:

  - The technical advisory group (TAG) for the prevalence estimates included experts who worked on estimates for maternal mortality (another sensitive area difficult to measure), bringing in unique perspectives and lessons learned to the work from outside the VAW data field.  Other members of the TAG mentioned the value of bringing in these partners.

  - Similarly, EU partners were engaged in the consultations for the femicide framework and online and technology facilitated violence against women and girls, allowing for an exchange between experts working in Europe with those working in the Global South (7).

  - Other partners included academic institutions in the regional training consortia and individual experts from international research organizations such as the South Africa Medical Research Council  and the Sexual Violence Research Initiative, and Demographic and Health Surveys (DHS), multilateral and bilateral agencies; government agencies in countries; international NGOs and country-based CSOs; and leading individual researchers.

- Working with country actors in collecting, producing, and using VAW data: Work in countries engaged all types of actors, including Ministries of Health, country NSOs, women machineries, and CSOs (7) For example, in its work on administrative data, Georgia included all data producers engaged in VAW prevention and response—government agencies in health, justice/policing, and social services, Geostat, data users, the ombudsperson, and CSOs.‬

- Linkages with other VAW initiatives were both synergistic and complementary: The most prominent example in this area is the support the Joint Programme provided to Women Count’s global, regional and national level VAW data initiatives, particularly in the areas of data demand and use.  This collaboration led to the powerful examples of using VAW data to influence policy and programme changes in countries. Some examples of Joint Programme and Women Count collaborative work are:

  - Technical support on VAW prevalence surveys implemented in Morocco, Kenya, Uganda and Tanzania.

  - Advocacy work with and support for national partners to commit resources to VAW prevalence studies and to strengthen administrative data systems.

(Data use is) one area where there is really no distinction between Women Count and the Joint Programme, in the sense that, the work we do, we do it together… if we are doing a survey…we are working with the Joint Programme on analysis…dissemination and advocacy… the data use (examples) that we report…are relevant for the JP.

-Women Count HQ

Joint Programme work contributed to and was enhanced by other global initiatives such as Spotlight Initiative. In East and Southern Africa, APHRC contributed the training curriculum they developed under the Joint Programme and helped host a five-day workshop.  With the Joint Programme on Essential Services, the Global Technical Guidance on VAW Administrative Data was rolled out in three sub-regions: the CARICOM countries, the Europe and Central Asia and Asia Pacific regions. The Joint Programme provided technical support to ensure that the work was aligned with the global standards identified in the Guidance on administrative data (7).

## 3.4 Relevance of the programme design

To what extent were programme activities appropriately designed to address identified priorities, including responding to changes due to circumstances that could not be anticipated?

## Finding 7: Activities were designed to address current and emerging priorities—the response to unexpected developments demonstrated resilience and creativity

As mentioned in the Background section, the Joint Programme’s three areas of work are the components identified as the critical inputs to achieving its stated goal of making quality data more available.  Likewise, the activities that were implemented under these three areas, as well as those that were planned during the period of programme implementation, were key inputs to achieving its three stated outcomes.  Apart from the documentation in the monitoring and evaluation (M&E) field that supports this, the evidence presented in this report makes it abundantly clear that the Joint Programme succeeded in meeting its stated goal, outcomes, and outputs.  In fact, the collaborative component of these activities—particularly in coordinating and convening both key sister agencies and the leading experts into consultative processes to support each area of methodological development and capacity building—was fundamental to programme success and sustainability.

All programmes face unpredictable changes when implementing activities in the real world.  Political shifts and adverse events may impose unanticipated barriers to planned activities, while other factors such as the unexpected availability of funds may create the potential for new opportunities. The difference between a successful programme and others less robust is the ability to pivot and effectively respond to these challenges and opportunities as they present.  Evidence shows that the Joint Programme was particularly savvy in its responses to these changes.

#### Key Results supporting this finding

- As evidenced in this report, the Joint Programme was highly successful in making quality VAW data available and accessible, including for monitoring policy and reporting commitments, and in laying a strong foundation to assure its continues collection and use.  New methods have been globally agreed-on and promoted by those involved in their development, global, regional and country capacity to collect, interpret and use data to effect change has increased notably, and the produced data has been leveraged to advocate for change, resulting in policy and programmatic shifts towards better preventing and responding to VAW.

- The Joint Programme was initially conceived to focus on the improvement of the availability, quality and use of survey prevalence data.  Due to the forced cancelation of activities during COVID-19, funding was freed up, enabling the Joint Programme to respond to the demands from countries asking for standards and guidance for the production and use of multi-sectoral administrative data from agencies and organizations providing support to women survivors of violence (7).

- Regional training courses adapted to barriers including COVID-19.  The Arab States partnership planned an online course due to the security situation in Lebanon, but when conditions allowed for it, an in-person component was designed and implemented to supplement the online course, using saved funds, with their GWI partners participating online. Sessions were recorded to address the unpredictable electricity outages so participants could log in when they could.  The East and Southern Africa partnership originally planned to conduct two workshops, one for each of the two regions included (southern and eastern), but was limited by budget constraints, considering how the global pandemic had affected travel-related costs. Instead, participants from both regions were accommodated in a single workshop.

- The Ladysmith collaboration changed its workplan to respond to changing global priorities around online and technology facilitated violence against women and girls and provided the Joint Programme with the needed background research for the consultative process.

- The COVID-19 pandemic posed both challenges and opportunities: The pandemic began 18 months into Joint Programme implementation, affecting all of its work moving forward.   Face-to-face meetings and travel were restricted, and the urgency of response and recovery continued to overstretch government officials and other partners. Delays were encountered and activities had to be canceled, postponed, or redesigned. In years after the start of these difficulties, the Joint Programme leveraged new and existing opportunities to adapt plans to fit the changing environment.  For example, expert meetings were  shifted to online platforms to enable the continuation of work during the pandemic, and extra funding created by canceled activities was used to develop the activity stream on administrative data (3,7). As soon as safe to do so, starting in July 2022, meetings resumed in-person.

- In response to the urgent demand for VAW data collection during the COVID-19 pandemic, the Joint Programme responded by developing guidance (described above) on safety and ethical considerations for remote data collection on measure VAW, and collaborated with UNFPA to develop a simple tool that provided guidance on how to decide if and when such data could be safely and ethically collected.

- The Joint Programme was very responsive to recommendations made by the Mid-term Reflection Exercise to the extent possible under its limited budget.  The three recommendations prioritized in the fifth Steering Committee meeting in July 2021 were: 1) increasing programme visibility through more consistent branding and communications,2) resource mobilization efforts, and 3) proposed revision of the results’ framework (7).  In response, the Joint Programme:

  - More consistently included acknowledgements of the Joint Programme’s contribution to its products (e.g., the Global Technical Guidance on Administrative VAW Data and in peer review publications (such as  Sardinha ,et al.), but there were still some inconsistencies (e.g., the Femicide Framework).

  - Developed a communications strategy to expand its outreach of products to relevant groups of stakeholders. This included a tool for planning product dissemination at the time they are being produced.

  - Presented products at high level events, such as at the 5 day Joint AfDB-COMESA-PARIS21-UNECA-UN Women regional workshop on Gender Statistics in 2022 (the East and Southern Africa regional training curriculum, the Global Technical Guidance on Administrative Data, and the Femicide Framework).

## 3.5 Efficiency of programme approach and management

How did Joint Programme management systems, human and financial resources, and processes including ongoing financial monitoring and budget reallocations inform and contribute to or hinder the achievement of programme objectives?

## Finding 8:  The Joint Programme maximized impact on a small budget

The total budget for 4.5 year Joint Programme was USD $ 5,488,436, with USD $2,599,436 allocated to UN Women and USD $2,889,000 to WHO.  The combined effect of the many activities implemented under the Joint Programme has fundamentally changed the landscape of the VAW data field, but these changes will be felt most keenly only several years down the road when more surveys employ the developed methods to produce new data.   For example, many of the consultative processes facilitated by the Joint Programme resulted in a specific agreed-on shift in the way VAW will be measured.  The Joint Programme also engaged all the important players and experts who are moving the field forward—including the UN Statistical Commission, country NSOs, statisticians, and researchers—to engage on up-to-date, state of the art methods to collect and produce VAW prevalence and administrative data.

This means that in several years hence, VAW service data will be enhanced in countries working on their administrative systems, and survey data will capture the areas of VAW for which the Joint Programme developed new (e.g., for online and technology facilitated violence against women and girls, psychological intimate partner violence, violence against older women, violence against women with disability).  Some of these revised or newly developed measures are already being used in surveys, and others will be used in the future, producing data in the next several years.  Data from these surveys or studies will eventually be used to shape policy reform and programmatic design that will result in better VAW prevention and response.

- Given that the budget for a single venture to create a set of new measures could reasonably total $350,000  totaling just the consultative processes convened by the Joint Programme and excluding everything else that the Joint Programme did, it is clear that the investment was small relative to the results it produced.

‬

In some areas, the Joint Programme was operating under limited funds and lack of needed staffing at HQ.  There were intense time commitments required to support countries and only a small HQ team at both agencies (only two personnel) for activities such as the country consultations process on the prevalence estimates and the extensive technical support offered to regions and countries.  For example, lack of personnel  imposed barriers to programme visibility, which is dependent on a strong knowledge management strategy.  Interview participants in the Mid-term reflection exercise commented on the lack of visibility to the extent that several asked for clarification on the Joint Programme.   The type of knowledge management strategy that would benefit an initiative like this is expensive and requires dedicated staff to implementing it.  This was recognized by the Joint Programme in the communications strategy developed in 2022.

## 3.6 Sustainability of the programme

To what extent were the Joint Programme’s strategies to support the production, analysis and use of VAW data designed to last into the medium and long term?

## ‬Finding 9:  Sustainability was planned into activity design in all three areas of the Joint Programme, with the strongest success in methodological development (Area 1)

The developed methodologies, availability of quality data, and strengthened capacities, will continue to drive the cycle of data demand and use.   Both capacity strengthening strategies—the regional training institutes and technical support given to regions and countries—have built a strong foundation of newly skilled country actors. Joint Programme work has started a momentum of new VAW data collection, demand and use that will continue as the new methods and measures are employed in surveys and administrative systems.  However, additional resources will be needed to ensure continued sustainability.

- The Joint Programme used a process to develop methodologies and measures that can also lead to their consistent use, engendering the production of new data.   The processes engaged a broad representation of key stakeholders in a consensual manner to engender the promotion and use of these new measures in data collection activities.  The Joint Programme was very successful in this strategy.  Participants involved in these processes agreed that a diverse range of key stakeholders were included, and described the meetings as transparent, participatory, and relevant to the VAW data field.

- The regional courses on the collection, interpretation and use of VAW prevalence data are in the process of being institutionalized in universities, laying a strong foundation for the availability of ongoing training. Both partners expressed that they plan to run the courses as part of their regular ongoing training programmes.  The Arab States put their course on the Blackboard platform and it is ready to be pitched to a donor, incorporated in future projects, and used as part of the master’s degree in gender studies.  The course can also be adapted and tailored to specific countries in the region. The technical foundation for the continuation and growth of these training courses is strong, but there are no specific plans to repeat them due to the need for funding (expressed by both partnerships).  Both partnerships mentioned the strain experienced by existing staff due to the time commitments involved in the lengthy process needed to successfully host these trainings.

  - The network of regional experts has been established by the first cohort of training participants in both regions and has continued for a year.  Faculty in both training partnerships are monitoring this network, but the plan is to have two self-managed groups in the future, as more cohorts are added.

- As a result of long-term technical support, ROs and COs are able to offer advice on VAW data collection, including working with NSOs.  The best example of this occurred in the Europe and Central Asia Region, where the RO is supporting a multi-county study of online violence.  At the country level, the Georgia UN Women CO established a partnership with Geostat during the first VAW survey (2017-2018) and has been working with them on other activities, since with technical support from the RO and HQ. The experience gained by Geostat during the first survey and in the intervening years has translated into less need for technical support for the second survey currently being conducted.  The deepened understanding of how these data can be used has created data demand, and an expressed commitment to VAW data collection:

Even with huge turnover there is institutional knowledge in place, they (Geostat) have become champions of gender stats.

-Georgia CO

‬

# 4 Conclusions

The gathered evidence to support the nine findings shows that the Joint Programme has transformed the VAW data landscape, thereby contributing to ending violence against women. By working collaboratively with over a hundred key stakeholders in the VAW data space to come to agreement on definitions, methodologies, measures, and standards for VAW data collection in both surveys and country administrative systems, the Joint Programme has assured that these developments will be used widely to collect and continue to produce new VAW data. These agreed-on methods are already being used in new VAW surveys and in VAW administrative data systems being established and they will continue to be promoted by those involved in developing them.  The work in building capacity at the global, regional and country levels has created a worldwide increase in skills and expertise in the collection, production and use of quality VAW data.  These two strategies have triggered a growing momentum of VAW data demand.  Finally, the Joint Programme has made an impact on national and global policies and programmes by supporting and facilitating the use of newly produced VAW data.  In sum, the Joint Programme has met its goal of increasing the availability and accessibility of VAW data, making it possible to inform and improve programmes and policies to protect and respond to a greater diversity of survivors.

The Joint Programme used a strong project design by working in three areas that strengthened and reinforced each other.  Apart from opening up new areas of VAW measurement, the methodological work has contributed to Leaving No One Behind in the VAW data field by exploring and formulating agreed-on ways to capture violence against women who are marginalized in country contexts and  whose experience cannot always be captured by  surveys.  The two-pronged capacity building strategies have served to increase capacity in countries and regions to be able to better collect, utilize and interpret these measures.  Both these strategies have driven the demand for VAW data and contributed to the use of data to improve VAW prevention and response.

In producing and making accessible the first comparable, national estimates for the prevalence of intimate partner violence, the Joint Programme provided a baseline for monitoring progress on SDG indicator 5.2.1 and raised global awareness about the urgency of VAW by engaging with almost all Member States.  The newly developed methodologies and measures addressed current priorities and gaps in VAW data, such as the experience of violence among older women, or defining ways to measure femicide. These new and improved methods will soon begin yielding additional VAW data for areas that were less understood before. For example, the new measures for psychological intimate partner violence will be employed in the WHO Multi-country Study instrument (that countries use as a reference for their tools when conducting dedicated VAW surveys) and in the domestic violence module of the DHS which is currently implemented in 57 countries approximately every five years.  Further, with Joint Programme technical support, 27 countries collected their own VAW data.

The Joint Programme was a pioneer in the area of strengthening administrative data on VAW, and has sparked an ever increasing demand, evidenced by country requests for financial and technical support in this area.  The development work to produce the background paper and Global Guidance involved several countries and regions in consultations on their work in this area such as developing systems, coordination mechanisms within and across sectors, and data sharing protocols. The Joint Programme became a go-to resource for inter-sectoral administrative data work.  Regions, countries and individual stakeholders described how critical this work is, for monitoring and improving survivor response.

The coordination role of the Joint Programme was ubiquitous and the strongest aspect of the Joint Programme’s approach. Collaboration was foundational to all Joint Programme work.  Decisions were supported by the advice of experts in each specialized area of work. The many partnerships established by the Joint programme took place at all levels, from convening sister UN agencies to working with country NSOs.  Specific efforts were made to engage a broad and diverse range of experts, including those that lent perspective on the work from other difficult to measure fields.

The results under Finding 7 demonstrate how the Joint Programme was able to quickly and effectively respond to the various challenges that arose during implementation, often turning them into opportunities rather than allowing them to become bottlenecks that would stall progress.  This included managing the many changes and difficulties posed by the global COVID-19 pandemic. More funding would have enhanced the work in several areas.  The HQ teams were understaffed and dedicated an enormous amount of time to activities like the WHO’s country consultations and UN Women’s extensive technical support to regions and countries.  Larger budgets for the regional capacity training partners would have enabled the partners in East and Southern Africa to hold two workshops instead of accommodating all participants from both East and Southern Africa into one.  More staffing and budget at HQ would have allowed for a stronger knowledge management strategy that would have increased the visibility of the Joint Programme.

Finally, many aspects of the Joint Programme have continued beyond the programming period and will into the future. The extensive engagement with stakeholders and experts was also pivotal to the sustainability of the methodological work. Individuals and groups involved with the various aspects of the Joint Programme continue to promote the agreed-on methodologies for collecting and producing VAW data. The regional capacity strengthening strategy was planned for the long term, by institutionalizing VAW prevalence data training courses into academic centers that serve their respective regions. The courses were successfully launched in 2022, sparking a demand for more training that could not be met. The partners need more financial support to permanently establish and conduct regular trainings, but the foundation for their continuation is firm.

In sum, the Joint Programme met its programme objectives and exerted a large impact on a small budget.  The work has planted seeds that will continue to grow and change the nature of the VAW data field. The result is that quality VAW data from surveys and administrative systems can better be leveraged for evidence-based decision making for policy makers and programme managers to develop or improve policies and programmes to better prevent and respond to violence against women.

# 5 Recommendations

These recommendations are based on the findings and conclusions that were guided by the evaluation criteria, as well as the comments of stakeholders interviewed and surveyed, when asked about what work they considered was important to continue.

Recommendation 1:  To build on the success of increasing the availability of quality VAW prevalence data, continue to update the VAW prevalence estimates on a regular basis, advance the development of agreed-on methodologies and measures for the prevalence of different forms of VAW and in areas to address data gaps, including among marginalized groups to further expand the contribution on Leaving No One Behind.

Given the Joint Programme’s success in improving, developing, and promoting globally agreed-on methods and measures of VAW to address current gaps, this work should be further expanded to keep pace with the dynamic state of the field. For example, emerging developments such as the increasing awareness and urgency around technology-facilitated violence while adequately investing in improving the measurement and data availability of  better known forms of VAW, such as sexual violence, and violence against marginalized groups where significant gaps persist. The activity design involving experts and major players in specific measurement areas through consultative processes was one reason for the remarkable achievements demonstrated in this area—as the stakeholders involved in the collaborative work will continue to promote the use of its products.   Further methodological work should be conducted in a similar manner.

- Future planning should consider whether the collaborative work required by specific consultations can best be accomplished online, in person, or in a hybrid combination. The pandemic changed the way we work overall, particularly with regard to face-to-face meetings.  We learned that much can be accomplished through online platforms; they are less expensive and make it easier to include more people to attend. However, evidence suggests that some tasks may be more amenable to online working than others. The benefits and drawbacks should be carefully balanced when there is a choice, as for some types of work, there is no replacement for in-person group interactions. One participant described the in-person format for the online and technology facilitated violence against women and girls as critical:

The main goal was to create the definition…You can use the same techniques online as you would in-person, but there is an element (that is missing) online.  Discussions were more interactive and needed this because we are creating a new idea.

-Participating Expert

- When planning the consultative processes for methodological work, develop a feedback mechanism to inform participants about next steps.

Advancing the work on exploring measures to understand VAW in groups that are missed by surveys will further contribute to Leaving No One Behind, ensuring the future laws and policies will offer protection to all women.  This includes developing appropriate methodologies for reaching these groups, including trans women and women in same sex relationships while ensuring continued investment and   preserving the progress that has been made in measuring violence against women more broadly, as this only started to receive attention in the past 10-15 years.

Continued capacity strengthening initiatives are needed around the meaning and interpretation of VAW prevalence data to further increase understanding in countries.  Using prevalence data to monitor progress in this area is challenging as people generally expect rates to go down as things improve, and up when conditions deteriorate.  Women’s willingness to disclose their experiences in surveys is influenced by many factors including societal context and the quality of the interview.  In a country where progress in VAW prevention and response is being made, demonstrated by increased understanding about VAW and reduced stigma, more women may be willing to disclose their experience over time, resulting in possible upward trends or no change between survey periods. Countries need help to disentangle these effects.  Further, though this was discussed in the WHO country consultations, many stakeholders expressed that countries still struggle to understand the differences between survey and administrative data.

Recommendation 2:  Expand the work on administrative VAW data in select countries with a focus on including CSOs, and support this work by strengthening M&E capacity for administrative data in countries

The last few years have seen a surge of interest in administrative VAW data, particularly during the COVID-19 pandemic which put women at increased risk for intimate partner violence given the stay-at-home orders around the world. The Joint Programme was already leading the global work on administrative VAW data and has made significant in-roads in select regions (the CARICOM countries, Europe and Central Asia, and Asia Pacific), effecting a growing understanding in countries about the potential use of this data to improve service provision to survivors. Administrative systems can and should also be used to track prevention programmes in countries.

There are many barriers that need to be addressed in further work. Administrative M&E mechanisms are weak or absent, M&E capacity among those working in institutions and organizations that produce this data is low, and protocols for data sharing both within and across sectors are often lacking. When systems do exist, they usually cover government provided services exclusively, leaving out CSOs which provide the majority services to survivors in many places, leaving a large gap in VAW service data. CSOs also lack M&E capacity, and  if they collect data the quality is often low. Despite these challenges, the demand for administrative data to track services and inform policies and programmes is high and the Joint Programme has attained marked results by working with several regions and countries.

Pacific Island countries have made the type of commitment needed to establish quality administrative data systems. Though the specific context  (many small island nations) demands a particular approach, the work there can serve as an example of the type of effort needed for other places to do the same:  The project is a planned 5-8 year initiative that involves systematically putting together the elements of an M&E system that coordinates government sectors and CSOs involved in survivor response at the national levels and is supported by a large donor investment.

- In expanding its work, the Joint Programme should focus on feasible objectives. Given the large investments of time and funding needed to fully establish administrative systems in countries, it is critical that the Joint Programme establishes realistic objectives for work in this area.  For example, a focus on establishing strong coordinating mechanisms that involve all actors in all areas of VAW prevention and response, preferably led by women’s machineries with multisectoral mandates would do a lot to advancing the eventual development and sustainability of quality VAW administrative systems in countries.

- M&E capacity to collect, produce and use VAW administrative data needs to be strengthened in countries.  To support the work of developing and establishing systems to collect and produce administrative VAW data, country partners need to understand basic M&E principles and how to apply them for these systems to function well. Rapid changes seen in the M&E of HIV in countries two decades ago were driven by developing coordinated administrative data systems to cover both prevention and treatment initiatives and programmes coupled with a dramatic increase in M&E capacity among country partners to collect, produce and use quality data through regularly offered regional training workshops and individual technical support to countries, much like the model the Joint Programme is using for VAW prevalence data.

- In regions where measuring prevalence has been challenging, such as the Gulf Cooperation Council  states (Saudi Arabia, Kuwait, the United Arab Emirates, Qatar, Bahrain, and Oman) where there is no prevalence data available, stakeholders suggested that work on administrative data would be better accepted since it would focus on services, and could provide in-roads to engaging countries in discussions on the possibility of and need for measuring prevalence as part of the wider context of women’s health surveys (such as using a tool like the DHS).

- Given the development and global acceptance of the Femicide Framework, the Joint Programme should work with country partners in policing and justice to understand what is needed to promote its use (e.g., capacity building, systems or tools to ensure the collection of quality data, safety protocols that need to be in place, etc.)

Recommendation 3:  Provide support to the regional training partnerships to address current funding gaps and develop an exit strategy to ensure the sustainability of the VAW prevalence data course, and add a similar, dedicated course for the M&E of administrative VAW for each region.

The regional training strategy was planned with sustainability in mind. Both training courses were established in academic institutions who formed consortia with partners with technical experience, enabling for learning and exchange. Both consortia successfully conducted workshops, evidenced ownership, and developed mechanisms for participants to continue sharing ideas and opportunities after the workshops ended.  All of these factors are key to successfully preparing the way for these courses to continue into long-term, and as stated, both partners expressed their intention to do so.

However, achieving complete institutionalization of the courses with eventual self-generated funding requires a long-term plan including financial investment from the donor partner for at least a few iterations of the workshops. Because these workshops are aimed at country partners including CSO staff, and not students who expect to pay tuition, it is likely that at least a proportion of each workshop cohort will need financial assistance to attend. Despite the obvious commitment to continue these courses, both partners currently lack a realistic method to do so.

There are many avenues to establishing sustainable regional training programmes in partner academic institutions. While the course could be expanded into an entire degree programme or be integrated as a specialty track in an ongoing degree programme, given the primary objective of strengthening country capacity for actors who work for government agencies or CSOs, it is more realistic to initially plan for a recurring short course or workshop that is offered once or twice a year. The AiW mentioned several of these suggestions as possibilities for the future, with the caveat of applying for a grant to do so. During a second phase, the Joint Programme should engage the two training consortia to collaboratively plan for the long term, including a funding timeline that will see each partner into eventual independence.

The second part of this recommendation refers to the need for instituting a new course to increase country capacity in the M&E of administrative VAW data to support the Joint Programme work in regions and countries.  There are many existing tools and course curricula that can be adapted and tailored for VAW data.  For administrative data systems to produce quality data, individuals charged with collecting, reporting, interpreting, and using the data need understand the purpose, use and methods to do so, including the same safety and ethical standards that apply to the collection of prevalence data. The recommendations/guidance will need to be tailored to existing information systems and piloted and evaluated before full implementation.

Recommendation 4:  Intensify efforts to support women’s machineries, CSOs, and other key country partners to leverage VAW prevalence and administrative data to advocate for policy and programmatic changes to better prevent and respond to violence against women and girls

The purpose of collecting and producing data is to use it to inform policies and programmes. This is why the most powerful results documented for the Joint Programme are those illustrating how VAW data was leveraged and effectively used to inform the development and revision of policies and programmes at the global and national levels.  During a second phase, the Joint Programme should further this work that resulted from the synergistic relationship with the Women Count Initiative and with regional and country offices.  One of the most powerful examples of planning for data use at the time of data collection occurred in Morocco when CSO partners were trained as enumerators for VAW survey data collection along with those from the NSO, meaning that the individuals who would use the data to advocate for change had the capacity to understand it from the very beginning.

Another way of empowering CSOs and others to leverage data to inform and change policy and programmes is to employ the use of tools designed specifically for this purpose. Many stakeholders—particularly country offices, spoke to the need for such tools to facilitate this work. A comprehensive set of data use tools that were designed specifically for using health sector data can be easily adapted for use in any sector, such as The Framework for Linking Data with Action.  Another source for data use in the VAW arena was the manual for research on VAW published by WHO and Path. The Joint Programme should employ these tools in its work to facilitate data use in countries.

Where to focus these efforts should be determined by the availability of high quality data in places that have political environments prepared for this type of work.  For example, the recent survey of violence among LGBTIQ+ persons conducted in Nepal (data availability) was conducted within an environment of strong advocacy and the political will to engage on these issues; in this type of context, data use to leverage policy change is likely to succeed.  South Africa was used as an example of where intimate partner prevalence data was available via the DHS in 2016, but since there was no VAW law and little political readiness to engage, the results could not be used then in the same effective manner. This recently changed with the laws signed in 2022.

Recommendation 5:  The distinct identity of the Joint Programme within the gender statistics arena should be preserved; consider changing the name to The UN Women-WHO VAW Data Initiative

As noted under Programme Coherence, the Joint Programme and Women Count have worked closely and synergistically which was advantageous to both initiatives. Women Count has relied on the Joint Programme for technical support on VAW data activities since that specific expertise rests with the Joint Programme, but the Joint Programme struggled to maintain an identity that was distinct from Women Count in the eyes of many stakeholders. In anticipation of a second phase, the Joint Programme has now been reflected in the Women Count Phase II project document, while maintaining its own identity, enhancing coordination between both programmes (7).  Women Count has made VAW data one of its thematic  priorities in its second phase Apart from the technical exchanges, this new arrangement places the Joint Programme in a more advantageous position to mobilize resources, through the Women Count initiative, for a second phase (7).

We brought two worlds together within UN Women—the two fields are speaking to each other and exploring the opportunities and how to fill gaps (with complementary work)…it brought us a new day of action.

-UN Women HQ

‬

Within this new structure, it will be critical to preserve the distinct work and identity of the Joint Programme.  The understanding that VAW data is part of the gender statistics ecosystem is clear, but VAW data is also part of the EVAW ecosystem, and is unique in its requirements for data production, dissemination, and use.  The collaboration between UN Women and WHO has been successful in changing the landscape of the VAW data field due to the unique combination of expertise and experience needed to meet these requirements while expanding the availability of VAW data.  The need for this partnership to continue as a distinct entity was expressed by the majority of stakeholders interviewed and surveyed.

Maintaining the identity of the Joint Programme is critical to give visibility to the importance of reliable, comparable, data on violence against women and to maximize the value of bringing together WHO and UN Women’s distinct mandates, expertise and networks.

- Unit Head, WHO

‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬

Recommendation 6:  In planning for a second phase, resource mobilization should include a knowledge management and communications strategy to create a distinct identity for the Joint Programme and an M&E plan to better capture results

### ‬

Raising funds for the second phase of the Joint Programme will require strategic measures and the effective positioning of the programme's distinct contributions to the VAW data landscape and EVAW ecosystem. It is important to appeal to donors, showcasing Joint Programme results and impacts using both quantitative and qualitative data.  For example, the patterns and trends of the prevalence of intimate partner violence can be combined with impact stories that bring these numbers to life.  However, programme visibility and identity is critical to resource mobilization activities.

The Joint Programme succeeded in increasing its visibility after the mid-term reflection exercise and recognized the need for a logo, but programme implementation was due to end within a year. The Joint Programme can explore this in a second Phase. Visibility is predicated on the look and thoughtful dissemination of results products created by staff skilled in these areas, for which there was no budget during the first phase. The knowledge management products developed by the Women Count Programme are a good example of products that are designed in a consistent way to grab and keep your attention. The Joint Programme should develop a strategic plan for knowledge management and communications along with the budget and staff (i.e., a copy editor) for producing and disseminating its products.

# ‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬Documents Reviewed‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬‬

## Publications

Ellsberg M, and Heise L. 2005 .  Researching Violence Against Women: A Practical Guide for Researchers and Activists. Washington DC, United States: World Health Organization, PATH.

Foreit, Karen, Scott Moreland Anne Lafond. 2006. Data Demand and Information Use in the Health Sector: A Conceptual Framework. MEASURE Evaluation, University of North Carolina at Chapel Hill. https://www.measureevaluation.org/resources/publications/ms-06-16a.html

Heise, Lori, Christina Pallito, Claudia Garcia-Moreno, Cari Jo Clark. 2019. Measuring psychological abuse by intimate partners: Constructing a cross-cultural indicator for the Sustainable Development Goals. SSM Population Health. https://doi.org/10.1016/j.ssmph.2019.100377

Kendall, Tamil. 2020. “A Synthesis of Evidence on the Collection and Use of Administrative Data on Violence against Women: Background Paper for the Development of Global Guidance.” New York: UN Women. https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2020/Synthesis-of-evidence-on-collection-and-use-of-administrative-data-on-VAW-en.pdf

Kimote, John. 2022 (October).  Final Evaluation: Making Every Woman and Girl Count: Supporting the monitoring and implementation of the SDGs through better production and use of gender statistics (Women Count) Programme.  Final Draft (not for public citation)

Maheu-Giroux, M. Sardinha, L., Stöckl, H. et al. 2022. A framework to model global, regional, and national estimates of intimate partner violence. BMC Med Res Methodol 22, 159. Available at: https://bmcmedresmethodol.biomedcentral.com/articles/10.1186/s12874-022-01634-5#citeas

MEASURE Evaluation. 2011.  Framework for linking data with action. Chapel Hill, NC, USA: Carolina Population Center, University of North Carolina.  https://www.measureevaluation.org/resources/publications/ms-11-46-b.html

MEASURE Evaluation. 2014.  Strengthening Family Planning Programs with Data: Creating a Culture of Data Demand and Use. Chapel Hill, NC, USA: Carolina Population Center, University of North Carolina.  https://www.measureevaluation.org/publications/fs-14-120.html

MEASURE Evaluation. 2018. Assessing Barriers to Data Demand and Use in the Health Sector: A Toolkit. Chapel Hill, NC, USA: Carolina Population Center, University of North Carolina. https://www.measureevaluation.org/resources/publications/ms-11-46-a.html

Meyer, Sarah R Meyer, Molly E Lasater, Lindsay Lee, Claudia Garcia-Moreno. 2020. Measurement of violence against women and disability: protocol for a scoping review. BMJ Open Dec 24;10(12):e040104. doi: 10.1136/bmjopen-2020-040104.

Meyer, Sarah R., Heidi  Stöckl, Cecilia Vorfeld, Kaloyan Kamenov, Claudia García-Moreno. 2022. A scoping review of measurement of violence against women and disability.  PLoS ONE 17(1): e0263020. https://doi.org/10.1371/journal.pone.0263020.

Sardinha L, García-Moreno C, Guthold R .2022. Global estimated prevalence of physical and/or sexual intimate partner violence against ever-partnered women by, age, 2018. Journal of Adolescent Health. Available at: https://www.jahonline.org/article/S1054-139X(21)00689-3/fulltext

Sardinha, Lynnmarie, Mathieu Maheu-Giroux, Heidi Stöckl, Sarah Rachel Meyer and Claudia García-Moreno. 2022. Global, regional, and national prevalence estimates of physical or sexual, or both, intimate partner violence against women in 2018.  Lancet 399: 803–13.

Stöckl H, Sardinha L, Maheu-Giroux M, et al. Physical, sexual and psychological intimate partner violence and non-partner sexual violence against women and girls: a systematic review protocol for producing global, regional and country estimates. BMJ Open 2021;11:e045574. doi:10.1136/bmjopen-2020-045574

UNEG. 2014.  Integrating Human Rights and Gender Equality in Evaluations. New York: UNEG. http://www.uneval.org/document/detail/1616.

UNEG . 2016.  Norms and Standards for Evaluation. New York: UNEG. http://www.unevaluation.org/document/detail/1914

UNEG. 2020. Ethical Guidelines for Evaluation. New York: UNEG.  http://www.unevaluation.org/document/detail/2866

United Nations Office on Drugs and Crime (UNODC), UN Women.  2022.  Statistical framework for measuring the gender-related killing of women and girls (also referred to as “femicide/ Feminicide”).  https://lac.unwomen.org/en/digital-library/publications/2022/08/marco-estadistico-para-medir-las-muertes-de-mujeres-y-ninas-por-razones-de-genero-femicIndividualo-feminicIndividualo

United Nations Economic and Social Commission for Western Asia (ESCWA). 2021.  Violence Against Women Survey Implementation Toolkit: Complete questionnaire for a stand-alone survey, English version.  Beirut:  ESCWA E/ESCWA/CL4.SIT/2021/MANUAL.3

United Nations Entity for Gender Equality and the Empowerment of Women (UN Women). 2020. Evaluation policy of the United Nations Entity for Gender Equality and the Empowerment of Women .  Executive Board of the United Nations Entity for Gender Equality and the Empowerment of Women, Second regular session 2020, Item 6 of the provisional agenda.  https://www.unwomen.org/en/digital-library/publications/2020/08/evaluation-policy-of-the-united-nations-entity-for-gender-equality-and-the-empowerment-of-women.

UN Women. July 2021. UN-Women Strategic Plan. UNW/2021/6

https://documents-dds-ny.un.org/doc/UNDOC/GEN/N21/186/22/PDF/N2118622.pdf?OpenElement

UN Women 2022.  Eliminating Violence Against Women and Girls (VAWG) Data Coordination Training

https://africa.unwomen.org/en/stories/news/2022/06/eliminating-violence-against-women-and-girls-vawg-data-coordination-training

UN Women. 2022. Final Annual Report: Making Every Woman Count, Moving the needle on gender data.  Reporting period: August 2016-December 2021.

UN Women. 2023. Making every Woman and Girl Count Phase II Brief. https://data.unwomen.org/sites/default/files/documents/Publications/2023/WomenCount_PhaseII_Brief.pdf

UN Women, World Health Organization (WHO) and United Nations Population Fund (UNFPA). 2020. Data Collection on Violence against Women and COVID-19: Decision Tree. https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2020/Decision-tree-Data-collection-on-violence-against-women-and-COVID-19-en.pdf

UN Women and WHO. Violence against women and girls. Data Collection during COVID-19. April 2020. https://www.unwomen.org/en/digital-library/publications/2020/04/issue-brief-violence-against-women-and-girls-data-collection-during-covid-19

UN Women and WHO. 2022. Global technical guidance: Improving the collection and use of administrative data on violence against women. New York: UN Women. https://www.unwomen.org/sites/default/files/2022-10/Improving-the-collection-and-use-of-administrative-data-on-violence-against-women-en.pdf

UN Women and WHO. 2022. Why collection of administrative data is vital to end violence against women and girls.  Visual Summary of Global technical guidance: Improving the collection and use of administrative data on violence against women. https://www.unwomen.org/sites/default/files/2023-07/improving-the-collection-and-use-of-administrative-data-on-violence-against-women-visual-summary-en.pdf

UN Women and WHO. 2022. 15 Essentials for a survivor-centred design of violence against women administrative data systems. https://www.unwomen.org/sites/default/files/2023-07/improving-the-collection-and-use-of-administrative-data-on-violence-against-women-brief-en.pdf

UN Women and WHO. September 2022.  Joint Programme on violence against women data. (Final four-pager)

UN Women and WHO. 2022.  Untitled. (Communications strategy—6 pager).

UN Women and WHO. 2023.  Technology-facilitated violence against women: Taking stock of evidence and data collection | Publications | UN Women – Headquarters. https://www.unwomen.org/en/digital-library/publications/2023/04/technology-facilitated-violence-against-women-taking-stock-of-evidence-and-data-collection

UN Women Independent Evaluation and Audit Services. (IEAS). 2020. Corporate evaluation of UN Women’s Flagship Programme Initiatives (FPIs) and the Thematic Priorities (TPs) of the Strategic Plan (SP) 2018–2021. https://gate.unwomen.org/Evaluation/Details?evaluationId=11471

UN Women IEAS.  2021. Corporate evaluation of UN Women’s UN system coordination and broader convening role in ending violence against women https://www.unwomen.org/en/digital-library/publications/2021/06/evaluation-un-women-un-system-coordination-and-broader-convening-role-in-evaw

UN Women IEAS. 2022. Evidence and lessons on types of UN Women support: A meta-synthesis of UN Women evaluations. https://gate.unwomen.org/Evaluation/Details?evaluationId=11578

WHO. 2021. Violence against women prevalence estimates, 2018: global, regional and national prevalence estimates for intimate partner violence against women and global and regional prevalence estimates for non-partner sexual violence against women. Geneva: World Health Organization; License: CC BY-NC-SA 3.0 IGO.

Executive Summary  and Global Factsheet

Regional factsheets : WHO African region, WHO region of the Americas, WHO Eastern Mediterranean region, WHO European region, WHO South-East Asia region, WHO Western Pacific region

WHO. 2019.  Thirteenth General Programme of Work, 2019–2023.  Geneva: World Health Organization; WHO/PRP/18.1. https://apps.who.int/iris/bitstream/handle/10665/324775/WHO-PRP-18.1-eng.pdf

## Documents Internal to the Joint Programme:

African Population and Health Research Center (APHRC) and the University of Ghana. 2022 (November) Capacity Development on Violence Against Women Prevalence Survey (CaVAWPreS) in Eastern and Southern African Region Short Course:  Training Curriculum.

Bloom , Shelah S. in collaboration with the Joint Programme team at UN Women and WHO. August 2021. UN Women and WHO Global Joint programme on violence against women data.  Mid-term reflection Exercise.

Gender Statistics Imperatives in Africa. Regional Workshop Concept Note (September 2022).

Gender Statistics Imperatives in Africa. Joint AfDB-COMESA-PARIS21-UNECA-UN Women Regional Workshop on Gender Statistics 26-30 September Nairobi, Kenya.

Terms of reference for Leaving No One Behind and Violence against Women: Data Collection Policy Paper Series (online violence, VAW and LGBTIQ+, VAW and migrants)

UN Women and WHO.  Joint Programme on strengthening methodologies and measurement and building national capacities for violence against women data. Project document. 2018.

UN Women and WHO. 2018 Annual Report: Joint programme on violence against women data.

UN Women and WHO. 2019 Annual Report: Joint programme on violence against women data.

UN Women and WHO. 2020 Annual Report: Joint programme on violence against women data.

UN Women and WHO.  2021 Annual Report: Joint programme on violence against women data.

### Online and technology-facilitated violence against women and girls (VAWG)

Concept Note (draft): Foundational Expert Group Meeting on Online and technology-facilitated violence against women and girls

Agenda for EGM on Online and technology-facilitated violence against women and girls: Towards a common definition UN Women headquarters- New York, USA  15-16 November 2022

### VAW against women living with disabilities

Concept Note for Measuring disability and violence against women Expert meeting

Agenda for Expert Meeting on VAW and Disability

Background Paper : Expert Meeting on VAW and Disability November 10-11, 2022  Geneva, Switzerland

Guiding  questions for Expert Meeting on VAW and Disability

### Psychological Intimate Partner Violence

Agenda for Expert Meeting on psychological intimate partner violence

Background Paper 1: Mapping and Overview of Survey Instruments on Psychological Intimate Partner Violence

Background Paper 2: Patterns of Women's Exposure to Psychological Violence: A Global Examination of Demographic and Health Data from Low- and Middle Income Countries

Guiding questions for Expert Meeting on psychological intimate partner violence

### Ethical Guidance for VAW research

Concept Note for Expert Meeting: Re-visiting safety and ethical recommendations for in-person and remote research VAW Geneva, Switzerland July 2022

Draft Agenda: Expert Meeting: Re-visiting safety and ethical recommendations for in-person and remote research VAW

Background paper on Ethics and Remote Surveys on VAW, Expert Meeting: Re-visiting safety and ethical recommendations for in- person and remote research VAW

Annex 1. Summary of recommendations for ethical research into VAWG from existing guidance.

# Annex 1: Interview Participants

| Respondent Type | Name of Organization | Link with JP work |
| --- | --- | --- |
| UN | UN Women HQ | Joint Programme VAW Data |
| UN | UN Women HQ | Joint Programme VAW Data |
| UN | WHO HQ | Joint Programme VAW Data |
| UN | WHO HQ | Joint Programme VAW Data |
| UN | UN Women HQ | Women Count HQ |
| UN | UN Women HQ | Women Count HQ |
| UN | UN Women RO | Women Count -ESARO |
| UN | UN Women RO | Women Count -East and Central Asia |
| UN | UN Women RO | EVAW Regional advisor -ESARO |
| UN | UN Women HQ | EVAW Section Chief |
| UN | UN Women HQ | Donor relations FCDO |
| UN | UN Women HQ | Research and Data |
| UN | WHO HQ | WHO DDI (Data Dept) |
| UN | WHO HQ | Director of SRH |
| UN | WHO HQ | Technical Officer |
| UN | WHO HQ | Technical Officer |
| UN | UN Women CO | Admin data, prevalence survey |
| UN | UN Women CO | Survey on GBV LGBTIQ+ |
| UN | UN Women CO | Admin data, prevalence survey |
| UN | UN Women MCO | Admin data |
| UN | UNFPA HQ | GBV advisor |
| UN | UNODC HQ | Femicide statistical framework |
| UN | ESCWA | Expert: Regional capacity building |
| EU | EIGE | Expert: Admin data, femicide , Online and technology facilitated violence against women and girls |
| EU | FRA | Expert: Online and technology facilitated violence against women and girls and others |
| Donor | FCDO | Donor |
| Research | AiW -LAU | Regional course partner-Arab States |
| Research | GWI | Regional course partner-Arab States |
| Research | APHRC | Regional course partner-East and Southern Africa |
| Research | University of Ghana | Regional course partner-East and Southern Africa |
| Research | SVRI | Expert: Ethical guidance |
| Research | MRC South Africa | Expert: TAG phone surveys |
| Research | University of Munich | Expert: TAG estimates |
| Research | ICF International (DHS) | Expert: TAG estimates, psychological |
| Research | Ladysmith | Ladysmith papers collaboration |
| Consultant | Independent | Administrative Data |
| Consultant | Independent | WHO research |
| Consultant | Independent | Expert: TAG older women |

# Annex 2: Joint Programme Technical and Operational Results

Table A2.1 presents Joint Programme technical achievements that resulted from activities implemented during its 54 month duration, from 22 June 2018 to 31 December 2022, as evidence for how the Joint Programme successfully met its goal and three expected outcomes.  Results are organized by both the outcome area and result-level (impact/goal, outcome, output) to which they directly or indirectly contributed.  Impact-level results are presented under the goal and key results in each of the three areas are presented under their respective outcomes.  The results that served as inputs to the achieved outcomes are presented under the 7 outputs.

Table A2.2 presents operation accomplishments that reflect Joint Programme strategic planning around the process of activity development and implementation.

Sources documenting these results in both tables are cited using footnotes to specific sources, numbered sources for general programme documents as follows:  (1) 2018 Annual Report, (2) 2019 Annual Report, (3) 2020 Annual Report, (4) Joint Programme Results 2021 1 pager, (5) WC MTR, (6) Joint Programme Two Pager-Funding Gaps (23 September 2020), (7) 2021 Annual Report 2021, (8) Joint Programme Key Results and Next Steps 2022 (4 pager) (9) 2022 Annual Report Excerpt on Technical Support.  The results captured in the MTR used sources 1-6; results captured from the period since mid-term are cited in footnotes and sources 7-9.

## Table A2.1: Joint Programme Technical Achievements

| Programme Impact (Goal-level results): Quality, comparable data on different forms of violence against women are available and collected over time to address national data gaps and meet policy and reporting commitments under the SDGs, CEDAW and the Beijing Platform for Action |  |
| --- | --- |
| - Global, regional, and national agreed-on prevalence estimates for intimate partner violence, and global and regional prevalence estimates for non-partner sexual violence, were produced, strategically disseminated, and are widely available. Based on an agreed on protocol, estimates for intimate partner violence were derived for 161 countries and areas, covering 90% of the global population of women and girls (aged 15+ years): - Peer-review publication (2020) on the agreed-on process to produce the estimates on intimate partner violence and non-partner sexual violence. - Initial launch of the estimates at 2 high level events (2021):, 1) Press conference at WHO, 2) Online presentation at the 65th Commission on the Status of Women. Other global and regional events based on the estimates followed (7) - Publication and dissemination of the Report, stand-alone Executive Summary (available in the 6 UN languages), and a series of Fact Sheets (one global and one for each of the six WHO regions), a key messages document and video, slide deck and infographics. (3) - An interactive, user-friendly data visualization platform presenting these estimates and the underlying source data was launched in June 2021. (7) - Paper (2022) in The Lancet documenting and describing the revised agreed-on estimates has been cited over 100 times. - An infographic article on prevalence of intimate partner violence in adolescent girls in the Journal of Adolescent Health - A video on the key findings of the IPV and NPSV global, regional and national prevalence estimates was launched at the SVRI Forum, 2022 - documenting and describing the revised agreed-on estimates has been cited over 100 times. - Peer-reviewed paper (2022) in BMC Medical Research Methodology presenting in detail the framework to model the global, regional and national estimates of intimate partner violence A peer-reviewed paper on the global and regional prevalence of non-partner sexual violence submitted to and under review for the WHO Bulletin, Policy and Practice - Establishment and expansion of WHO Global Database on the Prevalence of VAW. The database includes all source data from national and sub-national surveys along with correlates, denominators ,and quality indicators forming the basis for the following comparable global, regional and national estimates: 1) recent (within the last 12 months) physical and/or sexual intimate partner violence among ever-partnered women and girls aged 15+ years from 161 countries, 2) lifetime prevalence of intimate partner violence among ever-partnered women and girls aged 15+ years from 154 countries, and 3) lifetime non-partner sexual violence among women and girls aged 15+ years for 137 countries. This database will be updated with estimates from new data, as they become available. (3,7) - Establishment and expansion of an interactive platform for the WHO Global Database on the Prevalence of VAW that is accessible to the public, policymakers, national governments, researchers, and international agencies. This is user-friendly visualization platform that presents the global, regional and country estimates of physical and sexual IPV and NPSV either in map or graph format. The data can be searched by country or by WHO, SDG, Global Burden of Disease (GBD) or World Bank regions, by type of violence, lifetime or past 12 months’ violence prevalence period and by 5- and 10-year disaggregated age groups. The platform continues to be expanded in terms of functionalities with additional visualization (chart, graphs and map) and data download options, as well as additional levels of data disaggregation. - A total of 27 countries have collected VAW data with technical support from the Joint Programme, including nationally representative, dedicated VAW surveys as well as special studies focusing on particular forms of VAW including VAW among groups not usually included in national surveys. - 14 countries received technical support from the Joint Programme to conduct dedicated national VAW surveys: Albania, the Bahamas, Georgia, Grenada, Guyana, Jamaica (also conducted a VAWQ costing study), Kenya, Morocco, Saudi Arabia, Senegal, South Africa, Surinam, Tanzania, and Uganda.(8,9) - 12 countries in the Central Asia and Western Balkans region are conducting a study on online violence: Albania, Bosnia and Herzegovina, Georgia, Kazakhstan, Kyrgyzstan, Kosovo, Moldova, North Macedonia, Serbia, Tajikistan, Turkey, and Ukraine (9) - VAW data among women facing multiple and intersecting forms of discrimination: The Joint Programme supported Nepal to conduct a survey of violence among LGBTQI+ persons and Niger to conduct a survey among migrant women. - New, agreed-on methodologies and measures will broaden our understanding of VAW by producing data to fill existing gaps:: - 15 Countries will include and report on the newly developed, agreed-on measure of psychological violence in their coming national VAW prevalence surveys.(7) - 4 countries will include the set of questions on violence against older women developed with support of the Joint Programme : Bangladesh, Mexico, Kazakhstan, Indonesia) - 3 regions and 4 countries are developing VAW administrative data systems using the VAW global guidance on administrative data: Asia-Pacific and Europe and Central Asia regions, and CARICOM, countries; Georgia, Kiribati , Solomon Islands and Uganda ;(3) - Leveraging VAW data for policy and programmatic change at the global and national levels - Monitoring SDG target indicator 5.2.1:The agreed-on national estimates for intimate partner violence were accepted by the UN co-custodians as the baseline against which to monitor progress for recent intimate partner violence. (7) - National policy and programmatic changes to improve VAW prevention and response were effected in 4 countries as a result of Joint Programme support to partners in leveraging VAW survey data for advocacy. |  |
| Programme Outcome (1): Measurement and methodologies for VAW data collection and use are strengthened and disseminated, including for national, regional and global monitoring and reporting requirements for SDG target 5.2 indicators |  |
| - Methodologies for measuring areas of VAW to address existing gaps were developed and accepted in collaborations with a diverse and broad range of leading experts in each particular area, both within and external to the UN system. - Statistical framework for measuring the gender-related killing of women and girls (also referred to as “femicide/ Feminicide”) was endorsed by the United Nations Statistical Commission at its 53rd Session in March 2022 and will be added to the International Classification of Crime for Statistical Purposes, ensuring comparable data for regional and global aggregates and trends analysis. - Strengthening and developing agreed-on, new measures of VAW where data gaps exist based on expert consultation processes (7) - Psychological IPV - Violence against older women (over 60) - Violence against women with disabilities - Guidance on data collection on VAW during COVID-19 and like situations that limit the possibility of in-person data collection was produced in two forms: - The Decision Tree is a user-friendly tool depicting a simple pathway for deciding whether or not VAW data collection should take place within the context of the COVID-19 pandemic and is available in 15 languages, produced by Joint Programme and UNFPA.(3) - A Global Guidance Brief for data collection on VAW within the context of COVID-19 was produced and disseminated. - A Global Technical Guidance on the collection and use of administrative data on VAW was published in 2022 based on an international collaboration and consultations with several countries making progress towards developing VAW administrative data systems. |  |
| METHODOLOGY STANDARDS Output 1. Selected methods and standards for data collection and analysis are reviewed or developed, including for measurement of psychological violence, violence against older women, violence and disability status, and disseminated to ensure improved coherence and harmonization to produce prevalence data on VAW, including for the SDGs global monitoring indicator | Prevalence Data Related - Updated WHO Multi-Country Study questionnaire and implementation tools are publicly available and accessible. - Psychological intimate partner violence: Identified key domains for the definition, improved measurement and reporting of psychological intimate partner violence (7) and a paper published on the new measure. An expert group meeting and several technical working groups were convened in 2021 and 2022. A paper on the comparability and psychometric properties of the two most widely used measures of psychological IPV, challenges and recommendations published. Ongoing work to develop recommendations on how best to report on psychological IPV given measures currently in use as well as recommendations of further strengthening and standardizing the measurement of this form of violence. A briefing note summarizing the challenges alongside these recommendations is in preparation. - Women living with disabilities: Explored measures through a scoping review for capturing the experiences of violence faced by women with disabilities. An EGM was convened in 2022. The protocol for the scoping review paper was published in 2020, the scoping review was published in 2022 (7), the expert meeting report is published and a briefing note is undergoing final review. - Older women: Developed core set of questions on the experiences of violence by women over 60 to be added to existing VAW surveys or as a module within surveys. A computer-assisted personal interviewing version of this module and a Question by Question Guide have been developed to accompany the Module (7). Module cognitively and pilot-tested in Ghana. A briefing note summarizing the measurement challenges and making recommendations for strengthening measurement and availability of data on older women (link forthcoming). - Online and technology-related VAW: At an EGM convened in 2021, developed globally agreed conceptual definition of online and technology-related VAW to inform future work on quantitative and qualitative measurement. - Updated and revised WHO existing ethics and safety guidance/documentation on collecting VAW prevalence data in surveys, including the use of remote methods, based on recommendations of the expert group convened in 2022 and other inputs; and specific guidance on collecting VAW data through phone interviews that was based on the RGAs. - Laying the groundwork for capturing new areas of VAW: policy papers series describing current evidence and data on: a) violence based on gender identity and sexual orientation; b) online and technology-facilitated VAW. Administrative Data Related - Agreement on the first-ever statistical framework for measuring femicide: A total of 67 institutions/organizations from 54 countries (national statistical offices, criminal justice entities, public health institutions, gender equality entities, civil society organizations, academia, and international organizations) helped define the statistical framework for measuring the gender-related killings of women and girls (also, femicide/feminicide) in 2021. - Consultative process with multiple countries to develop a technical global guidance to design, plan, and implement the collection, management, analysis, reporting, and communication of administrative data on VAW. (3) - Background synthesis on administrative data was published in 2020. - A user-friendly package of tools was developed to disseminate the Global Technical Guidance on the collection and use of administrative data on VAW. - A visual summary of the guidance - A 2-page brief on survivor-centered approach - An animation video on VAW administrative data - A Take Five interview and social media tile |
| HARMONIZATION Output 2. National, regional and global VAW prevalence data are presented in a consistent way by different agencies and used for the monitoring and reporting of the SDG target 5.2 indicators | - Revision of the DHS domestic violence module to include women in non-cohabiting relationships, that is, never married women who had never lived with a partner in the questions on both lifetime and recent intimate partner violence (previous versions only included women who had ever lived with a partner). - The updated 2018 VAW prevalence estimates developed using Bayesian statistical modeling methods, producing comparable national, regional and global prevalence estimates for intimate partner violence and regional and global estimates for non-partner sexual violence. - Psychological intimate partner violence: WHO Multi-Country Study instrument & the DHS domestic violence module were revised/reworded to reflect new agreed-on questions. (2) Empirical analyses are ongoing; a briefing note with recommendations for reporting of psychological intimate partner violence is being finalized. - Facilitated the back-translation of the Arabic ESCWA Violence Against Women Survey Implementation Toolkit into English: This is a complete questionnaire for a dedicated VAW survey that was adapted for that region from the WHO Multi-Country Study instrument. The English version makes this example of a context-specific adaptation available to a wider audience. |
| Programme Outcome (2): Capacity of countries to collect VAW data in line with globally agreed standards is increased |  |
| - The Joint Programme strengthened regional and country capacity for collecting VAW prevalence and administrative data in line with international standards by 1) establishing training partnerships that institutionalized training courses for country stakeholders in the Arab States and East and Southern Africa regions; and 2) becoming recognized as a dependable source for quality technical support for regional and country offices planning to collect VAW data. - The Arab States and East and Southern Africa regional capacity building consortia each successfully developed & piloted training curricula for courses on the collection, analysis and use of VAW prevalence data. The curricula were each tailored to the needs of their respective regions and successfully piloted in workshops.. - 3 regional workshops (Beirut, 2018; Dar es Salaam & Cairo, 2019) brought together participants from NSOs, women’s machineries, and other national and regional stakeholders from over 25 countries. - Extensive technical support provided by the Joint Programme to regional, multi-country, and country offices on collecting VAW data has built local capacity and benefitted a total of 27 countries (9). - The UN Women Europe and Central Asia RO has demonstrated increased in capacity for collecting VAW data: The technical support given by UN Women HQ to the Europe and Central Asia RO (a general statistician) has resulted in her gaining enough specialized expertise for her to support VAW data activities in the region. The RO is providing technical support and leadership for a multi-country study on online violence in 12 countries, and for a second dedicated VAW survey in Georgia (2022-2023). For measuring emerging areas that will expand on the Georgia 2017 survey 2017 survey, such as technology-facilitated violence, UN Women HQ is providing specific input to augment this support. - Georgia Geostat (the NSO) has been able to take on a stronger role in the second VAW survey than during the first one, due to the support from UN Women. - The Joint Programme became known as a go-to source for technical support on VAW data collection: Nepal reached out to the Joint Programme for help on their violence among LGBTIQ+ people because a colleague told the CO it was available and high quality. |  |
| REGIONAL TRAINING PROGRAMMES Output 3. Long-term training programmes for conducting VAW prevalence surveys and analyzing/interpreting results in line with global standards are developed and implemented in 2 regions | - The Joint Programme supported the organization of the 5-day Joint AfDB-COMESA-PARIS21-UNECA-UN Women regional workshop on Gender Statistics (2022). - East and Southern Africa Regional Capacity Building Partners piloted course curriculum in an in-person training workshop on collecting, analyzing and using VAW prevalence data in 2022: 25 participants from 11 countries in Eastern and Southern Africa attended.(7) - Arab States Capacity Building Partners piloted course curriculum in a training workshop on collecting, analyzing and using VAW prevalence data in 2022: The course was delivered in a hybrid on-line/in-person format and the course is now on a Blackboard Platform ready to be used, modified and expanded; 21 participants came from 8 different countries in the region. (8) - Regional Training in coordination with Spotlight Initiative: Following the two-week regional training, a 5-day training on collecting VAW data was held with participants coming from academia, civil society organizations, and government organizations. - Regional workshop on measuring SDGs/VAW with ESCWA & UNSD: Beirut 2018: Regional Experts from Women’s machineries, support national women machineries to address VAW. (2) - Regional workshops convene country NSOs & women’s machineries. Shared understanding on importance of VAW surveys & methods (plan, implement, analyze & use). Critical input to partnerships: UN Women, WHO & UNFPA hosted workshop in Dar es Salaam, July 2019: 51 participants, 9 countries (Ethiopia, Kenya, Malawi, Mozambique, Rwanda, South Africa, Tanzania, Uganda, and Zimbabwe). Cairo, October 2019: UN Women, WHO, UN ESCWA: 35 participants, 12 countries (Egypt, Iraq, Jordan, Libya, Mauritania, Morocco, Palestine, Saudi Arabia, Sudan, Syria, Tunisia, Yemen). Critical inputs to the development of the regional capacity component. (2) - Launch of the 2 Regional partnerships in Jan 2021: Through a Call for Proposals, The Arab Institute for Women (AiW) at the Lebanese American University (LAU) in a consortium with the Global Women’s Institute at the George Washington University, and the African Population and Health Research Center (APHRC) which has experience on VAW surveys with the London School of Tropical Health and Medicine, in a consortium with University of Ghana were selected. (3) |
| REGIONAL NETWORK OF EXPERTS Output 4: A network of experts from different disciplines and regions is established to support the implementation of VAW prevalence surveys | - Network of Experts Forum: The participants from both regional training workshops are participating in online forums (one for each region) to share advice and experiencing on VAW data work. These forums are being monitored by faculty at both institutions who. also provide input to questions |
| TARGETED TECHNICAL SUPPORT Output 5. Strengthen country capacity to design and implement surveys to measure VAW prevalence in line with globally agreed methodological, ethical and safety standards, by providing technical support | - WHO country consultations as part of new VAW prevalence estimates work: Provided opportunity for strengthening national capacity in 72/194 countries to explain the meaning and importance of the prevalence estimates for intimate partner violence and non-partner sexual violence. (6) The key objectives of consultation process were: 1) Review national modelled IPV prevalence estimate & data sources used; 2) request any additional eligible surveys/studies that could be used; 3) Familiarize countries w/ statistical modelling approach used to derive the estimates. (3) Two webinars presented to explain the estimates, data and methods with 125 participants from all global regions including professionals from NSOs, women machineries, Ministries of Health, other relevant ministries and SDG focal points (3) - Extensive technical support to regions and countries on developing/implementing VAW surveys and administrative data systems to ensure alignment with globally agreed-on methodological and safety and ethical standards on VAW data collection: Regional/Multi-Country Offices: Asia Pacific MCO: Development of VAW administrative data systems; Caribbean MCO: Design of an open online course on Gender Analysis of Prevalence and Administrative Data on Violence against Women and Girls (7); Europe and Central Asia RO: VAW survey methods including different types of VAW, design, ethical and safety standards, and for the multi-country study on online violence to take place in in 12 countries in the Central Asia and Western Balkans region: Albania, Bosnia and Herzegovina, Georgia, Kazakhstan, Kyrgyzstan, Kosovo, Moldova, North Macedonia, Serbia, Tajikistan, Turkey, and Ukraine. Country Offices: Kenya: design and training related to the domestic violence module in the coming DHS, explanations on the challenges related to definitions for measurement of certain forms of VAW, such as non-partner sexual violence; Tanzania and Zanzibar: Development of VAW administrative data systems; Uganda: Development of administrative data systems; Morocco: survey design (costing questions, interviewing men); Albania: survey planning, implementation, reporting;(2) Georgia prevalence survey data use with NSO & women’s machineries; Joint Programme helped with sexual harassment questions. (1), input to second dedicated VAW survey (7). Input to VAW data-collection in: Grenada, Guyana, Saudi Arabia, South Africa, Suriname, Tanzania, (2) and Senegal (9). Bahamas Technical inputs shared on the Bahamas WHS questionnaire, field operations manual, research protocol including discussions on the safety challenges and potential risks of using zoom and other telephone communications applications as planned. (7) Nepal: technical inputs to violence among LGBTIQ+ survey; Niger: Technical inputs to survey on VAW among migrants; Jamaica: VAW costing survey (9) - Technical support to Women Count Rapid Gender Assessments during COVID-19: Provided substantive technical inputs to the Rapid Gender Assessment Surveys conducted to explore the effects of COVID-19 on employment & income. The Joint Programme provided input on VAW safety questions and established TAG of experts to ensure ethical and safe data collection. - Facilitated the back translation into English from the Arabic regional VAW Toolkit with UN ESCWA (2) - Support from kNOwVAWdata to review and contribute to the curricula developed by the 2 consortia in Arab States and East and Southern Africa. (1) |
| Programme Outcome (3): Demand for and use of national VAW data for advocacy, policy and programming to end violence against women and girls is increased |  |
| - Results of national VAW surveys were used to advocate for VAW-related policy and expansion of services. UN Women’s support for and close partnership with women’s machineries, CSOs, and other country actors has enabled country stakeholders to use their VAW survey data to successfully influence policy and programmatic change (1,2,8). - Georgia: Results from a 2017 VAW survey that measured sexual harassment were used in lobbying efforts that culminated in passing a first-time bill on sexual harassment in 2019. (2,8) - Morocco: The 2019 VAW survey led to the revision of the National VAW strategy, adopted in 2021, and to draft the National Intersectoral Programme on Women’s Empowerment. (2,8) - Jamaica : VAW survey data were used to support the development of the National Strategic Action Plan against Gender-Based Violence 2017-2027. (1,8) - Albania: Advocacy efforts using VAW survey data led to the establishment of the first rape crisis centre there, and an amendment to the criminal code covering psychological violence. (2,8) - The availability of the agreed-on global, regional national estimates for intimate partner violence and global and regional non-partner sexual violence among women and girls aged 15+ has pushed the global demand for VAW data. The WHO country consultation process included dialogues on the meaning and importance of the prevalence of intimate partner violence and non-partner sexual violence. The cumulative effect of these engagements with so many countries has increased the global understanding of the need for and purpose of data on violence against women and girls, creating a new demand for these data. |  |
| AWARENESS AND ADVOCACY Output 6: Increased awareness raising and advocacy at global, regional and country levels among governments, NGOs, including women’s organizations, academia and other relevant stakeholders, of the relevance of VAW data and the available methods and standards. | - Two publications are being prepared in addition to the several listed above under impact: 1) the association between child marriage and IPV among adolescent girls and 2) Trends for physical and sexual intimate partner violence. - Technical support to global initiatives: Contributions were made to the Secretary-General and the United Nations system-wide advocacy through information provided to the April 2020 Secretary-General Policy Brief on The Impact of COVID-19 on Women. (3) - COVID-19 Global Gender Response Tracker: In 2020, UN Women and UNDP co-created the Gender Response Tracker, a publicly accessible global monitoring tool that assessed the COVID-19 response from a gender perspective, and provides data to inform advocacy, policy and programming at global, regional and national levels. Joint Programme officers provided technical support to the tracker, and there is ample evidence documenting its use. (7) - Gender-Based Violence Action Coalition Global Indicator Framework: The Joint Programme provided technical inputs to the draft target and indicator framework as well as the data and research agenda to fill the gaps and needs over the next 5 years. (7) - Regional workshops 2018-2019: raised awareness of issues connected to and provided opportunity for advocacy for VAW data in respective regions; 2019: Dar es Salaam & Cairo, (2) Beirut (Women’s machineries) (1). - Participated in a Global & Regional Workshop 2018: UN World Data Forum in Dubai, United Arab Emirates; Regional Meeting: Collection of data on violence against women: Where do we stand? jointly organized by the Organization for Security and Cooperation in Europe and EIGE in Sarajevo, Bosnia, and Herzegovina. (1) - Rapid gender assessments (RGAs) on the impact of COVID-19 : Developed an interactive data dashboard on the Women Count Data Hub to improve accessibility of the VAW RGA data, increasing awareness of the importance of VAW data to inform EVAW policies. Joint Programme officers provided technical support to the RGAs. - In collaboration with Women Count, the Joint Programme conducted country and regional briefings sharing preliminary findings with national stakeholders before its release during the 16 Days of Activism. Country/regional briefings brought together over 100 national stakeholders from national women’s machineries, NSOs and in some cases civil society organizations. - Several countries expressed interest in using the findings, including Paraguay, Thailand, Jordan, Albania, Morocco, Bangladesh, Columbia, Kenya. (7) - Country profile for each of the 194 countries represented in the national estimates for the prevalence of intimate partner violence: Country profile for each of the 194 countries (and the occupied Palestinian territory) including available data sources (2000-2018); surveys/studies that were excluded; covariates for adjustment and odds ratios for the adjustments (if any) and their 95% confidence intervals; modelled fits for lifetime and past 12 months prevalence of intimate partner violence among ever-partnered women aged 15-49 years and aged 15 years and older; and the modelled national estimates (3) |
| DATA DEMAND & USE Output 7: Increased data demand & use at the global, regional and country levels as a result of advocacy with global partners and country governments, NGOs, including women’s organizations, academia and other relevant stakeholders. | Pushing Data Demand - Regional capacity strengthening Workshops (2019: Dar es Salaam & Cairo) built demand for VAW data in respective regions. (2) - The East and Southern Africa and Arab States regional training workshops triggered high interest and demand for VAW data and capacity building in both regions. - UN-Women CO in TZ facilitated a dedicated VAW survey in response to the Prime Minister’s request for new data to support drafting new VAW policy. - Several countries expressed the desire for conducting dedicated VAW surveys during the WHO country consultation process. Facilitating Data Use - Informing global political engagement with data collected by service providers & CSOs, and COVID-19 rapid gender assessments. (3) - UN Women supported multiple user-producer dialogues and other strategies to help women’s machineries, CSOs, government and other country stakeholders use recently collected VAW data for policy and programmatic change. (3,7,8) |

## Table A2.2: Joint Programme Operational Achievements

| Area of Programme Operation | Achievements |
| --- | --- |
| Unique contribution of the Joint Programme to EVAW |  |
| - The Joint Programme has advanced the agenda on VAW data to end violence against women: The Joint Programme worked collaboratively with over a hundred key stakeholders in the VAW data field to develop many new or revised agreed-on definitions, methodologies, measures, and standards for VAW data collection in both surveys and country administrative systems. The developed methods address current/previous gaps in VAW data, such as the experience of violence among older women, or levels of femicide in countries. These agreed-on methods are already being used in new VAW surveys and VAW administrative data systems and will continue to be promoted, resulting in the availability of data to ensure that programmes and policies protect and respond to a greater diversity of women and girls. - The Joint Programme is a distinct initiative in the VAW data field and the wider EVAW landscape, bringing together the distinct and complementary experience and expertise of UN Women and WHO. The two agencies joined forces to design and implement the combination of strategies and activities that successfully increased the availability of VAW data. The Joint Programme can be positioned as the key leader in expanding the collection, production and use of VAW data at the global, regional, and country levels. (7) |  |
| Collaborative Partnerships and coordination |  |
| Two U.N. Agencies Delivering as one | - Strong, unified collaboration leveraging the complementary skills and expertise and networks of UN Women and WHO with a clear division of labour (1,2,3,7) |
| Stronger links between HQ and regional/country offices within UN Women and WHO as a result of Joint Programme activities | - UN Women HQ is becoming recognized as the go-to resource for regional and country offices involved with VAW data-related activities. - WHO country consultation process for the revised VAW estimates provided opportunities for country and regional offices to engage with WHO HQ. |
| Twelve technical working collaborations that included over 100 leading international experts and other key stakeholders to develop and promote agreed-on methods, measures and standards to advance VAW data and research | - United Nations Inter-Agency Group - The UN Inter-Agency Working Group on Violence Against Women Estimation and Data (VAW-IAWGED) a UN initiative comprising WHO, UNICEF, UNFPA, UNODC, UNSD and UN Women (co-custodians of SDG Target 5.2) contributes to monitoring progress towards the achievement of this Target and UN Sustainable Development Goal 5. WHO, on behalf of the VAW-IAWGED has the function to produce and update the inter-agency estimates on the prevalence of violence against women including the 2018 prevalence estimates on intimate partner violence and non-partner sexual violence - SDG Indicators 5.2.1 and 5.2.2 respectively; - Technical Advisory Groups - An independent Technical Advisory Group (TAG) to the VAW-IAWGED support WHO’s role in the inter-agency working group, provide independent evaluation of the scientific, technical and strategic aspects relating to violence against women measurement and estimation methods, oversee and guide the methodological work for deriving the global, regional and national estimates for IPV and NPSV and, advise on strategies in relation to the effective dissemination and use of the violence against women estimates and related products. WHO Secretariat Members that produce WHO’s maternal mortality estimates are also involved in the consultations. - Regional Training and Capacity Strengthening - Phone surveys to collect data on VAW for the RGAs on VAW conducted during COVID-19 - Expert Group Meetings - Administrative data—background synthesis - Administrative data—Global Technical Guidance - Online and technology-facilitated VAW - Psychological intimate partner violence - Violence against women and disability - Violence against older women - Safety and ethical recommendations in researching VAW - Femicide - Non-partner sexual violence |
| Partnerships with academic and data institutions, including a focus on 2 regions, to increase VAW data capacity strengthening | - Demographic and Health Surveys (DHS), South African Medical Research Council, Sexual Violence Research Initiative - WHO in collaboration with the Pan American Health Organization (PAHO) and the London School of Hygiene and Tropical Medicine submitted revisions relating to the wording of questions and items measuring psychological/emotional IPV and non-partner sexual violence as well as appropriate use of denominators for non-partner sexual violence through the DHS-8 Questionnaire Consultation process conducted in March 2019. (2) - 4 academic institutions comprised the two regional training consortia for the Arab States and East and Southern Africa regions: Global Women’s Institute of George Washington University, Arab Institute for Women of the Lebanese American University; African Population and Health Research Center and the University of Ghana. (2) |
| Other UN-interagency collaboration | - Inter-Agency Working Group on VAW Data and Estimates, including of all the co-custodians for SDG target 5.2 indicators, i.e., WHO, UN Women, UNFPA, UNICEF, UNODC and UNSD. - UN Economic and Social Commission for Western Asia (ESCWA), the Economic Commission for Africa for capacity strengthening in Arab States and East and Southern Africa. - UNFPA: Development of the Decision Tree, kNOwVAWdata Initiative reviewed and contributed to the curricula developed by the regional training consortia. - Close collaboration with UNODC and its Center of Excellence, and UN Women’s Global Centre of Excellence on Gender Statistics (CEGS) on improving collection, comparability and amplifying the scope of data on femicide. - PAHO for the DHS revision (see above) |
| European Union | - European Institute for Gender Equality (EIGE) - European Union Agency for Fundamental Rights (FRA) |
| Other VAW initiatives | - Joint Programme on Essential Services for VAW survivors - Women Count - Spotlight initiative - kNOwVAWdata - The VAW administrative data and femicide activities coordinated with efforts led by other initiatives, such as the Spotlight Initiative in Latin America; engaging the former Special Rapporteur on violence against women and its causes and consequences in the Europe and Central Asian region to determine next steps to support the establishment of femicide watches (7) - Links between administrative data & measurement of femicide and coordinated work at the regional level, including: Spotlight Initiative in Latin America, with the technical leadership of the Economic Commission for Latin America and the Caribbean and engaging the former Special Rapporteur on violence against women and its causes and consequences in the East and Central Europe region to draw a road map determining ways forward to support the establishment of femicide watches in the region. |
| Joint Programme resilience: creative response to arising challenges |  |
| COVID-19 canceled activities and imposed restrictions on travel | - In response to the demand for VAW data in the unique context of the COVID-19 pandemic, the Joint Programme produced guidance on collecting data during the lockdown and the Decision Tree tool. Safety and ethical principles for VAW data collection were updated to address the use of virtual methods. - TAG and EGM in-person meetings were moved to virtual format. - Country consultations on the VAW estimates carried on despite the challenges with the time line and follow-ups being adjusted to accommodate the re-purposing of country VAW data focal points, especially Ministries of Health to COVID response activities. - In response to COVID-19, the regional training programmes prepared to deliver virtual trainings, but in-person trainings and travel were possible by the time the workshops were ready to be delivered in summer of 2022: East and Southern Africa delivered a two week in-person workshop; Arab States developed a hybrid course to enable in-person participation and still ensure the safety of participants due to security concerns in Beirut. - The work on administrative data was initially developed to use funding from canceled activities, and expanded as opportunities for regional and country work presented (e.g., Asia Pacific MCO, Jamaica). |
| Joint Programme Response to Recommendations made at Mid-term |  |
| Increase visibility to position the Joint Programme for future funding | - Joint Programme knowledge management products were presented with its logo or with specific acknowledgements (e.g., peer review publications) - Joint Programme Products/work was presented at high-level visibility global and regional events and - 3 Joint Programme products were presented at the 5 day Joint AfDB-COMESA-PARIS21-UNECA-UN Women regional workshop on Gender Statistics (2022): 1) the ESA regional course curriculum on collecting, analyzing and using VAW prevalence data; 2) The Global Technical Guidance on Improving the collection and use of VAW administrative data; 3) the Femicide framework. - Development of the Global Guidance on Administrative Data was presented: Presentations of the development of the global guidance at forums co-organized with Governments in Mexico and in the Western Balkans and Turkey region and during the regional partner technical workshops in the Arab States and East and Southern Africa with key partners promoted the work of the Joint Programme on VAW administrative data for global audiences. (7) - The Joint Programme and Women Count: Gender data was elevated as a cross-cutting Systemic Outcome of the UN Women 2022-2025 Strategic Plan, and the work of both UN Women programmes are integral to achieving this outcome. The two programmes have already worked together—particularly in data use for policy and programmatic change in countries—the Women Count examples of data use presented in its final annual report are also the results of Joint Programme work. The Joint Programme provided input to the Phase II Women Count project document. The Joint Programme will retain its distinctness as the VAW data initiative within the wider gender statistics project. |
| Expand on administrative data work | - The Global Guidance was released and used in 5 countries in 3 regions. |
| Minor changes to the results framework to better align with Joint Programme activities | - Modifications were made and multiple results have been captured under the revised outcomes and additional output. |
| Further development of collaborations with ROs | - UN Women strengthened their collaborations and connections though technical support and dialogue with the Asia Pacific, Europe and Central Asia, and East and Southern Africa regions |
| Develop a resource mobilization plan for a second Phase | - Women Count and the Joint Programme will join together in mobilizing additional resources for a second phase. |

# Annex 3: Expert Survey Report

This section describes the methods and results of the online survey of external experts who worked with the Joint Programme by participating in one or more consultative processes.

## Methods

All external experts who worked with the Joint Programme were invited to participate in the evaluation.  WHO and UN Women selected 12 experts for individual interview; the remaining 96 experts were included in a short, anonymous online survey.  The aim of the survey was to understand their experiences as experts working with the Joint Programme as participants in one or more of the following technical consultative processes.

- TAG on Administrative Data on Violence Against Women—Background review & Global Guidance (Administrative data)

- Regional Training TAG: Regional Capacity Strengthening on Measurement of Violence against Women in the East and Southern Africa and Arab Regions (Regional Training)

- Expert Group Meeting on Online and technology-facilitated VAWG: Towards a common definition (Online and technology facilitated violence against women and girls)

- Expert Group Meeting on Violence against Women and Disability (Disability)

- Expert Group Meeting on Re-visiting safety & ethical recommendations for in-person & remote research violence against women (Ethical & safety)

- Technical Advisory Group on  Phone surveys to collect data on VAW for the rapid gender analyses on VAW conducted during COVID-19 (RGA)

- Ladysmith papers (Ladysmith)

- Expert Group Meeting on Measurement of psychological intimate partner violence (Psych IPV)

- Expert Group Meeting on Violence against older women (Older women)

- TAG to the Inter-Agency Working Group on VAW Estimates and data (Estimates)

- UN Inter-Agency Working Group on VAW Estimates and data (Inter-Agency)

Qualtrics software was used for the survey which was left open for 5 weeks after the initial email.  A reminder email was sent one week before the survey closed. The survey asked respondents to rate eight items to describe their experience in the consultative process(es) in which they participated.  Experts who participated in multiple consultations were asked to rate the same 8 items for up to three different consultations.  The items were presented in a six-point Likert scale for how strongly they agreed or disagreed that:

- The consultative process (i.e., selection of participants, meeting objectives, agenda, the meeting itself) was transparent;

- The consultative process used a participatory approach;

- The consultations included a diverse range of experts;

- The area of work was relevant to the VAW data field;

- The objectives of the consultation were met;

- Participants were Informed of next steps following the meeting;

- Participants were Informed about the outcomes of the process;

- The resulting tools/methods developed will advance the field of EVAW.

Participants were given the option to comment on each set of ratings they provided and to provide suggestions on what work would be most strategic for the Joint Programme to plan in for a second phase.

## Results

### Survey response

The survey was sent to 96 experts; 26 responded before the survey closed.  One expert sent open-text answers by email after the survey closed and these were included in the comments.  There was at least one respondent linked with each of the 11 consultative processes listed.

Table A3.1 shows how many respondents submitted ratings for either one, two, or three consultative processes.  Over a third of the 26 respondents (8/26) were involved in more than one process, and six respondents were involved in 3 (or more) processes.  The Regi0nal training TAG was represented by only one participant, and two participants from the consultative process on the Ladysmith papers responded, but all other processes were represented by a range of 4-9 participants.

Table A3.1

| Number of Consultations rated | Number of respondents |
| --- | --- |
| 1 consultation | 26 |
| 2 consultations | 8 |
| 3 consultations | 6 |

### Experts reported positive experiences in Joint Programme working collaborations

The majority of respondents (23/26 who rated 1, 5 /8 who rated 2, 4/6 who rated 3) either strongly agreed or agreed that the consultations were transparent, participatory, included a diverse group of people, were relevant to VAW, and that objectives were met.  For the last three items pertaining to future steps there were between 2-4 people who reported that they didn’t know or disagreed.

The meetings were very successful and effective.

-TAG to the Inter-Agency Working Group

The meeting was well organized… the format encouraged full participation; the consultation process will be of great impact to our work on online gender-based violence in Uganda.

- Online and technology facilitated violence against women and girls

The work… was a complex, critical, and much needed… The collaborative work was a positive experience, with a diverse mix of technical experts involved in the process. The area of work remains complex and there are continuously new players in the field. It remains to be seen how the guidance will be piloted, rolled-out, used and have impact.

-Administrative data

The participatory consultative process was valuable in bringing a range of voices and experience to the table…opportune timing for review of current practice in a changing landscape and ensuring common agreement for best practice going into the future…unique in bringing together historical knowledge and experience.

- Updating Ethical and Safety standards

### Experts felt that a diverse range of stakeholders were convened

…to bring together various experts from numerous developing and developed countries to share their knowledge and experiences collecting data - and this affords members a wonderful opportunity to learn from each other.

.

Gathering the group of experts with different backgrounds and expertise made richer the discussions and agreed conclusions

### Participants expressed that the Joint Programme was important and unique:

The standardization, collection, and dissemination of the VAW data and gender statistics are challenging for many countries. I think the Joint Programme contributes to highlight the significance of data and provide support to improve the capacity of some countries.

(The Joint Programme) Brings together stakeholders and experts from around the globe to address these challenges. It is unusual to have a global approach.

Having high quality tools for data collection and resulting evidence about prevalence and incidence is needed in order to develop initiatives to end violence against women.

The advocacy arm of VAW has its own methodology … The Joint Programme provides a balance and ensures that the advocacy entities have reliable and valid data from which to draw their points of focus.

The joint program greatly contributes to joint work to end VAW, however, it would be great to have it termed as GBV rather than VAW for inclusivity and have non binary persons captured in definitions.

Challenges identified

I am unsure how the members were selected… or whether the consultation will lead to a change in recommended practice for measuring VAW with disability--but the consultative process was robust and provided the opportunity to review current and emerging practices. (VAW and Disability)

The objective of activity - to come up with modelled estimates for all the countries - was … more academically and politically interesting than practical and useful for policy…Despite a consultative process, countries do not understand how (the estimates) are derived or how they relate to their own national prevalence rates, which is what they use on the ground… The process cannot be replicated at country level...

The pressure for new VAW data (during the pandemic) was so immense that remote methods were going to be developed at all cost, despite all the advice against it…we had lots of discussions … some of us still have concerns about the mixed messages (and the risk for women) that this constituted (RGAs during COVID-19)

### Suggestions for Join Programme Work in a second phase

- Further capacity strengthening on understanding and using existing VAW data

- It would be useful to carefully document difference in data collection methodologies.  For example:  validation studies comparing VAW prevalence data collected in face-to-face, telephone, and online;   using stand-alone VAW surveys versus VAW modules in larger surveys, etc.

- Administrative data work:

  - Increase in-country staff capacity with workshops for public officers at the regional and country levels.

  - Help low-income countries to create the capacity to develop administrative data systems.

- Develop methods for measuring forms of violence that are not well understood, such as human trafficking and on-line child sexual exploitation, online and technology facilitated violence against women and girls, sexual harassment.

- Protocol and best practices for public -private partnerships in collaborating on VAW projects.

- For marginalized groups facing multiple forms of discrimination:

  - LGBTIQ+: focus on regional and national contexts and local nuances rather than a broad global context,

  - VAW in older women

  - Include sexual orientation, gender identity, gender expression and sex characteristics (SOGIESC) in VAW measurement and what takes places in these communities

## Conclusions

The survey results are not representative of the group of external experts in its entirety since there was such a low response rate.  However, the perspectives offered in the survey indicate that this group of respondents had very positive experiences in the expert consultations.  Experts expressed that the Joint Programme was doing important work to further the VAW data field, and they felt that the consultations—such a key part of Joint Programme activity strategy—were well done.  Similar sentiments about the value of the consultations were echoed in many interviews, and that these consultations ended in agreement on the many methodologies, measures, and strategies under discussions is, in of itself, evidence that demonstrates the success of these consultative processes.

# Annex 4: Publications produced by the Joint Programme at a glance

Outputs produced under the Joint Programme on VAW data Most resources are available in various languages. Different language versions can be found in the links provided.

Global, regional and country estimates of violence against women

WHO, on behalf of the United Nations Inter-Agency Working Group on Violence Against Women Estimation and Data (VAW-IAWGED) (2021) Violence against women prevalence estimates, 2018. Global, regional and national prevalence estimates for intimate partner violence against women and global and regional prevalence estimates for non-partner sexual violence against women. Available at: https://www.who.int/publications/i/item/9789240022256 WHO, on behalf of the United Nations Inter-Agency Working Group on Violence Against Women Estimation and Data (VAW-IAWGED) (2021) Violence against women prevalence estimates, 2018 Executive summary. Available at: https://www.who.int/publications/i/item/9789240026681 Global factsheet. Available at: https://www.who.int/publications/i/item/WHO-SRH-21.6 WHO African Region. Available at: https://www.who.int/publications/i/item/WHO-SRH-21.7 WHO region of the Americas. Available at: https://www.who.int/publications/i/item/WHO-SRH-21.11 WHO Eastern Mediterranean region. Available at: https://www.who.int/publications/i/item/WHO-SRH-21.8 WHO European region. Available at: https://www.who.int/publications/i/item/WHO-SRH-21.9 WHO South-East Asia region. Available at: https://www.who.int/publications/i/item/WHO-SRH-21.10 WHO Western Pacific region. Available at: https://www.who.int/publications/i/item/WHO-SRH-21.12 WHO. Global Database on the Prevalence of Violence Against Women. Web-based data visualization tool accessible at: https://vaw-data.srhr.org/ WHO (2022). Video. Violence against women prevalence data and estimates, data for action. Available at https://youtu.be/dzGOmwkKLMM Stöckl H, Sardinha L, Maheu-Giroux M, Meyer SR, García-Moreno C (2021) Physical, sexual and psychological intimate partner violence and non-partner sexual violence against women and girls: a systematic review protocol for producing global, regional and country estimates. BMJ Open 2021. Available at: https://www.ncbi.nlm.nih.gov/pmc/articles/PMC8378393/pdf/bmjopen-2020-045574.pdf Sardinha L, Maheu-Giroux M, Stöckl H, Meyer SR, García-Moreno C. (2022) Global, regional, and national prevalence estimates of physical or sexual, or both, intimate partner violence against women in 2018. Lancet. Available at: https://www.thelancet.com/article/S0140-6736(21)02664-7/fulltext Sardinha L, García-Moreno C, Guthold R (2022) Global estimated prevalence of physical and/or sexual intimate partner violence against ever-partnered women by, age, 2018. Journal of Adolescent Health. Available at: https://www.jahonline.org/article/S1054-139X(21)00689-3/fulltext Maheu-Giroux, M., Sardinha, L., Stöckl, H. et al. (2022) A framework to model global, regional, and national estimates of intimate partner violence. BMC Med Res Methodol 22, 159. Available at: https://bmcmedresmethodol.biomedcentral.com/articles/10.1186/s12874-022-01634-5#citeas Sardinha, L, Stöckl, H, Maheu-Giroux, M, Meyer SR, García-Moreno C (Under review) A persistent pandemic: the global prevalence of sexual violence against women. WHO Bulletin, Policy and Practice WHO on behalf of the United Nations Inter-Agency Working Group on Violence Against Women Estimation and Data (VAW-IAWGED) (2023) Checklist to ensure quality when planning surveys on the prevalence of intimate partner violence against women (2023 - In Press). Geneva. World Health Organization. 2023 WHO and UN Women (forthcoming end 2023) Briefing note on Non-partner sexual violence: data availability, methodological issues and recommendations for good practice. Geneva. World Health Organization

Psychological/emotional intimate partner violence

Clark C, Bergenfeld, I, Cheong, Y F, Najera, H, Sardinha, L, García-Moreno C, Heise, L(Under review) Women's Exposure to Psychological Violence: An Examination of Patterns in Low- and Middle-Income Countries (LMIC). Social Science and Medicine. Heise L, Pallitto C, García-Moreno C, Clark CJ (2019) Measuring psychological abuse by intimate partners: Constructing a cross-cultural indicator for the Sustainable Development Goals, SSM - Population Health, Volume 9100377, ISSN 2352-8273. Available at: https://www.sciencedirect.com/science/article/pii/S2352827318302490 Sardinha L, Garcia-Moreno C, Campo-Tena, L (forthcoming) Mapping and Overview of Survey Instruments on Psychological Intimate Partner Violence. WHO and UN Women (forthcoming) Briefing note on Psychological intimate partner violence: data availability, methodological issues and recommendations for good practice. Geneva. World Health Organization

Violence against older women

WHO. Module for measuring violence against women 60 years and older in the WHO Multi country study on women’ health and life experiences questionnaire and other VAW surveys or elder abuse surveys (Available on request; online publication forthcoming) WHO. Question-by-question Interviewer Manual for the survey module on violence against women 60 years and older. (Available on request; online publication forthcoming) WHO and UN Women (forthcoming) Briefing Note on Measuring violence against older women: data availability, methodological issues and recommendations for good practice. Geneva. World Health Organization. 2023 Mikton C, Campo-Tena L, Sardinha L, Yongjie Y, Garcia-Moreno C (forthcoming) Review of measurement instruments for violence against older women used in quantitative surveys conducted globally

Violence against women with disabilities

Meyer SR, Lasater ME, Lee L, et al. (2020) Measurement of violence against women and disability: protocol for a scoping review. BMJ Open 2020. Available at e040104.full.pdf (bmj.com) Meyer SR, Stöckl H, Vorfeld C, Kamenov K, García-Moreno C (2022) A scoping review of measurement of violence against women and disability. PLoS ONE 17(1): e0263020. Available at: https://journals.plos.org/plosone/article/comments?id=10.1371/journal.pone.0263020 WHO and UN Women (2023) Briefing note on Measuring violence against women with disabilities: data availability, methodological issues and recommendations for good practice. Geneva. World Health Organization. WHO on behalf of the United Nations Inter-Agency Working Group on Violence Against Women Estimation and Data (VAW-IAWGED) (2023) Checklist to ensure inclusion of women with disability, and the topic of disability, in research on violence against women. Geneva. World Health Organization. WHO (2023). Violence against Women and Disability: Expert Group Meeting Summary. Geneva. World Health Organization (Available on request; online publication forthcoming)

WHO Multi-country Study Instruments

WHO (2023) WHO Multi country study on women’ health and life experiences questionnaire- short version. (Available on request; online publication forthcoming). WHO (2023) WHO Multi country study on women’ health and life experiences questionnaire- updated long version (forthcoming). WHO (2023) Question-by-question interviewer manual WHO Multi country study on women’ health and life experiences questionnaire- short version. (Available on request; online publication forthcoming). WHO (2023) Question-by-question interviewer manual WHO Multi country study on women’ health and life experiences questionnaire - updated long version (forthcoming) WHO (2023). “Prioritizing Women's Well-being: Ethical and Safety Recommendations for Research on Violence against Women.” Updated edition. Including surveys, qualitative and intervention research, and remote methods. (Forthcoming)

Administrative data on violence against women

UN Women and WHO (2022) Global technical guidance: Improving the collection and use of administrative data on violence against women. Available at: https://www.unwomen.org/en/digital-library/publications/2022/05/global-technical-guidance-for-collection-and-use-of-administrative-data-on-violence-against-women UN Women and WHO (2023) Brief: Why collection of administrative data is vital to end violence against women and girls. Available at: https://www.unwomen.org/sites/default/files/2023-07/improving-the-collection-and-use-of-administrative-data-on-violence-against-women-visual-summary-en.pdf UN Women and WHO (2023) Brief: 15 essentials for a survivor-centred design of violence against women administrative data systems. Available at: https://www.unwomen.org/sites/default/files/2023-07/improving-the-collection-and-use-of-administrative-data-on-violence-against-women-brief-en.pdf UN Women and WHO (2023) Video: Administrative data on violence against women: what is it? Available at: https://www.youtube.com/watch?v=kHqoLplJTig UN Women (2023) Article: Take Five: How Spain is using administrative data to help end violence against women and girls. Available at: https://www.unwomen.org/en/news-stories/take-five/2023/07/take-five-how-spain-is-using-administrative-data-to-help-end-violence-against-women-and-girls UN Women (2020) Background paper: A synthesis of evidence on the collection and use of administrative data on violence against women. Available at https://www.unwomen.org/en/digital-library/publications/2020/02/background-paper-synthesis-of-evidence-on-collection-and-use-of-administrative-data-on-vaw

Gender-related killings of women and girls (femicide/feminicide)

UNODC and UN Women (2022) Statistical Framework for Measuring the Gender-Related Killings of Women and Girls (also referred to as Femicide/Feminicide). Available at: https://data.unwomen.org/publications/statistical-framework-measuring-gender-related-killings-women-and-girls-also-referred UNODC and UN Women (2022) Global estimates of gender-related killings of women and girls in the private sphere in 2021: Improving data to improve responses. Available at: https://www.unwomen.org/en/digital-library/publications/2022/11/gender-related-killings-of-women-and-girls-improving-data-to-improve-responses-to-femicide-feminicide

Violence against women during COVID-19

UN Women and WHO (2020) Violence against women and girls data collection during COVID-19. Available at: https://www.unwomen.org/en/digital-library/publications/2020/04/issue-brief-violence-against-women-and-girls-data-collection-during-covid-19Headquarters UNFPA, UN Women and WHO (2020) Decision tree: Data collection on violence against women and COVID-19. Available at: https://www.unwomen.org/en/digital-library/publications/2020/07/decision-tree-data-collection-on-violence-against-women-and-covid-19 UN Women (2020) Impact of COVID-19 on violence against women and girls and service provision: UN Women rapid assessment and findings. Available at: https://www.unwomen.org/en/digital-library/publications/2020/05/impact-of-covid-19-on-violence-against-women-and-girls-and-service-provision

Technology-facilitated violence against women

UN Women and WHO (2023) Technology-facilitated violence against women: Taking stock of evidence and data collection. Available at: https://www.unwomen.org/en/digital-library/publications/2023/04/technology-facilitated-violence-against-women-taking-stock-of-evidence-and-data-collection UN Women and WHO (2023) Brief: The state of evidence and data collection on technology-facilitated violence against women. Available at: https://www.unwomen.org/en/digital-library/publications/2023/04/brief-the-state-of-evidence-and-data-collection-on-technology-facilitated-violence-against-women UN Women and WHO (2023) Expert Group Meeting report: Technology-facilitated violence against women: Towards a common definition. Available at: https://www.unwomen.org/en/digital-library/publications/2023/03/expert-group-meeting-report-technology-facilitated-violence-against-women

Violence against vulnerable groups of women

UN Women and WHO (2023) Scoping review on the status of evidence and data collection on violence based on sexual orientation and gender identity. Forthcoming

State response and prevention to end violence against women

UN Women. Global Database on Violence against Women. Last updated in 2023 and accessible at: https://evaw-global-database.unwomen.org/en WHO (2021) Addressing violence against women in health and multisectoral policies: a global status report. Available at: https://www.who.int/publications/i/item/9789240040458

Regional courses on VAW prevalence data

The African Population and Health Research Center and the University of Ghana – School of Public Health (UG) (2023) Capacity Development on Violence Against Women Prevalence Surveys (CaVAWPreS) in East Africa. Forthcoming The Arab Institute for Women at the Lebanese American University and the Global Women’s Institute at the George Washington University (2023) Violence Counts! Strengthening Arab Regional Capacity to Collect Data on Violence Against Women. Forthcoming UN Women (2019) Video: Regional Workshop on Prevalence Surveys on Violence against Women in East and Southern Africa. Available at: https://www.youtube.com/watch?v=xShvdpYbB3g UN Women (2019) Video: Regional Workshop on Prevalence Surveys on Violence against Women in the Arab States. Available upon request

Online self-paced free course on VAW data

Apolitical, UN Women and WHO (2023) Course: Using Data to End Violence Against Women. Forthcoming on Apolitical’ s website

Direct contributions of the Joint Programme to related outputs

UN Women (2021) Measuring the shadow pandemic: Violence against women during COVID-19. Available at: https://data.unwomen.org/publications/vaw-rga UN Women (2022) Measuring the shadow pandemic: Collecting violence against women data through telephone interviews. An evidence-based technical guidance. Available at: https://data.unwomen.org/publications/measuring-shadow-pandemic-collecting-VAW-data-guidance UNDP and UN Women. COVID-19 Global Gender Response Tracker. Accessible at: https://data.undp.org/gendertracker/ UNDP and UN Women (2022) Government Responses to COVID-19: Lessons on gender equality for a world in turmoil. Available at: https://www.unwomen.org/en/digital-library/publications/2022/06/government-responses-to-covid-19-lessons-on-gender-equality-for-a-world-in-turmoil

Violence against women prevalence data and estimates, data for action - YouTube

https://www.youtube.com/watch?v=WVUGPjcmkjo&ab_channel=UNWomen

UN Women and WHO.  Joint Programme on strengthening methodologies and measurement and building national capacities for violence against women data. Project document. 2018.

Foreit, Karen, Scott Moreland Anne Lafond. 2006. Data Demand and Information Use in the Health Sector: A Conceptual Framework.  MEASURE Evaluation, University of North Carolina at Chapel Hill. https://www.measureevaluation.org/resources/publications/ms-06-16a.html

https://www.measureevaluation.org/our-work/data-demand-and-use.html

UN Women. 2020. Evaluation policy of the United Nations Entity for Gender Equality and the Empowerment of Women .  Executive Board of the United Nations Entity for Gender Equality and the Empowerment of Women, Second regular session 2020, Item 6 of the provisional agenda.  https://www.unwomen.org/en/digital-library/publications/2020/08/evaluation-policy-of-the-united-nations-entity-for-gender-equality-and-the-empowerment-of-women

UNEG . 2016.  Norms and Standards for Evaluation. New York: UNEG. http://www.unevaluation.org/document/detail/1914

UNEG. 2020. Ethical Guidelines for Evaluation. New York: UNEG.  http://www.unevaluation.org/document/detail/2866

UNEG. 2014.  Integrating Human Rights and Gender Equality in Evaluations. New York: UNEG. http://www.uneval.org/document/detail/1616

UNEG. 2020. Ethical Guidelines for Evaluation. New York: UNEG.  http://www.unevaluation.org/document/detail/2866

UN Women Independent Evaluation and Audit Services.  2021. Corporate evaluation of UN Women’s UN system coordination and broader convening role in ending violence against women https://www.unwomen.org/en/digital-library/publications/2021/06/evaluation-un-women-un-system-coordination-and-broader-convening-role-in-evaw

UN Women Independent Evaluation and Audit Service (IEAS). 2022 Evidence and lessons on types of UN Women support: A meta-synthesis of un women evaluations https://gate.unwomen.org/Evaluation/Details?evaluationId=11578

UN Women IEAS. 2020. Corporate evaluation of UN Women’s Flagship Programme Initiatives (FPIs) and the Thematic Priorities (TPs) of the Strategic Plan (SP) 2018–2021. https://gate.unwomen.org/Evaluation/Details?evaluationId=11471

Sources documenting the information presented in this section are cited using footnotes if drawn from interviews or specific sources.  The nine internal programme documents have been cited as they are in Annex 2, as follows:  (1) 2018 Annual Report, (2) 2019 Annual Report, (3) 2020 Annual Report, (4) Joint Programme Results 2021 1 pager, (5) WC MTR, (6) Joint Programme Two Pager-Funding Gaps (23 September 2020), (7) 2021 Annual Report, (8) 4 pager 2022, (9) 2022 Annual Report Excerpt on Technical Support.  The results captured in the MTR used sources 1-6; results captured from the period since mid-term are cited in footnotes and sources 7-9.

Members of this group were: WHO, UN Women, UNICEF, UNFPA, UNODC, UNSD

Members of this group were: Naeemah Abrahams, Sarah Bott, Kristin Diemer, Mary Ellsberg, Monica Howlett, Sunita Kishor, Maria Giuseppina Muratore, Nguyen Thi Viet Nga, Ruchira Tabassum Naved, Eva Gisela Ramirez Rodriguez, Charlotte Watts, İlknur Yüksel-Kaptanoğlu.

Multiple stakeholders expressed this in interviews.

The countries are: Albania, Bahamas, Bosnia and Herzegovina, Georgia, Grenada, Guyana, Jamaica, Kazakhstan, Kenya, Kosovo, Kyrgyzstan, Moldova, Morocco, North Macedonia, Nepal, Niger, Saudi Arabia, Senegal, Serbia, South Africa, Suriname, Tajikistan, Tanzania and Zanzibar, Turkey, Uganda, and Ukraine.

https://srhr.org/vaw-data

The module for measuring violence in women 60 years and above has been cognitively tested and piloted in 1 country; its use with additional countries planning surveys is being explored (Bangladesh, Mexico, Kazakhstan, Indonesia)

Interview with expert participant, and the DHS DV modules versions 7 and 8.

UNODC, UN Women.  2022.  Statistical framework for measuring the gender-related killing of women and girls (also referred to as “femicide/ Feminicide”) https://lac.unwomen.org/en/digital-library/publications/2022/08/marco-estadistico-para-medir-las-muertes-de-mujeres-y-ninas-por-razones-de-genero-femicidio-feminicidio

Interview with Georgia CO.

Interview with Asia-Pacific MCO.

UN Women and WHO. Violence against women and girls. Data Collection during COVID-19. April 2020. https://www.unwomen.org/en/digital-library/publications/2020/04/issue-brief-violence-against-women-and-girls-data-collection-during-covid-19

UN Women, WHO and UNFPA. 2020. Data Collection on Violence against Women and COVID-19: Decision Tree. https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2020/Decision-tree-Data-collection-on-violence-against-women-and-COVID-19-en.pdf

Several interviews with experts and countries.

WHO on behalf of the United Nations Inter-Agency Working Group on Violence Against Women Estimation and Data (VAW-IAWGED) .2023. Checklist to ensure quality when planning surveys on the prevalence of intimate partner violence against women (In Press). Geneva. World Health Organization. 2023.

Interviews with multiple stakeholders and results of the online survey of experts.

WHO and UN Women (online link forthcoming) Briefing Note on Measuring violence against older women: data availability, methodological issues and recommendations for good practice. Geneva. World Health Organization. 2023

WHO and UN Women (2023) Briefing note on Measuring violence against women with disabilities: data availability, methodological issues and recommendations for good practice. Geneva. World Health Organization.

WHO on behalf of the United Nations Inter-Agency Working Group on Violence Against Women Estimation and Data (VAW-IAWGED) (2023) Checklist to ensure inclusion of women with disability, and the topic of disability, in research on violence against women. Geneva. World Health Organization.

United Nations Economic and Social Commission for Western Asia (ESCWA). 2021.  Violence Against Women Survey Implementation Toolkit: Complete questionnaire for a stand-alone survey.  Beirut:  ESCWA E/ESCWA/CL4.SIT/2021/MANUAL.3 & KII interview.

UN Women and World Health Organization (WHO). 2022. Global technical guidance: Improving the collection and use of administrative data on violence against women. New York: UN Women. https://www.unwomen.org/sites/default/files/2022-10/Improving-the-collection-and-use-of-administrative-data-on-violence-against-women-en.pdf

UN Women. 2020. A synthesis of evidence on the collection and use of administrative data on violence against women. https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2020/Synthesis-of-evidence-on-collection-and-use-of-administrative-data-on-VAW-en.pdf

Interview with expert consultant.

The Arab Institute for Women at the Lebanese American University with the Global Women’s Institute at the George Washington University

The African Population and Health Research Center (APHRC) which has experience on VAW surveys with the London School of Tropical Health and Medicine, in a consortium with University of Ghana

African Population and Health Research Center (APHRC) and the University of Ghana. 2022 (November) Capacity Development on Violence Against Women Prevalence Survey (CaVAWPreS) in Eastern and Southern African Region Short Course:  Training Curriculum and interview with the Arab States consortia.

Interviews with both regional consortia..

Gender Statistics Imperatives in Africa. Joint AfDB-COMESA-PARIS21-UNECA-UN Women Regional Workshop on Gender Statistics 26-30 September Nairobi, Kenya.

Interviews with both regional consortia.

Ibid.

Interviews with regional  training consortia.

African Population and Health Research Center (APHRC) and the University of Ghana. 2022 (November) Capacity Development on Violence Against Women Prevalence Survey in Eastern and Southern African Region Short Course:  Training Curriculum.

Interviews with regional  training consortia.

Interviews with ROs and COs.

Interviews with WHO HQ

Interview with the Europe and Central Asia RO.

Interview with Tanzania CO.

Interview with Morocco CO (Mid-term Reflection interviews)

African Population and Health Research Center (APHRC) and the University of Ghana. 2022 (November) Capacity Development on Violence Against Women Prevalence Survey (CaVAWPreS) in Eastern and Southern African Region Short Course:  Training Curriculum.

See for example, the Regional Workshop of the M&E of HIV in Asia: https://www.measureevaluation.org/resources/training/capacity-building-resources/m-e-of-hiv-aids-programs-in-india-english/m-e-of-hiv-aids-programs-in-asia-english.html

MEASURE Evaluation. 2014.  Strengthening Family Planning Programs with Data: Creating a Culture of Data Demand and Use. Chapel Hill, NC, USA: Carolina Population Center, University of North Carolina.  https://www.measureevaluation.org/publications/fs-14-120.html

Interviews with WHO HQ.

Making Every Women and Girl Count Phase II. https://data.unwomen.org/sites/default/files/documents/Publications/2023/WomenCount_PhaseII_Brief.pdf

Interview with Georgia CO.

This was reflected in virtually all interviews with country and regional offices.

Interviews with experts and regional training partners

The countries were: Albania, Bangladesh, Cameroon, Colombia, Côte d’Ivoire, Jordan, Kenya, Kyrgyzstan, Morocco, Nigeria, Paraguay, Thailand and Ukraine

MEASURE Evaluation. 2018. Assessing Barriers to Data Demand and Use in the Health Sector: A Toolkit. Chapel Hill, NC, USA: Carolina Population Center, University of North Carolina. https://www.measureevaluation.org/resources/publications/ms-11-46-a.html

The 6 UN co-custodians are: UN Women, UNFPA, UNICEF, UNODC, UNSD, and WHO.

Interview with Women Count HQ

The center called “Lilium” is a one stop center based in a hospital setting which provides emergency services tailored for the needs of the survivors through a multidisciplinary team consisting of legal practitioners, gynecologists, pediatricians, psychiatrists, clinical psychologists, social workers, police officers, prosecutors, attorneys and nurses. See: https://www.undp.org/albania/news/albania-sets-first-center-support-victims-sexual-violence

Reiterated in many interviews and in the results of the online survey.

Interview with FCDO.

Multiple interviews.

Interviews with ROs and COs.

The consultative processes were:1) UN Inter-Agency Working Group on Violence against Women Estimation and Data (VAW-IAWGED)  for the violence against women prevalence estimates as co-custodians of SDG Target 5.2; 2) External independent TAG to the VAW-IAWGED for the Violence Against Women Prevalence Estimates, 2018 and  WHO Secretariat Members from the maternal mortality estimates team; 3) TAG for the Background Paper for the background paper on VAW administrative data; 4) TAG for the Global Technical Guidance on VAW administrative data; 5) TAG for the Regional Capacity Strengthening Initiative on Measurement of Violence against Women in the East and Southern Africa and Arab Regions; 6) EGM on Online and technology-facilitated VAWG: Towards a common definition; 7) TAG on Phone surveys to collect data on VAW (linked to the RGAs on VAW conducted during COVID-19); 8) TAG on the Ladysmith paper on the status of evidence and data collection on GBV among LGBTIQ+ people; 9) EGM on measures of violence against older women; 10) EGM on measures of psychological intimate partner violence; 11) EGM on violence against women and disability; 12) EGM on revising safety & ethical recommendations for collecting VAW data both in-person and using remote methods.

Expert interviews.

Interviews with UN Women  Europe and Central Asia RO and Georgia CO.

These examples are drawn from: Kimote, John. 2022 (October).  Final Evaluation: Making Every Woman and Girl Count: Supporting the monitoring and implementation of the SDGs through better production and use of gender statistics (Women Count) Programme.  Final Draft (not for public citation)

UN Women. 2022. Final Annual Report: Making Every Woman Count, Moving the needle on gender data.  Reporting period: August 2016-December 2021.

Foreit, Karen, Scott Moreland Anne Lafond. 2006. Data Demand and Information Use in the Health Sector: A Conceptual Framework. MEASURE Evaluation, University of North Carolina at Chapel Hill. https://www.measureevaluation.org/resources/publications/ms-06-16a.html

Midterm Reflection Exercise Interview with Joint Programme HQ

UN Women and WHO. Violence against women and girls. Data Collection during COVID-19. April 2020. https://www.unwomen.org/en/digital-library/publications/2020/04/issue-brief-violence-against-women-and-girls-data-collection-during-covid-19

UN Women, WHO and UNFPA. 2020. Data Collection on Violence against Women and COVID-19: Decision Tree. https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2020/Decision-tree-Data-collection-on-violence-against-women-and-COVID-19-en.pdf

Bloom, Shelah S. in collaboration with the Joint Programme team at UN Women and WHO.  August 2021 UN Women and WHO Global Joint programme on violence against women data.  Mid-term reflection Exercise.

Sardinha, Lynnmarie, Mathieu Maheu-Giroux, Heidi Stöckl, Sarah Rachel Meyer and Claudia García-Moreno. 2022. Global, regional, and national prevalence estimates of physical or sexual, or both, intimate partner violence against women in 2018.  Lancet 399: 803–13.

UN Women and WHO. 2022.  Untitled. (Communications strategy—6 pager).

Gender Statistics Imperatives in Africa. Joint AfDB-COMESA-PARIS21-UNECA-UN Women Regional Workshop on Gender Statistics 26-30 September Nairobi, Kenya (flyer)

This figure was the total budget for a USAID-funded activity to develop a set of standard measures for an area of gender and health that took place in 2014.  The activity was very similar to the ones coordinated by the Joint Programme in that they involved a global meeting of international experts to get agreement on definitions and a set of standard measures, and who acted as a technical advisory group while the measures were being drafted.  This project conducted several of these activities and all the budgets were in the same range.

Bloom , Shelah S. in collaboration with the Joint Programme team at UN Women and WHO.  August 2021. UN Women and WHO Global Joint programme on violence against women data.  Mid-term reflection Exercise.

UN Women and WHO. 2022.  Untitled. (Communications strategy—6 pager).

This statement is based on the results of several similarly designed measurement development activities that took place over the 20 year-long implementation period of a USAID M&E flagship project (MEASURE Evaluation).  Many of these measures are still being used extensively, well beyond the time of their development and even after the project’s end in 2018.  See for example the interactive, user-friendly reproductive health indicators database that provides detailed information on how they are measured and includes the VAWG indicators that were developed through a like-process in 2008 https://www.measureevaluation.org/resources/prh/rh_indicators.

Results of the online survey.

Interview with RO

For a list of countries, see https://dhsprogram.com/topics/gender/index.cfm

Interview with Asia Pacific MCO.

One of the best examples of this is the anti-GBV forum in Lesotho, headed by the Department of Gender, developed with support from GIZ in 2019, which is supporting the development of a national VAW administrative system there https://gender.gov.ls/about-the-department/

See the capacity building strategies employed through the two decades of the USAID-funded MEASURE Evaluation Project. https://www.measureevaluation.org/our-work/capacity-building.html

MEASURE Evaluation. 2011.  Framework for linking data with action. Chapel Hill, NC, USA: Carolina Population Center, University of North Carolina.  https://www.measureevaluation.org/resources/publications/ms-11-46-b.html

Ellsberg M, and Heise L. 2005 .  Researching Violence Against Women: A Practical Guide for Researchers and Activists. Washington DC, United States: World Health Organization, PATH.

Interview with UN Women Nepal CO

Expert interview.

UN Women. 2023. Making every Woman and Girl Count Phase II Brief. https://data.unwomen.org/sites/default/files/documents/Publications/2023/WomenCount_PhaseII_Brief.pdf

Stöckl H, Sardinha L, Maheu-Giroux M, et al. 2020. Physical, sexual and psychological intimate partner violence and non-partner sexual violence against women and girls: a systematic review protocol for producing global, regional and country estimates. BMJ Open 2021;11:e045574. doi:10.1136/bmjopen-2020-045574

Sardinha, Lynnmarie ,Mathieu Maheu-Giroux, Heidi Stöckl, Sarah Rachel Meyer, Claudia García-Moreno. 2022.  Global, regional, and national prevalence estimates of physical or sexual, or both, intimate partner violence against women in 2018.  Lancet 399:803-13.

Sardinha L, García-Moreno C, Guthold R (2022) Global estimated prevalence of physical and/or sexual intimate partner violence against ever-partnered women by, age, 2018. Journal of Adolescent Health. Available at: https://www.jahonline.org/article/S1054-139X(21)00689-3/fulltext

The video can be viewed at https://youtu.be/dzGOmwkKLMM

Sardinha, Lynnmarie ,Mathieu Maheu-Giroux, Heidi Stöckl, Sarah Rachel Meyer, Claudia García-Moreno. 2022.  Global, regional, and national prevalence estimates of physical or sexual, or both, intimate partner violence against women in 2018.  Lancet 399:803-13.

Maheu-Giroux, M., Sardinha, L., Stöckl, H. et al. (2022) A framework to model global, regional, and national estimates of intimate partner violence. BMC Med Res Methodol 22, 159. Available at: https://bmcmedresmethodol.biomedcentral.com/articles/10.1186/s12874-022-01634-5#citeas

Sardinha, L, Stöckl, H, Maheu-Giroux, M, Meyer SR, García-Moreno C (Under review) A persistent pandemic: the global prevalence of sexual violence against women. WHO Bulletin, Policy and Practice

The database can be accessed at:  https://vaw-data.srhr.org/homepage

UN Women. 2022. Final Annual Report: Making Every Woman Count, Moving the needle on gender data.  Reporting period: August 2016-December 2021.

Interviews with the Asia Pacific MCO and Europe and Central Asia RO.

UNODC, UN Women.  2022.  Statistical framework for measuring the gender-related killing of women and girls (also referred to as “femicide/ Feminicide”).  https://lac.unwomen.org/en/digital-library/publications/2022/08/marco-estadistico-para-medir-las-muertes-de-mujeres-y-ninas-por-razones-de-genero-femicIndividualo-feminicIndividualo

UN Women and WHO. Violence against women and girls.  Data Collection during COVID-19. April 2020. https://www.unwomen.org/en/digital-library/publications/2020/04/issue-brief-violence-against-women-and-girls-data-collection-during-covid-19

UN Women and World Health Organization (WHO). 2022. Global technical guidance: Improving the collection and use of administrative data on violence against women. New York: UN Women.

Heise, Lori, Christina Pallito, Claudia Garcia-Moreno, Cari Jo Clark. 2019. Measuring psychological abuse by intimate partners: Constructing a cross-cultural indicator for the Sustainable Development Goals. SSM Population Health. https://doi.org/10.1016/j.ssmph.2019.100377

Clark C, Bergenfeld, I, Cheong, Y F, Najera, H, Sardinha, L, García-Moreno C, Heise, L. 2023.  Patterns of Womenʼs exposure to psychological violence: A global examination of low- and middle-income countries.  SSM  Population Health. https://doi.org/10.1016/j.ssmph.2023.101500

Meyer, Sarah R Meyer, Molly E Lasater, Lindsay Lee, Claudia Garcia-Moreno. 2020. Measurement of violence against women and disability: protocol for a scoping review. Review BMJ Open Dec 24;10(12):e040104. doi: 10.1136/bmjopen-2020-040104; Meyer, Sarah R., Heidi  Stöckl, Cecilia Vorfeld, Kaloyan Kamenov, Claudia García-Moreno. 2022. A scoping review of measurement of violence against women and disability.  PLoS ONE 17(1): e0263020. https://doi.org/10.1371/journal.pone.0263020

Technology-facilitated Violence against Women: Towards a common definition. Report of the meeting of the Expert Group 15-16 November 2022, New York, USA

UN Women 2022.  Collecting Violence against Women Data through Telephone Interviews: an evidenced-based technical guidance. https://data.unwomen.org/sites/default/files/documents/Publications/Guidance_VAW_RGA-EN.pdf

UN Women and WHO. 2023.  Technology-facilitated violence against women: Taking stock of evidence and data collection | Publications | UN Women – Headquarters. https://www.unwomen.org/en/digital-library/publications/2023/04/technology-facilitated-violence-against-women-taking-stock-of-evidence-and-data-collection

UN Women. 2020. A synthesis of evidence on the collection and use of administrative data on violence against women. https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2020/Synthesis-of-evidence-on-collection-and-use-of-administrative-data-on-VAW-en.pdf

https://www.unwomen.org/en/digital-library/publications/2022/05/global-technical-guidance-for-collection-and-use-of-administrative-data-on-violence-against-women

https://www.youtube.com/watch?v=WVUGPjcmkjo&ab_channel=UNWomen

https://www.unwomen.org/en/news-stories/take-five/2023/07/take-five-how-spain-is-using-administrative-data-to-help-end-violence-against-women-and-girls

Interview with expert participant.

United Nations Economic and Social Commission for Western Asia (ESCWA). 2021.  Violence Against Women Survey Implementation Toolkit: Complete questionnaire for a stand-alone survey.  Beirut:  ESCWA E/ESCWA/CL4.SIT/2021/MANUAL.3 & KII interview, Neda Jafar.

African Population and Health Research Center (APHRC) and the University of Ghana. 2022 (November) Capacity Development on Violence Against Women Prevalence Survey in Eastern and Southern African Region Short Course:  Training Curriculum.

Interview with Europe and Central Asia RO.

Interview with Georgia CO

Interview with Nepal CO.

Gender Statistics Imperatives in Africa. Regional Workshop Concept Note (September 2022).

African Population and Health Research Center (APHRC) and the University of Ghana. 2022 (November) Capacity Development on Violence Against Women Prevalence Survey in Eastern and Southern African Region Short Course:  Training Curriculum

Djibouti , Ethiopia , Kenya, Malawi , Rwanda ,Tanzania, Somalia; Botswana, Eswatini, Lesotho,  Zimbabwe.

Egypt, Jordan, Lebanon, Libya, Morocco, Palestine, Tunisia, Turkey

https://africa.unwomen.org/en/stories/news/2022/06/eliminating-violence-against-women-and-girls-vawg-data-coordination-training

Interviews with the East and Southern Africa and Arab States partners.

Interview with UN Women AP MCO.

Interview with UN Women ECA RO.

Interview with UN Women Tanzania CO

Interviews with WHO HQ

Interviews with regional partners

Interview with Tanzania CO

Interview with WHO HQ

Multiple interviews with TAG and EGM participants, results of expert survey

The collaboration was noted by almost all stakeholders interviewed for the evaluation.

Interviews with UN Women regional and country offices

Interviews with WHO HQ

In July 2023, as part of ongoing JP work, an EGM on non-partner sexual violence was held.

Gender Statistics Imperatives in Africa. Joint AfDB-COMESA-PARIS21-UNECA-UN Women Regional Workshop on Gender Statistics 26-30 September Nairobi, Kenya (flyer)

Interview with Women Count HQ

The two consultative processes for Administrative Data—the TAG for the review and the TAG for the Global Guidance—were combined for the survey since these two groups were comprised of the same members (which wasn’t true for any of the other processes); therefore the number of processes asked about in the survey was 11.

This last point was also echoed in the KIIs that mentioned LGBTIQ+