UN Women Georgia

Final Evaluation of the UN Women Georgia project “Accelerating Implementation of Women, Peace and Security Agenda in Georgia” implemented from November 16, 2020 to March 31, 2025

Final Report

Marina Gurbo, International Consultant Dariko Bakhturidze, National Consultant June 24, 2025

Acronyms and Abbreviations

ABL	Administrative Boundary Line

CEDAW	Convention on the Elimination of All Forms of Discrimination against Women

CEDAW Committee	Committee on the Elimination of Discrimination against Women

CGE	Inter-Agency Commission on Gender Equality, Violence against Women and Domestic Violence

CSOs	Civil Society Organizations

DCAF	Geneva Centre for Security Sector Governance

EUMM	European Union Monitoring Mission in Georgia

GDF	Georgian Defence Forces

GIA	Gender Impact Assessment

GID	Geneva International Discussions

GIS	Georgian Intelligence Service

IDP	Internally Displaced Person

IDP Agency	Internally Displaced Persons, Ecomigrants and Livelihood Agency

IPRM	Incident Prevention and Response Mechanism

IWPR	Institute for War and Peace Reporting

MFA	Ministry of Foreign Affairs of Georgia

MIA	Ministry of Internal Affairs of Georgia

MIA Academy	Academy of the Ministry of Internal Affairs

MoD	Ministry of Defence of Georgia

MoIDPOTLHSA	Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia

NAP 1325	National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security

NATO	North Atlantic Treaty Organization

NSC	Office of the National Security Council

OSMRCE 	Office of the State Minister for Reconciliation and Civic Equality

PFBF	Peace Fund for a Better Future

PGA	Participatory Gender Audit

SSS	State Security Service of Georgia

UK CSSF	United Kingdom Conflict, Stability and Security Fund

UN Women	United Nations Entity for Gender Equality and the Empowerment of Women

UNSDCF	United Nations Sustainable Development Cooperation Framework

WAG	Women’s Advisory Group

WPS	Women, Peace and Security

WPSA	Women, Peace and Security Agenda

Table of Contents

Executive summary	4

1.	Introduction	10

1.1.	Description of the project	10

1.2.	The objectives of evaluation	12

1.3.	The context of the project	12

2.	Methodology	17

2.1.	Evaluation approach	17

2.2.	Evaluation standards	17

2.3.	Evaluation criteria and evaluation questions	19

2.4.	Data collection and analysis methods	20

2.5.	Evaluation sample and participation of stakeholders in evaluation	22

2.6.	Limitations	23

2.7.	Evaluation management and performance standards	23

2.8.	Ethical issues	24

3.	Findings	25

3.1.	Relevance	25

3.2.	Coherence	29

3.3.	Effectiveness and Impact	31

3.4.	Efficiency	40

3.5.	Sustainability	42

3.6.	Conflict sensitivity	44

3.7.	Inclusion	46

4.	Lessons learned	47

5.	Conclusions	47

6.	Recommendations	50

7.	Annexes	52

Annex 1 List of interlocutors	53

Annex 2 Result and Resources Framework	55

Annex 3 List of key documents	69

Annex 4 Evaluation Matrix	72

Annex 5 Stakeholders’ analysis	78

Annex 6 Data collection instruments	82

Annex 7 Terms of Reference	90

Annex 8 Evaluation Team Bios	99

List of Tables and Figures

Table 1 The Project Result Framework…………………………………………………………………………………………………….9

Table 2 Limitations and mitigation strategies…………………………………………………………………………………………22

Figure 1 Timeline of important events through the project implementation cycle	12

Figure 2 Progress towards achievement of gender equality and women’s empowerment and SDGs	13

Figure 3 Timeline of NAP 1325	14

Figure 4 The Project Theory of Change	17

Figure 5 Participation of stakeholders in evaluation	21

Figure 6 Perceptions of women of changes in access and capacities 	25

Figure 7 Community initiatives implemented by women’s groups and their beneficiaries	27

Figure 8 Major economic challenges experienced by IDP women 	29

Figure 9 Achievement of NAP 1325 targets by security sector institutions	31

Figure 10 Areas of strong alignment with NAP 1325	32

Figure 11 Alignment of advocacy to WPS Pillars	33

Figure 12 Use of tools and technologies by women	34

Figure 13 Participation of women in advocacy initiatives (based of the survey of 78 women-leaders)	35

Figure 14 Achievement of key targets at the Outcome level	36

Figure 15 Participation of women in the GID (Outcome level target of 30 percent) 	37

Figure 16 Participation of women in the GID (Outcome level target of 30 percent) 	37

Figure 17 Women’s representation in the security sector 	38

Figure 18 Distribution of the budget (percentage) by Output and the target group (GBP)	40

Figure 19 Implementation of the budget by Output and Year in USD 	41

Figure 20 Mapping of women-led CSOs engagement in networks and linkages to formal peacebuilding processes	43

Figure 21 7+1 Human Security Domains	43

Figure 22 Participation of women based on the status and age (ZOHO database, total of 256 women)	45

# Executive summary

The executive summary is meant to inform key stakeholders in the Government, representatives of the United Nations Country Team, non-UN actors and donors, as well broader audiences on the objectives of the final evaluation, its methodology and findings. It also includes key recommendations on enhancement of WPS mainstreaming in Georgia. The evaluation covered the period of the project implementation from November 2020 until March 2025.  In terms of geographical coverage, it was implemented in Tbilisi and 17 municipalities targeted by the project interventions.

- The Project Description

The project on “Accelerating Implementation of the Women, Peace and Security Agenda in Georgia” funded by the UK Government was implemented by UN Women Georgia since November 16, 2020, and its first phase concluded on March 31, 2024. The total budget was £1,420,776.05, funded by the UK CSSF and UK MoD. Under a new agreement, the project was extended for an additional year, from April 8, 2024, to March 31, 2025, with an additional £467,350.00 provided by the UK Integrated Security Funds (Foreign, Commonwealth and Development Office - FCDO). The project aimed to contextualize and localize the Women, Peace and Security (WPS) agenda in the context of the country through both top-down and bottom-up interventions, engaging state and non-state actors.  The project design was closely aligned with the objectives of 2020-2021 NAP and, consequently, with the 2022-2024 NAP 1325, which was developed with the project’s support. The project had a complex design incorporating 33 activities that engaged 750 IDP and conflict affected women and more than 1123 representatives of state institutions and agencies in a variety of capacity building interventions, advocacy and networking.

In terms of its geographical scope, the project targeted 17 municipalities most effected by conflict and displacement in the regions of Kvemo Kartli, Shida Kartli, Imereti, Samegrelo-Zemo Svaneti and Racha-Lechkhumi and Kvemo Svaneti, including the villages that are adjacent to the Administrative Boundary Lines (ABL) with Abkhazia, Georgia and Tskhinvali region/South Ossetia, Georgia. To enhance participation of IDP and conflict- affected women in formal and informal peace processes and to support localization of the WPS agenda and NAP 1325, UN Women partnered with three CSOs - the IDP Women’s Association “Consent”, the Women’s Information Center and the Women’s Fund “Sukhumi”.

Furthermore, the project interventions aimed at achieving transformative changes in the government’s efforts to implement the WPSA resulting in gender-sensitive policies, procedures and operations of security sector institutions to ensure a rights-based, gender equality approach and promote gender justice in all peace and political processes.  To achieve these transformative objectives, UN Women partnered with many governmental institutions, international NGOs and think tanks working on peace and security issues. The key government partners included the Government Administration (specifically the Inter-Agency Commission on Gender Equality, Violence against Women and Domestic Violence), the Ministry of Internally Displaced Persons from the Occupied Territories, Accommodation and Refugees of Georgia, the State Ministry for Reconciliation and Civic Equality (SMR), the Ministry of Defense (MoD), the Ministry of Internal Affairs (MIA), the Ministry of Foreign Affairs (MFA) and the State Security Service (SSS). To support state institutions in implementation of the NAP 1325 and mainstreaming of the WPS agenda, UN Women established a strategic partnership with the Geneva Centre for Security Sector Governance (DCAF).

Implementation of the project was challenged by the political situation in Georgia and geo-political tensions.  The adoption of the Law on Transparency of Foreign Influence coupled with the post-election crisis in 2024 and the Government’s decision to postpone the EU accession process created significant concerns. The new Law and ongoing political crisis could significantly impact the implementation of the WPS agenda in Georgia, as many organizations working on WPS issues rely on international funding and partnerships. This legislation could potentially further hinder the work of women's rights organizations, peacebuilding initiatives, and civil society groups that receive foreign support to implement crucial WPS programs, particularly those supporting conflict-affected women and IDPs.  Additionally, the controversy surrounding the law and subsequent protests strained relationships between civil society organizations and government institutions, potentially affecting collaborative efforts necessary for effective WPS implementation.

- Evaluation objectives

The evaluation covered the period of the project implementation from November 2020 until March 2025.  In terms of geographical coverage, the final evaluation was conducted in the areas in which the project had been implemented; the international and the local consultants travelled to 14 municipalities to interview women living in IDP settlements and conflict- affected villages alongside the ABL. The specific evaluation objectives were to:

- Analyze the relevance and coherence of the implementation strategy and approaches of the project

- Assess effectiveness and organizational efficiency in progressing towards the achievement of the project’s results as defined in the interventions

- Determine the impact of the intervention with respect to gender equality and women’s empowerment

- Assess the sustainability of the results achieved by the project

- Document lessons learned, best practices, success stories and challenges to inform future work of UN Women and the UK Government (FCDO) in the areas of WPS

- Identify strategies for replication and up-scaling of the project’s best practices

- Provide actionable recommendations for future programmatic developments and maximize ownership by partners in the country covered by the project.

- Evaluation methodology

The project was evaluated against the standard criteria of relevance, coherence, effectiveness, impact, efficiency, sustainability with conflict sensitivity and inclusivity added as crosscutting issues. The data collection methods were both quantitative and qualitative and included desk review, individual interviews and focus group interviews and an online survey.  In total, 170 respondents participated in interviews and focus groups discussions; IDP and conflict affected women constitute 90 percent of this group. In addition, an online survey was completed by 78 women-leaders in the network and 22 of them participated in the validation workshop conducted to collect their feedback on preliminary findings from the survey and focus group discussions.

- Key findings

The final report includes 16 findings. The main of them are the following:

Relevance

- The project design was based on the quality analysis of political, economic and socio-cultural aspects that identified root causes for low inclusion and participation of women who were most affected by conflicts;  the project strategies were most relevant to increase meaningful participation of IDP and conflict- affected women in peacebuilding and ensure that state institutions systematically collect information and data on needs of women and integrate them into policy and programme development.

- The project supported development and implementation of the 2022-2024 National Action Plan on UNSCR 1325; in this regard, the project addressed critical gaps in implementation of the previous plan such as lack of motivation among states institutions resulting in formal implementation of institutional gender equality strategies, lack of coherent integration of the WPS into local governance plans to address IDP and conflict- affected women’s needs in the conflict resolution and post- conflict recovery and development; limited participation of conflict -affected women in shaping coherent policies that target peace and security in the communities on both sides of the ABL.

Coherence

- UN Women established effective partnerships with UN and non-UN entities involved into formal peace processes in the region which ensured increased visibility of the WPS interventions at the national and international level. Establishment of the Women, Peace and Security Task force under the UN Gender Theme Group helped to organize some high-level meetings and activities which engaged stakeholders from state institutions, civil society, academia and think tanks. In addition, cooperation with the UN Women regional office (ECAS) resulted in organization of regional WPS forums and capacity building of peace ambassadors from Georgia and the region, and establishment of a multi-actor WPS platform. Nevertheless, the project would have benefited from better coherence with UN Women projects on violence against women,  local governance and women’s economic empowerment.

Effectiveness

- The project was effective in supporting security sectors institutions and other state agencies to implement activities and achieve targets defined in 2022-2024 NAP 1325; under the project, 247 officials (152 women, 95 men) from state institutions (GIS, IDP Agency, SMR, PDO, MFA, LEPL-Legal Aid, etc.)enhanced their knowledge on WPS issues and improved their skills of mainstreaming WPS Agenda in their institutions; several institutions like the Ministry of Defense (MoD) and the Ministry of Foreign Affairs (MFA) made significant strides in developing and implementing gender equality policies, career development opportunities for women, development of sexual harassment prevention mechanisms and improvement of collection of disaggregated data;

- Despite the significant improvement in gender-responsiveness of institutions policies and mechanisms, challenges prevail in terms of addressing gender stereotypes and promoting women to the senior leadership positions. Unconscious bias during the selection process results in women being underrepresented in senior decision-making positions across most institutions, particularly in the Ministry of Foreign Affairs and Ministry of Internal Affairs;

- In 2022-2023, the project partners from the civil society supported local municipalities in mainstreaming of NAP 1325 into local gender equality plans; 28 workshops and trainings were held, and 199 decision-makers and members of the Gender Equality Councils were trained on the issues of gender-responsive policy development, women, peace and security, gender budgeting, advocacy. However, the localization process was partially effective with more efforts needed to ensure that needs of IDP and conflict- affected women are taken into consideration and the WPS agenda is fully integrated at the local level

- The project contributed to capacities of 256 IDP and conflict- affected women to participate in formal peace processes and advocate for their rights and needs at the local and national institutions. In total, 700 women participated in the GID and IPRM meetings and in the annual Open Days where they could inform on needs of IDP and conflict- affected women and propose solutions to address their challenges; moreover, the project provided ample opportunities for women’s participation in peace and security processes by establishing the Network of Women and Youth Ambassadors that integrated about 240 members.

Impact

- Achievement of the project Outputs led to anticipated changes under the Outcomes such as increased gender sensitivity of peace formats (GID and IPRM) and participation of women’s CSOs and IDP and conflict-affected women in shaping peace and security processes. Participation of women in GID and IPRM increased during the project and reached the target of 30 percent. In terms of achievement of longer-term changes, some positive tendences may be acknowledged in relation to increased participation of women in leadership roles in security institutions and some line ministries. As for the impact on IDP and conflict-affected women, it would be impossible to measure the impact from the project due its limited scope of interventions to target multidimensional issues of security and, hence, self-reliance and resilience of these communities.

Sustainability

- Institutional gender responsive structures and processes developed at six security institutions with support of the project are likely to sustain; however, the backlash against civil society presents a threat to sustainable engagement of state institutions with IDP and conflict- affected women at the grassroots level and may undermine their critical role in promoting peace and security in their communities

- Sustainability of capacities built at the level of CSOs remains within the organizations and by mainstreaming of piloted by the project approaches into other interventions e.g. a human security approach, results of research and learning through regional networks; however, continuation of support to civil society, also by creating for them opportunities for engagement with state institutions and local governance is essential

- Several consultative platforms with involvement of women’s CSOs became sustainable such as at the Office of the State Minister of Reconciliation and at the Ministry of Foreign Affairs; there are some concerns about sustainability of the Network of Women and Youth Peace Ambassadors which presents the result of long-term advocacy efforts to consolidate peacebuilding initiatives; on a positive note, UN Women successfully executed the exit strategy and ensured transfer of developed under this project capacities into new projects, also implemented with support of UK Government.

Inclusion

- The project did not employ systematically inclusion strategies (LNOB) such as by age, socio-economic status, disability or other due to the extent of vulnerability of IDP and conflict -affected women in general. At the same time, inclusion of young women into the network was much appreciated by members of women’s networks who shared that having mixed group of women of different age, background, education level, sector (private sector, education, medical etc.) helped better prioritize problems and consolidate communities around their solution;  in addition to assessment of needs, which was exemplary under this project, pursuing more systematic inclusion based on better disaggregated data by civil society organizations would have been valuable to advocate for policies and measures that reflect the lived realities of affected women.

Conflict sensitivity

- The project raised capacities of civil society organizations in a gender-responsive conflict analysis and integrated the measures that guaranteed confidentiality and non-retaliation of women, particular from Abkhazia and South Ossetia, for their engagement to raise awareness of WPS and advocate for equal and meaningful participation of women in peace processes; integration of the human security methodology supported by development of a manual for civil society organizations and a training delivered to 150 women- leaders was most relevant to development of  a more coherent and collaborative approach to solution of complex and interconnected challenges faced by IDP and conflict- affected women in Georgia.

- Recommendations

Recommendation 1. UN Women should adopt a long-term, coherent strategy to drive transformative gender results in peace and security. This includes aligning project impact with sustainable change, strengthening partnerships, integrating cross-cutting themes, and improving coordination with women-led peacebuilding actors.

- Revise the project’s impact statement to reflect long-term transformation (e.g., resilience of IDP and conflict-affected communities), and update the Results and Resources Framework to account for assumptions and risks.

- Advocate for stronger involvement of state institutions in the 5th NAP 1325, including collaboration with networks representing IDP and conflict-affected women.

- Promote integration between WPS and other UN Women thematic areas (e.g., political participation, GBV, environmental resilience), and mainstream violence prevention and environmental resilience into project design.

- Define the role of the private sector in WPS and involve WEPs-affiliated companies in supporting women in conflict-affected areas.

- Expand the WPS database and map women-led organizations to identify synergies, improve coordination, and strengthen the Network of Women and Youth Ambassadors.

Recommendation 2. UN Women should strengthen bottom-up, gender-responsive approaches to support women’s participation in peacebuilding. Focus should be placed on community-level mobilization, empowering grassroots networks, clarifying roles of peace actors, and improving funding access.

- Disseminate social mobilization methodologies in IDP and conflict-affected communities and link with self-help groups and advisory bodies from other UN Women programmes.

- Work with the Network of Women and Youth Ambassadors to define its role, establish thematic sub-groups, and support participation in national and international WPS spaces.

- Build capacity of grassroots women’s networks to localize NAP 1325, partner with local institutions (e.g., NALAG), and monitor local gender equality plans.

- Collaborate with donors and partners to create grant mechanisms that fund women- and youth-led peacebuilding and confidence-building initiatives.

Recommendation 3. UN Women should strengthen evidence-based decision-making to enhance impact and learning across WPS initiatives. This requires clearly defining transformative change, improving data practices, using innovative tools, and embedding adaptive learning.

- Establish a clear definition of transformative change in women’s participation in the WPS agenda and introduce qualitative indicators that reflect grassroots empowerment.

- Ensure consistent, disaggregated data collection across implementing partners, including key indicators like employment, education, and disability.

- Promote use of participatory monitoring tools among women and youth groups and explore technology-based solutions for rapid data gathering.

- Conduct a human security baseline study (e.g., using a Human Security Index) in conflict-affected areas to guide programming.

- Undertake a midterm internal learning review in the next project phase to assess performance and generate lessons aligned with evaluation criteria.

# Introduction

This final report is submitted in response to the Terms of Reference for the final evaluation of the UN Women project “Accelerating Implementation of Women, Peace and Security Agenda in Georgia”. The report contains evaluation objectives and the scope of evaluation, description of the evaluation methodology, key findings, lessons learned, conclusions and recommendations. The evaluation has been conducted between December 27, 2024, and March 17, 2025.

## Description of the project

The project “Accelerating Implementation of the Women, Peace and Security Agenda in Georgia” funded by the UK Government has been implemented by UN Women Georgia since November 16, 2020, and it initially spanned 40 months, concluding on March 31, 2024. The total budget was £1,420,776.05, funded by the UK CSSF and UK MoD. Under a new agreement, the project's duration was extended by one year—from April 8, 2024, to March 31, 2025—with an additional £467,350.00 in funding provided by the UK Integrated Security Funds (Foreign, Commonwealth and Development Office - FCDO)

The project was designed to address the needs and interests of internally displaced (IDP) and conflict-affected women and girls as well as government and civil society partners in Georgia and aims at supporting the implementation of WPS agenda in Georgia.  As such, the project aims to contextualize and localize the Women, Peace and Security (WPS) agenda in the context of the country through both top-down and bottom-up interventions, engaging state and non-state actors. To this end, the project is set to contribute to the implementation of the following two outcomes and four outputs:

Table 1 The Project Result Framework

| Overarching goal/impact: Full implementation of the Women, Peace and Security agenda |  |
| --- | --- |
| Outcome 1: Increase in women’s meaningful and representative participation in conflict prevention and peacebuilding at the community and national level | Output 1.1: Increased capacity of women and girls (including internally displaced and conflict- affected) to meaningfully engage in conflict prevention and peacebuilding |
|  | Output 1.2: Mechanisms in place for increased meaningful and representative participation of women in conflict prevention and peacebuilding at the community and national level |
| Outcome 2: Increase in accountability of government, especially key security sector partners, to Women, Peace and Security commitments | Output 2.1: Government entities, including key security sector partners, have enhanced capacities and an evidence base to develop and implement the NAP 1325 |
|  | Output 2.2: Key security sector partners have enhanced capacities to mainstream gender into their policies, procedures and operations |

Achieving the full implementation of the WPS agenda in Georgia should advance gender equality, achieve the full, equal, direct and meaningful participation of women in peace and security processes, as well as in crisis response and recovery, and support the social cohesion and sustainable peace in the country. Under Outcome 1, the project interventions are aimed at achieving transformative changes in terms of (a) women’s increased and meaningful participation in peace and security decision-making spaces through social mobilization of conflict-affected communities, (b) the recognition of women’s expertise and live experiences among others by addressing them consistently throughout the peace and security processes.

In terms of its geographical scope, the project has targeted 17 municipalities most affected by conflict and displacement in the regions of Kvemo Kartli, Shida Kartli, Imereti, Samegrelo-Zemo Svaneti and Racha-Lechkhumi and Kvemo Svaneti, including the villages that are adjacent to the Administrative Boundary Lines with Abkhazia, Georgia and Tskhinvali region/South Ossetia, Georgia.

UN Women partnered with the IDP Women’s Association “Consent”, the Women’s Information Center and the Women’s Fund “Sukhumi”, three CSOs that have proven experience and capacities, as well as substantive theoretical and practical knowledge on IDP and conflict-affected women and youth needs and priorities. As well, these partners possess hands on experience in the NAP localization and advocacy experience to support the resolution of pressing issues and needs faced by IDP and conflict affected women.

Under Outcome 2, the project interventions aimed at achieving transformative change in the government’s efforts to implement the WPSA resulting in gender-sensitive policies, procedures and operations of security sector institutions to ensure a rights-based, gender equality approach and promote gender justice in all peace and political processes.  Achievement of results under this Outcome was critical to ensuring women’s rights, as well as engaging women from diverse social, political, economic backgrounds, geographies, age and/or diverse experiences in inclusive and sustainable peacemaking and peacebuilding. To that end, the project intended to contribute to achievement of national gender equality plans and international commitments of Georgia and, consequently, SDG 5 and SDG 16.

To achieve its transformative objectives, the project engaged a diverse set of stakeholders with clearly defined roles in advancing the Women, Peace and Security (WPS) agenda in Georgia. UN Women partnered with key government institutions, including the Government Administration (specifically the Inter-Agency Commission on Gender Equality, Violence against Women and Domestic Violence), the Ministry of Internally Displaced Persons from the Occupied Territories, Accommodation and Refugees of Georgia, the State Ministry for Reconciliation and Civic Equality (SMR), the Ministry of Defense (MoD), the Ministry of Internal Affairs (MIA), the Ministry of Foreign Affairs (MFA), and the State Security Service (SSS). New partnerships were also established with the National Security Council (NSC) and the Georgian Intelligence Service (GIS). These actors received technical support to strengthen gender-responsive policies and integrate the WPS agenda into their operations. Civil society organizations (CSOs) played a key role in mobilizing conflict-affected communities and advocating for the rights and participation of women and girls, while international partners such as the Geneva Centre for Security Sector Governance (DCAF) contributed technical expertise to strengthen institutional accountability. All stakeholders benefited from improved coordination, enhanced capacities, and greater progress toward inclusive and sustainable peacebuilding.

## The objectives of evaluation

This mandatory, final end-term external evaluation was conducted in accordance with the UN Women Evaluation Policy. It aimed to ensure accountability on behalf of UN Women to stakeholders and beneficiaries, and to enhance learning from the project, with the purpose of informing decision-making. The evaluation assessed the project’s achievements against the results and targets defined in the Project Document and aimed to draw lessons to improve the sustainability of benefits and support the continued enhancement of UN Women and UK Government interventions. The specific evaluation objectives were as follows:

- Analyze the relevance and coherence of the implementation strategy and approaches of the project

- Assess effectiveness and organizational efficiency in progressing towards the achievement of the project’s results as defined in the interventions

- Validate the project results in terms of achievements and/or weaknesses toward the outcome and outputs

- Assess how the project and its results relate and contribute to commitments and achievement of Sustainable Development Goals (SDGs) in Georgia

- Determine the impact of the intervention with respect to gender equality and women’s empowerment

- Assess the sustainability of the results achieved by the project

- Document lessons learned, best practices, success stories and challenges to inform future work of UN Women and the UK Government (FCDO) in the areas of WPS

- Identify strategies for replication and up-scaling of the project’s best practices

- Provide actionable recommendations for future programmatic developments and maximize ownership by partners in the country covered by the project.

Main evaluation users include UN Women, UK Government, the Inter-Agency Commission of the Government on Gender Equality and Ending Violence against Women and Domestic Violence Issues, as well as partners from line ministries representing the security sector; CSOs working with IDPs and conflict -affected women, representatives of women’s and youth’s networks; and local administrations implementing local plans on UNSCR 1325.  In addition, a broader scope of stakeholders (UN and non-UN) and donors may benefit from this evaluation findings and lesson learned to seek more synergies and collaboration with a variety of actors to promote the WPS agenda and participation of women in peace and security processes and decision making in the country.

The evaluation covered the period of the project implementation from November 2020 until March 2025.  In terms of geographical coverage, it was implemented in Tbilisi and 17 municipalities targeted by the project interventions.  The international consultant visited Georgia and traveled together with a national consultant to 14 locations including Kutaisi, Zugdidi and Gori to meet with women living in IDP settlements and conflict- affected villages alongside the ABL.

## The context of the project

The political and geopolitical situation in Georgia and the region

Complex challenges have shaped the project operating environment starting with the COVID-19 pandemic and continuing with multiple internal and regional crises, which all undermined political stability, resulted in economic slowdown had substantial security and political implications for the country, and exacerbated the implementation of the Women, Peace and Security (WPS) agenda in the country. The territories of Georgia as Abkhazia and the Tskhinvali region/South Ossetia remain a significant concern, with approximately 290,257 IDPs (as of 2021) , 53 percent of whom are women. Additionally, 46,620 individuals live along the Administrative Boundary Line (ABL) with Abkhazia, Georgia, and the Tskhinvali region/South Ossetia, Georgia.

Figure 1 Timeline of important events through the project implementation cycle

Before these events, Georgia experienced strong economic growth and wide-ranging reforms across all public sectors in 2019. Between 2010 and 2019, the country's GDP per capita grew steadily at an average rate of 4.8% annually. A significant milestone was reached in 2018 when Georgia advanced from a lower-middle-income to an upper-middle-income country according to the World Bank's GNI per capita classification. However, the COVID-19 pandemic had a particularly severe impact on women's social and economic conditions. Sectors traditionally dominated by women, such as trade, tourism, and hospitality, were among the hardest hit by the pandemic. According to the UN Women report, the impact of the COVID-19 pandemic was higher on women due to increased household burden (in particular, for large families with children), domestic violence, and deterioration in mental health.

The Russia-Ukraine war had far-reaching consequences for Georgia's development, extending well beyond its economic effects. The conflict's impact was multifaceted, touching numerous aspects of Georgian society. According to a 2022 joint report by UNHCR and World Vision, Georgia has become both a transit point and destination for Ukrainian refugees, with over 160,000 Ukrainians entering the country. As of October 2022, approximately 25,000 remained in Georgia. UNHCR's research shows that these refugees, particularly women, face multiple challenges. These include difficulties finding employment, navigating migration processes, and accessing essential services such as education, childcare, and psychological support.

It is important to note that the progress made on the WPS agenda over recent decades now faces serious risks. The adoption of the Law on Transparency of Foreign Influence , coupled with the post-election crisis and the Government’s decisions regarding the EU accession process , has created significant concerns. The new Law and ongoing political crisis could significantly impact the implementation of the WPS agenda in Georgia, as many organizations working on WPS issues rely on international funding and partnerships. This legislation could potentially hinder the work of women's rights organizations, peacebuilding initiatives, and civil society groups that receive foreign support to implement crucial WPS programs, particularly those supporting conflict-affected women and IDPs.

Additionally, the controversy surrounding the law and subsequent protests strained relationships between civil society organizations and government institutions, potentially affecting collaborative efforts necessary for effective WPS implementation. The situation has also raised concerns among international partners and donors who play a vital role in supporting Georgia's WPS initiatives, potentially impacting funding stability and international technical assistance for WPS-related programs.

It deems relevant for this evaluation to assess the project's contribution in relation to these developments and related policy documents, while also examining how changes in the political landscape might create opportunities for future UN Women initiatives. Additionally, it is important to analyze how these changes might affect partners' and stakeholders' ownership of project outputs and prospects for cooperation with the government.

Figure 2 Progress towards achievement of gender equality and women’s empowerment and SDGs

Even though, during the period of 2020-2024, the country moved some points up in overall performance (see Figure 2), significant challenges remain to achieve SDG 5 and SDG 16. According to the latest SDG report, Georgia continues to face major challenges in achieving SDG 5, though there has been modest improvement overall. The progress made in gender equality began to reverse during the 2020 political crisis and subsequent government changes. A significant symbolic setback occurred in 2021 when the government removed "Gender Equality" from the title of the Prime Minister's Advisor on Human Rights and Gender Equality position, signaling a shift in political priorities. This change was particularly concerning as it came at a critical time when several key policy documents were expiring. Multiple national strategies and action plans focused on gender equality and women's empowerment reached their end date in 2020. Their renewal process faced unexpected delays, creating a policy vacuum in crucial areas. Meanwhile, SDG 16 shows significant challenges, with progress remaining stagnant.

Figure 2 Achievement of SDG (2024)

There have been positive changes at the policy level during the project implementation cycle. In June 2022, the European Commission recommended to the EU Council that Georgia should be given the perspective to become a member of the European Union once the set of recommendations is addressed. Among the recommendations, it was stressed to notably consolidate efforts to enhance gender equality and fight violence against women.  At the end of 2022, several important framework documents were endorsed by the Government, namely: the Parliament approved the new State Concept on Gender Equality; 2022-2024 National Action Plan for combating domestic violence and violence against women and ensuring the protection of survivors; 2022 – 2024 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions 1325 on Women, Peace and Security. The Permanent Parliamentary Council on Gender Equality adopted the 2022-2024 Action Plan; by Resolution No. 88 of February 25, 2022, the Georgian Government tasked the Ministry of Finance with implementing a program budget marking system within the electronic budget planning framework. This system enables spending institutions to voluntarily classify requested funds and apply specific markings based on various thematic criteria, including climate change, gender considerations, and SDGs. In 2023 the parliament additionally approved the State Concept of Women's Economic Empowerment; National Human Rights Protection Strategy of Georgia for 2022-2030 and 2024-2026 Human Rights Protection Action Plan of Georgia.

Mainstreaming of the WPS agenda in Georgia

Figure 3 Timeline of NAP 1325

Georgia has actively embraced the global WPS agenda in response to its own conflicts. In 2023, Georgia ranked 39 out 177 countries (Index Score 0.812) according to the Global WPS Index.  As noted in the Women's Information Center's 2021 report ,  the country has made significant strides in implementing UNSCR 1325 and UNSCR 2250  at the local level over recent decades. Since adopting its first National Action Plan (NAP) in 2012, Georgia has continued to strengthen its commitment to the WPS agenda. The country is now implementing its fourth action plan (2022-2024), which marks an important milestone as the first plan with dedicated funding and specific budgets allocated for each activity. It is noteworthy that, in 2018, the localization process of the Women, Peace, and Security agenda was initiated.  As of today, the 2022-2024 National Action Plan of Georgia for the Implementation of the UN Security Council Resolutions on Women, Peace, and Security, along with the municipal Gender Equality/Women, Peace and Security Action Plans, serve as tools for the effective implementation of gender policies both at the national and local levels.

Despite Georgia’s active engagement in formulating and executing National Action Plans (NAPs) on Women, Peace and Security (WPS) since 2011, the thematic report of the Parliament of Georgia on the implementation of the Women, Peace and Security Agenda in Georgia highlights multiple issues that still require a systematic approach and immediate action from the state, such as  women’s low representation in peace processes and decision-making levels, including in the security sector; women’s low involvement in cyber security and countering violent extremism processes, as well as in the development of state policies and programs; the low awareness of IDP and conflict-affected women regarding human security and preparedness for crisis/emergency situations; the absence of policies and special mechanisms for preventing conflict-related sexual violence; the lack of mental health support programs; limited access to education, information, medication, healthcare, and public services, as well as state programs and finances.

According to the Public Defender’s (PDO) 2024 monitoring report, most state institutions have largely fulfilled their obligations outlined in the plan, aimed at empowering women in peace and security matters and increasing their participation.  The same PDO’s report mentions remaining challenges in the WPS agenda implementation process. While participation rate of women and youth in security and peace processes has increased, ensuring their effective involvement at the local level, including in decision-making processes, remains a challenge.  Women’s representation in conflict prevention mechanisms  remains low. Additionally, as Office of the State Minister of Georgia for Reconciliation and Civic Equality data shows in people-to-people diplomacy, only 16 percent of such initiatives were led by women’s organizations or focused on women’s issues in 2021 and 2022.

The CEDAW Committee welcomed the adoption of the fourth National Action Plan 2022–2024 to implement Security Council resolution 1325 (2000) and the creation of an advisory platform for the enhancement of women’s meaningful participation in peacebuilding; however, it also reminded that the full spectrum of the Security Council’s women and peace and security agenda as reflected in Council resolutions should be taking into considering when developing the next generation NAP.

Participation of women in decision making may be even more challenged due to the abolishment of the mandatory gender quotas by the Parliament on April 4, 2024. Prior to this decision, the Electoral Code of Georgia required that at least one out of every four persons on a party list must be a woman. The amendments have been adopted in an accelerated procedure, without prior public consultations, and without considering concerns raised by the President of Georgia, the Public Defender of Georgia, several representatives of the opposition and of the civil society, and by international organizations. The recent decisions of the Government to remove “gender equality” from the key document such as Gender Equality Strategy and replace it with equality between women and men shift the focus of the strategy from promotion of transformation of gender roles and norms that prevent women from meaningful participation in the society including in decision making on peace and security of the state.

Since  February 2023, when the legislation that required individuals, CSOs and media outlets that receive over 20 per cent of their funding from abroad to register with the Government was proposed by the Parliament,  many women’s CSOs have boycotted the work of the Gender Equality Council of the Parliament (GEC) by refusing to attend joint events and demanding the resignation of the Council’s Chairperson.  Approval of the Law on Foreign influence have caused the space for engagement and collaboration between the State and CSOs to shrink negatively: the work of the GEC and Inter-agency Commission on Gender Equality, Ending Violence against Women and Domestic Violence (CGE) progressed in 2023 without much engagement of women’s CSOs and women’s groups.

# Methodology

## Evaluation approach

Gender as a social institution  plays an important role in the social changes theories since gender relations are, like all social relations, constituted through rules, norms and practices by which resources are allocated, tasks are assigned, value is given, and power is mobilized. The evaluation sought evidence of changes in rules, norms and practices that could be attributed to the project interventions and that would have a transformative impact on power relations as giving women more power in influencing decision making in peace and security processes. The evaluation was theory-based meaning that the theory of change of the project was used as a hypothesis to guide assessment of the project design, interventions and results. According to the evaluation guidelines, the evaluation team reconstructed a project’s theory of change as represented in Figure 4. The reconstructed ToC was tested during the evaluation to assess whether it held true in the current context of Georgia. In addition, the ToC was used to enhance the inclusive and learning character of this evaluation and to promote discussion of processes and results by partners and beneficiaries, validation of assumptions and risks, and formulation of lessons learned and recommendations.

## Evaluation standards

This final evaluation was conducted according to the UNEG Norms and Standards for evaluation (2016) and the UNEG Code of Conduct for Evaluations in the UN System (2008). UN Women’s Independent Evaluation Service (IES) has developed the GERAAS, which has adapted UNEG Standards for Evaluation in the UN System to guide evaluation managers and evaluators on what constitutes a ‘good quality’ report at UN Women. The consultants ensured that the evaluation process and the final report followed the GERAAS quality standards. Human rights and gender equality were integrated at all stages of evaluation based on the UNEG guidance and the UN Women Handbook on how to manage gender-responsive evaluation (2022).  Finally, to answer the requirements for accountability at the inter-agency level against the performance indicators in the 2020 UN Disability Inclusion Strategy (UNDIS),  the consultants  reviewed the extent of mainstreaming of rights of people with disabilities across the project interventions.

Figure 4 The Project Theory of Change

Key risks:  lack of coherence among actors in integration WPS and gender equality into institutions, and interventions does not address the matter holistically (political, socioeconomic, ecological aspects; backlash against HR and GE due to regional and global conflicts and political instability in the country)

Clear framework for women’s participation in conflict prevention, peace and security

Government remains committed to Gender Equality and WPS agenda; Inclusive and accountable institutions achieved (SDG 16)

Outcome 1: Increase in women’s meaningful and representative participation in conflict prevention and peacebuilding at the community and national level

Outcome 2: Increase in accountability of government, especially key security sector partners, to Women, Peace and Security

Output 2.2: Key security sector partners have enhanced capacities to mainstream gender into their policies, procedures and operations

Output 1.2: Mechanisms in place for increased meaningful and representative participation of women in conflict prevention and peacebuilding at the community and national level

Critical assumptions:

- relevant to conflict prevention, peace and security national frameworks fully integrate women’s needs and rights

- UNSCR 1325 is fully operationalized, localized and funded

-Implementation of NAP 1325 and WPSA engages representatives of all sectors

-meaningful collaboration established between line ministries, CSOs, women leaders from conflict-affected communities and women -IDPs to promote women’s participation in peace

- mainstreaming of WPS into security sector institutions is based on disaggregated data

-  women involved in peacebuilding influence decision making in governance structures

Output 2.1: Government entities, including key security sector partners, have enhanced capacities and an evidence base to develop and implement the NAP 1325

Output 1.1: Increased capacity of women and girls (including internally displaced and conflict- affected) to meaningfully engage in conflict prevention and peacebuilding

linkage is evident                linkage is not evident

Root cases: social norms and stereotypes that persistently exclude women from political participation inc. peace negotiations; conflict- related sexual violence; GBV and VAG; low economic and environmental resilience of conflict -affected women

## Evaluation criteria and evaluation questions

The final evaluation was conducted according to the UNEG Norms and Standards for evaluation (2016), UNDP Evaluation Guidelines (2021), UNEG Ethical Guidelines for Evaluation (2020) and UNEG Guidelines on Integrating Human Rights and Gender Equality in Evaluations (2014).   The evaluation was based on the standard criteria of relevance, coherence, effectiveness, efficiency, sustainability. In addition, based on the donor request, the evaluation also explored whether the project had any impact in terms of producing any kind of longer-term results. Evaluation of cross-cutting issues included inclusion and conflict sensitivity. Guided by the key evaluation questions in the terms of reference (see attached in the Annex 9), the evaluation team developed a refined set of questions and sub-questions under the criteria. The full list of evaluation questions and specific indicators of success (standards) is included in Annex 4 (Evaluation Matrix). The list of reviewed documents is found in Annex 3.

The key evaluation questions are presented as follows:

Relevance:

- How does the project reflect and align with gender equality/WPS national strategic plans and normative frameworks as well as Georgia’s international obligations and commitments?

- Is the project design based on quality analysis, including gender and human rights-based analysis, risk assessments, socio-cultural and political analysis? To what extent did the project addressed the causes of gender-based inequalities and worked to transform harmful gender roles, norms and power relations?

- Were the programmatic strategies appropriate to address the identified needs of diverse groups of beneficiaries i.e. from the state institution, civil society, academia, media?  How well did the project address the needs of diverse groups of women including most vulnerable and marginalize in Geogia in a peacebuilding context?

Coherence:

- To what extent the project adheres to corporate strategic priorities of UN Women, the work of the UN Country Team (UNSDCF), the national plans to achieve SDGs, in particular SDG 5 and SDG 16?

- How does the project design match the complexity of national structures, systems and decision-making processes? To what extent have the partnerships developed under the project contributed to coherence of interventions between state institutions, civil society, UNCT and other actors in WPSA?

- To what extent has UN Women Georgia used strategically the agency’s comparative advantages to accelerate the WPSA in Georgia?

Effectiveness and Impact:

- What has been the progress made towards the achievement of the expected outcomes and expected results? What are the results achieved? Are there any unintended results?

- What are the reasons for the achievement or non-achievement of the project results?  What is the influence of the specific country’s context and circumstances on the achievement of results and operational effectiveness?

- To what extent have the project management structure and approaches (i.e. agile, adaptive management) contributed to the effective achievement of results? Does the project have effective monitoring mechanisms in place to measure progress towards results? How adaptable and rapidly does the project react to changing situations?

- To what extent have the capacities of relevant duty-bearers and rights-holders been strengthened? To what extent is the project changing the dynamics of power in relationships between different groups?

- What is the likelihood that the project results are bringing about gender transformative changes that address the root causes of gender inequalities – including prevailing social norms, attitudes and behaviors, discrimination and social systems?

- What evidence exists that the project has delivered longer term results from processes through to benefits?

Efficiency:

- Have resources (financial, human, technical support, etc.) been sufficient and allocated strategically to achieve the project outcomes and gender equality specific targets?

- To what extent were relevant stakeholders and actors included in the project planning and implementation? To what extent have partnerships established under the project contributed to efficiency of the project?

Sustainability:

- How effectively has the project been able to contribute to the generation of national ownership of the project’s outputs?

- What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time after the project phases out? To what extent has the project identified strategic partners that could pick up on supporting continued government and non-governmental action when the project comes to an end? What is their level of commitment to continue to replicate some project activities?

- To what extent has the project’s exit strategy been well planned and successful? To what extent has UN Women been able to promote replication of project successes?

Inclusion

- Did the implementing parties and their partners systematically integrate HR, GR and Inclusion of People with Disabilities in the project design and implementation? What -if any- types of innovative good practices have been introduced in the project for the meaningful participation and empowerment of IDP and conflict affected women and youth?

Conflict Sensitivity

- Did the implementing partners have an explicit approach to conflict-sensitivity, in particular in addressing gendered causes of conflicts in the WPS context in Georgia, i.e. VAWG? Were internal and external capacities of implementing partners adequate for ensuring an ongoing conflict-sensitive approach?

## Data collection and analysis methods

The data collection methods were both qualitative and quantitative methods. Qualitative methods included desk review, individual interviews and focus groups discussions. Individual interviews were conducted with representatives of the Government, line ministries and state agencies, as well as the project partners from CSOs, UN Women staff and representatives of UN and EUMM to peacebuilding formats (GID and IPRM), and representatives of services providers from international NGOs and think tanks. The purpose of individual interviews was to elicit perceptions of changes resulted from the project implementation related to enhanced capacities of duty bearers (security institutions) and right holders (IDP and conflict affected women) to promote the WPS agenda in Georgia.

The focus group discussions targeted IDPs and conflict- affected women in 17 municipalities targeted by the project. The purpose of focus group discussions was to provide opportunities to a significant number of women (and men) including most vulnerable to voice their opinion about the project interventions and changes in their capacities and transfer in power relations i.e., systematic inclusion of IDP and conflict affected women in peace and security processes in Georgia as national and local level. The other objective was to ensure that women of different backgrounds and living in different localities such as IDP settlements and villages along ABL were able to come together to share their opinion about the project intervention and results and how the impact of the project might be enhanced in future. In total, the evaluation teams interviewed 147 IDP and conflict-affected women and 5 men in 14 municipalities of Georgia.

Quantitative methods included an online survey, as well as collection of the project quantitative data (mainly, on beneficiaries and their participation).  The online survey targeted women-leaders mobilized by three partners from CSOs in the network. These women mobilized other women in their municipalities into informal groups or networks and coordinated advocacy and other initiatives of the project. Also, they were the target group of comprehensive capacity development provided by the project to right holders. The purpose of the online survey was to elicit their opinion of changes in capacities of women and their involvement in peace and security processes.

As mentioned before, quantitative methods included collection of administrative data by project management and Monitoring, Evaluation and Learning (MEL) focal points at partners’ organizations. The baseline information collected at the beginning of the project was used to assess to what extent targets had been achieved and to discuss reasons for their achievement or non-achievement (see Results and Resources Framework in Annex 2).

Finally, data collection approaches were culturally appropriate to reduce conflict- sensitivity and facilitate participation. For instance, participants from Abkhazia were ensured maximum security during online interviews. During the visits to municipalities, the evaluation team followed security recommendations provided by UN Women Georgia and partners from CSOs to avoid any topics that might be sensitive in the current political situations. During the field visits, the international consultant was provided with translation into the Georgian language.

Gender-responsive methods data collection methods were used to ensure that participants actively participate in the data collection and interpretation, i.e. appreciative inquiry to identify results and positive changes in capacity development and identification of success stories.  For instance, during the focus groups discussions, the participants were asked to identify what they believed had been the most significant changes in the results of the project. Data collection instruments are found in Annex 6.

Qualitative data analysis methods included content analysis. Content analysis involved systematically analyzing documents and interview protocols to identify patterns and themes in relation to evaluation questions and indicators (Annex 4 Evaluation Matrix).  Quantitative data was analyzed using SPSS and included, mainly, descriptive statistics to identify frequences, means and other. Multiply data sources (triangulation) such as quantitative data collected in the scope of the project, qualitative data from reports, interviews and research were used to test validity of identified patterns and themes. The use of human rights and gender equality responsive data analysis methods included comparing the data obtained during the interviews with existing information on the situation of HR & GE (i.e. monitoring and assessment reports, Gender Country Profile, etc.); identifying themes and responses which were common and different between groups of stakeholders including duty bearers and rights holders; interpreting the data in relation to power relationships and conflict; and comparing individual, human stories and case studies with general information found in the studies and reports prepared by the project and other research and information available in the country on gender equality and women’s participation in peacebuilding  and conflict prevention processes.

## Evaluation sample and participation of stakeholders in evaluation

Selection of participants (sampling) in this evaluation was informed by the stakeholder analysis conducted during the inception phase (see Annex 5) and followed the criteria for inclusion such as the position of stakeholders and beneficiaries to the project Outputs and deliverables, priorities for their inclusions (High, Medium, Low) based on criticality of their engagement for sustainability of results, and their role in the evaluation. To ensure that most vulnerable women could participate in focus group discussions, the evaluation team conducted a preliminary interview with representatives of three CSOs to identify their inclusion strategies and to communicate the evaluation team’s requirements for inclusion of women with disabilities and women- survivors of violence.  In selection of respondents for interviews and focus groups discussion, the evaluation team applied purposive, non- random sampling methods. In total, the evaluation reached 170 informants, out of which about 90 percent constituted IDP and conflict-affected women in 17 municipalities targeted by the project. The summary of beneficiaries and stakeholders’ participation in evaluation is presented in Figure 5.

Figure 5 Participation of stakeholders in evaluation

The evaluation team conducted a validation workshop with 22 women-leaders in the communities and representatives of three CSOs- partners to validate the findings from the online survey and focus group discussions and to collect their feedback into the evaluation findings and lessons learned.  In addition, the evaluation team made two presentations of the draft report to key partners and stakeholders and, separately, to a donor. The list of interlocutors by a stakeholder group is found in Annex 1.

## Limitations

Prior to the data collection, the evaluation team with support of the project team and key partners identified limitations that might affect participation of beneficiaries. The limitations were related to the political unrest in Georgia and the fact that many international organizations seized or put on hold cooperation with the Government after the elections in October 2024.  Cooperation of civil society with governmental institutions was limited since the Law on Foreign Influence was adopted in 2023. There were no limitations found to participation of representatives of right holders. Table 1 presents limitations and mitigation strategies employed by the evaluation team.

Table 2 Limitations and mitigation strategies

| Limitations | Risks | Mitigation strategies |
| --- | --- | --- |
| - Political crisis | The sample for national level duty bearers’ institutions may be not reached | - Data from interviews was supported by secondary data collection, such as institutional plans that integrate NAPs 1325 and WPS and interviews with capacity building providers- partners of the project; in addition, the evaluation team used the tracking tool used by UN Women to track implementation of recommendation from Participatory Gender Audits and Gender Impact Assessments - Reports of the service providers were consulted to validate findings from the desk review of institutional plans and other documents |
| - Reluctance of local administration to participate in the interviews due to the political crisis and civil unrest | The sample numbers may be not reached, and findings will not allow for generalization about the extent of mainstreaming of WPS into local policies and plans | - secondary data was collected such as gender equality plan, - monitoring data collected by UN Women and reports of partners from CSOs were used to evaluate the results of localization component |

The mitigation strategies proved effective, and, despite the limited participation of representatives of security institutions in the evaluation, use of secondary data and primary data from interviews with state institutions and training providers allowed for quality findings and conclusions.

## Evaluation management and performance standards

The evaluation team reported to the UN Women Georgia Monitoring and Evaluation Focal Point.  The Project Analyst was responsible for day-to-day management of the evaluation and ensured that the evaluation is conducted in accordance with the UNEG Evaluation Policies, United Nations Evaluation Group Ethical Guidelines and Code of Conduct for Evaluation in the United Nations system and other key relevant guidance documents. The evaluation process was supported by the UN Women Europe and Central Asia Regional Evaluation Specialist. The preliminary evaluation findings were presented to the Evaluation Reference Group comprised of representatives of UN Women, the project team at the UK Embassy and civil society partners. The Evaluation Reference Group reviewed the draft evaluation report and provided substantive feedback to ensure quality and completeness of the report.

## Ethical issues

The evaluation was conducted in accordance with the principles outlined in the UNEG Ethical Guidelines for Evaluation (2020). The following principles were followed throughout the evaluation:

Respect: the evaluation process and communication of results were conducted in a way that clearly respected the stakeholders’ dignity and self-worth.

Empowerment: the use of participatory and empowerment approaches methods was emphasized by the evaluators to ensure that all participants realized benefits from their participation in the evaluation and how it was related to realization of human rights, gender equality and women’s empowerment.

Informed consent: every participant was informed about the objectives of evaluation, and their participation was on a voluntarily basis, meaning that, at any time, all participants were given the rights to choose whether to participate and/or withdraw from the evaluation.

Inclusion and Non-Discrimination: equitable participation and treatment of all participants were ensured through the evaluation methodology; differences in culture, local customs, religious beliefs and practices, personal interaction and gender roles, age and ethnicity were mindfully weighted and considered when planning, carrying out evaluation and reporting on the results.

Do no harm:  the evaluation team ensured that no harm happened to the participants of the evaluation, in particular women in the communities; all meetings were held in safe places and no recording was made; notes from interviews did not contain full names and were not shared with anyone, as well,  data presentation and discussion in the report did not allow for their potential identification.

Fair representation: the selection of participants was done in relation to the aims of the evaluation, not simply because of their availability; the power imbalances were purposefully addressed by ensuring that data collection methods allowed for participation of the most vulnerable women from locations difficult to reach.

# Findings

## Relevance

Finding 1: The project objective of increasing in women’s meaningful and representative participation in conflict prevention and peacebuilding is well aligned with the CEDAW recommendations, as well as UNCF 2021-2025, UN Women Strategic Note and national framework documents. Through support to development and implementation of the 2022-2024 National Action Plan on UNSCR 1325, UN Women and their partners aimed at enhancing the commitment of the state to the WPS agenda.

Acceleration of the WPS agenda at the national and local level was seen as a leverage to promote more sustainable peace and development of the country which was not possible without women’s equal and meaningful participation in peacebuilding processes. To that end, support to localization of NAP 1325 as a key instrument to mainstreaming the WPS agenda at the national and local level enabled the project partners to engage with the formal peace processes such as Geneva International Negotiations (GID) and with relevant state agencies and ministries responsible for peacebuilding, security, conflict resolution and post-conflict recovery.

Coordinated by the Human Rights Secretariat of the Government of Georgia and with the direct support from this project, development of the fourth NAP was entirely a participatory process with involvement of local and international non-governmental organizations, relevant experts, civil society organizations, and other stakeholders. Moreover, 2022-2024 NAP 1325 was fully funded (27, 680 907, GEL or USD $10,426,877).  It should be noted that 2022-2024 NAP 1325 has three impact areas: women’s participation; elimination and prevention of violence; and women’s empowerment and protection. Out of 39 implemented activities, the UN Women project contributed to the implementation of 23 activities or 59 percent, although UN Women was initially indicated as a Partner Agency for 12 activities (24 percent of all activities).

The project design addressed most of recommendations from the CEDAW Committee such as the concerns related to the decreased involvement of Georgian women in peace negotiations (from 40 per cent in 2018 to 20 per cent in 2022) at the Geneva International Discussions (GID) to ensure a gender-responsive implementation of the ceasefire agreement.  One of the project targets was to increase participation of women in the GID to 30 percent which has been achieved by the end of the project. To address the recommendations related to implementation of the full spectrum of the WPS pinpointed in 10 UN Security Council resolutions (1325, 1820, 1888, 1889, 1960, 2106, 2122, 2242, 2467, and 2493), the project emphasized inclusion of women and youth in the national peace processes and in the local level dialogue. To that end, the project contributed to enhanced capacities of IDP and conflict- affected women in 17 municipalities and of women- led CSOs empowering them to become more vocal and organized in advocating for women’s needs related to conflict prevention and post-conflict recovery. According to the interviewed women at the grassroots level and representatives of civil society, the project was most relevant in addressing gaps related to lack of knowledge of the WPS agenda and relevant UN resolutions, as well as lack of mechanisms for women’s engagement.

As Figure 6 presents, 93 percent of women – beneficiaries of the project (out of 78 surveyed) believed their capacities had been enhanced as a result of the project capacity building interventions, while 95 percent of women thought that their access to participation in peace and security processes had been enhanced by the project due to interventions that targeted gender sensitivity of formal peace formats (GID and IPRM) and establishment of women’s WPS networks and advisory groups.

Figure 6 Perceptions of women of changes in access and capacities

Other relevant examples include support to institutionalization of women’s consultative or advisory WPS platforms and networks at the national level and at the security institutions and to increase women’s participation in people-to-people diplomacy initiatives in line with the General Recommendation 30 of the Committee on the Elimination of Discrimination Against Women on Women in Conflict Prevention, Conflict and Post Conflict Situations.  For instance, the proportion of people-to-people initiatives supported by Office of the State Minister for Reconciliation and Civic Equality through the Peace Fund for Better Future (PFBF) implemented by women constituted 40 percent in March 2025 comparing with 17 percent in 2019. As relevant to the UN SCR 1820, 1888, the project promoted establishment of sexual harassment and violence prevention mechanisms at six security institutions to ensure that women had equal opportunities for participation and career development.

Finding 2: The design was informed by results of monitoring of previous NAPs 1325 and several assessment and research studies conducted to identify root causes for low inclusion and participation of women who were most affected by conflicts. Relevant strategies have been designed to increase meaningful participation of IDP and conflict- affected women in peacebuilding and ensure that state institutions systematically collect information and data on needs of women and integrate them into policy and programme development.

The project design was based on the quality analysis of political, economic and socio-cultural aspects of women’s low participation in peace processes. The analysis of the previous NAPs 1325 and monitoring reports committed by the Public Defender’s Office in Georgia and civil society organizations  informs of high relevance of the project interventions that targeted the following key challenges for women’s meaningful participation in peacebuilding processes such as:

- lack of motivation among states institutions resulting in formal implementation of institutional gender equality strategies,

- lack of coherent integration of the WPS into local governance plans to address IDP and conflict- affected women’s needs in the conflict resolution and post- conflict recovery and development,

- limited participation of conflict affected women in shaping coherent policies that target peace and security in the communities on both sides of the ABL.

In relation to the latest, the key obstacles for participation of IDP and conflict affected women were found as low awareness of conflict-affected women about the peacebuilding processes , lack of women in “key positions” in the security structures, prevailing harmful gender stereotypes and perceptions of women and men’s roles and capabilities.    In addition, peacebuilding formats remained gender blind to ensure that women’s needs were considered in peace negotiations. For instance, human security issues constituted 78% of the IPRM agenda including, mainly, land cultivation or irrigation issues, negotiations over access to religious sites and graveyards for local communities, damage to property or access to property rights; and, less frequently, access to education and healthcare. While many of the agenda items affect conflict-affected women and men in specific ways, these were not discussed from a gender viewpoint.

Low participation was also affected by poverty levels in conflict-affected communities.  As it was acknowledged in the PDO monitoring report on the implementation of the NAP 1325 (2024), social- economic safety remains a problem for the populations living along the ABL. The closure of so-called checkpoints in the conflict-affected villages (with Abkhazia and South Ossetia) had further complicated the social-economic condition and security issues of vulnerable groups. To address these challenges, the project promoted improvement of basic living conditions of IPDs and conflict – affected communities by conducting assessment of two economic programmes implemented by the LELP IDP agency and providing women with small grants to address basic needs of IDP women and contribute to security in the communities.  A total of 41 initiatives were financed, with an overall budget of 46,200 GEL. As Figure 7 presents, most initiatives targeted improvement of school infrastructure, access to water, creating economic opportunities such as mills.

Figure 7 Community initiatives implemented by women’s groups and their beneficiaries

Finding 3.  The project Outputs were sufficient to achieve the changes identified at the Outcome level. The risk assessment was continuous and allowed for the project course correction to amplify opportunities for participation of women in formal and informal peacebuilding processes.  While the Theory of Change remains valid, some critical assumptions required revision to ensure better relevance to the current situation characterized by the backlash against gender equality and women’s rights in Georgia including the role of the civil society in implementation of the WPS agenda and UNSCR 1325.

The project’s Theory of Change defined the chain of results towards increased women’s participation in decision making in peacebuilding and conflict resolution processes (see Figure 4). Four project Outputs presented key milestones to be achieved to produce transformative changes at the policy, institutional and individual level to promote changes under two Outcomes. The cause- effect relationships between most of Outputs were well- established emphasizing the criticality of achievement of gender-responsiveness and accountability of security institutions (SDG 16) and peace formats (GID and IPRM) for increased meaningful participation of women including from most vulnerable groups in peace and security processes.

Having broadly formulated Outputs added to flexibility of the design which became important in the situation when political unrest and backlash against gender equality and women’s rights in Georgia affected stagnation of formal peace negotiations e.g., Gali district due to global and regional conflicts. The project interventions ensured ample opportunities for women’s participation in the regional and international WPS forums to prevent that the WPS capacities of women and their networks do not experience erosion and remain visible and active. It is noteworthy that UN Women had consciously pursued engagement with women’s CSOs and their inclusions in all project platforms, meetings and activities as risk mitigation measures. In addition, the Project Steering Committee, composed of representatives of UN Women and the project staff at the UK Embassy and key stakeholders played a pivotal role in ensuring interventions remained relevant and informed by risk assessment.

However, the validity of the theory of change depends largely on sustainability of commitment of the Government to gender equality and women’s empowerment and cooperation with civil society. While commitment of the state institutions targeted by the project remained strong due to their accountability for implementation of NAP 1325, cooperation with civil society saw a decline during the lifetime of the project. The latest was most disturbing given that the criticality of participation of civil society (along with state institutions) in implementation of the WPS agenda, which has been called upon in several resolutions on WPS. The strategies employed by UN Women to extend participation of women’s led CSOs and women’s rights advocate in global and regional WPS networks and forums were found relevant to enhance the role of women in peace and security processes and raise their visibility at the national level.  It was aligned with the project’s objective to ensure recognition of women’s expertise and live experiences among state institutions by addressing them consistently throughout the peace and security processes. The evaluation acknowledges the relevance of measures undertaken by UN Women to address regional peace and security and advocate for increased donor support for WPS to engage women’s CSOs and women and youth peace ambassadors to counter growing militarization and securitization in the region.

## Coherence

Finding 4: UN Women Georgia effectively leveraged its comparative advantages, including its technical expertise in NAP 1325, strong engagement with the WPS agenda, and access to international WPS platforms and forums. Building on results of the projects implemented in other thematic areas under the UN Women Strategic Note, the project added to coherence between interventions targeting gender equality and women’s empowerment and implementation of the WPS agenda. At the same time, it would have been beneficial to make better coherence with other programmes of UN Women, especially, on gender-based violence, local governance and women’s political participation.

Coherence was demonstrated by building on the existing experience of UN Women in mainstreaming gender equality and women’s empowerment in Georgia. Among key tools to promote WPS, UN Women used its experience in conducting Gender Impact Assessment (GIA) and Gender Participatory Audits (GPAs), establishment of sexual harassment and violence prevention mechanisms at workplace, and development of gender equality policies and plans at the level of security institutions. Furthermore, continuous support to local governance institutions on development and implementation of local gender equality plans allowed UN Women and their partners from civil society to integrate WPS issues as a part of NAP 1325 localization strategy. Furthermore, transfer of social mobilization methodology successfully piloted by UN Women under several projects e.g., on local governance and women’s economic empowerment, facilitated engagement of most vulnerable women and youth from IDP settlements and communities along the ABL to participate in peacebuilding initiatives.

The efforts of the project to accelerate the WPS agenda could have benefited from better coherence with other programmes implemented by UN Women, especially targeting gender-based violence and gender-responsive local governance. For instance, complementarity of mainstreaming of gender equality and women’s empowerment at the local governance institutions pursed by UN Women in a partnership with the National Association of Local Authorities of Georgia (NALAG) could have added to a greater integration of the WPS interventions in the gender equality policies and action plans (see Finding 7). Based on the analysis of six municipalities (Khoni, Zugdidi, Senaki, Kutaisi, Tskaltubo, and Khashuri), the evaluation established that the NAP 1325 priorities had been partially integrated into local action plans, with stronger alignment in some thematic areas and significant gaps in others.

As mentioned previously, the efforts of the project to address economic empowerment of IDP and conflict- affected women were appreciated by women-beneficiaries of the project and other community members.  Nevertheless, among the multidimensional security issues that IDP and conflict- affected populations living at the ABL continue facing, poverty remains a critical impediment to post-conflict recovery and resilience. A study by UN Women and ANOVA (2023) conducted under the project highlighted the severe economic hardship faced by IDP women in Georgia (see Figure 8).  According to the qualitative study, the impacts of the Georgian-Abkhaz and Georgian-Ossetian conflicts on the internally displaced population, including women, are mainly economic difficulties, poor living conditions, and the lack of development/self-realization opportunities. The main problems included: housing issues, unemployment, lack of personal development opportunities, inaccessibility of healthcare services, and domestic violence.

Figure 8 Major economic challenges experienced by IDP women

As shared by participants of focus group discussions, lack of economic opportunities affected overall motivation and activism of women and youth to participate in solutions of community problems. According to partners from CSOs and women-leaders, achieving better coherence between the WPS project and projects of UN Women Georgia and other actors on women’s economic empowerment would have allowed for a greater mobilization of women and youth to contribute to peace and security in their communities.

Finding 5: UN Women established effective partnerships with UN and non-UN entities involved into formal peacebuilding processes and security processes in the region which ensured increased visibility of the WPS interventions at the national and international level. The establishment of the WPS Task force under the UN GTG helped to organize some high-level meetings and activities which engaged stakeholders from state institutions, civil society, academia and think tanks. In addition, cooperation with the UN Women ECAS office resulted in organization of regional WPS forums and capacity building of peace ambassadors from Georgia and the regions, and establishment of a multi-actor WPS platform.

Out of the United Nations Country Team, UN Women remains one of two agencies (UNFPA) with strong programmatic support to implementation of the Government’s commitments under the NAP 1325. While it may be explained by the global position and expertise of UN Women in WPS, it also because the NAP 1325 is a stand-alone document that outlines the Government of Georgia commitments towards the WPS Agenda.

To advance meaningful participation and representation of women in building sustainable peace and security in the country and support the Government of Georgia in meeting with its obligations under the WPS agenda, the Task Force on Women, Peace and Security was established in October 2020. It is developed under the UN Gender Theme Group (GTG) chaired by UN Women. The TF on WPS comprised of 59 members, most of them being partners in this project, is co-chaired by UN Women and Kvinna till Kvinna South Caucasus Office. It allowed the project to organize some high-level meetings to raise recognition of the WPS expertise of civils society organizations and women at the grassroot level. For instance, EUMM and UN Women organized a meeting between the Committee for Civilian Aspects of Crisis Management delegation and grassroots women (4 women from ABL villages) and three women’s CSOs. The meeting was an opportunity for IDP and conflict- affected women, including young women’s CSOs, to have a direct exchange with 25 representatives of the EU member states about general safety and security around ABLs, human security needs and challenges experienced by women and girls on both sides of the ABL.  As well, the Open Day 2024 on WPS was organized by UN Women in cooperation with the UN Resident Coordinator’s Office, the Office of the UN Representative to the Geneva International Discussions (UNRGID), the United Nations Development Programme (UNDP), the Office of the United Nations High Commissioner for Refugees (UNHCR) and other UN agencies in Georgia. Annual WPS Open Day meetings with women engaged in peacebuilding-efforts, women- activists and representatives from women’s civil society organizations and from UN entities provided a significant platform to discuss the challenges to the implementation of the WPS agenda and the progress that had been made. According to the survey findings, women-leaders and WPS focal points in the communities highly appreciated opportunities that annual Open Days provided for expressing their needs and concerns related to peace and security.

As mentioned previously, the project interventions were closely aligned with NAP 1325 and their scope covered challenges under all four WPS Pillars, but with evident emphasis put on Participation. Better coherence would have been appreciated among UN and non-UN actors to promote full implementation of the WPS agenda (10 UNSC Resolutions on WPS).  The analysis of the WPS Task Force meeting minutes showed that there was more potential for TF to undertake a more consolidating role and foster stronger coherence among all actors.

## Effectiveness and Impact

Finding 6. The project was effective in supporting six security sectors institutions and other state agencies to implement activities and achieve targets defined in 2022-2024 NAP 1325. Although the level of achievement of targets differed among state institutions and agencies, the project contributed to enhanced gender- responsiveness of internal policies and processes that promoted participation of women in decision making. At the same time, transforming gender roles and norms in terms of participation of women in decision making would require better synergies with UN Women and other partners’ projects on women’s political participation.

Under the project, 247 officials (152 women, 95 men) from state institutions (GIS, IDP Agency, SMR, PDO, MFA, LEPL-Legal Aid, etc.) enhanced their knowledge on WPS issues and improved their skills of mainstreaming WPS Agenda in their institutions. According to the PDO report (2024) , most state institutions largely fulfilled the commitments outlined in NAP 1325, aiming to empower women and increase their participation in peace and security issues.

In the result of extensive capacity development that included training, conducting participatory gender audits and gender impact assessments, several institutions like the Ministry of Defence (MoD) and the Ministry of Foreign Affairs (MFA) made significant strides in developing and implementing gender equality policies and career development opportunities for women.  MoD and MFA also integrated WPS principles into their training programs, including pre-deployment training for peacekeeping missions and career development programs. The MoD established a centralized career management system to ensure transparency and fairness in professional development.

Almost all institutions improved their systems for collecting and analyzing sex-disaggregated data to monitor gender equality progress in recruitment and career advancement for women. In addition, most institutions established mechanisms for preventing sexual harassment and work-based violence which is most relevant to the WPS agenda (Pillar Prevention). Figure 9 presents the areas of progress based on the analysis of results undertaken by the evaluation team in six security sector institutions.

Figure 9 Achievement of NAP 1325 targets by security sector institutions

| NAP 1.1.1 | Production of sex-disaggregated data |
| --- | --- |
| NAP 1.1.3 | Produce of sex disaggregated data in the career development programs for employees |
| NAP 1.1.4 | Develop/ update/approve internal documents on gender equality policy |
| NAP 2.2.1 | Develop and introduce and/or improve mechanism in the security sector for the prevention and effective response to sexual violence, gender-based violence and sexual harassment cases |

However, challenges prevail in terms of addressing gender stereotypes and promoting women to the senior leadership positions. For example, despite some improvements, women remain underrepresented in senior decision-making positions across most institutions, particularly in the MFA and MIA. The MFA has a relatively balanced gender ratio overall, but men dominate senior diplomatic positions.  According to the study conducted by the Geneva Centre for Security Sector Governance (DCAF), unconscious bias prevented from transformation of gender norms, in particular in selection of women for leadership positions; changing the mindset in defence forces would take more time and it required ( and will require in future) constant awareness raising, as well as strong commitment of leadership to promote gender quality and women’s empowerment into all institutional processes and practices.   Enhancing sustainability of gender equality policies at the institutional level should help maintain the progress achieved in terms of women’s representation and leadership in the security sector.

Finding 7. Interventions that targeted localization of the WPS agenda were partially effective, also, due to erosion of cooperation between local governance institutions and CSOs after the Law of Foreign Influence was adopted in 2024. The project contributed to the relevance and inclusiveness of local gender equality plans but more effort would be needed to fully integrate the WPS agenda at the local level.

In 2022-2023, the NAP 1325 localization process went on a larger scale with support of the CSOs coalition led by IDP Women’s Association “Consent” (IDPWA). Within the framework of the project, 28 workshops and trainings were held, and 199 decision-makers and members of the Gender Equality Council were trained on the issues of gender-responsive policy development, women, peace and security, gender budgeting, and advocacy. The capacity development was complemented with raising awareness on the importance of women’s involvement in development and implementation of local policies. Integration of needs of IDP and conflict- affected women and WPS issues into the local gender equality plans was supported by strong advocacy using results of participatory assessments conducted by CSOs with active involvement of local women. Local action plans were developed in all 17 municipalities. Figure 10 presents the areas of strong alignment with NAP 1325.

Figure 10 Areas of strong alignment with NAP 1325

| #### Gender Equality Institutionalization | - All LAPs strengthen the role of Gender Equality Councils at the municipal level. - LAPs promote gender-sensitive governance and encourage the inclusion of women in local decision-making. - Municipalities implement gender-responsive budgeting aligning with NAP priorities. |
| --- | --- |
| Capacity Building & Awareness Raising | - LAPs include training for municipal employees and civil society on gender equality. - Some municipalities include training on international commitments, such as UN Security Council Resolution 1325. - Public awareness campaigns on gender-based violence (GBV) and early marriage prevention are present in most LAPs. |
| Gender-Disaggregated Data Collection & Monitoring | - LAPs prioritize collecting gender-related statistics to guide policymaking. - Regular reporting mechanisms are included in most local plans. |
| Economic Empowerment of Women | - LAPs focus on female entrepreneurship, employment programs, and labor market integration. - Several municipalities (e.g., Senaki, Zugdidi, Tskaltubo) promote gender-responsive economic initiatives, though these are often not explicitly linked to WPS goals. |

According to the analysis done by the evaluation team, the focus on prevention of gender-based violence (GBV) was found strong across all municipalities; local action plans (LAPs) included awareness campaigns, support for survivors, and legal protection measures making direct alignment to NAP 1325, which might provide an opportunity in future for women’s peacebuilding networks to address more holistically issues of security and prevention of violence against women and girls. At the same time, the needs of IDPs and conflict-affected women were marginally addressed. For instance, IDPs and conflict-affected women were mentioned in some LAPs but were not always prioritized; few municipalities like Senaki explicitly integrated IDPs into decision-making structures; Tskaltubo and Zugdidi, both municipalities with significant IDP populations, did not have specific WPS policies for them.

The latest may be explained by the allocation of responsibilities between municipalities and central government in addressing the needs of IDPs. The central government leads the processes related to resettlement, including the construction of apartment buildings, and the allocation of houses to IDPs and local authorities are not the part of the Interagency Steering Committee. Therefore, they could not bring positions of local authorities on IDP issues systematically to the Steering Committee or to any other decision-making bodies at the central level. Hence, when it comes to creating or developing the infrastructure and services around the new IDP settlements, local authorities systematically do not anticipate the service or infrastructure that new settlements may need, e.g., playgrounds or community spaces for children and adults etc. It explains that advocacy initiatives implemented by IDP women were much appreciated by local municipalities as these initiatives often included issues that remained beyond the local governance mandate and available budget such as creating playgrounds for children, solving problems with sewage and garbage removal and other.

Figure 11 Alignment of advocacy to WPS Pillars

Out of 79 advocacy initiatives analyzed by the evaluation team, 18 percent that could be linked to the NAP 2022-2024 included access to transportation and sport for youth, access to health services and renovation of education infrastructure. Of all advocacy activities, 92 percent were related to the Relief and Recovery Pillar and addressed the most essential needs of IDPs and communities living along the ABL (see Figure 11). Despite of some successful advocacy initiatives that added to security of women and their communities, like having more police patrols at the ABL and having women-police agents at the ABL crossing points, the findings pointed to the need for local municipalities to increase their alignment with the WPS agenda and add IDP-focused programmes for women and youth into the locals plans. The gaps that were identified by the evaluation included also lack of structured collaboration with the security sector, for instance, there was minimal engagement with security institutions (police, military, crisis management teams) reflected in LAPs.

Finding 8. The project has contributed to capacities of women to participate in formal peacebuilding processes and advocate for their rights and needs at the local and national institutions. There is good evidence of increased leadership of IDP and conflict -affected women and their aspirations to become self-reliant in advocating for their needs, although the role of CSOs remains critical in providing support and space for their dialogue with duty bearers from the central government and local administration.

The achievement of Outputs under Outcome 1 was found effective. Within the framework of the project, 13 training modules were developed, through which 265 women were trained. As a result of the implemented interventions, the awareness of women- leaders and women in the communities about UNSCR 1325 and the WPS agenda increased, which was supported by the findings from the survey. In addition, as data from the focus groups discussions suggested, their technical skills were improved in the use of modern technologies, as well as in matters of information gathering and documentation. Figure 12 summarizes the evidence of women using a variety of tools and technologies to support their cases. Furthermore, women’s awareness of the importance of their involvement in the process of local policy development and implementation increased, which improved practical outcomes in terms of planning and implementing the advocacy process. Additional activities included the involvement of women-

Figure 12 Use of tools and technologies by women

leaders in various events planned and implemented by the Coalition members’ organizations. The events were related to such issues as women, peace and security, gender-based violence, women’s political participation, etc. Also, a meeting of IDPs and conflict-affected women was organized with political party leaders and other members, which served to raise women’s political awareness.

Findings from the survey that was completed by 78 women-leaders informed about increased confidence and self-reliance of women in networks to influence the direction of social change. At the time of this evaluation, 47 percent of cases brought up by women were resolved or partially resolved and the solution of 53 percent was ongoing. There was also substantial evidence of increased capacities of women to advocate which was confirmed by women themselves, as well as Co-Chairs of GID, representatives of the IPRM format and participants of annual Open Days interviewed in the scope of this evaluation. A dedicated activity in the project design included targeted preparation of women by civil society partners to participate in formal peace processes and Open Days including training in presentation and argumentation skills and use of evidence.

It was also evident for evaluators that women were ready to take the next step towards implementation of a sustainable peacebuilding agenda. Some best practices included using structured tools by women’s groups to prioritise advocacy needs like SWOT and development of a longer –term advocacy plans.  At the same time, the results of focus group discussions with 148 IDP and conflict- affected women in 14 municipalities suggested that there were significant differences in women’s activism between IDP settlements and conflict-affected villages.  The level of women’s activism was found to be higher in locations where IDPs had been better integrated and lower in isolated IDPs’ settlements. Women-leaders of the networks reported that they had become more proactive and confident in advocating for the needs at the local administration. However, overall, women, especially those living in IDP settlements, remained rather passive and expected that active woman- leaders or CSOs would help solve their problems (see Figure 13). Despite of the common agreement that local municipalities increased their cooperation and IDP and conflict- affected women under this project, women felt that municipalities had stronger accountability to the civil society than to their constituents.

Therefore, organizing networking meetings of women from 17 municipalities was highly evaluated by the women interviewed by the evaluation team. Sharing experience and success stories made women more confident in their ability to promote positive changes in their communities. Majority of women in focus groups shared that support to networking was important to continue including also sharing experience in strategies to address security threats since women shared cased that some women had to step out of networks fearing retaliation for their participation in advocacy and involvement with NGOs.

Figure 13 Participation of women in advocacy initiatives (based of the survey of 78 women-leaders)

In connection with the previous finding related to lack of activities on peace and security in local gender equality plans, the evaluation found that more capacity development would have been necessary at the local level to recognize the complexity and interdependence of human security threats whether imposed by conflicts, lack of educational and employment opportunities, low access to livelihood and resources or negative impact of climate change and include these issues into advocacy for sustainable solutions that would address a variety of threats and contribute to resilience of communities. For instance, women’s groups in mountainous municipality of Mestia shared with the evaluators successful cases of improving access to essential for population services such as ATM and payment automats, which was most appreciated by retired, elderly people. Systematic removal of garbage was another example of a successful initiative that promoted access to services and, at the same time, ecological resilience of communities.

Finding 9: Achievement of the project Outputs led to anticipated changes under the Outcomes such as increased gender sensitivity of formal peace processes and participation of women’s CSOs and IDP and conflict-affected women in shaping peace and security processes. In terms of achievement of longer-term changes, some positive tendences should be acknowledged in relation to increased participation of women in leadership roles in security institutions and some line ministries. As for the impact on IDP and conflict-affected women, it would be impossible to measure the impact from the project due its limited scope of interventions to target multidimensional issues of security and, hence, self-reliance and resilience of these communities.

The project was highly effective in the achievement of targets set in the Result and Resources Framework (see Annex 2). According to the Theory of Change, increase in accountability of government, especially key security sector partners, to Women, Peace and Security (Outcome 2) should enhance participation of women in peace and security processes at national and local level.  As Figure 14 shows, support that the project provided to implementation of NAP 1325 (Indicator 2.1) resulted in greater gender mainstreaming into formal peace processes (Indicator 1.2) and institutional policies and practices (Indicator 2.2. and 1.4.).

Figure 14 Achievement of key targets at the Outcome level

Enhanced gender-sensitivity of institutional practices due to implementation of gender policies at six security institutions and other line Ministries (such as MFA and OSMRCE) resulted in achieved of targets related to engagement of state institutions with CSOs and women at the grassroots level on shaping peace and security processes. Under the project, UN Women organized a meeting - “Geneva International Discussions and Women, Peace and Security Agenda” for state institutions with participation of civil society organizations (CSOs). At the same time, commitment of responsible institutions to sustain new participation formats such as annual Open Days was increased (for instance, of the Ministry of Foreign Affairs). One of unexpected results that went beyond the project targets was the establishment of Women’s Advisory Board at the State Minister of Reconciliation and its institutionalization, which should ensure in the future greater cooperation with civil society that is most needed in the next phase of the project to ensure that needs and priorities of IDP and conflict-affected women are fully integrated into policymaking and implementation processes at the State Minister’s Office.

Participation of women from most vulnerable groups in the GID improved during the timeline of the project (see Figure 15), which was also due mainstreaming of WPS into the GID institutional set up i.e., development of gender equality strategy and establishment of a women’s advisory board to the UN Co-Chairs. According to the project data for 2025, the target of 30 percent was achieved, also in terms of inclusion. As for participation of women in the IPRM, it was 30 percent for Georgian participants , Abkhaz participants - 30 percent and Tskhinvali region/South Ossetian participants - 30 percent, which shows improvement from the previous years (Figure 16).

Figure 15 Participation of women in the GID (Outcome level target of 30 percent)

Figure 16 Participation of women in the GID (Outcome level target of 30 percent)

Despite the progress made at the level of Outcomes, achievement of longer-term changes or impact would be impossible to assess in the scope of this evaluation. The project impact was defined as full implementation of NAP 1325. So far, it remains the solely document that addresses multidimensional issues of WPS including security, health, education, economic empowerment and other aspects most pertinent to IDP and conflict-affected women youth. While the project was effective in supporting the Government in its implementation (50 percent), its scope does not allow for a comprehensive assessment of impact that it might have had on resilience of IDP and conflict-affected women and youth, which is seen as an ultimate, longer-term impact of interventions targeting displacement and post-conflict recovery. On the positive note, the project made significant efforts to increase participation and capacities of women to make meaningful contribution to security and resilience of affected populations, among them, women and youth. Also, some evidence suggests that participation of women in leadership positions is likely to increase in future in some security sector institutions (see Figure 17).

Figure 17 Women’s representation in the security sector

Finding 10: The project management was effective and having a country-based project team at UK Embassy added to the agility of the project in responding to risks raised by political and security challenges.  Monitoring results (milestones) in the Result Matrix was systematic and all indicators included baseline and targets. Reporting was done, mainly, on the level of activities rather than referring to the Theory of Change to discuss the impact of activities on achievement of Outputs and achievement of Outputs on Outcomes and validity of the assumptions. Creating a database on beneficiaries of the project (ZOHO) was meant to add to better disaggregation of data but completing of the database started late in 2024.

The management of the project was highly evaluated by partners and beneficiaries of the project. According to the UN Women project staff, having a dedicated country-based project team at UK Embassy was beneficial to ensure that the project remained on track towards achievement of targets. According to the representation of CSOs- partners, coordination within the Coalition of CSOs was satisfactory, although lacked internal learning of effectiveness of approaches implemented by partners in their municipalities. It was evident from the review of the partners’ documentation, all of them implemented a variety of monitoring activities and learning activities with their beneficiaries, however, the results of these activities were not reflected in their reports.  The latter, according to the partners, might be explained by the format of the report required by the donors, which did not provide space for the analysis of results.

In this connection, the UN Women’s reports to a donor contained rich information on achievement of targets and reasons for deviations, as well as risk analysis and mitigation measures. While some analysis of factors and challenges having positive or negative impact on achievement of targets was found in reports to donors and reflected in lessons learned, the project management would have benefited from the internal learning exercise which would have been most relevant in the challenging context of the project.  The evaluation identified only one report prepared by DCAF that assessed the extent of achievement of gender transformative results (change in mindset) which was conducted with participation of beneficiaries from the Ministry of Defense.

Disaggregation of data was mainly limited to sex. With transfers of the partners’ databases to ZOHO, the project had better opportunities to use data that was disaggregated by age, location, IDP or ABL status. Unfortunately, transfer to the ZOHO platform started close to the end of the project, therefore, the project was not able to benefit from analysis of disaggregated data. The evaluation team collected the data meant for the ZOHO from the civil society partners and findings from the data analysis are presentation in the section Inclusion.

## Efficiency

Finding 11. Allocation of the budget was relevant in terms of achievement of the objectives in increasing women’s participation in decision making on peacebuilding and security issues and implementation of the 2022-2024. Out of the total programmatic budget of 1205016.07 GPB, 32 percent can be traced to the WPS Participation Pillar.  The close alignment of the design to NAP 1325 led to a greater emphasis on building capacities of duty bearers from the Government and six security state institutions than of CSOs and rights holders.

Allocation of the budget was found relevant to the achviement of the project objectives. It is noteworthy that 32 percent of the project of the total programmatic budget 1205016.07 GPB was spent on the activities promoting participation of women in decision making related to conflict resolution, peacebuilding and security.   The project design was closely aligned with NAP 1325 and its implementation, which was defined as the overall goal of the project. In this connection, prioritization of building capacities of duty bearers from the Government and state security institutions to mainstream WPS to enhance gender-responsiveness of institutional structures and promote gender equity was evident. For instance, 41 percent of the programmatic budget was allocated under Output 2.2: Key security sector partners have enhanced capacities to mainstream gender into their policies, procedures and operations. As Figure 18 presents, more than 50 percent of the budget was allocated for capacity building interventions at the duty bearers’ institutions as compared with 17 percent allocated for capacity building of CSOs including support to WPS networking and 7 percent for capacity building of IDPs and conflict - affected women.

In relation to the latest, the evaluation team noted that UN Women and a donor had been considerate of cost-effectiveness of peace processes that depend on capacities of actors, among them peace ambassadors and activists at the grassroots level, and they prioritized empowerment of IDP and conflict- affected women and CSOs to enhance their participation in WPS. For instance, during the second phase of the project, a small grant component was added to support women’s initiatives in conflict-affected communities and IDP settlements.

Figure 18 Distribution of the budget (percentage) by Output and the target group (GBP)

Finding 12. Implementation of the project budget was effective despite the challenges related to adoption of Law on Foreign Influence and political unrest after the 2004 elections. Quality of expertise attracted by UN Women and commitment of the donor to its own strategies priorities under UK NAP 1325 added to the efficiency of the project and sustainability of the project results such as participation of women in peace formats and capacities of security sector institutions to implement NAP 1325.

With total duration of 51 months, the project was implemented in two phases. The first phase of the project was implemented from November 2020 until March 2024, then, due to the agreement between UN Women and the donor, the project received a 12-month extension. Following the extension of the project, the budget implementation increased only for Outputs 2.2 which contained such resources- intensive activities like mainstreaming of WPS into security sector institutions (in partnership with DCAF) to improve mechanisms to prevent and address discrimination and sexual harassment in the workplace.

As for Outputs 1.1 and 1.2., the project continued supporting a network of IDP and conflict-affected women and participation of women in the GID and IPRM and in annual Open Days on Women, Peace and Security – information-sharing and advocacy meetings between conflict-affected and IDP women and their organizations and high-level UN system representatives. The evaluation finds that the commitment of the donor (UK Government) to increased participation of women in peacebuilding formats during the second phase of the project was most valuable to prevent stagnation of the women’s engagement due to erosion of the cooperation between the Government and CSOs and, consequently, added to sustainability of IDP and conflict- affected women’s networks.  On a minor side, women-beneficiaries of the project interviewed during the evaluation mission suggested that a 12- module training might had been too intensive for the early phase of the project. Despite a few initiatives implemented by the CSO partners, the project could not provide for many opportunities for women to keep their knowledge and skills active due to its scope i.e., implement own initiatives in the areas of training, ensure transfer of skills to other women, engage with the content through any kind of thematic groups within the Network of Women and Youth Peace Ambassadors.

The project partners and beneficiaries appreciated commitment and support from 3 members UN Women project staff (WPS Project Coordinator, Project Analyst and Project Assistant) who were closely involved into most of activities and ensured effective monitoring of the project.  While the number of staff may be regarded as insufficient for a complex project with 33 activities, UN Women was able to attract high-level expertise from local CSOs, international NGOs and think tanks to ensure that capacity building activities were of relevance and good quality.

As may be seen from Figure 20, the project had a slow start, mainly, due to time taken  to define contractual agreements with partners and service providers (November 2020 - March 2021). Some differences between planned and actual costs are explained by delays in reporting by partners and service providers; for instance, by the end of the project there was USD 85,305.96 difference in between budgeted and actual costs due to the unliquidated advances.

Figure 19 Implementation of the budget by Output and Year in USD

|  | Nov 2020-March 2021 |  | April 2021-March 2022 |  | April 2022- March 2023 |  | April 2023-March 2024 |  | April 2024-March 2025 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual |
| 1.1 |  |  | $ 74,404.50 | $ 68,443.08 | $ 244,758.42 | $ 185,008.83 | $ 303,645.03 | $ 307,423.1 | $ 146,769.9 | $ 135,502.08 |
| 1.2 | $ 539.75 | $ 539.75 | $ 17,182.36 | $ 17,849.88 | $ 38,290.78 | $ 3,5974.86 | $ 42,595.54 | $ 31,973.35 | $ 10,091.32 | $ 10,091.32 |
| 2.1 |  |  | $ 48,936.89 | $ 43,561.88 | $ 36,791.33 | $ 41,125.18 | $ 34,412.30 | $ 34,032.02 | $ 43,269.54 | $ 28,699.22 |
| 2.2 |  |  | $ 45,070.38 | $ 41,309.49 | $ 298,199.38 | $ 242,069.99 | $ 173,273.29 | $ 163,740.1 | $ 178,096.3 | $ 118,628.52 |
| Total |  | $ 539.75 | $ 185,594.13 | $ 171,164.33 | $ 618,039.91 | $ 504,178.86 | $ 553,926.1 | $ 537,168.50 | $ 378,227.1 | $ 292,921.14 |
| % |  | 100% |  | 92% |  | 82% |  | 82% |  | 78% |

## Sustainability

Finding 13.  Support to implementation of NAP 1325 had its objective of increased ownership of WPS by the Government and at the level of responsible line ministries and agencies. Institutional gender -responsive structures and processes developed with support of the project are likely to sustain while changing gender roles and norms will require additional investment. The backlash against civil society presents a threat to sustainable engagement of state institutions with IDP and conflict- affected women at the grassroots level and may undermine their critical role in promoting peace and security in their communities.

While institutional capacity within the security sector institutions such as gender equality policies, sexual harassment prevention mechanisms, and training programmes, among others, is likely to be sustained, it remains crucial to ensure support to institutionalization of these practices to promote transformative results such as changes in gender norms and roles including increased representation of women in senior leadership and decision-making positions.

The exit strategy of the project integrated measures to ensure sustainability of several components of the project through ongoing and new UN Women programmes and project. For instance, Strengthening Women’s Leadership within the Defence Sector project supported by UK Government will ensure sustainability and upscale of the results such as Women’s Masterclass Programme, training on sexual harassment and other. Sustainability of capacities built at the level of CSOs remains within the organizations and by mainstreaming of piloted by the project approaches into other interventions e.g. a human security approach, results of research and learning through regional networks. However, continuation of support to civil society, also by creating for them opportunities for engagement with state institutions and local governance is essential. The backlash against civil society and against the progress that Georgia made to promote gender equality and women’s empowerment, presents a serious impediment to sustainability of new peacebuilding platforms and formats is the main concern.

At the time of writing this report, several consultative platforms with involvement of women’s CSOs became sustainable such as at the Office of the State Minister of Reconciliation and at the Ministry of Foreign Affairs. In addition, commitment of the donor (UK Government) to promote full implementation of the WPS agenda  in Georgia creates assurance that remaining gaps and challenges related to accountability of the state institutions and increased women’s participation in decision making on peace and security issues, are likely to be addressed in the following projects.

Finding 14. UN Women and their partners invested significant resources into development of peacebuilding networking opportunities for women and youth. The Network of Women and Youth Peace Ambassadors presents a result of long-term advocacy efforts to consolidate scattered peace initiatives implemented by CSOs, women’s leaders and advocates, experts and scholars and to increase their visibility and impact on peace and security on the national and regional level. Nevertheless, the role of the network in acceleration of the WPS agenda was not fully defined during the project, thus, affecting its sustainable engagement with WPS actors from different sectors and with most vulnerable women and youth.

The Network of Women and Youth Peace Ambassadors has been developed by 40 founding members, and, currently, it includes about 240 members. Sustainability of keeping of a such an extensive network depends on the strong commitment of the founding members, as well as active engagement in formal peacebuilding discussions and in grassroots level peacebuilding, conflict resolution and prevention initiatives. As stated in the Position of Women Peace Activists and Women-led Organizations in Europe and Central Asia: Insights for the 2025 Peacebuilding Architecture Review (4 December 2024) , women’s CSOs and activities bring critical grassroots knowledge and advocacy to international peace processes.

While the Network is seen as an asset in terms of providing timely update and information to Geneva International Discussions, IPRM, WPS Thematic Force at UN, it requires constant learning and engagement to avoid erosion of developed capacities and commitment. To that end, its role and linkages to formal peacebuilding formats, as well as informal WPS networks developed at the national and regional level, is still unclear. As Figure 21 presents, the project made significant efforts to increase involvement of CSOs in WPS platforms, however, their involvement with formal peace processes and with the WPS Focal Point, thematic task forces and other multi-actor platforms was not explicitly addressed in the exit strategy.

Figure 20 Mapping of women-led CSOs engagement in networks and linkages to formal peacebuilding processes

In addition, it is not clear how WPS capacities developed at 25 CSOs, 10 think tanks and 14 universities may be used to consolidate efforts of the project to increase involvement of women in decision making on peace, conflict prevention and security.  It is most likely that UN Women will continue its current approach by advocating inclusion of women from CSOs and at the grassroots level into thematic working groups and advisory boards, which is relevant in the current political situation. However, the consolidating role that the Network of Women and Youth Peace Ambassadors may play in strengthening of women’s influence on decision making in different Pillars and thematic areas of WPS and YPS requires better organization and utilization of existing expertise (and attracting new expertise) to provide valuable contribution to a variety of thematic and advisory groups at the national and regional level.

## Conflict sensitivity

Finding 15: The project raised capacities of civil society organizations in a gender-responsive conflict analysis and integrated the measures that guaranteed confidentiality and non-retaliation of women, particular from Abkhazia and South Ossetia, for their engagement and contributions to raising awareness of WPS and advocacy for equal and meaningful participation.

Figure 21 7+1 Human Security Domains

Economic Security

Health Security

Environmental Security

Personal Security

Community Security

Political Security

+ Gender Security

As acknowledged in the project document, conflict-affected populations living near the Abkhazian and South Ossetian ABLs, as well as IDPs living in various formal and informal settlements across the country continued to face various forms of human insecurity including socio-economic, environmental, political and conflict-related threats. In addition, increased global and geopolitical tensions have further exacerbated the already precarious human security situation affecting these communities. Integration of a human security approach under the project into assessment of needs of IDPs and conflict affected communities was meant to recognize the complexity and interconnected nature of the challenges and advocate for a more coherent and collaborative approach to their solution.

In cooperation with the National Women’s League, a training module was added to a 12-module programme on the topic of human security. A total of 6 trainings for 150 women- leaders were conducted in different regions on the following issues: situation management during natural and man-made disasters and conflicts, issues of medical aid and primary diagnosis, through both theoretical and practical examples. The project produced a manual  to support civil society organizations in Georgia to assess, monitor, analyze and report on human security of the conflict-affected population in a systematic and joint manner. It outlines a step-by-step approach to setting up and implementing a civil society-led human security monitoring programme or initiative. Built upon a gender and conflict-sensitive participatory approach, reporting on human security is intended to enhance grassroots advocacy and outreach to improve the situation of the conflict-affected population in Georgia.

Initially, the manual was developed for Public Defender’s Office and CSOs. After a two-day training, the partner CSOs further adopted the Monitoring Tools to adjust it to the local context and delivered trainings for the members of the Network of Women and Youth Peace Ambassadors. The initiative is found by the evaluation as most relevant considering the need for sustainable solutions to contribute to resilience of IDPs and conflict- affected communities. Moreover, women’s leadership in building safe and resilient communities may be affected by the current backslide of the current political discourse on gender equality and women’s rights presenting a political security threat to women-led CSOs and women’s networks. It is noteworthy that capacity development in human security monitoring was followed by its practical application: the Network members collected monitoring data, which was summarized in the brief report by the CSO coalition for further advocacy efforts. Integrating gender security with human security should help mitigate the gendered impacts of current threats and prevent the occurrence of future challenges.

So far, UN Women with partners implemented a variety of measures such as ensuring free legal consultations to CSOs and women whose security was threatened due to participation in the anti-government protests; personal security measures were consistently followed for women- participants of face-to-face diplomacy and peacebuilding formats, especially for women and youth from Abkhazia and South Ossetia.  Still, there is a need to strengthen capacities of CSOs and women’s network in implementation of coherent measures among partners to ensure sustainability of advocacy and safe participation of women and women-led CSOs in peace and security processes. The focus on participation of women was not pursued in balance with interventions on prevention. While it is most appreciated that UN Women persistently advocated for development of sexual harassment and violence prevention mechanisms at duty bearers’ institutions, these efforts should have been complemented by development of early warning systems that would provide for rapid assessment of security threats at the grassroots level.

Due to the project support, Institute for War and Peace Reporting (IWPR) continued development of the women4peace.net platform that united women -peacebuilders from the region. The evaluation team gives credit to the IWPR team in bringing attention to conflict-related sexual violence by sharing voices of women from Ukraine. Raising awareness on criticality of zero impunity for sexual and gender-based violence and its prevention should have been more emphasized in localization and advocacy interventions given that some of the project partners like Women’s Fund Sukhumi have strong programmes involving IDP women- survivors of violence in collaboration with local municipalities and state counterparts.

## Inclusion

Finding 16: IDP and conflict-affected women living in 17 municipalities constituted the largest group of beneficiaries under this project. This group remains most vulnerable due to their exposure to multiply challenges including lack of sustainable housing solutions, ownership of land, access to essential services, education and economic opportunities and exposure to security threats such as violence against women, lack of medical services, food security and other. Nevertheless, networks of women IDPs and conflict-affected  women could have benefited from more systematic strategies that promote diversity and intergenerational learning.

Despite the fact that partners from CSOs encouraged participation of youth, women- survivors of violence, women with disabilities, single mothers and other vulnerable women to participate in networks’ meetings and local initiatives, the project did not employ systematically inclusion strategies (LNOB) such as by age, socio-economic status, disability or other due to the extent of vulnerability of IDP and conflict -affected women in general. Inclusion of younger women into the network was much appreciated by members of women’s networks who shared with the evaluation team that mixed women’s and youth groups were more creative in terms of generation of ideas and solutions. In addition, having mixed group of women of different age, background, education level, sector (private sector, education, medical etc.) helped better prioritize problems and consolidate communities around their solution.

Figure 22 Participation of women based on the status and age (ZOHO database, total of 256 women)

It is commendable that some partners collected better disaggregated data than it was necessary for the ZOHO platform owned by UN Women (Figure 23). Additional information was collected on employment status, education level, and other social factors that may contribute to vulnerability such as single mother households; however, it was not approached in a coherent matter by all partners to allow for conclusions which subgroups of women remained excluded. For example, migration (also labour migration) was mentioned as one of the factors that contributed to insecurity of women and their families, especially children. The evaluation found that the inclusion of more systematically disaggregated data by civil society organizations had the potential to enhance on-the-ground perspectives, complement needs assessments, and strengthen advocacy for policies and measures that reflect the lived realities of affected women.

# Lessons learned

Lesson learned 1. Striking differences in living conditions and access to necessary services between IDP settlements and conflict- affected communities require adaptive approaches when planning interventions to address specific needs of women and communities, also in relation to the level of security and conflict patterns. In this regard, mainstreaming of a human security approach that is people- centered, context-based and participatory contributed to a greater relevance of responses and visibility of women’s contribution to safety and security of IDP and conflict-affected communities.

Lesson learned 2. Mainstreaming a conflict-sensitive approach when planning peacebuilding interventions at the grassroots level is essential to be able to identify the potential security threats for women’s participation and rapidly adapt mitigation measures to reduce these risks to a minimum level without sacrificing benefits produced by the WPS project.

Lesson learned 3. Sustainability of peacebuilding networks largely depends on creating linkages between women’s networks at the national level and regional/global level and on engaging women with local municipalities, formal peace infrastructures, thematic working groups and advisory boards at the state institutions and agencies working in the areas of WPS and YPS.

# Conclusions

Conclusion 1: By supporting full implementation of NAP 1325, the project targeted increased participation of women and youth in formal and informal peace processes including through empowering of IDP and conflict- affected women at the grassroot level to participate in decision making related to peace and security. The overarching project strategy of mainstreaming of the WPS agenda at the institutional and grassroots level attracted an impressive number of stakeholders from the Government, civil society, academia, research institutions and specialized agencies NATO, EUMM and others. The project design was based on the sound Theory of Change that incorporated key gaps and challenges to be addressed to enhance meaningful participation of women in peacebuilding. As most relevant, the project addressed low gender-responsiveness of institutional structures and processes at the security sector institutions, low gender responsiveness of formal peacebuilding processes, lack of secure spaces for women’s participation, low accountability of state institutions and local governance to women who are most affected by conflicts as IDP and conflict affected women living in IDP settlements and in the villages close the ABL.

Conclusion 2: Considering the shrinking space for civil society in Georgia and in the region and backlash against gender quality and women’s rights, the project provided a variety of opportunities for a women’s CSOs and IDP and conflict -affected women for networking and a dialogue with state institutions and local which proved to be an effective strategy. It also made commendable efforts in consolidation of women’s peacebuilding efforts by establishing the Network of Women and Youth Peace Ambassadors and engaging women-led CSOs and women at the grassroot levels in global and regional networks. While these opportunities added to overall capacity of women to meaningfully participate in peace and security processes at the national and local level, results from increased consolidation and better coherence among CSOs, women- activists and UN agencies in promoting of the WPS agenda are still to be seen. In this connection, the efforts of UN Women to support women’s networking through other WPS projects sustainability and promote their interaction with each other, with state institutions and formal peacebuilding processes are noteworthy.

Conclusion 3: The project raised visibility of the WPS agenda and the role of women in peace, security and conflict prevention and integration of WPS into higher education curriculum and research discourse added to advocacy for the role of civil society, women and youth for building sustainable peace and security in Georgia and in the ECAS region. Despite of the strong evidence of increased advocacy capacities of women’s CSOs and IDP and conflict affected women, better coherence between CSOs partners and members of the Network of Women and Youth Peace Ambassadors is needed to amplify the impact from a more consolidated women’s peacebuilding movement. The efforts of UN Women and partners from CSOs to include representatives of women-led CSOs and women-leaders in a greater number of advisory boards or thematic work groups should have been complemented by stronger thematic focus within the Network such as establishment of thematic groups e.g., gender-based violence, women’s political participation, cybersecurity and disinformation etc.

Conclusion 4: Better coherence with other projects, for example on local governance, could have added to the process of mainstreaming of the NAP 1325 into local gender equality plans. Establishment of the WPS Thematic Group under the UN GTG is a commendable achievement which allowed to organize several high-level meetings and regional events to raise visibility of WPS and advocate on recognition of a role of women in peace and security processes. Nevertheless, for future UN Women WPS interventions, fostering better synergies between UN and non-UN actors and their projects would be essential in the areas of local governance, security and resilience of communities, economic empowerment of women. While NAP 1325 targets include participation of state institutions and civil society, the role of the private sector in accelerating the WPS agenda in Georgia should have been explored in relation to economic empowerment of IDP and conflict-affected women and building resilience of communities.

Conclusion 5: The project was effective in achieving targets at the Output and Outcome level. The impact of the project may be defined as enhanced gender-sensitivity of peace formats and institutional practices at the security sector institutions. This resulted in increased participation of women in GID and IPRM formats. Also, participation of women in leadership positions is likely to increase in future in some security sector institutions i.e., Ministry of Defense and Ministry of Foreign Affairs. However, achievement of longer-term changes or impact on beneficiaries - IDP and conflict-affected women would be impossible to assess in the scope of this evaluation, mainly, due to the limited scope of the project to address multidimensional issues of human security and lack of baseline to measure changes in resilience and self-reliance of women in conflict affected communities. Nevertheless, the project made a significant contribution to capacities of CSOs and women to positively affect security and resilience of communities and to monitor human security at the grassroots level.  The project efforts to integrate a context- based human security approach by developing social profiles of communities provide an opportunity in future to measure impact of WPS projects on resilience of IDP and conflict- affected communities, among them women and youth.

Conclusion 6: The project prioritized to some extent engagement of youth and CSOs led by young women who were able to raise their capacities and participate in a variety of forums but coherence and complementarity between the WPS and YPS agendas should have been more systematically approached by ensuring more diversity and inclusion in women’s networks and initiative groups. In this regard, continuation of the donor support to the project is seen as essential by the evaluation team for scaling up the results through better consolidation of women’s groups at the grassroots level and stronger synergies between the WPS and YPS agenda and with projects implemented by other UN agencies that focus on youth and security.

Conclusion 7: The project made great strides towards inclusion of most vulnerable groups of women – IDPs and women living at the ABL- into peacebuilding processes. The challenges that IDP and conflict- affected women face are numerous and, often, interlinked, as was confirmed by several assessment studies committed under the project. Inclusion of IDPs needs into the Human Rights Action Plan provides opportunities for UN Women to advocate for a more coherent and comprehensive approach to their solution at the national level. The credit should be given to UN Women and partners in collecting data and reporting on needs and challenged faced by IDPs and conflict -affected communities living at the ABL. Moreover, the localization of NAP 1325 and implementation of advocacy and other initiatives by local women’s networks demonstrated the need for a people-centered and context-based approach to planning these interventions. Mainstreaming conflict-based analysis and a human security methodology into work on CSOs including the project partners added to capacities of CSOs to provide policy makers, national monitoring instruments (PDO), research institutions and think tanks with information and data that reflect real situation at the grassroot level for diverse populations.

Conclusion 8: Changes in the political situation in Georgia and increased geo-political tensions created challenges in cooperation of UN Women with the Government and between the Government and the civil society. The dramatic backlash against civil society and women’s rights demanded from the project staff and partners more agility in terms of revision of priorities and the need to address new security challenges. While the project made certain adjustments to the strategy, for instance, by focusing more on empowerment of IDP and conflict -affected women during the second phase of the project, it would have been valuable to enhance learning from the project experience by conducting an internal learning exercise to identify a broader scope of mitigation measures and reflect on their effectiveness. Other than that, introduction and piloting of tools that provide rapid assessment in the context and its conflict -sensitivity for IDP and conflict-affected women e.g., early warning systems etc. would have been beneficial considering that CSOs had opportunities under the project to adapt and pilot human security monitoring approaches.

# Recommendations

This section presents findings-based recommendations structured under three overarching strategic recommendations for UN Women Georgia, with 14 concrete steps developed from consultations with partners, stakeholders, and beneficiaries. Each step is directly linked to evaluation findings, conclusions, and lessons learned.

Recommendation 1: UN Women should develop a coherent strategy to advance transformative gender results in peace and security by aligning project impact with long-term change, strengthening partnerships, integrating cross-cutting themes, and enhancing coordination with women-led peacebuilding actors

Step 1: Revise the definition of the project’s impact to reflect long-term transformative change (e.g., increased resilience of IDP and conflict-affected communities), and update the Results and Resources Framework to incorporate realistic assumptions and risks (Related to Findings 3, 9; Conclusion 8);

Step 2: Advocate for stronger engagement of state institutions in the fifth NAP 1325, including activities requiring collaboration with women’s networks representing IDP and conflict-affected women (Related to Findings 6, 12, 13; Conclusion 1);

Step 3: Promote synergies between WPS and other UN Women thematic areas (e.g., women’s political participation, GBV/VAWG, environmental resilience), and consider mainstreaming prevention of violence and environmental resilience as cross-cutting issues in project design (Related to Finding 4);

Step 4: Define the role of the private sector in the WPS agenda and integrate activities involving WEPs-affiliated companies to support IDP and conflict-affected women (Related to Findings 4, 5; Conclusion 4);

Step 5: Continue developing the WPS database of women - peacebuilders and organizations; conduct a mapping exercise of women-led organizations to identify synergies, strengthen coordination, and reinforce the Network of Women and Youth Ambassadors (Related to Finding 14; Conclusion 6);

Recommendation 2: To promote women’s participation, UN Women is encouraged to strengthen bottom-up, gender-responsive approaches by expanding social mobilization in conflict-affected areas, empowering grassroots networks, clarifying the role of the Women and Youth Ambassadors Network, and facilitating access to funding for local peacebuilding initiatives

Step 6: Disseminate the social mobilization methodology in IDP and conflict-affected communities and establish linkages with women’s self-help groups and advisory structures developed under other UN Women programmes (Related to Finding 8);

Step 7: Conduct an envisioning exercise with the Network of Women and Youth Ambassadors to define its role; establish thematic sub-groups and support participation in national, regional, and international WPS forums (Related to Finding 14; Conclusion 2, 3);

Step 8: Build the capacity of grassroots women’s networks to localize NAP 1325; identify strategic partnerships (e.g., with NALAG) to promote dialogue between local authorities and conflict-affected women, and support monitoring of local gender equality plans (Related to Finding 7; Conclusion 4);

Step 9: Collaborate with donors and partners to design and implement grant mechanisms (e.g., calls for proposals) that enable women’s and youth groups to carry out peacebuilding and confidence-building measures in ABL communities (Related to Finding 5);

Recommendation 3: It is recommended that UN Women enhance its evidence-based decision-making on WPS by clarifying what constitutes transformative change, developing relevant qualitative indicators, standardizing data collection among partners, promoting the use of technology-driven monitoring tools, and institutionalizing adaptive learning processes

Step 10: Clearly define what constitutes a transformative effect in women's participation in peace processes and introduce qualitative indicators that reflect empowerment at the grassroots level (Related to Finding 3);

Step 11: Ensure consistency in the collection of disaggregated data across implementing partners, expanding data points to include employment status, education level, disability, and other factors impacting human security (Related to Finding 10);

Step 12: Promote participatory human security monitoring tools among women's and youth groups to assess impact on peace and security and explore technology-based approaches for rapid data collection (Related to Finding 15; Lesson Learned 1; Conclusion 7);

Step 13: Conduct a baseline study on human security (e.g., using a Human Security Index) in IDP settlements and conflict-affected areas to inform programming (Related to Finding 9; Conclusion 5);

Step 14: Implement an internal learning exercise at the midterm of the next project phase to assess relevance, coherence, effectiveness, sustainability, and conflict sensitivity, and to generate lessons linked to evaluation criteria (Related to Finding 10).

# Annexes

### Annex 1 List of interlocutors

| Name | Title | Institution | Contact |
| --- | --- | --- | --- |
| - Maka Peradze | Deputy Head of the Human Rights Secretariat | Administration of the Government of Georgia | mperadze@gov.ge |
| - Irina Yegorova | Political Affairs Officer | Office of the UN Representative to the Geneva International Discussions (UNRGID) | yegorova@un.org |
| - Tamar Sabedashvili | Deputy Country Representative | UN Women Georgia | tamar.sabedashvili@unwomen.org |
| - Kaori Ishikava | Country Representative | UN Women Georgia | kaori.ishikawa@unwomen.org |
| - Tamar Lobjanidze | Project Coordinator | UN Women Georgia | tamar.lobjanidze@unwomen.org |
| - Medea Gugeshashvili | Project Analyst | UN Women Georgia | medea.gugeshashvili@unwomen.org |
| - Zurab Khrikadze | Project Officer | UK Integrated Security Fund | zurab.khrikadze@fcdo.gov.uk |
| - Ana Nioradze | Defense Project Officer | UK Integrated Security Fund | Ana.Nioradze@fcdo.gov.uk |
| - Chris Reilly | Head of Programmes | British Embassy Tbilisi | Chris.Reilly1@fcdo.gov.uk |
| - Ketevan Murusidze | Monitoring and Evaluation (M&E) Specialist for the ISF Eastern Neighbourhood Programme | ISF | Ketevan.Murusidze@fcdo.gov.uk |
| - Sophio Rusetski | Acting Head of Gender Department | The Office of the Public Defender of Georgia | srusetski@ombudsman.ge |
| - Nargis Azizova | WPS Regional Advisor ECA RO | UN Women ECA | nargis.azizova@unwomen.org |
| - Tamar Kochoradze | Head of Department for Policy Analysis, Planning and International Relations | Office of the State Minister for Reconciliation and Civic Equality | t.kochoradze@smr.gov.ge |
| - Ekaterine Komakhidze | Head of Human Resources Policy Division, Human Resources Department | Ministry of Defense | ekomakhidze@mod.gov.ge |
| - Ekaterine Kharashvili | Lieutenant Colonel Deputy Head of Human Resources Policy Division of Human Resource | Ministry of Defense | ekharashvili@mod.gov.ge |
| - Christine Friis Laustsen | Gender Advisor | European Union Monitoring Mission in Georgia | Christine.LAUSTSEN@eumm.eu |
| - Elene Tsatsua | Professor | Ivane Javakhishvili Tbilisi State University | Helenatsatsua@gmail.com |
| - Solene Barbant | Programme Manager | DCAF | s.brabant@dcaf.ch |
| - Mari Mchedlishvili | Youth Peace Activist |  | marumchedlishvili@gmail.com |
| - Eleonora Tchania | Youth Peace Activist |  | eleonora.tchania@gmail.com |
| - Eliko Bendeliani | Youth Peace Activist |  | elikobendeliani@gmail.com |
| - Ana Nemsadze | Women, Peace and Security Direction Coordinator | Women's Information Center | nemsadzeanaa@gmail.com |
| - Julia Kharashvili | Director | Consent | julia.kharashvili@yahoo.com |
| - Marina Pochkhua | Deputy Chair | Consent | mpochkhua@gmail.com |
| - Alla Gamakharia | Chairperson | Fund “Sokhumi” | womansukhumi@gmail.com |
| - Meri Gelashvili | Co-founder | Fund “Sokhumi” | womenfund2003@gmail.com |

### Annex 2 Result and Resources Framework

| Annex A: Results Framework Project Title: Accelerating Implementation of the Women, Peace and Security Agenda in Georgia Duration: 51 months Project Development Goal/Impact: Full implementation of the Women, Peace and Security agenda Impact level indicators: - Global Women, Peace and Security Index Baseline: 95 out of 163; WPS index 0.777; ranked 46 of out 166 (2019/20) Target: Improvement of Georgia’s global ranking and/or overall score Source: Georgetown Institute for Women, Peace and Security (https://giwps.georgetown.edu/the-index/chapters/) - Number of IDP and conflict-affected people benefiting directly from improved socioeconomic conditions and improved human security Baseline: 0 Target: 33,000 Source: UN Women Progress Reports to the UK CSSF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| The project’s theory of change contributes to Outcome 5 of the UN Women Global Strategic Plan (2018-2021), and UN Women Georgia Strategic Note 2016-2020, Impact 4, that is formulated as follows: Women and girls contribute to and have greater influence in building sustainable peace and resilience and benefit equally from the prevention of conflict. As well as UN Women Georgia Strategic Note 2021-2025, Outcome 4: By 2025, conflict affected communities enjoy human rights, enhanced human security and resilience (UNSDCF Outcome 4). The action further and more specifically contributes to UN Women Georgia CO’s Annual Work Plans, Output 4.1: Governmental, public and civil society organizations possess the required capacities to implement WPSA-relevant policies and programmes (UNSDCF Output 4.3) and Output 4.2: Women are enabled and capacitated to take part in decision-making processes around the Women, Peace and Security Agenda (WPSA) (UNSDCF Output 4.3). UN Partnership for Sustainable Development (UNPSD) 2016-2020: - Focus area 1 on Democratic Governance, Outcome 1: By 2020 expectations of citizens of Georgia for voice, rule of law, public sector reforms, and accountability are met by stronger systems of democratic governance at all levels. - Focus area 5 on Human Security and Community Resilience, Outcome 7: By 2020 conflict affected communities enjoy better security and stronger resilience to conflict-induced consequences. UN Sustainable Development Cooperation Framework (UNSDCF) 2021-2025: - Outcome 4: By 2025, conflict affected communities enjoy human rights, enhanced human security and resilience. UK WPS NAP 2018-2022: - Strategic outcome 1 on Decision-making: An increase in women’s meaningful and representative participation and leadership in decision making processes, including conflict prevention and peacebuilding at community and national levels - Strategic outcome 5 on Security and Justice: Security and justice actors are increasingly accountable to women and girls, and responsive to their rights and needs UK WPS NAP 2023-2027: - Strategic Objective 1: Decision-making – increasing women’s meaningful participation, leadership and representation in decision-making processes - Strategic Objective 3: Humanitarian and crisis response – supporting the needs of women and girls in crises and ensuring they can participate and lead in responses - Strategic Objective 4: Security and justice – increasing the accountability of security actors, institutions and systems to women and girls and ensuring they are responsive to their rights and needs UK CSSF strategic focus areas: - Supporting diplomatic efforts to reduce outbreaks of violence and build space for dialogue including by maintaining international engagement on regional security issues and helping prepare for long-term political resolutions - Working with governments, local and international partners and civil society to support the implementation of reforms, strengthen state (and non-state) institutions (including security actors) and improve conditions for civil society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Outcome 1 Increase in women’s meaningful and representative participation in conflict prevention and peacebuilding at the community and national level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 1 assumptions/risks: - Project activities are not affected by any major crisis (economic, political, war and conflict, natural disaster) - Project partners and beneficiaries do not lack the interest or good will to participate in the project and work on the WPSA - Global health emergency: COVID-19 does not hinder project implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Outcome 1 Increase in women’s meaningful and representative participation in conflict prevention and peacebuilding at the community and national level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.1.: Proportion of women participants in Geneva International Discussions (GID) and Incident Prevention and Response Mechanism (IPRM) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: GID Georgian participants: 2020 – 17 per cent Abkhaz participants: 2020 – 0 per cent Tskhinvali region/South Ossetian participants: 2020 – 0 per cent Baseline: IPRM Georgian participants: 2020 – 20 per cent Abkhaz participants: 2020 – 0 per cent Tskhinvali region/South Ossetian participants: 2020 – 0 per cent |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (Project Year 1 - March 2022) |  |  |  | Milestone 2 (Project Year 2 – March 2023) |  |  |  |  |  | Milestone (Project Year 3 - March 2024) |  |  |  |  |  |  |  |  |  |  |  |  | Target (Project Year 4/end project March 2025) |  |  |  |  |
| Georgian participants:20 per cent Abkhaz participants:20 per cent Tskhinvali region/South Ossetian participants: 10 per cent |  |  |  | Georgian participants: 25 per cent Abkhaz participants: 25 per cent Tskhinvali region/South Ossetian participants:20 per cent |  |  |  |  |  | Georgian participants: 25 per cent Abkhaz participants: 25 per cent Tskhinvali region/South Ossetian participants: 25 per cent |  |  |  |  |  |  |  |  |  |  |  |  | Georgian participants: 30 per cent Abkhaz participants:30 per cent Tskhinvali region/South Ossetian participants: 30 per cent |  |  |  |  |
| Progress Achieved: |  |  |  | Progress Achieved: |  |  |  |  |  | Progress Achieved: |  |  |  |  |  |  |  |  |  |  |  |  | Progress Achieved: |  |  |  |  |
| Source: Ministry of Foreign Affairs of Georgia (for GID) and Office of the State Minister of Georgia for Reconciliation and Civic Equality (for IPRM); Data obtained by UN Women from the Women, Peace and Security Focal Points of the GID Co-Chairs’ teams. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.2.: Level of mainstreaming of the WPS agenda commitments into the GID process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2019 – Very low / gender blind |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (Project Year 1 - March 2022) |  |  |  | Milestone 2 (Project Year 2 – March 2023) |  |  |  |  |  | Milestone (Project Year 3 - March 2024) |  |  |  |  |  |  |  |  |  |  |  | Target (Project Year 4/end project March 2025) |  |  |  |  |  |
| Low / gender aware |  |  |  | Medium – gender sensitive |  |  |  |  |  | High – gender responsive |  |  |  |  |  |  |  |  |  |  |  | High – gender transformative |  |  |  |  |  |
| Progress Achieved: Low / gender aware In May 2019, GID Co-Chairs started to develop the Joint Strategy and Action Plan on WPS in the GID, which has been updated and finalized on 22 February 2021. |  |  |  | Progress Achieved: |  |  |  |  |  | Progress Achieved: |  |  |  |  |  |  |  |  |  |  |  | Progress Achieved: |  |  |  |  |  |
| Source: Annual Reports of the Secretary-General on WPS (S/PRST/2010/22); Studies by UN, EU, OSCE on gender mainstreaming in the GID and IPRM processes (DPPA);; Press Communiqués of the Co-Chairs of the GID; Press Communiqués of the IRPM. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.3: Existence of women’s consultative mechanisms on WPS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2020 - Consultation meetings prior to GID rounds between Co-Chairs and women’s groups - Information sharing meeting between Georgian participants of GID and women’s CSOs - Information sharing meeting between Georgian participants of GID and women’s CSOs, grassroots women |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (Project Year 1 - March 2022) |  |  |  | Milestone 2 (Project Year 2 – March 2023) |  |  |  |  |  | Milestone (Project Year 3 - March 2024) |  |  |  |  |  |  |  |  |  | Target (Project Year 4/end project March 2025) |  |  |  |  |  |  |  |
| - Consultation meetings prior to the GID rounds between the GID Co-Chairs and women’s groups - Information sharing meeting between Georgian participants of the GID and women’s CSOs - Information sharing meeting between Georgian participants of the GID and women’s CSOs, grassroots women - SMR WPS platform established - Technical proposal on Women’s Advisory Board (WAB) to the GID Co-Chais drafted |  |  |  | - Consultation meetings prior to the GID rounds between the Co-Chairs and women’s groups - Information sharing meeting between Georgian participants of the GID and women’s CSOs - Information sharing meeting between Georgian participants of the GID and women’s CSOs, grassroots women - SMR WPS platform established and functional - MFA WPS platform established - Advocacy and consultations on WAB establishment |  |  |  |  |  | - Consultation meetings prior to the GID rounds between the Co-Chairs and women’s groups - Information sharing meeting between Georgian participants of the GID and women’s CSOs - Information sharing meeting between Georgian participants of the GID and women’s CSOs, grassroots women - SMR WPS platform functional - MFA WPS platform functional - WAB established (at least informally) |  |  |  |  |  |  |  |  |  | - Consultation meetings prior to the GID rounds between the Co-Chairs and women’s groups - Information sharing meeting between Georgian participants of the GID and women’s CSOs - Information sharing meeting between Georgian participants of the GID and women’s CSOs, grassroots women - SMR WPS platform functional - MFA WPS platform functional - WAB established and functions formally |  |  |  |  |  |  |  |
| Progress Achieved: |  |  |  | Progress Achieved: |  |  |  |  |  | Progress Achieved: |  |  |  |  |  |  |  |  |  | Progress Achieved: |  |  |  |  |  |  |  |
| Source: Meeting notes from the information sharing and consultation mechanisms listed above; list of members and participants of the mechanisms listed above; Technical proposal on the establishment of the WAB. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.4.: Proportion of people-to-people diplomacy initiatives implemented by women’s CSOs and/or addressing women’s issues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2019 – 17 per cent (people-to-people initiatives supported by SMR / Peace Fund for Better Future (PFBF)) 2020 – 11 per cent |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (Project Year 1 - March 2022) |  |  |  | Milestone 2 (Project Year 2 – March 2023) |  |  |  |  |  | Milestone (Project Year 3 - March 2024) |  |  |  |  |  |  |  |  |  |  | Target (Project Year 4/end project March 2025) |  |  |  |  |  |  |
| SMR / PFBF - 30 per cent Other – at least 30 per cent |  |  |  | SMR / PFBF - 35 per cent Other – at least 30 per cent |  |  |  |  |  | SMR / PFBF – 37 per cent Other – at least 30 per cent |  |  |  |  |  |  |  |  |  |  | SMR / PFBF – 40 per ce nt Other – at least 30 per cent |  |  |  |  |  |  |
| Progress Achieved: |  |  |  | Progress Achieved: |  |  |  |  |  | Progress Achieved: |  |  |  |  |  |  |  |  |  |  | Progress Achieved: |  |  |  |  |  |  |
| Source: SMR annual report; PDO and CSO monitoring reports of WPS NAP; Monitoring tool of GTG Task Force on WPS initiatives by development partners. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 Increased capacity of women and girls (including internally displaced and conflict-affected) to meaningfully engage in conflict prevention and peacebuilding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 assumptions/risks - There is a certain minimum level of women’s participation in public life to build on - The government partners are open and receptive to the findings and recommendations generated by CSO and PDO monitoring of NAP 1325 implementation - Partners from civil society and academia are open and interested in incorporating WPS issues into their work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.1.a: Existence of organized functional network of IDP and conflcit-affected women influencing peace and development processes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2019 – No formal network of IDP and conflict affected women exists, they are consulted by other peace and development players on ad hoc and individual basis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) | Milestone 2 (March 2022) |  | Milestone 3 (September 2022) |  | Milestone 4 (March 2023) |  |  | Milestone 5 (September 2023) |  |  |  | Milestone 6 (March 2024) |  |  |  |  | Milestone 7 (September 2024) |  |  |  |  |  |  |  |  | Target (March 2025) |  |
| Yes - the informal network uniting 93 IDP and conflict-affected women created | Yes – the members of the informal network of IDP and conflict-affected women trained on WPS and on methodologies to conduct socio-economic needs’ assessment in their communities |  | Yes – the members of the informal network advocate to integrate recommendations identified through needs’ assessments: (a) in consultation and information sharing meetings on WPS listed under Indicator 1.3.; (b) in local planning and budgeting (including localized gender NAP that will also cover WPS NAP). |  | Yes – the IDP and conflict-affected women’s network formalized, and it advocates to integrate recommendations identified through needs’ assessments: (a) in consultation and information sharing meetings on WPS listed under Indicator 1.3.; (b) in local planning and budgeting (including localized gender NAP that will also cover WPS NAP). |  |  | Yes – formal network of IDP and conflict-affected women monitors implementation of the recommendations identified through needs’ assessments: (a) through consultation and information sharing meetings on WPS listed under Indicator 1.3.; (b) through local planning and budgeting (including localized gender NAP that will also cover WPS NAP). |  |  |  | Yes - organized and functional network of IDP and conflict-affected women in place and influences peace and development processes |  |  |  |  | Yes – functional network of IDP and conflict-affected women in place and shapes peace and development processes, the content, and the outcomes |  |  |  |  |  |  |  |  | Yes - organized and functional network of IDP and conflict-affected women in place and shapes peace and development processes, the content, and the outcomes |  |
| Progress Achieved: | Progress Achieved: |  | Progress Achieved: |  | Progress Achieved: |  |  | Progress Achieved: |  |  |  | Progress Achieved: |  |  |  |  | Progress Achieved: |  |  |  |  |  |  |  |  | Progress Achieved: |  |
| Source: List of network members; List of recommendations generated through the needs assessment conducted by the network members; UN Women project progress reports. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.1.b: Number of CSOs and think tanks working on conflict, peace, and security that mainstream Women, Peace and Security issues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2020 – CSOs and think tanks working on conflict, peace and security in Georgia have no structured WPS lens. UNW mapped these CSOs and think tanks and identified 10 leading ones that will be targeted for this work. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) |  | Milestone 2 (March 2022) | Milestone 3 (September 2022) |  |  | Milestone 4 (March 2023) | Milestone 5 (September 2023) |  |  |  |  |  | Milestone 6 (March 2024) |  | Milestone 7 (September 2024) |  |  |  |  |  |  |  |  |  | Target (March 2025) |  |  |
| 0 |  | 0 | At least 10 CSOs trained in WPS |  |  | At least the same 10 CSOs engaged in different conferences/events | At least the same 10 CSOs engaged in different conferences/events |  |  |  |  |  | At least same 10 CSOs engaged in different conferences/events |  | At least same 15 CSOs engaged in different conferences/events |  |  |  |  |  |  |  |  |  | At least same 15 CSOs engaged in different conferences/events |  |  |
| Progress Achieved: The project activity related to this indicator will commence in the second half of 2022. |  | Progress Achieved: The project activity related to this indicator will commence in the second half of 2022. | Progress Achieved: |  |  | Progress Achieved: | Progress Achieved: |  |  |  |  |  | Progress Achieved: |  | Progress Achieved: |  |  |  |  |  |  |  |  |  | Progress Achieved: |  |  |
| Source: Project documents detailing work with these CSOs and think tanks (meeting / training agendas; list of participants.) Achieved progress will be documented by UN Women through formal and informal reporting / communication with the donor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.1.c: Number of higher education institutions that have Women, Peace and Security issues in their curricula |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: According to findings of UNW mapping exercise of Universities in 2020, none of the universities with programs on international relations, conflicts, or peace, integrate WPS topics or have a WPS lens. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) |  | Milestone 2 (March 2022) | Milestone 3 (September 2022) |  |  | Milestone 4 (March 2023) | Milestone 5 (September 2023) |  |  |  |  |  | Milestone 6 (March 2024) |  |  | Milestone 7 (September 2024) |  |  |  |  |  |  |  | Target (March 2025) |  |  |  |
| 0 |  | 0 | 5 universities incorporate WPS in their curricula |  |  | The same 5 universities offer courses as per developed WPS curricula and organize student conferences on WPS | The same 5 universities offer courses as per developed WPS curricula and organize student conferences on WPS |  |  |  |  |  | The same 5 universities offer courses as per developed WPS curricula and organize student conferences on WPS |  |  | The same 5 universities offer courses as per developed WPS curricula and organize student conferences on WPS |  |  |  |  |  |  |  | The same 5 universities offer courses as per developed WPS curricula and organize student conferences on WPS |  |  |  |
| Progress Achieved: Negotiations underway with five universities: Tbilisi State University, Caucasus International University, Gori State Teaching University, Akaki Tsereteli State University and Sokhumi State University to integrate WPS issues in their curricula. |  | Progress Achieved: | Progress Achieved: |  |  | Progress Achieved: | Progress Achieved: |  |  |  |  |  | Progress Achieved: |  |  | Progress Achieved: |  |  |  |  |  |  |  | Progress Achieved: |  |  |  |
| Source: Actual syllabi of relevant courses of target higher education institutions; proceedings of annual student conference on WPS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To strengthen a network of IDP and conflict-affected women and youth and support their capacities on the WPSA to better engage in peace and security decision-making processes and demand increased accountability and implementation of the WPSA and localization of the NAP 1325 (NAP 1325, Activities 2.1.1 and 2.1.2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To support women’s CSOs (including CSO shadow reporting) and the PDO in regular monitoring and reporting of the NAP 1325 implementation at the national and local level, including reporting with a focus on IDP women and girls |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To partner with the Folke Bernadotte Academy to further develop the capacity of the LEPL Levan Mikeladze Diplomatic Training Centre of the Ministry of Foreign Affairs of Georgia to increase the capacity of women mediators, negotiators and technical experts working in the public sector on issues related to conflicts and peacebuilding (NAP 1325, Activity 1.2.1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To support capacity development on WPS to mainstream gender in the work of CSOs and think tanks working on conflict, peace, and security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To build a resource database on WPS that will be accessible, practical, and easy to digest, serving as a reference tool to enable grassroots and local women to learn more and meaningfully participate in peace and security processes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To establish and maintain a pool/roster of WPS experts, practitioners and women’s CSO representatives, as well as women and youth who have received trainings in dialogue, mediation, negotiation and peacebuilding and support the development of mentorship programmes for those interested in peacebuilding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To partner with higher education institutions to promote the integration of WPS topics into the curricula of relevant academic programmes (undergraduate and graduate levels) as well as student research interest in the WPS field |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To support confidence-building between Abkhaz, Georgian and South Ossetian women and engage them in confidence and peacebuilding efforts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To establish WPS Task Force of international development partners, among others, to support cross-ABL cooperation and partnership |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 Mechanisms in place for increased meaningful and representative participation of women in conflict prevention and peacebuilding at the community and national level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 assumptions/risks - Cultural resistance to women’s participation is susceptible to change with the right approach and strategies - There is a willingness from key international actors and parties engaged in formal peace negotiations to include women in conflict resolution processes - Sufficient security is in place for women to engage in confidence and peacebuilding efforts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.2.a: Proportion of recommendations shared by the women during the dialogues supported by the project that are taken up at the GID and/or IPRM sessions, as well as Open Days on WPS and/or reported back on their status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2019 – 0 per cent |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) |  | Milestone 2 (March 2022) | Milestone 3 (September 2022) |  |  | Milestone 4 (March 2023) |  |  | Milestone 5 (September 2023) |  | Milestone 6 (March 2024) |  |  |  |  |  |  |  | Milestone 7 (September 2024) |  |  |  |  |  |  |  | Target (March 2025) |
| 0 per cent |  | 5 per cent | 15 per cent |  |  | 20 per cent |  |  | 25 per cent |  | 30 per cent |  |  |  |  |  |  |  | 35 per cent |  |  |  |  |  |  |  | 35 per cent |
| Progress Achieved: Tracking of recommendations shared by women started. |  | Progress Achieved: | Progress Achieved: |  |  | Progress Achieved: |  |  | Progress Achieved: |  | Progress Achieved: |  |  |  |  |  |  |  | Progress Achieved: |  |  |  |  |  |  |  | Progress Achieved: |
| Source: Agenda of the meetings; meeting notes with recommendations’ tracking tool; Open Day on WPS reports and follow up meeting agendas with relevant stakeholders; UN Secretary General’s annual reports on WPS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.2.b: Number of IDP and conflict affected women taking place in the dialogues supported by the project around GID and/or IPRM sessions, as well as Open Days on WPS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 0 (2020) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) |  | Milestone 2 (March 2022) | Milestone 3 (September 2022) |  | Milestone 4 (March 2023) |  |  |  | Milestone 5 (September 2023) |  |  |  |  | Milestone 6 (March 2024) |  |  |  | Milestone 7 (September 2024) |  |  |  |  |  |  |  |  | Target (March 2025) |
| 200 (in events in this reporting period) |  | 100 (in events in this reporting period) | 50 (in events in this reporting period) |  | 100 (in events in this reporting period) |  |  |  | 50 (in events in this reporting period) |  |  |  |  | 100 (in events in this reporting period) |  |  |  | 50 (in events in this reporting period) |  |  |  |  |  |  |  |  | 100 (in events in this reporting period) 750 in total during the whole project |
| Progress Achieved: 200 1. 24 November 2020 -Open Day on WPS – 50 women 2. 29 October 2020 - IPRM Information Sharing Meeting – 50 women 3.24 May 2021 - IPRM information Sharing Meeting - 50 women 3. 26 April 2021 - GID Information Sharing Meeting – 50 women |  | Progress Achieved: | Progress Achieved: |  | Progress Achieved: |  |  |  | Progress Achieved: |  |  |  |  | Progress Achieved: |  |  |  | Progress Achieved: |  |  |  |  |  |  |  |  | Progress Achieved: |
| Source: Agenda of the meetings, lists of participants. Achieved progress will be documented by UN Women through formal and informal reporting / communication with the donor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To support a regular dialogue mechanism between the GID and IPRM participants and civil society, including women’s CSOs and IDP and conflict-affected women and youth (NAP 1325, Activities 2.2.1 and 2.2.2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To organize preparatory meetings with women’s CSOs and grass-roots women to identify specific issues for the GID/IPRM information meetings as well as for official negotiations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To advocate for the establishment of a standing consultative mechanism or women’s advisory board with women’s CSOs and grass-roots women to ensure their sustainable and structured engagement with the GID and IPRM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To further develop the virtual platform women4peace.net to amplify the voices of Abkhaz, Georgian and South Ossetian women and youth and shed light on women’s meaningful participation and contribution to peace and security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To establish and support regular dialogue mechanisms between IDP and conflict-affected women and representatives of the State Ministry for Reconciliation and Civic Equality (SMR) and the Ministry of Regional Development and Infrastructure (MRDI) on the needs and priorities identified by the project-mobilized women’s groups in the villages adjacent to the ABL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To enhance the partnership with the MFA to support the experience sharing of women mediators and negotiators locally, regionally, and internationally |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To support the establishment of a local and regional network of women peacebuilders (across the Balkans, the South Caucasus, and Central Asia) in order to promote an exchange of good practices and lessons learned and enhance intergenerational dialogues between women peacebuilders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - To organize annual Open Days on Women, Peace and Security – information-sharing and advocacy meetings between conflict-affected and IDP women and their organizations and high-level UN system representatives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Project Outcome 2: Increase in accountability of government, especially key security sector partners, to Women, Peace and Security commitments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 2 assumptions/risks: - Project partners do not lack the interest or good will to participate in the project and work on the WPSA - Gender mainstreaming work promoted by the project is sustainable after project phase-out - The tools and strategies promoted by the project are of quality and are well adapted to Georgia’s context - Sex-disaggregated data and gender analysis are available to inform effective policies and legislation to accurately reflect the needs of women, particularly IDP and conflict-affected women |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Outcome 2 Increase in accountability of government, especially key security sector partners, to Women, Peace and Security commitments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.1: Development of costed and budgeted NAP 1325 and its implementation rate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2020 – No WPS NAP in place |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (Project Year 1 - March 2022) |  |  |  |  |  |  |  |  |  |  |  | Milestone 2 (Project Year 2 – March 2023) |  |  | Target (Project Year 3/end project March 2024) |  |  |  |  |
| NAP 1325 developed, costed, and adopted |  |  |  |  |  |  |  |  |  |  |  | NAP 1325 implementation rate – 20 per cent |  |  | NAP 1325 implementation rate – 50 per cent |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Progress Achieved: 78 per cent |  |  |  |  |
| Source: Governmental decree approving the NAP 1325; annual monitoring report by the Government; independent monitoring report by the PDO on NAP 1325 implementation. Achieved progress will be documented by UN Women through formal and informal reporting / communication with the donor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.2.: Level of gender mainstreaming - integration of gender equality and WPS principles in Georgia’s security sector institutions and their enhanced capacities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2020 – Ministry of Defence (MoD) – Medium (gender equality strategy in place, gender equality action plan in draft format, sexual harassment complaints mechanism in place but weakly functional, institutional gender capacities (gender advisors/gender monitoring group) in place) 2020 – Ministry of Internal Affairs (MIA)- Low (gender equality strategy not developed, gender equality action plan not drafted, sexual harassment complaints mechanism in place but weakly implemented, human rights department working on DV/EVAW issues established and effective, institutional gender capacities (gender advisors/gender monitoring group) not in place) 2020 – State Security Service (SSS), Georgian Intelligence Service (GIS), National Security Council (NSC) – very low / gender blind |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (Project Year 1 - March 2022) |  |  |  |  |  |  |  |  |  |  |  | Milestone 2 (Project Year 2 – March 2023) |  |  | Target (Project Year 3/end project March 2024) |  |  |  |  |
| MoD – Medium MIA – Low SSS – Very low NSC – Very low GIS – Very low |  |  |  |  |  |  |  |  |  |  |  | MoD – Medium MIA – Medium SSS – Low NSC - Low GIS - Low |  |  | MoD – High MIA – Medium SSS – Low NSC - Low GIS - Low |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Progress Achieved: - MoD – High - MIA – Medium - SSS, NSC, GIS – Medium |  |  |  |  |
| Source: Participatory Gender Audit Reports, independent monitoring reports by the PDO on a) NAP 1325 implementation, and b) on the state of gender mainstreaming in state institutions (documents and mechanisms adopted on gender mainstreaming). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 Government entities, including key security sector partners, have enhanced capacities and an evidence base to develop and implement the NAP 1325 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.1.a: Share of Gender Impoact Assessment recommendations addressed by respective entities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2020 – 0 per cent |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) |  |  |  | Milestone 2 (March 2022) |  |  |  |  |  | Milestone 3 (September 2022) |  |  | Milestone 4 (March 2023) |  |  | Milestone 5 (September 2023) |  |  | Target (March 2024) |
| 0 per cent |  |  |  | 0 per cent |  |  |  |  |  | 10 per cent |  |  | 20 per cent |  |  | 25 per cent |  |  | At least 30 per cent in 2024 |
| Source: GIA report and follow-up advocacy meeting materials; Achieved progress will be documented by UN Women through formal and informal reporting / communication with the donor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.1.b: Number of Participatory Gender Audits conducted in the framework of the project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2020 - 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) |  |  |  | Milestone 2 (March 2022) |  |  |  |  | Milestone 3 (September 2022) |  |  |  | Milestone 4 (March 2023) |  |  | Milestone 5 (September 2023) |  |  | Target (March 2024) |
| 0 |  |  |  | 2 |  |  |  |  | 0 |  |  |  | 1 |  |  | 0 |  |  | 3 in 2024 |
| Source: PGA reports. Achieved progress will be documented by UN Women through formal and informal reporting / communication with the donor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 Key security sector partners have enhanced capacities to mainstream gender into their policies, procedures, and operations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 assumptions/risks - Security sector actors are open to integrating UNSCR 1325 into the sector reform process and to building capacity on gender equality - Women’s participation in the security sector leads to more gender-responsive security outcomes for the whole of society - Capacity development interventions of the project reach out to managers and senior officials - Training materials and tools/mechanisms developed are not too complex to be used by a wide range of relevant actors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.2.a: Number of security sector representatives (senior and technical level) reached by gender mainstreaming capacity development interventions of the project in the following institutions: Ministry of Defence (MoD), the Ministry of Internal Affairs (MIA) and the State Security Service (SSS) – as well as introduce and familiarize new security sector partners – the National Security Council (NSC) and the Georgian Intelligence Service (GIS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2020 - 250 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) |  |  |  |  | Milestone 2 (March 2022) |  |  |  |  |  | Milestone 3 (September 2022) |  | Milestone 4 (March 2023) |  |  | Milestone 5 (September 2023) | Target (March 2024) |  |  |
| 50 |  |  |  |  | 100 |  |  |  |  |  | 100 |  | 100 |  |  | 100 | 50 500 in total |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Progress Achieved: 1123 |  |  |
| Source: Training participants list, and training evaluations documented through project progress reports. MoU between UN Women and MoD, MoU between UN Women and MIA. Achieved progress will be documented by UN Women through formal and informal reporting / communication with the donor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.2.b: Share of trained officials by this project that demonstrate increased knowledge and commitment to take steps to integrate gender perspectives into their work (in the Ministry of Defence (MoD), the Ministry of Internal Affairs (MIA) and the State Security Service (SSS), the National Security Council (NSC) and the Georgian Intelligence Service (GIS)) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2020 – 0 per cent |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) |  |  | Milestone 2 (March 2022) |  |  |  |  | Milestone 3 (September 2022) |  |  |  |  | Milestone 4 (March 2023) |  |  | Milestone 5 (September 2023) | Target (March 2024) |  |  |
| N/A – no trainings in this reporting period |  |  | 95 per cent |  |  |  |  | 95 per cent |  |  |  |  | 95 per cent |  |  | 95 per cent |  |  |  |
| Source: Training evaluations documented through project progress reports. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.2.c: Proportion of PGA recommendations addressed by the audited entities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2020 – 0 per cent |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) |  | Milestone 2 (March 2022) |  |  |  | Milestone 3 (September 2022) |  |  |  |  |  |  | Milestone 4 (March 2023) |  |  | Milestone 5 (September 2023) | Target (March 2024) |  |  |
| N/A PGAs not yet completed |  | 5 per cent |  |  |  | 15 per cent |  |  |  |  |  |  | 20 per cent |  |  | 30 per cent | 40 per cent |  |  |
| Source: PGA reports and follow-up activities (work-plans, implementation reports). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.2.d: Network of women in defence and security established |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2021 - No |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) | Milestone 2 (March 2022) |  |  |  |  |  | Milestone 3 (September 2022) |  |  |  |  |  |  | Milestone 4 (March 2023) | Milestone 5 (September 2023) |  |  | Target (March 2024) |  |
| N/A | No (Work initiated) |  |  |  |  |  | No (Women trained to be a part of the network) |  |  |  |  |  |  | Yes (Network established) | Yes (Network functional) |  |  | Yes (Network functions independently) |  |
| Source: List of members of the network; Achieved progress will be documented by UN Women through formal and informal reporting / communication with the donor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.2.e: Number of women capacitated in leadership and mentoring through the network of women in defence and security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Baseline: 2021 - 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestone 1 (September 2021) | Milestone 2 (March 2022) |  |  |  |  |  | Milestone 3 (September 2022) |  |  |  |  |  |  | Milestone 4 (March 2023) | Milestone 5 (September 2023) |  |  | Target (March 2024) |  |
| N/A | 30 |  |  |  |  |  | 50 |  |  |  |  |  |  | 50 | 50 |  |  | 20 200 in total |  |
| Source: Training participants list, and training evaluations documented through project progress reports. Achieved progress will be documented by UN Women through formal and informal reporting / communication with the donor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

### Annex 3 List of key documents

Project documents:

- Project document (ProDocs with amendments until March 2025)

- Agreement between UN Women Georgia and FCDO (donor), 2020

- WPS donor agreement package with amendments, 2021 (7 documents)

- Annual Reports to Donors (2022, 2023, 2024)

- RMS Quarterly reports (5 documents)

- Partner narrative reports 2020-2024, 2024-2025

- Steering Committee I, 2022

- Steering Committee II, 2023

- Steering Committee III, 2024

- Geneva International Discussion Co-Chair meetings (minutes)

- IPRM minutes (internal reports)

- Open Day reports by year (2022, 2023, 2024)

- Monitoring data i.e., monitoring missions, databases, implementation tracking tools (NAP 1325, GIA, PGA) – 10 documents

Research and knowledge products produced under the project

- History of Localization of Women, Peace and Security Agenda in Georgia. Women's Information Center, 2023.

- Thematic Report of the Parliament of Georgia on the Implementation of the Women, Peace and Security Agenda in Georgia, 2023.

- Monitoring Report of the 2018-2020 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security. Public Defender of Georgia, 2021

- Monitoring Report of the 2022-2024 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security. Public Defender of Georgia, 2024

- Gender mainstreaming: A review of Georgia's recognized commitments and the status of their implementation. Public Defender of Georgia, 2021

- Women, Peace and Security Agenda in Georgia, Brief. UN Women.

- Independent Monitoring of the 2018-2020 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security, 2021.

- Needs assessment of populations living at the ABL and IDP settlements, 2023 (in Georgian)

- Women, ANOVA (2023) Views and Attitudes of Internally Displaced Women on Conflict Transformation, Reconciliation and Peace Building in Georgia

- UN WOMEN (2023). Monitoring of Human Security: Gender-Responsive Monitoring For The Civil Society. Manual for Civil Society Organizations

- DCAF (25 November 2024). Changing mindsets for gender equal security institutions: Georgia case study

Strategic planning documents

- UN Women Global Strategic Plan (2018-2021)

- UN Women Georgia Strategic Note 2016-2020

- UN Women’s Strategic Plan, 2022–2025

- UN Women Georgia Annual Work Plans

- UN Sustainable Development Cooperation Framework (UNSDCF) 2021-2025

UN Women evaluation reports

- UN Women Independent Evaluation Service. (2025). Corporate evaluation of UN Women's support to women's participation in peace processes. UN Women. New York. 2025

Reports and other related publications:

- GeoStat, “Man and Woman in Georgia”, 2024

- UN Women, Country Gender Equality Profile Georgia, 2023

- Voluntary National Review Georgia, VNR 2020

- Sustainable Development Report 2024, Georgia.

- Rapid Gender Assessment of COVID-19 Situation in Georgia - 2 wave. UN Women, 2021.

- Ukrainian Refugees in Georgia Assessment Report. UNHCR & World Vision, November 2022.

- OSCE Office for Democratic Institutions and Human Rights (ODIHIR)’s Legal analysis of the Law on Transparency of Foreign Influence, 2024.

- European Commission, Opinion on the EU membership application by Georgia, memo (17 June 2022).

- UN Security Council Resolution #1325 Monitoring the localization Process in Georgia. Women’s information Center, 2021.

- Government of Georgia Report on 2018-2020 NAP implementation

- Gender Analysis of the Ergneti Incident Prevention and Response Mechanism (IPRM), EU Monitoring Mission in Georgia, 2021

- Report on the Activities of the Office of the State Minister for Reconciliation and Civic Equality in 2023.

- Written Submission for 84th session of the Committee on the Elimination of Discrimination against Women (CEDAW). Public Defender of Georgia, 2023

- Sixth Periodic Report of Georgia on The Convention on the Elimination of All Forms of Discrimination against Women (CEDAW). Government of Georgia, 2020

- Joint Shadow Report on the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) To be presented to the UN Committee on the Elimination of Discrimination against Women. Prepared by 29 civil society organizations working on gender equality and women’s empowerment in Georgia, 2021.

National Policy Documents

- Vision 2030 – National Development Strategy 2016-2030

- The National Strategy on Protection of Human Rights – 2022-2030

- 2024-2026 action plan for human rights protection in Georgia

- 2022-2024 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security

- 2018-2020 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security

- 2016-2017 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security

- 2012-2015 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security

- State concept of gender equality of Georgia

- State concept of women's economic empowerment

- 2022-2024 Action Plan of the Permanent Parliamentary Council on Gender Equality

- The order #45 on "Women, Peace, and Security - Advisory Platform on Enhancing Women's Effective Participation in the Peacebuilding Process" by the State Minister for Reconciliation and Civic Equality, 22/04/2021

- The Law of Georgia on Occupied Territories, 2008

Evaluation reference materials:

- United Nations Evaluation Group (2016). Norms and Standards for Evaluation. New York: UNEG.

- The UN Women Evaluation Policy (2012) - http://undocs.org/en/UNW/2012/12

- UN Women Evaluation Strategy to Transform Women’s and Girls’ Lives, 2018-2021

- UNEG Code of Conduct for Evaluations - http://www.unevaluation.org/document/detail/100

- UNEG Ethical Guidelines - http://www.unevaluation.org/document/detail/102

- UNEG Guidance Integrating Human Rights and Gender in the UN System - http://www.uneval.org/document/detail/1616

- UN Women Evaluation Handbook - http://genderevaluation.unwomen.org/en/evaluation-handbook

- UN SWAP Evaluation Performance Indicator and related Scorecard - http://www.uneval.org/document/detail/145

### Annex 4 Evaluation Matrix

| Relevant evaluation criteria | Key Questions | Specific Sub- Questions | Data Sources and Data collection Methods | Indicators / Quality Standards |  | Methods for Data Analysis |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Relevance: Extent to which the objectives of a development intervention are consistent with beneficiaries’ requirements, country needs, global priorities and partners’ and donors’ policies. | - How does the project reflect and align with gender equality/WPS national strategic plans and normative frameworks as well as Georgia’s international obligations and commitments? - Is the project design based on quality analysis, including gender and human rights-based analysis, risk assessments, socio-cultural and political analysis? - Were the programmatic strategies appropriate to address the identified needs of diverse groups of beneficiaries i.e. from the state institution, civil society, academia, media? | 2.1. To what extent did the project addressed the causes of gender-based inequalities and worked to transform harmful gender roles, norms and power relations? - How well did the project address the needs of diverse groups of women including most vulnerable and marginalize in Geogia in a peacebuilding context? | - Desk review: legal, policy documents and reports (NAP 1325, VNR etc.); project documents and reports; CEDAW, UPR; - Desk review: baselines studies, ProDoc, ToC, project documents and analytical reports/knowledge product of UN Women and partners (CSOs, PDO) 3. Interviews: Project Management, partners and beneficiaries from state institution, civil society, academia, media; Focus groups discussions: women’s CSOs and informal groups/networks, women-leaders in conflict affected communities | - Evidence of alignment to specific activities and results in national strategic plans, gender equality policies and plans i.e. NAP UNSCR 1325 and the country’s internationally undertaken obligations - Evidence of quality analysis done by UN Women, UNCT (CCA) and other analytical input including collection of disaggregated data - Evidence of consultations done by UN Women and partners to ensure that needs of beneficiaries and stakeholders are regularly assessed and taken into account - Perceptions of partners and beneficiaries including from conflict affected communities of adequacy of inputs and strategies to achieve Outputs and contribute to Outcomes |  | Secondary data analysis (legal and policy planning documents) Qualitative methods (comparison of interview data to factual information, identification of common issues/differences as per position of power) |  |
| Coherence: The compatibility of the intervention with other interventions in a country, sector or institution. | - To what extent the project adheres to corporate strategic priorities of UN Women, the work of the UN Country Team (UNSDCF), the national plans to achieve SDGs, in particular SDG 5 and SDG 16? - How does the project design match with the complexity of national structures, systems and decision-making processes? - To what extent have the partnerships developed under the project contributed to coherence of interventions between state institutions, civil society, UNCT and other actors in WPSA? | 4.1. To what extent has UN Women Georgia used strategically the agency’s comparative advantages to accelerate the WPSA in Georgia? 4.2. To what extent has UN Women Geogia promoted coherence with other UN Women projects and related projects of other UN agencies? - Was the Steering Committee representative and effective in ensuring synergies in the area of WPS? - To what extent have the implementing parties used the local decision-making structures to foster participation of women in peace building processes at the grassroots level? | 4.-4.1. Desk review: UN Women Strategic Plan and SN Georgia, UN Women reports, UNSDCF, ProDoc, project reports; 4.1-4-2. Interviews: UN Women staff, UN RC, representatives of other agencies, UK Embassy/donor representatives, Steering Committee; PM of relevant to the WPS projects 5. Desk review: ProDoc, stakeholders’ analysis by UN Women, Steering Committee minutes 5.1.-5.2. UN Women staff, UN RC, representatives of other agencies, UK Embassy/donor representatives, Steering Committee members; | 4.-4.1 Evidence of systematic reference to UN Women strategic priorities, NAP 1325, UNSDCF, other framework documents, nationalized SDG targets 4.2. Evidence of coordination/coherence with related UN Women projects, other UN agencies 5.-5.1. quality stakeholder analysis from the power position to promote women’s participation in peacebuilding at national and grassroots level - Number of issues addressed/solved (by type and vulnerability) pertinent to peace and security - Value assigned by stakeholders and beneficiaries to effectiveness/ complementarity of partnerships for achievement of results |  | Qualitative (identification of reoccurring themes i.e., perceptions of beneficiaries and stakeholders) Quantitative: statistical analysis of cases solved through cooperation with local structures |  |
| Effectiveness: Extent to which the development intervention’s objectives were achieved, or are expected to be achieved, taking into account their relative importance. Effectiveness assesses the outcome level, intended as an uptake or result of an output. | - What has been the progress made towards achievement of the expected outcomes and expected results? - What are the reasons for the achievement or non-achievement of the project results? - Did the project have effective monitoring mechanisms in place to measure progress towards results? 10. To what extent have the capacities of relevant duty-bearers and rights-holders been strengthened? - What is the likelihood that the project results are bringing about gender transformative changes that address the root causes of gender inequalities? - In what way did the project contribute to knowledge base on WPS implementation in Georgia, in the region/globally? | 7.1. What are the results achieved? Are there any unintended results? Did the project produce any longer term results? - What is the influence of the specific country context and circumstances on the achievement of results and operational effectiveness? - To what extent has the adherence to corporate strategic priorities of UN Women and UK around WPS contributed to the project effectiveness? - How adaptably and rapidly does the project react to changing situations? 9.1. Was monitoring data collected and disaggregated according to relevant criteria (sex, age, ethnicity, location, income etc.)? 10.1. Do women participating in WPSA have capacities to engage effectively in peacebuilding and undertake leadership roles? 11.1. To what extent have the project systematically addressed prevailing social norms, attitudes and behaviors, discrimination and social systems that prevent women from meaningful participation in peacebuilding? 12.1. How were the knowledge products disseminated and shared with relevant stakeholders and representatives of women’s CSOs/WPS platforms and networks? | 7.-7.1. Desk review of project progress & annual reports; review of (publications, video, success stories, knowledge products, manuals and training programs 7.-8. Interviews: UN Women staff, partners from state institutions, CSOs; providers of training and advocacy campaigns; women’s peacebuilding networks 7.1.- 8.1. Focus groups discussions with CSOs and women’s networks, media; 8.2-8.3. Interviews: PM unit UN Women, PM unit at donors’, partners - Desk review: monitoring systems at UN Women and partners, minutes of Steering Committee minutes Interviews: project management, monitoring focal points 10.- 10.1. Desk review: recommendations from GIS and PGA reports; training/capacity building providers, reports of partners, to donors, success stories, knowledge products Interviews: representatives of state institutions participated in training and other capacity building activities; participants of Open Days, GID, IPRM Focus group discussions: CSOs, women’s networks, participants of peacebuilding and confidence building activities from conflict affected communities (national and regional level 11.-11.1. Desk review: reports of partners, to donors, surveys/research conducted under the project Focus group discussions: CSOs, women’s networks, participants of peacebuilding and confidence building activities from conflict affected communities (national and regional level Interviews: partners from CSOs, state institutions, participants of Open Days, GID, IPRM - Desk review: lesson learned; knowledge products, publications, social media etc. Interviews: UN Women communication specialists, partners, representatives of research institutions; | - extent of achievement of targets in the RRF - perception of results by partners and beneficiaries (by power relations) - lesson learned capture the reasons for achievement/non-achievement - quality of risk analysis and risk management - evidence of adaptive management approaches/tracking decision making - Evidence of ongoing monitoring/analysis of progress towards results - Evidence of collecting disaggregated data and using it to report on results - extent of commitment to WPSA at state institutions (% of recommendations integrated, allocation of staff, resources, other) - evidence of increased capacity of women- leaders, women-led CSOs and women at grassroots level to participate in decision making and peacebuilding processes - evidence of increased engagement of women and girls in conflict affected communities in conflict prevention and peacebuilding - perceptions of inclusivity of peacebuilding processes by those directly involved into them - Number of women (and men) in decision making positions in key institutions (WPSA) - Lessons learned shared and hold value for WPSA in the region and globally; - Evidence of dissemination of knowledge products (N of publications/posts, N of people by target audience reached including vulnerable women) |  | Qualitative (identification of reoccurring themes i.e., perceptions of beneficiaries and stakeholders) Quantitative (basic statistics – participation, access to services etc.) |  |
| Efficiency: Measure of how economic resources/inputs (funds, expertise, time, etc.) are converted to results. It is most commonly applied to the input-output link in the causal chain of an intervention. | 13. Have resources (financial, human, technical support, etc.) been sufficient and allocated strategically to achieve the project outcomes and gender equality specific targets? 14. To what extend were relevant stakeholders and actors included in the project planning and implementation? | 13.1. Were the resources adequate for the achievement of the objectives? 13.2. Were Output delivered on time? 14.1. To what extent have partnerships established under the project contributed to efficiency of the project? | - Desk review of the project budget utilization, interim/annual reports to donors, etc.), reports in Quantum Interviews: project management, financial specialists, partners (with allocated budget) 14.Desk review: minutes of Steering Committee meetings and decisions, ToRs/LoA with partners and stakeholders Interviews: project management, Steering Committee members, partners (with allocated budget), donors | 13.1.1 Adequacy of staffing, infrastructure and other resources 13.1.2. Ratio of resources allocation to capacity development of duty bearers / right holders 13.2.1. actual compared to planned expenditure by project output; 14.1.1. Evidence of involvement of relevant WPSA stakeholders and actors into planning and implementation 14.1.2. Utilization of partners’ resources (capacity, resources, coordination structures, etc.) for delivery of the project; |  | Quantitative (% and ratio of budget allocation per categories, per target group) Qualitative (perceptions of interviewees of efficiency) |  |
| Sustainability: Continuation of benefits from a development intervention after major development assistance has been completed. The probability of continued long-term benefits | 15. How effectively has the project been able to contribute to the generation of national ownership of the project outputs? 16. What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time after the project phase out? 17. To what extent have the project’s exit strategy been well planned and successful? | 15.1. What are the risks facing sustainability of the project Outputs and Outcomes? 15.2. How effective was the advocacy and communication component of the project for ensuring sustainability of results? 16.1. To what extent has the project identified strategic partners that could pick up on supporting continued government and non-governmental action when the project comes to an end? 16.2. What is their level of commitment to continue to replicate some project activities? 17.1. To what extent has UN Women been able to promote replication of project successes? | 15. Desk review: the project documents and products; reports to the donors; risk analysis; lessons learned; review of the state partners’ institutional strategies and implementation of NAP 1325/WPSA Interviews: the project management, partners from the state institutions, civil society 15.2. Desk review: communication and advocacy materials, communication briefs (events), reports Interviews: with the PM, partners from the line ministries, participants of advocacy and communication campaigns 16. Desk review: project reports; project proposals, other UN Women related projects Interviews: UN Women Director and DD, PM, partners Observation: Steering Committee meeting 17. Desk review: project reports; human success stories; project proposals, other UN Women related projects Interviews: UN Women Director and DD, PM, partners Observation: Steering Committee meeting | - Extent of integration of NAP 1325 and WPSA into partners and stakeholders’ - Strategies employed by UN Women to address risks to sustainability - N of people (men and women) reached by communication campaigns; N of people by target audience participated in advocacy activities 16. Likelihood of ownership of established inclusive peacebuilding structures by the partners (ministries, CSOs) 16.1. Evidence of partnerships established (between state actors, CSOs and women’s networks) to promote women’s participation and leadership in peacebuilding; 16.2. evidence of allocation of budget and other resources by partners for continued actions - Effectiveness of exit strategies 17.1. Evidence of scale-up strategies in the new project document/other related projects’ documents |  | Qualitative: perceptions of partners and beneficiaries; evidence of sustainability in policy documents, institutional plans etc. Quantitative ( project statistics) |  |
| Inclusion | - Did the implementing parties and their partners systematically integrate HR, GR and Inclusion of People with Disabilities in the project design and implementation? | 18.1. To what extent women- IDPs, PWD, other disadvantaged and marginalized groups have been included into the project activities? - What -if any- types of innovative good practices have been introduced in the project for the meaningful participation and empowerment of IDP and conflict affected women and youth? | - Desk review: the project design, theories of change; records/minutes of consultations with beneficiaries, protocols of monitoring trips to the locations; project proposals Interviews: PM, members of Steering Committee, CSOs Focus group discussions: conflict affected women- beneficiaries of the project, women-leader 18.2. Desk review: project reports to the donor, knowledge products Interviews: UN Women Country Director and DD, PM, partners | 18. N of IDPs beneficiated by the project (by sex, age, location, social status, disability, GBV survivors) 18.1. Evidence of systematic inclusion of women-IDP, PWD, marginalized groups 18.2. Likelihood of institutionalization of innovative good practices | Qualitative: perceptions of partners and beneficiaries |  |
| Conflict sensitivity | 19. Did the implementing partners have an explicit approach to conflict-sensitivity, in particular in addressing gendered causes of conflicts in the WPS context in Georgia, i.e. VAWG? | 19.1. Were internal and external capacities of implementing partners adequate for ensuring an ongoing conflict-sensitive approach? - Was there any unintended negative impact, also on conflicts, resulting from the project interventions? | - Desk review: project documents, training/ capacity building reports Interviews: project management, partners and their focal points in the conflict affected communities Focus group discussions: women-IDPs and conflict affected women, members of women’s networks/participants of GID and IPRM consultations | - Extent of mainstreaming of conflict-sensitive approach to the project interventions in the WPS context in Georgia 19.1. Evidence of increased capacities of partners to implement gender-sensitive risk analysis and conflict mitigation strategies 19.2. Perceptions of women -beneficiaries and partners of effectiveness of conflict mitigation strategies in the context of building in Georgia | Qualitative: (desk, review; Perceptions of beneficiaries of own security) |  |

### Annex 5 Stakeholders’ analysis

| Stakeholders | Category | Purpose of involvement in evaluation | Priority | Stage of the evaluation to engage them | Capacities in which stakeholders participate |
| --- | --- | --- | --- | --- | --- |
| Gender Equality Council (GEC) of the Parliament of Georgia | Duty bearers with the authority to make decision related to the intervention | Consult: evidence of impact of project on implementation of NAP 1325 and mainstreaming of WPS | High to Medium (Due to influence on new legislation as well as oversight on implementation of NAP 1325) | Data collection and analysis Report preparation | Informant |
| The Defense and Security Committee of the Parliament of Georgia | Duty bearers with the authority to make decision related to the intervention | Consult: evidence of impact of project on implementation of NAP 1325 and mainstreaming of WPS | High (Due to influence on new legislation as well as oversight on implementation of NAP 1325) and mainstreaming of WPS | Data collection and analysis Report preparation | Informant |
| Human Rights Secretariat, Advisor to the Prime Minister of Georgia on Human Rights issues | Duty bearers with the authority to make decision related to the intervention | Consult: evidence of impact of the project mainstreaming of NAP 1325 | High to Medium (Due to influence on new legislation as well as oversight on implementation of NAP 1325) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| The Inter-Agency Commission of the Government on Gender Equality and Ending Violence against Women and Domestic Violence Issues | Duty bearers with the authority to make decision related to the intervention | Consult: evidence of impact of project on gender- sensitive policy making; evidence of the project impact on implementation of NAP 1325 | High (Due influence on sustainability of gender equality and WPSA mainstreaming) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| Public Defender’s Office | National Human Rights Instrument/Secondary dutybearers with the authority to make decision related to the intervention | Collaborate (incorporate advice and concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (evidence of increased capacities of duty bearers to mainstream NAP 1325 and WPSA)) | Data collection and analysis Report preparation | Informant /member of Steering Committee Informant |
| MFA Georgia | Duty bearers with the authority to make decision related to the intervention | Consult (Incorporate advice and concerns to the greatest degree possible) | High (due influence on sustainability of gender mainstreaming through GID/IPRM) | Data collection and analysis Report preparation | Informant/participation in the Steering Committee meetings |
| Office of the State Minister for Reconciliation and Civic Equality | Beneficiary/Duty bearers with the authority to make decision related to the intervention | Collaborate (Incorporate advice and concerns to the greatest degree possible) | Medium to high (WPSA mainstreaming in GID/IPRM) | Data collection and analysis | Informant |
| Ministry of Defence | Beneficiary/Duty bearers with the authority to make decision related to the intervention | Collaborate (Incorporate advice and concerns to the greatest degree possible) | High (sustainability of gender equality mainstreaming into institutional structures and human resources policies) | Data collection and analysis | Informant /participant in the Steering Committee meetings |
| David Aghmashenebeli National Defense Academy | Beneficiary/Service provider | Consult (Incorporate advice and concerns to the greatest degree possible) | Medium to High (sustainability of WPSA mainstreaming into service provision) | Data collection and analysis | Informant |
| Ministry of Internally Displaced Persons from Occupied Territories, Labour, Health and Social Affairs | Beneficiary/ Duty bearers with the authority to make decision related to the intervention | Collaborate (Incorporate advice and concerns to the greatest degree possible) | High (due to influence on gender mainstreaming into policies that target IDPs) | Data collection and analysis | Informant |
| Ministry of Foreign Affairs LEPL Levan Mikeladze Diplomatic Training and Research Institute | Partner/service provider responsible for mainstreaming WPSA into training | Consult (Incorporate advice and concerns to the greatest degree possible) | High to Medium (sustainability of WPSA mainstreaming into service provision) | Data collection and analysis | Informant |
| The Geneva Centre for the Democratic Control of Armed Forces (DCAF) | Partner/service provider responsible for mainstreaming gender into Security Sector Reform (MoD, MIA etc.) | Consult (Incorporate advice and concerns to the greatest degree possible) | High (evidence of increased capacities of security sectors institutions to mainstream gender equality) | Data collection and analysis Report preparation | Informant/participant in the Steering Committee |
| Nordic Centre for Gender in Military Operations | Partner/service provider responsible for mainstreaming gender into Security Sector Reform (MoD) | Consult (Incorporate advice and concerns to the greatest degree possible) | Medium (evidence of increased capacities of security sectors institutions to mainstream WPSA) | Data collection and analysis | Informant |
| Austrian Centre for Peace | Partner/ service provider | Consult, integrate their feedback | Low to Medium (evidence of increased capacities of beneficiaries to mainstream WPSA) | Data collection and analysis | Informant |
| Geneva International Discussions (GID Co-Chairs) | Partner/Duty bearers with the authority to make decision related to the intervention | Consult (Incorporate advice and concerns to the greatest degree possible) | Medium to High (evidence of increased capacities of women-beneficiaries of the project) | Data collection and analysis | Informant |
| Office the United Nations Representative to the Geneva International Discussions (UNRGID) | Partner/Duty bearers with the authority to make decision related to the intervention | Consult (Incorporate advice and concerns to the greatest degree possible) | Medium to High (evidence of increased gender-sensitivity of GID processes/capacities of women-beneficiaries of the project) | Data collection and analysis | Informant |
| Ministry of Internal Affairs of Georgia | Beneficiary/ Duty bearers with the authority to make decision related to the intervention | Consult (Incorporate advice and concerns to the greatest degree possible) | Medium to High (evidence of increased capacities of duty bearers to mainstream WPSA) | Data collection and analysis | Informant |
| State Security Service of Georgia | Beneficiary/ Duty bearers with the authority to make decision related to the intervention | Consult (Incorporate advice and concerns to the greatest degree possible) | Medium to High (evidence of increased capacities of duty bearers to mainstream WPSA) | Data collection and analysis | Informant |
| Georgian Intelligence Service (GIS) | Beneficiary/ Duty bearers with the authority to make decision related to the intervention | Consult (Incorporate advice and concerns to the greatest degree possible) | Medium to High (evidence of increased capacities of duty bearers to mainstream WPSA) | Data collection and analysis | Informant |
| Institute for War and Peace Reporting (IWPR) | Partner/Secondary duty bearers involved into interventions | Consult, integrate their feedback | Medium (influence on gender/WPSA mainstreaming into media and research) | Data collection and analysis | Informant |
| Ivane Javakhishvili Tbilisi State University (TSU) | Partner/beneficiary/service provider | Consult, integrate their feedback | Medium to High (influence on WPSA mainstreaming into academia) | Data collection and analysis | Informant |
| ISET Policy Institute | Partner/service provider | Consult, integrate their feedback | Medium (influence on WPSA mainstreaming into research) | Data collection and analysis | Informant |
| 25 CSOs | Beneficiaries of training/ Secondary duty bearers | Consult (Incorporate advice and concerns to the greatest degree possible) | Medium (evidence of mainstreaming of WPSA into institutional structures and interventions) | Data collection and analysis | Informant |
| The Network of Women and Youth Peace Ambassadors | Beneficiaries/rights holders | Consult (Incorporate advice and concerns to the greatest degree possible) | Medium (evidence of mainstreaming of WPSA into institutional structures and interventions) | Data collection and analysis | Informant |
| IDP Women’s Association “Consent” | Partner/Secondary duty bearers who have direct responsibility for intervention at the grass root level | Collaborate (incorporate advice and concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (evidence of increased capacities of conflict affected women and IDPs, sustainability of interventions) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| Women’s Information Center (WIS) | Partner/Secondary duty bearers who have direct responsibility for intervention | Collaborate (incorporate advice, concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (evidence of increased capacities of conflict affected women and IDPs, sustainability of interventions) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| Women’s Fund Sukhumi | Partner/Secondary duty bearers who have direct responsibility for intervention | Collaborate (incorporate advice, concerns to the greatest degree possible, provide feedback, how their input was incorporated) | High (evidence of increased capacities of conflict affected women and IDPs, sustainability of interventions) | Data collection and analysis Report preparation | Informant /member of Steering Committee |
| Women’s groups and networks | Right holders/beneficiaries of the project (women-IDPs and conflict-affected women) | Collaborate to the greatest degree Provide opportunities for meaningful involvement Provide feedback, how their input was incorporated | High (evidence on relevance of interventions, changes in capacities to participate in peacebuilding, sustainability of women’s mobilization) | Data collection and analysis Report preparation | Informant |

### Annex 6 Data collection instruments

  - Interview protocols with the line ministries and security sector agencies

Relevance

- In what way did the project assist your institution in implementation of gender equality mainstreaming, also in connection with implementation of the NAP UNSCR 1325?

- Were you able to provide your opinion, concerns, and recommendations about the project activities? In case, yes, to who, how? Were your concerns and recommendations considered?

Coherence

- Do you think that synergies between UN Women and other actors in the areas of women’s participation in peacebuilding, women in security sectors are sufficient? If Yes, can you provide examples of complementarity between this project and other projects that your organization is involved into?

- Did you participate in the meetings of the Project Steering Committee? If Yes, was it representative and effective in ensuring synergies between participating institutions in the area of WPS? If No, with which organizations collaboration should be established, who should be invited into the Steering Committee?

Effectiveness

- What do you see as the main changes/results of this project i.e., organizational, individual etc.?

- To what extent has the project helped your institution in networking, exchange of experience, best practices, etc?

- Which results are likely to have a transformative impact on gender equality and women’s participation in peacebuilding in Georgia?

Efficiency

- How would you evaluate the sufficiency of capacity development activities? quality of expertise (training courses, PGA, GIA, etc.)?

Sustainability

- Is your institution going to ensure sustainability /take over any of the benefits produced by the project? If yes, which activities and products, developed capacity, mechanisms?

- To what extent will you be able to ensure sustainability of the project benefits with your own resources? Which factors may affect (positively or negatively) sustainability of the benefits produced by the UN Women project?

Inclusion

- To what extent do you think the benefits produced by the project are going to promote inclusion of vulnerable women and men, like PWD, conflict affected women (and men) living at the ABL and other and ensure that benefit from mainstreaming of WPSA in your institution?

Conflict sensitivity

- To what extent did the project implementation consider existing conflicts and possible impact of these conflicts on beneficiaries?

  - Focus group discussion protocol with representatives of women’s and youth’s networks

Relevance

- Which activities of the project did you find the most relevant to your needs, most useful for you/you your community? WHY?

- Were you able to provide your opinion, concerns, and recommendations about the activities? In case, Yes, to who, how? Were your concerns and recommendations considered?

Coherence

- Who did you collaborate with on peacebuilding activities/conflict resolution, etc.) such as other women networks, CSOs, local councils (administration), police and other? What do you think of this collaboration?

Effectiveness

- Which activities, in your opinion, have been most successful? Please elaborate what contributed, in your opinion, to the success of these activities?

- What did not go that well? Which factors, in your opinion, affected that (political, social, economic, cultural or other)?

- How would you define the main changes (or one significant change) that participation in this project brought up for you? women in your community? other community members?

- Were there any unintended/ unexpected results? What happened?

Efficiency

- What do you think about organization of meetings of women’s networks, meetings with representatives of GID, IPRM, security sector institutions/line ministries? What may be improved in future?

Sustainability

- Which activities do you think you may continue doing independently? For which activities do you need support, from whom?

Conflict sensitivity

- Was there any situation when your participation in peacebuilding activities created a conflict/threat to the security? How was it addressed or resolved if it was?

Inclusion

- Are there currently any groups of women, also men, who remain excluded from participation in peacebuilding, conflict prevention in your communities and/or at national level?

  - Interview protocol with the UN Women CO Director/Deputy Director, Project Management, M&E focal point

Relevance

- Can you describe the significance of this project to advance GEWE in Georgia and its place in relation to formerly and currently implemented projects and programmes?

- What was done to ensure that the project outputs and outcomes are/remain relevant to the needs of stakeholders and beneficiaries, national policy gender equality and women’s empowerment and international commitments?

Coherence

- What do you think about collaboration between implementing partners and other stakeholders? With which institutions did collaboration go very well? With which ones could it be better?

- Was the Steering Committee representative and effective in ensuring synergies between participating institutions in mainstreaming of WPGA? If No, with who collaboration should be established, who should be invited into the Steering Committee?

- To what extent did the Project benefit from interventions implemented by other UN agencies under the UNCF? Other international actors? Was the UN GTG instrumental in fostering synergies between UN agencies to promote GEWE and WPS?

Effectiveness

- Were the results achieved as expected? Please elaborate. Were there any unexpected achievements?

- Which of the achieved results may have any transformative impact in future on women’s participation in decision making and peacebuilding?

- What factors contributed to the achievement or non-achievement of the results? What would be your overall opinion of the external environment in which the project was implemented (political, economic, and cultural)? In what way was it favourable for the project and in what way not?

- What monitoring systems/instruments were there to observe the project performance, achievement of the results, test the assumptions and diagnose the risks? Was the monitoring system effective, in your opinion, to produce quality information and disaggregated data?

- How was the data from monitoring used? What do you think of visibility of the Project and its results for partners and beneficiaries?

Efficiency

- Were resources (human, financial, technical) sufficient to achieve the expected results?

- Were the main milestones achieved on time? If not, what the reasons for delay were and what effect had it on other milestones/components of the project?

- What do you think of the overall efficiency of the project management structures and approaches employed under the Project?

Sustainability

- What has been done to ensure national and local ownership over the activities and outputs of the Project? Which components are likely to enjoy most ownership and, consequently, sustainability?

- What are the main factors that may affect (positively, negatively) the sustainability of the benefits produced by the project?

- To what extent have communication and advocacy campaigns effective to create more favorable environment for women’s participation in WPS interventions in future?

- What scale-up strategies were employed to promote a wider impact on beneficiaries and WPSA mainstreaming?

Inclusion

- What was the extent of inclusion of beneficiaries from the target groups? Were there any vulnerable groups that were/remained excluded from participation in peacebuilding, for example people with disabilities? Why?

Conflict sensitivity

- To what extent did the project implementation consider existing conflicts and possible impact of these conflicts on beneficiaries?  What measures were put in place to reduce possibilities for the project interventions to contribute to conflicts/affect security of participants?

  - Interview with CSOs- partners of the project

Relevance

- To what extent was your participation in the project activities relevant for your organization/your beneficiaries?

Coherence

- How would you evaluate the extent of cooperation on the WPS issues among participating agencies from the government, civil society, women networks, and other counterparts? In what has the cooperation improved and between who(m)?

Effectiveness

- What do you see as the main results of the project (for women at the grassroot level, for representatives of line ministries, communities, civil society)?

- Do you see any positive shifts in how women and their participation in decision making and peacebuilding is perceived? Any changes in practices of involving women-IDPs and conflict-affected women into peacebuilding? How can these positive changes be explained, why did they happen?

- Which results of the project were more difficult to achieve and why?

- Do you think that monitoring of changes in relation to women’s participation was adequate to bring to light changes in capacities of women and their empowerment including undertaking leadership role in peacebuilding processes? If not, how can monitoring and reporting of these results be improved?

Efficiency

- What do you think about the sufficiency of resources (funding, time, human resources, expertise) to achieve the project outputs and outcomes?

- What do you think about the management approach and coordination in this project? What should be improved in the future?

Sustainability

- In what way are  you going to apply the knowledge and experience you got from your participation in the project?

- What is needed to ensure that women-IDPs, conflict- affected women, and their networks remain sustainable and make impact on the peacebuilding processes?

Inclusion

- To what extent do you think the project contributed to participation of diverse groups of women and addressed their human rights?

- Which groups of women remain excluded from participation in networks, peacebuilding activities and other activities under WPSA? Why do they remain excluded?

Conflict sensitivity

- Did you have any policies or mechanisms to prevent aggravation of conflicts as the result of the project interventions?

- What would you recommend for future interventions of UN Women and their partners to ensure that interventions do not lead to aggravation of conflicts?

  - Interview with stakeholders participating in GID and IPRM consultations and meetings with women-beneficiaries of the project

Relevance

- Do you think that solutions proposed by the project to promote women’s participation in peacebuilding were timely and relevant? In what way?

Coherence

- How would you evaluate the extent of cooperation on the WPS issues among participating agencies from the government, civil society, women networks, and other counterparts? In what has the cooperation improved and between who(m)?

Effectiveness

- What do you see as the main results of the project (for women participating in Open Days, information meetings and advocacy, for representatives of line ministries, communities, civil society)?

- Did you observe any changes in institutional practices of state agencies of involving women-IDPs and conflict-affected women into decision making and peacebuilding processes? How can these positive changes be explained, which factors contributed to these changes?

- To what extent, in your opinion, have capacities of women to play a more vocal role in peacebuilding processes and conflict prevention improved?

Efficiency

- What do you think about coordination between partners and stakeholders in this project?

Sustainability

- What is needed to ensure that women-IDPs, conflict- affected women, and their networks remain sustainable and make impact on the peacebuilding processes?

- Can you identify any best practices proposed by the project that may be scaled up and disseminated on the national, regional, and global level?

Inclusion

- To what extent do you think the project contributed to participation of diverse groups of women and addressed their human rights?

- Which groups of women remain excluded from participation in networks, peacebuilding activities and other activities under WPSA? Why do they remain excluded?

Conflict sensitivity

- Did you have any policies or mechanisms to prevent aggravation of conflicts as the result of the project interventions?

- What would you recommend for future interventions of UN Women and their partners to ensure that interventions do not lead to aggravation of conflicts?

  - A survey instrument to be administrated to the grassroot level women- members in peacebuilding networks and women-leaders

| Category | Statements/Questions |  |
| --- | --- | --- |
| Women’s sense of self-worth |  |  |
| 1. | Women in our community have knowledge of their rights and Women, Peace and Security issues due to training provided by the project |  Totally agree  Mostly agree  Mostly disagree  Totally disagree  I do not know |
| 2. | Women in our communities have strong abilities to participate in peacebuilding activities at local and national level |  Totally agree  Mostly agree  Mostly disagree  Totally disagree  I do not know |
| Women’s right to have and to determine choices |  |  |
| 3. | Just a few women in our community became more active in advocating for their rights at the local council |  Totally agree  Mostly agree  Mostly disagree  Totally disagree  I do not know |
| 4. | The women in our network effectively and powerfully participate in decision making at the local level |  Totally agree  Mostly agree  Mostly disagree  Totally disagree  I do not know |
| Women’s right to have access to opportunities and resources |  |  |
| 5. | Women have all necessary resources they need to influence peacebuilding |  Totally agree  Mostly agree  Mostly disagree  Totally disagree  I do not know |
|  | We learn from other networks and share our experience in peacebuilding and WPS work together with other women’s networks |  Totally agree  Mostly agree  Mostly disagree  Totally disagree  I do not know |
|  | Representatives of local municipalities more frequently involve women in decision making related to improvement of the situation for IDPs and conflict affected women |  Totally agree  Mostly agree  Mostly disagree  Totally disagree  I do not know |
| Women’s ability to influence the direction of social change |  |  |
|  | Women in our communities/ networks are aware about opportunities that exist at the national level to influence solution of problems of conflict-affected communities |  Totally agree  Mostly agree  Mostly disagree  Totally disagree  I do not know |
|  | Women in our network participate in most of activities that promote peace and security in our community |  Totally agree  Mostly agree  Mostly disagree  Totally disagree  I do not know |
|  | The civil society organizations play an important role in our community to support women’s participation in peacebuilding and decision making |  Totally agree  Mostly agree  Mostly disagree  Totally disagree  I do not know |

### Annex 7 Terms of Reference

CONSULTANT TERMS OF REFERENCE

| # I. Contract Overview |  |
| --- | --- |
| Consultancy Title: | INTERNATIONAL CONSULTANT / EVALUATOR FOR THE FINAL EVALUATION OF THE UN WOMEN PROJECT: “ACCELERATING IMPLEMENTATION OF WOMEN, PEACE AND SECURITY AGENDA IN GEORGIA’’ |
| Location: | Home-based, with travel to Georgia |
| Practice Area: | Gender Equality |
| Type of Contract: | Individual Contract |
| Category (Eligible applicants): | External |
| Post Type and Level: | International Consultant |
| Languages Required: | English |
| Starting Date: | 19 December 2024 |
| Duration of Contract: | 40 working days in the period of 24 December 2024 – 17 March 2025 |

# II. Consultancy Assignment

Background/Context UN Women, grounded in the vision of equality enshrined in the Charter of the United Nations, works for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security. The Women, Peace, and Security (WPS) agenda stands at a juncture to prevent conflicts, protect human rights, build peace, and promote relief and recovery from conflict and crisis. However, there are remaining global, regional, and local challenges for its full implementation due to institutional resistance and the lack of budgeting and of political will to meet the commitments under UN Security Council resolution 1325 (2000) on Women, Peace, and Security (hereinafter UNSCR 1325) and its sister resolutions. Further, crisis and conflict have profound and disproportionate impacts on women and girls, amplifying pre-existing inequalities. Since 2001, UN Women (previously UNIFEM) has provided continues support to partners in Georgia to increase meaningful participation of women in conflict prevention, transformation, resolution, and sustainable peacebuilding processes. Under the current project “Accelerating Implementation of Women, Peace and Security Agenda in Georgia” (2020-2024) and in line with the United Nations Sustainable Development Cooperation Framework (UNSDCF) for 2021-2025, UN Women supports the Government of Georgia to develop and implement the National Action Plan for the Implementation of the UN Security Council resolutions on Women, Peace, and Security (UNSCR 1325 (2000) et al.) and to achieve the targets of nationalized Sustainable Development Goals (SDGs) 5 and 16. UN Women partners with the UK Conflict, Stability and Security Fund (CSSF), now Integrated Security Fund (ISF) and the Ministry of Defence of the UK Government to contribute to the enhancement of women’s meaningful participation in peace and security processes and to increase Georgian Government’s accountability to implement the WPS agenda (WPSA) in Georgia. The project on “Accelerating Implementation of the Women, Peace and Security Agenda in Georgia” funded by the UK Government is specifically tailored to respond to the needs and interests of internally displaced (IDP) and conflict-affected women and girls as well as government and civil society partners in Georgia and aims at the supporting the implementation of WPS agenda in Georgia. Namely, the project addresses the problems at the individual, community, institutional and policy levels and proposes activities that will contribute to the overarching goal/impact of the project to advance gender equality, achieve the full, equal, direct and meaningful participation of women in peace and security processes, as well as in crisis response and recovery, and support the social cohesion and sustainable peace in the country. The project commenced on November 16, 2020, and initially spanned 40 months, concluding on March 31, 2024. The total budget was £1,420,776.05, funded by the UK CSSF and UK MoD. Under a new agreement, the project was extended for an additional year, from April 8, 2024, to March 31, 2025, with an additional £467,350.00 provided by the UK Integrated Security Funds (Foreign, Commonwealth and Development Office - FCDO). Within the framework of the above-mentioned projects, UN Women works with security sector actors, including the Ministry of Defense, the Ministry of Internal Affairs, the State Security Service, the Office of National Security Council, and the Georgian Intelligence Service to mainstream gender into the Security Sector Reform process and its outcomes. Herewith, to promote the implementation on the WPSA and mainstream gender, UN Women cooperates with the Ministry of Foreign Affairs, the State Ministry for Reconciliation and Civic Equality, the Ministry of Internally Displaced Persons from the Occupied Territories, Labor, Health, and Social Affairs of Georgia and the Ministry of Regional Development and Infrastructure of Georgia, as well as closely works with the target municipalities to support the localization of the WPSA. UN Women also continues to support the capacity development of women mediators and peacebuilders, and internally displaced and conflict-affected women at grassroots to ensure their direct and meaningful participation in peace processes, as well as creates spaces for effective engagement of women peace activists with the participants of formal peace and incident prevention processes (namely, the Geneva International Discussions and the Incident Prevention and Response Mechanisms). One of UN Women’s top priorities for the 2020-2024 period is to provide support for the localization of the fourth National Action Plan for the Implementation of the UN Security Council Resolutions on Women, Peace, and Security (2022-2024). The localization process is achieved through fostering the active participation of women and grassroots organizations, internally displaced and conflict-affected women in local policy planning and budgeting processes, and the capacity building of the local governments to advance the WPSA implementation. In this respect, UN Women is targeting 17 municipalities in the regions of Kvemo Kartli, Shida Kartli, Imereti, Samegrelo-Zemo Svaneti and Racha-Lechkhumi and Kvemo Svaneti, including the villages that are adjacent to the Administrative Boundary Lines with Abkhazia, Georgia and Tskhinvali region/South Ossetia, Georgia. # Purpose and the Use of Evaluation Upon the project completion, as established in the Project Document, a mandatory external final evaluation is to be conducted by UN Women for accountability and learning purposes. This main purpose of the final evaluation is assessing the achievement of project results and performance of the above-described interventions. Findings of the final external evaluation will inform UN Women Georgia’s future work in the area of Women, Peace and Security. The external evaluation will further identify lessons learned, best practices and challenges of the project “Accelerating Implementation of the Women, Peace and Security Agenda in Georgia” and its extended phase and will greatly inform the development of the follow-up programmatic interventions. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for women’s empowerment in Georgia and to facilitate UN Women’s strategic reflection and learning for programming in the area. The information generated by the evaluation will be used by different stakeholders to: - Contribute to building of the evidence base on effective strategies for the implementation of WPSA in the country. - Facilitate strategic reflection, learning and further planning for programming in the areas of WPS. - Strengthen national stakeholders and structures with the aim to increase sustainability of the results beyond the project. Main evaluation users include UN Women Country Office in Georgia as well as the UK Government (project donor). Furthermore, national stakeholders – civil society partners, grassroots conflict affected and IDP women and targeted state and non-state agencies will be also closely involved in the evaluation process to increase ownership of findings, draw lessons learned and make greater use of this final evaluation results. # Evaluation Objectives, Criteria and Questions The specific evaluation objectives are as follows: - Analyze the relevance and coherence of the implementation strategy and approaches of the project. - Assess effectiveness and organizational efficiency in progressing towards the achievement of the project’s results as defined in the interventions. - Validate the project results in terms of achievements and/or weaknesses toward the outcome and outputs. - To assess how the project and its results relate and contribute to commitments and achievement of Sustainable Development Goals (SDGs) in Georgia - Determine the impact of the intervention with respect to gender equality and women’s empowerment. - Assess the sustainability of the results achieved by the project. - Document lessons learned, best practices, success stories and challenges to inform future work of UN Women and the UK Government (FCDO) in the areas of WPS. - Identify strategies for replication and up-scaling of the project’s best practices. - Provide actionable recommendations for future programmatic developments and maximize ownership by partners in the country covered by the project. The evaluation will address the criteria of Project Relevance, Coherence, Effectiveness, Efficiency, and Sustainability. More specifically, the evaluation will address the key evaluation questions: - Relevance: A) How does the project reflect and align with gender equality/WPS national strategic plans and normative frameworks as well as Georgia’s international obligations and commitments? B) Is the project design based on quality analysis, including gender and human rights-based analysis, risk assessments, socio-cultural and political analysis? C) Were the programmatic strategies appropriate to address the identified needs of beneficiaries? - Coherence: A) To what extent the project adheres to corporate strategic priorities of UN Women and UK around WPS? B) Is the project achieving synergies between the larger UN Women’s portfolios and the work of the UN Country Team? C) Is the project achieving synergies between UN Women and key national stakeholders including national governments and CSOs? D) How does the project design match with the complexity of national structures, systems and decision-making processes? - Effectiveness: A) What has been the progress made towards achievement of the expected outcomes and expected results? What are the results achieved? B) What are the reasons for the achievement or non-achievement of the project results? C) Does the project have effective monitoring mechanisms in place to measure progress towards results? D) What is the influence of the specific country context and circumstances on the achievement of results and operational effectiveness? F) How adaptable and rapidly does the project react to changing situations? G) Which methods and approaches have (haven’t) worked well and why? H) What are the good practices, and the obstacles or shortcomings encountered? How were they overcome? I) To what extent have capacities of relevant duty-bearers and rights-holders been strengthened? J) What -if any- types of innovative good practices have been introduced in the project for the meaningful participation and empowerment of IDP and conflict affected women and youth? - Efficiency: A) Have resources (financial, human, technical support, etc.) been allocated strategically to achieve the project outcomes? B) Have the outputs been delivered in a timely manner? C) To what extend were relevant stakeholders and actors included in the project planning and implementation? - Impact: A) What evidence exist that the project has delivered longer term results from processes through to benefits? Have any unintended results been delivered? B) Is there a potential measurable impact of the project intervention on the target group across all dimensions of the project? C)To what extent is the project changing the dynamics of power in relationships between different groups? D)To what extent is the project bringing about gender transformative changes that address the root causes of gender inequalities – including prevailing social norms, attitudes and behaviors, discrimination and social systems? - Sustainability A) How effectively has the project been able to contribute to the generation of national ownership of the project outputs? B) What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time after the project phase out? C) To what extent has the project identified strategic partners that could pick up on supporting continued government and non-governmental action when the project comes to an end? D) Do national/local institutions demonstrate leadership commitment and technical capacity to continue to replicate some project activities? E) To what extent have the project’s exit strategy been well planned and successful? F) To what extent has UN Women been able to promote replication of project successes? The questions outlined above are preliminary and are expected to be revised and refined by the evaluation team during the inception phase of the evaluation. # Scope of the Evaluation The final evaluation of the project is to be conducted externally by an international external consultant/evaluator in a team with one national consultant/assistant evaluator. It is planned to be carried out in Tbilisi, Shida Kartli and Samegrelo regions, and completed in 40 working days in the period of 1 December 2024 – 17 March 2025. The final evaluation will include all aspects of the project and will cover almost the full project implementation period, including the extension phase. # Evaluation Design, Process and Methods The evaluation methodology will be mixed (quantitative and qualitative research methods and analytical approaches) to account for complexity of gender relations and to ensure participatory and inclusive processes that are culturally appropriate. A theory of change approach will be followed, and the consultants are expected to reconstruct, validate, and identify the gaps in the project’s theories of change (for each of the Outcomes). The reconstructed theories of change should elaborate on following how the project has contributed to creating an enabling legislative, policy, institutional and economically enabling environment in line with internationally binding standards on gender-sensitive governance systems and women, peace, and security in Georgia. Assumptions should be tested and explain both the connections between early, intermediate, and long-term project outcomes and the expectations about how and why the project has brought them about. By reconstructing the Theories of Change evaluators are also expected to identify challenges and gaps in the implementation of the project on “Accelerating Implementation of Women, Peace and Security Agenda in Georgia” for future improvement. Hence an eventual next phase of the project will benefit from a refined and tested Theories of Change. Interviews and focus group discussions with all key stakeholders involved in the project implementation, including but not limited to project team, government partners, NGO partners, beneficiaries, etc. The evaluation team should develop a sampling frame (area and population represented, rationale for selection, mechanism of selection, limitations of the sample) and specify how it will address the diversity of stakeholders in the intervention. The evaluation team should take measures to ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights; for example, the limitations of the sample (representativeness) should be stated clearly, and the data should be triangulated (cross-checked against other sources) to help ensure robust results. The evaluation process is divided in four phases: 1) Preparation, mainly devoted to structuring the evaluation approach, establishing reference group, preparing the TOR, compiling project documentation, and recruitment of the evaluation team; 2) Conduct, which involves reconstruction of theory of change, organizing inception meetings, drafting inception report and finalization of evaluation methodology, data collection and analysis, including desk research and preparation of interviews and focus groups, preparation of field missions and visits to project sites (data collection in the field will be implemented by national consultant based on the clear and specific guidelines from the international consultant); 3) Reporting, focusing on presentation of preliminary findings, developing draft and final reports; and 4) Use and follow-up, which will entail the development of management response by UN Women team and follow-up to the implementation of the management response. The consultant will be responsible only for Conduct and Reporting phases: - Conduct phase: at the beginning of the consultancy, the consultant will be provided with key sources of information for an initial desk review. The online inception meetings will be conducted with WPS Program team. In this phase an inception report that will include the refined evaluation methodology including data collection plan and instruments will be delivered. The inception report will be validated and approved by UN Women. Based on the inception phase, the consultant will carry out further in-depth desk review. Data collection will be carried out jointly by the international and national consultant. Online or face-to-face interviews and focus group discussions with key stakeholders, as relevant, will take place. Field missions will be conducted by international and national consultant jointly in line with data collection plan and instruments developed by the international consultant, while international consultant can also interview major English-speaking project partners online. National consultant will provide summaries of interviews in English to the consultant in line with the pre-agreed format and the international consultant will carry out further analysis. - Reporting phase: The collected information will be analyzed, and final evaluation report will be delivered. A validation meeting will be organized where the consultant will validate the final report with UN Women and Evaluation Reference Group (ERG) and submit for approval by UN Women. UN Women’s Independent Evaluation Service (IES) has developed the GERAAS, which has adapted UNEG Standards for Evaluation in the UN System to guide evaluation managers and evaluators on what constitutes a ‘good quality’ report at UN Women. All evaluations in UN Women are annually assessed against the framework adopted in GERAAS and hence the consultant should be familiar with GERAAS quality standards. In addition, UN Women is an UN-SWAP reporting entity, and the consultant will take into consideration that all the evaluations in UN Women are annually assessed against the UN-SWAP Evaluation Performance Indicator and its related scorecard. T The evaluation will be conducted in accordance with UN Women evaluation guidelines and UNEG Norms and Standards for evaluation and the UNEG Code of Conduct for Evaluations in the UN System. # Stakeholders Participation and Evaluation Management Structure The evaluation will be a consultative, inclusive, and participatory process and will ensure the participation of stakeholders engaged in the implementation of the project. The evaluation will be human rights and gender responsible, and an Evaluation Reference Group (ERG) will be established. The Evaluation Reference Group is an integral part of the evaluation management structure and is constituted to facilitate the participation of relevant stakeholders in the design and scope of the evaluation, raising awareness of the different information needs, quality assurance throughout the process and in disseminating the evaluation results. The Evaluation Reference Group will be engaged throughout the process and will be composed of relevant representatives of state and non-state stakeholders. The ERG group will review the draft evaluation report and provide substantive feedback to ensure quality and completeness of the report and will participate in the inception and validation meeting of the final evaluation report. The UN Women Georgia Monitoring and Evaluation Focal Point will serve as the Evaluation Task Manager, who will be responsible for day-to-day management of the evaluation and ensure that the evaluation is conducted in accordance with the sister entities Evaluation Policies, United Nations Evaluation Group Ethical Guidelines and Code of Conduct for Evaluation in the United Nations system and other key relevant guidance documents. The evaluation process will be supported by the UN Women Europe and Central Asia Regional Evaluation Specialist. Coordination in the field including logistical support will be the responsibility of UN Women. Within six weeks upon completion of the evaluation, UN Women has the responsibility to prepare a management response that addresses the findings and recommendations to ensure future learning and inform implementation of relevant projects. This is a consultative/participatory final project evaluation with a strong learning component. The management of the evaluation will ensure that key stakeholders are consulted. The international consultant will lead the evaluation in close coordination with one (1) national consultant. Description of Responsibilities/ Scope of Work The international consultant evaluator will benefit from technical and operational support of UN Women Country Office in Georgia. In more specific terms, the national consultant will be providing support to the international consultant will be supported by the national evaluator and will be responsible for the following tasks: - To conduct inception meetings/interviews with WPS Program staff and elaborate and submit the detailed inception report which contains evaluation objectives and scope, desk review, description of evaluation methodology / methodological approach, data collection tools, data analysis methods, key informants/agencies, evaluation questions, performance criteria, issues to be studied, work plan and reporting requirements. It should include a clear evaluation matrix linking all these aspects. - To elaborate and finalize the data collection plan (outlining the roles of international and national consultants) and data collection tools (e.g. guides and questionnaires) individually designed for each respondent/group of respondents to be used during the interviews and focus-groups with the key informants/interviewees. - To conduct individual interviews and focus groups discussions with the relevant stakeholders online and face-to-face with the support and together with national consultant. - To analyze the data and reconstruct, validate, and identify the gaps in the project’s theory of change based on the research findings. - To prepare a Power Point Presentation and an outline on preliminary findings and present to ERG and reflect the feedback shared at this presentation in the final report. - To produce and submit the draft and final evaluation reports in English. Format of the final evaluation report shall include the following chapters: Executive Summary, Project description, Evaluation purpose, Evaluation methodology, Findings, Lessons learned, Recommendations and Annexes (including interview list - without identifying names for confidentiality, data collection instruments, key documents consulted, Terms of Reference). Deliverables - Detailed Inception Report, which contains evaluation objectives and scope, findings from inception meetings with all relevant stakeholders, initial desk review, description of evaluation methodology/methodological approach, data collection plan and tools, data analysis methods, key informants/agencies, evaluation questions, performance criteria, issues to be studied, work plan and reporting requirements. It should include a clear evaluation matrix linking all these aspects - by 20 December 2024 (10 working days, home-based) - Data collected through interviews and focus group discussions - by 7 February (10 working days, in Georgia or home-based –fieldwork will be carried out by international consultant and national consultant jointly in line with the agreed guidelines) - Data analyzed and Power Point Presentation on preliminary findings conducted to highlight key evaluation findings and conclusions, lessons learnt and recommendations - by 21 February 2025 (5 working days, in Georgia or home-based) - Draft and Final Evaluation report & Evaluation brief that reflects key findings, conclusions and recommendations and deployed methodology (indicative samples will be provided by UN Women) in English taking into consideration comments and feedback collected from the presentation of preliminary findings. The report shall include the following chapters: Executive Summary, Introduction and Background, Evaluation approach and methodology, Findings, Conclusions, Lessons learnt, Recommendations and relevant Annexes - by 10 March 2025 (14 working days, home based). The evaluation team has to submit the initial draft of the evaluation report to Evaluation Reference Group after 10 working days and use the additional 4 days to address ERG comments/feedback and resubmit the final version to the Evaluation Task Manager). - Evaluation brief that reflects key findings, conclusions and recommendations and deployed methodology (indicative samples will be provided by UN Women) – by 17 March 2025 (1 working day). Deliverables; Expected completion time (due day); Payment Schedule (optional). - Detailed Inception Report, which contains evaluation objectives and scope, findings from inception meetings with all relevant stakeholders, initial desk review, description of evaluation methodology/methodological approach, data collection plan and tools, data analysis methods, key informants/agencies, evaluation questions, performance criteria, issues to be studied, work plan and reporting requirements. It should include a clear evaluation matrix linking all these aspects.; By 20 January 2024. - Data collected through interviews and focus group discussions - by 7 February (10 working days, in Georgia or home-based –fieldwork will be carried out by international consultant and national consultant jointly in line with the agreed guidelines).; By 7 February 2025; February 2025. - Data analyzed and Power Point Presentation on preliminary findings conducted to highlight key evaluation findings and conclusions, lessons learnt and recommendations – by 21 February; By 21 February 2025. - Draft and Final Evaluation report & Evaluation brief that reflects key findings, conclusions and recommendations and deployed methodology (indicative samples will be provided by UN Women) in English taking into consideration comments and feedback collected from the presentation of preliminary findings. The report shall include the following chapters: Executive Summary, Introduction and Background, Evaluation approach and methodology, Findings, Conclusions, Lessons learnt, Recommendations and relevant Annexes - by 10 March 2025 (14 working days, home based). The evaluation team has to submit the initial draft of the evaluation report to Evaluation Reference Group after 10 working days and use the additional 4 days to address ERG comments/feedback and resubmit the final version to the Evaluation Task Manager).; By 10 March 2025. - Evaluation brief that reflects key findings, conclusions and recommendations and deployed methodology (indicative samples will be provided by UN Women) by 17 March 2025 (1 working day); By 17 March 2025; March 2025. Consultant’s Workplace and Official Travel This is a home-based consultancy. As part of this assignment, there will be a trip to Tbilisi [Duration of stay: 10 days] and maximum of 2 trips to the regions of Georgia: [location: Zugdidi and Gori] [Duration of stay: 10 days in Zugdidi, 5 days in Gori].

# III. Competencies

# Core Values: - Respect for Diversity - Integrity - Professionalism # Core Competencies: - Awareness and Sensitivity Regarding Gender Issues - Accountability - Creative Problem Solving - Effective Communication - Inclusive Collaboration - Stakeholder Engagement - Leading by Example # Please visit this link for more information on UN Women’s Core Values and Competencies: # https://www.unwomen.org/en/about-us/employment/application-process#_Values - FUNCTIONAL COMPETENCIES: Ability to think, analyze and articulate strategically on programme development and results-based management - Ability to facilitate meetings with different levels of stakeholders - Excellent drafting and writing skills to produce and present concise and analytical discussion papers - Knowledge in results-based programming in support of gender and human rights - Technical knowledge in monitoring and evaluation. Ethical Considerations UNEG Ethical Guidance should be applied to the selection of methods for the evaluation and throughout the evaluation process. The consultant will sign the “Evaluation Consultants Agreement Form – UNEG Code of Conduct for Evaluation in the UN System” prior to the initiation of the evaluation process.

# IV. Required Qualifications

Education and Certification: - Advanced (at least Master) degree in one or more following areas: social sciences, gender studies, political science, social policy, development studies or another related field. - A first-level university degree in combination with seven (7) additional years of qualifying experience may be accepted in lieu of the advanced university degree. Experience: - At least 5 (five) years of practical experience in conducting evaluations of strategies, policies, and projects, in lieu of advanced degree, or 7 (seven) years of similar experience in case of first level university degree - At least 5 (five) years of experience and knowledge on gender equality, gender mainstreaming, gender analysis and women’s empowerment, in lieu of advanced degree, or 7 (seven) years of similar experience in case of first level university degree. - At least 5 (five) years of experience/knowledge of gender equality and women’s empowerment issues in Georgia and/or in the region, in lieu of advanced degree, or 7 (seven) years of similar experience in case of first level university degree. - Excellent analytical, facilitation and communications skills and ability to negotiate amongst a wide range of stakeholders. - Proved knowledge of human rights issues, the human rights-based approach to programming, human rights analysis and related mandates within the UN system will be considered as an asset. Languages: - Fluency in English is required.

# V. How to Apply

- Personal CV - PHF11 (P11 can be downloaded from: https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/About%20Us/Employment/UN-Women-P11-Personal-History-Form.doc ) - A cover letter (maximum length: 1 page) - Managers may ask (ad hoc) for any other materials relevant to pre-assessing the relevance of their experience, such as reports, presentations, publications, campaigns, or other materials.

# TOR Annexes

- UNEG Code of Conduct for Evaluations

- UNEG Ethical Guidelines

- UNEG Norms for Evaluation in the UN System

- UNEG Standards for Evaluation in the UN System

- UNEG Guidance Integrating Human Rights and Gender in the UN System

- UN Women Evaluation Handbook

- UN SWAP Evaluation Performance Indicator and related Scorecard

- Evaluation Consultants Agreement Form

### Annex 8 Evaluation Team Bios

International expert: With background in education (Master of Science) and policy analysis, Marina Gurbo has more than 15 years of international experience in capacity development, monitoring and evaluation. Having worked in Georgia as a capacity building and evaluation expert since 2008 (for UNDP, OSCE, UN Women), the consultant has substantive knowledge of the political and socio-economic context of the country and in-depth understanding of issues related to gender equality, women’ empowerment and confidence building.

In 2013-2018, Marina Gurbo worked intensively with women’s organizations in Georgia, Armenia and Azerbaijan implementing projects in the areas of gender equality, peace and security, women’s economic empowerment and prevention of domestic violence (i.e., EU-UNDP Georgia project COBERM, Kvinna till Kvinna) and assisted them in programme development and strengthening of RBM, HRBA and Gender Equality approaches in M&E. Most relevant assignments include the final evaluation of the project “Women for Equality, Peace and Development” implemented by the UN Women CO Georgia and of the project ´´ Gender Advisory Councils - increasing women’s role in social changes of regions´´ funded by the multi-donor Fund for Gender Equality (FGE) and implemented by Culture-Humanitarian Fund Sukhumi (NGO). Ms Gurbo conducted the final evaluation of the Joint Action for Women’s Economic Empowerment (JAWE) project implemented by UN Women in Georgian in 2018-2020.

She is included into several rosters for consultants such as UN Women Independent Evaluation Office Roster, UNDP ExPress Roster and other. Her special area of expertise includes theory-based evaluation and she delivered training on theories of change and reconstructed and developed ToCs for projects and UNDAF. She was involved into evaluation of the Partnership Framework for Development Kazakhstan 2016-2020 and supported the UNCT in Ukraine (in 2016), Kazakhstan (in 2020), and in Moldova (2021-2022) in drafting new partnership frameworks. In addition to having a proven track of analytical and evaluation reports, the consultant has strong expertise in evaluation design and methodology, quantitative and qualitative data analysis skills and is proficient in use of participatory and gender-responsive methods and techniques. She speaks fluently four languages, among them English and Russian.

National Expert:  Dariko Bakhturidze is a Monitoring, Evaluation, and Learning (MEL) expert and Feminist Researcher with over a decade of experience in research and international development. Holding a Master's degree in Gender Studies, which brings a unique intersectional perspective to research design and impact assessment. As a MEL expert, Dariko Bakhturidze has designed and implemented comprehensive monitoring frameworks for multi-stakeholder projects across Eastern Europe and the South Caucasus region. The consultant’s expertise spans the full project cycle, from developing theory of change models and results frameworks to conducting baseline studies, midterm reviews, and final evaluations. Dariko Bakhturidze is particularly skilled in mixed methods approaches, combining rigorous quantitative analysis (holds a Bachelor’s degree in statistics) with in-depth qualitative insights to capture both measurable outcomes and rich contextual understanding. Over the past three years, consultant led research projects across Eastern Europe and the South Caucasus, examining societal resilience in the context of information interference from hostile actors (for the FCDO program).

Dariko Bakhturidze is a Certified ILO Participatory Gender Audit Facilitator. As a feminist researcher, she led numerous researches, assessments, and evaluations focusing on gender equality and social inclusion, specializing in areas such as gender-based violence, women's economic empowerment, and gender mainstreaming in policy development. Through various projects, consultant has collaborated with different international and local organizations such as UN Women, United Nations Development Programme (UNDP), Council of Europe, World Vision, Women in Europe for a Common Future (WECF), Heinrich Boell Foundation South Caucasus, Women's Fund in Georgia, etc.

The project builds on the results of the 2019-2020 UK CSSF-funded project “Strengthening Women’s Meaningful Participation in Peacebuilding and Gender Mainstreaming in the Security Sector in Georgia”

Geostat (National Statistics Office of Georgia). n.d. “Gender Statistics Portal.” http://gender.geostat.ge/gender/index.php  (see: Social Protection).

Rapid Gender Assessment of COVID-19 Situation in Georgia - 2 wave, at https://georgia.unwomen.org/en/digital-library/publications/2021/03/rapid-gender-assessment-of-covid-19-situation-in-georgia-2-wave

Ukrainian Refugees in Georgia Assessment Report, November 2022, UNHCR, World Vision.

According to OSCE Office for Democratic Institutions and Human Rights (ODIHIR): “the law is incompatible with international human rights standards and the country’s commitments. The law, which defines civil society and media outlets as “organizations pursuing the interests of a foreign power” only for receiving funding from abroad, falls short of the strict requirements laid down in international human rights law”. See ODHIR full legal analysis

Protests continue in Georgia after the ruling Georgian Dream party announced on 28 November 2024 that it was suspending EU accession talks until 2028. The political crisis caused by the rejection of the legitimacy of disputed results of the October 26 parliamentary elections, rejected by the opposition political forces, President Salome Zurabishvili, and a big part of the civil society who assess them as rigged, was exacerbated by this declared U-turn on EU membership by authorities.

Sustainable Development Report 2024, Georgia.  https://dashboards.sdgindex.org/static/profiles/pdfs/SDR-2024-georgia.pdf

European Commission, Opinion on the EU membership application by Georgia, memo (17 June 2022)

https://giwps.georgetown.edu/country/georgia/

UN Security Council Resolution #1325 Monitoring the localization Process in Georgia, Women’s information Center, 2021

The United Nations Security Council unanimously adopted a historic resolution, UN Security Council Resolution 2250 on Youth, The Youth, Peace and Security Agenda in 2015, recognizing young peoples’ positive role in international peace and security.

History of Localization of Women, Peace and Security Agenda in Georgia. Women's Information Center, 2023

Ibid

Thematic Report of the Parliament of Georgia on the Implementation of the Women, Peace and Security Agenda in Georgia, 2023

Monitoring Report of the 2022-2024 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security. Public Defender of Georgia, 2024

Ibid

The Geneva International Discussions were launched in Geneva, Switzerland, in October 2008, to address the consequences of the 2008 August war in Georgia. The decision on the formation of such a format was adopted according to the 12 August 2008 Ceasefire Agreement. From that period the Geneva discussions are held four times a year. Co-chaired by the Organization for Security and Co-operation in Europe, the European Union and the United Nations the Geneva process brings together representatives of Georgia, the Russian Federation, the United States and Abkhazia, Georgia and the Tskhinvali region/South Ossetia, Georgia. The Incident Prevention and Response Mechanism (IPRM) – both in Ossetian and Abkhazian direction - was created in February 2009 because of the Geneva Discussions that followed the 2008 conflict in Georgia. The IPRM meetings are an opportunity to discuss such issues, as the identification of potential risks, the follow-up of incidents and the exchange of information, as well as problems affecting the communities daily. Besides, the hotline operates within the framework of this mechanism. Its main goal is the rapid response on concrete and specific incidents. The Incident Prevention and Response Mechanism meetings are co-facilitated by the OSCE and the European Union Monitoring Mission in Georgia (EUMM)

Women, Peace and Security Agenda in Georgia, Brief, UN Women

For the purpose of this report, gender is defined as socially constructed roles between men and women which are dynamic and change with time, see the Glossary at https://somalia.unfpa.org/sites/default/files/pub-pdf/Gender%20Report.pdf

https://www.un.org/en/content/disabilitystrategy/

Committee on the Elimination of Discrimination against Women, concluding observations on the sixth periodic report of Georgia, CEDAW/C/GEO/CO/6, 2 March 2023

The following reports and studies were analysed by the evaluation team: Women’s Information Center, Independent monitoring of the 2016-2017 Action Plan on Implementation of UN Security Council Resolution 1325 on Women, Peace and Security (2017); Women’s Information Center, UN Security Council Resolution 1325 Localization Process Monitoring in Georgia (Global Network of Women Peacebuilders, 2021);

Women, ANOVA (2023) Views and Attitudes of Internally Displaced Women on Conflict Transformation, Reconciliation and Peace Building in Georgia

EUMM (2021). Gender Analysis of the Ergneti Incident Prevention and Response Mechanism (IPRM)

Ibid

UN Women (4 December 2024). Inclusivity, Accountability, Resilience.  Position of Women Peace Activists and Women-led Organizations in Europe and Central Asia: Insights for the 2025 Peacebuilding Architecture Review.

UN Women, ANOVA (2023). Study on the Views and Attitudes of IDP Women towards Conflict Transformation, Reconciliation and Peacebuilding.

Women, Peace and Security Agenda in Georgia, Brief, UN Women

In 2023, the Parliament additionally approved the State Concept of women's economic empowerment; National Human Rights Protection Strategy of Georgia for 2022-2030; 2024-2026 Human Rights Protection Action Plan of Georgia. These documents refer to the WPS agenda.

Monitoring Report of the 2022-2024 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security. Public Defender of Georgia, 2024

DCAF (25 November 2024). Changing mindsets for gender equal security institutions: Georgia case study, available at https://www.dcaf.ch/changing-mindsets-gender-equal-security-institutions-georgia-case-study

The data was provided by the Ministry of Foreign Affairs (a brief letter)

The data was provided by the Ministry of Foreign Affairs (a brief letter)

Women, Peace and Security Agenda in Georgia, Brief, UN Women

The non-official data provided by the project team as reported in the EPR system

The UK WPS NAP 2023-2027 priorities include : Strategic Objective 1: Decision-making – increasing women’s meaningful participation, leadership and representation in decision-making processes; Strategic Objective 3: Humanitarian and crisis response – supporting the needs of women and girls in crises and ensuring they can participate and lead in responses; Strategic Objective 4: Security and justice – increasing the accountability of security actors, institutions and systems to women and girls and ensuring they are responsive to their rights and needs

The summary from discussions at WPS regional dialogue event in Moldova, 5-6 September 2024 organized with the support of the project

UN WOMEN (2023). Monitoring of Human Security: Gender-Responsive Monitoring For The Civil Society. Manual for Civil Society Organizations

The number of direct beneficiaries is calculated based on the ratio of conflict-affected and internally displaced communities that the project aims to reach through its capacity development and awareness-raising interventions.

Gender and patriarchal stereotypes are deeply rooted in rural and conflict-affected areas as well as the breakaway regions. As a consequence, while women often play an active role in informal track 2 processes and civil society engagement, they are not widely present and influential at the negotiating table and relevant decision-making. The number of women participating and their influence on the peace process is below the WPS standards. When numbers hit the critical mass of 30 per cent, this did not appear to be based on a systematic mainstreaming policy.

2019 – 17 per cent (2 women out of 12); 2018 – 40 per cent (4 women out of 10); 2017 – 40 per cent (4 women out of 10).

Previous years’ data unavailable publicly.

Previous years’ data unavailable publicly.

2019 – 20-30 per cent; 2018 – 33 per cent; 2017 – 33 per cent.

Previous years’ data unavailable publicly.

Previous years’ data unavailable publicly.

This indicator allows to track if and how Women, Peace and Security issues are addressed through the formal peace process (GID) and what are the actual outcomes of different participation /gender mainstreaming efforts.

In spite of some attempts to introduce WPS and gender mainstreaming in the GID process, WPS agenda was never included in the actual discussions. During the 2019-2020 CSSF-supported UN Women project on WPS, UN Women conducted a study on women’s meaningful participation in peace processes in Georgia and based on its findings and recommendations advocated with the GID Co-Chairs to advance the WPS agenda in the process.

Namely, EUMM released Gender Analysis of the Ergneti IPRM 2016-2020; UN Department of Political and Peacebuilding Affairs (DPPA) Gender Analysis of the GID upcoming in 2022.

This indicator provides evidence on the extent to which women are included in the people-to-people dialogue and allows analysis on the impact of women and their initiatives on peace processes. In 2019 SMR established the Peace Fund for Better Future (PFBF) operational as of 2020, which is a non-profit (non-commercial) legal entity dedicated to support peaceful conflict transformation and peacebuilding process and implementation of the peace initiative “A Step to a Better Future” including through improvement of the socio-economic situation of conflict affected population on both sides of the ABL, and facilitation of dialogue, cooperation, reconciliation and confidence building between divided communities.

During 2018, 66 projects were approved, out of which 10 projects were related to women’s issues or were implemented by women’s organizations (15 per cent).

In 2019, 64 projects were approved, out of which 11 projects were related to women’s issues or were implemented by women’s organizations (17 per cent).

In 2020, 36 projects were approved, out of which 4 projects were related to women’s issues or were implemented by women’s organizations (11 per cent).

During 2018-2020, in total 166 projects were approved, out of which 25 projects were related to women’s issues or were implemented by women’s organizations (15 per cent).

Source: PDO monitoring report of the WPS NAP (2021); CSO independent monitoring report of the WPS NAP (2021).

Reports from the Open Days feed into the UN Secretary-General’s reports on WPS to the UN Security Council. UN Women in New York serves as Secretariat for the Secretary-General’s Report.

This indicator provides evidence of the commitment of the government to WPSA and measures if and how key stakeholders identify priorities, determine responsibilities, allocate resources, and initiate strategic actions within a defined timeframe. This national-level strategy document outlines government’s approach and course of action around WPSA, outlining objectives and activities both on a domestic and international level to secure the human rights of women and girls in conflict settings; prevent armed conflict and violence, including against women and girls; and ensures the meaningful participation of women in peace and security. Therefore, the indicator serves to measure the commitment, transparency of the government, as well as coherence and coordination between the government agencies, increased ownership, and awareness on WPSA, all contributing to the increased accountability of the government to fully implement the WPSA.

Georgia adopted its first NAP in 2011. The 3rd NAP covering 2018 to 2020 was expiring at the project start. While the quality of successive NAP cycles improved in relation to measurable results, monitoring and evaluation, its costing and budgeting remains a challenge. Current 2018-2020 NAP does not have allocated budget for the implementation of the activities. The 2020 interim monitoring report of the Public Defender Office on NAP implementation found that gender mainstreaming progressed only in some State institutions and that coordination gaps between central, regional and local government that IDP and conflict-affected women’s access to information and inclusion, thus resulting in uneven NAP implementation. However, forth cycle of the NAP will be accompanied by the budget, due to the changes approved by the Government Decree 629 on the Approval of the Rules for Drafting, Monitoring and Evaluation of Policy Documents.

UNEG Ethical Guidelines: http://uneval.org/papersandpubs/documentdetail.jsp?doc_id=102; The UNEG Code of Conduct for Evaluation:

http://uneval.org/papersandpubs/documentdetail.jsp?doc_id=100

http://www.unevaluation.org/document/detail/100

http://www.unevaluation.org/document/detail/102

http://www.uneval.org/document/detail/21

http://www.uneval.org/document/detail/22

http://www.uneval.org/document/detail/1616

http://genderevaluation.unwomen.org/en/evaluation-handbook

http://www.uneval.org/document/detail/1452

The report was uploaded at   http://gate.unwomen.org/Evaluation/Details?EvaluationId=4886 .  Quality rating - Very Good