Socially Responsible Women-Run School Canteens Project: Report of the Final Evaluation

Amer Madi

Safa Abdel Rahman

Shawkat Sarsour

August 2012

First Draft

Index

Summary	3

1. Background	8

2.  Methodology	10

3. Evaluation Findings	12

3.1. Developments in the design of Phase II of the Programme and coherence of intervention logic	12

3.2. Programme start-up and expansion	15

3.3. Programme management, monitoring and reporting	18

3.4. Programme achievements and results	24

3.4.1. Outcome 1: to improve nutritional status among Palestinian children in targeted schools	24

3.4.2. Outcome 2: to achieve sustainable income for targeted women’s centers	28

3.4.3. Outcome 3: Women’s community involvement	31

3.5. Impact	31

3.5.1. At the level of participating schools, students and the community	31

3.5.2. At the level of canteen workers and their organisations	32

4. Conclusions and Recommendations	32

4.1. Conclusions	32

4.2. Recommendations	34

5. Annexes	37

5.1. Evaluation Terms of Reference	38

5.2. List of People Met	39

5.3. Information on the evaluation team consultants	44

# Summary

In 2008, the Government of Norway through its Representative Office to the Palestinian Authority (NRO)  extended support to UN Women to implement a one-year pilot project to promote school children’s health status and rural women’s economic security.  This pilot project, which was implemented during the 2008/2009 academic year, focused on building the capacity of 11 women organisations in the West Bank to run school canteens, while improving the quality, hygiene, and nutritional value of foods offered to students in these canteens.   At the end of 2008/2009 academic year, the project was subject to an external evaluation which recommended its continuation in a new phase.

In October 2009, NRO committed NOK 15 million (approximately US$ 2.25 million) for an expanded three-year programme which built on the success of the pilot project.  This was done on the basis of a Programme document titled “Development of Community-Based Business Model for Rural Women: Socially Responsible Development through Women-run School Canteens” which had been developed by UN WOMEN and MoE in parallel to the evaluation of the pilot phase.  The programme (hereinafter, interchangeably WRSCP) aimed at contributing to improving the health of school children and the livelihoods women in rural and marginalised communities in the West Bank through the creation of a sustainable business model of socially-responsible women-run school canteens that can be up-scaled at a national level.  Over the three academic years of its planned lifetime, the WRSCP envisaged, inter alia, building the physical and technical capacities of 28 women organisations to effectively run school canteens and food production enterprises; upgrading the physical infrastructure and facilities in some 230 school canteens to be conducive for the production and promotion of healthy foods and providing gradually-declining subsidies for the targeted women organisations to lease these canteens; and, as a result, generating sustainable employment opportunities for some 420 women.

More specifically, the WRSCP aspired to achieve the following outcomes:

- Outcome 1: To improve the nutritional status of Palestinian children in the targeted schools;

- Outcome 2: To achieve sustainable income for targeted women centers;

- Outcome 3: To increase community acceptance of women’s involvement in non-domestic economic activities;

An external evaluation of the programme was carried out during May-June 2012 by external consultants Amer Madi, Safa’ Abdelrahman and Shawkat Sarsour.  Methodology comprised initial documentary review, on which an inception report was based,  and meetings with a large number of programme stakeholders.

Conclusions

The overall impression of the evaluation team is positive, though the team acknowledges that a number of important activities planned remain to be implemnted.   The main justification for this positive impression is the fact that the programme has not only managed to scale-up and benefit from the lessons learned from the pilot phase on which basis it was designed, but it also succeeded in confirming that the socially responsible women-run school canteens can be viable and effective for both the advancement of gender equality and economic security and promoting school health policies.   In doing this,  the programme has shown that it remains relevant to the context in which it which operates.

Despite its unsmooth start-up and expansion which have resulted from insufficient planning and delays in implementation of activities, the programme was largely successful in delivering most of its planned outcomes and results.

The programme met its target of improving the variety and quality of affordable, healthy and nutritious foods available through school canteens by taking measures to ensure that diversified and nutritious foods are available in targeted school canteens.   It also met expectations in terms of improving students’ knowledge of nutrition and healthy eating habits, but this was mainly in the 159 schools it targeted in the first two years of operation as relevant activities have not yet been implemented in the schools that were targeted in the thir year.  Mixed results, however, were achieved in relation to the expectation of improving school canteens infrastructure due to the confluence of limited funding, uneven distribution of funds, and delays in implementation.    In some schools, installed canteen equipment was not fully utilised by women’s centers.

With regard to its intention of achieving sustainable income for targeted women’s centers, the programme was quite successful.  Of the 32 women centers that were running canteens during the programme’s last year of operations, 26 made profits and are able to pay their respective school canteens leases for the next year fully on their own, while the remaining 6 made profits but need further support to do the same. Sixteen centers (46% of the total targeted) were able to generate profits in-excess of their business reinvestment needs for next year (US$ 1,000-9,500) and are thus able to cover a good proportion of their non-canteen related expenditures.  This programme’s capacity building approach played a significant role in this achievement as it effectively built women’s centers capacities at various levels using proven methodologies and approaches.

Commendable achievements were made in relation to engaging women in school activities, though these did not live up expectations.  This was main because involvement was not systematic across the programme, with women’s centers mostly being involved as catering proveders than as partners.  However, it is acknowledged that the programme has paved the way for greater and more equal participation of women in their communities.

In terms of its impact at the level of the participating schools, students and community, the programme can be said to have achieved the following:

- contributed to improving overall quality of school environment in 159 schools, thereby contributing –albeit marginally- to improving the quality of education in these schools.

- reducing the burden of canteen supervision and conflict management, hence allowing school adminstrators to devote their attention to more substantive issues.

- providing opportunities for schools to complement and support student learning by reinforcing teachers’ messages about food; positively influencing students eating habits.

- improving the economic access to a more diversified foods for 85,000 students although unsystematically (i.e. poor students’ access to food from canteens did not improve significantly);

- improving food safety and hygiene for some 85,00 students through the introduction of good practices in food preparation, handling and storage in canteen operations.

The programme’s impact on the targeted women’s centers and canteen workers has also been quite impressive.   It has enabled 32 women’s centers to establish –for the first time- a sustainable enterprise, capable of meeting their constituency’s practical needs for culturally-accepted employment opportunities and strategically contributing to the sustainability of their organisation.  As a resul, women’s centers  feel more capable of representing their constituency’s interest at the local level.

The programme has generated employment opportunities for 416 poor women, many of whom working for the first time in their lives. On average these women made US$ 150 per month for an average period of 9 months per year.  While relatively low in both aggregate and hourly wage standards, the income women earned through the programme was in line with market wages hence only helped them realize better social status both at home and within their communities.

Recommendations

R1.  NRO should grant UN Women’s a no-cost contract extension a period of three months to allow for the implementation of delayed planned infrastructure development and school activities.  In the meantime, UN Women in closes collaboration with MoE and MAAN should develop a new project document for a third phase of the programme, utilising -to the extent possible- the findings and recommendations of this evaluation.

R2. In both the design and implementation of programme’s third phase, UN Women should demonstrate stronger needs-based planning and budgeting processes and mechanisms.  It also should ensure greater and more active participation of the Boards of the partner women’s organisations in the planning, implementation, monitoring and evaluation of the programme.  Hence, it is strongly recommended that the first three months of the programme’s new phase be dedicated  to school and women’s cenetrs’ selection and infrastructure needs assessments.  This would allow for the capacity building and infrastructure development activities to be implemented ahead of the beginning of the school year.   At the design and implementation stage, the new programme should plan for and allocate properly resourcing the needs assessment processes.

R3.  MoE and UN Women should develop a standard describing what a women-run school canteen should look like, and what facilities it should have.  For the purposes of initial programme planning, an average of US$ 12,000 could be budgeted for canteen equipment and infrastructure development, with contingencies for adjustment during implementation.  This initial figure should be revised upwards or downwards according to needs. Where needed, an additional amount should budgeted for bathrooms for women workers.  Actual allocation, however, should be based on needs.

R4. UN Women and MoE should agree on a revised formulation of the programme’s intervention logic and logframe.  This should be done with the view of ensuring accountability among the various partners for results.  For this purpose, it is extremely important to rethink the goal and outcomes of the programme, preferably giving more focus to women’s economic security and income (as opposed to women’s centers profits), attitudinal changes among students vis-à-vis eating habits, and community mobilisation in support of canteen operations.

R4. In conjunction with R3, MoE and UN Women should also set clearly what categories of they expect women’s centers to have on offer in the schools’ canteens on a daily and a weekly basis.  While this should be kept generic, it needs give sufficient guidance to women’s centers on what is expected of them.  The programme should devise a mechanism to monitor partner centers’ adherence to this standard, which should be the basis for an annual review of the centers’ performance in schools.

R5. The current phase’s management structure should be retained with the following additions:

- UN Women Programme Officer at UN Women (@50%)

- UN Women M&E and Reporting Officer (@100%)

- UN Women Business Development Advisor (retainer basis)

- MoE Programme Manager (@50%)

- MoE Filed Coordinator (100%)

R6. Given the fact that UN Women operates under the NEX modality, a significant level of implementation responsibility should be transferred to MAAN.  However, MAAN should ensure the allocation of highly qualified staff with gender and enterprise development expertises to the programme.  These staff should be fully dedicated the programme.

R7.  The programme’s committees established under the current phase should be activated and given more support and authority to be able to discharge their resposnibilities more effectively.  For this purpose, it is strongly recommended that the Programme Advisor at NRO is brought onto the PSC as member, along with the Deputy Ministry of Education and the MoE’s General Directors of Buildings and Finance and Adminstration.

R8.  The PSC should meet at least once every two months or when necessary.  It should keep a detailed record of its meetings and decisions in both English and Arabic.   Once signed by members, PSC meeting minutes should be widely circulated to programme partners.

R9. The PSC members, particularly UN Women’s Head of Office and MoE’s General Director of School Health, are strongly advised to organise joint field visits to schools and women’s centers.  This will not only have a positive effect at level of partners in the field, but it will also provide some context to the issues that get discussed at PSC meetings.

R11. In planning for and implementing capacity building:

- ensure timely provision of training;

- give greater emphasis to on-the-job coaching and training (as opposed to in-class training) in the areas of financial management, costing and cost control, marketing and communications;

- ensure that training methods follow learner-cantered approaches, including the preparation of customized training materials for the trainees to take away;

- make provisions for providing training on gender, particularly for programme field staff training;

- continue with the practice introduced in the last year of the project of integrating MoE staff involved in the programme in the capacity building programme both as trainers and trainees;

- give greater emphasis to documentation and dissemination of good business practices through monthly or quarterly newsletters

R12. The establishment of food production units at women’s centers has proven effective under the WRSCP and should be extended in the new phase.  To the extent possible, however, the establishment of food production units should be linked to the business model that the respective center will follow.  Hence, a clearer verification of infrastructure development and equipment needs should be ensured by the programme.  For initial planning purposes, a US$ 8,000 should be allocated for unit establishment and upgrading.  However, actual allocations should be based on both need and business model to be promoted.

R13. During the implementation of the next phase of the programme, UN Women and MoE should collaborate to commission a research to assess the financial performance of all canteen enterprises and document good business practices of partner women’s centers.  This research, which should also examine the financial conditions for the beneficiary schools, should be the basis for discussions between MoE and UN Women regarding adjustments in canteen lease fees.

R15. UN Women should plan for exit within a maximum of four years from the WRSCP, and plan well for its scaling-up.

# 1. Background

In 2008, the Government of Norway through its Representative Office to the Palestinian Authority (NRO)  extended support to a one-year pilot project that was jointly designed by the United Nations Entity for Gender Equality and the Empowerment of Women (UN WOMEN) and the Palestinian Ministry of Education (MoE) to promote school children’s health status and rural women’s economic security.  This pilot project, which was implemented during the 2008/2009 academic year, focused on building the capacity of 11 women organisations in the West Bank to run school canteens, while improving the quality, hygiene, and nutritional value of foods offered to students in these canteens.   At the end of 2008/2009 academic year, the project was subject to an external evaluation which was quite favourable of the achievements that the programme had accomplished in relatively short period of time, and consequently recommended NRO to extend its support to the project in a new phase.

In October 2009, NRO committed NOK 15 million (approximately US$ 2.25 million) in support to UN WOMEN for an expanded three-year programme which built on the success of the pilot project.  This was done on the basis of a Programme document titled “Development of Community-Based Business Model for Rural Women: Socially Responsible Development through Women-run School Canteens” which had been developed by UN WOMEN and MoE in parallel to the evaluation of the pilot phase.  The programme (hereinafter, interchangeably WRSCP) aimed at contributing to improving the health of school children and the livelihoods women in rural and marginalised communities in the West Bank through the creation of a sustainable business model of socially-responsible women-run school canteens that can be up-scaled at a national level.  The general expectation was that the WRSCP would “fine tune a business model that can balance the requirements for national-level up-scaling  with significant income for women employed by the [women’s organisations run] enterprises and a significant profit-margin for the women’s center.”

Over the three academic years of its planned lifetime, the WRSCP envisaged, inter alia, building the physical and technical capacities of 28 women organisations to effectively run school canteens and food production enterprises; upgrading the physical infrastructure and facilities in some 230 school canteens to be conducive for the production and promotion of healthy foods and providing gradually-declining subsidies for the targeted women organisations to lease these canteens; and, as a result, generating sustainable employment opportunities for some 420 women.

This was to be done through an expansion strategy whereby the programme targets the 61 schools and 6 women centers that had been involved in the pilot phase, and in parallel expand to target 50 additional schools and 5 new women centers in the first year. During the second year, the programme would continue providing support to the women centers and schools  that were targeted in the programme’s first year, adding 50 new schools and 5 women centers.  In the third year, it would continue supporting the schools and women centers that were targeted in the second year of the programme, adding the final batch of 50 schools and women centers. Support would include grants to schools for canteen infrastructure development and student activities over two years, and lease subsidies and capacity building for women centers.

More specifically, the WRSCP aspired to achieve the following outcomes:

- Outcome 1: To improve the nutritional status of Palestinian children in the targeted schools:  Through establishing a business model that ensures improving the quality and nutritional value of foods available in the targeted schools, the WRSCP envisaged reducing micronutrient deficiencies in foods available to students in the canteens of the targeted schools, and reducing short-term hunger and improving educational attainment among students.

- Outcome 2: To achieve sustainable income for targeted women centers: This outcome  was to be realized through building the managerial, technical and physical capacity of targeted women centers through training, coaching and food-production related infrastructure development, combined with providing a subsidised monopoly of these centers over the school canteens in the targets schools for a period of three years to enable them to build the financial and human capital necessary to effectively run the school canteens after the end of the programme’s support.

- Outcome 3: To increase community acceptance of women’s involvement in non-domestic economic activities: By enhancing women’s participation and involvement in school activities, in addition to increasing income for households, community’s acceptance of women’s involvement in non-domestic economic activities would be enhanced and underlying inequalities in power and resources which constrain women’s aspirations will be reduced.  Hence, the programme would go beyond technical and management skills to also focus on building women’s community mobilization skills (mobilizing by doing) so that their work expands beyond the domestic sphere and even the schools.  This will be achieved by creating community committees to support the project, conducting orientation workshops for the principals of the participating schools, and conducting gender awareness sessions with the parents.  In exchange for the grant to be provided to women centers at the beginning of the project, women centers would be organizing community events/initiatives at the school level; including open days for school children, summer camps, food festivals…etc. These initiatives were expected to increase the acceptance and support from schools to women centers and enhance community ownership of the project.  This increased exposure of the women's centers within their communities would encourage other women to join the center, which in turn will increase the centers' human and social capital.

The Programme Document’s logical framework included a different formulation of Outcome 1 above, namely: “Enhanced Partnership with MoE targeted directorates and schools to involve and support women centers and [community based organisations (CBOs)] in running school canteens.”  This outcome would be achieved through building the skills and knowledge of MoE staff and students to engage in activities promoting the healthy eating habits in support of women’s centers canteen enterprises, upgrading of canteens’ infrastructure in targeted schools, developing the canteens’ food menus to address nutrition deficiencies and identifying chronically poor student.

The formulations do not contradict each other; though, the first formulation is the one that appears in the Cost Sharing Agreement between NRO and UN Women.  The evaluation has taken both formulations into account, however.

The objectives of the evaluation itself were set out as:

- Assess to what extent the programme has fully implemented its activities, delivered outputs and attained the outcome specifically to measure the development results, gender equality, women’s empowerment and women’s human rights;

- Asses the partnership established between duty bearers and rights holders to ensure timely and effective response to improved livelihoods among women and improving health and nutrition of school children in line with national objectives and the Millennium Development Goals (MDGs).

- Measure the output, outcome, and/or impact of the programme on:

  - The nutritional status of students in the targeted schools and its impact on student concentration levels in the classroom;

  - Change in student health nutritional behavior;

  - Increase in community participation;

  - Changes in the school canteen infrastructure

- Provide analysis of efficiency of programme management and provision of recommendations for management of future programmes;

- Measure the longer term sustainability of the programme(decentralization, mobilization, networking and flexibility in responding to the women’s needs);

- Produce substantive evidence based knowledge by identifying best practices and lessons learned that could be useful for future programmes and development projects.

The 2009 evaluation of the pilot project have been a significant reference point.

# 2.  Methodology

The evaluation was conducted by Amer Madi (team leader) and Safa Abdel Rahman, with additional quality control provided by Shawkat Sarsour.  An initial review of key documentation, undertaken in May 2011, was the basis for an inception report with detailed plans for the review.  These included the development of questionnaires and interview guidelines for various stakeholders and beneficiaries, soliciting their perceptions of the management of the programme and its effectiveness and impact, in addition in-field observations guidelines.  The evaluation focused primarily on the current phase of the programme and the implementation of the Cost-Sharing Agreement between UN Women and NRO running from October 2009.

The field work (6 May – 28 June 2012) included initial meetings with UN Women discuss the evaluation methodology and work plan, further meetings with individual UN Women and NRO Programme Advisor, and in-depth interviews with the following stakeholders and key informants:

- UN Women’s staff involved in the project implementation; including UN Women Country Representative, Programme Analysts, WRSCP Project Assistant and Field Coordinators.

- MoE officials and senior staff engaged in project implementation at the Ministry’s Ramallah headquarters, including MoE’s field staff.

- All MoE’s staff engaged in the project implementation in the 14 education districts targeted by the programme;

- UN Women’s implementing partner’s staff (MAAN Development Center staff) and trainers;

- Board members and canteen staff of 23 (out of 35) women centers targeted by the programme;

- School administrators, teachers and students (127)  in a judgment sample of  33 (out of 209) beneficiary schools;

Interviews with women organisations and school administrators included site observations wherein the evaluation team visited school canteens and kitchens where snacks are prepared by women organisations and documented the status of these facilities using a ‘Field Visit Protocol’ to guide and make consistent the data collection process amongst the different team members visiting different areas and meeting different people at different times.

The evaluators also organised two central workshops with MoE and UN Women field staff.  These workshops focused primarily on identifying programme achievements, weaknesses and challenges, as well as identifying general recommendations for the future.

Preliminary findings were presented to and discussed with NRO, UN Women and MoE at a round table meeting on July  18, 2012, and draft report reflecting comments on the findings from this meeting was submitted on August 19th.   This final draft –which addresses comments received from UN Women, MoE and NRO on September 4, 2012 - was submitted on September 5, 2012.

# 3. Evaluation Findings

## 3.1. Developments in the design of Phase II of the Programme and coherence of intervention logic

The WRSCP was designed on the basis of the an internal review of the pilot project  that was implemented during the 2008/2009 academic year.  The internal review was organised in June 2009 with the participation of 30 representatives of all stakeholders: educational directorates, women centers, UNIFEM, MoE (school health department) and the implementing agency of the pilot phase (Juzoor). The review involved a one-day workshop that discussed projects strengths and weaknesses and formulated recommendations for future programming, which were refined and reflected in the Project Document for the three-year WRSCP.  Overall, WRSCP design as reflected in the Project Document prepared by UN Women and MoE exhibits significant improvements over the pilot phase, and commendably moves the programme in the direction of expansion and scaling-up.  The most notable improvements that were introduced in the second phase were: an increased focus on building a sustainable business model for socially responsible women-run school canteens; a more strategic and better resourced capacity building approach that responds to the actual needs of women centers and targeted schools; a significantly clearer partnership exit strategy (Box 1); a greater attention to strengthening the relationship between MoE and women centers as a prerequisite for sustainability; and a stronger emphasis on monitoring of operations of women’s centers through allocating human resources at the field level for this purpose.

Box 1: WRSCP Partnership and Exit Strategy

Each academic year, private business owners submit competitive bids to MoE to lease and individual school canteens. Being widely coveted by traders and local businessmen, bids for school canteens are usually very competitive, with the highest bidder usually awarded. Schools hold an interest in receiving high bids for leasing their canteens as the income they receive from this lease constitutes -for many of them, particularly the small schools- a significant part of their annual budgets. With limited access to financial resources, women centers and entrepreneurs are excluded de-facto from the bidding process. Within the framework of its School Nutrition Policy which prioritises leasing school canteens to women centers as opposed to individuals and in close collaboration with UN Women, MoE agreed to suspend the bidding process for canteens in the targeted schools and directly contract the targeted women centers to run school canteens against a lease equivalent to the average lease paid by private individuals during the three years preceding the programme. As part of its contribution to the WRSCP, MoE has also agreed to provide a discount of 30%. The WRSCP would support the women centers in paying the discounted lease fees for the first year by providing a 100% subsidy. In the second year, support would be limited to 30% subsidy, so that the women center would be able to fully cover the canteen lease fees in the preceding years through profits they generate from canteen operations. The subsidy acts as an incentive for the women centers to take on the canteens as an enterprise and helps them make sufficient savings for the next year and to remain financially strong.

In putting the development of a business model for women-run school canteens at the heart of the programme design in its second phase –which is a case in point example of a better context analysis, the WRSCP transcended the largely humanitarian nature of the pilot phase and set a higher standard of commitment for tangible results.  This has mainly been driven by the UN Women’s desire to demonstrate that the lower-than-expected results achieved in the pilot phase insofar as the sustainability of women run canteens can indeed be significantly improved with a more robust approach to capacity building and managerial follow-up.  As we shall examine later, however, the focus on sustainability and profitability of women centers’ canteen operations during implementation was –at times- too heavily emphasised at the expense of other programme results.

The intervention logic and results chain of the WRSPC as depicted in the programme’s logical framework were also improved. Greater emphasis was given to strengthening partnerships, and a specific outcome was formulated for this purpose.  This was in conjunction with UN Women and MoE’s desire to place building relationships between MoE and Women centers at the core of the project design.  The programme’s performance indicators were also reformulated to focus on more measurable results than those identified in the pilot phase.   Despite this, the programme’s intervention logic as depicted in the programme’s logical framework continued to have a number of important weaknesses, most of which were identified in the report of the evaluation of pilot project.  These weaknesses –which will be discussed later in the report- made monitoring and reporting on project results somewhat unsystematic.

In terms of its relevance to its operational context, the evaluation found WRSCP to be highly relevant to the policies and strategies of all partner organisations as well as to the strategic and practical needs of women beneficiaries and their organisations.  The programme directly meets Norway’s priorities in the areas of women’s economic and political participation, as identified in the Government of Norway’s Action Plan for Women’s Rights and Gender Equality in Development Cooperation.  Through its indirect focus on improving the quality of education through allocating resources to improving school environment and facilities, the programme also complements Norway’s support to other programmes that support the development of the Palestinian education system.  Morover, it complements Norway’s support to Palestinian rights-based organisations’ programmes in the areas of human and women’s rights, particularly those implemented by Juzoor Foundation for Health and Social Development, Association of Women Committees for Social Work-Palestine, and Tamer Institute for Community Education.

The WRSCP is also directly in tune with the Palestinian education sector policies and priorities as identified in the Education Sector Development Plan 2008-2012 (ESDP), and MoE’s School Nutrition Policy.  It particularly responds to ESDP’s  goal of improving student services under the plan’s quality improvement goal (Goal 2, Result 4), as well as MoE’s following school health related policies of: shifting towards providing appropriate health education; adopting the system of hygienic supervision at schools; facilitating the usage of school facilities to practice hygienic and environmental activities; rehabilitation of the school environment and sanitary facilities at school; and supporting/encouraging teachers in charge of the follow up of school activities.

Advancing women’s economic security and rights has always been one of the main programmatic priorities of UN Women priority in the oPt.  UN Women supports women to reshape conditions at both ends of the economic spectrum — from boosting women’s participation in economic policy-making to supporting efforts to provide women and their communities with practical skills needed for securing sustainable livelihoods.  Hence, and given the precarious situation of Palestinian women, the WRSCP directly contributes to the entity’s efforts aiming to create and promote effective models of community-level initiatives for advancing women’s human rights and eliminating gender inequality, as well as those that aim to advance the human rights of women and eliminating gender inequality through economic security.

In terms of its responsiveness to the needs of schools, the project is clearly relevant.  In interviews, school administrators, principals and teachers expressed a real need for improving their school canteens and the way they are operated, as well as genuine need for “un-conventional ways” of introducing quality improvements in their schools.  All interviewed teachers and administrators in the 33 schools visited by the evaluation team reported that they were keen to be part of the project once they learned about its objectives and work mechanisms.  The project promised –according to them- a new approach to integrating health and nutrition issues with canteen management functions, which they have long wanted.

Below, with some benefit of hindsight no doubt, we will highlight the main aspects of the WRSCP design and design process that might have been improved given what could have been known at that time. The value of doing this is two-fold. First, it helps identify where an issue that might have arisen later in program implementation had its roots in the problem of how the project was designed, or at least, in part resulted from the way it was designed and not simply in the way it was implemented. Second, identifying improvements may offer insights into how the anticipated future phase of the project should be designed.

- While both the internal review and the external final evaluation of the pilot project offered important recommendations for improving future programming, some of these were not adequately reflected in the WRSCP design. The most important of these were the need for allocating adequate financial resources for the development of both school canteens and women’s centers’ kitchens, and ensuring that these resources are applied in timely manner to facilitate the achievement of envisaged results.   The WRSCP earmarked the same amount of resources for individual canteen infrastructure development as in the pilot phase (US$ 4,000 per canteen), and included no measures to mitigate the likely risk of delayed transfer of funds to partner organisations.  In doing so, the programme set itself for facing the same challenges that were faced in the pilot phase, which had negatively affected the relationship between women centers and school adminstrators and undermined the former’s ability to put the types of expected healthy foods on offer in the school canteens.

- Section on Assumptions and Risk Management: Such a section was present in the project document, but was somewhat limited to a small number of somewhat obvious risks and rather optimistic assumptions.  A more  thorough analysis of the reasonability of assumptions, risks and their mitigation at the design stage would have prompted the designers to consider the possibility of their optimistic assumptions not being borne out and taking account of this possibility in the design. For example, not only would the project document have suggested the likely possibility of low sales volume in school canteens (which has great implications on both results and sustainability), it might have explored how this might affect the program and how to respond (risk management).   Similarly, a more careful analysis of the implications of the likely delay in the transfer of funds to MoE and the inability of the project to implement canteen infrastructure developments needed to ensure the ability of women centers to produce healthy foods in schools, would have promoted the designers to reconsider extending the programme’s implementation timeline and/or increase allocations to infrastructure development.  As it was, the wide scope and rapid pace of the programme design forced the designers to assume a best-case scenario which then the program was under pressure to live up to (to the detriment of some objectives as shall be discussed).

- The end-state of development of school canteens was not clearly defined in the project document.  The WRSCP design would have benefitted from a more detailed analysis of the schools canteens development needs insofar as stipulating what type of canteen would exist once the project is completed.  This, however, would have required the designers to undertake a detailed assessment of the infrastructure development needs of the target schools, and would have also required a more in-depth discussions over the technical design of these canteens with the Engineering Department of the MoE.  Doing this may have necessitated a smaller scale, which UN Women may not have wanted given its desire to scale-up the programme.

- The project’s logframe included several deficiencies.  This particularly in the articulation of outputs and indicators, and in the gap between outputs and outcomes (particularly for Outcome 1):  Several of the project’s performance indicators did not necessarily allow for measurement of results, reflecting a large attribution gap between the results envisaged and the performance indicators. In most instances, indicators were not specific, measurable, attributable, reliable, and time-bound (SMART). In other instances, measurement of the indicators was too costly (measuring reduction in transient hunger for example).  The fact that the baseline survey in the pilot phase could not capture most of the project’s indicators should have prompted a reformulation process, especially when considering that the final evaluation would have to be informed by the results of the baseline survey.

- Linked to the previous point, the programme design underestimated the complexity and difficulty of improving children’s nutritional status (Outcome 1):  The inability of the pilot project to demonstrate a sufficient level of effectiveness insofar as improving school children’s nutritional conditions could have been cited to justify a reformulation of the outcome related to nutrition. Emphasis, for example, might have been placed on increasing access of school children to affordable nutritious foods and/or changing school children’s food consumption habits; which are more realistic attainable outcomes than the one proposed.  Hence, the evaluation considers the theoretical underpinnings and the causal links within the project’s results chain related to improving the nutritional status of school children to be the weakest link in the project’s theory of change.  This weak link has affected the overall project’s achievements and –more importantly- expectations of partners during implementation.

## 3.2. Programme start-up and expansion

Following the signature of the financing agreement between NRO and UN Women and the receipt of the funds for the planned activities for the first six months, the Programme commenced in October 2009, a little over one month after the beginning of the 2009/2010 academic year.  Three months later, on 12 January 2010, UN Women initiated a bidding process for the component of the programme on women’s centers capacity development and establishment of food production units, on which basis a Cooperation Agreement was signed with  MAAN Development Center (MAAN) to provide capacity building services to women centers targeted during the lifetime of the programme.   MAAN launched the capacity development component in early April 2010 with an assessment of capacity development needs of the targeted organisations, and started implementing capacity development activities towards the end of the 2009/2010 academic year.   Also in April 2010, MoE and UN Women formalised their partnership agreement in a ceremony that was attended by the Minister of Education, Head of the oPt Office of UN Women and the Deputy Representative Office of Norway to the Palestinian Authority.

In the meantime, UN Women and MoE recruited the programme staff, established the Programme’s Steering and Coordination Committees (February and March 2010, respectively), provided support (in the form of discounted canteen lease subsidies as previously discussed) to 16 women’s organisations  to run the canteens in 109 schools (59 of the 61 schools targeted in the pilot project, and 50 new schools), and provided schools with funds to implement awareness raising activities on issues related to healthy eating habits and nutrition.  While UN Women and MoE had commendably planned for the late start of the programme by identifying the schools and women centers that will be targeted in the programme’s first year of operations and facilitating the access of the targeted women’s centers to the canteens prior to their payment of the canteens’ leases, very little else could be done to build the needed capacity within women centers to run school canteens and to ensure that the needed canteen infrastructure is in place to support a smooth implementation as envisaged in the programme design.  Hence, the women centers that were targeted in the first year had to work in existing (mostly decrepit) school canteens for the most part of the first year, and before developing the needed managerial and technical skills needed to effectively run school canteens.

The expansion phase in the second year was significantly more seamless, owning largely to better planning and needs assessment process that was undertaken during the 2009/2010 academic year and the school summer holiday of the same year, and a more timely transfer of funds by UN Women to partners.  During 2009/2010 academic year, UN Women and MoE collaborated on identifying the schools that will targeted during the second year and undertook a thorough needs assessment of their canateens’ development needs.  Accordingly, tenders for canteen development in the targeted schools were prepared,  bids awarded, and development works completed in time.  MAAN and UN Women also cooperated on selecting women centers and canteens workers for the second phase, assessing the capacity development needs of these centers, and providing them with the managerial and technical (food production) training they need to effectively run the school canteens.  The infrastructure development works for the schools canteens from the first year was also implemented in during the summer of 2010.

Nine new women centers were identified as partners to run 50 additional school canteens in the programme’s second year (2010/2011 academic year), in addition to the 16 centers from the pilot phase and the programme’s first year of operation.  Unfortunately, however, one women’s center targeted in the pilot phase was dismissed due to weak governance issues which could not be resolved by the programme.

Expansion in the the programme’s third year (2011/2012 academic year) was less successful than in the second year, but somewhat less problematic than in the first year.  Like the previous year, UN Women, MoE and MAAN identified the women centers and women workers that will be targeted in the programme’s third year, identified their needs and provided them with the necessary training to run school canteens.  However, unlike in the programme’s  second year, MoE could not undertake any canteen infrastructure development activities or awareness raising activities in the targeted schools in the third year due to the late transfer of funds from UN Women to MoE.  As a result, again in the third year, most of the women centers that were targeted in the programme’s third year had to reckon with running school canteens that do not meet the standards needed to facilitate women centers’ ability to produce, store and put on offer the types of healthy foods expected of them.  At the time of the evaluation, none of the 50 schools targeted in the third year had received funds to rehabilitate their canteen infrastructure or to implement student awareness raising activities.

Nine new women centers were identified as partners to run 50 additional school canteens in the programme’s third year (2011/2012 academic year), in addition to the 26 centers from the pilot phase and the programme’s first and second years of operation.  Two additional centers that were supported to run a total of 11 school canteens were dismissed in the third year due to gross mismanagement of financial affairs.  One of these centers was targeted in the pilot phase and the first year of the programme and received support to run 7 school canteens, while the other was a center from the programme’s second year of operations which had received considerable financial and technical support to run 4 school canteens in East Jerusalem.

The following findings emerge from the preceding discussion on programme expansion and the analysis of data gathered through discussions with programme stakeholders and the review of relevant programme documents:

- Planning for the programme expansion in the second and third years of operation in particular was done in a timely manner and in such a way that ensured that all programme stakeholders are properly informed about the programme and their specific roles and resposnibilities.  This was possible because school and women center selection and capacity building activities for women centers were completed before the beginning of the academic year.  This notwithstanding, planning for and implementation of expansion could have been significantly more effective had measures been taken to ensure the timely provision of funds for infrastructure development activities at both the school canteens and women’s centers kitchens levels.

- The Office of UN Women in the oPt has not yet developed into a fully functional and autonomous Country Programme, although it is currently in process of building its programmatic and programme support capacity in anticipation of transforming into one by the end of 2012. In the meantime, it continues to be dependent on the UN Women’s Headquarters and Sub-Regional Office in Jordan to provide several programme support services; including programme administration, finance and budgeting services. The limited financial and administrative autonomy of the UN Women’s Office in the oPt and limited ability to control the speed at which administrative and financial processes move has been a main reason behind the unsmooth expansion described above.   This necessitates that UN Women’s Office in the oPt gives considerable attention to operational and financial planning of its programmes to mitigate the impacts of possible delays in administrative and financial processes on programme results.  This should be done at least until the Office becomes less dependent of Headquarters and Sub-Regional Office services.

- The programme implementation faced further delays as result of financial control procedures within MoE.  While these were generally shorter than those caused by delays in the transfer of funds, they have undoubtedly negatively affected the way the programme developed and expanded from one year to the next.  Given that internal financial control has been a long standing procedure at MoE and one that is likely to persist, it is quite prudent from both MoE and UN Women to consider how to mitigate the delays it is likely to cause in future programmes.  This could include requesting the donor to waive the need for internal financial control or sub-contracting a third party to implement activities at the school level.

- While considerable efforts were put into assessing the needs, capacity and readiness of women centers to engage in the WRSCP, the relatively short time allocated to the needs assessment process and the largely quantitative tools used to assess needs did not allow the proper investigation of the governance of these centers and power dynamics within them.  The assessment process itself was also not sufficiently inclusive, with most assessment reports reviewed by the evaluation team having been based on meetings with one to three of the active members of the centers.   The limited time allocated to capacity assessment and the sub-par attention to governance matters in the WRSCP’s capacity assessment process rendered the inclusion of at least three women centers that eventually had to be dismissed for reasons related to weak governance that were not identified or mitigated.  It was also a key reason for the inclusion of centers that do not have the potential to build capacity, management prowess or commitment to sustain canteen enterprises on a socially-responsible basis.

## 3.3. Programme management, monitoring and reporting

As the executing agency, UN Women is responsible for the overall management of the WRSCP; hence accountable to the donor for its results, overall management, and finances. The WRSCP’s project document envisaged the following management structure:

- Within UN Women, the programme would be one of the entity’s economic security programmes and would thus be managed by the Programme Officer (PO) managing the portfolio of programmes in this area.  The Programme Officer would devote 25% of her time –as an in-kind contribution from UN Women- to the programme and would be responsible for the overall management, monitoring and reporting of the Programme.  The Evaluation in UN Women Headquarters would be directly involved in programme monitoring and reporting.  A Project Coordinator –paid by the programme- would support the PM in discharging her functions by following-up project implementation on day-to-day basis, and would dedicate 100% of her time to the programme.  Two Field Coordinators (FC) would be recruited with programme funds to support and follow-up programme implementation in the field in close collaboration with MoE staff involved in the programme.

- The General Directorate for School Health at MoE would be UN Women’s central implementing partner, with key roles in planning and management of the programme.  Through a designated Programme Manager (paid by MoE), a Central Coordinator (CC) and a Field Coordinator (paid by the programme) working under the direct supervision of the General Director of School Health,  MoE through its School Health Unit staff in the targeted directorates, would be responsible for identifying canteens’ development needs, coordinating and implementing school-level activities, facilitating women centers’ access to schools, and monitoring project implementation and results.

- A local NGO would be the implementing partner responsible for managing the day-to-day implementation of the project insofar as the women centers are concerned. This includes leading the planning and the development of all project deliverables related to building the capacity of women and their organizations and ensuring that the relevant outcomes are met. The NGO implementing partner would be contractually obligated to report on project implementation and results to UN Women.  The expectation was that the partner NGO would recruit a Project Coordinator and two field coordinators to manage the day-to-day operations of the project, and contract external consultants and trainers to undertake capacity development activities related to women centers.

- At the level of women’s centers, the elected Management Board (MB) of the targeted women centers would be ultimately responsible for overseeing the management of the canteen operations, including ensuring that school canteens are run effectively in accordance with the stipulations of lease agreements with the targeted schools which specify, inter alia, allowed and prohibited foods.  The MB would designate a committee from its ranks to be manage the canteen operations on a day-to-day basis, including coordination with school administrators to resolve arising operational problems.  A Canteen Coordinator would be hired to assist this committee in discharging its responsibilities.

Two committees would be established to guide the programme and oversee implementation, and maximise coordination among the programme’s partners, namely:

- The Programme Steering Committee (PSC) would be responsible for setting the overall direction of the programme and ensuring its adherence to agreed-upon timeline and results, including facilitating discussion and problem-solving among the programme’s three partners (MoE, UN Women and women’s centers) and developing short- and long-term plans for achieving the programme’s performance targets.  The SC would be made up of the General Director of School Health and the Head of Office of UN Women in the oPt; and it would meet once a month.  The agenda of the SC meetings would largely be formulated on the basis of emerging issues presented in monthly and semi-annual progress reports prepared by Field Coordinators and coalesced by UN Women.   An NRO representative would be invited to participate in the SC meetings.

- A Programme Management Committee (PMC) would be established in each of the education districts targeted to plan, follow-up progress and coordinate programme activities at the field level.  The PMC would consist of the UN Women and MoE Field Coordinators, and the Head of the School Health Unit in the respective MoE Education Directorate.  This committee would meet on a monthly basis to review progress and resolve arising operational challenges, including strengthening relations with schools and women centers serving them.  Principals of the targeted schools and a representative of the Women centers concerned would be invited to PMC meeting as necessary.

Programme monitoring, evaluation and learning would have a stronger emphasis in the WRSCP as a result of increased field-level presence of programme staff, enhanced coordination and reporting-based decision support mechanisms.  Improved monitoring would be strengthened by the involvement of the Evaluation Unit at UN Women’s Headquarters in designing monitoring and evaluation tools and guidelines.  FCs were envisaged to conduct regular field visits to the targeted schools and women’s centers to give UN Women and MoE a chance to ensure that there are no major deviances from the work plan or the budget.  A strong emphasis would be placed on monitoring the development of business models and women center’s adherence to their commitment of providing healthy foods in school canteens.  The FCs would provide a monthly report to the Steering Committee with a brief analysis on the project performance and recommendations for changes in the way the programme is being implemented on the basis of their visits.

A bi-annual progress report incorporating feedback from the SC would be submitted to the donor, providing a brief contextual analysis of the reporting period, achievements to date, any obstacles or variances in the workplan and in the budget.  This would be prepared in parallel to a financial report covering the same period.  Progress reports would be made available to all the programme stakeholders.

At the end of first academic year, the programme would be subject to an internal mid-term review by programme partners with the view of re-steering the programme as necessary.  A joint review involving all partners at the end of the second year of the programme would be organised with the purpose of adjusting plans and interventions for the third year. .

The evaluation was asked to examine the programme’s management arrangements and provide a judgment whether these, in both theory and practice, have effectively and efficiently facilitated the achievement of planned outcomes and results.   The following can be noted in this regard:

- The programme structure was implemented and staffed largely as planned both within UN Women and MoE, with MAAN selected as the programme’s NGO partner as noted above.  At the level of women’s centers, Canteen Coordinators were also hired and trained.  MBs of targeted women centers designated members from their ranks to oversee the aspects of programme implementation related to the women centers and these were effective to varying degerees.

- The programme’s field staff recruited by both UN Women and MoE were found to generally have the requisite training and capacity to discharge their contractual responsibilities, though some of them were found to lack the basic knowledge of gender concepts and analytical framework.  Through learning by doing, exchanging knowledge and –in the case of UN Women staff- getting partially engaged in the implementation other programmes, as well as their commendably extensive presence in the field they have built considerable experience and developed the skills needed to effectively support and coordinate programme implementation.

- The PSC was constituted  as the highest decision making structure in parallel with UN Women Office in the oPt and its Head.  The PMC was also established and its role and mandate was clearly articulated, so were committees at women’s centers.

- Also overall procedures for program and project planning and implementation were well laid out and followed. This was true for the planning and implementation process from women center and school selection through canteen workers selection to project preparation on through the contracting and project hand over process.  Clear Memos of Understanding (MoU), Project Cooperation Agreements (PCA) and Contracts well governed relationships between UN Women, MoE and MAAN and between UN Women and the women centers, and women centers and schools setting out the terms of agreements and relative roles and responsibilities.

- Processes and tools for programme planning, monitoring and financial documentation and reporting overall were also well designed, well-kept and followed.  These included forms for daily, weekly and monthly activity plans and reports; standard canteen monitoring forms; training evaluation forms; and several templates and forms designed specifically for monitoring the financial performance of individual canteens.  The annual internal reviews planned over the lifetime of the project were conducted with the active participation of all stakeholders, and recommendations were reflected in reports to the donor.

- Programme reporting was done at various levels largely as planned, with various staff and partners having various roles in the reporting process.  Two annual progress reports, covering respectively the first and second years of operations, and six semi-annual financial reports were prepared by UN Women and submitted to NRO by UN Women Headquarters upon clearance form the Reporting Focal Point and Finance Officer at UN Women Headquarters.  The evaluation reviewed these reports and found them to be well-written and of good quality.

However, the following observations can be made in terms of: i) differences between what was envisaged and what happened here that had  impacts on implementation and the achievement of objectives; and ii) programme management weaknesses:

- While the both the PSC and the PMC held several meetings during the programme’s lifetime, they were less capable of affecting programme implementation than envisaged.  The PSC did not meet on regular monthly basis as planned, and when it met (six times during the programme’s lifetime) it did not give adequate attention to resolving problematic issues with which it was presented.  Several factors contributed to this somewhat subpar performance, the most important of which are: i) the lack of the requisite level of decision-making authority over certain issues among the PSC members; ii) absence of donor representation on the PSC; iii) weak follow-up mechanisms; and iv) weak linkages in information flow from the field.  As the highest governance body  and in the spirit of being the highest level of policy guidance and decision-making, the PCS could, perhaps, have been more active in certain functions, where, as it turned out, such high level involvement appeared needed. While it was not necessary for the PSC to meet as frequently as every month, it may have, however, benefitted from the inputs and decision making authority of the Deputy Minister of Education; MoE General Directors of Finance and Administration, Buildings, and Education Directorates; and the Head of Office at NRO.

- Women Center Committees did not function as envisaged in the project document.  The majority of these committees seized to function shortly after they were established, and most school canteen management operations –including financial management and food production- were relegated de-facto to the either the chairwoman of the Board or the Canteen Coordinator.

- While MoE and UN Women made commendable efforts to develop programme monitoring tools and mechanisms, these were neither consolidated under a common monitoring framework nor developed in a such a way that enables comprehensive programme-wide monitoring and reporting as envisaged in the programme design.  The MoE’s monitoring activities focused largely on monitoring the diversity of foods in school canteens and checking the adherence of canteen workers to standard hygiene protocols against a standard checklist developed by the Ministry’s staff.  The UN Women monitoring developed a slightly more comprehensive monitoring system, but most of the monitoring efforts went into monitoring the sales volume and profitability of women centers. MAAN on the other hand mainly monitored training delivery and trainee satisfaction for which it was directly responsible, and saw no role for itself in monitoring the performance of women’s centers performance against programme results for which they were responsible.  This ‘silo-style’ approach to programme monitoring was not only unnecessary given the intricate and complementary linkages between the programme components, but it also contributed to creating a sense of a functional division of labour (and responsibility) among programme partners.  Combined with the lack of a clearly defined and agreed framework to govern programme monitoring, the programme’s ‘silo-style” approach to monitoring did help at all in strengthening partnership between them.

- Despite that all partners contributed to monitoring, reporting and production of knowledge on the programme, not enough was done to ensure dissemination of reports and key management decisions emerging from programme monitoring processes and activities to the partners. Minutes of PSC and PMC meetings were prepared jointly by UN Women with inputs from MoE’s Programm Coordinator but often did not get circulated to the concerned partners, including in certain instances field-level staff and school principals responsible for follow-up on decisions. Field Coordinators reports often did not get consolidated to inform PSC decisions.  Programme monitoring reports did not get shared with or circulated to MoE.  Proceedings of the programe’s internal reviews were also not shared among partners.  This is quite unfortunate not only because it is contrary to what has been explicitly committed in the Programme Document, but also because it left the impression among partners that reporting and knowledge production is the sole responsibility of UN Women; and also because it weakened accountability.

- Key programme staff or expertise was either not hired, resigned prematurely, or not available to the programme as originally expected. This created some human resource capacity gaps and contributed to increasing the programme management burden on field and support staff.  In some cases, it created some discontinuity and implementation problems. The most critical examples of human resource gaps identified by the evaluation are:

  - Three different UN Women POs were assigned to oversee programme management at various periods.  The PO from the pilot phase was assigned programme management responsibilities for a period of six months before she was reassigned to a different function within UN Women.  A second PO was hired rather swiftly, but resigned within four months relegating programme management to the Project Coordinator.  Again, a third PO was hired in 2011 but resigned shortly thereafter.  During the third year of operations, UN Women’s MDG-F Programme Manager was delegated the responsibility for managing the programme.  Due to the fact that the MDG-F Programme Manager had numerous projects within here portfolio starting in 2012, she had little time to dedicate to the programme.  The PO position proved to be critical not only from the perspective of programme management function, but also because it was necessary to provide leadership, guide coordination and foster relationships built among the project partners and resolve any problematic issues.  From the perspective of MoE officials interviewed, PO turnover rate has been among the key main management weaknesses of the programme; and one that often contributed to communication breakdown among partners.

  - While the Evaluation Office at UN Women’s Headquarters was involved in the project preparatory stages as planned, substantially more involvement was needed throughout the programme’s lifetime. In fact, given its planned scale, outcomes, and scaling-up intentions, the programme would have undoubtedly benefitted from the regular –possibly full-time- inputs of an M&E specialist. Such a specialist would have likely been able to develop a more coherent and integrated monitoring framework, significantly contribute to ensuring that decisions of various committees are more properly followed up, and shoulder some of the monitoring burden on the PC and FCs.

  - The role of MAAN in programme implementation was not sufficiently clear in the Cooperation Agreement signed with UN Women.  UN Women’s expectations from MAAN were quite high given the nature and rubric of the agreement signed it signed with MAAN.  These included the provision of substantially more technical assistance services and follow-up to the targeted women’s centers than what was provided, including overseeing women’s center’s financial performance vis-à-vis canteen operations on a regular basis.  MAAN on the other hand saw its role as a service provider of specifically defined capacity building tasks (training, coaching, and upgrading and equipping women’s centers kitchens).

  - Resources were not made available to MAAN to recruit field staff to build the capacity of women centers and follow programme implementation in the field on a full-time basis until the programme’s second year of operations.   Field staff hired by MAAN during the second year of operations neither had the requisite expertise in enterprise development nor were given –due to the previous point- a specific mandate to do so.

Some of these organizational and staffing issues were beginning to be addressed at the time of the evaluation. A new PO was being assigned to the programme to oversee programme closure and preparation for a new phase. MAAN and UN Women were discussing future renewed collaboration under clearer terms.  Similarly by this time, more efforts were being made to engage the donor in programme implementation and evaluation, consolidate monitoring data and identify lessons learned for future programming.

## 3.4. Programme achievements and results

Here we shall consolidate, present and assess the results of the WRSCP. We shall do

so against the programme’s stated outcomes and outputs.

### 3.4.1. Outcome 1: to improve nutritional status among Palestinian children in targeted schools

As discussed above, the programme aimed at improving school children’s nutritional status through engaging women’s centers in the running of school canteens with the view of improving the variety and quality of affordable nutritious foods available through the school canteens, improving levels of knowledge among students vis-a-vis nutrition and healthy eating habits, and improving schools’ canteens infrastructure.  The specific outputs were: i) reduced micronutrient deficiencies among the targetes school age children; and ii) short-term hunger decreases.

The programme met its target of improving the variety and quality of affordable, healthy and nutritious foods available through school canteens, although the extent of this varied from one school to another.   While the evaluation could not make comparisons between the quality and variety of foods available through the school canteens before and after the programme due to the lack of baseline information in this regard as well as the lack of an agreed upon standard for what should be on the offer through women’s centers in targeted canteens, interviews with MoE, school administrators, teachers, students and women’s centers strongly suggest that both the quality and variety of foods offered through school canteens has been significantly improved as a result of the programme.  Women centers introduced macronutrient-rich foods into the canteens that were previously unavailable, albeit to varying degrees as we elaborate below.  These include, inter alia, homemade pastries made with fortified flour, milk and eggs; different variety of sandwiches; cakes; cooked meals, fresh juices, dairy products; pop-corn; boiled chickpeas; and nuts.

In interviews, students expressed satisfaction with the new food varieties in their schools’ canteens and the prices thereof.  All food items sold through the school canteens were priced to accommodate students’ purchasing power, with most foods available in various sizes and additions to rendering them accessible to most student.  In several interview students and teachers noted that canteen prices are lower than market prices for comparable foods. A quick verification of market prices conducted by the evaluation team confirmedwhat teachers and students reported, though a few exceptions were found where canteen prices for sandwiches and pastries in some schools were slightly higher than market prices.

The evaluation team considers the ability of the project to introduce nutritious food varieties to be a significant and commendable achievement not only from the perspective of meeting anticipated outputs, but also because it paves the way for positively affecting children’s behaviour and food intake habits on the long term.  This is especially true given that the introduction of these foods often came to replace foods that hold no nutritional value.

This notwithstanding, school canteens found to offer diverse and home-made style foods had the following commonalities:

- managed by a well-established CBO, with strong leadership;

- managed by CBOs whose Board is committed to the project’s nutritional objectives and is aware of the need to cover costs;

- canteen management arrangements entail providing economic incentives for workers to increase sales and diversify own-production;

- located in schools whose principal and health committee are active and understand the dynamics of the running a canteen business in a school environment;

- sufficiently equipped with basic food production and storage facilities; and

- are followed by an MoE School Health Worker.

The proximity of schools to women centers was also found to influence the variety of food, but to a much lesser degree than expected as the existence of an incentive structure for increasing sales and food varieties in these canteens played a considerable role in offsetting the effect of the proximity factor.    Generally speaking, however, it can be schools that schools not easily accessible by women centers through public transport and/or located outside of the administrative boundary in which the center was located were run almost autonomously by women from the same communities in which these schools are located.  Thus, the extent to which the women center could monitor what is being offered in these canteens or deliver foods produced at the center was quite limited.    Unless incentives were provided for women running these school canteens to generate increased sales and produce foods themselves, these schools did not demonstrate the same achievements insofar as variety and availability of home-cooked foods as other schools that were near the women centers.

The programme also met expectations in terms of improving students’ knowledge of nutrition and healthy eating habits in the 159 schools it targeted in the first two years of operation, but not yet in the 50 schools that were targeted in the last year of operations.  Significant efforts are needed to affect students’ attitudes in this regard, however.  The programme delivered on its promise of raising students’ awareness and improving their knowledge of nutrition and healthy eating habits through extending community mobilisation and school awareness grants to the 159 partner schools from the programme’s first and second years of operation (average US$ 1,100 per school).  Owing to the delay in transfer of funds, the programme was not capable of achieving the same feat in the 50 schools that were added in the programme’s third year of operations however.

These grants were used by schools to implement such activities as: open health days focusing on nutrition and hygiene; summer camps; intra- and inter-school competitions focusing on health and food; publication of promotional materials including facts on nutrition, the food chain, and healthy lifestyles; wall paintings and murals with health-related messages; sporting events; student field trips; school media event; and workshops with parents.  Up to the evaluation, more than 1,000 community mobilisation activities involving parents and students; 1,600 small interactive school activities focusing on engaging students in activities that promote healthy eating habits; and 16 summer camps were implemented in the 159 schools targeted in the first two years of the programme’s operations.  More than 22,500 students seem to have benefited from these activities.

In an attempt to gauge the effectiveness of these awareness raising activities, a random selection of students from the schools that were asked to recall what they have learned through being exposed to these activities.  Remarkably, students answers reflected a high level of knowledge that the evaluation team did not expect.  Of the 128 students interviewed in 8 of the schools that had been involved in the programme in the first two years of operations and visited by the evaluation team, 107 mentioned that foods containing preservative and color (dye)  should be avoided; 92 highlighted that need for a balanced diet; 37 recalled the importance of fiber, fruits and vegetables; 117 highlighted the need to avoid eating deep fried foods and chips; 83 indicated to avoiding consumption of carbonated and energy drinks; and 32 stressed the importance of breakfast.  A smaller number of students  highlighted the importance of examining the expiration dates of foods before consumption and noting the nutritional facts displayed on food packages. When asked whether their eating habits have changed as a result of the knowledge they acquired as a result of the project, very few students confirmed their eating habits have changed. This was expected, however, given that children’s eating habits and taste preferences are hard to break on the one hand, and that attitudinal change requires time and reinforcements that are beyond the scope of the programme.  Students’ answers are quite impressive, but the degree to which they can be attributed to the programme’s awareness raising activities given the absence of a baseline data remains highly uncertain.

The key weaknesses noted by the evaluation team with regard to the programme’s community mobilisation and student activities relate to the limited linkages between the implemented activities and promoting canteen sales on the one hand, and the lack of a clearly articulated tangible targets for these activities.   Consequently, the quality and nature of implemented community mobilisation and student awareness activities, and their effectiveness vis-à-vis promoting eating healthy habits, varied substantially from one education district to another as different strategies were followede by MoE School Health Department Heads at the district level to disburse funds to schools and guide activities .  A more integrated, results-oriented  approach to knowledge building and community mobilisation in support of school canteens operations (as opposed to the piecemeal approach followed by the project) may have substantially improved the programmes overall results and those related to awareness raising.  Such an approach would have also improved the programme’s ability to document, monitor and report on tangible improvements in student’s health status and/or eating habits rather than focusing on quantitative achievements; i.e. number of activities implemented.

Mixed results were achieved in relation to the expectation of improving school canteens infrastructure, and more attention was needed to streamline gender consideration in infrastructure development.  In excess of US$ 875,000 were invested in school canteen development and rehabilitation activities up to the evaluation.  These included making provision for building new canteens in schools that either had inadequate canteens or did not have a canteen infrastructure altogether; construction of canteen umbrellas; installation of  steel benches and  canteen windows; connecting  canteens to water and electricity; and provision of equipment to school canteens

While the project investments have unquestionably improved the canteens’ physicals conditions and made them more conducive for promoting healthy foods, the evaluation found that substantial differences exist in the level of improvements introduced and the quality of works completed.  These differences were largely a function of inadequate financial resources allocated to canteen development, a lack of agreed upon standard for canteen development; i.e. definition of what kind of canteen we want to build or rehabilitate, and differences in the way funds were actually allocated to schools by MoE’s Heads of School Health Departments at the district level.

The results were uneven and starkly different physical conditions in targeted school canteens, with some schools’ canteens being located in underdeveloped, cramped quarters with no running water and electricity,  and others having been fully renovated and equipped.    The fact that some school canteens were not  sufficiently developed or rehabilitated and others were still under construction at the time of the evaluation made for a very difficult working environment for women.  This had implications on women’s centers ability to meet MoE’s expectations of producing and making available diversified foods.  Generally, foods in under-developed canteens were understandably limited in variety in comparison to more developed and newly built and equipped canteens.

The limited financial resources allocated to canteen development has rendered the programme unable to mainstream some basic gender considerations in the design of school canteens.  This was particularly true for canteens located in male schools, where women workers had no access to bathrooms they would be comfortable using in these schools.  While somewhat of a minor weakness, it is nonetheless unfortunate given the programme’s gender focus.

3) Despite achievements in food diversity and hygiene, the evaluation could not ascertain that tangible achievements have been made insofar as the programmes’ planned outputs relating to improving educational attainment, and reducing short-term hunger and micronutrient deficiencies among school children in the targeted schools.

Despite its positive influence on the factors that determine the nutritional status and educational attainment of school children, the expectation set out in the programme’s logical framework that it could achieve tangible, measurable and attributable results in this regard were overly ambitious.  The proramme’s inability to demonstrate achievements at this level, hence, should not, in our opinion, discredit the programme’s overall achievements, especially since it has unquestionably improved student’s access to healthier and more nutritious foods than before gone a long way in positively influencing their eating habits.

### 3.4.2. Outcome 2: to achieve sustainable income for targeted women’s centers

Through building the capacity of targeted women’s organisations to establish and sustainably run school canteens and small-scale food production enterprises, the programme expected to be able to enhance these organisation’s financial ability to respond to the practical and strategic needs of women while providing them with sustainable employment opportunities; hence, enhance their economic security and human rights.  The specific outputs were: i) existence of a pool of trained women in each women’s center; ii) functional production units established at each women’s center; and iii) business model developed that balances women’s centers profit margin with health and nutrition objectives.

The programme has demonstrated great success in building the capacity of women’s centers to run school canteens in the spirit of the social responsibility it espoused.  A great proportion of these centers were able to achieve financial sustainability in their canteen enterprises, and several of them managed to generate considerable profits (see pt. 2 below). This is considered a big accomplishment of the programme given that clear focus of the programme design on advancing women’s economic security through strengthening their agency.  In no small part, this accomplishment has been possible due to the close technical support and follow-up provided by UN Women to the targeted centers, and the highly effective capacity building approach implemented by MAAN.  The staff of both organisations, particularly those with field and training delivery and coaching responsibilities, should be commended for this feat.

In total, the programme targeted 35 women organisations working across the West Bank during its three years of operation, exceeding its target by 7 organisations.  However, the programme fell short of reaching its target of serving 230 schools as it only reached 209 schools. The total number of students served, however, remained in line with expectations (~85,000 students).  Given that the programme planned (and implemented) expanding to 110 schools in the first year of operations, and 50 schools per year thereafter, this deviation is understandable and should not be considered as problematic.

That said, the programme was generally successful in realising its planned outcome of achieving sustainable income for targeted centers, despite the dismissal of three centers. Of the 32 women centers that were running canteens during the programme’s last year of operations, 26 made profits and are able to pay their respective school canteens leases for the next year fully on their own, while the remaining 6 made profits but need further support to do the same. Sixteen centers (46% of the total targetd) were able to generate profits in-excess of their business reinvestment needs for next year (US$ 1,000-9,500) and are thus able to cover a good proportion of their non-canteen related expenditures.  The centers shared two or more of the following elements in their business model:

- centralized management of cost accounting and financial control, with strong involvement of  Board members;

- strong cost analysis  and cost reduction mechanisms, including: regular price shopping, bulk purchasing, labour cost reduction mechanisms (canteen workers paid to produce food) and internal processing of foods; and

- strong and fair sales-based incentives systems.

The programme’s capacity building approach was implemented largely as planned and was quite effective in building women’s centers’ capacities and knowledge sharing.  Training provided was found to be highly relevant to women’s centers capacity building needs, and of generally good quality.

The capacity-development component of the programme (implemented by MA’AN) followed what proved to be a simple and effective methodology based on participation, networking, and needs-based capacity- development, and follow-up. The capacity-development training component began with a needs assessment and a gap analysis of the targeted women who would be engaged in canteen operations.  The gap analysis identified the need for training in governance, canteen operations and management, human resources development, financial management, infrastructure and equipment, business services delivery and external relations.  The needs assessment formed the basis for both components of the capacity-development aspects of the project, including training and on-the-job coaching.

The training began with an orientation session to ensure that all parties understood the project objectives and its various components.  MA'AN followed-up with the women’s centres and the canteens through a technical training programme and on-the-job coaching and site visits, in order to ensure that the knowledge and skills gained through the training were implemented.  Networking was encouraged at every stage of the implementation, particularly in introducing the new women’s centres that would run the school canteens along with the existing canteens.  MA’AN provided the women’s centers with tools and equipment to produce healthy and cost-effective food to the schoolchildren in line with the needs assessment.

The technical training components were based on the Organizational Capacity Assessment Tool and the recommendation of the needs assessment and business needs assessment conducted by MA’AN.  The assessment focused on improving the financial and managerial capacities of the centres and in improving the quality of nutrients in the food being provided to the children. The CBOs received the basic skills and training necessary to manage and run the school canteens and to ensure sustainability and ability to carry out future projects.  The training topics included for each cluster were: canteen management (20 hours); bookkeeping (ten hours); leadership (ten hours); pricing and marketing (ten hours); quality control/hygiene (five hours); marketing (five hours); report writing (ten hours); technical training on food processing (40 hours); and on-the-job training (60 hours).  Over the lifetime of the programme, more than 110 training hours were provided to some 420 working women and ten men (working women and the management board members) at the 35 women’s centres targeted by the programme.  In conjunction with the management and financial training, women involved directly in in the production process, including the production of pastries, snacks and healthy sweets from the targeted these centers  received extensive training on food production skills.

The training courses were followed by specific on-the-job training (60 hours) with 15 women’s centres. Experts in quality control and food processing visited each centre to ensure that women were using the skills acquired during the training. The trainers visited these centres to review the policies and procedures instituted by the women after the training, noting that the women’s centres had implemented the systems learned during the training.

Interviews with women in the targeted centers revealed that these training and coaching interventions (particularly the latter) have had many positive results, including: application of proper management and financial systems in running the school canteens; understanding of good, healthy eating practices and translation into project activities; realization of their role as advocates against the consumption of unhealthy foods in their communities and reduction of the effects of unhealthy food advertisements by corporations; and observing and understanding children’s eating habits and helping to identify their preferences and change habits.

The above notwithstanding, discussions with programme partners revealed that the introduction of the following improvements to the capacity building approach may have further enhanced capacity building results and programme wide learning, while strengthening networking and partnerships: i) more timely provision of training; ii) greater focus on on-the-job coaching and training, particularly in the areas of financial management, costing and cost control, marketing and communications; iii) avoidance of lecture-centered training methodologies and greater integration of learner-cantered training methodologies, focusing more on practical problem-solving exercises; iv) integration of MoE staff involved in the programme in the capacity building programme both as trainers and trainees; v) greater focus on documentation and dissemination of good business practices; vi) streamlining ToT methodologies in the training programmes to enable women to gain the capacity to professionally design and deliver training programmes; and vii) expansion of exchange visits, including among MoE directorates.  Having discussed these improvements and examined training materials developed within the framework of the programme, the evaluation team concurs that such improvements would have indeed improved capacity building results, hence recommends their consideration in the design of the future phase of the programme.

The programme’s capacity building component also included the establishment of a food production unit for 15 women’s centers.  This involved providing these centers with food production equipment and tools, as well as upgrading of infrastructure needed to run the canteens.   The installation of these food production units has provided women centers with enhanced food production and storage capacity, as well as augmenting their ability to engage in other income generating food-production and catering activities.   The degree to which women’s centers have put this increased capacity to use in enhancing the efficiency of their canteen operations is believed to be somewhat on the low side.  This is mainly due to late delivery of equipment; late completion of infrastructure development works; relative disconnect between women’s centers perceived needs for equipment in terms of quality, size and utility and what they actually delivered; and –in some cases-  lack of knowledge on how to operate certain equipment and its redundancy.   While this is unfortunate given the potential impact food production could have on canteen operations, it is also understandable since the establishment of these units were not necessarily linked to a well-developed food production business model on the one hand, or adequately resourced on the other had.

### 3.4.3. Outcome 3: Women’s community involvement

The project envisaged enhancing women’s community involvement through enhancing school community and parent participation in education to undertake improvement of school facilities, and decreasing the underlying inequalities in power and resources which constrain women’s abilities to achieve them.

Commendable achievements were made in relation to engaging women in school activities. These included the participation of women in local and regional exhibitions organized by MoE, the organization of women of school activities (such as common lunches), the participation of women -in their capacity as members in the women centers- in schools’ Parents and Teachers Associations, the involvement of women in summer activities organized by schools, and the participation of women in open days organized at the school level.

The project has paved the way for greater and more equal participation of women in their communities.  While significant efforts are needed to eliminate all forms of social and economic inequalities women face,  considerable achievements were made in this direction.  The project has facilitated the dialogue between women centers and several community based organizations, which made it possible for women centers to forge partnerships for the first time with other community based organizations.  Organizations that had such relations were encouraged to build upon these relations and were provided with ideas for this purpose.  Nevertheless, significant more effort is needed before it can be said that the project has decreased deeply engendered inequalities.  The project did, however, pave the way for greater and more equal participation of women in their communities.

## 3.5. Impact

### 3.5.1. At the level of participating schools, students and the community

The following can be noted on the basis of field observations and partner interviews with regard to the impact of the programme on the participating schools:

- Through financing canteen infrastructure development, the programme has contributed to improving school environment conditions in 159 schools, thereby contributing to improving the quality of education in these schools.

- The programme has significantly reduced the burden of canteen supervision and conflict management that school principals in the majority of the targeted schools had to shoulder prior to the programme.  This, according to all interviewed principals, has significantly improved their ability to devote more time to other more important aspects of the education process.

- Canteen’s focus on the provision of healthy foods has provided opportunities for schools to complement and support student learning by reinforcing teachers’ messages about food, which has contributed to positively influencing students eating habits.  This was further supported by the grants provided by the programme for student activities.

- The programme improved the economic access of some 85,000 student to a more diversified foods through the introduction of affordbale foods through women-run canteens;

- Through introducing good food processing and handling practices within the targeted canteens, the programme has improved food safety and hygiene for some 85,00 students.

- On a somewhat limited scale, the programme has fostered improved relationships between the targeted schools and the community, which –at times- increased schools’ ability to mobilize community contributions to augment programme results.  For example, some schools were able to mobilize community cash contributions to undertake canteen-related infrastructure development, and others have been able to leverage canteen infrastructure development to mobilize community funding for general school rehabilitation.

### 3.5.2. At the level of canteen workers and their organisations

The programme’s impact on the targeted women’s centers and canteen workers has been quite impressive.

In relation to former, the programme has enabled 32 women’s centers to establish –for the first time- a sustainable enterprise project that is not only capable of meeting their main target group’s practical need for culturally-accepted employment opportunities, but also strategically contributes to the sustainability of their organisation.  This is quite significant given that more than two thirds of the targeted centers have had very little successes in establishing such enterprises in the past.   The fact that the women’s centers have become more responsive to the needs of their constituency at the local level have enhanced the legitimacy of these organisations and helped them gain recongnition at the local level. As a result, these organisations feel more capable of representing their constituency’s interest at the local level.

Through its lifetime, the Programme has generated employment opportunities for 416 poor women, many of whom working for the first time in their lives. On average these women made US$ 150 per month for an average period of 9 months per year.  While relatively low in both aggregate and hourly wage standards, the income women earned through the programme was in line with market wages hence only helped them realize better social status both at home and within their communities.  Many of the interviewed canteen workers used the word emancipated to describe the impact the programme has had on them.   Several others said that they feel more economically independent than ever as a result of the programme.

# 4. Conclusions and Recommendations

## 4.1. Conclusions

The overall impression of the evaluation team is positive, though the team acknowledges that a number of important activities planned remain to be implemnted.   The main justification for this positive impression is the fact that the programme has not only managed to scale-up and benefit from the lessons learned from the pilot phase on which basis it was designed, but it also succeeded in confirming that the socially responsible women-run school canteens can be viable and effective for both the advancement of gender equality and economic security and promoting school health policies.   In doing this,  the programme has shown that it remains relevant to the context in which it which operates.

Despite its unsmooth start-up and expansion which have resulted from insufficient planning and delays in implementation of activities, the programme was largely successful in delivering most of its planned outcomes and results.

The programme met its target of improving the variety and quality of affordable, healthy and nutritious foods available through school canteens by taking measures to ensure that diversified and nutritious foods are available in targeted school canteens.   It also met expectations in terms of improving students’ knowledge of nutrition and healthy eating habits, but this was mainly in the 159 schools it targeted in the first two years of operation as relevant activities have not yet been implemented in the schools that were targeted in the thir year.  Mixed results, however, were achieved in relation to the expectation of improving school canteens infrastructure due to the confluence of limited funding, uneven distribution of funds, and delays in implementation.

With regard to its intention of achieving sustainable income for targeted women’s centers, the programme was quite successful.  Of the 32 women centers that were running canteens during the programme’s last year of operations, 26 made profits and are able to pay their respective school canteens leases for the next year fully on their own, while the remaining 6 made profits but need further support to do the same. Sixteen centers (46% of the total targeted) were able to generate profits in-excess of their business reinvestment needs for next year (US$ 1,000-9,500) and are thus able to cover a good proportion of their non-canteen related expenditures.  This programme’s capacity building approach played a significant role in this achievement as it effectively built women’s centers capacities at various levels using proven methodologies and approaches.

Commendable achievements were made in relation to engaging women in school activities, though these did not live up expectations.  This was main because involvement was not systematic across the programme, with women’s centers mostly being involved as catering providers than as partners.  However, it is acknowledged that the programme has paved the way for greater and more equal participation of women in their communities.

In terms of its impact at the level of the participating schools, students and community, the programme can be said to have achieved the following:

- improving overall quality of school environment in 159 schools, thereby contributing to improving the quality of education in these schools.

- reducing the burden of canteen supervision and conflict management, hence allowing school administrators to devote their attention to more substantive issues.

- providing opportunities for schools to complement and support student learning by reinforcing teachers’ messages about food; positively influencing students eating habits.

- improving the economic access to a more diversified foods for 85,000 students;

- improving food safety and hygiene for some 85,00 students through the introduction of good practices in food preparation, handling and storage in canteen operations.

The programme’s impact on the targeted women’s centers and canteen workers has also been quite impressive.   It has enabled 32 women’s centers to establish –for the first time- a sustainable enterprise, capable of meeting their constituency’s practical needs for culturally-accepted employment opportunities and strategically contributing to the sustainability of their organisation.  As a resul, women’s centers  feel more capable of representing their constituency’s interest at the local level.

The programme has generated employment opportunities for 416 poor women, many of whom working for the first time in their lives. On average these women made US$ 150 per month for an average period of 9 months per year.  While relatively low in both aggregate and hourly wage standards, the income women earned through the programme was in line with market wages hence only helped them realize better social status both at home and within their communities.

## 4.2. Recommendations

R1.  NRO should grant UN Women’s a no-cost contract extension a period of three months to allow for the implementation of delayed planned infrastructure development and school activities.  In the meantime, UN Women in closes collaboration with MoE and MAAN should develop a new project document for a third phase of the programme, utilising -to the extent possible- the findings and recommendations of this evaluation.

R2. In both the design and implementation of programme’s third phase, UN Women should demonstrate stronger needs-based planning and budgeting processes and mechanisms.  Hence, it is strongly recommended that the first three months of the programme’s new phase be dedicated  to school and women’s cenetrs’ selection and infrastructure needs assessments.  This would allow for the capacity building and infrastructure development activities to be implemented ahead of the beginning of the school year.   At the design and implementation stage, the new programme should plan for and allocate properly resourcing the needs assessment processes.

R3.  MoE and UN Women should develop a standard describing what a women-run school canteen should look like, and what facilities it should have.  For the purposes of initial programme planning, an average of US$ 12,000 should be budgeted for canteen equipment and infrastructure development.  Where needed, an additional amount should budgeted for bathrooms for women workers.  Actual allocation, however, should be based on needs.

R4. UN Women and MoE should agree on a revised formulation of the programme’s intervention logic and logframe.  This should be done with the view of ensuring accountability among the various partners for results.  For this purpose, it is extremely important to rethink the goal and outcomes of the programme, preferably giving more focus to women’s economic security and income (as opposed to women’s centers profits), attitudinal changes among students vis-à-vis eating habits, and community mobilisation in support of canteen operations.

R4. In conjunction with R3, MoE and UN Women should also set clearly what categories of they expect women’s centers to have on offer in the schools’ canteens on a daily and a weekly basis.  While this should be kept generic, it needs give sufficient guidance to women’s centers on what is expected of them.  The programme should devise a mechanism to minitor partner centers’ adherence to this standard, which should be the basis for an annual review of the centers’ performance in schools.

R5. The current phase’s management structure should be retained with the following additions:

- UN Women Programme Officer at UN Women (@50%)

- UN Women M&E and Reporting Officer (@100%)

- UN Women Business Development Advisor (retainer basis)

- MoE Programme Manager (@50%)

- MoE Filed Coordinator (100%)

R6. Given the fact that UN Women operates under the NEX modality, a significant level of implementation responsibility should be transferred to MAAN.  However, MAAN should ensure the allocation of highly qualified staff with gender and enterprise development expertises to the programme.  These staff should be fully dedicated the programme.

R7.  The programme’s committees established under the current phase should be activated and given more support and authority to be able to discharge their resposnibilities more effectively.  For this purpose, it is strongly recommended that the Programme Advisor at NRO is brought onto the PSC as member, along with the Deputy Ministry of Education and the MoE’s General Directors of Buildings and Finance and Adminstration.

R8.  The PSC should meet at least once every two months or when necessary.  It should keep a detailed record of its meetings and decisions in both English and Arabic.   Once signed by members, PSC meeting minutes should be widely circulated to programme partners.

R9. The PSC members, particularly UN Women’s Head of Office and MoE’s General Director of School Health, are strongly advised to organise joint field visits to schools and women’s centers.  This will not only have a positive effect at level of partners in the field, but it will also provide some context to the issues that get discussed at PSC meetings.

R11. In planning for and implementing capacity building:

- ensure timely provision of training;

- give greater emphasis to on-the-job coaching and training (as opposed to in-class training) in the areas of financial management, costing and cost control, marketing and communications;

- ensure that training methods follow learner-cantered approaches, including the preparation of customized training materials for the trainees to take away;

- make provisions for providing training on gender, particularly for programme field staff training;

- integrate of MoE staff involved in the programme in the capacity building programme both as trainers and trainees;

- give greater emphasis to documentation and dissemination of good business practices through monthly or quarterly newsletters

R12. The establishment of food production units at women’s centers has proven effective under the WRSCP and should be extended in the new phase.  To the extent possible, however, the establishment of food production units should be linked to the business model that the respective center will follow.  Hence, a clearer verification of infrastructure development and equipment needs should be ensured by the programme.  For initial planning purposes, a US$ 8,000 should be allocated for unit establishment and upgrading.  However, actual allocations should be based on both need and business model to be promoted.

R13. During the implementation of the next phase of the programme, UN Women and MoE should collaborate to commission a research to assess the financial performance of all canteen enterprises and document good business practices of partner women’s centers.  This research, which should also examine the financial conditions for the beneficiary schools, should be the basis for discussions between MoE and UN Women regarding adjustments in canteen lease fees.

R15. UN Women should plan for exit within a maximum of four years from the WRSCP, and plan well for its scaling-up.

# 5. Annexes

## 5.1. Evaluation Terms of Reference

## 5.2. List of People Met

| Norwary Representative Office |  |  |
| --- | --- | --- |
|  | Signe Marie Breivik | Programme Advisor |
| UN WOMENOMEN |  |  |
| 1 | Alia El-Yassir | Head of Office |
| 2 | Fida' Amasha | Programme Analyst |
| 3 | Myasar Da'jan | Project Coordinator |
| 4 | Odate Hanna | Project Assistant |
| 5 | Rana A'wadeh | Field Coordinator - North |
| 6 | Samah Horoub | Field Coordinator - South |
| 7 | Shurouq Hijawi | Project Manager, Ma'an Development Center |
| 8 | Siham Rasheed | MDG-F Programme Manager |
| Ministry of Education and Higher Education |  |  |
| # | Name | Position/Duty Station |
| 1 | Abdel Ra'ouf Qur'an | Field Coordinator |
| 2 | Assma' Al-Shouli | Nablus |
| 3 | Ayman Al-Kurdi | Nablus |
| 4 | Fakhria Hamdan | Nablus |
| 5 | Maisa' Al-Younis | Ramallah Office |
| 6 | Mohammad Rimawi (Dr.) | School Health Director General |
| 7 | Mu'amar Shtaiwi | Environment Department Manager |
| 8 | Nazem Al-Jundi | Nablus |
| 9 | Rafeef Younis | Nablus |
| 10 | Rana Tayyem | WRSCP Administrative Coordinator |
| 11 | Shadi Suliman | Nablus |
| 12 | Suzan Totah | Head of Nutrition and Canteen Division – MoE-Ramallah |
| 13 | Zain Hamad | Nutritionist |
| Schools Interviews |  |  |
| # | Name | Position |
| 1 | ??? | Deputy School Principal - Jerusalem Mixed School, Nablus |
| 2 | Abdallah Zaid | School Supervisor - Abu Ali Mustafa Basic School, A'rabeh |
| 3 | Adnan Abu Youssef | Head of School Health Department - MEHE Tubas District |
| 4 | Adnan Sbeeh | health Field Staff - MEHE Tubas District |
| 5 | Ahmad Jayousi (Dr.) | Field Staff - MEHE Suburbs Districti of Jerusalem |
| 6 | Ahmad Mansour | Field Staff - MEHE Suburbs Districti of Jerusalem |
| 7 | Aisha Abu Snineh | Deputy School Principal -Fatima Azzahra' School, Sa'eer, |
| 8 | Ali Freehat | School Principal - Bilal Al-Awsat School, Al-Yamoun |
| 9 | Alia' Jawhar | Volunteer - Nahda Center of Abu Dis |
| 10 | Amal Mohammad Awad | Canteen Worker - Beit Umar Women Society |
| 11 | Amal Musa Barham | School Principal - Immatain Secondary Girls School, Immatain |
| 12 | Amira Mohammad Ibrahim | Canteen Worker - Beit Umar Women Society |
| 13 | Arwa Al-Kharoubi | School Secretay - Deir Ebzei' Secondary School, Deir Ebzei' |
| 15 | Atta Al-Froukh | School Principal - Martyer Qassem Jaradan School, Sa'eer |
| 16 | Ayda Abu Laban | Head of School Health Department, MEHE Southern Hebron District |
| 17 | Aziza Shalalda | Sa'eer Municipality |
| 18 | Basema Zagharir Thwaib | MEHE Bethlehem District |
| 19 | Basma Qataqta | Chairwoman - Beit Fajjar Women Society |
| 20 | Bassima Dwikat | Chairwoman - Beta Women Development Center |
| 21 | Dawlat Abu Mahmoud | Janata & Taqou' - MEHE Bethlehem District |
| 22 | Dina Al-Biltaji | field Staff - Fatima Azzahra' School, Sa'eer |
| 23 | Dunia Zaid | School Principal - Sirris Secondary Girls School, Sirris |
| 24 | Fadel Za'arir | School Prinicipal - Ja'far Basic School, Samou' |
| 25 | Fakhria Ahmad Sawan | Chairwoman - Rural Women Development Asociation, Imm Matain |
| 26 | Fathi Da'amseh | Health Committee Arttas Boys Basic School, Arttas |
| 27 | Fatima Assad Ne'irat | Canteen Supervisor Maithalon Women Center, Rural Women Development Committee |
| 28 | Fatima Mohammad Za'aqeeq | Canteen Worker - Beit Umar Women Society |
| 29 | Fawaz Barbarawi | School Principal - Beit Ummar Basic School for Boys, Beit Ummar |
| 30 | Firas Hasan | School Principal - Al-Naqoura School, Al-Naqoura |
| 31 | Ghazi Milhem | Principal - Abu Ali Mustafa Basic School, A'rabeh |
| 32 | Hala Abu Al-Hasan | Chairwoman - A'raba Center for Women Development |
| 33 | Hanan Marei | Field Staff - Abu Ali Mustafa Basic School, A'rabeh |
| 34 | Hanan Muhana | health Field Staff - MEHE Qabatia District |
| 35 | Hania Ahmad Irshaid | Health Committee - Fatima Ghazal School, Azzoun |
| 36 | Harbi Abu Hasan | School Secretery - Hajj Mustafa Abu Khaizaran School, Tubas |
| 37 | Huwaida Awaisa | Canteen Supervisor - Wadi Fare'a Charitable Women Center |
| 38 | Ibtisam Abu Murar | Canteen Worker - Beit Umar Women Society |
| 39 | Ibtisam Slaibi | Canteen Worker - Beit Umar Women Society |
| 40 | Imad Ma'ali | Technical Deputy - MEHE Suburbs Districti of Jerusalem |
| 41 | In'am Zaidan | School Principal - Deir Ebzei' Secondary School, Deir Ebzei' |
| 42 | Jamal Ayed | School Principal - Arttas Boys Basic School, Arttas |
| 43 | Jamal Tamimi | Sa'eer Municipality |
| 44 | Kamleh Jibreel | School Secretery - Al-Huria Basic School, Taqou' |
| 45 | Karima Said Awad | Canteen Worker - Beit Umar Women Society |
| 46 | Khairieh Herzallah | Head of School Health Department - MEHE Jenin District |
| 47 | Khalid Al-Hasan | School Principal - Hajj Mustafa Abu Khaizaran School, Tubas |
| 48 | Khalid Al-Lalieh | Committee - Martyer Qassem Jaradan School, Sa'eer |
| 49 | Khawla Abu Snineh | School Prinicipal - Fatima Azzahra' School, Sa'eer |
| 50 | Kholoud Khalaf Assakreh | Project Supervisor - Janata Women Center |
| 51 | Kifaya Abu Muhsen | Chairwoman - Rural Women Development Asociation |
| 52 | Laila Abdel Fatah Hussein | Canteen Worker - Beit Umar Women Society |
| 53 | Mahdi Hassoun | Technical Deputy - MEHE Tubas District |
| 54 | Maisoun Hamida | Committee - Al-Huria Basic School, Taqou' |
| 55 | Majeda Ahmad Oudeh | Treasurer - Beit Fajjar Women Society |
| 56 | Majeda Ramadan | Head of School Health Department - MEHE Bethlehem District |
| 57 | Manal Adawi | E'bbayat, Arrtas - MEHE Bethlehem District |
| 58 | Marwan Abu Rezeq | Field Staff - MEHE Suburbs Districti of Jerusalem |
| 59 | Mirvat Abu Sha'ban | Canteens Supervisor - Mahawer Center, Hebron |
| 60 | Mohammad Abu Hamad | Health Committee - Ja'far Basic School, Samou' |
| 61 | Mohammad Abu Ithrai' | Head of School Health Department - MEHE Hebron District |
| 62 | Mohammad Jaber | Head of School Health Department - Kufr Laqef Women Charitable Center |
| 63 | Muhanad Zakarneh | Head of School Health Department - MEHE Qabatia District |
| 64 | Murad Draghmeh | Deputy School Prinicipal - Hajj Mustafa Abu Khaizaran School, Tubas |
| 65 | Mu'tasim Zuraiq | School Health Committee - Al-Naqoura School, Al-Naqoura |
| 66 | Muzna Ghaleb | Canteens Supervisor - Beta Women Development Center |
| 67 | Myasar Dalalqa | Committee - Al-Huria Basic School, Taqou' |
| 68 | Naela Shawka | Adminstrative Officer - MEHE Bethlehem District |
| 69 | Naim Al-Badrani | Deputy School Principal - Ja'far Basic School, Samou' |
| 70 | Najah Ibrahim | Canteens Accountant - Beta Women Development Center |
| 71 | Nasri Kamel Assakreh | Janata Women Center |
| 72 | Nayfeh Ta'amra | School Prcinipal - E'byyat Seconday School, E'bbyat |
| 73 | Nehaya Hamarsha | Adminstrative Officer - MEHE Qabtaia District |
| 74 | Nehaya Suliman | School Principal - Haifa and Al-Wafa School, Beit Fajjar |
| 75 | Nisreen Al-Azzeh | Field Staff - MEHE Suburbs Districti of Jerusalem |
| 76 | Nisreen Bani Oudeh | health Field Staff - MEHE Tubas District |
| 77 | Nuha Abdel Rahman Eid | Health Committee - Immatain Secondary Girls School, Immatain |
| 78 | Othman Thaher | School Health Supervisor - Sirris Secondary Girls School, Sirris |
| 79 | Qassem Zaidan | Field Staff - Martyer Qassem Jaradan School, Sa'eer |
| 80 | Raeda | Field Staff - MEHE Suburbs Districti of Jerusalem |
| 81 | Raja' Habarneh | Canteen Worker - Beit Umar Women Society |
| 82 | Rana Nofal | Committee - Al-Huria Basic School, Taqou' |
| 83 | Rassem Khalifeh | School Helath Committee - Bassam Eshak'a School, Nablus |
| 84 | Reema Khalaf | Member of the BoD - Wadi Fare'a Charitable Women Center |
| 85 | Rima Said Awad | Canteen Worker - Beit Umar Women Society |
| 86 | Sabe' Shtaieh | School Principal - Bassam Eshak'a School, Nablus |
| 87 | Samah Daraghmeh | health Field Staff - MEHE Tubas District |
| 88 | Samir Fayez | Chairwoman - Wadi Fare'a Charitable Women Center |
| 89 | Samira Al-Sha'er | Chairwoman - Taqou' Women Center |
| 90 | Sana' ??? | School Principal - Haifa and Al-Wafa School, Beit Fajjar |
| 91 | Shorouq Hijawi | Maan Center |
| 92 | Suha Aqtash | Accontant - Beta Women Development Center |
| 93 | Suha Thiab | health Field Staff - MEHE Qabatia District |
| 94 | Suhad Shakhsheer | School Principal - Sabastia School, Sabastia |
| 95 | Suzan Shahin | School Principal - Ezzarieh Secondary Girls School, Ezzarieh |
| 96 | Tahani Al-Mghier | Canteens Supervisor - A'raba Center for Women Development |
| 97 | Tahani Abdeen | Committee - Al-Huria Basic School, Taqou' |
| 98 | Tareq Al-Zeer | Field Staff - MEHE Bethlehem District |
| 99 | Thana' Awwad | School Principal - Sawahreh Girls School, Sawahreh |
| 100 | Wafa' Balatieh | Member of the BoD - Wadi Fare'a Charitable Women Center |
| Women Centers |  |  |  |  |
|  | Adla Al-Ji'an | Chairwoman - Balatta Women Center |
| 1 | Fatima E'biat | Treasurer - Fassayel Auja Center |
| 2 | Fatima Hamad | Board Member/Worker - Balatta Women Center |
| 3 | Hala Al-Shouli | Worker - Thatt Al-Nitaqeen Center |
| 4 | Hani Musa Sanad | Deputy Chairman - Arrtas Cultural hiretage Center |
| 5 | Lubna Masa'id | Deputy Chairwoman - Fassayel Auja Center |
| 6 | Maha Al-Njoum | Manager/ Chairwoman - Fassayel Auja Center |
| 7 | Mahmoud Ahmad Sa'ar | Chairman - Arrtas Cultural hiretage Center |
| 8 | Myasar Yassin | School Canteens Supervisor - Thatt Al-Nitaqeen Center |
| 9 | Rima Rohanim | Secretery of the Board - Fassayel Auja Center |
| 10 | Samah Swalha | Chairwoman - Thatt Al-Nitaqeen Center |
| 11 | Samar Jum'a | School Canteens Supervisor - Nasawi Asskar Women Association |
| 12 | Shojoun Siam | Supervisor - Nasawi Asskar Women Association |
| 13 | Suhair Kayyed | Chairwoman - Kobar Women Association |
| 14 | Waheeba Saleh | PR Member - Nasawi Asskar Women Association |
| 15 | Wala' Bassam | Field Supervisor - Fassayel Auja Center |
| 16 | Wedad Abdallah | School Canteens' Supervisor /Board Member - Kobar Women Association |
| 17 |  |  |
| School Canteens Workers |  |  |  | Thatt Al-Nitaqeen Center, Al-Naqoura Mixed School |
| 1 | Shadia Hasheesh | Thatt Al-Nitaqeen Center, Al-Naqoura Mixed School |
| 2 | Imm Hamed | Al-Quds Mixed School, Balatta Women Center |
| 3 | Myasar Mustafa Zammel | Mustafa Abu Khayzaran School, Tubas |
| 4 | Jinan Abdel Latif | Ghassan Al-Shak'a School, Nablus |
| 5 | Fatima | Ghassan Al-Shak'a School, Nablus |
| 6 | Abla | Women Committees |
| 7 | Hana' | Women Committees |
| 8 | Mahdieh Mahmoud | Imm Matain Secondary School |
| 9 | Nuha Swedan | Fatima Ghazal School, Azzoun |
| 10 | Amal Swedan | Fatima Ghazal School, Azzoun |
| 11 | Suha Shalaldeh | Qassem Jaradat School, Sa'eer |
| 12 | Aisha Abu Snineh | Fatima Azzhara' Basic School, Hebron |
| 13 | Sara Sufian Jibreel | Al-Huria School, Taqou' |
| 14 | Imm Samir | Arrtas Basic Boys School, Arrtas |
| 15 | Samir | Arrtas Basic Boys School, Arrtas |
| 16 | Majeda Oudeh | Supervisor, Beit Fajjar |
| 17 | Khawla Aref | Haifa Girls School, Beit Fajjar |
| 18 | Karima Aref | Haifa Girls School, Beit Fajjar |
| 19 | Madiha Al-Halabi | Ezzarieh Girls School, Ezzarieh |
| 20 | Hamda | Sawahra School, Sawahra |
| 21 | Yusra Khalil | E'bbyat School, Ebbyat |

## 5.3. Information on the evaluation team consultants

Amer Madi is a consultant with the Al Sahel consulting firm based in the West Bank. He has an MBA from Eastern Michigan University. He specialises in socio-economic research; gender; planning, monitoring, evaluation and management. He has provided capacity-building support, carried out baseline assessments and impact assessments and led mixed-method evaluations for a wide range of local and international NGOs, UN agencies and public sector organisations.      He has also designed and delivered several training programmes, including two 40-hour training programmes on gender mainstreaming in poverty alleviation and rural development programmes (IFAD) and qualitative assessment methods (WFP). In 2009, Mr. Madi led the evaluation of the pilot phase of the Women-Run School Canteens project.

Safa’ Abdelrahman is a private sector development expert and a professional project manager with a demonstrated experience in policy analysis and managing complex development projects.  Her critical mass of experience is in the Information and Telecommunications Technology (ICT), and the fast moving consumer goods (FMCG) sectors.  Ms. Madi was the Executive Director of the Palestinian Information Technology Association of Companies (PITA), a non-governmental member-based organization that advocates for the ICT sector’s interests and growth.  Throughout her tenure with PITA, she led several initiatives that set a mark for PITA’s work within the sector, including organizing the first national ICT exhibition (ExpoTech), leading the preparation of the ICT sector’s plan within the framework of the Palestinian Education Initiative, and contributing to the drafting of several policy analysis briefings.  She is also the chairwoman of the Palestine Internet Society (www.isoc.ps).  Ms Madi was commissioned by Solutions for Development Consulting, a private consulting firm, to manage InTajuna, an SDC- and private sector-funded project that aimed to maximize awareness and shift preferences of the Palestinians towards Palestinian made products.  While with Solutions, Ms. Madi also coordinated trade policy research that sought to prepare and disseminate a joint Palestinian and Israeli private sector agreed position paper on the future trade relationships and agenda with the aim of revitalizing the Palestinian Economy and enhancing future cooperation between the two sides. In December 2008 Ms. Madi was hired by GTZ to serve as an advisor to the Private Sector Development Programme (PSDP), a programme that provides technical support to private sector institutions and Palestinian Authority institutions working to support private sector development and regulation. Within her scope in the PSDP Ms. Madi was responsible for the design and management of the two components of the programme which aimed at strengthening the capacities of Ministry of National Economy and key private sector organizations to improve the regulatory, administrative and institutional framework conditions and support structures for the SMEs in Palestine.  Ms. Madi joined Al-Sahel Co. as a senior management consultant in April 2011.

Shawkat Sarsour has very substantial experience of civil society development and of donor harmonisation/aid effectiveness. His recent consultancy assignments in the oPt include a review of multi-donor funded support to NGO Development Center, reviews of donor support to the Palestinian Ministries of Agriculture and Social Affairs, as well as several evaluations of bi- and multilateral capacity building interventions.

These outcomes appear in the Cost-Sharing Agreement signed between UN Women and NRO.  A different formulation of outcomes 1 and 2 appears, however, in the Programme Document.

In line with R7, there is no need to augment UN Women’s field presence capacity.

At that time, UN Women was called UNIFEM.

UN Women, Project Document, pg. 9.

These outcomes appear in the Cost-Sharing Agreement signed between UN Women and NRO.  A different formulation of outcomes 1 and 2 appears, however, in the Programme Document.

The project would cover, respectively, 100% and 30% of the cost of the lease of the school canteens for the first and second year of the project to enable the women centers to build the financial capital (through profit) to pay the lease fully on their own during the third year of the project.

The schools canteens lease subsidy.

Trish Silkin provided valuable inputs to the review reports.  For further information on the review team consultants please see Annex I.

MoE policies stipulate that canteen leases must be paid to the school by the lessee within one week of the beginning of the academic year.   Schools have to show proof of receipt of payment in their budget submissions to MoE to be able to get these budgets approved for expenditure on operational non-salary expenditures.

While canteen infrastructure development needs were identified early in the programme, tenders for infrastructure works could not be floated before the MoE receives funds from UN Women for this purpose.    Moreover, infrastructure work could not be initiated during the academic year.

Training of women’s centers targeted in the first year of the programme was conducted by MAAN during the first months of the second semester of the Programme’s first year.  This meant that 6 of the 15 women centers targeted in the first year of the programme ran school canteens for a whole semester without necessarily having the capacity to do so.  Some of them faced serious financial problems as a result.

The PA has implemented a host of reforms between 2002 and 2004 to improve public financial management and transparency.   These reforms included establishing tight controls over commitments and expenditures through placing Ministry of Finance Financial Controllers in every line ministry to approve all financial commitments and payments made by line ministries, including payments against donor-funded and approved activities.  While a positive development, the financial control function often causes delays in processing contracts and payments due to the limited human resources and complex procedures.

Example of such lack of authority include expediting transfer of funds and forcing schools to adhere to some of their contractual obligations to the women centers.  This was especially true in three of the six meetings held where staff subordinate to the General Director of School Health and the Head of UN Women oPt Office represented their organisations in the PSC meeting.

The contract agreement drawn between women’s centers and the respective schools for the lease of the canteen stipulated the general types and categories of foods that women’s centers should make available in the canteens.  Stipulations, however, did not provide enough clarity with regard to the variety that needs to be available (for example, how many different varieties of sandwiches shoud be available during the week and on a daily basis; what substitution can be made).  Expectations with regard to the types and proportion of the foods on offer that need to be produced by women’s centers were also not clearly formulated.  This not only rendered MoE officials’ judgement on improvements in food variety largely subjective, but it sometimes lead to conflicts between MoE staff and women’s centers.

Thirty two of the 33 the school principals interviewed during the evaluation indicated to substantial improvements in the quality and variety of foods available through their school’s canteen.  The one principal that did not indicate to improvements in this regard did not dismiss that the quality and variety of food is good, and highlighted that the women that were running her school’s canteen before the project had offered the same foods that were offered by the women center.

The evaluation team requested to obtain detailed financial information on the programme’s expenditures but did not receive them.  Hence, the figure of US$ 875,000 is based on average of US$ 5,500 allocated per schools over two years for canteen rehabilitation and equipment.  The actual figure, however, is believed to be significantly higher given the fact that additional funds were allocated to canteen development from savings accrued as result of favourable changes in the NOK/US$ exchange rate.

The evaluation found sharp contrasts in the way funds are allocated to individual schools in the different districts.  For example, in South Hebron District the Head of the School Health Department allocated US$ 4,000 dollars to each beneficiary school for canteen development.  In Nablus, allocations were made on the basis of perceived priorities of the Head of the School Health Department in the district.  This meant that schools were receiving anywhere between US$ 1,000 – US$ 10,000 for canteen development.  In Bethlehem,  the Head of the School Health Department in the district exercised own discretion in allocating funding, but generally tried to be equitable in allocating funds.  In North Hebron District, funds were allocated for canteen skeletal works in some schools, which forced women centers to operate from existing structured.  In Qalqlia, canteen infrastructure funds were in a few instances allocated to schools that were not participating in the programme.  According to MoE, “Some schools in Qalqilia didn't need canteen rehabilitation or was not possible, therefore funds were transferred to other schools participating in programme.”

The approach to capacity building was implemented as planned, but the timing of training delivery was not during the first and second years.

Impact areas discussed here are limited to those for which data was available to the evaluation team and those that can be either gauged or measured with a fair level of accuracy.  Impact that could not be measure or ascertained by the evaluation team, including potential impact areas highlighted in the ToR but could not be verified, are not covered in this section.   Also not covered here are the negative impacts.  These were largely anecdotal and could not be verified by the evaluation team.

In line with R7, there is no need to augment UN Women’s field presence capacity.

Dr. Rimawi was not available for an in-depth interview.  The evaluation team was able to meet with him, however, during the evaluation kick-off meeting held at MoE.