Terms of Reference - Final Project Evaluation “Advancing Women’s Economic and Social Rights in Serbia and Montenegro” 
Background, Purpose and Use of Evaluation
Over the past years, UN Women has provided support to national and local stakeholders in strengthening democratic governance and advancing gender equality through initiatives aimed at enhancing women’s ecomonic and social rights.
In 2010, the UN Women Sub-regional Office for Central & South Eastern Europe (CSEE) has launched a four-year regional project „Advancing Women’s Economic and Social Rights in Serbia and Montenegro“, financed by the Government of the Kingdom of Norway and UN Women. The project is a follow-up to two UNIFEM CEE sub-regional projects that were implemented in 2006-2009, namely “Accountability for Protection of Women’s Human Rights” (in Bosnia and Heregovina, Kosovo under SCR 1244, Montenegro, and Serbia) and “Gender-Responsive Budgeting in South-East Europe” (in Albania, Bosnia and Herzigovina, F.Y.R. Macedonia, and Serbia). 

The overarching goal of the project is to contribute to the elimination of gender-based discrimination in the labour markets in Serbia and Montenegro by strengthening the capacities of duty-bearers and rights-holders to implement international and national commitments to women’s economic rights. The project aims to strengthen the capacities of key labour market institutions, employment services and complaint mechanisms (labour inspectorates, judges, the ombudsman’s office) in both Serbia and Montenegro to mainstream gender in their policies, operations and budgets. It will also strengthen the capacities of gender equality mechanisms (GEMs) on all administrative levels (national, provincial and local levels) and gender advocates in civil society to advocate and to integrate gender equality into laws, strategies, policies and budgets.
This final evaluation of the project is donor mandated and in compliance with UN Women’s Evaluation Policy requiring mandatory evaluation of programmes with budgets over 1 million USD.. 

The evaluation will: 

· assess UN WOMEN’s contribution to results, including the effectiveness of programming, strategies in implementing global commitments within national priorities for fostering women’s economic and social rights.

· map the contextual factors that enabled or restricted the achievement of results, provide an assessment scheme to measure their impact on the project. 
· evaluate UN WOMEN’s organizational performance with respect to the project.  
· evaluate the project design, project strategies, project management, including project monitoring. 
· assess the stakeholder’s and beneficiaries perspective on the usefulness of interventions and their overall satisfaction with the project.

It will set forward-looking recommendations on how to strengthen UN WOMEN’s programming, monitoring, and evaluation system at the project and other relevant levels. 

The final evaluation will support the planning of follow-up activities by identifying successful approaches and spaces to further enhance performance. The final evaluation will serve as a tool and learning product to secure future progress.  

The evaluation’s primary audience are the project stakeholders, donors, partner organisations, as well as UN WOMEN field-based and regional offices and headquarters. 

Context of the Evaluated Project

The “Advancing Women’s Economic and Social Rights in Serbia and Montenegro” project continued previous efforts to enhance women’s rights (in particular economic and social rights) in the two countries. 
Over the past years, both Serbia and Montenegro have established legal and policy frameworks supporting the advancement of women’s rights and gender equality, and established gender equality mechanisms at the executive level. European integration, a key political priority for both countries, has to a large extent, driven changes in legislation, policies and institutional frameworks. One of the key national commitments is in the area of improvement of women’s economic position, as stated in National Action Plans on gender equality, and in light of the fact that women’s participation on the labour market is still not on par with that of men. Provisions related to women’s labour rights are included in the Gender Equality Laws and Labour Laws of the two countries. However, policy and legal commitments have not been fully implemented and translated into concrete advances for women, especially those from specific groups of the population. The latest CEDAW Committee Concluding Observations for Montenegro (as of October 2011) and for Serbia (as of June 2007) point to implementation gaps and to the need for challenging still entreched gender stereotypes that affect women’s equal access to and benefiting from paid formal employment. 
Description of the Project

“Advancing Women’s Economic and Social Rights in Serbia and Montenegro” regional project is funded by UN Women and the Government of the Kingdom of Norway with a total project budget of 2,600,504 USD. The project started in January 2010 and is planned to finish in December 2013. The project covers Serbia and Montenegro.
Chain of results:
The overarching goal of the project is to contribute to the elimination of gender-based discrimination in the labour markets in Serbia and Montenegro by strengthening the capacities of duty-bearers and rights-holders to implement international and national commitments to women’s economic rights. 

Advancing towards this goal, the project focuses on achieving the following three outcomes:

Outcome 1: Relevant laws and bylaws, and national, provincial and local policies and budgets related to economic security and rights, especially employment, are passed or amended to be more in line with international and national commitments to gender equality and women's human rights.

Outcome 2: Key policy institutions, service delivery institutions and complaint mechanisms in Serbia and in Montenegro have increased capacities and improved procedures and incentives to implement existing laws and policies that promote and protect women's economic security and rights, especially with regards to employment.
Outcome 3: Gender Equality Mechanisms (GEMs), gender equality experts, advocates and their organizations and networks in Serbia and Montenegro enhance their capacity and influence to ensure that there are strong gender equality dimensions in laws and national, provincial and local policies, strategies and budgets that are relevant to women's economic security and rights.
In order to achieve these outcomes, specific outputs are: 

Output 1.1.: A relevant body of knowledge on the development of laws, bylaws and national, provincial and local policies and budgets that promote gender equality and protect women's labour rights is produced and made accessible.
Output 1.2.: Effective mechanisms for dialogue on the development and improvement of laws, bylaws, policies and budgets  that promote gender equality and protect women's labour rights exist, between key policy institutions, service delivery institutions and complaint mechanisms, on the one hand, and GEMs and other gender equality advocates, on the other hand.
Output 2.1.: Capacities of key policy, service delivery and social dialogue institutions on the national, provincial and local levels to mainstream gender equality and women’s human rights into their policies, operations and budgets are enhanced.
Output 2.2.: Capacities of complaint mechanisms to mainstream gender equality and women’s human rights into their policies and operations are enhanced.
Output 3.1.: Gender Equality Mechanisms (GEMs) at all administrative levels have increased their capacity to integrate gender into laws and bylaws, as well as national, provincial and local strategies, policies and budgets.

Output 3.2: Gender equality advocates, experts and their organizations and networks have strengthened their capacities to advocate for gender-responsive laws, policies, strategies, budgets, and practices of employers to advance women's economic security and rights at national, provincial and local levels.
Key project strategies:
Capacity development of duty-bearers,  capacity development  of rights-holders and evidence-based policy advocacy are key strategies for the project.
Linkages to UN WOMEN strategic documents and national priorities

The project outcomes and outputs feed directly into current UN Women CSEE Workplan for 2012-2013 (previously CEE Sub-regional Strategy (2008-2011). 

Thematically, the project focuses on the advancement of women’s economic and social rights in the context of ongoing policy and institutional reforms in Serbia and Montenegro that are driven predominantly by the EU integration processes, but importantly, focusing also on the implementation of relevant CEDAW Committee recommendations and recommendations following the 2009 EU Progress Reports for Serbia and Montenegro. 
Project Partners

To achieve the above mentioned outcomes the project engages various partners from government at different levels (national, provincial, local), independent human rights institutions, civil society and academia. 
Institutions in Serbia: 

· Ministry of Labour, Employment and Social Policy – Labour Inspectorate
· Ministry of Finance and Economy

· Judicial Academy

· National Employment Service

· Gender Equality Council

· Social and Economic Council 

· Commissioner for the Protection of Equality 

· Statistical Office of the Republic of Serbia

· Global Compact Serbia 

· Provincial Secretariat for Economy, Employment and Gender Equality

· Republic Protector of Citizens

· Provincial Ombudsman

· Commission for Gender Equality of the Municipality of Stara Pazova

· Commission for Gender Equality of the City of Kragujevac

Civil society organizations and associations of employers institutions in Serbia: 

1. Center for Support of Women (Kikinda and Novi Sad) 

2. Association of Business Women (Belgrade) 

3. Victimology Society of Serbia (Belgrade) 

4. Fenomena (Kraljevo) 

5. Femina Creativa (Subotica)

6. Women’s Center (Užice)

7. Women’s Initiative (Priboj)

8. Peščanik (Kruševac)

9. Serbian Association of Employers.

Institutions in Montenegro: 

· Department for Gender Equality of the Ministry for Human and Minority Rights 

· Employment Agency 

· Office of Protector of Human Rights and Liberties in Montenegro

· Parliamentarian Committee for Gender Equality

Civil society organizations and association of employers in Montenegro:

· ANIMA– Center for Women`s and Peace Education

· Center for Development of Nongovernmental Organizations (CRNVO)

· Montenegrin Federation of Employers

· SOS Telephone for Women and Children Victims of Violence Podgorica

· Women’s Alliance for Development

Execution and Project Management 

UN WOMEN (CSEE SRO) served as the executing and implementing agency of the project through the Project Office Serbia.
Structure of Project Management:

· Project manager (international) based in Belgrade, Serbia, reporting the Regional Programme Director for Central and South Eastern Europe 
· Project associate for the overall project, based in Belgrade, Serbia 

· Two national project officers in Serbia, focusing on women’s labour rights and gender responsive budgeting respectively

· National project officer in Podgorica, Montenegro

The Project had a coordination/advisory mechanism „Partner Coordination Group“, which acted as a forum for coordination among project partners, and policy and quality assurance, providing strategic and policy guidance to support the achievement of programme results and ensuring stakeholder participation. 
Scope of Evaluation, Key Evaluation Issues, Questions and Criteria

The evaluation is a final project evaluation. It will cover activities conducted in the project’s two countries Serbia and Montenegro that have taken place since the beginning of the project (January 2010) until the time of the evaluation. 

Evaluation Questions:

For the purposes of this evaluation, the key questions identified by the stakeholders were organized in line with OECD DAC criteria under several main evaluation criteria: relevance, effectiveness, efficiency, sustainability, and (road to) impact
. Furthermore, the evaluation will assess capacity development, partnerships, visibility and RBM/monitoring/evaluation as cross-cutting themes.
Relevance and Coherence:

1. To what extent do the project’s objectives and target groups address identified needs in the national and regional context?

2. Were the relevant normative and strategic frameworks adequately articulated within UN WOMEN (internally)? 
3. Are the objectives formulated at the start of the project still valid? Were there any changes within the environment of the project which would lead to a need to re-phrase them?
Effectiveness:

4. To what extent did adequate planning and project design contribute to the achievement of the programme objectives? 
a. What are the changes produced by the project at the national and regional level? 
b. Were the changes produced by the project in line with the objectives? 

c. What has been the progress made towards achievement of the expected outcomes and expected results? 
d. What are the results achieved? 
e. To what extent were the originally defined objectives of the intervention realistic (achievable)?
5. Is the project design articulated in a coherent way? Are goals, outcomes, and outputs clearly articulated? 
6. What were the reasons for the achievement or non-achievement of results? 
a. To what extent is UN Women particularly well placed to manage this project and to work towards its objectives? 
b. Which factors enable UN Women to effectively engage in the activities of the project?
c. To what extent have the existing management structures supported the programming and implementation, including monitoring?  
d. How were lessons learned identified in previous UN Women evaluations utilized to inform this project and its management structures?
7. How were relevant actors and stakeholders included in UN WOMEN programming and implementation, incl. policy advocacy processes? To what extent have beneficiaries been satisfied with the results? (Please use scoring and consider using an online survey to reach to a larger number of beneficiaries.)

8. To what extent did the project produce unintended effects?
Efficiency:

9. To what extent were the project funds managed effectively? Could the activities and outputs been delivered with fewer resources without reducing their quality and quantity? 

10. Have UN Women’s organisational structure, managerial support and coordination mechanisms effectively supported the delivery of the project?
Sustainability:

11. Is the project supported by national/local institutions? Do these institutions demonstrate ownership of the project results, leadership, commitment and technical capacity to maintain/implement the benefits of the project? 

12. What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time following the end of the project? In how far were the project results institutionalized? 
Impact (road to):

13. What are the intended and unintended, positive and negative, long term effects of the project?

14. What would the development have been like without the project intervention? 
Forward looking insights
:
15. Should women’s economic rights (WER) programming continue in the future? Were the approaches and strategies used by UN WOMEN effective, relevant and potentially sustainable? Which other approaches/beneficiaries etc. should be considered? 

16. What did the stakeholders and beneficiaries consider as the most necessary approaches/areas of future WER interventions in their respective countries? At the regional level?

The final set of evaluation questions will be agreed in the inception report. 
The project performance should be assessed based on the scoring rubric (Table 1) for the following evaluation domains, countries, the regional aspect and finally at the project level. In the overall project assessment, the country-based activities should be weighted with 30% (Montenegro) and with 70% (Serbia) .
	
	Montenegro
	Serbia
	Project overall

	Relevance/Coherence
	
	
	

	Effectiveness
	
	
	

	Efficiency
	
	
	

	Sustainability
	
	
	

	Impact
	
	
	

	Capacity Development
	
	
	

	Partnerships, Coordination
	
	
	

	RBM/M&E
	
	
	


Table 1: Scoring rubric for project’s performance 

	Rating
	Performance description

	Excellent (Always) 
	Performance is clearly very strong or exemplary in relation to the evaluation question/domain. No gaps or weaknesses were identified.

	Very good (Almost always)


	Overall strong, but not exemplary performance on virtually all aspects of the evaluation question/domain. Weaknesses are not significant and are managed effectively.

	Good (Mostly, with some exceptions)
	Performance is reasonably strong on most aspects of the evaluation question/domain. No significant gaps or weaknesses, and less significant gaps or weaknesses are mostly managed effectively.

	Adequate (Sometimes, with many exceptions)
	Performance is inconsistent in relation to the question. There are some serious but non fatal gaps/weaknesses. Meets minimum expectations/requirements as far as can be determined.

	Poor (Never or occasionally with clear weaknesses evident)
	Performance is unacceptably weak in relation to the evaluation question/domain. Serious and widespread weaknesses on crucial aspects. Does not meet minimum expectations/requirements.

	Insufficient evidence 
	Evidence unavailable or of insufficient quality to determine performance.


Source: Adapted from “Policy and Guidelines for the Conduct of External Evaluation and Review”, New Zealand Qualifications Authority, September 2009 and further drawing on Rich Tobin.

Evaluation Approach
The overall approach of this evaluation is utility-focused, as advised by some of the intended users of the evaluation, and aligned with UN WOMEN’s evaluation strategy guidelines, UNEG norms and standards, and based upon emerging recommendations from the field of project evaluation. (Relevant information and background notes can be obtained from http://www.unwomen.org/about-us/evaluation/). The evaluation should adhere to UN WOMEN Evaluation Report Quality Standards. 

UN WOMEN’s evaluations are expected to adhere to a framework supporting human rights-based (HRBA), results-oriented and gender responsive monitoring and evaluation. Towards this purpose, the evaluation of the project will encompass the principles of gender equality and human rights, ensuring that the evaluation process respects these normative standards, and aims for progressive realization of the same by respecting, protecting and fulfilling obligations of non discrimination, access to information, and ensuring participation through a combination of consultative and participatory evaluation approach. For more details on human rights and gender equality in evaluation refer please to the UNEG Handbook Integrating Human Rights and Gender Equality in Evaluation – Towards UNEG Guidance.

The evaluation will be conducted in a transparent and participatory process involving relevant UN WOMEN stakeholders and partners.

The evaluating team may further define the overall approach by adopting complementary methodologies and approaches.

Evaluation Process

The evaluation process will consist of the following phases:

· Preparation, mainly devoted to structuring the evaluation approach, preparing the TOR, compiling programme documentation, and hiring the evaluation team; (implemented by UN WOMEN).
· Inception, which will involve discussion and if need be reconstruction of theory of change, project activities analysis, inception consultations, inception report with detailed timeline, distribution of responsibilities among team members and  evaluation methodology; a list of stakeholders will be provided by UN WOMEN at the beginning of the evaluation.

· Data collection and initial analysis, including country based collection of information (national conslutants), desk reviews and field visits of team leader and team members. 

· Data analysis, interpretation and synthesis stage, focusing on structuring of findings, analysis of findings, their interpretation and presentation in a  full draft evaluation report (full draft evaluation report is a fully completed report with all annexes).
· Submission of draft evaluation report for feedback from UN WOMEN and incorporation of relevant feedback.
· Validation of draft report by stakeholders (minimum 4 stakeholders per country).

· Finalization of report.
· Preparation of a Management Response and uploading the report on the Evaluation Resource Centre site (implemented by UN WOMEN).
Tentative schedule of evaluation activities: 

	Phase and Deliverables
	Timeline 
	Responsible person and estimated # of workdays (WD)

	Start of contract 
	No later than by 10 September
	M&E Specialist in cooperation with CEESRO Operations Manager

	Inception report and preparation of field missions
	10 - 20 September
	Evaluation team

Team Leader 5.5 WD

Nat Cons 3 WD

	UN Women provide feedback on inception report
	27 September
	

	Field mission 

Data collection in field & initial analysis
	1st half of October 
	Evaluation Team Leader and National Consultant 
Team Leader 8 WD (5 days in Serbia, 3 days in Montenegro)
Nat Cons 8 WD (5 days in Serbia, 3 days in Montenegro)

	Data analysis, interpretation & synthesis
	
	Evaluation team



	Submission of full draft evaluation report to UN WOMEN for feedback and quality assurance
	
	Evaluation team

Team Leader 9 WD

Nat Cons 4 WD

	
	
	M&E Specialist, Project Manager, CEESRO Programme Specialist, UN Women Eval Office (if needed)

	Incorporation of feedback by UN WOMEN and submission of final draft to UN WOMEN
	5 November - 10 November
	Team Leader 2.5 WD

Nat Cons 2 WD 

	Review of final draft by UN WOMEN (if needed another round of feedback/incorporation of feedback)
	 11 November – 25 November
	M&E Specialist, Project Manager, CEESRO Programme Specialist

	Final draft sent for validation to stakeholders
	25 November
	Nat Cons 0.5 WD

	Validation by stakeholders
	2 December
	Stakeholders (Project Advisory Board and other stakeholders)

	Submission of final eval report with incorporated  feedback from stakeholders
	4 December
	Nat Cons 0.5 WD

Team Leader 0.5 WD

	Preparation and approval of management response 
	5 December – 11 December
	M&E Specialist, Project Manager, CEESRO Programme Specialist, Regional Programme Director/OIC

	Dissemination of final eval report
	12 December
	M&E Specialist


An updated, more detailed, schedule of evaluation activities will be part of the inception report, but the overall timeline of the evaluation and the key deliverables should not be significantly changed.
Evaluation Design and Methods
For its design, the evaluation will deploy a theory of change approach
 to analyze how UN Women’s support is provided in advancing gender responsive policies. The theory of change will take into consideration the UN Women Strategic Plan 2011-2013 and other strategic and policy frameworks that inform UN Women’s work in this area.

The evaluation will use a variety of data collection methods and sources with a view to triangulate data. The methods should be participatory, ensure collection of disaggregated data, interrogate gender roles, be context and culturally sensitive and whenever possible mixed (qualitative and quantitative). 

Following methods are suggested for answering the evaluation questions: 

· Desk review of documents

· Semi-structured key informant interviews

· Group discussions

· Face-to-face and self administered, incl. online, surveys

The evaluators should suggest further methods as appropriate.

Existing information sources:
The evaluation team needs to make themselves familiar with UN WOMEN and other documents to engage with the background of the project and the situation of women’s rights in the region. 

Key documents in this regard are:

· Project documentation, incl. logical framework, budgets, donor progress reports, mid-term review report etc.

· Strategic documents of UN WOMEN (Annual Workplan 2011-2013)

· CEDAW comments 

· National Strategies on Gender Equality
· UNDAF reports in the countries

Existing information sources about the project will be shared electronically via an online collaboration platform (dropbox). 

Stakeholder Participation:
This evaluation has been created with an inclusive approach, incorporating suggestions for the evaluation from members of the Evaluation Reference Group who play advisory and decision-making role in this evaluation. 
Expected Products:
All deliverables should be submitted to the evaluation task manager. The reports should be written in English, in a succinct and user-friendly language. 

· An inception report. The report will contain: 

· Description of evaluation objectives, scope, methodology/methodological approach, data collection, list of key informants/agencies, review of evaluation questions, performance criteria, issues to be studied.
·  Description of theory of change/intervention logic

· Work plans for all members of the evaluation team with clear timelines and responsibilities.

· Evaluation matrix (with at least eval questions, indicators, methods of data collection, data sources, evaluation criteria)
· A full draft evaluation report. Should be no more than 40 pages (excluding Annexes). The structure of the full draft and final reports should be as follows:

· Executive Summary (to be prepared for final report)

· List of acronomyms

· Programme description

· Evaluation Purpose

· Evaluation Methodology and Process

· Findings organized by evaluation questions (numbered)

· Lessons Learnt/Good Practices

· Recommendations

· Annexes (including interview list without identifying names for sake of confidentiality/anonymity, data collection instruments, list of all  documents consulted, Terms of Reference, evaluation matrix)
· Validation of findings at the national level in the form of a meeting with stakeholders  or electronically (to be determined in consultation with UN WOMEN)) 
· A final report with incorporated feedback of UN WOMEN and stakeholders. 
Evaluation Team - Composition, Experience and Competencies Requirements

A team of 2 consultants will be recruited for this evaluation. The team will consist of Team Leader (Senior Evaluation Consultant) and one national consultant based in Serbia, who will cover both Serbia and Montenegro. 

The team leader will have essential expertise in development programme evaluation, ability to conduct qualitative and quantitative analysis, requisite skills in facilitation, interviewing and writing/reporting, and language proficiency in English.

The team member will have evaluation related expertise, knowledge of gender issues and public administration. S/he will be fluent in English and the respective local language/s.

All team members need to be familiar with human rights and gender responsive approach to evaluation.

Team Leader: Competencies, Experience, Education and Language requirements: 

· At least 5 years of demonstrated experience in evaluation of international development projects and programs

· Demonstrated evaluation experience on gender issues incl. gender responsive policies, women’s empowerment, public administration
· Demonstrated work experience in/on South Eastern Europe 

· Demonstrated experience with applied research with data collection, analytical and presentation skills and demonstrated ability to structure information

· Excellent interpersonal, communication and interview skills

· Excellent writing skills in English
· Experience as a team leader of multinational teams, demonstrated cultural sensitivity

· Prior experience working for international organizations

· Master’s degree in a relevant field (social sciences, e.g. sociology, political science, international relations, legal studies, public policy, international development) field 

· Integrity

· Knowledge of the local language is an advantage.
Team members: Competencies, Experience, Education and Language requirements 

· At least 3 years of demonstrated experience in evaluation, data collection, incl. interviews, analysis
· Knowledge of gender issues and public administration in Serbia and Montenegro
· Master’s degree in a relevant field (social sciences, e.g. sociology, political science, international relations, legal studies, public policy, international development) field
· Proven experience as a team member in multinational teams
· Integrity

· Excellent language knowledge of the respective state language 
· Good writing skills in English.

Ethical Code of Conduct

All members of the evaluation team are required to follow the UNEG ethical code of conduct. (hhtp://www.unevaluation.org/unegcodeofconduct)

Management of Evaluation

This evaluation is managed by the UN WOMEN Sub-regional office for Central and South Eastern Europe.  The Evaluation Task Manager in UN WOMEN is the CSEE SRO Monitoring and Evaluation Specialist. 

� The Impact will be assessed to the extent possible given the timing of the evaluation. In the context of this project evaluation, the “effectiveness” criteria will measure the extent of achievement of outcomes and outputs. “Efficiency” will assess quantitative and qualitative outputs, in relation to the inputs of the project. The questions categorized under “relevance” will assess the coherence of the project’s vision and strategies with UN WOMEN’s organizational goals, the regional contexts and strategies and how the project adapted to these factors. Evaluation questions that refer to “sustainability” examine whether and how the benefits generated will continue at the end of the project, for a reasonably long period of time. Sustainability may refer to the financial or technical capacity of partner organizations to continue the initiative, national ownership of the initiative, and adaptive, operational, or management capacities of national partners.  





� The theory of change approach to evaluation is a widely deployed evaluation methodology that makes assumptions explicit about how program is supposed to work and create social change. It focuses on the causal relationships between resources, activities, short-term and long-term outcomes and the context of the intervention, including its unintended consequences. Like any planning and evaluation method, theory-driven evaluations require the stakeholders to be clear on long-term goals, identify measurable indicators of success and formulate actions to achieve goals. However, its focus on causal relations between resources, activities, outcomes and the context of intervention makes this method particularly suitable for the assessment of complex programmes. The theory-driven approach makes the programme transparent, allowing the stakeholders to see how it is thought to be working from multiple perspectives. It helps to identify critical areas and issues on which the evaluation should focus. Overall, a theory-driven approach by mapping a process of change from beginning to end establishes a blueprint for the work ahead and anticipates its effects, and it reveals what should be evaluated, when, and how.





1

