United Nations Entity for Gender Equality and the Empowerment of Women

Terms of Reference - Final Project Evaluation

“Advancing the Implementation of UNSCR 1325 on Women, Peace and Security in the Western Balkans (2011-2013)”

Job Title:	Senior Evaluation Consultant

Vacancy:	External

Duty Station:  Sarajevo, Bosnia and Herzegovina with travel to Kosovo (under SCR 1244), the former Yugoslav Republic of Macedonia, and the Republic of Serbia

Advertised:	Internationally

Language:	English

Contract type:	Service Contract

Duration:	25 days

Starting date:	01 July 2013

BACKGROUND

Western Balkan conflicts of the 1990s led to the emergence of new states and entities where security, including at the sub-regional level, continues to play a critical role in post-conflict reconstruction, democracy building and the protection and promotion of human rights. This state of affairs, coupled with national aspirations to join the European Union has offered a set of unique opportunities for governments, security actors and civil society to work together in democratizing and mainstreaming gender within their security sector and other relevant structures, policies, procedures and budgets.  Against positive tides for progress are considerable obstacles, some of which reside within the legacy of conflict that disproportionately affected women and girls, especially in terms of sexual violence (and continued stigmatization), social/familial disintegration and economic disempowerment. The conflict/post-conflict period served to strengthen an environment characterized by high levels of gender based violence and discrimination, including within the political sphere where women are by in large excluded from post-conflict decision making processes. Such exclusion invariably leads to a deficits in adequately addressing women’s and girl’s concerns, their human rights and post-conflict accountability.

Within thematic peace and security mandate in the Western Balkans, UN Women efforts dedicated to addressing the above referenced are articulated under the regional project, Advancing the Implementation of UNSCR 1325 on Women, Peace and Security in Western Balkans. This initiative that commenced in January 2011 and concludes in December 2013 supports key security and civil society actors in advancing the implementation and monitoring of commitments under UNSCR 1325 (and related Resolutions 1820, 1888, 1889 and 1960) in national/territorial laws, policies, strategies and plans in Bosnia and Herzegovina, Kosovo (under SCR 1244), the former Yugoslav Republic of Macedonia, the Republic of Serbia, and regionally (South-East Europe/Western Balkans).  In this latter regard, the project fosters regional cooperation and networking (between civil society, gender experts, advocates, civil servants, and parliamentarians) through the development of an enabling environment for information and knowledge sharing and the exchange of good practice on the implementation women, peace and security commitments.  This outcome is being achieved through the discharge of the following three outputs:

Output 1: Improved individual and institutional capacities of key security actors at different levels to formulate, implement and effectively monitor commitments under UNSCRs 1325, 1820,1888 and 1889 (and CEDAW);

Output 2: Increased capacities of women's organizations to effectively advocate for women's and girls' human rights and needs in conflict and post-conflict situations and to monitor commitments under relevant international and national/territorial frameworks (CEDAW, UNSCR resolutions, national/territorial laws, strategies and action plans); and

Output 3: Enhanced regional cooperation, coordination and networking among specialized governmental and non-governmental actors towards the fulfillment of women's and girls' human rights and security needs in South East Europe and the Western Balkans.

The purpose and role of evaluation in UN Women is to enhance accountability, inform decision-making and to contribute to learning on the best ways to achieve gender equality and women’s empowerment through its operational and normative work.  As a member of the United Nations Evaluation Group (UNEG), UN Women follows its norms and standards. UN Women evaluations also adhere to gender equality principles and are rights responsive.

Within the above context, the final evaluation of Advancing the Implementation of UNSCR 1325 on Women, Peace and Security in Western Balkans will:

- Assess UN Women’s contribution to results, including the effectiveness of programming strategies in implementing global commitments within national/territorial and sub-regional priorities for fostering peace, security and gender equality;

- Investigate the contextual factors that enabled or restricted the achievement of results;

- Evaluate UN Women’s organizational performance with respect to this project; and

- Asses the perspective of stakeholders and beneficiaries on the usefulness of interventions and their overall satisfaction with the project.

The final project evaluation will also set forward-looking recommendations on how to strengthen UN Women’s UNSCR 1325 programming and monitoring and evaluation systems at the country and sub-regional levels.  In addition, the evaluation will support the planning of follow-up activities by identifying successful approaches and spaces to further enhance performance; it will serve both as a tool and a learning product.  Primary audiences of the final evaluation are project stakeholders, donors, partner organisations, and UN Women project, country and regional offices and headquarters.

EVALUATION SCOPE, KEY ISSUES AND CRITERIA

This evaluation is a final project evaluation. It will cover activities conducted in Bosnia and Herzegovina, Kosovo (under SCR 1244), the former Yugoslav Republic of Macedonia and the Republic of Serbia, that have been implemented since the beginning of the project (January 2011) until the time of the evaluation.  The evaluation will also take into account activities through November 2013).

For the purposes of this evaluation, the key questions identified by stakeholders and project activity implementation were organized in line with OECD DAC criteria under the following main evaluation criteria: relevance, effectiveness, efficiency, sustainability, and impact.  Further, the evaluation will assess capacity development, partnerships, visibility and results based management/monitoring/evaluation as cross-cutting themes.

Evaluation Questions

Relevance and Coherence:

- Do project objectives and target groups address identified needs in the national/territorial and sub-regional context?

- Were relevant normative and strategic frameworks effectively articulated within UN Women (internally)?

Effectiveness:

- Is the project design articulated in a coherent way? Are project outcomes, outputs and activities clearly articulated? To what extent were the originally defined objectives of the intervention realistic (achievable)? Was the project well planned?

- What are the changes produced by the project at the national/territorial and sub-regional levels? What has been the progress made towards the achievement of expected outputs and outcomes? What results were achieved? What were the reasons for the achievement or non-achievement of results?

- To what extent are beneficiaries satisfied with project results?

- How were lessons learned, identified in the mid/term evaluation utilized to inform this project?

- What was/is UN Women’s comparative advantage in designing and implementing this project and women, peace and security programming in general?

Efficiency:

- Were project funds managed effectively? Could the activities and outputs been delivered with fewer resources without reducing their quality and quantity?

Sustainability:

- Is the project supported by national/territorial and local institutions and civil society? Do these institutional and civil society actors demonstrate ownership of project results, leadership, commitment and technical capacity to maintain/implement the benefits of the project?

- What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time following the end of the project?

Impact (road to):

- What are the intended and unintended, positive and negative, long term effects of the project?

- What would the development have been like without the project intervention?

Cross-cutting themes:

- Capacity Development: How did the project contribute to capacity development of its stakeholders/beneficiaries? What adaptive or management capacities of national/territorial and sub-regional partners have been supported?

- Partnerships and Coordination: How were relevant sub-regional and national/territorial actors and stakeholders included in UN Women programming and implementation?

- Visibility: Did the project implement UN Women visibility guidelines?

Forward looking insights:

- Should UN Women UNSCR 1325 programming continue into the future? Were the approaches and strategies used by UN Women effective, relevant and potentially sustainable? Which other approaches/beneficiaries etc. should be considered?

- What did stakeholders and beneficiaries consider as the most necessary areas of future UNSCR 1325 intervention at the national/territorial and sub-regional levels?

Evaluation Approach

The overall approach of this evaluation is utility-focused, as advised by the intended users of the evaluation, and as aligned with UN Women’s evaluation strategy guidelines, and UNEG norms and standards. (Relevant information and background notes can be obtained from http://www.unwomen.org/about-us/evaluation/). The evaluation should adhere to UN Women Evaluation Report Quality Standards. UN Women evaluations are also expected to adhere to a framework supporting human rights-based (HRBA), results-oriented and gender responsive monitoring and evaluation. Towards this purpose, the project evaluation will encompass the principles of gender equality and human rights, ensuring that the evaluation process respects these normative standards, and aims for the progressive realization of same by respecting, protecting and fulfilling obligations of non discrimination, access to information, and ensuring participation through a combination of consultative and participatory evaluation approaches.  For more details on human rights and gender equality in evaluations, please refer to the UNEG Handbook Integrating Human Rights and Gender Equality in Evaluation – Towards UNEG Guidance.

The evaluation will be conducted through transparent and participatory processes involving relevant UN Women stakeholders and partners. The Senior Evaluation Consultant may further define the overall approach by adopting complementary methodologies and approaches.

At all times, the Senior Evaluation Consultant will discharge her/his duties in an independent and impartial manner.

Evaluation Process

The Senior Evaluation Consultant will be responsible for overall delivery under the present terms of reference.  She/he is expected to travel to Bosnia and Herzegovina, Kosovo (under SCR 1244) the former Yugoslav Republic of Macedonia and the Republic of Serbia in order to collect data for the evaluation. Data collection in these countries will be supported by project national coordinators who will not attend stakeholder interviews.

The evaluation will consist of the following phases:

- Preparation, mainly devoted to UN Women structuring the evaluation approach, developing the terms of reference, compiling project documentation, and hiring the senior evaluation consultant.

- Inception, which will involve a desktop review and analysis of project activities, inception consultations, inception report with a detailed timeline, and the development of an evaluation methodology (a list of stakeholders will be provided by UN Women at the beginning of the evaluation).

- Data collection and initial analysis, including the country based collection of information, desk reviews and field visits.

- Data analysis, interpretation and synthesis, focused on the structuring of findings, analysis of findings, their interpretation and presentation in a full draft evaluation report (full draft evaluation report is a fully completed report with all annexes).

- Submission of draft evaluation report for feedback from UN Women and the incorporation of relevant feedback.

- Finalization of report and distribution to stakeholders.

- Preparation of a Management Response and uploading the report on the Evaluation Resource Centre site (implemented by UN Women).

Evaluation Design and Methods

The final evaluation will take into consideration the UN Women Strategic Plan 2011-2013 and other strategic and policy frameworks that inform UN Women’s work in this area. The evaluation will use a variety of data collection methods and sources with a view to data triangulation. The methods should be participatory, ensure the collection of disaggregated data, interrogate gender roles, be context and culturally sensitive and whenever possible, mixed (qualitative and quantitative).

The following methods are suggested for answering the evaluation questions:

- Desk review of documents

- Semi-structured key informant interviews

- Group discussions

- Face-to-face and self administered, incl. online, surveys

The Senior Evaluation Consultant should suggest further methods as appropriate.

Existing information sources: The Senior Evaluation Consultant will need to make her/himself familiar with UN Women and other documents to engage with the background of the project and the situation of women’s rights in the sub-region.

Key documents in this regard include:

- Project documentation, incl. logical framework, budgets, donor progress reports, mid-term review report etc.

- Strategic documents of UN Women (Annual Work plan 2011-2013)

- CEDAW comments

- UNSCR 1325 National Action Plans and Action Plans

Existing information sources about the project will be shared electronically.

Management of Evaluation

This evaluation is managed by the UN Women Sub-regional office for Central and South Eastern Europe through the Project Manager of Advancing the Implementation of UNSCR 1325 on Women, Peace and Security in the Western Balkans.

Ethical Code of Conduct

The senior Evaluation Consultant is required to follow the UNEG ethical code of conduct.

DELIVERABLES

Under the overall supervision of the Regional Project Manager of Advancing the Implementation of UNSCR 1325 on Women, Peace and Security in Western Balkans, the senior evaluation consultant will bear responsibility for the following deliverables:

- An inception report. This report will contain:

  - Description of evaluation objectives, scope, methodology/methodological approach, data collection, list of key stakeholders/partners, a review of evaluation questions, performance criteria, and issues to be analyzed.

  - A work plan with clear timelines.

  - A clear evaluation matrix.

- A full draft evaluation report. Should be no longer than 40 pages long (excluding Annexes). The structure of the full draft and final reports should be as follows:

  - Executive Summary (to be prepared for the final report)

  - List of Acronyms

  - Project Description

  - Evaluation Purpose

  - Evaluation Methodology and Process

  - Findings

  - Lessons Learnt/Good Practices

  - Recommendations

  - Annexes (including an interview list – without identifying names for the sake of confidentiality/anonymity, data collection instruments, a list of all  documents consulted, and the terms of reference)

- A final report with the feedback of UN Women and other designated stakeholders included.

All deliverables should be submitted to the Regional Project Manager. The reports should be written in English, in a succinct and user-friendly language.

COMPETENCIES

Integrity

- Demonstrates consistency in upholding and promoting the values of UN Women in actions and decisions, in line with the UN Code of Conduct.

Cultural Sensitivity/Valuing Diversity

- Demonstrates an appreciation of the multicultural nature of UN Women and the diversity of its staff.

Ethics and Values

- Has political acumen;

- Creates and promotes an enabling environment for open communication;

- Contributes to an emotionally intelligent organization; and

- Shares knowledge across the UN, building a culture of knowledge sharing/learning.

Expertise

- Substantive knowledge of the women, peace and security agenda (reflected in UNSCR 1325, 1820, 1888, and 1889) in the Western Balkans and worldwide;

- An overall client-oriented approach that meets the standards outlined in the Standards for Evaluation in the United Nations System;

- A profound knowledge of relevant international gender/human rights frameworks;

- Results-based management (strong organizational and time management skills, and the ability to meet deadlines).

Drafting / Communication

- Excellent interpersonal, communication and interview skills;

- Excellent report writing and presentation skills; and

- Cultural sensitivity and adaptability – communicates effectively with and relates to people of different cultures.

REQUIRED SKILLS AND EXPERIENCE

Education and Experience:

- Degree in law, political science, gender studies, security, or a related discipline;

- A minimum of 10-15 years of relevant professional experience, specifically in the area of evaluating international development oriented initiatives and organizations;

- A substantial international track record of conducting different types of evaluations, including process, outcome and impact evaluations in different countries with a variety of organizations;

- A demonstrated experience with applied research with data collection, analytical and presentation skills and demonstrated ability to structure information;

- Previous experience with the United Nations and/or other international organisations is considered an asset as is previous work on the women, peace and security agenda;

- Strong analytical, writing and communication skills in English; and

- Strong computer skills.

Language Requirements

- Fluency in spoken and written English;

- Knowledge of Bosnian, Croatian and/or Serbian language is considered an asset.

Candidate Evaluation Process

UN Women applies a fair and transparent selection process that takes into account both the technical qualification of potential consultants as well as the financial proposals submitted in support of consultant applications. Candidate applications will be evaluated using a cumulative analysis method taking into consideration the combination of applicant qualifications and a financial proposal. The contract will be awarded to the individual consultant whose offer has been evaluated and determined as:

- responsive/compliant/acceptable, and

- having received the highest score out of below defined technical and financial criteria.

Only candidates obtaining a minimum of 49 points in the technical evaluation will be considered for financial evaluation.

| Criteria | Total points | Max. Points |
| --- | --- | --- |
| Technical Evaluation (70%) | 70 |  |
| Relevant work experience |  | 40 |
| Experience specific to mid-term and final evaluations of UN initiatives |  | 20 |
| Experience in gender |  | 10 |
| Financial Evaluation (30%) | 30 |  |
| TOTAL | 100 |  |

The maximum number of points assigned to the financial proposal is allocated to the lowest price proposal. All other price proposals receive points in inverse proportion. A suggested formula is as follows:

Application Process

Qualified candidates are requested to apply online via this website. Applications should contain:

- A cover letter stating your interest in and qualifications for the advertised position.

- Financial Proposal (USD daily fee).

This designation is without prejudice to divergent positions on status and is in line with United Nations Security Council Resolution 1244 and the 2010 advisory opinion of the International Court of Justice.

In the context of this project evaluation, the “effectiveness” criteria will measure the extent of achievement of outcomes and outputs. “Efficiency” will assess quantitative and qualitative outputs, in relation to the inputs of the project. The questions categorized under “relevance” will assess the coherence of the project’s vision and strategies with UN Women’s organizational goals, the sub-regional context and strategic priorities. In addition, the evaluation should also examine the external factors that influenced the project’s strategies and how the project adapted to these factors. Evaluation questions that refer to “sustainability” examine whether and how the benefits generated will continue at the end of the project, for a reasonably long period of time. Sustainability may refer to the financial or technical capacity of partner organizations to continue the initiative, national ownership of the initiative, and adaptive, operational, or management capacities of national partners. To the extent possible, the evaluation will also assess the impact (road to impact) of the project, i.e. the long-term effects of the intervention. It is however understood that given the timing of the evaluation (towards the end of the intervention) and the scope of the intervention, it may be the case that impact cannot be yet sufficiently assessed.

These are to be recorded for future interventions of UN Women.