# TERMS OF REFERENCE

FINAL EVALUATION

SUPPORTING GENDER EQUALITY IN THE CONTEXT OF HIV AND AIDS

1. BACKGROUND

Gender inequality and persistent violations of women’s human rights continues to be a key driver of the epidemic. It fuels an increase in infection rates, and reduces the ability of women and girls to cope with the epidemic. Often, women have less information about HIV and fewer resources to take preventive measures. Today, women represent nearly 54 percent of the people living with HIV/AIDS (PLWHA) globally, and young women account for 60 percent of new infections.  In some regions, the statistics paint a starker picture which show that the spread and impact of HIV and AIDS disproportionately affects women and adolescent girls who are socially, culturally, biologically and economically more vulnerable. In Sub-Saharan Africa, women and girls account for 58 percent of Africans living with HIV, and young women aged 15-24 are at least eight times more likely than men to be HIV-positive. Alongside Sub-Saharan Africa, the Caribbean is the only other region where women and girls outnumber men and boys living with HIV; in 2009, an estimated 53 percent of people living with HIV/AIDS were women. In Asia, women too are accounting for a growing proportion of HIV infections overall, up from 21 percent in 1990 to 35 percent in 2009.

While international consensus and commitment has increasingly acknowledged the centrality of gender equality to the HIV response since 2001,  significant gaps remain in policy, programmatic and budgetary responses to the needs and rights of women.

PROGRAMME DESCRIPTION

Supporting Gender Equality in the Context of HIV and AIDS is a joint management programme by the European Commission (EC) and UN Women, with a total budget of €2,450,353.  The overall objective of the programme seeks to ensure that gender equality and human rights are integrated into key policies, programmes, actions and budgets to address HIV/AIDS at the national level. Implemented in Cambodia, Jamaica, Kenya, Papua New Guinea (PNG), and Rwanda, the programme’s specific, outcome-level objectives are:

- HIV-positive women’s organizations and women affected by HIV/AIDS in 5 selected countries provide leadership for and influence the shaping of policies, programmes, and resource allocations that address the HIV/AIDS epidemic; and,

- Enhanced national commitment to and action for addressing gender equality in the national AIDS response in 5 selected countries.

Key areas of intervention focused on building the leadership capacity of women living with HIV as well as the capacity of networks of women living with HIV to enable their participation in policy and decision making spaces and holding their governments to account. The programme carried out mappings and assessments of organizations and networks of women living with HIV to identify capacity needs and to prioritize training and other capacity-development interventions to strengthen their organizational, leadership, strategic planning, advocacy and networking skills. The programme also facilitated the identification of priorities and development of a common agenda among women living with HIV (WLHIV).

It also enhanced staff and institutional capacities of National AIDS Coordinating Authorities (NACAs) to integrate gender equality and human rights considerations into policies, programmes and budgets as well as the capacity of other line ministries involved in the multi-sectoral HIV response. In some countries, the programme worked closely with the ministries of gender or women’s affairs to strengthen the integration of HIV in their respective policies and programmes. Gender audits, on-going institution-wide trainings, development of training materials and tools, and the placement of Gender Advisors in NACAs formed part of a comprehensive package of capacity development support provided by the programme.  The programme also created and/or expanded the space for policy dialogue, consultation and advocacy between networks of women living with HIV and NACAs through high level dialogues and the inclusion of women living with HIV and their networks in global, regional and national processes and served to strengthen the linkages and the quality of the relationship of these vital stakeholders.

Primary partners under this programme included the staff of the National AIDS Coordinating Authorities (NACAs), other line ministries, such as ministries of gender or women’s affairs (as in the case of some countries), organizations and networks of women living with HIV, as well as HIV/AIDS service organizations, UN Women country and regional offices as well as other UN System partners, especially UNAIDS.

During the course of the programme, UN Women requested two no-cost extensions from the European Commission, which extended the programme implementation period by 15 additional months.  The first no-cost extension, submitted in June 2011 and approved in December 2011, was requested to ensure that the there was a full 36 months to implement the Action; given the initial difficulties and delays related to identifying and recruiting Gender Advisors with expertise in both gender and HIV programming in many of the programme countries, lengthy procurement and hiring processes; the need to align programme with the UNAIDS Joint Programme of Support in each country; and developing and validating country implementation plans, which included consultations with wide base of stakeholders to build ownership and commitment.  The second no-cost extension was requested and approved in November 2012 seeking an additional three months to enable national partners to finalize specific and strategic planned activities, that were essential for anchoring exit strategies of the Action overall. In part, this additional time was needed because of the delay in receiving the 2nd Instalment from the European Commission as well as scheduling conflicts among key stakeholders towards the end of the year which resulted in the cancellation or the postponement of certain activities.

Since the start of the programme, four important developments at global level have taken place that have strengthened international commitments vis-à-vis gender equality and the AIDS response and that enabled UN Women to strengthen its organizational positioning within the UN System and its position as a global champion of gender equality and women’s rights:

In 2010, in an effort to build momentum and translate political commitment into action and resources, UNIFEM (now part of UN Women), as a key partner, worked in close collaboration with UNAIDS to roll out the Agenda for Accelerated Country Action for Women, Girls, Gender Equality and HIV at country level to ensure that national AIDS policies and programmes are responsive to women and girls’ needs and rights. Almost eighty countries have developed national action plans on women, girls, gender equality and HIV, or taken other steps to address gender-related drivers of their national epidemic.  The Agenda for Women and Girls addresses three key issues: (a) knowing, understanding, and responding to the particular and various effects of the HIV epidemic on women and girls; (b) translating political commitments into scaled-up action to address the rights and needs of women and girls in the context of HIV; and (c) championing leadership for an enabling environment for the fulfillment of women’s and girls’ human rights and their empowerment, in the context of HIV. It has been launched in 90 countries.

Second, in 2011, the UN Entity for Gender Equality and Empowerment (UN-Women) was established. UN Women joins together four agencies focused on the advancement of gender equality and women’s empowerment in the UN system. By linking the normative and operational mandates of these agencies, UN Women can ensure that important global standards on gender equality are implemented through concrete actions at country level, and that new policy developments genuinely respond to women’s actual needs. UN Women is the lead driver and lead voice advocating for gender equality, in line with national priorities and international norms and policies. It also has the mandate to lead, coordinate and promote the accountability of the UN System in advancing gender equality and empowerment of women. The creation of UN Women has brought greater political urgency, focus and coherence to addressing issues of gender.

Third, and building on its predecessors, the 2011 Political Declaration, “Intensifying Our Efforts to Eliminate HIV/AIDS” strengthened the international community’s resolve to eliminate gender inequality, gender-based abuse and violence, and to increase the capacity of women and adolescent girls to protect themselves from HIV infection.  It also recognized UN Women as a new stakeholder in global efforts to combat HIV, especially in its role of promoting gender equality and the empowerment of women.

Finally, in June 2012, UN Women became the 11th Co-Sponsor of the Joint United Nations Programme on HIV/AIDS (UNAIDS), strengthening its position in inter-agency efforts to promote and ensure that gender equality remains at the center of global and national HIV responses.

2. JUSTIFICATION AND PURPOSE OF EVALUATION

The final, end-of-programme evaluation will be conducted by an independent, external team. It is mandatory, undertaken as agreed with the European Commission (EC) and in line with UN Women’s Evaluation Policy. The overall purpose of the Final Evaluation is to assess programmatic progress and challenges at the outcome level, with measurement of the output level achievements and gaps, including to what extent these achievements (or non-achievements) affected outcome-level progress. The final evaluation will examine programme implementation in the five countries as well as global level efforts, particularly in facilitating and supporting the participation of women living with HIV at key global fora and contributing to South-South exchange and the creation of learning.

It will consist of a desk review, country-level visits, in-depth interviews with UN Women staff (at HQ, regional, and country levels), national level partners, including UN System partners, and the EC. The final evaluation will also contribute to results-based management through a participatory approach that documents results achieved, challenges to progress, and programme contributions to the integration of gender equality and human rights into key policies, programmes and actions to address HIV/AIDS in the five programme countries.

In the course of programme implementation, the EC commissioned two Results-Oriented Monitoring (ROM) exercises in October 2010, at the mid-point of the Action, and in June/July 2012. UN Women also undertook an internal mid-term review of the programme between December 2011 – February 2012, which consisted of a programme and operational assessment and a global convening with programme countries, including national partners, to validate findings and recommendations. The Global Convening also provided programme countries and national stakeholders with an opportunity to exchange, share and discuss key achievements and effective approaches. These reviews are important inputs that will support the final evaluation. Recommendations made by the 2nd ROM exercise should be fully integrated in the evaluation process.

Evaluation Objectives: The specific objectives of the final evaluation are to:

- Analyze the relevance and effectiveness of programmatic strategy and approaches;

- Validate programme results in terms of achievements (or non-achievement) toward the outcomes and outputs at country level, with a critical examination of how and to what extent the programme contributed to enhancing the enabling environment for the integration of gender equality in national HIV responses;

- Assess the potential for sustainability of results and the feasibility of continued, on-going, nationally led efforts in each of the five countries

- Document lessons learned to inform and strengthen UN Women’s governance approach vis-à-vis integrating gender equality and human rights into key policies, programmes and actions to address HIV and AIDS as well as the future work of global, regional, and national stakeholders in this area. This includes documentation of any limitations in order to improve and refine programming approaches and interventions.

Use of Evaluation: The information and evidence generated by the evaluation will be used by UN Women, the European Commission, national partners, and other stakeholders to:

- Contribute to the evidence base on effective approaches and strategies for addressing and integrating gender equality and women’s human rights in global and national HIV responses; including enhancing the leadership and participation of networks of women living with HIV.

- Support advocacy, programming and resource mobilization efforts of implementing countries to sustain outcomes; as well as UN Women regional and country offices with respect to gender equality and HIV programming;

- Facilitate a process of strategic reflection and learning for UN Women, UN system partners, and donors with respect to effective governance strategies and approaches for making the AIDS response work better for women.

- Provide necessary information about how the programme affected the working relationship between UN Women and the EC at country level.

- SCOPE OF THE EVALUATION

The scope of the final evaluation will be defined along the lines of timeframe, geographic coverage, and thematic scope.

Timeframe: The timeframe of the evaluation will cover 1 January 2009 – 31 March 2013, which includes the initial 36-month implementation period and the additional 15 months that were approved under the two no-cost extensions.

Geographic scope: The evaluation will assess implementation in Cambodia, Jamaica, Kenya, Papua New Guinea and Rwanda; it will also consider policy advocacy and the facilitation of knowledge dissemination efforts at global level. Country visits to the implementation countries will be conducted; in this regard, consideration should be given to working through regional - or country – based consultants. The evaluation will also assess the global management of the programme over its lifetime.

Thematic scope:  The evaluation will examine how the programme contributed to the effective integration of gender equality and human rights in key policies, programmes and actions to address HIV/AIDS at the national level; the strategies/approaches used to enable HIV-positive women’s organizations and women living with or affected by HIV and AIDS to provide leadership for and influence the shaping of policies, programmes and resource allocations and to enhance national commitment to and action for addressing gender equality in national AIDS responses in the five countries. It will also look at how the programme in the five countries aligned with other similar initiatives to build synergies and maximize impact. It will highlight programme results and impacts, including unintended or unexpected outcomes, as well as identify the challenges faced, good practices and lessons learned. Finally, the final evaluation will consider the ways in which global efforts contributed to national implementation and how country-level work influenced global advocacy and policy.

Evaluation Criteria: The evaluation will address the five evaluation criteria of: relevance, effectiveness, efficiency, sustainability, and impact.  Given that this evaluation directly follows the end of the programme implementation period, the evaluation will assess and make informed statements about the potential for sustainability and immediate impact of the programme.

The evaluation questions below are organized by each criterion and focus on the main, planned areas of programmatic achievement as described in the Project Document and Logical Framework. Where relevant, questions have been formulated and adapted from the assessment framework used in EC-ROM exercises.

Illustrative Questions:

These are illustrative questions. It is expected that the evaluation team will revise the overall analytical framework and refine the evaluation questions during the Inception Phase.

- Relevance

- To what extent are the specific objectives of the programme still valid? How has the programme taken into account findings and recommendations of previous assessment or review exercises to strengthen the relevance of the programme?

- Have activities and expected results of the programme been consistent with the overall goal and the attainment of objectives as well as intended impacts?

- Were selected programmatic approaches and strategies appropriate to address the identified needs of stakeholders and beneficiaries?

- How, and in what way, did the programme build synergies with other similar UN system or donor interventions?

B. Effectiveness

- What have been the advocacy and policy contributions of the programme at national and global levels with respect to gender equality and the HIV response?

- To what extent have national partners increased their technical knowledge and skills as well as organizational capacity for integrating gender equality into national HIV policies, plans and actions?

- How did the recruitment of Gender Advisors in each of the five countries affect programme implementation and contribute to the achievement of expected results and specific objectives?

- How, and through what mechanisms, did the programme increase the participation of networks of women living with HIV in national and subnational policy and decision making spaces?

- To what extent has the programme contributed to strengthened partnerships in national HIV responses between National AIDS Coordinating Authorities (and other government partners where relevant) and organizations or networks of women living with HIV?

- What influence have contextual factors (political, social, economic, and other) had on the effectiveness of the programme? (Consider conducting cross-country comparison based on country case study findings).

- How has the programme adapted (when necessary) to changing external conditions to ensure benefits for target groups?

- How effectively has programme management monitored performance and results and supported communication of these results internally and/or externally?

- Did UN Women provide relevant and timely technical support to partners?

- How has the programme shared and disseminated results and learning on good practices (country, regional and/or global levels) vis-à-vis integration of gender equality in national HIV responses and the leadership and participation of networks of women living with HIV?

C. Efficiency

- Did the programme contribute positively to the work of EC and UN Women in the programme countries?

- Have resources (financial, human, technical support, etc.) been allocated strategically to achieve programme outcomes?

- Have programme resources been sufficient to deliver results and contribute to programme outcomes?

- To what extent have programme management arrangements facilitated (or hindered) effective implementation and efficient achievement and delivery of results?

D. Sustainability

- What is the level of programme ownership by national partners and how will it be sustained (or not) after the end of external support? To what extent have relevant target beneficiaries actively involved in decision-making concerning programme orientation and implementation?

- Is there a defined strategy for sustaining increased knowledge and capacity of NACAs on integrating gender in policies, programmes, plans, and budgets?

- Is there a defined strategy for sustaining the leadership and participation of networks of women living with HIV in national HIV responses?

- Are there plans to continue with some or all of the project’s activities?

E.  Impact

- How have programme’s global policy efforts informed country implementation in each of the five countries? How have country experiences and lessons been integrated into global level advocacy or policy efforts?

- What documented or measurable changes have occurred, since the start of the programme, as a result of increased national capacity to integrate/mainstream gender equality in national HIV responses in each of the five countries and the ability of WLHIV to engage and participate in national (or local) level processes? Do these changes illustrate a positive, negative or neutral shift in the integration of gender equality?

- Are national stakeholders, particularly NACAs and other policymakers, more cognizant of the purpose and value of women’s participation and leadership, especially that of WLHIV organizations and networks? Are there mechanisms in place to sustain this engagement beyond the end of the programme?

4. AVAILABLE INFORMATION SOURCES

The Evaluation Team will have access to a number of information sources, including:

- Programme Document and Logical Framework;

- Inception Workshop Report, April 2009

- Programme Country Annual Implementation Plans

- Monitoring Frameworks and Reports (internal)

- UN Women Progress and Financial Reports to the Donor (3)

- EC ROM Monitoring Mission Reports, November 2010 and August 2012 (includes synthesis report, country-specific reports, tabular ratings)

- Mid-Term Programme and Operational Assessment, December 2011, (including inceptions report; stakeholder questionnaires, transcripts of stakeholder interviews);

- Global Mid-Term Review Workshop, February 2012 (agenda, presentations, reports)

- Available project documentation (i.e. mapping studies, workshop reports, presentations, etc.)

- Mid-Term Review of UNAIDS Agenda for Accelerated Country Action for Women, Girls, Gender Equality and HIV (2012).

5. EVALUATION APPROACH AND METHODOLOGY

The Evaluation team will rely on a mixed-method approach that is aligned with the final questions matrix (to be completed by the evaluation team in consultation with the Core Reference Group).  Following an initial desk review and brief discussions with key stakeholders, the Evaluation team will refine and finalize the methodology and analytical framework, which will be validated by the Core Reference Group. The methodology should incorporate rights-based, participatory approaches and ensure that gender equality is considered throughout.

The evaluation will draw on the findings of the two ROM missions, which provide valuable information on programme’s relevance, effectiveness, efficiency, potential sustainability and impact prospects. It will also consider to what extent the recommendations have been addressed. Another important input for the evaluation is the internal mid-term review UN Women carried out. The mid-term review consisted of a programme and operational assessment as well as a global workshop held with programme countries to validate the findings and recommendations.

The three, main phases of the final evaluation are:

Phase I. Inception phase:

- Conduct  an initial desk review of available documents

- Conduct preliminary interviews (via skype or phone) with key stakeholders to refine the evaluation scope, questions and methodology.

- Draft an Inception Report for review by the Core Reference Group.

- Refine the evaluation methodology/question matrix based on Core Reference Group feedback.

Phase II. Intensive Research Phase

- Conduct in-depth review of relevant programme/project documents and reports,

- Undertake five country visits;

- Collect survey data from beneficiaries and staff of national AIDS coordinating authorities; and where relevant other participating line ministries (i.e. ministries of gender/women’s affairs).

- Deliver PowerPoint presentation of key findings for each country visited.

- Conduct in-depth interviews with global, regional and country level UN Women staff, grantees, donor representatives, and others as necessary;

Phase III. Analysis and Report Writing

- Review and analyze all available data;

- Prepare and submit a first draft of the synthesis evaluation report to Core Reference Group for comments;

- Deliver a PowerPoint Presentation of key findings, lessons learned, and recommendations at Global Convening with UN Women, European Commission, and national partners (venue to be determined); [Please do not include these costs in your financial proposal; UN Women will cover travel and DSA separately]

- Revise report based on feedback of Core Reference Group and Global Convening;

- Submit final report.

6. MANAGEMENT OF THE EVALUATION

The evaluation will be managed by the HQ Programme Manager, Gender Equality and HIV/AIDS. Management of the evaluation will also be guided by two consultative bodies: the Core Reference Group and the Broad Reference Group.

The HQ-based Programme Manager will serve as Task Manager, managing the overall and day-to-day aspects of the evaluation and ensuring participatory consultations with the European Commission, UN Women’s geographic sections as well as regional and country offices as required.  She will coordinate the selection and recruitment of the evaluation team, manage contractual agreements, budget and personnel involved in the evaluation. The Programme Manager will provide essential documents and data to the evaluation team, facilitate communication and timely feedback between the evaluation team and key evaluation stakeholders; and ensure the timely submission of expected deliverables. The Programme Manager will also be responsible for preparing a management response in consultation with programme countries that addresses the findings and recommendations to ensure future learning and inform implementation of their relevant programmes.

The Core Reference Group will provide direct oversight, safeguard independence, and give technical input over the course of the evaluation. It will provide guidance on evaluation team selection and key deliverables (Inception Report, Draft Evaluation Report) submitted by the evaluation team. It will also support the dissemination of the findings and recommendations.

The Broad Reference Group will be informed throughout the evaluation process and will be asked to participate at strategic points during the evaluation, including briefings by the evaluation team of findings and recommendations. It will also support the dissemination of the findings and recommendations.

7. EXPECTED PRODUCTS AND TIMELINE

The final evaluation will be carried out from 22 April 2013 to 19 August 2013.  All deliverables will be in English and submitted to the Evaluation Task Manager. Table 1 provides an indicative timeframe, including due dates for deliverables and to whom.

- An inception report which includes detailed evaluation methodology, revised evaluation question matrix, data collection tools and analysis methods, and workplan (with corresponding timeline). The Inception Report will also identify list of information sources, including key stakeholders.  The Evaluation Team will ensure that the evaluation process is ethical and that participants in the evaluation will be protected in adherence to UNEG norms and standards and UNEG Ethical Guidelines, see http://www.unevaluation.org/ethicalguidelines).

- Power point presentation(s) to each country at the close of each field visit. Presentations will outline preliminary findings, lessons learned, good practices and recommendations to key stakeholders.

- First Draft Evaluation Report; which contains country profiles

- Powerpoint Presentation to Global Convening of UN Women staff, EC, and national partners on main findings/recommendations and proposed dissemination strategy; and,

- Final Evaluation Report. Refer to Annex 2 for proposed format.

TABLE 1

|  | Primary Activities | Deliverable |
| --- | --- | --- |
| Inception Phase |  |  |
| 22 April 2013 – 24 April 2013 | Debrief with Evaluation team, discuss and jointly review TOR. |  |
| 6 May 2013 | Evaluation Team submits Inception Report, including proposed methodology, selection criteria, and workplan (with agreed upon deliverables and timeframe) | Inception Report |
| 10 May 2013 | Convene Core Reference Group to discuss Inception Report and provide feedback to Evaluation Team, finalize methodology, questions and workplan. | Final Evaluation Methodology, Question Matrix, and Workplan |
| Intensive Research Phase |  |  |
| 6 May – 5 July 2013 | In-depth document review as well as interviews with global, regional and national UN Women staff, partner organizations |  |
| 20 May -5 July 2013 | Evaluation Team conducts country visits. [Due consideration should be given to partnering/collaborating with in-country consultants.] | Powerpoint presentations delivered to each country with summary of main findings |
| Analysis & Report Writing Phase |  |  |
| 8-24 July 2013 | Analysis and review of data and preparation of first draft |  |
| 24 July 2013 | Evaluation Team submits first draft Evaluation Report | First draft Evaluation Report |
| 25 July 2013 | Disseminate and circulate Draft Evaluation Report to Core and Broad Reference Groups. (UN Women) |  |
| 29 July 2013 | Team Leader delivers Powerpoint presentation to participants at UN Women’s Global Convening on preliminary findings, main recommendations, challenges and opportunities. | Powerpoint Presentation on key findings, lessons and recommendations. |
| 19 August 2013 | Submission of Final Evaluation Report |  |

8. EVALUATION TEAM COMPOSITION, QUALIFICATIONS AND SKILLS

The final evaluation will be conducted by an independent evaluation team of at least three experts. The Team Leader and Team members should have the requisite and complementary skills set (individually and jointly) to undertake a complex, multi-country end-of-programme evaluation. Consideration should be given to partnering/collaborating with in-country consultants.

The Evaluation Team Leader will demonstrate experience and expertise in leading and managing large programme evaluations.  S/he will be responsible for coordinating the evaluation as a whole; including internal evaluation team coordination and logistics, preparation of the work plan, dissemination of all methodological tools, delivery of the expected evaluation outputs and all presentations.  Specifically, the Evaluation Team Leader is expected to bring the following expertise:

- At least a master’s degree, PhD preferred, in social sciences, preferably in gender, public health/HIV, evaluation or social research;

- Technical expertise in gender, HIV programming, and national planning processes

- A minimum of 12 years of experience in complex, out-come level evaluations, and at least five in evaluation of large, multi-country programmes.

- A strong record in designing and leading complex evaluations.

- Experience working with multi-stakeholders essential: governments, civil society organizations (CSOs), and the United Nations/ multilateral/bilateral institutions.

- Experience in participatory approach is an asset. Facilitation skills and ability to manage diversity of views in different cultural contexts.

- Strong knowledge and regional experience is preferred, especially in any of the countries covered by the programme.

- Strong ability to translate complex data into effective-written reports demonstrating high level analytical ability and communication skills.

- Detailed knowledge of the role of the UN and its programming, particularly that of UN Women, is desirable.

- Proficiency in English required; with ability to work in French preferred.

The Team Leader is required to submit two examples of evaluation reports recently completed where s/he contributed significantly as the lead writer.

The Evaluation Team Member(s) should demonstrate skills in the following areas:

- A master’s degree related to any of the social sciences, preferably in gender, public health/HIV, evaluation or social research;

- At least five years of experience in gender, human rights and HIV programming.

- Extensive knowledge and experience in the application of quantitative and qualitative evaluation methods;

- A minimum of 5-7 years of experience in conducting evaluations.

- High level of data analysis skills

- Strong analytical and writing skills.

- In-country or regional experience preferred

- Ability to work within a team.

- Proficiency in English required, with ability in French preferred.

- Experience with the UN is an asset.

The evaluation team should have gender balance and geographic representation. The language skill composition should reflect the official languages of the countries to be evaluated: English and French.

9. UNITED NATIONS EVALUATION GROUP CODE OF CONDUCT

The evaluation will be carried out following UNEG Ethical Guidelines for Evaluation in the UN System and UNEG Code of Conduct for Evaluators as well as the UN Women Evaluation Policy, which stipulates that evaluations in UN Women will be independent and abide to the following evaluation standards: Participation and inclusiveness, Utilization-Focused and intentionality, Transparency, Independence and Impartiality, Quality and Credibility as well as Ethical Standards.

For UNEG Ethical Guidelines for Evaluation in the UN System, please refer to:

http://www.uneval.org/search/index.jsp?q=ethical+guidelines

For UNEG Code of Conduct for Evaluators, please refer to: http://www.unevaluation.org/unegcodeofconduct

TOR Annexes:

Annex 1: Evaluation Team Selection Criteria

Annex 2: Final Evaluation Report Format

Annex 1: Evaluation Team Selection Criteria

The selection of the Evaluation Team will be based on the fulfillment of the specification established in the TOR. The submitted proposals will be assessed on three main categories: the quality of the technical proposal; the expertise and competencies of the evaluators, as demonstrated in CVs, gender balance and diversity of team; and the financial proposal.  The categories are assigned different weighting, which will total 100%.

- Technical Proposal (35%)

- Evaluation Matrix: The matrix clearly addresses the TOR, relating evaluation Questions with evaluation Criteria, with Indicators and with Means of Verification.

- Evaluation approach and methodology: The proposal presents a specific approach and a range of methods for gathering and analyzing qualitative and quantitative data that are feasible and applicable in the timeframe and context of the evaluation, and incorporates human rights and gender equality perspectives.

- Work plan: The timeframe and resources indicated in the financial proposal are realistic and useful for the needs of the evaluation.

- Motivation and ethics: The evaluators reflect clear professional commitment with the subject of the assignment and follow UNEG ethical code of conduct.

- Team Composition (35%)

- The team leader’s and all team’s experiences and qualifications meet the criteria indicated in the TOR. The team is gender balanced and cross-culturally diverse.

- Financial Proposal (30%)

- The budget proposed is sufficient for applying the data gathering techniques and for obtaining reliable data for the evaluation in the timeframe indicated.

Annex 2

PROPOSED FORMAT OF FINAL EVALUATION REPORT

Final evaluation report:

      - Executive Summary (maximum five pages)

      - Programme description

      - Evaluation purpose

      - Evaluation methodology

      - Findings

      - Conclusions

      - Lessons learned

      - Recommendations

      - Annexes, (including interview list, without identifying names in the interests of confidentiality/ anonymity; data collection instruments; key documents consulted; Terms of Reference.)

UNAIDS Source: Core Epidemiology Slides, November 2012.

UNICEF, 2011, Opportunity in crisis: Preventing HIV from early adolescence to young adulthood, p. 4.

UNAIDS, 2012, Report on the Global AIDS Epidemic, p. 70.

WHO, UNICEF and UNAIDS, 2011, Global HIV/AIDS Response: Epidemic Update and Health Sector Progress towards Universal Access—Progress Report 2011.

UNAIDS, 2010, Report on the Global AIDS Epidemic, p. 35.

Key global commitments on HIV/AIDS include the 2001 Declaration of Commitment adopted by 189 Member States at the UN General Assembly Special Session on HIV/AIDS (UNGASS), which specifically outlines gender equality commitments.   In 2006, at the five year review of the General Assembly Special Session of 2001, States reaffirmed the commitments made in the 2001, and agreed to setting national targets for 2010 on the provision of prevention, care and treatment (with interim targets for 2008).  The 2006 Political Declaration on HIV/AIDS also further recognized that gender inequalities and all forms of violence against women increase their vulnerability to HIV/AIDS.

See UNAIDS, 2012, Together We Will End AIDS, p. 70; Report of the Secretary General Report, 2012, United to End AIDS: Achieving the Targets of the 2011 Political Declaration, A/66/757.  Refer also to http://www.whatworksforwomen.org/.

Initial duration of implementation period was 36 months.

http://www.unaids.org/en/media/unaids/contentassets/documents/unaidspublication/2010/20100226_jc1794_agenda_for_accelerated_country_action_en.pdf

National launches aimed to raise awareness and accelerate action on the issue of women, girls, gender equality and HIV. It brought together high level stakeholders from diverse constituencies, including government representatives, networks of women living with HIV, civil society, development partners and the UN system to discuss operationalization of the Agenda as adapted to the national context.

UN Women brings together: UN Development Fund for Women (UNIFEM), Division for the Advancement of Women (DAW), Office of the Special Adviser on Gender Issues and the Advancement of Women (OSAGI), and UN International Research and Training Institute for the Advancement of Women (UN-INSTRAW).

Previous key global commitments on HIV/AIDS include the 2001 Declaration of Commitment adopted at the UN General Assembly Special Session on HIV/AIDS (UNGASS), which specifically outlines gender equality commitments.   In 2006, at the five year review of the General Assembly Special Session of 2001, States reaffirmed the commitments made in the 2001, and, among other things, further recognized that gender inequalities and all forms of violence against women increase their vulnerability to HIV/AIDS.

Results-Oriented Monitoring (ROM) exercises are external reviews carried out by a consortium contracted by the European Commission. It consists of interviews with the project stakeholders aiming to assess the project in terms of (i) relevance and design, (ii) efficiency, (iii) effectiveness, (iv) impact, and (v) sustainability.

The recommendations made in the first ROM mission were addressed as part of the second ROM.