END OF PROGRAMME EVALUATION

OF THE PROJECT

‘ACTION TO PROMOTE THE LEGAL EMPOWERMENT OF

WOMEN IN THE CONTEXT OF HIV AND AIDS’

03/2010 – 11/2013

Project 74882

IMPLEMENTED BY UN WOMEN

SUPPORTED BY CIDA - now called the Department of Foreign Affairs, Trade and Development (DFATD)

Evaluation Team

David Moore: Overall Team Leader

Kathleen Webb: Senior Evaluation Expert and Evaluation Field Work Team Leader

Shingaidzo Mupindu: Evaluation Team Member

9 May 2014

ABBREVIATIONS

ABANTU	ABANTU for Development (Kenya)

ACHPR	African Commission On Human and Peoples’ Rights

AIDS	Acquired Immune Deficiency Syndrome

ALNAP	Active Learning Network for Accountability and Performance

ARV	Antiretroviral

AVEGA	Association of Genocide Widows Agahozo (Rwanda)

CEASOP	Collaborative Efforts to Alleviate Social Problems (Uganda)

CEDAW	The Convention on the Elimination of All Forms of

Discrimination against Women

CfP	Call for Proposals

CIDA	Canadian International Development Agency

CIRRDOC	Civil Resource Development and Documentation Centre (Nigeria)

CO	Country Office

COHRE	Centre on Housing Rights and Evictions

CONGEH		Coalition des ONG et OCB du Cameroun œuvrant dans le domaine des Établissements Humains (Cameroon)

CPRC	Chronic Poverty Research Centre

DFATD	Department of Foreign Affairs, Trade and Development

(Global Initiative Directorate)

DFID	Department For International Development (UK aid agency)

DIALOGUE ON SHELTER	Dialogue on Shelter for the Homeless in Zimbabwe Trust

FGD	Focus Group Discussion

FWPIR-HIV-AIDS	Fund for Women’s Property and Inheritance Rights in the Context of HIV/AIDS (the programme under review)

FIDA	International Federation of Women Lawyers (Ghana)

GAC	Grants Approval Committee

GCBO			            Grassroots and Community-Based Organizations

GID	Global Initiative Unit

GROOTS	Grassroots Organizations Operating Together in

Sisterhood (Kenya)

HIV	Human Immunodeficiency Virus

HOP	House Of Peace – Tanzania

HRW	Human Rights Watch

IEC	Information, Education & Communication

IFI	Instituto de Formación Integral S.L.U

KII	Key Informant Interview

LCC	Land Consultation Clinics (Cameroon)

LRF	Legal Resources Foundation – Zimbabwe

M&E	Monitoring and Evaluation

MDG	Millennium Development Goals

MWEDO	Maasai Women Development Organization (Tanzania)

NAWLOG	National Women Lobby Group – Malawi

NGO	Non-Government Organisation

NSA	Non-State Actor

Ntengwe	Ntengwe for Community Development (Zimbabwe)

OA	Organizational Assessment

OECD	Organization for Economic Cooperation and Development

PDG	People’s Dialogue on Human Settlements (Ghana)

PMF	Performance Monitoring Framework

Prodoc	Programme Document

RESEAU	Réseau des Femmes Œuvrant pour le Développement Rural -Rwanda

RBM	Results-Based Management

SWID	Slum Women’s Initiative for Development (Uganda)

TOR	Terms of Reference

TRG	Technical Review Group

UGANET	Uganda Network On Law, Ethics And HIV/AIDS – Uganda

UNAIDS	The Joint United Nations Programme on HIV and AIDS

UNDAF	United Nations Development Assistance Framework

UNEG	United Nations Evaluation Group

UN Women	United Nations Entity for Gender Equality and the Empowerment of Women

WDG	Watchdog Group

WLHIV	Women Living with HIV

WLSA	Women and Law in Southern Africa -Zimbabwe

WPIR	Women Property and Inheritance Rights

WPIR-HIV-AIDS	Women Property and Inheritance Rights in the context of HIV/AIDS

YWAP	Young Widows Advancement Programme – Kenya

Table of Contents

EXECUTIVE SUMMARY	6

1.	Findings	6

2.	Lessons learned	9

3.	Recommendations	10

1	Programme description	13

1.1	Background of the WPIR-HIV Programme 2010-2013	13

1.2	Main log frame elements	13

1.2.1	Development Goal, Expected Outcomes, and Indicators	13

1.2.2	Internal logic, the results chain, and the main elements of the programme	14

1.3	Synthesis of the background to the legal empowerment of women in the context of HIV/AIDS	15

1.3.1	Main elements of the programme	16

1.4	Developments coming out of the end of the programme	16

1.4.1	Regional Policy Dialogue Conference (28 – 29 October, 2013)	16

2	Evaluation PURPOSE	17

2.1	Evaluation objectives and evaluation matrix framework	17

2.2	Evaluation Scope	17

2.3	The evaluation’s intended use and its audience	18

3	EVALUATION Methodology	19

3.1	Introduction	19

3.2	Evaluation Process	19

3.3	Evaluation Team	22

3.4	Limitations of the evaluation	22

4	FINDINGS AND ANALYSIS	23

4.1	Findings and analysis on relevance	23

4.1.1	Alignment of the WPIR-HIV projects with international and regional norms	23

4.1.2	Alignment of the 20 Grantee projects to rights, priorities and needs of targeted RHs	27

4.1.3	The extent to which the 20 grantee projects were consistent with the overall goal and the attainment of outcomes	28

4.1.4	Degree of Realism of Project Results based on the Context and Implementation Period	28

4.1.5	Monitoring indicators and their degree of coherence	30

4.1.6	The degree of coherence and appropriateness of the programmatic approaches and strategies that the grantees used for identifying the needs of stakeholders and RHs	31

4.1.7	The degree to which appropriate and sufficient outreach efforts were made to include and reach relevant DBs and RHs	32

4.2	Findings and Analysis on Effectiveness	33

4.2.1	Overview	33

4.2.2	Conclusion	34

4.2.3	Achievement of the Expected Results	34

4.2.4	Progress towards Outcome Area 1	34

4.3	Findings and Analysis on Efficiency	38

4.3.1	Strategic use of Project Resources	38

4.3.2	Building on existing initiatives and capacities	39

4.3.3	UN Women management efficiency	39

4.3.4	Extent of programme linkages with other UN Women or UN system initiatives (UNAIDS Joint programmes of support, delivering as one or relevant UN theme groups)	41

4.4	Findings and analysis on potential for sustainability	41

4.4.1	Extent to which UN Women has established a body of relevant information, materials and/or tools on women’s property and inheritance rights in the context of HIV and AIDS	41

4.4.2	The extent of synergy creation and the potential for durability of created partnerships	42

4.4.3	Other factors that are likely to affect project sustainability	43

4.5	Factors influencing performance	43

4.5.1	Programme design	43

4.5.2	Appropriateness and clarity of the strategies	44

4.5.3	Quality of the Stakeholder Partnerships	45

5	Conclusions	45

5.1	Relevance and coherence	45

5.2	Effectiveness	45

5.3	Efficiency	46

5.4	Sustainability	47

5.5	Achievement of outcomes and outputs	47

6	Lessons Learned	48

7	Recommendations	50

7.1	Donor and government partner strategies	50

7.2	Evidence-based knowledge	51

7.3	Portfolio diversification	51

7.4	Project Implementation	52

# EXECUTIVE SUMMARY

## Findings

The evaluation of the programme, ‘Action to Promote the Legal Empowerment of Women in the Context of HIV and AIDS’; Project 74882, 2010-2013, has produced 25 main findings, presented explicitly in chapter 4, below. They are presented here implicitly under the following OECD evaluation criteria:

Relevance: Grantee Projects

The programme responds fully to the ongoing initiatives of the 20 grantees, other donors, and partners working in the sector of women’s property and inheritance rights in sub-Saharan countries which are severely affected by the HIV epidemic to address the needs, priorities and rights of women, who constitute 54% of adults living with HIV. The programme’s subject matter was legal empowerment of those women deprived of their legal rights due to stigmatization and violence. UN Women’s approach was to work directly with experienced community-based organizations (CBOs) implementing projects at the intersection of the HIV epidemic and women’s property rights.

The programme was completely aligned with the relevant international and regional norms addressing women’s rights in the context of the HIV epidemic and the rights, priorities and needs of the targeted women. In the main, the grantee projects’ results or outputs set for the three outcomes were realistic and coherent in terms of the strategies and grassroots-level activities which would address issues in short term projects. The programme was well aligned with CIDA’s Legal Empowerment of Women Initiative, CIDA’s Children and Youth Strategy, and with CIDA's gender equality policy (please note that CIDA is now called DFATD).

To some extent, Outcome 1 was not specific enough with respect to a stated output for national-formal level change to legal frameworks and processes. I.e., the outputs were all community based, not national. National level players are best placed to change national level legal statutes. But Outcome 1’s outputs were very realistic for grassroots-level advocacy and lobbying using traditional forums and processes of reconciliation. The programme approaches and strategies were very relevant to the grassroots environment and strengthened the capacity of grantees to work with women suffering from property rights’ violations; and increased the evidence base concerning the most appropriate modalities and means to identify and work with women.

Effectiveness: Grantee Projects and UN Women

The programme has by and large achieved its outputs. The strategies and approaches used by the grantees were – generally speaking – effective because they produced the expected results as designated in the log frame matrix of the programme, and because the results have significantly enhanced the situation of women in the context of the HIV epidemic and violations of their property and inheritance rights in nine countries of sub-Saharan Africa.

For Outcome 1, the programme significantly increased the number of community legal frameworks and processes that would effectively promote and protect women’s property and inheritance rights in the context of the HIV epidemic, such as legal aid clinics, local tribunals, watchdog groups, paralegal teams and champion cells. The programme generally won the support of the local communities where it was implemented. The high quality of ready, willing and able partnerships contributed to the successful achievements of the programme. The utilization of a body of trained volunteer paralegals was crucial to the programme strategy because the paralegals played a significant role in training, sensitization and legal support activities, and because they filled a human resource gap at the grassroots level. But the number of paralegals per village is far below what is needed in some grantees’ projects. Eight grantees made progress towards changing the national-level legal frameworks and legal procedures regarding women’s property and inheritance rights in Cameroon, Ghana, Kenya, Nigeria and Zimbabwe. Five grantee projects directly challenged customary laws, or tried in their activities to enforce legislation protecting women.

For Outcome 2, the projects increased the evidence base concerning legal empowerment for the targeted women, especially regarding procedures and training for the dimensions of empowerment. “Empowerment” may be defined as a multi-dimensional social process helping people gain control of their lives within several dimensions (sociological, psychological, economic, legal) and at various levels (individuals, groups, communities).  The programme as a whole explored these dimensions.

The activities in Phases I and II in the 30 grantee projects have generated a body of information and materials that are relevant to women’s property and inheritance rights in the context of the HIV epidemic. The creation of a body of trained volunteer paralegals was key to the success of the programme because the former, with assistance from professional legal workers such as lawyers, have assumed (albeit with different degrees of success and sustainability) the primary role of guiding the women through legal processes.

The outputs for Outcome 3 enjoyed a positive movement towards future impact. An estimated 71,010 persons (85% of them women) received support from the 20 grantee projects in Phase I. In Phase II this figure was 59,734 persons (again, mostly women); who were supported via the grantee projects. Taken together, the programme assisted a total of 130,774 persons including women rights holders of various categories, and duty bearers. By training local women and men, citizens and leaders, widows and women living with HIV (WLHIV), paralegals, lawyers, and other stakeholders at the grassroots level, the programme has significantly built up local-level ownership and support for safeguarding and promoting women’s property and inheritance rights in the context of the HIV epidemic. Entrenched attitudes of opinion leaders, traditional leaders, and ordinary village men and women which limit or negate women’s property and inheritance rights, reportedly improved as a result of grantee projects’ activities to raise the awareness and expand the knowledge base about women’s property and inheritance rights.

Overall, the programme design exhibits many strengths which built on the prior experience and strategic priorities of UN Women to target and reduce discrimination against women and WLHIV in particular.

The programme should have better defined and ranked the strategies and their applicability to the achievement of the results for each outcome. For Outcome 1, separate strategies for national and district/community-level strategies should have been defined. An empowerment-for-change strategy should have been developed and well defined, for better programme implementation and as regards the other cross cutting strategies. In the absence of a before and after statistically representative baseline of the number of people trained, it is not possible to state empirically, and with certainty, how many women and men stakeholders in the different grantee projects have changed their knowledge, attitudes, and practices concerning women’s property and inheritance rights in the context of the HIV epidemic.

Efficiency: Grantee Projects and UN Women

Overall, grantees successfully used the programme resources in both phases to implement activities to achieve the programme’s overall development goal. The budget resources per grantee had a ceiling of USD 75,000. In some cases where key populations at higher risk were located in remote areas (e.g., MWEDO, in Tanzania, which worked with 500 Maasai women), funds were reportedly insufficient for covering the transportation costs to visit the remote areas. Generally, funds were used efficiently and helped build up local capacities of rights holders and duty bearers. As the executing agency, UN Women was reported to be efficient in administering the small grants funds, and used a transparent system that included clear selection criteria, and open and accountable adjudication of the results of the CfPs.

Potential for Sustainability: Grantee Projects and UN Women

The potential for future sustainability ranges from medium to high as the programme has built on, and built up, the capacities of local organizations and local governance and featured significant volunteerism. There are several threats to sustainability. Examples include Zimbabwe (WLSA), where the informal justice system that has been created with project support still depends on WLSA for legal aid support, creating a degree of dependency. Also in Zimbabwe (WLSA and LRF), there is inadequate after legal service support and follow-up which can create other future unintended challenges, and this means that – potentially – gains made in the earlier work will not to be sustained.

In a number of grantee projects, there is in evidence the complaint that funding was insufficient to allow sufficient and sustained field work in remote areas, for example in the case of MWEDO, working with Maasai women in Tanzania. In other grantee projects, sustainability is threatened by the large project area: the cost of logistics (distances to be driven by car, driver hours, petrol/diesel consumption, accommodations when in the distant project area) is prohibitive and threatens sustained activities.

Grantee projects have built up local-level support in many cases. Organizations such as ABANTU, AVEGA, GROOTS and local authorities have actively addressed HIV and AIDS and the violation of women’s property and inheritance rights. Several new bodies and groupings of human capital have been successfully created as a result of the programme: e.g., the paralegal cadres, champions for justice, watchdogs, and farming cooperatives. All of these benefited from training, and awareness raising. Moreover, their capacity to deliver was enhanced by the programme support to paralegals, albeit with some problems of quality that could be redressed with further support.

The programme utilized a small grants fund mechanism and therefore should not be expected to be sustainable in so short a period. Similar types of programmes would often have a minimum five-year time frame. This is because capacity strengthening and changing attitudes and practices in sensitive areas such as HIV/AIDS and property and inheritance rights are expected to take a long time. The time needed to create awareness and change negative practices such as asset stripping of women and their dependents, as well as reduce other manifestations of gender-based violence (cf. Annex 21: UN AIDS Goals 7 and 8, and Annex 20: UN AIDS Fact Sheet. Adolescents, young people and HIV) in the context of HIV and AIDS would be greater than a three-year period. Note that the theory of change for the programme specifies how legal empowerment could reduce gender-based violence against women in the context of asset stripping and violent denial of women’s property and inheritance rights.

On a positive note, in all the grantee projects analysed by the evaluator, the level of support achieved from grassroots stakeholders was very high given the short period of time.

Conclusions

The evaluated programme was financed by the Canadian government, which has an international commitment to empowering women and promoting gender equality. Indeed, the programme under review is part of the CIDA Legal Empowerment of Women Initiative, which aims to ‘support projects that advance women’s legal empowerment, with a particular focus on property rights, helping those affected and infected by HIV reduce their vulnerability to the epidemic and improve their ability to mitigate its consequences’. Additionally, the programme’s design fully reflects the major policy areas of the international community and of the UN system for promoting women’s equality and empowering women. The WPIR-HIV programme is well aligned with the six priorities of the UN Women Strategic Plan (2012-2013).

The Small Grants Fund was a relevant mechanism to directly reach communities. The CfP mechanism permitted a transparent system based on clear eligibility criteria to operate. The handouts on M & E visits during the CfP period provided information useful to the grantees in the form of mentoring and orientation. The interviewed grantees specified that they saw the leaflets and information on CfP as training or preparation, making it easier for them to write their proposals and write reports according to UN Women guidelines.

The PMF was well designed and was introduced in a fairly efficient way to the grantees, so that the latter were able, with periodical support, from UN Women M&E specialists in the country offices (HQ also provided technical guidance when requested by the UN Women country office) to report on their projects’ progress according to a standardized framework of indicators that has permitted some degree of aggregation and generalization of the overall results of the programme. Additionally, as was the case with the CfP modality, introducing the PMF increased the knowledge of the participating grantees, and provided considerable capacity building and training in results-based management of development interventions for the technical staff of the grantees.

In terms of educating people who were either ignorant of, or unsympathetic to, the problems faced by women facing discrimination and violence in connection with property and inheritance rights violations, it is clear that many duty bearers at community and higher levels – who are very often men – have learned to accept that advocating for women’s property and inheritance rights is an obligation, and that they must make greater efforts towards fulfilling it. These duty bearers are found in the official criminal justice systems (e.g., police, lawyers, magistrates, judges) and in the customary or traditional justice systems in the different programme countries.

In addition to training and enhancing the knowledge, attitudes, and practices (KAP) concerning women’s property and inheritance rights of duty bearers at several levels of government, the evaluation team finds that the programme reportedly enhanced the knowledge and self-esteem of thousands of the most vulnerable women and female minors (females under 15) in sub-Saharan Africa. This is a considerable achievement, and has led to a decline in suffering and stigma among the women clients in the grantee projects.

Among the women empowered are WLHIV and women with AIDS, female minors (child-headed households), women who have been expelled violently from their homes, women survivors of sexual violence and gender-based violence, and indigenous women such as Maasai women in Tanzania. These vulnerable and disempowered women and girls at the grassroots level have been assisted by the individual grantee projects to learn about their legal rights, and then subsequently to demand justice with assistance from paralegals and lawyers that have been provided via the programme. In many cases these women have successfully reclaimed their homes, lands, and livelihoods. This, again, is another major achievement of the programme.

There are some concerns about sustainability. These were raised in particular by some of the most experienced grantees (IFAD, MWEDO, GROOTS, LRF, and CIRRDOC). In particular, sustainability and social feasibility problems affect the paralegals and the technical support to be provided by lawyers to paralegals, and by both lawyers and paralegals to women clients. The paralegals appear in most cases to be in need of some kind of allowance to help them to continue in their work. At some point, the governments involved in the programme – especially the programme countries with relatively big economies like Kenya and Nigeria- would need to assume some increased responsibility for their paralegals.

There is however, a fairly large risk that, now that the grantee projects are no longer receiving funding, the paralegal services may decline, or even stop.

## 2.	Lessons learned

The main lessons learned are as follows:

Operational lessons

Length of time for implementation has been too short: A programme of this nature which aims to change knowledge, attitudes, and practices was overly ambitious given its original two-year timeline. Even when granted an extra year, time allotted has proven insufficient to cement the programme’s very real achievements in promoting women’s property and inheritance rights.

Importance of finding the correct entry points: A sense of ownership and shared vision results from the identification of stakeholders who are willing and able to participate in a project. The 20 grantees selected in Phase I were very experienced in terms of development and specifically in the area of women’s rights in the context of HIV and AIDS. Over time they had developed strong relationships with various partners in civil society. They built on these relationships and also developed new relationships with cultural and religious leaders. The good relationship with these leaders enabled the programme to gain an entry point for organising awareness-raising meetings. Working closely with the traditional leaders validated the programme’s objectives and activities in the communities’ eyes, especially the work of the paralegals. Thus men and women were open to new ideas and information about women’s property and inheritance rights.

Despite the short duration of the programme’s implementation, impact can be created by a combination of the right strategy and the right entry point: As a result of the grantees’ general success in building relationships and creating community-level entry points, it was easier in several cases to overcome resistance and to reconcile disputes between women and those who had denied them their rights.

Appropriate institutional arrangements with respect to fund distribution and consultation render the roles of different partners (donors, grantees) clearer and permit a timely completion of activities. The programme was well managed by UN Women, evidenced by a decentralized management of funds distribution and regular monitoring. A regional representative based in Nigeria worked closely with the grantees to respond to any questions grantees might have had regarding the programme. There were also several monitoring missions conducted by a regional team. The small grants mechanism also worked well in Phase I, as evidenced by the systematic process taken to select qualifying grantees, starting with the CfPs. The CfP modality ensured that the grantees knew what was expected of them. This is demonstrated by the fact that the activities were mostly completed on time.

Efficient tracking of funds makes it easier to coordinate expenditures during project management. UN Women had a system of funds distribution which ensured accountability and timely distribution of the funds in several tranches and pending reporting in a narrative and financial report format. The grantees expressed satisfaction with the fact that there was some degree of flexibility with respect to the budget lines, which made it easier for them to manage the funds as intended.

A bottom-up approach where support is directed at RHs at the grassroots level still requires national-level support and consultation. Mainly a sustainability issue, an absence of government buy-in and no / insufficient setting-up of national spending categories in the annual budget to pay for paralegals’ wages, travels costs, and other allowances will ultimately threaten the work achieved in this programme (see recommendations).  This lesson implies that the programme design should have included activities such as working directly with governments to advocate for, and assist in, helping to identify costs and setting up of national spending categories for paralegal services for women living with HIV.

Monitoring activities are time consuming even if they do provide capacity enhancement of GCBOs: The constant monitoring activities were a challenge. UN Women and the grantees had to monitor progress, in order to support the paralegals and the partners in the communities. However, because many of the activities were based in very rural areas, the grantees needed additional funds to pay for transport / logistics costs to monitor the activities (see recommendations).

Development lessons

The process of law reform takes a very long time, and it takes resources to support legal reform. The programme was a good initiative but needed more resources for the normative, legislative work, which is a long-term process that depends on lobbying and research (see recommendations).

## Recommendations

Based on the evaluation findings in the report and supporting evidence, the following recommendations are made to support the way forward:

## Donor and government partner strategies

Recommendation 1: It is recommended to fund a new programme providing financial and technical support to the nine countries; and also to start the programme in other countries in the Africa region.

The evaluation has highlighted: (1) the challenges faced by women who are excluded and victimized due to stigmatization in the context of the HIV epidemic; and (2) the readiness of grassroots civil society to address the problem of the structural and cultural inequalities concerning women’s property and inheritance rights, often on a volunteer basis. However, funding is a problem for some grantees, and certainly for the smaller GCBOs.

The recommended future programme would be financed for a minimum of five years with a budget of at least USD 5 million.  Given that the timeline of the programme was somewhat restricted, a future programme would need more time to achieve a more sustained and empirically demonstrable impact. At least 20% of the individual budgets for grantees working in geographically large areas with remote target groups should be allocated for logistics (petrol, transport) to permit sufficient outreach. In the evaluated programme, monitoring activities were time consuming, even if they did provide capacity enhancement of GCBOs. The constant monitoring activities were a challenge. UN Women and the grantees had to monitor progress, in order to support the paralegals and the partners in the communities. However, because many of the activities were based in very rural areas, the grantees needed additional funds to pay for transport/logistics costs to monitor the activities. In all cases, financial provision for logistics and transport to get out to remoter areas was insufficient; this negatively affected the potential reach of the programme and the individual grantee projects.

In the suggested future programme, it is recommended to: (1) include pilot activities in all countries to begin the move towards officially recognised formalization and standardization with regards to the curriculum and length of the training for paralegals; (2) make a more substantial financial provision for permitting M&E activities, necessary for measuring progress against targets; and (3) include before and after statistically robust baselines of the new programme’s universe, so that exact inferences can be made concerning Knowledge, Attitudes, and Behaviour with the collected data at the end of the programme.

Additionally, some of the GCBOs work in large areas, and their target groups are far away (e.g., MWEDO, working with the Maasai women in Tanzania). Furthermore, the programme implementation period was too short to achieve the full potential of the individual grantee projects and, hence, of the overall programme.  There is, therefore, a need for a further extension of the financial and technical support provided to the nine countries funded, and also to start the programme in other countries in the Africa region, in order to consolidate and build on the progress achieved so far.

It is clear that it would be more feasible to achieve the related goals of obtaining national-level repeal of discriminatory laws and the drawing up, discussion, approval, and enactment of new, pro-women legislation if more time were allocated for this process. One way of allowing more time for this lengthy process is to include a one- or two-year pilot phase before commencing implementation for the recommended new programme proper at the grassroots level.

A recommendation coming out of the lessons learned is that the empirical basis for evidence and impact monitoring needs to be improved. In the future, a sample of 10%, randomly selected, of the grantee projects could be extensively monitored, with statistically representative before and after samples of women in the context of the HIV epidemic and violations of women’s property and inheritance rights. The data could then feed into scientific publications in international journals publishing in the area of women’s property and inheritance rights in the context of the HIV epidemic. Publications with empirical evidence on progress in the field of women’s property and inheritance rights in the context of the HIV epidemic will make it more likely for UN Women to attract more money for future programmes as part of the response to HIV.

Recommendation 2: In the interest of sustainability of the paralegals as an entity and of the paralegals’ activities helping women living with HIV to obtain their legal rights to inheritance and property, it is recommended that UN Women in future programmes works directly with sub-Saharan African governments to advocate for, and assist in, helping to identify costs and setting up of national spending categories for paralegal services for women living with HIV.

## Evidence-based knowledge

Recommendation 3: UN Women is recommended to take the lead in consolidating the new knowledge acquired during the WPIR-HIV programme, via peer-reviewed, social scientific publications that have women’s rights, and women’s property and inheritance rights as primary areas of their concern. Three examples of these journals, or institutions, that have already published works on women’s property and inheritance rights, are ICRW (International Centre For Research on Women); World Development; and Human Rights Watch. The new information on women’s property and inheritance rights, obtained by the outcomes of the programme and from research conducted by the grantees themselves, needs to be synthesized and shared amongst partners.

## Portfolio diversification

Recommendation 4: Small grant portfolios in similar future programmes should be diversified to provide separate funding for grantees willing to lobby and advocate for national-level changes in laws, to repeal those which discriminate, and to enforce those that support women’s legal empowerment.

With the exception of eight grantees, the grantees mostly had experience working at grassroots level, supporting communities in many areas, including human rights. This provided the programme with many approaches using local traditional courts and traditional cultural leaders.

There are currently significant gaps in the nine African countries with respect to developing, clarifying and repealing laws. The national laws may also contradict those at community level. However, the traditional courts at grassroots level have proven effective in avoiding long, drawn-out court cases. The time taken to hear and process justice for local communities is usually shorter at grassroots level and less costly. The shorter time frame was also found to be favourable to women, whose health was often also fragile.

While the traditional courts were found to be valuable, there is always the risk that national-level policies and legal statutes can override them. There is therefore an urgent need to diversify portfolios to bring in a mix of grantees working at both the national (formal) level and grassroots (informal) level in a given country.

If donors ensure that an umbrella organisation is set up at national level (of any country funded), under which at least one national-level grantee would implement the programme, and also one grassroots grantee, this could allow the recommended portfolio diversification. Under the umbrella organisation, managed by UN Women, to give an example, the grantees could share strategies and findings. The end goal should be to change the formal laws so that they better protect women.

## Project Implementation

Recommendation 5: Expand empowerment strategies Expand, develop and fine-tune project strategies to cover all aspects of empowerment (legal, political, social and economic), paralegal training and support and conduct TOT courses so that empowerment can continue after the programme has come to an end.

# Programme description

## Background of the WPIR-HIV Programme 2010-2013

With funding from CIDA, in March 2010 UN Women launched the programme, ‘Action to Promote the Legal Empowerment of Women in the Context of HIV and AIDS’. The programme ended in November 2013. UN Women tendered an end-of-programme evaluation in 2013, retaining IFI to carry out the task. This report presents IFI’s evaluation findings, conclusions, recommendations and lessons learned.

## Main log frame elements

For the full PMF, see Annex XIX.

### Development Goal, Expected Outcomes, and Indicators

Development Goal: Women living with or affected by HIV and AIDS fully assert their property and inheritance rights, and thereby reduce their vulnerability to and are better able to mitigate the impacts of HIV and AIDS.

Expected outcomes and outputs:

The programme had three expected outcomes as follows:

OUTCOME 1:

Increase in number of legal frameworks and processes that effectively promote and protect women’s property and inheritance rights in the context of HIV/AIDS.

OUTPUTS FOR OUTCOME 1:

Output 1.1:

Enhanced knowledge and awareness of duty bearers responsible for the development, revision, and implementation of relevant legal frameworks and processes of the need to protect women’s property and inheritance rights.

Output 1.2: Duty bearers and gender equality advocates have access to effective mechanisms for dialogue with each other for developing or improving legal frameworks and processes that promote and protect women’s property and inheritance rights.

Output 1.3: Increased capacity of women infected or affected by HIV/AIDS to file property and inheritance cases in court and/or informal justice systems.

OUTCOME 2:

Strengthened enabling environment for promoting and protecting women’s property and inheritance rights at the community level.

OUTPUTS FOR OUTCOME 2:

Output 2.1: Relevant evidence base created on women’s community level experiences with claiming their property and inheritance rights.

Output 2.2: Enhanced knowledge and awareness of community-level opinion leaders of the need for them to exert an oversight role in resolving property grabbing and inheritance issues.

Output 2.3: Community members, including men and boys, aware of the need to actively support the realization of women’s property and inheritance rights.

Output 2.4: Enhanced knowledge and skills of legal service providers (including paralegals) available at the community level to assist women in protecting their property and inheritance rights.

Output 2.5: Legal and judicial community service providers and their organizations have access to effective mechanisms for knowledge exchange and mutual technical support for their work on women’s property and inheritance rights.

OUTCOME 3:

Women living with and/or affected by HIV and AIDS and their organizations better able to claim and advocate for the realization of their property and inheritance rights.

OUTPUTS FOR OUTCOME 3:

Output 3.1: Increased number of Women living with and/or affected by HIV and AIDS who are aware of their property and inheritance rights and of available access to the legal systems and/or support.

Output 3.2: Women living with and/or affected by HIV and AIDS and their organizations have increased knowledge and skills to effectively advocate for and monitor the realization of women’s property and inheritance rights.

After a Performance Monitoring Framework (PMF) validation workshop held in New York on 5 April 2011, a PMF framework was designed to support monitoring and reporting of results by the grantees. The PMF was initiated after the selection of grantees for Phase I was completed. At the same time, a regional coordinator and a funds manager were appointed to provide technical support to the grantees in both phases.

### Internal logic, the results chain, and the main elements of the programme

#### Internal logic

The programme’s internal logic is:

Goal: the overarching long-term results that the programme is hoping to contribute to (but that are not likely to be achieved during the programme’s lifetime).

Outcomes: the broader, mid-term results that the overall programme is aiming to contribute to during its lifespan.

Outputs: the specific short-term results that the programme wants to achieve and that it is accountable for.

The programme was designed as a small grants mechanism directly targeting community-based and grassroots organizations (CGBOs) and networks working at the intersection of HIV and AIDS and women’s property and inheritance rights. Funds were to be provided directly to twenty community-based and community organizations (or grantees) based in nine sub-Saharan countries, all of them severely affected by the HIV and AIDS epidemic.

By directing small, catalytic grants to community-level organizations (rather than through governments, INGOs and other donors) UN Women intended by this strategy to address structural inequalities that make women more vulnerable to HIV and AIDS, specifically those concerning access to rights and resources related to property and inheritance. Spelled out, there is in general either an absence of, or an ineffective presence of, at the level of the grassroots, state institutions promoting women’s rights, especially women’s property and inheritance rights, in the programme countries, and the strategy thus has implicitly attempted to fill in the lacunae between state service provision in the legal areas relating to women’s property and inheritance rights and the reality on the ground especially in remoter, rural areas, but in urban and peri-urban areas as well.

#### Results Chain

The results chain is as follows:

- Outcome 1 and its related outputs address anything to do with legal framework and processes that are relevant in view of women’s property and inheritance rights in the context of HIV and AIDS. This includes the role of duty bearers responsible for the development and implementation of these frameworks.

- Outcome 2 and its related outputs capture everything related to the enabling environment for women’s property and inheritance rights at the community level. This includes achievements related to working with community opinion leaders (e.g. traditional leaders), improving legal and judicial services available at the community level (e.g. through paralegals), as well as working with ‘ordinary’ community members including men and boys.

- Outcome 3 and its related outputs capture all achievements that have to do with changing the knowledge, skills, and behaviour of women living with and/or affected by HIV and AIDS and their organizations (i.e. the capacity of rights holders).

- These outcomes should lead to the achievements as expressed by the indicators, reproduced above.

## Synthesis of the background to the legal empowerment of women in the context of HIV/AIDS

The evaluation’s findings can be better understood if the social and political backdrop can be adequately described, and if benchmarks against which the evaluation team can compare programme progress can be isolated from the analysis of key background factors.

The 2011 UN political declaration on HIV and AIDS stated, among other things, that ‘women and girls are still the most affected by the epidemic and that they bear a disproportionate share of the caregiving burden, and that the ability of women and girls to protect themselves from HIV continues to be compromised by physiological factors, gender inequalities, including unequal legal, economic and social status…’. Drawing from the 2011 political declaration, UNAIDS articulated targets for 2015 to guide collective action.

As reported by the UN Women project document (Prodoc), research suggests that women who own property or otherwise control economic assets have higher incomes, a secure place to live, and greater bargaining power within their households. These factors enable women to better protect themselves from risks of HIV infection, to be more empowered to negotiate safer sex, and to avoid the need to engage in transactional sex (for money, food, or shelter).

The other side of this situation is that women living with HIV are at greater risk of having their land grabbed, etc. The programme was designed to carry out prevention and mitigation activities. Increasing economic assets and ensuring legal rights and legal redress mechanisms empower WLHIV to cope with the impact of AIDS on their families and communities, particularly after the loss of the main breadwinner in the family. Ensuring women’s rights to ownership of property and control over productive assets is therefore increasingly recognized as a critical step towards achieving the MDGs, particularly goal three – promoting gender equality and women’s empowerment, and goal six – combating HIV/AIDS, malaria and other diseases.

At a UN Conference held in 2010 to discuss progress towards the achievement of the Millennium Development Goals (MDGs) by 2015, attention was drawn to Goal 6.A of the MDGs: ‘That HIV/AIDS spread would have halted by 2015 and the spread of HIV/AIDS would have begun to reverse’. At that time it was noted that despite improvements in access to interventions to care for people living with HIV, stigma, discrimination and erroneous or absent legislation continued to hinder progress in the fight against HIV/AIDS.

The 2011 UN political declaration on HIV and AIDS stated, among other things, that ‘women and girls are still the most affected by the epidemic and that they bear a disproportionate share of the caregiving burden, and that the ability of women and girls to protect themselves from HIV continues to be compromised by physiological factors, gender inequalities, including unequal legal, economic and social status…’. Drawing from the 2011 political declaration, UNAIDS articulated targets for 2015 to guide collective action.

### Main elements of the programme

In Phase 1 of the programme, UN Women published Calls for Proposals (CfPs) from community-based and grassroots organizations in sub-Saharan Africa that were all working in the area of WPIR-HIV and AIDS. The CfPs resulted in 645 applications. An in-depth proposal review process within a three-tiered review process (due diligence, Technical Review Team, Grants Appraisal Committee) was conducted over a period of six months (September 20, 2010 – March 10, 2011) followed by a no-objection phase with country offices. UN Women then awarded small grants of up to USD 75,000 to 20 grantee organizations in nine countries: Kenya, Uganda, Tanzania, Cameroon, Ghana, Malawi, Nigeria, Rwanda, and Zimbabwe. The successful grantees signed agreements and implemented interventions aimed at contributing to the three programme outcomes over the period of 12 months for Phase I, from April 2011 – April 2012. The agreements with the 20 grantees were signed during the following three timelines as follows: 18 April 2011 – 17 April 2012 / 29 April 2011 – 28 April 2012 / 9 May 2011 – 8 May 2012.

The exact and full programme period is 31 March 2010 to 30 Nov 2013 which makes 44 months. The original agreement with Canada was 31 March 2010-31 March 2012 for 1 million CAD. It was amended with an extension of 9 months till 31 Dec 2012 and another 1 million CAD. A second amendment extended the programme till 30 Sept 2013 with another 1 million CAD. A last 2 months no cost extension was agreed, taking the programme period till 30 Nov 2013 (see Annex XIV for the WPIR-HIV portfolio description).

## Developments coming out of the end of the programme

### Regional Policy Dialogue Conference (28 – 29 October, 2013)

The programme culminated in a two-day conference entitled, ‘Peer Learning Exchange and Regional Policy Dialogue on Women’s Property and Inheritance Rights in the Context of HIV and AIDS’, hosted by UN Women, and held in Banjul from 28 – 29 October, 2013. The date and venue were chosen to coincide with the 54th Session of the African Commission Human and Peoples’ Rights (ACHPR) based in Banjul and meeting from 22 October – 5 November, 2013.

The conference served as an opportunity for Phase II grantees and some of their stakeholders to inform participants about WPIR-HIV-AIDS in their respective countries; to highlight effective strategies and discuss policies to address implementation challenges or to support scale-up of successful practices. It also served as an opportunity for participants to strengthen commitments to safeguarding and implementing WPIR-HIV-AIDS.

The event was also attended by regional representatives of the International Community of Women Living with HIV, the African Centre for Human Rights and Democracy, and two ACHPR commissioners. The latter were the Special Rapporteur on the Rights of Women in Africa and Chairperson of the Committee on the Protection of the Rights of People Living with HIV and Those at Risk, Vulnerable to and Affected by HIV.

The recommendations and findings made at the Regional Policy Dialogue Conference did not inform this evaluation; because this conference was held after fieldwork was completed.

# Evaluation PURPOSE

This chapter describes the aim of the evaluation, its intended use and audience.

Evaluation objectives and evaluation matrix framework

As stated in the TOR for the evaluation, the evaluation’s five specific objectives are:

- to assess the design and effectiveness of the small grants mechanism as an instrument of targeting community and grass-roots organizations and for responding to priorities and needs of women living with or affected by HIV and AIDS

- to assess and validate the relevance and effectiveness of strategies and approaches used by grantees

- to validate results in terms of achievement (or non-achievement) with a critical examination of how and to what extent outputs/results contributed to the programme’s three key outcomes

- to assess the potential for sustainability of results

- to document good practices and lessons learned to inform and strengthen UN Women’s programming approaches and interventions in this area

An analytical framework was developed during the inception phase against which the evaluation team analysed findings from questionnaires and other sources against the evaluation criteria. As the programme was implemented over a short period of 12 months per phase, it was decided that the evaluation team would focus on the following four OECD/DAC criteria. These are:

- Relevance: The extent to which a development intervention conforms to the needs and priorities of target groups and the policies of recipient countries and donors

- Effectiveness: The extent to which a development intervention has achieved its objectives

- Efficiency: The extent to which the costs of a development intervention can be justified by its results, taking alternatives into account

- Potential for sustainability: The likelihood of continuation of benefits of a development intervention after the cessation of development assistance

## Evaluation Scope

The time period of the scope of the evaluation is the programme implementation period of 31 March 2010 to 30 Nov 2013 (4 years, 44 months).  The field sample comprised seven grantee projects and a virtual sample of the remaining 13 grantee projects; all (with the exception of Uganda) interviewed over a study period of 21 days. Table 2 below shows the evaluation study sample including both intended and actual numbers interviewed by the evaluation team.

The evaluation covers two phases in the period, 31 March 2010 to 30 Nov 2013. In Phase I, 20 grantee organizations in nine sub-Saharan African countries received support from 2010 – 2011. In Phase II, grants were awarded to 10 of the 20 grantee organizations that had previously been awarded funds in Phase I. The geographic scope of the grantee projects was the four regions of sub-Saharan Africa where UN WOMEN was working, namely: the East and Horn of Africa (Kenya, Tanzania, and Uganda), West Africa (Ghana and Nigeria), Central Africa (Cameroon and Rwanda) and Southern Africa (Malawi and Zimbabwe). Table I below shows the 20 grantees funded in Phase I and the 10 supported in both Phase I and Phase II, by country and by region.

| Table 1: GEOGRAPHIC SCOPE OF GRANTEE PROJECTS (WPIR-HIV AND AIDS) |  |  |  |
| --- | --- | --- | --- |
| EAST AND HORN OF AFRICA | KENYA | UGANDA | TANZANIA |
|  | 1. ABANTU for Development Phase I 2.Grassroots Organizations Operating Together in Sisterhood (GROOTS) Phase I & II 3. Young Widows Advancement Programme (YWAP) Phase I & II | 4. Collaborative Efforts to Alleviate Social Problems (CEASOP) Phase I 5. National Community of Women living with HIV/AIDS (NACWOLA) Phase I 6. Slum Women’s Initiative for Development (SWID) Phase I 7. Uganda Network on Law, Ethics and HIV/AIDS (UGANET) Phase I | 8. Maasai Women Development Organization (MWEDO) Phase I & II 9. House of Peace (HOP) Phase I |
| WEST AFRICA | GHANA | NIGERIA |
|  | 10. International Federation of Women Lawyers (FIDA) Phase I & II 11. People’s Dialogue on Human Development (PDG) Phase I | 12. Civil Resource Development and Documentation Centre (CIRRDOC) Phase I & II |
| CENTRAL AFRICA | CAMEROON | RWANDA |
|  | 13. Coalition des ONG et OCB du Cameroun œuvrant dans le domaine des Établissements Humains (CONGEH) Phase I & II | 14. AVEGA: Association of Genocide widows Association Phase I & II 15. Réseau des Femmes œuvrant pour le Développement Phase I & II |
| SOUTHERN AFRICA | MALAWI | ZIMBABWE |
|  | 16. National Women Lobby Group (NAWLOG) Phase I | 17. Dialogue on Shelter for the Homeless Trust in Zimbabwe Phase I 18. Legal Resources Foundation (LRF) Phase I 19. Ntegwe for Community Development (NTEGWE) Phase I & II 20. Women and Law in Southern Africa Research and Education Trust (WLSA-Zimbabwe) Phase I & II |

## The evaluation’s intended use and its audience

UN Women, CIDA, and grantees will use the information, findings and recommendations to inform and strengthen policy, programme and advocacy interventions in future programming regarding women’s legal empowerment in the context of HIV/AIDS.

Specifically, the findings and analysis will be used to:

- contribute to building the evidence base on effective legal empowerment approaches and strategies for addressing gender inequality and human rights in the context of HIV/AIDS

- facilitate a process of strategic refection and learning for UN Women, UN system partners, CIDA, national and local policy makers, and civil society partners on integrating programming on legal empowerment of women living with or affected by HIV AIDS as part of a strengthened and more effective gender-responsive AIDS response

- strengthen UN Women’s advisory and policy support to country office teams and national partners

# EVALUATION Methodology

## Introduction

The evaluation used a rights-based, participatory approach to eliciting information from RHs, because the evaluation team wished to avoid top-down, extractive data-gathering in favour of participatory approaches. The evaluation team therefore adopted a mixed-method data collection approach to engage RHs (primary beneficiaries) and the DBs (stakeholders at national and community levels) who facilitated the individual projects within the programme.

## Evaluation Process

The evaluation was carried out between September 2013 and March 2014 (cf. Annex VI, Evaluation Phases and Tasks per Phase). Field data collection took 21 days from 30 September – 26 October 2013. 211 persons were interviewed in Kenya, Rwanda, Nigeria and Zimbabwe (7 grantees or 211 persons). Additionally, the evaluation team (Kathleen Webb, Shingaidzo Mupindu only) continued with Skype and telephone interviews for the 13 remaining grantees, DFATD, and UN Women focal persons until 18 December 2013 (26 interviewees). Analysis and report writing proceeded from 26 October until 28 April 2014. For the timeline, see Annex XI.

Inception Phase

A methodology was identified after the inception report’s approval. Following the inception meeting the methodology was later revised in agreement with UN Women’s evaluation unit. A set of main and sub questions was developed and questionnaires and question guides were drawn up. The evaluation team also reviewed all relevant programme files to identify the specific stakeholders (see Annex VII: Stakeholder Mapping).

The field sample comprised seven grantee projects and a virtual sample of the remaining 13 grantee projects; all (with the exception of Uganda) interviewed over a study period of 21 days. The table below shows the evaluation study sample including both intended and actual numbers interviewed by the evaluation team.

| Table 2: EVALUATION STUDY SAMPLE |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PART A: FIELD VISITS SAMPLE |  |  |  |  |  |  |  |  |  |  |  |
| Studied by | Country | UN Women Focal Points Sample Size |  | Grantees | Stakeholders Sample Size |  |  | Grantee Staff Sample Size |  | Beneficiaries Sample Size |  |
|  |  | Intended | Actual |  | Intended | Actual |  | Intended | Actual | Intended | Actual |
| Team leader | Kenya (East & Horn of Africa | 1 | 1 | GROOTS | 10 | 26 |  | 5 | 5 | 10 | 5 |
|  |  |  |  | ABANTU | 10 | 3 |  | 5 | 2 | 10 | - |
| Team leader | Rwanda (Central Africa) | 1 | 1 | AVEGA | 10 | 9 |  | 5 | 2 | 10 | 7 |
|  |  |  |  | RESEAU | 10 | 24 |  | 5 | 5 | 10 | 19 |
| Team Member | Nigeria (West Africa) | 1 | 2 | CIRDDOC | 10 | 7 |  | 5 | 5 | 10 | 32 |
| Team Member | Zimbabwe (Southern Africa) | 1 | 1 | WLSA | 10 | 8 |  | 5 | 2 | 10 | 12 |
|  |  |  |  | LRF | 10 | 9 |  | 5 | 8 | 10 | 16 |
| Total to be interviewed |  | 4 | 5 | 7 | 70 | 86 |  | 35 | 29 | 70 | 91 |
| Grand total of persons intended for interviews in the field: 179 (Actual total = 211) |  |  |  |  |  |  |  |  |  |  |  |
| PART B : PHONE INTERVIEWS (AND/OR EMAILS, SKYPE) |  |  |  |  |  |  |  |  |  |  |  |
| Studied by | Country | UN WOMEN Focal Points |  | Name of Grantee |  |  | Grantee Manager |  |  |  |  |
|  |  | Intended | Actual |  |  |  | Intended |  |  | Actual |  |
| Team Leader | Cameroon | 1 | - | CONGEH |  |  | 1 |  |  | 1 |  |
| Team Leader | Tanzania | 1 | 1 | MWEDO |  |  | 1 |  |  | 2 |  |
|  |  |  |  | HOP |  |  | 1 |  |  | 2 |  |
| Team Member | Uganda | 1 | 1 | CEASOP |  |  | 1 |  |  | 1 |  |
|  |  |  |  | NACWOLA |  |  | 1 |  |  | - |  |
|  |  |  |  | SWID |  |  | 1 |  |  | 1 |  |
|  |  |  |  | UGANET |  |  | 1 |  |  | 1 |  |
| Team Member | Malawi | 1 | - | NAWALOG |  |  | 1 |  |  | 1 |  |
| Team Leader | Ghana | 1 | 1 | FIDA |  |  | 1 |  |  | 2 |  |
|  |  |  |  | PDG |  |  | 1 |  |  | 2 |  |
|  |  |  |  | YWAP |  |  | 1 |  |  | 2 |  |
|  |  |  |  | Ntegwe |  |  | 1 |  |  | 1 |  |
|  |  |  |  | Dialogue on Shelter |  |  | 1 |  |  | 1 |  |
| Total phone interviews |  | 5 | 3 |  |  |  | 13 |  |  | 17 |  |
| PART C: Others |  |  |  |  |  |  | Intended Sample Size |  |  | Actual Size |  |
| Add DFATD Global Initiative Directorate |  |  |  |  |  |  | 1 |  |  | 2 |  |
| Add UN Women HQ staff |  |  |  |  |  |  | 4 |  |  | 2 |  |
| Add other donors working on similar projects |  |  |  |  |  |  | 2 |  |  | 2 |  |
| Total others |  |  |  |  |  |  | 7 |  |  | 6 |  |
| Total intended phone interviews: 25 (Actual phone interviews = 26) |  |  |  |  |  |  |  |  |  |  |  |

Data Collection Phase

As the above table shows, the team intended to interview 204 persons, as agreed upon during the inception period. The actual number interviewed was 237 persons. There were some gaps in the fieldwork due to challenges in communication and logistics. The evaluation team relied solely on a documentation search in order to evaluate NACWOLA (Uganda), because the staff members who had worked with the programme had moved on since 2012 (when Phase I ended).

Data Analysis and Report Writing Phase

During information analysis and report writing, the evaluation team analysed field data from the earlier data collection phase. This information was triangulated by type of interview (focus group discussions [FGDs], key informant interviews [KIIs]) against observations and documentation. Where useful, the results were developed into tables or other graphs. After completing the analysis and synthesis of the preliminary findings, lessons learned and recommendations, a PowerPoint was presented to UN Women on 12 November 2013, followed by feedback to the evaluation team. Additional documentation was requested from UN Women and received. A draft report was prepared, submitted on 2 December 2013 and later revised in February – March 2014 (cf. Annex XI, timeline).

Data Sources

The documentation review confirmed that stakeholders comprise a diverse group in civil society. Data sources described RHs such as women living with HIV/AIDs, DBs such as government, UN Women and donor officials, and MDBs, such as the grassroots organisations, CBOs, and NGOs comprising the grantees working with women RHs. The data collection methods employed were: document review; KIIs, FGDs, Skype and telephone interviews, case studies and field observations. The methods used were basically the five question guides and a case study template (cf. Annex V: field date collection tools). The tools included questions on gender equality and human rights issues. The data sources are described below. Anonymity was upheld, as per the TOR’s instructions, where required.

Documentation

The document review was mainly based on background documents provided by UN Women, including general management documents and grantees’ reports. It also involved the review of regional and international instruments on gender equality, women’s rights, property and inheritance rights, and HIV and AIDS. Furthermore, the evaluation team reviewed additional literature to complement and substantiate the analyses and recommendations. The documents reviewed provided information on the programme context, background, activities, and achievements. The information obtained was triangulated whenever possible with information from other data sources (cf. Annex II: list of references).

Key Informant interviews

KIIs took place in person, using the question guides (Tool 2), in the countries the team visited. Furthermore, using the medium of Skype or telephone, the question guides in Tool 2 were used to elicit key informants’ impressions of the programme. The in-depth interviews allowed a certain depth of information to be gathered. Respondents who were unable to go through all the questions in the question guide during the in-depth interview session forwarded the completed question guides to the evaluation team electronically later on.

Using Tools 1, 2, 4 and 5, the team gathered information on all aspects of the programme, as specified in the TOR. The question guides permitted the team to execute systematic data collection, allowing the interviewer and interviewee to discuss topics including sensitive ones in detail and to add additional topics for discussion. The question guide was the primary method for interviewing respondents such as UN Women focal persons, HQ staff, grantee management, local leaders, community groups and other stakeholders.

Focus Group Discussions

The FGD method of evaluation allows small groups of six to eight persons to explore topics in depth. Topics broached during FGD sessions included: the perceived relevance of the grantee projects to the interviewed women, and the potential for sustaining the project activities after the cessation of funding. The FGDs mainly utilized question areas specified in Tool 3, for interviewing the programme RHs in the field, namely women with HIV/AIDS or women confronting infringements of their inheritance and property rights. In Rwanda, the women RHs interviewed included genocide widows.

Direct Observations

In cases where the outputs were tangible (such as recovered property from women who had been disinherited), the team directly observed events in order to obtain information on services, goods, or assets received by RHs.

Case Studies

During the field interviews with RHs, the team selected one success story to serve as a case study per country and documented the sequence of events which occurred over time.

## Evaluation Team

The consultant provided the overall management of the evaluation activities. The evaluation team comprised Kathleen Webb, team leader and monitoring, evaluation and reporting expert, and Shingaidzo Mupindu, evaluator and gender and development expert. The two experts worked concurrently when conducting fieldwork and desk reviews for the 20 grantee projects in the period September – November 2013. David Moore joined the evaluation in January 2014, conducted some interviews by Skype, and revised the main evaluation report between 20 January and 28 April 2014 in close cooperation with the two above-mentioned consultants.

UN Women’s role: The evaluation team was supported by the UN Women HQ programme manager, gender equality and HIV and AIDS; and was also guided by the core reference group and the broad reference group. The HQ-based programme manager supported liaising with the country office and the donor. The programme manager provided essential documents and facilitated communication. The core reference group provided direct oversight and technical guidance. The broad reference group was kept informed and participated in the evaluation process at strategic points.

## Limitations of the evaluation

The evaluation was conducted as intended with some challenges. The seven field sites in Kenya, Zimbabwe, Rwanda and Nigeria were visited as intended. The evaluation team members worked closely together, despite being in different countries and not meeting physically. They managed to carry out the tasks, despite challenges with internet connections, which made online communication time consuming and difficult to achieve. Additionally, there was the challenge of the long fieldwork distances to be covered, and, in some cases, poor roads. The latter problems made it difficult for the evaluation team to follow the schedules jointly set with the grantees. In Malawi, the UN Women focal persons were unavailable for interview. In Uganda, one grantee, NACWOLA was not interviewed as attempts to  contact the organization  were not successful.

Finally, as mentioned above, the evaluation was conducted before the policy dialogue; the latter has therefore not informed this evaluation’s findings and recommendations.

It is useful to refer now to Annex XVIII:  Outcome 1 results/outputs for phase 1 & 2 (national level activities) and Annex XIII (Phase I and II achievements of Outcomes 2, 3), which provide information on what the programme achieved before reviewing the findings in chapter 4 below.

# FINDINGS AND ANALYSIS

## Findings and analysis on relevance

### Alignment of the WPIR-HIV projects with international and regional norms

Finding 1: The WPIR-HIV projects were well aligned to the relevant international and regional norms addressing women’s rights in the context of HIV and AIDS.

The requirements of the CfP were for grantee proposals to address at least one of the following three outcome areas: (1) Strengthening legal frameworks and processes that promote women’s rights and eliminate gender inequality in the context of HIV/AIDS, particularly in relation to WPIR;  (2) Building the capacity of legal professionals and paraprofessionals (i.e. paralegals), informal justice system service providers to implement adequate legislation or remove gender discriminatory provisions in existing legislation relating to HIV/AIDS toward promoting and protecting women’s rights to property and inheritance; and (3) Enhanced capacity and influence of gender equality experts, advocates and their organizations and networks to ensure that national HIV/AIDS laws, policies and strategies uphold and promote women’s rights.

By default, the grantee projects would be unlikely to be insufficiently aligned with international and regional norms promoting WPIR-HIV-AIDS. The detailed eligibility criteria set out in the CfP tender documentation for GCBOs and the technical specifications therein concerning scope of potential projects and their expected results were an efficient mechanism for promoting programme goals (see Efficiency below, 4.3) because the eligibility criteria did not allow for projects to be proposed that would not promote women’s property and inheritance rights in the context of HIV-AIDS (see Lessons Learned, chapter 6).

The principal, relevant international and regional norms and benchmarks that the grantee projects were evaluated against are found in Annex XV. Some key aspects of the HIV-related norms which are relevant to the programme being evaluated are described below:

#### The HIV-related norms

The Declaration of Commitment on HIV/AIDS 2001.  This covers (the following points are not an exhaustive list from the quoted document):

- Care, support and treatment: This includes, of relevance to the programme under review, the key question of improving government health services and reducing access barriers to heath care, viz.: “Access to medication is a fundamental element for achieving progressively the right of everyone to the highest possible standard of physical and mental health (para. 15). Human resources and health and social infrastructures must be strengthened in order to deliver prevention, treatment, care and support services (para. 22). Effective prevention, care and treatment strategies require behavioural change; increased access to vaccines, condoms, microbicides, lubricants, sterile injecting equipment, drugs, including antiretroviral therapy, diagnostics, and increased research and development (para. 23). The lack of affordable drugs, a feasible drug supply and adequate health systems is hindering an effective response to HIV/AIDS, especially for the poorest people (para. 25)”.

- “Countries should increase access to drugs through innovation and domestic industries consistent with international law, and the impact of international trade agreements on access to drugs should be further evaluated (para. 26)”.

- HIV/AIDS and human rights: This includes, of relevance to the programme under review, an emphasis on reducing gender based violence against women, viz.: “By 2005, implement strategies to empower women, protect their human rights, and reduce their vulnerability to HIV/AIDS by eliminating all forms of discrimination and violence against women and girls, including harmful traditional practices, abuse, rape, sexual violence, battering and trafficking (para. 61).”)

- Children orphaned and made vulnerable by HIV/AIDS:  This includes, of relevance to the programme under review, the key question of loss of inheritance and violence, viz.:  “By 2003, develop and, by 2005, implement strategies for creating supportive environments for orphans, girls and boys infected and affected by HIV/AIDS by providing: counseling and psychosocial support; enrolment in school; access to shelter, good nutrition, health and social services; and protection from abuse, violence, exploitation, discrimination, trafficking and loss of inheritance (para. 65)”.

#### The Political Declaration on HIV 2006

This document stresses several factors of high relevance to the programme under review, viz.:

- Para 7: The burden of HIV on women, and stresses that gender inequalities and violence against women and girls is an exacerbating factor in increasing, viz. :”Remain deeply concerned, however, by the overall expansion and feminization of the pandemic and the fact that women now represent 50 per cent of people living with HIV worldwide and nearly 60 per cent of people living with HIV in Africa, and in this regard recognize that gender inequalities and all forms of violence against women and girls increase their vulnerability to HIV/AIDS”;

- Para 15:  Recognize further that to mount a comprehensive response, we must overcome any legal, regulatory, trade and other barriers that block access to prevention, treatment, care and support; commit adequate resources; promote and protect all human rights and fundamental freedoms for all; promote gender equality and empowerment of women; promote and protect the rights of the girl child in order to reduce the vulnerability of the girl child to HIV/AIDS;

- Para 29: Commit ourselves to intensifying efforts to enact, strengthen or enforce, as appropriate, legislation, regulations and other measures to eliminate all forms of discrimination against and to ensure the full enjoyment of all human rights and fundamental freedoms by people living with HIV and members of vulnerable groups, in particular to ensure their access to, inter alia, education, inheritance, employment, health care, social and health services, prevention, support and treatment, information and legal protection, while respecting their privacy and confidentiality; and developing strategies to combat stigma and social exclusion connected with the epidemic;

- Para 30: Pledge to eliminate gender inequalities, gender-based abuse and violence; increase the capacity of women and adolescent girls to protect themselves from the risk of HIV infection, principally through the provision of health care and services, including, inter alia, sexual and reproductive health, and the provision of full access to comprehensive information and education; ensure that women can exercise their right to have control over, and decide freely and responsibly on, matters related to their sexuality in order to increase their ability to protect themselves from HIV infection, including their sexual and reproductive health, free of coercion, discrimination and violence; and take all necessary measures to create an enabling environment for the empowerment of women and strengthen their economic independence; and in this context, reiterate the importance of the role of men and boys in achieving gender equality;

#### The current Political Declaration on HIV and AIDS 2011.

This document has many areas directly relevant to the programme under review. The following two paragraphs (the following points are not an exhaustive list from the quoted document) are directly relevant to property, inheritance and violence against girls and women issues:

- Para 21: “Remain deeply concerned that, globally, women and girls are still the most affected by the epidemic and that they bear a disproportionate share of the caregiving burden, and that the ability of women and girls to protect themselves from HIV continues to be compromised by physiological factors, gender inequalities, including unequal legal, economic and social status, insufficient access to health care and services, including for sexual and reproductive health, and all forms of discrimination and violence, including sexual violence and exploitation”;

- Para 76:  “Advancing human rights to reduce stigma, discrimination and violence related to HIV. “Commit to intensify national efforts to create enabling legal, social and policy frameworks in each national context in order to eliminate stigma, discrimination and violence related to HIV and promote access to HIV prevention, treatment, care and support and non-discriminatory access to education, health care, employment and social services, provide legal protections for people affected by HIV, including inheritance rights and respect for privacy and confidentiality, and promote and protect all human rights and fundamental freedoms, with particular attention to all people vulnerable to and affected by HIV”;

The mechanisms that permit monitoring of sub Saharan African countries’ progress towards fulfilling their commitments concerning WPIR-HIV-AIDS as expressed in the international and regional norms and benchmarks include the list in Annex XV.

CEDAW: All the countries in the programme under review have ratified CEDAW. Acceptance of CEDAW obliges states to undertake a series of measures to end discrimination against women in all forms, including: (1) to incorporate the principle of equality of men and women in their legal system, abolish all discriminatory laws and adopt appropriate ones prohibiting discrimination against women; to establish tribunals and other public institutions to ensure the effective protection of women against discrimination; and (3) to ensure elimination of all acts of discrimination against women by persons, organizations or enterprises.

A key issue concerning point 1 (abolish all discriminatory laws), which is of particular concern for the programme under review is the existence of different customary laws in sub-Saharan Africa. Recent anthropological studies of women’s property and inheritance rights in Ghana, Kenya, Mozambique, Rwanda and Uganda rightly underline how ‘inheritance conjures some of the most sensitive political economy questions in many sub-Saharan African societies, including the status of women, land ownership and control, and the social legitimacy and capacity of statutory and customary systems of governance.’

Customary systems of land governance: A major objective of the grantee projects has been to challenge the customary systems of land governance, which discriminate against women, and which are enshrined by constitutions such as Ghana, Mozambique and Uganda, for example.

Finding 2: Five grantee projects directly challenged customary laws, or tried in their activities to enforce legislation protecting women.

Five grantee projects directly challenged customary laws, or tried in their activities to enforce legislation protecting women, viz.: ABANTU (Kenya), CIRDDOC (Nigeria), FIDA (Ghana), NACWOLA (Uganda), NAWOLG (Malawi). Three examples from paraphrased evaluation field data corroborate this finding, viz.:

- In Kenya, ABANTU probably achieved one of the highest memorable results by lobbying successfully to get the UPAR law passed and steps taken towards property distribution.  Indeed, ABANTU staff also reported that more time is needed to address the issues of resistance at policy making, i.e., that lobbying efforts will need to continue after the end of this grantee project;

- In Zimbabwe (WLSA), the grantee project spearheaded and successfully advocated for inclusion of property and inheritance clauses in the amended Zimbabwe constitution (2013); broadened the formal legal framework through policy engagement and advocacy e.g. for law reform; drafted the model legislation on women’s property and inheritance rights in the context of HIV-AIDS which is currently (November 2013) awaiting approval with policy makers; and set up and is coordinating the Women Inheritance Property Network in Zimbabwe.

- In Malawi (NAWLOG), among the significant achievements of this grantee are: (a) provision of legal aid to women who had been disinherited; (b) women repossessed their property within the context of the Wills and Inheritance Act; (c) project lobbying concerning the interpretation of this legislation has resulted in a review of the Marriage and Divorce Act, Land Act, Registered land Act and the Land Acquisition Act.

Beijing and its follow-up:

Finding 3: There is a direct link between the aims of some of the grantee projects and key strategic objectives of the Platform for Action that was held in Beijing in September 1995.

There is a direct link between the aims of some of the grantee projects and key strategic objectives of the Platform for Action  held in Beijing in September 1995, e.g., strategic objective H.2.: ‘Integrate gender perspectives in legislation, public policies, programmes and projects’. Examples of grantee projects advocating for women’s rights in national legislation or in other project activities are: (1) ABANTU’s project which advocated for the enactment of Kenya’s National Unclaimed Financial Assets Bill; (2) CIRDDOC’s project to reduce discrimination against women in Nigeria by inter alia capacity building of anti-VAW committees and mapping discriminatory, customary laws; and (3) FIDA’s project that aimed to ensure that Ghanaian AIDS policies uphold WPIR.

Protocol to the African Charter on Human and Peoples' Rights on the Rights of Women in Africa:

Finding 4: The programme was aligned with key provisions of the protocols promoted by ACHPR.

The programme was aligned with key provisions of the protocols promoted by ACHPR (e.g., Articles 2, 8, 14, 20, 21). Examples of grantee projects that specifically address the above-cited articles are:

| Table 3: ALIGNMENT BETWEEN GRANTEE PROJECTS AND KEY PROVISIONS OF THE PROTOCOLS PROMOTED BY ACHPR |  |
| --- | --- |
| Article | Grantee project examples |
| Article 2: Elimination of Discrimination against Women | ABANTU Kenya; GROOTS Kenya; LRF Zimbabwe; NAWOLG Malawi |
| Article 8: Access to Justice and Equal Protection before the Law | FIDA Ghana; Réseau Rwanda |
| Article 14: Health and Reproductive Rights | FIDA GHANA; UGANET Uganda |
| Article 20: Widows' Rights | AVEGA Rwanda |
| Article 21: Right to Inheritance | CIRDDOC Nigeria; Dialogue on Shelter Zimbabwe |

Despite being aligned with international and regional norms and standards, the operating environments under which the 20 grantee projects were implemented in the nine countries is not uniform. The details on the ground of women’s property and inheritance rights in the context of HIV-AIDS are different in the nine programme countries, for a number of reasons. In analysing the programme’s effectiveness (see below 4.2) the sociological, cultural, and legal factors that emerged to either facilitate or hinder the success of the individual grantee projects are analysed.

UN Women’s mandate and norms:

Finding 5: The WPIR-HIV programme is well aligned to the six priorities of the UN Women Strategic Plan (2012-2013).

UN Women’s mandate is to promote gender equality and the empowerment of women. The WPIR-HIV programme is well aligned to the six priorities of the UN Women Strategic Plan (2012 – 2013). The activities that the grantee projects carried out fully reflect the priorities of the UN Women Strategic Plan, viz.:

| Table 4: Priorities of the UN Women Strategic Plan | Grantee project examples |
| --- | --- |
| Increasing women’s leadership and participation | Dialogue on Shelter Zimbabwe (training female paralegals) |
| Increasing women’s access to economic empowerment and opportunities | ABANTU Kenya (enact Financial Assets Bill); WLSA (Phase II) Zimbabwe (legal services provided to women; and income generation activities added to the project) |
| Preventing violence against women and girls, and expanding access to services | ABANTU Kenya (legal, advisory services); CIRDDOC Nigeria (anti-VAW activities) |
| Increasing women’s leadership in peace, security and humanitarian responses | CEASOP Uganda (enhance women’s capacity and strengthen women’s self help groups) |
| Strengthening the responsiveness of plans and budgets to gender equality at all levels | FIDA Ghana (advocacy at high levels to get Ghanaian AIDS policies to uphold WPIR) |

CIDA (now called DFATD):

Finding 6: The programme is well aligned with CIDA’s Legal Empowerment of Women Initiative, CIDA’s Children and Youth Strategy, and with CIDA's gender equality policy.

The programme is part of the CIDA (now DFATD) Legal Empowerment of Women Initiative, a commitment of 5 million Canadian dollars over a five-year period. The initiative is intended to ‘support projects that advance women’s legal empowerment, with a particular focus on property rights, helping those affected and infected by HIV reduce their vulnerability to the epidemic and improve their ability to mitigate its consequences’. The programme is also aligned with CIDA’s Children and Youth Strategy, viz.: ‘strengthen and implement national protection legislation and mechanisms to safeguard the human

rights and security of children and youth and to protect them, particularly girls, against violence and exploitation.’  The programme is also in line with CIDA's gender equality policy.

### Alignment of the 20 Grantee projects to rights, priorities and needs of targeted RHs

Finding 7: The 20 grantee projects funded in Phases I & II were well aligned with the rights, needs, and priorities of RHs (defined as WLHIV or women potentially at risk of HIV/AIDS), with the possible exception of one grantee project in Zimbabwe (grantee: Dialogue on Shelter for the Homeless).

One example illustrates this finding, viz., AVEGA, Rwanda: The project design was based on a prior needs assessment to establish which problems are related to property and inheritance rights. Of the 1,125 widows interviewed by AVEGA, about 80% showed signs of trauma, and 67% were HIV-positive. Members and beneficiaries of AVEGA infected and affected by HIV/AIDS were reportedly incapable of pursuing their property and inheritance rights because of ill health, lack of money, trauma, and stigma. Women members of AVEGA who were HIV positive lived with the daily threat of being dispossessed. There were insufficient interventions and programmes to redress their precarious situation The AVEGA example above shows that prior needs assessments and the grantee’s intimate knowledge of the reality on the ground permitted the design of projects that completely reflect the expressed needs of WLHIV or women potentially at risk of HIV/AIDS.

The field interviews also corroborated the fact that the women and men RHs involved in the projects perceived that the activities reflected their stated needs and priorities.

### The extent to which the 20 grantee projects were consistent with the overall goal and the attainment of outcomes

In Phase I, all 20 projects specifically targeted WLHIV or women at risk of HIV and/or affected by HIV and AIDS; all 20 aimed to strengthen access to women’s property and inheritance rights. In some projects, e.g., Ntengwe, Zimbabwe, equal emphasis is placed assisting women and girls who are living with or affected by HIV/AIDS. Thus, training was also provided to the police, traditional leaders, local government paralegals as well as teaching women and girls directly in order to empower them face-to-face in community training sessions.

Particularly vulnerable groups are targeted in some of the projects: e.g., (1) MWEDO targets indigenous Maasai women living with or affected by HIV/AIDS in Tanzania; and (2) AVEGA targets doubly disadvantaged women (meaning that they are genocide widows, and also affected by HIV), women who are genocide widows and who are living with or affected by HIV/AIDS.

In Phase II, all 10 projects specifically target WLHIV or women potentially at risk of HIV/AIDS and all aim to strengthen access to women’s property and inheritance rights. Examples of particularly vulnerable groups that were targeted for empowerment in some of the projects are: (1) Ntengwe, Zimbabwe, which targeted high-risk sex workers (sex workers –at least in West and Central Africa- are often at a higher risk of HIV infection) in a geographical area (Victoria Falls) with a high HIV prevalence rate; and (2) GROOTS, Kenya, which targeted geographical areas with high levels of asset stripping and property rights violations.

### Degree of Realism of Project Results based on the Context and Implementation Period

Finding 8: The project results/outputs set for the three outcomes were realistic in terms of the current strategies and grassroots-level activities employed by the grantees. To some extent, Outcome 1 was not entirely relevant to the grassroots levels grantee projects, because it has proven difficult for 12/20 GCBOs to influence national-level (formal) legal frameworks and processes.

The grantees were free to select any of the three outcomes they felt they could best focus on in their individual grantee project. They designed the individual strategies and activities as a reflection of what would be required to achieve each output for each outcome.

The choice of strategies that grantees used was realistic because they could address the factors that characterise HIV/AIDs and women’s property and inheritance rights in the specific, local geographical location and socio-cultural backdrop. An example is the factor, ‘protecting women and girls from HIV means protecting against GBV and promoting economic independence’. GBV and economic independence were not explicit objectives or outputs of the programme, but nevertheless are implicitly included in the programme because the latter was aligned with the main concerns of the HIV-related norms  (reviewed above, 4.1.1), and were more of an indirect result or outcome.

By the end of the Phase I projects, the grantees selected for Phase II were able to understand better the links between the prevention of GBV and economic independence, thereafter implementing interventions to protect, shelter and economically empower women. Recipients of funding in Phase II carried out economic empowerment activities through small loans and cooperatives. This learning-by-doing approach demonstrates that the grantees could carry out coherent interventions to achieve the expected results.

Finding 9: The programme implementation period was too short to achieve the full potential of the individual grantee projects, for all three outcomes.

It was not possible to achieve tangible results within the short implementation period. Changing national policies, civil codes, and implementing new laws concerning women’s property and inheritance rights so that they are no longer discriminatory or harmful to women would require a longer-term programme. The field data (Annex IX) substantiate the latter finding that time of implementation was insufficient. For example: (1) Staff interviewed in Kenya (ABANTU) reported that much time was needed to address the issues of resistance at policy-making level towards reunifying the target group with resources, and also creating awareness; and (2) in Cameroon (CONGEH), informants stated that a longer time period in a national programme with multiple donors is needed to reverse the trends of stigma and asset stripping.

Small grants mechanism: Field data reproduced in Annex IX do not provide details on perceptions of grantees about the small grants mechanism. However, the field data do reveal information useful to the evaluation concerning the amount of the grants. E.g., in Tanzania, MWEDO had identified 500 women within 15 wards of Arusha region who were to be reached through local dialogue sessions at village and district level with government and traditional leaders to reach a common understanding. The problem was one of efficiency again, and not due to any fault in the modality of the small grants mechanism. The time period was too short to reach all the women in such remote areas, and it took until the second phase to reach all 500 women.

Finding 10: The strategy to provide increased knowledge and skills on inheritance and property rights to those in power, and to people who deny women their inheritance or property rights in the local communities, was coherent.

The training sessions, awareness raising, and capacity building at the grassroots level of traditional leaders, opinion setters, and perpetrators of wrongs against women, reportedly (see Annex IX) empowered community-level opinion leaders to exercise an oversight role in resolving property grabbing, using their newly acquired knowledge about women’s property and inheritance, which in turn contributed to the projects being seen in a very positive light, especially by women victims. Attitude change therefore occurred, albeit slowly, especially in nomadic communities in Tanzania and Kenya.

Overall programme strategy: The overall programme strategy is to achieve the development objective by means of advocacy; awareness-raising; capacity development; community education and community mobilization; data collection; legal service provision and coordination; and to undertake these activities using the small grants mechanism to fund grantee projects which collectively follow the programmatic approach.

Regarding e.g., Output 1.2 (duty bearers and gender equality advocates have access to effective mechanisms for dialogue with each other for developing or improving legal frameworks and processes that promote and protect women’s property and inheritance rights), programme monitoring reports describe how there were increased spaces for dialogue between gender equality advocates and DBs to develop and improve legal frameworks and processes that promote and protect women’s property and inheritance rights at regional, national and mostly at local levels. Field data also corroborate this positive impact (see Annex IX for examples).

Concerning e.g., Output 2.5: (legal and judicial community service providers and their organizations have access to effective mechanisms for knowledge exchange and mutual technical support for their work on women’s property and inheritance rights), a programme progress report and an evaluation skype interview demonstrate how grantees supported mechanisms aimed at strengthening linkages of these mechanisms with local-level authorities in order to facilitate access to justice for WLHIV.

Paraphrased field data on Ghana (FIDA), indicate a high level of achievement meeting the three expected outcomes. Women infected or affected by HIV and AIDS received paralegal and legal support towards preventing asset-stripping and addressing it through legal cases. Some HIV positive children benefitted from medical and financial support, and mentoring to help them live positively.  (This was not an intended outcome, but an indirect or unintended result.)

### Monitoring indicators and their degree of coherence

From an empirical, evaluation perspective, the indicators used to track any supposed progress towards achieving programme goals will be crucial. The PMF framework outlines the strategy for measuring progress of the programme against its envisaged results. The main users of the PMF were (1) UN Women (HQ) so programme staff could keep track of overall progress against envisaged results; (2) grantee organizations so the latter could collect information to illustrate their specific contributions to overall results; and (3) UN Women country offices, to assist grantees in planning/reporting. UN Women country offices also tracked programme progress, in addition to assisting grantees in reporting. UN Women country offices undertook monitoring missions and had the overall understanding of the results being achieved in their country.

Stating the numbers of participation in the various activities does not fully validate the appropriateness of the strategies used by grantees on its own. The indicators were set by UN Women (Annex XVIII) and were to be measured numerically. The case studies and results of interviews (Annex IX), describe the reported high enrolment – measured by the numerical indicators – in training, and substantial participation of local leaders. These facts validate the appropriateness of the strategies. The fact that individual women often went on to become paralegals and trainers is also a testament to the appropriateness of the strategies.

It was a good practice that 12 of the 20 grantee projects in Phase I executed baseline surveys to establish parameters to enable measurement of indicators. As reported in a programme monitoring report, twelve grantees carried out baseline surveys or community-led mappings to establish existing norms, practices and services with respect to WPIR and to document women’s experiences and challenges with accessing them at community level.

Another central evaluation question has also been to find out whether grantees were able to use the indicators that make up the building blocks of the PMF framework. To judge from the monitoring reports grantees wrote, and comments in the field during the evaluation assessment, the indicators were adequate for their intended job, and easy enough to use. Interviewed grantees also stated that they highly appreciated the support from UN Women HQ, UN Women country offices, and the programme coordinator based in the Nigeria office in the form of track changes, comments, and suggestions to improve monitoring reports and their individual PMFs. To judge from comments made to the evaluation team, although initially challenging to use, the grantees became used to using the PMF system for monitoring and reporting on progress.

### The degree of coherence and appropriateness of the programmatic approaches and strategies that the grantees used for identifying the needs of stakeholders and RHs

Finding 11: The programmatic approaches and strategies increased the evidence base on ways and means to identify and meet the needs of rights holders.

In Phase I, 20 grantees were expected to advance strategic action regarding women’s property and inheritance in the context of HIV and AIDS. The grantees broadly adhered to several strategies over the 12-month period, viz.: advocacy; data collection and research; capacity building; public outreach and awareness raising; service delivery (including legal aid); creation of legal reform networks and accountability / monitoring mechanisms of the practical application of policies and laws.

In Phase I, 126 organizations and groups (stakeholders, RHs, government officials, and others) benefited from advocacy; data collection and research; capacity building; public outreach and awareness raising; service delivery (including legal aid); creation of legal reform networks and accountability/monitoring mechanisms of the practical application of policies and laws.

The strategies were broadly relevant to the development goal. But there was one anomaly: some of the grantees used training materials that they already had developed before the project started or inherited from other projects. This was positive because it saved on costs and effort; but some of the training materials were not specific, and hence not completely relevant, to specific grantee projects.

In Phase I, 36 groups and organizations benefited from advocacy; data collection and research; capacity building; public outreach and awareness raising; service delivery (including legal aid); creation of legal reform networks and accountability/monitoring mechanisms of the practical application of policies and laws. In this connection 175 meetings, workshops and outreach sessions took place.

In Phase II, the 10 selected grantees were expected to deepen existing initiatives and partnerships that had been shown to have demonstrated strong results, such as the delivery of rights-based training, to more women, men, and other family members. Additionally, activities directed at grassroots women were expanded to include contiguous areas. In Phase II, the selected grantees identified an urgent need for economic empowerment to be added to the grantee project activities, because vulnerable women cannot afford to go to training sessions because they need to earn income every day. Some grantees, such as WLSA in Zimbabwe, introduced or scaled up this service (see Annex IX).

Table 5 below shows analysis of all the outputs. Table 5 illustrates how the outputs were aligned to the strategies and to the three categories of RHs (individuals, organizations and meetings/outreach activities). When reading the table below, note that there is some overlap between the three categories. The evaluation team divided the findings into three areas to reflect the direct support to women (category 1), women and men and youth who were trained (category 2) and the meetings which followed to disseminate the new knowledge acquired from category 2 organizations/groups. Note that category 3 increased in Phase 2 as expected of the grantees (10) who were to use the second phase to disseminate the knowledge they had acquired.

| ###### Table 5: TEMPLATE RELATING 3 CATEGORIES OF SUPPORT TO OUTPUTS AND STRATEGIES OF WPIR-HIV |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CATEGORIES OF BENEFICIARIES (3) |  |  |  |  |  |
| 1. INDIVIDUAL BENEFICIARIES: (at least 85% are women) supported by mentoring, training, legal support, shelter |  | 2.ORGANIZATIONS/GROUPS: group RHs, supported with training |  | 3. MEETINGS/WORKSHOPS/ OUTREACH: means to benefit men and women by awareness raising, mobilization and information drives |  |
| Output | Strategy used | Output | Strategy used | Output | Strategy used |
| ###### 2.1, 3.1, ###### 3.2. | capacity strengthening, community mobilization, partnership/ coalition building, service delivery, accountability/monitoring mechanisms of policies/laws | 2.4, 2.5. | advocacy, partnership/ coalition building, capacity strengthening, accountability/ monitoring mechanisms of policies/laws | 1.1, 1.2, 2.2, 3.2, 2.5 | data collection and research, public outreach/ awareness raising, community mobilization |

### The degree to which appropriate and sufficient outreach efforts were made to include and reach relevant DBs and RHs

There is very strong evidence that sufficient outreach efforts were made to include and reach relevant DBs and RHs. Two examples suffice, viz.:

AVEGA Rwanda: Training for DBs included: 102 paralegals trained in the relevant skills of the need to protect widows’ property and inheritance rights in the context of HIV/AIDS. Training and sensitization for RHs included 25 cases of women who were assisted to take their cases to local authorities and who were able as a result of project assistance to get their property back.

GROOTS Kenya: There was considerable outreach to WLHIV. At least 166 women infected by HIV have gained knowledge and skills to effectively advocate for and monitor the realization of WPIR. These women are now reportedly aware of their property inheritance rights and of the available access to community-based support and other formal justice mechanisms and processes. A community-led mapping exercise was conducted to establish the magnitude of WPIR in the project area; this knowledge enabled project activities to be needs based and to reflect needs of women. Training was provided to watchdog group members, community leaders, and leaders from each constituency who were significantly involved in designing the work plan and developing the performance-monitoring framework.

Field data (Annex IX) also corroborate the above examples of successful outreach; and shows that there are variations in the degree to which grantees succeeded in achieving sustained outreach activities, viz.:

In Rwanda, AVEGA was very successful in achieving outreach at a grassroots level. Informants reported that: (1) one good output from the project was the creation of new bodies at district level by the Ministry of Justice to address disputes; (2) AVEGA established a strong relationship with this Ministry and attended quarterly meetings on the issues with them and other ministries. (3) Women reported being empowered by the training and support from AVEGA and also joined AVEGA; (4) Women reported less knowledge on HIV and AIDS than on legal statutes and those interviewed had not been tested; (5) AVEGA created mobile free legal aid agencies in the rural areas that are easily accessed by the communities; (6) This enabled the paralegals to teach the beneficiaries and saved them time and money.

In the above example of AVEGA, two factors are crucial in assessing the success in outreach: (1) AVEGA had before the programme already established a network and working relationships with women; (2) Rwanda is very small, and relatively easy to get around compared to say Kenya and Nigeria.

Finding 12: Distance was a barrier to efficiency in some grantee projects.

Since distance was a barrier to efficiency in some grantee projects; the recommendation follows that in a future programme, allowance should be made for geographical distance, and budget allocation for transport and logistics could be higher in big countries (Kenya, Nigeria), and lower in smaller ones (Rwanda).

## Findings and Analysis on Effectiveness

### Overview

Finding 13: Entrenched attitudes, which limit or negate women’s property and inheritance rights, continue to be a challenge to improving women’s rights. The programme did reportedly contribute to changing negative attitudes and perceptions that hinder women’s access to their property and inheritance rights in the nine countries. The progress made was a result of grantee projects’ activities to raise the awareness and knowledge base about women’s property and inheritance rights of opinion leaders, traditional leaders, and ordinary village men and women. However, not all traditional leaders acquired new knowledge about women’s property and inheritance rights as a result of grantee projects.

The evaluation team based its findings on analysis of results from available documentation study, field and phone interviews. The team also conducted an in-depth review of the recorded performance per grantee in order to quantify the number of rights holders and duty bearers reached by the overall programme with respect to the outcomes. The results of this review are shown in 16 tables (Annex XIII: Phase I & II achievements of outcomes 2, 3) which analyse the number of RHs and DBs supported and also the number of activities related to outputs and results intended for the outcomes.

Field data corroborate the results reported in Annex XIII, but not completely.

The team met 86 stakeholders and 91 beneficiaries who expressed satisfaction with the content of the training, especially (1) its simplicity of explanation (experiential training methods were used); and (2) ease of access to the training.

In some of the visited field sites, local leaders (cultural and political or religious traditional leaders), who had tended to oppose improving women’s property and inheritance rights, reported that they had changed their attitudes as a result of grantee project activities. Furthermore, these men reported that they had gone on – inspired by the grantee projects – to become trainers, motivators, mobilizers, and champions.

The evaluation team interviewed villagers and traditional leaders in the field sites, and corroborated the pro-women changes in knowledge, attitudes, and practices of some (but not all) male leaders, reported immediately above, as exemplified by the following two cases from field work data:

- In Nigeria (CIRRDOC), as a result of the grantee project, there reportedly took place (1) modification by traditional rulers of customs that violate inheritance and property rights of women especially in the context of HIV; and (2) the existence of male and traditional leaders who became anti-VAW champions spearheading anti-VAW actions (Annex IX).

- In Kenya (YWAP), the grantee project successfully involved local leaders. The project was able to involve cultural and religious leaders in capacity building and succession planning. Stakeholders and women were also invited to become YWAP members.

The above two cases do not indicate that the programme faced significant challenges as regards changing entrenched patriarchal male views. For example, in one case in Zimbabwe (WLSA), male leaders are still very much in control in rural areas, and still, reportedly, dominate women, as shown by field data. However, in peri-urban areas in Zimbabwe, it is a best practice to involve males in challenging cultural practices that negate women’s property and inheritance rights through Padare (a men’s forum).

### Conclusion

The above examples show mixed results regarding the degree of success in changing entrenched patriarchal attitudes about women’s property and inheritance rights. It is an ambitious goal to attempt to change deeply held views about women in the space of a total of three years; and the evaluator concludes that the programme needs extending and that the individual grantee projects need more time to achieve the desired impact in this area.

### Achievement of the Expected Results

Finding 14: The programme provided 130,774 people in nine sub-Saharan countries with increased access to information about women’s legal, property and inheritance rights. Most of these beneficiaries were women RHs.

The programme’s achievement regarding expected outputs/results is therefore highly satisfactory; with the highest achievement being accorded to Outcomes 2 and 3 because the outputs designed for Outcome 1 overlapped with those of Outcomes 2 and 3 with respect to grantee-reporting.

### Progress towards Outcome Area 1

Finding 15: The WPIR-HIV AIDS programme significantly increased the number of community-level legal frameworks and processes that effectively promote and protect women’s property and inheritance rights in the context of HIV and AIDS.

Outcome 1 refers to: increase in number of legal frameworks and processes that effectively promote and protect women’s property and inheritance rights in the context of HIV and AIDS. The two outputs identified for this outcome were to be measured by two indicators related to increase in number of legal frameworks and processes and evidence of DBs actively supporting the development and revision of legal frameworks.

Programme activities included inter alia the dissemination of information materials, and organizing conferences and meetings. The grassroots activities were carried out as expected, but they overlapped with activities designed for the other two outcomes. For example, meetings and discussions organized under Output 1.2. would address issues that were supposed to be covered under meetings for Output 2.2. There was no clear definition of activities for national-level stakeholders (who were best placed to advocate and lobby for legal changes) and the PMF implies outputs would be achieved at community level.

Nevertheless, eight of the 20 grantees were able to carry out national-level activities that promise ultimately to improve legislation to better promote and protect women’s property and inheritance rights.

Annex XVIII  (Outcome 1 results/outputs for phase 1 & 2  (national level activities) shows considerable achievements, viz.: (1) Increase in number of legal frameworks and processes that effectively promote and protect women’s property and inheritance rights in the context of HIV and AIDS; (2) Enhanced knowledge and awareness of duty bearers responsible for the development, revision, and implementation of relevant legal frameworks and processes of the need to protect women’s property and inheritance rights.

Annex XIII (Phase I & II achievements of Outcomes 2, 3) shows where grantees succeeded in facilitating improved legal frameworks and processes to enable government actors and gender equality advocates at national level to change legislation. There was also some progress with Output 1.1 because district and community stakeholders increased their number of meetings to discuss how to improve the situation for the targeted women. There were 100 meetings held in Phase I and 175 meetings in Phase II. Although not disaggregated by the different outcomes, since the meetings served as an opportunity to carry out activities related to all three outcomes, the results show how many of these meetings were held to publicly discuss how to support the women targeted for assistance (Output 1.2).

The above finding was substantiated when the evaluation team interviewed 91 women in the field and was able to hear their stories first hand (cf. Annex X, for four examples). The interviewed women reported that they were now more able to discuss their situation with government and community institutions. In all cases, the interviewed women reported receiving advice and referrals to third parties that reportedly helped them find solutions. For some, the legal battle will take much more time than the programme implementation period; but the women reported being hopeful of finding a solution.

The grantees were able to develop new information, e.g., IEC materials, to support the individual grantee projects. This IEC material could be used for future programmes, similar to the programme under review. The IEC materials inspected are generally very relevant to the situation of women’s property and inheritance rights. The IEC materials included community brochures, booklets, cultural manuals, videos, case records (of paralegals) and case studies of the women (Output 1.2). There is some evidence reported in interviews and documentation, that where interaction occurred (as shown in the annex XVIII), knowledge and awareness increased (Output 1.3). There were also cases where government actors and gender equality actors discussed face to face how to improve legal frameworks (Output 1.2).

In Phase 1, the eight grantees able to advocate and lobby for legislative changes at national level were from Cameroon, Kenya, Malawi, Nigeria and Zimbabwe. In Phase II, only four of the eight grantees managed to push for law reform or enactment of legislation pertaining to women’s property and inheritance rights. In the case of GROOTS (Kenya) no progress was made. However, the other three grantees working on national-level advocacy and lobbying made some progress (see Annex XVIII Outcome 1 Results/Outputs for Phase 1 & 2 ([National-Level Activities]).

#### Progress towards Outcome Area 2

Outcome 2 was: strengthened enabling environment for promoting and protecting women’s property and inheritance rights at the community level. Its stated outputs were: the creation of a relevant evidence base on women’s community-level experiences with claiming their property and inheritance rights (Output 2.1.); enhanced knowledge and awareness of community-level opinion leaders of the need for them to exert an oversight role in resolving property grabbing and inheritance issues (Output 2.2.); community members, including men and boys, aware of the need of actively supporting the realization of women’s property and inheritance rights (Output 2.3.); and, enhanced knowledge and skills of legal service providers (including paralegals) available at the community level to assist women in protecting their property and inheritance rights (Output 2.4).

Finding 16: A wide evidence base was created by the programme, reflected in the case studies carried out by each of the grantees.

Women interviewed who participated in Phase I & II grantee projects reported that they were able to gain information from other women, opinion leaders and watchdog groups (Output 2.1.) that resulted in their being able to access legal rights assistance.

For example, field data show how in the case of (1) Rwanda (Réseau), Réseau and its stakeholders took great care in the process of identification, empowerment and organization of women into cooperatives dealing mainly with agriculture. These remain active and are generating income. A major challenge is ill health of some members with AIDS who are too weak to farm like other members. The approach of integrating women with HIV and AIDS in existing sensitized cooperatives was very successful (Annex IX).

Other interviewed women also reported having learned important new knowledge, viz.:

- How to protect themselves against asset stripping by registering births and marriages, and by making wills with their spouses

- Which actions to take to obtain shelter and other support

- Step by step procedures to regain access to assets, land

- Step by step procedures on how to protect themselves and their children against GBV

- How to become empowered legally, socially and economically

Note that this finding is based on qualitative evaluation data and does not contradict Finding 19 below, which refers to quantitative data.

Interviewed women affected by or infected with HIV and AIDS reported being more empowered and thus more able to claim their rights. To take two examples, paraphrased evaluation data (see Annex IX) show how: (1) in Tanzania (HOP), the project’s holistic approach (psychological counselling, food, medical care and vocational training) was very appropriate to the full range of support women and girls needed; support to girls using recognized, acceptable means such as peer educators was effective. The peer educators also received training, conducted monitoring of rights awareness, petition signing, and organized petition-writing competitions; and (2) in Rwanda, Réseau was funded in both Phases 1 and 2 and met the expectations of the targeted beneficiaries.

In addition to the evaluation field findings, reproduced immediately above, programme-monitoring reports indicate a strengthened enabling environment for promoting and protecting women’s property and inheritance rights at the community level. For example, in Nigeria, a CIRDOCC PMF report states that women who are denied their rights report directly to the Anti-VAW committee. The committee is made up of traditional rulers, lawyers, etc. and referral to service providers is made easier. Relatives are afraid to dispossess widows (especially AIDS widows) of their property because of the fear of reprisal, punishment or prosecution by the Anti-VAW Committees. Workshop evaluation reports revealed that traditional rulers and women leaders are more aware of the need to promote the protection of women’s property and inheritance rights and they made commitments in this respect.

Finding 17: Phase II expanded the Phase I activities of outreach, workshops and meetings. Phase II grantee projects continued to disseminate new knowledge about WPIR, using materials and the experiences gained from Phase I.

The evaluation team conducted rapid research on reported changes in knowledge, attitudes, and practices of women’s property and inheritance rights that could be reasonably adduced to have resulted from activities executed by the individual grantee projects. As the tables 1 – 16 (Annex XIII) show, in Phase I, 126 organizations/groups were exposed to – and possibly acquired – new knowledge. This figure decreased to 36 training sessions in Phase II, followed by 175 outreach activities (an increase from Phase I, when 100 outreach sessions were held

Finding 18: The utilization of a body of trained volunteer paralegals was crucial to the programme strategy because the paralegals played a significant role in training, sensitization and legal support activities, and because they filled a human resource gap at the grassroots level. But the number of paralegals per village is far below what is needed in some grantees projects.

Interviewed paralegals stated that the duration of the paralegal training was too short to enable retention of new ideas and systematic learning.

In some grantee organizations, which relied on paralegals, lawyers supported the training of the paralegals. However, in other instances, where lawyers were scarce or not available to train them, the training reportedly was of insufficient technical depth. This problem is not unique to this programme; most pro bono legal work probably faces this challenge. This problem also reportedly characterised some volunteer lawyers, who in theory volunteer to provide their services for free, but who reportedly prefer to go and represent their paying clients if there is a conflict in their work calendar. This occurrence was observed in some cases to inconvenience the already stressed women clients whose cases might take even longer to resolve.

At the time of the evaluation, none of the countries concerned recognized the paralegal as an entity in the legal system, although some changes are reportedly underway (October 2013) to push for their recognition.

In one organization (NACWOLA, Uganda) paralegals were trained but did not reportedly carry out any awareness raising activities or provide any legal services in the community because they, reportedly, lacked incentives or allowances.

In all grantee projects, the paralegals were not paid, being required to work as unpaid volunteers.  Inputs from the paralegals were reportedly deficient and this may have been due to the lack of incentives/salary (as well as being due to (1) patchy or insufficient support from lawyers working pro bono; (2) the paralegals having to do other things apart from unpaid volunteering to earn a living).  The latter two problems are vital sustainability issues, as well as constituting technical, quality-of-service matters.

Some of the paralegals interviewed reportedly signed up for training in anticipation of acquiring jobs or payment in the future on a semi-permanent or even permanent basis.

#### Progress towards Outcome Area 3

Outcome 3 proposes that: women living with and/or affected by HIV and AIDS and their organizations are better able to claim and advocate for the realization of their property and inheritance rights. As per Output 3.1, there would be an increased number of women living with or affected by HIV and AIDS who become aware of their rights as a result of the programme.

Finding 19: In the absence of a before and after statistically representative baseline of the number of people trained, it is not possible to state numerically, the degree to which this output was achieved.

Although an estimated 71,010 people in Phase I received awareness raising, education and legal support, it cannot be empirically known, or proven, in the absence of a before and after statistically robust baseline of this universe, if the training has led to increased ability to claim and advocate for one’s property / inheritance rights.  This finding concerns Outcome 3, outputs.

This section does not contradict the reported positive achievements reported earlier above (page 36), nor the case study in Zimbabwe of Susan Moyo (below, this page).   Interviewed women stated that they were able to make their case and claim their rights. This is evidence that they are aware of their rights.  The discussion in this section is stressing the need to generate large-scale data, which are more convincing than qualitative data, which are of necessity small scale.

A lesson learned concerning attribution may be inferred here. I.e., that without executing before and after statistically robust baselines of a defined programme universe, it cannot be empirically proven in statistical terms what achievements are attributable to the programme/specific grantee projects, and what changes have actually taken place.

A recommendation coming out of this lesson learned is to include before and after statistically robust baselines of a defined programme universe, so that exact inferences can be made concerning achievements in numerical terms with the collected data at the end of the programme.

Finding 20: In many cases the women assisted by the programme’s grantee projects have successfully reclaimed their homes, lands, and livelihoods (examples from field data were quoted in the preceding chapters, and are reproduced in Annex IX). This, again, is another major achievement of the programme.

Despite the above caveats, it may nevertheless be assumed – based on the anecdotal evidence from the field work data – that there have been achievements that have led to the successful obtaining of several women’s property and inheritance rights. The following example from Zimbabwe illustrates this assertion, viz.:

Case Study Zimbabwe: Susan Moyo… was part of the local HIV and AIDS peer education drama group, where she would create drama performances of her real life experience, narrating that she was divorced and (had) lost her matrimonial home because of her HIV positive status. At one soccer match that took place in the area, she acted the drama and an elderly lady who is part of the WLSA-supported watchdog leadership was in the crowd. When she heard Susan’s story she approached her and told her about WLSA. She was introduced to WLSA, which… successfully represented her in court. Her former husband and his new wife were ordered to move out of the house. Susan is now back in the house with her children. She is renting out part of the house and using the proceeds to pay school fees for the children. Susan indicated that after what she has gone through she is now a champion and helps others in similar situations to fight for their rights, by introducing them to WLSA. She was married customarily and as a lesson learned she encourages women to endeavour to have their marriages registered even if they are married customarily. She appreciates the support she got from WLSA and reported that it saved her life and gave a career to her children (from Annex IX).

The 16 tables in Annex XIII summarize the evaluation team’s findings, based on triangulation of interviews and documentation study. The tables show that the programme benefited three main groups: individuals (mainly women) who received support via training and legal support; the general public (comprising women and men) who attended meetings/workshops and outreach sessions to be trained about WPIR and to take part in campaigns, and; organizations and groups that received training.

## Findings and Analysis on Efficiency

### Strategic use of Project Resources

There was some flexibility in the budget lines, which the grantees reportedly appreciated. But generally the biggest reported gap was shortage of funding for the following three strategies: (1) data collection and research; (2) public outreach and awareness creation; (3) legal services.

Some of the grantees also expressed concern that funding arrived late. This meant that activities could not be started at the time planned. This reportedly caused a log jam of activities when the monies finally arrived, as there was insufficient time to carry out activities which had been designed for a longer period of time.

Some grantees reported implementing the project activities for only 8 months in the first phase (instead of one year) as a result of the above-mentioned delays in their receiving instalments.

The area of awareness creation and changes in KAP required more time than was allowed in the programme and individual project design. When the programme started in 2011, there was reportedly a lack of data; in some cases, data were needed to describe the target beneficiary needs and issues. This data lack made the execution of baseline surveys necessary, which were very expensive. It was expected that baselines, mapping and monitoring would cost 1-2% of the individual budgets, which was unrealistic. Furthermore, the programme was expected to generate information and conduct research, yet the miscellaneous budget line under which this fell was too low. This meant that in some cases, brochures and booklets produced were not of good quality or user friendly, in all cases observed.

Most of the budget overall in the programme went towards training, workshops and meetings/seminars, which was appropriate in order to achieve the outcomes using the six strategies of the programmatic approach.

The grantees that were relatively financially independent (e.g., AVEGA-Rwanda, FIDA-Ghana, WLSA-Zimbabwe, LRF-Zimbabwe, and CIRRDOC-Nigeria) executed a significant number of income-generating activities that benefited the WPIR-HIV projects because they helped finance them. These more experienced and financially independent grantees were also able to build on the experiences they had previously gained in managing income-generating activities and could apply these to economic empowerment activities. Finally, the target groups in grantee projects were able to utilize the services offered by the better-off grantees, such as training and health services.

### Building on existing initiatives and capacities

The grantees operating in Phase 1 already had carried out initiatives addressing poverty, women’s rights and economic empowerment. The knowledge and experience gained from these activities were valuable to the successful implementation given the short time period of the projects. Examples are the presence of income generating activities in some grantee organizations, such as AVEGA (Rwanda).

AVEGA had schools, gardens, and a health centre. Most of the grantees did not have a significant number of institutional income-generating activities so there were many cases where grantees had to depend on the support from other stakeholders.

Some of the types of support that grantees with fewer human and/or financial resources depended on were:

- Use of office space, phones and transport owned by stakeholders (government ministries or individuals)

- Modification of existing brochures and booklets at times with inappropriate content and which was not therefore user friendly, relevant, or attractive. In many cases, these materials were not translated into the various languages used in the rural areas

- Release of some full time workers and replacing them with volunteers

There was a high level of volunteerism due to the general acceptance of the projects by the local populations.  The use of volunteers is a positive step and can contribute to sustainability. But in many cases, technical legal and land tenure skills were needed and were not available in the volunteer population.

There was a high level of volunteerism due to the general acceptance of the projects by the local populations.  The use of volunteers is a positive step and can contribute to sustainability. But in many cases, technical legal and land tenure skills were needed and were not available in the volunteer population.

An example of this problem – already mentioned above – was the gap in lawyers who were supposed to participate for free in the projects by providing training, legal advice and mentoring. Professional lawyers’ participation in grantee projects was very important for training the paralegals and for monitoring policies and laws. However, at crucial junctures in the projects, lawyers were not always available, since there was no provision in project budgets to pay lawyers for training paralegals. This statement is true of all the grantees (grantee budgets have been inspected).

There was, additionally, not enough attention paid to TOT training which would made it possible for future training to continue. The evaluation team studied the quality of the paralegal training materials and found them to be weak in terms of attention to content, and user friendliness.

These deficiencies are crucial, considering that the paralegals had perhaps the most important roles to play, especially as regards the strategies of public outreach and awareness creation, and community mobilization. In many cases, the paralegal training was conducted after the first quarter of the 12-month projects and in many cases it was only of short duration. This meant that paralegals reported not being able to recall their training content when interviewed by the evaluation team. Finally, there was reportedly not enough provision in the budget for communication costs of the paralegals to enable them to reach RHs and local authorities.

### UN Women management efficiency

The programme included a small grants mechanism which UN Women administered efficiently by developing a three-tier system which ensured transparency and accountability.

The small grants fund – financed by CIDA (now called DFATD) – was established as a competitive small grants mechanism. Its grant making and operational processes were aligned with the existing systems and good practices of other trust funds managed or administered by UN Women. A rollout programme (developed by UN Women and the former CIDA in August 2010) was adhered to within the foreseen timeline. A Regional Funds Secretariat was then established in Abuja, Nigeria. The UN Women Project Coordinator was based in the Nigeria office, supervised by the National HIV/AIDS Programme Officer. In addition, UN Women country office focal points and M&E officers provided support to each of the grantees in their country. Technical support, oversight and monitoring, liaising with the donor, etc. were carried out by the Programme Manager (part-time) in the UN Women office in New York. These all together constituted the support to the grantees. The secretariat and specifically the project coordinator were responsible for the day-to-day management of the small grants component at regional and country levels.

The programme started with a CfP, drawn up in September 2010 by UN Women HQ, the fund manager (based in Nigeria) and the regional offices, namely Central Africa Regional Office (CARO), West Africa Regional Office (WARO), East and Horn of Africa Regional Office (EHARO) and Southern Africa Regional Office (SARO). This was followed by widespread advertising on electronic networks, radios and in local newspapers. There was also an outreach to potential grassroots and community-based organizations and partners. The CfP was sent out to all UN Women country offices, including those not having HIV and AIDS in their country focus; this could have created challenges in support mechanisms. As a first step, applicants had to submit a concept paper which, if accepted, was followed by a proposal request. The fund secretariat coordinated the screening and review of a total of 645 applications as shown in Table 6, below:

| Table 6: APPLICATIONS AND AMOUNT REQUESTED BY SUB-REGION |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Number of Applications | Percent of Applications | Amount Requested | Percent Requested |
| Central Africa (CARO) | 45 | 7% | USD 3,002,635 | 7% |
| East and Horn of Africa (EHARO) | 364 | 56% | USD 24,266,956 | 54% |
| Southern Africa (SARO) | 144 | 22% | USD 11,122,470 | 25% |
| West Africa (WARO) | 92 | 14% | USD 6,568,322 | 14% |
| Total | 645 | 100% | USD 44,960,383 | 100% |

There was satisfaction expressed by all parties with the fairness of the eight selection criteria. The evaluation team reviewed the criteria and found they were quite rigorous, free and fair and in line with project cycle management and evaluation criteria. This relationship is shown in the template in Annex XVII: Analysis of Criteria.

The transition period between the ending of the project coordinator’s contract and the assumption of the coordinative responsibilities at UN Women HQ, was not smooth, with some grantees – even during the evaluation – sending their documents to the coordinator and expecting a response. The call for proposals was sent out to all UN Women country offices, including those not having HIV and AIDS in their country focus and this could have created challenges in support mechanisms.

According to UN Women staff, there was a community of practice on email. But it was not an active space; it was more of a passive, sharing of information space. The shared community of practice among the grantees was not active -as mentioned above- because the issue of connectivity had not been foreseen to a sufficient degree. Nevertheless,  some of the grantees were selected on their strengths as grassroots organizations. Some grantees may have missed an opportunity to benefit from coordinated sharing and learning from each other. This opportunity later came in a revised form of a regional conference, but the programme had already ended.

The PMF was drawn up by an evaluation consultant and the following staff participated in the workshop: evaluation team members in New York, the Programme Officer from the Nigeria office, who supervised the regional coordinator, the programme manager and the policy advisor from New York, the regional teams from Africa in New York, and the donor. This monitoring tool was then scaled down.

Some grantees indicated that the PMF was difficult to use initially because there was, reportedly, no adequate training provided on the PMF by UN Women. Additionally some grantees indicated a lack of follow-up on their projects and field visits from some UN Women country offices.

### Extent of programme linkages with other UN Women or UN system initiatives (UNAIDS Joint programmes of support, delivering as one or relevant UN theme groups)

The programme is intrinsically linked to initiatives of UN Women’s and CIDA (now DFATD) that promote women’s rights and gender equality. The programme’s strategies, in particular (1) the small grants mechanism facility; (2) the focus on the village level, and (3) training cadres of paralegals who then disseminate messages and provide legal advice in the villages, have significantly enhanced efforts to capitalize on lessons learned from other UN Women programmes on gender equality and HIV/AIDS.

Since the programme reflects UN Women and UN family policies there is every reason to believe that this type of programme will be sustained by future financing from donors.

## Findings and analysis on potential for sustainability

### Extent to which UN Women has established a body of relevant information, materials and/or tools on women’s property and inheritance rights in the context of HIV and AIDS

Finding 21: The activities in Phases I & II in the 30 grantee projects have generated a body of information and materials that are relevant to women’s property and inheritance rights in the context of HIV and AIDS.

One example from paraphrased field data illustrates this finding:  In Kenya, GROOTS (1) organized one workshop for sharing of knowledge between counties leading to promotion of understanding between different ethnic groups; (2) Activities selected succeeded in rallying and amplifying evidence via the use of their excellent tools/models. Watchdog groups, home-based care alliances, champions for transformative leadership received training and copies of training materials.

The sustainability challenge that the individual grantees face, and that the programme faces as a whole, is how to maintain and replenish these materials (pamphlets, audio visuals, leaflets, flyers, etc.) that have been developed with donor funding for imparting knowledge to women about women’s property and inheritance rights in the context of HIV and AIDS. Once leaflets are used up, more money is needed to print new ones. If grantees do not have ownership of the proofs and manuscripts used to create materials, then it is more likely that they will not be able to continue replenishing their supply of educational materials once they have been depleted.

A further programme or a new phase of the completed programme, which donors could finance, could include as an activity area the collation and reproduction of the materials in published formats, in some of the major, relevant languages (e.g., French, English, Swahili) in the programme countries. This would create a published body of knowledge that could be sustained for the work which needs to continue in the sector of women’s property and inheritance rights in the context of HIV and AIDS in each country.

Achievements concerning knowledge generation relevant for learning and advocacy in relation to the legal empowerment of women in the context of HIV and AIDS

At the grantee level, field data show that the programme contributed to knowledge generation. Men and women, villagers, and village leaders, religious leaders, and chiefs, have been educated about women’s property and inheritance rights in the context of HIV and AIDS. The education and training materials also encouraged widows (in GROOTS Kenya) to become leaders. These materials have been deposited in the body of knowledge of the members of the target villages.

The extent that grantee project strategies have built up local-level ownership and support for safeguarding and promoting women’s property and inheritance rights in the context of HIV and AIDS

Finding 22: By training local women and men, citizens and leaders, widows and WLHIV, paralegals, lawyers, and other stakeholders at the grassroots level, the programme has significantly built up local-level ownership and support for safeguarding and promoting women’s property and inheritance rights in the context of HIV and AIDS.

There are several examples corroborating Finding 21 above that can be read in the field data (Annex IX). Viz., one paraphrased example is presented here:

- In Rwanda, Réseau significantly reinforced local networks of women and village leaders to promote women’s property and inheritance rights in the context of HIV and AIDS. There was extensive involvement of local authorities, including local police, in gender promotion, advocacy, social affairs, and judicial systems. The grantee project also worked with women’s networks on human rights, counselling, and HIV and AIDS support groups at local and district levels. Réseau took great care in the process of identification, empowerment and organization of women into cooperatives dealing mainly with agriculture. The latter remain active and are generating income. The challenge is ill health of some members with AIDS who are too weak to farm like other members. The approach of integrating women with HIV and AIDS in existing sensitized cooperatives was very successful.

### The extent of synergy creation and the potential for durability of created partnerships

The extent to which grantees collaborated and coordinated with other organizations or initiatives to create synergies – and whether these partnerships can be sustained after the ending of external support – is a complex question to answer, because the situation is different for each grantee. Some grantees have a long track record; have worked with several donors and other partners previously; and have some professional staff, a volunteer base, a system of records and even publications, and a relatively strong funding base (e.g., GROOTS, AVEGA).

Without these minimum requirements, it is difficult for an NGO to collaborate, partner, and coordinate with other organizations or initiatives mainly because that NGO will not have sufficient institutional memory or in-house technical know how, and insufficient project references to enable them to offer something to potential partners.  It is consequently even more challenging for a grassroots organisation to meet these above-mentioned minimum requirements; by nature, grassroots organisations tend to be fairly restricted geographically, whereas NGOs have more often an urban profile and will have contacts and a physical presence in cities or towns.

In conclusion, on this point, the field data (Annex IX) show that there are a number of success stories in this regard:

- In Rwanda, field data show that in addition to the mobile legal clinics that AVEGA set up, a new body emerged during Phase 2, called the Réseau des Citoyens Network, which is directed at providing guarantors for defending women’s land rights. Furthermore, AVEGA involved in their grantee project the National Women’s Council and National Youth Council at the district level, which organisations supported the paralegal services provided to women and their dependents. There is every reason to believe that this productive relationship will continue to function into the future, because AVEGA is a professional and dynamic organisation that had a well-established base of women members and clients before the UN Women programme.

- In Zimbabwe, WLSA is a member of the East and Southern Africa Women Inheritance Network, which promotes the sharing of inheritance and property rights practices. By default, the experiences and new ideas emanating from the WLSA grantee project can be passed on to other women’s organisations in Southern Africa, and are likely to be sustained in the future.

### Other factors that are likely to affect project sustainability

There are several threats to sustainability. In Zimbabwe, (WLSA), the informal justice system that has been created with project support still depends on WLSA for legal aid support, creating a dependency syndrome of sorts. Also in Zimbabwe, (WLSA), there is inadequate after legal service support and follow up which can create other future unintended challenges, and this means that – potentially – gains made in the earlier work will not to be sustained.

In other grantee projects, sustainability is threatened by the large project area: the cost of logistics is prohibitive and threatens sustained activities: e.g., (1) in Nigeria (CIRDDOC), ‘[The] geographical coverage of the project is... minimal. For sustained impact [the] geographic area needs to be expanded’; and e.g. (2) for ABANTU (Kenya) the project ‘faced a challenge in maintaining strong working grassroots relationships due to distance, funding limitations and long-standing management challenges (staff few in number, quality and quantity)’ (Annex IX).

Conclusion on sustainability

Grantee projects have built up local-level support in the cases reviewed above. Organizations such as ABANTU, AVEGA, GROOTS, CIRRDOC, LRF, MWEDO, and WLSA and local authorities have actively addressed HIV and AIDS and the violation of women’s property and inheritance rights.

Several new bodies and groupings of human capital have been successfully created as a result of the programme, such as the paralegal cadres, champions for justice, watchdogs, and farming cooperatives. All of these benefited from training and awareness raising. Moreover, their capacity to deliver was enhanced by the programme support for paralegals, albeit with some problems of quality that could be redressed by further support.

The programme was a short-term small grants fund and therefore should not be expected to be sustainable over so short a period. Similar types of programmes, such as those financed by UNDP, DANIDA, and EU, would normally have a minimum five-year time frame. This is because capacity strengthening and changing attitudes and practices in sensitive areas such as HIV/AIDS and property and inheritance rights is expected to take a long time. The time needed to create awareness and change retrogressive practices as well as reduce gender-based violence in the context of HIV and AIDS would be greater than a three-year period.

Nevertheless, on a positive note, in all the grantee projects analysed by the evaluator, the level of support achieved from grassroots stakeholders was very high given the time limitations.

In many cases, local authorities and leaders expressed satisfaction with the programme as the issue of women being denied legal rights was long standing. In this sense, the programme has served as the light at the end of the tunnel, and it is recommended that a further programme be financed as soon as possible to enable the progress achieved to be consolidated and to continue in the sub-Saharan countries where problems concerning women’s property and inheritance rights in the context of HIV and AIDS are almost overwhelming.

## Factors influencing performance

### Programme design

##### Finding 23: The programme design exhibits many strengths, which built on the prior experience and strategic priorities of UN Women to target and reduce discrimination against women.

One programme strength was its utilization of previous experiences with management trust funds, and the emphasis on a transparent Call for Proposals system, especially as regards the Phase I selection process. Although the time taken to conduct the CfP extended over six months, the final selection of the 20 grantees was viewed positively. Interviews with each of the grantees and other stakeholders such as UN Women focal persons substantiated this finding. The three-tier process for Phase I was particularly well designed and motivated the grantees to carry out their projects diligently and mostly on time. The 8-point scoring system was also well designed as it demonstrated many aspects of project cycle management and related well to evaluation criteria.

The selection of grantees from a wide geographical area was also a strength as it allowed a diverse representation of approaches using the agreed-upon strategies.

The programme benefited from a PMF which provided a logical framework matrix, drawing out possible project activities from the outputs set for each of the three expected outcomes. The PMF was designed after the selection process, but was found to have been useful for both phases with respect to mid and final reporting. However, as a monitoring tool for the community and district-level stakeholders, and the grantee management team, the logical framework, as reflected in the PMF, was less useful as some grantee staff could not understand it well.

The funds were disbursed by New York; the country offices supported the preparations and signing of the implementing partner agreements. According to the grantees, this was not, however, enough and they needed more support and mentoring.

### Appropriateness and clarity of the strategies

The grantees reported using all six strategies during implementation, but were not able to state clearly which strategies were used in a particular phase, as they were more concerned with reporting by outcome. The ten grantees in Phase II were expected to expand on what was achieved in Phase I, and to them this meant increasing the number of outreaches, meetings and workshops. The increase in outreaches from 100 (Phase I) to 175 (Phase II) shows this was carried out. However, it is not clear what strategies were used for the different outcomes in order to reach the expected output.

Finding 24: The programme has contributed to a wider body of knowledge on the subject matter of legal empowerment.

An empowerment-for-change strategy should have been developed and well defined, for better programme implementation and as regards the other cross cutting strategies, and to complement the generated wider body of knowledge referred to in Finding 24 above.

A proposed empowerment-for-change framework would have included provision for socio economic and other short-term, emergency support of women living with HIV while they were being assisted to claim their property and inheritance rights. Additionally, such a framework would have ideally included detailed baseline welfare and wellbeing indicators, to track (hoped-for) progress in women’s empowerment as related to property and inheritance rights over time; and as designed and expressed by the women themselves, using participatory methods.

Following Kabeer, an empowerment-for-change framework would try and “fill the gap” between the three following elements of empowerment for women: (1) resources (defined broadly to include not only access, but also future claims, to both material and human and social resources); (2) agency (including processes of decision making, as well as less measurable manifestations of agency such as negotiation, deception and manipulation); and (3) achievements (well-being outcomes)”.  The third dimension in particular underlines the need –already argued above- for detailed knowledge, attitudes and practices before and after studies to capture these elements of an empowerment for change framework.

The programme has contributed to a wider body of knowledge on the subject matter of legal empowerment. According to the grantees, it was soon noted that the empowerment needs of women had many dimensions beyond legal empowerment. In the case of the programme, the issue of economic empowerment soon arose and several grantees had to implement economic activities. These income-generating activities enabled women to earn some income, and also to obtain temporary shelters. It was also noted that there was an emerging need to define psychological components of empowerment. It was assumed that if the women gained the legal assets they had been denied, that the women would then be empowered. However, according to the beneficiaries interviewed by the evaluation team, the most beneficial part of the successful outcome of their legal cases, was re-joining the social fabric of the families and communities they were once part of.

### Quality of the Stakeholder Partnerships

Finding 25: The high quality of ready, willing and able partnerships contributed to the successful achievements of the programme.

During the evaluation, a review of the early stages of Phase I was discussed to get an understanding of the level of resistance/acceptance of the programme when it was first implemented. On the whole, the grantees reported that resistance was quickly overcome due to their established relationships and the trust created with stakeholders they had worked with in the past, but also those selected for the programme. The grantees endeavoured to bring on board stakeholders from five to ten civil society groups and government ministries. The stakeholders were ready to participate and also provide other support such as offices. Of particular importance with respect to resistance to the programme ideas in the first quarter of Phase I, traditional rulers and police quickly joined in the programme.

Another aspect of stakeholder partnerships was the use of radio blitzes (GROOTS, Kenya gave 300 women radios in Phase I) and mass distribution of pamphlets (CEASOP, Uganda reached 500,000 persons with brochures, and FIDA, Ghana, used radio mobile clinics and reached 170,253 women in Phase II). Using the right partners saved money and time according to the grantees, and also resulted in new and emerging groups such as watchdog groups and male champions (GROOTS, Kenya).

# Conclusions

## Relevance and coherence

The evaluated programme was financed by the government of Canada, which has an international commitment to empowering women and promoting gender equality. Indeed, the programme is part of the CIDA Legal Empowerment of Women Initiative, which aims to ‘support projects that advance women’s legal empowerment, with a particular focus on property rights, helping those affected and infected by HIV reduce their vulnerability to the epidemic and improve their ability to mitigate its consequences’.

Additionally, the programme’s design fully reflects the major policy areas of the international community and of the UN system for promoting women’s equality and empowering women and girls. The WPIR-HIV programme is well aligned to goals 1, 5, and 6 (especially on human rights) of the UN Women Strategic Plan (2012-2013). The choice of nine sub-Saharan countries was coherent due to their very high HIV prevalence rates, and to their large number of attested property and inheritance rights’ violations.   It was relevant – especially given the rather short time frame of the programme – to select GCBOs that had previous experience of working with women’s property and inheritance rights’ violations.

## Effectiveness

Overall the strategy of teaching women about their rights, and of harnessing grassroots and community leaders, as well as training cadres of paralegals, has proven to be fairly effective. Nevertheless, a programme of this nature attempting to change KAP of entrenched tenets concerning women’s property and inheritance rights needs much more time than two or three years to be effective in the long run and to lead to permanent change and demonstrable impacts.

Nevertheless, many of the outputs have been achieved, and this is beginning to lead to impact.

In terms of educating people who were either ignorant of, or unsympathetic to, the problems faced by women facing discrimination and violence in connection with property and inheritance rights violations, it is clear that many duty bearers at community and higher levels – who are very often men – have learned to accept that advocating for women’s property and inheritance rights is an obligation that they must make more efforts to fulfil. These duty bearers are found in the official criminal justice system (e.g., police, lawyers, magistrates, judges) and in the customary or traditional justice system in the different programme countries.

In addition to training and enhancing the KAP concerning women’s property and inheritance rights of duty bearers at several levels of government, the programme greatly enhanced the knowledge and self esteem of thousands of the most vulnerable women and female minors in sub-Saharan Africa. This is a considerable achievement, and has undoubtedly led to a decline in suffering and stigma among the women clients in the grantee projects.

Among the women empowered, are WLHIV and women with AIDS, adolescent girls (child-headed households), women who have been expelled violently from their homes, women survivors of sexual violence and GBV, and ‘doubly exploited’ women such as Maasai women in Tanzania. These vulnerable and disempowered women and girls at the grassroots level have been assisted by the individual grantee projects to learn about their legal rights, and then subsequently to demand justice with assistance from paralegals and lawyers that have been provided via the programme. In many cases these women have successfully reclaimed their homes, lands, and livelihoods (examples from field data were quoted in the preceding chapters, and are reproduced in Annex IX). This, again, is another major achievement of the programme.

Among the notable achievements the following may be highlighted:

- Finding 14: The programme provided 130,774 people in nine sub-Saharan countries with increased access to information about women’s legal, property and inheritance rights. Most of these beneficiaries were women.

- Finding 15: The WPIR-HIV AIDS programme significantly increased the number of community-level legal frameworks and processes that effectively promote and protect women’s property and inheritance rights in the context of HIV and AIDS.

- Finding 16: A wide evidence base was created by the programme, reflected in the case studies carried out by each of the grantees.

## Efficiency

The major efficiency issues concern the strategic use of project resources. Although there was some flexibility in the budget lines, generally the biggest reported gap was shortage of funding for the following three strategies: (1) data collection and research; (2) public outreach and awareness creation; (3) legal services.

Some of the grantees also expressed concern that funding arrived late. This meant that activities could not be started at the time planned. This reportedly caused delays in commissioning activities. Quality of some outputs may have been reduced as there was insufficient time to carry out the activities which had been designed for a longer period of time.

Some grantees reported implementing the project activities for only 8 months in the first phase (instead of one year) as a result of the above-mentioned delays in their receiving instalments.

The area of awareness creation and changes in KAP required more time than was allowed in the programme and individual project design. When the programme started in 2011, there was reportedly a lack of data; in some cases, data were needed to describe the target beneficiary needs and issues. This data lack made the execution of baseline surveys necessary, which were very expensive. It was expected that baselines, mapping and monitoring would cost 1-2% of the individual budgets, which was unrealistic. Furthermore, the programme was expected to generate information and conduct research, yet the miscellaneous budget line under which this fell was too low. This meant that in some cases, brochures and booklets produced were not of good quality or user friendly in all cases observed.

Most of the overall budget in the programme went towards training, workshops and meetings/seminars, which was appropriate in order to achieve the outcomes using the six strategies of the programmatic approach.

The grantees that were relatively financially independent (e.g., AVEGA-Rwanda, FIDA-Ghana, WLSA-Zimbabwe, LRF-Zimbabwe, and CIRRDOC-Nigeria) executed a significant number of income-generating activities that benefited the WPIR-HIV projects because they helped finance them. These more experienced and financially independent grantees were also able to build on the experiences they had previously gained in managing income-generating activities and could apply these to economic empowerment activities. Finally, the target groups in grantee projects were able to utilize the services offered by the better-off grantees, such as training and health services.

The programme started with a CfP, drawn up in September 2010 by UN Women HQ, the fund manager (based in Nigeria) and the regional offices, namely Central Africa Regional Office (CARO), West Africa Regional Office (WARO), East and Horn of Africa Regional Office (EHARO) and Southern Africa Regional Office (SARO). This was followed by widespread advertising on electronic networks, radios and in local newspapers. There was also an outreach to potential grassroots and community-based organizations and partners.

The PMF was well designed and was introduced in a fairly efficient way to the grantees, so that the latter were able, with periodical support from UN Women HQ, to report on their projects’ progress according to a standardized framework of indicators that has permitted some degree of aggregation and generalisation of the overall results of the programme. Additionally, as was the case with the CfP modality, introducing the PMF permitted an increase in professionalization of the participating grantees, and considerable capacity building and training in results-based management of development interventions for the technical staff of the grantees.

## Sustainability

There are some concerns about sustainability. These were raised in particular by some of the most experienced grantees (IFAD, MWEDO, GROOTS, LRF, and CIRRDOC). In particular, sustainability and social feasibility problems affect the paralegals and the technical support to be provided by lawyers to paralegals, and by both lawyers and paralegals to women clients. The paralegals appear in most cases to be in need of some kind of allowance to help them to continue in their work. At some point, the governments involved in the programme – especially the richer ones like Kenya, Tanzania, and Nigeria – would need to assume some increased responsibility for their paralegals.

There is however, a fairly large risk, now that the grantee projects are no longer receiving funding, that the paralegal services may decline, or even stop. A further risk to the target groups’ ability to retain and impart to others the newly acquired knowledge about women’s property and inheritance rights is the fact that the training materials in several instances were reported to not always be high quality or intelligible to the language speakers of certain groups, or user friendly (examples of this latter problem are reproduced in field data in Annex IX).

## Achievement of outcomes and outputs

The programme has achieved its three outcomes and achieved most of its outputs. In turn, it has made progress towards its goal with the following tangible results: by the end of Phase II of the WPIR-HIV programme, an estimated 130,774 persons (85% of them women) living with or affected by HIV and AIDS in nine sub-Saharan African countries are now able to assert their property and inheritance rights and thereby reduce their vulnerability to HIV and AIDS. In addition, 162 organizations and groups (most of them in place before WPIR-HIV started) had their capacity improved to support their communities and specifically the targeted women. A total of 275 meetings, workshops and outreaches were held to sensitize and mobilize the local population.

Despite the relatively short duration of the programme, legal frameworks and processes to promote and protect women’s property and inheritance rights have increased at the grassroots level. Furthermore, the programme went far beyond this achievement, and eight of the 20 grantees made progress in changing and repealing legal statutes at national levels.

The programme started with a fairly reliable evidence base on the subject matter of women’s property and inheritance rights, including global statistics produced by UNAIDS and others.

The data and research on women’s property and inheritance rights formed a body of knowledge that was complemented by the addition of the results of studies such as needs assessments and baseline surveys conducted by grantees with bigger funding or more professional staff, and a longer track record in women’s property and inheritance rights. Two examples are the prior needs assessment and special studies respectively of FIDA Ghana, and GROOTS Kenya.

The knowledge base available to the programme grantees formed the basis for the programme design, and provided baseline data for the 20 grantees when writing their proposals and conducting training programmes.

The programme has shown the efficacy of addressing the legal empowerment of the targeted women by using effective strategies, engaging stakeholders who were ready and able to volunteer their services, and, in Phase II, building on the achievements of Phase I, by increasing previously established outreach services. The number of meetings, workshops, and outreach sessions increased from 100 in Phase I to 175 in Phase II, a 75% increase.

Due to the programme, there was a greater understanding achieved among the general – especially male – population of the immediate needs of women in the context of HIV/AIDS and how to address those problems in favour of disadvantaged women.

There is an emerging need to address how to help women with the next steps in their lives (after legal aid has been successful), such as getting remarried and its implications. It emerged that the dimensions of empowerment go far beyond legal empowerment and also cover social, economic and political issues. The evidence gathered during the 30-month period will make a significant contribution to the general evidence base on women’s property and inheritance rights.

In terms of efficiency, the funds, although limited, were reportedly well used by the grantees in both phases and efforts were made to ensure complete accountability for the funds. The UN Women management structure was efficient and used a decentralized Africa-based approach for management, a systematic, transparent means to deliver funds to grantees as soon as they were selected. The modality was the small grants fund.

The programme has done well, given the challenges in selecting grantees capable of running ambitious projects, the relatively limited resources provided, and the general stigma towards legal empowerment of women affected by or living with HIV - AIDS.

# Lessons Learned

The following lessons are derived from the evaluation:

Operational lessons

- Length of time for implementation has been too short: Although the programme has been highly appreciated and is beginning to show impact, a programme of this nature which aims to change knowledge, attitudes, and practices was overly ambitious given its original two-year time line. Even when granted an extra year, this has proven insufficient to cement the programme’s very real achievements made in promoting women’s property and inheritance rights.

- Concerning the alignment of the WPIR-HIV projects with international and regional norms, the detailed eligibility criteria set out in the CfP tender documentation for GCBOs and the technical specifications therein concerning scope of potential projects and their expected results were an efficient mechanism for promoting programme goals because the eligibility criteria did not allow for projects to be proposed that would not promote women’s property and inheritance rights in the context of HIV-AIDS.

- Importance of finding the correct entry points: A sense of ownership and shared vision results from the identification of stakeholders who are willing and able to participate in a project. The 20 grantees selected in Phase I were very experienced in terms of development and specifically in the area of women’s rights in the context of HIV and AIDS. Over time they had developed strong relationships with various partners in civil society. They built on these relationships and also developed new relationships with cultural and religious leaders. The good relationship with these leaders – who are normally respected by the communities – enabled the programme to gain an entry point for organising awareness-raising meetings. Working closely with the traditional leaders validated the programme’s objectives and activities in the communities’ eyes, especially the work of the paralegals. Thus men and women were open to new ideas and information about women’s property and inheritance rights.

- Despite the short length of time of the programme’s implementation, impact can be created by a combination of the right strategy and the right entry point: As a result of the grantees’ general success in building relationships and creating community-level entry points, it was easier in several cases to overcome resistance and to reconcile disputes between women and those who had denied them their rights.

- Appropriate institutional arrangements with respect to fund distribution and consultation render the roles of different partners (donors, grantees) clearer and permit a timely completion of activities. The programme was well managed by UN Women, evidenced by a decentralized management of funds distribution and regular monitoring. A regional representative based in Nigeria worked closely with the grantees to respond to questions grantees might have had regarding the programme. There were also several monitoring missions conducted by a regional team. The small grants mechanism worked well in Phase I, as evidenced by the systematic process taken to select qualifying grantees, starting with the CfPs. The CfP modality ensured that the grantees knew what was expected of them. This is demonstrated by the fact that the activities were mostly completed on time.

- Efficient tracking of funds makes it easier to coordinate expenditures during project management. UN Women had a system of funds distribution which ensured accountability and timely distribution of the funds in several tranches and pending reporting in a narrative and financial report format. The grantees expressed satisfaction with the fact that there was some degree of flexibility with respect to the budget lines, which made it easier for them to manage the funds as intended.

- A bottom-up approach where support is directed at RHs at the grassroots level still requires national-level support and consultation. Mainly a sustainability issue, an absence of government buy-in and no/insufficient setting-up of national spending categories in the annual budget to pay for paralegals’ wages, travels costs, and other allowances will ultimately threaten the work achieved in this programme (see recommendations).

- Monitoring activities are time consuming even if they do provide capacity enhancement of GCBOs: The constant monitoring activities were a challenge. UN Women and the grantees had to monitor progress, in order to support the paralegals and the partners in the communities. However, because many of the activities were based in very rural areas, the grantees needed additional funds to pay for transport/logistics costs to monitor the activities (see recommendations).

Development lessons

- As a body of evidence increases, so does the need for new definitions (e.g. empowerment) and approaches (new strategies). When the grantee projects started, the focus was on legal empowerment, whereby women would obtain their legal rights. This was very effective because many women were unaware of these rights. Over time, the grantees noted that there were many dimensions to empowerment and that economic empowerment was necessary. In plain language, poor women may not have time to go to training sessions as they live from day to day. This meant finding means to link the women to funds and means to gain an income. This was important because many of the cases were urgent: the women and their dependants had been driven from their homes and needed shelter. There was also a need to understand and meet the social needs of the women. They wanted reconciliation with their families and to be part of the social fabric again.

- The process of law reform takes a very long time, and it takes resources to support legal reform. The programme was a good initiative but needed more resources for the normative, legislative work, which is a long-term process that depends on lobbying and research (see recommendations).

- Women were not the only target group of the programme: The capacity building, training, and orientation activities did not only benefit women. Men, who tend to dominate certain institutions such as the police, courts, traditional justice systems, and local society, have also been apprised of women’s property and inheritance rights. Children were also included by default, for example in Zimbabwe, especially in the case of the child-headed households where relatives and neighbours and others constitute a threat to children maintaining the household’s assets, land and other resources left them by their deceased parents.

# Recommendations

Based on the evaluation findings in the report and supporting evidence, the following recommendations are made to support the way forward:

## Donor and government partner strategies

Recommendation 1: It is recommended to fund a new programme providing financial and technical support to the nine countries; and also to start the programme in other countries in the Africa region.

The evaluation has highlighted: (1) the challenges faced by women who are excluded and victimized due to stigmatization in the context of the HIV epidemic; and (2) the readiness of grassroots civil society to address the problem of the structural and cultural inequalities concerning women’s property and inheritance rights, often on a volunteer basis. However, funding is a problem for some grantees, and certainly for the smaller GCBOs.

The recommended future programme would be financed for a minimum of five years with a budget of at least USD 5 million.  Given that the timeline of the programme was somewhat restricted, a future programme would need more time to achieve a more sustained and empirically demonstrable impact. At least 20% of the individual budgets for grantees working in geographically large areas with remote target groups should be allocated for logistics (petrol, transport) to permit sufficient outreach. In the evaluated programme, monitoring activities were time consuming, even if they did provide capacity enhancement of GCBOs. The constant monitoring activities were a challenge. UN Women and the grantees had to monitor progress, in order to support the paralegals and the partners in the communities. However, because many of the activities were based in very rural areas, the grantees needed additional funds to pay for transport/logistics costs to monitor the activities. In all cases, financial provision for logistics and transport to get out to remoter areas was insufficient; this negatively affected the potential reach of the programme and the individual grantee projects.

In the suggested future programme, it is recommended to: (1) include pilot activities in all countries to begin the move towards officially recognised formalization and standardization with regards to the curriculum and length of the training for paralegals; (2) make a more substantial financial provision for permitting M&E activities, necessary for measuring progress against targets; and (3) include before and after statistically robust baselines of the new programme’s universe, so that exact inferences can be made concerning Knowledge, Attitudes, and Behaviour with the collected data at the end of the programme.

Additionally, some of the GCBOs work in large areas, and their target groups are far away (e.g., MWEDO, working with the Maasai women in Tanzania). Furthermore, the programme implementation period was too short to achieve the full potential of the individual grantee projects and, hence, of the overall programme.  There is, therefore, a need for a further extension of the financial and technical support provided to the nine countries funded, and also to start the programme in other countries in the Africa region, in order to consolidate and build on the progress achieved so far.

It is clear that it would be more feasible to achieve the related goals of obtaining national-level repeal of discriminatory laws and the drawing up, discussion, approval, and enactment of new, pro-women legislation if more time were allocated for this process. One way of allowing more time for this lengthy process is to include a one- or two-year pilot phase before commencing implementation for the recommended new programme proper at the grassroots level.

A recommendation coming out of the lessons learned is that the empirical basis for evidence and impact monitoring needs to be improved. In the future, a sample of 10%, randomly selected, of the grantee projects could be extensively monitored, with statistically representative before and after samples of women in the context of the HIV epidemic and violations of women’s property and inheritance rights. The data could then feed into scientific publications in international journals publishing in the area of women’s property and inheritance rights in the context of the HIV epidemic. Publications with empirical evidence on progress in the field of women’s property and inheritance rights in the context of the HIV epidemic will make it more likely for UN Women to attract more money for future programmes as part of the response to HIV.

Recommendation 2: In the interest of sustainability of the paralegals as an entity and of the paralegals’ continuing activities helping women living with HIV to obtain their legal rights to inheritance and property, it is recommended that UN Women in future programmes works directly with sub-Saharan African governments to advocate for, and assist in, helping to identify costs and setting up of national spending and institutional categories for paralegal services for women living with HIV.

## Evidence-based knowledge

Recommendation 3: UN Women is recommended to take the lead in consolidating the new knowledge acquired during the WPIR-HIV programme, via peer-reviewed, social scientific publications that have women’s rights, and women’s property and inheritance rights as primary areas of their concern. Three examples of these journals, or institutions, that have already published works on women’s property and inheritance rights, are ICRW (International Centre For Research on Women); World Development; and Human Rights Watch. The new information on women’s property and inheritance rights, obtained by the outcomes of the programme and from research conducted by the grantees themselves, needs to be synthesized and shared amongst partners.

## Portfolio diversification

Recommendation 4: Small grant portfolios in similar future programmes should be diversified to provide separate funding for grantees willing to lobby and advocate for national-level changes in laws, to repeal those which discriminate, and to enforce those that support women’s legal empowerment.

With the exception of eight grantees, the grantees mostly had experience working at grassroots level, supporting communities in many areas, including human rights. This provided the programme with many approaches using local traditional courts and traditional cultural leaders.

There are currently significant gaps in the nine African countries with respect to developing, clarifying and repealing laws. The national laws may also contradict those at community level. However, the traditional courts at grassroots level have proven effective in avoiding long, drawn-out court cases. The time taken to hear and process justice for local communities is usually shorter at grassroots level and less costly. The shorter time frame was also found to be favourable to women, whose health was often also fragile.

While the traditional courts were found to be valuable, there is always the risk that national-level policies and legal statutes can override them. There is therefore an urgent need to diversify portfolios to bring in a mix of grantees working at both the national (formal) level and grassroots (informal) level in a given country.

If donors ensure that an umbrella organisation is set up at national level (of any country funded), under which at least one national-level grantee would implement the programme, and also one grassroots grantee, this could allow the recommended portfolio diversification. Under the umbrella organisation, managed by UN Women, to give an example, the grantees could share strategies and findings. The end goal should be to change the formal laws so that they better protect women.

## Project Implementation

Recommendation 5: Expand empowerment strategies. Expand, develop and fine-tune project strategies to cover all aspects of empowerment (legal, political, social and economic), paralegal training and support and conduct TOT courses so that empowerment can continue after the programme has come to an end.

The World Bank (Deepa Narayan (ed.), Empowerment and Poverty Reduction a Sourcebook,Washington, DC, 2002,) defines empowerment as follows: “Empowerment is the expansion of assets and capabilities of poor people to participate in, negotiate with, influence, control, and hold accountable institutions that affect their lives. The four key elements of empowerment that must underlie institutional reform are: (1) Access to information; (2) Inclusion/participation; (3) Accountability; (4) Local organizational capacity”.  Empowerment approaches for the World Bank can be promoted across a broad range in development interventions: (a) Provision of basic services; (b) Improved local governance; (c) Improved national governance; (d) Pro-poor market development; (e) Access by poor people to justice.

Naila Kabeer argues that:  “women's empowerment is about the process by which those who have been denied the ability to make strategic life choices acquire such an ability”. (Kabeer, N., 2001, 'Resources, Agency, Achievements: Reflections on the Measurement of Women's Empowerment', in Discussing Women's Empowerment -  Theory and Practice, ed. A. Sisask, Sida Studies No. 3, Stockholm, pp. 17-59.

There were strictly speaking only 20 grantees in total; not 30. However, budgetarily, there were 30 grantee projects, because 10 of the 20 grantees were financed for a further phase so they could build on what they had already done.

CIDA is now called the Department of Foreign Affairs, Trade and Development (DFATD). CIDA and the earlier Department of Foreign Affairs and International Trade (DFAIT) of Canada were merged in 2013.

Source: The Performance Monitoring Framework.

This implies legal frameworks at national and community levels.

Source: Action to Promote the Legal Empowerment of Women in the Context of HIV and AIDS. Guidance for Grantees and UN Women on using the Performance Monitoring Framework (PMF), June 2011, p. 2.

Duty bearers are those individuals responsible for ensuring that people’s rights are being realized - for example, government representatives or decision-makers for customary laws. The complementary term to ‘duty bearers’ is ‘rights holders,’ which refers to all individuals who are eligible to claiming and asserting a certain right.

The term ‘enabling environment’ refers to the sum of influencing factors at the community level that support or hinder women’s ability to claim their property and inheritance rights.
10 This includes those women who are not (yet) directly affected by HIV and AIDS but are more vulnerable to the epidemic due to their economic/property situation (e.g. widows who are unable to claim their inheritance).

UNAIDS, (2010), Global Report on the Global AIDS Epidemic, p. 7, refers to both statements in the paragraph.

‘United Nations A/RES/65/277 General Assembly Distr.: General 8 July 2011. Sixty-fifth session Agenda item 10 resolution. Annex 95th plenary meeting 10 June 2011 Resolution adopted by the General Assembly [without reference to a Main Committee (A/65/L.77)] 65/277. Political Declaration on HIV and AIDS: Intensifying Our Efforts to Eliminate HIV and AIDS’  http://www.unaids.org

In Phase I, the proposals passed through three tiers of assessment. These were a due diligence process, Technical Review Group and finally a Grant Appraisal Committee.

The venue choice was strategic because it permitted the conference participants to link up with the ACHPR. The latter is a quasi-judicial body tasked with promoting and protecting human rights and collective (peoples') rights throughout the African continent as well as interpreting the African Charter on Human and Peoples' Rights and considering individual complaints of violations of the Charter.

As stated in the TOR (p. 24).

Grantee projects are referred to as WPIR-HIV/AIDS projects, or ‘Women Property and Inheritance Rights in the context of HIV and AIDS’.

CIDA is now called the Department of Foreign Affairs, Trade and Development (DFATD).

Tool 1: Question Guide for UN Women HQ and Country Staff and CIDA/DFATD Global Initiative Directorate. Tool 2: Question Guide for Grantees. Tool 3: Question Guide for Women Beneficiaries. Tool 4: Question Guide for Stakeholders (duty bearers, gender equality advocates, community groups, etc.). Tool 5: Question Guide for Organizations (donors) involved in similar programmes. Tools 1, 2, 4 and 5 were developed so they could be used in either KIIs or FGDs, depending on the situation and the number of persons ready to be interviewed.

Summary of the Declaration of Commitment on HIV/AIDS. United Nations General Assembly Special Session on HIV/AIDS 25-27 June 2001, New York. Joint United Nations Programme on HIV/AIDS (UNAIDS) 2002.

Source: United Nations A/RES/60/262. General Assembly. Resolution adopted by the General Assembly [without reference to a Main Committee (A/60/L.57)] 60/262. Political Declaration on HIV/AIDS. The General Assembly Adopts the Political Declaration on HIV/AIDS annexed to the present Distr.: General 15 June 2006. Paragraph 7.

General Assembly. Distr.: General 8 July 2011. Sixty-fifth session. Agenda item 10. Resolution. Annex. 95th plenary meeting 10 June 2011. Resolution adopted by the General Assembly [without reference to a Main Committee (A/65/L.77)] 65/277. Political Declaration on HIV and AIDS: Intensifying Our Efforts to Eliminate HIV and AIDS.

Cf. Elizabeth Cooper, ‘Women and Inheritance in 5 Sub-Saharan African Countries: Opportunities and Challenges for Policy and Practice Change’ n.d. http://www.chronicpoverty.org/uploads/publication_files/cooper_inheritance_women.pdf

Cf. Elizabeth Cooper, op. cit., p. 3.

Cf. Elizabeth Cooper, op. cit., p. 6.

http://www.un.org/womenwatch/daw/beijing/index.html

http://www.achpr.org/instruments/women-protocol/

Cf. CIDA’s Policy on Gender Equality. Gender Equality Policy And tools, 2010: http://www.acdi-cida.gc.ca/INET/IMAGES.NSF/vLUImages/Policy/$file/Policy-on-Gender-Equality-EN.pdf

Reporting guidance for grantees. Fund for women’s property and inheritance in the context of HIV/AIDS. Final narrative report. Project Title: property and inheritance legal support for women genocide survivors infected and affected by HIV/ AIDS project. Grantee Organization: AVEGA: Association of Genocide Widows Agahozo, p. 3.

FWPIR-HIV-AIDS 2010 Call for Proposals. Organization name:  AVEGA: Association of Genocide Widows Agahozo, section 4.

Source:http://www.unaids.org/en/resources/presscentre/featurestories/2012/december/20121212sexworkguidance/; and cf. Papworth E et al. Journal of the International AIDS Society 2013, 16(Suppl 3): “The HIV epidemic in the West and Central Africa (WCA) appears to have distinct dynamics compared to the rest of sub Saharan Africa, being more concentrated among key populations such as female sex workers (FSWs), men who have sex with men (MSM), people who inject drugs (PWID) and clients of FSWs.”

The Declaration of Commitment on HIV/AIDS 2001; the Political Declaration on HIV2006; and the current Political Declaration on HIV and AIDS 2011.

UN Women, Action to Promote the Legal Empowerment of Women in the Context of HIV. First Progress Report to the Canadian International Development Agency, March 2010 – September 2011, pp. 14-15, 2011.

UN Women Action to Promote the Legal Empowerment of Women in the Context of HIV. Second Progress Report to the Canadian International Development Agency, October 2011 – May 2012, p. 16.

Interview held on 20 February 2014.

Action to Promote the Legal Empowerment of Women in the Context of HIV (74882), First Progress Report to the Canadian Development International Agency, March 2010 – September 2011, p. 16.

They are: AVEGA, CIRRDOC, FIDA-Ghana, Dialogue on Shelter, GROOTS Kenya, House of Peace, MWEDO, National Community of Women Living with HIV/AIDS in Uganda, NTENGWE, SWID, UGANET and WLSA.

At the beginning of the programme there was a coordinator and a fund team in place who supported grantees as well.

Column 1 refers to counselling.

Column 2 refers to training, Phase 1 mostly.

Column 3 refers to the intentions of Phase 2, whereby awareness creation increased.

Reporting Guidance For Grantees. Fund For Women’s Property and Inheritance In the Context of HIV/AIDS. Final Narrative Report. AVEGA. Property and Inheritance Legal Support for Women Genocide Survivors Infected and Affected by HIV/AIDS Project.

Fund For Women’s Property and Inheritance In the Context of HIV/AIDS. Mid-Term Progress Report, October 2011. GROOTS Kenya.

Reporting Guidance For Grantees. Fund For Women’s Property and Inheritance In the Context of HIV/AIDS. Final Narrative Report. Project Title: ‘Promoting Respect for the Rights of Women to Property and Inheritance in the Context of HIV/AIDS.’ Grantee Organization: Civil Resource Development and Documentation Centre.

UN Women regions in Africa were Central Africa (CARO), East and Horn of Africa (EHARO), Southern Africa (SARO)

West Africa (WARO). As well as supporting the Small Grants Fund, the regional offices supported monitoring efforts.

Kabeer, N., 2001, 'Resources, Agency, Achievements: Reflections on the Measurement of Women's Empowerment', in Discussing Women's Empowerment -  Theory and Practice, ed. A. Sisask, Sida Studies No. 3, Swedish International Development Agency, Stockholm, pp. 17-59.

AVEGA (Rwanda) implemented agricultural cooperatives drawn from existing cooperatives but specially tailored to women with HIV and AIDS who had been denied their property. The other members worked with the women and supported their lower energy levels. The Evaluation team was able to interview the beneficiaries of this approach. This approach was also noted with WLSA where Empowerment circles focussed only on legal empowerment.