- TERMS OF REFERENCE

- for an Independent External Mid-term Evaluation of the Pacific Regional Ending Violence against Women Facility Fund

# Background

# Grounded in the vision of equality enshrined in the Charter of the United Nations, UN Women works for the elimination of discrimination against women and girls, the empowerment of women, and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security.  Placing women’s rights at the centre of its efforts, UN Women is mandated to lead and coordinate United Nations System efforts to ensure that commitments on gender equality and women’s empowerment and gender mainstreaming translate into action throughout the world. It provides strong and coherent leadership in support of Member States’ priorities and efforts, building effective partnerships with civil society and other relevant actors. A goal of the UN Women strategic plan for 2013-2017 is to “Prevent violence against women and girls and expand access to services”.

# UN Women is guided by the Beijing Declaration and Platform for Action of the Fourth World Conference on Women, the Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW) and the follow-on CEDAW General Recommendation 19 of the United Nations (1992) referring specifically to violence against women, the 1993 Declaration on Ending Violence Against Women, the Millennium Declaration, the Vienna Declaration and Programme of Action of the World Conference on Human Rights, and various UN instruments.

UN Women Fiji Multi-Country Office (MCO), in close consultation with key stakeholders, identified the main constraints preventing Pacific organizations and government departments from successfully addressing violence against women (VAWG) through a three year process of ongoing consultations (2006-2008) and workshops with the donor, civil society and government sectors. The two main issues identified were: (i) limited access to financial resources, and related need for skills building in financial management, project design, monitoring and evaluation to the standard required by donors, and (ii) knowledge and capacity needed to plan and implement projects more strategically and within a rights based framework for concrete  results and outcomes.

In order to directly address these gaps, in March 2009, UN Women Fiji MCO established the Pacific Regional Ending Violence against Women Facility Fund (also referred to as ‘the Project’) initially in 5 countries - Fiji, Kiribati, Nauru, Papua New Guinea and Solomon Islands. It was designed specifically to meet the needs of Pacific Island countries and organisations to advance efforts to prevent and eliminate violence against women. The Project was first implemented for a three year period from mid-2009 to mid-2012, and was subsequently extended to June 2013, then December 2017.

## In 2011, the Australian government announced that it would contribute AUD5.2M to the project. This prompted the expansion of the project to three more countries; Samoa, Tonga and Vanuatu, and prompted a revised strategy and consolidation of capacity development including results based monitoring.

The ‘goal/long-term result’ of the Project is as follows: “civil society organisations and key government departments working to eliminate violence against women in Pacific countries are effectively implementing programmes, projects and actions for the response and prevention of violence against women in their communities and countries”.  The Project outcome is that “selected organisations are more effective in preventing and responding to violence against women and girls.”

The Theory of Change for the Project is that “through increased financial resources and capacity development, organisations in the Pacific will provide more effective, comprehensive and holistic services to survivors of violence, their families and their communities, and will support progressive development of primary prevention strategies to end intergenerational cycles of violence against women and girls.”  The Theory of Change rests on a situation analysis that highlighted under-resourced and weak civil society and state organisations in the VAWG arena that were constrained in their ability to implement effective programmes and influence policy, the importance of focusing attention on both prevention and response to effectively counter VAWG, and the central role of documenting learning to enhance the response.

The aim of the project is to ensure that innovative and committed organisations working to end VAW are able to access:

- Financial resources, though a grants scheme of an appropriate and manageable size (USD$3,000-$25,000 in 2009 to 2011 and USD$10, 000-$100,000 in 2012 to date);

- Capacity development opportunities that are structured and operated to respond appropriately to the specific needs of local organisations in Pacific island countries, and;

- Knowledge building and sharing through strategic approaches, learning opportunities, South-South exchange and tools to end VAW from a women’s human rights and gender perspective.

Since its launch in March 2009 to March 2015, the project has awarded 43 grants with a value of USD $1,907,490 (herein referred to as the ‘grantees’) for projects in seven countries. Nauru has not been successful in receiving grant funding.

Through the Project, UN Women is prioritizing the prevention of and response to VAWG as part of its work under the Development Results Framework Goal 3 ('Women and girls live a life free from violence'). The Project progresses towards this goal through the provision of grants, technical advisory services and capacity-development of governments and civil society organisations to enable them to create systemic approaches to prevent and respond to VAW cases, expand the availability of services for survivors, improve the policy environment to end VAW including taking steps to prevent violence from occurring in the first place by working with schools, media establishments, faith based organisations  and community groups to promote community-based solutions. The Project is also creating learning spaces and exchanges amongst Pacific organisations that are working to end VAW, the development of knowledge products and tools and the implementation of evidence-based programmes.

Grantees include women’s groups, community-based and faith-based organisations, as well as government departments. Grants are allocated through a competitive process and reviewed and selected at national and regional levels by committees. The distribution of funds to the grantees has been accompanied by a capacity development program that includes:

- In Country Technical Assistance, Mentoring and Advisory Services in Ending VAW

- In Country Training on Ending VAW implemented by the Fiji Women’s Crisis Centre (FWCC) and other service providers.

- Sponsorships to Regional Training Programmes conducted by FWCC.

- National and regional learning and knowledge exchanges and attachments

- Training and mentoring support in Advocacy and Engagement; Prevention; Organisational and Project Management; and Services provided by implementing partners.

During the project’s early years, it was designed as a small grants facility, offering grants from $3,000 – 25,000 USD to sometimes nascent organisations for small scale work.  Capacity building was offered widely to anyone, funded by this project, though not connected to grants.  Limited technical support was provided to grantees, as it was unclear yet what their main restraints were due to limitations in reporting.  Results and financial reporting were significant challenges for grantees, limiting the understanding of the effects of the Fund.

In 2011-2012, several major strategic shifts were made to correct the identified weak areas the project experienced.  The project strengthened grant criteria to attract more qualified organisations that could meet the minimum requirements for programme implementation, reporting and financial systems.  Capacity development support was linked to grants, strengthening the investment in grantees organisations and the opportunity for follow up with participants.  UN Women scaled up technical support offered directly by the team, implemented a much strengthened monitoring and evaluation framework and significantly bolstered its attention on results reporting.

In 2014, the Project underwent an independent audit of Fiji based grantees managed by UN Women Headquarters, completed an Evaluability Assessment and a Formative Evaluation.

The Formative Evaluation found that that the Project is contributing to progress in ending violence against women and girls in the Pacific.  The evaluation found that the strategic and operational changes that were implemented beginning in 2012 allowed the project to make corrections bringing it into sharper focus on results and deliver support and grants to more qualified organisations.  The Project is a highly sought after resource for a wide range of organisations addressing VAWG, valued for the combination of personalized technical assistance with grant funding, and attention to supporting organisational capacity to better deliver on EVAW and gender equality programming. The Project has been effective in supporting work that reaches a diverse audience and target groups, such as women with disabilities, LGBTQI-identified persons, rural women, sex workers, etc.

The project is a constantly evolving or “rolling” type of programme, with successive Calls for Proposals that have changed in focus and design as needed.

The project has received funding from the Australian government’s Department of Foreign Affairs and Trade (DFAT) and the National Committees for UN Women in Australia and New Zealand.

- Purpose and Use of the Evaluation

The overall objectives of this evaluation are to assess:

- Relevance: extent to which the objectives of the project are consistent with beneficiaries’ requirements, country-needs, and partners’ and donors’ policies;

- Effectiveness: extent to which the project’s objectives were achieved, or are expected to be achieved

- Efficiency: measure of how economically resources/inputs (funds, expertise, time, etc.) are converted to results;

- Sustainability: the probability of continued long-term benefits from the project; the resilience to risk of the net benefit flows over time; and

- Inclusiveness: extent to which diverse groups are included as stakeholders in the project.

- The progress and implementation of accepted recommendations from the formative evaluation

Use of the evaluation report

- The evaluation findings will be used by UN women Fiji MCO for making decisions on the overall future direction and design of the Project.

- The evaluation will be used by DFAT and other potential partners to assess progress of the project, and to inform future funding allocations.

- The evaluation findings will also be used as guidance for further deliberations and assessment by UN Women Fiji MCO and key stakeholders on progressing recommendations from the Formative Evaluation.

- Both duty bearers and rights holders (particularly women and other groups subject to discrimination) are intended users of the evaluation, as they are the main concerned parties that the Project seeks to support. The evaluation will be used to improve assistance provided to these groups through the Fund.

- The findings of the project’s mid-term evaluation will inform the project’s linkages to UN Women Fiji MCO’s work relating to UN Joint programming on Ending Violence against Women portfolio and vice versa.

- The findings will further be used by UN Women Fiji MCO’s as part of its continuing work to identify and strengthen linkages between programme areas: elimination of violence against women, political participation, leadership, human rights and access to justice, climate change and disaster risk resilience and women’s economic empowerment.

The project’s evaluation cycle to date and the positioning of the Mid Term Evaluation and follow-on activities is as follows:

- Internal Review and Assessment (internal) – implemented from end 2011- 2012

- Evaluability Assessment – 2013

- Formative Evaluation – fourth quarter 2013/first quarter 2014

- Mid-Term Evaluation – third quarter 2015

- End-line Evaluation/Impact Assessment – end of programme in 2017

- The Scope of the Evaluation

Evaluation scope: Considering the strategic shifts instituted in 2011-2012 in the implementation of the Project and in particular the expansion of the grant scopes and expectations, the evaluation focuses largely on the 2012-2014 roll-out implementation period, with some attention to the lessons and any evidence of the use of outputs/ intermediate outcomes from the early phase of the project.  It will focus attention on the Project’s  Relevance, Efficiency, Effectiveness, Sustainability and Inclusiveness and will include a review of the extent to which recommendations made during the Formative Evaluation have been put into place, and what effects this has had.  It includes Inputs, Activities, Outputs and Use of Outputs, and any available information on Intermediate Outcomes.  It focuses at both macro and micro levels.  In alignment with the intention of the project, much of the attention of the MTR is focused on target groups (the grant recipients, with some attention on their target groups- including beneficiaries, rights holders and duty bearers).

Geographical coverage: The evaluation will focus on a subset of funded projects from the 2012-2014 Calls for Proposals. The plan is for the evaluators to make field visits to the following project countries – Fiji, Kiribati, PNG, Samoa, Solomon Islands, Tonga and Vanuatu.

Stakeholder coverage:  The evaluation will reach out to all principal stakeholders, i.e. project beneficiaries, project grantees, the FWCC, SPC-Regional Rights Resource Team, Capacity Development Implementing Partners in: Prevention (UN Volunteer), Organisational and Project Management; and Response Services for Survivors, relevant UN agencies (including UNFPA OHCHR), bilateral donors (DFAT, National Committee of UN Women Australia, National Committee of UN Women New Zealand) and stakeholders working on EVAW but not directly with the project (such as other service providers, donors, etc).  The evaluation report will include a stakeholder analysis map.

Substantive scope: The evaluation will analyze the relevance, effectiveness, efficiency, inclusiveness and sustainability of the project’s objectives in terms of results achieved against objectives, change on human rights and gender equality and partner capacities (technical and organizational), ownership of stakeholders and sustainability of  project outcomes.

Evaluation Approach: The evaluation approach, data collection and analysis methods must be clearly human rights-based and gender sensitive.  Evaluation data to be disaggregated by sex, ethnicity, age and disability.

4. Evaluation questions

The consultants should be guided but not limited to the scope of the evaluation questions listed below. The consultants should raise and address any other relevant issues that may emerge during the evaluation:

4.1 Relevance

Relevance questions:

- Are the programme objectives addressing identified rights and needs of the target groups in national and regional contexts?

- To what extent are the objectives of the project consistent with beneficiaries’ needs, country-needs and regional priorities in other words, are the project’s goals still relevant in the Pacific?

- What rights does the project advance under CEDAW and other international development commitments related to women’s human rights and gender equality?

- To what extent is the project informed by substantive and tailored human rights and gender analyses that identify underlying causes and barriers to human rights and gender equality?

- To what extent is the project informed by needs and interests of diverse groups of stakeholders through consultation?

- To what extent have stakeholders participated in the project?

- Assess whether the project design / re-design  was logical and coherent in a) taking into account the roles, capacities and commitment of stakeholders and b) in realistically achieving the planned outcomes.

4.2 Effectiveness

Effectiveness questions:

- What has been the progress made towards achievement of the expected outcomes and expected results?   What are the results achieved thus far in the project?

- Does this project have clear and realistic outcomes, supported by a robust logic and the extent that the  theory of change is still valid;

- To what extent have a human rights based approach and a gender mainstreaming strategy been incorporated in the design of the project including the Theory of Change and results framework as well as in the implementation of the project?

- The quality of the project’s key outputs and activities is as expected;

- How well the project has addressed the needs of women with disabilities and other more vulnerable groups.

- What is UN Women’s comparative advantage in designing and implementing this project? What is the benefit of linkages to UN Women’s other programming areas (women’s economic empowerment, leadership, climate change, etc)?

- Does the project have effective monitoring mechanisms in place to measure progress towards results?

- To what extent have the recommendations of the project’s Formative Evaluation conducted in 2014 been followed?

4.3 Efficiency

Efficiency questions:

- What measures have been taken during planning and implementation to ensure that resources are efficiently used?

- Could the activities and outputs been delivered with fewer resources, or with a different mix/scope of resources without reducing their quality and quantity?

- Have UN Women’s organizational structure, managerial support and coordination mechanisms effectively supported the delivery of the project?

- Does UN Women have the necessary systems and processes to implement the project in an efficient and timely manner?

- Is the project cost-effective, i.e. could the outcomes and expected results have been achieved at lower cost through adopting a different approach and/or using alternate delivery mechanisms?

4.4 Sustainability

Insights into aspects of sustainability should be noted, and recommendations about sustainability included in the evaluation report. The Consultant to identify alternate approaches and future models for delivery and lessons learnt.

Sustainability questions:

- What operational capacity of national partners, also known as capacity resources, such as finance, and staffing, has been strengthened?

- What adaptive or management capacities of national partners, such as learning, leadership, programme and process management, networking and linkages have been supported?

- What technical capacity of national partners, such as those related to implementing stronger human rights based approaches, development of policy advocacy skills, and monitoring and reporting capacities related to EVAW, have been supported and strengthened?

- Sustainability of results with grant target groups?

- Since 2009, the project has been operating in the Pacific and managed by UN Women Fiji MCO. In 2015, the project will devote more attention to transition planning: Shall it be continued under UN Women management, handed over to another institution after 2017, or perhaps closed?  If transitioned to another institution, to whom and under what conditions?

4.5 Inclusiveness

Inclusiveness questions:

- How inclusive is the project in supporting marginalised and vulnerable groups?

- How inclusive is the project in involving key stakeholders in governance and management of the project?

5. Information Sources

Existing information sources of the project include: project Document, project donor reports, Calls for Proposals, Meeting Minutes of the selection of the proposals received for each Call, training reports, mission reports, monitoring and evaluation framework, previous evaluation reports and responses/analyses of these, etc.

Project documents for each individual grant which includes project objectives, expected outcomes and outputs, timeframe, Work-plan; budget, contract agreements, individual project narrative reports, media or materials produced by the project, completion reports, financial reports and contract amendments.

- UN Women Pacific Regional EVAW Facility Fund Project Document (2008 and revised in 2012).

- Annual Donor progress reports and annexes

- Annual UN Women Fiji MCO Workplans

- Pacific Regional EVAW Facility Fund Project M&E Framework.

- UN Women Strategic Plans

- Pacific Islands’ Forum National and Regional Action Plans for Ending Violence Against Women, Leaders’ Communiqué and other instruments.

- Family and Health Safety Studies and VAW prevalence reports

- CEDAW Concluding Observations for all eligible countries that have ratified the Convention.

- Partnership Agreements between Australia and UN Women.

- Australia’s DFAT Gender Strategy.

- UN Women Fiji MCO Internal Reports on project strategy/donor meeting, Regional Project Appraisal Committee Meetings, National Short-Listing Committee Meetings.

- Samples of Grantees’ progress reports, training beneficiaries’ Learning Diary, Follow-Up Action Plans and Reports six months after the Training.

6. Methodology and process

The Mid-Term Evaluation will include both qualitative and quantitative data collection.

The Team Leader will prepare a detailed draft evaluation plan which will be finalised following an inception meeting and consultations with UN Women and the Evaluation Reference Group.  The draft evaluation plan will be prepared after desk review of program documentation. Full review of key documents will form part of the independent evaluation and will be conducted after the plan has been approved.

# The evaluation plan should outline in detail the methodology to be used for assessing the outcomes of the project; the process for information collection and analysis, including an emphasis on qualitative tools such as questionnaires and/or questions to be asked during discussions; identification of any challenges anticipated in achieving the evaluation objectives; allocation of tasks of the evaluation team; review the time frame for the evaluation; sampling method and selection criteria for project sites to be visited; a consultation schedule identifying key stakeholders to be consulted and the purpose of consultations; and other activities/research to be undertaken.

The suggested methods for the evaluation include analyses of various sources of information, including in-depth desk review and documentation analysis (project’s progress and donor reports, workshops’ and mission reports, knowledge and advocacy products, previous evaluations and responses to evaluations, survey, and other appropriate documentation produced); conducting surveys of individual projects, meeting with the project partners; field visits to project sites; in-depth interviews with key stakeholders, focus group discussions and other means to allow cross-validation of data.

The evaluation will make use of Appreciative Inquiry methods to discover what works well and to understand the elements of success so that they can be replicated.

Based on consultations with UN Women Fiji MCO, the consultants will visit selected project sites to validate the findings of the desk review and documentation analysis, and identify best practices and lessons learned. To make this evaluation more participatory, there will be a stakeholder meeting at which the initial findings are presented.  UN Women will work with the evaluation team to make sure the meeting includes a wide variety of stakeholders, including some grantees and donors. The evaluation team will also hold separate meetings with and interview partners from government institutions, civil society organizations, as well as the UN Country Team and donor community.

The evaluation report will detail methodological measures for sampling and application of ethical standards.  The evaluation will take care to address issues of informed consent and protection, in addition to applying human rights and gender equality principles throughout.

7. Tentative Project Evaluation Timeline

The Project Evaluation will be conducted according to the following tentative timeline:

Stage 1: Preparation & Initial Desk Review

| Task | Responsible Party | Number of days | Remarks |
| --- | --- | --- | --- |
| Programme documents’ initial desk review | Evaluation team | 4 | home-based |
| Development of evaluation plan, stakeholder analysis and preparation of an Inception Report | Evaluation team in cooperation with UN Women Fiji MCO | 3 | Home- based |
| Consultations with the UN Women Fiji MCO and reference group to finalize the evaluation plan, identify projects for in-depth analysis and reach an agreement on the proposed methods | Evaluation team in cooperation with UN Women Fiji MCO and the Evaluation Reference group | 3 | in Suva |

Stage 2: Data Collection and Analysis

| Task | Responsible Party | Number of days | Remarks |
| --- | --- | --- | --- |
| Develop data collection tools and instruments and testing the tools. | Evaluation team | 5 | in Suva |
| Conduct field trips to project sites, including in-depth interviews, survey(s) and focus group meetings | Evaluation team in cooperation with UN Women Fiji for logistics | 30 | Various sites, overlapping time with team members |
| Conduct in-depth interviews and focus group meetings in the Pacific according to the agreed list | Evaluation team | 5 | in selected sites |
| Data classification, systematization, and analysis | Evaluation team | 3 | in Suva |
| Draft the initial report, which summarizes key findings and recommendations | Evaluation team | 5 | in Suva |

Stage 3: Analysis and Dissemination of Evaluation Results

| Activity | Responsible Party | Number of days | Remarks |
| --- | --- | --- | --- |
| Present initial findings and recommendations at a meeting including UN Women and the members of the evaluation reference group for initial feedback. | Evaluation team in cooperation with UN Women Fiji MCO and reference group | 1 | UN Women will organize the meeting in Suva. |
| Incorporate comments and feedback from the evaluation reference group meeting and prepare draft report | Evaluation team | 6 | Home-based |
| Share draft report with UN Women and the evaluation reference group and incorporate comments and feedback to revise and finalize the full evaluation report. | Evaluation team in cooperation with UN Women Fiji MCO and evaluation reference group | 4 | Home-based |

Time frame for the consultancy: Estimated start date is 20 July.  The evaluation report is expected by 8 October 2015.

8. Deliverables

Expected key products will include:

- Deliverable 1: An agreed evaluation inception plan report. The inception report should contain evaluation objectives and scope, description of evaluation methodology/methodological approach, data collection tools, data analysis methods, key informants/agencies, evaluation questions, performance criteria, issues to be studied, work plan and reporting requirements. It should include a clear evaluation matrix relating all these aspects. The inception report shows how each evaluation question will be answered by way of: proposed methods; proposed sources of data; and data collection procedures. The inception report should also include a proposed schedule of tasks, activities and deliverables, designating a team member with the lead responsibility for each task or product.  To be presented to UN Women Fiji MCO and the evaluation reference group. Due after 2 weeks, by 31 July 2015.

- Deliverable 2: Present preliminary findings to UN Women following data collection for first review.

- Deliverable 3: Present preliminary findings and recommendations to the evaluation reference group.  By 2 September 2015.

- Deliverable 4: Draft evaluation report to be submitted to UN Women Fiji MCO for first review.  By 11 September 2015.

- Deliverable 5: Draft evaluation report to be shared with reference group for review and comments. By 22 September 2015.

- Deliverable 6: An analytical and comprehensive final evaluation report not exceeding 50 pages (plus annexes) to be submitted to UN Women Fiji MCO.  The report is to be written in a clear, concise and easily understood manner, making use of visual representations of data where possible.  Due 8 October 2015.  The evaluation report should be structured as follows:

Executive Summary (maximum five pages)

Programme description

Evaluation purpose

Evaluation methodology

Findings

Lessons learnt

Recommendations

Annexes (including interview list – without identifying names for sake of confidentiality/ anonymity, data collection instruments, key documents consulted, Terms of Reference).

9. Evaluation Report

The evaluation and report will be guided in structure and style by the good practice guidelines for evaluation reports.  UN Women reviews all evaluation reports according to the Global Evaluation Reports Assessment and Analysis System (GERAAS) framework.  The report will be guided by these criteria.

10. Management of the evaluation

The evaluation team will work in close collaboration and consultation with project staff and management structure as per the table below.

To inform participation in the evaluation and reference group, a stakeholder analysis will be conducted.

| Who: Actors and Accountability | What: Key Roles and Responsibilities |
| --- | --- |
| Project Principal Representative (UN Fiji MCO Representative or Deputy Representative) | - Safeguard the independence of the evaluation exercise and ensure quality of evaluations - Responsibility of management responses to the evaluation |
| Evaluation Reference Group (to be informed by stakeholder analysis and include UN Women and DFAT)- to include internal and external stakeholders | - Provide inputs on the management plan of the evaluation - Participate in the review of the evaluation plan including review design and methodology, sampling method and provide comments to the evaluation team and the UN WOMEN Evaluation Task Manager. - Observe the process of the evaluation - Provide comments no the initial findings, the draft evaluation reports and final report, particularly regarding recommendations |
| UN Women Evaluation Task Manager (EVAW Specialist/ Programme Manager) | - Ensure the decisions to be made on time for the evaluation team - Facilitate a management response to the evaluation and ensure the implementation of committed actions in the management response - Facilitate recruitment and selection of the evaluation team - Facilitate communication between the evaluation team and senior management, project staff and stakeholders - Monitor evaluation implementation and provide guidance to the evaluation team - Report to management and the Evaluation Reference Group on any significant deviation from the evaluation plan - Facilitate dissemination of evaluation mid-term and final findings to stakeholders - Help identify the projects to be visited |
| Regional Project Manager, Programme Officer | - Prepare TOR for the evaluation ensuring participation of stakeholders - Ensure the close communication with the evaluation team during the whole evaluation process. - Clarify questions raised during the evaluation - Help identify the projects to be visited, based on criteria established in the evaluation plan - Provide all the document information sources the evaluation team requires |
| Programme Assistant | - Help arrange the travel to the project sites and other logistic issues. - NOTE: Evaluation team may need to hire locally available assistants for logistical help, translations, etc. |
| Evaluation team leader | - Lead the whole evaluation process, with responsibility for delivery of the deliverables, implementation and reporting of the evaluation. - Work closely with and supervise the evaluation team member. Manage the evaluation process in timely manner - Communicate with UN Women whenever it is needed - Conduct desk review and interviews etc. - Conduct field visits to the project sites identified and collect data. - Report to UN Women and the evaluation reference group when required - Produce the inception report - Produce the final report |
| Evaluation team member | - Contribute to the whole evaluation process substantively - Share responsibilities for conducting desk review and interviews. - Conduct field visits to the project sites identified and collect data as needed - Provide substantive inputs to the inception report, - Provide substantive inputs to the final report. |

11. Team Composition

The evaluation will be conducted by 2 experienced evaluators, one evaluation team leader and expert, and one evaluation team member. Experts will be selected and recruited based on the requirements outlined below.

The lead evaluator is expected to lead the process and work closely with the national consultant. S/he will function as the Team Leader, managing the evaluation process in a timely manner, and is primarily responsible for writing and producing the final report.

The evaluation team member will contribute to the process substantively, sharing responsibilities for conducting desk review and interviews, provide substantive input to the report, and its review.  In the case that the lead evaluator is not from the Pacific, the evaluation team member should assist with contextualizing the evaluation.

While the Evaluation team will work in an independent manner, UN Women, as the agency responsible for administering the Project will provide logistical and other support to facilitate the evaluation team mission, particularly for field visits, including the provision of professional interpreters to accompany the international consultant during field visits, if required.

Required Expertise/Qualifications for the lead evaluator

Team leader

- Advanced degree in relevant discipline (e.g., evaluation, management, gender, development and social studies, sociology, political science, etc.);

- Strategic thinking and proven expertise in gender analysis;

- At least 10 years’ experience in programme evaluation and proven accomplishment in undertaking evaluations, including  leading evaluations of multi-stakeholder programmes for multilateral organizations

- Experience in conducting complex evaluations in the development field and with international organizations (at least 8 evaluation of which at least two as team leader)

- Knowledge in results-based programming in support of women’s  human rights, violence against women and gender equality;

- Excellent inter-personal and communication skills

- Excellent written and spoken English and presentational capacities

- Extensive knowledge of qualitative and quantitative evaluation methods

- Knowledge of the UN system a strong asset.

- Knowledge of the development context of the Pacific and preferably previous experience in development initiatives in the region;

- Excellent drafting and writing skills to produce and present concise and analytical reports and communicate clearly with evaluation stakeholders;

- Excellent interpersonal and teamwork skills.

Required Expertise/Qualifications for the evaluation team member

- Advanced degree in relevant disciplines (e.g., gender, development and social studies, sociology, political science, etc.);

- At least 5 years of experience in evaluation and assessment assignments with the multilateral and bilateral organizations;

- Work experience with international organizations and intergovernmental bodies in the above mentioned fields.

- Proven working experience in the area of gender equality, women’s empowerment and women’s rights;

- Native ability in one of the languages used in one of the 7 target countries for the Project and fluency in written and spoken English;

- Knowledge of evaluation methods.

- Knowledge of the Pacific region and the UN system.

- Ability to facilitate multi-stakeholder discussions;

- Excellent interpersonal and teamwork skills.

12. Evaluation ethics

Evaluations in the UN will be conducted in accordance with the principles outlined in UNEG Norms and Standards for Evaluation in the UN System,  by the UNEG ‘Ethical Guidelines for Evaluation’, and ‘Integrating Human Rights and Gender Equality in Evaluations’ . These documents will be attached to the contract. Evaluators are required to read the Norms and Standards and the guidelines and ensure a strict adherence to it, including establishing protocols to safeguard confidentiality of information obtained is during the evaluation.

13. Application Procedure:

Interested applicants please submit the following to pacific.registry@unwomen.org

- Application letter

- Curriculum vitae

- Personal History Form (P11) (see attached form)

- Proposed full evaluation budget including daily rates, travel/airline costs, daily travel allowances, fees for the evaluation team member, local assistants, meeting expenses, etc.

- Sample evaluation reports related to violence against women, gender equality and women’s human rights

Deadline for Application: before midnight 1st July 2015, Fiji Time

An Evaluability Assessment examines the extent to which a project or a programme can be evaluated in a reliable and credible fashion.  An Evaluability assessment calls for the early review of a proposed project or programme in order to ascertain whether its objectives are adequately defined and its results verifiable.”

Purpose of formative evaluation is “to provide some early insights into a programme, and inform management and staff about the components that are working and those that need to be changed in order to achieve the intended objectives”, UN Women (2009). Guidance on Defining Evaluation Types and Modalities, UN Women, New York, United States.

More information on the GERAAS framework is available at http://www.unwomen.org/~/media/headquarters/attachments/sections/about%20us/evaluation/evaluation-geraasmethodology-en.pdf

http://uneval.org/document/detail/1616