Final Report

On

Final Project Evaluation - Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options

Submitted to

Submitted by

The Nielsen Company (Bangladesh) Limited

House#70, Road#15/A, Dhanmondi R/A,

Dhaka – 1209, Bangladesh

Phone: 880-2-9125839, 9127743, 01713271573

waliul.matin@nielsen.com

December 31, 2015

December 31, 2015

UN WOMEN Bangladesh

House No: 11 A, Road No: 113, Gulshan-2

Dhaka-1213, Bangladesh

Subject: Final report for conducting “Final Project Evaluation on Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options.”

Dear Sir/Madam:

Please find the attached final report for conducting “Final Project Evaluation on Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options”.

Should you have any query, please feel free to contact us.

We look forward to hearing from you soon.

Yours sincerely,

Waliul Mutasim Matin

Director, Social Research

The Nielsen Company (Bangladesh) Limited

Table of Contents

Executive Summery	i

1.	Introduction	1

1.1	Background	2

1.2	Purpose of the Evaluation	2

1.3	Objective of the Evaluation	3

2.	Methodology	4

2.1 Sources of Data	4

2.3 Evaluation Population/Source of Information	4

2.4 Quantitative Method	4

2.4.1 Sample Size Calculation	4

2.4.2 Quantitative Sample Distribution	5

2.4.3 Sampling Selection Procedure	6

2.5 Qualitative Method	6

2.6 Secondary Data through Desk Review	7

3.	Findings	8

3.1	Key Household and Beneficiary Information	8

3.2	Capacity Building Activities	12

3.3	Improvement in Beneficiaries’ Socio-economic State	18

3.4	Improvement in Knowledge and Existing Practices	23

3.5	Changes in Decision Making Role and Social Security Situation	31

Impact on reducing gender discrimination and violence	35

3.6	Impacts over Policy Implementation and Stakeholder Level	38

4.	Recommendation	40

5.	Conclusion	43

ANNEX	44

Annex 1: Evaluation Matrix	45

Annex 2: Tables	46

Annex 3: Quantitative Tool	55

Annex 4: Qualitative Tools	85

Annex 5: FGD conduction schedule	101

List of Tables (in Annex)

Table 1: Age of the respondents (%)	45

Table 2: Marital Status of the respondents (%)	45

Table 3: Relationship of the respondents with the Head of the Households (%)	45

Table 4: Religion of the respondents (%)	46

Table 5: Educational qualification of the respondents (%)	46

Table 6: Primary and secondary occupation of the beneficiary women (%)	46

Table 7: Household income level of the respondents (%)	47

Table 8: Trainings received by the respondents under RVWACC project (%)	48

Table 9: Initiatives taken for women under project (%)	48

Table 10: Involvement in IGA by the women of the evaluation areas (%)	49

Table 11: Average earning members of the beneficiary households (Frequency)	49

Table 12: Purposes of savings by the respondents (%)	50

Table 13: IGA activities by the respondents and/or female members of their household (%)	50

Table 14: Project impacts on beneficiary women’s lives (%)	51

Table 15: Role played in household decision making based on gender (%)	51

Table 16: Household assets ownership according to sex (%)	52

Table 17: Perpetrators of violence against women (%)	53

List of Figures

Figure 1: Perception of Respondent on HH Class Wealth-wise (%)	11

Figure 2: Female members in households receiving IGA trainings (%)	13

Figure 3: Contribution of trainings (%)	14

Figure 4: Types of trainings received on disaster management (%)	15

Figure 5: Females involved in household IGA & livelihoods	19

Figure 6: Spending of earning (%)	20

Figure 7: Purposes of utilization of natural resources (%)	24

Figure 8: Source of knowledge about climate change	26

Figure 9: Initiatives taken by the Disaster Management Committee (%)	27

Figure 10: Topics discussed in the monthly courtyard meetings (%)	28

Figure 11: Sources of Domestic and Drinking Water (%)	29

Figure 12: Types of Latrines Used in the HHs (%)	30

Figure 13: Comparative scenario of ownership of household assets by male and female members of family (%)	34

Figure 14: Experience of violence in community in last 1 year (%)	36

# Executive Summery

UN Women is working to reduce vulnerability of women affected by climate change. In December 2011, UN Women launched the project, “Reducing Vulnerability of Women Affected by Climate Change through Livelihood Options” which is supported by the Royal Norwegian Embassy in Dhaka and implemented by Bangladesh Rural Advancement Committee (BRAC). The overall development goal of the project is to increase access to sustainable and alternative livelihoods for women in communities vulnerable to the impact of climate change as well as to enhance their role as change agents to influence policies, strategies and programmes on climate change adaptation and mitigation measures.

To understand the result/contributions and lessons learned in the areas of gender equality and climate change; an evaluation was planned to conduct. The evaluation was also targeted to feed learning into UN Women’s efforts to promote gender equality in Disaster Risk Reduction and Climate Change Adaptation in the post-2015 development scenario in Bangladesh.

Mixed methods were applied to meet the evaluation objectives and comparing baselines & qualitative inputs. Therefore, a combination of sources of data (primary and secondary) has been utilized for the data collection. Among 10 districts; the project areas, final evaluation was conducted in 5 disaster-prone districts using a purposive selection method where the mixture of coastal districts, flood-prone districts and drought-prone districts was maintained. A total of 400 beneficiary women were interviewed through face to face interview. For qualitative data Key Informants Interview (KII), Focus Group Discussion (FGD), Observation, and Case Study for good/best practices were used and information was collected from partners & stakeholders i.e. representatives from relevant ministries, trust, national & international NGOs, UN, embassy and researchers & experts on gender and climate change.

In a nutshell, the project has succeeded in several ways. The trainings and hardware support provided to the beneficiary women have been really appreciated by them and women have started their journey on the way to self-sufficiency and prosperity. The climate vulnerable women have utilized the hardware support and made some positive changes in their livelihoods such as income generation, disaster preparedness, WASH etc. Almost all the beneficiary women who received trainings are utilizing the skills and knowledge earned through these trainings. The women have been made aware of climate change impacts in their lives and are encouraged to plant more and more and trees which is a very good initiative. The beneficiary women as well as the community people are now more prepared for any small scale disaster than ever before. They know well what to do when disaster will strike into their life. However; the overall sanitation and hygiene practice of the beneficiaries is still to be improved a lot. Even though the beneficiaries acknowledged that they have learned about these issues from discussions and trainings under the project, they are not applying them in practice which must to be investigated. The community women can more freely move in the areas than before and are more confident after engaging themselves into livelihood earnings but the issue of women empowerment and gender discrimination has not been improved much. In fact, there hasn’t been any significant change in the decision making role played by men and women at all levels. So there are more scopes for the project to intervene in this issue.

The project has significant impacts over policy/advocacy and stakeholder level. UN Women and the Bangladesh Climate Change Trust (BCCT) initiated a series of training workshops on Mainstreaming Gender Equality in Climate Change for government officials. The training programme acknowledges the need for and importance of gender responsive climate-smart development. With improved knowledge of and capacity in gender mainstreaming from the perspective of rights in climate change efforts, relevant actors are sensitized to contributing towards gender equality within their sphere of influence. UN Women has also developed the capacity of practitioners at government, UN, research organizations, and I/NGOs to mainstream gender equality in climate change adaptation, disaster risk reduction and humanitarian actions. Moreover; UN Women has contributed in the review of the existing and formulation of the new National Plan for Disaster Management (NPDM) of the Ministry of Disaster Management and Relief and in DRR & CCA area of 7th five year plan.

The project initiatives were undoubtedly relevant and appropriate according to local as well as national need, and have showered positive and effective impacts on the community overall. Now the sustainability of the project depends on how efficiently the beneficiaries utilize their knowledge, skills and grants received through this project. The project can be a role model for other government and private organizations who can take similar initiatives for the ultra-poor people of the disaster-prone areas of our country.

# Introduction

“When we went to the shelter home, all of our clothing was wet. There was no such environment so that we can change our dress. Finding no other way I, like other women there, spent the night with that wet clothing……………………………There were so many people in the shelter home and was only one toilet. The women couldn’t get scope to use the toilet because of the pressure of the men.”

The statement was published in a report of a daily newspaper on 17th December, 2015. It is from a female victim of cyclone Aila, occurred in 2009, of Huisenpara village of Kuakata Upazila under Patuakhali district. This is a very common scenario in the context of Bangladesh since it occupies fifth position in the world ranking of the most vulnerable countries to natural disasters (UNFPA World Population report 2015) and women are usually more vulnerable than men to all kinds of disasters and climate related impacts due to gender inequalities in various social, economic and political institutions in Bangladesh.

The number of natural disasters that took place all over the world in last two years broke all the previous records. Millions of people have become homeless because of these disasters. Due to natural disasters and wars (manmade disasters) the most vulnerable group are the children and the female groups. Women have limited access to and control over natural resources, or money and more importantly are less mobile and have limited access to information. This lack of access to resources and information along with less mobility make women more vulnerable to any type of disaster.

State of World Population 2015 titled “Shelter From the Storm- A transformative agenda for women and girls in a crisis-prone world” published by UNFPA shows that approximately 20.60 million women and adolescent girls have become unsheltered because of natural and manmade disasters in last two years. It also says that the mortality and sickness rate of mother, new born babies and children are the highest during disaster periods. In the years of 2014 and 2015, 75.0% of the victims, who needed humanitarian aid the most, belong to the female, children and adolescent group. In fact, usually 4.0% of the victims affected by disasters are pregnant women.

Moreover the natural disasters like floods and cyclones damage the economic livelihoods of women like livestock and poultry raring, fish farming, tree plantation, agriculture and animal fodder preparing. Increased salinity, after cyclone, decreases soil productivity and it’s difficult to plough wet soil after flood. Sand deposition as a result of flood and river erosion affects production of crops. As a result, there is a net loss in income, which in turn, leads to lower savings, thus making it even harder for households to save something against the rainy days and cope with disasters.

Like other developing countries, women and girls in Bangaldesh bear the burden of fetching water for their families and spend significant amounts of time daily hauling water from distant sources. The water from distant sources is rarely enough to meet the needs of the household and is often contaminated, such that women and girls also pay the heaviest price for poor sanitation. Given the changing climate, inadequate access to water and poor water quality does not only affect women, their responsibilities as primary giver, and the health of their families.

## Background

UN Women grounded in the vision of equality enshrined in the Charter of the United Nations, works for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security. UN Women (previously as UNIFEM) has been operating in Bangladesh since 2006.

UN Women is working to reduce vulnerability of women affected by climate change. In December 2011, with generous financial support (USD 2.88 million) from the Government of Norway, through the Royal Norwegian Embassy in Dhaka, the United Nations Entity for Gender Equality and the Empowerment of Women (UN Women) launched the project, “Reducing Vulnerability of Women Affected by Climate Change through Livelihood Options”.The project eneded in 2015. The overall development goal of the project is to increase access to sustainable and alternative livelihoods for women in communities vulnerable to the impact of climate change as well as to enhance their role as change agents to influence policies, strategies and programmes on climate change adaptation and mitigation measures. The expected outcomes to which the project contributes are:

Outcome 1: Gender-sensitive policy measures adopted to mitigate women’s vulnerability to the effects of climate change;

Output 1.1: Policy on social protection measures for women affected by climate change drafted.

Output 1.2: Enhanced capacity to form and use networks to advocate for gender equality to be integrated in climate change policies and programs (networks could include, for example, entrepreneurs from grass roots, local government functionaries, representatives from CSOs/NGOs, experts of gender and climate change and members of academia).

Output 1.3: Policymakers access necessary knowledge and expertise to mainstream gender into climate change policies.

Outcome 2: Enhanced economic opportunities for women living in areas vulnerable to the effects of climate change contribute to women’s livelihoods.

Output 2.1: Capacities of women vulnerable to, or affected by climate change, are strengthened to engage in various micro enterprises and green businesses.

Output 2.2: Organizational capacity of women vulnerable to climate change is strengthened to manage natural resources and enable access to available resources.

## Purpose of the Evaluation

The purpose of final evaluation was to demonstrate results achieved by the project and contributes important lessons learned in the areas of gender equality and climate change.

The evaluation was also targeted to feed learning into UN Women’s efforts to promote gender equality in Disaster Risk Reduction and Climate Change Adaptation in the post-2015 development scenario in Bangladesh.

## Objective of the Evaluation

Overall objective of this final evaluation was to cover all aspects of the project’s work both at a policy and institutional level and in the field since the beginning of it. The main objective of this final evaluation was to provide an independent assessment of whether the project has been implemented in line with the commitments given in the approved project document.

The evaluation focused on-

1. Relevance – the extent to which the project was consistent with and contributing to local and national development priorities viz. gender equality in disaster risk reduction and climate change adaptation and UN Women’s mandate.

2. Effectiveness – the extent to which progress towards project objectives have been achieved.

3. Results/Impacts – the positive and negative, and foreseen and unforeseen, changes and effects driven by project-supported interventions. Results include direct project outputs, short-to medium term outcomes, and longer-term impact including national benefits, replication effects and other, local effects.

# Methodology

## 2.1 Sources of Data

As proposed; mixed methods were applied to meet the evaluation objectives and comparing baselines & qualitative inputs. Therefore, a combination of sources of data has been utilized for the data collection. The sources of data were:

- Primary data from the target beneficiaries of grass-root communities & women and partners & stakeholders through quantitative and qualitative approaches.

- Secondary data through review of documents related to project (such as project log frame, baseline report, and other available evaluation report), local & national report on vulnerability of women affected by climate change.

## 2.3 Evaluation Population/Source of Information

Grass-roots level communities as well as the beneficiaries from 5 disaster-prone districts were targeted as primary source of information for the evaluation. Using statiscally significant formula, a sample size of 400 respondents for quantitative evaluation was drawn (details in next sub-sections). Moreover, the project sought to analyse and influence the policy environment to enable gender responsive programmes and strategies of climate change adaptation, mitigation and disaster risk reduction. Therefore, besides the beneficiary women, the final evaluation also targeted policy makers and forums that are discussing the country’s social protection framework, development plan (five year plan); sector specific plans have access to the necessary knowledge and technical expertise to address the needs of women affected by climate change. Consequently, study population/source of information was as follows:

- Project beneficiaries (women of different groups)

- Partners & stakeholders i.e. representatives from relevant ministries, trust, national & international NGOs, UN, embassy and researchers & experts on gender and climate change

## 2.4 Quantitative Method

For quantitative sampling; statistical formula was used and Face to face interviews were conducted using the semi-structured questionnaire with project beneficiary women.  There were 4 categories of beneficiary women groups in the evaluation areas based on the project intervention i.e. those who received leadership training, those who received livelihood training, those who received psychosocial training and other general members of the groups formed in each union.

### 2.4.1 Sample Size Calculation

The questionnaire survey was conducted among the target population of beneficiary women. To have a representative sample the following formula was used to capture all the target indicators.

| n=Z2pqe2×Deff | p = Expected value of the indicator= 50% q = (1- p) e = Margin of error = 5% Deff = Design effect =1 Z-score = 1.96 at standard of 95% confidence interval |
| --- | --- |

Thus, with the above assumptions the required sample size for the final evaluation worked out to be 385 which were then rounded to 400 project beneficiaries out of 19,100 for face to face survey at HH level.

### 2.4.2 Quantitative Sample Distribution

The programme was implemented in 80 unions of 40 upazilas under 10 disaster-prone districts. Among the 10 districts, final evaluation was conducted in 5 disaster-prone districts using a purposive random selection method where the mixture of coastal districts, flood-prone districts and drought-prone districts was maintained. In this regard; 3 districts out of 5 coastal districts, 1 district from flood-prone districts, and 1 from the drought-prone districts were randomly selected. Following are the area-wise sample distribution among the target women beneficiaries:

| Type | Name of Districts | Name of Upazilas | Name of Unions | Sample |
| --- | --- | --- | --- | --- |
| Coastal Districts | Patuakhali | Kalapara | Dholashar | 40 |
|  |  |  | Latachapli | 40 |
|  | Satkhira | Shyamnagar | Munshigonj | 40 |
|  |  |  | Gabura | 40 |
|  | Cox’s Bazaar | Teknaf | Sabrang | 40 |
|  |  |  | Nhila | 40 |
| Flood-prone District | Sirajganj | Raiganj | Brammagacha | 40 |
|  |  |  | Nalka | 40 |
| Drought-prone District | Natore | Sadar | Kafuria | 40 |
|  |  |  | Satni | 40 |
| Total |  |  |  | 400 |

Include Map

As per the programme design there are 10 women groups in each union. Each group consists of 25 beneficiaries among whom 1 woman received leadership training, 1 woman received psychosocial training and 5 women received livelihood inputs as well as livelihood trainings. Nielsen covered at least 4 groups in each union where 50 beneficiaries who received leadership training, 156 who received livelihood trainings and inputs, 25 beneficiaries who received psycho-social trainings and 169 general group members were interviewed.

### 2.4.3 Sampling Selection Procedure

Following was the sample selection procedure of the evaluation:

- The list of target population/beneficiary in the project areas were provided by UN WOMEN and BRAC. Nielsen used the list as sampling frame.

- From the list of target population/beneficiary of the mentioned 4 groups; eligible respondents were selected randomly.

- In case of non-response (for reasons like unwillingness, unavailability, etc.) the desired sample size covered ‘with replacement’.

## 2.5 Qualitative Method

Qualitative data provided such insights which might help further programme design. Therefore, different qualitative techniques were employed for collecting data from different types of target groups and stakeholders to have an understanding of the project impact. For qualitative data the following tools were used:

- Key Informants Interview (KII)

- Focus Group Discussion (FGD)

- Observation

- Case Study for good/best practices

Respondents for the qualitative calls were selected through purposive sampling technique. In that case; the individuals who were assumed to provide the key information regarding the study objectives was considered as a respondents. The sample distribution for the qualitative approaches was as following:

| Tools & Techniques | Target Respondent/s/Source | Sample |
| --- | --- | --- |
| KII | Representative from DDM | 1 |
|  | Representative from BRAC | 5 |
|  | Representative from BCAS | 2 |
|  | Representative from Royal Norwegian Embassy | 1 |
|  | Pioneer Researchers and Experts on Gender and Climate Change | 2 |
| Total KIIs |  | 11 |
| FGD | Beneficiary women | 5 |
|  | Direct and/or indirect community members at grass-root level (both female & male) | 5 |
| Total FGDs |  | 10 |
| Observation | Targeted 10 project areas | 5 |
| Total Observations |  | 5 |
| Case Study | Beneficiary women | 10 |
| Total Case Studies |  | 10 |

## 2.6 Secondary Data through Desk Review

Following are the list of documents has been reviewed during the final evaluation:

- UN Women Country Office Strategic Note 2014-2016

- Project Document

- Annual Progress Reports of the project

- Baseline on trends and impact of climate change on women in vulnerable areas

- Situation analysis identifying livelihood needs of climate vulnerable women

- Climate Change and Migration: Gender Perspectives

- Assessing the role of UDMCs especially the women members in mainstreaming GE

- Study Report on Climate resilient and empowering livelihoods for Women

- Policy briefs for mainstreaming gender dimensions in climate change policy dialogues and advocacy

- Reports on (i) focal point training, (ii) ‘costing methodology’ think shop report

(iii) High Level Meeting side event report, (iv) stories at UN Women websites on the project

# Findings

## Key Household and Beneficiary Information

Before implementing the project, research and a gender study of climate impacts on livelihoods was done in the project areas (coastal areas of Satkhira, Khulna and Bagerhat district on the south-west coast Patuakhali district on the south-center coast and Cox’s Bazar district on the southeast coast of Bangladesh, flood areas of Shariatpur, Sunamganj and Sirajganj, flood areas of Natore and Singra which have been affected by droughts and river bank erosion as well as other climate change factors such as nor’westers and autumn storms, hail storms and severe cold waves during winter).

According to the briefing sheet based on the research and a gender study of climate impacts on livelihoods performed, the coastal belt of Bangladesh is highly exposed to various climatic factors including variations in temperature, erratic behavior of rainfall, cyclonic events, droughts and salinity intrusion (Rabbani et al., 2013). These climatic factors are what make the lives of the coastal people vulnerable to climate change. Women from these coastal areas stated that they regularly suffered from more frequent cyclones, salinity intrusions, higher tidal surges, coastal flooding, extreme temperatures, lack of rainfall, or droughts, coastal erosion and water logging.

On the other hand, most of Bangladesh lies in the delta of three of the largest rivers in the world. These rivers have a combined peak discharge in the flood season of 180,000 m3/sec (the second highest in the world, after the Amazon) and carry approximately two billion tons of sediment each year. Floodplains occupy 80% of Bangladesh making it susceptible to river and rain water flooding and, in lower-lying coastal areas, to tidal flooding during storms (MoEF, 2009). According to the study, the women in the flood prone areas claimed that they faced more and sometimes earlier flooding, higher flood water levels, sudden floods and round the year river erosion. Some other climate factors such as erratic rainfall, hail storms, cold waves, fog and droughts in the summer are also prominent.

Again, droughts have become a recurrent natural phenomenon of northwestern Bangladesh in recent decades. Droughts in Bangladesh are seasonal and can devastate crops, causing great hardship to agricultural laborers. In recent decades, the hydro-climatic environment of north-western Bangladesh has been aggravated by environmental degradation. According to the study, the women in the drought prone areas are the most vulnerable to the impacts of climate change. Due to changing weather patterns and frequent disasters women face new challenges every day. They suffer prolonged and recurrent droughts, sudden hail storms, nor’westers, severe cold and fog during winter and floods and erosion due to erratic rainfall which aggravate shortage of fresh water, irrigation water, and shortage of fodder, diseases, pest attacks and most of all food insecurity.

From the effectiveness study done by BCAS, titled “Immediate Effectiveness of the Project ‘Reducing vulnerability of women affected by climate change through viable livelihood options”, it came out that before the project started, women in the areas were mainly confined to household duties and chores. While some women worked as day laborers, their numbers were very few. Growing vegetables on homesteads and raising poultry and cattle for eggs and milk were also parts of the daily lives of women in the areas. In Teknaf, in the district of Cox’s Bazaar, most of the women interviewed explained that they never disobeyed the decisions of their husbands. The Teknaf area is a heavily religious area, and several women said that a person in the area felt working outside the house was ‘going against religion’. Mossammot Begum from the Sabrang Union of Teknaf said, “My husband told me that if I went to BRAC’s meetings and got involved in their project I would become a Christian.”

So considering the situations of the project areas, the selection of project implementation areas seems completely relevant. The large women group vulnerable to frequently occurred natural calamities received assistance under the project which helped them not only to reduce their vulnerability to climate change impacts but also to improve their socio economic condition by adopting viable livelihood options.

The target respondents were aged 15 years and above for the final evaluation. This was not considered as any criteria for respondent selection. The beneficiaries were selected randomly where the youngest of all appeared to be aged 15. The average age of the respondents in the three evaluation areas ranges between 34-38 years. Most of the respondents came from the age group of 45+ years (24.75%) and 30-34 years (21.75%). (See table 1 in annex)

FGD with beneficiary women in Sirajganj

Among the 400 beneficiaries (of the project) interviewed, 78.75% were found to be married during the final evaluation; the remaining consist of widow, separated and single group of women. So the project reached out all types of beneficiaries who are really vulnerable like widow, separated and single and were highly in need of the project assistance. (See table 2 in annex)

In the survey questionnaire it was tried to find out what percentage of households are led by female heads. Among the targeted households, 77.50% of the household heads were male while 22.5% were female. (See table 3 in annex) The respondents had an average family member of 4-5 including 2-3 children per household. In terms of religion, majority of the respondents were Muslim (93%). Only 6.75% were Hindu women and 0.25% Christians. (See table 4 in annex)

Usually the village women are not expected much to be educated. Most of the rural girls in remote areas do not get chance to go to school and even if they somehow manage to go to school, their education ends mostly within the range of primary education. From the evaluation it came out that 36.75% of our respondents were illiterate, 20.30% were able to sign their names and 28.25% women either completed primary level of education or dropped out from school before completion. 14.0% read from class 6-10 while only 0.5% of the targeted women passed SSC (Secondary School Certificate) examination or similar examinations. (See table 5 in annex)

One of the goals of the project was to introduce the women beneficiaries with new viable livelihood options that will enable them to become self-sufficient and help them to become more disaster resilient. So the occupational status of the respondents is an important indicator in this evaluation. The highest percentage of respondents in all the evaluation areas mentioned homemaking as their primary occupation; in drought-prone area (Raiganj) the highest 77.50% respondents chose homemaking as their primary occupation while in the flood-prone area the lowest 25.0% respondents mentioned it as their primary occupation. Except from homemaking, respondents also mentioned about other income generating activities as their primary and secondary occupation. The livelihood options of the respondents will be discussed in a more detailed way in section 3.2 and 3.3. (See table 6 in annex)

From the quantitative survey it is found that 64.25% beneficiaries interviewed under the evaluation have monthly average household income between BDT 5,001 – 10,000 which is less than the amount found in Household Income and Expenditure Survey (HIES) 2010. As per HIES-2010; monthly income per HH in Bangladesh is BDT 11,479 and this income is for rural and urban areas are BDT 9,648 and BDT 16,475 respectively. More than one-fourth of the households had income below or equal to BDT 5,000. Only 7.50% households had income level between BDT 10,001 – 15, 000 and rest of the 1.75% households had income level between BDT 15, 001- 30,000. No household under the study in flood-prone area (Raiganj) and drought-prone area (Natore Sadar) had income above BDT 15,000 and only 1-5% of the households in these two study areas had income level between BDT 10,001 – 15,000 (See table 7 in annex). Comparing to the baseline study of the programme it is found that annual average income of the households has increased after the programme intervention significantly which is shown in the below table:

Comparison of annual income of households during baseline and evaluation

|  | Total income during Baseline 2011 | Total income during final evaluation 2015 | Increase in Income | Increase in % |
| --- | --- | --- | --- | --- |
| Male headed household income in BDT | 75, 673 | 90,072 | 14,399 | 19.03 |
| Female headed household income in BDT | 46, 985 | 65,040 | 18,055 | 38.43 |
| Household annual income in BDT | 71, 833 | 84,636 | 12,803 | 17.82 |

As the table shows, in all the three categories the total annual income actually raised in a significant portion compared to the baseline. The most interesting point is that in case of female headed households the annual income increased by the highest percentages (38.43%) after the project intervention whereas income of male headed households increased by 19.03%. It may imply that the beneficiary women are contributing to their household income with the help of their own earning wich became possible for the financial as well as technical support received from the project and those households that are run by female head may be utilizing their resources more efficiently since they can influence their household decisions more.

Income level indicates the socio-economic status of the households. The beneficiaries were also asked, according to them, at which socio-economic category they think they fall into. The following figure projects their responses:

Figure 1: Perception of Respondent on HH Class Wealth-wise (%)

According to the baseline, 42.25% households in the drought-prone area and 42.93% respondents in the flood-prone area said that they were very/extreme poor whereas from the above figure (after programme intervention) it is found to be 31.25% and 18.75% respectively which means in drought-prone areas extreme poverty is reduced by 11.0% and in flood-prone areas it is reduced by more than double. In coastal areas the situation hasn’t varied much though. So the extreme poverty level in the beneficiary households has been declined significantly and they now think them to be better-off than before the project intervention situation.

Observation 1:

Place: Shyamnagar, Satkhira

Observation Date: 13th December, 2015

Observation Starting Time: 11.00 am

Observation Ending Time: 4.00 pm

Mathurapur is a cyclone- and flood-prone and one of the poorest areas situated in Shyamnagar Upazila of Satkhira district. The major primary occupations in the area are farming, agricultural wage labour and food for work. It still has a low literacy rate and a poor transportation system. Although the main public road is comparably in a good shape, people still have to walk from their living place to access motorcycle, motor van and bus which are the main mode of transportation. Majority of the people use mobile phone, but number of people owning one is comparably low. A number of mobile shops exist in the area seeing to the demand of their communications need.

The social fabric in the village is still predominantly patriarchal with domestic violence being a daily occurrence and male household head being the sole decision maker in the family.  Dowry is another major problem in that area and has not improved much since the project started. It was understood from the visit and conversation with the community people that the project has worked in two major ways in the area resulting in women empowerment to an extent – one through knowledge transfer on self-efficacy and disaster preparedness and two, through asset transfer that has resulted in income generating activities for the women.

There is a disaster management committee in the area, but has been found to be dysfunctional with little knowledge on the issue and the local representative showed indifference in this regard as well. The project has provided hands-on training to the beneficiary women for emergency management for the next 2/3 years focusing on pre-disaster preparedness, coping during disaster and post-disaster activities. A discussion with the targeted women showed visible confidence among them on their capacity to deal with disaster situations. It was also understood from the visit and conversation with the community people that expressing opinions and instilling confidence among the women associated with the project was another major output from the project. In respect to violence against women, child marriage and domestic violence, the situation has improved notably since the project came into effect.

From quick discussions with the local community it was found that the project selected the poorest segment of the project area. We observed ‘Mathurapur Disaster Resistance Women Group’ which is the group of 25 beneficiary women of the project. They were provided with training on varied topics and 5 of the 25 women were beneficiaries of asset transfer that valued BDT 14,000 each. Two beneficiaries - Putul and Koushlya Rani had received incentives for starting grocery shop and currently have goods are BDT 28,000-30,000 in value. Anita has started ‘Crab Point’ with asset and her weekly income amount to BDT 800-1,500. On the other hand, Sita Rani is successfully running her tailoring shop. Another beneficiary Rahima launched her rice shop but discontinued later on.

## Capacity Building Activities

Grocery shop of a beneficiary woman in Sabrang

The “Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options” project covered 80 unions of 40 upazilas under 10 districts among which 5 were cyclone-prone or coastal areas (Khulna, Satkhira, Bagerhat, Cox’s Bazar, and Patuakhali), 3 were flood and flash flood-prone areas (Sirajganj and Sunamganj), and 2 were drought-prone areas (Natore and Chapainabaganj). In total 19,100 women were the direct beneficiaries of the project forming 768 groups in three eco-zones where the women were selected on the basis of being most vulnerable and highly affected by climate change who do not have access to any other programme or institution. Before the project began, awareness-raising programmes were held, mainly among the extreme poor people of each area. From these programmes potential female candidates were selected. After selection, an orientation program was held with the women. Each union contains 10 groups of beneficiary women and each group is comprised of 25 group members. Among 25 members 5 were selected for providing grants and livelihood training to start alternative livelihoods. Each woman was provided with a grant of 14,000 taka in the form of raw materials or assets like sewing machine, livestock, poultry, seeds, paddy, etc. so that they can start up a new business or become involved into new viable livelihood options based on their preference.

While the quantitative survey was conducted, around 72.0% respondents out of 240 in coastal areas said that they received training while 56.25% respondents in Raiganj and 37.50% respondents in Natore sadar out of 80 in each area said that they received such training under the programme. The beneficiary women mentioned about around 15 types of trainings. Mostly among the respondents of the quantitative survey, women received training on homestead gardening, small poultry, horticulture, tailoring, small business or shop, and cattle fattening. (See table 8 in annex) The figure below illustrates the comparative analysis of percentage of women receiving livelihoods or Income Generating Activites (IGA) training before and after the project.

Figure 2: Female members in households receiving IGA trainings (%)

As the figure above shows, percentage of IGA or livelihood training receivers have increased at significant level in all three areas after the project intervention compared to the baseline situation. For example, it was found during the baseline that in the drought-prone area 5.42% respondents received trainings on IGA activities (from other programmes) and during the evaluation 37.50% respondents said that they received such trainigns under the project. The percentage increases significantly imply that the selection of the beneficiaries under the project was appropriate since most vulnerable women were selected and majority of them did not come under any training sessions or other similar programmes.

After this training provided by BRAC, now we can earn something and contribute to the family along with our husbands.

-A beneficiary from Nhila, Cox’s Bazar

97.58% of the respondents who received training agreed upon the fact that the trainings contributed to better livelihood activities. On one hand the beneficiaries have become able to manage viable livelihood options with these trainings and financial grants which led to reduction of poverty and on the other hand their increased earning helped them to become more prepared for disasters incidents which led to reduction in their vulnerability to climate change impacts. While many of them earlier wanted to get involved with such activities, they couldn’t do so since they neither had the skill nor had the capital since they were the left out group from any financial support like micro credit and similar programmes.

Figure 3: Contribution of trainings (%)

According to 85.12% respondents out of 173 training receivers, these trainings increased their income; 63.64% women think that they have now increased access to more livelihood option and 28.93% women think that these trainings helped them to identify disaster resilient livelihoods. The women beneficiary group said in the FGDs that they spend their earnings for their family and children’s education. Some women have even opened DPS (Deposit Premium SCheme) with their earnings.

A women involved in tailoring in Dakkhin Patmora, Nhila

Beside alternative livelihood training, from each women group one woman was provided with leadership skills training and another one was provided with psycho-social training both of whom in turn trained the remaining women of the their group.

The leadership training focused on several issues like dealing with disaster situations, teamwork to accomplish tasks, teamwork during disasters, leading from the front through examples and guidance, respecting the opinions of others, etc. This training increased their confidence level to great extent and it raised the realization among them they can also play an important role during critical times. They can not only save their own life and family from disasters but others’ as well.  Kabita Rani Mandal, a beneficiary from Shyamnagar, said, “Before receiving this training I used to wait for other people’s help to save my and my children’s life during disaster periods. In fact my husband faced great difficulty to look after all the members of our family alone. But now in such situation I can provide immense support to my husband and try to help other people as well. This training also taught me how to convince other people in times when a unified decision making is needed on some issue”.

On the other hand, the psychosocial training taught them how to become more resilient to the common disasters frequently occurred in their areas, and how to help others become more resilient as well. The trainees came into learn from the training sessions how to keep oneself calm during stress, anxiety and disasters, how to counsel people affected by disasters, and the do’s and don’ts during disasters. “We are told to move the children, pregnant women, and aged people to safe place during disasters at first; pregnant women should be especially taken care of. We have to always keep dry foods, fuel, and light ready at home. As soon as any danger signal is shown, we should not be panicked, instead, we should immediately go to shelter home and take the livestock and poultry to safe place as well. Before going to shelter home, we must take dry foods and other necessaries along with us and dig some of the foods under the yard so that we can use them in case of emergency after the disaster is over”, a training receiver from Teknaf Upazila said. The training also raised awareness among the participants on violence against women and girls; it taught them to raise their voice against such crimes instead of silently accepting them as their misfortune.

Among the 400 respondents in the quantitative survey, 71.75% said that they received training on disaster management in the three regions. In the cyclone-prone areas, 78.75% beneficiaries received training on disaster management while two-third of the beneficiaries in flood-prone and drought-prone areas received such training.

Figure 4: Types of trainings received on disaster management (%)

N=287 (MR)

From figure 3 it is found that most of the beneficiaries in the cyclone-prone areas received training on disaster preparedness (94.18%) while almost half of the beneficiaries received training on rescue, health related issues and two-third of the beneficiaries received training on water purification and safe sanitation. In case of flood-prone area (Raiganj), 77.08% beneficiaries received training on disaster preparedness and 81.25% beneficiaries received training on health issues. Besides, 58.33% beneficiaries received training on rescue and 64.58% and received training on water purification and safe sanitation. In case of drought-prone area (Natore sadar), 81.25% beneficiaries received training on health related issues, 72.0% beneficiaries received training on disaster preparedness and 64.58% beneficiaries received training on water purification and safe sanitation.

Moreover, 77.08% respondents in cyclone-prone areas and 93.75% respondents in flood-prone areas admitted that special initiatives have been taken through this project for women to cope with disasters. In contrast, according to 97.50% beneficiaries in drought-prone area (Natore Sadar) no such initiatives have been adopted.

There are varieties of issues that the respondents mentioned regarding the initiatives taken by the project to cope with climate change and natural disasters. More than 25.0% respondents mentioned about creating awareness about carrying dry food and safe water during disaster periods; 14.50% respondents said that they have learned about taking people to safe shelter from the project; 11.07% respondents said that the project arranged training sessions for women to make them more disaster resilient and made them aware of climate change. Among the other initatives mentioned by the respondents were learning how to protect homestead and life from disaster, provided training on making house in higher places and raising the plinth of the houses, learning to keep cattle and poultry in higher places, created awareness on raising plinth of their houses, provided higher training to the women on life skill development, provided training on tree plantation, provided useful training on capacity building, provided training on post flood preparation, give financial help, helped to increase confidence through training, raising awareness on disaster management, and women, specially pregnant women, children, and older people should get first priority to take shelter.  (See table 9 in annex)

FGD participants in Sabrang, Teknaf

While conducting the baseline, the respondents mentioned about several barriers reducing their capacity of disaster preparedness. The most frequent problem stated by them was financial problem since absence of proper financial stability constraints them from saving to buy and store foods for times of crisis. Lack of awareness was the second prevalent cause. Among the other causes there were religious barriers, mismanagement, underdeveloped road, etc. During the final evaluation, respondents in the evaluation area were asked if those barriers to disaster preparedness have been reduced after the programme intervention. In the quantitative survey, 88.75% beneficiaries in cyclone-prone areas, 98.75% beneficiaries in flood-prone area and 93.75% beneficiaries in drought-prone area have admitted that the barriers to disaster preparedness in their family have been reduced after the programme intervention.

In the qualitative study, the beneficiaries said that they didn’t know that it is possible to reduce the amount of loss incurred by natural disasters to large extent following proper disaster preparedness and management plan. Earlier a disaster hit their area and used to destroy all their belongings, and take away thousands of valuable lives. Now they are aware of what to do when disaster comes and how to protect their lives and assets from these disasters. Women who are engaged into income generating activities can save a portion of their earnings for disaster periods. This increase in their awareness and saving capacity has reduced the barriers to disaster preparedness in their community. One participant in the FGD in Kazipur in Sirajganj during conducting the effectiveness study of the project said that during floods, her husband would take all the decisions, and more often than not, since he was not well versed on household matters, things would go wrong and they would lose a sizeable amount of their property to things such as river bank erosion. “After receiving the training from BRAC, I am now able to take sound decisions for myself and my family and now we are better off in this regard.” Shahida Begum stated that becoming economically independent has given her the confidence she needed to tackle the adversities of nature and the disasters that accompany the hindrance that is climate change. “I must admit that I did not know a whole lot about climate change and the impact it was having in our area and our lives. It was only during the project that I found out about it and was able to link all the changes including weather variations that were being observed in our region. Previously, I used to think that people are incapable of shielding themselves from the bad impacts of these adversities, but now I know that a little preparedness can help you not only cope through them, but also stand back on your feet quite easily after they are gone.”

Besides providing training to beneficiary women on disaster management and psycho-social issues, the representative UDMC members of selected unions were also provided training which was aimed at providing female members capacity building training and making them realize the importance of their own and other female members’ participations. The women now are able to raise their voice during meetings of respective UDMCs. The male members who took part in the training have become much more cooperative to female members, and are taking steps to ensure that all other male members of the committee also do the same. They have already put their training into action and initiating activities in their communities through their UDMCs that might benefit the women in their communities.

Case Story

Setara Begum, Teknaf

I have 5 members in my family. From last few years, my husband could not work due to having an injury in his leg. Moreover, due to various climatic disasters, my family was suffering a lot from poverty. We couldn’t even have a proper meal some days. Under such circumstances, I took training from BRAC.  I learnt many useful things like- how to start a business, how to make caps, how to cultivate vegetables and how to protect ourselves during a disaster from that training. We started a grocery shop with the money we got from BRAC after that training. And after meeting up all the needs of my family, we managed to buy a auto-rickshaw from the money we earned from the grocery shop. This auto-rickshaw is helping our family a lot. I would like to mention about the training on disaster preparedness. We learnt how to take our cattle in shelter, how to protect our homestead and assets etc. from that training. Now I know how to start fresh even after a disaster.  This project has made us self-dependent and self-sufficient.

Observation 2:

Place: Kalapara, Patuakhali

Observation Date: 15th December, 2015

The study took the endeavor to observe the changes in the lives of the community people of Tolatoli village of Kalapara Upazila, Patuakhali. It was found from the activities and discussion with the community people that they were benefitted through the training on disaster preparedness and asset transfer for viable livelihood options. They have showed increased level of awareness on women’s rights and empowerment, child marriage and domestic violence as well as on risk mitigation during disaster situations and rehabilitation after the disaster. People were pleased with the selection of ultra-poor as beneficiaries in the project scheme and have shown skill in employing the training lessons through getting involved in economic activities that include goat farming, tailoring and running grocery shop.A great amount enthusiasm was observed among the community where the project took place to get involved and change their economic and social standing and they asked for taking up more such projects.

## Improvement in Beneficiaries’ Socio-economic State

As described in the previous section, the beneficiaries under this project were also given such supports and the success rate is found to be almost 100.0%. As the respondents in the quantitative survey during the evaluation were asked if they or any female member of their household is involved with income generation or livelihood activities, 90.42% respondents in coastal areas, 90.0% respondents in flood prone area and 61.25% respondents in drought prone area said that they are involved with IGA activities. The income generating activities of the respondents are listed below with along with percentage.

It is found through the quantitative survey that the beneficiary women and/or other female members of their family are involved with a wide range of income generating activities. There are total 24 types of activities mentioned by the respondents (See table 10 in annex). Most of the respondents are involved with small poultry, homestead gardening, small poultry, tailoring, livestock rearing, small business and horticulture. Some work as day laborers and handicraft producers. Others are involved in different activities like dry fish processing, agriculture, cap making, fishing, etc. Area wise there isn’t much variation but in Raiganj Upazila most of the women are involved in tailoring and small business while in the three coastal areas small poultry and homestead gardening is much practiced.

If someday my husband fails to earn anything, I arrange the meal for my family with my own earning.

-A beneficiary from Nhila, Cox’s Bazar

I was given 3 goats. The goats gave kids. Now I have 7 goats. Now I earn more money than before.

-A beneficiary from Shyamnagar

The figure below illustrates the comparative change in percentage of women involved with income generating activities (IGA) and livelihood earning between the baseline and end line evaluation.

Figure 5: Females involved in household IGA & livelihoods

As the figure above shows, except from involvement in IGA by beneficiaries in the drought-prone area (Raiganj Upazila), all other percentages for both the indicators have increased at significant level after the project intervention compared to the baseline.

Tailoring shop of Amina Begum in Sirajganj

The monthly income level of the households, number of earning members in the family are important indicators of the current socio-economic status of the respondents. On an average, there are 2 income earning members in the beneficiaries’ households (See table 11 in annex). The interpretation becomes clear from the statements of the respondents in the qualitative study. According to Laila Akter from Nhila union of Teknaf Upazila, “Previously I used to depend on my husbands’ income for all the household expenditures. If he fell sick or didn’t go to work any day, the whole family had to keep fast for that day. But now, after I’ve got livelihood support from BRAC (which was the implementing partner of UN Women in this project), I earn myself 1500-2000 taka per month and can support my husband in bearing our family. If someday my husband fails to earn anything, I arrange the meal for my family with my own earning.” All other respondents in qualitative study agreed with Laila Akter at this point. So the livelihood support provided to the beneficiary women through this project has played a vital role in increasing the number of income earning members in their respective families which in turn reduced their poverty level.

Shop of a beneficiary woman in Ali Akbor Para, Nhila

Figure 6: Spending of earning (%)

The figure shows that most of the women still hand over their earnings to the male member of their family. On the other hand, it is also noteworthy that more than half of the women are re-investing their earning in the livelihood activities, either in the same activity or in some other activity. This means that the women are trying to continue the prosperity they achieved through these livelihood options. They are trying to improve their economic condition more. And this will enable them to become less vulnerable to climate change impacts than before.

Now the beneficiary women save; earlier they couldn’t even imagine about maintaining any savings after all their monthly expenditures.

-KII with PO in Kalapara

When people earn more, they tend to save more. So savings is an important indicator to see whether the beneficiaries are on the way of achieving economic prosperity or not. As the beneficiaries were asked if they have any savings, 11.25% beneficiaries said that they do have savings. In the flood-prone and drought-prone areas 22 beneficiaries said that they have savings while 57 beneficiaries in coastal areas said that they have savings. The figures might seem too small but the saving scenario of the beneficiaries was even worse before the project intervention which is reflected from a concerned PO of the programme area during KII while mentioning about the positive effects of the project who said that women now have a tendency to save. Before the project intervention neither they had the ability to save nor they realized the need of savings. But now the women have become much more conscious and have started this savings practice. And this has been possible because the beneficiary women are now able to support their husbands in earning their livelihood and they contribute to their family earning which creates surplus which is further turned into savings.

We, the community women, contribute 10 taka each week to raise fund so that one day we can use it for a greater purpose.

-Participant in FGD in Dhulishar, Kalapara

Out of 79 beneficiaries who said that they have savings, 67.09% of the beneficiaries have saved for the purpose of their children’s education and 41.77% for their children’s marriage. Around one-fourth of the beneficiaries have saved money as precaution to reduce vulnerability – this purpose is found to be the highest in cyclone-prone areas (33.33%) (See table 12 in annex). So saving for disaster risk reduction or vulnerability to disaster is practiced in the communities though in lower percentages. But since the project has made the beneficiary women more aware of the climate change and the incidence of various natural disasters as a result of climate change, the community people now at least feel the need for maintaining a part of their earnings as savings for the purpose of disaster preparedness. As the practice of maintaining savings for disaster preparedness and management has been initiated among the beneficiaries, a larger portion of the community people is expected to do the same following the others. And this is the part where the programme hits its goal- growing realization among the beneficiaries as well as other community people to save for disaster preparedness which can play a vital role in reduction of their vulnerability to climate change impacts like frequent small scale natural disasters. As their income will rise, the percentage of saving practices and amount of savings is also expected to rise.

The respondents were also asked if they received any credit during last 12 months. Almost 87.0% of the beneficiaries have not taken any credit/loan in the last 12 months which indicates the improvement of their socio-economic condition; they are no more dependent on the credit sources of Mohajon, Dadon, Foria, etc. which actually croak all their belongings instead of doing any good to them.

Case Story

Layla Khatun, Shyamnagar

I used work as a day labourer before Aila (cyclone). After Aila, I lost my house. I did not receive any relief even. One day some project personnel suggested me to go to Munsiganj and attend a meeting. In that meeting, we were taught about water and sanitation, how to boil water etc. After 25 days, I was given paddy worth BDT14000. I learnt how to make rice from paddy and did so after going back home. I started selling rice and saving money for myself. In last 3 years, I managed to knit a fish net and a boat. I made the fish net from the money I received by selling rice. I started fishing and selling fishes. Now I can earn up to BDT12000 per month. I also received training on disaster preparedness. Now I know how to take shelter in a higher place, how to keep important papers in safe place, how to keep house clean after a disaster etc. I also learnt about women empowerment from these trainings. Now we can earn and our husbands also value us. My family helps me in various household works. We are very happy now.

Observation 3:

Place: Natore Sadar, Natore

Observation Date: 13th December, 2015

Observation Starting Time: 11.00 am

Observation Ending Time: 4.00 pm

Kafuria and Satni are two drought-prone unions in Natore district though the frequency of drought has decreased in recent years. These two areas are comparably less-populated and people have been observed to be modest and peace-loving. Transportation is an easily available facility here with auto-van and CNG being the best mode of conveyance. People also enjoy electricity and mobile phone services in the area.

This observation was aimed at understanding the changes that took place as an effect of the project input. Conversation with the community gave us the idea that a number of non-profit organizations including the project intervener have been working in the area for a long time and have contributed in the transformation of the conservative and patriarchal social fabric of the region. People have shown contentment in decreasing cases of domestic violence, child marriage, murder and rape in the area. Children from every family in the area go to school and the parents have shown increasing awareness for their children’s education. Women are enjoying relative economic independence as well as freedom to make decisions. They have also talked about relative social acceptability as an impact of the awareness projects. Majority of the women in the two unions are involved in income generating activities through livestock and poultry farms as well as small shop. Dowry has been identified as the only major problem which has not improved much since project inception.

The community showed high level of satisfaction in terms of the process of selecting beneficiary for the project as it ensures that the ultra-poor receive the benefits. A meeting with one of the 5 beneficiaries of the asset transfer facility revealed that she was happy with the services provided by the project intervener. She received a sewing machine as an asset as well as training to start her own business. She is now contributing financially to her family’s well-being. The women under this project are receiving training on disaster management through regular yard meetings provided by the project intervener. These trained women are involved in successive awareness meetings with their peers and other women in the neighborhood and is successfully raising awareness on emergency management and their rights. Although almost all of them complained of non-cooperation from the government during disasters, they have expressed contentment with the training received from the project as it has made them better to deal with it.

## Improvement in Knowledge and Existing Practices

As it is already mentioned in the project background, one of the expected outcomes of the project was to strengthen the organizational capacity of women vulnerable to climate change so that they can manage natural resources and enable access to available resources in their locality. The respondents in the quantitative survey during the evaluation were asked if they utilize the natural resources available in their area. About 88.50% of the beneficiary women said that they utilize natural resources (minerals, tress and forests, river/pond/natural springs, stone/soil/sand etc.) in their respective areas. The major purposes for using natural resources mentioned by the respondents have been shown in the following figure:

Figure 7: Purposes of utilization of natural resources (%)

Homestead gardening done by a beneficiary woman in Sirajganj

As the figure shows, almost all of the respondents in the three research area mentioned about household purpose. In cyclone-prone areas (Teknaf, Shyamnagar and Kalapara) nearly half of the respondents mentioned about income earning activities while in flood-prone area (Raiganj) more than three-fourth of the respondents mentioned about it. In both of the cyclone-prone and flood-prone areas around one-fourth of the respondents mentioned about the purpose disaster management. On the other hand, in drought-prone area (Natore Sadar) no respondent mentioned about disaster management whereas only 12.50% respondents mentioned about IGA activities. Participants in the FGDs said that through the courtyard meetings and discussion sessions they have become aware of how they can use the various natural resources scattered around them for household chores as well as for income earning activities and disaster management purposes while not degrading the environment. They were not concerned about preserving natural resources before like planting trees. Now they know that planting more and more trees is necessary for environmental protection and deforestation is highly responsible for climate change which in turn results into frequent natural calamities. So now they are more conscious of planting trees and protecting them as well.

Another expected outcome of the project was to enhance economic opportunities for women living in areas vulnerable to the effects of climate change to contribute to women’s livelihoods. During the quantitative survey, 95.75% women said that women in the study areas are involved in different income generating activities.

In total the respondents mentioned about around 22 types of IGA activities. The leading income generating activity in the study areas is livestock and poultry farming with 69.45% of women mentioning about it. Other major income generating activities include tailoring (69.45%), handicraft (54.05%), food for work (42.82%), small shop (39.16%) and small business (19.84%) (See table 13 in annex). Out of the first five income generating ways that obtained highest percentages, four of them are those on which activities the project provided training to the beneficiary women. Besides, a significant percentage of women also mentioned about rice processing, crab fattening, etc. on which the project provided training as well. So the project actually helped the community women get out of the boundary of their house and become involved in IGA activities that not

Livestock rearing by a beneficiary woman in Sirajganj

only can contribute to economic prosperity but also can play a vital role in reducing their vulnerability to climate change impacts.

Women are more vulnerable to the effects of climate change than men—primarily as they constitute the majority of the world’s poor and are more dependent for their livelihood on natural resources that are threatened by climate change. Furthermore, they face social, economic and political barriers that limit their coping capacity. Coupled with unequal access to resources and to decision-making processes, limited mobility places women in rural areas in a position where they are disproportionately affected by climate change.

Since women fall under the threat of climate change more than the men do, they must know about it and its overall impact on their lives so that they can take preventive measures before any serious hazard shatters their life. While the evaluation was conducted, 96.0% of the total respondents claimed that they have heard about climate change. Analyzing the baseline study it is found that 89.47% respondents knew about climate change so the knowledge level increased by almost 6-7% in last three years. The following figure illustrates the different sources from which the respondents came into know about climate change impacts.

Figure 8: Source of knowledge about climate change

N=385 (MR)

The above figure illustrates that more than 90% of the respondents heard about climate change from NGO workers (not necessarily from UN Women partner NGO but also from other NGOs working in those areas) while during the baseline study 83.63% respondents who knew about climate change impacts said that they came into know about it by their own observation. There was a time when these people depended solely on their past experience and observations for any kind of prediction regarding climate change and natural calamities but now they are able to receive more reliable and accurate information from NGO services.

While the respondents were asked if they found the project helpful in any way to recover or prepare themselves in advance from the climate change impacts, 89.75% respondents in total felt that the project has helped them to recover or prepare in advance for climate change impacts; in the drought-prone area (Raiganj) almost 99.0% beneficiaries think so while in the other two regions around 90.0% beneficiaries think so. In the qualitative study the beneficiaries said that many of them received training on disaster preparedness under the project. They are told during the training sessions what to do when disasters come like going to safe shelter with family, to pack valuables, to keep polythene bags, etc. They are also told to raise the plinth of their houses to prevent them from going under water. They are suggested to take their livestock and poultry animals to a safe place (Killa) before any disaster strikes. Those who received trainings shared their learning with other community people. Thus the community people are now better prepared to face frequent and small scale natural disasters than ever before. And they are confident if any natural calamity suddenly bursts upon them, the loss that may occur will be less than before.

A Disaster Management Committee (DMC) plays a vital role in the community at all stages of disasters. It is a responsibility of a DMC to perform and monitor all the tasks from making the community people aware about the coming disaster to take them to safe shelter and providing them all kind of assistance in recovering from the disaster impact. As the respondents were asked, 80.83% respondents in the cyclone-prone area and 66.25% respondents in the flood-prone area said that there exists disaster management committee in their respective areas. But in the drought-prone area (Natore Sadar) 95.0% respondents said that they have no DMC in their community while there must be a DMC in each union formed by government. This implies that the UDMCs in the respective unions are not well-functioning since most of the community inhabitants are not even aware of their existence.

On the other hand those who said that they have DMC in their respective area were asked about the role played by the DMC at different stages in disaster periods. The figure below illustrates the result.

Figure 9: Initiatives taken by the Disaster Management Committee (%)

N=251 (MR)

According to most of the respondents who said that disaster management committee is formed in their area, DMC makes everyone aware of disaster when it tends to come. In the cyclone-prone areas 78.35% respondents and in flood-prone area 67.92% respondents said that DMC helps them to go to shelter home but in drought-prone area no respondent mentioned about this activity. Same is the case for relief distribution; no respondent in the drought-prone area mentioned about relief distribution by DMC while 35.57% respondents in cyclone-prone areas and 20.75% respondents in flood-prone area mentioned about it. Nearly one-third of the respondents in cyclone-prone areas as well as flood-prone area said that they received financial help from DMC while all of the respondents having DMC in their area said that they received financial help from DMC.

A dynamic initiative taken under the project was to arrange periodical courtyard meetings with the beneficiary women group in each union so that they can discuss their problems and share their insights and ideas, plan, and activities they are practicing with each other. The objective of initiating this meeting is to keep the beneficiaries in touch with one another and to sustain the project impacts in the community so that the beneficiaries can identify and solve their problems by themselves through discussion. During the quantitative survey, 88.0% respondents said that their community had periodic courtyard meetings. In Raiganj and Natore Sadar almost 100.0% of the beneficiaries said that they had courtyard meetings whereas in the coastal areas around 82.0% beneficiaries said that they had courtyard meetings. And those meetings are held mostly in monthly basis.

As the beneficiaries were asked about the topics usually discussed in the courtyard meetings, they mentioned about variety of issues.

Figure 10: Topics discussed in the monthly courtyard meetings (%)

Figure 11 demonstrates that more than 92% beneficiaries mentioned about WASH (Water, Sanitation and Hygiene) issues followed by DRR (Disaster Risk Reduction) (86%), and raising awareness on VAW (44%). Though small in percentage, some respondents in coastal areas and Natore Sadar mentioned about issues like child marriage, dowry system, income earning method, poultry, cattle breeding, AIDS, etc. as well but in Raiganj no respondent mentioned about any of these issues. In Raiganj a large percentage of respondents mentioned about raising awareness against VAW (67.50%) compared to the other two regions.

According to the beneficiary women in FGDs, they sit in monthly courtyard meetings for nearly 2-2.5 years which is initiated by the project concerned authority and a coordinator from the programme in their respective areas regularly monitor this meeting. Saleha Akter, a beneficiary women in Nhila, Cox’s Bazaar said, “We have become aware of health and sanitation, childcare, etc. issues through these meetings”. Khurshida Begum from Kafuria said, “We have learnt in the courtyard meetings about domestic violence against women. We have also learnt what to do if anyone falls under acid attack. Awareness on different issues like land, rights and responsibilities, hygiene and sanitation, etc. are also discussed in the courtyard meetings”.

There is no doubt that the initiative of monthly courtyard meetings is really a good one. Those who received trainings on leadership building, psycho-social issues, and livelihood options, share their learning with other community women in these meetings so that other women may bring improvement in their situation by following them. The women share the discussed topics with other women who were not present in the meeting. So the meetings play a fruitful role in spreading the knowledge earned by the beneficiary women through the project, for instance, if someone adopts a good technique in livelihood earning or builds sanitary latrine in her house other women can follow it as well. It also enabled the beneficiary women to continue and, in fact expand, the progress made through the project even after its termination.

The respondents were asked some questions about their practices regarding their use of source of collecting waters and latrines to find out the increase in their knowledge and awareness about WASH issues after project intervention. The following figure shows the sources of drinking and domestic water used in the beneficiary households and the later shows the types of latrines used by them.

Figure 11: Sources of Domestic and Drinking Water (%)

52.50% of the households under evaluation in cyclone-prone areas use deep tube well while 36.67% use shallow tube well. In the flood-prone area 93.75% households under evaluation uses shallow tube well for the purpose of drinking and domestic water; deep tube well water is used by a very small percentage of beneficiaries. In the drought-prone area 71.25% households under evaluation uses shallow tube well and 28.75% households uses deep tube well. The baseline shows that 46.53% households in coastal areas had access to deep tube wells while the percentage has increased to 52.50% after project intervention. On the other hand, the access to shallow tube well by the beneficiaries has been increased compared to the baseline in all the three evaluation areas. Use of surface water has been decreased to 33.33% in the coastal areas compared to the baseline value (39.90%).

Figure 12: Types of Latrines Used in the HHs (%)

The sanitation condition in the project areas is still quite poor. Around 16.0% beneficiary households use safe latrines (Ring slab (water sealed), Septic latrine and Pit covered deep latrine) while around 70-75% beneficiary households use unhygienic latrines.

It is to be noted that beneficiaries during FGDs said that they have been taught about wash, sanitation, and hygiene issues by the programme representatives of their respective areas. They have been told to use safe latrines and drink safe water, to wash hands after defecation and before having meal, etc. They have also been told to keep their house and yards clean and dry. In fact they said that they share these information with other people of their community. So it is a dichotomy that the beneficiaries are acknowledging the learning they have obtained from the project but not implementing them in practice which demands further investigation in the evaluation areas regarding these issues.

Results of the quantitative survey says that almost 100% women beneficiaries in Raiganj and Natore sadar feel that the climate change/disaster risk has been reduced through new kind of livelihoods whereas around 80% respondents in the three coastal areas under evaluation think so. Nearly three-fourth of the respondents think that this programme has made women aware of the climate change impact while nearly half of the respondents think that the programme has managed new livelihood options for women. 32.75% women beneficiaries think that it has established participation of women in climate risk management and it has formed new small entrepreneurs. Besides, 10.25% women think that the programme has established participation of women in local government activities as well. (See table 14 in annex)

Observation 4:

Place: Raiganj, Sirajganj

Observation Date: 14th December, 2015

Situated near the Naf River, Nhila is a major cyclone-prone union in Teknaf Upazila, Cox’s Bazar. River erosion is another major problem contributing to the worsening poverty scenario in the region. Our area of study was Ali Akbar Para in this union with majority of people living below poverty line and unplanned construction of houses in the village. The major occupations of the people are digging, fish farming and salt cultivation. The area is characterized by low living standard, illiteracy and diseases and the situation has worsened with easy availability of drugs. Cyclone, which is a regular disaster phenomenon, has negative effects not on the livelihood of people but also on their psychology, particularly on the women and children. We learned through talking to the women that the situation has improved a bit in last two years with the trainings they have received through project. The project was successful to some extent in terms of providing economic independence to the beneficiaries. People in the area also believe that they are now capable of dealing with cyclone due to the training provide on disaster management.  We also observed satisfaction among the community with the training provided on viable livelihood options to them.

But more projects are being recommended for Sabrang, Ali Akbar Para, South Patmora Para, Nikon Ghali, Katabonia and other neighboring areas for two reasons – one, the number of poor living in the area and in need of help is greater than the project beneficiaries and two, the women are still vulnerable due to lower rate of education, child marriage and dowry. There was lack of government activities for economic development as well as disaster management in the area.

## Changes in Decision Making Role and Social Security Situation

The aim of the project was not only to make the beneficiary women less vulnerable to climate change impacts through introducing them with viable livelihood options but also to establish significant role to play in decision making of the household issues as well as in disaster preparedness and management by them. Since the women have received different trainings on disaster management and viable livelihood options and have become self-sufficient with the financial support they received under the project, it is reflected in their roles played in home and outside as well. Their voice is no more suppressed under the male voices of the family. Their decisions are in fact valued by their husband and in laws. They have gained the strength to raise their voice against any injustice done to them and are able to fight for their own rights and dignity. This is not a mere interpretation but a fact that has been expressed by the beneficiary women themselves during the qualitative study. Some changes in the decision making role in the households are apparent in the tables presented below.

Roles played in meeting up food deficit according to sex (%)

| Different Periods | Male | Female | Both | N/A | N |
| --- | --- | --- | --- | --- | --- |
| Normal period | 20.5 | 32.75 | 45.0 | 1.75 | 400 |
| Disaster period | 17.5 | 27.5 | 53.0 | 2.0 | 400 |
| Post Disaster period | 17.0 | 29.0 | 52.0 | 2.0 | 400 |

During the baseline, the respondents were asked who usually played decision making role in mea preparation, meal distribution, and meeting up food deficit. It is found that in case of meal preparation and distribution, the traditional role playing is followed where women are mainly assigned to these tasks by default. In case of meeting up food deficit percentage of women have been found to be more than the percentage of men in all three cases (normal period, disaster period, and post-disaster period) while most of the respondents said that both of them take part in this task. So male members of a family are no longer the sole bread earner of the family; women share this responsibility equally.

In terms of household and communication decisions, women in rural areas are not usually permitted to give their opinion in important decision making like choosing occupation, getting their children married, children’s education, conceiving a baby, etc. because of the patriarchal societal structure of our country. But in the areas where the evaluation took place was found a radical change in this type of decision making pattern. Most of the respondents in the quantitative survey during evaluation said that household decisions regarding engaging in new income generating activities, giving marriage, conceiving baby, use of savings, and obtaining VGD/VGF are usually taken by both of the male and female members of the family. In fact, except from conceiving baby and male going to work, all other decisions in the list shows that the percentages are higher for those who think that the decisions are taken by mainly female members than those who think that the decisions are taken by the male members (See table 15 in annex). From the qualitative study it came out that this change has become possible because of the increasing participation of women in outside and income generating activities arranged under the project. This project has made them not only less vulnerable than before but also made their way to become more self-reliant smoother.

Figure 13: Roles in family regarding disaster related issues (%)

In case of disaster related issues like going to shelter home, engaging in new livelihood opportunities, collecting relief materials, etc., most of the respondents said that both male and female members of their family take part in these activities and higher percentages of respondents think that women usually carry out these tasks than the respondents who think that men usually do these tasks in all the evaluation areas (Note: The figure only consists of the replies those responded to the question; the remaining percentages go to the Not Applicable (N/A) category). From the baseline record it is found that only 11.48% women in total actually played role in such kinds of activities. So women are now, after the project intervention, more involved into pre- and post disaster activities. Very few percentage of women now depend on the help of the male members of the family while most of them, in fact, look after themselves as well as their family during disaster times.

During the quantitative survey the pattern of ownership of household assets according to sex was tried to be explored whether any change in it has occurred. The result is shown in the figure below.

Figure 14: Comparative scenario of ownership of household assets by male and female members of family (%)

As it can be seen from the above figure, almost all the domestic assets (listed in the survey questionnaire) owned by the households are mostly under male domination. A few exceptions are like 45.0% women in Kalapara and 41.25% women in Natore Sadar had the ownership of poultry while 31.25% women in Shyamnagar had the ownership of livestock; 36.25% women had the ownership of their house (Table 16 in annex). The statistics imply that though the beneficiary women said during the qualitative study repeatedly that they have now greater access to household decision making and outside home activites, there is very little change in their ownership of primary household assets which means that the women folk are actually okay with this pattern of asset ownership and they have taken it for granted that men should be the owners of these assets. But it is also to be noted that the listed household assets are mostly long term assests that are consumed for a long period (that is, these assets were perhaps purchased before baseline and still being used) and the project lasted for only three years starting in 2011. So it is a very short period in which it is quite impossible to reverse the pattern of household asset ownership in significant percentages. The beneficiary women have just boarded on the journey to earn their own livelihood and become self-relient. So it is natural that they it would take time to establish women ownership on these household assets. If the women utilize their skills and earnings in a proper way, it would not be possible for them to buy the household assets with their own earning.

Though any major disaster didn’t take place during the project period, the respondents were asked about the problems mostly faced by the women during and after disaster periods to capture a comparative picture between the before and after state of the project beneficiaries. Based on the received results, a comparison is made between the baseline where the respondents mentioned about the problems faced and final evaluation where the respondents said that they now think that they would face these problems. The percentages have been decreased by significant level in case of most of the indicators. The comparison is shown in the table below.

Problems faced by community women during and after disasters (%)

| Indicators | Baseline value | End line value |
| --- | --- | --- |
| Water and sanitation problem | 96.70 | 63.90 |
| Insecurity | 69.57 | 55.60 |
| Healthcare problem | 84.76 | 29.96 |
| Domestic violence | 37.95 | 5.78 |

The percentages of women who thought that they would face water and sanitation problem during disasters has been reduced by almost 33.0% while in case of insecurity it has been reduced by around 15.0% and in case of domestic violence it has been reduced by nearly 32.0% compared to the baseline value. Percentages of women who thought that they would face healthcare problem has been decreased drastically by 54.80%. The beneficiary women said while participating into the FGDs that they have been made aware of the security and safety issues of women during the disaster periods. They now take extra care of pregnant and aged women in disasters times and pay especial attention to children and adolescent girls. They have also been made aware of different water borne diseases that break out especially in the post-disaster periods. They have been told to keep their courtyard and house clean and dry, and to drink purified water so that they do not fall sick. These lessons provided through the training sessions and courtyard meetings helped enabling the community women go through less social insecurity problem as well as health problems during and after disaster time which actually made them less vulnerable to climate change impacts than initial stage.

## Impact on reducing gender discrimination and violence

The women in our country often face discriminatory behavior by the society and even sometimes in their family. Incidents of violence against women in our country like acid throwing, domestic violence for dowry, rape, eve teasing, etc. have become very common news of the daily newspapers. Gender discrimination is faced by them at every stage their life. The women in rural areas go through these problems more frequently as they are usually less educated and therefore less empowered. The lack of their participation in income generating activities makes them more vulnerable to violence. In addition, prevailing prejudices of the rural society have awarded the male members of a family a superior position to the female members by birth.

FGD in Natore

The respondents in both the quantitative and qualitative study were asked if they face any kind of discrimination in receiving their payments while selling their goods or production in the market. In the quantitative study, around 52.0% respondents in the coastal area and 72.50% respondents each in Raiganj and Natore sadar said that they do not face discrimination. In case of getting actual price of the self-priced commodities, around 83.0% respondents in coastal areas and more than 90.0% respondents think that they get the actual price. In the qualitative study the participants said that they faced gender based discriminatory behaviour at home as well as in society much less than before. According to them, they can now move freely in their community and go anywhere as they wish. They no more feel inferior to their male counterparts. In fact, they now act as strength for their husband. As discussed before, the discrimination between men and women is deep rooted in our societal structure which is difficult to be completely eradicated within one or two years. But the progress made during last three years is praiseworthy.

During quantitative evaluation, the respondents were asked if they experienced any incident of violence against women in their community in last 1 year.

Figure 15: Experience of violence in community in last 1 year (%)

I could get the opportunity to go to school but I want my daughter to be educated. That’s why I spend my earnings for her education.

-A beneficiary from Shyamnagar

37.92% respondents in cyclone prone areas, 61.25% respondents in flood prone areas and 68.75% respondents in drought prone areas said that they have observed such incidents in their community. Among these respondents, more than 80% respondents in all the study areas mentioned about torturing by husband, around half of the respondents mentioned torturing by in laws, and one-fourth of the participants mentioned torturing by family members (See table 17 in annex). Around 12.0% (48 out of 400) respondents, in total, said that they have faced violence in their own life during last 1 year and among these 48 respondents again 79.59% mentioned about torturing by husbands. While conducting the qualitative study, beneficiaries said that domestic violence against women has declined in their community significantly. Decline in child marriage has also declined radically. Through the meetings and discussion sessions, the project personnel have made aware of the eligible age of girls and boys to get married, and the consequences faced by girls as a result of early marriage. So now they realize the demerits of getting their children married at an early age. In fact many of the beneficiary women said that they spend their earnings on their children’s education. But the tradition of giving and taking dowry hasn’t been diminished yet. No marriage takes place without dowry and the situation is the same for all the three areas. “The representative from BRAC has prohibited us to give and take any kind of dowry; it is prohibited by law and those who demand and take dowry are severely punished by law. But who pays heed to them?! Marriage without dowry is impossible here. The poor ones give one lac and the solvent ones give up to five lac as dowry in their daughters’ marriage”, said by a beneficiary woman during FGD.

Case Story

Jorina Akhter, Raiganj

I have been living in this area for last 25 years. I can see that the position of women have become better recently. Violence against women, discrimination etc. has reduced. I know about the activities of BRAC in this area and I attended their meetings as well. In those meetings, they discuss about disaster preparedness, protecting oneself during a disaster etc. These meetings are held once in every month. My husband was Hindu and he became Muslim after we got married. We faced many difficulties then and our economic condition became worse. From BRAC, I received 5 goats. By looking after those, I managed 5 more and by selling them I bought a cow. Now my economic condition is better than before and I believe that by the next 5/6 years, it will be even better. Now I am earning freely. But it was not that easy before. I faced many obstacles. Now we know about dowry and most of the marriages are now done without any dowry here. I am treated equally in my family and most of the women are now concerned about their rights after receiving training from BRAC.

Observation 5:

Place: Shyamnagar, Satkhira

Observation Date: 11-15 December, 2015

Raiganj is 40 km away from Sirajganj Sadar and is prone to severe flood during rainy season. Almost the entire region except the high points gets inundated as the rain begins damaging local schools, bazar and roads. Life is comparably better in dry season when people cultivate vegetables for livelihood. The area has seen development in the recent years – both in terms of economic and human development. The area has good transport facility, bridge and culvert as well as electricity connection.

Based on the conversation with the women in area it was found out that most of them are economically independent through livestock and poultry business and do not face major hurdles. Domestic violence, child marriage and violence against women were not observed in the area. The community people did not report of such incidence even during disaster period. Women showed satisfaction in terms decision making power within the family and it has been the direct impact of the awareness raising programmes conducted by the project intervener. The only problems that have been repeatedly quoted by the community were dowry and economic damage from disasters.

There were visible impact of the project on two sections – one was on the economic capacity of the women and the other was on awareness on disaster preparedness of the community. We found one disabled woman who started a grocery shop from the asset provided by the project intervener and is now running two from the profit of the first grocery shop. Another beneficiary woman who was socially outcast due to her change of religion is comparably in better economic position due to the asset provided from the project. A level of satisfaction was noticed among the community people on the training provided on disaster preparedness. The emergency preparedness training has resulted in mitigation of damage and a sense of security among the people. Most of the people have approved of the project impact on economic improvement and women empowerment in the area and opined on the need of launching more such projects.

## Impacts over Policy Implementation and Stakeholder Level

Women’s well-being and life choices are highly influenced and undermined by many socio-economic, political and environmental forces including climate change. The climate change impacts are affecting women disproportionately and making them extremely vulnerable. In addition to that, they face gender inequity and various forms of discriminations in economic and social lives, which again lead to higher rate and deeper level of poverty, environmental and social insecurity. Hence, appropriate policy and institutional measures are required to empower them and reducing their vulnerability to climate change. In Bangladesh, set of policies are in place in the realms of environmental management and conservation, climate change and economic development, but the existing policies and strategies do not address adequately the climate change impacts on women, adaptation needs of women and gender dimensions (equity, fairness and justice) in addressing climate change. Policies and programmes are to be reviewed and reformed to make these gender-sensitive and pro-poor. There is also urgent need for capacity building of the actors and stakeholders who are engaged in women’s empowerment for reducing their social and environmental risks and vulnerabilities.

Impacts over policy/advocacy level

At policy/advocacy level; UN Women and the Bangladesh Climate Change Trust (BCCT) initiated a series of training workshops on Mainstreaming Gender Equality in Climate Change for government officials from 32 ministries/departments/agencies. Key government officials have been sensitized about gender and climate change and capacitated with necessary skill so that they can contribute in gender mainstreaming of climate change initiatives of their respective Ministries and Departments. The training programme acknowledges the need for and importance of gender responsive climate-smart development. With improved knowledge of and capacity in gender mainstreaming from the perspective of rights in climate change efforts, participants committed themselves to contributing towards gender equality within their sphere of influence.

In addition; a symposium was held in Dhaka titled: “CCA & DRR for Gender Sensitive Frontier” where different stakeholders including respective government high officials from different Ministry, representative from Royal Norwegian Embassy, practitioners had attended.  Several researches and documents such  as Baseline Study, the Needs Assessment report, and the Master Class training Manual were disseminated during a critical period while the seventh five year plan, National Plan for Disaster Management were being formulated. Thus they got to appreciate the gender aspects which hopefully would have a positive impact in terms of integration of gender equality in the national policy instruments.

UN Women also engaged climate vulnerable women in several side-events where they shared their experience of engaging in alternative livelihoods. These initiatives helped the policymakers to understand the ground reality of the vulnerable women and struggle for changing their livelihoods with positive notion. Lessons learned from the sessions contributes to sensitize different stakeholders about relevance of the project “Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options” and way forward.

Moreover; UN Women has contributed in the review of the existing and formulation of the new National Plan for Disaster Management (NPDM) of the Ministry of Disaster Management and Relief. This has resulted in incorporating gender aspects for the first time in the NPDM 2016-2020, which was in the draft form till 2015. UNDP approached UN Women to provide the technical support for gender inputs.

Institutional capacity building level

The Bangladesh Centre for Advanced Studies (BCAS), research partner of “Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options” project, has increased capacity for gender-sensitive research. This will increase the overall knowledge base on the gendered impacts of climate change and contribute to gender-responsive policies and programmes. With the technical support and close collaboration of UN Women over the years; BCAS is integrating issues of gender equality in their research processes, including how they conceive and design research projects, as well as data collection protocols.

UN Women has developed the capacity of practitioners at government, UN, research organizations, and I/NGOs to mainstream gender equality in climate change adaptation, disaster risk reduction and humanitarian actions.  Moreover; the capacity of Union Disaster Management Committee (UDMC) to address gender issues in their risk reduction and response initiatives have been assessed and training module drafted to increase their capacity in light of the capacity gaps identified.

UN Women has provided substantive feedback and contributed in national consultation on HFA2 (Sendai Framework for DRR) led by the Department of Disaster Management to include GE perspective in it. As a result government’s position paper did include gender aspects.  UN Women also tried engaging MOWCA in the national consultation on draft HFA2 doc; which has been sent to Department of Disaster Management.

# Recommendation

As the project comprised of three interlinked issues i.e. climate change, vulnerability of women and viable livelihood options; the evaluation was designed to measure its relevance, effectiveness and results/impacts through a combination of quantitative and qualitative techniques. There are lots of initiatives have been taken to reduce vulnerability of women and adopting their viable livelihood options in last few decades in Bangladesh. However; gender issues itself a cultural phenomenon and if we want see through a gender lens; it’s not very easy to understand the changes as well as the role of women in climate change issues.

Considering the fact, this final evaluation tried to understand how much resilient are women in climate change preparedness.  It is observed that the initiatives taken for women under the project intervention have somewhat similarities with other stakeholder’s initiatives to reduce vulnerability of women. However, unveiling the vulnerability of women due to climate change and initiatives to reduce them through viable livelihood options itself a distinguished platform in contemporary Bangladesh. Subsequently, something new areas of women engagement could be added in intervention design, therefore; needs of the target people could be contextualized and climate adaptive livelihood options i.e. floating gardening, use of disaster resilient seeds in agriculture are very important to change their lives in this regard.

Regarding disaster preparedness information system, this project tried to make community people aware about it. In addition, it is very important to develop women friendly early warning system. Keeping in mind about the cultural traditions of women’s mobility, early warning system for women could be designed as their participation and mobility in outside home activities is developing gradually in Bangladesh. Moreover, in disaster issues, school component (especially girl’s school) could be added as girl students can be the frontline actors of making women aware about vulnerability of women due to disaster and its way forward. In this connection, institutional capacity building could be an important area of project strength.

In this development paradigm shifting era, participatory approach in any project is must and there should be an exercise to collect beneficiary expectations during project design so that ownership can grow within the people for its sustainability. Mainstream disaster management committees such as Union Disaster Management Committee (UDMC) should come forward with a participatory manner to connect people with their activities from community to household level. Local governance system should come up with an effective action plan to improve gender and DRR governance and make UDMC more accountable in this regard. Participatory approaches should be designed in such a way so that it gets a pro-people outfit eventually and which will make people capable to contribute in project sustainability.

It is obvious that the vulnerability of women has been reducing due to multilayer interventions of multi stakeholders such as government, NGO and private organizations at the community level in health sector, educational sector, training, IGA as well as self-dependency of women over the period. There should be a link with different activities performing in the specific community to have coordination so that project intervention would be more relevant and effective. To address the gender sensitiveness it is important to fix the ratio of female and male beneficiary in the project intervention area.

Government should be encouraged to incorporate gender perspectives into their national policies, action plans and other measures on sustainable development and climate change, through carrying out systematic gender analysis; collecting and utilizing sex-disaggregated data; establishing gender-sensitive benchmarks and indicators; and developing practical tools to support increased attention to gender perspectives.

The main points emerging from this evaluation study are summarized as recommendations in the below section that could be followed if such programmes are initiated further in future:

- If this kind of project is implemented further in future, the coverage of project beneficiaries can be more diversified considering marital status, head of household, ethnicity and religion. The divorced, widow and separated women could be brought under the programme intervention in greater portion since they are usually more vulnerable to any kind of problems, whether it is socio-economic or disaster event. A comprehensive list of such disadvantaged group of people could be developed in every Union Parishad, Upazilla and District and take appropriate adaptation actions in next phase or future projects.

- Since most of the project beneficiaries are illiterate or less educated village women, if the trainings were provided in local language by some local experts then it would have been convenient for both the participants and the trainer. Field level project staffs have also suggested this.

- In the project curriculum there could be some adult education programme, at least for the beneficiaries aged between 20-30 who consist of around one-fourth of the respondents, so that the capacity of the women is enhanced much more and they can utilize the knowledge and support earned from the project more efficiently.

- Usage of safe sanitation and drinking water from deep tube-well found to be very poor in all the project areas. Either the beneficiaries are not applying their knowledge about WASH in practice or they cannot afford to do so. The project has further scope to work in this issue in future to improve the hygiene and sanitation practice of the community people. Therefore, Behavior Change Communication (BCC) component could be added in the project design, if possible. In light of BCC; following issues could be considered during developing message on WASH:

- Messages could highlight the diverse consequences of not drinking safe water and using sanitary latrine specially loss of health, income, relationship, cost for medication, communication, treatment, negative effect on people’s health and development, educational outcomes of community people linking with getting different disease (diarrhea, pneumonia, other hygienic related diseases) for not adopting WASH.

- Message could contain demonstration of proper of hand washing with soap with special focuses on the benefit to growth and development of children as well as the community people under WASH component.

- Communication messages may also give equal emphasize on all critical parts of WASH i.e. safe drinking water, use of sanitary latrine, personal hygiene and cleanliness of all category of community people.

- The selection of livelihood options on which the beneficiaries have been trained could be something more disaster resilient like more technology based agricultural method. Empowering adaptation projects can initiate women’s engagement in productive sectors that connects women to different productive activities, beyond the domestic sphere. So future programme should promote livelihoods that are empowering and climate resilient.

- Home-based livelihoods for women vulnerable to climate change can reinforce gender norms about ‘women appropriate’ work which will increase the women empowerment as well as their income.

- To improve women’s participation and leadership in local level disaster management committees; UN Women should work with UDMC committees as well as the women members. Working with the women would build their capacity and confidence, and working with UDMC builds more capacity to think and work on gender to help creating more enabling environment for women UDMC members.

- It is essential to address the stigma of inequalities and recovery actions should be taken in women’s representation and leadership at all levels of CCA/DRR to create transformational changes.

- The gap between the community people and the UDMCs has to be removed. The participation of women in UDMCs has to be increased and their active role needs to be ensured. Therefore; a group could be formed consist of proactive and/or efficient women who will maintain communication with women and UDMC on a regular basis to remind them about their role and responsibilities and help them to participate in UDMC provided activities.

- The evaluation data indicates that 10% of the children have been dropped-out and engaged with IGA. If scholarships or educational stipends could be offered for these poor children, then probably the dropout rate could be decreased even more. Education for girls could be enhanced in these disaster-prone areas by building more girls’ schools which could be utilized also as shelter centers during disasters like floods and cyclones.

- The good practices like courtyard meetings, new viable livelihood options adopted by beneficiary women, raising funds and tendency to save, etc. should be shared and introduced in other unions where the project hasn’t been implemented through the beneficiaries themselves which will make the positive impacts of the project to sustain in an auto generating mechanism. This practice should be spread even among the women of different nearby unions. This positive externality effect may magnify the project outputs to ten times.

- Since the project activities are subject to both time and budget constraints, to continue the progress earned through the project initiatives as well as to bring a greater portion of the population of these disaster prone areas under the positive impacts of the project, micro finance programme with low interest rate than regular can be initiated for the inhabitants of these disaster prone areas. In fact, as the beneficiary women were asked what types of training they want in future, near about half of the women demanded microfinance for better livelihood.

- It is evident that violence against women increases during and after disaster situation, but the issue was not addressed by the project. Therefore; it is recommended to take this issue seriously and shape future gender focused DRR programme in such a way that prevent.

- These remote disaster prone areas will remain deprived of many facilities that people of other parts of our country enjoy unless the infrastructure of these areas is not improved. Schooling of children, selling self-produced goods to Upazila or district markets, carrying patients and pregnant women to hospitals in emergency, conveying relief materials in disaster periods, etc. are highly disrupted due to infrastructure problem here. In fact, one of the factors that constrained the project activities to some extent is the poor infrastructure condition. This problem needs to be solved; therefore, this project could suggest strongly the government to look after infrastructural development of these areas.

- At national level gender mainstreaming; MOWCA should take the lead.

# Conclusion

It is mentioned earlier that the project was initiated with a three-fold purpose of establishing viable alternative livelihood options for the most vulnerable women of the three disaster prone eco-zones to reduce their vulnerability to climate change like frequently occurred natural calamities as well as to establish a strong role of women in decision making both inside and outside home activities. The recommendations made above are some areas where there is scope of further intervention. But the attempts taken to implement the objectives of the project have been proved to be really fruitful. The project played a role to make beneficiary women come out the four walls of their household breaking the barriers usually faced by rural women. Their participation in IGA and disaster preparedness & management activities has been increased significantly. Awareness regarding climate change and its impact, how to cope with climate change, disaster preparedness and management, and WASH issues have been raised than that of past among the direct beneficiaries of the project and the community people through sharing. The beneficiary women can now take part in important decision making of the family in many occasions and their male counterparts value their decisions as well.

In hindsight; it is evident that the project initiatives were inevitably relevant and appropriate according to local as well as national need, and have showered positive and effective impacts on the community overall. Though the direct beneficiaries of the project are 19,100 women, positive impacts of the project activities have been found among the whole community also. Now the sustainability of the project depends on how efficiently the beneficiaries utilize their knowledge, skills and grants received through this project. More projects like this should be implemented in our country and greater portion of the population especially the women of these remote, neglected, disaster prone areas need to be brought under their benefits.

# ANNEX

# Annex 1: Evaluation Matrix

| Sl No. | Area of Information | Source of Information | Tools & Techniques Used |
| --- | --- | --- | --- |
| Relevance |  |  |  |
| 01 | To what extent are the project results, outcomes, outputs consistent with national, local priorities and needs of intended beneficiaries? | Partners & Stakeholders | KII |
| 02 | To what extent are the project results and strategies relevant to UN Women’s overall goals of gender equality and women’s empowerment; and BCO strategic note? | Partners & Stakeholders | KII |
| Effectiveness |  |  |  |
| Did the program achieve satisfactory results in relation to stated objectives? |  |  |  |
| 03 | To what degree the project has been successful to sensitize stakeholders on the importance of incorporating gender issues in climate change adaptation policies and programmes? | Partners & Stakeholders, target beneficiaries | KII, face to face interview, FGD |
| 04 | To what extent has livelihood support resulted in increasing women’s disaster preparedness capacity? | Partners & Stakeholders, target beneficiaries | KII, face to face interview, observation, FGD, case study |
| 05 | To what extent capacity of the institutions (implementing partners, relevant stakeholders, GO institutions) and individuals (beneficiary, disaster management committee members) have been enhanced to advocate for gender equality in DRR-CCA? | Partners & Stakeholders | KII, observation |
| Results/Impacts |  |  |  |
| 06 | Are there any changes in women’s lives vulnerable to disasters and climatic events brought about by the project intervention? | Partners & Stakeholders, target beneficiaries | KII, face to face interview, case study, observation, FGD |
| 07 | What are the intended and unintended, positive and negative, long term effects of the project? | Partners & Stakeholders, target beneficiaries | KII, face to face interview, case study, observation |
| 08 | Identify lessons that enabled or constraint to achieving the results. | Partners & Stakeholders, target beneficiaries | KII, face to face interview, case study |

# Annex 2: Tables

Table 1: Age of the respondents (%)

| Category | Cyclone-Prone Areas | Flood-prone Areas | Drought-prone Areas | Total |
| --- | --- | --- | --- | --- |
| 15-19 years | 0.83 | 0 | 1.25 | 0.75 |
| 20-24 years | 6.25 | 6.25 | 16.25 | 8.25 |
| 25-29 years | 15.83 | 12.5 | 22.5 | 16.5 |
| 30-34 years | 24.17 | 18.75 | 17.5 | 21.75 |
| 35-39 years | 19.58 | 15 | 10 | 16.75 |
| 40-44 years | 9.58 | 17.5 | 10 | 11.25 |
| 45+ years | 23.75 | 30 | 22.5 | 24.75 |
| Avg. age (in years) | 36.3 | 38.2 | 34.7 | 36.4 |
| N | 240 | 80 | 80 | 400 |

Table 2: Marital Status of the respondents (%)

| Category | Cyclone-prone Areas | Flood-prone Areas | Drought-prone Areas | Total |
| --- | --- | --- | --- | --- |
| Single | 0.42 | 1.25 | 0 | 0.5 |
| Married | 75.42 | 83.75 | 83.75 | 78.75 |
| Widow | 14.58 | 12.5 | 8.75 | 13 |
| Separated | 6.67 | 1.25 | 6.25 | 5.5 |
| Divorced | 2.92 | 1.25 | 1.25 | 2.25 |
| N | 240 | 80 | 80 | 400 |

Table 3: Relationship of the respondents with the Head of the Households (%)

| Category | Cyclone-Prone Areas | Flood-prone Areas | Drought-prone Areas | Total |
| --- | --- | --- | --- | --- |
| Self | 23.33 | 16.25 | 22.5 | 21.75 |
| Wife | 68.33 | 82.5 | 76.25 | 72.75 |
| Daughter | 1.25 | 0 | 0 | 0.75 |
| Sister | 0.83 | 0 | 0 | 0.5 |
| Mother | 5.42 | 1.25 | 1.25 | 3.75 |
| Daughter-in-law | 0.83 | 0 | 0 | 0.5 |
| N | 240 | 80 | 80 | 400 |

Table 4: Religion of the respondents (%)

| Category | Cyclone-Prone Areas | Flood-prone Areas | Drought-prone Areas | Total |
| --- | --- | --- | --- | --- |
| Muslim | 91.67 | 92.5 | 97.5 | 93 |
| Hindu | 7.92 | 7.5 | 2.5 | 6.75 |
| Christian | 0.42 | 0 | 0 | 0.25 |
| N | 240 | 80 | 80 | 400 |

Table 5: Educational qualification of the respondents (%)

| Category | Cyclone-Prone Areas | Flood-Prone Area | Drought-Prone Area | Total |
| --- | --- | --- | --- | --- |
| Illiterate | 40.42 | 36.25 | 26.25 | 36.75 |
| Signatory | 17.5 | 31.25 | 18.75 | 20.5 |
| Class 1-5 | 31.25 | 25.0 | 22.5 | 28.25 |
| Class 6-8 | 7.92 | 5.0 | 22.5 | 10.25 |
| Class 9-10 | 2.5 | 2.5 | 8.75 | 3.75 |
| SSC/Dakhil | 0.42 | 0 | 1.25 | 0.5 |
| N | 240 | 80 | 80 | 400 |

Table 6: Primary and secondary occupation of the beneficiary women (%)

| Occupations | Cyclone-prone Areas |  | Flood-prone Area |  | Drought-prone Area |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Primary occupation | Secondary Occupation | Primary occupation | Secondary Occupation | Primary occupation | Secondary Occupation |
| Agricultural crop production/farming | 1.25 | 6.25 | 1.25 | 1.25 | 0 | 2.50 |
| Agricultural wage labor | 0.83 | 6.25 | 2.50 | 1.25 | 0 | 0 |
| Non- farming day labor | 12.08 | 17.08 | 3.75 | 1.25 | 5 | 7.50 |
| Livestock and poultry | 6.25 | 32.08 | 13.75 | 10.0 | 1.25 | 18.75 |
| Food for work/money (soil cutting, road maintenance, etc.) | 0.83 | 4.17 | 3.75 | 0 | 1.25 | 0 |
| Fry collection | 0.42 | 8.33 | 0 | 0 | 0 | 0 |
| Crab collection | 0.42 | 4.17 | 0 | 0 | 0 | 0 |
| Handicraft (swing, handloom, cottage, etc.) | 1.25 | 9.17 | 15.0 | 11.25 | 0 | 2.50 |
| Business | 13.33 | 4.17 | 16.25 | 2.50 | 3.75 | 7.50 |
| Service | 0.83 | 0 | 1.25 | 0 | 3.75 | 1.25 |
| Housewife | 56.67 | 24.58 | 25.0 | 51.25 | 77.50 | 17.50 |
| Housework (paid work) | 0 | 0.42 | 5.0 | 5.0 | 5.0 | 2.50 |
| Tailor | 3.75 | 5.83 | 11.25 | 0 | 2.5 | 12.50 |
| Teacher | 0.83 | - | 0 | - | 0 | - |
| Nurse | 0.42 | - | 0 | - | 0 | - |
| Beggar | 0 | - | 1.25 | - | 0 | - |
| Shrimp collection | 0.42 | - | 0 | - | 0 | - |
| Fish farming | - | 0.83 | - | 0 | - | 0 |
| Fruit/timber production | - | 0 | - | 1.25 | - | 1.25 |
| Tuition | - | 0.42 | - | 0 | - | 0 |
| Fish processing | - | 0.42 | - | 0 | - | 0 |
| Weaving fish nets | - | 0 | - | 1.25 | - | 0 |
| Not applicable | - | 7.50 | - | 20.0 | - | 36.25 |
| N | 240 | 240 | 80 | 80 | 80 | 80 |

Table 7: Household income level of the respondents (%)

| Category | Cyclone-Prone Area | Flood-Prone Area | Drought-Prone Area | Total |
| --- | --- | --- | --- | --- |
| Up to BDT. 5,000 | 26.25 | 28.75 | 25.0 | 26.50 |
| BDT. 5,001 - 10,000 | 60.0 | 70 | 71.25 | 64.25 |
| BDT. 10,001- 15,000 | 10.83 | 1.25 | 3.75 | 7.5 |
| BDT. 15,001- 20,000 | 1.25 | 0 | 0 | 0.75 |
| BDT. 20,001- 25,000 | 1.25 | 0 | 0 | 0.75 |
| BDT. 25,001-30, 000 | 0.42 | 0 | 0 | 0.25 |
| Avg. income of male headed households (estimated) | - | - | - | 5420 |
| Avg. income of female headed households (estimated) | - | - | - | 7506 |
| Avg. income (estimated) | 7388 | 6413 | 6688 | 7053 |
| N | 240 | 80 | 80 | 400 |

Table 8: Trainings received by the respondents under RVWACC project (%)

| Received Trainings | Cyclone-prone areas | Flood-prone area | Drought-prone area | Total |
| --- | --- | --- | --- | --- |
| Homestead gardening | 65.32 | 35.56 | 26.67 | 55.24 |
| Small Poultry | 49.71 | 24.44 | 13.33 | 40.73 |
| Horticulture | 36.42 | 24.44 | 23.33 | 32.66 |
| Tailoring | 32.37 | 28.89 | 33.33 | 31.85 |
| Small shop/business | 21.97 | 46.67 | 23.33 | 26.61 |
| Cattle fatting | 20.23 | 4.44 | 13.33 | 16.53 |
| Rice Processing | 6.36 | 0 | 10 | 5.65 |
| Dry Fish Processing | 6.94 | 0 | 0 | 4.84 |
| Handicrafts | 5.2 | 4.44 | 0 | 4.44 |
| Net Making | 2.31 | 0 | 0 | 1.61 |
| Handloom | 0 | 4.44 | 0 | 0.81 |
| Cattle | 0 | 0 | 6.67 | 0.81 |
| Day labor | 0 | 0 | 3.33 | 0.4 |
| Crab cultivation | 0.58 | 0 | 0 | 0.4 |
| N | 173 | 45 | 30 | 248 |

Table 9: Initiatives taken for women under project (%)

| Initiatives | Cyclone-prone Areas | Flood-prone Area | Drought-prone Area | Total |
| --- | --- | --- | --- | --- |
| How to take people in safe shelter | 17.3 | 6.66 | 50 | 14.5 |
| Created awareness about carrying dry food and safe water | 18.38 | 44 | 50 | 25.96 |
| Women get training on disaster resilience | 15.68 | - | - | 11.07 |
| How to protect homestead and life from disaster | 12.97 | - | - | 9.16 |
| Provide training on making house in higher place | 3.78 | 20 | - | 8.4 |
| Raising awareness on disaster management | 3.24 | 6.67 | - | 4.2 |
| Learn to keep cattle in high place | 2.16 | 9.33 | - | 4.2 |
| Women, specially pregnant women, children, and older people should get first priority to take shelter | 9.72 | - | - | 6.88 |
| Created awareness on raising plinth of the house | - | 8 | - | 2.29 |
| Provide higher training to the women on life skill development | 3.24 | - | - | 2.29 |
| Provide training on tree plantation | 0.54 | 4 | - | 1.53 |
| Provide useful training on capacity building | 0.54 | 2.67 | - | 1.15 |
| Provide training on post flood preparation | - | 4 | - | 1.15 |
| Give financial help | 0.54 | - | - | 0.38 |
| Increasing confidence through training | - | 1.33 | - | 0.38 |
| N | 185 | 75 | 2 | 262 |

Table 10: Involvement in IGA by the women of the evaluation areas (%)

| Category | Cyclone-prone area | Flood-prone area | Drought-prone area | Total |
| --- | --- | --- | --- | --- |
| Small Poultry | 37.33 | 22.22 | 28.57 | 32.84 |
| Homestead gardening | 35.48 | 23.61 | 14.29 | 29.88 |
| Tailoring | 25.81 | 40.28 | 30.61 | 29.59 |
| Livestock | 26.73 | 33.33 | 20.41 | 27.22 |
| Small business | 21.66 | 44.44 | 16.33 | 25.74 |
| Horticulture | 23.04 | 15.28 | 12.24 | 19.82 |
| Day labor | 15.67 | 1.39 | 2.04 | 10.65 |
| Handicrafts | 10.14 | 12.50 | 4.08 | 9.76 |
| Dry Fish Processing | 5.99 | 0 | 2.04 | 4.14 |
| Rice Processing | 4.15 | 1.39 | 4.08 | 3.55 |
| Fish and shrimp cultivation | 4.61 | 1.39 | 0 | 3.25 |
| Embroidery/ Batiks and printing | 0.92 | 11.11 | 0 | 2.96 |
| Net Making | 0.92 | 1.39 | 2.04 | 1.18 |
| Domestic worker | 0.46 | 0 | 6.12 | 1.18 |
| Fishing | 1.84 | 0 | 0 | 1.18 |
| Agriculture | 0.92 | 0 | 4.08 | 1.18 |
| Service | 0.46 | 1.39 | 2.04 | 0.89 |
| Collect wood | 1.38 | 0 | 0 | 0.89 |
| Knitting | 0 | 2.78 | 0 | 0.59 |
| Loom work | 0 | 2.78 | 0 | 0.59 |
| Tuition | 0.92 | 0 | 0 | 0.59 |
| Sewing cap | 0 | 1.39 | 0 | 0.3 |
| Digging | 0 | 1.39 | 0 | 0.3 |
| N | 217 | 72 | 49 | 338 |

Table 11: Average earning members of the beneficiary households (Frequency)

| Category | Cyclone-prone Areas | Flood-prone Areas | Drought-prone Areas | Total |
| --- | --- | --- | --- | --- |
| Avg. Male | 1.2 | 1.1 | 1.1 | 1.1 |
| Avg. Female | 1 | 1 | 1 | 1 |
| Avg. Total | 1.9 | 1.7 | 1.5 | 1.8 |
| N | 239 | 78 | 80 | 397 |

Table 12: Purposes of savings by the respondents (%)

| Category | Cyclone-Prone Areas | Flood-prone Areas | Drought-prone Areas | Total |
| --- | --- | --- | --- | --- |
| To reduce vulnerability/risk to disaster | 33.33 | 7.69 | 11.11 | 26.58 |
| To buy assets | 8.77 | 38.46 | 0 | 12.66 |
| To invest into a new business | 7.02 | 23.08 | 22.22 | 11.39 |
| For the purpose of children's education | 77.19 | 46.15 | 33.33 | 67.09 |
| For son/daughter's marriage | 42.11 | 53.85 | 22.22 | 41.77 |
| Haven't plan anything yet | 1.75 | 0 | 22.22 | 3.8 |
| Those responded | 100 | 100 | 100 | 100 |
| N | 57 | 13 | 9 | 79 |

Table 13: IGA activities by the respondents and/or female members of their household (%)

| Category | Cyclone-Prone Areas | Flood-prone Areas | Drought-prone Areas | Total |
| --- | --- | --- | --- | --- |
| Agricultural crop production/farming | 59.32 | 28.75 | 11.94 | 44.65 |
| Livestock and poultry | 72.03 | 58.75 | 73.13 | 69.45 |
| Tailor | 60.17 | 67.5 | 77.61 | 64.75 |
| Food for work/money (soil cutting, road maintenance, etc.) | 50.85 | 30 | 29.85 | 42.82 |
| Dry Fish Processing | 22.03 | 0 | 0 | 13.58 |
| Crab collection | 24.58 | 0 | 0 | 15.14 |
| Fish farming | 3.39 | 1.25 | 0 | 2.35 |
| Shrimp culture | 2.97 | 0 | 0 | 1.83 |
| Handicraft (swing, handloom, cottage, etc.) | 55.51 | 55 | 47.76 | 54.05 |
| Rice Processing | 5.08 | 6.25 | 4.48 | 5.22 |
| Fruit/timber production | 2.12 | 1.25 | 0 | 1.57 |
| Business | 22.03 | 13.75 | 19.4 | 19.84 |
| Service | 4.66 | 1.25 | 26.87 | 7.83 |
| Work abroad | 0 | 1.25 | 1.49 | 0.52 |
| Housewife | 6.78 | 11.25 | 0 | 6.53 |
| Housework (paid work) | 5.93 | 12.5 | 28.36 | 11.23 |
| Small Shop | 44.07 | 23.75 | 40.3 | 39.16 |
| Teacher | 8.05 | 1.25 | 2.99 | 5.74 |
| Forest resource collector (bawali/mouali) | 0.42 | 0 | 0 | 0.26 |
| Day labourer | 0 | 0 | 1.49 | 0.26 |
| Shrimp collection | 0.42 | 0 | 0 | 0.26 |
| Producing salt | 0.42 | 0 | 0 | 0.26 |
| Those responded | 100 | 100 | 100 | 100 |
| N | 236 | 80 | 67 | 383 |

Table 14: Project impacts on beneficiary women’s lives (%)

| Category | Cyclone-Prone Areas | Flood-prone Areas | Drought-prone Areas | Total |
| --- | --- | --- | --- | --- |
| Made women aware of the climate change impact | 77.5 | 65 | 73.75 | 74.25 |
| Established participation of women in climate risk management | 31.25 | 55 | 15 | 32.75 |
| Formed new small entrepreneur | 34.17 | 75 | 25 | 40.5 |
| Established participation of women in local government activities | 11.25 | 17.5 | 0 | 10.25 |
| Managed new livelihood options for women (e.g. homestead gardening) | 43.33 | 35 | 58.75 | 44.75 |
| Ran new income generating project for women (Handicraft or others) | 25.42 | 25 | 45 | 29.25 |
| Formed local people based organization (C.B.O) in participation of women | 1.67 | 1.25 | 0 | 1.25 |
| Don't know | 0.42 | 0 | 0 | 0.25 |
| Those responded | 100 | 100 | 100 | 100 |
| N | 240 | 80 | 80 | 400 |

Table 15: Role played in household decision making based on gender (%)

| HH Decision (Normal period) | Male | Female | Both | N/A | N |
| --- | --- | --- | --- | --- | --- |
| Engage in new income generating activities | 14.25 | 17.25 | 44.0 | 24.50 | 400 |
| Give marriage | 3.25 | 10.5 | 36.0 | 50.25 | 400 |
| Conceiving a baby | 5.0 | 3.75 | 64.75 | 26.5 | 400 |
| Use saving | 2.0 | 4.0 | 18.25 | 75.75 | 400 |
| VGD/VGF | 3.25 | 8.75 | 23.5 | 64.50 | 400 |
| Female going outside the homestead | 16.25 | 28.0 | 45.25 | 10.50 | 400 |
| Female going to work | 14.50 | 25.75 | 46.5 | 13.25 | 400 |
| Male going to work | 47.75 | 3.50 | 22.0 | 26.75 | 400 |
| Education of Children | 3.0 | 16.75 | 64.0 | 16.25 | 400 |

Table 16: Household assets ownership according to sex (%)

|  | Kalapara |  |  | Shyamnagar |  |  | Teknaf |  |  | Raiganj |  |  | Natore Sadar |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Male | Female | Both | Male | Female | Both | Male | Female | Both | Male | Female | Both | Male | Female | Both |
| House | 82.5 | 11.25 | 6.25 | 81.25 | 13.75 | 5 | 48.75 | 36.25 | 15 | 82.5 | 17.5 | 0 | 65 | 15 | 20 |
| Business/ Shop structure | 83.75 | 12.5 | 3.75 | 85 | 15 | 0 | 91.25 | 8.75 | 0 | 86.25 | 12.5 | 1.25 | 93.75 | 3.75 | 2.5 |
| Radio | 100 | 0 | 0 | 98.75 | 1.25 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 |
| TV/VCD | 97.5 | 1.25 | 1.25 | 100 | 0 | 0 | 100 | 0 | 0 | 98.75 | 1.25 | 0 | 98.75 | 0 | 1.25 |
| Mobile Phone | 51.25 | 18.75 | 30 | 73.75 | 15 | 11.25 | 63.75 | 30 | 6.25 | 76.25 | 10 | 13.75 | 88.75 | 6.25 | 5 |
| Livestock | 60 | 8.75 | 31.25 | 61.25 | 31.25 | 7.5 | 83.75 | 16.25 | 0 | 80 | 11.25 | 8.75 | 75 | 12.5 | 12.5 |
| Poultry | 16.25 | 45 | 38.75 | 73.75 | 25 | 1.25 | 95 | 5 | 0 | 90 | 10 | 0 | 43.75 | 41.25 | 15 |
| Boat | 98.75 | 0 | 1.25 | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 |
| Fishing Instruments | 90 | 2.5 | 7.5 | 95 | 5 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 |
| Rickshaw/ Van/ Related others | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 |
| Sewing machine | 98.75 | 1.25 | 0 | 100 | 0 | 0 | 96.25 | 3.75 | 0 | 100 | 0 | 0 | 100 | 0 | 0 |
| Motorbike | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 |

Table 17: Perpetrators of violence against women (%)

| Category | Cyclone-Prone Areas | Flood-prone Areas | Drought-prone Areas | Total |
| --- | --- | --- | --- | --- |
| Torturing by husband | 83.52 | 81.82 | 97.96 | 86.67 |
| Torturing by in laws | 60.44 | 41.82 | 14.29 | 43.59 |
| Torturing by family members | 24.18 | 32.73 | 18.37 | 25.13 |
| Acid throwing | 2.2 | 1.82 | 0 | 1.54 |
| Demand of Dowry | 36.26 | 63.64 | 24.49 | 41.03 |
| Eve teasing | 9.89 | 10.91 | 0 | 7.69 |
| Harassment | 2.2 | 3.64 | 14.29 | 5.64 |
| Those responded | 100 | 100 | 100 | 100 |
| N | 91 | 55 | 49 | 195 |

# Annex 3: Quantitative Tool

Informed Consent

Salam/Adab. I’m_________________ from Nielsen Bangladesh and we are conducting project evaluation on “Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options” focusing on older people’s community response practices in the event of disasters. We would appreciate your cooperation in responding to the questions.  This interview will take approximately 25-30 minutes. The information you provide will be kept strictly confidential. You will not be identified, or be able to be identified, in any of the reports we plan to write. This information is ONLY being used to examine some social contexts.

| Household Identification |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Zone GjvKv |  |  |  |  |
|  | District †Rjv |  |  |  |  |
|  | Upazila Dc‡Rjv |  |  |  |  |
|  | Union BDwbqb |  |  |  |  |
|  | Village MÖvg |  |  |  |  |
|  | Household Sl. No. evwoi wmwiqvj bv¤^vi |  |  |  |  |

Section A: Household Information

| Sl. No. | Questions and Filters | Coding Categories |  |  | Code |  | Skip |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name of the Household Head (HH) cwievi/Lvbv cÖavv‡bi bvg |  |  |  |  |  |  |
|  | Sex wj½ (Lvbv cÖav‡bi) | Male cyi“l |  |  | 1 |  |  |
|  |  | Female gwnjv |  |  | 2 |  |  |
|  | Age of the respondent (in complete years) DËi`vZvi eqm | ………….Years -------------eqm |  |  |  |  |  |
|  | Marital status of the respondent DËi`vZvi ˆeevwnK Ae¯’v | Single AweevwnZ |  |  | 01 |  |  |
|  |  | Married weevwnZ |  |  | 02 |  |  |
|  |  | Widow weaev |  |  | 03 |  |  |
|  |  | Separated wew”Qbœ |  |  | 04 |  |  |
|  |  | Divorced ZvjvKcÖvßv |  |  | 05 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |
|  | Relationship of the respondent with HH DËi`vZvi mv‡_ cwievi cÖav‡bi m¤cK© | Self wb‡R |  |  | 01 |  |  |
|  |  | Wife ¯¿x |  |  | 02 |  |  |
|  |  | Husband ¯^vgx |  |  | 03 |  |  |
|  |  | Son †Q‡j |  |  | 04 |  |  |
|  |  | Daughter †g‡q |  |  | 05 |  |  |
|  |  | Brother fvB |  |  | 06 |  |  |
|  |  | Sister †evb |  |  | 07 |  |  |
|  |  | Father evev |  |  | 08 |  |  |
|  |  | Mother gv |  |  | 09 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |
|  | Religion of the respondent DËi`vZvi ag© | Muslim gymwjg |  |  | 1 |  |  |
|  |  | Hindu wn›`y |  |  | 2 |  |  |
|  |  | Christian wLª÷vb |  |  | 3 |  |  |
|  |  | Buddhist †eŠ× |  |  | 4 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |
|  | Ethnicity of the respondent Avcwb †Kvb Avw`evmx m¤cÖ`v‡qi Aš—f©z³? | Bengali evOvwj |  |  | 01 |  |  |
|  |  | Chakma PvKgv |  |  | 02 |  |  |
|  |  | Tripura wÎcyiv |  |  | 03 |  |  |
|  |  | Garo Mv‡iv |  |  | 04 |  |  |
|  |  | Shantal mvuIZvj |  |  | 05 |  |  |
|  |  | Marma gvigv |  |  | 06 |  |  |
|  |  | Murong gyis |  |  | 07 |  |  |
|  |  | Rakhain ivLvBb |  |  | 08 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |
|  | What is your educational Qualification? Avcwb KZ`~i covïbv K‡i‡Qb? | Illiterate Awkw¶Z |  |  | 01 |  |  |
|  |  | Signatory wjL‡Z co‡Z Rv‡b |  |  | 02 |  |  |
|  |  | Class 1-5 1g-5g †kªYx |  |  | 03 |  |  |
|  |  | Class 6-8 6ô-8g †kªYx |  |  | 04 |  |  |
|  |  | Class 9-10 9g- 10g †kªYx |  |  | 05 |  |  |
|  |  | SSC/Dakhil Gm.Gm.wm/g¨vwUªK/`vwLj |  |  | 06 |  |  |
|  |  | HSC/Alim GBQ.Gm.wm/Avwjg |  |  | 07 |  |  |
|  |  | Graduate/Fazil øvZK/dvwhj |  |  | 08 |  |  |
|  |  | Masters/Kamil øvZKËi/Kvwgj |  |  | 09 |  |  |
|  |  | Engineer/Doctor BwÄwbqvi/Wv³vi |  |  | 10 |  |  |
|  |  | Technical/Vocational KvwiMix/f‡Kkbvj |  |  | 11 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |
|  | What is your primary occupation? (Single Response) Avcbvi cÖavb †ckv wK? (GKwU DËi n‡e) | Agricultural crop production/farming K…wlKvR |  |  | 01 |  |  |
|  |  | Agricultural wage labor eiMv Pvwl |  |  | 02 |  |  |
|  |  | Non- farming day labor w`b gRyi |  |  | 03 |  |  |
|  |  | Livestock and poultry cïcvjb I Lvgvi |  |  | 04 |  |  |
|  |  | Food for work/money (soil cutting, road maintenance, etc.) Kv‡Ri wewbg‡q Lv`¨ (gvwU KvUv, iv¯—v wVK Kiv, BZ¨vw`) |  |  | 05 |  |  |
|  |  | Fry collection jvKwo msMÖn |  |  | 06 |  |  |
|  |  | Crab collection KvuKov aiv |  |  | 07 |  |  |
|  |  | Fish farming gvQ Pvl |  |  | 08 |  |  |
|  |  | Shrimp culture wPswo Pvl |  |  | 09 |  |  |
|  |  | Handicraft (swing, handloom, cottage, etc.) nv‡Zi KvR/ ¶z`ª KzwUi wkí (†mjvB, ZvuZ, BZ¨vw`) |  |  | 10 |  |  |
|  |  | Transport (rickshaw/van/cart/boatman) hvbevnb Pvjvb (wiKmv, f¨vb, Mi“i Mvwo, †bŠKv, BZ¨vw`) |  |  | 11 |  |  |
|  |  | Fruit/timber production KvVz‡i/dj Drcv`K |  |  | 12 |  |  |
|  |  | Business e¨vemv |  |  | 13 |  |  |
|  |  | Service PvKwi |  |  | 14 |  |  |
|  |  | Work abroad we‡`‡k KvR K‡ib |  |  | 15 |  |  |
|  |  | Housewife M„wnYx |  |  | 16 |  |  |
|  |  | Housework (paid work) M„ncwiPvwiKv |  |  | 17 |  |  |
|  |  | Tailor `wR© |  |  | 18 |  |  |
|  |  | Teacher wk¶K/wkw¶Kv |  |  | 19 |  |  |
|  |  | Student QvÎx |  |  | 20 |  |  |
|  |  | Forest resource collector (bawali/mouali) evIqvwj/†gŠqvj |  |  | 21 |  |  |
|  |  | Unemployed †eKvi |  |  | 22 |  |  |
|  |  | Aged e„× |  |  | 23 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |
|  | What is your secondary occupation? (if any) (Multiple Response) Avcwb wK Gi cvkvcvwk Ab¨ †Kvb †ckvi mv‡_ RwoZ Av‡Qb? (GKvwaK DËi m¤¢e) | Agricultural crop production/farming K…wlKvR |  |  | 01 |  |  |
|  |  | Agricultural wage labor eiMv Pvwl |  |  | 02 |  |  |
|  |  | Non- farming day labor w`b gRyi |  |  | 03 |  |  |
|  |  | Livestock and poultry cïcvjb I Lvgvi |  |  | 04 |  |  |
|  |  | Food for work/money (soil cutting, road maintenance, etc.) Kv‡Ri wewbg‡q Lv`¨ (gvwU KvUv, iv¯—v wVK Kiv, BZ¨vw`) |  |  | 05 |  |  |
|  |  | Fry collection jvKwo msMÖn |  |  | 06 |  |  |
|  |  | Crab collection KvuKov aiv |  |  | 07 |  |  |
|  |  | Fish farming gvQ Pvl |  |  | 08 |  |  |
|  |  | Shrimp culture wPswo Pvl |  |  | 09 |  |  |
|  |  | Handicraft (swing, handloom, cottage, etc.) nv‡Zi KvR/ ¶z`ª KzwUi wkí (†mjvB, ZvuZ, BZ¨vw`) |  |  | 10 |  |  |
|  |  | Transport (rickshaw/van/cart/boatman) hvbevnb Pvjvb (wiKmv, f¨vb, Mi“I Mvwo, †bŠKv, BZ¨vw`) |  |  | 11 |  |  |
|  |  | Fruit/timber production KvVz‡i/dj Drcv`K |  |  | 12 |  |  |
|  |  | Business e¨vemv |  |  | 13 |  |  |
|  |  | Service PvKwi |  |  | 14 |  |  |
|  |  | Work abroad we‡`‡k KvR K‡ib |  |  | 15 |  |  |
|  |  | Housewife M„wnYx |  |  | 16 |  |  |
|  |  | Housework (paid work) M„ncwiPvwiKv |  |  | 17 |  |  |
|  |  | Tailor `wR© |  |  | 18 |  |  |
|  |  | Teacher wk¶K/wkw¶Kv |  |  | 19 |  |  |
|  |  | Student QvÎx |  |  | 20 |  |  |
|  |  | Forest resource collector (bawali/mouali) evIqvwj/†gŠqvj |  |  | 21 |  |  |
|  |  | Unemployed †eKvi |  |  | 22 |  |  |
|  |  | Aged e„× |  |  | 23 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |
|  |  | Not applicable cÖ‡hvR¨ bq |  |  | 88 |  |  |
|  | How many members are there in your family? Avcbvi cwiev‡i KZRb m`m¨ Av‡Q? | Male cyi“l: |  |  |  |  |  |
|  |  | Female gwnjv: |  |  |  |  |  |
|  |  | Children wkï: |  |  |  |  |  |
|  |  | Total †gvU: |  |  |  |  |  |
|  | What occupation is your husband involved with? (Multiple Response) Avcbvi ¯^vgx †Kvb †ckvi mv‡_ RwoZ Av‡Q? (GKvwaK DËi m¤¢e) | Agricultural crop production/farming K…wlKvR |  | 01 |  |  |  |
|  |  | Agricultural wage labor K…wl w`b gRyi |  | 02 |  |  |  |
|  |  | Non- farming day labor w`b gRyi |  | 03 |  |  |  |
|  |  | Livestock and poultry cïcvjb I Lvgvi |  | 04 |  |  |  |
|  |  | Food for work/money (soil cutting, road maintenance, etc.) Kv‡Ri wewbg‡q Lv`¨ (gvwU KvUv, iv¯—v wVK Kiv, BZ¨vw`) |  | 05 |  |  |  |
|  |  | Fry collection jvKwo msMÖn |  | 06 |  |  |  |
|  |  | Crab collection KvuKov aiv |  | 07 |  |  |  |
|  |  | Fish farming gvQ Pvl |  | 08 |  |  |  |
|  |  | Shrimp culture wPswo Pvl |  | 09 |  |  |  |
|  |  | Handicraft (swing, handloom, cottage, etc.) nv‡Zi KvR/ ¶z`ª KzwUi wkí (†mjvB, ZvuZ, BZ¨vw`) |  | 10 |  |  |  |
|  |  | Transport (rickshaw/van/cart/boatman) hvbevnb Pvjvb (wiKmv, f¨vb, Mi“i Mvwo, †bŠKv, BZ¨vw`) |  | 11 |  |  |  |
|  |  | Fruit/timber production KvVz‡i/dj Drcv`K |  | 12 |  |  |  |
|  |  | Business E¨vemv |  | 13 |  |  |  |
|  |  | Service PvKwi |  | 14 |  |  |  |
|  |  | Work abroad we‡`‡k KvR K‡ib |  | 15 |  |  |  |
|  |  | Tailor `wR© |  | 16 |  |  |  |
|  |  | Teacher wk¶K/wkw¶Kv |  | 17 |  |  |  |
|  |  | Forest resource collector (bawali/mouali) evIqvwj/†gŠqvj |  | 18 |  |  |  |
|  |  | Unemployed †eKvi |  | 19 |  |  |  |
|  |  | Aged e„× |  | 20 |  |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |

Section B: Household Socio-Economic Information

| Sl. No. | Questions and Filters | Coding Categories |  |  |  | Code | Skip |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Please mention the household land information pattern. (Please Read Out) `qv K‡i Avcbv†`i cwiev‡ii Rwg msµvš— Z_¨¸†jv ejyb¦ (c‡o †kvbvb) | Ownership Pattern (gvwjKvbvi aib) | Code (†KvW) |  |  | Amount of Land (decimals) (Rwgi cwigvb †Wwmgv‡j) | Total Current Value of Land (†gvU Rwgi eZ©gvb gyj¨) |  |
|  |  | Homestead Land emZevwoi Rwg | 01 |  |  |  |  |  |
|  |  | Owned Agricultural Land K…wlRwg | 02 |  |  |  |  |  |
|  |  | Owned Shrimp Gher wPswoi †Ni | 03 |  |  |  |  |  |
|  |  | Fish Culture in Owned Pond gvQ Pv‡li cyKzi | 04 |  |  |  |  |  |
|  |  | Fallow Land Abvev`x Rwg/cwZZ Rwg | 05 |  |  |  |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |  |
|  | What amount of land is at present owned by the female members of the above mentioned land? Dc‡i †hme RvqMv Rwgi K_v ej‡jb Zvi g‡a¨ Avcbv‡`i cwiev‡ii bvix m`m¨‡`i gvwjKvbvq wK cwigvb Rwg Av‡Q? | ……………..Decimal ---------------†Wwmgvj |  |  |  |  |  |  |
|  | Please describe the ownership of household assets according to sex in the given format. (Please Read Out) (Sex code: Male=1 Female=2 Both= 3) `qv K‡i ewY©Z wRwbm¸†jvi g‡a¨ bvix -cyi“l wnmv‡e gvwjKvbvi m¤cwK©Z welq¸wj eY©bv Ki“b¦ (c‡o †kvbvb) (wj½ †KvWt cyi“l=1, bvix=2, Df‡qB=3) | Asset |  | Code |  | Quantity | Sex Code |  |
|  |  | House evwo |  | 01 |  |  |  |  |
|  |  | Business/ Shop structure e¨vemv/†`vKvb |  | 02 |  |  |  |  |
|  |  | Radio †iwWI |  | 03 |  |  |  |  |
|  |  | TV/VCD wUwf/wfwmwW |  | 04 |  |  |  |  |
|  |  | Mobile Phone †gvevBj †dvb |  | 05 |  |  |  |  |
|  |  | Livestock Mevw` cï |  | 06 |  |  |  |  |
|  |  | Poultry Lvgvi |  | 07 |  |  |  |  |
|  |  | Boat †bŠKv |  | 08 |  |  |  |  |
|  |  | Fishing Instruments gvQ aivi wRwbmcÎ |  | 09 |  |  |  |  |
|  |  | Rickshaw/ Van/ Related others wiKmv/f¨vb/Ab¨vb¨ hvbevnb |  | 10 |  |  |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |  |
|  | What is the current total monthly income of your household? (From different sources) (Single response) eZ©gv‡b Avcbvi cwiev†ii gvwmK Avq KZ? (wewfbœ Drm wgwj‡q) (GKwU DËi n‡e) | Up to BDT. 5, 000 5,000/- UvKv ch©š— |  |  |  | 01 |  |  |
|  |  | BDT. 5, 001 – 10, 000 5,001/- †_‡K 10,000/- UvKv |  |  |  | 02 |  |  |
|  |  | BDT. 10, 001- 15, 000 10,001/- †_‡K 15,000/- UvKv |  |  |  | 03 |  |  |
|  |  | BDT. 15, 001 – 20, 000 15,001/- †_‡K 20,000/- UvKv |  |  |  | 04 |  |  |
|  |  | BDT. 20, 001 – 25, 000 20,001/- †_‡K 25,000/- UvKv |  |  |  | 05 |  |  |
|  |  | BDT. 25, 001- 30, 000 25,001/- †_‡K 30,000/- UvKv |  |  |  | 06 |  |  |
|  |  | BDT. 30, 001 – 35, 000 30,001/- †_‡K 35,000/- UvKv |  |  |  | 07 |  |  |
|  |  | BDT. 35, 001 – 40, 000 35,001/- †_‡K 40,000/- UvKv |  |  |  | 08 |  |  |
|  |  | BDT. 40, 001 – 45, 000 40,001/- †_‡K 45,000/- UvKv |  |  |  | 09 |  |  |
|  |  | BDT. 45, 001 – 50, 000 45,001/- †_‡K 50,000/- UvKv |  |  |  | 10 |  |  |
|  |  | More than BDT. 50, 001 50,000/- UvKvi Dc‡i |  |  |  | 11 |  |  |
|  | Which household class do you belong to wealth-wise? Avw_©K Ae¯’v we‡ePbvq Avcwb †Kvb †kªYxi Aš—f©z³ e‡j Avcwb g‡b K‡ib? | Very Poor Pig `wi`ª |  |  |  | 1 |  |  |
|  |  | Poor `wi`ª |  |  |  | 2 |  |  |
|  |  | Middle ga¨weË |  |  |  | 3 |  |  |
|  |  | Rich abx |  |  |  | 4 |  |  |
|  |  | Very rich weËkvjx |  |  |  | 5 |  |  |
|  | What are the sources of your drinking and domestic water? (Multiple Response) Avcbviv †Kv_v †_‡K LvIqvi Ges M„n¯’vwj Kv‡Ri Rb¨ cvwb wb‡q Av‡mb? (GKvwaK DËi m¤¢e) | Deep tube well Mfxi bjK’c |  |  |  | 01 |  |  |
|  |  | Shallow tube well AMfxi bjK’c |  |  |  | 02 |  |  |
|  |  | Pond/ Ditch/ wetland cyKz‡ii cvwb |  |  |  | 03 |  |  |
|  |  | River b`xi cvwb |  |  |  | 04 |  |  |
|  |  | Dug well LbbK…Z Kzqvi cvwb |  |  |  | 05 |  |  |
|  |  | Pipeline/ Supply water mvc­vB‡qi cvwb |  |  |  | 06 |  |  |
|  |  | Pond sand Filter (PSF) cyKz‡ii cwi‡kvwaZ cvwb |  |  |  | 07 |  |  |
|  |  | Rainwater harvesting system (RWHS) e„wói cvwb msi¶‡bi gva¨‡g |  |  |  | 08 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |  |
|  | What type of latrine do you use? (Single Response) (Please observe and then circle the code) Avcbviv wK ai‡bi ev_i“g/cvqLvbv/ শৌচাগার e¨envi K‡ib? (GKwU DËi n‡e) (mivmwi wR‡Ám bv K‡i `qv K‡i ch©‡e¶Y Ki“b Ges Zvici †KvW mv‡K©j Ki“b) | Septic latrine †mcwUK U¨vsK j¨vwUªb |  |  |  | 1 |  |  |
|  |  | Ring slab/offset latrine (water sealed) ¯¬ve j¨vwUªb (IqvUvi wmjW) |  |  |  | 2 |  |  |
|  |  | Pit/covered deep latrine wcU/XvKbvIqvjv j¨vwUªb |  |  |  | 3 |  |  |
|  |  | Ring slab/offset latrine (without water sealed) ¯¬ve j¨vwUªb (IqvUvi wmjW Qvov) |  |  |  | 4 |  |  |
|  |  | Peat/un- covered deep latrine wcU/XvKbvwenxb j¨vwUªb |  |  |  | 5 |  |  |
|  |  | Hanging/open latrine Szjš— /Db¥y³ j¨vwUªb |  |  |  | 6 |  |  |
|  |  | No latrine ev_i“g/cvqLvbv/ শৌচাগার †bB |  |  |  | 7 |  |  |
|  | How many income earning members are there in your household? Avcbv‡`i evwo‡Z KZRb DcvR©bKvix m`m¨ Av‡Qb? | …..……………………..Male -------------------------cyi“l |  |  |  |  |  |  |
|  |  | ………………………Female -----------------------gwnjv |  |  |  |  |  |  |
|  |  | ………………………….Total ----------------------†gvU |  |  |  |  |  |  |
|  | Have you faced any difficulty regarding income earning activities in past 2 years? Avcbviv Kx weMZ 2 eQ‡i Avcbv‡`i RxweKv wbe©v‡n †Kv†bv cÖKvi Amyweavi m¤§yLxb n‡q‡Qb? | Yes n¨vu |  |  |  | 1 | 210 |  |
|  |  | No bv |  |  |  | 2 | 212 |  |
|  | If yes, in which months do you usually face difficulty?(Multiple Response) hw` n‡q _v‡Kb Zvn‡j †Kvb gv‡m mvaviYZ Avcbviv ¶wZMÖ¯’ n‡q _v‡Kb? (GKvwaK DËi m¤¢e) | Boishakh ˆekvL |  |  |  | 01 |  |  |
|  |  | Jaishtha ˆR¨ô¨ |  |  |  | 02 |  |  |
|  |  | Ashar Avlvp |  |  |  | 03 |  |  |
|  |  | Srabon kªveY |  |  |  | 04 |  |  |
|  |  | Vadra fv`ª |  |  |  | 05 |  |  |
|  |  | Ashin Avwk¦b |  |  |  | 06 |  |  |
|  |  | Kartik KvwZ©K |  |  |  | 07 |  |  |
|  |  | Ogrohayon ANªvY |  |  |  | 08 |  |  |
|  |  | Poush †cŠl |  |  |  | 09 |  |  |
|  |  | Magh gvN |  |  |  | 10 |  |  |
|  |  | Falgun dvj¸b |  |  |  | 11 |  |  |
|  |  | Chaitra ˆPÎ |  |  |  | 12 |  |  |
|  | Has the difficulty been reduced in past 2 years compared to the years before the programme intervention? weMZ 2 eQ‡i wK GB mgm¨v K‡g‡Q Av‡Mi †P‡q? (†cÖvMÖv‡gi Av‡Mi Ae¯’vi mv‡_ Zzjbv K‡i ejyb) | Yes n¨vu |  |  |  | 1 |  |  |
|  |  | No bv |  |  |  | 2 |  |  |
|  | How much do you spend monthly, on average, in the given sectors? (Please read out) GLb Avwg Avcbv‡K wKQz Lv‡Zi bvg eje †h¸‡jv‡Z Avcbviv gvwmK KZ LiP K‡ib ej‡eb¦ (c‡o †kvbvb) | Source of Expenditure E¨v‡qi LvZ |  |  |  | Code | Amount UvKvi cwigvb |  |
|  |  | Food (including value of quantity consumed from own production) Lv`¨ eve` (wb‡Ri Drcvw`Z `ªe¨ †_‡K µq mn) |  |  |  | 01 | ………………Taka ---------------UvKv |  |
|  |  | Education wk¶v eve` |  |  |  | 02 | ………………Taka ---------------UvKv |  |
|  |  | Energy (electricity, fuel) R¡vjvwb eve` (we`¨yr, R¡vjvwb) |  |  |  | 03 | ………………Taka ---------------UvKv |  |
|  |  | Transportation (mobile/telephone bills) hvZvqvZ I †hvMv‡hvM eve` (hvbevn†Yi fvov I †gvevBj/†Uwj‡dvb wej) |  |  |  | 04 | ………………Taka ---------------UvKv |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  | ………………Taka ---------------UvKv |  |
|  | How much do you spend yearly, on average, in the given sectors? (Please read out) GLb Avwg Avcbv‡K wKQz Lv‡Zi bvg eje †h¸‡jv‡Z Avcbviv evrmwiK KZ LiP K‡ib ej‡eb¦ (c‡o †kvbvb) | House repair Ni †givgZ eve` |  |  |  | 01 | ………………Taka ---------------UvKv |  |
|  |  | Various type of repair Ab¨vb¨ †givgZ eve` |  |  |  | 02 | ………………Taka ---------------UvKv |  |
|  |  | Cloth †cvkvK µq eve` |  |  |  | 03 | ………………Taka ---------------UvKv |  |
|  |  | Cost of cultivation (seed, fertilizer, irrigation, tractor, etc.) Pvlevm/K…wlKvR eve` (exR, mvi, †mP, Îv±i, BZ¨vw`) |  |  |  | 04 | ………………Taka ---------------UvKv |  |
|  |  | Medical purpose (normal and disaster period) wPwKrmv eve` |  |  |  | 05 | ………………Taka ---------------UvKv |  |
|  |  | Festival Drme/AbylVvb eve` |  |  |  | 06 | ………………Taka ---------------UvKv |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  | ………………Taka ---------------UvKv |  |
|  | Do you have any savings? Avcbvi/Avcbvi cwiev‡ii wK †Kvb mÂq Av‡Q? | Yes n¨vu |  |  |  | 1 | 215 |  |
|  |  | No bv |  |  |  | 2 | 216 |  |
|  |  | Don’t know/Can’t say Rvwbbv/ej‡Z cvwibv |  |  |  | 9 |  |  |
|  | If yes, for what purpose did you save? (Multiple Response) hw` †_‡K _v‡K Zvn‡j †Kb mÂq K‡i‡Qb ej‡eb wK? (GKvwaK DËi m¤¢e) | To reduce vulnerability/risk to disaster `y‡h©vM Gi SzuwK/`y‡h©vMRwbZ `ye©jZv Kgvbi Rb¨ |  |  |  | 01 |  |  |
|  |  | To buy assets m¤c` †Kbvi Rb¨ |  |  |  | 02 |  |  |
|  |  | To invest into a new business bZzb †Kvb e¨emvq UvKv LvUvbi Rb¨ |  |  |  | 03 |  |  |
|  |  | For the purpose of children’s education †Q‡j‡g‡q‡`i wk¶vi Rb¨ |  |  |  | 04 |  |  |
|  |  | For son/daughter’s marriage †Q‡j‡g‡q‡`i Rb¨ we†qi Rb¨ |  |  |  | 05 |  |  |
|  |  | Haven’t plan anything yet GLbI cwiKíbv Kwiwb |  |  |  | 06 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |  |
|  | Have your household received any amount of credit/loan in last 12 months? Avcbvi cwievi †_‡K wK weMZ 12 gv‡m †Kvb FY/UvKv avi †bqv n‡q‡Q? | Yes n¨vu |  |  |  | 1 | 217 |  |
|  |  | No bv |  |  |  | 2 | 221 |  |
|  | If yes, from which sources and who have received the credit/loan? (Multiple Response) (Sex code: Male=1, Female=2, Both= 3) hw` †bqv n‡q _v‡K Zvn‡j †Kv_v †_‡K †bqv n‡q‡Q Ges †K wb‡q‡Q? (GKvwaK DËi m¤¢e) (wj½ †KvWt cyi“l=1, bvix=2, Df‡qB=3) | Source Drm |  |  | Code †KvW | Sex Code wj½ †KvW |  |  |
|  |  | GO miKvwi cÖwZôvb †_‡K |  |  | 01 |  |  |  |
|  |  | NGO GbwRI †_‡K |  |  | 02 |  |  |  |
|  |  | Dadon/ Mohajon/ Foria `v`b/gnvRb/dwiqv †_‡K |  |  | 03 |  |  |  |
|  |  | Relative AvÍx‡qi KvQ †_‡K |  |  | 04 |  |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |  |
|  | What amount of credit/loan have you received? hw` wb‡q _v‡Kb Zvn‡j wK cwigvY FY wb‡q‡Qb? | …..……………………..Male -------------------------cyi“l |  |  |  |  |  |  |
|  |  | ………………………Female -----------------------gwnjv |  |  |  |  |  |  |
|  |  | ………………………….Total ----------------------†gvU |  |  |  |  |  |  |
|  | For what purposes have you spent the received credit/loan? (Multiple Response) †Kvb Lv‡Z Avcbviv GB UvKv e¨q K‡i‡Qb? (GKvwaK DËi m¤¢e) | Food purchase Lvevi wKb‡Z |  |  |  | 01 |  |  |
|  |  | Education †Q‡j‡g‡qi covïbvi Rb¨ |  |  |  | 02 |  |  |
|  |  | Energy (Power, thatch, kerosene) Rvjvwb/we`¨yr/Lo/‡Kiwmb |  |  |  | 03 |  |  |
|  |  | Transport hvZvqvZ/hvbevnb |  |  |  | 04 |  |  |
|  |  | Disaster preparedness `y‡h©vM cÖ¯‘wZ/cÖkgb |  |  |  | 05 |  |  |
|  |  | House construction evwo †givgZ |  |  |  | 06 |  |  |
|  |  | Various types of construction (general and disaster period) wewfbœ wbg©vY Kv‡Ri Rb¨ (Ggwb mg‡q Ges `y‡h©v‡Mi mg‡q) |  |  |  | 07 |  |  |
|  |  | Cloth Kvco †Kbvi Rb¨ |  |  |  | 08 |  |  |
|  |  | Tractor U¨©v±i †Kbvi Rb¨ |  |  |  | 09 |  |  |
|  |  | Medical (natural and disaster period) wPwKrmvi Rb¨ (Ggwb mg‡q Ges `y‡h©v‡Mi mg‡q) |  |  |  | 10 |  |  |
|  |  | Festival Drme/AbylVvb Dcj‡¶ |  |  |  | 11 |  |  |
|  |  | Debt pay FY cwi‡kva Ki‡Z |  |  |  | 12 |  |  |
|  |  | Dowry †g‡qi we‡q†Z †hŠZzK †`qvi Rb¨ |  |  |  | 13 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |  |
|  | What amount of loan is unpaid up to this time in your family? GLb ch©š— Gi g‡a¨ wK cwigvY FY †kva Kiv evwK Av‡Q? | ………………………….Taka --------------------------UvKv |  |  |  |  |  |  |
|  | Do you utilize the natural resources in your area in your day to day life? Avcbviv wK ˆ`bw›`b Kv‡R GjvKvi cÖvK…wZK m¤c‡`i (Lwbi AvKwiK, MvQcvjv, ebR½j/cvnvo, b`x/cyKzi/Sibv, cv_i/gvwU/evwj, BZ¨vw`) †Kvb e¨envi K‡i _v‡Kb? | Yes n¨vu |  |  |  | 1 |  | 222 |
|  |  | No bv |  |  |  | 2 |  | 223 |
|  | If yes, how they use these natural resources? (Multiple Response)¦ hw` K‡i _v‡Kb Zvn‡j wKfv‡e K‡ib? (GKvwaK DËi m¤¢e) | For household purpose M„n¯’vwj Kv‡R |  |  |  | 01 |  |  |
|  |  | For income earning activities/livelihood purpose RxweKv wbe©v‡ni Rb¨ |  |  |  | 02 |  |  |
|  |  | For disaster management `y‡h©vM cÖkg‡bi Rb¨ |  |  |  | 03 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |  |
|  | Are women in your area engaged in any type of income generating activities? Avcbv‡`i GjvKvi gwnjviv wK †Kvb iKg Avq DcvR©bKvix Kg©Kv‡Êi mv‡_ RwoZ? | Yes n¨vu |  |  |  | 1 |  | 224 |
|  |  | No bv |  |  |  | 2 |  | 301 |
|  | If yes, what are those activities? (Multiple Response) hw` _v‡Kb Zvn‡j †m¸‡jv wK ai‡bi Kg©KvÊ? (GKvwaK DËi m¤¢e) | Agricultural crop production/farming K…wlKvR |  |  |  | 01 |  |  |
|  |  | Livestock and poultry cïcvjb I Lvgvi |  |  |  | 02 |  |  |
|  |  | Tailor `wR© |  |  |  | 03 |  |  |
|  |  | Food for work/money (soil cutting, road maintenance, etc.) Kv‡Ri wewbg‡q Lv`¨ (gvwU KvUv, iv¯—v wVK Kiv, BZ¨vw`) |  |  |  | 04 |  |  |
|  |  | Dry Fish Processing ïuUwK cÖwµqvRvZKiY |  |  |  | 05 |  |  |
|  |  | Crab collection KvuKov aiv |  |  |  | 06 |  |  |
|  |  | Fish farming gvQ Pvl |  |  |  | 07 |  |  |
|  |  | Shrimp culture wPswo Pvl |  |  |  | 08 |  |  |
|  |  | Handicraft (swing, handloom, cottage, etc.) nv‡Zi KvR/ ¶z`ª KzwUi wkí (†mjvB, ZvuZ, BZ¨vw`) |  |  |  | 09 |  |  |
|  |  | Rice Processing Pvj cÖwµqvRvZKiY |  |  |  | 10 |  |  |
|  |  | Fruit/timber production KvVz‡i/dj Drcv`K |  |  |  | 11 |  |  |
|  |  | Business e¨vemv |  |  |  | 12 |  |  |
|  |  | Service PvKwi |  |  |  | 13 |  |  |
|  |  | Work abroad we‡`‡k KvR K‡ib |  |  |  | 14 |  |  |
|  |  | Housewife M„wnYx |  |  |  | 15 |  |  |
|  |  | Housework (paid work) M„ncwiPvwiKv |  |  |  | 16 |  |  |
|  |  | Small Shop †QvU †`vKvb |  |  |  | 17 |  |  |
|  |  | Teacher wk¶K/wkw¶Kv |  |  |  | 18 |  |  |
|  |  | Forest resource collector (bawali/mouali) evIqvwj/†gŠqvj |  |  |  | 19 |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |  |
|  | Is there any difference between the payments made to the male and female workers? gwnjv Ges cyi“l Kg©x‡`i cvwikªwgK G wK †Kvb cv_©K¨ Av‡Q? | Yes n¨vu |  |  |  | 1 |  |  |
|  |  | No bv |  |  |  | 2 |  |  |

Section C: Climate Change Impact

| Sl. No. | Questions and Filters | Coding Categories | Code | Skip |
| --- | --- | --- | --- | --- |
|  | Have you heard about climate change? Avcwb wK Rjevqy cwieZ©b m¤c‡K© ï‡b‡Qb? | Yes n¨vu | 1 | 302 |
|  |  | No bv | 2 | 304 |
|  | If yes, from where have you heard about it? (Multiple Response) hw` ï‡b _v‡Kb †Kv_v †_‡K ï‡b‡Qb? (GKvwaK DËi m¤¢e) | Observation by own self wb‡Ri ch©‡e¶‡Yi gva¨‡g | 01 |  |
|  |  | Local elite person ¯’vbxq MY¨gvb¨ e¨vw³‡`i KvQ †_‡K | 02 |  |
|  |  | Teacher GjvKvi wk¶K/wkw¶Kvi KvQ †_‡K | 03 |  |
|  |  | NGO workers GbwRI Kg©x‡`i KvQ †_‡K | 04 |  |
|  |  | Local government representative ¯’vbxq miKvi cÖwZwbwa‡`i KvQ †_‡K | 05 |  |
|  |  | Government worker (block supervisor, health worker) miKvwi Kg©x‡`i KvQ †_‡K (e­K mycvi fvBRvi, ¯^v¯’¨ Kg©x‡`i KvQ †_‡K) | 06 |  |
|  |  | Colleagues mnKigx‡`i KvQ †_‡K | 07 |  |
|  |  | Friends eÜy-evÜex‡`i KvQ †_‡K | 08 |  |
|  |  | Research paper M‡elYv cÎ †_‡K | 09 |  |
|  |  | Mass media MY †hvMv‡hvM gva¨g †_‡K | 10 |  |
|  |  | Not sure wbwðZfv‡e ej‡Z cviwQ bv | 11 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | How does climate change affect your/your family member’s life? (Multiple Response) Rjevqy cwieZ©b wKfv‡e Avcbvi ev Avcbvi cwiev‡ii Dci cÖfve †d‡j? (GKvwaK DËi m¤¢e) | Damaged assets m¤c‡`i ¶wZ mvab K‡i | 01 |  |
|  |  | Damaged crops dm‡ji ¶wZ mvab K‡i | 02 |  |
|  |  | Caused death cÖvYnvwb N‡U | 03 |  |
|  |  | Affecetd livelihood options RxweKvi Dci cÖfve †d‡j | 04 |  |
|  |  | Affected children’s education †Q‡j‡g‡qi covïbvi Dci cÖfve †d‡j | 05 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Have your household income sources or household assets been affected by climatic/natural disasters in last 2 years? Avcbvi cwiev‡ii RxweKv wbe©v‡ni gva¨g ev Avcbv‡`i †Kvb m¤c` wK weMZ 2 eQ‡i cÖvK…wZK `y‡h©v‡Mi gva¨‡g ¶wZMÖ¯’ n‡q‡Q? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | Have climatic disaster affected your children’s education in the last 2 years? cÖvK…wZK `y‡h©v‡Mi Kvi‡Y wK weMZ 2 eQ‡i Avcbv‡`i cwiev‡i †Q‡j-‡g‡q‡`i cov‡kvbvi †Kvb ¶wZ n‡q‡Q? | Yes n¨vu | 1 | 306 |
|  |  | No bv | 2 | 308 |
|  | If yes, what type(s) of children dropped out mainly? hw` n‡q _v‡K Zvn‡j †Kvb ai‡bi wkïiv mvaviYZ ¯‹zj †_‡K S‡i c‡o/Kv‡`i wk¶vjvf ¶wZMÖ¯’ nq? | Male child †Q‡j wkï | 1 |  |
|  |  | Female child †g‡q wkï | 2 |  |
|  | What happened to the children when they dropped out from the school? hLb wkïiv S‡i c‡o ZLb Zviv wK K‡i? | Involved in HH work evwoi KvR K‡i | 01 |  |
|  |  | Involved in income generating activities cwievi †K DcvR©‡b mvnvh¨ K‡i | 02 |  |
|  |  | Do nothing wKQzB K‡i bv | 03 |  |
|  |  | Got married we†q n‡q hvq | 04 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Did the project help you in some way to recover or prepare in advance? GB †cÖv‡R± wK Avcbv‡`i `y‡h©vM Avmvi Av‡MB Zv †_‡K i¶v †c‡Z ev Gi ¶q¶wZ Kgv†Z †Kvbfv‡e mvnvh¨ K‡i‡Q? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |

Section D: Migration

| Sl. No. | Questions and Filters | Coding Categories | Code | Skip |
| --- | --- | --- | --- | --- |
|  | Did your family members migrate from here in last 2 years? Avcbv‡`i cwievi †_‡K †KD wK weMZI 2 eQ‡i GB GjvKv †_‡K Ab¨ †Kv_vI P‡j wM‡q‡Q? | Yes n¨vu | 1 | 402 |
|  |  | No bv | 2 | 405 |
|  | If yes, which household member(s) migrated? hw` wM‡q _v‡K Zvn‡j Kviv wM‡q‡Q? | Male cyi“l | 1 |  |
|  |  | Female gwnjv | 2 |  |
|  |  | Both Df‡qB | 3 |  |
|  | What is the nature of migration? GB ¯’vbvš—‡ii aib wK iKg? (wZwb wK ¯’vqxfv‡e P‡j wM‡q‡Qb bv mvgwqKfv‡e wM‡q‡Qb?) | Permanent ¯’vqxfv‡e/wPiZ‡i | 1 |  |
|  |  | Temporary mvgwqKfv‡e/wKQzw`‡bi Rb¨ | 2 |  |
|  | Why did s/he migrate?(Multiple Response) wZwb †Kb P‡j wM‡q‡Qb? (GKvwaK DËi m¤¢e) | To have good job fvj PvKwii Avkvq | 01 |  |
|  |  | For economic purpose A_©‰bwZK Kvi‡Y | 02 |  |
|  |  | For educational purpose covïbv Ki‡Z | 03 |  |
|  |  | Due to health problems Amy¯’Zvi Kvi‡Y/wPwKrmv wb‡Z | 04 |  |
|  |  | Could not cope with the climatic disasters ˆeix AvenvIqvi mv‡_ gvwb‡q wb‡Z cv‡ibwb | 05 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Has women trafficking in your area due to disaster been reduced in last 2 years? Avcbv‡`i GjvKv‡Z wK cÖvK…wZK `y‡h©v‡Mi Kvi‡Y bvix cvPvi Gi NUbv weMZI 2 eQ‡i Av‡Mi †P‡q K‡g‡Q? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  |  | No such incident takes place bvix cvPv‡ii NUbv N‡U bv | 3 |  |

Section E: Gender Division of Labor and Decision Making Rights

| Sl. No. | Questions and Filters |  |  |  |  | Coding Categories |  |  |  |  |  | Code |  | Skip |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Describe the decision making process of your family by Sex. (Plesae Read Out) Avcbv‡`i cwiev‡i wewfbœ Kv‡Ri †¶‡Î wm×vš— MÖnY Gi †¶‡Î bvix-cyi“l Gi fzwgKv wbY©q Ki“b¦ (c‡o †kvbvb) Sex Code: Male=1, Female=2. Both=3 (wj½ †KvWt cyi“l=1, bvix=2, Df‡qB=3) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Code | Normal Period ¯^vfvweK mg‡q |  |  |  |  | Disaster Period `y‡h©vM Gi mg‡q |  |  |  | Post-Disaster `y‡h©vM cieZ©x mg‡q |  |  |  |
|  | Meal Lvevi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Meal preparation ivbœv Kivi †¶‡Î | 01 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Meal distribution Lvevi cwi‡ekb Kivi †¶‡Î | 02 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Meet up food deficit Lv`¨ NvUwZ †gUvbi †¶‡Î | 03 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Selling of Household assets cvwievwiK m¤cwË wewµ Kivi †¶‡Î |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Sell livestock Mevw` cï wewµ Kivi †¶‡Î | 04 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Sell food crops Lv`¨km¨ wewµ Kivi †¶‡Î | 05 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Sell seeds exR wewµ Kivi †¶‡Î | 06 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Sell ornaments Mnbv wewµ Kivi †¶‡Î | 07 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Sell trees MvQ wewµ Kivi †¶‡Î | 08 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Sell houses evwo wewµ Kivi †¶‡Î | 09 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Sell land Rwg wewµ Kivi †¶‡Î | 10 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Activity | Code |  | Normal Period ¯^vfvweK mg‡q |  |  |  |  | Disaster Period `y‡h©vM Gi mg‡q |  |  | Post-Disaster `y‡h©vM cieZ©x mg‡q |  |  |  |
|  | Buying Household Assets cvwievwiKfv‡e m¤cwË µq Kivi †¶‡Î |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Buy livestock Mevw` cï µq Kivi †¶‡Î | 11 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Buy food crops Lv`¨km¨ µq Kivi †¶‡Î | 12 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Buy seeds exR µq Kivi †¶‡Î | 13 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Buy jewelry Mnbv µq Kivi †¶‡Î | 14 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Buy trees MvQ µq Kivi †¶‡Î | 15 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Buy house evwo µq Kivi †¶‡Î | 16 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Buy land Rwg µq Kivi †¶‡Î | 17 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Receive Credit FY †bqv |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Receive credit from Mohajon gnvR‡bi KvQ †_‡K FY †bqvi †¶‡Î | 18 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Receive credit from relatives AvÍxq-¯^R‡bi KvQ †_‡K FY †bqvi †¶‡Î | 19 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Receive credit from bank e¨vsK †_‡K FY †bqvi †¶‡Î | 20 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Receive credit from NGO GbwRI †_‡K FY †bqvi †¶‡Î | 21 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Receive credit from GO miKvwi cÖwZôvb †_‡K FY †bqvi †¶‡Î | 22 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Agricultural Work K…wlKvR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Type of crop to cultivate wK ai‡bi km¨ Drcv`b n‡e †mB wm×vš— †bqvi †¶‡Î | 23 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Mortgage out land Rwg eÜK ivLvi †¶‡Î | 24 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Household Work M„n¯’vwj KvR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collection of water cvwb Avbv | 25 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Collection of natural resources (e.g. fuel wood) cÖvK…wZK m¤c` msMÖ‡ni †¶‡Î (R¡vjvwb, KvV, BZ¨vw`) | 26 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Household Decision evwoi †h‡Kv‡bv wm×vš— †bqvi †¶‡Î |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Engage in new income generating activities bZzb †Kvb DcvR©b¶g Kv‡R †XvKvi †¶‡Î | 27 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Give marriage we‡q †`qvi †¶‡Î | 28 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Conceiving a baby ev”Pv/mš—vb †bqvi †¶‡Î | 29 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Use saving mÂq e¨q Kivi †¶‡Î | 30 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | VGD/VGF wfwRwW/wfwRGd †bqvi †¶‡Î | 31 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Communication †hvMv‡hvM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Female going outside the homestead †g‡q‡`i evwoi evB‡i hvIqvi wm×vš— †bqvi †¶‡Î | 32 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Female going to work †g‡q‡`i KvR Kivi †¶‡Î | 33 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Male going to work cyi“l‡`i Kvh Kivi †¶‡Î | 34 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Education of Children †Q‡j‡g‡q‡`i covïbv msµvš— wm×vš— †bqvi †¶‡Î | 35 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 |  | 3 |
|  | Disaster Preparedness/Prevention `y‡h©vM c~e© cÖ¯‘wZ/cÖwZKvi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Going to a shelter Avkªq †K‡›`ª hvIqvi †¶‡Î | 36 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 | 3 |  |
|  | Engage in alternative livelihood activities Ab¨ †Kvb RxweKv wbe©vn Kivi †¶‡Î | 37 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 | 3 |  |
|  | Collection of relief material ÎvY mvgMÖx msMÖ‡ni †¶‡Î | 38 | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 | 3 |  |
|  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 1 |  | 2 |  | 3 | 1 |  | 2 | 3 | 1 | 2 | 3 |  |
|  | Do the women now (after the programme intervention) face any problem due to climatic disaster during disaster and after disaster? Avcbv‡`i GjvKv‡Z wK †g‡qiv wK `y‡h©v†Mi mgq Ges `y‡h©vM cieZ©x mg‡q †Kvb mgm¨vi m¤§yLxb nq? |  |  |  |  | Yes n¨vu |  |  |  |  |  | 1 |  | 503 |  |
|  |  |  |  |  |  | No bv |  |  |  |  |  | 2 |  | 601 |  |
|  | What types of problems do they face? (Multiple Response) n‡j wK ai‡bi mgm¨vi m¤§yLxb nq? (GKvwaK DËi m¤¢e) |  |  |  |  | Insecurity wbivcËvi Afve |  |  |  |  |  | 01 |  |  |  |
|  |  |  |  |  |  | Domestic violence cvwievwiK wbh©vZb |  |  |  |  |  | 02 |  |  |  |
|  |  |  |  |  |  | Increased work load Kv‡Ri cwigvY †e‡o hvIqv |  |  |  |  |  | 03 |  |  |  |
|  |  |  |  |  |  | Increased drop out from school ¯‹zj †_‡K S‡i cov wkïi msL¨v †e‡o hvIqv |  |  |  |  |  | 04 |  |  |  |
|  |  |  |  |  |  | Restriction of mobility (to shelter, relief collection, etc.) PjvP‡j Amyweav m„wó (Avkªq †K‡›`ª hvIqv, ÎvY msMÖn, BZ¨vw`) |  |  |  |  |  | 05 |  |  |  |
|  |  |  |  |  |  | Water and sanitation problem cvwb I ev_i“g e¨envi msµvš— Amyweav |  |  |  |  |  | 06 |  |  |  |
|  |  |  |  |  |  | Healthcare problem ¯^v¯’¨ msµvš— Amyweav |  |  |  |  |  | 07 |  |  |  |
|  |  |  |  |  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |  |  |  |  |  |  |  |

Section F: Coping and Adaptation Strategies

| Sl. No. | Questions and Filters | Coding Categories | Code | Skip |
| --- | --- | --- | --- | --- |
|  | Do you think the barriers to disaster preparedness in your family have been reduced after the programme intervention? Avcwb wK g‡b K‡ib †h GB †cÖv‡R‡±i c‡i Avcbv‡`i cwiev‡i `y‡h©v†Mi c~‡e© cÖ¯‘wZ †bqvi †¶‡Î †hme evav wQj †m¸‡jv Av‡Mi †P‡q K‡g †M‡Q? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | Is there any special initiative taken for women to cope with disasters through the programme? GB †cÖvMÖv‡gi AvIZvq gwnjv‡`i Rb¨ wK `y‡h©vM †gvKv‡ejv Kivi Rb¨ †Kvb we‡kl e¨e¯’v/D‡`¨vM †bqv n‡q‡Q? | Yes n¨vu | 1 | 603 |
|  |  | No bv | 2 | 604 |
|  | If yes, what are those initiatives? (Open ended) hw` n‡q _v‡K Zvn‡j †m¸‡jv wK `qv K‡i ej‡eb wK? (Db¥y³) |  |  |  |
|  | Is there any difference between the male and female roles in the local government and NGOs initiatives to cope with a disaster? wewfbœ GbwRI Ges miKvwi fv‡e †hme D‡`¨vM †bqv n‡q‡Q `y‡h©vM †gvKv‡ejvi Rb¨ †mLv‡b wK †Q‡j Ges †g‡q‡`I f’wgKvq †Kvb cv_©K¨ Av‡Q? | Yes n¨vu | 1 | 605 |
|  |  | No bv | 2 | 608 |
|  | If yes, what do they do during disaster preparedness? hw` †_‡K _v‡K Zvn‡j Zviv `y‡h©vM c~e©eZ©x mg‡q wK K‡i? | Male: czi“l t |  |  |
|  |  | Female: bvix t |  |  |
|  | What do they do during disaster period? Zviv `y‡h©vMKvjxb mg‡q wK K‡i? | Male: czi“l t |  |  |
|  |  | Female: bvix t |  |  |
|  | What do they do after disaster? Zviv `y‡h©vM cieZ©x mg‡q wK K‡i? | Male: czi“l t |  |  |
|  |  | Female: bvix t |  |  |
|  | Is there any disaster management committee formed in your area? Avcbv‡`i GjvKvq wK †Kvb `y‡h©vM cÖkgb KwgwU MwVZ n‡q‡Q? | Yes n¨vu | 1 | 610 |
|  |  | No bv | 2 | 609-611 |
|  | If no, do you think there is any need to form one? hw` bv _v‡K Zvn‡j Avcwb wK g‡b K‡ib †h `y‡h©vM cÖkgb KwgwU MV‡bi `iKvi Av‡Q? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | If there’s any disaster management committee, what initiatives have been taken by the disaster management committee of your area? (Multiple Response) hw` †Kvb `y‡h©vM cÖkgb KwgwU _v‡K Zvn‡j Zviv wK ai‡bi c`‡¶c wb‡q‡Q Gi g‡a¨? (GKvwaK DËi m¤¢e) | Aware everyone mevB‡K mZK© Kiv | 01 |  |
|  |  | Take to the shelter Avkªq †K‡›`ª wb‡q hvIqv | 02 |  |
|  |  | Financial help Avw_©Kfv‡e mvnvh¨ Kiv | 03 |  |
|  |  | Distribute relief ÎvY mvgMÖx weZiY | 04 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Have you or any of your family members received any training on disaster management? Avcwb ev Avcbvi cwiev‡ii †Kvb m`m¨ wK `y‡h©vM cÖkg‡bi Dci †Kvb cÖwk¶Y †c‡q‡Qb? | Yes n¨vu | 1 | 612 |
|  |  | No bv | 2 | 614 |
|  | If yes, then what types of training did you receive? (Multiple Response) hw` †c‡q _v‡Kb Zvn‡j wK ai‡bi cÖwk¶Y †c‡q‡Qb? (GKvwaK DËi m¤¢e) | Disaster preparedness `y‡h©v‡Mi c~e© cÖ¯‘wZ | 01 |  |
|  |  | Rescue training D×vi Kvh©µg Gi Dci cÖwk¶Y | 02 |  |
|  |  | Health related ¯^v¯’¨ msµvš— | 03 |  |
|  |  | Water purification and safe sanitation cvwb we†kvwaZKib Ges wbivc` ev_i“g/cvqLvbv | 04 |  |
|  |  | Leadership Building †bZ…Z¡ cÖ`vb msµvš— | 05 |  |
|  |  | Psycho-Social Training g‡bv-mvgvwRK cÖwk¶Y | 06 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | From which organization(s) did you receive the training? (Multiple Response) †Kvb cÖwZôvb †_‡K Avcwb cÖwk¶YwU †c‡q‡Qb? (GKvwaK DËi m¤¢e) | Govt. Organization miKvwi cÖwZôvb | 01 |  |
|  |  | BRAC eª¨vK | 02 |  |
|  |  | From any trained person †Kvb `¶ e¨vw³i KvQ †_‡K | 03 |  |
|  |  | From old senior †Kvb eq¯‹/AwfÁ e¨vw³i KvQ †_‡K | 04 |  |
|  |  | Neighbors cÖwZ‡ekxi KvQ †_‡K | 05 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Do you and your community women have a periodic court yard meeting? Avcbv‡`i GjvKvq gwnjv‡`i wb‡q wK wbqwgZ DVvb ˆeVK nq? | Yes n¨vu | 1 | 615 |
|  |  | No bv | 2 | 701 |
|  | If yes, how frequently do you arrange these meetings? hw` n‡q _v‡K Zvn‡j KZ w`b cici nq? | Weekly mvßvwnKfv‡e | 1 |  |
|  |  | Fortnightly 14 w`b cici | 2 |  |
|  |  | Monthly gvwmK | 3 |  |
|  | What issues are discussed in those meetings? GB ˆeVK¸‡jv †Z wK wK welq Av‡jvPbv nq? | WASH cvwb, ¯^v¯’¨ Ges ¯^v¯’¨m¤§Z cvqLvbv msµvš— welq | 1 |  |
|  |  | DRR `y‡h©v†Mi SzuwK Kgvb msµvš— welq | 2 |  |
|  |  | Raising awareness on violence against women bvixi cÖwZ mwnsmZvi wel‡q m‡PZb Kiv |  |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |

Section G: Livelihood of Women/ Capacity Building Activity

| Sl. No. | Questions and Filters | Coding Categories | Code | Skip |
| --- | --- | --- | --- | --- |
|  | Are you or any female member of your Household involved with income generation or livelihood activities? Avcwb ev Avcbvi cwiev‡i Ab¨ †Kvb bvix m`m¨ wK †Kvb DcvR©b¶g †Kvb Kv‡Ri mv‡_ RwoZ Av‡Q? | Yes n¨vu | 1 | 702 |
|  |  | No bv | 2 | 703 |
|  | If yes, what are those activities? (Multiple Response) n‡j wK ai‡bi Kv‡Ri mv‡_ RwoZ Av‡Q? (GKvwaK DËi m¤¢e) | Homestead gardening evwo‡Z mewR Drcv`b | 01 |  |
|  |  | Horticulture evwoi Av‡kcv‡k Pvlvev` | 02 |  |
|  |  | Small Poultry †QvU Lvgvi | 03 |  |
|  |  | Fish and shrimp cultivation gvQ I wPswo Pvl | 04 |  |
|  |  | Livestock Mevw` cï cvjb | 05 |  |
|  |  | Tailoring `wR© | 06 |  |
|  |  | Embroidery/ Batiks and printing G¤^ªBWvwi/evwUK Ges wcÖw›Us | 07 |  |
|  |  | Handicrafts KzwUiwkí | 08 |  |
|  |  | Small business ¶z`ª e¨emv | 09 |  |
|  |  | Net Making gvQ aivi Rvj †evbv | 10 |  |
|  |  | Dry Fish Processing ïuUwK cÖwµqvKiY | 11 |  |
|  |  | Rice Processing Pvj cÖwµqvRvZKiY | 12 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Have you/any female member of your household received training on income generation or livelihood activities? Avcwb ev Avcbvi cwiev‡ii †Kvb bvix m`m¨ wK RxweKv wbe©vn c×wZi Dci †Kvb cÖwk¶Y †c‡q‡Qb? | Yes n¨vu | 1 | 704 |
|  |  | No bv | 2 | 710 |
|  | If yes, what types of training have you/they received? (Multiple Response) hw` †c‡q _v‡Kb Zvn‡j wK‡mi Dci cÖwk¶Y †c‡q‡Qb? (GKvwaK DËi m¤¢e) | Homestead gardening evwo‡Z mewR Drcv`b | 01 |  |
|  |  | Horticulture evwoi Av‡kcv‡k Pvlvev` | 02 |  |
|  |  | Small Poultry †QvU Lvgvi | 03 |  |
|  |  | Dry Fish Processing ïuUwK cÖwµqvKiY | 04 |  |
|  |  | Cattle fatting Mevw` cï †gvUv-ZvRvKib | 05 |  |
|  |  | Tailoring `wR© | 06 |  |
|  |  | Handicrafts KzwUiwkí | 07 |  |
|  |  | Handloom ZvuZwkí | 08 |  |
|  |  | Net Making gvQ aivi Rvj †evbv | 09 |  |
|  |  | Small shop/business ¶z`ª e¨emv | 10 |  |
|  |  | Rice Processing Pvj cÖwµqvRvZKiY | 11 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | From which organization have you/they received the training? (Multiple Response) Kv‡`i KvQ †_‡K GB cÖwk¶Y †c‡q‡Qb? (GKvwaK DËi m¤¢e) | Govt. organization miKvwi cÖwZôvb | 01 |  |
|  |  | Expert from BRAC eª¨vK Gi `¶ cÖwk¶K | 02 |  |
|  |  | From any local expert ¯’vbxq †Kvb `¶ †jv‡Ki KvQ †_‡K | 03 |  |
|  |  | From old senior eq¯‹ ev AwfÁ e¨vw³i KvQ †_‡K | 04 |  |
|  |  | From other group members MÖ“‡ci Ab¨vb¨ gwnjv‡`i KvQ †_‡K (hviv cÖwk¶Y †c‡q‡Q) | 05 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Has the training contributed to better livelihood activities? GB cÖwk¶Y wK Avcbv‡`i RxweKv wbe©v‡ni Dbœq‡bi †¶‡Î †Kvb Ae`vb ivL‡Z †c‡i‡Q? | Yes n¨vu | 1 | 707 |
|  |  | No bv | 2 | 708 |
|  | If yes, please describe how? (Multiple Response) hw` †i‡L _v‡K Zvn‡j wKfv‡e? (GKvwaK DËi m¤¢e) | Increased income DcvR©b e„w×i gva¨‡g | 01 |  |
|  |  | Increased access to more livelihood options bZzb ai‡bi RxweKv wbe©v‡ni c×wZ †kLvbi gva¨‡g | 02 |  |
|  |  | Helped to identify disaster resilient livelihoods `y‡h©vM w¯’wZ¯’vcK RxweKv wbe©vn c×wZ †kLvbi gva¨‡g | 03 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Do you suggest any other training for women in future which could be helpful for you to cope with the climate change induced vulnerabilities in case of livelihood options? Avcwb wK Avi †Kvb cÖwk¶‡bi K_v ej‡Z cv‡ib hv Avcbv‡`i fwel¨‡Z `y‡h©v‡Mi Øviv m„ó RxweKv wbe©vnRwbZ mgm¨v/ `ye©jZv ¸‡jv KvwU‡q DV‡Z mvnvh¨ Ki‡Z cv‡i? | Yes n¨vu | 1 | 709 |
|  |  | No bv | 2 | 710 |
|  | If yes, what are they? (Multiple Response) hw` n¨vu nq Zvn‡j †mB cÖwk¶Y¸‡jv wK n‡Z cv‡i? (GKvwaK DËi m¤¢e) | Microfinance for better livelihood ¶z`ª F‡Yi gva¨‡g RxweKv wbe©vn | 01 |  |
|  |  | Account maintain of NGO GbwRI Gi wnmve †`Lv†kvbv | 02 |  |
|  |  | Road construction iv¯—v †givgZ | 03 |  |
|  |  | Better agricultural training DbœZ gv‡bi K…wl welqK cÖwk¶Y | 04 |  |
|  |  | Homestead gardening evwoi Av‡kcv‡k mewR evMvb Kiv | 05 |  |
|  |  | Horticulture bvm©vwi Kiv | 06 |  |
|  |  | Loan management FY e¨ve¯’vcbv | 07 |  |
|  |  | Technical training KvwiMwi cÖwk¶Y | 08 |  |
|  |  | Sericulture †ikg Pvl | 09 |  |
|  |  | Pottery g„rwkí | 10 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Do the female of your household/community have access to market for selling goods? Avcbvi ev Avcb‡`i cwievi/GjvKvq gwnjviv wK evRv‡i/nv‡U Zv‡`i Drcvw`Z wRwbm wewµ Ki‡Z cv‡ib wKbv? | Yes n¨vu | 1 | 711 |
|  |  | No bv | 2 | 720 |
|  | Where do they sell their goods? (Multiple Response) Zviv †Kv_vq G¸†jv wewµ K‡i? (GKvwaK DËi m¤¢e) | Local market ¯’vbxq evRv‡i | 01 |  |
|  |  | Upazila market Dc‡Rjv evRv‡i | 02 |  |
|  |  | District market †Rjv evRv‡i | 03 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Who help the women to sell the products in market? (Multiple Response) Kviv Zv‡`i GB wRwbm¸wj wewµ Ki‡Z mvnvh¨ K‡i? (GKvwaK DËi m¤¢e) | Women herself gwnjviv wb‡RivB wewµ K‡i | 01 |  |
|  |  | Male member of the family evwoi cyi“l m`m¨iv wewµ K‡i | 02 |  |
|  |  | Relatives AvÍxq‡`i gva¨‡g wewµ K‡i | 03 |  |
|  |  | Middlemen ga¨mË†fvMx‡`i/`vjvj‡`i/dwiqv‡`i gva¨‡g wewµ K‡i | 04 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Do the women get the actual price of their self-produced commodities? gwnjviv wK Zv‡`i Drcvw`Z `ªe¨mvgMÖxi h_vh_ g~j¨ cvq? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | Is there any discrimination between the payment of male and female sellers? gwnjv Ges cyi“l we‡µZv‡`I cÖvß `v‡gi g‡a¨ wK †Kvb cv_©K¨ _v‡K? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | Is there any obstacle for women to sell their products in the market? gwnjv‡`i evRv‡i Zv‡`i Drcvw`Z `ªe¨mvgMÖx wewµ Kivi †¶‡Î wK †Kvb iKg evavi m¤§yLxb n‡Z nq? | Yes n¨vu | 1 | 716 |
|  |  | No bv | 2 | 718 |
|  | If yes, what steps have been taken to remove the obstacles in last 2 years? (Multiple Response) hw` n‡q _v‡K Zvn‡j weMZI 2 eQ‡ii g‡a¨ wK wK c`‡¶c †bqv n‡q‡Q GB evav¸‡jv `~i Kivi Rb¨? (GKvwaK DËi m¤¢e) | Social awareness mvgwRK m‡PZbZv m„wó Kiv n‡q‡Q | 01 |  |
|  |  | Ensuring equal rights of men and women cyi“l I gwnjv‡`i mg AwaKvi wbwðZ Kivi †Póv Kiv n‡q‡Q | 02 |  |
|  |  | Development of communication system †hvMv‡hvM/hvZvqvZ e¨e¯’vi DbœwZ Kiv n‡q‡Q | 03 |  |
|  |  | Encouraging women in small business gwnjv‡`i ¶z`ª e¨emvq DrmvwnZ Kiv n‡q‡Q | 04 |  |
|  |  | No steps have been taken yet †Kvb c`‡¶c †bqv nqwb | 05 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Have the steps taken been proved to be fruitful? †hme c`‡¶c †bqv n‡q‡Q †m¸‡jv wK mdj n‡q‡Q? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | Generally what do you/your female family members do with the money earned from selling commodities? (Multiple Response) GB Drcvw`Z wRwbm wewµ K‡i Avcbviv †h UvKv cvb Zv w`‡q mvaviYZ Avcbviv wK K‡i _v‡Kb? (GKvwaK DËi m¤¢e) | Hand over the earned money to the male member of the family cwiev‡ii cyi“l m`‡m¨i Kv†Q UvKv w`‡q †`qv nq | 01 |  |
|  |  | Invest in same livelihood activities H Kv‡RB Avevi AwR©Z UvKv LvUvb nq | 02 |  |
|  |  | Invest in other livelihood activities Ab¨ †Kvb RxweKv wbe©vn c×wZ‡Z H UvKv LvUvb nq | 03 |  |
|  |  | Deposit in bank e¨vsK G Rgv Kiv nq | 04 |  |
|  |  | Invest in NGO GbwRI †Z LvUvb nq | 05 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Is that earned money sufficient to cope with climate change induced disaster? GB DcvwR©Z UvKv wK Rjevqy cwieiZ‡bi Øviv m„ó `y‡h©vM †gvKv‡ejvi Rb¨ h‡_ó e‡j Avcwb g‡b K‡ib? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | Has the climate change/disaster risk been reduced through new kind of livelihoods? †h bZzb ai‡bi RxweKv wbe©vn c×wZ Avcbv‡`i †kLvb n‡q‡Q †m¸‡jvi Øviv weMZ 2 eQ‡i Avcbv‡`i GjvKvq Rjevqy cwieZ©b ev `y‡h©vM Gi SzuwK wK wKQzUv K‡g‡Q e‡j Avcwb g‡b K‡ib? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | How the capacity of women do you think has been developed to reduce risks induced by climate change through this programme? (Multiple Response) GB †cÖvMÖv‡gi gva¨‡g Avcbv‡`i GjvKvi Rjevqy cwieZ©‡bi d‡j m„ó SzuwK Kgvbi †¶‡Î gwnjv‡`i ¶gZv wKfv‡e e„w× †c‡q‡Q e‡j Avcwb g‡b K‡ib? (GKvwaK DËi m¤¢e) | Made women aware of the climate change impact gwnjv‡`i Rjevqy cwieZ©‡bi cÖfve m¤c‡K© m‡PZb K‡i‡Q | 01 |  |
|  |  | Established participation of women in climate risk management Rjevqy cwieZ©‡bi d†j SzuwK Kgvb Ges Gi mwVK e¨e¯’vcbvi †¶‡Î gwnjv‡`i AskMÖnY cÖwZôv K‡i‡Q | 02 |  |
|  |  | Formed new small entrepreneur bZzb ¶z`ª gwnjv D‡`¨v³v m„wó K‡i‡Q | 03 |  |
|  |  | Established participation of women in local government activities gwnjv‡`i ¯’vbxq miKvwi Kg©Kv‡Ê AskMÖnY cÖwZôv K‡i‡Q | 04 |  |
|  |  | Managed new livelihood options for women (e.g. homestead gardening) gwnjv‡`i Rb¨ bZzb bZzb RxweKv wbe©vn c×wZ wkwL‡q‡Q | 05 |  |
|  |  | Ran new income generating project for women (Handicraft or others) gwnjv‡`i Rb¨ bZzb Avq DcvR©bKvix Kg©Kv‡Êi e¨e¯’v K‡i‡Q | 06 |  |
|  |  | Formed local people based organization (C.B.O) in participation of women gwnjv‡`i AskMÖn‡Y GjvKvi gvby‡li Øviv wewfbœ ms¯’v MwVZ n‡q‡Q | 07 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |

Section H: Violence against Women and Social Safety Net of Women

| Sl. No. | Questions and Filters | Coding Categories | Code | Skip |
| --- | --- | --- | --- | --- |
|  | Did you experience any violence against women in your community in last 12 months? Avcwb wK Avcbvi GjvKvq weMZ 1 eQ‡i bvixi cÖwZ NwUZ †Kvb mwnsmZvi NUbv Rv‡bb? | Yes n¨vu | 1 | 802 |
|  |  | No bv | 2 | 803 |
|  | If yes, what type of violence was it? hw` †R‡b _v‡Kb Zvn‡j †mwU wK ai‡bi mwnsmZv (kvwiwiK/gvbwmK wbh©vZb) wQj? | Torturing by husband ¯^vgxi Øviv wbh©vZb | 01 |  |
|  |  | Torturing by in laws k¦ïi evwoi †jv‡Ki Øviv wbh©vZb | 02 |  |
|  |  | Torturing by family members wb‡Ri cwiev‡ii †jv‡Ki Øviv wbh©vZb | 03 |  |
|  |  | Acid throwing GwmW wb‡¶c | 04 |  |
|  |  | Demand of Dowry †hŠZzK Gi Rb¨ Pvc cÖ‡qvM | 05 |  |
|  |  | Eve teasing Bf wUwRs | 06 |  |
|  |  | Rape al©b | 07 |  |
|  |  | Harassment nqivwb (†hŠb/gvbwmK/Ab¨ †Kvbfv‡e) | 08 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Did you or any female member in your family face any violence in your own life in last 12 months? Avcbvi cÖwZ/ Avcbvi cwiev‡ii †Kvb bvixi cÖwZ weMZ 1 eQ‡i †Kvb mwnsmZvi NUbv N‡U‡Q wK? | Yes n¨vu | 1 | 804 |
|  |  | No bv | 2 | 807 |
|  | If yes, what was it? hw` N‡U _v‡K Zvn‡j †mwU wK ai‡bi mwnsmZv (kvwiwiK/gvbwmK wbh©vZb) wQj? | Torturing by husband ¯^vgxi Øviv wbh©vZb | 01 |  |
|  |  | Torturing by in laws k¦ïi evwoi †jv‡Ki Øviv wbh©vZb | 02 |  |
|  |  | Torturing by family members wb‡Ri cwiev‡ii †jv‡Ki Øviv wbh©vZb | 03 |  |
|  |  | Acid throwing GwmW wb‡¶c | 04 |  |
|  |  | Demand of Dowry †hŠZzK Gi Rb¨ Pvc cÖ‡qvM | 05 |  |
|  |  | Eve teasing Bf wUwRs | 06 |  |
|  |  | Rape al©b | 07 |  |
|  |  | Harassment nqivwb (†hŠb/gvbwmK/Ab¨ †Kvbfv‡e) | 08 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Was it acceptable to you? GUv wK Avcbvi Kv‡Q MÖnb†hvM¨ wQj? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | Was any action taken against it? GB NUbvi wei“‡× wK †Kvb c`‡¶c †bqv n‡qwQj? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | Do the women face any social security risk due to climate change impact anymore? Avcbv‡`i GjvKvi gwnjviv wK Rjevqy cwieZ©b msµvš— †Kvb cÖfv‡ei Kvi‡Y †Kvb iKg mvgvwRK wbivcËvnxbZvq †fv‡M GLbI? | Yes n¨vu | 1 |  |
|  |  | No bv | 2 |  |
|  | Are the women aware of social safety net right provided by the government? Avcbv‡`i GjvKvi gwnjviv wK miKv‡ii wewfbœ mvgvwRK wbivcËv †eóbxi e¨vcv‡i Rv‡b? | Yes n¨vu | 1 | 809 |
|  |  | No bv | 2 | 810 |
|  |  | Don’t know/Can’t say Rvwbbv/ej‡Z cvwibv | 9 |  |
|  | Can you tell us about any such social safety net program? (Multiple Response) Avcwb wK GiKg †Kvb mvgvwRK wbivcËv †eóbxi bvg ej‡Z cvi‡eb? (GKvwaK DËi m¤¢e) | VGD wf wR wW | 1 |  |
|  |  | VGF wf wR Gd | 2 |  |
|  |  | Food for Work Kv‡Ri wewbg‡q Lv`¨ | 3 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | Is there any NGO activity beside any government program to ensure women’s social safety net? miKv‡ii cvkvcvwk Ab¨ †Kvb Gb wR I wK Avcbv‡`i G ai‡bi †Kvb mvgvwRK wbivcËv †eóbx w`‡q _v‡K? | Yes n¨vu | 1 | 811 |
|  |  | No bv | 2 | 812 |
|  | If yes, what are they? (Multiple Response) w`‡j †Kvb cÖwZôvb¸‡jv †`q? (GKvwaK DËi m¤¢e) | BRAC eª¨vK | 01 |  |
|  |  | Rupantor iƒcvš—i | 02 |  |
|  |  | TMSS wU Gg Gm Gm | 03 |  |
|  |  | RDRS Avi wW Avi Gm | 04 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  | What sustainable initiatives are taken to ensure women’s social safety net?(Multiple Response) (Ask the respondent Question 812 only if she circles “Yes” in either 808 or 810) Avcbv‡`i GjvKvq gwnjv‡`i mvgvwRK wbivcËv †eóbx wbwðZKi‡Yi Rb¨ wK ai‡bi †UKmB c`‡¶c †bqv n‡q‡Q? (GKvwaK DËi m¤¢e) (hw` 808 A_ev 810 Gi †KvbUvq n¨vu nq Zvn‡j 812 wRÁvmv Ki“b) | Economic empowerment of women gwnjv‡`i A_©‰bwZK ¶gZvqb | 01 |  |
|  |  | Increase of women’s literacy rate gwnjv‡`i wk¶vi nvi e„w× | 02 |  |
|  |  | Enhance participation of women in social activities mvgvwRK Kg©Kv‡Ê gwnjv‡`i AskMÖnY e„w× | 03 |  |
|  |  | Enhance participation of women in local government ¯’vbxq miKv†ii Kg©Kv‡Ê gwnjv‡`i AskMÖnY e„w× | 04 |  |
|  |  | Develop women’s decision making gwnjv‡`i wm×vš— MÖn‡bi AwaKvi cÖwZôv | 05 |  |
|  |  | Develop women’s health system gwnjv‡`i ¯^v‡¯’¨i DbœwZ mva‡b e¨e¯’v MÖnY | 06 |  |
|  |  | CBO formation with the contribution of women gwnjv‡`i AskMÖn‡b GjvKvi evwm›`v‡`i wb‡q ms¯’v MVb | 07 |  |
|  |  | No inititiative has been taken yet †Kvb c`‡¶c †bqv nqwb | 08 |  |
|  |  | Other (Specify) Ab¨vb¨ (D‡j­L Ki“b) |  |  |
|  |  | Don’t know/Can’t say Rvwbbv/ej‡Z cvwibv | 99 |  |

Thank the Respondent and Close the Interview!

DËi`vZv †K ab¨ev` w`‡q mv¶vrKvi †kl Ki“b!

# Annex 4: Qualitative Tools

Evaluation of the Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options Project

The Nielsen Company (Bangladesh) Limited

Focus Group Discussion Guideline

Target Respondents: Beneficiary Women Group

Time: 1 hour and 30 minutes (approximately)

Greetings

mvjvg/Av`ve, Avwg ............| Avwg wbj‡mb bvgK GKwU Avš—R©vwZK M‡elYvg~jK ms¯’v †_‡K G‡mwQ| eZ©gv‡b Avgiv Avcbv‡`i GjvKvq “Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options” bv‡g GKwU †cÖv‡R‡±i g~j¨vqb KiwQ| AvR‡Ki GB Av‡jvPbvq AskMÖnb Kivi Rb¨ Avgv‡`i c¶ †_‡K Avcbv‡`i‡K Avš—wiK ab¨ev`| Avgiv wek^vm Kwi Avcbviv Avcbv‡`i GB GjvKvi cÖwZwbax wn‡m‡e Avcbv‡`i GjvKvi gvbylRb m¤ú‡K© mwVK I ¸i“Z¡c~Y© K_v ej‡Z cvi‡eb| Avcbv‡`i gZg‡Zi gva¨‡g GB GjvKvi gvbylR‡bi gZvgZ D‡V Avm‡e| Avgv‡`i GB M‡elYvi Rb¨ Avcbv‡`i gZvgZ A‡bK †ewk ¸i“Z¡c~Y©|

Norms

Avgiv GLv‡b GKwU Av‡jvPbvi Rb¨ GKwÎZ n‡qwQ| Avgiv mevB GLv‡b K_v ej‡ev Ges mevi gZvgZ MÖnb Ki‡ev G†¶‡Î †Kvb fyj ev mwVK e‡j wKQzB †bB| GB gy³ Av‡jvPbvq Avgiv Avkv Kwi Avcbviv mevB hvi hvi wbR wbR gZvgZ e¨³ Ki‡eb|

Ice Breaking

Avgv‡`i GB Av‡jvPbvi Rb¨ GKwU wbqg Av‡Q Avi Zv n‡”Q Avgiv GKmv‡_ mevB K_v bv e‡j GK GK K‡i K_v ej‡ev, G Rb¨B †h Avgiv Avcbv‡`i mevi g~j¨evb K_vB ïb‡Z PvB Ges Avgiv AviI PvB †h, mevB mevi K_v Rvwb| ZvB Avwg Aby‡iva Ki‡ev hLb †KD wKQz e‡j ZLb Zvi K_v Avgiv mevB †hb ïwb Ges Zvi K_v †kl nevi ci wb‡R ewj|

Avgv‡`i Kv‡Q GKwU †QvU †iKW©vi Av‡Q (‡iKW©viwU AskMÖnbKvix‡`i †`Lvb) Avcbv‡`i †`qv mKj g~j¨evb Z_¨ Avgv‡`i c†¶ †bvU K‡i †bqv m¤¢e n‡e bv Ges g‡bI ivLv hv‡e bv| ZvB hw` Avcbviv AbygwZ cÖ`vb K‡ib Z‡e Avgiv Avcbv‡`i †`qv Z_¨ mg~n †iKW© K‡i wb‡Z cvwi hv wK bv cieZ©x‡Z Avgv‡`i wi‡cvU© wjLvi Kv‡R LyeB mnvqK n‡e| Avcbviv †h Z_¨/gZvgZ cÖ`vb Ki‡eb Zv m¤c~Y© †Mvcb ivLv n‡e|

hw` Avcbviv ivwR _v‡Kb Zvn‡j Avgiv Avgv‡`i Av‡jvPbv ïi“ Ki‡Z cvwi| Avwg wK †iKW©viUv Pvjy Ki‡Z cvwi| Avgiv hw` G‡K Ac‡ii mv‡_ cwiwPZ nB Zvn‡j Avgiv AviI mnRfv‡e mK‡ji mv‡_ Av‡jvPbv Ki‡Z cvie, Avcbviv `qv K‡i mevB Avcbv‡`i cwiPq †`‡eb wK?

Start the Discussion

GLb wK Avgiv gyj Av‡jvPbvq †h‡Z cvwi?

General Questions:

  - For how many years are you living in this area?

GB GjvKvq Avcbviv KZw`b a‡i Av‡Qb?

  - Do you know about “Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options” programme implemented in your community? If yes, what do you know about it?

Avcwb wK BRAC Gi ZË¡veav‡b Avcbv‡`I GjvKvq cwiPvwjZ h‡_vchy³ RxweKv wbe©v‡ni cÖwk¶‡Yi gva¨‡g Rjevqy cwieZ©‡bi Kvi‡Y ¶wZMÖ¯’ gwnjv‡`i `ye©j w`K¸‡jv Dbœq‡bi K_v Rv‡bb? Hw` †R‡b _v‡Kb Zvn‡j wK Rv‡bb? GB †cÖv‡R‡±I j¶¨ I D‡Ïk¨ wK ej‡Z cv‡ib? Kvi KvQ †_‡K †R‡b‡Qb?

Relevance:

  - Are you satisfied with the program initiatives? If yes, to what extent?

Avcwb K GB †cÖv‡R‡±I M„nxZ c`‡¶c¸j wb‡q mš‘ó? KZUzKz?

| Very much | Partly | Somewhat | Not at all |
| --- | --- | --- | --- |
| A‡bK †ewk | AvswkK/wKQzUv | †gvUvgywU | GK`gB bv |

  - Which activity did you like the most and why?

GB †cÖv‡R‡±I †Kvb c`‡¶cwU Avcbvi me‡P‡q †ekx cQ›` n‡q‡Q Ges †Kb?

  - Was there any activity that you think was unnecessarily implemented?

Ggb †Kvb Kg©KvÊ wK wQj GB †cÖv‡R‡±I AvIZvq hv Avcbvi g‡b nq GK`g B AcÖvmw½K wQj? n‡j †mwU wK wQj? †Kb AcÖvmw½K g‡b n‡q‡Q?

  - Do you think there are still activities necessary to do to reduce disaster risk in the community that have not been initiated yet? If yes, what are those activities?

Avcbvi wK g‡b nq †h Ggb Avi †Kvb Kg©KvÊ wQj hv GB †cÖv‡R‡±I AvIZvq Avm‡Z cviZ wKš‘ Av‡mwb? n‡j †m¸‡jv wK?

Effectiveness:

General

- How did the project fulfill the needs of community people?

Avcbv‡`I g‡Z GB cÖ‡R±wU Avcbv‡`I Ges Avcbv‡`I GjvKvi gvby‡li cÖ‡qvRb †gUv‡Z KZUv m¶g n‡q‡Q?

Disaster Management

- Have your household income sources and/or household assets been affected by climatic/natural disasters in last 2 years?

weMZ 2 eQ‡I Avcbv‡`I cwiev‡ii DcvR©‡bi Drm, Avcbv‡`I ab-m¤c`, †Q‡j‡g‡q‡`I wk¶v e¨e¯’v, BZ¨vw` welq wK Rjevqy cwieZ©‡bi Kvi‡Y m„ó cÖvK…wZK `y‡h©v‡Mi Øviv †Kvbfv‡e ¶wZMÖ¯’ n‡q‡Q? n‡j wK wK welq ¶wZMÖ¯’ n‡q‡Q Ges ¶wZi cwigvY †Kgb? Avcbviv GB Ae¯’v †_‡K †ei n‡q Avmvi Rb¨ wK K‡i‡Qb? †m‡¶‡Î †cÖv‡R‡±I f’wgKv KZUzKz?

- Is there any DMC in your community? If yes, how well does it work?

Avcbv‡`I GjvKvq wK †Kvb `y‡h©vM e¨e¯’vcbv KwgwU Av‡Q? _vK‡j GB KwgwUi m`m¨ Kviv? †mwU wK KvR K‡i? GwU wK Zvi `vwqZ¡ mwVKfv‡e cvjb K‡i? GB KwgwU wK †cÖv‡R± ïi“ nIqvi Av‡MI wQj?

- Did you or any of your family members receive any training on disaster management? If yes, then what types of training did you receive? Who provided the training?

Avcwb ev Avcbvi cwiev‡ii †KD wK `y‡h©vM Gi c~e© cÖ¯‘wZ, `y‡h©vM e¨e¯’vcbv Ges `y‡h©vM cÖkgb Gi Dci †Kvb cÖwk¶Y †c‡q‡Qb? †c‡j †K w`‡q‡Q GB cÖwk¶Y? †mLvb †_‡K Avcwb wK wk‡L‡Qb?

- Do you and your community women have a periodic court yard meeting? If yes, how frequently do you arrange these meetings? What issues are discussed in those meetings? Are the meetings fruitful?

Avcwb Ges Avcbv‡`I GjvKvi gwnjviv wK wbqwgZ DVvb ˆeVK K‡ib? Ki‡j KZw`b cici K‡ib? †mB ˆeVK¸‡jv‡Z wK wK welq Av‡jvPbv K‡ib Avcbviv? GB ˆeV‡Ki wPšZv Avcbv‡`I gv_vq wKfv‡e Avmj? GB ˆeVK¸‡jv †_‡K wK Avcbviv †Kvb DcKvwiZv cvb?

Women Empowerment

- Are you or any female member of your Household involved with income generation or livelihood activities? If yes, what are those activities? Generally what do you/the female family members do with the money earned? Did you/any female member of your household receive training on income generation or livelihood activities? What types of trainings were provided? Who provided the trainings? Did the training contribute to better livelihood activities? To what extent are you satisfied with the training?

| Very much | Partly | Somewhat | Not at all |
| --- | --- | --- | --- |
| A‡bK †ewk | AvswkK/wKQzUv | †gvUvgywU | GK`gB bv |

Avcwb ev Avcbvi cwiev‡ii †Kvb gwnjv wK DcvR©bKvix †Kvb Kv‡Ri mv‡_ RwoZ Av‡Qb? _vK‡j wK ai‡bi Kv‡Ri mv‡_ RwoZ Av‡Qb? MvaviYZ Avcbviv GB DcvwR©Z UvKv w`‡q wK K‡ib? Avcwb ev Avcbvi cwiev‡ii †Kvb gwnjv wK GB †cÖv‡R‡±I AvIZvq `y‡h©v‡Mi Øviv Kg cÖfvweZ nq Ggb †Kvb RxweKv wbe©vn c×wZi Dci cÖwk¶Y †c‡q‡Qb? †c‡j wK ai‡bi cÖwk¶Y †c‡q‡Qb? †K cÖwk¶Y w`‡q‡Q Avcbv‡`i? cÖwk¶YwU Avcbv‡`I KZUv Kv‡R †j‡M‡Q Ges wKfv‡e? cÖwk¶‡Yi d‡j `y‡h©v‡Mi Øviv wK Avcbv‡`I Rxeb I RxweKv GLb Av‡Mi †P‡q Kg cÖfvweZ nq? cÖwk¶YwUi e¨vcv‡I Avcwb KZUv mš‘ó?

Hviv cÖwk¶Y †c‡q‡Qb Zviv wK hviv cvbwb Zv‡`I G welq¸wj Rvwb‡q‡Qb?

- Do you suggest any other training for women in future which could be helpful for you to cope with the climate change induced vulnerabilities? If yes, what are they?

Avcbviv wK GiKg Avi †Kvb cÖwk¶‡Yi K_v ej‡Z cv‡ib †hUv †c‡j Avcbv‡`I myweav nZ?

- Do you face any obstacles in the income generating activities or selling your commodities in the market? If yes, what are those obstacles? Are the obstacles reduced over the past 2 years? If yes, to what extent and how?

RxweKv wbe©v‡ni †¶‡Î Ges wb‡R†`I Drcvw`Z cY¨ wewµ Kivi †¶‡Î Avcbviv wK †Kvb iKg evavi m¤§yLxb nb? N‡j †m¸‡jv wK? GB †cÖv‡R‡±I gva¨‡g wK †mB evav¸‡jv K‡g‡Q e‡j Avcwb g‡b K‡ib? K‡g _vK‡j KZUzKz K‡g‡Q Ges †Kb Avcwb GiKg g†b K‡ib?

- Is there any gender discrimination prevailing in your community? If yes, what types of discrimination? (such as unequal payment for same work, in getting price of self-produced commodities, in decision making like family planning, children’s education, livelihood earning, disaster management, etc., in carrying out household chores, etc.)

Avcbv‡`I GjvKvq wK bvixcyi“l mevB‡K mgvb gh©v`v †`qv nq? Avcbv‡`I gwnjv‡`I gZvg‡Zi gyj¨ †`qv nq? Bvixcyi“‡li g‡a¨ †Kvb cv_©K¨ Kiv nq bv? (†hgb GKB Kv‡Ri Rb¨ wfbœ cvwikªwgK †`qv, cY¨ wewµi mgq Kg cyi“l‡`I Zzjbvq Kg g~j¨ cvIqv, cwiev‡ii ¸i“Z¡c~Y© wm×všZ †bqvi AwaKvi bv _vKv, `y‡h©vM e¨e¯’vcbvq †Kvb f’wgKv bv _vKv, BZ¨vw`) GB †cÖv‡R‡±I c‡I wK Av‡Mi Zzjbvq bvix‡`I cÖwZ ˆelg¨ wKQzUv K‡g‡Q? wKfv‡e?

- What types of socio-economic risks/violence/violation of basic human rights (such as domestic violence, dowry, rape, acid throwing, early marriage, eve teasing, child labour, human trafficking etc.) do you or the women in your community usually face? (Please read out the options given in parenthesis) Have these incidents been reduced in last 2 years? If yes, to what extent?

Avcbv‡`I GjvKvq gwnjviv wK ai‡bi mwnsmZvi (cvwievwiK mwnsmZv, †hŠZzK, evj¨ weevn, Lyb, al©Y, GwmW wb‡¶c, Bf wUwRs, bvix cvPvi, BZ¨vw`) wkKvi n‡q _v‡K ev wK ai‡bi wbivcËvnxbZvq †fv‡M? `y‡h©v‡Mi mgq wK GB mgm¨v¸†jv AviI cÖKU nq? †cÖv‡R‡±I Kvi‡Y wK GLb G¸‡jv Av‡Mi †P‡q K‡g‡Q? K‡¤¬ KZUzKz K‡g‡Q? wK †`‡L Avcwb GUv eyS‡Z cvi‡jb?

Coverage:

  - Do you think that the programme has successfully selected its beneficiaries (considering need, age, minorities/ religion, disability, socio-economic status)?

Avcbv‡`I wK g‡b nq †h GB cÖ‡R±wU Zvi myweav‡fvMx‡`I mwVK fv‡e evQvB K‡i‡Q (cÖ‡qvRb, eqm, aig/m¤cÖ`vq, kvixwiK A¶gZv/cÖwZeÜx, Av_©-mvgvwRK Ae¯’v BZ¨vw` we‡ePbvq)?

  - Have the most vulnerable households been provided with the livelihood trainings?

Me‡P‡q `wi`ª cwievi¸‡jvB wK cÖwk¶Y/mvnvh¨ †c‡q‡Q?

  - Do you think that there are certain group of people received support that should not have been supported? If yes, who are they?

Avcbv‡`I g‡Z Ggb †KD wK GB †cÖv‡R‡±I AvIZaxb wQj hv‡`I Avm‡j Gi AvIZvq covi K_v bv? _vK‡j Zviv Kviv?

  - Do you think that there are certain group of people that should receive support not been supported? If yes, who are they?

Avcbv‡`I g‡Z Ggb †KD wK GB †cÖv‡R‡±I AvIZaxb wQjbv hv‡`I Avm‡j Gi AvIZvq covi K_v? _vK‡j Zviv Kviv?

  - Has the programme covered the issue of women empowerment in identifying and providing livelihood support? Has the livelihood support resulted in increasing women’s disaster preparedness capacity?

`y‡h©vM w¯’wZ¯’vcK RxweKv wbe©v‡ni †hme cÖwk¶Y †`qv n‡q‡Q gwnjv‡`I Zv wK Avcbv‡`I GjvKvq bvixi ¶gZvqb cÖwZôv Ki‡Z cÖZ¨¶ ev c‡iv¶ fv‡e †Kvb f’wgKv †i‡L‡Q? GB cÖwk¶Y¸†jv Ges †cÖv‡R‡±I Ab¨vb¨ Kg©Kv‡Êi gva¨‡g wK `y‡h©vM c~e© cÖ¯‘wZ, `y‡h©vM e¨e¯’vcbv Ges `y‡h©vM cÖkg‡bi †¶‡Î gwnjv‡`i m¶gZv I f’wgKv D‡j­L‡hvM¨ nv‡I †e‡o‡Q?

Results/Impact:

- Has the economic condition of your family changed over the past 2 years? If yes, to what extent?

GB †cÖv‡R‡±I d‡j Avcbv‡`I Avw_©K Ae¯’vi wK †Kvb DbœwZ N‡U‡Q weMZ 2 eQ‡i? n‡j KZUzKz Ges wKf‡e `qv K‡I eY©bv Ki“b|

- GB †cÖv‡R‡±I d‡j `y‡h©vM †gvKv‡ejvi †¶‡Î Avcbv‡`i wK †Kvb DbœwZ N‡U‡Q weMZ 2 eQ‡i? n‡j KZUzKz Ges wKf‡e `qv K‡I eY©bv Ki“b|

- What changes can be seen in the lives of community people as a result of this programme?

GB †cÖv‡R‡±I d‡j Avcbv‡`I GjvKv I GjvKvi gvby‡li g†a¨ wK †Kvb cwieZ©b j¶¨ K‡i‡Qb? K‡I _vK‡j †m¸‡jv wK?

- Is there any negative effect of the project? If yes, what are they?

GB †cÖv‡R‡±I Kvi‡Y wK Avcbv‡`I Rxe‡b ev GjvKvq †Kvbiƒc ¶wZKi/Lvivc cÖfve c‡o‡Q?

- Can you please share any example/s or good/best practices in terms of the impact of the RVWACC project in your community?

GB †cÖv‡R‡±I Kvi‡Y N‡U‡Q ev m¤¢e n‡q‡Q Ggb †Kvb D‡j­L‡hvM¨ NUbv ev fvj †Kvb D‡`¨v‡Mi K_v ejyb|

Sustainability & Connectedness:

  - Do you think the benefits of the programme will continue as the programme has come to an end?

- If yes, how long and how efficiently?

- If no, what can be done to ensure the sustainability of the programme?

Avcbv‡`I wK g‡b nq h GB †cÖv‡R± eÜ n‡q hvIqvi ci I Avcbviv Gi †_‡K †kLv fvj w`K¸‡jv Pvwj‡q †h‡Z cvi‡eb? n¨vu n‡j, KZw`b ch©šZ cvi‡eb? bv n‡j, Ggb wK Kiv †h‡Z cv‡I hv‡Z Avcbviv GwU Pvwj‡q wb‡q †h‡Z cv‡ib?

  - Do you think such programmes should be implemented in your community as well as other communities in future? Please share your valuable opinion on the more effectiveness of RVWACC project so that it could be implemented in other areas.

Avcbviv wK g‡b K‡ib †h fwel¨‡Z G ai‡bi AviI †cÖvMÖv‡gi `iKvi Av‡Q Avcœv‡`i?`qv K‡I GB †cÖv‡R‡±I e¨vcv‡I Avcbv‡`I mvwe©K gZvgZ w`b hv‡Z fwel¨‡Z GiKg †Kvb †cÖv‡R± Kivi †¶‡Î GKwU mywbw`©ó w`K wb‡`©kbv cvIqv hvq|

Close the interview and thank the respondent!

mKj‡K ab¨ev` Rvwb‡q Av‡jvPbv †kl Ki“b||

Evaluation of the RVWACC Project

The Nielsen Company (Bangladesh) Limited

Focus Group Discussion Guideline

Target Respondents: Direct/Indirect Community Members (Male & Female) at grass root level and UDMC members

Time: 1 hour and 30 minutes (approximately)

Greetings

Salam/Adab. I’m_________________ from Nielsen Bangladesh and at present we are conducting “Final evaluation of Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options”. Information provided by you will be kept strictly confidential and will only be used for research purpose. It is absolutely your discretion whether you will agree or not to be interviewed. You can refuse to answer any or all the questions. Thank you in advance for your cooperation. Do you want to know anything else about this study? Can we start the discussion now?

mvjvg/Av`ve, Avwg ............| Avwg wbj‡mb bvgK GKwU Avš—R©vwZK M‡elYvg~jK ms¯’v †_‡K G‡mwQ| eZ©gv‡b Avgiv Avcbv‡`i GjvKvq “Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options” bv‡g GKwU †cÖv‡R‡±i g~j¨vqb KiwQ| AvR‡Ki GB Av‡jvPbvq AskMÖnb Kivi Rb¨ Avgv‡`i c¶ †_‡K Avcbv‡`i‡K Avš—wiK ab¨ev`| Avgiv wek^vm Kwi Avcbviv Avcbv‡`i GB GjvKvi cÖwZwbax wn‡m‡e Avcbv‡`i GjvKvi gvbylRb m¤ú‡K© mwVK I ¸i“Z¡c~Y© K_v ej‡Z cvi‡eb| Avcbv‡`i gZg‡Zi gva¨‡g GB GjvKvi gvbylR‡bi gZvgZ D‡V Avm‡e| Avgv‡`i GB M‡elYvi Rb¨ Avcbv‡`i gZvgZ A‡bK †ewk ¸i“Z¡c~Y©|

Norms

We are gathered here for a discussion. We all will talk in this discussion. We will receive everyone’s opinions. There is nothing right or wrong in this discussion. This is an open discussion and we would expect that all of you would express your opinions without any hesitation.

Avgiv GLv‡b GKwU Av‡jvPbvi Rb¨ GKwÎZ n‡qwQ| Avgiv mevB GLv‡b K_v ej‡ev Ges mevi gZvgZ MÖnb Ki‡ev G†¶‡Î †Kvb fyj ev mwVK e‡j wKQzB †bB| GB gy³ Av‡jvPbvq Avgiv Avkv Kwi Avcbviv mevB hvi hvi wbR wbR gZvgZ e¨³ Ki‡eb|

Ice Breaking

We have one basic rule in this session and the rule is we will allow only one person to speak at a time.The reason is, we respect everyone and we want to make sure that everyone is listened. We want to have an organized session, and in order to do this, we request all of you that you pay attention to the person who is speaking, and wait for him/her to finish.

Again, we would like to remind you that this discussion will remain completely anonymous and confidential.

We have this small tape recorder (Show the recorder to the respondent); so that we can be sure that we are capturing everything you are saying and we will be taking notes to make sure we do not miss any important point.

Now if you all permit, may we please get to know each other? Let's go around the table and introduce ourselves.

Avgv‡`i GB Av‡jvPbvi Rb¨ GKwU wbqg Av‡Q Avi Zv n‡”Q Avgiv GKmv‡_ mevB K_v bv e‡j GK GK K‡i K_v ej‡ev, G Rb¨B †h Avgiv Avcbv‡`i mevi g~j¨evb K_vB ïb‡Z PvB Ges Avgiv AviI PvB †h, mevB mevi K_v Rvwb| ZvB Avwg Aby‡iva Ki‡ev hLb †KD wKQz e‡j ZLb Zvi K_v Avgiv mevB †hb ïwb Ges Zvi K_v †kl nevi ci wb‡R ewj|

Avgv‡`i Kv‡Q GKwU †QvU †iKW©vi Av‡Q (‡iKW©viwU AskMÖnbKvix‡`i †`Lvb) Avcbv‡`i †`qv mKj g~j¨evb Z_¨ Avgv‡`i c†¶ †bvU K‡i †bqv m¤¢e n‡e bv Ges g‡bI ivLv hv‡e bv| ZvB hw` Avcbviv AbygwZ cÖ`vb K‡ib Z‡e Avgiv Avcbv‡`i †`qv Z_¨ mg~n †iKW© K‡i wb‡Z cvwi hv wK bv cieZ©x‡Z Avgv‡`i wi‡cvU© wjLvi Kv‡R LyeB mnvqK n‡e| Avcbviv †h Z_¨/gZvgZ cÖ`vb Ki‡eb Zv m¤c~Y© †Mvcb ivLv n‡e|

hw` Avcbviv ivwR _v‡Kb Zvn‡j Avgiv Avgv‡`i Av‡jvPbv ïi“ Ki‡Z cvwi| Avwg wK †iKW©viUv Pvjy Ki‡Z cvwi| Avgiv hw` G‡K Ac‡ii mv‡_ cwiwPZ nB Zvn‡j Avgiv AviI mnRfv‡e mK‡ji mv‡_ Av‡jvPbv Ki‡Z cvie, Avcbviv `qv K‡i mevB Avcbv‡`i cwiPq †`‡eb wK?

Start the Discussion

Now that we have introduced ourselves, we can go to the main discussion.

GLb wK Avgiv gyj Av‡jvPbvq †h‡Z cvwi?

General Questions:

  - For how many years are you living in this area?

GB GjvKvq Avcbviv KZw`b a‡i Av‡Qb?

  - Do you know about “Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options” programme implemented in your community? If yes, what do you know about it?

Avcwb wK BRAC Gi ZË¡veav‡b Avcbv‡`I GjvKvq cwiPvwjZ h‡_vchy³ RxweKv wbe©v‡ni cÖwk¶‡Yi gva¨‡g Rjevqy cwieZ©‡bi Kvi‡Y ¶wZMÖ¯’ gwnjv‡`i `ye©j w`K¸‡jv Dbœq‡bi K_v Rv‡bb? Hw` †R‡b _v‡Kb Zvn‡j wK Rv‡bb? GB †cÖv‡R‡±I j¶¨ I D‡Ïk¨ wK ej‡Z cv‡ib? Kvi KvQ †_‡K †R‡b‡Qb?

Effectiveness:

Disaster Management

- Have your household income sources and/or household assets been affected by climatic/natural disasters in last 2 years? Have climatic disasters affected your children’s education in the last 2 years?

weMZ 2 eQ‡I Avcbv‡`I cwiev‡ii DcvR©‡bi Drm, Avcbv‡`I ab-m¤c`, †Q‡j‡g‡q‡`I wk¶v e¨e¯’v, BZ¨vw` welq wK Rjevqy cwieZ©‡bi Kvi‡Y m„ó cÖvK…wZK `y‡h©v‡Mi Øviv †Kvbfv‡e ¶wZMÖ¯’ n‡q‡Q? n‡j wK wK welq ¶wZMÖ¯’ n‡q‡Q Ges ¶wZi cwigvY †Kgb? Avcbviv GB Ae¯’v †_‡K †ei n‡q Avmvi Rb¨ wK K‡i‡Qb?

- Is there any DMC in your community? If yes, how well does it work?

Avcbv‡`I GjvKvq wK †Kvb `y‡h©vM e¨e¯’vcbv KwgwU Av‡Q? _vK‡j GB KwgwUi m`m¨ Kviv? †mwU wK KvR K‡i? GwU wK Zvi `vwqZ¡ mwVKfv‡e cvjb K‡i? GB KwgwU K‡e †_‡K Av‡Q Avcbv‡`I GjvKvq?

- Did you or any of your family members receive any training on disaster management? If yes, then what types of training did you receive? Who provided the training?

- Avcwb ev Avcbvi cwiev‡ii †KD wK `y‡h©vM Gi c~e© cÖ¯‘wZ, `y‡h©vM e¨e¯’vcbv Ges `y‡h©vM cÖkgb Gi Dci †Kvb cÖwk¶Y †c‡q‡Qb? †c‡j †K w`‡q‡Q GB cÖwk¶Y? †mLvb †_‡K Avcwb wK wk‡L‡Qb?

Women Empowerment

- Are you or any female member of your Household involved with income generation or livelihood activities? If yes, what are those activities? Generally what do you/the female family members do with the money earned?

Avcwb ev Avcbvi cwiev‡ii †Kvb gwnjv wK DcvR©bKvix †Kvb Kv‡Ri mv‡_ RwoZ Av‡Qb? _vK‡j wK ai‡bi Kv‡Ri mv‡_ RwoZ Av‡Qb? MvaviYZ Avcbviv GB DcvwR©Z UvKv w`‡q wK K‡ib? Avcwb ev Avcbvi cwiev‡ii †Kvb gwnjv wK `y‡h©v‡Mi Øviv Kg cÖfvweZ nq Ggb †Kvb RxweKv wbe©vn c×wZi Dci cÖwk¶Y †c‡q‡Qb? †c‡j wK ai‡bi cÖwk¶Y †c‡q‡Qb? †K cÖwk¶Y w`‡q‡Q Avcbv‡`i? cÖwk¶YwU Avcbv‡`I KZUv Kv‡R †j‡M‡Q Ges wKfv‡e? cÖwk¶‡Yi d‡j `y‡h©v‡Mi Øviv wK Avcbv‡`I Rxeb I RxweKv GLb Av‡Mi †P‡q Kg cÖfvweZ nq? Hviv cÖwk¶Y †c‡q‡Qb Zviv wK hviv cvbwb Zv‡`I G welq¸wj Rvwb‡q‡Qb?

- Avcwb wK Avcbv‡`I GjvKvi gwnjviv wK wbqwgZ DVvb ˆeVK K‡ib G e¨vcv‡I Rv‡bb? Rvb‡j Kvi Kv‡Q †R‡b‡Qb? GB ˆeVK¸‡jv†Z hv Av‡jvPbv nq Avcbv‡`I wK †m¸‡jv Rvbvb nq?

- Do you face any obstacles in the income generating activities or selling your commodities in the market? If yes, what are those obstacles? Are the obstacles reduced over the past 2 years? If yes, to what extent and how?

RxweKv wbe©v‡ni †¶‡Î Ges wb‡R†`I Drcvw`Z cY¨ wewµ Kivi †¶‡Î Avcbviv wK †Kvb iKg evavi m¤§yLxb nb? N‡j †m¸‡jv wK? †mB evav¸‡jv wK Av‡Mi †P‡q K‡g‡Q e‡j Avcwb g‡b K‡ib? K‡g _vK‡j KZUzKz K‡g‡Q Ges †Kb Avcwb GiKg g†b K‡ib?

- Is there any gender discrimination prevailing in your community? If yes, what types of discrimination? (such as unequal payment for same work, in getting price of self-produced commodities, in decision making like family planning, children’s education, livelihood earning, disaster management, etc., in carrying out household chores, etc.)

Avcbv‡`I GjvKvq wK bvixcyi“l mevB‡K mgvb gh©v`v †`qv nq? Avcbv‡`I gwnjv‡`I gZvg‡Zi gyj¨ †`qv nq? Bvixcyi“‡li g‡a¨ †Kvb cv_©K¨ Kiv nq bv (†hgb GKB Kv‡Ri Rb¨ wfbœ cvwikªwgK †`qv, cY¨ wewµi mgq Kg cyi“l‡`I Zzjbvq Kg g~j¨ cvIqv, cwiev‡ii ¸i“Z¡c~Y© wm×všZ †bqvi AwaKvi bv _vKv, `y‡h©vM e¨e¯’vcbvq †Kvb f’wgKv bv _vKv, BZ¨vw`)? Av‡Mi Zzjbvq bvix‡`I cÖwZ ˆelg¨ wK wKQzUv K‡g‡Q? Kg‡j wKfv‡e?

- What types of socio-economic risks/violence/violation of basic human rights (such as domestic violence, dowry, rape, acid throwing, early marriage, eve teasing, child labour, human trafficking etc.) do you or the women in your community usually face? (Please read out the options given in parenthesis)Have these incidents been reduced in last 2 years? If yes, to what extent?

Avcbv‡`I GjvKvq gwnjviv wK ai‡bi mwnsmZvi (cvwievwiK mwnsmZv, †hŠZzK, evj¨ weevn, Lyb, al©Y, GwmW wb‡¶c, Bf wUwRs, bvix cvPvi, BZ¨vw`) wkKvi n‡q _v‡K ev wK ai‡bi wbivcËvnxbZvq †fv‡M? `y‡h©v‡Mi mgq wK GB mgm¨v¸†jv AviI cÖKU nq? GLb wK G¸‡jv Av‡Mi †P‡q K‡g‡Q? Kg‡j KZUzKz K‡g‡Q? wK †`‡L Avcwb GUv eyS‡Z cvi‡jb?

Coverage:

  - Have the most vulnerable households been provided with the livelihood trainings?

Me‡P‡q `wi`ª cwievi¸‡jvB wK cÖwk¶Y/mvnvh¨ †c‡q‡Q?

  - Do you think that there are certain group of people received support that should not have been supported? If yes, who are they?

Avcbv‡`I g‡Z Ggb †KD wK GB †cÖv‡R‡±I AvIZaxb wQj hv‡`I Avm‡j Gi AvIZvq covi K_v bv? _vK‡j Zviv Kviv?

  - Do you think that there are certain group of people that should receive support not been supported? If yes, who are they?

Avcbv‡`I g‡Z Ggb †KD wK GB †cÖv‡R‡±I AvIZaxb wQjbv hv‡`I Avm‡j Gi AvIZvq covi K_v? _vK‡j Zviv Kviv?

Results/Impact:

- Has the economic condition of your family changed over the past 2 years? If yes, to what extent?

Avcbv‡`I Avw_©K Ae¯’vi wK †Kvb DbœwZ N‡U‡Q weMZ 2 eQ‡i? n‡j †Kb, KZUzKz Ges wKf‡e n‡q‡Q `qv K‡I eY©bv Ki“b|

- `y‡h©vM †gvKv‡ejvi †¶‡Î Avcbv‡`i wK †Kvb DbœwZ N‡U‡Q weMZ 2 eQ‡i? n‡j †Kb, KZUzKz Ges wKf‡e n‡q‡Q `qv K‡I eY©bv Ki“b|

- What changes can be seen in the lives of community people as a result of this programme?

GB †cÖv‡R‡±I d‡j Avcbv‡`I GjvKv I GjvKvi gvby‡li g†a¨ wK †Kvb cwieZ©b j¶¨ K‡i‡Qb? K‡I _vK‡j †m¸‡jv wK?

- Is there any negative effect of the project? If yes, what are they?

- GB †cÖv‡R‡±I Kvi‡Y wK Avcbv‡`I GjvKvq †Kvbiƒc ¶wZKi/Lvivc cÖfve c‡o‡Q?

Sustainability & Connectedness:

  - Do you think such programmes should be implemented in your community as well as other communities in future? Please share your valuable opinion on the more effectiveness of RVWACC project so that it could be implemented in other areas.

Avcbviv wK g‡b K‡ib †h fwel¨‡Z G ai‡bi AviI †cÖvMÖv‡gi `iKvi Av‡Q Avcœv‡`i?`qv K‡I GB †cÖv‡R‡±I e¨vcv‡I Avcbv‡`I mvwe©K gZvgZ w`b hv‡Z fwel¨‡Z GiKg †Kvb †cÖv‡R± Kivi †¶‡Î GKwU mywbw`©ó w`K wb‡`©kbv cvIqv hvq|

Close the interview and thank the respondent!

mKj‡K ab¨ev` Rvwb‡q Av‡jvPbv †kl Ki“b||

Evaluation of the Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood OptionsProject

The Nielsen Company (Bangladesh) Limited

Observation Checklist

| Detailed Address with Landmark |  |
| --- | --- |
| Observation Start Time |  |
| Observation End Time |  |
| Name of Observer |  |

The majorfeatures will be observed during observation includes but not limited to:

†h welq¸‡jv †ekx ¸i“‡Z¡I mv‡_ ch©‡e¶Y Ki‡Z n‡e †m¸‡jv wb‡æ Dwj­wLZ njt  (wKš‘ ch©‡e¶Y Gi g‡a¨B mxgve× _vK‡e bv)

- Please collect the observation time, place, address, issues, and background information of the participants.

`qv K‡I ch©‡e¶‡Yi mgq, RvqMv, wVKvbv, †hme welq ch©‡e¶Y Ki‡Qb †m¸ji bvg Ges AskMÖnYKvix‡`I m¤c‡K© hveZxq Z_¨ msMÖn Ki“b|

- Please explain the observation point/issues.

ch©‡e¶Y Gi welq¸wj e¨vL¨v Ki“b|

- Please try to observe the overall situation (households, activities, norms, values) of the coastal/flood prone/drought prone areas.

†h †h GjvKvq Avcwb ch©‡e¶Y Ki‡Qb (mvBK¬b/eb¨v/Liv cÖeY) †mB GjvKvi mvwe©K Ae¯’v, †mLv†b emevmKvix cwievi¸‡jvi wewfbœ Kg©KvÊ, wPšZv-‡PZbv, g~j¨‡eva, ixwZ-bxwZ, BZ¨vw` ch©‡e¶Y Kivi †Póv Ki“b|

- Please try to observe carefully the condition (incidents, behaviors, perceptions, beliefs, practices) of the women in the study areas.

†h †h GjvKvq Avcwb ch©‡e¶Y Ki‡Qb (mvBK¬b/eb¨v/Liv cÖeY) †mB GjvKvi bvix‡`I eZ©gvb Ae¯’v ch©‡e¶Y Ki“b (Zv‡`I AvPvi-e¨envi, wPšZvaviv, wek¦vm, KvRKg©, wewfbœ NUbv, BZ¨vw`)

- Please try to observe the changes in knowledge regarding disaster preparedness, disaster management, disaster risk reduction situation, disaster resilient livelihood options, gender discrimination of community people.

†h †h GjvKvq Avcwb ch©‡e¶Y Ki‡Qb (mvBK¬b/eb¨v/Liv cÖeY) †mB GjvKvi gvby‡li, we‡kl K‡I bvix‡`I, `y‡h©v‡Mi c~‡e© cÖ¯‘wZ †bqvi aib, `y‡h©vM e¨e¯’vcbv, `y‡h©v‡Mi ¶wZ Kgvbi Rb¨ M„nxZ e¨e¯’v/c`‡¶c, `y‡h©vM w¯’wZ¯’vcK RxweKv wbe©vn c×wZ evQvB, BZ¨vw` AZ¨všZ ¸i“‡Z¡I mv‡_ ch©‡e¶Y Ki“b|

- †h †h GjvKvq Avcwb ch©‡e¶Y Ki‡Qb (mvBK¬b/eb¨v/Liv cÖeY) †mB GjvKvi GjvKvi mvwe©K wbivcËv e¨e¯’v Ges `y‡h©v‡Mi mgq wbivcËvi wbðqZv, bvix‡`I cÖwZ mgv‡Ri AvPiY, bvix-cyi“l †f`v‡f`, bvixi cÖwZ mwnsmZv, bvix ¶gZvqb, evj¨ weev‡ni nvi, wk¶vi nvi, †hŠZzK cÖ_vi cÖPjb, BZ¨vw` AZ¨všZ ¸i“‡Z¡I mv‡_ ch©‡e¶Y Ki“b|

- Please try to observe the changes in the socio-economic conditions of the households after the RVWACC project.

GjvKvi cwievi¸‡jvi Avw_©K Ae¯’v ch©‡e¶Y Ki“b Ges †cÖv‡R‡±I ci AwZ-`wi`ª cwievi¸‡jvi Ae¯’vi †Kvb DbœwZ n‡q‡Q wKbv Zv Rvbvi †Póv Ki“b|

- Please try to observeif women & vulnerable groups have access to facilities

Bvixiv Ges AwZ`wi`ª I me‡P‡q bvRyK cwievi¸‡jv wewfbœ my†hvM-myweav Ges †cÖv‡R‡±I mydj cv‡”Q wKbv Rvbvi †Póv Ki“b|

- Please try to observe the role of local government institutions, local service provider institutions, Union Disaster Management Committee (UDMC) any other groups under this project.

†h †h GjvKvq Avcwb ch©‡e¶Y Ki‡Qb (mvBK¬b/eb¨v/Liv cÖeY) †mB GjvKvi GjvKvi ¯’vbxq miKv‡ii cÖwZôvb, BDwbqb `y‡h©vM e¨e¯’vcbv KwgwU G¸‡jvi f’wgKv ch©‡e¶Y Ki“b|

- Please try to observe the changes made through this project in the community or locality.

†cÖv‡R‡±I gva¨‡g GjvKvq †hme cwieZ©b G‡m‡Q †m¸‡jv ch©‡e¶Y Ki“b|

- Please try to observe the availability of hardware and software support and its functionality in the community.

†cÖv‡R‡± †hme e¯‘MZ Ges Ae¯‘MZ, A_©vr cÖZ¨¶ I c‡iv¶ mvnvh¨ †`qv n‡q‡Q †m¸‡jvi Kvh©KvwiZv ch©‡e¶Y Ki“b|

- Please try to observe age of the infrastructure/s.

GjvKvi †hvMv‡hvM I hvZvqvZ e¨e¯’v A_©vr iv¯Zv-NvU, weªR, mvu‡Kv, hvbevnb, †dv‡bi e¨envi, we`¨y‡Zi e¨envi, BZ¨w`I eZ©gvb Ae¯’v Ges G¸‡jvi †gqv` ch©‡e¶Y Ki“b|

- Please try to collect opinion on whether the vulnerable groups are using the facilities or not. If not, why?

Av‡kcv‡ki gvby‡li KvQ †_‡K gZvgZ wbb †h GjvKvi me‡P‡q `wi`ª Ges `ye©j cwievi¸‡jvB wK †cÖv‡R‡±I my‡hvM-myweav †fvM Ki‡Z cvi‡Q bvwK|

Evaluation of the Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood OptionsProject

The Nielsen Company (Bangladesh) Limited

Case Study Checklist

Target Group: Beneficiary Women

| Name of Respondent |  |
| --- | --- |
| Detailed Address with Landmark |  |
| Designation |  |
| Contact Number |  |
| Interview Start Time |  |
| Interview End Time |  |
| Name of Interviewer |  |

Salam/Adab/Good Morning/Good Evening. I have come from a research firm named The Nielsen Bangladesh. We are conducting an Evaluation of the Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options Project In your area. Your opinion is important to us. We assure you that your opinion and speech will be kept secret and only be used for research. We will be grateful if you would be kind enough to spare us some of your valuable time. mvjvg/Av`ve¦ Avwg XvKvq Aew¯’Z wbj‡mb evsjv‡`k bv‡gi GKwU M‡elYv ms¯’v †_‡K G‡mwQ¦ RxweKv wbe©v‡ni †¶‡Î bvixiv cÖvK…wZK `y‡h©v‡Mi Kvi‡Y wKfv‡e ¶wZMÖ¯’ nq Ges Zv‡`i GB ¶q¶wZi cwigvY wKfv‡e Kgvb hvq Zv wb‡q Avcbv‡`i GjvKvq KwZcq bvix‡`i BD Gb DIg¨vb Ges eª¨vK Gi †hŠ_ D‡`¨v‡M wKQz cÖwk¶Y †`qv n‡q‡Q I mvnvh¨ Kiv n‡q‡Q¦ GB †cÖv‡R‡±i gva¨‡g wewfbœ cwiev†ii e`‡j hvIqvi Mí Avgiv Rvb‡Z PvB¦ Avcbvi Kvwnbx Avcwb wb‡Ri gZ K‡i ej‡Z cv‡ib¦Avcbviv hv ej‡eb Zv m¤ú~b©iæ‡c †Mvcb ivLv n‡e¦ M‡elYvi †Kvb ch©v‡q ejv n‡e bv †h, GB gšZe¨wU Avcwb K‡i‡Qb¦ Avcbvi bvg cwiPq ejv n‡e bv ïay M‡elYvi Kv‡Ri Zv e¨envi Kiv n‡e¦ GUv Avgv‡`i M‡elYv Kv‡Ri bxwZ Ges Avgiv Zv ‡g‡b Pwj¦

The following points will be discussed with the respondents:

- Please collect socio-economic and background information from the participants.

`qv K‡I AskMÖnYKvixi hveZxq Z_¨ Ges Zvi Av_-©mvgvwRK Ae¯’vi wPÎ msMÖn Ki“b|

- Can you please tell us your story/experience about the mentioned issue such as attaining economic independency/economic empowerment/fighting against disaster? (How, when and what happened, any other significant issues regarding your experience)?

cÖwk¶‡Yi gva¨‡g Avw_©K ¯^wbf©iZv jvf, Avw_©K Dbœqb mvab, `y‡h©vM †gvKv‡ejv, `y‡h©v‡Mi c‡I Ny‡I `vuovb, bvixi ¶gZvqb, BZ¨vw` m¤cwK©Z Kvwnbx msMÖn Ki“b|

- How did RVWACC project help you in this regard? What attempt was taken through this project?

GB †cÖv‡R± wKfv‡e †mLv‡b f’wgKv †i‡L‡Q †mUv D‡j­L Ki“b|

- Can you please tell us about the role of your family, community, local government institutions, local service provider institutions or any other institutions affiliated with it? What actions did they take?

GB NUbvq Zvi cwievi, GjvKvi gvbylRb, ¯’vbxq miKvi, Ab¨b¨ ¯’vbxq †mev`vZv cÖwZôvb ev Ab¨ †h †KD †Kvb ai‡bi f’wgKv †i‡L‡Q wKbv Ges ivL‡j wK ai‡bi f’wgKv †i‡L‡Q wR‡Ám Ki“b|

Thank the participant and close the interview!

DËi`vZv †K ab¨ev` w`‡q mv¶vrKvi †kl Ki“b!

Final Evaluation of the Project “Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options Project”

The Nielsen Company (Bangladesh) Limited

Key Informant Interview Checklist

Target Respondent: Stakeholder at National Level

| Name of the Respondent |  |
| --- | --- |
| Designation |  |
| Institution |  |
| Contact Number |  |
| Interview Start Time |  |
| Interview End Time |  |
| Name of Interviewer |  |

General Question

- Have you heard of the project named Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options Project? (Give them clue that UN Women implemented the project)

Avcwb wK Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options Project m¤ú‡K© ï‡b‡Qb? (Zv‡`i aviYv cÖ`vb Ki“b †h cÖKíwU BDGb I‡gb-Gi)

- If yes, your level of engagement (are you invited to any of the project’s event, were you consultant, were you implementing partners…etc.)

n¨vu n‡j, cÖK‡íi mv‡_ Avcbvi m¤ú„³Zv †Kb (Avcbv‡K wK cÖK‡íi †Kvb Kvh©µ‡g Avgš¿Y Rvbv‡bv n‡q‡Q? Avcwb wK ai‡bi civgk© w`‡q _v‡Kb? Avcwb wK cÖ‡qvMKvix †Kvb cvU©bvi? BZ¨vw` cÖkœ Ki“b)

- Please tell us something about the objectives of Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options Project.

`qv K‡i Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options Project -Gi D‡Ïk¨ m¤ú‡K© Avgv‡`I wKQz ejyb|

Relevance

- To what extent are the project results, outcomes, outputs consistent with national and local priorities? (Prior share some of the results achieved by the project)

GB †cÖv‡R‡±i †h dj cvIqv †M‡Q Zv RvZxq Ges ¯’vbxq AMÖvwaKvi cÖvß welq¸‡jvi mv‡_ KZUv msMwZc~Y© wQj e‡j Avcwb g‡b K‡ib?

- To what extent are the project results, outcomes, outputs consistent with the needs of intended beneficiaries?

GB †cÖv‡R‡±i †h dj cvIqv †M‡Q Zv GB †cÖv‡R‡±i myweav‡fvMx‡`i cÖ‡qvR‡bi mv‡_ KZUv msMwZc~Y© wQj e‡j Avcwb g‡b K‡ib?

- To what extent are the project results and strategies relevant to UN Women’s overall goals of gender equality and women’s empowerment; and BCO strategic note?

GB †cÖv‡R‡± e¨eüZ/ cÖ‡qvMK…Z Kvh©µg¸‡jv Ges Gi †_‡K cÖvß dj UN Women’s overall goals of gender equality and women’s empowerment; and BCO strategic note Gi mv‡_ KZUv msMwZc~Y©?

Effectiveness

- Do you think it is important to incorporate gender issues in DRR CCA discourse?

Avcwb wK g‡b K‡ib †h DRR-CCA Kvh©µ‡g wj½ mgZvi welqwU  AšÍf©~³ KivUv Ri“ix ?

(NB: DRR-Disaster Risk Reduction, CCA-Climate Change adaptation)

(‡bvU: wWAviAvi: `~‡hv©MKvjxb SuywK Kgv‡bv, wmwmG- Rjevq~ cwieZ©b mv‡_ gvwb‡q †bqv)

- How far UN Women was able to do that through their project?

GB cÖK‡íi gva¨‡g BDGb I‡gb GwU KZUv AR©b Ki‡Z †c‡i‡Q?

- What else can be done?

G‡¶‡Î Avi Kx Kiv †h‡Z cv‡i?

- To what degree the project has been successful to sensitize stakeholders on the importance of incorporating gender issues in climate change adaptation policies and programmes?

Rjevq~ cwieZ©b wewfbœ, bxwZ wba©viY I Kvh©µ‡gi †¶‡Î wj½ mgZv ev bvix cyi“l mK‡ji AskMÖn‡Yi welqwUi e¨cv‡i GB cÖK‡íi †÷K‡nvìvi‡`i ms‡e`bkxj Kivi †¶‡Î cÖKíwU KZUv mdj n‡q‡Q e‡j Avcwb g‡b K‡ib?

- To what extent has livelihood support resulted in increasing women’s disaster preparedness capacity? How?

GB cÖK‡íi gva¨‡g bvix‡`i †h jvBfwjûW mv‡c©vU †`qv n‡q‡Q Zvi Kvi‡Y bvix‡`i `¶Zv ev m¶gZ KZUv †e‡o‡Q e‡j Avcwb g‡b K‡ib? wKfv‡e †e‡o‡Q?

- To what extent capacity of the individual (beneficiary, disaster management committee members) has been enhanced to advocate for gender equality in DRR-CCA?

e¨w³MZ ch©v‡q (myweav‡fvMx, `~‡h©vM e¨e¯’vcbv KwgwUi m`m¨) Kxfv‡e DRR-CCA -‡Z wj½xq mgZv wel‡q `¶Zv e„w× †c‡q‡Q?

(NB: DRR-Disaster Risk Reduction, CCA-Climate Change adaptation)

(‡bvU: wWAviAvi: `~‡hv©MKvjxb SuywK Kgv‡bv, wmwmG- Rjevq~ cwieZ©b mv‡_ gvwb‡q †bqv)

- To what extent capacity of the institutions (implementing partners, relevant stakeholders, GO institutions) have been enhanced to advocate for gender equality in DRR-CCA?

GB cÖK‡íi gva¨‡g implementing partners, relevant stakeholders, GO institutions-‡`i DRR-CCA Kg©Kv‡Û wj½xq mgZv weav‡bi G¨W‡fv‡Kwm Kivi ¶gZv Ges B”Qv wKfv‡e †e‡o‡Q e‡j Avcwb g‡b K‡ib?

Results/Impacts

- Did you find any changes brought by the projects?

Avcwb wK GB cÖK‡íi Kvi‡Y †Kvb cwieZ©b jÿ¨ K‡i‡Qb?

- If yes, what are those?

n¨vu n‡j, †m¸‡jv Kx?

- What are the issues that pull behind achieving objective of the project i.e. reducing vulnerability of the rural poorest women and incorporating gender issues in DRR-CCA discourse?

Kx Kx Kvi‡Y GB cÖK‡íi D‡Ïk¨ AR©‡bi †¶‡Î ‡hgb- wWwWAvi-wmwmG wel‡q MÖv‡gi bvix‡`i SzuwK wbik‡bi wel‡q wcwQ‡q co‡Z n‡”Q?

- Are there any changes in women’s lives vulnerable to disasters and climatic events brought about by the project intervention? If yes, in which cases and to what extent? GB cÖK‡íi Kvi‡Y `~‡h©vM I Rjevq~ cwieZ©‡bi mgq bvix‡`i Rxe‡bi SzwK Kgv‡bvi wel‡q †Kvb cwieZ©b G‡m‡Q? n¨vu n‡j, †Kvb †ÿ‡Î Ges wKfv‡e?

- What are the lessons that enabled or constraint to achieving the results?

Ggb †Kvb wel‡qi/NUbvi (lessons learnt) K_v wK D‡j­L Ki‡Zcv‡ib †hUv GB †cÖv‡R‡±i Kvw•¶Z dj jv‡fi †¶‡Î mnvqZv K‡i‡Q ev evav m„wó K‡i‡Q?

- How much the programme succeeded in reaching its goals compared to the initial expectations before starting the project?

GB †cÖvMÖvgwU ïi“ nIqvi Av‡M Gi †h cÖviw¤¢K j¶¨ I D‡Ïk¨ wQj Zvi †cÖw¶‡Z Gi j¶¨ ev¯—evq‡b KZUv mdj n‡q‡Q e‡j Avcwb g‡b K‡ib? hw` g‡b K‡ib mdj n‡q‡Q Zvn‡j wK‡mi †cÖw¶‡Z Avcwb GiKg g‡b Ki‡Qb?

Sustainability

- Do you think that the beneficiaries will succeed in carrying on the positive effects of the benefits and support they are given? If yes, to what extent? If no, why?

Avcwb wK g‡b K‡ib myweav‡fvMxiv mdjZv AR©b Ki‡Z cvi‡e hw` Zv‡`i myweav mnvqZv †`qv nq? n¨vu n‡j, wKfv‡e? bv n‡j, †Kb?

- What could be the overall suggestion/s if there is any scope to modify the project for a better implementation in near future?

mvwe©Kfv‡e GB cÖK‡í Kx ai‡bi cwieZ©b Avbv cÖ‡qvRb e‡j Avcwb g‡b K‡ib hv‡Z fwel¨‡Z GwU AviI mdjfv‡e cwiPvjbv m¤¢e nq?

- What should be done to incorporate gender issue in DRR, CCA and humanitarian efforts?

wj½xq welqwU wWwWAvi, wmwmG Ges wnD‡gwb‡Uwiqvb cÖ‡Póvq AšÍf~©³ Kivi Rb¨ Kx Kiv †h‡Z cv‡i?

- What role you want UN Women to play in this regards?

GB †¶‡Î BDGb I‡gb Kx ai‡bi f~wgKv ivL‡Z cv‡i e‡j Avcwb g‡b K‡ib?

Thank the Respondent and Close the Interview!

# Annex 5: FGD conduction schedule

| Area | Venue Address | Date | Starting Time | Ending Time | No. of Participants |
| --- | --- | --- | --- | --- | --- |
| Cox’s Bazar | Sabhrang, Teknaf | December 12, 2015 | 3.30 p.m | 5.50 p.m | 08 |
|  | Nhila, Teknaf | December 14, 2015 | 11.00 a.m | 12.30 p.m | 08 |
| Natore | Katakhali, Chatni | December 13, 2015 | 3.20 p.m | 4.05 p.m | 10 |
|  | Narayanpara, Kafuria, Natore Sadar | December13, 2015 | 11.30 a.m | 12.30 p.m | 10 |
| Sirajganj | Kayem Village, Nalka | December 14, 2015 | 11.15 a.m | 12.05 p.m | 10 |
|  | Hasil, Raghunatpur-2, Brahmagacha, Raiganj | December 14, 2015 | 2.05 p.m | 3.00 p.m | 10 |
| Satkhira | House of Kaushalya Rani, mathurapur, Munshiganj, Shyamnagar | December 13, 2015 | 2.00 p.m | 4.00 p.m | 08 |
|  | House of Khalil Morol, Dumuria, Gabura, Shyamnagar | December 14, 2015 | 2.00 p.m | 4.10 p.m | 07 |
| Patuakhali | House of Mahinur Begum, West Dhulishar, Kalapara | December 15, 2015 | 10.30 a.m | 1.00 p.m | 06 |
|  | House of Anima Rani, Tolaoli Village, Latachapli Union, Kalapara | December 15, 2015 | 2.30 p.m | 5.15 p.m | 09 |

Daily ProthomAlo, 17th December 2015

Extracted from ToR

Purposive sampling, also known as judgmental, selective or subjective sampling, is a type of non-probability sampling technique.