Mid Term Evaluation of the Joint Programme on Prevention of Gender Based Violence (JPGBV) Against Young Women and Adolescent Girls

Final Report

28.09.2016

# Acknowledgements

The Mid-Term Evaluation of the Joint Programme on Gender Based Violence was jointly commissioned by UNICEF, UN Women, DANIDA and Ministry of Women Affairs Gender and Community Development. The Evaluation Team would like to express its gratitude to all organisations for their guidance and facilitation of the development of the inception report through inception meetings and sharing of documentation for the programme.

Secondly, we would like to acknowledge the unwavering support received from the Ministry of Women Affairs, Gender and Community Development, Ministry of Justice, Legal and Parliamentary Affairs, Ministry of Health and Child Care, Ministry of Public Service, Labour and Social Welfare, Ministry of Home Affairs and the Judicial Service Commission.

Thirdly, our gratitude is extended to the implementing partners for the Joint Programme on Gender Based Violence: [World Vision, Women’s Trust working in partnership with Tag a Life International, Students and Youths Working on Reproductive Health Action Team (SAYWHAT), Justice for Children in collaboration with Women and Law in Southern Africa (WLSA) and Zimbabwe Women Lawyers Association (ZWLA), Childline, and Family Support Trust (FST)] who shared programme documents for our review and facilitated our field visits.

Last but not least, we extend our appreciation the all the respondents who shared information and insights on their perceptions of the JPGBV in the districts (Beitbridge, Bindura and Makoni) they work and/or reside. Without your support, this exercise would have been futile.

Evaluation Team

Dr. Nyasha Madzingira: Team Leader

Mavis Kahwemba: GBV Consultant

Lazarus Muchabaiwa: Economist

Ngonidzaishe Marimo: Quality Assurance

# Table of Contents

Acknowledgements	ii

Table of Contents	iii

List of Figures	v

List of Tables	v

Acronyms	vi

Executive Summary	viii

1	Introduction	1

2	Background	1

2.1	Gender Based Violence among Adolescents Girls and Young Women	1

2.2	Programme Description	2

2.2.1	The JPGBV Outcomes and Outputs	3

3	About the Evaluation	4

3.1	Purpose of the Evaluation	4

3.2	Evaluation Objectives and Scope	4

4	Methodology	6

4.1	Sampling	6

4.2	Data Collection Methods	8

4.2.1	Primary data sources	8

4.2.2	Secondary data sources	8

4.3	Data Analysis	8

4.4	Review and Validation Process	9

4.5	Stakeholder Participation	9

4.6	Ethical Considerations	9

4.7	Limitations	10

5	Findings	11

5.1	Relevance	11

5.1.1	Needs of beneficiaries	11

5.1.2	Needs and priorities of institutional stakeholders	12

5.1.3	Alignment with international, regional and national priorities	12

5.2	Validity of Design	13

5.2.1	Programme design	13

5.2.2	Theory of Change	15

5.2.3	Programme results and targets	16

5.2.4	Appropriateness of indicators	17

5.2.5	Attention to gender and human rights	17

5.2.6	Design of the joint programme	18

5.3	Efficiency	23

5.3.1	Value for Money Assessment	23

5.3.2	Timeliness in delivery	26

5.3.3	Human resources for the programme	28

5.3.4	Monitoring programme results and performance	28

5.3.5	Measures taken during planning and implementation to ensure resources are efficiently used	30

5.3.6	Joint Programming modality and gender equality and women’s empowerment results	31

5.4	Partnerships	32

5.4.1	Complementary and synergistic effects in the broader gender sector and with the Access to Justice Programme	32

5.4.2	Government participation and ownership	33

5.4.3	Partnerships in the programme	34

5.4.4	Implementation capacity of partners	34

5.4.5	Support and coordination of donor to the programme	35

5.5	Effectiveness	35

5.5.1	Achievement of outputs and outcomes	35

5.5.2	Positive and negative unintended results of the JPGBV	51

5.6	Sustainability	51

5.6.1	Strategies that have been put in place to ensure sustainability of results	51

5.6.2	Sub-National level sustainability	53

5.6.3	Community level sustainability	53

5.6.4	Scaling up for sustainability	54

6	Conclusion and Lessons Learned	54

6.1	Conclusion	54

6.2	Lessons Learned	55

6.2.1	Programme design	55

6.2.2	Programme implementation	55

6.2.3	Improving effectiveness of joint programming	56

7	Recommendations	57

7.1	Programme design	57

7.2	Programme implementation	58

7.3	Programme management	58

8	Annexes	59

8.1	Annex 1: Terms of Reference	59

8.2	Annex 2: Evaluation Framework	75

8.3	Annex 3: Theory of Change	82

8.4	Annex 4: VfM Assessment for Victim Friendly Clinics	83

8.5	Annex 5: VfM Assessment of Childline Helpline and Drop in Centre	90

8.6	Annex 6: List of Interviewees	97

8.7	Annex 7: List of Documents Reviewed	99

8.8	Annex 8: Tools	101

8.8.1	Key informant Guide UNWOMEN and UNICEF	101

8.8.2	Key Informant Interview Guide: Min of Gender and Judicial Services Commission,	104

8.8.3	Key Informant Interview Guide: Other Government Ministries Agencies and Institutions	106

8.8.4	Implementing Partners	107

8.8.5	Key Informant Interview Guide: Community Leaders	109

8.8.6	Discussion Guide/Most Significant Change Stories: Beneficiaries	110

8.8.7	Focus Group Discussion Guide: Beneficiaries	111

8.8.8	Focus Group Discussion: Non-Beneficiaries	112

Annex 9: Consent Forms	113

## List of Figures

Figure 1: Training of Church Leaders in Beitbridge	45

Figure 2: SAYWHAT Anti-GBV Ambassadors	45

## List of Tables

Table 1: Number of Interviewees for each methodology	7

Table 2: Alignment of the JPGBV to national commitments	12

Table 3: Division of labour in implementing the joint programme	18

Table 4: Economy assessment	26

Table 5: Programme delivery rates	27

Table 6: Partner delivery rates	27

Table 7: Outcome 1 achievements	35

Table 8: Summary of Key Results for Outcome 1	36

Table 9: Outcome 2 achievements	40

Table 10: Summary of Key Results for Outcome 2	40

Table 11: Outcome 3 achievements	47

Table 12: Survivors and type of service received	47

Table 13: Summary of Key Results for Outcome 3	48

Table 14: Number of girls and young women reached by Childline	49

# Acronyms

| AIDS ACRWC A2J CA CEA CEDAW | Acquired Immunodeficiency Syndrome African Charter on the Rights and Welfare of the Child 1999 Access to Justice Convening Agent Cost Effectiveness Analysis Convention on the Elimination of All forms of Discrimination against Women |
| --- | --- |
| CFP CPEA | Community Focal Person Criminal Code, Criminal Procedures, and Evidence Act |
| CRC | Convention on the Rights of the Child |
| CSO | Civil Society Organisation |
| DANIDA | Denmark's development cooperation under the Ministry of Foreign Affairs |
| EFZ FGD | Evangelic Fellowship of Zimbabwe Focus Group Discussion |
| FST | Family Support Trust |
| GBV | Gender based violence |
| GC GoZ | Gender Commission Government of Zimbabwe |
| HIV JCT | Human Immunodeficiency Virus Justice for Children Trust |
| JPGBV | Joint Programme of Gender Based Violence |
| JSC | Judicial Service Commission |
| KII KRA MICS MSC MoJLPA MPSLSW MWAGCD | Key Informant Interviews Key Result Area Multiple Indicator Cluster Survey Most Significant Change stories Ministry of Justice, Legal and Parliamentary Affairs Ministry of Public Service, Labour and Social Welfare Ministry of Women’s Affairs Gender and Community Development |
| NAP NBSLEA OECD/DAC OVC PCA PUNO RBM | National Action Plan for OVC National Baseline Survey on Life Experiences of Adolescents Development Assistance Committee of the Economic Cooperation and Development/Development Assistance Committee Orphans and Vulnerable Children Partner Cooperation Agreements Participating United Nations Organisation Results-based management |
| SADC | Southern African Development Cooperation |
| SAYWHAT | Students And Youth Working on Reproductive Health Action Team |
| ToR | Terms of Reference |
| TA UN UNDP | Threshold Analysis United Nations United Nations Development Programme |
| UN Women | United Nations Entity for Gender Equality and the Empowerment of Women |
| UNEG | UN Evaluation Group |
| UNICEF | United Nations Children’s Fund |
| VFC | Victim Friendly Court |
| VFM | Value for Money |
| VFU | Victim Friendly Unit |
| WHO WLSA | World Health Organisation Women and Law in Southern Africa |
| ZDHS ZIMSTAT ZNASP ZWLA | Zimbabwe Demographic and Health Survey Zimbabwe National Statistics Agency Zimbabwe National HIV and AIDS Strategic Plan Zimbabwe Women’s Lawyers Association |

# Executive Summary

Background

Description of the programme

To complement government efforts in addressing GBV, UNICEF and UN Women designed a Joint Program on Prevention of Gender Based Violence (JPGBV) against adolescent girls (10-19 years) and young women (20-24 years). The programme is also implemented at the national level. UNICEF and UN Women are partnering with the Ministry of Women Affairs Gender and Community Development (MWAGCD), as the lead government agency to implement the programme. UNICEF is the designated administrative agent (responsible for financial reporting) under the pass through arrangement while coordination on a day to day is done jointly. To facilitate jointness in programme implementation, a steering committee was put in place to “coordinate, oversee and monitor the implementation” of the programme. Members of this structure were MWAGCD, the Danish Embassy and the two UN agencies.

The governmental partners are:  1) MWAGCD; (2) Ministry of Justice, Legal and Parliamentary Affairs (MoJLPA); (3) Ministry of Health and Child Care (MoHCC); (4) Ministry of Public Service, Labour and Social Welfare (MoPSLSW); (5) Ministry of Home Affairs; and (6) the Judicial Service Commission (JSC). The non-governmental partners for the programme are: World Vision; Women’s Trust working in partnership with Tag a Life International; Students and Youths Working on Reproductive Health Action Team (SAYWHAT); Justice for Children Trust (JCT) in collaboration with Women and Law in Southern Africa (WLSA) and Zimbabwe Women Lawyers Association (ZWLA); Childline; and Family Support Trust (FST).

The specific outcomes of the programme are:

- Outcome 1:  National normative and financial GBV framework strengthened

- Outcome 2: Improved preventive measures for GBV

- Outcome 3: Strengthened service delivery for survivors of GBV

Context of the programme

Zimbabwe, like many countries in the world, experiences high levels of gender based violence (GBV) especially among girls and young and adult women as confirmed by several national studies. In response to these challenges, the Government of Zimbabwe (GoZ) intensified efforts in addressing GBV by putting in place systems and structures to redress GBV, including rape. The GoZ is signatory to various regional and international declarations on the rights and protection of women, girls and children which have been domesticated through various legislation and policy.

Purpose of the evaluation

The purpose of the evaluation was to provide an early indication on the achievement of output level-results. It aimed at assessing progress against objectives contained in the log frame, to check if the programme was on track, and if any adjustments were needed, draw conclusions about the programme strategy and inform future programming. Furthermore, the evaluation of the JPGV was meant to provide useful lessons learnt that would inform implementation of the JPGBV and other similar programmes in the future.

The midterm evaluation was also to provide credible and useful information on the added value of Joint Programs in enhancing the achievement of results on gender equality, children’s’ rights and the empowerment of women through improved UN system coherence and efficiency by using joint designs and implementation process.

Evaluation objectives and scope

The objectives of the midterm evaluation were to primarily assess relevance, effectiveness and efficiency. Specifically the evaluation sought to:

- Assess the relevance of JPGBV to the national level priorities and alignment with regional and international agreements and conventions on gender equality, women’s empowerment and children’s rights. The mid–term evaluation was to ascertain the extent to which the JPGBV has been conceptualised, planned and designed jointly to respond to international, regional and national goals and commitments on gender equality and women’s empowerment and the extent to which the JPGBV was informed by needs and interests of diverse groups of stakeholders and beneficiaries.

- Assess progress in achieving planned outputs stated in the programme document, revised log frame and programme outline and document any intended and unintended effects on gender equality, women’s empowerment and children’s rights, including the use of innovative approaches.  It would assess the replicability of the programme at national scale, the ownership of the programme by the government and the contribution of the programme in building the capacity of the government to drive the Gender equality, women’s empowerment and Child-sensitive social protection agenda. The evaluation assessed the contribution of the program in strengthening the capacity of partners (e.g. financial capacity, technical quality of programmes etc.) in complementing government efforts and collaboration.

- Measure how cost effectively JPGBV resources/inputs were converted to results and assess whether or not the JPGBV strategies and interventions deliver Value for Money.

The evaluation was for the period from inception until 30 December 2015.

Evaluation Methodology

The evaluation was undertaken in a participatory manner with the Reference Group being the main instrument for facilitating engagement between the evaluation team, implementers and the donor in reviewing of outputs from the process. The evaluation used a combination of qualitative and quantitative research methods. All data from the field visits was collated, triangulated and verified before conclusions were made.

Evaluation Findings

The findings of the evaluation are organised according to the key themes of analysis: relevance, validity of design, efficiency, partnerships and coordination, effectiveness and sustainability.

Relevance

In this evaluation, relevance answered the question: “To what extent are the objectives and activities of the Joint Program consistent with the evolving needs and priorities of the beneficiaries, partners, and stakeholders?”

The programme is relevant to the context of the country and local communities. The evaluation noted that the programme is relevant to the needs of beneficiaries and meets the needs and priorities of stakeholders. Implementation approaches allowed stakeholders to lead the GBV response in districts.  The programme is directly supporting the MWAGCD to implement its mandate with relation to gender and GBV in particular. By facilitating a local stakeholder driven response, the JPGBV offers opportunities for ownership of GBV initiatives. Programme is well aligned to international, regional and national priorities on gender such as the National Gender Policy (NGP 2013-2017, the National GBV Strategy 2012-2015, the Girls Empowerment Framework, the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence in Zimbabwe and the National Action Plan (NAP) for Orphans and Vulnerable Children (OVC). Further, the programme objectives are aligned to the CEDAW and have contributed to prioritisation for implementation of 7 CEDAW Committee Concluding Recommendations for Zimbabwe.

Validity of design

Validity of design covered the following aspects (1) programme design (2) programme intervention logic (3) Programme results and targets (4) appropriateness of indicators (5) gender and human rights approaches and (6) duplication, coherence and synergies.

Programme design: The programme design was appropriate for addressing GBV among adolescent girls and young women. The “upstream” and “downstream” focus allows for the programme to support behaviour and attitude change while unlocking institutional bottlenecks that undermine efforts to eradicate GBV. The programme fund was flexible in approach providing opportunities for improving effectiveness. Given the many changes to the log frame in two years, shows the programme could have benefited from an inception phase to validate the design.

Programme Theory of Change: Theory of change of the programme was largely logical and remained relevant during the evaluation period. It demonstrates the causal factors and clearly outlines the strategic fit of the programme. Some linkages have been undermined by implementation of the programme and gaps in design:

- limited linkages between evidence from programme implementation in the three districts and the policy level work;

- sequencing of behaviour change interventions after the social norms study may have compromised achievement of results because of insufficient time lag for the results chain to materialize within the programme life;

- the programme had no specific focus on gender dynamics that influence power relations and subsequently GBV in intimate partner relationships. This impedes achievement of the causality chain towards reduction of GBV occurrence;

- the fear of losing a livelihood source is a major contributory factor to under reporting of GBV. This is not well recognised in the programme theory of change; and

- as many perpetrators of GBV, especially sexual violence, are family members, some communities were fearful of reporting because imprisonment of the perpetrator would hurt relations with the extended family. This issue is not well articulated in the programme design and theory of change.

Programme results and targets: Results, targets and indicators for the programme are largely realistic, within the control of the programme and achievable within the timeframe. However, two indicators under Outcome 2 need revisiting because they are activity based while others related to changes in knowledge have no baseline or system for collecting the information to inform progress.

Appropriateness of indicators: Majority of the indicators are appropriate, measurable and within the confines and capacities of the programme. Majority of the indicators also had baseline values available.

Gender and human rights: The programme is firmly premised on gender sensitive and rights based approaches. It also recognises men’s role in GBV and specifically targets them.

Duplication, coherence and synergies: The evaluation did not observe any duplication in the implementation of the programme as the division of labour between UNICEF and UN Women was clear and provided distinct areas of focus.

Design of the joint programme: In the programme design document, day to day coordination of the programme was planned to be done jointly. The lack of a specific PUNO responsible for overall coordination and requisite human resources, in the design, to do so led to challenges in programme wide coordination. The Steering committee has been left as the main platform for ensuring coordination of the programme. Nonetheless, this is inadequate to achieve coordination and make programme implementation jointly. The result has been several missed opportunities to improve programme effectiveness. Sharing of outputs, though not a significant occurrence in the programme design, can lead to a focus on delivery of activities instead of results as accountability for each PUNO remains at the activity level. There is need therefore to change management of those outputs that are co-shared. The deliberate effort by the PUNOs to operate in similar districts for the community level supported implementation of the envisaged theory of change as it enables them to complement their actions. It was important in the JPGBV to come up with operating procedures for the programme. This would harmonise implementation and financial procedures for the PUNOS as they operate with different process structures. Lastly, review of minutes of the Steering Committee shows important decisions were made that have improved efficiency of the programme. But the discussions were not informed by structured monitoring data on the programme undermining the depth of contribution of the governance structure.

Efficiency

Efficiency measures the extent to which the programme has used the least costly resources possible in order to achieve the desired results. The indicator assessed (1) measures taken during planning and implementation to ensure efficient use of resources (2) timeliness in delivery (3) value for money (4) programme governance (5) Joint programming modality and gender equality and women’s empowerment results, and (6) monitoring programme results and performance.

Value for money: The programme implementation presents good economy as unit costs are reasonable. Ideally, the financial cost of managing a case at a victim friendly clinic is $207.66 and the economic cost is $285.22 (See Annex 4 for calculation). Comparing these costs, the JPGBV victim friendly clinics were economic having managed each case at a financial cost of $179.82 and an economic cost of $247.24 (see Annex 4 for calculation). The financial cost of managing a case is $153.53 and the economic cost is $347.39 (See Annex 5). The JPGBV sites where economic having managed each case at an economic cost of $165.19. Through community outreach, meetings and Facebook, SAYWHAT reached 9368 beneficiaries, 51% of whom were females. The project was economic with a cost per beneficiary of $10.66. World Vision reached 28,871 with 50%female coverage. Cost per beneficiary was $4.98.which also represents good economy.

Timeliness of implementation: Programme delivery rates are significantly lower than planned and undermined by significant delays in implementation activities due to the multi-stakeholder nature of some activities and delays in disbursement of funds to CSO partners. After 83% of the planned implementation period had been forgone, expenditure stood at 57.61% of planned budget.

Human resources for the programme: Judging from the human resources allocated to the programme and those financed by the programme the programme management is adequately staffed. However, the distribution of input and streamlining coordination need to be clarified to ensure the available resources are used more efficiently for the programme.

Monitoring and evaluation: Although a joint Results Framework was developed by the PUNOs, each PUNO monitored their own activities using existing tools and approaches in the agencies. This has undermined jointness in programme implementation and making approaches and quality even among programme partners. The monitoring framework adopted for the joint programme was not consistent with the requirements of the joint programming modality (joint tools, joint monitoring visits etc.). The monitoring of systems building, an important focus of the programme to build sustainability remains weak.

Measures taken during planning and implementation to ensure resources are efficiently used: Fiduciary risk management is strong in the programme underpinned by UN fiduciary management systems. However, some of the provisions, such as annual PCAs for CSO partners are not ideal for the nature of results intended by the programme at the community level. This may be undermining efficient use of resources.  The JPGBV PUNOs have adopted approaches that are providing gains in efficiency of resource use such as building on on-going initiatives. Contribution of staff of the UN agencies contributed to lowering costs (to the programme) for management demonstrating the efficiency gains of contracting UN agencies.

Joint programming modality and gender equality and women’s empowerment results: Using the traction of UN Women in the gender sector and that of UNICEF in the child protection sector, the two UN agencies were more easily able to bring stakeholders together than would have been the case as individual agencies. The pace at which legislative reviews were concluded also demonstrates the value addition of UN agencies in programmes aimed at normative reforms. More could have been done however to mobilise CSOs to support the legislative review process thereby increasing visibility and urgency of this agenda.

Partnerships

Complementary and synergistic effects in the broader gender sector and with the Access to Justice Programme: The design of the JPGBV compliments the Justice for Children in Zimbabwe Programme implemented by UNICEF through strengthening implementation of the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence in Zimbabwe. The JPGBV supports capacity building of the referral pathway which ensures more survivors reach the justice system and with appropriate care, support and evidence. The anti-GBV structures at the district level have brought the issue of gender to the forefront and are facilitating collaborations between actors in implementing interventions to address gender.

Government participation and ownership: Government of Zimbabwe’s participation, under the leadership of the MWAGCD, has been central in the programme from conception to implementation. The ministry has led implementation of the anti-GBV committees in the three districts and participated in programme governance and oversight through the Steering Committee. Other key government ministries leading several initiatives of the JPGBV the MoPSLSW for the social norms study and the Ministry of Health and Child Care (MoHCC) on the development of clinical guidelines for management to survivors of sexual abuse and violence.

Partners in the programme: CSO partners selected for the programme have adequate technical capacity and a track record of delivery in their area of expertise and are well known to the UN agency contracting them. However, coordination among partners needs to be improved with creation of a partner specific coordination structure where synergies can be harnessed in a systematic manner.  The programme also explored partnerships outside the programme such as with UNFPA on the National Action Plan on Child Marriages, Centre for Applied Legal Research (CALR) on the revisions to the Children’s Act. These partnerships enhanced both efficiency and effectiveness of the programme.

Implementation capacity of partners: Delivery rates for partners were significantly high despite the challenges with delays in funding. In all areas beneficiaries of the programme showed satisfaction with the knowledge and services provided demonstrating the capacity to deliver services.

UNCEF and UN Women’s technical and resource management, coordination role in the delivery of the joint programme: The UN agencies had sufficient technical capacity to carry out the mandate. UNICEF has demonstrated capacity to fulfil its designated role of Administrative Agent for the JPGBV under the pass through arrangement accountable for effective and impartial fiduciary management. Disbursements and consolidated financial reports were done timely with audited accounts provided annually. A gap in the allocation of roles and responsibilities was the failure by the programme to nominate a Convening Agent, a role partly played by UNICEF.

Support and coordination of donor to the programme: The donor has been closely involved in the programme. The Steering Committee has been a useful structure to facilitate their participation in decision making and steering its direction. Apart from the Steering Committee the donor also provided technical assistance in areas such as communication Apart from the Steering Committee the donor also provided technical assistance in areas such as communication and M and E. For example in communication the donor communication focal point provided opportunities to profile change stories coming out of the JGBV programme while the M and E focal point supported the revision of the Results Framework providing quality assurance and at Steering Committee meeting requiring PUNO’s reporting and accountability towards results.

Effectiveness

Effectiveness measured the extent to which the programme has achieved its intended outputs and objectives as per indicators in the Programme Log frame.

Outcome 1:  National normative and financial GBV framework strengthened: The main indicator for Outcome 1 is the number of CEDAW concluding recommendations related to GBV addressed or implemented by the MWAGCD. The target by end of year 2 was 7 recommendations implemented or addressed. Of the 10 CEDAW concluding remarks related to GBV, seven are being implemented through the district level anti-GBV structures. Results frameworks and action plans were developed for the three districts to facilitate implementation of these recommendations. Of the four Outputs under Outcome 1, three were achieved.

Output 1.1: Strengthen capacity of the Ministry of Justice to align legislation with the Constitution and international commitments on women and girls – achieved.

Output 1.2: Enhanced knowledge-base of line-Ministries and Parliament on budgeting and advocating for implementation of the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence

This output was postponed to year three.

Output 1.3: Strengthened capacities of Gender Equality Advocates to influencing zero-tolerance and increased resources for implementation of GBV commitment.

Support to gender advocates resulted in one advocacy strategy being developed. Furthermore, two position papers were developed and submitted to parliament in June 2015.

Output 1.4: Improved Leadership and capacity of Ministry of Women Affairs, Gender and Community Development to co-ordinate the implementation of GBV commitments.

Achieved through revival of anti-GBV committees to implement CEDAW recommendations and support to the MWAGCD at national level. This has resulted in several CEDAW recommendations for Zimbabwe having begun to be implemented.

Outcome 2: Improved preventive measures for GBV: Outcome 2 was only partially achieved. The Social Norms Strategy was to be premised on a social norms study, which had not been concluded at the time of the evaluation. There was progress with regards religious and traditional leaders.

Output 2.1: Enhanced national evidence strategy on social norms fuelling GBV and increased knowledge on effective behaviour change interventions to inform existing and future programming on the prevention of violence against women and girls.

Innovative methodology to measure social norms was developed and piloted in collaboration with UNICEF Innocenti Research Centre, University of Edinburgh and Women’s University in Africa during the evaluation period. Also, secondary data analysis of National Baseline Survey on Life Experience of Adolescent (NBSLEA), literature review on GBV and violence against children completed, all of which will significantly contribute to the social norms strategy.

Output 2.2: Improved knowledge amongst girls to seek services and know their rights to better protect themselves against violence in accordance with strategic area 3 Safety and Protection in the Girls and Young Women’s Empowerment Framework

In 2016 following the Constitutional Court Ruling banning child marriages in Zimbabwe, the main focus of this output was revised to focus on the implementation of the Campaign on Ending Child Marriages through collaboration with CSOs and Ministry of Women Affairs Gender and Community Development. The work undertaken by the CSOs will contribute towards raising awareness of girls and their parents and communities on effects of child marriages, prevention measures and where to seek services for those at risk of early marriages to protect themselves.

Output 2.3: Strengthened capacities of traditional and religious leaders; men and boys to implement strategies that address negative social norms such as child marriage and forced marriage.

The JPGBV supported three CSO partners to build and strengthen the capacity the stated target groups. World Vision engaged umbrella bodies on religious institutions and mainstreamed gender in the curricular of 6 Theological colleges. Further church leaders in Makoni, Bindura and Beitbridge trained on gender developed action plans which they implemented including integrating issues of GBV in their sermons. SAYWHAT through the male ambassadors in the three districts reached out to men through regular village/community forums on GBV. At tertiary education institutions, Men to men Clubs and Heforshe Clubs were formed and young men were engaged and mobilised to take actions to end GBV on campuses. Justice for Children Trust trained traditional leaders and traditional courts officials on the law relating to GBV.

Outcome 3: Strengthened service delivery for survivors of GBV: Outcome 3 was achieved. The programme supported 4,019 adolescent girls and young women age 13-24 years in the three districts who experienced any form of violence/abuse (target was 3,000). Output 3.1 aimed at strengthening capacity of government and civil society to promote accessible survivor focused GBV services for girls and young women was partially achieved.

Sustainability

Sustainability measured the extent to which the programme had inbuilt sustainability mechanisms at national, sub-national and community level.

At national level, the JPGBV has inherent sustainability mechanisms reflected in the capacity development of relevant ministries in addressing GBV and development of legislation and government action plans concerning specific GBV issues. The UN agencies are incorporating activities funded under the JPGBV in alternative programmes and annual work plans from core funding. At sub-national level, the Anti-GBV Committees in the three rural districts have become established district structures that will guarantee continuity of activities. CSO/Government collaboration established at national level is replicated at sub-national level for increased institutional involvement and engagement at sub-national and community level. At community level, national duty-bearers and rights holders participate and are included in the programme at community level. The JPGBV is implemented through established government structures and utilising community cadres.

Analysis: While the work on building systems and capacity has been evident in the programme, effectiveness and sustainability of these initiatives is undermined by several issues. First the government is resource constrained and may not be able to recruit, apply and sustain the capacity being advocated in the programme. It would be prudent to explore how; for example, the work on Clinical Guidelines on Managing Sexual Abuse can be incorporated in current health systems strengthening initiatives such as the Health Development Fund. Further training of nurses needs to overcome the reluctance of health staff to attend court cases which in turn makes them shun attending to survivors of GBV as they will be required to present evidence in court. For example, of the five trained at Beitbridge Hospital on two were available. The reluctance stems from the fear of interrogation process by advocates in court.

The threat from waning motivation due to lack of resources is there given the amount of funding for gender including GBV work (which undermines implementation of the committee’s plans). The anti-GBV committees will continue to meet if there are resources for programming as a committee. Without this the Committee will be reduced to a “talk show” and overtime may become dysfunctional a fate that has befallen several gender based violence committees at this level in the past e.g. the Inter-ministerial task force on GBV. The MWAGCD is one of the poorly funded ministries in government. In the 2014/2015 the ministry was allocated a paltry US$50,000 for programmes. It is therefore clear that the MWAGCD will not be able to sustain the committees in the short term and a strategy is required in the remaining period to sustain them. The programme should explore linkages with other programmes e.g. the Integrated Support Programme, and other GBV related programmes in Zimbabwe to support the committees. To do this it will need to demonstrate the effectiveness of the committees in enhancing locally driven anti-GBV responses – which are inherently sustainable in the long term. Other opportunities such as including the private sector in the committees could serve as an avenue of sourcing financing for the committees’ activities. Given the above, it may be advisable for the programme to consider focusing and strengthening the current three districts than engage new ones. However, the evaluation is also aware that the programme has already begun the process of reviving and strengthening the anti-GBV structures in the five districts. In this case it is advisable for the programme to consider ways to support and strengthen the existing anti-GBV Committees in the three districts (Beitbridge, Bindura and Makoni).

Recommendations

The following recommendations are premised on the findings of the evaluation. While the evaluation was framed as a mid-term evaluation, it was conducted towards the tail end of the programme. Therefore the recommendations provided below are aimed to assist the programme build a strong exit strategy and more so how a similar programme in the future needs to be designed and implemented

Programme design

- Recommendation 1: Considering that GBV is mainly in the “home”, that is, perpetrated by close relations, fear of the loss of livelihood which is mainly provided by the perpetrators and extended family is a real concern among survivors which poses the risk of undermining efforts to reduce GBV occurrence. It is therefore recommended that UN agencies should consider incorporating livelihood support in a GBV programme.  It is not envisaged that the contracted CSOs or the UN agencies should deliver this support – as it requires specialised knowledge, but rather stronger linkages between the GBV action and other programmes delivering livelihoods support to specifically target survivors of GBV as part of efforts to mainstream gender. (Responsibility: UNICEF and UN Women)

- Recommendation 2: Challenge of overlapping responsibilities of MWAGCD and MoPSLSW vis a vis the role they play for provision of services for the girl child and young women (interpretation of the law and policy). Given that reporting was being undermined by the availability of safe homes for overnight stay and reprieve in the period of abuse, it is recommended that future GBV programmes by UN agencies and government considers supporting places of safety for  adolescent girls with children and adult women and their children.  However, this has to be underpinned by harmonisation of the SOPs for Shelters and the Children Act’s Safe Placement Procedures for Children. MWAGCD and MoPSLSW need to agree on their respective roles and responsibilities and if needed work towards amendment of legislation for further clarification of these. (Responsibility: UNICEF and UN Women)

- Recommendation 3: Considering a large number of adolescents are found in school system, the GBV programme should address lack of systematic engagement with engaging with the Ministry of Education and create linkages with the existing Education sector work (such as EDF). There are also possibilities of linking with other UNICEF interventions in schools such as the safe schools initiative. Lack of doing the above will be a missed opportunity. (Responsibility: UNICEF)

- Recommendation 4: There should be a continued investment in strengthening of government capacity to address GBV using existing systems strengthening initiatives. An existing opportunity includes the Health Development Fund which can take up roll out of the Clinical Guidelines for the Management of Sexual Abuse. UN Women working with the MWAGCD needs to continue strengthening the three pilot anti-GBV committees. To do this, UN Women needs to support financing of activities and reviews of progress on GBV. A study that provides an in-depth analysis of the effectiveness and lessons learned from the Anti-GBV Committees needs to be conducted. The results would showcase the usefulness of the structures to leverage support from other stakeholders involved in gender programming at the district level.   (Responsibility: UNICEF and UN Women)

- Recommendation 5: The lack of an inception phase undermined planning and verification of the programme design. An inception phase, ideally six months, would have enabled the programme implementers to validate the design, development of a harmonised monitoring framework, established of programme coordination structures and revise certain features of the programme early on in its implementation. In the future, it is recommended that the DANIDA considers an inception phase in programmes of this nature. (Responsibility: DANIDA, UNICEF and UN Women (in designing future joint programmes).

Programme implementation

- Recommendation 6: The programme had no baseline for indicators related to knowledge, attitudes and behaviour change. Because of this measurement of results achieved by the programme at this level is difficult. There is need for a future programme to conduct a baseline survey at the onset in order to measure its achievements. This should be supported by an inception phase. (Responsibility: UNICEF and UN Women).

Programme management

- Recommendation 7: Consider having a full time joint programme coordinator from the inception to enhance coordination of the programme. The coordinator will be responsible for coordinating the activities of the agencies in the joint programme but housed in the nominated coordinating agency. This has to be incorporated in the design of joint programmes and its financing. The coordinator would help to identify opportunities for joint implementation of activities thus enhancing efficiencies expected from a joint programme.   (Responsibility: UNICEF and UN Women).

- Recommendation 8:  While each individual UN agency monitored its components, this is insufficient in the context of joint programming. It is undermining programme wide monitoring. The programme has to:

  - have one M&E system – tools, guidelines and results framework; and

  - incorporate systematic joint monitoring visits. (Responsibility: UNICEF and UN Women)

- Recommendation 9: The strong fiduciary risk management of the UN Women systems obligates UN Women to disburse funds on a quarterly basis and for 80% of all disbursement to be utilised and verified before the next disbursement is made. In some instances, the exercise of this fiduciary risk management was not timely thereby affecting time period for implementation. Considerations for time needed in the exercise of these fiduciary risk management processes need to be factored in future programme implementation.  (Responsibility: UN Women)

- Recommendation 10: The programme has not had strong documentation of results. The evaluation observed significant results and lessons that could benefit from in-depth profiling. It is recommended that in the remaining period of the programme, the participating UN agencies priorities documentation of results, lessons and best practices from the programme. (Responsibility: UNICEF and UN Women).

# Introduction

This report presents findings of the mid-term evaluation of the Joint Programme on Prevention of Gender Based Violence (JPGBV) Against Young Women and Adolescent Girls (JPGBV). The evaluation was conducted by a three member team:

- Team Leader: Dr. Nyasha Madzingira

- Lazarus Muchabaiwa: Economist

- Mavis Kahwemba: Gender Specialist

- Quality Assurance: Ngonidzaishe Marimo

Though a mid-term evaluation, it was conducted close to the end of the programme due to the lengthy process of recruiting the evaluators. The process to carry out a midterm evaluation started in July. The negotiations with the Ministry (Ministry of Women Affairs Gender and Community Development) were completed by September. The recruitment process was done through UNDP on behalf of UNWOMEN, and was initiated in October and was finalized end of January. Given the delays it was decided to have the evaluation cover up to end of 2015.

# Background

## Gender Based Violence among Adolescents Girls and Young Women

Gender based violence (GBV) is a well-documented public health, human rights, economic and social concern throughout the world. According to the 2010-11 Zimbabwe Demographic and Health Survey (ZDHS), 30% of all women age 15-49 years reported that they had experienced physical violence since the age of 15, while 27% of women had experienced sexual violence since the age of 15, of which nine out of ten cases were perpetrated by the woman’s spouse, partner or boyfriend. Twenty two percent of women who have had sexual intercourse reported that their first experience was forced against their will. Further, only 37% of women who experience physical or sexual violence have sought help.

The National Baseline Survey on Life Experiences of Adolescents, 2011 indicated that 33% of females of age 18-24 years reported that they had experienced some form of sexual violence before reaching the age of 18 years, while nine percent of males reported the same. About 51.8% of females and 45% of males disclosed the abuse. The same study showed that 64% of females and 76% of males of age 18-24 years reported experiencing some form of physical violence. Of these, only 3.5% of females and 2.7% of males received professional help.

Studies have indicated that adolescent girls and boys marry before the age of 18. The Multiple Indicator Cluster Survey (MICS) 2014 showed that one in four girls (24.5%) and 1.7% of boys age 15-19 years were currently married or in union. Among women age 15-49 years about one in twenty (4.9%) were married before age 15 and among women age 20-49 years, about One in three (32.8%) were married before age 18. The MICS findings confirm those from the ZDHS 2010/11 that showed that 33% of women age 20-49 years are married or in union before age 18.

The GoZ is a party to various regional and international instruments on the rights and protection of women, girls and children. At international level, these include the International Labour Organisation (ILO) Convention on the Worst Forms of Child Labour number 182 of 1999; the Convention on the Elimination of All forms of Discrimination Against Women (CEDAW), 1998; and the Convention on the Rights of the Child, 1989. Regional instruments ratified include the SADC Protocol on Gender and Development, 2008; the African Charter on the Rights and Welfare of the Child, 1999; and Protocol to the African Charter on Human and People’s Rights on the Rights of Women in Africa 1995.

Various legislation enacted or reviewed to domesticate these international commitments provide a framework through which the Government of Zimbabwe responds to protection and addressing rights of women and children. Reforms and amendments have been made to the criminal code; domestic violence act; and constitutional amendments with regard to women’s and children’s rights. The government also developed the National Gender Based Violence Prevention Strategy 2012-2015 to improve the efforts of Government, civil society and donors to prevent and respond to GBV. The Goal of this GBV Strategy is to reduce all forms of gender based violence in Zimbabwe by 20 percent by 2015. The National GBV strategy has four key result areas which are: Prevention; service provision; coordination and research; documentation, monitoring and evaluation. Further, several policies, strategies and programmes have been initiated to promote achievement of the rights of women and children including: gender responsive budgeting; the National Action Plan for OVC (NAP I 2006-10 and NAP II 2011-15); the Protocol on the Multi-sectoral Protocol on the Management of Sexual Violence, 2012; the National Gender Policy 2013-2017; and the girls’ and young women’s empowerment framework 2014. While the government has a good framework for addressing GBV funding for GBV programming has been limited. Secondly many programmes on GBV have addressed adults and children but there remained a gap in addressing specific needs and GBV among adolescents (10-24 years) as a special group.

## Programme Description

To complement government efforts in addressing GBV, UNICEF, UN Women and the Ministry of Women Affairs Gender and Community Development (MWAGCD) designed a Joint Program on Prevention of Gender Based Violence (JPGBV) against adolescent girls (10-19 years) and young women (20-24 years). UNICEF is the nominated administrative agent (AA) while coordination is done by the two Participating United Nations Organisations (PUNOS) (UN Women and UNICEF) on a day to day basis. The Joint Programme on Prevention of Gender Based Violence Against Young Women and Adolescent Girls (JPGBV) is a three year program (2013-2016). The program started in November 2013.The initial plan was to implement in 10 districts. These were reduced to three districts for full service delivery and five for limited activities after the call proposals revealed that the funds were inadequate to implement in ten districts. The final three districts in which the project is being implemented are: Beitbridge, Bindura and Makoni.

The programme works with government and Civil Society Partners. The main government Partners include: (1) MWAGCD; (2) Ministry of Justice, Legal and Parliamentary Affairs (MoJLPA); (3) Ministry of Health and Child Care (MoHCC); (4) Ministry of Public Service, Labour and Social Welfare (MoPSLSW); (5) Ministry of Home Affairs; and (6) the Judicial Service Commission. The implementing partners are: World Vision; Women’s Trust working in partnership with Tag a Life International; Students and Youths Working on Reproductive Health Action Team (SAYWHAT); Justice for Children Trust (JCT) in collaboration with Women and Law in Southern Africa (WLSA) and Zimbabwe Women Lawyers Association (ZWLA); Childline; and Family Support Trust (FST).

The total funding for the programme is US$4,915,730.00.

### The JPGBV Outcomes and Outputs

The initial Log frame for the programme was revised in in March 2014, April 2015 and February 2016 to address the following:

- Adjusting the geographical coverage of programme in line with available resources and aligning to districts that already had Victim Friendly Units in place.

- Re-focusing of outcomes, outputs, indicators, and means of verification and targets to be succinct.

- At present, there are no national official indicators or targets on social norms. The preventive indicators and targets added in the revised Log frame under Outcome 2 aim to address this gap.

Based on these revisions, below are the outcomes and outputs of the JPGBV Log frame:

Outcome 1:  National normative and financial GBV framework strengthened

Output 1.1: Strengthen capacity of the Ministry of Justice to align legislation with the Constitution and international commitments on women and girls.

Output 1.2: Enhanced knowledge-base of line-Ministries and Parliament on budgeting and advocating for implementation of the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence.

Output 1.3 Strengthened capacities of gender equality advocates to influencing zero-tolerance and increased resources for implementation of GBV commitments.

Output 1.4: Improved Leadership and capacity of MWAGCD to co-ordinate the implementation of GBV commitments.

Outcome 2: Improved preventive measures for GBV

Output 2.1: Enhanced national evidence strategy on social norms fuelling GBV and increased knowledge on effective behaviour change interventions to inform existing and future programming on the prevention of violence against women and girls.

Output 2.2: Improved knowledge amongst girls to seek services and know their rights to better protect themselves against violence in accordance with strategic area 3 Safety and Protection in the Girls and Young Women’s Empowerment Framework.

Output 2.3: Strengthened capacities of traditional and religious leaders; men and boys to implement strategies that address negative social norms such as child marriage and forced marriages.

Outcome 3: Strengthened service delivery for survivors of GBV

Output 3.1: Strengthen capacity of government and civil society to promote accessible survivor focused GBV services for girls and young women.

# About the Evaluation

## Purpose of the Evaluation

The purpose of the evaluation was to provide an early indication on the achievement of output level-results. It aimed at assessing progress against objectives contained in the log frame, to check if the programme was on track, and if any adjustments were needed, draw conclusions about the programme strategy and inform future programming. Furthermore, the evaluation of the JPGV was meant to provide useful lessons learnt that would inform implementation of the JPGBV and other similar programmes in the future.

The midterm evaluation was also to provide credible and useful information on the added value of Joint Programs in enhancing the achievement of results on gender equality, children’s’ rights and the empowerment of women through improved UN system coherence and efficiency by using joint designs and implementation process.

## Evaluation Objectives and Scope

The objectives of the midterm evaluation were to primarily assess relevance, effectiveness and efficiency. Specifically the evaluation sought to:

- Assess the relevance of JPGBV to the national level priorities and alignment with regional and international agreements and conventions on gender equality, women’s empowerment and children’s rights. The mid–term evaluation was to ascertain the extent to which the JPGBV has been conceptualised, planned and designed jointly to respond to international, regional and national goals and commitments on gender equality and women’s empowerment and the extent to which the JPGBV was informed by needs and interests of diverse groups of stakeholders and beneficiaries.

- Assess progress in achieving planned outputs stated in the programme document, revised log frame and programme outline and document any intended and unintended effects on gender equality, women’s empowerment and children’s rights, including the use of innovative approaches.  It would assess the replicability of the programme at national scale, the ownership of the programme by the government and the contribution of the programme in building the capacity of the government to drive the Gender equality, women’s empowerment and Child-sensitive social protection agenda. The evaluation will also assess the contribution of the program in strengthening the capacity of partners (e.g. financial capacity, technical quality of programmes etc.) in complementing government efforts and collaboration.

- Measure how cost effectively JPGBV resources/inputs were converted to results and assess whether or not the JPGBV strategies and interventions deliver Value for Money.

Secondary objectives included:

- Identifying and documenting key contributions and added value of short term intended and unintended, positive and negative effect of the JPGBV program on women and girls in Zimbabwe.

- Assessing the extent to which JPGBV has led to complementary and synergistic effects in the broader gender sector and how this has been done; the role and contribution of the GoZ in steering and supporting the implementation of the programme; if the program has strengthened national ownership through participation and inclusion of the government including provincial and district level structures; the nature and quality of partnerships forged during programme implementation and assess how the implementing partners worked together during programme implementation; the implementation capacity, performance and spending rates of the partners that are implementing the program; and the support and coordination of the donor to the programme, including timeliness of tranche payments, strategic direction and coordination.

- Assessing and documenting the strategies that have been put in place to ensure sustainability of results; the possibility of continuation of benefits accrued to date from the JPGBV intervention and recommend any other strategies for sustainability based on lessons learned from other programs and evaluations. The evaluation considered four dimensions of sustainability namely- Sustainability of the results of JPGBV implementing partners; Community level sustainability; Scaling up for sustainability; and Sustainability challenges and mitigatory strategies.

- Reviewing the monitoring systems that were put in place and make recommendations for improving monitoring systems for similar programs especially joint programs. Review and update the programme risk matrix.

- Reviewing how adequate, efficient, effective and responsive UNICEF and UN Women are in achieving the technical and resource management role for the program.

- Assessing how effective the joint program was in terms of coordination, partnership, implementation procedures, within relevant UN Agencies in terms of sharing of resources, cost reduction, and any benefits of a joint program.

- Assessing how the management structure of the joint program is working, identify strengths and areas that need strengthening.

- Assessing any inter-linkages between UNICEF access to justice program and UNICEF’s component of the JPGBV.

The evaluation was for the period from inception until 30 December 2015.

# Methodology

The evaluation was undertaken in a participatory manner with the Reference Group being the main instrument for facilitating engagement between the evaluation team, implementers and the donor in reviewing of outputs from the process. The evaluation also used a combination of qualitative and quantitative research methods. Qualitative data collection approaches were used to answer the specific evaluation questions as detailed in the Evaluation Framework (Annex 2). In addition to providing information to answer the evaluation questions, qualitative data was used to provide explanation to emerging themes in the analysis. Quantitative data on the other hand was used to determine: progress on the log frame; and data on outputs to determine specific questions on efficiency (e.g. determining delivery rates). Quantitative data was obtained from secondary data sources.

Gender and human rights were incorporated in the evaluation in various ways. First the evaluation methodology ensured rights holders and duty bearers were both included in the process of data collection. Second, the data collection approach utilised recognised the implications gender has in respect to women’s inability to express themselves in the presence of women, especially on issues of GBV. Therefore, separate groups of women and men, and boys and girls were interviewed during the evaluation. All data collected from primary and secondary data sources was sex disaggregated. The tools that were utilised for the evaluation explored impact of the programme on the realisation of the rights of women and girls with regards GBV.

Key guiding principles of the evaluation were:

- Human rights – The evaluation assessed if the key principles in human rights were integrated i.e. availability of services, access to services, awareness raising, participation and control.

- Participatory and inclusivity –The evaluation used participatory methods for data collection (case studies, FGDs, KI interviews) and respondents include both beneficiaries and non-beneficiaries.

- Gender equity/non-discrimination - The evaluation assessed if the key principles as in the Girls’ empowerment framework were integrated i.e. availability of services, access to services, awareness raising, participation and control.

- Independence, objectivity and impartiality to ensure credibility and legitimacy to evidence based evaluation results – the evaluation team maintained independence of opinion supported by verified facts.

## Sampling

At the national level all stakeholders that contributed to the programme as beneficiaries or implementers were interviewed. This included the two participating UN agencies, government ministries and departments and non-governmental organisations. Interviews were conducted with a purposively selected individual deemed to have the knowledge of and experience with the JPGBV.

All target districts of the programme were visited for the evaluation (Bindura, Beitbridge and Makoni). In each district interviews were held with agencies in the VFS and those participating in the anti-GBV committee. Community level interviews were held with the following groups:

a)	young men;

b)	young women;

c)	adult men;

d)	adult women;

e)	community leaders (traditional and religious);

f)	nurses at local clinics; and

g)	community based volunteers e.g. CFPs.

These respondents were selected based on participation and self-selection. Self-selection occurred in that, communities were informed of the evaluation and discussions and asked to attend. Those that attended were interviewed.

Table 1 provides information on the number of people met during the study.  A total of 454 boys, girls, women and men were interviewed during the evaluation. A total of 43 traditional and religious leaders were also spoken to. All members of the Steering Committee and all CSO partners were interviewed.

Table 1: Number of Interviewees for each methodology

| Method | Respondent | Number of interviews planned | Actual conducted |
| --- | --- | --- | --- |
| National level |  |  |  |
| KII | UNICEF | 2 | 1 |
|  | UNWOMEN | 2 | 2 |
|  | DANIDA |  | 2 |
|  | Ministry of Women Affairs, Gender & Community Development | 1 | 1 |
|  | Ministry of Justice | 1 |  |
|  | Ministry of Health and Child Care | 1 | 1 |
|  | Ministry of Public Service Labour and Social Welfare | 1 | 1 |
|  | Judicial Services Commission | 1 | 1 |
|  | Prosecutor General | 1 |  |
|  | Police VFU | 1 |  |
|  | Leonard Cheshire Disability Zimbabwe Trust | 1 | 1 |
|  | National based CSO partners (FST, SAYWHAT, JCT, ZWLA, WILSA, World Vision, Women’s Trust) -2 per partner | 14 | 14 |
|  | Total | 26 | 24 |
| District level |  |  |  |
| FGD | Adolescent girls (10-19) | 90 | 103 |
|  | Young women (20-24) | 90 | 107 |
|  | Women non-beneficiaries | 90 | 91 |
|  | Men beneficiaries | 90 | 72 |
|  | Boys beneficiaries | 90 | 81 |
|  | Traditional leaders | 15 | 35 |
|  | Religious leaders | 15 | 18 |
|  | Total number interviewed per district | 480 | 507 |
| KII | Regional Magistrate | 2 | 3 |
|  | Entry meeting with the anti-GBV structures | 3 | 3 |
|  | One stop centre staff (if applicable) | 1 | 3 |
|  | Ministry of Health and Child Care | 3 | 2 |
|  | CSO staff | 7 | 7 |
|  | Ministry of Women Affairs, Gender & Community Development | 3 | 3 |
|  | Department of Social Services | 3 | 4 |
|  | Police VFU | 3 | 3 |
|  | Other members of the anti-GBV structures | 3 | 3 |
|  | Total KIs per district | 28 | 31 |
| MSC story | Adolescent girls (10-19) | 1 | 1 |
|  | Young women (20-24) | 1 | 1 |
|  | Total per District | 2 | 2 |

## Data Collection Methods

Primary and secondary sources of data were utilised to inform findings of the evaluation. The mix of methods allowed for information to be triangulated and verified.

### Primary data sources

Qualitative data collection was mainly comprised of Focus Group Discussions (FGDs); Key Informant Interviews (KIIs); and Most Significant Change (MSC) case study stories.

The process of developing tools was participatory. The Reference group reviewed the tools and revisions requested incorporated by the evaluation team. This included: tailoring the tools to the different stakeholders of the programme. See Annex 9 for the tools used.

### Secondary data sources

Quantitative data was drawn from mainly secondary data sources specific to the project:

- partner and JPGBV programme reports;

- programme budgets from partners;  and

- statements of expenditure from partners.

Literature for outcomes was limited to project documents because the programme was not national but localised.

Other programme specific literature such as:

- Steering Committee meeting minutes;

- Quarterly and Annual report by the PUNOs to DANIDA; and

- Programme design document.

## Data Analysis

All data from the field visits was collated, triangulated and verified before conclusions were made. Qualitative analysis used thematic analysis that distils trends in the qualitative data on different themes of analysis. MS Excel software was used for this analysis. The quantitative data was used to measure progress on the targets. MS excel was used to analyse quantitative data related to the cost efficiency assessment.

## Review and Validation Process

The Evaluation Reference Group made up of representatives of the main stakeholders of the JPGBV was constituted. The Evaluation Reference Group was responsible for reviewing all outputs (Inception and Draft Report) and providing advice on the design of the evaluation.

## Stakeholder Participation

Primary stakeholders of the JPGBV (UN agencies, government ministries, and CSOs) participated in the evaluation in various ways as:

- reviewers of the evaluation design;

- respondents during the consultations;

- reviewers of the draft evaluation report; and

- participants in the national validation workshop

The stakeholders were selected based on their participation and interests in the programme. A reference group and management committee were established as structures to facilitate stakeholder participation. The management committee consisted of members of the Steering Committee (PUNOs, DANIDA and MWAGCD). The two structures were responsible for reviewing outputs and advising on an appropriate approach and methodology of the evaluation.

Beneficiary participation was facilitated during data collection (using methods highlighted in section 3.2).

## Ethical Considerations

Ethics is defined as the values and morals upheld during interaction with others during the collection of data and the dissemination of findings (Merriam, 1988). The Evaluation observed the following:

- Full consent was obtained from the participants before everything else because voluntary participation in the evaluation was a priority. Consent forms developed for the evaluation are in annex 9.

- Research participants were not subjected to harm in any way.

- Respect for the dignity of research participants was prioritized.

- The protection of the privacy and anonymity of individuals participating in the evaluation was ensured (participants are not be identified in report).

- Confidentiality of the evaluation data was ensured and participants assured of this. Where there was need to refer a case then the participant was informed of shared confidentiality (consent form).

- Any deception or exaggeration about the aims and objectives of the evaluation were avoided.

- Any type of communication in relation to the evaluation was done with honesty and transparency.

- Any type of misleading information, as well as representation of primary data findings in a biased way was avoided.

- The use of offensive, discriminatory, or other unacceptable language was avoided in Interviews/Focus group discussions

- Highest level of objectivity in discussions and analyses was maintained throughout the evaluation.

Furthermore the evaluation took cognisance that marginalised and vulnerable groups, who in some cases might have gone through forms of gender based violence, will be involved in the consultations. The evaluation, therefore, adhered to ethical standards for interviewing survivors of GBV as provided in the WHO guidance document on consultations with GBV survivors.

## Limitations

The following were limitations of the evaluation:

- Some stakeholders could not be interviewed as they were not available during the period of interviews e.g. members from the MoJLPA. This is did not affect the contents of the evaluation as the results were well documented.

- the evaluation was conducted at the tail end of the programme. The evaluation is for the period from inception to 30 December 2015. Activities conducted in the last year, 2016, are not covered by the evaluation. The report has been developed as a mid-term evaluation report and captures recommendations for an on-going programme.

# Findings

This section presents findings of the evaluation organised according to the following:

- Relevance;

- Validity of Design;

- Efficiency;

- Effectiveness; and

- Sustainability.

## Relevance

The evaluation of relevance answered the question: “To what extent are the objectives and activities of the Joint Program consistent with the evolving needs and priorities of the beneficiaries, partners, and stakeholders?”

### Needs of beneficiaries

Finding 1: The programme is relevant to the needs of beneficiaries.

Firstly, GBV among adolescents and young women was noted as an issue of concern in all target communities visited.

‘The Joint Programme On Prevention of Gender Based Violence (JPGBV) Against Young Women and Children is a good programme and is of relevance to Bindura District given the high prevalence rate of GBV in the district especially in the mining and farming compounds’. KII Bindura District

Secondly, the lack of knowledge was highlighted as one of the main drivers of GBV. The evaluators came across numerous cases of adolescents and young women who had experienced abuse but had either no knowledge of where to report or whether the incident was an abuse of their rights.

Community members credited activities of the programme in raising their awareness leading to high reports of abuse after these awareness meetings. This was also confirmed by partners who highlighted increase in reporting of abuse after awareness visits.

Third, while increased knowledge and awareness triggered reporting of cases, in some cases children and young women remained powerless to report as majority of abuse is perpetrated in the home by close relatives. To address this concern, the introduction of Community Focal Persons provided opportunities for identification of such cases and avenues to report in confidence – “these women are like spies in our community. They look for girls and women being abused and assist them to report and get assistance. It makes people fear abusing girls and women” (men in Beitbridge). Working with Childline and promoting their free call in services also played a role. Last, through supporting revival of the anti-GBV structures in the three districts the programme managed to also galvanize stakeholder interest on the issue of GBV. This contributed to strengthening of the referral pathway for GBV survivors as each stakeholder was called to action.

### Needs and priorities of institutional stakeholders

Finding 2: The programme meets the needs and priorities of stakeholders.

The programme is directly supporting the MWAGCD to implement its mandate with relation to gender and GBV in particular. It is providing opportunities for strengthening the MWAGCD coordination role through the revival of the anti-GBV committees in the three districts. Direct support for strengthening capacities of stakeholders in the referral pathway e.g. police and nurses, has potential to contribute to improving service delivery in the referral pathway for GBV survivors and ultimately implementation of the Zimbabwe government’s procedures on multi-sectoral management of sexual abuse in Zimbabwe.

While there are several structures that deal with abuse including: the Child Protection Committee and Victim Friendly Sub-committee – the anti-GBV committees provide a platform where GBV (a result of gender power relations) receives special focus. Anti-GBV committees therefore introduced an apex platform for convergence of multi-sectoral stakeholders on GBV. This has enabled local stakeholders to define localized responses to GBV through district specific results frameworks. It has also facilitated collaborations between organisations and with government.

By facilitating a local stakeholder driven response, the JPGBV offers opportunities for ownership of GBV initiatives. Interviews with stakeholders in the three districts showed there is a motivation among stakeholders to address GBV as highlighted by the functionality of the anti-GBV committees (through consistent quarterly meetings and joint implementation in instances). Several stakeholders highlighted how the structure had helped them. VFU and staff from the DCWPS in Beitbridge highlighted how the anti-GBV committee had enhanced collaborations with other departments and ministries especially the MWAGCD. In Makoni, multi-stakeholder collaborations were undertaken during awareness visits in communities and Orange Day commemorations.

### Alignment with international, regional and national priorities

Finding 3: Programme is well aligned to international and regional priorities on gender.

The programme objectives are aligned to the CEDAW and have contributed to prioritisation for implementation of 7 CEDAW Committee Concluding Recommendations for Zimbabwe. JPGBV directly contributed to development of Results Frameworks by each of the three target districts to implement four of these prioritized recommendations (see section 4.3 for more details on these recommendations). The JPGBV directly contributes to assisting the Government of Zimbabwe meet its commitments in SADC Gender Protocol and Development Articles 20 to 25 under Part 6 of the protocol. It also directly contributed to Part 1 Articles 6 to 8 on legal rights (Domestic Legislation, Equality in Accessing Justice, and Marriage and Family Rights).

Finding 4: Programme is well aligned to national priorities on gender

Table 2 illustrates how the programme is aligned to national priorities.

Table 2: Alignment of the JPGBV to national commitments

| National Development Plan/Policy | Relevant strategy/outcome |
| --- | --- |
| National Gender Policy (NGP 2013-2017) | the JPGBV is aligned to all policy strategies of the GBV pillar of the gender policy (conducive legal and policy environment for eradication of all forms of GBV, eradication harmful religious and cultural practices, social norms, beliefs and attitudes reinforce acceptance of GBV, strengthening of multi-sectoral stakeholders, strengthening institutional and coordination mechanisms for addressing GBV at all levels, and encourage open platforms such as for men to discuss GBV.) |
| National GBV Strategy 2012-2015 | JPGBV is aligned to the following key result areas (KRA) of the National GBV Strategy: - KRA 1: Prevention - KRA 2: Service Provision - KRA 4: Coordination The strategy seeks to ensure effective coordination and prevention of gender based violence initiatives and the strategy places special focus to addressing safety and protection for girls and women. |
| Girls and Young Women’s Empowerment Framework | The JPGBV is aligned to the Girls and Young Women’s Empowerment Framework by specifically addressing Pillar 3 – Safety and Protection. |
| Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence in Zimbabwe | The Protocol promotes a coordinated and integrated approach to sexual abuse and has been expanded to include girls and women – who share the brunt of sexual violence. The JGBV supports implementation of the through capacity building and enhancing coordination of the multi-sectoral referral pathway. |
| National Action Plan (NAP) for Orphans and Vulnerable Children (OVC) | The NAP for OVC seeks among other issues to enhance safety and protection of children. The vision of the Programme is that by 2020 all children in Zimbabwe will live in a safe, secure and supportive environment that is conducive to child growth and development. The JPGBV directly contributes to this aspiration by supporting initiatives for the protection of adolescent girls against all forms of GBV |

## Validity of Design

Under validity of the design the evaluation addressed the following issues guided by the evaluation questions:

- Programme design;

- Programme intervention logic;

- Programme results and targets;

- Appropriateness of indicators;

- Attention to gender and human rights; and

- Design of the joint programme.

### Programme design

Finding 5: The programme design was appropriate.

It addressed both upstream (policy and legal framework that supports anti-GBV efforts) and downstream issues (service provision, reduction of incidences of GBV). As one stakeholder put it, “addressing the revisions to legislation especially on child marriage and age of sexual consent will help address the dilemma we are currently facing in handling child marriages.” It addressed the key drivers of GBV – harmful cultural practices and social norms (reducing incidence), and weak service provision in the referral pathway (increased protection and access to justice).

Some partners e.g. World Vision deepened their knowledge of the underlying causes and understanding of the target group through additional gender analysis studies which enhanced relevance of their work. For example, through their gender analysis of church umbrella bodies World Vision realised that not all apostolic sects are polygamists and not all are anti-hospitalization or medication or ignorant of the bible. Second they realised that some church umbrella bodies already had gender policies. This analysis helped the organisation improve appropriateness of their activities through redefining the problem to be addressed.

Finding 6: The programme fund was flexible in approach providing opportunities for improving effectiveness.

The initial proposal planned to implement the community level component of the programme in ten districts. Responses to calls for Proposals for CSO implementing partners revealed that the budget available for this component was inadequate to provide services in the ten districts at the scale required to achieve impact. As a result, the programme was reduced to three districts while keeping the same target of 5,000 girls and young women to be reached by programme activities. As reported in the Annual report for 2015 and observed in the field, this approach enables the programme to build a critical mass and concentration to influence change in programme outcomes. In doing this, the programme avoided the common pitfalls of similar programmes in Zimbabwe where programme activities have been spread thinly across a large geographic expanse undermining effectiveness.

Flexibility also enabled the programme take advantage of emerging opportunities for advancing its objectives. The work on the National Action Plan on Child Marriage is an example of such an opportunity which is providing a means of influencing the Government of Zimbabwe to prioritise measures to eradicate child marriages.

Finding 8: The programme could have benefited from an inception phase to validate the design.

While the programme fund remained flexible, including three revisions to the results framework (2014, 2015 and 2016) and changes or removal of some activities (e.g. abandonment of shelters), these many changes to a programme over two years may point to a need to have had  the programme design validated during its inception phase to ensure targets and activities were realistic.

Furthermore the programme had to establish formal partnership agreements with national partners at the national level (for normative work) and local level (for the anti-GBV structures). The process of partnership building was slow affecting implementation of activities especially in the first year. Incorporating a period for planning implementation of the programme and partnership building could have provided opportunities for improving efficiency of implementation.

Finding 9: The evaluation finds that targeting girls in two age groups (10-18 and 19-24) was appropriate in the Zimbabwe context because the age group 10-24 is often left out in programming for GBV.

The programme addresses violence as a result of -“gender dynamics”- or relations between male and females. Understanding and addressing the power relations between males and females that perpetuate GBV would be critical for the programme’s success. UN Women is a specialist in this area. Secondly, neither agency could have addressed the issues individually as they required an integration of the case management system (under child protection and led by UNICEF) and the GBV thematic area (led by the UN Women). Therefore a joint programme between the two agencies made sense and provided opportunities for enhancing work in both the case management and GBV. Of particular importance has been the work of the programme on supporting effectiveness of the referral pathway by bringing together the case management system, Victim Friendly System, and the Gender sector together through the district anti-GBV committees. This would have been difficult to achieve with each individual agency working separately with their individual programmes.

### Theory of Change

Finding 10: Theory of change of the programme was largely logical and remained relevant during the evaluation period. Some linkages have been undermined by implementation of the programme and gaps in design.

As illustrated in the Theory of change, Annex 3, the intervention logic for the programme is clear. It is premised on an appropriate justification and strong context analysis. It demonstrates the causal factors and clearly outlines the strategic fit of the programme. The operating environment of the programme has not changed significantly within the evaluation period to affect the causality linkages suggested in the Theory of Change for the programme.

There are some considerations to improve the results logic. First, there are limited linkages between evidence from programme implementation in the three districts and the policy level work. For example, the programme could have highlighted specific cases or implications of the delays in harmonisation of legislation on the efforts to address GBV among adolescent girls and young women to enhance work on influencing reforms in legislation and policy. The Beitbridge case where stakeholders, even after case conferencing, could not find a solution to a challenge of a man impregnating girls between ages 17-18 years because they were hamstrung by the inconsistencies between the age of sexual consent in the Criminal Law and Codification Act and the new Constitution of Zimbabwe.

Second, as discussed earlier, sequencing of behaviour change interventions after the social norms study may have compromised achievement of results because of insufficient time lag for the results chain to materialize within the programme life. This is known to implementers and in 2015 a decision was made to go ahead with the behaviour change activities.

Finding 12: The programme had no specific focus on gender dynamics that influence power relations and subsequently GBV in intimate partner relationships of adolescent girls. This impedes achievement of the causality chain towards reduction of GBV occurrence.

Inability to negotiate sexual encounters in intimate relationships was recognized as a key driver of GBV among adolescent girls and young women (NBSLEA, 2012). To its credit the programme had planned to develop guidelines for girls’ empowerment tools, informed in part by the Girls Empowerment Framework, to be used for this purpose but was suspended pending finalization the social norms study. This was a noble idea as the empowerment tools present at the time would have done more harm therefore needed to be revised. Given: (i) the urgency of the matter and (ii) that such a results chain was unlikely to be achieved in the life of the project; and (iii) that others such as those implementing the Adolescent Sexual and Reproductive Health (ASRH) strategy were already addressing this issue (girls empowerment) through the National ASRH guidelines, it could have been prudent to build on these and finalise their revisions pending completion of the social norms study.

Finding 13: The fear of losing a livelihood source is a major contributory factor to under reporting of GBV. This is not well recognised in the programme theory of change.

The evaluation noted that there was a gap in service provision to survivors especially livelihood support. GBV survivors often found it difficult to report GBV occurrence due to fear of losing their current livelihood sources as perpetrators were in most cases close relations whom they depend on for support. The potential risk of straining relations with the extended family after reporting a perpetrator who is a relative is a deterrent factor for some as they provide a social safety net. The project implementers had noted this challenge. While it is not expected for the programme to implement livelihoods activities, opportunities could have been explored to link with other livelihoods programmes government and non-governmental funded in target districts.

Finding 14: As many perpetrators of GBV especially sexual violence, are family members, some communities were fearful of reporting because imprisonment of the perpetrator would hurt relations with the extended family. This issue is not well articulated in the programme design and theory of change.

As recognised by communities and stakeholders interviewed, GBV mainly occurs in the home. This presents a myriad of challenges for reporting, centred on avoidance of disrupting the immediate and extended family fabric by not reporting the abuse. This essentially makes GBV a private matter. Thus while the adolescent girls and young women may know their rights there is need to provide a conducive context for them to exercise that right. CFPs and Childline hotline were instruments to support reporting of GBV occurrence. However, communities highlighted that much more needs to be done as GBV was getting hidden in families due to increased knowledge of the consequences for a perpetrator. Specific recommendations were to provide channels for discreet reporting, improve confidence in the justice delivery system, and improve support for livelihoods in the event a survivor is ex-communicated from the family or loses a livelihood source.

### Programme results and targets

Finding 15: The results are measurable and targets achievable within the context of the programme (capacity of partners and participating UN agencies and the activities)

Results for the programme are largely realistic, within the control of the programme and achievable within the timeframe. There were several processes to refine the log frame for the programme. It underwent three revisions (2014, 2015 and 2016) to refine the results and review the targets (mainly downwards). The revisions were based on realities encountered during implementation and not anticipated at programme design stage (absence of shelters in districts, minimum budget floor for GBV vis-a-vis economic situation of the country etc.) and pace of implementation of some activities.

### Appropriateness of indicators

Finding 16: Majority of indicators were appropriate and measurable but a few indicators (two out of 19) did not have a system for collecting data to inform them (give proportional of indicators)

Almost all indicators had baseline values available and were within the confines of the partners’ capacity to collect. The indicators had also undergone revisions by programme implementers to ensure they are SMART.

There were some challenges noted by the evaluation. First, there is no baseline, tool or system to measure indicators under Output 2.2 and 2.3.

Second, some indicators are at the activity level and not results, therefore are not fit in a results framework:

- number of girls reached with awareness raising modules; and

- number of line ministries and parliament committees informed on the costs associated with implementation of the multi-sectoral protocol enabling them to advocate for increased financing for the implementation of the protocol.

Alternative indicators are needed to measure results of these activities. In this way the programme can be steered towards realization of the anticipated results chain as envisaged in the Theory of change.

### Attention to gender and human rights

Finding 17: Programme is firmly premised on human rights and gender.

Human rights: GBV is addressed from a rights perspective. It targets rights holders and duty bearers and addresses the normative framework that supports the realization of women’s and children’s rights. The programme’s work on the revision of the Children’s Act, Child Marriages Action Plan, support for the referral system all enable the establishment of an appropriate framework that supports the right to remain free from violence or receive the necessary services when this has occurred. Addressing social and cultural norms that perpetuate GBV is also a central focus of the programme.

Gender: The programme’s design is correctly underpinned by the understanding that GBV is a result of power relations between men and women and therefore both men and women need to be targeted.  Activities such as the “He4She” campaign, the “men to men” dialogues and activities targeted at traditional and religious leaders who are mainly men ensure that men are a central focus of the response as main perpetrators of GBV.

The efforts on raising awareness rights of women and girls can be undermined by negative perceptions of rights by community gatekeepers and men. In one area of Beitbridge, it was noted a politician had denied the project discussion of rights because they were misunderstood as increasing child delinquency.  Men on the other hand, in Makoni, were of the opinion that women were now abusing these rights. Such sentiments, though still low at the moment, can escalate and undermine gains made in knowledge and achievement of behaviour change if not managed well.

### Design of the joint programme

UNICEF was designated the Administrative Agent (AA) for the JPGBV under the pass through arrangement accountable for effective and impartial fiduciary management. The proposal document provides dual responsibility for coordination of the programme. It states, “UNICEF and UN Women will coordinate on a day to day basis and in collaboration with the Government (specifically, MWAGCD). To facilitate jointness in programme implementation, a steering committee was put in place to “coordinate, oversee and monitor the implementation” of the programme. Members of this structure were MWAGCD, the Danish Embassy and the two UN agencies. The Steering Committee structure was borrowed from the success of a similar structure in the joint programme between UNICEF and UNDP on the “Justice for Children” programme. The Steering Committee was guided by Terms Reference designed to clarify its purpose and responsibilities in the JPGBV.

The Division of Labour adopts a mix of outcome and output sharing and output specific responsibilities between the UN agencies. Table 3 provides details of the approach to division labour in implementing the joint programme.

Table 3: Division of labour in implementing the joint programme

| Result | Lead |
| --- | --- |
| Outcome 1: National normative and financial GBV framework strengthened | UN Women and UNICEF |
| Output 1.1: Strengthen capacity of the Ministry of Justice to align legislation with the Constitution and international commitments on women and girls. | UN Women and UNICEF |
| Activity 1.1.1: Support Ministry of Justice and Legal Affairs to develop domestication (legislative reform) agenda, based on recommendations of recent reviews and subsequent provision of technical support to legal drafters of the Ministry of Justice and Legal Affairs to draft key legislative amendments for submission to Cabinet | UNICEF |
| Activity 1.1.2: Conduct gender and age analysis of the Criminal Code, Criminal Procedures, and Evidence Act (CPEA) against the standards set out in the Constitution and international instruments, and support advocacy for alignment of legislation | UN Women |
| Activity 1.1.3 : Finalise Girls Empowerment Framework – print and disseminate | UNICEF |
| Output 1.2: Enhanced knowledge-base of line-Ministries and Parliament on budgeting and advocating for implementation of the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence | UNICEF |
| Output 1.3: Strengthened capacity of gender equality advocates to influencing zero-tolerance and increased resources for implementation of GBV commitments | UN Women |
| Output 1.4: Improved Leadership and capacity of Ministry of Women Affairs, Gender and Community Development to co-ordinate e implementation of GBV commitments | UN Women |
| Outcome 2: Improved preventive measures for GBV | UN Women and Unicef |
| Output 2.1: Enhanced national evidence strategy on social norms fuelling GBV and increased knowledge on effective behaviour change interventions to inform existing and future programming on the prevention violence against women and girls. | UNICEF |
| Output 2.2: Improved knowledge amongst girls to seek services and know their rights to better protect themselves against violence in accordance with strategic area 3 Safety and Protection in the Girls and Young Women’s Empowerment Framework | UNICEF |
| Output 2.3: Strengthened capacities of traditional and religious leaders; men and boys to implement strategies that address negative social norms such as child marriage and forced marriages. | UN Women |
| Outcome 3: Strengthened service delivery for survivors of GBV | UNICEF and UN Women |
| Output 3.1: Strengthen capacity of government and civil society to promote accessible survivor focused GBV services for girls and young women | UN Women and UNICEF |
| Activity 3.1.1: Finalise minimum standards for clinical management of sexual abuse and support implementation by health centres (in coordination with relevant players) | UNICEF |
| Activity 3.1.2: Support service providers to deliver psycho-social support and medical services for survivors of sexual and gender-based violence in 3 districts | UNICEF |
| Activity 3.1.3: Support to legal aid service providers to expand legal aid services to survivors in 3 rural districts | UN Women |
| Activity 3.1.4: Support capacity of government and civil society to implement the Multi-Sectoral Protocol on the Management of Sexual Abuse and Violence in 8 districts | UNICEF |

Analysis

There are four issues identified in the evaluation of the joint programme design:

- Coordination and governance;

- Division of Labour;

- Operating procedures; and

- Programme governance.

Coordination and governance

Finding 18: From a programme design perspective, there is lack of clarity on the PUNO responsible for coordination leading to challenges of programme coordination.

While the JPGBV programme document provides for UNICEF as the administrative agent, coordination has no specific PUNO lead mentioned. This lack of clarity creates gaps in programme wide coordination as observed by the evaluation and elaborated in earlier sections. To address this challenge, UN agencies participating in Joint programmes are encouraged to nominate a Convening Agent (CA) accountable for coordination among participating organizations and for consolidating narrative reporting. By consolidating reports to the donor, UNICEF partly played this CA role. With the lack of a proper formalized agreement on roles and responsibilities with regards coordination – through a commonly agreed accountability framework that defines roles and results and provides a firewall for the dual responsibility of a UN agency (fund management and programme implementation) – coordination of the programme was always going to be a challenge. These issues need to be addressed in the joint programme.

Finding 19: The Steering committee has been left as the main platform for ensuring coordination of the programme. Nonetheless, this is inadequate to achieve coordination and make programme implementation jointly. The result has been several missed opportunities to improve programme effectiveness.

The Steering Committee allowed for PUNOs, MWAGCD and the donor to understand what each PUNO was doing and determine progress in activities but there was need to improve jointness in the delivery of work to leverage on each PUNO’s comparative advantage especially with CSO partners. Coordination of partners across the entire programme was adhoc and unstructured resulting in missed opportunities.  The evaluation came across cases of collaborations between partners, such as on Orange Days or awareness visits but these were adhoc and not systematic. Information sharing between partners was also not strong and in some cases affected some results for other partners. One partner (operating at national level) trained journalists on reporting on GBV. However, the journalists faced a dearth of stories to write. In this case the sharing of stories from the field such as the cases in Beitbridge (adult man impregnating several girls between ages 17-18 years) or elsewhere in the programme could have been important to highlight for the trained journalist enhancing effectiveness of this training.

There were opportunities to harness the comparative advantages of the two UN agencies.  For example, the evaluation found that in areas where the UN Women funded JCT led consortium were implementing activities a community cadre, Community Focal Person (CFP), was established. This was not the case in other areas where the programme partners funded by UNICEF were working yet CFPs were recognised as an important structure that enabled identification of adolescent girls and young women who were victims of GBV (but were unable to disclose due to fear), or an avenue for discreet reporting of abuse. Given the recognised importance of this structure by community members, better coordination could have resulted in the structure being found in all project areas of the programme, with the JCT led consortium and UN Women providing technical assistance.

Nonetheless it is the evaluation’s opinion there were some missed opportunities. The bottom up link between work at the normative level and evidence from the bottom – district and community level could have improved attention to the issue of shelters. As detailed earlier, there were inconsistencies between the SOPs for shelters developed by the MWAGCD and the Children’s Act regards to mixing of children and adults in shelters. The SOPs advocate for “mothers and their children” to be accommodated in a similar shelter while the Children’s Act prohibits mixing of adults and children.

The target group for GBV shelters under SOPs are: Women survivors of GBV and their children. The SOP admission standard states that a woman needs to be old enough to consent to being housed in the safe house (victims/survivors above the age of 15 years of age). Children’s Act- Placement of all girls under the age of 18 is the responsibility of DSS, and placement in institutions/shelters should only be the last resort.

This inconsistency has proved a challenge for implementers at the district level as they found it difficult to separate the abused mother from here children. In Makoni the evaluators came across a case of a young woman with two children who was abused and living on the streets of Rusape town. The matter came to the attention of the DCWPS. They could find a shelter for the children at Simukai children’s Home but found it difficult for the mother as she could not mix with children in a “shelter”. Such circumstances can negatively affect reporting as well as service provision for the children. Bringing together 1) the expertise of UN Women under SOPs and UNICEF on the Children’s Act and child protection; and 2) the leadership role and convening power in the gender and child protection sectors of the two agencies,   there was an opportunity to influence revisions on the Children’s Act with regards this issue.

Secondly, at the beginning of the programme UN Women held an RBM training workshop with all its partners and developed joint implementation plans. Further two more meetings were held with all the CSOs partners contracted by UN Women and UNICEF to review progress in implementation and for further training in RBM. While this was great start for the CSO partners to work together, this practice was not followed through by creating a regular meeting platform for the CSOs to ensure continued coordination while implementing the programme in the districts.

As the programme has progressed there has been a growing recognition among PUNOs of the need to engage each other more and explore opportunities for enhancing efficiency through use of each other’s strengths. In 2015 a joint communications and referral pathway workshop was held for all partners in the programme using UNICEF’s strength in communication for development and experience in the referral pathway.

Division of labour

Finding 20: Sharing of outputs though not a significant occurrence in the programme design, can lead to a focus on delivery of activities instead of results as accountability for each PUNO remains at the activity level. There is need therefore to change management of those outputs that are co-shared.

As detailed in Table 3 above, the two PUNOs shared two out of eight outputs. This is not a significant problem. However, co-sharing outputs poses the risk of lowering accountability to the activity level for the PUNOs as the focus on delivering their activities and not necessarily the overall achievement of the output as no PUNO is overall responsible for it. The absence of a commonly agreed accountability framework for the PUNOs in the programme magnifies this risk.

Finding 21: The deliberate effort by the PUNOs to operate in similar districts for the community level supported implementation of the envisaged theory of change as it enables them to complement their actions.

Although implemented by two UN agencies, the programme was designed with activities that complemented each other to contribute to the desired objectives. This coherent design was enhanced by ensuring the division of labour did not result in the agencies implementing in different districts. For example in Makoni the evaluation observed the complimenting work of ZWLA (UN Women funded) and Childline (UNICEF funded) providing legal assistance and psychosocial support respectively to survivors of GBV. The same was observed in Beitbridge with GBV survivors identified by CFPs (established under UN Women funding) being referred to FST (UNICEF funded) for medical attention, Childline for psychosocial support and WLSA (UN Women funded) for legal aid and advice. This approach represents good practice in joint programming and is a divergence from the norm where you UN agencies tend to implement in districts where they already have established activities resulting in disjointed implementation.

Operating procedures

Finding 22: It was important in the JPGBV to come up with operating procedures for the programme. This would harmonise implementation and financial procedures for the PUNOS as they operate with different process structures.

There was no common agreed operating procedure for the joint programme. Its absence has posed challenges for the PUNOs to harmonise implementation approaches and financial reporting. For example the nominated AA uses their own systems to report to the donor which may be different to what is in use with other PUNOs posing challenges for the AA to fulfil its obligation to the donor on behalf of the PUNOs. This issue is also noted in the annual reports to the donor as they state:

“The inter-agency collaboration between UNICEF and UNWOMEN has faced challenges in respect to the operations procedures and differing mandates of the two agencies. On the operations side this has an impact on the possibility of accurate financial reporting and have raised a need for the agencies to develop and agree on a common way rather than a ‘UNICEF’ or ‘UNWOMEN’ way. This relates both strategies for programme implementation, focus areas, and reporting templates.  Lessons learned for future joint programming include a need for the participating UN agencies to develop joint procedures for the purposes of the programme, prior to programme implementation.” (Annual Report 1 April 2014 to 31 March 2015 to DANIDA in Zimbabwe)

Operating procedures have been found to be a useful instrument to harmonise approaches and agree on reporting templates and processes to support: 1) the nominated AA in financial reporting; and 2) enhance work of the nominated coordinating agency.

Programme governance

Findings 23: Review of minutes of the Steering Committee shows important decisions were made that have improved efficiency of the programme. But the discussions were not informed by structured monitoring data on the programme undermining the depth of contribution of the governance structure.

From review of minutes of the Steering Committee it is clear important decisions were made that have strengthened implementation of the programme e.g. review of the log frame to enhance efficiency, concentrating the programme in three districts instead of 10, removal of shelters from the funding due to envisaged low value for money of investing in the infrastructure etc. The Steering Committee also offered PUNOs another channel, apart from the quarterly and annual reports, to engage with the donor and enhance the donor’s oversight of the programme.

However, as observed in the minutes of the Steering Committee meetings and discussions with PUNOs, discussions were not often informed by structured monitoring data on the programme performance. Discussions were mainly pitched at the activity level. The discussions do not shift focus even minutes of meetings in the middle or end of year.

## Efficiency

Efficiency measures the extent to which the programme has used the least costly resources possible in order to achieve the desired results. This section responds to the following questions as per the Terms of Reference:

- Has JPGE implementation strategy and execution been efficient and cost effective?

- Has there been an economical use of financial and human resources? Have resources (funds, human resources, time, expertise, etc.) been allocated strategically to achieve outcomes?

- Have resources been used efficiently? Have activities supporting the strategy been cost-effective? In general, do the results achieved justify the costs? Could the same results be attained with fewer resources?

- Have programme funds and activities been delivered in a timely manner?

- Are the monitoring and evaluation systems that JPGBV has in place helping to ensure effective and efficient programme management?

### Value for Money Assessment

Due to limited data to carry out meaningful VfM analyses for Cost Efficiency and Cost Effectiveness, it was agreed to re-focus the VfM analysis to determining benchmarking for “systems-building for clinical services for victims” (i.e. how much does it cost to set up, train and finally hand over services to Government?). Considering the ultimate aim of the Service Delivery component of the JPGBV (or any UN interventions in Service Delivery) is systems strengthening through capacity building of government duty bearers and not simply direct service delivery, this economic analysis would be useful to the participating UN agencies. Such bench-marking can also guide the new Child Protection Fund II (CPF) (2016-2020) implemented by UNICEF– especially for scaling up of Child Protection Service Delivery component, and future programs that will contribute to gender based violence prevention including the Heath Development Fund.

Furthermore it was also agreed to extend the focus of the VfM to an analysis of the cost efficiency and effectiveness Childline’s operations – using helpline and drop-in centre data as well as victim friendly clinics because Such information would be valuable to make a strategic decision about what, how and where to invest in a resource scarce operating environment.

The VfM assessment, therefore, answers the following questions on VfM:

- What is the cost of setting up and annual running costs of a drop in centre and helpline services?

- In what way does a drop-in centre offer value for money compared to a helpline?

- What is the cost (bench marking) for setting up, building capacity and handing over clinical management services to Government? (a victim friendly clinical management centre for survivors of sexual abuse)

Limitations: The unavailability of outcome data and approaches of the help line and drop in centre undermined the team’s ability to fully answer the questions asked for the evaluation as detailed below.

It may not be helpful to compare only outputs of the two models because of the double counting and the differences in approach: This is because some cases handled by the drop-in centres are referred from helpline. For example, the Drop-in Centre Social Worker and community volunteer counsellors also conduct follow-up home visits in their local district on reports of child abuse and neglect reported to the national 116 Helpline or via the Free Postal Service to verify the report of child abuse received. Thus, the two models are not exclusive but complementary. Secondly the helpline offers referrals and counselling while the drop in centre offers both of these services plus long term psychosocial support, and in some cases home visits accompanied by Department of Child Welfare and Protection Services (DCWPS) and Victim Friendly Unit (VFU). Thus, the drop in centre, in comparison, offers much more than the counselling provided by the helpline. The approach of the drop in centre results in more holistic and specialised care due to the face to face interaction. It may be more informative to compare these at cost effectiveness level than output alone. However, this is not possible, in this case, as outcome data is not available for the two models for either the drop in centre or helpline. All indicators required for cost effectiveness require outcome level data.

Conclusion: Value for Money was limited to an assessment of economy.

Finding 24: The programme implementation presents good economy as unit costs are reasonable.

Survivor Friendly Clinics

Economy

Ideally, the financial cost of managing a case at a survivor friendly clinic managed by FST is $207.66 and the economic cost is $285.22 (See Annex 4). Comparing to these costs, the FST survivor friendly clinics were economic having managed each case at a financial cost of $179.82 and an economic cost of $247.24.

Efficiency

The FST survivor friendly centres were cost saving to the tune of $27.84 (financial cost) $38.28 (economic cost) and thus attained cost efficiency.

Value for money

Given that the victim friendly clinics achieved both economy and efficiency, we conclude that the JPGBV offered strong VfM in this respect.

Benchmarking Cost from government perspective: Setup and annual running costs

It would cost between $46,510.00 and $64,510.00 to setup child friendly clinic in a refurbished a four to six roomed structure with basic equipment, furniture and adequately trained staff.  It would cost the government $7,477.00 in medical and psychosocial support; $27,573.00 in labour costs; and $4894.50 for administration support summing up to $42,544.50 annual financial costs.

Helpline

Set up cost for future benchmarking

It costs $271, 755.00 to set up a basic helpline centre operated by staff indicated in Annex 5.

Economy Benchmark

The annual running cost of a helpline is $0.28 per child reached which increases to $0.37 per child reached when capital costs are spread annually. When considering cases managed as output, it costs $16.50 per case managed (financial) and $21.89 economic cost per case managed (See Annex 5).

Drop in Centres

Set up cost

It costs $80,040.00 to set up a drop in centre and $19,543.40 per year when spread over its useful life (See Annex 5).

Economy

Ideally, the financial cost of managing a case is $153.53 and the economic cost is $347.39. The JPGBV sites where economic having managed each case at an economic cost of $165.19 (See Annex 5).

Efficiency

Having managed cases at an economic cost of $165.19 against the ideal cost $347.39, the JPGBV drop in centres were cost efficient (see Annex 5).

Value for money

Given that the drop in centres achieved both economy and efficiency, we conclude that the JPGBV drop-in centre project offered Strong Value for Money (see Annex 5 for VfM strength diagnosis).

Other partners in the JPGBV

Table 4 shows cost per beneficiary reached whilst table 5 highlights equity in coverage. Cost per beneficiary was obtained by dividing total beneficiaries into total expenditure. To determine cost effectiveness, unit costs from comparable projects highlighted under Table 4 are used as benchmarking.

Through community outreach, meetings and Facebook, SAYWHAT reached 9368 beneficiaries, 51% of whom were females. The project was economic with a cost per beneficiary of $10.66. World Vision reached 28871 with 50%female coverage. Cost per beneficiary was $4.98.which also represents good economy.

.

Table 4: Economy assessment

| Partner | Cost per beneficiary, US$ | Comparison unit cost | Unit cost, US$ | Cost effectiveness |
| --- | --- | --- | --- | --- |
| World Vision | 4.98 | MOHCC/NAC National Unit Cost Matrix | 8.30+ | Cost effective |
| SAYWHAT | 10.66 | UNFPA | 23.43** | Cost effective |
| Justice for Children | 25.25 |  |  |  |

***UNFPA ASRH program cost of reaching out of school youths

+Cost includes community mobilisation and cost of reaching a person by media

### Timeliness in delivery

Finding 25: Programme delivery rates were significantly lower than planned and undermined by significant delays in implementation activities due to the multi-stakeholder nature of some activities and delays in disbursement of funds to CSO partners

Table 5 provides financial expenditure as of 31 December 2015. After 75% of the planned implementation period had been forgone, expenditure stood at 56.18% of planned budget. This discrepancy is a cause of concern as a significant portion of the budget remained to be utilised when the programme was entering its exit phase. Among the Outcomes, implementation of Outcomes 1 and 2 lagged behind the most with only 47.50% of the funds utilised. Delivery rates under Outcome 1 were undermined by the non-achievement of delivery of target activities under Output 1.2, and Output 1.4.

Outcome 2 delivery rates were significantly affected by the long delays in the social norms study which in turn undermined the development of social norms strategy. The study is coordinated through an inter-ministerial committee whose leadership has changed hands between MWAGCD and later the MoPSLSW. The study was planned to be completed in the first year but was still to be completed at the time of the evaluation. Its delay has also had a ripple effect on other sequential activities such as the development of a social norms strategy which is yet to be started as it awaits the findings of the study.

Outcome 3, implemented mainly through CSO partners, shows significant expenditure rate (71.75%) when compared to the other two Outcomes. This is also supported by the analysis of partner expenditure rates for the same outcome which averaged 95.58% (See Table 6). While the delivery rates were significantly high for partners, there were issues with timely disbursements that affected timely and quality implementation. Discussions with partners showed disbursements were delayed by up to three months into the implementation period.  If start-up and closure are taken into consideration, CSO partners had an average of four to five months to implement activities in their annual PCA grants. This becomes insufficient to achieve transformational objectives. For example, awareness activities aimed at changing knowledge and attitudes require time to nurture the results. In the projects visited single visits to communities were made in the rush to complete the targeted activities in the short period left for implementation before liquidation and request for the next tranche. This is negatively affecting achievement of results.

Delays in disbursements are inherent in UN agencies due to the process of signing cooperation agreements and assessment of fiduciary risk. Assessments of organisational capacity have indeed provided safeguards against fiduciary risk with one CSO partner strengthening their financial management systems as a result of these processes. For, UNICEF specifically the signing of PCAs coincided with global changes in cooperation agreements which slowed the contracting process of CSOs.

Larger upfront disbursements and longer periods of implementation per round of disbursement (e.g. six months) between liquidations were suggested as helpful to offset the delays in disbursements. The delays in implementation also increased the costs of implementation as overheads costs increase for similar activities. Some partners received cost extensions for overheads to implement activities in their original PCA.

Table 5: Programme delivery rates

|  | Planned | Funds Utilized (in USD) |  | % utilisation |
| --- | --- | --- | --- | --- |
| National normative and financial GBV framework strengthened | 540,730.00 |  | 451,368.36 | 83.47% |
| Improved primary preventive measures for GBV | 1,671,348.00 |  | 709,926.26 | 42.48% |
| Improved services delivery for prevention and protection of GBV | 1,769,663.00 |  | 1,255,082.75 | 70.92% |
| Operational research | 98,315.00 |  | - | 0.00% |
| Monitoring and Evaluation | 344,101.00 |  | 73,090.85 | 21.24% |
| In-direct costs (in-country and HQ recovery costs) | 442,416.00 |  | 272,416.00 | 61.57% |
| Administration agent fee (1%) | 49,157.00 |  | - | 0.00% |
| Total Utilized | 4,915,730.00 |  | 2,761,884.22 | 56.18% |

Source: JPGBV Quarterly Reports to Steering Committee (1st October 2015 to 31st December 2015). Report provides cumulative expenditure for the period since inception to 31 December 2015.

Table 6: Partner delivery rates

| Partner | Budget, US$ | Expenditure | Delivery rate (%) |
| --- | --- | --- | --- |
| FST | 245,230.00 | 245,230.00 | 100.0% |
| Childline | 367,024.00 | 321,986.01 | 87.7% |
| Women’s Trust | 110,258.00 | 92,068.00 | 83.5% |
| Musasa | 361,805.20 | 361,805.20 | 100.0% |
| World Vision | 149,926.00 | 143,635.00 | 95.8% |
| SAYWHAT | 99,900.00 | 99,900.00 | 100.0% |
| Justice for Children | 164,579.00 | 152,898.00 | 92.9% |
| Total | 1,498,722.20 | 1,417,522.21 | 94.6% |

*Budget Expenditure 2014-December 2015

As a result of the delays in expenditure the programme has received a no-cost extension until October 2016.

### Human resources for the programme

Finding 26: Judging from the human resources allocated to the programme and those financed by the programme the programme management is adequately staffed. However, the distribution of input and the streamlining coordination need to be clarified to ensure the available resources are used more efficiently for the programme.

In general the amount of time allocated to the programme by different staff increased with age of the programme. The different approaches were taken by the two agencies to provide human resources to support implementation of the programme. Human resources allocated to the programme by UNICEF were financed from other lines of funding than the JPGBV while majority of UN Women staff were fully financed by the programme (EVAW Specialist and the UN Volunteer). These different approaches reflect the size and the capacity of the two organisations and in particular how the JPGBV has been able to support capacity within UN Women as a new agency. The programme also received contribution funding for a coordinator of the joint programme from Norway for six months in 2014 and until July 2015. The coordinator was housed in UN Women.

Senior staff, from both agencies, also contributed time for oversight of the programme with core funding from agencies demonstrating the high level commitment for its delivery.

Overall, the analysis of human resources raises questions on the right structure to deliver a joint programme. One of the issues, given the need to bring the programme implementation “together”, could have been a programme unit structure to ensure its coordination. Without this structure coordination of the activities of the two agencies becomes a challenge as each agency will be focused on delivering on its activities.

### Monitoring programme results and performance

Finding 27: Although a joint Results Framework was developed by the PUNOs, each PUNO monitored their own activities using existing tools and approaches in the agencies. This has undermined joint action in programme implementation and quality even among programme partners. The monitoring system adopted for the joint programme was not consistent with the requirements of the joint programming modality (joint tools, joint monitoring visits etc.). The monitoring of systems building, an important focus of the programme to build sustainability was limited.

The monitoring system includes a joint Results Framework, joint tools and templates for monitoring as well as the conducting of joint monitoring visits. In the JPGBV, each PUNO monitors its activities under the joint programme separately and using pre-existing tools and approaches within the agency. UNICEF uses its existing “promising quality tool” to assess the quality of services offered by its civil society partners and wellbeing of children. Quarterly monitoring visits to project sites are undertaken. Partners hold quarterly meetings to discuss progress and allows for cross-partner learning. Since late 2015, joint monitoring visits were conducted with partners to emphasise the interconnectedness of activities being implemented by the partners under UNICEF. UN Women on the other hand conducts quarterly monitoring visits to its project sites and partners and undertakes joint monitoring visits with the MWAGCD. Further partners submit quarterly narrative progress reports against the log frame targets and indicators.

Joint monitoring has been weak in the programme. This is an issue that the PUNOs acknowledged and in late 2015, a joint monitoring visit was conducted to address this issue.

Analysis of the M&E system above shows that the current M&E framework being used for the JPGBV has gaps that need to be addressed to ensure the conduct of monitoring, review and learning is programme wide not confined in each PUNO. In this regard the JPGBV could definitely benefit from a harmonised M&E framework that provides the tools, guidelines, timeframe and type (joint and individual) for conducting monitoring visits, templates for the individual and joint monitoring by the agencies and monitoring data and its disaggregation to inform discussions in the Steering Committee. This framework would build on the existing tools and approaches used by the PUNOs ensuring programme wide standardised monitoring. Each PUNO had element in their M&E that could benefit the other the programme as well. The Promising quality tool could be used programme wide, the partner coordination meetings could have been held for all partners in the programme,  and the joint monitoring visits with the MWAGCD could be also conducted by all PUNOs.

Because of the lack of this framework, monitoring visits by the individual partners were seen as disempowering and demotivating by some DDOs where they would hear from civil society partners in their district of a visit conducted by a UN agency in the JPGBV without the agency visiting them as the lead of the JPGBV activities in the district. This approach, harmonized M&E framework, is important because joint programmes remove mandates boundaries and entail agencies having to work with non-traditional partners. The limited number of joint monitoring visits (donor, MWAGCD (head office) and the UN agencies) to verify reports provided by the UN agencies may also be a symptom of this lack of a harmonized M&E framework.

A review of all the Steering Committee minutes for the evaluation period shows that monitoring data was not used in -a structured way to inform decisions in the meetings. This can be a consequence of the lack of a harmonized M&E framework as well.

The programme evaluation also shows limited documentation of the many changes and stories that could influence “up-stream” work observed during the consultation phase of the evaluation. The case of the man in Beitbridge highlighted earlier, the success story of the nurse in Mtetengwe village, Beitbridge and the challenges they face (see section 4.5), and in-roads made by World Vision in Union of Development of the Apostolic and Zionist Churches Africa (UDACIZA) using the channels of Hope method to recognize GBV and the negative effects of child marriages. A meeting with traditional leaders in Makoni showed some of the interesting work being done by some traditional leaders – where they take advantage of food aid distribution to spread the message on GBV because both men and women will be present.

One critical intervention approach of the JPGBV was systems building and capacity building to ensure sustainability of the results. While there are indicators that measure capacity building, systems strengthening is not reflected in the indicators and resultantly there is very little systematic reporting on the status of systems building. For example, one of the anti-GBV committee (from Makoni) has provided annual GBV status in their district for 2014 and 2015 in while Beitbridge and Bindura are still to do so. Further, there is no reporting on their functionality in terms of activities they are conducting and achievements. Thus there is lack of clarity on the extent to which these platforms are now able to continue activities on their own in the three districts. It would be important to conduct a learning exercise in the three districts understand the factors that enhance and undermine functionality of the anti-GBV structures to 1) build an appropriate exit plan; and 2) inform roll out to the additional five districts.

### Measures taken during planning and implementation to ensure resources are efficiently used

Finding 28: Fiduciary risk management is strong in the programme underpinned by UN fiduciary management systems. However, some of the provisions, such as annual PCAs for CSO partners are not ideal for the nature of results intended by the programme at the community level. This may be undermining efficient use of resources.

UN agencies have strong fiduciary risk management systems which include financial audits and partner capacity assessments before contracting and disbursements are made. This ensures funding is used for the intended purposes. The reporting framework and structures (quarterly reports and the Steering Committee) improved efficiency in use of financial resources. Several decisions were made from this framework including the cancellation of one PCA because of issues on capacity to deliver, the removal of the activity on conducting an exchange visit to Kenya to using knowledge already inherent in the agencies to implement the safe shelter.

It is standard practice that UN agencies to offer Partner Cooperation Agreements (PCAs) on annual basis. In the context of the JPGBV these annual grants were not ideal given the transformational objectives of some partners – changing knowledge and attitudes. One year grants negatively affect planning the sequence of transformational activities which ideally require multi-year programming. For example, some partners who had PCAs for year one were not sure whether the programme will continue. Processes of second year funding had not been completed at the time of the evaluation. The UN agencies partly addressed this structural challenge through contracting partners with on-going work in some of the three districts e.g. Childline, FST and World Vision but was difficult to achieve for some activities e.g. legal aid assistance which was not present in two of the districts (Beitbridge and Makoni).

It is important to note that since 2015, UNICEF globally, has shifted from providing PCAs annually to multi-year contracting because of this challenge.

Finding 29: The JPGBV PUNOs have adopted approaches that are providing gains in efficiency of resource use.

Majority of the partners contracted for the programme by the two UN agencies were resident in the districts enabling close supervision of activities and less project establishment costs. Joint workshops such as that on communication for development helped reduce duplication and therefore improved efficient use of resources. Only one has been held so far and these may need to continue.

Quarterly monitoring visits were conducted by the individual UN agencies to oversee implementation of their activities and provide technical advice. As one partner said, “the visit by UN Women helped us to change the way we were implementing some activities to make them more effective.”

In instances the programme built on on-going initiatives that reduced cost of implementation and improved achievement of results. For example, the JPGBV complimented initiative on development of the National Action Plan for Ending Child Marriage by providing resources for the undertaking of consultations with stakeholders and communities to inform its development while UNFPA (the UN agency leading this initiative) funded other components of the process.

Another, example is the partnership formed between the Centre for Applied Legal Research (CALR) and UNICEF to support review of the Children’s Act in accordance with the recommendations made through the legislative review carried out through the JPGBV and alignment to the Constitution. CALR was already supporting MoJLPA to align the Children’s Act with the Constitution with support from the European Commission (EC). The joining of forces allowed UNICEF to build on the momentum and willingness to reform already created by CALR to ensure recommendations such as increase in age of marriage, and age of consent can be reflected are included in the amendment. The partnership also resulted in UNICEF and CALR cost sharing the process with overall cost gains to the JPGBV.

Finding 30: The role of UN staff contributed to lowering costs (to the programme) for management demonstrating the efficiency gains of contracting UN agencies.

The programme management costs can be lowered because UN organisations have large pool of human resources that can be mobilised. For example both UNICEF and UN Women financed some of the staffing for the programme from other means overall reducing costs of implementation to the programme.

### Joint Programming modality and gender equality and women’s empowerment results

Finding 31: There are notable achievements that have occurred that would not have been possible had each PUNO worked individually but these are not wide spread in the JPGBV. Inadequate coordination at district level of the joint programme is hindering the extent to which efficiency gains of a UN joint programme can be obtained.

Several advantages are expected from joint programmes:

- a costing study of joint programmes (JPs) shows that JPs can indeed reduce transaction costs for partners;

- through coordination greater collaborations between UN agencies, taking advantage of individual comparative advantage, can be achieved with positive results on development;

- improves upstream results on policy reform and advocacy; and

- specifically for gender – increases visibility and legitimacy of gender issues.

In the context of the JPGBV, working together the two UN agencies have reduced the number of agencies the MoJLPA had to work with on legislative revisions. Without the JPGBV MoJLPA would have worked individually with the two agencies to address legislative revisions with regards children and gender increasing their transaction costs. More could have been done however to mobilise CSOs to support the legislative review process thereby increasing visibility and urgency of this agenda. The pace at which legislative reviews were concluded also demonstrates the value addition of UN agencies in programmes aimed at normative reforms (See section 5.5 for more details on this).

Using the traction of UN Women in the gender sector and that of UNICEF in the child protection sector, the two UN agencies were more easily able to bring stakeholders together for the anti-GBV committees than would have been the case as individual agencies. The anti-GBV structures will add value to the two PUNOs current work on: 1) strengthening the referral system; and 2) raising the profile of gender at the district level. By bringing together the Victim Friendly System, case management system and GBV, the programme has provided opportunities for strengthening the referral pathway and case management as more stakeholders are involved. For example in Beitbridge the MWAGCD was now being involved in child case conferencing something not done before the anti-GBV structure was established. The anti-GBV structures also revitalised the focus on gender in the district as they incorporated district stakeholders from the highest level – the District Administrator’s Office. There were also instances of collaboration between stakeholders during community awareness visits facilitated by the committee, something not possible before it as there was no platform for sharing gender specific activities. CATCH and ZWLA were collaborating on awareness visits to ensure the message was more comprehensive (to include legal issues). Discussions on GBV in the committees highlighted the impact of gender power relations, and the causes of the imbalance in power in this relationship thereby raising the profile of gender issues.

There are coordination challenges that have undermined effectiveness. Based on the analysis in section 5.2.6 under coordination and governance, these issues can be summarised as follows:

- weak partner coordination which has resulted in CSO partners not harmonising approaches in community based awareness work;  and

- missed opportunities for harmonising implementation of the SOPs for shelters developed by the MWAGCD where UN Women is overall concerned and Children Act’s Safe Placement Procedures for Children where UNICEF is overall concerned provide challenges for implementers in placing children and their mother in safe shelter.

## Partnerships

Under partnerships and coordination, guided by the Terms of Reference, the evaluation assessed: 1) the extent to which the programme led to complementary and synergistic effects in the broader gender sector and how this had been done; 2) government participation and ownership; 3) partnerships developed for the programme; and 3) capacity of implementing partners; 3) UNICEF’s and UN Women’s technical and resource management, coordination role in the delivery of the joint program; 4) support and coordination from the donor.

### Complementary and synergistic effects in the broader gender sector and with the Access to Justice Programme

Finding 32: The JPGBV has strong linkages with the Justice programme at both strategic and operational levels which provides potential for supporting effectiveness of the referral pathway.

In terms of synergies, it was envisaged that the JPGBV would support work in the DANIDA funded Accelerated Access to Justice for Children in Zimbabwe Programme (A2J) implemented by UNICEF. At the strategic level, the design of the JPGBV compliments the A2J through strengthening implementation of the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence in Zimbabwe. The JPGBV supports capacity building of the referral pathway which ensures more survivors reach the justice system and with appropriate care, support and evidence. The programme added output 1.2 in 2015 to directly support implementation of the A2J programme by funding the costing of access to justice for GBV survivors being conducted with funding from the A2J programme. The output aims to strengthen implementation of the Protocol on the Multi-sectoral Management of Sexual Abuse and Violence in Zimbabwe to enhance support for GBV survivors including performance of the justice sector.

Another activity implemented to directly support the A2J programme and reported in monitoring reports is the support provided by UNICEF to the Inter-ministerial Committee for Legislation Drafting through partnership with MoJLPA and MSWLSP especially starting with the Children’s Act, which addresses the age of marriage, inheritance, and other issues related to justice for children. It supports the A2J program through advocating for a separate legislation for child justice.

The Victim Friendly System and its sub-committees at the Regional courts are undermined by lack of data from the police Victim Friendly Unit (VFU) and health sector. Through the JPGBV, UN Women and UNICEF have been lobbying the Police VFU headquarters for access to GBV data of cases reported at police VFU. If successful this will greatly enhance planning and implementation of responses in the Victim Friendly System.

Interactions through the anti-GBV committees also strengthened case management and access to justice institutions such as case conferencing by bringing to the conference more stakeholders than was available previously to discuss options for addressing challenges faced in particular cases of abuse. For example, through the anti-GBV committee in Beitbridge, the Case Conference (discussed and set in the anti-GBV committee meeting) for the man allegedly impregnating girls between the ages 16-18 was attended by several stakeholders not usually in case conferencing such as MWAGCD and the District Administrator. This is also supported by DCWPS staff in Makoni who confirmed that the anti-GBV committee assisted them to coordinate relevant work with the MWAGCD.

Finding 33: The anti-GBV structures at the district level have brought the issue of gender to the forefront and are facilitating collaborations between actors in implementing interventions to address gender.

The link between JPGBV with other gender programmes is visible in the three districts. Through interactions in the anti-GBV committees collaborations between CSOs in the programme and those out of the programme were observed especially on awareness visits. In Makoni, ZWLA has provided technical support to CSOs on legislation and legal issues during awareness visits ensuring support by these organisations is well rounded. Support for legislation review supports initiatives in the gender sector though more could have been done to mobilise sector for these reviews.

### Government participation and ownership

Finding 34: Government of Zimbabwe’s participation has been central in the programme from conception to implementation but ownership of the programme outputs is not yet clear because evidence of commitment to implement outputs was not present at the time of the evaluation.

The MWAGCD has led implementation of the anti-GBV committees in the three districts and participated in programme governance and oversight through the Steering Committee. Various government ministries have led several initiatives of the JPGBV. An inter-ministerial committee led by MoPSLSW was established for the social norms study. Ministry of Health and Child Care (MoHCC) led the development of clinical guidelines for management to survivors of sexual abuse and violence although these are still to be approved since completion in May 2015.

Ownership of the programme activities especially work of the anti-GBV committees was observed from the MWAGCD district staff. For examples, quarterly meetings of the anti-GBV committee have been conducted without financial support. In the words of one DDO, “the anti-GBV committee has assisted us to carryout out our mandate in the absence of financial support from the head office because as you know the government has no money.” At the national level, a multiplicity of action plans have been developed or are being developed – it is not clear how government will prioritise implementation of these action plans given that other initiatives such as the Girls Empowerment Framework and Broad Based Economic Empowerment of Women (BBEEW) have all suffered lack of implementation.

### Partnerships in the programme

Finding 35: CSO partners selected for the programme have adequate technical capacity and a track record of delivery in their area of expertise

All partners are well known to the UN agency contracting them. Some such as Childline and FST were already being funded by UNICEF from the Child Protection Fund (CPF) with JPGBV enabling them to continue their work with additional focus on community based work targeting adolescent girls and young women. The JCT consortium comprised of three well-known CSO providers of legal aid and assistance for children and women in Zimbabwe (JCT, ZWLA and WLSA).

As highlighted before in this report, coordination among partners needs to be improved with creation of a CSO partner specific coordination structure where synergies can be harnessed in a systematic manner. Collaborations between partners are adhoc for activities such as Orange Day celebrations, awareness raising and provision of services to GBV survivors.

Partnerships outside the programme such as that established for the development of the National Action Plan for Ending Child Marriages are important to: (1) achieve cost efficiency through economies of scale; and (2) coordinate the implementation of GBV actions and reduce administrative burden on national partners. There were concerns from key stakeholders that the GBV sector was not coordinated as each agency brought forward their interests burdening stakeholders. The stakeholders highlighted for a common working framework or plan among UN agencies concerning work on GBV (UNDP, UNFPA, UNICEF and UN Women). The UN already has a Gender Results Group which brings together all the UN agencies and therefore programming could conform to this framework.

### Implementation capacity of partners

Finding 36: The quality of support offered to beneficiaries demonstrates that the partners selected had the capacity to implement the activities.

The selected partners were well known in the services for which PCAs were granted and had presence in the selected districts. In all areas beneficiaries of the programme showed satisfaction with the knowledge and services provided demonstrating the capacity to deliver services.

Box 1: Beneficiary perceptions on quality of service provided

“We rate the programme a 10. We are very happy with the knowledge they gave us on GBV.” FGD with traditional leaders, Beitbridge “The training was helpful. We now know about GBV and what to do when people come with GBV cases” .FGD religious leaders, Makoni “The training from SAYWHAT has been really helpful. We rate the quality of training an 8 out of a ten….I have been able to use the training to discuss with my peers on GBV…SAYWHAT provides use support and is in constant contact with us.” Anti-GBV ambassadors, SAYWHAT, Bindura “The training we received from WLSA was adequate to help us serve our communities.” FGD with CFPs, Beitbridge “The information we received on GBV was good. We have no complaints.” FGD with men in the community Beitbridge “Childline staff were friendly and helpful. I am very satisfied with how they helped me. I am what I am now because of them.” A child benefiting from Childline psychosocial support, Makoni

### Support and coordination of donor to the programme

Finding 37: The donor was involved in decisions through the Steering Committee.

The Steering Committee has been a useful structure to facilitate their participation in decision making and steering its direction. Apart from the Steering Committee the donor also provided technical assistance in areas such as communication as an example.

## Effectiveness

Effectiveness measures the extent to which the JPGBV has achieved its intended outputs and objectives. Progress on results at outcome and output level is measured as per indicators in the Programme Log frame.

### Achievement of outputs and outcomes

The discussions in this section are based on the last revised log frame of March 2016. As discussed earlier the programme has gone through two revisions, one in 2015 and another in 2016.

Outcome 1:  National normative and financial GBV framework strengthened

The main indicator for Outcome 1 is the number of CEDAW concluding recommendations related to GBV addressed or implemented by the MWAGCD.

Table 7: Outcome 1 achievements

| Indicator | Baseline | Programme Targets | Target 2015 (Y2) | Achieved 2015 (Y2) |
| --- | --- | --- | --- | --- |
| Number of CEDAW concluding remarks related to GBV prevention and response addressed/ implemented by Government | 1 | 10 | 7 | 6 |

Finding 38: Outcome 1 was achieved.

Of the 10 CEDAW concluding remarks related to GBV, four are being implemented through the district level anti-GBV structures as part of the MWAGCD’s implementation of CWEDAW recommendations for Zimbabwe. These recommendations include:

- Put in place comprehensive measures to prevent and respond to violence against women and girls in accordance with the Committee’s general recommendation No. 19;

- Encourage women to report incidents of domestic and sexual violence, by de-stigmatizing victims and raising awareness about the criminal nature of such acts;

- Collect statistical data on domestic and sexual violence disaggregated by sex, age, nationality, and relationship between the victim and perpetrator.

Results frameworks and action plans were developed for the three districts to facilitate implementation of these recommendations. While plans are in place, it has been relatively easy for district level stakeholders to implement points 1) and 2) as the anti-GBV structures facilitated collaborations and complimenting actions among already on-going projects on GBV in the districts. Shelters have been a major concern in all districts visited due to lack of financial resources to build them. This has been further undermined by the inconsistency in the policy framework with regards shelters between the Standard Operating Procedures (SOPs) for Safe Homes for GBV Survivors developed by the MWAGCD and the Children’s Act administered by the MoPSLSW, SOPs encourage shelters for mothers and children while the Children’s Act Safe Placement Procedures for Children does not allow adults and children to be in the same shelter.

The anti-GBV structures have found it difficult to report on progress on GBV with statistics as some sectors, health and police, can only provide information at headquarters level. There is also no annual reporting on the progress of implementing the CEDAW recommendations at the national level by the MWAGCD.

In late 2015 the JPGBV contributed to the Government of Zimbabwe, through collaborations with CSOs and other UN agencies prioritising for implementation of three more CEDAW recommendations:

- More vigorously address harmful practices by expanding public education programmes and by effectively enforcing the prohibition of such practices, in particular in rural areas;

- Use innovative measures targeting the media to strengthen understanding of the equality of women and men, to enhance a positive and non-stereotypical portrayal of women; and

- Provide effective protection against violence and discrimination against all groups of women.

Outcome 1 had five outputs. Table 8 provides a summary of achievements of targets for the different outputs while the sections below provide details of achievements in the outputs.

Table 8: Summary of Key Results for Outcome 1

| Output Indicators | Baseline | Programme Targets | Target 2015 (Y2) | Achieved 2015 (Y2) |
| --- | --- | --- | --- | --- |
| Output 1.1: Strengthen capacity of the Ministry of Justice to align legislation with the Constitution and international commitments on women and girls. |  |  |  |  |
| Framework for legislative reform developed and finalised; number of priority legislative revisions drafted and submitted to MoJLPA | 0 | 1 | Framework finalised | Framework on legislative reform finalized; At least 2 priority legislative revisions drafted and one legislative amendment submitted to cabinet; |
| Output 1.2: Enhanced knowledge-base of line-Ministries and Parliament on budgeting and advocating for implementation of the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence |  |  |  |  |
| Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence costed | No costing | Costing presented to Line-Ministries & Parliament | Postponed to 2016 with suggested changes. | Postponed with suggested changes. |
| Number of line- Ministries and parliament committees informed on the costs associated with implementation of the Multi-Sectoral Protocol enabling them to advocate for increased financing for the implementation of the protocol | 0 | 4 Ministries/ 3 Parliament Committees sensitized on the outcome of the costing | Postponed to 2016 with suggested changes | Not measured. Result changed to costing of the Multi-sectoral protocol. |
| Output 1.3:Strengthened capacities of Gender Equality Advocates to influencing zero-tolerance and increased resources for implementation of GBV commitments |  |  |  |  |
| Advocacy strategy finalised | 0 | Advocacy strategy in place | 1 advocacy strategy | 1 Advocacy Strategy developed |
| Number of position papers developed and presented to parliamentarians | 0 | 3 Position papers | 2 Position papers | 2 position papers developed. Submitted to parliament in June 2015; Gender Equality Advocates Platform established; |
| Output 1.4: Improved Leadership and capacity of Ministry of Women Affairs, Gender and Community Development to co-ordinate the implementation of GBV commitments. |  |  |  |  |
| Result Based GBV Monitoring Framework developed and finalized | 0 | Result Based GBV Monitoring system established in minimum 3 rural districts | Anti-GBV coordination structure established in three districts | Anti-GBV coordination structure established in 3 districts Result Based GBV Monitoring Frameworks developed in 3 districts (Beitbridge, Bindura & Makoni) |
| Consolidated reports on GBV produced by Ministry of Women Affairs, Gender and Community Development from three rural districts. |  | MWAGCD produce annual consolidated reports | MWAGCD produce annual consolidated reports | Annual Reports on GBV not developed due to limited access to information from relevant ministries |
| Output 1.5: Strengthened capacity of the Gender Commission (GC) to monitor implementation of gender equality laws, policies and commitments, and recommend laws and policy reforms including women’s political participation and ending child marriages. |  |  |  |  |
| Number of knowledge products produced on child marriage and investigative mandate of independent commissions | 0 | 2 | 0 | Not applicable |
| Recommendations on law and policy reform developed by commissioners and submitted to parliament | 0 | 1 | 0 | Not applicable |

Output 1.1: Strengthen capacity of the Ministry of Justice to align legislation with the Constitution and international commitments on women and girls

Finding 39: The JPGBV achieved Output 1.1 targets

The MWAGCD with funding from the JPGBV coordinated the development and finalization of the Legislative Review Framework or domestication report which was approved by the minister of the MoJLPA. The report was aimed at providing concrete suggestions on alignment of national legislation with the Zimbabwean Constitution and international standards (CRC and CEDAW). Since approval, UNICEF and UN Women have been providing technical assistance through the JPGBV for legislative review beginning with the Children’s Act and the Criminal Codification and Reform Act. At the time of the evaluation the Draft bill for the Children’s Act was approved by MoJLPA and the MoPSLSW and was awaiting presentation to the cabinet. Analysis of the Criminal Code had been finalised and draft legislative amendments and recommendations were submitted to the Law Development Commission and the MoJLPA.

Other normative results include:

- JPGBV supported the MWAGCD to facilitate the adoption of the National Plan of Action on Child Marriages;

- finalisation, printing and dissemination of 500 copies of the Zimbabwe National Action Plan to end Rape and Sexual Violence; and

- developing, finalising, printing and disseminating the Girls and Young Women’s Empowerment Framework.

To support service provision to survivors of GBV under outcome 3, the JPGBV supported the MOHCC in the development of Guidelines for Clinical management of GBV Survivors used by FST to train health personnel.

These many results at the normative level within two years are commendable and demonstrate the value UN agencies can bring in legal and policy reforms.

Output 1.2: Enhanced knowledge-base of line-Ministries and Parliament on budgeting and advocating for implementation of the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence

Finding 40: Activities under Output 1.2 were postponed to year three.

It is the evaluation’s opinion that, given the intended results of this output and the time for implementation (one year or less) there is not enough time to fully realise the results of this of this output before closure of the project.

Output 1.3: Strengthened capacities of Gender Equality Advocates to influencing zero-tolerance and increased resources for implementation of GBV commitments

Finding 41: The targets for Output 1.3 were achieved

A two-year Advocacy Strategy and two Position Papers on alignment of laws and gender responsive budgeting on GBV were developed. It was not clear how the agenda for position papers were linked with evidence coming from implementation of GBV efforts in districts and communities as well as experiences of survivors.  Given earlier evidence, it is the evaluation’s opinion that the anti-GBV structures could have been used more in providing this evidence.

The JPGBV supported coalition building between young women’s movement and youth wings in political parties and newly elected youth parliamentarians (Gender Equity Advocates) to undertake advocacy to scrutinising government commitments, including gender sensitive budgeting. The Women´s Trust and Tag-A-Life International established a WhatsApp platform for Gender Equality Advocates (newly elected young parliamentarians, junior parliamentarians and young political leaders as well as members of civil society) to dialogue on GBV issues. Advocacy campaigns on violence against women were carried out in public spaces, through print and electronic media, and events organized in Harare to sensitize members of the public on GBV, women’s rights and entitlements in terms of the law. Using the Global UN Orange Campaign as a framework and platform for organizing, Gender Equality Advocates held specific events during the 16 Days of Activism against Gender Based Violence and continued to hold advocacy and sensitization events on the 25th of every month. At the time of the evaluation results from these activities were still to be observed.

Output 1.4: Improved Leadership and capacity of Ministry of Women Affairs, Gender and Community Development to co-ordinate the implementation of GBV commitments

Finding 42: Output 1.4 was partially achieved as one of two indicators was achieved

The JPGBV supported the MWAGCD to coordinate the development of Results Based GBV Monitoring Frameworks and Action Plans in each of the three districts (Beitbridge, Bindura and Makoni) to facilitate the implementation of the CEDAW recommendations. Anti-GBV committees received technical capacity on monitoring and on Results Based Management. The MWAGCD developed a tool which was utilized by anti-GBV structures on laws that address GBV and the CEDAW Concluding recommendations to Zimbabwe. The MWAGCD, through the Anti-GBV Committees, was to develop a consolidated annual report on GBV but this was not fulfilled due to limited access to information from relevant government ministries. The PUNOs have been discussing with Police and Victim Friendly Courts to find ways of improving data accessibility. The benefits of these discussions are still to be seen.

The Anti-GBV structures are functional in the three districts, with meetings held once a quarter. The meetings review the progress made in the previous quarter, share achievements and challenges, and plan for the next quarter. The anti-GBV structures in all three districts have organised Orange Days together demonstrating the multi-sectoral nature of the issue. Several examples of partnerships between members of the anti-GBV committee on awareness visits and case follow up were observed by the evaluators. The three districts where the JPGBV is implemented commemorated the 16 Days of Activism through the anti-GBV committee. Increased collaboration between partners and stakeholders through anti-GBV committees is helping to provide a comprehensive service package to GBV survivors. In Makoni it was highlighted how the MWAGCD was now involved in many of the activities of stakeholders working on GBV than was the case previously as often CSOs would skip the District Development Officer and go straight to communities. This would undermine leadership of the MWAGCD. While the coordination capacity of the MWAGCD has been improved, the lack of financial resources in some cases (e.g. internet, printing, fuel) has negatively affected their capacity to convene the stakeholders and have oversight on implementation.

Output 1.5: Strengthened capacity of the Gender Commission (GC) to monitor implementation of gender equality laws, policies and commitments, and recommend laws and policy reforms including women’s political participation and ending child marriages.

Finding 43: Output 1.5 indicators are to be assessed at the end of the programme as this  Is a new output (and new activities) started from early 2016. Therefore no activities were anticipated during the period under review.

Outstanding from Outcome 1:

At the end of the evaluation period the following were still outstanding issues:

- At the time of the evaluation Guidelines and Training Guidelines for Clinical management of GBV Survivors were yet to be approved by the MOHCC;

- The Social Norms study is yet to be completed;

- Limited implementation of the Girls Empowerment Framework due to inadequate resources by the MWAGCD. However, the presence of the framework provides opportunities for gender advocates to lobby for resource allocation for girls empowerment and also guide interventions focused on girls’ empowerment by non-state actors ;

- Costing of the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence in Zimbabwe is still outstanding with the activity planned for 2016;

- Anti-GBV Committee reporting is limited due to lack of access to information from relevant ministries and departments;

Only one the outstanding gap above, resourcing of the Girls Empowerment Framework, cannot be resolved within the remaining period of the programme.

Outcome 2: Improved preventive measures for GBV

Finding 44: Outcome 2 was not fully achieved but many of the activities can be completed within the remaining period.

Outcome 2 aimed to improve preventive measures for GBV to reduce negative social norms that tolerate GBV. Strategic, measurable, evidence based Social Norms Strategy was to be developed to guide this process. Its development was to be premised on a social norms study. However the social norms study was not completed at the time of the evaluation (with only the literature review and secondary analysis of the NBSLEA survey data) which in turn delayed development of the Social Norms Strategy.

Table 9: Outcome 2 achievements

| Indicator | Baseline | Programme Targets | Target 2015 (Y2) | Achieved 2015 (Y2) |
| --- | --- | --- | --- | --- |
| National efforts to reduce negative social norms that tolerate GBV are guided by a strategic, measurable, evidence based strategy | No strategy | Strategy implementation commenced and on track | Strategy drafted and evidence-base used to inform existing GBV programming | In July 2014 the social determinants study was launched; A secondary analysis of the National Baseline Survey was analysed in 2015 on the Life Experiences of Adolescents was undertaken in collaboration with ZIMSTAT; A literature review has been done and is currently being finalised |

Summary of findings:

- Multi-Country Study on the Drivers of Violence Against Children on-going

- Further analysis of the National Baseline Survey on the Life Experiences of Adolescents (NBSLEA) to identify the determinants of violence against children done.

- Traditional and religious leaders empowered to take measures on GBV issues and taking the lead to talk about GBV at gatherings, and refer cases beyond their jurisdiction.

- Increased awareness and knowledge of GBV issues leading to increased reporting of cases.

- Increased dialogue and interpersonal communication at community level on GBV issues.

- Increased collaboration between partners and stakeholders through anti-GBV committees helped in the provision of a comprehensive service package in the three districts.

- Strengthened community response to GBV.

Table 10: Summary of Key Results for Outcome 2

| Output Indicators | Baseline | Programme Targets | Target 2015 (Y2) | Achieved 2015 (Y2) |
| --- | --- | --- | --- | --- |
| Output 2.1: Enhanced national evidence strategy on social norms fuelling GBV and increased knowledge on effective behaviour change interventions to inform existing and future programming on the prevention of violence against women and girls. |  |  |  |  |
| Existence of national social norms study and strategy (Y/N) | No social norms/determinants study No strategy | Study and Strategy finalised and implementation coordinated by government mechanism | Strategy implementation commenced. | In July 2014 the social determinants study was launched; A secondary analysis of the National Baseline Survey was analysed in 2015 on the Life Experiences of Adolescents was undertaken in collaboration with ZIMSTAT; A literature review has been done and is currently being finalised |
| Output 2.2: Improved knowledge amongst girls to seek services and know their rights to better protect themselves against violence in accordance with strategic area 3 Safety and Protection in the Girls and Young Women’s Empowerment Framework. |  |  |  |  |
| # adolescent girls reached with awareness raising modules | 0 | 5,000 | 2,000 | 28,000 (includes those reached through social media) |
| Percentage of targeted young women and girls who know where to seek support | 0 | 80% (all the targeted girls) | 80% (all the targeted girls) | No data collected yet for this indicator by the programme as there were no tools or system to collect data for the indicator. |
| Output 2.3: Strengthened capacities of traditional and religious leaders; men and boys to implement strategies that address negative social norms such as child marriage and forced marriages. |  |  |  |  |
| Number of traditional and religious leaders, and men putting in place and implementing protective measures that address negative practices such as child marriage and forced marriage | 0 | 500 traditional and religious; men and youth leaders | Identification and sensitisation of religious and traditional leaders, men and boys groups | 167 Traditional and religious leaders were reach by the programme. Some actions observed include the mainstreaming of GBV in 6 Theological Colleges Curriculum, incorporation of GBV in UDACIZA (an outstanding result of the programme). However, the exact number of leaders putting in place mechanisms to address GBV could not be determined as this indicator is not tracked. |
| Proportion of targeted traditional leaders, religious leaders and men who report increased knowledge on GBV | 0 | 60% of targeted of traditional and religious leaders, and men report increased knowledge on GBV | Identification and sensitization of traditional and religious leaders, men and boys groups | Responses from participants in FGDs revealed increased knowledge. Religious leaders showed how they were treating GBV differently as a result of increased knowledge on GBV. Traditional leaders showcased some of the initiatives around raising awareness and attempting to change perceptions of GBV. However, the monitoring system did not collect data on this indicator to quantify the extent of this knowledge among targeted leaders. |

Output 2.1: Enhanced national evidence strategy on social norms fuelling GBV and increased knowledge on effective behaviour change interventions to inform existing and future programming on the prevention of violence against women and girls

Finding 45: Output 2.1 was not yet achieved.

The national social norms study and strategy were to be developed under Output 2.1. Both documents are yet to be developed. Zimbabwe is participating in a Multi-Country Study (Zimbabwe, Vietnam, Peru and Italy) on the Drivers of Violence Against Children which aims to identify social norms that promote violence in particular against girls and young women. As part of the first phase of the study, a secondary analysis of the National Baseline Survey on the Life Experiences of Adolescents (NBSLEA) to identify the determinants of violence against children was carried out as discussed above. The study was led by UNICEF Office of Research Innocenti in collaboration with the University of Edinburgh and the Women’s University of Africa. The findings of the further analysis were presented in June 2015.Furthermore a draft literature review to explore existing knowledge on violence against children in Zimbabwe has been finalised and preliminary results presented in 2015. Outstanding at the time of the evaluation was the undertaking of Qualitative data collection in selected communities to finalise the social norms study. The main reasons for this delay were that: 1) the study is managed through an inter-ministerial committee chaired by the MoPSLSW, this multi-stakeholder approach slowed processes; 2) the transfer of responsibility from the MWAGCD to the MoPSLSW also stalled progress in the study; and 3) delays in the finalisation of the methodology and selection of the local partner due in part to the lengthy multi-stakeholder review processes.

Output 2.2: Improved knowledge amongst girls to seek services and know their rights to better protect themselves against violence in accordance with strategic area 3 Safety and Protection in the Girls and Young Women’s Empowerment Framework

Finding 46: There is no quantitative programme data to measure Output 2.2

The indicator for this output was: % of targeted adolescent girls and young women who know where to seek support. Measurement of achievement of this output could not be done as there is no programme specific data to do so (see section 4.3 for more details). PUNOs delegated responsibility for data collection to partners through their PCAs. However, without the necessary tools and methods for data collection, partners did not collect this information consistently. Nonetheless, anecdotal evidence from discussions with communities, adolescent girls and young women, shows improvement on the knowledge of where to seek support.

“We now know where to report when there is GBV. WLSA also taught us how to take up deceased estate issues when widowed and over property issues… We are sometimes intimidated by offenders but we know we can go to traditional leaders or use boxes placed at schools by World Vision”. Group of young women Chamunanga, Beitbridge.

“When one of us get raped we can report to the police, teacher, neighbour, village health worker, the clinic nurse or write in suggestion box at school”. Group of adolescent girls, Mtetengwe, Beitbridge

Output 2.3: Strengthened capacities of traditional and religious leaders; men and boys to implement strategies that address negative social norms such as child marriage and forced marriages.

Finding 47: The programme has made significant strides in building capacity of traditional and religious leaders as observed in the communities visited by the evaluation. However, the indicator could not be measured as this was not collected systematically because there were no tools and methodology to measure the number of traditional religious leaders putting in place actions to address GBV.

The JPGBV Programme, through the activities of World Vision, JCT and SAYWHAT, sensitised religious leaders, traditional leaders, and men to transform their perceptions and doctrines that perpetuate gender-based violence. Results of these actions show their potential to influence changes in behaviour, but these results are still not widespread in the programme areas. There are indications that there is greater knowledge among chiefs on GBV and how to handle GBV cases in the community. Religious leaders spoken to in all three districts highlighted how the programme had enabled them to understand GBV and how they should handle it as leaders. While knowledge is increasing, changes in terms of actual initiatives aimed at reducing GBV are still minimal. These vary with how moderate the traditional leader is to cultural practices and principles. In Ward 5 (Chamunanga) of Beitbridge women spoken to in an FGD highlighted that traditional leaders were speaking about GBV at public gatherings while in Mtetengwe, the group of men felt that while traditional leaders had been given the knowledge they were still deep rooted in tradition.

“Community leaders are very active against GBV in this community and refer a victim to the police with a letter”. Group of women, Chamunamga, Beitbridge.

“Cousin marriages are going down but some of the perpetrators are traditional leaders here”. Group of men Mtetengwe, Beitbridge.

There is covering up of child marriages in communities in fear of imprisonment. Effective custodial sentence is being given to those who marry minors to give strong messages to the community. Regional Magistrate, Bindura.

In some communities, traditional leaders are taking the lead to talk about GBV at gatherings, and they now know which cases to deal with and the ones to refer.

“We talk about GBV at public gatherings. We do this especially when there is a food distribution because this is when the men will also be available”. Traditional leaders, Ward 15, Makoni.

Across all districts it was highlighted that because man traditional leaders are knowledgeable they were now referring cases they cannot handle to the police as dictated by law.

“Traditional leaders are now more aware of what to do. In the past they would preside over sexual abuse cases but they now refer to us [the police]”.VFU, Bindura.

“Traditional leaders are now aware of what to do with different GBV cases…There is more knowledge of the referral pathway”. DDO, Makoni

“We had several workshops on GBV, child abuse and child protection. We got to know that people are handling issues at community level that are supposed to be reported to the police, for example rape cases.” Community leaders, Bindura.

The JPGBV programme, through World Vision, has been specifically targeting religious leaders using their Cannels of Hope methodology. It includes a series of dialogues on GBV and how the church can address it. These dialogues helped provide peer to peer advice and a platform to showcase what each of the members is doing so as to encourage change and action:

‘After sensitization pastors took back the program to their assemblies. In my ministry we use ministries like courting chemistry, couples’ meetings, some use newsletters, poetry and drama. We would report to each other for example a bishop from the Vapostori sect brought a register of 80 fellow bishops he had taught about GBV’. Religious Leader, Bindura.

The process has had profound changes in the conduct of churches with regards to GBV:

‘At the men’s fellowship, men are being taught about GBV and how to relate to their wives. At my church we have a motto that says women should be beaten by the revelation of the Word of God not physically’. Religious Leader, Bindura.

The JPGBV supported World Vision to influence apex bodies of religious organisations including the Union for Development of the Apostolic Churches in Zimbabwe (UDACIZA), Evangelical Fellowship of Zimbabwe (EFZ) to develop gender and GBV policies aimed at preventing, addressing and supporting survivors of GBV in their churches. The inroads made with UDACIZA should be commended. Members of UDCIZA are well known for engaging in child marriages, and discrimination of women and their refusal to desist from such practices despite government interventions. Getting the umbrella body to develop a gender mainstreaming strategy and putting in place mechanisms to address GBV among its members is a significant result in this context.

Figure 1: Training of Church Leaders in Beitbridge

To support long sustainability of knowledge on gender and GBV among religious leaders, World Vision through JPGBV directly influenced revisions in 6 of 11 Theological Colleges curricular to incorporate gender and GBV as a core subject.

SAYWHAT engaged young men in universities and tertiary institutions as advocates of change called Anti-GBV Ambassadors. SAYWHAT managed to engage men and boys to increase their knowledge levels on human rights, gender equity and equality as well as appreciation of their responsibility in the elimination of Violence against Women and Girls. The trained men and boys who were conferred as GBV change agents formed He4She clubs in their respective communities.

The Men to Men campaign for which a document was developed for possible replication in other areas, is a systematic strategy to engage men, raise awareness, and promote prevention of violence and support access to services for adolescent girls and young women.

Figure 2: SAYWHAT Anti-GBV Ambassadors

The Men to Men campaign managed to steer dialogue on the effects of GBV on women and girls through social media platforms as well as print and media houses. During the week of the launch (25th March 2015) over 3000 people were reached out to via Facebook post and   pictures. The campaign received international recognition via twitter by individuals and partners in the SRH programming as evidenced by the re-tweets and favourites.

In the target communities, men interviewed agreed that gender and GBV was being discussed albeit a majority of men were not being involved. Men reflected that the fear of arrest or legal ramifications of abuse was contributing to the discussions and change in practice.

“GBV is reducing in this area because men are now afraid of going to prison.” Group of men in Mtetengwe, Beitbridge

“We still find it difficult to get men involved in the discussions on GBV and women’s rights although GBV is decreasing because they fear being reported to the police.” Men’s forum Makoni

While changes are beginning to emerge, there are still some issues that the programme could consider:

- School going children have not been adequately addressed due to limited access to schools. Even though Childline managed to reach six schools (about 400 children) with GBV campaigns in the three districts, a general perception from focus group discussions is that more needs to be done to reach children in schools. The programme faced difficulties to enter into schools although there are limited successes recorded by Childline in Makoni district.

- Inadequate of IEC materials and discussion guides was raised in focus group discussions as a major gap identified in the programme. SAYWHAT noted that there are no standardised discussion guides to initiate dialogue at community level. Beneficiaries requested for the provision of IEC materials to use as an instrument for spreading knowledge on GBV. In Beitbridge respondents highlighted that the IEC materials and discussion guide need to be translated into local language for effectiveness.

- Most GBV cases are perpetrated within families and usually the offenders are relatives or known persons to the survivor, as such reporting or non-reporting of cases is affected by other social-cultural factors. In Beitbridge, participants in the review noted that the Venda culture, for example, encourages concealment of issues within the family.

- Communities had inadequate knowledge on court processes, and rights of alleged offenders, as they queried why a perpetrator is released in no time after an arrest. This negatively affected reporting of cases. There are also no feedback mechanisms by the courts to alert communities on the return of the offender to the community under bail. This issue was also noted as a gap in the workshop held by the programme in October 2015 for district level staff to identify gaps in the Victim Friendly System. While the workshop resulted in stakeholders providing action plans to resolve the gaps, these were still to bear fruit at the time of the evaluation.

Outcome 3: Strengthened service delivery for survivors of GBV

Finding 48: Outcome 3 was achieved

Under Outcome 3, the programme was to reach 3000 adolescent girls and young women aged 13-24 years who experienced any form of violence/abuse prior to age 18 who received relevant support in line with the Multi-Sectoral Protocol on the Management of Sexual Abuse and Violence in the 3 target districts by end of year two.

Table 11: Outcome 3 achievements

| Indicator | Baseline | Programme Targets | Target 2015 (Y2) | Achieved 2015 (Y2) |
| --- | --- | --- | --- | --- |
| Number of girls and young women aged 13-24 years who experienced any form of violence/abuse prior to age 18 who received relevant support in line with the Multi-Sectoral Protocol on the Management of Sexual Abuse and Violence in the 3 target districts | 0 | 5000 survivors receive a holistic range of support, in line with the Multi-Sectoral Protocol on the Management of Sexual Abuse. in 3 districts, over 3 years | 3000 | 4,019 |

Data from the programme shows that a total of 4,019 cases of adolescent girls and young women received support through the programme. Table 12 provides a breakdown of the services. It can be seen from Table 12 not all beneficiaries that went through programme supported services received all services as may have been necessary. In Bindura and Beitbridge challenges arose with referrals to other service providers not located at the point of referral. Survivors may not visit the next referral point either because of costs or frustrations of moving from one service provider to the next as they are not at one location. For example a child may receive psychosocial support at Child line or medical assistance from FST but may decide not to seek legal recourse. In Makoni, the “One Stop Centre” has helped in this regard with a survivor receiving police, medical, psychosocial and legal aid services in one place increasing the possibility of the survivor receiving a comprehensive service package. Data in Table 13 also shows a majority of psychosocial support clients do not get medical assistance demonstrating the potential value addition convenience in access to services (potentially through “One Stop Centres) can bring in ensuring comprehensive service provision to beneficiaries. The high cases of legal aid among young women correspond to issues of inheritance and divorce cases as a majority are married. This is also supported by the low number in this group receiving medical assistance.

However, this analysis needs to be treated with caution as a study is required to fully understand the reasons for these discrepancies as such information (including trace survey of service recipients) was not collected during the evaluation.

Table 12: Survivors and type of service received

| Service | No. Adolescent girls | No. young women | Total reached |
| --- | --- | --- | --- |
| Psycho-social support | 1426 | 0 | 1426 |
| Legal Aid | 800 | 1035 | 1835 |
| Medical services | 549 | 209 | 758 |
| Total | 2775 | 1244 | 4,019 |

Source: programme monitoring reports

Table 14 provides a summary of status of the outcome.

Table 13: Summary of Key Results for Outcome 3

| Output Indicators | Baseline | Programme Targets | Target 2015 (Y2) | Achieved 2015 (Y2) |
| --- | --- | --- | --- | --- |
| Output 3.1:Strengthen capacity of government and civil society to promote accessible survivor focused GBV services for girls and young women |  |  |  |  |
| Number Victim Friendly sub-systems (health services, psychosocial support, legal aid, and shelter services) available and accessible in line with the Multi-Sectoral Protocol in the target districts | Limited legal aid, psycho-social support and specialized health services in the three districts (TBC following baseline study) | 3 rural districts implement services in alignment with the Multi-Sectoral Protocol (All three districts fully operational in respect to shelter, legal aid, psycho-social support and specialized health services) | Legal aid, psycho-social support and specialised health services in place in 3 districts | Achieved. Psychosocial support is provided by Child Line Legal aid services by JCT consortium Specialised survivor friendly health services provided by FST |

Output 3.1: Strengthen capacity of government and civil society to promote accessible survivor focused GBV services for girls and young women

Finding 49: Output targets are achieved.

The rise in the reporting of rape cases can be attributed to the awareness campaigns in the Joint Program. Old cases are now being opened because of the sensitization through awareness campaigns and outreach programs. Even high profile people in communities like prophets and traditional healers are now being reported. The VFU in Beitbridge highlighted that one police staff, three teachers and one headman had been reported and convicted of sexual abuse charges. In 2015, the JPGBV managed to increase the number of girls and young women receiving GBV services in the three programme districts. An FST report indicates that in 2013, the organisation had managed to reach 524 girls and young women, but the number increased to 670 in 2015. FST provides health and psychosocial services through its clinics Some Focus group discussions on support feedback on services – psychosocial, health and legal aid.

“Community members are also now reporting cases of child marriages because they are now aware that it is an offense. Also in courts there is significant increase of cases from the police which are being reported by communities”. Bindura Anti-GBV Committee.

Through the JPGBV programme with support from FST, the MOHCC developed Minimum Standards for Clinical Management of sexual violence and the guidelines for training on clinical management of sexual violence and a training package on the guidelines. The guidelines are to be used in training to enhance the capacity of health service providers to provide adequate services to survivors of GBV. The guidelines await MOHCC approval. The training of nurses under the JPGBV conducted by FST increased the number of health professionals able to deal confidently with GBV survivors. But discussions show there are challenges that undermine use of this knowledge and need to be addressed: 1) some health staff do not want to be involved in court processes to give evidence – one doctor trained in Beitbridge has not used the training for this reason, another trained nurse turned away a survivor and referred her to Beitbridge hospital; 2) nursing staff are rotated within a hospital – so a trained nurse cannot be guaranteed a designate for survivors; and 3) only one nurse trained in health clinics, in cases when the nurse is not available survivors cannot be attended – such cases were encountered in Mtetengwe Beitbridge.

Table 14 shows the statistics for Childline on the number of girls and young women reached by August 2015. Through support of the programme Childline managed to increase the number of girls and young women benefit from psychosocial support from 455 in August 2014 to 1,426 in August 2015. Table 7 below highlights some of the achievements.

Table 14: Number of girls and young women reached by Childline

|  | Target (Sept 2014 – Aug 2015) | Achieved (Sept 2014 – Aug 2015) |
| --- | --- | --- |
| Adolescent girl and boy survivors of violence and abuse in the 3 districts access psycho-social services | 1,500 | 1,426 (66.85 girls; 33.2% boys) |
| Strengthen the capacity of duty bearers (parents/carers, government officers, traditional and religious leaders) to prevent, detect, and respond timely to incidences of violence and abuse against girls and young women, and boys in the 3 districts. | 3,000 | 6,601 |

In October 2014, a consortium of three legal aid organisation, (JCT, ZWLA and WLSA) started providing legal services for GBV survivors in Bindura, Beitbridge and Makoni. The training of community para-legal staff under the programme strengthened provision of legal services at community level. Anecdotal evidence (from communities and stakeholders) from the mid-term evaluation shows that more cases are being reported, go through the courts and offenders are jailed. Unlike before the JPGBV, there is a reduction in withdrawal of cases at the court (Regional Magistrate Bindura).

“The court according to the national prosecutor has not been withdrawing cases of GBV for the past 4/5 months; perpetrators are facing consequences for their actions. Women are now also brave enough to report cases of GBV as witnessed by an influx of GBV reported cases.” Anti-GBV Committee, Bindura.

In the three districts, the courts have noted a general increase in the number of GBV cases reported. For example, according to the Makoni Victim Friendly Unit (VFU) 86 cases were reported in the first quarter of 2014 and 110 cases were reported in the same period in 2015. The increase in reported cases was been attributed to the increase in awareness.

“The court has noted an increase in people seeking information on cases of custody and maintenance; this can be attributed to awareness campaigns that have been happening” Regional Magistrate Makoni.

“Reported cases of rape of minors are now on the rise, 3-4 cases are dealt with on a daily basis and an average of 20 to 30 a month. The courts have been very effective as there are no pending cases; people have been tried and sentenced. There is also high conviction in cases involving minors with strong sentences ranging from 25, 65 and even a 100 years in jail. Our district has been accused of filling up Chikurubi with the maximum sentences. This is sending strong messages to perpetrators”. Key Informant, Bindura.

“Community members are also now reporting cases of child marriages because they are now aware it is an offense. Also in courts there is significant increase of cases from the police which are being reported by communities”’ Bindura Anti-GBV Committee.

Outcome 3: Outstanding Activities

Safe temporary sheltering was identified as the missing link in the referral system. Stakeholders stated that there was a need for safe accommodation and shelter services to survivors awaiting their cases to be heard, particularly for adult women survivors and their children, pregnant adolescent girls, mothers under the age of 18, and mothers/guardians accompanying child survivors to court. An assessment of potential shelters conducted before the evaluation in Bindura, Beitbridge, and Makoni confirmed the lack of shelters for women survivors of GBV above the age of 18, and mothers under the age of 18 in these three districts. In Bindura SOS Villages is the main organisation providing shelter services for children and youth. In Beitbridge IOM has reception and support centres that offer temporary shelter to travellers whose cases will be with the Department of Immigration and Department for Social Services (DSS), while in Makoni girls and boys survivor of violence are referred to Simukai. Non-availability of safe houses for young women in all districts is undermining access to services and reporting. For example, a survivor may need to spend a night in the district centre in order to receive all the necessary services before travelling back. Without accommodation they either sleep in the open/unsafe accommodation exposing them to further abuse, or have to find paid accommodation (which increases the costs of accessing services). On another note, some survivors are fearful of reporting (especially in instances when the abuse occurs in the home) for fear destitution after reporting as they will have nowhere to stay. Therefore the absence of shelters introduces a real risk of case reporting apathy in the long run.

“At one time a survivor slept at the hospital because of lack of safe shelter”.

Key Informant, VFU Bindura.

However, the construction of shelters has to be underpinned by harmonisation of procedures between the SOPs for Safe Homes for GBV Survivors and the Safe Placement Procedures for Children in the Child Act.

Other gaps identified are that:

- In Bindura district, rural communities indicated that they face challenge in accessing health services after hours and during weekends because clinics will be closed.

‘The hospital Survivor Friendly Clinic closes at around 4\5 pm during the week and is closed during the weekend. This means if say a child is raped say after 5 or during the weekend he/she has to wait for them to open without any kind of assistance. This put survivors at risk for disease and unwanted pregnancy.’ Anti-GBV Committee, Bindura.

- In Bindura, it was highlighted that geographical coverage of the Police district is bigger than the Bindura administrative district resulting in the police managing cases outside the project geographic area without strong referral pathways.

- Survivors have to travel to urban areas to receive Post Exposure Prophylaxis. Survivors of GBV in most cases are poor and unable to meet costs of such travel.

- Safety nets are not addressing livelihood for survivors of GBV. Economic empowerment or livelihoods activities currently not available during the period under evaluation. However, Childline, and FST had started vocational skills training for survivors;

- Witness expenses highlighted as a challenge: a potential advocacy issue with Judicial Service Commission.

### Positive and negative unintended results of the JPGBV

Finding 50: There were some unintended results of the JPGBV observed by the MTE.

The MTR of the JPGBV identified some positive and negative unintended results emanating from the implementation of the programme. Sensitisation that increases community awareness on GBV, especially for girls and young women, was achieved in the programme as discussed under effectiveness. However, some community members especially men perceive this empowerment of women as negative since in their words

“…women have taken their rights too far”, Community Leaders, Manhenga Village in Bindura.

The perception is that women now have misconceptions of what their rights are as men are now leaving in fear of being reported and/arrested for small misunderstandings that may arise in the home. The community leaders further noted that

“…the youths are no-longer controllable because the law protects them; they report their parents when they want to discipline them.”

If such perceptions are not redressed, it has the risk of reversing gains from the JPGBV as men in the communities begin to reverse their positive opinions on women’s rights which can in turn result in repeat cycle of violence against adolescent girls and young women. There is need for the JPGBV to monitor and investigate such sentiments to improve messaging.

On a positive note, due to the sensitisation and awareness from the JPGBV, the review found out that men survivors of abuse are also seeking information on how they can receive support.

## Sustainability

Taking cognisance of the fact that this is a mid-term evaluation and, therefore, maybe too early to assess sustainability of results; this evaluation assessed and documented the strategies that have been put in place to ensure sustainability of results. The strategies for sustainability were assessed at national, sub-national and at community levels.

Finding 51: Several strides have been made to support sustainability through: training of nurses and the accompanying Clinical Management of Sexual Abuse to support clinical service support for GBV survivors within the public health sector; building capacity of the referral pathway (by supporting implementation of the Multi-Sectoral Management of Sexual Abuse and Violence in Zimbabwe) and strengthening the case management system. There are however challenges that might undermine sustainability and need to be urgently addressed in the remaining period.

### Strategies that have been put in place to ensure sustainability of results

The JPGBV has inherent sustainability mechanisms reflected in the capacity development of relevant ministries in addressing GBV and development of legislation and government action plans concerning specific GBV issues. The programme strengthened the technical capacity of the MoJLPA (the Judicial Services Commission, Department of Public Prosecutions); The MWAGCD; the Ministry of Home Affairs (the Zimbabwe Republic Police Victim Friendly Unit); and the MoHCC. Training enhances knowledge and provides a channel for continued utilization of skills in the system. This facilitates Government ownership and stewardship of the programme and ensures the continuity of outcome results.

“To ensure sustainability in whatever intervention carried out by CSOs such as Childline, it involves the Department of Social Welfare so that when the project comes to an end the Department is aware and can carry on from there.” Anti-GBV Committee, Bindura.

“Bindura Rural District Council now have a GBV structure with a gender champion in charge to deal with the issues of GBV even if the funding is no longer coming.” ibid.

The services to the survivors of GBV within the JPGBV are implemented within an agreed framework, the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence in Zimbabwe developed in line with international and regional legislation ratified by the country, as well as national legislation, policy and practice. Costing of the Protocol, which is yet to be undertaken, allows Government to plan as it is informed on the resource requirements for GBV. The programme developed training manuals, guidelines and IEC materials that can be used in continued GBV activities. These include training the Clinical Guidelines and the Training Guidelines for Clinical Management of survivors of survivors of GBV developed by the MoHCC with support from UNICEF, the Men to Men Model developed by SAYWHAT which can be replicated in other districts. Enhanced technical capacity of Parliamentarians and staff from Government Ministries ensures that advocacy for legislative change on prevention of GBV is on-going.

Analysis: While the work on building systems and capacity has been evident in the programme, effectiveness and sustainability of these initiatives is undermined by several issues. First the government is resource constrained and may not be able to recruit, apply and sustain the capacity being advocated in the programme. It would be prudent to explore how; for example, the work on Clinical Guidelines on Managing Sexual Abuse can be incorporated in current health systems strengthening initiatives such as the Health Development Fund. Further training of nurses needs to overcome the reluctance of health staff to attend court cases which in turn makes them shun attending to survivors of GBV as they will be required to present evidence in court. For example, of the five trained at Beitbridge Hospital on two were available. The reluctance stems from the fear of interrogation process by advocates in court.

Other initiatives to sustain outputs

Through the Women’s Trust, the technical capacity of journalists to report objectively on GBV issues was developed. Implementing partners have set up sustainability mechanism for continued discussion on GBV through social/multi-media platforms (SAYWHAT, Women’s Trust). This provides a platform for continued debate and engagement on GBV. Initiated social dialogue and inter-personal communication on GBV issues in communities is inherent in discussions and debates, ensuring continuity of sensitization and awareness.

To ensure sustainability, the main partners in the Joint Programme, UN Women and UNICEF, have incorporated some activities in the JPGBV into other programmes they are supporting. UNICEF has incorporated activities of the JPGBV in the new Child Protection Fund and in its annual work plan. UN Women, in partnership with other UN agencies, has developed the National UN Joint Programme on GBV. The programme is still to be finalised and receive funding.

### Sub-National level sustainability

At sub-national level, the Anti-GBV Committees in the three rural districts have become established district structures that will guarantee continuity of activities. CSO/Government collaboration established at national level is replicated at sub-national level for increased institutional involvement and engagement at sub-national and community level.

Analysis: The threat from waning motivation due to lack of resources is apparent given the amount of funding for gender including GBV work (which undermines implementation of the committee’s plans). While the GBV committees have continued to hold meetings without the programme’s support the unavailability of resources to help implement deliberations and agreements will, overtime, reduce motivation of stakeholders. Without this the Committee will be reduced to a “talk show” and overtime may become dysfunctional a fate that has befallen several gender based violence committees at this level in the past e.g. the Inter-ministerial task force on GBV. The MWAGCD is one of the poorly funded ministries in government. In the 2014/2015 the ministry was allocated a paltry US$50,000 for programmes. It is therefore clear that the MWAGCD will not be able to sustain the committees in the short term and a strategy is required in the remaining period to sustain them. The programme should explore linkages with other programmes e.g. the Integrated Support Programme, and other GBV related programmes in Zimbabwe to support the committees. To do this it will need to demonstrate the effectiveness of the committees in enhancing locally driven anti-GBV responses – which are inherently sustainable in the long term. Other opportunities such as including the private sector in the committees could serve as an avenue of sourcing financing for the committees’ activities. Given the above, it may be advisable for the programme to consider focusing and strengthening the current three districts than engage new ones. However, the evaluation is also aware that the programme has already begun the process of establishing anti-GBV structures in the five districts. In this case it is advisable for the programme to consider ways to support and strengthen the existing anti-GBV Committees in the three districts (Beitbridge, Bindura and Makoni).

### Community level sustainability

National duty-bearers and rights holders participate and are included in the programme at community level. In the three districts where the JPGBV is being implemented, traditional leaders (chiefs, headmen), political leaders (councillors) religious leaders and parents have been sensitised on GBV and some incorporated GBV messaging in their activities and programmes. The communities are sensitised by community leaders, CBOs and behaviour change facilitators also assist in ensuring sustainability. The programme is bringing back child protection responsibilities to the community and duty bearers. The success of World Vision in influencing majority of theology colleges to incorporate gender as a core subject in their curriculum is likely to increase the number of religious leaders with knowledge of gender in the long run.

The JPGBV worked with pre-existing community level cadres (CPCs, Ward Development Coordinators and Behaviour Change Facilitators) enhancing their skills and knowledge on GBV and legal advice. This approach will enhance of actions being sustained.

As the JPGBV works with cadres such as Ward Development Coordinators, Community Focal Persons, Behaviour Change Facilitators, Child Care Workers, and para-legal strained by ZWLA at community level addressing the issues of GBV, this will help with continuity of programme activities since these are community members utilising community structures. SAYWHAT has trained GBV Ambassadors, not only from the universities but from the community for continuity of the program. CBOs will also help in the sustenance of programme activities. In some cases the programme has linked with structured already present in the communities such as the Padare men’s Forum in Makoni which has been in existence since 2001, the CFPs from CPCs for the etc. This approach is likely to sustain results at this level.

Another requirement for programme sustainability is the ability to mobilise local resources to fund programme activities. On implementing partner, Childline secured funds from localised fundraising and donations (collections from shops, engagement of local business) which channels can continue to be used in the future. While this is a good initiative the funds are low to sustain the work at the current scale. Lobbying government for budgets that are child/women friendly should continue and is the most sustainable option.

### Scaling up for sustainability

Finding 52: In general, there is appreciation of the interventions and willingness to scale but undermined by the resource constrained environment.

Anti-GBV structured for example have been noted by the MWAGCD as a success and with potential to increase coordination for GBV. However, scaling is undermined by resources.

The same picture can be painted for the work on clinical management for sexual abuse.

As discussed earlier, scale up will need the interventions to be incorporated in other on-going programmes and systems strengthening initiatives e.g. the HDF.

# Conclusion and Lessons Learned

## Conclusion

This section presents conclusions of the JPGBV evaluation.

Table 11: Performance of the JPGBV

| Criterion | Summary Findings |
| --- | --- |
| Relevance | Programme is well aligned to international, regional and national priorities on gender. It is relevant to context of the country and local communities, to the needs of beneficiaries and meets the needs and priorities of stakeholders. The gaps noted by the evaluation are a lack of livelihood support to survivors who required such services and limited focus on girls’ empowerment initiatives especially on issues to negotiate sexual encounters in intimate relationships |
| Efficiency | Fiduciary risk was well managed. The Joint programme provided visible advantages in policy reforms, efficiency in engaging multiple stakeholders in a multi-sectoral response. There was no budget overrun by any partner. However, timeliness in delivery was a constant challenge during the implementation period. |
| Partnerships Coordination | The design of the JPGBV compliments the Justice for Children in Zimbabwe Programme implemented by UNICEF through strengthening implementation of the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence in Zimbabwe. |
| Effectiveness | By 30 December 2015, progress in implementing the programme had been made but output achievement as being undermined by slow delivery rates. Results at outcome level were still emerging and not wide spread in the programme areas. |
| Sustainability | At national and subnational levels, the JPGBV has inherent sustainability mechanisms reflected in the capacity development of relevant ministries in addressing GBV and development of legislation and government action plans concerning specific GBV issues. The three districts have established Anti-GBV Committees that will guarantee continuity of activities. Duty-bearers and rights holders participate and are included in the programme at community level. |

The JPGBV was well designed and addresses challenges of GBV that are an area of concern in Zimbabwe affecting mainly girls, women and children. For the programme to have the intended impact, it needs to run for a longer period of time and to increase its geographical coverage in the three districts and to be scaled-up to all districts. Activities such as sensitisation, awareness campaigns and exchange programs should be scaled up to reduce GBV.

## Lessons Learned

The following are lessons that have been drawn from the evaluation. They are organised according to: 1) programme design; 2) programme implementation; and 3) improving effectiveness of joint programmes.

### Programme design

- Lesson 1: The theory of change needs to carefully assess the length of time it takes for the intended change to occur. In the JPGBV activities related to girls’ empowerment were to be based on the results of a social norms study. Given a three year project it was unlikely that the programme would achieve the entire envisaged change and achieve its results targets related to girls’ empowerment.

### Programme implementation

- Lesson 4: In GBV programmes, conducting a gender analysis prior to intervention enables context specific response and higher chances of success. Through conducting a gender analysis prior to implementation activities of their grant enabled World Vision to implement appropriate interventions for the target group revisiting the problem to be addressed presented in their grant proposal. Through this experience, a programme aimed at changing behaviour and practice with regards to GBV would greatly enhance its effectiveness by putting in place provisions for grantees to conduct gender analyses before implementation to revisit their design presented in the grant proposal.

- Lesson 5: The programme demonstrates that positive outcomes can be achieved by mobilising local stakeholders to lead anti-GBV efforts. There are in many cases multiple resource channels for anti-GBV actions. A locally driven response ensures better coordination of these multiple actions and higher efficiency in use of such resources resulting in lower costs for benefits.

- Lesson 6: For transformational objectives to be realised, partner agreements need to be multi-year. In this arrangement an organisation plans sequential activities according to the theory of change with the first year used for laying the foundation of the programme and subsequent years for activities building on the theory of change. If the programme works with CSOs to implement these activities, as demonstrated by the JPGBV, annual grants are not the most ideal. Multi-year grants as compared to annual grants are more effective in achieving transformational objectives.

### Improving effectiveness of joint programming

Joint implementation among UN agencies, is one of the instruments for the UN “Delivering as One” approach. As demonstrated by the JPGBV it requires implementing out of the “norm” for UN agencies involved and to plan critically how to make the programme one in delivery. Specific lessons from the JPGBV in this regard include the following:

- Lesson 7: The JPGBV shows that having steering committee as a governance structure of the programme is good practice. In addition to the Steering Committee a separate coordination structure that brings the CSOs of the different UN agencies together was required to enhance coordination at this level.

- Lesson 8: The JPGBV shows having all UN agencies implementing in similar districts increases potential to realise programme complementarity envisaged in programme design. While the JPGBV had some weaknesses in facilitating structured collaborations and complementarities between CSO partners of the different UN agencies, having both UN agencies working in similar districts enhanced opportunities for provision of comprehensive services for women and GBV survivors.

- Lesson 9: A joint programme can bring unique advantages through technical expertise from each UN agencies. For example, using their individual comparative advantages and positioning in the sectors, UNICEF and UN Women enabled the programme to effectively bring stakeholders from child protection, and the victim friendly system and those from the gender sector into one platform – the anti-GBV committee. This would have been difficult to achieve without the joint approach. As observed by the evaluation, the structures are bringing benefits to the anti-GBV agenda in the districts.

- Lessons 10: Joint programming means UN agencies have to effectively work with principal government partners in the programme. In the case of the JPGBV UN Women had to work with the Department of Child Welfare and Protection Services while UNICEF needed to engage with the MWAGCD at all levels.

- Lesson 11: A joint programme provides opportunities for policy harmonisation in multi-sectoral programmes. In the JPGBV, inconsistencies between the SOPs for Safe Homes for GBV Survivors developed by the MWAGCD (with support from UN Women) and the Children’s Act Safe Placement Procedures for Children administered by the MoPSLSW. SOPs encourage shelters for mothers and children while the Children’s Act does not allow adults and children to be in the same shelter. This has undermined placement of young mothers and their children in safe shelters.  Given that UN Women works with MWAGCD and UNICEF works with the MoPSLSW, an opportunity was available to move towards policy coherence using the leverage of the two agencies in their individual sectors.

# Recommendations

The following recommendations are premised on the findings of the evaluation. While the evaluation was framed as a mid-term evaluation, it was conducted towards the tail end of the programme. Therefore the recommendations provided below are aimed to assist the programme build a strong exit strategy and more so how a similar programme in the future needs to be designed and implemented.

## Programme design

- Recommendation 1: Considering that GBV is mainly in the “home”, that is, perpetrated by close relations, fear of the loss of livelihood which is mainly provided by the perpetrators and extended family is a real concern among survivors which poses the risk of undermining efforts to reduce GBV occurrence. It is therefore recommended that UN agencies should consider incorporating livelihood support in a GBV programme.  It is not envisaged that the contracted CSOs or the UN agencies should deliver this support – as it requires specialised knowledge, but rather stronger linkages between the GBV action and other programmes delivering livelihoods support to specifically target survivors of GBV as part of efforts to mainstream gender. (Responsibility: UNICEF and UN Women)

- Recommendation 2: Challenge of overlapping responsibilities of MWAGCD and MoPSLSW vis a vis the role they play for provision of services for the girl child and young women (interpretation of the law and policy). Given that reporting was being undermined by the availability of safe homes for overnight stay and reprieve in the period of abuse, it is recommended that future GBV programmes by UN agencies and government considers supporting places of safety for  adolescent girls with children and adult women and their children.  However, this has to be underpinned by harmonisation of the SOPs for Shelters and the Children Act’s Safe Placement Procedures for Children. MWAGCD and MoPSLSW need to agree on their respective roles and responsibilities and if needed work towards amendment of legislation for further clarification of these. (Responsibility: UNICEF and UN Women)

- Recommendation 3: Considering a large number of adolescents are found in school system, the GBV programme should address lack of systematic engagement with engaging with the Ministry of Education and create linkages with the existing Education sector work (such as EDF). There are also possibilities of linking with other UNICEF interventions in schools such as the safe schools initiative. Lack of doing the above will be a missed opportunity. (Responsibility: UNICEF)

- Recommendation 4: There should be a continued investment in strengthening of government capacity to address GBV using existing systems strengthening initiatives. An existing opportunity includes the Health Development Fund which can take up roll out of the Clinical Guidelines for the Management of Sexual Abuse. UN Women working with the MWAGCD needs to continue strengthening the three pilot anti-GBV committees. To do this, UN Women needs to support financing of activities and reviews of progress on GBV. A study that provides an in-depth analysis of the effectiveness and lessons learned from the Anti-GBV Committees needs to be conducted. The results would showcase the usefulness of the structures to leverage support from other stakeholders involved in gender programming at the district level.   (Responsibility: UNICEF and UN Women)

- Recommendation 5: The lack of an inception phase undermined planning and verification of the programme design. An inception phase, ideally six months, would have enabled the programme implementers to validate the design, development of a harmonised monitoring framework, established of programme coordination structures and revise certain features of the programme early on in its implementation. In the future, it is recommended that the DANIDA considers an inception phase in programmes of this nature. (Responsibility: DANIDA, UNICEF and UN Women (in designing future joint programmes).

## Programme implementation

- Recommendation 6: The programme had no baseline for indicators related to knowledge, attitudes and behaviour change. Because of this measurement of results achieved by the programme at this level is difficult. There is need for a future programme to conduct a baseline survey at the onset in order to measure its achievements. This should be supported by an inception phase. (Responsibility: UNICEF and UN Women).

## Programme management

- Recommendation 7: Consider having a full time joint programme coordinator from the inception to enhance coordination of the programme. The coordinator will be responsible for coordinating the activities of the agencies in the joint programme but housed in the nominated coordinating agency. This has to be incorporated in the design of joint programmes and its financing. The coordinator would help to identify opportunities for joint implementation of activities thus enhancing efficiencies expected from a joint programme.   (Responsibility: UNICEF and UN Women).

- Recommendation 8:  While each individual UN agency monitored its components, this is insufficient in the context of joint programming. It is undermining programme wide monitoring. The programme has to:

  - have one M&E system – tools, guidelines and results framework; and

  - incorporate systematic joint monitoring visits. (Responsibility: UNICEF and UN Women)

- Recommendation 9: The strong fiduciary risk management of the UN Women systems obligates UN Women to disburse funds on a quarterly basis and for 80% of all disbursement to be utilised and verified before the next disbursement is made. In some instances, the exercise of this fiduciary risk management was not timely thereby affecting time period for implementation. Considerations for time needed in the exercise of these fiduciary risk management processes need to be factored in future programme implementation.  (Responsibility: UN Women)

- Recommendation 10: The programme has not had strong documentation of results. The evaluation observed significant results and lessons that could benefit from in-depth profiling. It is recommended that in the remaining period of the programme, the participating UN agencies priorities documentation of results, lessons and best practices from the programme. (Responsibility: UNICEF and UN Women).

# Annexes

## Annex 1: Terms of Reference

Section 3: Terms of Reference (TOR)

Pay particular attention maybe from chapter 5 and 6 and Tools 3,8, 9,10,13,14. UN Women evaluation handbook

- Background

Gender based violence (GBV) is a well-documented public health, human rights, economic and social concern throughout the world. In an effort to promote concerted evidence based programming, the Government of Zimbabwe released new baseline data on violence against women and children in 2012. In 2012 it was reported that 47% of women experienced either physical or sexual violence within their lifetime and 1 in 3 girls experienced sexual violence before the age of 18, with less than 3% having received professional help.

In response to these challenges the government of Zimbabwe has intensified efforts in addressing these challenges by putting in place systems and structures to address GBV including rape. The government developed The National Gender Based Violence (GBV) Strategy 2012- 2015 which seeks to improve the efforts of Government, civil society and donors to prevent and respond to gender-based violence. The Goal of this GBV Strategy is to reduce all forms of gender based violence in Zimbabwe by 20 percent by 2015. The National GBV strategy has four key result areas which are: Prevention, service provision, coordination and research; documentation, monitoring and evaluation. In 2013, the government enacted a Gender Responsive Constitution and the government has prioritized aligning laws and policies to the new Constitution and this includes laws and policies that seek to address GBV. Other additional initiatives by government to address the challenges include among others: the establishment of inter -ministerial committee on prevention of rape in May 2014 and the Launch of the National Campaign against Rape and Sexual ABUSE ON 26 June 2014.  The launch was attended by among others: members of the police force, prison services, and nurses, representatives from line Ministries, churches, traditional leaders, students and civil society organisations.  Representatives from all these sectors made commitments to play a part in the implementation of the National Action Plan to end rape and sexual violence.  More recently, on 30 July 2015, Zimbabwe joined other countries in the African Union to combat against early marriages. A plan of action on prevention of early marriages is in the making. At the coordination and implementation level, the multisectoral protocol for prevention of sexual offenses has been adopted and a coordination mechanism established that meets at national and district levels regularly. Despite these efforts and commitments by Government to ending violence against women and children in the country there still remains challenges including: the slow implementation of the laws and policies; the absence of well-resourced legal aid programmes; low legal literacy among women and communities; a weak referral system between the police, legal aid providers and justice delivery structures; and entrenched patriarchal values which are being addressed by male involvement. Underreporting of GBV is still chronic and in general, access to justice is low. Social norms continue to vindicate abusive practices and women and children’s lack of awareness of rights contributes to sustain the problem. The programmes that do exist generally do not have an explicit focus on the specific needs of adolescent girls.

To complement the government efforts, UNICEF and UN Women designed a Joint Program on Prevention of Gender Based Violence (JPGBV) against young women and adolescent girls. This programme has a specific focus on adolescent girls and young women, building up on existing initiatives and to fill the gaps identified through consultations with stakeholders.  The JPGBV is a three year program with implementation timeframe of 2013 – 2016. Though the program was commissioned in 2013, actual implementation of the program started in 2014. The Program is being implemented with support from the Government of Denmark/ Royal Danish Embassy of Harare (DANIDA).

It is upon this background that UNICEF and UN Women Zimbabwe, is commissioning a mid-term evaluation of the Joint Programme on Prevention of GBV against young women and adolescent girls.Mid Term Evaluation is conducted at the middle of the period of implementation of a programme with the purpose of providing an early indication on the achievement of output level-results; it aims at assessing progress against objectives contained in the log frame, check if a programme is on track, and if any adjustments are needed, draw conclusions about the programme strategy and inform future programming.

The midterm evaluation will be guided by UN Women and UNICEF Evaluation Policies and United Nations Evaluation Group (UNEG) guidelines on Integrating Human Rights and Gender Equality in evaluation (http://www.uneval.org/document/detail/1616) and UNEG Guidelines on Joint Evaluations (http://www.uneval.org/document/detail/1620). The guiding frameworks for the evaluation include Convention on the Elimination of All Forms of Violence against Women; Beijing Platform for Action, Convention on the Rights of the Child and other relevant international and regional frameworks. The evaluation will be guided by the following key principles: national ownership and leadership; fair power relations and empowerment; participation and inclusivity; independency and impartiality; transparency; quality and credibility; innovation. UNEG Ethical Guidelines and UNEG Code of Conduct for evaluation will guide the evaluation.

2. Description of the program

UNICEF is the Administrative Agent for the JPGBV and UN Women is a participating agent.  The JPGBV is managed by a steering committee which comprise of UNICEF, UN Women, DANIDA and Ministry of Women, Gender and Community Development. The JPGBV has a total budget of 2$4,915,730.00 and to date a total of 3,966,925.91 has been disbursed with 51, 25% being allocated to UNICEF and 48, 75% allocated to UN Women.

- In order to deliver results for the JPGBV, UNICEF and UN Women are working with both governmental and civil society partners. The Judicial Service Commission is the lead organisation that UNICEF is partnering with within this program to address the rights of survivors of sexual violence as per the multisectoral protocol. UN Women supported partners are: World Vision, Women’s Trust working in partnership with Tag a Life International, Students and Youths Working on Reproductive Health Action Team (SAYWHAT), Justice for Children in collaboration with Women and Law in Southern Africa (WLSA) and Zimbabwe Women Lawyers Association (ZWLA). UNICEF supported partners are: Childline, and Family Support Trust, and Musasa in the past. These partners are implementing the program in the three districts (Makoni, Beitbridge and Bindura) in collaboration with the Ministry of Women Affairs, Gender and Community Development and district anti-Gender Based Violence structures.  Other Government partners in the implementation of this joint program are Ministry of Public Service, Labour and Social Welfare, Ministry of Health and Child Care, Ministry of Justice, Legal and Parliamentary Affairs as well as the Judicial Service Commission.

- The JPGBV objectives and results were revised during the course of implementation and therefore the consultant will be expected to make use of the revised Log frame when assessing progress in achievement of set results. The main objectives of the program are:

- To strengthen the preventive and protective normative and financial framework through domestication of the CRC and CEDAW and by increasing budgets for implementation of GBV commitments.

- To improve primary prevention of gender-based violence through social and economic empowerment of at least 5,000 girls and by changing harmful social norms among duty bearers.

- To scale up access to critical gender-and child sensitive services (health, welfare, shelter, legal aid and security response as well as other necessary referrals) for at least 5,000 survivors in 10 rural districts.

- The program is expected to deliver the following results:

Outcome 1:  National normative and financial GBV framework strengthened

Output 1.1: Strengthen capacity of the Ministry of Justice to align legislation with the Constitution and international commitments on women and girls.

Output 1.2: Enhanced knowledge-base of line-Ministries and Parliament on budgeting and advocating for implementation of the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence

Output 1.3Strengthened capacity of gender equality advocates to influencing zero-tolerance and increased resources for implementation of GBV commitments.

Output 1.4: Improved Leadership and capacity of Ministry of Women Affairs, Gender and Community Development to co-ordinate e implementation of GBV commitments

Outcome 2: Improved preventive measures for GBV

Output 2.1 Enhanced national evidence strategy on social norms fuelling GBV and increased knowledge on effective behaviour change interventions to inform existing and future programming on the prevention violence against women and girls

Output 2.2: Increased knowledge and skills among adolescent girls and young women to exercise their rights, access services and protect themselves against violence

Output 2.3: Strengthened capacities of traditional and religious leaders; men and boys to implement strategies that address negative social norms such as child marriage and forced marriages.

Outcome 3: Strengthened service delivery for survivors of GBV

Output 3.1: Strengthen capacity of government and civil society to promote accessible survivor focused GBV services for girls and young women

- Program Geographical focus:

The program is implemented at a national level (policy and financial framework, social norm strategy, advocacy and resource mobilisation) and in selected districts for actual implementation. At program inception the proposal was to implement the program in 10 districts but as per the note to file that provides the UNICEF and UN Women’s justification for the refocusing of the joint GBV project in terms of its geographical coverage. The number of districts were reduced to eight and three, respectively, for different aspects of the program.  8 districts there the victim friendly system is also function in have been selected for monitoring reporting on national commitments; sensitisation on GBV and coordination, implementation and coordination of Multi-Sectoral Protocol on the Management of Sexual Abuse and Violence. These districts are: 1. Bindura, 2. Centenary, 3. Chipinge, 4. Makoni, 5. Beitbridge, 6. Gwanda, 7. Umzingwane, 8. Bulilima (the victim friendly court is in Plumtree). The three rural districts for service provisions for survivors and pilot social norms preventive initiatives are (and Bindura) Makoni, Beitbridge. This evaluation will be conducted in the three districts (Makoni, Bindura and Beitbridge).

Program Focus Population

The primary focus population is: Adolescent girls and Young Women aged between 10-24 years and Secondary focus population are children and women survivors of gender based violence.

- Evaluation Purpose, objectives and evaluation users

Overall purpose of the midterm evaluation

The mid-term evaluation of the Joint Programme on Prevention of GBV against young women and adolescent girls is being implemented in accordance to the JPGBV monitoring and evaluation plan and Project Document approved by the Steering Committee. The overall objective of the mid-term evaluation is to assess progress made towards achievement of the JPGBV programme expected results since its inception in 2013 and lessons learnt from this evaluation will inform remaining JPGBV programme implementation and future programme design within the gender equality, children’s rights and women’s empowerment sector in Zimbabwe. The midterm evaluation will also provide credible and useful information on the added value of Joint Programs in enhancing the achievement of results on gender equality, children’s’ rights and the empowerment of women through improved UN system coherence and efficiency by using joint designs and implementation process.

Specific objectives of the mid-term evaluation

The specific objectives of the mid-term evaluation are guided by the OECD criteria of relevance, efficiency, effectiveness and impact. However, taking cognizance of the fact that this is a mid-term evaluation and will therefore focus on the effect of short term results on the lives of women and girls.

The objectives of the midterm evaluation are to primarily assess:

Relevance:

- To assess relevance of JPGBV to the national level priorities and alignment with regional and international agreements and conventions on gender equality, women’s empowerment and children’s rights. The mid –term evaluation will ascertain the extent to which the JPGBV has been conceptualised, planned and designed jointly to respond to international, regional and national goals and commitments on  gender equality and women’s empowerment and the extent to which the JPGBV was informed by needs and interests of diverse groups of stakeholders and beneficiaries.

Effectiveness:

- Assess progress in achieving planned outputs stated in the programme document, revised log frame and programme outline and document any intended and unintended effects on gender equality, women’s empowerment and children’s rights, including the use of innovative approaches.

- Assess the replicability of the programme at national scale, the ownership of the programme by the government and the contribution of the programme in building the capacity of the government to drive the Gender equality, women’s empowerment and Child-sensitive social protection agenda. The evaluation will also assess the contribution of the program in strengthening the capacity of partners in complementing government efforts and collaboration.

Efficiency:

- The mid-term evaluation will measure how economically JPGBV resources/inputs were converted to results; considering inputs and outputs i.e. assessing value for money and management of the budget. The evaluation will assess whether or not the JPGBV strategies and interventions deliver VfM. Document particular examples of cases in the programme where VfM successes and/or failures are evident.

- Assess whether the Joint Programming modality lead to better GE/WE results.

Project Outputs and Outcomes

The evaluation will identify and document any key contributions and added value of short term intended and unintended, positive and negative effect of the JPGBV program on women and girls in Zimbabwe.

The evaluation will:

- Document the benefits of the program to women and girls;

- Document the Most Significant Changes (MSC), if any brought by the program to date

The evaluation will identify and document intended and unintended short term results at the output level based on the Logical Framework as a basis for comparison so as to establish the effects of the intervention.

Partnerships and coordination:

- Assess the extent to which JPGBV has led to complementary and synergistic effects in the broader gender sector and how this has been done

- Assess the role and contribution of the GoZ in steering and supporting the implementation of the programme

- Assess if the program has strengthened national ownership through participation and inclusion of the government including provincial and district level structures

- Assess the nature and quality of partnerships forged during programme implementation and assess how the implementing partners worked together during programme implementation.

- Assess the implementation capacity, performance and spending rates of the partners that are implementing the program.

- Assess the support and coordination of donor to the programme, including timeliness of tranche payments, strategic direction and coordination

Sustainability

Taking cognisance of the fact that this is a mid-term evaluation and therefore maybe too early to assess sustainability of results; this evaluation will assess and document the strategies that have been put in place to ensure sustainability of results. The evaluation will assess the possibility of continuation of benefits accrued to date from the JPGBV intervention and recommend any other strategies for sustainability based on lessons learned from other programs and evaluations. The evaluation should consider the following dimensions of sustainability:

- Sustainability of the results of JPGBV implementing partners given the level of ownership generated, effective partnerships established and capacity strengthened through JPGBV processes. The evaluation should assess the strategies which have been put in place by UNICEF, UN Women and partners to enhance sustainability and document or present any best practices from within the program or other similar programs for enhancing sustainability of prevention of GBV interventions.

- Community level sustainability – assess ownership, participation and inclusion of national duty-bearers and rights-holders.

- Scaling up for sustainability - The evaluation should ascertain the possibility of scaling up of the interventions in Zimbabwe.

- Sustainability challenges and mitigatory strategies – the evaluation should identify possible challenges that might affect sustainability of the programme and suggest solutions to overcome them.

- Review monitoring system and risk management

- Review the monitoring systems that were put in place and make recommendations for improving monitoring systems for similar programs especially joint programs. Review and update the programme risk matrix.

- UNICEF’s and UN Women’s technical and resource management, coordination role in the delivery of the joint program

- Review how adequate, efficient, effective and responsive UNICEF and UN Women are in achieving the technical and resource management role for the program.

- Assess how effective the joint program was in terms of coordination, partnership, implementation procedures, within relevant UN Agencies in terms of sharing of resources, cost reduction, and any benefits of a joint program.

- Assess how the management structure of the joint program is working, identify strengths and areas that need strengthening.

Assess interlinkages with the UNICEF access to justice program

- The consultants are expected to assess any interlinkages between UNICEF access to justice program and UNICEF’s component of the JPGBV. The evaluation will not focus on documenting the access to justice program and its results but only identify any interlinkages or connections between the access to justice program and UNICEF component of the JPGBV.

Users of the evaluation

The mid-term evaluation report will be used to inform the Steering Committee in implementing its mandate of oversight and strategic guidance of the JPGBV for the remainder of the implementation period. Specific users will include UN Women and UNICEF program staff, the Ministry of Women Affairs, Gender and Community Development (MWAGCD) and other key government departments, responsible partners and the donor in planning and implementation of the joint programme. UN Women, UNICEF, responsible partners, donors and government partners of the joint program will be specifically responsible for developing management responses and action plans to the evaluation findings and recommendations.

The final evaluation report will be made publicly available on the UN Women Global Accountability and Tracking of Evaluation (GATE) System http://gate.unwomen.org/ and UNICEF www.unicef.org/zimbabwe. It will also be disseminated during national and district meetings such as the National Gender Forum; district level anti-GBV structures with government departments and representatives of civil society organisations and UN Gender Result Group meetings.

4. Evaluation Criteria and evaluation questions

The evaluators will develop specific review questions, samples of which are set out below, to be addressed through the consultative development of an evaluation framework using the Development Assistance Cooperation (DAC) evaluation criteria of relevance, efficiency, effectiveness, sustainability. The below questions are for guidance and should be elaborated by the evaluators as seen fit in the inception report.

Relevance: - the extent to which the activities designed and implemented were suited to priorities and realities

- Are the activities and outputs of the programme consistent with the overall goal; intended outcomes and effects?

- How relevant is the program to the needs and priorities of the beneficiaries, national, regional and international priorities?

Effectiveness: - the extent to which the programme has achieved its intended outputs and objectives

- Has the programme made sufficient progress towards its planned objectives ad results /has the programme achieved its planned objectives and results within its specified time period?

- How effective has the JPGBV been in implementing its stated objectives?

- Has the programme been appropriately responsive to political, legal, economic, institutional, etc., changes in the country?

- In which areas does the programme have the greatest achievements? Why this and what is have been the supporting factors? How can the programme build on or expand these achievements?

- In which areas does the programme have it’s the least achievements? What have been the constraining factors and why? How can they be overcome?

- What, if any, alternative strategies would have been more effective in achieving the programme objectives?

Efficiency: - the extent to which the intervention uses the least costly resources possible in order to achieve the desired results

- Has JPGE implementation strategy and execution been efficient and cost effective?

- Has there been an economical use of financial and human resources? Have resources (funds, human resources, time, expertise, etc.) been allocated strategically to achieve outcomes?

- Have resources been used efficiently? Have activities supporting the strategy been cost-effective? In general, do the results achieved justify the costs? Could the same results be attained with fewer resources?

- Have programme funds and activities been delivered in a timely manner?

- How have the steering committee and pillar expert panels contributed to the success of the programme?

- Does programme governance facilitate good results and efficient delivery? Is there a clear understanding of the roles and responsibilities by all parties involved?

- Are the monitoring and evaluation systems that JPGBV has in place helping to ensure effective and efficient programme management?

Partnerships and coordination

- To what extent has the JPGBV led to complementary and synergistic effects in the broader gender sector and how this has been done;

- How have stakeholders been involved in programme implementation? How effective has the programme been in establishing national ownership? Is programme management and implementation participatory and is this participation contributing towards achievement of the programme objectives?

Positive and negative changes produced by the JPGBV, directly or indirectly, intended or unintended

- What are the main effects of JPGBV activities? This should include positive and negative changes produced by JPGBV’s interventions, directly or indirectly, intended or unintended.

- To what extent can the changes/results that have been achieved be attributed to the inputs, strategies, actions and outputs of the JPGBV?

- UNICEF’s and UN Women’s technical and resource management, coordination role in the delivery of the joint program

- To what extent are UNICEF and UN Women effective and responsive in achieving the technical and resource management role for the program?

- To what extent has been the JPGBV effective in coordination, partnership, implementation procedures, within relevant UN Agencies in terms of sharing of resources, cost reduction, and any benefits of a joint program?

5. Scope of the midterm evaluation

Time frame for the evaluation: The Evaluation will provide an assessment of JPGBV from project inception in 2013 to October 2015.

Programmatic focus:  Assess progress towards achieving expected results, measured against the revised log frame and also compare original and revised log frame to assess original plans and identify reasons for the changes and document lessons learnt from the process (see attached). The assessment should capture differentiated results on young women and adolescent girls.

- Identify and document any short term and intermediate results achieved as a result of the program

- Assess Progress towards achieving program outcomes by the end of the programme implementing period.

- Consider whether the JPGBV logical framework requires updating (fit for purpose check).

Geographical coverage: The evaluation will cover all the three districts which are: Makoni, Beitbridge and Bindura. The Evaluation team will visit the three districts to discuss with stakeholders involved in the program including program direct beneficiaries who are young women and adolescent girls and indirect beneficiaries; anti-GBV structures coordinated by the Ministry of Women Affairs, Gender and Community Development other government departments as well as the Multisectoral Protocol (Victim Friendly System) and observe progress and achievements and to meet programme beneficiaries. The rationale for the selection of districts would be included in the presentation to the Review Group.

Partners: All of the partners involved in implementing the program will be involved in the evaluation including the district level anti-GBV structures and VFS committees. The evaluation will be done at different levels: UN level (UN Women and UNICEF), implementing partners and at community level taking into account the monitoring information collected by the Ministry of Women Affairs, Gender and Community Development, UN Women and UNICEF, the timeframe and resources available.

6. Methodology

The evaluation will be utilisation-focused, gender and human rights responsive and follow a mixed methods approach and a desk review of program overview should be done. These complementary approaches will be deployed to ensure that the study:

- responds to the needs of users and their intended use of the evaluation results;

- provides both a substantive assessment of JPGBV results, while also respecting gender and human rights principles throughout the evaluation process, allowing for the participation and consultation of key stakeholders (rights holders and duty-bearers) to the extent possible;

- utilises both quantitative and qualitative data collection and analysis methods to enhance triangulation of data and increase overall data quality, validity, credibility and robustness and reduce bias and will consider among other processes a desk review, meetings, consultations, workshops with different groups of stakeholders;

- Consider data collection instruments and methods for example interviews, observations, focus groups, and site visits.

The evaluation will follow the UN Women Evaluation Policy, UNICEF Evaluation Policy and the United Nations Evaluation Group (UNEG) Norms and Standards for Evaluation in the UN system and abide by UNEG Ethical Guidelines and Code of Conduct and any other relevant ethical codes.

The evaluation methodology will be developed by the Evaluation Team and presented for approval to the Evaluation Reference Group. The methodology should use a combination of quantitative and qualitative research methods and should explicitly outline how it will integrate a human rights based approach and explore the possibility of utilising participatory methods for developing case studies. Data should be disaggregated by sex and according to other relevant parameters.

Data collection methods

Some of the data collection tools to be used during the evaluation are:

Desk review

The Team will consult all available documentation in preparation for the review, including Program documents, minutes of the Steering Committee meetings; quarterly reports, annual reports and programme implementation and research reports from UNICEF and UN Women, implementing partners, and this documentation will be made available in good time.

Interviews with Key Informants

The team will conduct a range of interviews with key informants and stakeholders (including implementing partners and their national counterparts), and will visit and interview relevant Ministries and government agencies, local and international implementing partner organisations, community leaders, programme beneficiaries, key staff at UNICEF, UN Women and DANIDA.

Focus group discussions

The team will conduct focus group discussions with direct and indirect beneficiaries of the program.

Significant stories

During the interview the evaluators will support beneficiaries of the program to document their stories on how the program has impacted on their lives.

7. Stakeholder participation

Key stakeholders to be considered include participating UN Women, UNICEF, JPGBV implementing partners, the funding partner, Ministry of Women Affairs, Gender and Community Development and other key government departments. Following UNEG Evaluation guidelines and UN Women Evaluation Policy the evaluation will aim at engaging particularly different groups throughout the process. The evaluation will establish a management and reference group and members of these groups will be involved at various stages during the evaluation process. This includes, inter alia, providing comments on the TOR, approving the final report, and supporting the utilisation and dissemination of the evaluation findings. Further information on evaluation management arrangements and roles and responsibilities of different stakeholders is provided below in the TOR under Management of the evaluation section.

8. Expected deliverables

The evaluation team is expected to provide:

Deliverable 1: Present and discuss an Inception Report to the Management Group and Reference Group at an inception meeting. An inception report which contains evaluation objectives and scope, description of evaluation methodology/methodological approach, the evaluation questions, data collection tools, data analysis methods, key informants/agencies, detailed work plan and reporting requirements. It should include a clear evaluation matrix relating all these aspects and a desk review with a list of the documents consulted. (5 pages max excluding annexes).

Deliverable 2: First draft report to MWAGCD, UN Women and UNICEF. The Draft evaluation report (20 pages max excluding annexes) which should be delivered within the agreed timeframe in the work plan to allow stakeholder discussion of the findings and formulation of recommendations.

Deliverable 3: Submission of second draft report incorporating feedback from the management group.

Deliverable 4: Deliverable 4 will be in two parts i.e. (i) PowerPoint presentation of the second draft report to the management team including feedback from the reference group received through emails and feedback received from the management team. (ii) A template with feedback received from reference group members and how the comments have been addressed and incorporated in developing the draft report.

Deliverable 5: Presentation of the findings at a validation workshop to be organised by the Ministry of Women Affairs, Gender and Community Development, UN Women and UNICEF.

Deliverable 6: Production of final report incorporating comments from stakeholders. Final evaluation report (30 pages max excluding annexes) which should be structured as follows:

- Title Page, table of contents, acronyms

- Executive Summary (maximum five pages)

- Purpose of the evaluation

- Evaluation objectives and scope

- Evaluation methodology including consultation structures put in place during the evaluation process

- Context of subject

- Description of the subject

- Findings

- Lessons Learnt

- Conclusions

- Recommendations

- Annexes (including but not limited to: original Terms of Reference, List of documents reviewed, Data collection tools used, List of UN agencies, implementing partners, staff and other stakeholders consulted).

The final evaluation report will be made publicly available at the UN Women GATE website http://gate.unwomen.org/. It will be quality-rated based on UN Women GERAAS criteria available at http://www.unwomen.org/en/about-us/evaluation/decentralized-evaluations. Following UN Women’s Evaluation Policy, a management response will be prepared together with all key stakeholders within 6 weeks after completion of the report. It will specify the key actions to be taken, key partners to be involved in carrying out the actions and the timeframe for implementation. When preparing the response, inputs will be sought from all parties to whom recommendations are addressed including partners and donors.

List of Interviewees

| Method | Respondent |
| --- | --- |
| National level |  |
| KII | UNICEF |
|  | UNWOMEN |
|  | DANIDA |
|  | Ministry of Women Affairs, Gender & Community Development |
|  | Ministry of Justice - Judicial Services Commission, Legal Aid Directorate |
|  | Ministry of Health and Child Care |
|  | Ministry of Public Service Labour and Social Welfare |
|  | Judicial Services Commission |
|  | Parliamentarians |
|  | Prosecutor General |
|  | Police VFU |
|  | National based CSO partners (FST, SAYWHAT, JCT, ZWLA, WILSA, World Vision, Women’s Trust) |
|  | Implementing partners for the Access to Justice Programme - Leonard Cheshire Disability Zimbabwe Trust. |
| District level |  |
| KII | Regional Magistrate |
|  | One stop centre staff (if applicable) |
|  | Ministry of Health and Child Care |
|  | CSO staff |
|  | Ministry of Women Affairs, Gender & Community Development |
|  | Department of Social Services |
|  | Police VFU |
|  | Other members of the anti-GBV structures |
| Community Level |  |
|  | Community leaders - Chiefs / Headman and the Religious leaders |

9. Work plan and Time Frame for Deliverables

| Activity | No. of days | Deliverables Division of labour to be determined between the evaluation team | Responsibility |
| --- | --- | --- | --- |
| Stage 1: Briefing with UN Women, UNICEF and the Ministry of Women Affairs, Gender and Community Development. Preparation for the study, documentation review, work plan and methodology finalisation, meetings with stakeholders, preparation of inception report. | ½ day meeting with UN Women and UNICEF 4.5 days drafting inception report | Draft inception report including a detailed evaluation plan, methodology and evaluation tools. | Evaluation Managers and the two consultants |
| Stage 2: Presentation of inception report and data collection tools to the Management Group and circulating it to the reference group for written feedback. | 1 | Inception report is finalised, methodology and evaluation plan is agreed on | Consultants |
| Stage 3: Field visit for data collection and data analysis | 21 | Field visit update | Consultants |
| Stage 4: Draft report writing and submission of draft report to MWAGCD, UN Women and UNICEF | 10 | Draft report | Consultants |
| Stage 5: Incorporation of the feedback from the management group | 1 | Second draft | Management group submit comments to Consultants |
| Stage 6: Email circulation of the report to the reference group | 1 | Consolidation of feedback from the reference group in a table to be shared with the management group | Evaluation managers email draft report to Reference Group members |
| Stage 7: Presentation of the feedback from the reference group and the second draft to the management group | 1 | Incorporation of the feedback from the reference group (as agreed by the management group) and management group in a third draft | Consultants |
| Stage 8: Presentation of the findings at a validation workshop | 1 | Power point presentation | Consultants |
| Stage 9: Finalisation of evaluation report and submission. | 4 | Comments from stakeholders are incorporated into final report | Consultants |
| Total | 45 working days |  |  |

The evaluation will be conducted by a local firm with an evaluation team composed of 2 researchers, team leader with extensive experience in conducting evaluations including complex and or joint evaluations with a focus on gender equality and women’s empowerment will be overall responsible for the design of the evaluation process and ensuring submission of a consolidated high quality report and a technical expert with governance, budgeting, gender equality, human rights programming background who will provide support in carrying out the research, finalising the relevant components of it and drafting inputs for the overall report.

10. Management of the Evaluation

UN Women and UNICEF, in partnership with MWAGCD will co-manage the evaluation and under the guidance of the UN Women Representative and UNICEF Chief of Child Protection UN Women Monitoring and Evaluation Officer and UNICEF Child Protection Specialist will be the designated Evaluation Managers for this process to ensure that the evaluation terms of reference are fully satisfied.  The Evaluation Managers will coordinate the evaluation process and make follow-up on the evaluation team. The Evaluation Managers will oversee the development of the Evaluation report and coordinate work with the Management Group (Steering Committee) and the Reference Group.

The Management Group which is the Program Steering Committee is the decision making body with the responsibility of approving reports i.e. inception report and the evaluation report. Management Group TORs will guide the work of the Evaluation Management Group. The management Group will include:

- MWAGCD representative

- The Evaluation Managers

- UN Women and UNICEF Program Officers

- DANIDA Representative(s)

The Evaluation Reference Group will provide support for the evaluation at the technical level.They will review and provide comments to the inception report and the draft report. The Reference Group members will provide comments to the inception report and draft report either through meetings or online via email communications.  The role of the group will not lead to influencing the independence of the evaluation, but rather to ensure a robust and credible evaluation process and ensure the use of the evaluation findings and recommendations through formalized management responses and associated action plans. The work of the Reference Group will be guided by the agreed TORs for the Reference Group. The members of the Reference Group will be:

- The Evaluation Task Managers

- Responsible partners implementing the program

- District Level MWAGCD Officers

- VFS coordinator

11. Logistics

Ministry of Women Affairs, Gender and Community Development will take primary responsibility for arranging this evaluation and providing access for the evaluation team to the districts and by providing contact information such as email addresses and phone numbers.  Ministry will also provide any relevant data available to the evaluation team. UN Women and UNICEF will facilitate this process by providing contact information such as email addresses and phone numbers of their respective partners. Ministry will also accompany the team to the field visits whenever possible.

UN Women and UNICEF will oversee the logistics of the evaluation and provide support to MWAGCD for the arrangements as needed.  They will also accompany the evaluation team to the districts and will provide transportation for the district visits.

The evaluation team will be responsible for taking care of: office space, administrative and secretarial support, telecommunications, transport for appointments in Harare, field allowances within their budgets and printing of documentation, etc. The evaluation team is also responsible for the dissemination of all methodological tools such as questionnaires, conducting interviews; group discussions etc.

12. Selection of the Evaluation Team

The Mid-Term evaluation will be conducted by a local firm with two national consultants, one of whom will be the team leader. The team will additionally receive inputs from delegated members of the Ministry of Women Affairs, Gender and Community Development, UN Women and UNICEF.

Required expertise of Firm / Organisation Submitting Proposal;

Organisation/Firm

Organisation/ firm submitting proposal should possess the following;

- Excellent reputation of organisation and staff (Competence / Reliability)

- Proven general organizational capability which is likely to affect implementation – e.g. management structure; financial capability

- Clear quality assurance procedures – clearly demonstrating the systems and procedures in place for quality assurance.

- Proven organizational experience in conducting the type of work:

Extensive experience and knowledge in conducting evaluations (quantitative and qualitative methods)

- Organisational commitment to gender equality, women’s empowerment and children’s rights and knowledge and experience in evaluating gender equality interventions.

- Knowledge and understanding of Results Based Management methodologies.

- Extensive experience in evaluating donor funded programmes with focus on gender equality and women’s empowerment

Required Skills and Experiences:

Team Leader

A national consultant with the following skills and experience

- Master level and above educational background in social sciences or a related field;

- 8 – 10 years’ experience and knowledge in conducting evaluations (quantitative and qualitative methods) including complex and or joint program evaluations.

- Extensive experience in conducting evaluations with a focus on gender equality, women’s empowerment  and children’s rights

- Extensive knowledge and understanding of Results Based Management methodologies;

- Experience and understanding of gender equality, human rights, children’s rights and women’s empowerment programming of UN agencies, development partners and government;

- Application and understanding of UN Mandates on Human Rights and Gender Equality;

- Knowledge of regional/country/ local context will be an asset;

- Proven experience and excellent networking and partnership skills with UN agencies, government and CSOs;

- Excellent communication skills, both verbal and written and strong presentation skills;

- Excellent spoken and written English (all deliverables to be in English). Working knowledge of Shona and/or Ndebele will be an asset;

- Capacity to work independently and use own equipment.

Technical Expert

Required Skills and Experiences:

A national consultant with the following skills and experience

- Master level and above educational background in social sciences or a related field;

- 6-8 years of experience and understanding of governance, budgeting, gender equality, human rights programming of UN agencies, development partners and government;

- Extensive experience and knowledge in conducting evaluations (quantitative and qualitative methods) with a focus on governance, value for money, budgeting issues;

- Application and understanding of UN Mandates on Human Rights and Gender Equality;

- Knowledge and understanding of Results Based Management methodologies;

- Knowledge of regional/country/ local context;

- Proven experience and excellent networking and partnership skills with UN agencies, government and CSOs;

- Excellent communication skills, both verbal and written and strong presentation skills;

- Excellent spoken and written English (all deliverables to be in English). Working knowledge of Shona and/or Ndebele will be an asset;

- Capacity to work independently and use own equipment.

The independence of the evaluation team is outlined by the UNEG Norms and Standards as well by the UN Women Evaluation Policy and UNICEF Evaluation Policy. According to the UN Women Evaluation Policy, evaluation in UN Women will abide to the following evaluation standards: Participation and Inclusiveness, Utilization-Focused and Intentionality, Transparency, Independence and Impartiality, Quality and Credibility as well as Ethical Standards. UNEG Norms and Standards and the UN Women Evaluation Policy are publicly available under http://www.unwomen.org/about/evaluation.php;

UNICEF Evaluation Policy is publicly available onhttp://www.unicef.org/about/employ/files/2013-14--Final_approved_Revised_Evaluation_Policy.pdf

The Evaluation team is to act according to the agreed and signed Terms of Reference and to proceed according to all stated agreements.

- UNEG Norms and Standards and Ethical Code of Conduct

This mid-term evaluation will be conducted in accordance with the principles outlined in the UNEG ‘Ethical Guidelines for Evaluation’. The consultants must safeguard the rights and confidentiality of information providers, interviewees and stakeholders through measures to ensure compliance with legal and other relevant codes governing collection of data and reporting on it data. The consultants must also ensure security of collected information before and after the evaluation and protocols to ensure anonymity and confidentiality of sources of information where that is expected. The information knowledge and data gathered in the evaluation process must also be solely used for the evaluation and not for other uses with the express authorization of UN Women, UNICEF and partners.

The UN Evaluation Group Ethical Code of Conduct is available on the website of the United Nations Evaluation Group (UNEG) under http://www.uneval.org/index.jsp and should be referred to for guidance in conducting the evaluation.

14. Submission of Proposals

The local firm is required to submit the following: (i) Technical proposal accompanied with two CVs i.e. (a) CV for the team leader and (b) CV for the technical expert.  Technical proposals should not be more than 5 pages excluding CVs and annexes and should not repeat the terms of reference. The recommended font type is ARIAL, font size 12 and single line spacing. CV should be no more than 2 pages. (ii) Financial Proposal submitted separately from the Technical Proposal.

## Annex 2: Evaluation Framework

| Evaluation criterion | Detailed questions/Issues | Indicators | Methods and sources |
| --- | --- | --- | --- |
| Relevance | - Are the activities and outputs of the programme consistent with the overall goal; intended outcomes and effects? | the JPGBV was jointly conceptualised, planned and designed Activities address key problems identified in the Programme document | Key informant interviews (UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions; Community leaders) FGDs with beneficiaries (young women and adolescent girls; non-beneficiaries men and women) Most significant change stories (adolescent girls and young women Literature review - Programme document and Logframe |
|  | - How relevant is the program to the needs and priorities of the beneficiaries, national, regional and international priorities? | Programme activities are aligned to the National GBV Strategy; National Gender Policy; SADC Protocol on Gender and Development The African Charter on the Rights and Welfare of the Child (ACRWC); CEDAW; CRC; Activities address the needs and priorities of beneficiaries | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions; Community leaders) FGDs with beneficiaries (young women and adolescent girls; non-beneficiaries men and women) Most significant change stories (adolescent girls and young women Literature review - Programme document and Logframe; National GBV Strategy; National Gender Policy; SADC Protocol on Gender and Development The African Charter on the Rights and Welfare of the Child (ACRWC); CEDAW; CRC; Beijing Platform of Action. |
| Efficiency | - Has JPGBV implementation strategy and execution been efficient and cost effective? | Programme implementation is aligned to annual workplan Implementation within budgets Non or positive variance Cost per unit as compared to similar programmes Cost of transfer as compared to similar programmes Cost saving measures | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender; CSOs) Literature review - Programme document and Logframe; Programme budget; Financial reports; Programme Reports (quarterly and annual); |
|  | - Has there been an economical use of financial and human resources? Have resources (funds, human resources, time, expertise, etc.) been allocated strategically to achieve outcomes? | Human resources are adequate and properly qualified Investments are made based on the programme design/plan of activities Mechanisms put in place to review and improve approaches Selection of partners provides the programme with required capacity and strategic positioning to achieve objectives Cost saving measures | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |
|  | - Have resources been used efficiently? Have activities supporting the strategy been cost-effective? In general, do the results achieved justify the costs? Could the same results be attained with fewer resources? | Cost per unit as compared to similar programmes Cost of transfer as compared to similar programmes Cost/beneficiary analysis Incremental cost Alternative implementation approaches Cost saving measures | Key informant interviews (UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme budget; Financial reports; Programme Reports (quarterly and annual); |
|  | - Have programme funds and activities been delivered in a timely manner? | Activities delivered according to workplans Timeliness in disbursement of funds | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme budget; Financial reports; Programme Reports (quarterly and annual); |
|  | - How have the steering committee and pillar expert panels contributed to the success of the programme? | Decisions made that influenced programme strategic direction | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review – Minutes of Steering Committee meetings |
|  | - Does programme governance facilitate good results and efficient delivery? Is there a clear understanding of the roles and responsibilities by all parties involved? | Government structures and decisions made that influenced programme strategic direction Stakeholders understand their roles and responsibilities in programme management and governance Programme management and governance arrangements allow for efficient implementation of the programme activities | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); Minutes of Steering Committee meetings |
|  | - Are the monitoring and evaluation systems that JPGBV has in place helping to ensure effective and efficient programme management? | Programme monitoring and evaluation systems in place and functional Mechanisms put in place to monitor programme activities are providing adequate evidence to inform programme implementation Relevant data (guided by programme indicators and Monitoring framework) is collected in a systematic manner Recommendations made that influenced programme strategic direction | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); Minutes of Steering Committee meetings |
| Effectiveness | - Has the programme made sufficient progress towards its planned objectives ad results /has the programme achieved its planned objectives and results within its specified time period? | % achievement of outcomes and outputs expressed in the Programme Document and Results Framework Annual output delivery rate | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |
|  | - How effective has the JPGBV been in implementing its stated objectives? |  |  |
|  | - Has the programme been appropriately responsive to political, legal, economic, institutional, etc., changes in the country? | Changes to the programme’s objectives, indicators and targets in line with the changing context. | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |
|  | - In which areas does the programme have the greatest achievements? Why this and what is have been the supporting factors? How can the programme build on or expand these achievements? | Areas of greatest achievement Reasons for achievement Recommendations build on or expand on programme achievements | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |
|  | - In which areas does the programme have it’s the least achievements? What have been the constraining factors and why? How can they be overcome? | Areas of least achievement Constraining factors Recommendations to address the challenges | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |
|  | - What, if any, alternative strategies would have been more effective in achieving the programme objectives? |  |  |
|  | - What are the main effects of JPGBV activities? This should include positive and negative changes produced by JPGBV’s interventions, directly or indirectly, intended or unintended. | Positive and negative changes produced by JPGBV’s interventions, directly or indirectly, intended or unintended | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |
|  | - To what extent can the changes/results that have been achieved be attributed to the inputs, strategies, actions and outputs of the JPGBV? | Changes attributable to JPGBV programme | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |
| Sustainability | - To what extent has the programme inbuilt sustainability mechanisms | Level of ownership of the programme among partners Strategies which have been put in place to enhance sustainability of the programme Level of community ownership, participation and inclusion of national duty-bearers and rights-holders. Scalable activities and cost of scale-up Sustainability challenges and mitigatory strategies Progress towards Political Ownership and Stewardship & towards Institutional Ownership: Increased political leader/institution involvement and engagement; increased government support for community efforts; Increased institutional involvement and engagement Potential sustainable financing of the prevention of GBV: Proportion of local funding; Increased mobilization of local resources (Government; private sector etc); Sustainable health financing strategy developed; Public Private Partnerships established; Increased capacity of civil society to mobilize resources. Challenges to sustainable financing and the mitigatory measures: Commitment for long term funding/funding until local resources are adequate; Identifying low hanging fruits; Number of activities that can be continued without UN agency funding | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions; Community leaders) FGDs with beneficiaries (young women and adolescent girls; non-beneficiaries men and women) Most significant change stories (adolescent girls and young women Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions; Community leaders) Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions; Community leaders) Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions; Community leaders) |
| Partnerships and coordination | - To what extent has the JPGBV led to complementary and synergistic effects in the broader gender sector and how this has been done; | Mechanisms put in place to ensure JPGBV complements other gender programmes in Zimbabwe Evidence of benefits of economies of scale, cost sharing, knowledge sharing, technical support between the JPGBV and other gender programmes | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |
|  | - How have stakeholders been involved in programme implementation? How effective has the programme been in establishing national ownership? Is programme management and implementation participatory and is this participation contributing towards achievement of the programme objectives? |  | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs, Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |
| UNICEF and UNWomen technical and resource management, coordination role in the JPGBV | - To what extent are UNICEF and UN Women effective and responsive in achieving the technical and resource management role for the program? | Coordination mechanisms put in place to ensure a coherent programme Programme is responsive to change in context | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs, Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |
|  | - To what extent has been the JPGBV effective in coordination, partnership, implementation procedures, within relevant UN Agencies in terms of sharing of resources, cost reduction, and any benefits of a joint program? | Evidence of benefits of economies of scale, cost sharing, knowledge sharing, technical support between the JPGBV and other gender programmes | Key informant interviews(UNICEF; UN Women; UNDP; Ministries of Gender, Justice, Health, Public Service; CSOs; Government Institutions) Literature review - Programme document and Logframe; Programme Reports (quarterly and annual); |

## Annex 3: Theory of Change

## Annex 4: VfM Assessment for Victim Friendly Clinics

ANNEX 1: Victim Friendly Clinics Economic Evaluation

The Victim Friendly Clinics analysis is based on the Build-Operate-Transfer model used by Family Support Trust (FST) in Zimbabwe. Best practices internationally entail an independent centre, attached to a hospital, to offer victim friendly clinical and psychosocial services. The main argument for such a model is to ensure faster attendance to sexual abuse victims, remove the victim from potential stigmatization in the general outpatient ward, and ensure access to victim friendly services from staff dedicated and trained in such services.

Victim Friendly Centre Set Up Costs

In order to set up a victim friendly Clinical Management Centre offering basic services, a minimum of the expenditures listed in tables 1 and 2 are required. Appendix 4 explains the costs of meetings and trainings in detail and their rationale. $46,510.00 is required to finance the minimum equipment and minimum training for a clinic offering basic victim friendly services when the host health facility has space to for a minimum of 4 rooms for renovations/refurbishment. These are capital costs, however, which means that spreading them over their useful life, the annual set up costs fall to $12,000.00 per annum.

Table 1: Set up costs: where renovation/refurbishment is an option

| Assets | Financial Cost ($) | Economic cost* ($) |
| --- | --- | --- |
| Baseline Survey | 680.00 | 188.64 |
| Direct Consultative Meetings | 1,020.00 | 282.96 |
| Start Up Training | 19,120.00 | 5,304.07 |
| Stakeholder Meetings | 1,000.00 | 277.41 |
| Frontline staff Training | 8,500.00 | 2,357.98 |
| Building Refurbishment | 7,000.00 | 840.00 |
| Equipment | 8,190.05 | 2,540.15 |
| Official Handover | 1,000.00 | 277.41 |
| Total Set up cost | 46,510.05 | 12,068.62 |

*See Appendix 1

Table 2: Set up costs: where a new structure is needed

| Assets | Financial Cost ($) | Economic cost*($) |
| --- | --- | --- |
| Building Refurbishment | 25,000.00 | 3,010.42 |
| Equipment | 8,190.05 | 2,540.15 |
| Start Up Training | 19,120.00 | 5,304.07 |
| Baseline Survey | 680.00 | 188.64 |
| Direct Consultative Meetings | 1,020.00 | 282.96 |
| Stakeholder Meetings | 1,000.00 | 277.41 |
| Frontline staff Training | 8,500.00 | 2,357.98 |
| Official Handover | 1,000.00 | 277.41 |
| Total Set up cost | 64,510.10 | 14,239.04 |

Table 2 shows the same information for the case where the host health facility does not have enough space to accommodate the victim friendly centre within existing buildings. In such a case, a new structure will have to be constructed at an estimated cost of $25,000.00. This is the amount that was spent by FST in building the Bindura Hospital Victim Friendly Centre. The set up costs in this case amount to $64,510.00 although when capitalised annually falls down to $14,239.00 per year which is comparable to the case where refurbishment is possible.

Annual Victim Friendly Centre Running Costs

Table 3 shows the breakdown of annual running costs. It would cost the government $7,477.00 in medical and psychosocial support. These costs consist of bus fares for victims and their company for the disadvantaged. It also consists of drugs, scans and other medical costs required by the victims. Community outreach costs are part of the approach to raise awareness in the community to prevent child sexual abuse, refer and report such cases. Out reaches are important to carry out in order for the victim friendly centre to be effective, receive cases within the 72 hour window period as well as reduce child sexual abuse. It would cost the government $27, 573.00 in labour costs. These include annual salary, bonus, and one month leave. Public Health facilities normally assign nurses for the roles of counsellor, clinic manager and outreach. Appendix 5 uses state registered nurses for costing labour of counsellor, outreach officers as well as clinic managers. With the initial trainings, these nurses should be in a position to undertake the same tasks as those in FST clinics. FST clinics are run with 13% administration support expenses. Assuming the same cost, the government would need an additional $4,894.50 for administration which consists of utilities and security. The total annual cost of a victim friendly clinic amounts to $42,544.50 for the government.

Table 3: Annual Running Costs

|  | Government ($) | FST ($) |
| --- | --- | --- |
| Medical and Psychosocial Support | 7,477.00 | 7,477.00 |
| Prevention through Community Outreach | 2,600.00 | 2,600.00 |
| Other running Costs* | 27,573.00 | 47,750.00 |
| Total Direct Cost | 37,650.00 | 57,827.00 |
| Indirect Costs: Admin support | 4,894.50 | 7,517.51 |
| Total Cost | 42,544.50 | 65,344.51 |

*See Appendix 3

VfM Assessment of JPGBV Victim Friendly Centres

Table 4: JPGBV cost per beneficiary

| Assets | Description | Financial Cost+ ($) | Economic Cost++ ($) |
| --- | --- | --- | --- |
| Building Refurbishment | See appendix 1 | 7,000.00 | 840.00 |
| Equipment | See appendix 1 | 8,190.05 | 2,540.15 |
| Start Up Training | See Appendix 4 | 19,120.00 | 5,304.07 |
| Baseline Survey | See Appendix 4 | 680.00 | 188.64 |
| Direct Consultative Meetings |  | 1,020.00 | 282.96 |
| Stakeholder Meetings |  | 1,000.00 | 277.41 |
| Frontline staff Training |  | 8,500.00 | 2,357.98 |
| Official Handover |  | 1,000.00 | 277.41 |
| Total set up cost |  | 46,510.00 | 12,069.00 |
| Annual Operational Costs |  |  |  |
| Medical and Psychosocial Support | From FST | 4,362.00 | 4,362.00 |
| Labour | See Appendix 2 figures | 27,825.00 | 27,825.00 |
| Total annual running costs |  | 32,187.00 | 44,255.60 |
| Output |  |  |  |
| Reached per site* |  | 179 | 179 |
| Target* |  | 155 | 155 |
| VFM |  |  |  |
| Target cost per beneficiary | Running cost over target coverage | 207.66 | 285.52 |
| Actual cost per beneficiary | Running cost over actual coverage | 179.82 | 247.24 |
| Cost Saving |  | 27.84 | 38.28 |

+Financial cost is the actual cost incurred/expected to be incurred.

++Economic cost spreads the asset cost over useful asset life. See appendix 1. Costs are discounted at 12% per annum which is used by the Ministry of Finance for public sector projects discounting. The rationale for discounting is that the money invested in capital items today represents an opportunity to invest that money in money and capital markets and bring interest to the government at the rate of 12 % per annum. Appendix 1 highlights the total interest foregone, the life spans used for these and other investments and annual apportionments.

*The JPGBV sites reached a total of 536 beneficiaries against a target of 466. The average was obtained by dividing these figures by 3.

Table 4 shows cost per beneficiary reached after adjustments to spread costs of capital and trainings over 5 years. Cost per beneficiary was obtained by dividing total beneficiaries into total (adjusted) expenditure. These costs were incurred over 6 months from July 2015 to December 2015. The economic costs are inclusive of set up costs.

Economy

Table 4 establishes the average cost per beneficiary for the JPGBV Victim Friendly Centre sites. The target costs relate to the cost per beneficiary for the targeted coverage (155) whilst the actual relates to the actual reached (179) per site. Annual running costs are made up of labour, medical support and psychosocial support as obtained from FST. The financial cost of managing a case at a victim friendly clinic was $207.66 and the economic cost $285.22. The JPGBV victim friendly clinics were economic having managed each case at a financial cost of $179.82 and an economic cost of $247.24.

Efficiency

The program was more efficient in utilizing resources as it reached more beneficiaries than expected from the budgeted cost. The 3 clinics had a target of 466 which they surpassed to 536 averaging 179 per clinic suggesting resources were utilized 15.5% more efficiently than expected. As shown in table 4, the JBGBV victim friendly centres were cost saving to the tune of $27.84 (financial cost) and $38.28 (economic cost) and thus attained cost efficiency.

Value for money

Given that the victim friendly centres achieved both economy and efficiency, we conclude that the JPGBV offered strong Value for Money.

Appendix 1: Building and Equipment

| Asset | Unit cost ($) | Quantity | Total cost ($) | Life span | Annua-lization factor | 2015 ($) | 2016 ($) | 2017 ($) | 2018 ($) | 2019 ($) | Interest foregone ($) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Doctors Exam Couch | 333.50 | 1 | 333.50 | 5 | 0.28 | 92.52 | 92.52 | 92.52 | 92.52 | 92.52 | 129.08 |
| Doctors Examination Lamp- Simplex | 524.40 | 1 | 524.40 | 5 | 0.28 | 145.47 | 145.47 | 145.47 | 145.47 | 145.47 | 202.97 |
| BP Machine- Mercury | 56.35 | 1 | 56.35 | 5 | 0.28 | 15.63 | 15.63 | 15.63 | 15.63 | 15.63 | 21.81 |
| Medical Digital Scale | 149.50 | 2 | 299.00 | 5 | 0.28 | 82.95 | 82.95 | 82.95 | 82.95 | 82.95 | 115.73 |
| Heitometer | 41.00 | 2 | 82.00 | 5 | 0.28 | 22.75 | 22.75 | 22.75 | 22.75 | 22.75 | 31.74 |
| Blood Pressure Machine | 130.00 | 1 | 130.00 | 5 | 0.28 | 36.06 | 36.06 | 36.06 | 36.06 | 36.06 | 50.32 |
| 72" Stationery Cabinet | 414.00 | 1 | 414.00 | 5 | 0.28 | 114.85 | 114.85 | 114.85 | 114.85 | 114.85 | 160.24 |
| 4 Drawer Filing Cabinet | 414.00 | 1 | 414.00 | 5 | 0.28 | 114.85 | 114.85 | 114.85 | 114.85 | 114.85 | 160.24 |
| Drug Cabinet | 414.00 | 1 | 414.00 | 5 | 0.28 | 114.85 | 114.85 | 114.85 | 114.85 | 114.85 | 160.24 |
| Wall Clocks | 20.00 | 4 | 80.00 | 3 | 0.42 | 33.31 | 33.31 | 33.31 | 33.31 | 33.31 | 19.92 |
| DVD Player | 50.00 | 1 | 50.00 | 3 | 0.42 | 20.82 | 20.82 | 20.82 | 20.82 | 20.82 | 12.45 |
| Office Fan | 35.00 | 4 | 140.00 | 5 | 0.28 | 38.84 | 38.84 | 38.84 | 38.84 | 38.84 | 54.19 |
| 21" TV set | 300.00 | 1 | 300.00 | 3 | 0.42 | 124.90 | 124.90 | 124.90 | 124.90 | 124.90 | 74.71 |
| Capri CR170 Small Fridge | 450.00 | 1 | 450.00 | 5 | 0.28 | 124.83 | 124.83 | 124.83 | 124.83 | 124.83 | 174.17 |
| Visitors Chairs-No Arm | 88.52 | 15 | 1,327.80 | 5 | 0.28 | 368.34 | 368.34 | 368.34 | 368.34 | 368.34 | 513.92 |
| Office Chairs | 105.00 | 5 | 525.00 | 5 | 0.28 | 145.64 | 145.64 | 145.64 | 145.64 | 145.64 | 203.20 |
| 3 Drawer Desk | 250.00 | 3 | 750.00 | 5 | 0.28 | 208.06 | 208.06 | 208.06 | 208.06 | 208.06 | 290.29 |
| Receptionist Desk | 400.00 | 1 | 400.00 | 5 | 0.28 | 110.96 | 110.96 | 110.96 | 110.96 | 110.96 | 154.82 |
| HP Compaq Computer Desktop | 1,000.00 | 1 | 1,000.00 | 3 | 0.42 | 416.35 | 416.35 | 416.35 | 416.35 | 416.35 | 249.05 |
| LaserJet Printer All in One HP | 500.00 | 1 | 500.00 | 3 | 0.42 | 208.17 | 208.17 | 208.17 | 208.17 | 208.17 | 124.52 |
| Total Equipment |  |  | 8,190.05 |  |  | 2,540.15 | 2,540.15 | 2,540.15 | 2,540.15 | 2,540.15 |  |
| 4 roomed building construction | 25,000.00 | 1 | 25,000.00 | 50 | 0.12 | 3,010.42 | 3,010.42 | 3,010.42 | 3,010.42 | 3,010.42 | 125,520.83 |
| Total Assets | 30,675.27 |  | 33,190.05 |  |  | 5,550.57 | 5,550.57 | 5,550.57 | 5,550.57 | 5,550.57 |  |

Appendix 2: FST JPGBV Labour

| FST Labour | Salary ($) | Months | July-December ($) |
| --- | --- | --- | --- |
| Human Resources costs: Counsellor, Nurse, Outreach officer, secretary, doctor consultant | 3,975.00 | 7 | 27,825.00 |
|  |  | Annual budget | 7 Moths portion |
| Medical and Psychosocial support | 7,477.00 | 7 | 4,361.58 |

Appendix 4: Detailed explanation on costs of trainings and meetings

Familiarization and Consultation

In order to familiarize with the environment, a baseline survey and mapping exercise is required in the area of interest. This involves gathering primary and secondary data on child sexual abuse and gender based violence at an estimated cost of $680.00 for 2 research visits. 3 meetings are then necessary to consult hospital management teams, PMDs and other provincial and community leadership to reach memorandum of understanding at a cost of $340.00 per meeting and total cost of $1,020.00.

Forensic Examination Training

Medical personnel need to be trained on forensic medical examination skills, completion of medical affidavit forms, counselling skills and court appearances for a minimum of 5 days. Although the clinic can run with 4 staff members, a minimum of 25 people is recommended to take care of staff attrition as well as train staff from surrounding clinics who will handle similar cases and refer them to the victim friendly management centre timeously. The facilitators will require $500.00 a day for 5 days whilst the trainees will require funding for travelling to training facilities and a subsistence allowance. The total budget for forensic training gets to $16,000.00. After training, 4 key staff will need work based mentorship (attachment) for a week at a cost of $780.00 each in one week which sums to $3,120.00.

Stakeholder Meetings

Stakeholder meetings will be required to ensure key organizations which work with children and government departments have a common understanding to work together and network with the clinic and other service providers. These meetings are critical in that they facilitate smooth coordination in the network for the provision of case management through referrals and support in other key services to victims of abuse. A budget of $1,000.00 is required over 2 meetings to reach 20 key people.

Front line Staff Training

This training is given to frontline staff who admit victims of abuse at clinics and hospitals. They are trained in sensitivity of handling child abuse victims and ensure that they are empowered with relevant information governing sexual abuse and how to talk to them without further traumatizing them. A single 3 day workshop for 20 people is expected to cost $8,500.00.

Handover and Opening Ceremony

This is an official ceremony to create awareness of the existence of the clinic. An estimated $1,000.00 is required to finance travel costs of officials and refreshments at the ceremony.

## Annex 5: VfM Assessment of Childline Helpline and Drop in Centre

The evaluation of Drop-in centres and Help line seeks to establish setup costs, running costs, economy as well as efficiency. Comparison of the two models may not be helpful as they complement each other.

The 3 JPGBV drop- in centres managed 903 cases at a cost of $149,166.00 (after adjusting for annualization of capital and trainings). This implies a cost of $165.19 (appendix 7) per case managed at drop- in centres which represents economic savings of $182.20 per case.

Helpline Evaluation

Set up costs

In order to set up Helpline, a minimum of capital expenditures listed in appendix 1 are required. The total cost amounts to $271,755.00. Spreading over the assets over their useful life gives an annual economic cost of $64,601.00 per year.

Annual running costs

Annual running costs are shown in table 1. Labour costs amount to $122,850.00 per year. Labour consists of 30 Counsellors who work on 8 hour shifts, their supervisors titled team leader and call centre officer, a data capturer and an ICT officer and his 2 assistants (interns). Other annual running costs as listed in table 1 amount to $49,364.00. Total annual financial running costs amount to $198,046.10 and economic costs $267,024.59.

Table 1: Annual Running costs

| Other Expenses | Description | Cost ($) |
| --- | --- | --- |
| Labour | See appendix 2 | 122,850.00 |
| Annual induction training new staff |  | 3500.00 |
| Fixed Cellular Terminals rentals |  | 504.00 |
| Utilities |  | 5700.00 |
| Fuel |  | 2760.00 |
| Stationery and consumables |  | 6000.00 |
| Repairs and maintenance |  | 2400.00 |
| Licenses : internet cyberoam |  | 3500.00 |
| Insurance |  | 5000.00 |
| IEC material |  | 5000.00 |
| Marketing and public relations |  | 15000.00 |
| Total | Including Labour cost from (Appendix 2) | 172214.00 |
| Admin 15% |  | 25832.10 |
| Total annual financial cost |  | 198046.10 |
| Total annual economic cost | Financial Cost + Capital annualization cost (Appendix 1) | 267024.59 |
| Helpline |  |  |
| a. Total calls per year |  | 720000 |
| Total annual financial cost per centre per call |  | 0.28 |
| Total annual economic cost per centre per call |  | 0.37 |
| b. Total cases per year |  | 12000 |
| Total annual financial cost per centre per case managed |  | 16.50 |
| Total annual economic cost per centre per case managed |  | 22.25 |

Economy

Childline estimates that helpline receives 720,000 calls per year. This sums up to $0.28 per call received in financial terms as and $0.37 in economic terms per call received. Alternatively, Childline also estimates managing 12,000 cases per year which gives $16.50 per case managed in financial terms and $21.89 in terms of economic costs per case managed. These figures are standalone which will only become useful for future reference.

Drop- in Centre Economic Evaluation

Set up costs

Constructing a new structure for a drop- in centre with 4 standard sized offices would cost $25,000.00. A vehicle for use in community outreach would cost around $38,000.00. Adding equipment to these capital costs yields set up costs of $80,040.00 or $19,543.40 per year when spread over its capital life span as shown in appendix 3.

Annual running costs

Annual labour costs amount to $22,800.00 (appendix 4) and other expenses $16,767.00 giving a total annual financial cost of $42,987.00 and economic cost of $62,530.00. Labour costs consist of a social worker, drop-in assistant and a student attachee or Community Volunteer each getting remuneration highlighted in appendix 4.

Table 2: Drop- in Centre annual running costs

| Expense |  | Cost ($) |
| --- | --- | --- |
| Labour |  | 22,800.00 |
| Trainings twice arear |  | 3000 |
| Annual meeting/excursion |  | 700 |
| preloaded computer license |  | 480 |
| speakers and headphones |  | 120 |
| rentals |  | 3600 |
| Therapeutic Toys |  | 150 |
| Indoor games |  | 300 |
| Stationery and Consumables |  | 2400 |
| Communications (internet, airtime) |  | 1200 |
| Case follow ups (200L fuel) |  | 230 |
| Therapeutic support groups sessions |  | 2400 |
| Total | Including Labour cost from (Appendix 5) | 37380 |
| Admin support 15% |  | 5607 |
| Annual running financial cost per centre |  | 42987 |
| Add asset capitalization |  | 17365.21 |
| Annual Economic cost per centre | Financial Cost + Capital annualization cost (Appendix 4) | 60352.21 |
| Annual financial cost per beneficiary per centre |  | 153.525 |
| Annual Economic cost per beneficiary per centre |  | 335.29 |

Table 3: Drop-in centre output and costs

| JPGBV Drop-in |  | $ or Amount or cases |
| --- | --- | --- |
| Total Economic cost |  | 149,166.00 |
| Cases managed |  | 903 |
| Cost per case managed |  | 165.19 |
| Cost Savings |  | 170.00 |

Economy

Childline estimates that 7,000 cases are received across 25 drop- in centres which implies an average of 280 cases per centre at a unit financial cost of $153.53 and economic cost of $347.39 as shown in table 2. The JPGBV sites managed 903 cases in total at an economic cost of $149,166.00 which yields an economic cost of $165.19 as shown in table 3.

Efficiency

The economic cost of $165.19 attained by the JPGBV drop- in centres against the cost per case $347.39 established in table 2 shows that the JPGBV drop- in centres were cost efficient. The program actually operated at a cost saving of $170.00 per case.

Value for money

Given that the drop- in centres achieved both economy and efficiency, we conclude that the JPGBV drop- in centre project offered Strong Value for Money (see appendix 5 for VFM strength diagnosis).

Appendix 1: helpline Building and Equipment Annualization

| Item | Cost | Units | Total cost | Life span | annualization factor | 2015 | 2016 | 2017 | 2018 | 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cubicle | 50.00 | 23 | 1,150.00 | 5 | 0.28 | 319.02 | 319.02 | 319.02 | 319.02 | 319.02 |
| Highback chair | 105.00 | 3 | 315.00 | 5 | 0.28 | 87.38 | 87.38 | 87.38 | 87.38 | 87.38 |
| Footrest | 80.00 | 12 | 11,040.00 | 5 | 0.28 | 3,062.60 | 3,062.60 | 3,062.60 | 3,062.60 | 3062.60 |
| Mirror | 200.00 | 12 | 2,400.00 | 5 | 0.28 | 665.78 | 665.78 | 665.78 | 665.78 | 665.78 |
| Two way mirror call centre office | 300.00 | 4 | 6,900.00 | 5 | 0.28 | 1,914.13 | 1,914.13 | 1,914.13 | 1,914.13 | 1914.13 |
| Desk officer+ desk+ data capturer= 3 | 250.00 | 3 | 750.00 | 5 | 0.28 | 208.06 | 208.06 | 208.06 | 208.06 | 208.06 |
| Kitchen Table/ 4 chairs | 500.00 | 1 | 500.00 | 5 | 0.28 | 138.70 | 138.70 | 138.70 | 138.70 | 138.70 |
| Stove | 450.00 | 1 | 450.00 | 5 | 0.28 | 124.83 | 124.83 | 124.83 | 124.83 | 124.83 |
| Microwave | 100.00 | 1 | 100.00 | 5 | 0.28 | 27.74 | 27.74 | 27.74 | 27.74 | 27.74 |
| Fridge | 400.00 | 1 | 400.00 | 5 | 0.28 | 110.96 | 110.96 | 110.96 | 110.96 | 110.96 |
| Couch | 900.00 | 1 | 900.00 | 5 | 0.28 | 249.67 | 249.67 | 249.67 | 249.67 | 249.67 |
| Bean Bag | 100.00 | 1 | 100.00 | 3 | 0.42 | 41.63 | 41.63 | 41.63 | 41.63 | 41.63 |
| coffee Table | 80.00 | 1 | 80.00 | 5 | 0.28 | 22.19 | 22.19 | 22.19 | 22.19 | 22.19 |
| Networking (setting up voice and data connection) | 4,000.00 | 1 | 4,000.00 | 5 | 0.28 | 1,109.64 | 1,109.64 | 1,109.64 | 1,109.64 | 1109.64 |
| 23 desktops | 600.00 | 23 | 13,800.00 | 5 | 0.28 | 3,828.25 | 3,828.25 | 3,828.25 | 3,828.25 | 3828.25 |
| Licenses : antivirus | 2,400.00 | 1 | 2,400.00 | 5 | 0.28 | 665.78 | 665.78 | 665.78 | 665.78 | 665.78 |
| Printer all in one | 500.00 | 1 | 500.00 | 3 | 0.42 | 208.17 | 208.17 | 208.17 | 208.17 | 208.17 |
| Database devt | 6,000.00 | 1 | 6,000.00 | 5 | 0.28 | 1,664.46 | 1,664.46 | 1,664.46 | 1,664.46 | 1664.46 |
| Black box | 500.00 | 1 | 500.00 | 3 | 0.42 | 208.17 | 208.17 | 208.17 | 208.17 | 208.17 |
| Servers for database | 2,000.00 | 1 | 2,000.00 | 3 | 0.42 | 832.70 | 832.70 | 832.70 | 832.70 | 832.70 |
| Aircon x3 call centre helpline and server | 3,500.00 | 3 | 10,500.00 | 3 | 0.42 | 4,371.66 | 4,371.66 | 4,371.66 | 4,371.66 | 4371.66 |
| 52 inch real time Monitor | 1,500.00 | 1 | 1,500.00 | 3 | 0.42 | 624.52 | 624.52 | 624.52 | 624.52 | 624.52 |
| Laptop | 700.00 | 1 | 700.00 | 3 | 0.42 | 291.44 | 291.44 | 291.44 | 291.44 | 291.44 |
| UPS | 6,000.00 | 1 | 6,000.00 | 3 | 0.42 | 2,498.09 | 2,498.09 | 2,498.09 | 2,498.09 | 2498.09 |
| Generator | 6,900.00 | 1 | 6,900.00 | 5 | 0.28 | 1,914.13 | 1,914.13 | 1,914.13 | 1,914.13 | 1914.13 |
| Fixed Cellular Terminals setup- 7 lines cost | 1,750.00 | 1 | 1,750.00 | 5 | 0.28 | 485.47 | 485.47 | 485.47 | 485.47 | 485.47 |
| Telecel/Netone 2 lines + landline set up | 100.00 | 1 | 100.00 | 5 | 0.28 | 27.74 | 27.74 | 27.74 | 27.74 | 27.74 |
| Telecel/Netone 2 lines + landline set up | 100.00 | 1 | 100.00 | 5 | 0.28 | 27.74 | 27.74 | 27.74 | 27.74 | 27.74 |
| Email setup | 1,000.00 | 1 | 1,000.00 | 5 | 0.28 | 277.41 | 277.41 | 277.41 | 277.41 | 277.41 |
| software and hardware for call center | 76,700.00 | 1 | 76,700.00 | 5 | 0.28 | 21,277.33 | 21,277.33 | 21,277.33 | 21,277.33 | 21277.33 |
| Vehicle Minibus | 40,000.00 | 1 | 40,000.00 | 5 | 0.28 | 11,096.39 | 11,096.39 | 11,096.39 | 11,096.39 | 11096.39 |
| Building | 88,000.00 | 1 | 88,000.00 | 50 | 0.12 | 10,596.67 | 10,596.67 | 10,596.67 | 10,596.67 | 10596.67 |
| Total Set up cost |  |  | 271,755.00 |  |  |  |  |  |  |  |
| Total assets annualized |  |  |  |  |  | 64,600.97 | 64,600.97 | 64,600.97 | 64,600.97 | 64600.97 |

Appendix 2: Labour Based on Harare Centre

| Staff | Number | Minimum Qualifications |  | Annual Salary ($) |
| --- | --- | --- | --- | --- |
| Counsellors | 30 paid in stipends ($6 per day shift & $11 per night) | Diploma in relevant qualification + 3 years experience working with children; |  |  |
| Call Centre officer | 1 | Degree in Social work/relevant social science + 3 years exp + driving license |  |  |
| Team leader | 1 | Diploma in relevant qualification+ 3 years experience working with children |  |  |
| Data Capturer | 1 | Diploma in relevant qualification dev studies/social sciences/M&E + 3 years experience |  |  |
| ICT interns | 2 | ICT degree Students |  |  |
| ICT Officer | 1 | Degree in ICT + 3 years exp |  |  |
| Total labour expenses 35 staff for one year |  |  |  | 122,850.00 |

Appendix 3: Drop-in centre Building and Equipment Annualization

| Item | units | Unit cost | total | Life Span | annualization factor | 2015 | 2016 | 2017 | 2018 | 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| office desks | 4 | 300.00 | 1,200.00 | 5 | 0.28 | 332.89 | 332.89 | 332.89 | 332.89 | 332.89 |
| backrest chairs | 3 | 200.00 | 600.00 | 5 | 0.28 | 166.45 | 166.45 | 166.45 | 166.45 | 166.45 |
| lockable filing cabinets | 1 | 300.00 | 300.00 | 5 | 0.28 | 83.22 | 83.22 | 83.22 | 83.22 | 83.22 |
| desktop computer, laptop (Core i3 | 2 | 600.00 | 1,200.00 | 3 | 0.42 | 499.62 | 499.62 | 499.62 | 499.62 | 499.62 |
| Hard drive | 1 | 100.00 | 100.00 | 3 | 0.42 | 41.63 | 41.63 | 41.63 | 41.63 | 41.63 |
| Al in one printer | 1 | 500.00 | 500.00 | 3 | 0.42 | 208.17 | 208.17 | 208.17 | 208.17 | 208.17 |
| Therapeutic Toys | 1 | 300.00 | 300.00 | 3 | 0.42 | 124.90 | 124.90 | 124.90 | 124.90 | 124.90 |
| Rug | 1 | 100.00 | 100.00 | 3 | 0.42 | 41.63 | 41.63 | 41.63 | 41.63 | 41.63 |
| Kiddy 4 chairs, table, basket set | 1 | 100.00 | 100.00 | 5 | 0.28 | 27.74 | 27.74 | 27.74 | 27.74 | 27.74 |
| visitors chairs | 7 | 60.00 | 420.00 | 5 | 0.28 | 116.51 | 116.51 | 116.51 | 116.51 | 116.51 |
| cfi desks | 2 | 150.00 | 300.00 | 5 | 0.28 | 83.22 | 83.22 | 83.22 | 83.22 | 83.22 |
| pre loaded desktop computer, laptop Core i3 21 inch monitor | 2 | 650.00 | 1,300.00 | 3 | 0.42 | 541.25 | 541.25 | 541.25 | 541.25 | 541.25 |
| Library Books | 1 | 500.00 | 500.00 | 5 | 0.28 | 138.70 | 138.70 | 138.70 | 138.70 | 138.70 |
| Library book shelves | 1 | 800.00 | 800.00 | 5 | 0.28 | 221.93 | 221.93 | 221.93 | 221.93 | 221.93 |
| swivel stools | 4 | 180.00 | 720.00 | 5 | 0.28 | 199.74 | 199.74 | 199.74 | 199.74 | 199.74 |
| Dynamic software | 1 | 5,000.00 | 5,000.00 | 3 | 0.42 | 2,081.74 | 2,081.74 | 2,081.74 | 2,081.74 | 2,081.74 |
| Projector | 1 | 300.00 | 300.00 | 3 | 0.42 | 124.90 | 124.90 | 124.90 | 124.90 | 124.90 |
| Garden child play centre mountings | 1 | 1,000.00 | 1,000.00 | 5 | 0.28 | 277.41 | 277.41 | 277.41 | 277.41 | 277.41 |
| Generator back up | 1 | 1,500.00 | 1,500.00 | 5 | 0.28 | 416.11 | 416.11 | 416.11 | 416.11 | 416.11 |
| Indoor games | 1 | 300.00 | 300.00 | 3 | 0.42 | 124.90 | 124.90 | 124.90 | 124.90 | 124.90 |
| Waiting area bench | 1 | 500.00 | 500.00 | 5 | 0.28 | 138.70 | 138.70 | 138.70 | 138.70 | 138.70 |
| Vehicle | 1 | 38,000.00 | 38,000.00 | 5 | 0.28 | 10,541.57 | 10,541.57 | 10,541.57 | 10,541.57 | 10,541.57 |
| New Building (4 roomed) | 1 | 25,000.00 | 25,000.00 | 5 | 0.28 | 832.23 | 832.23 | 832.23 | 832.23 | 832.23 |
| Total set up cost |  |  | 80,040.00 |  |  |  |  |  |  |  |
| annualised capital cost |  |  |  |  |  | 17,365.21 | 17,365.21 | 17,365.21 | 17,365.21 | 17,365.21 |

Appendix 4: drop-in centre labour

| Designation | Qualifications | Monthly salary | Annual cost |
| --- | --- | --- | --- |
| Social worker | Degree in social work, drivers licence- at least 3 years experience |  |  |
| Drop-in assistant | Diploma social work/sciences 3 years experience |  |  |
| Student attachee/Community Volunteers/CCWs | degree student in social work |  |  |
| Total Annual Labour Cost for 3 staff of the drop in centre |  |  | 22,800.00 |

## Annex 6: List of Interviewees

| NAME | DESIGNATION | MINISTRY/ORGANISATION |
| --- | --- | --- |
| Stephen Nyaruwata | Director, Gender | MWAGCD |
|  |  | Ministry of Justice, Legal and Parliamentary Affairs |
| Dr Bernard Madzima | Director, Family Health | Ministry of Health and Child Care |
| Michelle Gudo | EVAW Specialist | UN Women |
| Revai Makanje Aalbaek | Deputy Country Representative | UN Women |
| Siyma Barkin Kuzmin | Child Protection Specialist | UNICEF |
| Noriko Izumi Viggo Aalbaek | Chief of Child Protection | UNICEF DANIDA |
| Esther Savanhu |  | DANIDA |
| Madrine Chiku | National Gender Coordinator | World Vision |
| T. Muchinguri | Programme Coordinator | Family Support Trust |
| D. Kanyimo | Programme Officer | WILSA |
| K. Munyoro | Legal Information Officer | WILSA |
| S. Muengwa | Programme Officer | Justice for Children |
| M. Chinoona | Education Officer | Cheshire |
| G Chivandire | Programme Coordinator | Cheshire |
| RatidzaiMoyo | Case Quality Manager | Childline |
| Ygainnia Hamandawana | MER Coordinator | Childline |
| Luta Shaba | Director | The women’s Trust |
| Vimbai Mlambo | Programme Manager | SayWhat |
| Sendisa Ndlovu | Programmes Officer | SayWhat |
| BEITBRIDGE DICTRICT |  |  |
| Ms. Maposa | Acting Provincial Development Officer | MWAGCD |
| Mr. Siduli |  | MWAGCD |
| Mr. Mabeta | Regional Magistrate | Min of Justice, Legal and Parliamentary Affairs |
| Mr. Nkomo |  | Department of Social Services |
| Ms.Mlambo |  | Department of Social Services |
| Precious Bhadha | Assistant Inspector | VFU, Beitbridge District |
| Angeline Muzamani | Senior Nurse | Mtetengwe Clinic |
| FGD Community Focal Persons | 4 Beitbridge Urban CFPs | Beitbridge |
| FGD Traditional Leaders | Ward 5 Chamunanga | Beitbridge |
| FGD Young Women | Ward 5 Chamunanga | Beitbridge |
| FGD Traditional Leaders | Ward 6 Mtetengwe | Beitbridge |
| FGD Boys | Ward 6 Mtetengwe | Beitbridge |
| FGD Girls | Ward 6 Mtetengwe | Beitbridge |
| FGD Women | Ward 6 Mtetengwe | Beitbridge |
| FGD Men | Ward 6 Mtetengwe | Beitbridge |
| BINDURA DISTRICT |  |  |
| J. Hove | Provincial Development Officer | Min of Women Affairs, Gender and Community Development |
| Mafusire | Provincial Gender Officer |  |
| Elizabeth Nkoma | District Development Officer |  |
| Lydia Hlabati | Assistant DA |  |
| Desman Maringire |  | ZAPSO |
| Pauline Chima |  | Local Government |
| TatendaMuchenjekwa |  | Childline |
| A. Karuru | District AIDS Coordinator | National AIDS Council |
| G. Mudambu | Public Prosecutor | National Prosecuting Authority |
| E. Singano | Provincial Magistrate | Ministry of Justice, Legal and Parliamentary Affairs |
| T. Marimo | Social Services Officer | Min of Labour and Social Services |
| FGD SayWHAT Ambassadors | SayWhat Ambassador | BUSE |
| E. Manjoro | Outreach and Training Officer | Family Support Trust |
| FGD Teachers | 4 Teachers | Muchapondwa School |
| FGD girls | 8 primary school girls | Muchapondwa School |
| Maud Chasakara | Most Significant Change Story | Justice for Children Trust |
| DainahKabaya | Most Significant Change Story | Justice for Children Trust |
| Molly Kapasura | Most Significant Change Story | Justice for Children Trust |
| FGD Community Leaders | Manhenga Village | Bindura |
| FGD girls | Non beneficiaries (8 members) | Manhenga Clinic |
| FGD Women | Beneficiaries (10 members) | Chiveso Clinic |
| FGD Men | FGD men (beneficiaries) | Chipadze |
| Rev H. Mazonde | Religious Leader | Harvest House International Church |
| Ass Inspector JoselinePaswavaviri | VFU | ZRP Victim Friendly Unit |
| MAKONI DISTRICT |  |  |
| EmillioChihono | District Development Officer | MWAGCD |
| ChiedzaMasvovere | Anti GBV Committee Chairperson | Fact |
| Gift Makotsi | Social Services Officer | Department of Social Services |
| L.Z. Chipadza | Regional Magistrate | Min of Justice, Legal and Parliamentary Affairs |
| A.Guta | Teacher | Vengere High School |
| ChengetayiNyamukapa | Programmes Manager | Childline |
| A.Guta | Teacher | Vengere High School |
| FGD girls | 4 Students | Vengere High School |
| FGD young women | 5 beneficiaries | Rusape |
| FGD women | 24 women | Ward 15 |

## Annex 7: List of Documents Reviewed

Annex B Justification for request of refocusing of the Project 15 May 2015

Austrian Development Cooperation, 2009. OECD/DAC Guidelines for Project and Programme Evaluations.

Census and Statistics Act Chapter 10:05.  Act 1/1971, 19/1989, 22/2001 (S.4)

Danida, 2015. Note for the Record. Background and Recommendations for Implementation of the Shelter Component of the Joint UNICEF and UN Women Programme on Prevention of Gender Based Violence (JPGBV) 19 May 2015.

DFID, 2011. DFID’s Approach to Value for Money (VfM). Department for International Development, accessed on 15 March 2016 online at http://betterevaluation.org/search/site/value%20for%20money

Fleming F, 2013. Evaluation Methods for Assessing Value for Money.  accessed on 15 March 2016 online at http://betterevaluation.org/search/site/value%20for%20money.

Merriam, 1988. Ethical Considerations. http://www.ukessays.co.uk/essays/social-policy/ethical-considerations.php

Ministry of Labour and Social Services. The National Action Plan for Orphans and Vulnerable Children 2011-2015.

MWAGCD, 2014. The Girls’ and Young Women’s Empowerment Framework.

MWAGCD, 2013. National Gender Policy 2013-2017.

MWAGCD, and UNWomen, 2014. Capacity Strengthening of MWAGCD Anti GBV sub structures to prevent and respond to violence against adolescent girls and young women. BeitbridgeDistrict Report.

MWAGCD, and UN Women, 2014. Capacity Strengthening of MWAGCD Anti GBV sub structures to prevent and respond to violence against adolescent girls and young women. Bindura District Report.

MWAGCD, and UN Women, 2014. Capacity Strengthening of MWAGCD Anti GBV sub structures to prevent and respond to violence against adolescent girls and young women. Makoni District Report.

SayWhat Annual Report November 2014-November 2015.

UN Women and UNICEF. JPGBV Revised Logframe 2016.

UN Women and UNICEF. Mission Report 18 November 2015.

UN Women and UNICEF. 2015. Annual Report ZIMBABWE Prevention of Gender Based Violence Against Adolescent Girls and Young Women. A joint UNICEF and UNWOMEN programme with the Government of Denmark/Royal Danish Embassy Office Harare.

UN Women and UNICEF. Final revised draft GBV Logframe May 2015

UN Women. A Report on a Baseline Study on Gender Based Violence against Adolescent Girls and Young Women in Beitbridge, Bindura and Makoni Districts. Draft 28 august 2015.

UN Women, 2015. How to Manage Gender-Responsive Evaluation. Evaluation Handbook

UN Women 2014. Guide for the Evaluation of Programmes and Projects with a Gender, Human Rights and Intercultural Perspective.

UNICEF and UN Women, 2013. Standard MOU for Multi-Donor Trust Funds and Joint Programmes Using Pass-Through Fund Management.

UNICEF and UN Women. 2013. Final Adolescent Girls Concept Note Danida 02.08.13

Theory of Change for the Programme

World Vision Final Report October 2014-September 2015.

Zimbabwe National Statistics Agency (ZIMSTAT), United Nations Children’s Fund (UNICEF) and Collaborating Centre for Operational Research and Evaluation (CCORE), 2013. National Baseline Survey on Life Experiences of Adolescents, 2011.

ZIMSTAT and ICF International 2012. Zimbabwe Demographic and Health Survey 2010-11. Calverton, Maryland: ZIMSTAT and ICF International Inc.

## Annex 8: Tools

### Key informant Guide UNWOMEN and UNICEF

Relevance

- What process was undertaken to identify rights and needs of adolescent girls and young women to address GBV and inform the programme desing?

- How were stakeholders involved in programme design?

- How have the programme objectives addressed identified rights and needs of adolescent girls and young women in national and regional contexts?

- How is the programme aligned to national, regional and international policies, strategies, agreements and conventions? Explain.

- To what extent has the programme contributed to the national priorities stipulated in key documentation (National Gender Policy, National GBV Strategy)?

- Have there been changes to the programme since inception? What were the reasons behind the changes?

Efficiency

- What criteria was used in the selection of partners to ensure that they provide the programme with required capacity and strategic positioning to achieve objectives?-

- What measures have been taken during planning and implementation to ensure that resources are efficiently used?

- Have programme funds and activities been delivered in a timely manner and within budgets? If not, what were the bottlenecks encountered? How were they addressed?

- Are there opportunities for implementing the programme differently in a way that provides value for money in the future?

- What were the constraints (e.g. political, practical, and bureaucratic) to addressing GBV efficiently during implementation? What level of effort was made to overcome these challenges?

For the JPGBV monitoring:

- What mechanisms were put in place to monitor programme activities to provide adequate evidence to inform programme implementation and measure progress towards results? Were these monitoring mechanisms able to identify challenges and were the necessary follow up actions taken to address these challenges? Give examples.

- Are M&E mechanisms providing adequate evidence to inform programme implementation?

Effectiveness

- What key results have you achieved with the programme? (Probe for the three outcomes: National normative and financial GBV framework strengthened; Improved preventive measures for GBV;  Strengthened service delivery for survivors of GBV)

- What are the areas of greatest/least achievement and reasons for the achievement/non-achievement (identify constraining and enabling factors)?

- How were the constraining factors addressed?

- Of the achievements, which ones do you recommend for the programme to build on or expand on?

- Are unintended positive or negative results produced by the actions of the JPGBV?

- How have the capacities of beneficiaries in dealing with GBV been strengthened?

Sustainability

- What strategies are in place to enhance sustainability of the programme? To what extent do they facilitate ownership by government, stakeholders and beneficiaries; and ensure outcome results will continue?

- What is the likelihood that the benefits from the program will be maintained for a reasonably long period of time if the program were to cease?

- Is the program supported by national/local institutions? Which ones? Do these institutions, including Government and stakeholders, demonstrate ownership, leadership commitment and technical and financial capacity to continue to work with the program or replicate it? PROBE the following:

  - To what extent has the program generated political support?

  - What proportion of the program is funded from local resources?

  - Has there been an increase in local funding for the program (government, private sector etc?

  - Is there a sustainable health financing strategy for GBV?

  - Is there a strategy for Public/Private Partnerships for GBV programming?

- To what degree are communities owning programme activities? PROBE: community initiatives, participation of duty bearers, mobilisation of rights holders etc.

- Based on your experience with the programme which components of the program should be carried over into a future phase (scalable activities and cost of scale-up), and are there any recommendations for their improvement?

- Have you developed civil society capacity to mobilize resources?

Partnership and Coordination

- What mechanisms were put in place to ensure the JPGBV complements other gender programmes in Zimbabwe

- How well were the responsibilities delineated and implemented in a complementary fashion?

- How well have the coordination functions been fulfilled? Are there any challenges/ What are the challenges, if any?

- Have the management and implementation capacities (participating UN agencies, IPs) been adequate?

- How (if at all) has the programme made strategic use of coordination and collaboration with other programmes ((1)UNICEF access to justice program, work with the Victim Friendly Courts and Multi-sectoral Protocol on the Management of Sexual Abuse in Zimbabwe; and (2) UN Women work on GBV) to increase its effectiveness and impact? PROBE: Examples of such collaborations and coordination.

Joint programming

- What coordination mechanisms were put in place to ensure a coherent programme?

- How has the "jointness" of the programme contributed to its effectiveness?  Provide examples

- Has the "jointness" of the programme contributed to the efficiency of programme implementation and management? if so, how (Examples: economies of scale in service provision, cost sharing, knowledge sharing, technical supports, economies of scale in provision of services, use of comparative strengths of UN agencies to improve effectiveness)?

Lessons learnt and Recommendations

- What are the key lessons you have learned in implementing the JPGBV (programme desing, programme management, establishing a multi-sectoral approach to providing GBV services to survivors, human rights approach to service provision)?

- If you were to implement another JPGBV what would you do differently? Why?

### Key Informant Interview Guide: Min of Gender and Judicial Services Commission,

General: As a government Ministry/Institution what is your role /specific interventions in the JPGBV programme?

Relevance

- How were you involved in the design of the programme?

- How has the programme enabled you to address GBV for girls and women in Zimbabwe (the judiciary system for Judicial Services Commission)?

- How is the programme aligned to your plans to addressing GBV for young women and girls in Zimbabwe?

- How has the programme contributed to your priorities for addressing GBV among this target group?   Explain.

- If not mentioned how about to the national priorities stipulated in key documentation (National Gender Policy, National GBV Strategy, Multi-Sectoral Protocol on The Management of Sexual Abuse in Zimbabwe)?

- Have there been changes to the programme since inception? What were the reasons behind the changes?

Efficiency

- How were you involved in the selection of CSO partners for the programme?

- What is your opinion on their capacity to deliver and their  strategic positioning to achieve objectives allocated to them?

- What measures have been taken during planning and implementation to ensure that resources are efficiently used?

- Have programme funds and activities been delivered in a timely manner and within budgets? If not, what were the bottlenecks encountered? How were they addressed?

- Are there opportunities for implementing the programme differently in a way that provides value for money in the future?

- What were the constraints (e.g. political, practical, and bureaucratic) to addressing GBV efficiently during implementation? What level of effort was made to overcome these challenges?

For the JPGBV monitoring:

- What mechanisms were put in place to monitor programme activities to provide adequate evidence to inform programme implementation and measure progress towards results? Were these monitoring mechanisms able to identify challenges and were the necessary follow up actions taken to address these challenges? Give examples.

- Are these M&E mechanisms providing adequate evidence to inform programme implementation?

Effectiveness

- What key results have you achieved with the programme? (Probe for the three outcomes: National normative and financial GBV framework strengthened; Improved preventive measures for GBV;  Strengthened service delivery for survivors of GBV)

- What are the areas of greatest/least achievement and reasons for the achievement/non-achievement (identify constraining and enabling factors)?

- How were the constraining factors addressed?

- Of the achievements, which ones do you recommend for the programme to build on or expand on?

- Are there unintended positive or negative results produced by the actions of the JPGBV?

- How have the capacities of beneficiaries in dealing with GBV been strengthened?

Sustainability

- What strategies have you put in place to enhance sustainability of the programme results?

- What is the likelihood that the benefits from the program will be maintained for a reasonably long period of time if the program were to cease?

- In terms of funding for GBV:

  - To what extent has the program generated political support for GBV supporting?

  - What proportion of the program is funded from local resources?

  - Has there been an increase in local funding for the program (government, private sector etc?

  - Is there a sustainable health financing strategy for GBV?

  - Is there a strategy for Public/Private Partnerships for GBV programming?

- To what degree are communities owning programme activities? PROBE: community initiatives, participation of duty bearers, mobilisation of rights holders etc.

- Based on your experience with the programme which components of the program should be carried over into a future phase (scalable activities and cost of scale-up), and are there any recommendations for their improvement?

Partnership and Coordination

- What mechanisms did you put in place to ensure the activities funded by JPGBV also compliment and collaborate with existing initiatives addressing GBV?

- How well were the responsibilities delineated and implemented in a complementary fashion?

- How well have the coordination functions been fulfilled? Are there any challenges/ What are the challenges, if any?

- Have the management and implementation capacities (participating UN agencies, IPs) been adequate?

Joint programming

- What coordination mechanisms were put in place to ensure a coherent programme?

- How has the "jointness" of the programme contributed to its effectiveness?  Provide examples

- Has the "jointness" of the programme contributed to the efficiency of programme implementation and management? if so, how (Examples: economies of scale in service provision, cost sharing, knowledge sharing, technical supports, economies of scale in provision of services, use of comparative strengths of UN agencies to improve effectiveness)?

Lessons learnt and Recommendations

- What are the key lessons you have learned in implementing the JPGBV (programme desing, programme management, establishing a multi-sectoral approach to providing GBV services to survivors, human rights approach to service provision)?

- If you were to implement another JPGBV what would you do differently? Why?

### Key Informant Interview Guide: Other Government Ministries Agencies and Institutions

General

As a government Ministry/Institution what is your role /specific interventions in the JPGBV programme?

Relevance

- How has the programme enabled you to address GBV for girls and women in Zimbabwe?

- How is the programme aligned to your plans to addressing GBV for young women and girls in Zimbabwe?

- How has the programme contributed to your priorities for addressing GBV among this target group?   Explain.

Efficiency

- Have programme funds and activities been delivered in a timely manner and within budgets? If not, what were the bottlenecks encountered? How were they addressed?

- Are there opportunities for implementing the programme differently in a way that provides value for money in the future?

Effectiveness

- What key results have you achieved with the programme? (Probe for the three outcomes: National normative and financial GBV framework strengthened; Improved preventive measures for GBV;  Strengthened service delivery for survivors of GBV)

- What are the areas of greatest/least achievement and reasons for the achievement/non-achievement (identify constraining and enabling factors)?

- How were the constraining factors addressed?

- Of the achievements, which ones do you recommend for the programme to build on or expand on?

- Are there unintended positive or negative results produced by the actions of the JPGBV?

- How have the capacities of beneficiaries in dealing with GBV been strengthened?

Sustainability

- What strategies have you put in place to enhance sustainability of the programme results?

- What is the likelihood that the benefits from the program will be maintained for a reasonably long period of time if the program were to cease?

- In terms of funding for GBV:

  - To what extent has the program generated political support for GBV?

  - What proportion of the program is funded from own resources?

  - Has there been an increase in local funding for the program related activities?

- Based on your experience with the programme which components of the program should be carried over into a future phase (scalable activities and cost of scale-up), and are there any recommendations for their improvement?

Lessons learnt and Recommendations

- What are the key lessons you have learned in implementing the JPGBV (programme desing, programme management, establishing a multi-sectoral approach to providing GBV services to survivors, human rights approach to service provision)?

- If you were to implement another JPGBV what would you do differently? Why?

### Implementing Partners

General

- What was your organisation’s role/specific interventions in the JPGBV? When did you start this role/interventions?

Relevance

- What key result area of the JPGBV is your project contributing to?

- What mechanisms are available to compliment and collaborate with other CSO partners on the programme? Are these adequate and useful? Please provide examples of the benefits you have derived from these mechanisms.

- How are your activities under this JPGBV addressing identified rights and needs of adolescent girls and young women in the target communities?

- Have there been changes to the programme or your activities since inception of your contract? What were the reasons behind the changes?

Efficiency

- What measures have been taken during planning and implementation to ensure that resources are efficiently used?

- Have programme funds and activities been delivered in a timely manner and within budgets? If not, what were the bottlenecks encountered? How were they addressed?

- Are there opportunities for implementing the programme differently in a way that provides value for money in the future?

- What were the constraints (e.g. political, practical, and bureaucratic) to addressing GBV efficiently during implementation? What level of effort was made to overcome these challenges?

For the JPGBV monitoring:

- What mechanisms were put in place to monitor programme activities to provide adequate evidence to inform programme implementation and measure progress towards results? Were these monitoring mechanisms able to identify challenges and were the necessary follow up actions taken to address these challenges? Give examples.

- Are M&E mechanisms providing adequate evidence to inform programme implementation?

Effectiveness

- What key results have you achieved with the programme? (Probe for the three outcomes: National normative and financial GBV framework strengthened; Improved preventive measures for GBV;  Strengthened service delivery for survivors of GBV)

- What are the areas of greatest/least achievement and reasons for the achievement/non-achievement (identify constraining and enabling factors)?

- How were the constraining factors addressed?

- Of the achievements, which ones do you recommend for the programme to build on or expand on?

- Are unintended positive or negative results produced by the actions of the JPGBV?

- How have the capacities of beneficiaries in dealing with GBV been strengthened?

Sustainability

- What strategies are in place to enhance sustainability of the programme? To what extent do they facilitate ownership by government, stakeholders and beneficiaries; and ensure outcome results will continue?

- What is the likelihood that the benefits from the program will be maintained for a reasonably long period of time if the program were to cease?

- Is the program supported by national/local institutions? Which ones? Do these institutions, including Government and stakeholders, demonstrate ownership, leadership commitment and technical and financial capacity to continue to work with the program or replicate it?

- To what degree are communities owning programme activities? PROBE: community initiatives, participation of duty bearers, mobilisation of rights holders etc.

- Based on your experience with the programme which components of the program should be carried over into a future phase (scalable activities and cost of scale-up), and are there any recommendations for their improvement?

- Are there potential avenues for resource mobilization to support the activities you are implementing under JPGBV in the future? Please provide the evidence.

Partnership and Coordination

- What coordination mechanisms were put in place to ensure a coherent programme?

- How well were the responsibilities delineated and implemented in a complementary fashion?

- How well have the coordination functions been fulfilled? Are there any challenges/ What are the challenges, if any?

- Have the management and implementation capacities (participating UN agencies, IPs) been adequate?

- How (if at all) has the programme made strategic use of coordination and collaboration with other programmes ((1)UNICEF access to justice program, work with the Victim Friendly Courts and Multi-sectoral Protocol on the Management of Sexual Abuse in Zimbabwe; and (2) UN Women work on GBV) to increase its effectiveness and impact? PROBE: Examples of such collaborations and coordination.

Joint programming

- How has the "jointness" of the programme contributed to its effectiveness?  Provide examples

- Has the "jointness" of the programme contributed to the efficiency of programme implementation and management? if so, how (Examples: economies of scale in service provision, cost sharing, knowledge sharing, technical supports, economies of scale in provision of services, use of comparative strengths of UN agencies to improve effectiveness)?

Lessons learnt and Recommendations

- What are the key lessons you have learned in implementing the JPGBV (programme desing, programme management, establishing a multi-sectoral approach to providing GBV services to survivors, human rights approach to service provision)?

- If you were to implement another JPGBV what would you do differently? Why?

### Key Informant Interview Guide: Community Leaders

Relevance

- Is GBV an issue of concern in your community? Explain.

- What forms of GBV are you aware of? Instruction: The most common form will be physical violence. If only one type of GBV is mentioned, explain to the group the types of GBV and refer to these throughout the discussion. After explaining ask: Which types of GBV are most common in this area (also specifically probe child marriages if not mentioned)?

- What are the main causes of GBV in this community? Is anything being done to address these causes? Who is doing this? Instruction: If many NGOs focus on the NGO being evaluated. How do you see the success of their work? Why do you say so…can you provide me some examples of this success?

- Do you think their work is addressing the real causes of GBV in this community?

Participation in the programme

- Have you attended any meeting organized by [name of NGO] discussing GBV?

- Was this meeting helpful? In what ways was it helpful to you and in your work as a community leader? PROBE: initiatives they have undertaken to address causes of GBV.

- Was the information provided adequate for you? How have you used the knowledge gained in your community?

- Who else has been organizing similar meetings? When you compare these to those by [name of NGO] which ones have been more helpful and why?

- On a scale of 1-10 how satisfied are you with the work of [name of NGO] with regards reducing GBV among young women and girls (10-24 years)?

Effectiveness

- When you compare before the entry of [name of NGO] in this community, [2014/2015] on issues of GBV among young women and girls (10-24 years) do you see any difference in:

- Men’s involvement and attitudes towards addressing GBV

- Girls’ knowledge of GBV and their ability to seek help when GBV occurs

- Ability of police, clinics, courts and social welfare to handle those that would have experienced GBV

- Number of girls and women reporting cases of GBV and which cases are mostly reported

- Are there community structures for addressing GBV? When were these initiated?  What are some of their successes? What challenges do they face?

Sustainability

- Do you think the results you mentioned above will be there for a long time to come? Why?

- What else needs to be done to ensure GBV among young women and girls (10-24 years) is reduced?

- What else needs to be done to ensure those young women and girls (10-24 years) who undergo GBV are supported by the community and service providers (police, health, courts, social welfare)?

Lesson learned

- When you look at the work being done to address GBV in your community by NGOs and government what do you think needs to change?

- What are they doing well and less well?

### Discussion Guide/Most Significant Change Stories: Beneficiaries

- Tell us how you first became involved with this project and what you involvement in the project was?

…………………………………………………………………………………………………………………………………………..

……………………………………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………………………

- From your point of view, describe a story that best describes the most significant change that has resulted from your involvement in this project.

…………………………………………………………………………………………………………………………………………..

……………………………………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………………………

- Why is the story significant to you?

…………………………………………………………………………………………………………………………………………..

……………………………………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………………………

- Are there areas in your life you feel the project could have done more to address? What are these and why?

…………………………………………………………………………………………………………………………………………..

……………………………………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………………………

……………………………………………………………………………………………………………………………………………

### Focus Group Discussion Guide: Beneficiaries

GBV Awareness and Prevention

- Are you aware of [NGO Name]? What are they doing in this community?

- If GBV related activities are not mentioned ask: Are there any activities they are implementing that are aimed at reducing violence against women and girls?

- How have you benefited from these activities?  On a scale of 1-10 how do you rate the appropriateness of this support to you and to reducing GBV in the community?

- Have you seen any changes as a result of these activities in relation to GBV in your community and benefits to you in particular when compared to before they were implemented?

- On a scale of 1-10 (providing reasons for your rating):

  - how satisfied are with the activities of this NGO in your community?

  - Changes in GBV occurrence among girls and women in this community?

- Is there anything that needs to change in the programmes of these NGOs?

- Has the community come up with their own initiatives to address GBV in this community? Can you explain how these initiatives cam about? What are these and are they still on-going? Do these face any specific challenges? What have been their successes?

- Before 2013 did you have such initiatives? Why?

- How are men and boys involved in reducing GBV? How does this compare to the past (before 2013)?

- When you experience GBV where do you report? How confident are you to report to these places? Why?

Support to GBV Survivors

- What mechanisms are in place to support survivors of GBV?

- What support have you received to equip you to prevent GBV (through training, information exchange, etc). Who provided it? Instruction: If many NGOs focus on the NGO being evaluated. Was support provided by [NGO evaluated] adequate? What else needs to be done?

- What support, if any, do survivors of GBV receive in this community? What help and from whom? (safe shelter; clinic/hospital; victim friendly services; legal services)

- How useful do you think this support is? (clinic/hospital; victim friendly services; legal services; community; community leadership)

- What else can be done to support survivors of GBV? What can be done for perpetrators?

- What are your recommendations to improve service provision?

### Focus Group Discussion: Non-Beneficiaries

Prevention of GBV

- Is GBV an issue of concern in your community? Explain.

- What forms of GBV are you aware of? Instruction: The most common form will be physical violence. If only one type of GBV is mentioned, explain to the group the types of GBV and refer to these throughout the discussion. After explaining ask: Which types of GBV are most common in this area?

- What are the main causes of GBV in this community? Is anything being done to address these causes? Who is doing this? Instruction: If many NGOs focus on the NGO being evaluated. How do you see the success of their work? Why do you say so…can you provide me some examples of this success?

- Is there anything that needs to change in the programmes of these NGOs?

- Has the community come up with their own initiatives to address GBV in this community? Can you explain how these initiatives cam about? What are these and are they still on-going? Do these face any specific challenges? What have been their successes?

- Before 2013 did you have such initiatives? Why?

- How are men and boys involved in reducing GBV? How does this compare to the past (before 2013)?

- What community leaders? How are they involved in reducing GBV? How does this compare to the past (before 2013)?

- Do you see any outstanding challenges in addressing GBV in your community? What are these?

Support to GBV Survivors

- What mechanisms are in place to support survivors of GBV?

- What support have you received to equip you to prevent GBV (through training, information exchange, etc). Who provided it? Instruction: If many NGOs focus on the NGO being evaluated. Was support provided by [NGO evaluated] adequate? What else needs to be done?

- What support, if any, do survivors of GBV receive in this community? What help and from whom? (safe shelter; clinic/hospital; victim friendly services; legal services)

- How useful do you think this support is? (clinic/hospital; victim friendly services; legal services; community; community leadership)

- What else can be done to support survivors of GBV? What can be done for perpetrators?

- What are your recommendations to improve service provision?

# Annex 9: Consent Forms

Mid Term Review of the Joint Programme onPrevention of Gender Based Violence (JPGBV) Against Young Women and Adolescent Girls

INFORMED CONSENT FORM

INSTRUCTION: Each questionnaire should be accompanied with this consent form.

Introduction: My name is ………from Development Solutions (DS). DS has been hired by UN Women and UNICEF to evaluate the Joint Programme on Prevention of Gender Based Violence (JPGBV) Against Young Women and Adolescent Girls. The evaluation is assessing progress made towards achievement of JPGBV expected results since its inception, check if it is on track, and if any adjustments are needed, draw conclusions about the programme strategy and inform future programming.

In this evaluation we are speaking to adolescent and young women between ages of 15-24 years in three Districts: Beitbridge, Bindura, and Makoni. The information you shall provide me shall be used in strict confidence and your name shall not appear during the analysis of this information as we shall consolidate views from young people like you we are talking to from your area and other two districts. Furthermore, the information will only be used solely for this evaluation and in no way shall the information you provide us lead to any follow up on personal issues you will raise. It is your right to refuse to participate in this survey, or to answer any of the questions if you feel uncomfortable giving an answer.

Would you like to participate in this survey?

1= Yes  			2= No

| Sign | Date |
| --- | --- |

Now that you have agreed to participate in this survey I shall ask you several questions for which I would like your honest response. If at any time you feel you do not want to continue with the interview please feel free to let me know and we will stop.

Mid Term Review of the Joint Programme onPrevention of Gender Based Violence (JPGBV) Against Young Women and Adolescent Girls

INFORMED CONSENT FORM

INSTRUCTION: Each questionnaire should be accompanied with this consent form.

Introduction:ZitaRangundinonzi  ………weku Development Solutions (DS). DS yakapiwabasa ne UN Women and UNICEF yekuongororachirongwachavochavaiitapamwechetekudziviriramhirizhongapakatipevarumenevakadzivakatarisananevanasikanauyemadzimaiechidiki - Joint Programme on Prevention of Gender Based Violence (JPGBV) Against Young Women and Adolescent Girls. Ongororoiyiirikutarisabudiriroyakaitwamaereranonezvaitarisirwakuitwakubvachirongwaichi chichi tangwa, uyekuonakutichirongwaichichichirimugwararacho here, kuonakuti pane zvinodakagadziriswa here, uyekuzowanazvatingatauramaereranonemarongerwoakaitwachirongwaichinekuzorairazvirongwazvakaitaseichochizvingazodakuitwamuneramangwana (draw conclusions about the programme strategy and inform future programming).

Tirikukurukuranevanasikananemadzimaiechidikikubvirapamakoreguminemashanukusvikamakumimavirinemana (15-24 years) vemunzvimbodzinoti: Beitbridge, Bindura, neMakoni. Zvamuchatiudzazvichashandiswanenzirayakavanzikauyezitarenyuharizoshandiswemberisezvotichabatanidzamaoneroevamwevezerarenyuvatichakurukurawonavovenzvimbodzatambotauraidzi. Zvamuchatiudzazvichashandiswapaongororoinochete, uyehazvizoshandiswakukuteeraikuzobvunzwamimwemibvunzomuneramangwana. Ikodzeroyenyukurambakukurukuranenipahurukuroino kana kurambakupinduramimweyemibvunzoyandinayo kana mukanzwamusingasunungukekuipindura.

Munobvuma here kukurukuraneni/nesumuongororoino?

1= Hongu			2= Kwete

| Sign | Zuva |
| --- | --- |

Zvamabvumakukurukuraneni/nesu, ndavekukubvunzaimibvunzoyandinokumbiramhindurodzakavimbika. Ndiziviseicheronguva kana mukanzwakutihamuchadakuendereramberikupinduramibvunzoyandinayondobvandamira.

There are discussions with UNFPA to take over implementation of the Training Guidelines.

Zimbabwe National Statistics Agency (ZIMSTAT) and ICF International, 2012. Zimbabwe Demographic and Health Survey 2010-11. Calverton, Maryland: ZIMSTAT and ICF International Inc.

ZIMSTAT, UNICEF and Collaborating Centre for Operational Research and Evaluation (CCORE), 2013. National Baseline Survey of Life Experiences of Adolescents, 2011.

ZIMSTAT, 2015. Zimbabwe Multiple Indicator Cluster Survey 2014, Final Report. Harare, Zimbabwe.

CFPs were introduced by the JCT consortium and are drawn from the community based Child Protection Committees (if available). Their role was to continue awareness activities on GBV identify GBV survivors and refer them to appropriate service providers, and provide para-legal services.

Marimo, N, Mpofu, N, Tichagwa W. (2013) End of Programme Evaluation of the Gender Support Programme. An evaluation report prepared for UN Women

The programme attempted to address this issue through the empowerment circles facilitated by ZWLA and JCT but their focus was too narrow to provide this support.

See ZIMSTAT (2015) Zimbabwe Demographic Health Survey Preliminary Results

UNICEF, UNFPA, Ministry of Health and Child Care, European Commission, GIZ etc. were at the forefront of these initiatives.

The ZDHS (2015) found that majority of perpetrators of violence for women were the current or former husband or partner. The NBSLEA (2012) found that majority of perpetrators of abuse for adolescents (78%) were boyfriends or romantic partners.

Specific Measurable Achievable Realistic Timebound

These indicators include: (1) Number of traditional, religious leaders and men putting in place and implementing protective measures that address negative practices such as child marriages and forced marriages; (2) Proportion of targeted  traditional and religious leaders and men who report increased knowledge of GBV; (3) Percentage of targeted women and girls who know where to seek support; and (4) Number of girls and young women aged 13-24 who experienced any form of violence/abuse prior to the age of 18 who received relevant support in line with the Protocol on the Multi-Sectoral Management of Sexual Abuse and Violence in Zimbabwe in the three target districts.

See, UNDG (2014) Guidance Note on Joint Programmes. https://undg.org/wp-content/uploads/2015/02/Guidance-Note-on-Joint-Programmes.pdf

UNDG (2015) Protocol on the Administrative Agent for Multi Donor Trust Funds, Joint Programmes, and One UN Funds.

Orange Day is a day set aside to advocate against GBV on the 25th of every month.

the JCT consortium comprised of ZWLA and WLSA.

See: Marimo, N. Ahikire, J. 2015. End of Programme Evaluation of the Uganda the UN Joint Programme for Gender Equality. Evaluation report prepared for UN Women

Marimo, N and Opio, D. 2016. End of Project Evaluation of the UNICEF and UN Women Joint Gender Peace Initiative Programme in Northern Uganda. Evaluation report prepared for UN Women and UNICEF; and

Marimo, N. and Nyirongo, G. Mid-Term Evaluation of the Joint UN Zambia Green Jobs Programme. Evaluation report prepared for ILO

See: Marimo, N. Ahikire, J. 2015. End of Programme Evaluation of the Uganda the UN Joint Programme for Gender Equality. Evaluation report prepared for UN Women.

Although to some extent the double counting can be set off by discounting the extent of overlap between the helpline beneficiaries and those of the drop in centre using Childline M&E data.

See Annex 4 for more details.

See Annex 5 for more details.

See Annex 5 for more details

Activities relate to conducting costing of the multi-sectoral protocol and subsequently engaging parliamentarians on the outcome of the costing exercise.

The plan was to complete rolling Anti-GBV committees in five districts by end of second year. Only three districts had anti-GBV structures established in the evaluation period.

Some UDACIZA members refuse to take the sick formal medical attention, engage in rampant child marriages.

See, Betts, J. eta al (2013) Joint Evaluation of Joint Programmes on Gender Equality in the United Nations System. https://www.unfpa.org/sites/default/files/admin-resource/JGP%20Evaluation%20Synthesis%20Report.pdf

Ronald, C. (2011) Costs and Benefits of Coordination of United Nations Operational Activities for Development. Paper presented at DESA conference. http://www.un.org/esa/coordination/pdf/final_report_2011.pdf

Output 1.2: Enhanced knowledge base of line Ministries and Parliament on budgeting and advocating for Implementation of the Protocol on the Multi-sectoral Management of Sexual Abuse and Violence in Zimbabwe.

Marimo, N. and Mbwanda, L. (2013) Evaluation of the Victim Friendly Initiative (1997-2012). A consultancy report prepared for Save the Children in Zimbabwe

The practice is when a girl child is given to an uncle for marriage at birth. The girl is officially married more often than not when she has just finished primary school. It’s a cultural tradition in Beitbridge.

There are discussions with UNFPA to take over the implementation of the Guidelines for clinical Management of Sexual Violence.

Zimstat (2012), National Baseline Survey on the Life Experiences of Adolescents.

Zimstat (2012), National Baseline Survey on the Life Experiences of Adolescents.

*approx, based on UN Operational Exchange Rate as of July 2013 and does not include 8% HQ Recovery Cost)

This age group is consistent with the national Girl’s Empowerment Framework.