# Final Evaluation of the Global Programme: Women’s Economic Empowerment and Integration into the Value Chain of the Coca-Cola Company in Brazil, Egypt and South Africa

Evaluation Report

| Prepared for: |  |  | UN Women, New York, USA |
| --- | --- | --- | --- |
| Prepared by: |  |  | Goss Gilroy Inc. Management Consultants Suite 900, 150 Metcalfe Street Ottawa, ON K2P 1P1 Tel: (613) 230-5577 Fax: (613) 235-9592 E-mail: ggi@ggi.ca |
| date: |  |  | January 27, 2017 |

Acronyms	i

Executive Summary	ii

1.	Background	1

1.1	Introduction	1

1.2	Purpose and Objective of the Evaluation	1

2.	Context and Programme Overview	2

3.	Approach and Methodology	6

3.1	Approach	6

3.2	Methodology	7

4.	Findings	9

4.1	Relevance	9

4.2	Effectiveness	13

4.3	Efficiency	25

4.4	Sustainability	31

4.5	Impact	36

5.	Lessons from the Programme	48

5.1	Overall	48

5.2	Country-specific	50

6.	Conclusions	55

7.	Recommendations	58

Annexes	61

Acronyms

CEBDS		-	Brazilian Business Council for Sustainable Development

CEO		-	Chief Executive Officer

DAC	-	Development Assistance Committee (of the Organization of the Economic

Cooperation and Development)

DSBD		-	Department of Small Business Development, South Africa

EDF		-	Enterprise Development Facilitator

EGP		-	Egyptian Pound

FG		-	Focus Group

GE		-	Gender Equality

HR		-	Human Rights

IBAM		-	InstitutoBrasiliero de Admistraaco Municipal

IBM		-	International Business Machines Corporation

ICCB		-	Instituto Coca-Cola Brasil

ILO		- 	International Labour Organization

KII		-	Key Informant Interview

MCO		-	Multi-country Office

MoLD		-	Ministry of Local Development, Egypt

MSME		-	Micro, Small, and Medium Enterprise

NGO		-	Non-government Organization

SC		-	Steering Committee

SDF		-	Social Fund Development, Egypt

SME		-	Small and Medium-sized Enterprise

TCCC		-	The Coca-Cola Company

TOR		-	Terms of Reference

UN		-	United Nations

UNDP		-	United Nations Development Programme

UN Women	-	UN Entity for Gender Equality and the Empowerment of Women

USD		-	United States Dollar

VSLA			Village Savings and Loans Association

WE		-	Women’s Empowerment

WEE		-	Women’s Economic Empowerment

WEF		-	World Economic Forum

WEPs		-	Women’s Empowerment Principles

WEPs-5&6	-	Women’s Empowerment Principles 5 and 6

WMN		-	Wahed Men El Nas, Egypt

ZAR		-	South African Rand

Executive Summary

The United Nations Entity for Gender Equality and the Empowerment of Women (UN Women) and the Coca-Cola Company (TCCC) have been engaged in a global partnership with a goal to increase women’s economic empowerment, especially those who are most excluded. The partnership reflecting UN Women’s strategic objectives and TCCC’s 5by20 initiative aimed to bring together TCCC’s resources, business expertise and market access with UN Women’s expertise in advancing women’s rights and enabling environments for women’s empowerment and gender equality at the country level, as well as from a global perspective.

Purpose, objectives and scope

The purpose of this evaluation was to assess the progress of the programme in achieving intended results, in addition to identifying valuable lessons and providing recommendations for future expansion and scale-up of the work on women’s economic empowerment. It assessed the relevance, effectiveness, efficiency, sustainability and impact of the programme. The evaluation covered the entire period of the programme implementation from November 2012 to December 2015 and assessed the global and country-level (Brazil, Egypt and South Africa) programme components.

Context

The programme came to an end in December 2015. The programme for each country was designed at the country level. Overall, tailored strategies were used by the programme in each country to best respond to specific challenges and opportunities for women’s economic empowerment in Brazil, Egypt and South Africa. The final independent evaluation was undertaken by an external evaluation team, as part of UN Women’s agreement with TCCC.

Approach and methodology

The evaluation team used a collaborative and participatory approach in conducting the evaluation. The evaluation adopted a transparent and inclusive approach to ensure a utilization-focused evaluation findings and recommendations. The evaluation used multiple methods to collect and assess evidence on the Development Assistance Cooperation (DAC) evaluation criteria. Both the qualitative and quantitative data were collected from primary and secondary sources. Key methods to collect data across the three countries and at corporate level included: review of documents (>75), key informant interviews (60), focus group discussions (21 with 194 participant), site visits (18) and observations. Data collected was triangulated with various stakeholders and secondary data sources, as applicable.

Key findings and lessons learned

Key findings and lessons included:

Relevance

- The programme was designed with a goal to increase women’s economic empowerment, focusing specifically on those who are most excluded. Given the economic, cultural and political contexts in the three countries (Brazil, Egypt and South Africa), the programme was highly relevant. Overall, the programme design, be it training on business and entrepreneurial skills (all the three countries), asset transfer (Egypt) employability (Brazil), and promotion and implementation of Women’s Empowerment Principles (WEPs), specially principles 5 and 6 – WEPs-5&6, (Brazil), was appropriate to reach the intended objectives set out for each country; this included training materials, tools, and the business models (including advocacy and technical assistance in case of WEPs-5&6).  The programme was not only aligned to but also contributed to the corporate level and country level objectives of UN Women and TCCC and the 5by20 initiative, with reference to women’s economic empowerment.

Effectiveness

Women Trained

Brazil		- 21,500

Egypt		-   4,170

South Africa	- 18,033

The programme implementation arrangements, effective partnerships, and programme management were effective to achieve the targets set for each country. The programme reached a total of 42,703 women (target – 37068 women) including entrepreneurs, recyclers and young women entering the job market. Strong local partners and good coordination were crucial to implement the business model chosen in each country, whether it was through one “main” partner (as in Brazil and South Africa) or four different partners (as in Egypt).

- Partnership (UN Women-TCCC) worked well when there was a common understanding and a shared goal, with mutual trust, transparency and joint ownership of both “good and bad”, as seen from the working of the Steering Committee, and the teams in Brazil and South Africa.

- Programme management structures and joint planning and decision-making contributed to effective partnership in Brazil and South Africa. Senior management commitment was also crucial in the countries for the UN Women–TCCC partnership. Furthermore, “joint messaging” from Steering Committee to the countries and within the country in South Africa (by the country team) was an important element for effective programming to achieve the stated objectives.

- Overall, most of the programme’s direct actions including delivery of training and development of training materials and tools have proved to be effective in all the three countries, irrespective of the model and approach. The promotion of WEPs has been more effective in Brazil than in the other two countries. This was also because the promotion of WEPs was a primary focus for the Brazil team as part of their intended objective; however, it was too early for the evaluation to assess outcomes and/or the extent of implementation of WEPs (specifically principles 5 and 6) by the signatory companies in Brazil.

Efficiency

- In spite of large start-up delays in Brazil (18 months) and Egypt (28 months), all three countries were able to complete the programme activities on time (with a three-month no cost extension). The programme was implemented within the budget. The unutilized funds from Brazil were allocated to South Africa to continue to the programme for additional six-months. The ability of the programme to leverage additional resources and in-kind contributions in the countries added value.

- The programme reflected high efficiency in terms of rate of people trained per day during the implementation period and also the cost at which they were trained, compared to many similar development sector programmes.

Sustainability

- There has been high level of support, ownership and leadership commitment at the national level from private sector companies and business organizations in Brazil and the Government in South Africa. The Government in Egypt has also shown support to the programme. The programmes have also attracted support and ownership from national partners and local organizations in all three countries during the time of the programme.

- The models in each country have proved to be unique and successful in their respective contexts. The models are scalable and replicable in varying degrees, in an appropriate context. The South Africa model is likely to be the easiest model to scale-up and/or replicate in many countries/contexts in private-public partnerships (compared to the models of other two countries), in reaching and training women entrepreneurs for women’s economic empowerment.  The Egypt model is replicable if a strong micro-credit partner could be identified or the programme includes a considerable portion of its budget for purchase and distribution of assets (asset transfer). The Coletivos component in Brazil is likely to continue in Brazil, as it was already an on-going initiative through the support from TCCC/ICCB, even before UN Women-TCCC programme.  The WEPs component of the Brazil programme is replicable by UN Women through its own resources or in partnership with private and public companies.

- The programme has been able to transfer knowledge and build capacities at various levels starting from women and communities to trainers and organizations. There is institutionalization and increased knowledge in all three countries in terms of WEPs among all partners, including TCCC and UN Women.

Impact

- The empowerment of women through capacity development was at the core of the UN Women-TCCC programme, reaching women across three countries. The contribution of the programme through capacity building was evident from women using the skills learned in establishing and sustaining their micro-business, applying for employment and/or managing the cooperative.

- Women entrepreneurs have increased access to networking and business supports in some ways; most commonly through the formation of informal small groups of people who attended training (still in early stages).  Events organized in the countries by the programme and interests shown by local government and private companies have been other instances where women entrepreneurs have been able to access and/or access business support.

- The programme has increased economic opportunities and access to livelihoods for poor and excluded women in the three countries, with better success in South Africa and Egypt compared to Brazil. This was seen from increased income, better financial management, expansion of business and better ability to meet basic needs. An indirect benefit to women who attended the training was their increased confidence and self-esteem.

- While Egypt and South Africa increased awareness on gender equality and women’s economic rights among women entrepreneurs trained and through public events, it is not very evident how much the programme contributed to the increased awareness in the communities. However, the success of this programme has evoked interest among few private sector companies in South Africa. On the other hand Brazil has been very successful in promoting and creating awareness in the larger community and among the private sector companies including documented changes.

Conclusions

The programme has proved to be a good example and a success story of public-private partnerships, in contributing to women’s economic empowerment. The intent to test out various models in different countries has also generated a lot of learning for both organizations for future programming and partnerships. Trust, transparency and investing time to understand each other were key factors in the partnership and successful implementation. Overall, it was a good investment with positive results.

Recommendations

The following recommendations are based on the findings and conclusions presented in the report. The recommendations are focused towards future programming and partnerships on women’s economic empowerment.

Recommendation 1: UN Women should ensure the following in its future programming:

- Developing an exit strategy, irrespective of whether the programme is going for a next phase, a scale-up or a closure; and executing it as part of the programme before the end of the programme and/or its current phase.

- Having a well-defined monitoring system in place right from the beginning of the programme. Thoughtful planning, beyond baseline/endline or training satisfaction surveys should be put into developing the systems. This should include: data collection schedule; mechanisms and tools during the programme; and, data collection to capture outcome results in addition to output indicators.

- Allowing sufficient time for “front-end planning” especially when partnering with organizations with different organizational culture and/or from entirely different sectors. This is a lesson for TCCC at country level also.

- Ensuring that there is an opportunity for cross-country exchange of information and learning in Global Programmes, specifically when it is on women’s economic empowerment. These could be virtual meetings once or twice a year (if budget is a constraint).

Recommendation 2: UN Women should replicate (adopt/adapt) the programme governance and management structures and practices while working with private sector companies and other “donors” on a Global Programme. However, UN Women is likely to require a dedicated person to manage and coordinate at headquarters level and with countries if it is a large programme implemented in several countries.

- Continue the practice of having a committed small global steering committee at the corporate level with a two-tier structure at the country level – a country steering committee and a project management committee with regular productive meetings; this has proved to cement the partnership and implement the programme effectively.

- This programme was considered a pilot and implemented only in three countries. Therefore the Global Steering Committee was able to provide oversight and also provide direct inputs to countries, when required. However, this (direct inputs) may not always be possible when the programme is large and implemented in several countries. Even within UN Women, coordination is required for the programme among divisions (Programme, Strategic Partnerships and Communication, etc.). Hence UN Women should consider having dedicated personnel to coordinate private sector partnership programmes. Preferably this person should not be coordinating “other donor” programmes.

- With increasing efforts of UN Women to collaborate with the private sector, the UN Women Programme Division should create a specialized unit or a section to manage all the private sector partnership programmes. The dedicated person suggested in the earlier recommendation can be part of this programme unit. This will help UN Women to manage these programmes more effectively and efficiently with appropriate focused monitoring and reporting.

Recommendation 3: UN Women should strive to leverage its comparative advantage and technical expertise on WEE by partnering with organizations that bring business expertise and provide economic opportunities for women in their value chain. At the same time, UN Women should keep in mind that private sector companies bring unique strengths to development projects, especially their communication and outreach capabilities, in addition to their business expertise. These capabilities could increase UN Women programmes visibility and outreach, and broaden its impact.

- UN Women should identify more private sector companies that can support it in achieving its development agenda and goals, and with business opportunities that are relevant to target communities.

- At the same time UN Women should look at opportunities to partner with private sector companies and  add value their programmes that address women’s economic empowerment at the grassroots (as in 5by20 initiative).

Recommendations 4: UN Women and TCCC should explore opportunities to continue partnership.

- Within the 5by20 initiative, replicating/scaling up the simpler South Africa model would be more feasible in many contexts. It  has been more successful in the retail segment in  building capacities of women entrepreneurs to establish and sustain their business (among the three countries);

- At a more corporate level, explore how both partners can add value to each other’s overall strategic objectives, in terms of women’s economic empowerment (building on the lessons and synergies from this programme).

Recommendation 5: UN Women should keep in mind that while partnering with private sector companies, finding the balance between “development objectives” and “business objectives” is crucial for a successful and long-term mutually beneficial partnership. This requires a frank and open communication and building trust.

- Based on experience and lessons from the programme, it is important to consider the private sector as a strategic partner and not as a “donor’. It is important to capitalize on and add value to each other’s strengths; and,

- Focusing on optimizing the entry point and partnership with the private sector through engagement on levels that can benefit both partners. This may vary country to country, when trying to design/implement a global programme.

1.	Background

## 1.1	Introduction

The United Nations Entity for Gender Equality and the Empowerment of Women (UN Women) and the Coca-Cola Company (TCCC) have been engaged in a global partnership with a goal to increase women’s economic empowerment, especially those who are most excluded. The partnership, reflecting the goals of UN Women’s Strategic Plan 2011-2013 and TCCC’s global 5by20 Initiative, was envisaged to build on the strengths of each organization with a focus on developing innovative business models for women’s entrepreneurship and social leadership to advance women’s economic empowerment.

The collaboration aimed to bring together TCCC’s resources, business expertise and market access with UN Women’s expertise in advancing women’s rights and enabling environments for women’s empowerment and gender equality at the country level, as well as from a global perspective.

The Global Programme Women’s Economic Empowerment (WEE) and Integration into the Value Chain of TCCC in Brazil, Egypt and South Africa, was launched in November 2012, as a part of the partnership. With the programme coming to an end in December 2015, UN Women planned to conduct an independent evaluation as envisaged in the programme and as part of an agreement with TCCC.

## 1.2	Purpose and Objective of the Evaluation

As stated in the programme document and in the agreement with TCCC, this final independent evaluation was undertaken by an external evaluation team.  The purpose of this evaluation was to assess the progress of the programme in achieving intended results, in addition to identifying valuable lessons and providing recommendations for future expansion and scale-up of the work on women’s economic empowerment. The evaluation was expected to review the programme design, implementation arrangements and achievement of results to assess the improvements in the three participating countries – Brazil, Egypt and South Africa.

Overall, the evaluation aimed to:

- Analyze programme outcomes and assess effectiveness of the approach and strategies used by the programme countries to increase women’s economic empowerment;

- Examine programme results in relation to the intended outcomes and outputs as well as unintended results (positive or negative) and identify the strengths and weaknesses in programme design and implementation to scale-up the lessons learned and improve future programming on women’s economic empowerment;

- Examine critical factors that enable or hinder effective achievement of intended results.

- Draw key lessons on the role of partnerships and multi-stakeholder mechanisms in the achievement of planned outputs and outcomes;

- Provide recommendations on how to address the critical factors that hinder effective achievement of intended results;

- Document lessons learned and best practices and provide recommendations to inform future work on women’s economic empowerment;

- Assess institutional capacity and potential for sustainability of the on-going work in programme countries; and,

- Assess implementation models and managerial structures created for the partnership.

The evaluation documented history and learning of the partnership as a whole and on-the-ground including some of the relevant anecdotes from women who have participated in the various training programs.  The evaluation also strived to capture key learnings and insights that may be shared: a) externally to share the learning from successful models for women’s economic empowerment that have been implemented and may be scaled-up; and, b) internally to continue to inform TCCC and UN Women programme partnership and implementation.

Evaluation Coverage and Scope

The main audience for this evaluation are expected to be the senior management of UN Women, TCCC, the programme coordinators and the national partners. The evaluation covered the entire period of the programme implementation from November 2012 to December 2015 and assessed the global and country-level programme components.

2.	Context and Programme Overview

Globally, WEE has been identified as a stand-alone objective that is critical not only for gender equality but also for overall development and poverty reduction. Improving the economic status of women can lead to better outcomes at the individual, family and community levels and has ripple effects across society. The Fourth World Conference on Women in Beijing in 1995 provided important momentum in efforts to advance WEE through the Beijing Platform for Action. Commitments to promote women’s economic rights and independence were made and these included, “access to employment, appropriate working conditions and control over economic resources” and efforts to “facilitate women’s equal access to resources, employment, markets and trade.”

UN Women was established in 2011 by UN General Assembly (GA) resolution 64/289 to assist Member States and the UN system in progressing more efficiently and effectively towards the goal of achieving gender equality and the empowerment of women (GEEW).

At the same time TCCC was also focusing on the development of women inside and outside the organization and had created a Women’s Leadership Council, internally. As part of this intent and as a public commitment, TCCC launched the 5by20 initiative in 2010. The 5by20 initiative aims to expand economic opportunity for five million women entrepreneurs across the Company’s global value chain by the year 2020 through a combination of core business operations, cross-sector partnership, and strategic social investment.

It was in this context that TCCC and UN Women started discussions which led to the partnership and development of the Global Programme – Women’s Economic Empowerment (WEE) and Integration into the Value Chain of TCCC in three countries – Brazil, Egypt and South Africa. The countries were selected, taking into account various aspects including being a 5by20 country, UN Women priority, and the ability of teams (from both sides) to come together on the ground and produce results. Additionally, Brazil and South Africa were among the first four countries of the 5by20 initiative, when it was launched in 2010.  Among other reasons, Egypt was selected as it would also be an opportunity to create a model to work in a difficult environment. Egypt, in the Middle-east region, was coming out of a political crisis situation; that had an impact on the socio-economic situation in the country. All the three countries selected are middle-income countries.

The overall goal of the programme was to increase women’s economic empowerment through the development and implementation of sustainable models. Ultimately, the aim was to use these models to scale-up and/or replicate to other private and public companies, Government and non-governmental organizations (NGOs) within the participating countries and possibly adapt to other countries. Tailored strategies were used to best respond to specific challenges and opportunities for women’s economic empowerment in Brazil, Egypt and South Africa.

Depending on the local requirements programme implementation strategies involved some or all of the following:

- Enhancing women’s entrepreneurial capacity and skills so that they have greater ability to establish and grow their business, increase their earnings, create new jobs in their communities so they can better manage and sustain their business;

- Supporting excluded women to establish small businesses by providing access to assets and credits;

- Supporting recyclers to enhance the organizational development of recycling cooperatives and increase their earnings;

- Fostering awareness regarding human rights and gender equality among programme beneficiaries;

- Advocacy and awareness creation for the adoption of gender sensitive procurement policy and capacity development of private and public companies to implement gender equality commitments and WEPs in their system wide operations, networks and supply chain; and,

- Raising awareness and advocate for women’s economic rights and the value of women’s economic participation both at the community and national levels.

The programme was implemented for a period of three years (November 2012 – December 2015) with a total budget of USD 3,974,355.  The actual launch was in early 2013. The programme goal and outcomes for each participating country is presented as a snapshot in Table 1.

Table 1:  Programme Goal and Participating Country Outcomes - Snapshot

| Programme Goal | Increased women’s economic empowerment through sustainable models |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Brazil |  | Egypt | South Africa |  |
| Country Outcomes | 1. Low-income women entrepreneurs (community leaders and artisans) have increased access to economic opportunities and resources to manage and sustain their businesses | 2. Increased commitment and implementation of affirmative procurement policies and other policies promoting WEE in private and public sector companies. | 1. Women have increased economic opportunities and access to livelihoods, especially those who are poor and most excluded. | 1. Sustainable business ventures enhance the livelihoods of low-income women entrepreneurs | 2. Low-income women entrepreneurs have increased networking access and business support mechanisms. |
| Country Outputs | 1.1. Ability of women community leaders and artisans is strengthened to create, legalize and/or manage their businesses more efficiently. 1.2. Capacity of women entrepreneurs from Manaus is strengthened to have increased access to relevant credit services. 1.3. Knowledge of women community leaders and artisans about gender equality and civic rights enhanced. 1.4. Entrepreneurial skills of community peers of women community leaders and artisans enhanced. | 2.1. A model for affirmative procurement policies targeting women-owned and women-majority businesses is demonstrated. 2.2. Capacity of Brazilian government and private sector institutions to formulate affirmative procurement policies and other policies promoting WEE strengthened. | 1.1. Women entrepreneurs in target communities have increased capacity and skills to establish and sustain their own kiosks and tricycle stores. 1.2. Women have access to assets, resources and products to establish their own businesses. 1.3. Local communities have increased awareness of women’s economic rights and the benefits of women’s economic participation. | 1.1. Financial literacy and business management skills of local women entrepreneurs strengthened to establish sustainable business ventures | 2.1. Business network opportunities provided for low-income women entrepreneurs. 2.2.Knowledge-sharing platform promoting horizontal and vertical learning established 2.3. Partnerships and links established between women entrepreneurs and organizations providing business support services and programmes, including financial services. |

Source: Compiled from Project Document (dated November 5, 2012) and Annual Progress Report of 2015

The programme for each country was designed at the country level jointly with TCCC counterparts. The strategies were developed to implement the programme to achieve results at the country level, within the overall mandate. The following paragraphs provide a quick summary of the program in each country.

- The programme in Brazil aimed to increase low-income women’s access to economic empowerment and opportunities; thereby extending the benefits to their communities and families. The implementation strategy was focused on Coletivo Coca-Cola, a shared value platform of the Instituto Coca-Cola Brazil (ICCB), to incorporate gender equality and human rights perspectives in order to improve women’s connections to the company’s value chain. The programme focussed on three Coletivos, namely, Recycling, Entrepreneurship, and Retail, for the implementation. For each Coletivo, a specific set of activities were designed and carried out. The programme also had a second pillar that intended to promote and implement the Women’s Empowerment Principles (WEPs), with special focus on principle 5 – related to supporting women entrepreneurs and creating opportunities within companies` value chain; and principle 6 -related to the promotion of women`s empowerment and gender equality at community level (WEP5&6). The programme was implemented in 25 states in Brazil. Key partners in Brazil included Instituto Brasileiro de Administração Municipal (IBAM), Plano B, Cicla, and Ipsos.

- The main focus of the programme in Egypt has been on women’s integration into the value chain through implementation in the three Safe Cities communities in Cairo (Ezbet El Hagana, Imbaba and Mansheyat Nasser) as well as five governorates in Upper Egypt, namely, Minya, Beni Suef, Assiut, Sohag and Fayoum. Key partners included: Social Fund for Development (SFD), Wahed Men El Nas (WMN) and NGOs supporting the implementation of the UN Women Safe Cities programme in Egypt.

- The programme in South Africa aimed to empower women entrepreneurs and support them in addressing the barriers related to developing, growing and sustaining their businesses. In order to achieve this goal, the programme applied different strategies that include, but are not limited to, training, mentoring and networking. The first year of the programme focused its intervention in two provinces (Gauteng and Northwest Provinces). In the second year, the programme expanded its geographical outreach by adding two other provinces (Mpumalanga and Eastern Cape). In the third year, it further expanded outreach in two more provinces (Kwazulu-Natal and Western Cape Province). Key partners included government (Department of Small Business Development - DSBD), bottling companies of TCCC. Hand in Hand Southern Africa, New World Project and local level stakeholders (municipalities, churches, community-based organizations, etc.).

3.	Approach and Methodology

## 3.1	Approach

The evaluation used a collaborative and participatory approach in conducting the evaluation. The evaluation adopted a transparent and inclusive approach to ensure a utilization-focussed evaluation findings and recommendations. The evaluation is equity-focussed and results are outcome-oriented. The evaluation has been grounded on gender and human rights principles, as per UN Women Evaluation Policy.  The evaluation team has adhered to the UN norms and standards in conducting and reporting the evaluation.

The evaluation analyzed programme outcomes and assessed the effectiveness of the process and strategies used by the programme countries to increase women’s economic empowerment. It also examined programme results in relation to the intended outcomes and outputs and identified the strengths and weaknesses in programme design and implementations, to scale-up the lessons learned and improve future programming on women’s economic empowerment.

Furthermore, the evaluation examined critical factors that enable or hinder effective achievement of intended results and draw key lessons on the role of partnerships and multi-stakeholder mechanisms in the achievement of planned outputs and outcomes. The evaluation assessed institutional capacity and potential for sustainability of the on-going work in programme countries. Additionally the evaluation also looked at the implementation models and the management structures created for the programme.

As part of the evaluation approach, a detailed evaluation matrix was developed. The evaluation matrix presented evaluation criteria and questions with indicators and means of verification. It was further refined with inputs from UN Women – headquarters and the country offices.

## 3.2	Methodology

The evaluation team used a mixed-method approach, as a best practice, to collect data. The use of a mixed-method approach helped to triangulate the evidence gathered and analyzed. Triangulation helped to strengthen evaluative conclusions.  The following methods were used to collect data and evidence.

- Desk review of documents and secondary data – A comprehensive document/desk review was undertaken in two stages – a) during the inception phase the key programme document were reviewed; and b) during the data collection phase. The review included programme/project documents including budgets, annual progress reports, and results framework, training reports, secondary data, national documents and literature, among others.  In addition to corporate documents, the team also collected and reviewed documents from the three countries to identify information to address the evaluation criteria - relevance, efficiency, effectiveness, sustainability and impact, in addition to lessons learned. Furthermore, the team also looked at the monitoring data/system in each country, as applicable. This included baseline and other relevant project data. The list of (more than 75) documents/videos reviewed is presented in Annex A.

- Key informant interviews (KIIs) – Interviews (individual and group) and consultations were carried out as per finalized protocols adapted to specific categories of stakeholders (Table 2) and aligned with evaluation framework. Interviews were semi-structured and conducted in person (in the countries during country missions) and through Skype/telephone with corporate level managers. The interviews helped to gather diverse insights and perspectives on various aspects of the programme including relevance, efficiency, effectiveness, impact and sustainability. Furthermore, insights into aspects of women’s economic empowerment and country-specific lessons learned, issues and challenges were also gathered to help in future programming, during the interviews. List of stakeholders interviewed is presented in Annex B.

Table 2: Categories of Stakeholders Interviewed

| Categories of Stakeholders | Global | In-country |
| --- | --- | --- |
| The Coca-Cola Company | 3 | 11 |
| UN Women | 4 | 12 |
| CSO/NGO/Local | - | 18‡ |
| Government | - | 5 |
| Others† | - | 7 |
| Total | 7 | 53 |

† Others include individual interviews with entrepreneurs at the site of their business

‡ Group interviews/focus groups discussions of NGO representatives and private sector managers in Brazil has been included under focus groups

- Focus groups – During the one-week country missions to Brazil, Egypt and South Africa, focus group discussions were conducted with women entrepreneurs at project sites, in addition to NGO representatives and private sector managers. Appreciative inquiry techniques were used, as applicable. This helped to understand relevance, effectiveness, sustainability and impact of the programme on the ground, from the perspective of the women. It also helped to recognize challenges and issues, if any, from the perspective of the entrepreneurs. The summary of focus group discussion is provided in Table 3.

- Observations – Semi-structured observations were carried out to note possible pre-post changes in activities, behaviours, practices and systems during visits to project sites in the three countries. During the country missions women entrepreneurs were observed at their business sites.

Table 3: Focus Group and Site Visit Summary

|  | Brazil | Egypt | South Africa |
| --- | --- | --- | --- |
| Key informant interviews (KIIs) | 12 | 13 | 27 |
| Focus Group (FG) locations | 15 (See below) | 3 (Mansheyet, Nasser and Fayoum) | 3 (Khayelitsha, Mantusulu, Kagiso) |
| FG participants (#) | 123‡ | 27 | 44 |
| Site visits | Oswaldo Cruz, Coopama, Campinho, Tubiacanga, Jardim Marista, Nova Esperanca, Beija Flore, Cocamare Brasilandia, (spread across 3 States) | Mansheyet, Nasser and Fayoum | Khayelitsha, Mantusulu, Kagiso, Vosloorus (spread across 3 provinces) |

‡ Includes group interviews of NGO representatives (25) and private sector managers (4) in Brazil

Limitations include:

- The main challenge was the availability of the stakeholders for interviews and discussions, within the timeframe of one-week country mission. This was largely overcome with close planning along with country teams (which included several meetings during the lead time before the mission) and the efficient logistics support by country teams. Alternates were found when the main contact was not available in the country teams. The evaluation team was also flexible in their time to meet with stakeholders.

- Programme monitoring system, mostly reflected output data. The evaluation used data collected by Ipsos in South Africa and in Brazil to complement qualitative findings from discussion during the evaluation. In Brazil the system already existed prior to the programme (which proved advantageous to the programme).

4.	Findings

The evaluation findings presented in this section are based on information gathered through the review of documents, interviews with key stakeholders, discussions with entrepreneurs and observations during field visits in the countries. The findings are organized according the Development Assistance Committee (DAC) evaluation criteria – relevance, effectiveness, efficiency, sustainability and impact.

## 4.1	Relevance

Q1. Were the programmatic approaches and strategies appropriate to address the problem and to achieve planned results?

In order to assess the relevance of the programme, the evaluation examined if the programme’s approaches and strategies were appropriate to address the problem and to achieve planned results. It also looked at whether the programme design was appropriate for the cultural, political and economic context in the three countries, in addition to alignment to UN Women and TCCC objectives.

Appropriateness and relevance of programme objectives set for the programme in the countries and alignment to UN Women and TCCC Goals

The overall programme goal of increasing women’s economic empowerment (WEE), and its objective for women to have increased opportunities and access to livelihoods, are aligned with both the UN Women’s strategic plans, and TCCC’s goals. Women’s economic empowerment in rural and poor areas is one of the strategic impact areas of the UN Women’s Strategic Plans 2011-2013, and 2014-2017. Similarly, the programme’s goal and objectives are consistent with TCCC’s global 5by20 initiative, which aims at enabling the economic empowerment of five million women across the company’s value chain by 2020.

Even though the programme was envisaged during the UN Women’s Strategic Plan 2011-2013, it is still relevant and appropriate to the current Strategic Plan 2014-2017 – contributing to Impact 2 “: “Women especially the poorest and most excluded, are economically empowered and benefit from development”. Furthermore, the corporate evaluation on UN Women’s contribution to WEE, noted that WEE provides an important entry point for addressing all areas of UN Women works, including recovery, leadership and HIV/AIDS.

In all the three countries, the programme was not only aligned but also contributing to the UN Women’s Strategic Notes and Annual Work Plans as well as the United Nations Development Assistance Frameworks (UNDAFs) of Brazil, Egypt and South Africa. Furthermore, it was also found to add value to ongoing programmes, and national priorities. For example:

- In South Africa, the programme was aligned and contributing to one of the four focus areas – “inclusive growth and decent work” – of the South Africa-UN Strategic Cooperation Framework 2013-2017; and,

- Implementing the WEPs in Brazil was also part of the global strategy of UN Women and hence a component of the UN Women-TCCC programme.

Additionally, at the country level the programme was also contributing to TCCC’s 5by20 initiative objectives and targets in Brazil, Egypt and South Africa.

Appropriateness of the programme design to reach intended outcomes

The programme was focussed on addressing the needs of the vulnerable populations, specifically women entrepreneurs managing micro-businesses.  The evaluation examined if the programme design was appropriate to reach the intended outcomes in the three countries. Based on discussions globally and in the countries, it could be said that the approaches and strategies adopted by the programme were relevant to achieve the planned results.

Overall, the quality of the training content, the pedagogy adopted and trainers/educators used were reported and observed to be of very high relevance. The training content was similar yet different and it was adapted to each country. For example:

- In Brazil, Instituto Coca-Cola Brasil (ICCB) incorporated human rights, gender equality and women’s empowerment contents into its training material;

- In Egypt, the ILO’s training material (i.e. GET Ahead for Women in Enterprise Training Package) was simplified to reach the targeted audience; and,

- In South Africa, the TCCC training material along with Hand in Hand material were adapted and simplified and made more “community-friendly” – for example using pictures, simplified “business jargons,” and local examples that trainees could relate to and understand.

While all countries strived to achieve women’s economic empowerment, each country had its own set of unique programme components to reach the intended outcomes:

- Brazil – Training for women entrepreneurs, recycling cooperatives and youth (on entrepreneurship for Coletivo Entrepreneurship, on cooperative management for Coletivo Recycling and on employability in Coletivo Retail) and WEPs promotion and technical assistance for its implementation to private and public sector companies;

- Egypt – Training for women entrepreneurs, complemented by asset transfer; and,

- South Africa- Training for women entrepreneurs.

As part of the strategy, South Africa and Brazil included men in their training program, as community gate keepers and/or to be considered inclusive. However, these modifications came subsequently in the programme. Egypt did not target men, although it was reported that there were instances where men accompanied women and attended the training.

From discussions, it was noted that situation (context) analysis was carried out as part of designing the programme in all three countries. Although some stakeholders may report that a needs assessment was not done. For example in Egypt, although the strategies were deemed appropriate, evidence was not sought on the actual needs of women in the target communities. Hence, there were some doubts about “retail” as an appropriate entry point for women in the TCCC value chain, where other options like recycling could have been considered. Doubts about the appropriateness of “refrigerators” as an asset were also raised.

Overall, strategies that address the economic inequality of women, including capacity building and asset transfers, were acknowledged as effective strategies to empower women economically. In Brazil, the strategies for supporting recycling cooperatives contributed to strengthening the organizations.

Future programming, at the design stage, should consider the development of an exit strategy and plans to execute it.

Appropriateness of the programme design for the cultural, political and economic context in the countries

Overall, the programme design and strategies were found to be appropriate for the respective countries. Interviews and discussions carried out in the three countries and the review of documents revealed that the programming was appropriate to the respective cultural, political and economic context of the countries.

Although Brazil, Egypt and South Africa are middle-income countries, there are gender and income inequalities, as seen from Table 4.

Table 4: Global Indicators for the Countries

| Country | Brazil | Egypt | South Africa |
| --- | --- | --- | --- |
| Human Development Index Rank (2014) | 75 | 108 | 116 |
| Gender Inequality Index (2014) | 0.457 | 0.573 | 0.407 |
| Gini-coefficient | 52.7 | 30.8 | 65.0 |

Source: Human Development Report – UNDP (2015)

The overall unemployment rate in Brazil is 11.8 percent (approximately 12 million people); however it is 33.6 percent among women. Young people are also affected by unemployment (24 percent for those between the ages of 18 to 24).. The recyclers are among some of the most socially vulnerable groups in the country. Almost all of them find this activity to be the only possible or feasible means to earn a living to meet their immediate survival needs, given the constraints they face in the job market. Profitability in this market has been very unpredictable, as it is   directly linked to the market value of the materials and the availability of supply of solid waste. They work in one of the most unhygienic professions and any support to improve their working conditions is relevant. In 2010, after several years of discussions, the National Policy of Solid Waste was approved in Brazil, which stated that the recycling cooperatives will be responsible for recycling in the cities and the private sector companies must support them financially. Due to this critical role played by cooperatives, it was important to strengthen their organizational capacities to increase future opportunities for women recyclers to leverage funding from the private sector.

The 2015 Global Gender Gap Index, which measures disparities between men and women across countries, ranks Egypt at 136 out of 145 countries worldwide. According to this report, women have significantly lower participation in the labor force than men (26% vs 79%). Similarly, the unemployment rate among women was (24%); more than double that of men (9.1%).

In South Africa, the programme design was very appropriate and relevant to the socio-economic context. As stated, the programme was designed after conducting a situation analysis. The unemployment rate for women (27.7%) was higher than the unemployment rate for men (23.1%).

The documentation and discussions held throughout this evaluation confirmed the programme’s appropriateness for each of the countries’ respective economic, political and cultural contexts.

Some interesting perceptions noted, included:

- In Brazil, in some cases, the human rights, gender equality and women’s empowerment content did not seem to connect with people who lived in challenging environments. Specifically, for the members of the recycling cooperatives who live in harsh social environment, discussions on these issues were not directly related to their immediate survival needs (although the issues may be relevant); and,

- Some divergent views were noted about the micro-credit made available to vulnerable women in Egypt and whether retail was a better option vis-à-vis recycling or artisan work within the TCCC value chain. However, there was no strong business case evident to prove other-wise.

The continued demand in South Africa from entrepreneurs and the interest by the Department of Small Business Development (DSBD) in the “UN Women-TCCC programme trained women entrepreneurs” to help them under the DSBD initiatives reinforces the appropriateness of the programme’s design to achieve intended outcomes.

## 4.2	Effectiveness

Q2. To what extent has the programme been successful in achieving the intended outcomes and results? What has been achieved?

As part of assessing the effectiveness of the programme, the evaluation examined the implementation arrangements, partnerships developed, monitoring of the performance and results by the programme management at various levels and direct actions taken by the programme (including conducting training and development of tools, etc.).

In order to get a better perspective on the implementation arrangement, partnerships and monitoring of results were assessed at the global and country level.

Effective partnership development

The evaluation looked at how effective the partnership development was in the countries, specifically with national partners and TCCC, to deliver programme results.  It also looked at existing gaps, if any and why they existed.

At the corporate level, the partnership between TCCC and UN Women, although it was announced in September 2011,  took several frank and open discussions to envisage on how the programme would work. It is important to keep in mind that these are two organizations with different organizational cultures and business processes from entirely different sectors.

The effectiveness of this partnership should be seen from the context that the partnership was established at a time when UN Women was in its initial years, after its creation as a new entity, through a merger of several UN entities. UN Women was beginning to carve a niche identity within the UN system and globally, with its mandate on gender equity and empowerment of women. While UN Women was also focusing to collaborate with the the private sector; it had never partnered with a private sector for programme implementation, at the time of this programme conception.  At the same time TCCC was a mature and much larger organization with a globally well-known brand. It was noted that while TCCC had experience working with other UN agencies, the 5by20 team had largely collaborated with NGOs. So one of the first steps in this partnership was to take the time to understand each other - “where each one came from”; and “what each one meant by empowerment of women”. There was a strong commitment at the top level from both organizations to make the partnership and the programme work. It was seen as an innovative public-private partnership programme by most stakeholders met during the evaluation.

At the global and corporate level, the UN Women and TCCC partnership has been working together to reach out to key stakeholders with critical roles to play in the economic empowerment of women to create a sustainable impact.  The partnership facilitated UN Women’s engagement in the World Economic Forum (WEF)’s Annual Meeting in Davos in 2015 and the Africa Regional Meeting in Cape Town.  TCCC continues to be a member and participate in UN Women’s Private Sector Leadership Advisory Council, launched in June 2014. Additionally TCCC’s digital global team provides advice and guidance to the UN Women global online platform for WEE (EmpowerWomen.org) and its social media strategy. It was noted that TCCC has been featured as one of the key partners on the platform. Furthermore, it was noted that TCCC joined as a partner, in 2016,   to develop a global diagnostic tool to support companies in the implementation of WEPs.

Unlike a typical “traditional donor relationship” model, UN Women–TCCC was a strategic partnership, in spite of TCCC being the “funding agency” for the programme.  The partnership at the corporate level (in the Steering Committee) was grounded in trust, transparency and common shared goals with joint messaging. There was mutual learning for both organizations.

The partnership between UN Women and TCCC in Brazil took its time but worked well in terms of designing and implementing the programme. During interviews with UN Women, TCCC and ICCB teams, separately, each one of them reported that the three organizations made decisions together (joint decision-making) in all matters of the programme. The partnerships established with different stakeholders for both the Coletivos and WEPs components were quite strategic. The programme also benefitted from the existing local partnership of NGOs, Coletivos and recycling cooperatives through the ICCB’s ongoing initiative, in addition to the partnership between public and private companies that were already WEPs signatory and Federal Government Gender and Race Pro Equity Program. The partnership with IBAM helped the programme in getting technical support to develop training curricula based on gender equality and human rights principles. Plano B and Cicla are two other organizations involved at the Coletivo level to develop training methodology incorporating gender equality and human rights concepts and developing pre-post assessment tools incorporating gender equality and human rights content.

A highlight in the Brazil programme was the partnership with the Brazilian Business Council for Sustainable Development (CEBDS) and the informal network of companies that have recently signed the WEPs (specifically principles 5 and 6), along with the other companies that were already signatories of the WEPs.

In Egypt, the UN Women-TCCC partnership managed to come together at the time of implementation to carry out the various components envisaged in the programme. The evolving of the “partnership“ in Egypt had some challenges, largely due to the fact that  both teams seemed to have had diverging views regarding many milestones. Although the relationship was collaborative, the evaluation noted from the discussions that each partner may have had different expectations from this partnership.  As noted during discussion, this misalignment of expectations may also be attributed to the diverging approaches of both partners; UN Women’s approach was more focused on developmental results and advocacy, while TCCC’s approach may have been more “business oriented”.  During the discussions in Egypt, it was noted that TCCC Egypt played a major role in joint decision-making about major programme milestones with UN Women Egypt; this was also essential to move the programme forward, specifically because of the turnover in UN Women Egypt. Constant turnover of senior management also partially contributed to the slow development of the partnership including miscommunications and differences in expectations.

UN Women-TCCC programme also forged other partnerships which were complementary; and, added value to the success of the programme in Egypt. This included:

- The partnership with SFD, a quasi-governmental organization providing loans to entrepreneurs and small business, was effective and smooth and contributed to a large extent to the achievement of results for the programme (including bringing in additional funds of USD 1,610,000). SFD also provided training to the women entrepreneurs;

- The partnership with WMN, a national charitable organization, brought capacities in handling logistics and ability to connect with the poorest of the poor. Along with delivery of refrigerators, WMN provided basic goods (valued at USD 62,000) to women, from its own budget. WMN’s work also attracted local television coverage (unintended benefit from the partnership); and,

- The partnership with non-government organizations (NGOs), specifically CARE (due to UN Women’s earlier programming collaboration) helped to identify about 24 percent of the 4,170 participants in the programme. Some of the trainers used in the programme were from other NGOs.

In many ways, the TCCC-UN Women partnership in South Africa mirrored the corporate level partnership style and functioning. Both UN Women South Africa and TCCC South Africa have been involved right from the programme proposal and design stage and started dialogue to understand each other. This also enabled South Africa to start implementation without much time lag. Hand in Hand was identified as an implementing partner, through the UN Women procurement process and came on board in February 2013.

- A collaborative approach was fundamental to the programme design planning, management and implementation in South Africa. The three programme partners (TCCC South Africa, UN Women South Africa and Hand in Hand) worked together through the mechanisms established for the programme. The “jointness” in planning and working was highlighted by the three partners, during their separate interviews. All three worked as equal partners (not the “usual” donor – implementer relationship), largely due to the personnel involved - their relationship and commitment – and partly, also due to the interesting fact that UN Women was a co-manager (with TCCC South Africa)) and co-implementer (with Hand in Hand). It was seen as “Best in Class” by TCCC (corporate).

The key factors for the success of the partnership in South Africa included:

- Coming to a common understanding was very important to the partnership (given that the organizations came from different sectors with organizational cultures and way of working and making decisions). The partners took into consideration the importance and the need to have shared vision and shared space, early in the process. There were challenges; nevertheless the partners had ironed out and learned to work toward the common goal. Understanding ethics, boundaries was important. So they decided to have red (don’t go there), grey (discuss and sort out) and green (go ahead and do) areas.

- The partnership (TCCC-UN Women- Hand in Hand) with “common values” and trust, in many ways “mirrored” the working style and principles of the Global Steering Committee. The partnership in South Africa was seen as “Best in Class” by TCCC. There was common messaging down the line to the field which was evidenced in the effective collaboration between bottler/bottler representatives and Hand in Hand field team without any formal agreements (although some difficulties were encountered in a few pockets but they were sorted out to a large extent). It is important to keep in mind these bottlers (are independent companies) and bottlers’ representatives are not staff of TCCC.

The “Golden Triangle” partners (as referred to by TCCC South Africa) have also been able to cement a partnership with DSBD which focuses on provision of support to micro and small business and cooperatives. During the duration of the programme, it was able to get support from the New World Project (UNDP and TCC foundation project). There were also several informal local level partnerships which supported the programmes by providing venues for training. The highlight of local level partnerships was the use of the EDUBUS, provided by the bottler in Western Cape Province, for training.

Furthermore, UN Women South Africa was able to leverage its partnership with IBM to support the design of the Management Information System (MIS), at no cost.

Implementation arrangements

The programme’s implementation arrangement and management was well structured, with a Steering Committee at the global level coupled with country specific arrangements to achieve overall programme goals and country specific objectives. At the country level, both Brazil and South Africa were more coordinated and structured with country Steering Committees, comprised of the key partners, with regular meetings (Figure 1) – refer also to discussions for each country. While the TCCC and UN Women country teams had respective internal organizational reporting relationships on the programme, they worked together to implement the programme activities in their respective countries.

Figure 1: Global Structure – Implementation

Global Steering Committee

One of the key factors for the successful implementation of this Global Programme was the (Global) Steering Committee and how it functioned. At the global level, the Steering Committee comprised of six members – three from TCCC and three from UN Women.  Unlike in many programmes where the Steering Committee is formed with members getting involved after the programme is launched or just before the implementation, the members of the UN Women-TCCC Programme Steering Committee began their discussions a year prior, initially starting with Global Director of 5by20 and Director of Partnerships and Director of Programming in UN Women. This also laid the foundation to create directions on how to move forward on the programme.

In addition to the core members of the Steering Committee, additional members (two to three others) came in for meetings, initially to provide thematic or programmatic expertise. The Steering Committee at the global level not only provided strategic directions but also kept track of potential issues/challenges. The committee met regularly in New York with at least one meeting each year in the participating countries. In the initial period, there were more frequent meetings and weekly calls and country teams also participated in some of the calls to present plans. The approach to the mandate and decision-making “style” of the committee also contributed to the successful implementation of the programme. This included:

- Providing oversight at the same time paying attention to the details;

- Being flexible in allowing the countries to decide on the model and the implementation arrangements (more treating as a pilot enabling an opportunity to learn);

- Common messaging to the country teams; and,

- “Being up front (with each other) so that the right thing is moving forward for implementation”

One key point that was noted during the discussions at the country level, as part of overall implementation arrangements, was that in the three years the programme was implemented the country teams did not have an opportunity to talk to each other, as there was no mechanism. It could be seen as an area for improvement for future programming to ensure cross-country sharing and learning; not only because it is a good practice, but also because it addresses a recent evaluation finding that UN Women staff members across the organization have a wide variance in capacity and knowledge in the area of women’s economic empowerment (especially in areas of linking women to markets, statistical strengthening for WEE, and women and technology, among others).

Brazil

Although it took time (18 months), the implementation arrangements created for the programme in Brazil were quite adequate to carry out the two streams of activities – one was to reach  low-income women (including recyclers, youth and entrepreneurs); and, the other was to reach private/public sector companies to ensure increased commitment to WEPs, specifically principles 5 and 6. At the top, the Brazil Steering Committee comprised of senior management from UN Women Brazil, TCCC Brazil and ICCB and the project managers (from UN Women and ICCB) which met once every two months. Furthermore, there was an “executive committee” which was comprised of programme managers from ICCB and UN Women that met more frequently (Figure 1). The implementation arrangement/ operational model is illustrated in Figure 2.

In Brazil, the main objective was to reach the women through Coletivos with the new focus on human rights, gender equality and women’s empowerment. The mechanisms to reach women through Coletivos were already in existence for training that was being provided by ICCB. The arrangement of having a field analyst work in partnership with a local educator proved to be quite effective.  In the Coletivos, there are around 110 local NGOs supporting the training on Retail and Entrepreneurship and there are more than 300 recycling cooperatives in different parts of the country.

Figure: 2: Implementation Arrangement and Operational Model - Brazil

HR – Human Rights; GE – Gender Equality; and, WE – Women Empowerment; WEP – Women Empowerment Principles

Note: This was created by the evaluation to illustrate, in general, the overall model of Brazil programme and not the specific activities in the Coletivos. It must be noted that a wide range of activities were adapted and carried out for each type of Coletivo.

By the end of 2014, UN Women recruited a dedicated person to implement the work on promotion and technical support to companies for the implementation of WEPs, as well as identification and dissemination of best practices from companies, with guidance of UN Women Brazil and oversight from TCCC/ICCB.

Egypt

It took a considerably long time (about 75% of the programme time of three years) to come to an agreement on the operational model and implementation arrangements in Egypt, due to various internal and external reasons (discussed subsequently in the report). Nevertheless, the implementation was carried out in a professional manner to exceed targets within a short time frame (of eight months). The coordination mechanism was highlighted as the key to successful implementation of various programme components and the achievement of targets.

There were no formal structures; however, there was regular communication between UN Women and TCCC in Egypt; and, UN Women with its partners. The programme in Egypt focused on the “home-based retail outlet” model wherein assets (in the form of refrigerators and Coca-Cola ice-boxes) were provided to 1,500 women (with the programme budget) and the rest were provided with micro-credit by SFD, (from their resources) after training all the women.

Figure 3: Implementation Arrangement and Operational Model - Egypt

In order to implement the programme, there were four different partners (Figure 3).  SFD, WMN and other NGOs were contracted by UN Women Egypt, while Freecool, the refrigerator supplier, was identified by TCCC Egypt and contracted by WMN. Multiple partners were involved in the implementation of the programme – identification of beneficiaries (SFD and CARE), training of entrepreneurs (SFD and, local NGOs), and asset transfer (micro-loans from SFD and refrigerator distribution through WMN). At the request of UN Women Egypt, CARE supported the programme in the identification of beneficiaries, because of its relationship with UN Women on other programmes; there was no formal contract involved. It was also noted from discussions that WMN, supported in collecting additional information on beneficiaries identified.

South Africa Monthly Meetings

These meetings were:

- A “report back” of the monthly progress made by each field team member;

- An occasion to build capacity of field teams;

- A platform for knowledge sharing of good practices from different geographical locations and cultural contexts; and,

- An opportunity to review emerging threats/issues and opportunities in various “markets”/programme areas.

Interviews in Egypt highlighted that although the coordination mechanism worked well, there were no set formal protocols for coordination. Nevertheless, partners and their staff communicated on a regular basis at time of implementation.  Interviews also showed although there were roles and responsibilities for each partner, there were often confusions about those roles, because partners did not respect communication protocols. Many of them expressed that they were confused on “who is doing what” and to “whom they were reporting”.

South Africa

South Africa was relatively quick to put the structures and mechanisms in place and start implementation. In South Africa, one of the highlights of the programme was its governance structure and how it worked (refer Figure 1). From interviews with relevant key stakeholders it could be seen that this structure ensured clarity of roles and responsibilities, accountability for delivery of activities and reporting of results on time.  The effectiveness of the implementation arrangements could be attributed to:

- Clear terms of reference  for the project steering committee, comprised of management representatives from TCCC, UN Women and Hand in Hand Southern Africa;

- Quarterly Steering Committee meetings and when required, extraordinary meetings, to review progress, assess challenges and opportunities to strategize for the subsequent quarter; and,

- Monthly meetings of UN Women and the Hand in Hand team (both senior management and the programme field team – trainers from the field) benefited the implementation in several ways (refer box on monthly meetings).

Contractually, Hand in Hand was the implementing partner for UN Women South Africa. However, in this programme, as discussions revealed UN Women worked not only as co-manager (due its partnership with TCCC) but also as co-implementer. Nevertheless, the arrangement and partnership worked well (Figure 4).

Figure 4: Implementation Arrangement and Model – South Africa

In the “co-implementation” arrangement, UN Women focused on programme planning and management, technical support, coordination, monitoring and evaluation, financial oversight, government engagement and overall reporting, Hand in Hand focused on the mobilization on the ground, identifying entrepreneurs, recruiting and training of trainers, providing training, follow-up and interaction and relationship with bottlers and their representatives, at the local level. The trainers in the field were managed by a Lead Trainer/Provincial Manager. Each trainer in the field had one or two enterprise development facilitators (EDFs). TCCC South Africa provided the connection to the bottlers and their retailers (many of them are micro-businesses). While all three organizations were involved, TCCC South Africa led the bottler-engagement discussions. Once the bottler gave the go-head, Hand in Hand connected with the local team and coordinated the operations. On the ground the Hand in Hand team did the identification of entrepreneurs, from the list provided by the bottlers and then complementing it through door-to-door, road shows, community gate-keepers and local associations, as applicable. In terms of implementation, it was noted that while entering a new community, the Hand in Hand team met with the community gate keepers and explained about the programme and its intended activities. This was also crucial for the success of the programme.

Overall, it could be seen that the coordination mechanisms and implementation arrangements in South Africa worked exceptionally well. This was also highlighted in the findings of an earlier study conducted in 2015, commissioned by TCCC.

Monitoring performance and results

At the corporate level, the monitoring of the progress, performance and results was done at the Steering Committee. In addition to reviewing and taking actions during the Steering Committee meetings and other additional telephone meetings, reports were submitted from the UN Women country offices to the UN Women headquarters. Until the programme implementation started in the countries, specifically in Brazil (June 2014) and Egypt (July 2015), the Steering Committee reviewed progress on planning and implementation arrangements and provided guidance, as required.

In Brazil, the programme benefitted from the already existing robust monitoring system present in ICCB and used by the Coletivos. The monitoring system includes an online database with output level information (number of participants) and a systematic data collection process (baseline and post-training) at the outcome level. It was conducted by a social research firm who has, together with the ICCB team, developed measures to assess the extent to which the “graduates” from the Coletivos Retail and Entrepreneurship have developed the skills they needed. The monitoring system also helped to track whether the graduates have been able to find a position in the job market or start/strengthen their self-owned businesses, among other indicators and which recycling cooperatives are getting stronger over time and whether participants are increasing their income and self-esteem.  After the launch of the Brazil programme with inputs from UN Women, the human rights, gender equality and women’s empowerment perspectives were included into the measuring tools to enable measuring of increases in participants’ knowledge about human rights and gender equality as well as the extent to which participants were discussing these within their social/family circles.

A key lesson in Brazil, as reported by UN Women Brazil, was the missed opportunity to conduct a workshop on gender equality, human rights and women’s empowerment for the social research company, in the initial stages (similar to the one conducted for TCCC/ICCB). This would have saved quite a bit of time and efforts during the revisions to make the instruments adequate for the UN Women-TCCC programme requirements.

Brazil programme’s WEPs component person (from UN Women), directly monitored the promotion and implementation of WEPs by tracking some key indicators, including the (i) number of signatory companies, (ii) specific products to be delivered (quality, timing), (iii) number of participants and quality of the events promoted within the realm of the initiative, (iv) number of companies participating in the Federal Government Gender and Race Equity Programme.

Although the programme in Egypt reported regularly to the UN Women headquarters, the main components of the programme did not start until July 2015. These earlier reports were primarily on programme planning activities, definition of the business model, and selection criteria of the beneficiaries.

As part of monitoring, a baseline survey and a post-intervention survey were conducted. Most of the monitoring data was at output level – number of coolers delivered, number of training delivered, participants, etc. Adjustments were made, accordingly, based on daily monitoring data, during the implementation stage.  The post-intervention survey also collected both quantitative and qualitative data on programme indicators. With the programme coming to end the recommendations have not been taken into account yet.  It was understandable that there was no mid-term evaluation as the programme was implemented in eight months.

In South Africa, there was a push for monitoring since they started implementation very early in the programme. At the country level, the progress towards reaching the targeted women entrepreneurs was closely monitored through monthly meetings (that included trainers from the field) and field visits. Challenges and issues were noted and addressed during the monthly meetings and at the country level Steering Committee.  In addition to the regular monthly meetings, monitoring also included site visits by the project management team. Spot checks were also conducted by the management team as part of verification and monitoring. This also ensured the quality of results, in addition to support on the ground.

A database was created for the entrepreneur and the enterprise they were associated with. Initially hard copy forms were filled out and entered into a spreadsheet. Later a MIS system was developed and the back log of forms was updated into the new system. Although it took a while to clear the back log due to the programme constantly adding new entrepreneurs and enterprises, the new MIS system has the baseline data of entrepreneurs who have completed the training.

The trainers had started submitting case studies every month and success stories were noted or captured in videos during field missions by management team/national trainers to report on programme outcomes. Nevertheless, there was no systematic tracking of increase in income, savings, assets acquired, among others, in the programme. The evaluation used quantitative data from the longitudinal study of Ipsos South Africa to complement the qualitative findings. The MIS system developed was found to be capable of capturing these data; however the system by the time it was fully operational, it was too late in the programme (as reported during the discussions).

Another aspect for improvement in the programme monitoring mechanism was the reporting on follow-up of entrepreneurs. The programme in South Africa would not have succeeded (to this extent) without follow-up conducted by the trainers and EDFs on the ground. However, it was largely under-reported/never reported. Although monitoring system and/monthly reports did not reflect the extent of follow-up done,   there was ample evidence, during the field visits for this evaluation, that there was informal and demand-driven follow-up being done in the communities/municipalities– although not in a “structured” manner. Examples of comments from women entrepreneurs “I can text him (EDF) when I have doubt…..he comes to help” and “It is good that they are here (in the community)…..I can recheck (validate) what I am doing is right” reflected the informal follow-up which were never reported. Follow-up and support by trainers and EDFs was reported in all the focus group discussions and interviews with women entrepreneurs.

There is potential to maximize the value of the MIS system developed (for future programming) by:

- Using the system to track information about trainees such as income, savings, assets bought, etc. Tracking over time will help in measuring the impact of training on women to improve economically;

- Using tablets/smartphones to enter and report data, instead of entering data on paper and then re-entering into the system could make it more efficient and effective (it will help the first point also); and,

- Tracking follow-up visits of trainer/EDFs and correlating to see the effect on increased income in the business and women’s economic situation.

Effectiveness of direct actions – Training and development of tools

Overall, the programme’s direct actions including training and the development of tools have proved to be effective in all three countries, irrespective of the model and approach taken by each of these countries. Additionally, the advocacy and technical assistance regarding WEPs-5&6 in Brazil has also proved to be effective. Highlights of direct actions include:

- The training materials in all three countries used simple language and were contextualized to the local situation. This enabled women to understand better which  has contributed  to results in increased knowledge and awareness be it business and entrepreneurial skills (in all three countries) or employability, cooperative management, human rights, gender equality and women’s empowerment (specifically in Brazil). An example from Egypt on the effectiveness of training, as remarked by a women entrepreneur “whenever their children take any of the goods they sell, women pay for whatever their children have taken, to ensure that their businesses do not make a loss” . This was never done, before they attended the training;

- Women (and also men) learned and increased knowledge on book-keeping, marketing, customer relations and service, inventory management, and cash-flow management, among others due to the programme’s training (highlighted during discussions in Egypt and South Africa);

- The programme has also trained trainers and educators in the three countries. The capacities remain in the communities. They also have access to trainer manuals, informative brochures, an educational flipchart, and videos developed specifically to support the programme contents, where applicable;

- In Brazil, the programme was successful in incorporating gender-equality dimensions in the Sustainable Procurement Manual of the Brazilian Business Council for Sustainable Development (CEBDS).  It was noted that the manual was distributed during the International Trade Centre’s Women Vendors Exhibition and Forum in Brazil in September 2015;

- In Egypt, along with training, women entrepreneurs were provided with assets (refrigerators or micro-loans);

- Direct actions of the training have led to interest from the government at the national level in Egypt (Ministry of Local Development) and South Africa (DSBD) and investment in South Africa by DSBD; and,

- In South Africa, the direct actions and success due to the training women entrepreneurs has attracted the private sector for discussion (e.g. Barclays, Unilever, and Technoserve) and also the TCCC bottlers.

Some not so positive results include:

- The peer-support group efforts in South Africa required longer-term support to be more sustainable and transition into a cooperative; and,

- The training contents on human rights, gender quality and women’s empowerment in some cases did not seem to have resonated with members of recycling cooperatives who lived in harsh social environment, as these did not directly relate to their immediate survival needs.

More detailed discussion on the impact of the programme is presented in subsequent section.

## 4.3	Efficiency

Q3. How efficiently has UN Women implemented the programme?

As part of assessing efficiency, the evaluation looked at the implementation time, allocation and use of financial and human resources, expenditure vis-à-vis planned budget, presence of monitoring and evaluation and it quality, and the coordination/communication between headquarters (specific to this programme).

Implementation of programme on time and per work plan

The startup of the programme was delayed in all the countries. One of the key factors noted for this delay, was that the programme did not envisage the “front-end planning” time, when diverse organizations of this nature come together; it takes time to establish trust and come to a common understanding. This depended on the people involved and was made worse by the turnover of personnel. While the programme implementation was delayed (largely attributed to planning and agreeing to a plan of activities and “coming together”), the project ended on time (with a 3-month no cost extension). Targets were almost met (South Africa – 77.8% of 25,000 women target) and met or exceeded (in Egypt and Brazil) and within the budget.  Based on documents reviewed and discussions, factors that hindered implementation include:

- Both TCCC and UN Women (at local level in all three countries) did not envisage the time for “front-end planning”. In hindsight this was a lesson learned, when two organizations of this nature come together for an important cause/programme. This included understanding each other, creating a trusting relationship, defining what needs to be achieved and how, in addition to a “shared value”;

- The time taken to start implementation varied among countries depending on the “dynamics” between the two teams (TCCC and UN Women) – ranged from four  months (in South Africa) to 28  months (Egypt);

- The complex political situation (in Egypt), the economic crisis that affected prices of recycling material (in Brazil) and xenophobic protests (in South Africa) were  external factors beyond the scope of the programme;

- Programmes were tweaked a bit in Brazil and in Egypt (outputs, business model, supplier finalization, awareness creation plans), which led to more discussions; and,

- Agreeing on the criteria to identify beneficiaries (Egypt).

While the “original target” was 8,068, Brazil was able to exceed the target by the end of three years, reaching women in entrepreneurship, recycling and retail Coletivos.  Furthermore, while the overall objectives and efforts to produce meaningful results remained the same, it was noted during the evaluation, from discussions and review of documents, that the original plan was reviewed and revised by the partners in Brazil a few times (with appropriate approvals by Global Steering Committee) during the course of the programme.  For example, the deletion of “output 1.2” (refer Table 1 presented earlier) – access to micro-credit pilot in Manaus; and, the substitution of Coletivos Art and Community Leadership with Coletivo Retail. Lack of feasibility and change in ICCB strategy were noted as key reasons for these two changes.

Based on study findings in 2014, Egypt initially planned to use the kiosk-model. However, several limitations were noted subsequently and the programme adopted the home-based outlet model.

On a positive note, despite delays the teams in the countries along with their partners where able to achieve or come close to achieving the targets within the timeframe. In many ways taking the time to plan facilitated efficient implementation and carrying out of the activities.

Resource allocation

Overall, based on discussions with stakeholders at various levels and a review of information provided, it could be said that resources (human and financial) were allocated reasonably well, with some exceptions. In general there were no complaints on how the finances were allocated or spent. It was reported that in Brazil, UN Women made joint decisions with ICCB/TCCC before contracting or allocating money for spending. In South Africa, UN Women, TCCC and Hand in Hand met every quarter as part of Steering Committee and discussed, among others, financial matters. Furthermore, there has been audit from TCCC, which has not found any inappropriateness.

Stakeholders remarked that while the programme overall stayed within the budget, the amounts between years and between line items could have been moved and reallocated. So there may be line to line huge variations; this was also because the model and activities were “evolving” after the programme clock started, especially in Brazil and Egypt.

Human resources

In general, the allocation of human resources was appropriate in terms of implementation. This could be seen from the fact:

- A small team from UN Women and TCCC/ICCB worked together in Brazil. UN Women Brazil had two dedicated personnel, recruited to implement the programme; one to work with Coletivos of Coca-Cola component and other on the promotion of WEPs component; and,

- In South Africa, there was one dedicated person from UN Women and TCCC working on the programme.

The positive note about having a dedicated person for the programme (as seen in Brazil and South Africa), was that it helped build a better relationship and effective coordination with TCCC in the countries.

The TCCC programme contact in all the three countries and the senior management remained constant throughout the life of the programme. However, there was constant turnover of the UN Women senior management in all the three countries, especially in a programme which required top management buy in and ownership. While Brazil and South Africa were fortunate that the senior management who came in stayed connected and very involved, especially in South Africa, Egypt was hindered in many ways due to the turnover at the senior management level almost every year during the programme’s life. While Egypt started the programme with two dedicated staff, changes meant the programme, as noted during discussions, became an “orphan programme” and there was insufficient level of ownership of the programme especially when programme activities were slow at the beginning.  The situation in Egypt (as a country) was another reason that compounded the issue of making the programme an “orphan”.

The turnover situation was not very different at the Steering Committee level for UN Women. Fortunately there was one constant person throughout the programme time and the senior managers that joined subsequently have stayed very committed to the project. However, it was noted that “catchup” takes time. Two of TCCC team members remained constant in the Steering Committee and provided continuity and leadership.

Contracting Process

UN Women’s contracting process also contributed to delays in all three countries. All the “implementing partners” contracted were good and appropriate but the process was considered long. This was considered to be in contrast to the processes in TCCC. In South Africa, the implementation partner was contracted on a yearly basis, for this three year period programme.  This definitely caused uncertainty and turnover of trainers. Furthermore, delays in payment from UN Women were bridged by the implementing partner, to ensure programme continuity. While due diligence is important, it should not cause start-up delays or hinder programme implementation/continuity.

Financial resources

The programme worked within its overall budget (USD 3.974 million) and the countries also worked within their respective budgets – Brazil (USD 1.07 million), Egypt (USD 1.07 million) and South Africa (USD 1.30 million). It was reported that there was unutilized funds (USD 300,000 – 350,000) as of December 2015 from Brazil due to currency fluctuation; this was given to South Africa in 2016, to continue the programme for additional six month.

The countries’ teams have also leveraged financial and in-kind contributions from their partners. Examples included:

- SFD - USD 1.61 million for micro-loans (Egypt);

- WMN – USD 62,000 for basic goods for women as complementary along with refrigerators delivery (Egypt);

- EDUBUS from PenBev, a TCCC bottler in Western Cape Province (South Africa),made available to the programme at no cost for training purpose (used as a mobile training venue);

- In kind contributions of venues to conduct training in all countries;

- Refreshments at some sites by TCCC bottlers (South Africa);  and,

- Vehicles from Jobs Fund were allowed to be used by Hand In Hand for this programme (South Africa), which helped mobility of trainers.

Furthermore, there were instances that financial/in-kind support was also provided for specific events from country offices of UN Women and TCCC. Expertise and connections of the two organizations added further value to the programme in the countries. It was noted that the Coletivos operations (in Brazil) were ongoing, funded by TCCC Brazil/ICCB, even before this programme (and has continued during and after the programme); so it has not been seen as funds leveraged by the programme.

Given the fact that the targets were nearly achieved or exceeded in the three countries reflected that the targets set were appropriate.  Based on information available, the evaluation tried to calculate the overall cost of training one participant (Table 5). It reflects the gross total cost per person trained. The purpose is to reflect on aspects of efficiency of the overall programme and not compare countries. It must be noted that content and duration of the training varied among countries and among Coletivos in Brazil. Each country was also unique in the processes used to identify women for training and also the development of the training curricula and tools.

In all three countries, the costs associated with training one woman ranged between USD 28 to USD 62. This included cost of identification, recruitment and training of an individual. It also includes cost of development of training manuals, training materials and tools, as applicable, and all overhead of the programme in the country. Although Brazil had a lower cost, it must be noted in Brazil a large part of overheads were covered by TCCC/ICCB due to its ongoing initiative with the Coletivos. In Egypt and South Africa the mechanism and operations were created specifically for the programme. Compared to similar projects in the development sector (for financial literacy, entrepreneurial skills to start business etc.) for which the normal costs ranged from $100 to $200 per trainee, this indicates an overall high level of cost-efficiency.

Table 5: Summary of Training Cost

| Country | Total Trained | Overall Budget (2013-2015) | Trained per day (250 working days/year) | Cost per Trainee |
| --- | --- | --- | --- | --- |
| Brazil | 21,500†† | US$ 1.07 million | 57‡ | $28* |
| Egypt | 4,170 | US$ 1.07 million | 24‡‡ | $62** |
| South Africa | 23,166† | US$ 1.30 million | 31 | $56 |

†† Includes women entrepreneurs, recyclers and young women

† Includes 5,133 men trained directly as part of the programme

‡ Calculated based on the fact the actual implementation was only for 18 months

‡‡ Calculated based on the fact that the actual implementation of the project was only for 8 months

* Calculated after subtracting the unused money returned (estimated USD 325,000) and amount allocated for WEP component (USD 150,520) from the overall budget amount

** Calculated after subtracting the cost of assets from the budget value (1500 refrigerators and boxes) which was 76% of the overall budget/spent

While Brazil and Egypt were able to achieve momentum to reach targets within a short period of time, South Africa was able to maintain a constant momentum throughout the three year period. Assuming 250 working days a year, the number of people trained each day indicates high level of efficient coordination and consistent effort (Table 5).

Programme monitoring and reporting

The evaluation intended to assess the quality of the programme monitoring and reporting. Similar to programmes designed by each country, the monitoring mechanism and tools were also designed and used “differently” in each country.

- In Brazil, a robust system already existed for monitoring results of the work carried out by the Coletivos (see also discussions earlier). This system was already in place in the Coletivos when the partnership between UN Women and TCCC/ICCB started. For Coletivo Retail and Entrepreneurship, they conduct data collection every six months from a sample of approximately 1,000 participants stratified by the TCCC bottlers’ coverage area. For Coletivo Recycling, a sample of 30 cooperatives was created and more than 300 recyclers are interviewed in 4 six-month waves since April 2014. Reports are produced after each wave of data collection and the instruments have been reviewed frequently to become more appropriate and responsive to needs.  This meant there was longitudinal data available. With the launch of the UN Women-TCCC programme human rights, gender equality and women’s economic concepts were introduced into the measuring tool, which now also measures the increase in knowledge and awareness on these concepts. A baseline survey was conducted upon introduction of the revised indicators. The data collection was carried out by an external social research firm. However, for the WEPs component of the programme, it was reported that programme team (WEPs person from UN Women) monitored the promotion of WEPs by tracking key indicators, including number of signatories, number of participants in key events, among others.

- In Egypt, there was a baseline survey (347 women) and a post-intervention survey (338 women). The post-intervention survey also included focus groups discussions with 49 women. It collected quantitative and qualitative data on programme indicators. It was also reported during discussions that there were training satisfaction surveys (which the evaluator was not preview to); however, the post intervention survey report incorporated findings on learning of new skills from the training survey. There was daily monitoring electronically and by telephone on the progress during the implementation stage.

- In South Africa, a database was created for the entrepreneur and the enterprise they were associated with. The system allowed each entrepreneur to have a system generated ID and prevented double entry by restricting use of primary entrepreneur ID twice. For example, the system will not allow one to enter same phone number and also, checked for duplication of national ID number. Initially hard copy forms (very detailed) were filled and entered into a spreadsheet. Later a MIS system was developed and the back log of forms was updated into the new system.  However, this system is yet to be maximized for its capabilities.  For example, the paper forms still being used and a data-entry person is required to re-enter the form data into the system (which may not seem to indicate  efficiency; however, the programme team reasoned that it helped verifying  the accuracy of data and prevent possible double counting of entrepreneurs). The trainers submitted case studies every month, along with their monthly reports. However, the monitoring did not capture follow-up which was largely under-reported/never reported.

Coordination/communication between headquarters and the Country Offices

As discussed earlier, the Global Steering Committee had a joint communication strategy and messaging to their respective country offices to avoid miscommunication and confusion. The Steering Committee members spoke openly and frankly and arrived at what message should be sent to the countries. One of the best examples was how the Steering Committee was able to diffuse the situation and the get the two sides to work together and achieve the targets set for Egypt.

While country offices had their respective obligations to their headquarters, the country teams, especially in South Africa (much earlier in the 3-year period) and Brazil subsequently, jointly agreed upon decisions/strategies at their end, before communicating with their respective headquarters. This was found to be a much easier process.

Discussions, at the UN Women country offices revealed that the turnover at the headquarter team meant additional efforts from the country to keep headquarters updated. In general the headquarters team was found to be resourceful and supportive by the country teams.

An interesting point noted in all countries was, even if UN Women and TCCC had cordial working relations, the actual report shared was only through “proper protocol route” through their headquarters, even if they informally shared results/numbers at the country level.

Overall, discussions at the country level revealed that coordination and communication between headquarters and the country teams worked well and met the expectations. The countries felt that appropriate support and push was received from headquarters, as required. However it was noted, the close attention and the direct support provided by the Steering Committee in this pilot programme may not be possible in a large multi-country programme.

## 4.4	Sustainability

Q4. What is the likelihood that the benefits from the programme will be maintained for a reasonably long time when the programmes ceases?

In addition to looking at likelihood of programme benefits continuing, the evaluation also looked at scalability and replicability of the programme.

From the evidence gathered during field missions, there was no doubt that skills provided to the entrepreneurs will help them continue to operate their business successfully for a reasonable period of time. As evidenced from discussions with entrepreneurs it could be seen that they are practicing various aspects of the financial management, marketing and customer relations, in addition to sustaining and growing their businesses (see details in effectiveness/impact sections).

There is a high likelihood that the benefits of the programme will be maintained for a reasonably long period of time when the programme ceases, for both beneficiaries and the key participating NGOs/implementer. However, the programme and the beneficiaries do not exist in isolation from their context, which imposes limitations to the sustainability of those benefits. Therefore, for beneficiaries threats to sustainability may fall outside of the scope of the programme. Threats include increased utilities and goods’ prices, competing priorities and basic needs such as health, and obligations to local traditions and customs, in addition family relationships and commitment. Additionally, the formation of “natural groups” which is evident in some countries (Egypt and South Africa) is likely to continue.

The evaluation also looked at support and commitment/ownership from national/local institutions, mechanisms that the programme has put in place for sustainability of results, and evidence of strengthened institutional and community capacities.

Support, ownership, and leadership commitment from national and local institutions for the programme

Based on documents reviewed and discussions in the countries, it could be said that there were positive signs (in varying degrees) of support for ownership and leadership from national and local institutions in each of the three countries – Brazil, Egypt and South Africa.

- At the natioDSBDnal government level, there was evidence of support, ownership and commitment in Egypt and South Africa. These included:

  - In Egypt, the Ministry of Local Development (MoLD) has shown interest in the programme and it was reported that it has been adopted as part of its national plan for development.

  - Furthermore in Egypt, SFD (a quasi-government institution) was key to the successful implementation of the programme in Egypt. As a self-sustainable institution and with strong leadership commitment and ownership, it is likely SFD could continue to carry on with the programme activities on its own.

  - The DSBD (in South Africa) has shown interest in the programme because of the positive results seen due to training, which has contributed to its mandate to the development of micro and small business. The recent workshops in 2016 (funded by DSBD), attended by 920 women entrepreneurs, trained by the programme, is strong evidence of the Government support and commitment. The participants of these workshops are eligible to apply for equipment/machinery required to expand/consolidate their business. It was reported that DSBD is also preparing a blue print to implement its plan; it is developing an implementation framework to identify provincial and municipal roles.

- During field mission and discussion with government stakeholders, evidence of local government / municipalities interest to support the programme was seen in South Africa.’ They indicated their ability to finance some activities (with reference to supporting women entrepreneurs). During discussions it was noted that the municipalities have resources to support women “entrepreneur groups”. DSBD also reported to be working on a framework to work through municipalities. Although these have not been leveraged by the programme within the programme timeframe of three years, it was noted that these are being taken up in 2016, through the new partnership of UN Women and the South Africa team with DSBD. Already DSBD has funded training; and UN Women and the South Africa team are working to build on this relationship to continue further and scale-up or replicate.

- In terms of support from other national institutions that are likely to continue include:

  - ICCB, in Brazil, has been committed to carrying out the training to Coletivos, which now includes human rights, gender equality and women’s empowerment.

  - The Brazil Business Council for Sustainable Development (CEBDS) has incorporated gender equality and women’s empowerment in their Sustainable Procurement Manual.   The manual serves as the guide for 70 large companies working in Brazil which account for more than about 40% of the Brazilian GNP and over 1 million direct jobs.

  - “EDUBUS” by TCCC bottler in Western Cape, South Africa (made available at no cost for training purposes).

- With reference to support, commitment from national NGOs and community organizations, these include:

  - Hand in Hand in South Africa has been a great and committed partner with strong leadership and capacity to implement and deliver. The “layered-trainer model” has been used by Hand in Hand prior to the programme. It can continue training at a smaller scale with its own funds; however, it would require financing to scale-up.

  - WMN in Egypt brought in its own finance (USD 62,000) to complement the programming

- Lastly, the strong partnership and leadership of UN Women and TCCC globally and, specifically in Brazil and South Africa, could be leveraged further.

Mechanisms in place due to the programme to ensure sustainability of results

A key limitation of the programme was that none of the countries had an exit strategy, an important element to ensure sustainability. Although important for all three countries, it was crucial for Egypt and South Africa, given the fact that in Brazil the initiative was ongoing (without human rights, gender equality and women’s empowerment elements), even before the UN Women-TCCC Programme was launched.  That said, in addition to training tools, manuals, videos and flipcharts among others used during training that are available at the country level for continued use in all three country;  some actions have been taken by the countries (discussed below) to put some mechanisms in place:

- In Brazil, it was basically through the incorporation of human rights, gender equality and women’s empowerment and/or WEP-5&6s into:

  - Training curricula of ICCB and its Coletivos; and,

  - Sustainability Procurement Manual of CEBDS;

  - WEPs brochure with local cases for each principle; and,

  - WEPs strategy by UN Women Brazil.

- In Egypt, mechanisms included:

  - Transfer of assets to women (ensures income generation if they continue to use);

  - Life-time guarantee for refrigerator maintenance; and,

  - Mitigation against sale of refrigerators (transfer contract that prohibits sale of refrigerators for two years.

- In South Africa,

  - The collaboration with DSBD will help the successful “trained women entrepreneurs” move to the next level. This is complementary to the programme results; and,

  - The TCCC bottlers have shown interest to continue the activities. These discussions have to be pursued and finalized.

However, none of these mechanisms reflect scaling-up to reach more women and/or women entrepreneurs, with the exception of the interest from TCCC bottlers in South Africa, which is yet to be finalized. The collaboration with the DSBD in South Africa is a positive step as it was noted that activities of training and providing assets to trained women has already started in 2016. Discussions also revealed that DSBD was open to scaling up especially to rural areas or areas that have been prioritized (either the Presidential poverty nodes or the development corridors). The DSBD also indicated that they could possibly bring on board other partners within government systems, for instance the Skills, Education and Training Authorities (SETAs) technical skills training.

The primary focus of the organizations in Egypt and South Africa has been support to women’s economic empowerment through entrepreneurship and business skill development and/or asset transfer. In Brazil, the focus was largely on incorporating the human rights, gender equality and promotion and implementation of WEPs-5&6.

Knowledge transfer and capacity building of partners and degree of institutionalization

Findings are based on discussions with stakeholders and observations on the ground in the countries.

The whole premise of the UN Women-TCCC programme was about knowledge transfer and capacity building (be it business and entrepreneurial skills or knowledge and increased commitment on WEPs-5&6). In all three countries knowledge transfer and capacity building were core components of the programme, with the exception of Egypt (which also had asset transfer indirectly increase capacity).

Evidence collected during this evaluation indicated that:

- The knowledge transferred through the training of the trainers at various levels in all three countries (including educators in Brazil) whether it was financial management, business and entrepreneurial skills or the human rights and gender equality perspective, has been transferred to women in the countries;

  - This was reflected in women putting into practice what they learned, specifically the women entrepreneurs;

  - While awareness about human rights, gender equality and women’s empowerment has increased in Coletivos in Brazil, it is likely to take a longer period of time to see the impact;

- The tools and modules provided in the programme are available with partners and other organizations, in addition to women in the community (in all three countries);

- Most of the trainers, in all three countries were from the communities/municipalities/ Coletivos. This meant the capacity built was available locally and can be utilized further;

- In Brazil, the number of companies that have signed the WEP-5&6 and the mobilizing movement around gender equality and women’s empowerment within the companies was a sign of creating an enabling environment;

- All partners involved have either increased their knowledge either in terms of WEPs and/or strengthened their capacities in implementation of women’s economic empowerment programmes. It could be said that they have been institutionalized at least to some extent.

Going forward, there are two aspects with reference to sustainability – one is to take a proportion of entrepreneurs (who are ready) to the next level, and the other is activities to reach out to more women entrepreneurs, in terms of women’s economic empowerment. Ideally, both should happen simultaneously; however, it will depend on the strategic priorities at the country level based on programme objectives in addition to availability of finances and other resources.

The models in each country have proved to be unique and successful in their respective contexts. The programme models are scalable and replicable in varying degrees depending on the context. The models can be used in other programmes, specifically the ones related to women’s economic empowerment. From the results and outcomes on women’s economic empowerment, it could be seen that the models in Egypt and South Africa are more likely to be replicable and or scalable, with tangible results, in appropriate contexts (more so the latter) in reaching women entrepreneurs, using a private-public partnership. The South Africa model is likely to be the easiest model to scale-up and/or replicate in many countries/contexts in private-public partnerships (compared to the models of other two countries) in reaching and training women entrepreneurs for women’s economic empowerment.  The Egypt model is replicable if a strong micro-credit partner could be identified or the programme includes a considerable portion of its budget for purchase and distribution of assets. The WEPs component of the Brazil programme can be replicated by UN Women in its own programming globally and in other countries through partnerships with private sector or on its own through resources from traditional donors. The Coletivos component of the Brazil programme was made possible mainly because of the already existing structure and mechanisms through the support of TCCC/ICCB in Brazil. Introduction of human rights, gender equality and women’s empowerment concepts into existing training programmes and curricula is replicable in several contexts and in various programmes.

In order to scale-up/replicate, it is important that the government and other businesses see value not only in the programme (the success in the country) but also on the model that enabled it; simpler to implement is better.

## 4.5	Impact

Q5. To what extent has the programme achieved the intended programme objectives?

Contribution to capacity development of women entrepreneurs to establish and sustain their businesses

Capacity building and empowerment of women has been at the core this programme. The reports reviewed indicated that the programme provided training to 42,703 women (see box). In all three countries women have received training on how to strengthen their business – this included training to improve their capacities in management and operations of their businesses. This was very evident from the discussions with women entrepreneurs during focus groups and one-on-one interviews.

Comments from Recycling Cooperatives – Brazil

“As you can see, we are very poor. We struggle on a daily basis to keep the cooperative alive. If we could use the money from the rewards provided by the project every six months also to fund part of our operations, it would give us some breathing space. As it is now, we can only use that money to buy things. Of course, they are of great help, but sometimes it is just too hard take care of the business expenses and also pay the workers.”

“Our cooperative could be in a much better position if we could use the money from the rewards as a ‘working capital’. This way, we could have more flexibility to sell our recycled materials when the market price is right without losing a lot of money with fluctuation of prices. Also, we could, to some extent, try to avoid exploitation from the middle men by having a greater stock and try to sell directly to the companies.”

“The planning we do with the facilitator from ICCB has been essential. Those activities have helped us become more attentive to details and processes that have ensured the increase in our production. However, we live in very difficult situations. We need more material help. For instance, we do receive protection gloves and uniforms, but they last for a short period given the harsh conditions they are used every day. We end up using inadequate protection for long periods since we do not have money to buy new ones.”

Women Trained

Brazil  	  	- 21,500

Egypt 	  	-   4,170

South Africa 	- 18,033

In Brazil, the programme’s training reached women and/or young women in diverse Coletivos – Entrepreneurship (630), Retail (16,669) and Recycling (4201). The Brazil programme incorporated human rights, gender equality and women’s empowerment aspects into the training curricula to train women and youth to become entrepreneurs, to manage operations of business/cooperatives, or to find a new job. The programme trained members of the 304 participating recycling cooperatives on how to strengthen their business/improve managing the cooperatives. About one-fourth of these recycling cooperatives were reported to have improved their management and operational capacity from basic to intermediate. However, it was noted from ICCB, that more than 90 percent of these cooperatives achieved their respective internal business improvement targets set for the last 6-month period. While these improvements in the cooperatives lead to rewards, the ground realities they faced added more complications. (see box). Harsh contextual conditions, however, influenced a high turnover of people working in the recycling cooperative. It was noted that strengthening of the recycling cooperatives was a medium to long-term process.

There was general perception that the component to develop capacity to become entrepreneurs was not particularly successful in the way it was structured and has been discontinued by ICCB/TCCC; however, interestingly, in the Coletivo Entrepreneurship 89 percent of women reported that the training helped them develop their business skills. A new way of reincorporating entrepreneurship training into the new format for the Coletivos Platform has been developed and the outcomes are yet to be seen, outside the programme’s life.

In Egypt, women entrepreneurs not only have improved their knowledge and skills but have also applied them to sustain and/or expand their business. During focus groups, several women indicated that they owned businesses in the past, but they were not successful in sustaining them.  Many of them attributed the failure of previous businesses to their lack of knowledge of work planning, calculating profits and losses, and their inability to separate business and personal accounts.  As a result of training, the majority of women indicated that they were able to manage their money and profits better. In addition, some indicated that they were planning to increase their inventory to attract more clients. Moreover, many of them undertook marketing activities, including knocking at the doors of their neighbours and asking them if they will purchase goods from them, rather than going to the marketplace. The post-intervention survey also indicated an increase in knowledge among women; this included book-keeping (37.6%), conducting market survey (22.1%) and promotion and marketing (12.4%).

Capacity Built

“The training offered at Coletivo Retail was essential for me to get my first job. I did not know how to talk in an interview or how to dress or how to prepare a CV. The training gave me the confidence I needed to do well in the interview.” (Brazil)

“In the past, I did not know if my business was making a profit or a loss. But after training, I know how to calculate profit or loss” (Egypt)

I am not good with numbers – they made me understand and now I balance my books” (South Africa)

In South Africa, the contribution to capacity development of the women entrepreneurs to establish and sustain has been impressive. The uniqueness about South Africa programme was that the results have been achieved just by providing soft skills (building capacity) with no direct financial support or asset transfer to the entrepreneurs from the programme. The training comprised of five unique 2-hour modules. There was flexibility of timing to conduct the training and also how the 10 hours of training was completed (as per the priority of women). In some cases the women took up to three months to complete all the modules. The key highlight of the training was that concepts of enterprise management were simplified without losing the main essence of it, for micro and small entrepreneurs; many of them had not completed school. The manuals were in simple English and had pictorial illustrations.

It was noted that trainings were offered in local languages prevalent in the area. This was made possible by design, as the trainers and the enterprise development facilitators (EDFs) were selected from the community/municipality area. This made it easier to contextualize at local level. Discussions with entrepreneurs (both focus groups and key informant interviews) and with key community stakeholders highlighted that the delivery of the module was micro-entrepreneur-friendly. In addition to the basic training, the entrepreneurs were able to get specific clarifications for their business.  The ability of the trainers to relate and communicate with the women entrepreneurs was evident during the discussions (see box).

Comments from Focus Groups about Training

“We can express freely during training sessions”

“I am able to speak one to one”

“They never tell me what I ask is stupid”

“

All the women entrepreneurs (in South Africa) who participated in the focus group also indicated that they learned from the training and the training has been useful to them. This also mirrored the Ipsos study findings (98% indicated that they learned from training, 97% were satisfied about the quality of training; and 98% indicated it was relevant to the business). Most of them reported they had never had such an opportunity or even access to such an opportunity, even though some women had been running a business (in different versions) for more than 15 years. The training not only met the expectations of women entrepreneurs but also community stakeholders who were involved in some instances. As remarked by one discussant - “they delivered what was promised.”

Overall, the contribution of the capacity building was evident from the results seen from the practice of the skills learned by the women entrepreneurs. The results have even evoked the interest of DSBD to work with 920 women (trained by the programme) to provide support for additional equipment/infrastructure – this number is likely to increase in the future.

Women entrepreneurs increased access to networking and business support

Focus group discussions in the countries clearly indicated that women entrepreneurs in some cases managed to form collaborative relationships to mitigate risks to improve business opportunities. In many cases, these were informal and among women whom they met in training. These collaborations in most cases meant going to a wholesaler and buying in bulk giving them cost savings which increased profit margin or staying competitive by  (as in the case of South Africa where they have to ward off competition from “foreigners”).

Positive examples of access to business support gained by women include:

- The newly formed relationships with Coca-Cola distributors who they were not familiar with before the training (Egypt);

- The connection to refrigerator repair agency - as the programme has secured a life time guarantee for maintenance – (Egypt);

- Women formed groups to access additional services and benefits from local government level and also individually able to access support from DSBD/national government through the recent workshops for selected “programme trained women”(South Africa); and,

- Talking to each other has helped to avoid bad customers, or not giving credit on sales to those customers (in some areas in South Africa).

“They don’t abandon us”

“They don’t disappear after training”

(Stakeholder comments about trainers)

Additionally, in South Africa the programme organized a networking event “iBusiness Journey Yami” (My Business Journey) in 2015, bringing 150 women entrepreneurs (trained by the programme) to share their experiences with peers and thus promote peer learning. Peer Support Groups were another effort undertaken in South Africa under the programme (120 groups created). The evaluator was not able to meet any of these groups and the effectiveness on the working of these groups was not very evident (not highlighted) during the discussions with key stakeholders. The evaluation noted that these groups take a longer time to bond and work effectively.

Nevertheless, formation of “natural groups” and their success was noted especially in Egypt and South Africa. These “ natural groups”, normally of 3-4 women, met to share notes or on most occasions joined to make bulk purchases (cost saving – due to shared transport cost and better discounts). These “natural groups” are likely to continue (even after the programme).

Furthermore, the trainers (in all countries), enterprise development facilitators (in South Africa) and educators (in Brazil) lived in and around the communities and were available for follow-up and/or clarification. This was more evident in Brazil and South Africa, as the programme was implemented for a longer period of time than in Egypt. This was something unique where the trainers were closer to the community (must be seen as a best practice in building capacities on the ground). The remarks of the stakeholders reflected that (see box).

Increased economic opportunities and access to livelihoods, for the poor and excluded

Egypt – Comments from Women Entrepreneurs

“When I have some profit, I invest it in a new product. Now, I am selling some “galabias” [women’s long dress] as well” in addition to what I received from the programme.”

“Now with the Coca-Cola refrigerator and the goods, I have more income than before, which helps in my household expenses. Even though income does not cover all my needs, I am grateful to have it”.

Based on observations and discussions in Brazil, Egypt and South Africa with entrepreneurs and stakeholders (not involved in the Programme directly) and programme stakeholders, it was evident that overall the programme, has contributed successfully to increased opportunities and access to livelihoods, especially for the poor and excluded.  While the results are quite positive in both Egypt and South Africa, the results were mixed in Brazil.

- In Egypt, The programme contributed to an increase in women’s participation in the labour market. The programme strategy of provision of assets (refrigerators – 1,500 women; and, micro-loans – 2,670 women) coupled with training on business skills development were obvious vehicles to open doors for increased economic opportunities and access to livelihoods for the women. The post-intervention survey in Egypt indicated that 100 percent of the women who participated in the survey indicated an increased income. This was also reflected during discussions in the focus groups. While all the women (in focus groups) indicated increased income, many indicated expansion/growth in their business (indicated by higher inventories or more stock-keeping units). For example, a woman indicated that she started a business with an inventory of EGP 750 (USD 55), and in less than a year she has grown her business indicated by the value of the current inventory, she has - EGP 1,750 (USD 128).  Women also reported that after their participation in the programme (and due to the assets received), they have been able to increase their income and profit. Even though it may be low, it still made a positive change to their livelihoods and they now need less assistance from their family and friends. This was noted in the context that the delivery of assets took place less than nine months ago.

South Africa – Comments from Women Entrepreneurs

Business diversification/growth

- “I was in “fast food” business, now I am adding a bakery division…………and I hope to expand into more locations in the future”

- “I was doing only pillow cases and curtains, now I have added bedspreads also to complement my other products”

- “I am able to employ a person now”

- “I built a garage for the shop…….so no need to worry about rain now”

- “Before I used to sell food only at lunch time, now I also sell during breakfast and also added cool drinks and coffee/tea to my business”

Daily Record Keeping

- “I now monitor the cash flow for “big items” and ”small items” separately”

- Before I used to take money from the business to buy food for the house and when time comes for buying stocks I have to go take money from my husband or other relatives………now after the training, I do not take money from any one…I can manage the business and also provide for the house”

Basic expenses

- “I am now able to go to the doctor for myself and also for my grandchildren, instead of a clinic”

- “I am able to pay for school transport for my children”

Asset building

- “ I have been able to add two more rooms to my house”

- “I have been able to complete construction of my which was left unfinished for several years due to economic difficulties. I have also been able to buy furniture”

- “Me not asking money from my husband, is helping to expand our house from the money from his income – to accommodate our 7 children (4 own and 3 adopted)”

Personal development

- I have enrolled in University of Johannesburg to become a teacher. I have been able to pay my school fees from additional income due to better business management”

In South Africa, the programme trained the 18,033 women entrepreneurs (in addition to 5,133 men) on various aspects of business – financial management (including keeping records, costing), inventory management, marketing, client relations and service, understanding markets, among others.  In addition to success stories reported in documents and videos, it was evident from the discussion with women entrepreneurs during focus groups and interviews at their business site that the programme contributed and enabled the women to increase economic opportunities and/or better livelihoods. Most of these women were poor and did not have access to these training before.

Ipsos Findings in South Africa – May 2016 (selected examples)

- Average business sales increased from ZAR 1214 (USD 90) in June 2014 to ZAR 1772 (USD 130) in December 2015 (statistically significant)

- Variability in women’s total income (month to month) has decreased since December 2013

- Women are better able to afford basic expenses (statistically significant)

- Participation in formal and informal networks is low/static

- Most women (92%) report that their business has improved (a lot-58% and somewhat-34%) as a result of the training – (average of 4 waves of data collection)

- Average amount saved by women each month has increased since December 2013

Source: Ipsos, South Africa (2016)

In South Africa, all women entrepreneurs during discussions indicated that their income has increased after training. Discussions with stakeholders in the country and Programme documents indicated an increase of five percent to 25 percent, a range indicated by some women during discussions, when they were able to quantify (approximately). From discussions with entrepreneurs and stakeholders and observations on site, it could be seen that they not only have been able to sustain the business, but several of them have been able to diversify or grow their business, which was indicated by their increase in volume of sale, new products added or new lines of business. It was not possible for the evaluation to quantify what proportion of women entrepreneurs were able to do this from project data.

- Women entrepreneurs in South Africa also indicated that they were able to save more which was either used for reinvestment in their business/buying stocks or other needs at home.  They were able to meet their basic expenses at home better – “we don’t have to ask our husband for money to buy food for the children”.  This contributed to increased self-esteem. One of the key aspects all women learned from training that contributed to improve the economic conditions was their ability to manage finance, keeping daily records, costing of goods for pricing, learning to keep personal finances separate from business finance, managing credit and cash flow in business, budgeting and calculating profit and loss (some even did by “product/business” lines – one example was “bottle accounting”). Other important aspects that helped women in improving economic opportunities (and increased income) was learning about customer relations and customer care, understanding market and competition and how to position their business. (See box for some comments from women entrepreneurs in South Africa). Many of these discussions (qualitative results) have also been reflected in the findings of the longitudinal study conducted by Ipsos in South Africa (see box for some selected examples).

- Discussions with women entrepreneurs, in South Africa also gave insights into how they have taken initiative to identifying new business opportunities – expanding operations beyond their physical shop – including reaching out to schools, mobile operations, etc. A few of the women even reported to have promoted their business through Facebook and WhatsApp.  It was also noted during discussions with stakeholders and documents that some women have started to take salaries from their business, discussions with women entrepreneurs revealed that while this was beginning to happen, it is likely to take a longer time to see everyone take a salary (a finding similar to Ipsos study). During discussions with women, it was also noted than many of them who availed of credit before from informal sources have now been able to manage without loans, at the same time they are able to save better. Some of them indicated that they participate in the informal saving groups in the communities. Some reported depositing in the banks. Some entrepreneurs have started to charge interest for their credit sales.

The programme in Brazil put in tremendous effort to train low-income women to become entrepreneurs, to strengthen business of recycling cooperatives and train young women (16-24 years of age) in low-income families to access the job market. Overall the programme trained 16,669 women in retail (77.5%), 4,201 recyclers (19.5%) and 630 young women (3.0%). The impacts on income in Coletivo Recycling and Coletivo Entrepreneurship were mixed. Programme monitoring data showed that during the duration of the programme, the income of the members of the recycling cooperatives generally did not change or slightly decreased. However there are also instances of income increases of five percent to 30 percent, but these numbers varied depending on the time of year when the data was collected (e.g. in December – likely to have higher income). It was

Comment from Brazil

“The Coletivos is the only place in this very poor and huge neighborhood to offer free courses to the youth… It is an opportunity for them to realize that they can have a life and a career outside drug trafficking or entering the local militia.”

important to take note of the contextual factors when analyzing the results in Brazil; this includes the overall economic crisis in the country and the decrease in market prices for solid waste. In respect to the entrepreneurship training of the few women the evaluation was able to meet, there was only one success story. One of the difficulties for this entrepreneur was getting access to capital to start even a small business. This “entrepreneurship” component of the programme was seen as a “pilot” and has been discontinued due its lack of effectiveness to show results.

- Another major challenge faced by the programme in Brazil, was in achieving increased economic opportunities in the training related to youth empowerment through building capacity to obtain a job.. From the records and the discussions it could be seen that about 30 percent of the graduates (low-income youth), from the Coletivo Retail training, were able to access their first job and therefore start to generate new income for them and their families. It was noted that there was small dedicated team in TCCC/ICCB to help youth find jobs by creating a roster of 300 companies which are linked to TCCC value chain in Brazil.

- As per the theory of change the WEPs component in Brazil, focusing on principles 5 and 6, is expected to contribute to increased women’s economic empowerment; however, it was noted to be too early to see the results at the time of this evaluation. There is further support required for the WEPs signatory companies to progress and implement affirmative procurement policies. Nevertheless, companies committing to be signatories to WEPs-5&6 has been a positive step in this direction.

Another interesting aspect was the increase in self-esteem and confidence among women entrepreneurs, reflected in a stakeholder remark – “I now think I have a job….….previously, I used to think I was unemployed”.

Women entrepreneurs in Egypt and South Africa (based on discussions during focus groups and interviews with them) were unanimous in their views that they have better self-esteem and higher confidence, now after the training. However, in Brazil, the measures (Rosenberg Scale) used to assess participant self-esteem indicated wide variation – within Coletivo and among Coletivo. Among women members of recycling cooperatives, after an initial increase, there was a general decrease of 14%. Among the young women participating in the Coletivo Retail, the first cohort studied indicated a decrease (12%) while the second cohort indicated an increase in self-esteem (6.3%). For the women in the Coletivo Entrepreneurship, the results were similar – decrease of self-esteem in the first cohort (13.5%) followed by a substantial increase in the second cohort (46.9%), which was also reflected, during discussions. The Ipsos South Africa 2016 report noted higher confidence was linked to the increase in personal income and there was no statistical relationship between higher confidence and increased business sales.

The team was not able to meet with women entrepreneurs who did not succeed in their business (after training), in all three countries. However, discussions with stakeholders and review of documents reviewed that there were cases that have not been successful.  Factors contributing to failures and drop outs include:

- Severe illness to one or more family members.  In some cases the family (even it has many members) is solely dependent on the women entrepreneur and when she falls ill, the business collapses (Egypt and South Africa);

- Negative family or community influence on the entrepreneur (creating a false sense of expectations (specifically about money) – because it is a UN Women / TCCC programme (South Africa);

- Security and crime situation (many of them are likely not registered);

- Competition from “foreigners” (an issue in South Africa) – the training has helped many to face competition;

- Inability to access finance (Brazil and South Africa);

- Lack of support after training (Brazil); and,

- The women entrepreneur can lose interest/enthusiasm.

Additionally, businesses could come to halt due to family relationship gone bad or other issues. For example a woman in South Africa was running the business in her mother-in-law’s place (with no rent paid or lease agreement); so when her mother-in-law decided not to allow her daughter-in-law to run the business and locked the place without any notice, the woman was caught unaware without any income/money or place to run her business and she was forced to sell her stock at below market prices just to get out of the premises.. This was a learning to create an agreement and was subsequently advised during training.

Discussions on the ground indicated that there were cases of failures, largely due to external factors beyond the control of the programme, as in Brazil, the economic crisis, the evaluation felt that support after training (in Brazil) could have been addressed by the programme.

Both Egypt and South Africa had several common positive results due to the programme, including increased income, and growth in business, less financial assistance from others and increased ability to meet basic expenses which all indicate the contribution of the programme to increased economic participation and economic empowerment of women in these countries.

Increased awareness on women’s economic rights/gender equality and the benefits of women’s economic participation

The extent of promotion of women’s economic rights, gender equality and benefits of women’s economic participation varied widely among the countries, although positive. The maximum gains from the efforts in Brazil.

The signing of the CEO Statement of Support for the Women's Empowerment Principles, developed by UN Women and the UN Global Compact by TCCC CEO (at the time of launch of this Programme) enhanced corporate leadership for gender equality in the workplace, the marketplace and the community. The partnership with TCCC also enabled UN Women Executive Director to present/deliver remarks in several sessions at the World Economic Forum in Davos (including the reception of 500 prominent guests, hosted by TCCC), on the importance of/barriers for gender equality and women’s economic participation.

Comments from Brazil on WEPs Component of the Programme

“We have signed the WEPs (5&6) in 2015. The partnership with UN Women has helped us start developing a strategy to carry out gender affirmative procurements when buying from supplies……we are also starting a project to prevent violence against women in some communities were our factories are located”

“The WEPs are a start, but we need to do a lot more if we want to see things different in our country”

“Signing the WEPs (5&6) meant that the company has made a political commitment to promote gender equality and women’s empowerment. It is a first step, as it takes time for the results to show………the companies in Brazil are still learning how they can implement the WEPs”

“There is a government programme (Pro-Equidade) created to accredit companies based on practical measures adopted to promote gender and race equality. It has been recently opened to private companies also. Initially WEPs was seen as a less robust alternate to Pro-Equidade. But now WEPs is seen as an entry point or the first step for Brazilian companies to get accredited by Pro-Equidade”

The Brazil programme reactivated the informal network of companies who had signed the WEPs in the past through several discussions. The Programme in Brazil has been very successful in increasing the number of WEPs signatories (adopting principles 5 and 6) from 58 in 2014 to 77 by the end of 2015 – these efforts have been further continued and at the time of this evaluation this number has risen to 98 with the perspective of well surpassing the 100 signatories’ threshold before the end of 2016. The programme in Brazil has also contributed to the increase in the number of companies applying to obtain the seal of quality from the Brazilian Federal Government’s Gender and Race Equity Programme.  Additionally, it was noted that the programme’s efforts on WEPs component also has led UN Women Brazil to sign agreement with three other companies including Citi. The WEPs component and the integration of human rights, gender equality and women’s empowerment aspects into the Coletivos training has contributed to increased awareness on gender equality and women’s empowerment (see box for stakeholder comments from discussions). However, at the Coletivos level, the educators remarked that it takes time to make people understand the concepts of human rights and gender equality in order to result in behaviour change; this cannot be done within the training or programme timeframe.

In Egypt, SFD conducted seminars as part of the programme to increase awareness on women’s economic rights and the benefits of women being involved in economic activities. TCCC Egypt organized public events promoting the programme and its link to women’s economic empowerment. The majority of the women entrepreneurs indicated during the focus group discussions that they face no resistance in their family/household, because their husbands are ill or are a seasonal worker with  wages that will not be able to support the family.  The support/no resistant to women being engaged in economic activity was also reflected in the end-line survey. Overall, the programme achieved its intended objectives; it contributed in building women’s capacity to manage and sustain their businesses, increased their economic opportunities by increasing their income and opportunities to expand their businesses. However, there was no conclusive evidence that suggests that the programme contributed in increasing awareness about women’s economic empowerment rights at the community level in Egypt.

In South Africa, the programme besides its alignment to national interests in terms of women’s economic empowerment was also in the forefront because of the success and impact of the programme. The programme also highlighted the importance of involving men, a community gate keeper, a fact acknowledged by various stakeholders during discussions as part of this evaluation.

Both in Egypt and South Africa, the programme increased awareness on women’s economic rights/gender equality and the benefits of women’s economic participation, through its various public events and media communications. However, the impact cannot be measured. The interest shown by companies like Barclays, Unilever, and Technoserve, in South Africa to understand the work and explore possible collaborations could be seen as a proof of increased awareness due to the communications and the level of success of the programme.

Documented changes of incorporation of women’s empowerment principles within the private sector and public companies

At the global level, at the time of the launch of the this programme TCCC CEO also signed a CEO Statement of Support for the Women's Empowerment Principles, developed by UN Women and the UN Global Compact, to bolster corporate leadership for gender equality in the workplace, marketplace and community. This also demonstrated the commitment to leadership on gender equality and women's empowerment as a business imperative.

Among the three countries, most of the progress with evidence on documented changes to the incorporation of women’s empowerment principles within the private sector and public companies were from programming in Brazil.

The first and very important outcome produced by the programme was in Brazil; this was the inclusion of human rights and gender equality principles in the Sustainable Procurement Manual edited by the Brazilian Business Council for Sustainable Development. This manual is used by the Council’s affiliated companies which includes 70 of the largest business groups in the country.

Interviews revealed that there is a commitment by TCCC Brazil’s procurement department to start implementation of affirmative procurement processes within their supply chain in the near future. The potential for positive impact of such initiatives, given the importance of TCCC in the Brazilian market, is expected to be high. Although other companies might have already adopted some affirmative actions towards women’s economic empowerment through their procurement processes, the exact number was not known to stakeholders interviewed. As highlighted earlier, the Programme in Brazil has also been very successful in increasing the number of WEPs signatories (adopting principle 5 and 6) to 77 in 2015 and 98 at the time of this evaluation.

5.	Lessons from the Programme

The lessons from the programme, summarized below, are based on discussions with key informants at various levels (corporate and in the country) synthesized with information gathered from the document review. The lessons have been grouped into overall programme and country specific lessons.

## 5.1	Overall

The best practices emerging from the programme, included:

- Having a frank and open dialogue, to understand each other, including where each one comes from, what it means, the “language”, to create an atmosphere of trust and transparency. Coming from two different sectors this was important;

- The governance structure – Steering Committee (at the global level) and the commitment of its members was crucial and how it functioned. Unlike many programmes, the Steering Committee members were already in discussion, even before the programme was launched; Lessons included:

  - Being open to discuss what worked, what did not work and how to make it work – “with no glossing over” as remarked by a stakeholder;

  - Addressing issues together. There was common messaging from both sides down to their respective country teams, specifically when addressing issues at the country level;

  - Taking joint responsibilities – “good or bad”;

  - Ensuring a collaborative engagement at the country level; and,

  - Providing oversight but at the same time being attentive to details.

- Being up front so that the right thing is moving forward for implementation.

- Flexibility in allowing the country to decide on the model it wanted to use in the country to implement the programme – treating it as a pilot enabled an opportunity to learn;

- Successful UN agency and private sector partnership – a model that can be replicated (with some “tweaking”); and,

- A “donor” could be a “strategic partner” (a valuable lesson for UN Women).

Some of the challenges that affected the programme’s ability to achieve desired results, included:

- It took a longer time than initially thought to start implementation, in the countries. As one stakeholder remarked, “It does not start as soon as contract is signed and the money is sent”.  The building blocks have to be put in place, especially when two organizations come from entirely different sectors and organizational cultures (even though they might have a common agenda of women’s economic empowerment);

- Linked to the above, is the time for the “front-end” planning for the key partners at various levels; this was not planned or budgeted for at the country level;

- Ensuring that the teams (in TCCC and UN Women) in the countries worked together. This was hindered by various factors, including :

  - Two organizations coming from entirely different sectors with different organizational cultures (including the “language”) and the way of managing projects and achieving results;

  - Turnover of people – while TCCC had a consistent team in all three countries, UN Women (as a new entity) was faced with challenges of turnover including at the senior management (country representative) level in all three countries leading to loss of corporate (project) memory and time taken to recap and bring them on board. It  was valuable that Brazil and South Africa had dedicated project managers in UN Women;

  - The time taken to agree upon a “shared goal” and activities to be undertaken in the country;

- Monitoring data on key outcome indicators at the country level; and,

- External context – political upheavals (in Egypt); economic context (in Brazil); and protests and xenophobia (in South Africa).

In terms of potential practices or tools from the programme that can be replicated include:

- The models in each country are unique and are all  replicable in other countries, depending on the context, and programme objectives, with some adaptations;

  - The model in South Africa might be the simplest (and very focussed) to achieve women’s economic empowerment and integration into TCCC or private sector value chain;

- Similarly training tools from all countries are adaptable and replicable to other countries;

- Having programme governance structures that are committed, overall (globally) and in the countries;

- (In the UN Women context) - Having countries plan the programme (bottom-up) to contribute to the overall goal of a global programme financed by single “donor” – different projects with similar objectives contributing to one global goal; and,

- Ensuring that at least one person in the programme/project is constant or dedicated for the entire life of the programme (specifically in the countries) with a commitment to the project, especially when working in partnership - e.g. South Africa and Brazil.

Areas of improvement for the overall programme design, planning and implementation, included:

- One area that UN Women and TCCC should consider for a programme of this nature is the time for “front-end” planning and “coming together”;

- Another aspect that the UN Women would want to consider is the procurement mechanism, which could at times affect project/programme start and continuation (especially if contracting is done year to year for a three-year programme/project) – which also led to trainers leaving before the end of the years, due to uncertainty of continuation, as noted in South Africa;

- Exchanges (even virtual meetings, if cost was a consideration) among the three country teams coordinating the Global Programme - Brazil, Egypt and South Africa could ensure cross-country programme  sharing and learning and help them to think of innovative ways to improve their respective work. This was important not only as a best practice, but also specifically in this case as it was a pilot. The programme missed out on this opportunity during its life time; and,

- Scope to improve monitoring at the country-level (in varying degrees) including creating a baseline not only for output indicators but also for outcome indicators.

## 5.2	Country-specific

These are lessons from the programme specific to each country. If there were common lessons (positive and negative aspects) they have been addressed in the “overall” section earlier.

BRAZIL

Best practices from Brazil included:

- The strategy of embedding human rights, gender equality and women’s empowerment contents within existing training activities or in manuals targeting women, other populations or organizations (public and private) has seemed to be very successful to produce positive results and become sustainable in the long-run; and,

- The approaches adopted to promote the WEPs were very successful, especially the inclusion of human rights, gender equality and women’s empowerment content in a guideline to orient sustainable development practices among companies that have a wide penetration in the whole country.

Key challenges that affected the programme in Brazil to achieve results included:

- ICCB, in agreement with UN Women Brazil, initially selected some Coletivos to be part of the Programme (e.g., arts and community leadership), which were subsequently not included due to lack of feasibility, among other reasons. Also, the Coletivos Entrepreneurship, even though included in the implementation, did not provide the expected results;

- Establishing strategies to work with the recycling cooperatives in terms of promoting human rights, gender equality and women’s empowerment issues proved to be way more challenging than initially expected. The current strategies adopted by the Programme’s field analysts to do this work are being questioned about whether they will produce the desired results. Strengthening recycling cooperative is a medium to long-term process;

- One limiting aspect for Coletivos Retail is that the training was not enough to bridge some structural gaps related to communication (literacy, language, speech etc.) for enrolled youth. The Programme has a greater probability to benefit more people if a local NGO partner can provide additional support to the youth to help them bridge these structural gaps; and,

- Challenges faced by community trainers, as per discussions with them, included:

  - The contents on human rights, gender equality and women’s empowerment did not have enough time within the training curricula to be properly addressed; and,

  - The difficulty they face in dealing with the issue of sexual orientation and identity. Since there are no specific guidelines on this subject in the training and educational materials they have available from the programme, they found themselves in some “tricky” situations without knowing how to proceed. – Discussions with UN Women revealed that this was not part of the training curricula.

Some areas where the programming in Brazil can be improved included:

- The robust system for monitoring programme results is based on quantitative measures.  There is a need to collect more qualitative information about what is going on in the field, especially when they need to explain why some expected results are not becoming a reality or when contradictory results are obtained;

- Number of indicators to be tracked over time by the monitoring system seems to be overwhelming. It could focus on key indicators at staggered time frames;

- Reconsider how the themes of human rights, gender equality and women’s empowerment are included in the lessons plans. Community trainers were finding it difficult to return the focus of students to the technical issues discussed in the class after they start discussing the human rights, gender equality and women’s empowerment themes; and,

- Monitoring tools need to be reviewed to measure better the progress of companies on WEPs. The tool of the WEPs Brazil Award can be considered as a potential monitoring tool.

EGYPT

The best practices emerging from the Egypt programming included:

- Outsourcing local trainers for training delivery created administrative efficiencies. It also enabled the use of language and examples from the local contexts that participants could relate to;

- Using simplified proven curriculum - simplified version of the proven ILO GET Ahead for Women in Enterprise Training Package - played an important role in enabling better learning outcomes for women;

- Asset transfers as a model for women economic empowerment accompanied by training was perceived to be the cornerstone of this programme; and,

- Identifying strategic partners - local organizations such as SFD and WMN - was essential for the timely implementation of the programme.

Key challenges that affected the ability of the programme in Egypt to achieve desired results included:

- Unstable political situation in the country, which caused delays to programme activities;

- Diverging implementation approaches and expectations between the programme partners (UN Women and TCCC in Egypt) affected the programme’s timelines, and resulted into substantial investments in consensus building; Examples include:

  - Kiosks model (which was not feasible and therefore led to changes in programme plan); and,

  - Choice of refrigerator supplier (import vs. local supplier);

- The above two also affected the time available to achieve increased awareness in the local communities about women’s economic rights and the benefits of women’s economic empowerment.  Additionally, the lack of measurement or tracking of these results could also be a contributing factor for non/low achievement.

Some areas of improvement for the Egypt programme include:

- Ensuring that the strategies and models are based on evidence and appropriate to the targeted communities (e.g. kiosk tricycles, retail outlets, refrigerators) and that they meet the actual needs of women entrepreneurs (even if the programme is relevant to the context);

- Ensuring clarity of roles and responsibilities among implementing partners and having regular communication and information exchange (e.g. monthly meetings etc.);

- Having a framework and structure to manage expectations and having an open and frank dialogue (UN Women and TCCC); and,

- Having more balanced time for planning and implementation, particularly the latter.  The short time frame to implement (8 months) the programme meant no time to carry out a mid-term evaluation and no time to track outcomes.

SOUTH AFRICA

Important best practices emerging from the South Africa programme included:

- Coming to a common understanding was very important to the partnership. It should be noted that the organizations came from entirely different sectors and organizational cultures, way of working and making decisions. It was important to have a shared vision and shared space. Although there were challenges, the partners had ironed out and learned to work toward to the common goal. Understanding ethics and boundaries was important. They decided to have red (don’t go there), grey (discuss and sort out) and green (go ahead and do) areas;

- The partnership (TCCC-UN Women- Hand in Hand) with “common values” and trust in many ways “mirrored” the working style and principles of the Global Steering Committee. It was seen as “Best in Class” by TCCC (corporate). Highlights included:

  - Common messaging down the line to the field;

  - All three worked as equal partners (not the “usual” donor – implementer relationship), largely due to the people involved - their relationship and commitment – and partly, also due to the interesting fact that UN Women was a co-manager (with TCCC) and co-implementer (with Hand in Hand);

  - The effective partnership was also reflected on the ground – in the support and working relationship of bottlers/bottler representatives and trainers in the field, in general (some issues noted); and,

  - Contribution of “EDUBUS” by a bottler – making the bus (modified as mobile classroom) available for training purposes at no cost;

- Functional and effective project governance, structure and processes:

  - Steering Committee (meeting quarterly) with senior management of the UN Women, TCCC and Hand in Hand; and,

  - Monthly project management meetings between UN Women and Hand in Hand senior management, operational managers and trainers from the field. This facilitated not only “report back from the field” and feedback on the reports but also opportunity to address challenges, look at opportunities and also build capacities of trainers (refreshers and peer-to-peer learning), in addition to team bonding/building;

- Linked to the above three is the level of coordination among the three partner organizations;

- Layered capacity building model (all of them were Hand in Hand staff on contract), entrenched in the community – enabling follow-up, sustainability of capacities, trust in the communities:

  - At the national level one lead trainer supported by provincial mangers (where applicable) at the top level;

  - “Provincial trainers” in the communities (selected from the community/municipality they work in – many with community social worker background); and,

  - One of two enterprise development facilitators (from the communities/ municipalities they work in) under each provincial trainer;

- Having a dedicated full-time person (UN Women). Continuity of key implementing people and top management support commitment was very critical to the success in South Africa;

- Creating the “buy-in” and ownership in DSBD leading to investment in women entrepreneurs;

- Focused (and  innovative) approach to target women who already have a “business”; and,

- Training men, who are community gatekeepers.

The key challenge was the year-to-year contract of the implementing partner, which meant difficulty in maintaining trainers and enterprise development facilitators. Although Hand in Hand lost some people, it was able to cope.

Potential practices from South Africa that could be used and/or replicated elsewhere included:

- The model of implementing the training program is a potential best practice that could be adopted/adapted to any development programme that is building capacities. The programme had one lead trainer at the national level;

- Ability to show tangible results in a capacity building initiative. It has already attracted new partners;

- The model can also be replicated in other emerging markets for developing micro-enterprises in general and specifically focused on women. Adding technology would help in monitoring and tracking. A good simple model for 5by20;

- The entrepreneurs could be targeted for other programmes. This has been already seen from the fact, 920 of them were selected for workshops organized by DSBD and UN Women. These workshops complemented the UN Women- TCCC programme – and the participants were eligible to apply for equipment purchase; and,

- The database created could be used for planning other programmes. However, in addition to ensuring clarity of database ownership, security and maintenance, care must be taken to respect local privacy laws.

Some areas where the programme in South Africa could be improved include:

- The process of contracting an “implementing partner” for a well-defined three-year programme. This will ensure continuity of people and activities and avoid uncertainties;

- Some of the key entrepreneurs could be identified as mentors – this is being addressed in 2016; women (40) have been selected from different provinces and are being trained to be mentors; and,

- While monitoring was good, it largely focused on the implementation to ensure the achievement of targets. There is scope to improve reporting of follow-up (hugely under-reported), and also tracking key indicators that are relevant to the outcomes of the programme (e.g. income, savings, employees, etc.) during the life of the programme.

6.	Conclusions

The conclusions have been drawn based on evidence that emerged during the evaluation and the identified lessons learned.

Relevance

The programme was designed with a goal to increase women’s economic empowerment, especially those who are most excluded. Given the economic, cultural and political contexts in the three countries (Brazil, Egypt and South Africa), the programme was highly relevant. The global indicators and national statistics reflect income inequality, gender inequality, and lower participation of women in labour market, and higher unemployment rate for women, as compared to men, in all three countries. Overall, the programme design, be it training on business and entrepreneurial skills (all the three countries), asset transfer (Egypt),  employability (Brazil) and promotion of WEPs (Brazil), was appropriate to reach the intended objectives set out for each country; this included training material, tools and the business model.  The programme was not only aligned to but also contributed to the corporate level and country level objectives of UN Women and TCCC and 5by20 initiative, with reference to women’s economic empowerment.

Effectiveness

The programme implementation arrangements, effective partnership and programme management were effective to achieve/almost achieve the targets set for each country. The programme reached a total of 42,703 women including entrepreneurs, recyclers and young women entering the job market.  A committed Steering Committee at the global level providing oversight and also paying attention to details and being flexible to allow countries to decide on the business model and implementation arrangements was an important factor contributing to the effectiveness of the programme. Partnership (UN Women-TCCC) worked well when there was a common understanding and a shared goal, with mutual trust, transparency and joint ownership of both “good and bad”, as seen from the working of the Steering Committee, and the teams in Brazil and South Africa. Programme management structures and joint planning and decision-making contributed to effective partnership in Brazil and South Africa. Senior management commitment was also crucial in the countries for the UN Women–TCCC partnership.

Strong local partners and good coordination were crucial to implement the business model chosen in each country, whether it was through one “main” partner (as in Brazil and South Africa) or four different partners (as in Egypt). Furthermore, “joint messaging” from Steering Committee to the countries and within the country in South Africa (by the country team) was an important element for effective programming to achieve the objectives.

Although Brazil benefitted from an already existing monitoring system, there was scope to improve monitoring mechanism in varying degrees, in all the countries. Overall, most of the programme’s direct actions including delivery of training and development of training materials and tools have proved to be effective in all the three countries, irrespective of the model and approach. The promotion of WEPs has been more effective in Brazil than in the other two countries. However, it was too early for the evaluation to assess outcomes and/or the extent of implementation of WEPs (specifically principles 5 and 6) by the signatories in Brazil.

Efficiency

The programme showed mixed results in terms of efficiency.  In spite of large start-up delays in Brazil (8 months) and Egypt (28 months), all three countries were able to complete the programme activities on time (with three month no cost extension) with the support from strong local partners and efficient coordination. Delays in implementation were due to time taken to agree on the business model, programme outputs and/or criteria for selection of suppliers/beneficiaries/local partners, in addition to team “dynamics” and/or external factors. Although allocation of human resources was found to be appropriate, the turnover of staff and senior management (country representatives) in UN Women at various levels affected programme planning and implementation in in varying degrees. Having a dedicated programme person in UN Women increased programme efficiency (as seen from South Africa and Brazil).

The programme was implemented within budget.  The ability of the programme to leverage additional resources and in-kind contribution in the countries added value.  While due diligence is important, there is scope to improve contracting process in the UN Women system to avoid delays.

The programme reflected high efficiency in terms of rate of people trained per day during the implementation period and also the cost at which they were trained, compared to many similar development sector programmes.

Sustainability

There is no doubt the skills provided to entrepreneurs will help them continue to operate their businesses successfully for a reasonable period of time.  They have been able to put into practice the concepts and skills they have learned from the training with positive results. However, the entrepreneurs do not exist in in isolation from their context, and so the threats to sustainability may be beyond the scope of the programme.

There has been a high level of support, ownership and leadership commitment at the national level from private sector companies and business organizations in Brazil and Government in South Africa. The Government in Egypt has also shown support to the programme. The programmes have also attracted support and ownership from national partners and local organizations in all three countries during the time of the programme.

Lack of exit strategies was seen as a limitation in terms of mechanisms to ensure sustainability.  The models in each country have proved to be unique and successful in their respective contexts. The models are scalable and replicable. On one end there is the South Africa model which is straight forward (simple) and easier to replicate and scale-up with right partner (s) in many contexts, in terms of developing business and entrepreneurial skills in  retail, while on the other end the “creative” Brazil model will be successful in promoting and integrating WEPs.  Replicating and achieving the same success in WEPs as in Brazil could prove to be difficult in some contexts.  The model in Egypt is also a scalable and replicable in appropriate contexts, if there is a committed local partner to complement the programme with micro-loans from their own funds.

The programme has been able to transfer knowledge and build capacities at various levels starting from women and communities to trainers and organizations. There is institutionalization and increased knowledge in all three countries in terms of WEPs among all partners, including TCCC and UN Women. UN Women has also evolved into much stronger organization in terms of its technical expertise and comparative advantage since its inception.

Impact

The empowerment of women through capacity development was at the core of the programme, reaching 42,703 women across the three countries. The contribution of the programme through capacity building was evident from the women using the skills learned in establishing and sustaining their micro-business, applying for employment and/or managing the cooperative. Women entrepreneurs have increased access to networking and business support in some ways; most commonly through the formation of informal small groups of people who attended training (still in early stages). Events organized in the countries by the programme and interests shown by local government have been other instances where women entrepreneurs have been able to access business support mechanisms. The programme has increased economic opportunities and access to livelihoods for the poor and excluded women in the three countries with better success in South Africa and Egypt compared to Brazil. This was seen from increased income, better financial management, expansion of business and better ability to meet basic needs. An indirect benefit to women who attended the training was their increased confidence and self-esteem. While Egypt and South Africa increased awareness on gender equality and women’s economic rights among women entrepreneurs trained and through public events, it is not evident how much the programme contributed to the increased awareness in the communities. However, the success of this programme (in terms of women’s economic empowerment and integration into the value chain) has evoked interest among a few private sector companies in South Africa. On the other hand Brazil has been very successful in promoting and creating awareness on human rights, gender equality and women’s empowerment in the larger community and specifically, among the public and private sector companies including documented changes.

Overall Conclusion

Overall, the programme has proved to be a good example and a success story of public-private partnership, in contributing to women’s economic empowerment. The intent to test out various models in different countries has also generated a lot of learning for both organizations for future programming and partnerships. Trust, transparency and investing time to understand each other were key factors in the partnership and successful implementation. Overall, it was a good investment with positive results.

7.	Recommendations

The following recommendations are based on the findings and conclusions presented in the report. The recommendations are focused towards future programming and partnerships on women’s economic empowerment.

Recommendation 1: UN Women should ensure the following in its future programming:

- Developing an exit strategy, irrespective of whether the programme is going for a next phase, a scale-up or a closure; and executing it as part of the programme before the end of the programme and/or its current phase.

- Having a well-defined monitoring system in place right from the beginning of the programme. Thoughtful planning, beyond baseline/endline or training satisfaction surveys should be put into developing the systems. This should include: data collection schedule; mechanisms and tools during the programme; and, data collection to capture outcome results in addition to output indicators.

- Allowing sufficient time for “front-end planning” especially when partnering with organizations with different organizational culture and/or from entirely different sectors. This is a lesson for TCCC also.

- Ensuring that there is an opportunity for cross-country exchange of information and learning in Global Programmes, specifically when it is on women’s economic empowerment. These could be virtual meetings once or twice a year (if budget is a constraint).

Recommendation 2: UN Women should replicate (adopt/adapt) the programme governance and management structures and practices while working with private sector companies and other “donors” on a Global Programme. However, UN Women is likely to require a dedicated person to manage and coordinate at headquarters level and with countries if it is a large programme implemented in several countries.

- Continue the practice of having a committed small global steering committee at the corporate level with a two-tier structure at the country level – a country steering committee and a project management committee with regular productive meetings; this has proved to cement the partnership and implement the programme effectively.

- This programme was considered a pilot and implemented only in three countries. Therefore the Global Steering Committee was able to provide oversight and also provide direct inputs to countries, when required. However, this (direct inputs) may not always be possible when the programme is large and implemented in several countries. Even within UN Women, coordination is required for the programme among divisions (Programme, Strategic Partnerships and Communication, etc.). Hence UN Women should consider having dedicated personnel to coordinate private sector partnership programmes. Preferably this person should not be coordinating “traditional donor” programmes.

- With increasing efforts of UN Women to collaborate with the private sector, the UN Women Programme Division should create a specialized unit or a section to manage all the private sector partnership programmes. The dedicated person suggested in the earlier recommendation can be part of this programme unit. This will help UN Women to manage these private sector partnership programmes more effectively and efficiently with appropriate focused monitoring and reporting.

Recommendation 3: UN Women should strive to leverage its comparative advantage and technical expertise on WEE by partnering with organizations that bring business expertise and provide economic opportunities for women in their value chain. At the same time, UN Women should keep in mind that private sector companies bring unique strengths to development projects, especially their communication and outreach capabilities, in addition to their business expertise. These capabilities could increase UN Women programmes visibility and outreach, and broaden its impact.

- UN Women should identify more private sector companies that can support it in achieving its development agenda and goals, and with business opportunities that are relevant to target communities.

- At the same time UN Women should look at opportunities to partner with private sector companies and  add value their programmes that address women’s economic empowerment at the grassroots (as in 5by20 initiative).

Recommendations 4: UN Women and TCCC should explore opportunities to continue partnership.

- Within the 5by20 initiative, replicating/scaling up the simpler South Africa model would be more feasible in many contexts. It  has been more successful in the retail segment in  building capacities of women entrepreneurs to establish and sustain their business (among the three countries);

- At a more corporate level, explore how both partners can add value to each other’s overall strategic objectives, in terms of women’s economic empowerment (building on the lessons and synergies from this programme).

Recommendation 5: UN Women should keep in mind that while partnering with private sector companies, finding the balance between “development objectives” and “business objectives” is crucial for a successful and long-term mutually beneficial partnership. This requires a frank and open communication and building trust.

- Based on experience and lessons from the programme, it is important to consider the private sector as a strategic partner and not as a “donor’. It is important to capitalize on and add value to each other’s strengths; and,

- Focusing on optimizing the entry point and partnership with the private sector through engagement on levels that can benefit both partners is critical. This may vary country to country, when trying to design/implement a global programme.

Annexes

Annex A - List of Documents Reviewed

Corporate Documents

- Women’s Economic Empowerment and Integration into the Value Chain of The Coca-Cola Company in Brazil, Egypt and South Africa – Third Progress Report (January – December 2015

- Provisional Financial Donor Report for Period Ended December 31, 2015

- Women’s Economic Empowerment and Integration into the Value Chain of The Coca-Cola Company in Brazil, Egypt and South Africa – Final Progress Report (January 2013 – December 2015)

- UN Women – TCCC Steering Committee Meeting (May 12-13, 2015), Final Notes

- An Empowered Future – Corporate Evaluation of UN Women’s Contribution to Women’s Economic Empowerment – UN Women Independent Evaluation Office, NY – December 2014

- UN Women – TCCC Steering Committee (October 28, 2014) Notes

- Women’s Economic Empowerment and Integration into the Value Chain of The Coca-Cola Company in Brazil, Egypt and South Africa – Second Progress Report (January – December 2014

- Interim Financial Donor Report for Period Ended December 31, 2014

- Mid-term Evaluation of the Women’s Entrepreneurs Project in South Africa, 2014

- Baseline Study for the Design and Implementation of a Programme to Support “Women’s Economic Empowerment and Integration in the Value Chain” – Final Report, June 2014.

- Women’s Economic Empowerment and Integration into the Value Chain of The Coca-Cola Company in Brazil, Egypt and South Africa – First Progress Report (January – December 2013

- Interim Financial Donor Report for Period Ended December 31, 2013

- Project Document – Women’s Economic Empowerment and Integration into the Value Chain of The Coca-Cola Company in Brazil, Egypt and South Africa – dated November 5, 2012

- UN Women and The Coca-Cola Company Partnership on Women’s Economic Empowerment - Country Guidance Note (undated)

- UN Women Strategic Plan 2014-2017

- UN Women Strategic Plan 2011-2013

- TCCC – 5by20 Overview (http://www.coca-colacompany.com/5by20)

- The Coca-Cola Company’s 5by20 Initiative – Empowering Women Entrepreneurs across the Value Chain – Harvard Kennedy School and Business Fights Poverty, 2013

- Coca-Cola 2011/2012 Sustainability Report – Women’s Economic Empowerment (http://www.coca-colacompany.com/sustainabilityreport/we/womens-economic-empowerment.html), November 7, 2012

Documents Specific to South Africa

- Project Overview - Briefing Presentation by UN Women South Africa, October 3, 2016

- Presentation on EWEP by Hand in Hand, Southern Africa, October 3, 2016

- Minutes of Meeting between UN Women, Department of Small Business Development, Hand in Hand and TCCC – August 2, 2016

- Minutes of Meeting between UN Women, Department of Small Business Development, Hand in Hand and TCCC – August 18, 2016

- Impact Evaluation of Coca-Cola’s 5by20 Program – Final Report for South Africa Pilot – May 2016 (Power Point Presentation)

- Presentation on South Africa Program to Global Steering Committee – May 12, 2016

- The Small, Medium and Micro Enterprise Sector of South Africa – Research Note by University of Stellenbosch and Small Enterprise Development Agency (SEDA), South Africa, January 2016

- Summary Presentation – 5by20 Validation Visit, South Africa November 10-12, 2015 by Anne Euler and Ivaylo Dimov

- UN Women – TCCC Partnership South Africa Update – October 2015

- Presentation of South Africa Program to Steering Committee, Johannesburg – May 12, 2015

- Mid-term Evaluation of Women Entrepreneurs Project in South Africa by Rosa Izquierdo

- Monitoring Plan for EWEP in 2015

- Draft Concept Note -  Workshops to Integrate Empowerment of Women Entrepreneurs Project (EWEP) Beneficiaries Into Department Of Small Business Development’s Informal Micro Enterprise Development Programme (undated)

- Initial Concept Note – UN Women and the TCCC  Women’s Economic Empowerment Partnership in South Africa (undated)

- South Africa – United Nations Strategic Cooperation Framework 2013-2017, Final Draft, May 2012

- EWEP Event and Success Story videos

Documents Specific to Egypt

- Baseline Survey Report- 2015

- Detailed Report on Women's Economic Empowerment Project (in Arabic)- by Social Funds for Development

- Focus Groups Guide- Baseline Survey

- Implementation Update: January 2016

- Implementation Update: August 2015

- Implementation Update: July 2015

- Internal UN Women Update: 18 March 2015

- Partners Financial Contribution (Excel sheet)

- Pre-Post Survey Questionnaire

- Progress Report - Women's Economic Empowerment (in Arabic)- by Social Funds for Development

- Project Work Plan March 2015

- Strategic Note UN Women Egypt Country Office

- Strategic Plan June-December 2015

- Success Stories (videos)

- TCCC May 2015 Steering Committee: Country Update Egypt

- Women's Economic Empowerment and Integration into the Value Chain of the Coca-Cola Company "Egypt"- Performance Monitoring Plan April 2015

- Women's Economic Empowerment and Integration into the Value Chain of the Coca-Cola Company "Egypt"- Post Intervention Survey Report

Documents Specific to Brazil

- Brazil Updates for October TCCC Global Steering Committee Meeting

- Relatório Metodológico Reciclagem 2015

- Brazil - Detailed implementation plan 13 10 2014 (recalibrated plan)

- Implementation Costs and Expenditure Plan (30 04 2015)

- Apresentação Reciclagem_Ondas 0 1 2 e 3_ Interpretações IPSOS + ICCB -  06Set (002).pptx

- Brazil Updates for January_2015_TCCC Global Steering Committee Meeting ng (FINAL)

- Budget Control - Expenses, Committed and Planned

- Caderno de Leitura (Projeto Gênero e Direitos Humanos - Construindo Diálogos para a Autonomia Econômica)

- CEBDS - Manual of Sustainable Procurement (http://biblioteca.cebds.org/manual-de-compras-sustentaveis)

- Coletivo e a Parceria com a ONU Mulheres - Setembro de 2014

- Coletivo e Parceria com a ONU Mulheres - Setembro de 2015

- Coletivo Entrepreneurship – Guide for Entrepreneurs (http://www.onumulheres.org.br/wp-content/uploads/2016/04/Guia-bxa-res_completo.pdf)

- COLETIVO RECICLAGEM descritivo

- Coletivo Retail – video about gender equality (Video): (https://www.youtube.com/watch?v=ZCGLC-vziRc)

- Coletivo Retail – video about human rights (Video): (https://www.youtube.com/watch?v=hGKAaVoDlSs)

- Coletivo Retail – video about women’s empowerment (Video): (https://www.youtube.com/watch?v=6RSc_XYezig)

- Compilação Resultados_Parceria ICCB_ONUMulheres_Junho_2016

- Descrição do Col Varejo e Reciclagem

- SP Evaluation_BRAZIL - Final Case Study Report

- Summary Monitoring Results UN Women Partnership Brazil – August 5 2016

- TCCC BRAZIL Update (10 06 2015 - v3 FINAL)

- TCCC Brazil Abril 2015 updated report

- WEPs Brazil Awards (Website): (http://premiowepsbrasil.org)

- WEPs Guidebook (http://www.onumulheres.org.br/wp-content/uploads/2016/04/cartilha_WEPs_2016.pdf)

- WEPs website (http://www.weprinciples.org)

- WEPs Avaliacao Coca

Annex B - List of Stakeholders Interviewed

Global / Corporate Level Stakeholders (6)

| A.H. Monjurul Kabir | Head, Asia and the Pacific Section, UN Women, New York |
| --- | --- |
| Natia Cherkezishvili | Programme Specialist, Asia and the Pacific, Programme Division, UN Women, New York |
| Nancy Aburi | Account Manager, Partnership Unit, UN Women, New York |
| Kirstin Hetle | Former Director, Strategic Partnership Unit, UN Women, New York |
| Charlotte Oades | VP Global Director, Women’s Economic Empowerment, TCCC, London, UK |
| Angie Rozas | Group Director, Women’s Economic Empowerment, TCCC, Atlanta |
| Missy Owens | Director, Public Affairs and Diplomatic Relations, TCCC, New York |

Egypt (13)

| Alaa Hassan | M&E Consultant, Cairo |
| --- | --- |
| Amal Salah | Trainer, Gameya Lel Shabab- Local NGO- Cairo |
| Ahmed Aboul Gheit | Trainer, Gameyat El Shabab- local NGO- Cairo |
| Fatma Darweesh | Trainer, Social Funds for Development (SFD)- Fayoum |
| Karam Hussein | Trainer, Social Funds for Development (SFD)- Fayoum |
| Maha Ezzat | Trainer, Social Funds for Development (SFD)- Fayoum |
| Kholoud Soliman | Manager, Social Funds for Development (SFD)- Cairo |
| Ghada Makady | Senior Manager, - Public Affairs and Communication, TCCC Middle East and North Africa |
| Hoda Kamal El Mankabady | Programme Specialist, UN Women Egypt Country Office |
| Ashraf Aly | Finance Officer, UN Women Egypt Country Office |
| Gielan El Messiri | Senior Manager, UN Women Egypt Country Office |
| Amr Kamel | Manager, Wahed Men El Nas (WMN) |
| Mohamed Magdy | Project Officer, Wahed Men El Nas (WMN) |

South Africa (27)

| Anne Githuku-Shongwe | Representative – UN Women Multi-Country Office, South Africa |
| --- | --- |
| Themba Kalua | Deputy Representative – UN Women Multi-Country Office, South Africa |
| Susan Kimathi | Project Manager, UN Women Multi-Country Office, South Africa |
| Kizito Nsanzya | Regional M&E Specialist, UNFPA, RO for East and Southern Africa |
| Vukani Magubane | Director, Public Affairs and Communications Coca-Cola Southern and Eastern Africa |
| Asyia Sheik-Ojwang | Head of Public Affairs, Coca-Cola South Africa |
| Lawernce Gadzikwa | CEO, Hand in Hand Southern Africa |
| Sibongile Sibanda | Lead Trainer, Hand in Hand, Southern Africa |
| Portia Tsenyane | Trainer, Kagiso, Gauteng South Africa |
| Prudence Melares | Trainer, Vosloorus, Gauteng, South Africa |
| Samuel | Enterprise Development Facilitator, Kagiso, Gauteng, South Africa |
| Mzwandile Dwangu | Former Trainer, Western Cape, South Africa |
| Bonginkosi Ntlazulwane | Trainer, Western Cape, South Africa |
| Bukiwe Sojiji | Trainer, Western Cape, South Africa |
| December Dithake | Provincial Manager, Hand in Hand, Mpumalanga, South Africa |
| Kgotlelo Mogakane | Trainer, Matsulu, Mpumalanga, South Africa |
| Nokhanyo Dezele | Entrepreneur, Khayelitsha, Western Cape, South Africa |
| Zandile Nxumalo | Entrepreneur, Vosloorus, Gauteng, South Africa |
| Mbali Patricia Luvuno | Entrepreneur, Vosloorus, Gauteng, South Africa |
| Lehlohonolo Khauoe | Community Development Coordinator, Department of Cooperatives and Traditional Development, Vosloorus, Gauteng, South Africa |
| Lizo Songanga | Operational People Leader, Penbev (TCCC Bottler), Khayelitsha, Western Cape, South Africa |
| Semopo Mokgabudi | Deputy Director, Informal Business, Department of Small Business Development, Pretoria, South Africa |
| Miduelu Mkhabuva Jeremiah Nkosi Rayond Nkousi | Ward Counsellors, Matsulu, Mpumalanga, South Africa |
| Mavis Mathebula | Entrepreneur, Matsulu, Mpumalanga, South Africa |
| Martha Maphanga | Entrepreneur, Matsulu, Mpumalanga, South Africa |

Brazil (12)

Nadini Gasman		Representative, UN Women Brazil Country Office (CO)

Ana Carolina Querino	Programme Manager, UN Women Brazil CO

Rafaela Lamounier	Programme Associate, UN Women Brazil CO

Adriana Carvalho	Adviser on WEE, UN Women Brazil CO

Vanessa Tarantini	Partnership and Engagement – Executive Secretariat Network of the Global Compact Brazil

Pedro Massa		Shared Value Director, TCCC Brazil

Ana Tacite		Manager Programs, ICCB, Brazil

Adriana Fendt		Manager Planning and Finance, ICCB Brazil

Isa Lopes		Education Coordinators, Social Institute Coca-Cola Brazil

Guilherme Oliveira	Human Resources Manager, ICCB Brazil

Maicon Lopes		Operations Manager, ICCB Brazil

Aline Chagas		M&E Analyst, Social Institute of Coca-Cola Brazil

Annex C – Data Collection Instruments

Interview Guide for UN Women Staff

(Questions to be tailored for HQ and country staff)

- How were you involved in this UN Women – TCCC programme? What were your roles and responsibilities, specific to this programme? How did it fit into your overall portfolio/responsibility of your work in UN Women?

- Could you please explain how this UN Women – TCCC partnership come about? What has been the highlight of this partnership? What can be leveraged further?

- How (and why) were the countries selected?

- In your opinion, how were the programmatic approaches and strategies appropriate (at global level and at participating country level) to address the problems and achieve intended results? What could have been done differently with reference to programme design, approach (in terms of cultural, political or economic context)? Please comment on programme design and targets set.

- How were the needs in participating countries determined and taken into account in programme design? How could this be improved (more inclusive) in the future?

- How were partners identified in each participating country? Please comment on the partnerships (formal or informal, their roles and responsibilities, did the partners deliver, their performance, what worked and what did not, challenges). What needs to be done in the future to have more effective partnership?

- What have been highlights of the progress made / results achieved in the programme?  What have been the enabling as well as the hindering factors in achieving results? How were they overcome?

- Could you please talk about the implementation arrangements for the programme in the country? – (planning, decision making, horizontal/vertical communications, resource allocation, etc.) How did they contribute or hinder the programme in achieving results? What could have been done differently?

- In your opinion, was the programme implemented on time and within allocated resources (HR, financial, technical, etc.? What were the challenges (including adequacy of resources)? How were they overcome?

- Please comment on the monitoring and reporting mechanism/system (at global and country level)? Is there anything that you think could be done better / improved in terms of project/programme monitoring? Please explain

- Please comment on training conducted and capacity development activities of the programme? What has been direct impact due to this, in general and specific to women entrepreneurs in target communities (to start and sustain business)? Has there been trickle down/snow-ball effect or institutionalization of capacities?  Why or why not? Please explain. What needs to be done for to ensure that?

- In your opinion, what is the level of support/ownership/commitment to this programme, from national/local institutions? What should be done to ensure this (so that it can be scaled-up/replicated)?

- How does the programme fit into national (government) programmes and/or private sector value chains?

- Could you please comment on the following with examples? If there is no positive impact due to the programme – why? What should be done?

  - The extent to which women entrepreneurs have increased access (due to the programme) to networking and business support

  - The extent to which poor and excluded have increased economic opportunities and access to livelihoods (due to the programme)

  - The extent to which the programme has raised awareness of women’s economic rights and the benefits of women’s economic participation

  - Incorporation of women economic empowerment principles with the private sector companies (since the start of the programme)

- Were there any unexpected outcomes (both positive and negative)? How important were they?

- What has the programme done to ensure continuity of programme activities and positive changes (from the programme)? (exit strategy, mechanism in place, resources, local/national ownership, etc.).  In your opinion how likely would the programme activity and positive changes continue?)

- In your opinion, what are the best practices emerging from the programmes? Can you please provide examples of tools, practices that could be scaled-up or replicated?

- What are the lessons learned from challenges faced in the programme? (List examples of challenges and how they were overcome/could have been avoided)

- Overall, what are areas of improvement, (if you have not mentioned earlier)?

Interview Guide for TCCC staff

- How were you involved in this UN Women – TCCC programme? What were your roles and responsibilities, specific to this programme? How did it fit into your overall portfolio/responsibility of your work in TCCC?

- How did TCCC - UN Women partnership start? Why was this partnership important? What was unique or different in this partnership? How did it add value or complement the 5by20 initiative?

- How were the countries selected? Any criteria - needs, strengths, great to pilot, etc.

- Overall, what were the highlights of the programme? Where did it fall short? What could have been done?

- What was the level of involvement of TCCC at the country level?

- What are your thoughts on programme design, approaches and strategies (globally and in the country)? Were they relevant? Did they work? What were issues? How could they be improved /done differently?

- In your opinion were the resources provided and timeframe to achieve intended objectives adequate? Please comment

- In your opinion, did the programme monitor and report progress appropriately?

- How did the implementation arrangements/mechanisms and partnerships work or did not work in the countries? What was good and what needs to be improved in terms of long-term continuity?

- In your opinion, what is the level of support/ownership/commitment to this programme, from national/local institutions? What should be done to ensure this (so that it can be scaled-up/replicated)?

- To what extent did the programme contribute to getting beneficiaries integrated into TCCC value chain? Was it effective and efficient – in what way? What can be improved/ done differently?

- Could you please comment on the following with examples? If there is no positive impact due to the programme – why? What should be done?

  - The extent to which women entrepreneurs have increased access (due to the programme) to networking and business support

  - The extent to which poor and excluded have increased economic opportunities and access to livelihoods (due to the programme)

  - The extent to which (the programme) has raised awareness of women’s economic rights and the benefits of women’s economic participation?

  - Incorporation of women economic empowerment principles with the private sector companies (since the start of the programme)

- Were there any unexpected outcomes (both positive and negative)? How important were they?

- What has the programme done to ensure continuity of programme activities and positive changes (from the programme)? (exit strategy, mechanism in place, resources, local/national ownership, etc.).  In your opinion how likely would the programme activity and positive changes continue?)

- Were there any best practices for scale-up or replication or lessons for future programming?

- Any other comments or suggestions for improvement (if not mentioned earlier)

Interview Guide for National Partners (Government and Others)

- How were you involved in this UN Women – TCCC programme? What were your roles and responsibilities, specific to this programme? How did it fit into your overall portfolio/responsibility of your work?

- To the extent that you are aware of, what was unique about this programme? What were the highlights?

- What are your thoughts on programme design, approaches and strategies (globally and in the country)? Were they relevant? Did they work ? What were issues? How could they be improved /done differently?

- In your opinion, how did the implementation arrangements/mechanisms and partnerships work or did not work in the countries? What was good and what needs to be improved in terms of long-term continuity?

- Could you please comment on the following with examples? If there is no positive impact due to the programme – why? What should be done?

  - The extent to which women entrepreneurs have increased access (due to the programme) to networking and business support

  - The extent to which poor and excluded have increased economic opportunities and access to livelihoods (due to the programme)

  - The extent to which (the programme) has raised awareness of women’s economic rights and the benefits of women’s economic participation?

  - Incorporation of women economic empowerment principles with the private sector companies (since the start of the programme)

- Were there any unexpected outcomes (both positive and negative)? How important were they?

- What has the programme done to ensure continuity of programme activities and positive changes (from the programme)? (exit strategy, mechanism in place, resources, local/national ownership, etc.).  In your opinion how likely would the programme activity and positive changes continue?)

- In your opinion, what is the level of support/ownership/commitment to this programme, from national/local institutions? What should be done to ensure this (so that it can be scaled-up/replicated)?

- Were there any best practices for scale-up or replication or lessons for future programming?

- Overall, what could be done to improve /scale-up or replicate this programme?

- Any other comments or suggestions for improvement (if not mentioned earlier)

Focus Group Discussion Guide with Beneficiaries

- Could you please briefly state your name, where do you live, the organization you are affiliated with (if you belong to one), and what is your relationship with the TCCC/UN Women Global Programme (how long have you been involved, what roles have you played)?

- Think back and remember a time when you were most excited and proud to be part of the programme, and tell a story about that time. What happened? Who was involved?  What role did you play?  What were the contributing factors? (Probe for anything related to women entrepreneurship, access to networking and business support, increased economic opportunities and access to livelihoods)

- If you had to identify the most significant changes that have occurred as a result of the programme, what would they be?  Why are they so significant?  (Probe for changes at the system level and unexpected changes)

- What do you value most about the programme and the way it is being implemented? How do you assess the support provided by the programme in terms of training, development of tools, monitoring, and feedback/recommendations?

- To what extent and how has the programme set in place mechanisms to ensure the results produced will be sustainable in the long run? Have you got (i) people well prepared and committed, (ii) a strong and committed organization, and (iii) enough, diversified and sustainable sources of support (financial and technical)?

- Imagine that it is now 2020 and the programme has achieved its main goals for this phase.  How would the situation for you, your colleagues, your organization, your community/ neighborhood look like? What made it happen?  Who was involved?  What did you/they do? (Probe for anything related to women entrepreneurship, access to networking and business support, increased economic opportunities and access to livelihoods)

- Imagine you were walking in the street and found a magic lamp. After cleaning it, a genius appears and grants you three wishes for the programme as it moves into this next phase. What would they be? Why?

Focus Group Discussion/Group Interview Guide for of Local Partner Organizations

- Could you please briefly describe your and your organization’s relationship with the TCCC/UN Women Global Programme?

- Why and how your partnership with the programme was established? What gaps did it intend to bridge? How relevant and appropriate to your organization were/are the programme’s main objectives?

- If you had to identify the most significant changes that have occurred as a result of the programme, what would they be?  Why are they so significant?  (Probe for changes (i) related to women entrepreneurship, access to networking and business support, increased economic opportunities and access to livelihoods; (ii) beyond the most direct programme beneficiaries and at the system level; and (iii) unexpected positive or negative changes)

- What do you value most about the programme and the way it is being implemented? How do you assess the support provided by the programme in terms of training, development of tools, monitoring (including the use of M&E tools), and feedback/recommendations?

- What is your assessment of the timing of the programme’s activities? How did the schedule enhance and/or hinder programme’s results? Were there any constraints in relation to the human or financial resources destined to the programme (amount, flow, budget rubrics etc.)?

- To what extent and how has the programme set in place mechanisms to ensure the results produced will be sustainable in the long run? Have you got (i) people well prepared and committed, (ii) a strong and committed organization, and (iii) enough, diversified and sustainable sources of support (financial and technical)?

- Imagine that it is now 2020 and the programme has achieved its main goals for this phase.  How would the situation for you, your colleagues, your organization, your community/ neighborhood look like? What made it happen?  Who was involved?  What did you/they do? (Probe for anything related to women entrepreneurship, access to networking and business support, increased economic opportunities and access to livelihoods)

- Imagine you were walking in the street and found a magic lamp. After cleaning it, a genius appears and grants you three wishes for the programme as it moves into this next phase. What would they be? Why?

Annex D – Terms of Reference

TERMS OF REFERENCE (TOR)

For the Final Evaluation of the Global Programme  Women’s Economic Empowerment and Integration into the Value Chain of the Coca-Cola Company in Brazil, Egypt and South Africa

1. BACKGROUND & PROGRAMME OBJECTIVES

1.1 Programme Overview

UN Women and the Coca-Cola Company (TCCC) engaged in a global partnership to increase women’s economic empowerment. Working together, UN Women and TCCC aim to address common barriers hampering women’s access to economic empowerment and develop innovative business models for women’s entrepreneurship and social leadership and contribute to sustainable women’s economic empowerment at the systemic level in Brazil, Egypt and South Africa. UN Women Country Offices are responsible for programme planning, implementation and management.

Launched in 2013, the three-year global partnership between TCCC and UN Women works to empower 40,000 women in South Africa, Egypt and Brazil, with a focus on disadvantaged and excluded communities.

As part of the global partnership, UN Women also carried out advocacy to strengthen the enabling environment for women’s effective business development and management. UN Women and TCCC reached out to other key stakeholders with critical roles to play in the economic empowerment of women, working towards sustainable impact on an even greater scale.

A global communication strategy was developed by UN Women in collaboration with TCCC based on the contributions received through the country strategies.

The success of the programme will be assessed based on the extent to which programme interventions lead to improving women’s economic empowerment in participating programme countries: South Africa, Egypt and Brazil, by enhancing women’s business and entrepreneur skills leading to their empowerment.

1.2 Programme Goal, Objectives & Strategies

The overall goal of the programme is to increase women’s economic empowerment, through development and implementation of sustainable models to advance women’s economic empowerment with the objective to use these models to upscale and replicate to other private and public companies, Government and NGOs within the countries and possibly adapted to other countries. The programme will be implemented through tailored strategy to best respond to specific challenged and opportunities for women’s economic empowerment in South Africa, Egypt and Brazil. Depending on local needs programme implementation strategies will imply:

- To enhance women’s entrepreneurial capacity and skills so that they have greater ability to establish and grow their business, increase their earnings, create new jobs in their communities, so they can better manage and sustain their business;

- To support excluded women to establish small business by providing access to assets and credits;

- To strengthen the adoption of gender sensitive policy and develop capacity of private and public companies to apply gender equality and women empowerment principles in their system wide operations, networks and supply chain;

- To raise awareness and advocate for women’s economic rights and the value of women’s economic participation both at the community and national levels;

The programme implementation period is three years (November 2012 – December 2015) with a total budget of USD 3,974,355. The actual project was launched in early 2013.

The programme goals and outcomes in each participating country are:

South Africa

| Outcomes | Outcome 1: Sustainable business ventures enhance the livelihoods of low-income women entrepreneurs. Outcome 2: Low-income women entrepreneurs have increased networking access and business support mechanisms. |
| --- | --- |
| Outputs | Output 1.1: Financial literacy and business management skills of local women entrepreneurs strengthened to establish sustainable business ventures (addressed in Year 1 and work in progress). Output 2.1: Business network opportunities provided for low-income women entrepreneurs. Output 2.2: Knowledge-sharing platform promoting horizontal and vertical learning established. Output 2.3: Partnerships and links established between women entrepreneurs and organizations providing business support services and programmes, including financial services (started to address in Year 1). |

Egypt

| Outcomes | Outcome 1: Women have increased economic opportunities and access to livelihoods, especially those who are poor and most excluded. |
| --- | --- |
| Outputs | Output 1.1: Women entrepreneurs in target communities have increased capacity and skills to establish and sustain their own kiosks. Output 1.2: Women have access to assets, resources and products to establish their own businesses. |

Brazil

| Outcomes | Outcome 1: Low-income women entrepreneurs (community leaders and artisans) have increased access to economic opportunities and resources to manage and sustain their businesses. Outcome 2: Increased commitment and implementation of affirmative procurement policies and other policies promoting WEE in private and public sector companies. |
| --- | --- |
| Outputs | Output 1.1: Ability of women community leaders and artisans is strengthened to create, legalize and/or manage their businesses more efficiently (started in year 1). Output 1.2: Capacity of women entrepreneurs from Manaus is strengthened to have increased access to relevant credit services. Output 1.3: Knowledge of women community leaders and artisans about gender equality and civic rights enhanced (started in year 1). Output 1.4: Entrepreneurial skills of community peers of women community leaders and artisans enhanced (started in year 1). Output 2.1: A model for affirmative procurement policies targeting women-owned and women-majority businesses is demonstrated. Output 2.2: Capacity of Brazilian government and private sector institutions to formulate affirmative procurement policies and other policies promoting WEE strengthened. |

a. Capacity Development:

Through capacity building, the programme strengthens the capacity of women in entrepreneurship by equipping with necessary skills to increase their potential for active engagement in economic processes and business development. The programme follows an approach that defines desired capacities, assesses capacity needs, identifies capacity interventions and systematically monitors change in the existing capacities. Capacity development interventions include training, technical assistance, development of resources and accessibility of information, among others.

b. Knowledge Building and Information Sharing:

The programme invests in knowledge sharing and exchange activities to ensure coherence and sound technical assistance. By developing number of knowledge products programme aimed to ensure transfer of knowledge for women’s economic empowerment. Knowledge products also aim at providing information and knowledge to facilitate capacity development in participating countries on women’s economic empowerment and entrepreneurship.

c. Partnership building, coordination and engaging with multiple stakeholders:

By engaging with multiple stakeholders (government, TCCC, local companies) and creating or strengthening spaces for multi-stakeholder dialogue and strengthening joint commitment towards women’s economic empowerment.

1.3 Programme Management

The programme is managed by a joint UN Women Programme and Private Sector teams based in headquarters (HQ), and participating country teams comprising of a Programme Manager, and programme staff. Programme managers recruited in each project country are responsible for ensuring the overall implementation and day to day management of the programme at the country level.

1.4 Previous Evaluation Activities

A mid-term independent evaluation was conducted in late 2014, for South Africa Project. The evaluation found the project to be relevant, with dedicated and flexible management that enabled activities to be conducted in a trusted and collaborative way. The evaluation found that project partners were fully engaged and teams in the capital and in the field were knowledgeable. The findings and recommendations provide a useful review that contribute to the strategic focus areas of this Evaluation.

2. FINAL EVALUATION

2.1 Purpose of the Evaluation

The final Evaluation will be independent and conducted by an external team. It is mandatory as reflected in the programme document and agreed with the TCCC. The Evaluation is being undertaken towards the completion of programme implementation. The Evaluation will assess improvements in project participating countries by reviewing the programme design, implementation arrangements and achieved results and outcomes. It will assess progress of the programme against stated outputs and outcomes, as well as identify valuable lessons and recommendations to further expand on and scale-up the work on women’s economic empowerment.

2.2 Objectives of Evaluation

The main objectives of the Evaluation are as follows:

- Analyze programme outcomes and assess effectiveness of the approach and strategies used by the programme countries to increase women’s economic empowerment.

- Examine programme results in relation to the intended outcomes and outputs and identify the strengths and weaknesses in programme design and implementation to scale-up the lessons learned and improve future programming on women’s economic empowerment.

- Examine critical factors that enable or hinder effective achievement of intended results.

- Draw key lessons on the role of partnerships and multi-stakeholder mechanisms in the achievement of planned outputs and outcomes.

- Provide recommendations on how to address the critical factors that hinder effective achievement of intended results.

- Document lessons learned and best practices and provide recommendations to inform future work on women’s economic empowerment.

- Assess institutional capacity and potential for sustainability of the on-going work in programme countries.

- Assess implementation models and managerial structures created for the partnership

2.3 Main Audience

The main audience of the Evaluation is UN Women senior management, TCCC, programme coordinators and national partners.

2.4 Evaluation Coverage and Scope

The scope of the Evaluation will be defined by the timeframe and geographic coverage. The scope will include the project design, implementation and management, lessons learned, replicability and recommendations for current and future projects and initiatives.

Timeframe: The Evaluation will cover programme implementation from November 2012 until December 2015.

Geographic scope: The Evaluation will assess global and country-level programme components. With regard to the country-level assessment, the Evaluation team will conduct field visits in participating programme countries (South Africa, Egypt and Brazil).

2.5 Evaluation Criteria & Corresponding Draft Questions

The Evaluation will address the five criteria of relevance, efficiency, effectiveness, sustainability, and impact. In addition, the Evaluation will endeavor to collect any lessons learned to date that can support programme implementation and future efforts. The Evaluation will make informed statements about the anticipated sustainability and potential for impact of the programme, based upon the results achieved to date.

The following potential Evaluation questions are organized by each of the five Evaluation criteria. They are focused on the main, planned areas of programmatic achievement as described in the Project Document.

| Table 1: Potential Evaluation Questions |  |  |
| --- | --- | --- |
| Criterion | Main Evaluation Questions | Sub-Questions |
| Relevance | 1. Were the programmatic approaches and strategies appropriate to address the problem and to achieve planned results? | 1.1 Is the programme design the most appropriate way to reach intended outcomes? Are there other more efficient ways to achieve similar results? 1.2 Is the programme design appropriate for the cultural, political, and economic context of the selected country? |
| Efficiency | 2. How efficiently has UN Women implemented the programme? | 2.1 How efficiently and timely were programme activities implemented as per the work plans? 2.2 Have resources (financial, human, technical support, etc.) been allocated strategically to achieve the programmatic outcomes? Are expenditures in line with the planned programme budgets? If not, have revisions been made to the budgets? 2.3 What has been the quality of the programme monitoring and reporting including the use of various M&E tools? |
| Effectiveness | 3. What has been the progress made towards achievement of the expected outcomes and expected results? What are the results achieved? | 3.1 Is the implementation arrangement for the programme effective to achieve planned objectives? If not, how can it be improved? 3.2 How effective are the partnerships developed with national partners, the TCCC for delivering intended results of the programme? What are the existing gaps, and why do they exist? 3.3 How effectively has the programme management monitored performance and results of the programme? 3.4 What has been the effectiveness of direct actions such as conducting training, developing tools and providing recommendations? |
| Potential Sustainability | 4. What is the likelihood that the benefits from the programme will be maintained for a reasonably long period of time when the programme ceases? | 4.1 Is the programme supported by national/local institutions? Do these institutions demonstrate leadership commitment to continue the work of the programme or replicate it? 4.2 How has the programme set in place mechanisms to ensure sustainability of its results? 4.3 To what extent has the programme supported knowledge transfer and capacity building of partners and what is the degree of institutionalization of approaches developed under the programme framework? |
| Impact | 5. To what extent has the programme achieved the intended programme objectives? | 5.1 Has the programme achieved the intended objectives? What are the gaps? 5.2 To what extent has the programme contributed to capacity development of Women entrepreneurs in target communities to establish and sustain their businesses? 5.3 To what extent women entrepreneurs have increased access to networking and business support? 5.4 To what extent has the programme increased economic opportunities and access to livelihoods, especially for the poor and excluded? 5.5 To what extent programme increased awareness on women’s economic rights and the benefits of women’s economic participation? 5.6 What documented changes have occurred since the start of the programme to incorporation of women empowerment principles within the private sector companies? |
| Lessons Learned | 6. What can we learn from this programme that will inform future work on women’s economic empowerment? | 6.1 What are the best practices emerging from the programme? 6.2 What were the challenges that affected the programme’s ability to achieve desired results? 6.3 Have any potential practices or tools been used during the programme that could be replicable elsewhere? 6.4 What areas can be improved in regard to programme design, planning and implementation, especially with respect to setting targets, accelerating effective delivery of results and sustainability and impact? |

2.6 Evaluation Methodologies and Process

a. Methods

The Evaluation will be a transparent and participatory process and will use a mixed-methods approach, primarily qualitative, that aligns with the final matrix of questions (to be completed by the Evaluation team in consultation with the Reference Group). However, it will also include quantitative data collection/analysis as feasible. The evaluation will be based on gender and human rights principles, as defined in the UN Women Evaluation Policy,2 and adhere to the United Nations norms and standards for evaluation in the UN System.

The following data sources may be utilized, with data triangulated to ensure validity and reliability:

- Desk review of documents

- Review of baseline data

- Interviews and focus groups

- Case studies

- Surveys

b. Evaluation process

Inception Phase:

• Conduct an initial desk review of available documents.

• Conduct brief interviews (via Skype or phone) with key stakeholders to refine the Evaluation scope and methodology.

• Draft an Inception Report to be reviewed by the Reference Group.

• Refine the Evaluation methodology/question matrix based on feedback and integrate proposed changes (as appropriate) into the final inception report.

Data Collection Phase:

• A more in-depth review of specific documents.

• Review existing baseline data (primarily from individual country-based research studies) to determine the available data with which to measure progress.

• Conduct a quantitative survey, as feasible and in consultation with the Reference Group.

• Conduct field visits – minimum 5 days mission - to interview key stakeholders and review national documents (as available).

• Conduct follow-up, in-depth interviews with global, and national UN Women staff, partner organizations, TCCC, and others as necessary.

Analysis and Report Writing Phase:

• Review and analysis of all available data.

• Prepare first draft of the synthesis Evaluation report.

• Receive feedback from Reference Group on draft report and revise (as appropriate).

• Submit final report and share main findings/recommendations through a final Evaluation meeting with the Reference Group.

The Evaluation results will be shared with UN Women, Programme as well as Strategic Partnership Division and participating country offices used to inform and improve future programming on women’s economic empowerment and private sector partnership.

Proposed Format of Final Evaluation Report

Final evaluation report:

- Executive Summary (maximum five pages)

- Programme description

- Evaluation purpose

- Evaluation methodology

- Findings

- Conclusions

- Lessons learned

- Recommendations

- Annexes, (including interview list, without identifying names, in the interests of confidentiality/anonymity; data collection instruments; key documents consulted; cased studies with country examples, Terms of Reference)

2.7 Evaluation Management

The Evaluation will be managed by Programme Division and Private sector team at UN Women Headquarters and the entire process will be conducted in accordance with UN Women Evaluation guidelines and UN Evaluation Group (UNEG) norms, standards and ethical guidelines.3 There will be oversight body established: the Reference Group to be consulted at agreed-upon points for review, comments, and guidance and provide advisory services to the overall evaluation process. The Programme Division team at HQ will manage the day-to-day aspects of the Evaluation process in collaboration with Evaluation Office.

This Evaluation will be a participatory process and the Evaluation manager will consult with the TCCC, UN Women Programme Division and Private sector as well as programme country offices as required. At the end of the Evaluation, the Programme Division and Private sector team will draft the management response, in consultation with the Reference Groups, and support dissemination of the Evaluation report, findings and recommendations.

The Reference Group will provide direct oversight of the Evaluation process. The group will input into Evaluation preparatory documents and documents submitted by the Evaluation team. The Reference Group will comprise of the Programme and Private Sector Division at UN Women HQ, a counterpart at the TCCC and three programme participating countries/coordinators will liaise with pertinent multi-stakeholder groups at the national level to inform them of the Evaluation process.

3 TIMEFRAME & DELIVERABLES

Following in-depth preparatory work, the Evaluation will be conducted from 1st of June – 20 September 2016 .

There will be six main deliverables produced during the Evaluation:

- Inception Report: This report will include a detailed Evaluation methodology, Evaluation question matrix, proposed data collection tools and analysis approach, and Evaluation work plan (with corresponding timeline).

- Briefing to each country at the beginning of the field visit.

- Field visits and PowerPoint Presentations to each country at the close of the field visit.

- First draft of the Evaluation Report; UN Women should review the draft evaluation report to ensure that the evaluation meets the required UN Women quality criteria

- PowerPoint Presentation to Reference Group on Main Findings/Recommendations and proposed dissemination strategy.

- Final Evaluation Report.

The following table provides an indicative timeframe and activities for the Evaluation and the corresponding deliverables:

| Table 2: Timeframe |  |  |
| --- | --- | --- |
| Timeframe | Primary Activities | Output |
| Inception Phase |  |  |
| 7 June 2016 | Initial meeting with evaluation team either in-person or via Skype (depending on where they are located) | Timeframe and work plan agreed |
| 18 June 2016 | Evaluation team submits a draft Inception Report, including proposed methodology, work plan, and agreed-upon deliverables/timeframe. | Draft Inception Report |
| 18 -25 June 20016 | Convene Reference Group to discuss Inception Report, provide feedback to evaluation team, finalize methodology, questions, and work plan. | Evaluation Methodology, Question Matrix, and work plan |
| 1 July 2016 | Evaluation team submits revised Inception Report, and UN Women HQ shares the final inception report with country programme offices. | Final Inception Report |
| Data Collection Phase |  |  |
| 4 – 10 July 2016 | Evaluation team conducts three country visits. | Field visits Completed |
| 10– 24 July 2016 | Concurrently, evaluation team conducts further document review, interviews with global, regional UN Women staff, partner organizations, donors, etc. | Review and Analysis of data |
| Analysis, Report Writing and Validation Phase |  |  |
| 4 August 2016 | Evaluation team submits first draft evaluation report, including summary country-level reports and summary of global efforts. | 1st draft evaluation report |
| 18 August 2016 | UN Women HQ, the reference group and Evaluation Division review first draft and provide feedback | Feedback gathered |
| 18-27 August 2016 | UN Women HQ compiles all the feedback and shares with evaluation team | Feedback compiled and shared |
| 8 September 2016 | Evaluation team submits final evaluation report | Final Evaluation Report |

4 EVALUATION Team Composition

The final evaluation will be conducted by an independent evaluation team of at least three experts. The team leader and Team members should have the requisite and complementary skills set (individually and jointly) to undertake a complex, multi country programme evaluation.

The Evaluation Team Leader will demonstrate experience and expertise in leadership and coordination of Evaluations. The evaluation team leader will be responsible for coordinating the evaluation as a whole, including internal evaluation team coordination and logistics, preparation for the work plan, dissemination of all methodological tools, delivery of the expected evaluation outputs and all presentations

Specifically, the Evaluation Team Leader is expected to have the following expertise:

- At least masters degree, PhD preferred, in social sciences, preferably in gender, evaluation or social research;

- Technical expertise in gender equality and women’s economic empowerment;

- Extensive knowledge of and experience applying qualitative and quantitative Evaluation methods, particularly at the outcome level;

- A strong record in designing and leading Evaluations; 10 years of working experience in evaluation, and at least 5 in evaluation of development programmes. Experience in evaluation of programs with budget over USD 1million.

- Expert data analysis skills;

- Strong ability to translate complex data into effective, written reports;

- Experience in gender analysis.

- Detailed knowledge of the role of the UN and its programming is desirable.

- Process management and facilitation skills;

- Familiarity with the key policies related to the women’s economic empowerment, particularly women entrepreneurship;

- Familiarity with UN Women policies and programmes related to women’s empowerment;

- In-country or regional experience in at least one of the identified countries/regions;

- English language proficiency knowledge of Portuguese will be an asset.

The team leader is expected to submit at least one example of evaluation reports recently completed where s/he contributed significantly as the lead writer.

Evaluation Team Member(s) should demonstrate skills in the following areas:

- A masters degree related to any of the social sciences, preferably in gender, evaluation or social research;

- Extensive knowledge and experience in the application of quantitative and qualitative evaluation methods;

- A minimum of 5-7 years of experience in conducting evaluations;

- High level of data analysis skills

- Strong analytical and writing skills;

- In-country or regional experience preferred

- Knowledge of thematic areas covered by the programme is desirable

- Ability to work within a team

- Proficiency in English required, knowledge of Portuguese will be an asset;

- Experience within the UN is an asset.

Overall, the evaluation aimed to: analyze programme outcomes and assess effectiveness of the approach and strategies used by the programme countries to increase women’s economic empowerment; examine programme results in relation to the intended outcomes and outputs as well as unintended results (positive or negative) and identify the strengths and weaknesses in programme design and implementation to scale-up the lessons learned and improve future programming on women’s economic empowerment; draw key lessons on the partnership, best practices, factors that enable and hinder intended results; assess institutional capacity and potential for sustainability of the on-going work in programme countries; and, assess implementation models and managerial structures created for the partnership.

Although a no cost extension was given up to March 2016

The evaluation was conducted between mid-August 2016 and January 2017 by a three-member team

Development Assistance Committee of the Organization for Economic Cooperation and Development

Country missions were undertaken between September 25, 2016 and October 10, 2016

This was revised overall target, after the Brazil target was revised

The evaluation noted, while all the women trained were entrepreneurs in Egypt (4170) and South Africa (18,033), only a small proportion of them were entrepreneurs in Brazil. Out of the total 21,500 women trained in Brazil 16,669 were from retail, 4,201 from recycling and 630 from entrepreneurship Coletivos.

It was reported that the unutilized portion in Brazil was due to currency fluctuation

While Egypt and South African had a very focused approach towards women’s economic empowerment, Brazil had a wider approach

Among the three countries, the South Africa model has been more successful in terms building capacities which led to clear economic improvement outcomes with women entrepreneurs (due to women putting into practice the knowledge gained from training)

http://www.unwomen.org/~/media/Headquarters/Attachments/Sections/Executive%20Board/EB-2011-AS-UNW-2011-09-StrategicPlan-en.pdf

The 5by20 Initiative is TCCC’s global commitment to enable the economic empowerment of five million women entrepreneurs across the company’s value chain by 2020 (http://www.coca-colacompany.com/5by20)

The actual start of the programme was in early 2013.

Terms of Reference (TOR) of the Final Evaluation for the Global Programme WEE and the Integration into Value Chain of TCCC in Brazil, Egypt and South Africa

Beijing Platform for Action 1995, Strategic Objectives F1 and F2

Comprised of 17 women executives from diverse background with many years of experience within TCCC system. The team was sponsored by the CEO and supported by Human Resources.

Launched at the 2010 Clinton Global Initiative in New York

It was a joint agreement between UN Women Brazil and the ICCB to cancel Output 1.2 by removing the microcredit pilot in Manaus from the scope of the programme, due to lack of local feasibility, among other reasons. This proposal met no objection when it was presented to the Global Steering Committee. Henceforth, the programme no longer reported on this output (Annual Report 2015).

These were the initial outputs and outcomes for Brazil which were redefined in June 2014; however the logical framework was not revised by the Programme.

The Coletivo Platform was first designed to equip young people throughout Brazil with the technical and life skills required to access employment. Women comprise 70 per cent of total Coletivo participants. The Coca-Cola Brazil Institute is responsible for the operation of this platform.

From the programme documents and annual reports it was noted that the initial focus was on four Coletivos, including the Coletivo Community Leadership, which was dropped subsequently.

See http://www.weprinciples.org/

UN Women Evaluation Policy 2012 (http://www2.unwomen.org/~/media/headquarters/attachments/sections/library/publications/2012/11/unw-2012-12-un-women-evaluation-policy%20pdf.pdf?v=1&d=20141013T121501)

UNEG Norms and Standards 2016 (http://www.unevaluation.org/document/detail/1914)

The evaluation was conducted by a three-member team between mid-August 2016 and January 2017. The field visits to the countries were undertaken between September 25, 2016 and October 10, 2016.

Country missions were undertaken between September 25, 2016 and October 10, 2016.

Logistical and time constraints will be kept in mind in planning the number of key informant interviews and number of focus groups/group meetings with beneficiaries, for each country

For Brazil, it also includes recyclers and young first-time job seekers

Includes women, men, recyclers and youth

Development Assistance Committee (DAC) of the Organization for Economic Cooperation and Development - Criteria for Evaluation - http://www.oecd.org/dac/evaluation/daccriteriaforevaluatingdevelopmentassistance.htm

UN Women Strategic Plan 2014-2017 – Updated Development Results Framework, p 9. http://www.unwomen.org/~/media/Headquarters/Attachments/Sections/Executive%20Board/2013/Annual%20Session/DevelopmentResultsFramework-2014-2017%20pdf.pdf

An Empowered Future – Corporate Evaluation of UN Women’s Contribution to Women’s Economic Empowerment – UN Women Independent Evaluation Office – December 2014

Final Case Study Report – Brazil CO – UN Women Corporate Evaluation on Strategic Partnerships for GEWE – June 2016

As noted during the evaluation and as informed by Brazil programme team, “Entrepreneurship” was the least focussed Coletivo among all Coletivos in Brazil, in the programme. The main focus of Brazil programme was on Recycling cooperatives and Coletivo Retail

It was noted during discussions that men accompanied woman for safety/security reasons and also out curiosity.

Arriving at a decision (by the country team) on the business model to be implemented and the refrigerator supply arrangements took a long time which was a key reason for the start-up delay in Egypt

IBGE, Pnad Contínua (Pesquisa Nacional por Amostra de Domicílios Contínua). http://www.ibge.gov.br/home/estatistica/pesquisas/pesquisa_resultados.php?id_pesquisa=149

http://www.ipea.gov.br/agencia/images/stories/PDFs/situacao_social/131219_relatorio_situacaosocial_ mat_ reciclavel_brasil.pdf

Law 12, 305 of August 2, 2010 institutes the National Policy on Solid Waste (http://www.mma.gov.br/estruturas/253/_arquivos/125_publicacao17052011041349_253.pdf)

https://www.usaid.gov/egypt/gender-equality-and-womens-empowerment

http://www.eg.undp.org/content/egypt/en/home/ourwork/womenempowerment/overview.html

DBSD plans to provide equipment to 29, 000 people in three years (2016-2018)

The Coca-Cola Company and UN Women Form Global Partnership to Accelerate Women’s Economic Empowerment - http://www.unwomen.org/en/news/stories/2011/9/the-coca-cola-company-and-un-women-form-global-partnership-to-accelerate-women-s-economic-empowermen (September 21, 2011)

In July 2010, the United Nations General Assembly created UN Women, the United Nations Entity for Gender Equality and the Empowerment of Women. In doing so, UN Member States took an historic step in accelerating the Organization’s goals on gender equality and the empowerment of women. - See more at: http://www.unwomen.org/en/about-us

TCCC is a Forum partner. The support from TCCC to engage was important

The membership to this Council is only invitation

https://www.empowerwomen.org/en

A mobile training bus with interior of training class room with audio-visual facilities

An Empowered Future: Corporate Evaluation on UN Women’s Contribution to WEE, December 2014, p16.

Part of the reason for the delay was due to the transfer of the UN Women Country Representative, who was a key actor in the initial discussions and planning

Youth was the focus for Retail Coletivos

These analysts are ICCB professionals who are involved in the capacity assessment of recycling cooperative members

Educators are professional from local NGOs where the workshops are conducted

The structure included one manager, two coordinators, 26 field analysts who trained 110 local educators

It was also a unique situation for Hand in Hand as normally a development partner is not co-implementing.

DNV GL carried out field work for the audit validation. It was commissioned by TCCC in 2015.

Ipsos Brazil

Sustainable Procurement Manual - http://cebds.org/wp-content/uploads/2015/09/Sustainable-Procurement-Manual.pdf

This is a revised target from the original target of 13,000 to be reached by Coletivos. The slow start in Brazil programme was also attributed partly to the change in the Coletivo Platform expansion strategy for 2014. Therefore, TCCC and UN Women in Brazil presented their case to a reduced target of 8,068.

Despite appropriate approvals, the changes were not reflected in the programme logic models as seen from Table 1, compiled from programme’ report at the end of the third year.

Yearly detailed budget was not reviewed by this evaluation

While the person in South Africa remained constant throughout the life of the programme; in Brazil, the person that was there during the design process left UN Women for 1.5 years and then came back. During this period, a new coordinator was hired, who remained only for a very short period of time. After she left, a programme associate was hired.

Egypt was coming out the 2011 revolution; there was immense “traditional donor” interest and project investment in to the country, mostly on advocacy. Given the history of UN Women predecessors, it was likely there was leaning and preference for advocacy projects with larger budgets. No project database verification was done for this by the evaluation; however, the possibility was indicated during discussions with some stakeholders.

As reported in South Africa

South Africa was also given bridging funds to carry on the programmes for another 6 months

The interior of the bus was modified into a classroom setting with audio-visual equipment to conduct training. The bus was owned by the TCCC bottler, but was given to the programme team (at no cost) when requested. This helped going to the communities to conduct training

Only women who were given refrigerators were part of the survey

Initially, in regards to some strategic decisions about the Programme, TCCC first established alignments with their own headquarters individually. Then, they had to negotiate how they would make the decision taking into account the perspectives brought to the table by their headquarters. At some point, they realized that this procedure was creating additional work for them and, in most situations, causing unnecessary delays in making some important decisions. They devised a strategy to prevent this from happening, which was to agree on what they thought was the best way to go about an issue among them in Brazil before they would consult with their respective headquarters. Both UN Women and TCCC in Brazil thought it was better process.

As discussed earlier, this was after constant pursuing at the national level by UN Women and TCCC for two years. DBSD was created only in 2014.

Furthermore, City of Cape Town had earlier indicated interest and had discussions with the programme team

It was noted that South Africa had received two tranches of additional funding with two six-month extensions and additional targets.

The training and mechanisms were  in existence even before UN Women-TCCC programme was launched

Sustainable Procurement Manual, May 2014, CEBDS, Rio de Janeiro, (http://cebds.org/wp-content/uploads/2015/09/Sustainable-Procurement-Manual.pdf), p46-47

During discussions in Brazil it was noted that other companies have also indicated interest provide financial support to promote the WEPs and other UN Women campaigns (e.g. Accenture, Avon, Dow, Ernst & Young, IBM Brazil, Correios, Propeg, Television Globo, Heads Marketing and Publicity, Gol Airlines, Walmart and ABRH-SP)

The bus is modified into classroom seating set-up with audio-visual equipment. It can go to the community. It is a mobile educational/training facility.

http://www.onumulheres.org.br/wp-content/uploads/2016/04/cartilha_WEPs_2016.pdf

http://premiowepsbrasil.org/

The evaluation noted during discussions which was also reported in the Annual Report for 2015 that “in the case of Coletivo Recycling in Brazil, the number of beneficiaries are not cumulative and it is likely that are cases where the same beneficiaries trained in 2014 could have participated in the 2015 cycle”. Of the total trained in Brazil programme, only 4,201 were from recycling cooperatives. The rest were from retail (16,669) and entrepreneurship (630) Coletivos.

Women trained in Egypt and South Africa were all entrepreneurs and in Brazil it included recyclers, youth and entrepreneurs

Training of Coletivo members was an ongoing programme of TCCC/ICCB in Brazil.

The training covered creation of cooperatives, safety and quality of life, administrative management, people management, infrastructure, plan and production, partnership building, financial management and gender equality and human rights

It was understood that these cooperatives set business improvement targets every month. These may not necessarily be increased revenue or sales. They are more to improve process and efficiency and may eventually lead to business profitability or increased income. The cooperatives are provided a reward for achieving the target.

Based on information from ICCB

The 5 modules - Keeping Daily Records, Understanding my Market, Marketing my Business, Managing Income and Expenses and Managing My Inventory

338 women participated in the survey

Men were included based on suggestions from community gate keepers

The money for each product was put in respective bottles or boxes, so when she had to replenish stocks she did not have to look anywhere else.

Longitudinal Impact Study conducted from December 2013 to December 2015 by TCCC and Ipsos South Africa with 101 women entrepreneurs who participated in the TCCC-UN Women South Africa programme.

This (30%) was reported to be the programme target. It was noted that the target was intentionally set at that level, as it was not intended to be job placement programme but a youth empowerment programme that has an aspect of job assistance.

Interestingly, it was reported in one of the focus groups that many who got the job tended to be male, “white”, and above 18 years old – apparently the most commonly sought profile in the job market.

Information from programme monitoring in Brazil

The study reported that higher confidence had a statistically significant positive correlation with increase in personal income, but did not have statistically significant correlation with increase in business income.

And many expatriates come to visit

http://www.unwomen.org/en/news/stories/2014/1/ed-to-attend-wef-annual-meeting-in-davos

It was noted that a number of dedicated events, promoted by reputed companies (such as Accenture, Avon, Dow and Ernst and Young) helped to increase the number of WEPs signatory companies, in Brazil

As noted from stakeholder interviews

http://cebds.org/en/about-cebds/about-us/

Non-traditional “donors”/funding organizations (not from the development/not-for-profit/government sectors) approach and work differently.

Country representatives were usually appointed for fixed terms and moved to the next assignment/posting at the end of their term.

Managers involved in day to day operations of the programme implementation

While South Africa came to an agreement in less than 6 months, Brazil took 18 months and Egypt took 28 months to start implementation

It should be kept in mind that this was an already ongoing initiative of ICCB where in human rights, gender equality and women’s empowerment aspects were incorporated

The two key partners (TCCC and UN Women) in the country took a long time to agree upon the business model to be implemented and refrigerator supply arrangements

Also commended by the audit report by DNV GL in 2015

Many development projects focussed on economic empowerment promote starting new businesses. EWEP was that way different.

The evaluation noted, while all the women trained were entrepreneurs in Egypt and South Africa, only a small proportion of them were entrepreneurs in Brazil.

For day to day programme management and operations

Teams in TCCC did not change

Among the three countries, the South Africa model has been more successful in terms building capacities which led to clear economic improvement outcomes with women entrepreneurs (due to women putting into practice the knowledge gained from training)

The evaluation criteria align with the UN Evaluation Group (UNEG) evaluation criteria.