Final Evaluation Report For UN Women

Final Evaluation of the 2nd Phase EVAW Programme: Promote Efforts for National Legislation on Domestic Violence and Upscale the Multi-sector Model in China

Lewis Husain

Lichao Yang

31st July 2017

ACKNOWLEDGMENTS

The evaluation team benefited from strong support from UN Women and from the All China Women’s Federation in making available documentation and in organising and facilitating fieldwork in the pilot counties. Staff of multiple departments in Yilong, Ningxiang, and Jingyuan were welcoming and supportive of the evaluation team’s work. Without this support, data collection would have been impossible. The evaluation team would particularly like to recognise the contribution of a number of domestic violence victims who made themselves available for discussions with the evaluation team. Any errors or inaccuracies are the responsibility of the evaluation team.

ACRONYMS

ACWF 		All-China Women’s Federation

DAC 		Development Assistance Committee of the OECD

DV		domestic violence

EVAW 		End Violence against Women

GDP		gross domestic product

MCH 		maternal and child health

MOCA 		Ministry of Civil Affairs

MOJ 		Ministry of Justice

MPS 		Ministry of Public Security

NGO 		non-governmental organisation

NHFPC 		National Health and Family Planning Commission

NPC 		National People’s Congress

OECD		Organisation for Economic Co-operation and Development

ToR 		terms of reference

TOT 		training of trainers

EXECUTIVE SUMMARY

This report provides a final evaluation of the 2nd Phase EVAW Programme: Promote Efforts for National Legislation on Domestic Violence and Upscale the Multi-sector Model in China. The purpose of the evaluation is to assess the extent to which the programme achieved its expected goals and to provide recommendations to strengthen future interventions on domestic violence prevention and response. The report is intended for national and sub-national policymakers in China and for donors.

Domestic violence in China is a significant risk to the health and wellbeing of women and has a negative impact on social development. China is making progress in developing responses to domestic violence and violence against women, notably through the issuing of the Family Violence Law (effective March 2016), which follows a number of other pieces of national and provincial legislation which prohibit domestic violence and affirm that violence against women is a human rights violation. Despite this, according to a 2011 survey by the National Bureau of Statistics and All-China Women’s Federation (ACWF), “24.7% of Chinese women have experienced abuse, assault, restriction of personal freedom, economic control, and/or forced sex during marriage”. These figures are thought to underestimate the prevalence of domestic violence. Factors believed to underlie apparent low prevalence levels include under-reporting and traditional norms which frame domestic violence as a private affair and as acceptable behaviour, norms which persist despite provisions in law and regulations.

The programme of “Preventing and Responding to Domestic Violence in China through a Multi-sectoral Approach” (EVAW I), supported by the Ending Violence Against Women (EVAW) Trust Fund and the programme of “Promote Efforts for National Legislation on Domestic Violence and Upscale the Multi-sector Model in China” (EVAW II), supported by the Chinese Government, were established to support China in developing functioning systems to respond to domestic violence, through piloting a multi-sectoral prevention and response mechanism in three Chinese counties, and through supporting national legislation on domestic violence incorporating internationally accepted standards and definitions. EVAW II (2014-2017), builds on EVAW I, which laid the foundations of a domestic violence prevention and response model in three Chinese counties, though this remained at an early stage of development by the end of the programme in 2012.

EVAW II has sought to further develop this work, and to contribute to the protection of women in China from domestic violence through national legislation and improved and expanded services. The programme has supported training and capacity building in three pilot counties to improve awareness and understanding of domestic violence, and to promote better responses by the county governments to domestic violence through the adoption of improved work practices and through strengthening the multi-sectoral cooperation mechanisms initiated under EVAW I. Based on comparatively mature models for multi-sectoral cooperation developed over course of both phases of the programme, materials were developed synthesising these for more widespread dissemination, and efforts were made to promote scale up in the three pilot provinces. The programme also organised collation and translation of materials on other countries’ good practices as a reference for Chinese legislators, and organised study trips to Canada and the UK to provide a number of Chinese officials with first-hand experience of other countries’ practices, with the aim of contributing to the national legislative process.

Data for the evaluation was collected in June 2017. Data collection methods included a comprehensive documentation review; in-depth interviews and small group interviews with primary stakeholders in three pilot counties and their parent provinces; and surveys of with government departments involved in the pilot, and of training participants.

Key findings: Relevance, effectiveness, efficiency, sustainability and impact

Relevance. The evaluation finds that the programme’s approach of developing multi-departmental management and referral systems, and of carrying out training of government agencies/staff to respond to the needs of victims of domestic violence, is relevant in the pilot counties and in China more broadly. Work supported by the programme to create awareness of domestic violence and change norms and behaviours is highly relevant to China’s current context. The evaluation also finds, however, that the focus of the programme has been reactive (dealing with the consequences of domestic violence), rather than proactive (preventing domestic violence), and that there has been little focus on prevention, early detection, and other pre-emptive interventions. The evaluation finds that the programme was designed in a way that is relevant to China’s political and institutional structure, in simultaneously following top-down (supporting legislation) and bottom-up (developing sub-national models) approaches, and that it takes into account the need to engage stakeholders from multiple ministry systems to provide joined up services. The evaluation also finds, though, that there are likely to be limits to the impact of the approach used in this programme of development and scale up of sub-national models, and that greater work through specific ministry systems to promote ministry-specific regulations, guidance, etc, is likely to be needed in subsequent stages of programming. The programme demonstrates good fit with UN Women’s mandate and that of the principal partner institution, the All China Women’s Federation, and with UN Women’s mandate and comparative advantage in China as a natural interlocutor for the ACWF, which is de facto the led agency on domestic violence.

Effectiveness. The evaluation finds that outputs/outcomes have been achieved, but that indicators are limited in their ability to reflect real-world programme achievements. Effective coordination and management structures were put in place between UN Women, ACWF and the pilot counties to ensure programme implementation.

Efficiency. Evidence available shows that resources have been efficiently used: for a relatively limited budget, the programme has carried out multiple trainings in all pilot counties, and in Beijing, has carried out study trips to two countries, and has collated and translated a substantial amount of documentation into Chinese to serve as a resource for decision makers and legislators. In addition, the programme has catalysed change, and leveraged resources, in the pilot counties. Programme design, management and supervision measures are adequate to the programme, but would benefit from improvement. Examples include use of a theory of change to underpin programme design, and improved monitoring indicators more capable of reflecting real world changes.

Sustainability. The evaluation finds that multi-department and referral systems established in the pilot counties are relatively institutionalised and should be considered basically sustainable, though individual participating departments in all counties raise a number of challenges relating to their work. Although there is no reason to think at present that these challenges directly undermine the sustainability of the programme’s achievements, it is possible that they may do so if not addressed. The pilot counties appear to be making judgements regarding sustainability based on current volumes of service delivery. If numbers of reported cases change following introduction of the Family Violence Law, as should be expected, this could create pressure on resources and have an impact on sustainability. The Family Violence Law provides a good context to ensure the sustainability of the systems established through this programme, with the caveat that changes in policy or in incentive systems in one or more ministry system associated with the models developed in the counties could have an impact on sustainability of the county models. Scale up and consolidation of the pilot county models should be understood as a way of ensuring the sustainability of these models. From evidence available, it is not clear the extent to which these models will be scaled up or sustained at provincial (or larger) scale without increased support from provincial governments.

Impact. The evaluation finds substantial intermediate impacts on county administrative systems and processes, which are established and functioning. Knowledge and awareness of domestic violence are changing in the three pilot counties (albeit from different starting points), and there is evidence of a degree of normative change, though this is challenged by entrenched norms and attitudes that support traditional gender roles and may condone violence. The multi-departmental referral system and service provision by individual departments in the pilot counties has reached a large number of victims of domestic violence over the course of the programme (2014-2017), but it is hard to accurately assess impacts for victims. Limitations on data from the counties mean that it is not possible to get a full picture of referral activity, while a systematic assessment of case outcomes for domestic violence victims was outside the scope of this analysis, both in terms of time and data availability. Findings regarding the work of individual government departments in the pilot counties suggest that, despite the establishment of referral systems and the provision of training to all departments on procedures for providing services to domestic violence victims and/or handling of domestic violence cases, at least a proportion (and possibly a high proportion) of cases are being handled in ways that are not consonant with the norms and standards supported by this programme. Changing embedded institutions and systems is expected to require continued effort, but will likely be important for ensuring better outcomes for victims of domestic violence.

Conclusions

The evaluation concludes that EVAW II has been broadly successful its immediate objectives at the output and outcome level, that the implicit theory of change underlying the programme is sound, but that there is a need for more and sustained work both in the pilot counties and more broadly if the broader aims of the programme are to be achieved.

Very substantial progress has been made in increasing capacity in the pilot counties, and in building management systems for coordinating the work of multiple departments on domestic violence, as well as building referral systems able to coordinate services between different government departments, and activities supported by the programme (principally training) are almost universally recognised for their quality and appropriateness. However, the evaluation also concludes that training and capacity development are insufficient on their own to achieve deep institutional change, and that this is necessary to change the ways that domestic violence cases are dealt with in order to change final outcomes for victims. More work is required to better understand the institutional factors that have an influence on cases and outcomes, particularly (though not exclusively) in the police and judicial systems. This points to a need for continued support to anti-DV work in the pilot counties, but also supports the view that county-level piloting likely has inherent limits due to the ways that system-level incentives impinge on the decisions of county governments and individual government departments. Fundamentally reforming such systems is likely to require work that can promote change in system-level incentives and institutions.

A major objective of the programme was to provide scaleable models that could be rolled out in the pilot provinces. The evaluation concludes, overall, that this has been a mixed success. While the county models are now relatively mature, the current evidence of scale up is limited, and in two of three provinces it does not appear at present that provincial government or agencies are providing the support that will likely be necessary to achieve widespread coverage. At an institutional level, the evaluation concludes that greater support will be needed to achieve widespread scale up. Although a number of training and other materials have been developed, other counties are almost certain to require support in building the kinds of systems that the pilot counties have successfully developed. Support to capacity development is likely to be critical.

The programme has worked to develop a cadre of individuals in the three counties with capacity to carry out follow-on training. This appears to be a promising start, but at present these resources are clearly insufficient to the task of carrying out the kind of widespread training that will be needed to broadly disseminate knowledge to, and to support development of coordination and referral mechanisms in, non-pilot counties in the pilot provinces (let alone nationally), while supporting deep institutional change in these non-pilot counties will surely require time and support. Support at this scale clearly exceeds the capability of any one donor organisation, and these conclusions point to the need for government support for widespread capacity development.

EVAW II provided support to translation and compiling of a range of documentation intended to inform legislation and organised visits to Canada and the UK to examine other countries’ practices. The evaluation concludes that, while it is likely that these activities will have had some impact, impact appears limited, with the caveat that better access to interviewees might have resulted in a different conclusion.

Main achievements

Main achievements of the project are: (1) supporting the development and consolidation of multi-sectoral prevention and response mechanisms in three Chinese counties and providing services to victims of domestic violence in these counties; (2) creating and sustaining strong working relationships with the pilot counties and building commitment among relevant governmental and other agencies to work on preventing and responding to domestic violence; (3) achieving a high degree of penetration of training on domestic violence among staff of relevant agencies in the three pilot counties; (4) developing materials describing the multi-sectoral prevention and response models developed in the pilot counties that can be broadly shared and help promote dissemination of these pilot counties’ experiences; (4) achieving a degree of dissemination of the pilot county models in the three pilot provinces; (5) collating and translating a large body of materials that can serve as a reference for Chinese decision makers and legislators.

Key implementation challenges

Key implementation challenges that arose from the design of the programme were as follows: (1) The programme shows the difficulty of using training and capacity building to achieve deep institutional change where strong institutions or systemic incentives promote less desirable outcomes for victims of domestic violence. (2) While county-level piloting in China is a common mode of intervening for donor agencies, the programme provides a degree of evidence that such approaches have limitations in their ability to change strong institutions and systemic incentives, and that other approaches, including working through ministry systems to promote top-down change, are necessary complementary approaches. (3) While there is some evidence for scale up of the county models, the programme also shows that county piloting does not automatically lead to provincial buy in and enthusiastic dissemination or scale up. This points to the need for more consideration of how to involve provincial agencies and engage them to actively support scale up.

Priority recommendations

Strategic level

- EVAW II has been largely reactive, in setting up systems to deal with domestic violence cases, and provide support to victims, after the fact. This is useful, but in future programming, it would be beneficial to consider how to include a greater focus on early detection and prevention in subsequent work, including assessing of at risk women/families.

- As the evaluation has shown, training and capacity building appear to be limited in their ability to bring about substantial institutional transformation in the absence of changes in systemic institutions and incentives. In future programming, UN Women should consider what aspects of developing coordinated responses to domestic violence should be addressed through small-scale piloting in counties, and what requires centrally-driven, top-down change through the government and legal systems, and where the strengths of both bottom-up and top-down approaches lie. This could be linked to an assessment of personnel assessment practices in use in the pilot counties (both good practices and practice likely to create inappropriate incentives) as a reference point for other counties during scale up.

Training, capacity building and raising awareness

- Encourage pilot counties to create needs-based, financed and systematic approaches to follow-on training to ensure that training is ongoing, and that it reaches all relevant departments and penetrates to the grassroots. Consider developing targets for training activities. Encourage use of needs analysis by counties/departments and tracking of training needs over time. Encourage pilot counties to explore greater use of cross-departmental training groups, and attempt to gain government backing for the inclusion of training in the work of all government departments.

- Programme-provided or supported training should more thoroughly consider the differences between the three pilot counties and the specific needs of participants from different departments. Training design could make use of participatory needs assessment approaches. UN Women / ACWF should consider reviewing the content of training to increase content on how to communicate with domestic violence victims, counselling and related practical skills.

- Increase the stress on gender concepts in training. Continue to stress the importance of clearly understanding domestic violence and differentiating it from other phenomena. Consider more clearly defining and specifying the scope and nature of domestic violence, from a narrow focus on close relatives / within marriage to include violence among cohabiting, unmarried couples, and among former partners who have separated or between divorced.

- The programme has trained a number of TOT trainees. While this is a positive things, this capacity will need to be strengthened and updated over time, including with content on new legislation and on best practices in other places. Much stronger training capacity will need to be built to underpin scale up of the models developed by EVAW II province- or nation-wide (see comments on scale up, below). Work at this scale is beyond the capacity of any one donor. UN Women and ACWF should consider how they can advocate for the mainstreaming of such training and support work by central government, ministries and/or provincial governments to ensure that training is of high quality and that it reflects the values and concerns of UN Women / ACWF.

Building systems and institutionalising work in the pilot counties

- The evaluation found that systems for recording data on DV in the pilot counties are limited in their ability to clearly show the extent of the problem. Getting a better understanding of incidence is important to guiding the public policy response. UN Women and ACWF should consider carrying out a more in-depth assessment of systems currently in use for recording instances of domestic violence by all relevant departments, and should encourage counties to develop unified recording systems and information sharing systems and/or consider providing technical/financial support for developing cross-departmental, integrated information systems.

Work of participating departments

- A number of things require systematic investigation: how DV cases are treated in the courts in the pilot counties, and the bases for legal judgements in DV cases / divorce cases involving DV; knowledge, attitudes and behaviour of judges and other legal professionals involved in DV cases and specific training needs of judges and other legal professionals involved in DV cases; evidential requirements in DV cases and the impact of these on outcomes; how oversight and management of DV cases are carried out in courts in the pilot counties; the extent to which mediation is being used in DV cases, under what exact circumstances, by what agencies, what qualifications or requirements are for mediators, and whether/how systematic oversight is carried out.

- DV shelters: Consider summarising best practices from the pilot counties on systematically including domestic violence victims in designing services. Consider assessing best practices among domestic violence shelters in the pilot counties and developing a checklist of features for DV shelters to be considered during design. There appear to be few provisions for long-term shelter for victims in need of this, or differentiated/targeted support for complex DV cases. Consider whether there is a need for long-term domestic violence shelters/support, and how this might be met.

- Health facilities: Investigate possible financial barriers to access to treatment in health facilities and consider developing guidance for the health and family planning system in the pilot counties on dealing with DV cases where there is no ability to pay. Consider investigating the assessment of symptoms that may be linked to domestic violence by grassroots-level health facilities, especially ones that should be considered to have comparatively lower capacity, and what proportion of potential DV cases is likely to be accurately detected under current conditions.

Programme design and supervision

- Monitoring mechanisms: In subsequent programmes, consider how to develop more robust monitoring mechanisms that can more accurately reflect real world changes, especially at the outcome level. Examples could include changes in numbers of high / medium / low risk cases, changes in classification of cases as domestic violence vs. ‘family conflicts’, etc. Monitoring frameworks used in EVAW II did not include any assessment of outcomes for DV victims. In subsequent programming, it would be beneficial to investigate more fully outcomes of actual cases through the mediation and court systems and what support is needed to achieve better outcomes.

TABLE OF CONTENTS

1.	INTRODUCTION	11

2.	PROGRAMME DESIGN	14

2.1	Programme logic and theory of change	14

2.2	Programme structure and activities	15

2.3	Budget and spending	16

3.	BACKGROUND TO THE EVALUATION	17

3.1	Evaluation purpose and objective	17

3.2	Evaluation criteria and questions	17

3.3	Evaluation methods and data collection	18

3.4	Ethics, gender and human rights considerations	20

4.	TRAINING, CAPACITY BUILDING AND RAISING AWARENESS	22

4.1	Consolidated findings	22

4.2	Training	23

4.3	Training design: methods and content	23

4.4	Changing knowledge and awareness	24

4.5	Changing norms and values	25

4.6	Changing behaviour	25

4.7	Further actions and recommendations	28

5.	BUILDING SYSTEMS AND INSTITUTIONALISING WORK	29

5.1	Consolidated findings	29

5.2	Main features of county systems	30

5.3	Forms of coordination in the pilot counties	31

5.4	Further actions and recommendations	39

6.	FINDINGS ON WORK OF PARTICIPATING DEPARTMENTS	40

6.1	Consolidated findings	40

6.2	Domestic violence shelter system	40

6.3	Public Security Departments / Legal Aid Centres	42

6.4	Medical system	43

6.5	Education department	44

6.6	Omissions	44

6.7	Further actions and recommendations	45

7.	INTERVIEWS WITH DOMESTIC VIOLENCE VICTIMS	46

8.	PROSPECTS FOR SCALE UP	48

8.1	Consolidated findings	48

8.2	Data used	49

8.3	Programme support to scale up	49

8.4	Sichuan	50

8.5	Hunan	50

8.6	Gansu	51

8.7	Further actions and recommendations	51

9.	SUPPORT TO NATIONAL-LEVEL LEGISLATION	52

10.	PROGRAMME DESIGN, MANAGEMENT AND SUPERVISION	54

10.1	Consolidated findings	54

10.2	Data	54

10.3	Findings	54

10.4	Comments, further actions and recommendations	55

11.	SYNTHESIS OF FINDINGS, CONCLUSIONS AND RECOMMENDATIONS	56

11.1	Synthesis of main findings	56

11.2	Conclusions and findings against DAC criteria	59

11.3	Recommendations	63

12.	EVALUATION TERMS OF REFERENCE	67

13.	ANNEX 2: LOGFRAME AND DATA	77

14.	ANNEX 3: INTERVIEWS AND MEETINGS	79

15.	ANNEX4: PRIVACY STATEMENT	81

16.	ANNEX 5: COUNTY SURVEY DATA	82

17.	ANNEX 6: TRAINING SURVEY DATA	111

LIST OF TABLES

Table 1: Main features of county systems	30

Table 2: Referral data	34

Table 3: Ranking of referrals	36

Table 4: Use of domestic violence shelters	41

Table 5: Overview of evidence for scale up	49

Table 6: Findings against DAC criteria	61

Table 7: Recommendations	64

Table 8: Findings against logframe indicators	77

INTRODUCTION

As elsewhere in the world, domestic violence in China is a significant risk to the health and wellbeing of women and has a negative impact on social development. China is making progress in developing responses to domestic violence and violence against women, notably through the issuing of the Family Violence Law, promulgated in December 2015 and effective from March 2016, which follows a number of other pieces of legislation, including the Marriage Law (revised 2001) and the Law on the Protection of Rights and Interests of Women (amended 2005) which prohibit domestic violence and affirm that violence against women is a human rights violation. The majority of China’s provinces have issued regulations on the prevention of, and response to, DV, and national guidelines exist regarding the role of the ACWF and other government agencies in addressing DV. Despite this, according to a 2011 survey by the National Bureau of Statistics and All-China Women’s Federation (ACWF), “24.7% of Chinese women have experienced abuse, assault, restriction of personal freedom, economic control, and/or forced sex during marriage”. These figures are thought to underestimate the prevalence of domestic violence.

The EVAW Programme to Promote Efforts for National Legislation on Domestic Violence and Upscale the Multi-sector Model in China has piloted reforms in three Chinese counties, Yilong (Sichuan), Ningxiang (Hunan) and Jingyuan (Gansu), discussed more in Section 2. A 2010 baseline study carried out in the three pilot counties found high levels of domestic violence, though only violence against women that took place within couples, including cohabitating partners, was considered. The study made use of questionnaires, in-depth interviews and focus groups in villages/communities in each pilot site. The study found that, across the three counties, “the percentage of men who have perpetrated domestic violence at least once is 42.2%, and the percentage of women who have suffered from domestic violence at least once is 43.5%”. At a provincial level, apparent rates of DV were highest in Hunan, followed by Gansu, and then Sichuan. The study found verbal abuse to be the most common form of violence, but also found serious incidents of physical violence, including use of weapons. The study also found a higher frequency of violence among older age groups up to and including the 40-59 years group, a negative correlation between violence and educational attainment, and the importance of childhood experience in male propensity to violence.

Factors believed to underlie apparent low prevalence levels include under-reporting and traditional norms which frame domestic violence as a private affair and as acceptable behaviour. Such norms persist despite provisions in law that prohibit domestic violence and that state that violence against women is a human rights violation, and despite the increasing number of provinces that have established regulations on the prevention of, and response to, domestic violence, and cross-ministry policy on this. The programme of “Preventing and Responding to Domestic Violence in China through a Multi-sectoral Approach”, supported by the EVAW Trust Fund (EVAW I) and the programme of“Promote Efforts for National Legislation on Domestic Violence and Upscale the Multi-sector Model in China” (EVAW II), supported by the Chinese Government, were established to support China in developing functioning systems to respond to domestic violence, through piloting a multi-sectoral prevention and response mechanism in three Chinese counties, and through supporting national legislation on domestic violence incorporating internationally accepted standards and definitions. EVAW II, implemented between July 2014 and July 2017, builds on EVAW I (2010-2012), which laid the foundations of a domestic violence prevention and response model in three Chinese counties. Due to limited time and a cumbersome management model, EVAW I succeeded in establishing preliminary multi-sectoral cooperation mechanisms in the three counties, but these remained at an early stage of development by the end of the programme in 2012. These systems had a number of limitations requiring strengthening for the approach to better serve the needs of victims of domestic violence:

The external, final evaluation of the programme in 2012 found that the local DPVR models were established and functioning in the three pilot sites in Hunan, Sichuan and Gansu Provinces. The three pilot sites have established preliminary tailored, multi-sectoral cooperation mechanisms at county level, with prevention of DV and response to the multiple needs of DV survivors as top priorities. However, the local DVPR models were still in early stages of development. In particular, the referral mechanism at community level still needed further improvement to ensure services meet the needs of DV survivors. While evaluators observed a moderate increase in DV awareness among the general public, uptake of DV services did not to increase significantly.

business case for EVAW II makes clear the need for substantial change to the ways to commonly-accepted normative framings of domestic violence, that individual government agencies require detailed operational guidance on how to deal with cases of domestic violence, and that there is a need for greater cross-government cooperation to address domestic violence:

Despite these advances, significant challenges remain in the effective prevention of and response to DV. Domestic violence continues to be treated as a family affair, unless the victim is seriously injured or killed, causing the issue to become public. Unfortunately there is a high social tolerance for minor injuries and “less violent” incidences of gender-based violence which stems from unequal power relations. This high tolerance is also widespread within government agencies and NGOs and affects the quality of services provided to survivors by health, police, legal, and social services agencies. Without specific guidance set out in policies or legislation, the response by government agencies and NGOs continues to be fractured along sectoral lines. At the service level, there is still inadequate coordination between health, legal, psychosocial, and emergency accommodation services provided to survivors. At the systems level, government agencies and NGOs involved in the prevention of and response to DV have traditionally failed to adequately share information and to work together to change laws and policies.

In addition,

the EVAW joint programme highlighted the need for a DV Law that addresses violence against women, children, the elderly and the disabled occurring within the home or within intimate relationships. As [the Family Violence Law] was already on the National People’s Congress’ (NPC) legislative agenda, it was suggested that more efforts should be made to 1) support the drafting process of the law to incorporate internationally accepted standards and definitions; 2) further develop the multi-sectoral DPVR models in Hunan, Sichuan and Gansu provinces for national scaling-up, based on the pilot model established during the previous EVAW programme.

The current programme, EVAW II builds on EVAW I. Details of programme design and focus are discussed in the next section.

The remainder of the report is structured around thematic sections. For clarity, these present evidence on discrete aspects of work carried out by the counties or supported by the programme, rather than consolidating all findings together. The concluding section provides a summary of findings, and presents findings against the evaluation hypotheses and DAC criteria, before providing overall conclusions. The report is structured as follows:

- Section two, Programme design, sets out the design of the EVAW II programme and basic information on the pilot counties as background to the analysis in the report.

- Section three, Background to the evaluation, describes the purpose and objective of the evaluation, evaluation criteria and questions, methods and data collection, and ethics, gender and human rights considerations.

- Section four, Training, capacity building and raising awareness, discusses training carried out by the programme and synthesises evidence from the two surveys (the county survey and survey of trainees) and integrates this with findings from interviews and focus groups. The section discusses findings related to knowledge/awareness, as well as the extent to which it is possible to see changing knowledge and awareness translating into changes in norms and behaviour.

- Section five, Building systems and institutionalising work, presents evidence on the establishment and functioning of multi-departmental systems in the programme pilot counties, including Inter-departmental coordination mechanisms and Referral systems.

- Section six, Findings on work of participating departments, presents information from county surveys and fieldwork regarding the anti-DV work of the main participating agencies, summarises findings and provides suggestions.

- Section seven, Interviews with domestic violence victims, summarises findings from interviews with DV victims in three counties and provides suggestions.

- Section eight, Prospects for scale up, presents initial findings regarding scale up in each of the pilot provinces and assesses the prospects for scale up.

- Section nine, Support to national-level legislation, provides a discussion of how work supported by the programme has contributed to national legislation.

- Section ten, Programme design, management and supervision, discusses issues of programme design, monitoring and supervision and provides suggestions.

- Section eleven, Synthesis of findings, conclusions and recommendations concludes, provides a synthetic response to the key evaluation questions listed above, and presents a consolidated list of recommendations given in the report.

- Annexes present the evaluation terms of reference (ToR), data against the programme logframe, list interviews and meetings carried out during data collection, provide the privacy statement used, and provide data from the county and trainee surveys.

PROGRAMME DESIGN

This section presents the programme design  and logic as  background to provide context to the evaluation that follows.

Programme logic and theory of change

EVAW II sought to contribute to and achieve the following goals, outcomes, and outputs:

- Overall Goal: To protect women from DV in China through national legislation and improved and expanded services.

- Outcome: Government took measures to better address DV in China by adopting international standards and the multi-sectoral model in the 3 pilot provinces.

- Output 1: Increased knowledge of international standards and of the value of the multi-sectoral prevention and response model implemented under the programme among decision-makers at national level.

- Output 2: Enhanced capacity of multi-sectoral service providers and community workers to provide coordinated quality services based on the needs of DV survivors in the pilot sites in Ningxiang County of Hunan Province, Jingyuan County of Gansu Province, and Yilong County of Sichuan Province.

- Output 3: Increased willingness among policy makers at provincial level in Hunan, Sichuan and Gansu to replicate multi-sector model throughout the three provinces.

Programme documents do not set out a detailed theory of change for the programme, and the logical links between activities, outputs, outcomes and goals of the programme are not clearly specified. However, based on a reading of programme documentation and discussions with key partners, the evaluation team summarise logic of the programme in the diagram to the right. This was included in the Inception Report and ratified by UN Women.

The inception report noted a number of weaknesses in the programme theory, logframe or indicators used for programme monitoring. More information on this is provided on Section 10.

In addition, the following graphic was developed by the evaluation team during fieldwork to attempt to capture the process through which the programme is attempting to catalyse change through training in the counties. This graphic and analysis elaborates on the theory of change and hypotheses set out above and draws on analyses of training/capacity building that frame this as an intervention whose effect is visible in multiple stages, from change in knowledge/awareness, to change in behaviour/norms, through to change in organisations, institutions and practices. The arrow designates the intended/hoped for direction of change. The graphic places change along this axis in the context of larger-scale legal, social and institutional changes which may either promote or hinder change. The graphic will be drawn on selectively in the following sections to frame the argument on how the programme is promoting change and the barriers to change.

Programme structure and activities

Principal activities supported by the programme:

- Output 1: advocacy for DV law drafting team, compilation and translation of international and national best practices in DV law formulation and implementation, organisation of study tours for legislative decision-makers to understand the DV intervention best practice.

- Output 2: capacity building of multi-sector service providers in the pilot sites, through large-scale, multi-department  training provided by national experts, and training of trainers in the pilot counties.

- Output 3: Develop DVPR Model best practice and advocacy materials for replication and hold public communication campaigns in the pilot counties; organizing advocacy workshops, targeting multi-sector decision-makers from three respective provinces to advocate for the DVPR Model replication throughout the three provinces.

Partners in the programme were as follows:

- At the national level, ACWF was responsible for implementation and coordination of counties’ participation in the programme.

- Two national-level experts were involved in supporting programme implementation, through training, or in design and supervision, Professor Li Hongtao (China Women’s University), and Ouyang Yanwen (Hunan Police University).

- At the provincial level, the branches of the Women’s Federation in each province had a small role in convening dissemination meetings at the end of the programme (early 2017) to publicise the models developed by ‘their’ counties.

- In the pilot counties, leadership of the programme was principally the responsibility of the county Women’s Federation, working in collaboration with a number of other local government departments and their subsidiary implementing agencies, including the following: the Public Security Department; the Justice Department / Legal Aid Centre and Courts; the Department of Health and Family Planning (and subsidiary Hospitals and clinics); the Department of Civil Affairs (and subsidiary domestic violence refuges); and grassroots-level official agencies (largely community management offices). In one county, the local Education Department was also included. A fuller explanation of the roles of the different departments is given in Section 5.2.

The programme worked in three pilot counties, which remained stable between EVAW I and EVAW II. The counties are Yilong (Sichuan), Ningxiang (Hunan) and Jingyuan (Gansu). These counties roughly represent different geographical areas and levels of development in predominantly rural central/western China. Yilong is a primarily agricultural county located in north-eastern Sichuan province, in a comparatively hilly region, and at a distance of around 250km from Chengdu, the provincial capital. The county population is 1.01 million, of which 71% is classified as rural. Yilong is designated a national poverty county, with a per capita GDP of 17,910 Rmb. Ningxiang is a comparatively developed county in located in the north-east of Hunan, only an hour and a half from Changsha, the provincial capital, and included in Changha’s economic development zone. The county population is 1.4 million, of which 44% is classified as rural. The county has a per capita GDP of 87,826 Rmb. Jingyuan is located in the east of Gansu Province on the upper reaches of the Yellow River. The county is around 150km from Lanzhou, the provincial capital. The county population is 0.51 million, of which 90% is classified as rural. The county has a per capita GDP of 15,376.

Budget and spending

The total budget for the programme was USD 750,000, comprising USD 500,000 funding by UN Women which was the contribution from Chinese government to UN Women, and a human resource and in-kind contribution from ACWF of USD 250,000. Of UN Women’s budget, approximately 70% was spent on direct provision of activities (training, collation and translation of materials, meetings, field trips and overseas visits), with the remainder going to staff time (UN Women and ACWF), monitoring and overheads.

BACKGROUND TO THE EVALUATION

This evaluation was designed, and data collection was carried out, between May and July 2017. An inception report, containing full methodology for the evaluation, was submitted to UN Women in May 2017. UN Women’s ToR for the evaluation is reproduced in Annex 1 for reference.

Evaluation purpose and objective

In line with the ToR, the evaluation assessed UN Women’s programme on ‘Promoting Efforts for National Legislation on Domestic Violence and Upscale the Multi-sector Model in China (2nd Phase EVAW)’, implemented by ACWF. Under this, the scope of the evaluation was limited to the programme funded by the Government of China over 3 years (July 14th 2014 – July 15th 2017), with a total budget of USD 500,000. The evaluation focused on the 2nd Phase EVAW overall, programme achievements at outcome level, assessed the programme impact against its original design where possible; and identified key successes, lessons and experiences arising during programme implementation at national level and in one county in each of the three selected provinces, namely Hunan, Gansu and Sichuan provinces. The evaluation also assessed the management and coordination structure of the programme and analysed its benefits and shortcomings against the achievements and impact of the programme. The evaluation also provides recommendations for UN Women / ACWF based on findings from the current programme. Full details of methodology and approach can be found in the Inception Report for this evaluation.

Evaluation criteria and questions

As stated in the Inception Report, the evaluation assesses the 2nd Phase EVAW based on the OECD Development Assistance Committee (DAC) criteria of relevance, effectiveness, efficiency, impact and sustainability. Based on this analysis, it provides recommendations to inform future programming and strategic direction:

- Relevance: extent to which the expected results are consistent with beneficiaries’ requirements, country-needs, global priorities, UN Women’s mandate and comparative advantage and partners’ and donors’ policies;

- Effectiveness: extent to which 2nd Phase EVAW outputs/outcomes were achieved, including coordination, management and institutional structure of the programme implementation.

- Efficiency: measures of the programme delivery (monitoring and indicators) and how economically resources/inputs (funds, expertise, time, etc.) are converted to results.

- Sustainability: The probability of continued long-term benefits from the programme results; and

- Impact: change/progress in lives of women and girls suffering violence and possible change/progress in mind set of different stakeholders throughout the programme implementation in contributing to transformational change for gender equality and women's empowerment.

Additionally, the evaluation considered:

- Relationships and coordination with national and sub-national stakeholders, decentralized structures and systems, and identify opportunities for improved collaboration and coordination.

- Relevance, efficiency, and sustainability of the convergence approach in line with the OECD-DAC criteria for evaluation, together with integration of human rights, gender equality and environmental sustainability in line with UN Women’s evaluation criteria.

Key evaluation questions addressed were are as follows:

- Assess the overall Programme progress to analyze to what extent the Programme has met its objectives and targets at outcome and output level;

- Identify the key Programme achievements, lessons (specific or broader Programme lessons), innovations, good practices and experiences that deserve further dissemination;

- Identify the Programme’s contribution to positive policy changes at national and sub-national levels over its implementation period;

- Assess the Programme impact when possible;

- Assess the effectiveness and appropriateness of Programme management and coordination at national level and in Programme sites in Hunan, Gansu and Sichuan provinces to establish multi-sectoral preventing and response approach involving All China Women’s Federation (ACWF), Ministry of Civil Affairs (MOCA), Ministry of Public Security (MPS), National Health and Family Planning Commission (NHFPC), Ministry of Justice (MOJ), Supreme People’s Court, and Supreme People’s Procuratorate.

- Analyze the effectiveness of technical support provided by UN Women;

- Determine whether the Programme is appropriately addressing sustainability and assess the possibility of long-term sustainability of activities that the Programme has supported;

- Based on the above, develop recommendations at operational and strategic level for UN Women its future support to anti-DV work in China.

Evaluation methods and data collection

    - Methods

Given limitations in logframe indicators discussed in the Inception Report (and discussed in more detail in Section 10 of this report), the evaluation team developed several hypotheses to clarify the links between activities supported by the programme and hoped-for outputs, and to guide data collection and analysis. Hypotheses are based on the logframe, supplemented by programme documentation reviewed during the inception period. Full details are available in the Inception Report.

- Hypothesis 1: Activities supported by the programme, including translation of foreign anti-DV legislation, circulation of materials summarising international best practice on tackling DV, and study trips to countries with notable anti-DV practices contribute to improved understanding among law drafters and key themes are selectively incorporated into national DV law.

- Hypothesis 2: Support provided by the programme to county implementing agencies, principally in the form of training and capacity building, contributes to counties’ strengthening of multi-sectoral anti-DV systems and adoption of international practices.

- Hypothesis 3: Capacity building and advocacy activities supported by the programme, including trainings and workshops, increase national participants’ knowledge of international standards and of the value programme’s multi-sectoral model.

- Hypothesis 4: Support provided by the programme to county implementing agencies, principally in the form of training, improves the ability of multi-sectoral service providers and community workers to provide coordinated quality services based on the needs of DV survivors.

- Hypothesis 5: Dissemination activities supported by the programme, principally dissemination meetings held in the three provinces, increase provincial policy makers’ willingness to replicate models developed in the pilot sites.

In the Inception Report, the evaluation team noted that this programme is not a standalone effort to improve China’s anti-domestic violence legislation and provide models for multi-sectoral coordination and response to domestic violence. The programme builds on a body of prior work in the pilot counties and their parent provinces, on existing legislative processes at the national level, including on interventions carried out during the first phase of the programme (2010–2012). Programme activities are consequently unlikely to be unique causes of any observed effects, but should rather be considered contributing causes. The evaluation should therefore be seen as a contribution analysis, which seeks to assess the contribution of the programme to hoped-for changes. The evaluation assesses the extent to which the Programme has met its objectives and targets at outcome and output level. The evaluation team are not primarily interested in assessing the activity level of programming, except to the extent that it can be considered to have a direct bearing on outputs/outcomes, or where the evaluation team judge’s there to be weak links from the activity–output level within the programme logic.

The evaluation employed mixed quantitative and qualitative methods, listed below. Analysis makes use of quantitative analysis of survey responses, plus qualitative analysis of interview data and documents.

- Review of all relevant programme documentation

- Interviews and focus groups with key individuals and agencies both at the national level and in the pilot sites

- Data request / survey of implementing partners in the pilot counties

- Survey of training participants in the pilot counties

    - Data collection

Data collection was carried out in June 2017. Main components of data collection were as follows:

- Desk review of programme documents, and materials developed and used through the programme (summaries of county models, training materials, translated laws, best practice guidelines, etc).

- Interviews with Beijing-based stakeholders: UN Women, the All China Women’s Federation. There were a number of groups that the evaluation team hoped to interview, but with which it was not possible to set up interviews – principally central government  departments other than ACWF.

- Interviews with key programme advisors: Professor Li Hongtao (China Women’s University), and Ouyang Yanwen (Hunan Police University).

- Field visits to three pilot counties, including interviews and focus groups with a range of stakeholders, including community representatives and a number of DV victims/survivors.

- Interviews were carried out in each provincial capital with a range of provincial level stakeholders including the provincial Women’s Federation and other departments engaged in anti-DV work.

- A full list of all interviewees and focus group / meeting participants is given in Annex 2.

- Data request in the form of a survey of county government departments/agencies participating in the programme. the survey covered all three counties, and key participating departments in each county, and requested a range of information relating to implementation, successes, and challenges of the programme. Responses to the survey are cited in the text as follows, e.g.: [CS/Q10] (county survey / question 10).

- Training survey. 130 participants in county-level training organised by the programme were surveyed to regarding their participation in training, learning, and application of learning. Survey results are included as Annex 5.

    - Constraints to data collection and other methodological constraints

The evaluation team would like to recognise the hard work and cooperation of the pilot counties in setting up meetings and visits to the range of partner agencies in each county. Despite this, there were a number of limits to data collection in the pilot counties:

- Time for data collection was relatively limited. The evaluation team visited three provinces and the three pilot counties over a period of ten days. Inevitably, time spent travelling detracted from the actual time available in each county. On average, one and a half to two days were available for fieldwork in each county. This was adequate for interviews/meetings with all main departments involved in the programme, and with community members and a small number of DV victims, but it precluded visits to any remoter sites within the pilot counties. One consequence of this is that all data collection is likely to reflect the comparatively better conditions obtaining in the county towns. There is no way of assessing the degree to which more peripheral townships and villages differ from this.

- In all places, meetings were set up by local implementing agencies and/or their partners. This is inevitable when carrying out such local-level fieldwork in China. While there is no reason to believe that this introduces specific bias into data collection, it is likely that the evaluation team would be shown predominantly good examples of practice.

- During county fieldwork visits, the only health agencies visited by the evaluation team were maternal and child health (MCH) centres. Other health facilities are reported to be involved in the programme in all counties, but the choice of arranging meetings with MCH centres is likely due to the close links between the family planning system, under which MCH centres fall, and the Women’s Federation system. In no county was the evaluation team able to visit a low-level healthcare facility (below county-level: township, village, etc).

- The evaluation team had only limited contact with courts in the pilot counties; less than with other partners involved in the programme.

- Only in Jingyuan did the evaluation team meet with someone in a genuine leadership position at county level (County Head, or Party Secretary). While there is no reason to think that this distorts the data collected, it means that the analysis is at least somewhat incomplete.

- Limited follow up data collection was carried out with non-pilot counties. Following fieldwork, the evaluation team’s assessment was that enough information was available on the potential for scale up from fieldwork in the pilot counties and through multi-stakeholder meetings convened in the provinces. The exception to this was one non-pilot county which was interviewed during the provincial discussion held by the evaluation team in Gansu.

- Some data in the county survey are inconclusive, either due to incompleteness of data, or because of inconsistencies / lack of clarity in data or definitions used.

- Limited data were available allowing an assessment of actual outcomes for victims of domestic violence in the police or legal systems, and such an assessment was outside the scope of this evaluation. Where possible,  however, we have drawn on data made available in the counties  to inform our analysis and/or triangulate our findings.

The evaluation team attempted to overcome the limitations to data collection by triangulating responses given by different departments and counties, and by cross-referencing interview and focus group findings against documents, figures and survey responses where possible. Where the evaluation team has doubts over data or where different sources of information/data are conflicting, we have attempted to recognise this in the report text, to present a balanced picture, and to provide what we consider to be the likely best interpretation.

Ethics, gender and human rights considerations

Domestic violence is associated with broader gender inequality and should be understood from a gender perspective. There is complex relationship between violence and the denial of a woman’s social, economic, political and legal rights and their ability to participate in the processes that influence society. Violence against women also has a major impact on a woman’s right to health. In order to prevent violence against women in any community it is important to understand it in context: it’s origins, how it operates, the myths associated with it and the mechanisms and attitudes that perpetuate it.  It is also important to explore how victims perceive this violence, how the victim is perceived within the community and what consequences there are for the perpetrator within that community and society.

The evaluation team integrated gender analysis into the evaluation. In the three programme counties, as elsewhere in China, norms, culture and society give greater status, influence, control and power to men. This appears to be particularly obvious in northern China. Gender analysis helps us explore the nature of DV in the programme sites and is integrated throughout the evaluation process. The evaluation team systematically asks questions about the differences between the sexes with respect to:

- traditional gender roles, norms, values, expectations and entitlement in three project counties;

- patriarchal practices and unequal power relations between men and women in three project counties;

- the links between the above and anti-DV work supported by the programme.

Domestic and family violence violate human rights. In the pilot counties, in particular, the evaluation team found that it violates women’s right to life, women’s physical and mental health, women’s right to hold opinions without interference and women’s right to be free from torture and other cruel, inhuman or degrading treatment or punishment. However, as the term ‘human rights’ is regarded as politically sensitive in the Chinese context, the evaluation team highlights the practical applications of human rights in the evaluation, for example, whether participants have been empowered to understand that DV is a human rights issue, whether participants have enhanced ability and accountability to respect, protect and fulfil women’s human rights for a life free from domestic violence.

TRAINING, CAPACITY BUILDING AND RAISING AWARENESS

This section analyses the impacts of training in the pilot counties, both training directly supported by the programme and, to an extent, follow-on training carried out by the pilot counties themselves, or by individual departments in those counties. The evaluation team adopted a simple schematic model to understand the likely process of impact of training, for carrying out of activities to increasing knowledge/awareness to changing norms and behaviours. Analysis in this section follows that model and assesses the effectiveness of training through the levels of impact that one should hope to see.

Consolidated findings

- Survey and interview data show that training was well-designed and carried out and that it is, for the most part, relevant or highly relevant to the work of trainees targeted in the training. Most trainees rate the training as extremely useful. Survey responses show that overwhelmingly trainees think that the training has given them at least a basic understanding of domestic violence and of the principles and practice of work of their departments in preventing and halting domestic violence. Interviewees report that the training has imparted a lot of legal and practical information regarding domestic violence and that they are able to make use of this in their work and/or impart this to others. Practical information on China’s law on domestic violence and similar documents were included as annexes to training materials and trainees state that these have been useful in their work.

- Although the training was well targeted and very relevant to trainees, in the assessment of the evaluation team, there are a number of areas in which improvements could be made in subsequent training design, including through better tailoring to individual counties’ situations; more clearly stressing practical skills, such as communication, alongside legal information; more strongly stressing gender perspectives; and more clearly emphasising correct definitions of, and specifying the scope and nature of, domestic violence.

- The evaluation found that training is creating awareness of concepts and theory of domestic violence, with a majority of trainees stating that they have a basic/good understanding of domestic violence following training, and assenting to normative statements describing domestic violence as a result of patriarchal culture and institutions and as a rights issue. The programme, and training carried out through the programme, are clearly influencing understandings and knowledge and, to an extent norms of trainees, but it appears that entrenched norms are hard to change fundamentally in a relatively short timeframe. Both survey and interview evidence show that misconceptions around the attribution of fault, and possible remedies for domestic violence, persist.

- Interviews carried out during fieldwork tend to indicate that norms are related, at least to an extent, to levels of development. The three pilot counties have different starting points: interviewees in Ningxiang and Jingyuan, for example, related very different underlying assumptions about expected male and female roles and the acceptability of violence. All counties appear to be making progress in improving knowledge and changing norms, but the degree of progress visible at present differs between counties. This should be considered natural, and supports the need for continued training and widespread training and awareness raising work.

- At the level of behaviour, a number of interviewees in all counties reported incidents in which they had been able to use knowledge regarding domestic violence in their work or in dealing with others.

- The organisation of follow-on training differs in the three programme counties and between different departments in each of the counties, with some reporting relatively strong support for organised follow-on training, and others reporting little such support. Given the progress made by the programme, but also the need for sustained and deepened training, the evaluation team believe that it is important to create more systematic approaches to training in the counties.

The remainder of the section discusses detailed evaluation findings supporting the above analysis.

Training

Training is the main activity supported by the programme in the counties, and a substantial component of this analysis. Programme-supported training has used materials developed during the first phase of the programme, the Handbook on multi-departmental cooperation for the prevention and halting of domestic violence. Participants in trainings have largely been from a number of government agencies (Women’s Federation, Public Security Department, Health and Family Planning Department, Justice Department, Civil Affairs Department and shelters), as well a number of domestic violence victims and community-level staff. The scope of this evaluation includes large-scale trainings, as well as training-of-trainers trainings, carried out in the three pilot counties. Assessment is based on surveys administered with trainees and focus group discussions carried out during fieldwork, and contains the following main components:

- Training design: methods and content

- Changing knowledge and awareness

- Changing norms and values

- Changing behaviour

Survey data on training were collected through two surveys: the survey of departments taking part in the programme in the pilot counties, discussed above, and a survey targeting trainees in the three counties. Survey respondents were selected randomly from training name lists provided by the county Women’s Federation offices. 130 surveys were collected (n = Yilong, 51; Ningxiang, 33; Jingyuan, 46). Of respondents, 31.6% report that their work is closely related to domestic violence, 55.4% report that their work has some relation to domestic violence. Of the remaining 15%, around 9% report that they are victims of domestic violence and that their work is not closely related to domestic violence. The remaining 6% report that their work is not very relevant to domestic violence. In addition to this, the evaluation team held focus group discussions with trainees in the three programme counties, principally representatives of county-level departments/agencies or community-level representatives. Focus group discussions averaged 5-12 people.

Following the anti-DV training, the awareness and conscientiousness of institutions involved in responding to DV have improved. As one police officer from Yilong Police Bureau said, “After participating in two trainings, I learned a lot about the legal situation regarding DV and improved my awareness. I become more victim-centred, more active and more responsible in anti-DV work. We used not to pay attention to this – in almost ten years of working at the grassroots level, we never considered this important. Now we know that it is important. The attitude of 110 operators can be crucial. Improving our understanding is important – the Police Department is on the frontline of anti-DV work. Take the idea of ‘victim-centred’ services – before, most people thought that if there was domestic violence, then the victim must be partly to blame. Now, we understand that it is important to understand the multiple problems victims face, we differentiate more between cases, and are more able to consider the real needs of victims and act in a more professional way. Cases are handled in a more codified way ”.

Following the anti-DV training, the awareness and conscientiousness of institutions involved in responding to DV have improved. As one police officer from Yilong Police Bureau said, “After participating in two trainings, I learned a lot about the legal situation regarding DV and improved my awareness. I become more victim-centred, more active and more responsible in anti-DV work. We used not to pay attention to this – in almost ten years of working at the grassroots level, we never considered this important. Now we know that it is important. The attitude of 110 operators can be crucial. Improving our understanding is important – the Police Department is on the frontline of anti-DV work. Take the idea of ‘victim-centred’ services – before, most people thought that if there was domestic violence, then the victim must be partly to blame. Now, we understand that it is important to understand the multiple problems victims face, we differentiate more between cases, and are more able to consider the real needs of victims and act in a more professional way. Cases are handled in a more codified way ”.

Training design: methods and content

Survey results show that design of the training in the second phase of the programme is quite closely integrated with work carried out in the first phase of the programme, and that it made use of materials developed during that phase. In terms of human rights principles, in interviews with training designers and trainers, interviewees recognise that violence against women denies women their most basic human rights and is also a major threat to the social and economic development of communities.

Training was well-designed, made use of participatory methods, and was practical in orientation. Following training, 80% of participants state that they have at least a basic understanding of domestic violence, and 80% state that they have at least a basic understanding of the principles and practices of work of their departments in preventing and stopping domestic violence. Almost 40% state that cases used/discussed during training have an extremely close link to real situations encountered during their work, and around one third state that cases used/discussed during training have a basic link to real situations encountered during their work. 70% of respondents state that the participation of victims of domestic violence in the work of their agency/department is extremely important. Most training participants state that they following training have a good understanding of law related to domestic violence and trust in the law. During fieldwork discussions, most interviewees (including community representatives) stated that since the release of China’s law on domestic violence law in March 2016, they have seen improvements in anti-domestic violence work in their working environment and/or life.

Annexes to the training materials contain practical and useful information. For example, more than half of survey respondents state that they have used materials related to China’s law and regulations included as annexes in their work. According to one interviewee from Yilong,

Previously, I didn’t have an in-depth knowledge of domestic violence prevention and hadn’t thought about this, meaning that I wasn’t able to tell people about this in detail when carrying out awareness raising activities (xuanchuan). During training, the teacher summarised a lot of legal information for us, and now we can clearly explain this to others, and help women understand whether they are victims of domestic violence.

Use of participatory training methods appears to have been considered effective by trainees, and many trainees recall use of these methods and the setting of training. Trainees’ assessment of the content of the training is highly positive, with most (60%) rating the content as extremely useful.

In our assessment, the training has a number of areas where improvements could be made:

- Training design could more thoroughly consider the differences between the three pilot counties and the specific needs of participants from different departments. Training design could make use of participatory needs assessment approaches.

- From fieldwork, it appears that the main content of training relates to law, and legal knowledge/processes. Content on how to communicate with domestic violence victims, counselling and related practical skills could be stressed more.

- Gender concepts and approaches appear to have been insufficiently stressed in the training (this is discussed in more detail below).

- There appears to be a need to more clearly define and specify the scope and nature of domestic violence, particularly the following:

- The scope of domestic violence should be expanded from a narrow focus on close relatives. Survey results show that without exception, respondents define domestic violence as occurring within marriage. As recent research shows, violence among cohabiting, unmarried couples, and among former partners who have separated or between divorced former spouses should also be included in the scope of domestic violence.

- Clearer specification of degrees of severity of domestic violence. Training should make clear that although many cases of violent behaviour are not sufficient to warrant involvement of police or to be deemed criminal behaviour, such behaviours should still be considered domestic violence, and that victims still require help and support.

- As both surveys and fieldwork show, the vast majority of trainees understand domestic violence as physical violence, and this is reflected in the instances of violence that they report encountering during their work. They have little understanding of other forms of violence, such as economic or sexual violence.

Changing knowledge and awareness

Overall, trainees’ understandings of concepts and theory of domestic violence are clear. The majority of trainees state that they understand the nature, forms, characteristics and causes of domestic violence (41.5% state that they have a very good understanding, 43.1% state that they have a basic understanding), while 79.2% agree with the statement that “the basic cause of domestic violence is the existence patriarchal cultural and institutional systems and of unequal rights of different sexes”, and 83.1% agree with the statement that “domestic violence is a serious infringement of the human rights of women”. In focus group discussions in Ningxiang and Yilong, participants stated clearly that this is related to traditional cultural norms that view men as superior to women, and to women’s inferior economic status as compared to men. As one trainee stated in discussion, “after training, I came to understand that for whatever reason it occurs, domestic violence is illegal”. As the Chair of Yilong Women’s Federation stated,

Before, people used to think that when the husband comes home, and his wife doesn’t even get him a glass of water, then he should beat her! People don’t think that way anymore. Before, people would suggest to women [who were victims of violence] to make more of an effort. Now people understand that violence is not acceptable, whatever the circumstances – even if your wife has done something wrong, it’s still not ok to beat her.

Despite these changes, there is evidence that training is not yet creating obvious, large-scale changes in awareness. Survey results show that 31.5% of trainees believe that “perpetrators and victims of domestic violence both have responsibility for domestic violence”, while 16.2% of respondents state that “domestic violence can be solved by women making more of an effort to look after the interests of men”. These findings were mirrored by fieldwork findings, for example those in Yilong in which one highly-experienced (and decorated) stated that “if a woman makes more of an effort with her appearance and the housework, it can stop her husband beating her”. A proportion of county-level staff from multiple departments, as well as a majority of community-level staff and residents interviewed state that in cases of domestic violence “both the husband and wife are at fault”. In some, but by no means all, cases interviewees were able to state that the main root cause of domestic violence is the inequality in rights in relations between husband and wife.

The above evidence tends to indicate that gender and rights-based approaches have been insufficiently communicated through training.

Changing norms and values

The basic fundamental approach to combating domestic violence is through changing traditional gender norms. Challenging traditional concepts of gender and gender values is an important aim of this programme. During fieldwork, the evaluation team found similar attitudes to domestic violence in all three programme counties, but that there are differences, seemingly largely related to differences between the counties’ levels of economic development and cultural openness and openness in people’s ways of thinking. These factors have led to substantial differences between the counties. For example, in Ningxiang community-level respondents stated that “domestic violence, men beating women, has been unacceptable for many years, especially among the young – no-one would tolerate this kind of behaviour”, whereas in Jingyuan a community group leader stated that “if you annoy your husband, you can expect him to beat you … When we got married, the woman who introduced us said to our face that husbands should beat their wives, that a bit of light beating is fine. [A lot of people] still think that way now”. This indicates the difference in starting points in the different pilot counties, regarding gender norms and practices. Given the different starting points, it is not reasonable to expect that the three counties would reach similar points in reforming traditional gender norms.

Changing awareness and gender norms is a long-term endeavour – it is hard to change embedded traditional norms and gender consciousness through short term training activities. As discussed above, although we can see changes in understanding of domestic violence, change is not yet sufficiently deep to challenge embedded social conceptions of gender, and from there challenge traditional norms and values. Saying this, in all pilot counties, it is possible to see that the range of trainees involved in the programme, including those from county-level agencies and community (shequ) representatives have made progress, though from different starting points.

Changing behaviour

A fundamental part of the logic of the programme is to use training to promote increasing awareness/knowledge, increase skills, and from there change behaviours. However, this is a long-term process, and one which it is, too early to comprehensively assess at this stage. Despite this, the evaluation team noted a number of encouraging changes in behaviour. Discussion in this section is divided into a number of components, discussed in turn below.

    - Changes brought by programme-organised training

Survey results and interviews in the pilot counties indicate that, to an extent, training has actively changed behaviours, for example in Yilong, trainees from all departments stated that the establishment of a multi-departmental system had developed into a system of mutual supervision and mutual-motivation, saying that ”if everyone else is doing it, my department mustn’t make a mistake”, and that this had transformed people’s attitudes and behaviours. One interviewee from the police system stated that “after taking part in training, I became more active and conscientious in my work on domestic violence – as a low-level police officer, my previous attitude to domestic violence was quite indifferent. In almost ten years working at the grassroots, I had come across a lot of cases of domestic violence, but never considered them important, but now I do”. In Ningxiang, community-level staff showed penetrating understandings of domestic violence, and anti-domestic violence work, and stated that this is now a mission for them, something they care deeply about, and that they are working hard to propagate knowledge on domestic violence and to help domestic violence victims to get aid and support. One domestic violence victim in Jingyuan stated that, through participation in programme activities she had understood a lot about domestic violence and the causes of domestic violence, and was more willing to pass on this knowledge during her work (including through conversations with her colleagues), to promote positive messages, and to help other domestic violence victims escape from violence.

The survey found that in all counties, respondents were able to give examples of how training had influenced their practice. For example, one trainee in Yilong stated that through training they had learnt how to help domestic violence victims contact the police and the women’s federation, to gain a divorce, and to avoid becoming a repeat victim of violence. One trainee from Ningxiang gave the example of assisting a victim of domestic violence in accessing a shelter and contacting the police station, while in Jingyuan on respondent described passing on knowledge about domestic violence to victims who asked for assistance, and persuading them to seek legal assistance and legal protection.

    - Follow-on training

‘Training of trainers’ (TOT) was organised in each county to develop a cadre of local staff capable of carrying out training on domestic violence within their own organisations/systems and within the community. Survey responses show that each county has carried out follow-up trainings locally. For example, Yilong Women’s Federation organised four trainings targeting grassroots cadres, grassroots Women’s Federation staff, etc. Ningxiang organised five such trainings, including ones for staff whose work relates to domestic violence, and within-county training of trainers sessions. Jingyuan organised five trainings.

Following training, 35.4% of trainees state that they have passed on a lot of knowledge of, or skills related to, domestic violence to their colleagues, while 58.5% state that they have passed on some. From fieldwork/interviews, it appears that trainees in the police system are well-placed to carry out follow-on training through, for example, weekly meetings and/or virtual training sessions capable of reaching large numbers of people. For example, members of police staff from both Yilong and Jingyuan have carried out trainings specific anti-domestic violence training within their counties’ police systems, as well as carrying out awareness raising activities at a county level. This is encouraging, though it is not possible to know the effectiveness of this training. Other departments appear to have done little such systematic follow-on training. In county interviews, the most common form of follow-on described was ‘making use of meetings to carry out training’ (yi hui dai xun), which is almost certain to be less effective than systematic training.

It is clearly important that counties continue to carry out training, both within government departments and within the community, and that the extent and reach of this be deepened. Although the scale of training carried out to date appears limited, this should not be attributed ‘TOT trainees’, but rather:

- No targets were set for local-level follow-on training, and no targeted handbook for follow-on training was provided to TOT trainees.

- Without official support for, and organisation of, follow-on training, it will be hard to develop organised training at scale. This requires support from county government to support the inclusion of training in the work of all departments.

Comparatively speaking, Ningxiang’s follow-on training has emphasised the important of including grassroots staff. Although Ningxiang Women’s Federation does not appear to have a systematic programme of follow-on training, community-level staff have not only learned a lot about domestic violence, but have also shown significant changes in awareness and behaviour. For example, the chair of the Women’s Federation in one community, Huang, showed evidence of thoroughly reflecting on domestic violence, its causes, and her work, and had in recent years done a lot of work to disseminate knowledge about domestic violence in the community where she works, as well as actively intervening in cases of domestic violence, including integrating tools made available through the programme into her work. As Huang stated,

I got a lot from the training. Working for the women’s federation, I had come across cases of domestic violence before. I would normally try to carry out mediation in such cases; I wouldn’t carry out a risk assessment, I’d attempt to reconcile the couple, or try to educate both husband and wife and give them a telling off – local government has status with the people. But now, having taken part in training, lots of my thinking and my ways of working have changed; I won’t automatically think of trying mediation – first I’ll do a risk assessment, and try to persuade the victim to explain truthfully what happened. Before, I didn’t know how to listen, but now I am conscious of my listening skills, and try to reassure the woman that I am professional. People’s situations are very varied; it may be that her situation isn’t suited to mediation. Now, I’ll also refer women to other departments – referral is much more than it was before, including with health facilities and with the police station. We’ve developed an effective network.

The above reflects differences in the impact of the training in the counties – the difference in knowledge, attitudes and changes in behaviour in Yilong and Ningxiang are very great. In the view of the evaluation team, apart from differences in programme implementation this is linked to the starting points in the different counties. Hunan is a province which has done a lot of work on dealing with domestic violence, and which has had a long period of work on changing understandings and awareness of domestic violence. Compared with the other two pilot counties, Ningxiang has extended its work to the grassroots/community level and developed a very strong base for responding to domestic violence.

    - Grassroots awareness raising activities

Interviews in all counties stressed the importance of grassroots-level awareness raising work (xuanchuan) for increasing popular understanding and fundamentally changing traditional views of domestic violence. Survey results show that awareness raising regarding the domestic violence law work is a component of all counties’ activities. Counties have used posters, leaflets, booklets, calendars, etc, as part of multi-strand activities to increase knowledge of domestic violence, including in townships and rural areas.

The following are examples of activities supported by the pilot counties, though are by no means exhaustive: Yilong Public Security Department printed 100,000 leaflets titled “building a harmonious society and opposing domestic violence”, and distributed them through grassroots police stations. They also organised legal lectures, and other activities, targeting students, rural residents, and women and children. In total, they calculate that they have reached 170,000 people/times. Ningxiang Public Security Department distributed 5,000 copies of materials explaining the law on domestic violence and processes for accessing official anti-domestic violence services, as well as related activities. They calculate that they have reached 35,000 people/times. Jingyuan Public Security Department distributed 20,000 copies of materials regarding the domestic violence law through police stations, as well as other domestic-violence related materials. They have also organised a range of activities to disseminate information about domestic violence in communities, companies, schools through disseminating materials, carrying out lectures, providing legal advice, etc. They calculate that they have reached 200,000 people/times.

Feedback during community-level discussions tends to indicate that awareness raising activities by Justice Departments in the counties have had the greatest impact. In Ningxiang, for example, all thirteen community representatives interviewed, irrespective of age, were able to accurately report to the evaluation team knowledge on domestic violence and that this was acquired through activities/materials organized/distributed by the county’s Justice Department. Counties report that they make use of Women’s Day and other specific events to publicise domestic violence. From interviews in the counties, it appears that there are differences in counties’ practices.

Further actions and recommendations

- Further develop follow-on training, through developing targets for training activities and providing resources for these.

- Attempt to gain government backing for the inclusion of training in the work of all government departments.

- The programme has trained a number of TOT trainees. This capacity will need to be strengthened and updated over time, including with content on new legislation and on best practices in other places.

BUILDING SYSTEMS AND INSTITUTIONALISING WORK

Systems for coordinating the work of different departments involved in domestic violence response have principally been developed locally by the local Women’s Federation and other collaborating departments. Equally, the ways in which local government departments (including police, legal departments, courts, health, and shelters) provide services to victims of domestic violence varies somewhat between counties. Training provided by the programme has contributed to the development of these systems, but does not fully determine their operation or functioning.

Consolidated findings

- A number of forms of inter-departmental coordination are in operation in the pilot counties, including regularised high-level meetings, referral systems, and working-level links. All counties report stable mechanisms for leadership coordination on domestic violence, principally led by the Women’s Federation, though the frequency of inter-departmental meetings varies by county. Few counties appear to use ad hoc coordination meetings frequently. All counties rate these coordination systems as functioning well and there is a high degree of consistency in how different departments/counties assess the function of coordination meetings. Below the formal inter-departmental meeting system, working-level coordination between departments involved in domestic violence work is emerging. This appears to show institutionalisation of inter-departmental working practices, though it is possible that the degree of institutionalisation differs between counties.

- All, or nearly all, departments surveyed responded that they are aware of the services that their department should provide, that they are aware of what services are available from other departments, and they have specific information on which offices and/or people to contact during referral, and that staff have received training on referral work. For all but one department consulted, the inter-departmental meeting system does not create difficulties for their work, or extra burden. All departments surveyed responded that inter-departmental cooperation has advantages, compared to each department working in isolation on DV cases, and there is broad consistency in counties’ and departments’ rationalising of this.

- County survey data appears to show that referral is routinised in the three counties. Referral patterns differ by county, and levels of referral appear to be low in some cases. Analysis of referral data seems to show that referrals to the justice system (Justice Department or Legal Aid) are among the most common destinations for referrals in the counties, which appears to be a positive finding. From the survey data, where referral does not take place, it is not possible to state what reasons for this are or what actions have been taken in cases that were not referred. Within-system referral is an important component of overall coordination within the counties’ systems, appears to differ by department, and may merit further investigation. A number of barriers to referral were raised during fieldwork, and merit further exploration. Data on follow up on domestic violence cases appears to be limited and is unlikely to accurately reflect the real number of cases in which follow up is carried out.

- Levels of reporting of domestic violence are likely to underestimate its incidence, and systems currently used for reporting and recording numbers of cases are likely to only capture a subset of case, and to suffer from a number of biases/inadequacies. It appears to be important to develop better data reporting and recording systems that can more accurately assess incidence of domestic violence and provide a better basis for resource allocation and decision making.

- Counties are including domestic violence in performance assessment. Done well, this has the potential to be a positive thing; done badly, this could create poor systemic incentives for dealing with domestic violence. There appears to be merit in better assessing how these are functioning and how to create appropriate systemic incentives.

- Leadership attention to, and backing for, inter-departmental working is strongly stressed as important in all programme counties. While counties/departments state that they are not concerned about the sustainability of systems built through this programme, they list a number of challenges to their work on domestic violence. These are summarised in Section 4.2.3 and would benefit from further discussion with the counties. Most counties/departments report that a degree of public financial support for domestic violence work is available; this is a positive thing and should help sustain the results of this programme. However, if, as should be hoped, the number of domestic violence cases reported to authorities continues to increase, this may create a burden on funding/resources going forward. One area in which ongoing support and resources are likely to be necessary is in support for continued and deepened training.

The remainder of the section discusses detailed evaluation findings supporting the above analysis.

Main features of county systems

The following table summarises the main responsibilities of participating agencies in the three pilot counties.

Table 1: Main features of county systems

| Departments/mechanisms | Mandates/functions |
| --- | --- |
| Cross-department meeting mechanism | - All counties - Led by Women’s Federation |
| Referral system in place | - All counties - Differences in patterns of referral |
| Main point for coordination of management of individual cases | - First responder follow-up system in place in all counties |
| Data sharing / cross-department information system in place? | - Departments report data sharing but unified cross-department information sharing mechanisms not in place |
| Women’s Federation | - Leading coordination of multiple participating departments - Recording complaints - Referral to other departments - May coordinate follow-on training within county - May engage in mediation of DV cases |
| Public Security Department | - DV included in work of 110 hotline - Responding to reports of domestic violence - May carry out mediation of DV cases - Issuing warning letters - Collecting/providing evidence for use in legal cases - Referral to other departments |
| Justice Department / Legal Aid Centre | - Providing legal aid - Referral to other departments - Subsidiary agencies may engage in mediation of DV cases |
| Courts | - Processing domestic violence and/or divorce cases - Issuing of protection orders - Courts may also organise panels of judges (he yi ting) and invite women’s federation and community representatives to take part in DV cases |
| Hospitals and clinics, under direction of Department of Health and Family Planning | - Providing treatment and some counselling - Recording of clinical evidence of DV - Referral to other departments |
| Department of Civil Affairs | - Set up and manage DV shelters |
| Education Departments | - Education department/institutions included in Ningxiang - Awareness raising activities (xuanchuan) have been carried out in educational institutions in all counties |
| Grassroots-level official agencies | - Community (shequ) office involved in all counties - Community-level Women’s federation, police stations, clinics, etc, involved in all counties - Village officials and management of residential communities (xiaoqu) involved, though patterns of involvement may differ |
| Media coverage | - Reforms in all counties have been covered by local, and sometimes national, media |

Forms of coordination in the pilot counties

The evaluation team identified the following main forms of coordination on domestic violence present in the plot counties:

- inter-departmental coordination including different county-level departments involved in responding to domestic violence, both at leadership and working levels;

- referral mechanisms linking departments involved in responding to domestic violence;

- within-system coordination.

These forms of coordination are discussed in the following sections.

    - Inter-departmental coordination mechanisms

Main findings regarding inter-departmental coordination are as follows:

- Inter-departmental coordination structures exist in all three pilot counties [CS/Q2]. All departments surveyed in each pilot county rate the functioning of the coordination mechanism as 4 or 5, out of a maximum 5 points [CS/Q6]. Main constituent departments are the Women’s Federation, the Public Security Department, the Justice Department, the Department of Health and Family Planning, and the Department of Civil Affairs. The main coordination body in each county is stated as the Women’s Federation [CS/Q5]. Although all departments are nominally equal partners, in most counties, Civil Affairs seems to play a relatively minor role, while the Public Security Department has a substantial role in all counties. In Ningxiang, the Education Department is also directly involved. Interviews appear to show some differences in the relative strength and participation of other departments (discussed below). In all cases, the principal agencies involved appear to be county-level departments; township-level agencies do not appear to be involved in coordination meetings.

- From responses to the survey of the pilot counties, inter-departmental coordination meetings appear routinised, though the frequency varies between counties: Yilong and Ningxiang report that routine coordination meetings are held every quarter, while Jingyuan report that meetings are held every month. Ningxiang report that the frequency of meetings has decreased as inter-departmental cooperation has become more routinised, requiring less high/management-level coordination. Survey responses indicate that ad hoc coordination meetings are uncommon: only Jingyuan reports using such meetings, though responses from Ningxiang show specific departments calling irregular meetings [CS/Q3].

As a judge from the justice department in one county said, “I feel my work is on stronger ground now and that other departments are supporting me. The work has a great deterrent effect on abusers. DV victims used to rely on their families, now they can rely on the government ”.

As a judge from the justice department in one county said, “I feel my work is on stronger ground now and that other departments are supporting me. The work has a great deterrent effect on abusers. DV victims used to rely on their families, now they can rely on the government ”.

There is a high level of consistency in pilot counties’ survey responses regarding the function of coordination meetings [CS/Q4], both across departments in individual pilot counties and across counties. Main functions are listed as: information/experience sharing and inter-departmental communication; increasing inter-departmental coordination; discussing problems encountered during ADV work and how to resolve them; and discussing DV cases and case follow up.

- According to survey results [CS/Q9, CS/Q10], all but one department involved in the pilot state that inter-departmental coordination has not created work difficulties (kunnan) for their department, led to a lack of clarity over departmental mandates, or led to burdensome (fansuo) work practices. In almost all survey responses, individual departments describe the inter-departmental coordination mechanism as beneficial. Benefits cited include: clarifying the relative roles of different departments in dealing with domestic violence; increasing cooperation or communication; and establishing a system of named individuals in each department with responsibility for liaison with other departments.

Following the establishment of the multi-departmental anti-domestic violence system, the degree of professionalism with which cases are handled appears to have increased. As one lawyer in Yilong describes it, “Now there is a system for multi-departmental cooperation, the working process of different departments has become more regulated and professional, and can more effectively protect victims’ rights. For instance, evidence collection by police departments at the scene of the DV incident has a great impact in maximizing the rights of DV victims, while health departments now record injures, and the cause of injuries, in detail, and this information is important evidence in the judicial process .”

Following the establishment of the multi-departmental anti-domestic violence system, the degree of professionalism with which cases are handled appears to have increased. As one lawyer in Yilong describes it, “Now there is a system for multi-departmental cooperation, the working process of different departments has become more regulated and professional, and can more effectively protect victims’ rights. For instance, evidence collection by police departments at the scene of the DV incident has a great impact in maximizing the rights of DV victims, while health departments now record injures, and the cause of injuries, in detail, and this information is important evidence in the judicial process .”

- One department is an exception to this positive appraisal, stating that the department leading cooperation lacks clarity over the division of responsibility between different departments, lacks understanding of domestic violence work and processes, and that it is necessary to increase mutual understanding between departments.

As  one police officer stated, “previously, we had to rely on personal relationships to refer [DV victims) to other government departments, but now we can do that through regularized channels”.

As  one police officer stated, “previously, we had to rely on personal relationships to refer [DV victims) to other government departments, but now we can do that through regularized channels”.

All departments surveyed responded that inter-departmental cooperation has advantages, compared to each department working in isolation on DV cases [CS/Q10]. Survey responses cite the following main advantages: clarifying the mandates of different department and regularising work procedures; ensuring that DV victims can access governmental services; providing multiple and integrated services to DV victims and preventing gaps in services provided by different departments; increasing the strength of anti-DV work through cooperation; creating a network of people working

on DV; allowing referral to appropriate services (e.g. medical services, shelters). Responses from multiple departments recognise the importance of inter-departmental collaboration in addressing the complex/plural needs of DV victims.

- Interviewees stated clearly that leadership attention and support are necessary to the successful development of the programme. A finding in many fieldwork interviews was that departments involved in the programme stressed the importance of strong leadership support for inter-departmental cooperation, including financial support, backing for related policies, administrative support, etc. Interviewees also stressed the importance of leaders’ prioritising (zhongshi) work on domestic violence in supporting their engagement in this work, and in clarifying and increasing its legitimacy.

- Counties are including anti-domestic violence work in departmental and/or government personnel assessment systems (kaohe/kaoping). According to interviews, anti-domestic violence work is included in personnel assessment in multiple ways; the departments assessed, the departments doing the assessment, and the forms of assessment used (including indicators, targets, etc) appear to differ between counties. Inclusion of anti-domestic violence in personnel assessment is likely to create career and material incentives for targeted departments to attach importance to domestic violence, though without further investigation it is not possible to say how this is currently functioning. Managed well, such systems could create incentives for government departments to respond appropriately to domestic violence; managed poorly, they could create perverse incentives – such as to under-report cases, to downplay the importance of the problem, or to treat domestic violence cases in certain ways. This may be the case where domestic violence is treated as a public order (wei wen) issue. Current practices may deserve further attention with a view to summarising best practices and effective indicators that could be used by pilot counties and/or non-pilot counties during scale up.

- Counties report that working-level coordination takes place between formal, high-level coordination meetings. Interviewees in Ningxiang and Jingyuan, particularly, report that good working links are now established between key departments involved in the programme, and that these allow easy communication and problem-solving between departments. For example, interviewees in both places report that it is easy to call colleagues in other departments on matters relating to specific domestic violence cases, or to convene small scale, working-level meetings with colleagues from other departments to discuss or deal with aspects of specific cases. In some cases (notably Jingyuan) colleagues from different departments involved in work on domestic violence through the programme have set up WeChat groups to facilitate communication.

- The key departments pushing the programme appear to differ somewhat in the pilot counties. While in Ningxiang and Yilong, interviews indicate that the Women’s Federation is the lead agency in domestic violence work, with support from the police and other departments, in Jingyuan the local Public Security Department appears to play the de facto leading role, to the extent that one local police officer frequently speaks on behalf of the programme, and the Women’s Federation believes that the Public Security Department is a suitable institutional ‘home’ for anti-domestic violence work, because of its greater resources and institutional capital in the local administrative system, compared to the Women’s Federation. In counties where one or two departments are particularly close and have a driving role in ADV work, it is possible that other departments’ needs/interests are insufficiently articulated.

- Strong working-level links, as discussed here, appear to be an indicator of the institutionalisation of the inter-departmental coordination structures being put in place by the programme, though it appears that these links are, to an extent at least, inter-personal, meaning that there is a possibility that they could be eroded if there is significant staff turnover in any of the key departments involved in the programme. The degree of institutionalisation of these links may differ between counties.

- Jingyuan is a pilot county for reform of the Women’s Federation, through which the county Women’s Federation has county-level approval to bring individuals from other departments into work of the Women’s Federation. According to interviews, this allows the women’s federation to easily convene meetings, without the need for specific approval and increases the legitimacy of their cross-departmental work.

    - Referral system

The following table summarises counties’ survey responses regarding inter-departmental referral (figures cover the second phase of the programme, 2014-2017).

Table 2: Referral data

| Referring department |  |  | Referral to other departments (by destination department) |  |  |  |  |  |  |  |  | Referral from other departments (by source department) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total/ DV cases | Total / followed up | WF | PD | Health | JD/LA | Court | Law | CA/R | GPO | Home | WF | PD | Health | JD | Court | Law. | CA/R |
| Yilong |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Health | 66 | 62 | 25 |  |  |  |  |  |  |  |  | 45 |  |  |  |  |  |  |
| WF | 134 | no data |  | 48 | 45 | 65 |  |  | 8 |  |  |  | 19 | 25 |  |  |  |  |
| CA/R | 33 | 22 |  |  |  | 13 |  |  |  |  |  | 8 |  |  |  |  |  |  |
| PD | 187 | 69 | 19 |  |  |  |  |  |  |  |  | 48 |  |  |  |  |  |  |
| Sub-total |  |  | 44 | 48 | 45 | 78 |  |  | 8 |  |  |  |  |  |  |  |  |  |
| Ningxiang |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Health | no data | no data | 17 |  |  | 25 | 8 | 5 |  | 11 | 15 |  |  |  |  |  |  |  |
| WF | 502 | 426 | 37* | 125 |  | 140 | 75 |  | 49 |  |  |  | 5 | 28 |  |  |  | 13 |
| CA/R | 58 | 17 | 49 |  | 6 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |
| PD | 1,537 | 1,537 | 126 |  |  |  |  |  |  |  |  |  | ✓ |  |  | ✓ |  | ✓ |
| Sub-total |  |  | 229 | 125 | 6 | 169 | 83 | 5 | 49 | 11 | 15 |  |  |  |  |  |  |  |
| Jingyuan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Health | 150 | 85 | 20 | 24 |  | 79 |  |  | 22 |  |  |  | 7 |  |  |  |  |  |
| WF | 150 | 130 | 25* | 26 | 12 | 65 |  |  | 2 |  |  |  | 7 | 5 |  |  |  | 3 |
| CA/R | 22 | 22 | 6 |  | 1 |  |  |  |  |  |  | 4 |  |  |  |  |  |  |
| PD | 225 | 46 | 7 |  |  |  |  |  |  |  |  | 26 |  |  |  |  |  |  |
| JD/LA | 320 | 146 |  |  |  |  |  |  |  |  |  | 65 |  |  |  |  |  |  |
| Sub-total |  |  | 58 | 50 | 13 | 144 |  |  | 24 |  |  |  |  |  |  |  |  |  |
| Notes: (1) Total/ DV cases: total number of DV cases processed by department. (2) Total / followed up: total number of DV cases followed up on by department. (3) Abbreviations of departmental names used in the table: WF, Women’s Federation; PD, Public Security Department; health, Health and Family Planning Department and/or clinics, hospitals; JD/L, Justice Department / legal aid; law, lawyer; CA/R, Civil Affairs Department / shelter; GMO, General Management Office (Zhong Zhi Ban), a county government department whose mandate includes social management, stability. (4) Note that WF* refers to sub-county branches of the women’s federation – i.e. downward referral within the WF system. (5) A tick (✓) is used to indicate sources of referrals where only aggregate figures are given in survey responses, and breakdown by individual departments is not possible. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Main findings from survey data:

- Knowledge, awareness, and service provision:

Following the establishment of the multi-departmental anti-DV system, different departments’ responsibilities have become clearer and more institutionalized – as one police officer in Jingyuan Police Bureau explained: “Our responsibilities include responding to calls for assistance,  investigating and collecting evidence, assisting victims to access the health centre and get their injuries assessed, informing Civil Affairs to assess the victim’s vulnerability, and giving a warning to the perpetrator of and monitoring him”.

Following the establishment of the multi-departmental anti-DV system, different departments’ responsibilities have become clearer and more institutionalized – as one police officer in Jingyuan Police Bureau explained: “Our responsibilities include responding to calls for assistance,  investigating and collecting evidence, assisting victims to access the health centre and get their injuries assessed, informing Civil Affairs to assess the victim’s vulnerability, and giving a warning to the perpetrator of and monitoring him”.

- All departments that provided responses (n = 14/15) report that they are aware of the services that their department should provide [CS/Q18], that they are aware of what services are available from other departments, and they have specific information on which offices and/or people to contact during referral [CS/Q17].

- All departments that provided responses (n = 14/15) report that they carry out ‘participatory’ [CS/Q16] discussions with DV victims during the course of providing services. Where examples of this are given, these include using victim-centred approaches, approaches designed to elicit information on the form/frequency of violence, injuries, background and or family situation, providing information on other available services, etc.

- All departments that provided responses (n = 14/15) report that staff have received training on referral processes [CS/Q14], though it is impossible to state with certainty how assessments of the need for referral are made, especially at lower levels of the administrative system.

- Overall levels of referral:

- There are a number of caveats regarding data on overall levels of referral: (a) Analysis is complicated by the incompleteness of data for some counties/departments. (b) It is not possible to state exact figures for number of referrals as a proportion of overall cases received, as individual cases may be referred to more than one department, meaning that figures listed under Referral to other departments in the above table may contain overlaps.

- Saying this, there appears to be a large range in the rates of referral as a proportion of total cases between departments and between counties. For example, Yilong’s Health Departments / hospitals appear to only refer cases around 37% of the time, whereas Jingyuan’s Health Departments / hospitals appear to refer cases around 82% of the time. According to figures supplied, Jingyuan’s Public Security Department appears to only refer cases 3% of the time, vs. Ningxiang’s Public Security Department, which appears to refer cases around 8% of the time. No reason for such discrepancies in levels of referral is obvious from the survey data and none was uncovered during fieldwork. (Though note that survey data were analysed following fieldwork, meaning that it was not possible to systematically include this point in fieldwork interviews.) Reasons for non-referral deserve more systematic exploration.

- The survey data are unable to accurately reflect actions taken by individual departments where referral does not take place. For example, in Yilong’s Health Departments / hospitals, it is unclear what action has been taken in cases that were not referred. It is possible to guess that such cases were treated but not referred to other departments, but it is not possible to be sure or to state reasons for this. In the case of Civil Affairs / shelters, this is a puzzle: given the relatively limited function of Civil Affairs / shelters in the county systems, it is hard to guess why so few cases would be referred to other departments.

- Patterns of referral differ by county:

- In Yilong and Ningxiang, excluding referrals from the Women’s Federation (and with the partial exception of referrals from Civil Affairs in Ningxiang), the Women’s Federation is the largest recipient of referrals from other departments, seemingly indicating a high degree of centrality in inter-departmental referral. In Jingyuan, excluding referrals from the Women’s Federation, the Justice Department / legal aid is the largest recipient of referrals.

- If all referrals, including those from the Women’s Federation, are taken into account, main departments receiving referrals are as follows:

Table 3: Ranking of referrals

| County | Ranking of referrals |
| --- | --- |
| Yilong | Justice Department / Legal Aid > Public Security Department > Health > Women’s Federation. |
| Ningxiang | Women’s Federation > Justice Department / Legal Aid > Public Security Department > Court > Civil Affairs > other. |
| Jingyuan | Justice Department / Legal Aid > Women’s Federation > Public Security Department > Civil Affairs > Health. |

- While there are differences in patterns, the Justice Department / Legal Aid and Public Security Department are much more prominent as recipients of referrals. This appears to be a positive finding, indicating that at least a proportion of cases are finding their way to the legal/police system through referral.

- Ningxiang appears to show a comparatively mature pattern of referral, with referral across a greater number of departments.

- It is hard to interpret figures for case follow up. In principle, follow up rates for each department should equal 100% of cases received by that department. It appears that data for this point are incomplete.

Main findings from fieldwork:

- Discussions convened with multiple departments in the pilot counties indicate that inter-departmental referral is a routinised component of work. Systematic data on the use of referral forms were not collected, but where referral forms were discussed with interviewees, it was stated that they are a useful mechanism, allowing regularised referral.

- Multiple patterns of referral between lower administrative levels (e.g. community (shequ), township, village, etc) and higher administrative levels (county) exist within individual official systems (i.e. Women’s Federation, Police, Justice, Health, Civil Affairs). The importance of this is likely to vary by system / official agency. The ways in which intra-system referral operates within the three-tier health system, for example, is sure to differ from vertical referral within the police system. The accuracy of detection of DV cases and provision of appropriate services/referral is likely to be linked to the degree to which systematic awareness raising / training has been carried out at low levels, as well as changes in institutional processes and cultures.

- Barriers to referral between different services were not systematically examined during fieldwork, but a number of points were raised by county officials. The main example given, in multiple cases, was the unwillingness of DV victims to seek legal punishment for their abuser (the main example given was husband) because of considerations of family stability, children’s education, loss of farm labour, income, etc. Why there are breakages in referral, or why victims refuse referral to other services, appears to warrant further, systematic, investigation.

- Of the three pilot counties, Jingyuan appears to have a reasonably codified follow-up system, with requirements for follow up with DV victims within a specific time, depending on the seriousness of the case as assessed using the risk assessment form developed and provided through the programme.

- There are some questions regarding data being collected by different departments in the counties:

- In some cases, individual figures for numbers of DV cases from different counties / departments collected during fieldwork differ from figures collected through the survey. Examples include figures for use of shelters, which were stated to be very low in all counties (see below), substantially below the figures given in response to the survey.

- At least to an extent, the ways in which cases/data are recorded are likely to influence apparent case numbers. For example, in one county, figures for DV case numbers provided to the evaluation team by the Women’s Federation are derived from complaints (jiefang) to the county-level Women’s Federation. According to interviews, figures from the community (shequ) level are not, or are only irregularly, integrated with county-level figures. This is likely to mean that county figures underestimate the number of cases. In the Public Security Department system, however, figures are derived from reports to the 110 hotline, which is county-wide and is likely to be more reliable. In the health system, recording of a case as an incidence of domestic violence appears to rely on medical expertise in spotting the signs of this.

- Discussions carried out by the evaluation team in all counties pose the question of how DV cases are defined and whether uniform definitions are being applied across departments and counties, particularly at lower levels of the administrative system, where awareness and capacity are likely to be lower. This will clearly be more important in cases where within-system referral is important and/or cases are first coming into contact with lower-level official agencies.

- While almost all departments in all counties state that they have departmental systems for recording DV cases and that they share data will other departments [CS/Q12], counties do not, at present, keep unified records of all departments’ figures. In one county where this the evaluation team explored this in some detail, it was stated that departments keep their own records, based on their own reporting. It does not appear possible, strictly speaking, to sum numbers of DV cases from figures provided by different agencies. In our understanding, this makes assessment of actual numbers of cases being dealt with, system-wide impossible.

- Domestic violence figures in all counties are capturing numbers of cases that come into contact with official agencies (government departments, hospitals, clinics, etc). This almost certainly underestimates the extent of domestic violence. Although it is not strictly possible to sum numbers of DV cases in each county, reported figures appear low compared to county populations. There appear to be a number of possible reasons for this:

- Low levels of public awareness and/or willingness to seek the support of official agencies lead to few victims coming forward and therefore low apparent levels of DV. In two of the programme counties, officials reported that apparent levels of DV are increasing, which they attribute to increased popular awareness (the exception is Yilong, which reported falling case numbers following the DV law).

- It is likely that some cases that should be categorised and treated as DV are not being dealt with as such. There appear to be two main possible reasons for this: First, where capacity levels are low, especially at low levels in the multiple administrative systems involved in the programme, rates of detection are likely to be low. Second, in a number of discussions in the programme counties, it became apparent that there is a degree of confusion in distinguishing domestic violence from other, more customary, ways of classifying family-related problems, for example as ‘family conflict’ (jiating jiufen). In one community (shequ) in one county, for example, separate records are kept for ‘family conflicts’ and ‘domestic violence’, though example instances of ‘family conflict’ that were explained to the evaluation team included physical violence that should, in our view, be considered domestic violence.

- (Note that even though such behaviour persists, the fact that counties now have systems for recording domestic violence, and that it is likely that cases which would previously have been considered family-related problems are, at least to an extent, being increasingly classified as domestic violence.)

- The apparently widespread use of mediation (tiaojie) in family-related problems is also likely to have an effect on apparent levels of DV. Many interviewees confirmed that the use of mediation in minor family-related problems is common, but it is hard to be sure how assessments of what constitutes a serious/minor problem are being made, and few interviewees were able to give very specific answers to this question. The ways in which such cases are dealt with and recorded will have an impact on apparent DV incidence.

    - Challenges and provisions for sustainability

- Counties’ survey responses describe a number of challenges to developing effective inter-departmental coordination mechanisms and/or work of their departments on domestic violence response. These are synthesised below. By far the most commonly cited challenge was limited human and financial resources.

- Limited human and financial resources to deal with high, and increasing, volumes of work. In some cases this may affect staff ability to provide correct services.

- Need for stronger leadership and coordination, which is hard for the Women’s Federation to provide.

- Difficulties in clearly defining and specifying the responsibilities of different departments in supporting DV victims. Absence of an agency with a specialised mandate to deal with domestic violence cases.

- Need for participation by a greater range of departments, and more public participation, in multi-departmental coordination.

- Difficulties of information sharing between departments.

- Too few staff available specialised in domestic violence cases, especially at grassroots levels / among frontline staff.

- Staff turnover can lead to an unstable anti-DV work force and/or temporary suspension of cooperation between departments.

- Many DV victims are unwilling to proactively seek support, and/or traditional attitudes towards domestic violence mean that victims are unwilling to speak out.

- Difficulties in changing understandings of domestic violence among staff.

- Difficulties in changing understandings of domestic violence among public, and/or need for more awareness raising (xuanchuan) work.

- The tools currently available for supporting DV victims are limited.

- Difficulties in collecting complete/sufficient evidence on DV cases and/or need for greater clarity over responsibility for evidence collection in order to improve the effectiveness of warning letters and protection orders.

- Limited staff capacity in health agencies / facilities to accompany and guard DV victims

- Difficulty of enforcing economic penalties among family members.

- Approaches to the prevention of domestic violence are not yet well developed.

Note that these issues are cited as challenges at the current time, and are likely to require ongoing support and/or intervention. Some challenges are likely to become more acute if numbers of domestic violence cases reported increase, as should be hoped (see below).

- In addition to the importance of leadership support, stressed in all counties, and discussed above, individual departments have received a degree of financial / in kind support from the parent counties for work linked to this programme [CS/Q27]. Individual departments’ reporting of support is not consistent, but main themes visible from these data are as follows:

- Counties have funded development and ongoing costs for shelters.

- A number of departments point out the effective in-kind contribution of person time / labour of their department.

- One health department lists a financial contribution for facilities and services related to domestic violence (presumably related to the establishment of a dedicated domestic violence centre).

- Multiple departments report financial support for developing/distributing awareness raising materials.

These appear to be costs that will need to be covered from somewhere if services are to be sustained.

- A majority of departments surveyed responded that they intend to continue working on domestic violence, and that they have public funds allocated for this purpose [CS/Q28], though two departments in Yilong state that they do not have funds specifically allocated. The most commonly cited uses of funds allocated are training and awareness raising activities.

- Saying this, interviews in all counties downplayed problems of sustainability. Interviewees were uniformly confident that few resources are needed to maintain the current multi-departmental and referral systems, and that these systems are now sufficiently embedded to be able to continue functioning smoothly following the end of the programme.

- One area in which the evaluation team believe ongoing financial support is likely to be particularly necessary is in carrying out follow-up training and awareness raising activities in the counties. Many counties/departments stressed the need for ongoing training due to staff turnover, while the evaluation team note that the difficulty of changing norms and practices will require ongoing work. This will require financial support.

- Most pilot counties have experienced a degree of leadership turnover during the course of this programme, and/or between phases one and two of the programme. This is inevitable in China’s local government system, but creates a challenge to sustaining local pilot reforms. Where work is strongly embedded in departments or at grassroots levels, this is likely to provide some insulation against weakening of support due to leadership changes. Ningxiang has made substantial efforts in training and embedding new norms at the community (shequ) level; it should be hoped that such approaches increase the robustness of local systems.

- As discussed elsewhere in this report, reporting of domestic violence cases is increasing. If, as should be hoped, reporting increases in line with increasing public awareness and lower barriers to seeking support, one should expect demand for services to increase. At present, counties appear to be planning and allocating resources on a more or less ‘business as usual’ scenario. This may be inadequate if demand increases substantially.

Further actions and recommendations

- A number of the above findings point to the importance of informal institutions/structures in the operation of local inter-departmental coordination. A large part of Jingyuan’s strength, for example, is likely to lie in the strong links between specific individuals who have come through this programme together. While this is a positive thing, it remains to be seen how a system based on comparatively personalised links will be sustained over time, or in the event that there are personnel changes.

- Consider further investigation of personnel assessment practices (both good practices and practice likely to create inappropriate incentives) as a reference point for other counties during scale up.

- Referral systems have been set up in all counties and appear to be functioning; however, patterns of inter-departmental referral differ between counties, and levels of inter-departmental referral differ between counties and departments, for reasons which are not clear. It appears important to better understand conditions under which referrals currently are likely to take place, barriers to referral, and how these can be lowered or overcome.

- Data on DV cases available at present suffer from a number of flaws and almost certainly underestimate population incidence of DV. There appear to be a number of reasons for this, including the fact that data currently only capture cases that come into contact with official agencies, reluctance to report DV, and ways in which DV cases are assessed/recorded and dealt with. It appears important to gain a better understanding of the incidence of DV in the pilot counties. This is likely to require other approaches to assessment, possibly including survey data, making better use of clinical data, oral histories, and other methods.

- Consider creating unified inter-departmental recording/data systems in the counties, based on common definitions and input methods to improve the quality of data on DV cases.

FINDINGS ON WORK OF PARTICIPATING DEPARTMENTS

This section provides findings regarding the work of participating departments in the three pilot counties from fieldwork and interviews.

Consolidated findings

Multiple departments in the programme counties have set up systems for dealing with domestic violence, and the programme has provided support to this, though it has not, in most cases, been directly responsible for developing of counties’ systems. The role of the programme should be seen as contributing to change, rather than directly creating change. Section three, above, described the training that has been carried out in the programme counties and the extent to which knowledge/awareness, and behaviours/norms appear to be changing. Section four showed that functioning inter-departmental management and referral systems have been set up, though noted a number of questions around their use and the extent to which they are able to respond to widespread need. This section shows many positive practices in the counties’ work, but evidence from local interviews tends to indicate that although practices are changing, problematic areas remain. In the assessment of the evaluation team, the main difficulties that are visible exist at the level of changing behaviours/norms, as well as organisations, institutions and practices. The main examples of this appear to be the apparently widespread use of mediation in DV cases, and the outcomes of legal cases reviewed by the evaluation team.

The programme was not designed to work specifically on reform to the way DV cases are handled in the courts in the pilot counties or to reform actual institutional structures and processes that underpin use of mediation (though it is reported that mediation was discussed multiple times in programme trainings, including its undesirability in cases of DV).

However, it appears likely that change at the level of institutions that underpin and sustain such practices is necessary to improve outcomes for DV victims. Given the difficulties visible in changing popular perceptions of DV, and the fact that widespread attitudinal/behavioural change is likely to be a long-term process, and one which is dependent, at least in part, on levels of economic and social development and openness, it appears that changes at the level of organisations and institutions are particularly needed.

Following the establishment of the multi-departmental anti-DV system, the Women’s Federation has been playing an important role in anti-DV work. As one staff member in Jingyuan stated, “My major responsibilities include the daily work of directing and coordinating different departments’ work, setting up a complaint centre, and providing help to DV victims and assisting victims of serious domestic violence to apply for a protection order, as well as doing anti-DV promotion and training, providing psychological counselling, and directing and assessing the anti-DV work of different townships and county-level institutions ”.

Following the establishment of the multi-departmental anti-DV system, the Women’s Federation has been playing an important role in anti-DV work. As one staff member in Jingyuan stated, “My major responsibilities include the daily work of directing and coordinating different departments’ work, setting up a complaint centre, and providing help to DV victims and assisting victims of serious domestic violence to apply for a protection order, as well as doing anti-DV promotion and training, providing psychological counselling, and directing and assessing the anti-DV work of different townships and county-level institutions ”.

The remainder of the section discusses detailed evaluation findings supporting the above analysis.

Domestic violence shelter system

Shelters for domestic violence victims were visited in the three pilot counties, and discussions held with managers/staff. Main findings are as follows:

- Overall, all counties report low levels of use of shelters. Most domestic violence victims come to shelters through referral from other departments. All counties report that there is little change in the numbers of domestic violence victims making use of shelters over time.

Table 4: Use of domestic violence shelters

| County | Use of shelter, 2014 to date (person/times) | Average length of stay |
| --- | --- | --- |
| Yilong | 33 | 3 nights |
| Ningxiang | 59 | 3 nights |
| Jingyuan | Approx. 20 | 1 night |

- Shelters take different forms in the three counties: Ningxiang and Jingyuan have established fixed shelters in local social assistance centres (jiuzhu zhan); Yilong uses a mixed model of fixed shelters combined with a ‘mobile shelter’ system in which local hotels are contracted to provide temporary shelter facilities.

- The standard of facilities offered in the three counties’ fixed shelters differ substantially: Ningxiang’s shelter is in a peaceful and pleasant environment; outsiders are not routinely allowed access to the facility; the shelter is somewhat isolated from other areas of the social assistance centre, providing a degree of privacy, though common areas are shared. Yilong’s shelter is situated fairly centrally in the county town in a gated compound. Facilities are basic. Jingyuan’s shelter is poorly situated, on the edge of the county town. To get to it, one must pass through an area in which most buildings have been knocked down and not yet rebuilt. This is likely to be unpleasant and may be unsafe. While the compound is walled, the gate was not guarded at the time of our visit. The standard of accommodation provided varies: Ningxiang’s shelter appears to offer the most comfortable facilities, followed by Jingyuan’s, then Yilong’s.

- In all three counties, the shelter is situated in a building whose principal use is to provide shelter to the destitute or homeless, or to the elderly. The evaluation team did not interview women who had used the shelter in any of the counties, but the impression of the evaluation team was that this exposed domestic violence victims to a potentially threatening environment. Ningxiang has gone some way to mitigate this by clearly sealing off the area used by domestic violence victims from other areas of the building, though common areas (including dining areas, etc) remain shared.

- Yilong’s decision to use a mobile shelter system was based on safety considerations. We did not visit hotels used as shelters, however, and cannot comment on the facilities available or how the safety of victims is ensured.

- All counties describe the main function of their shelter as providing temporary accommodation, food and necessities, as well as allowing referral to other services. Two counties reported that they provide some kind of counselling or psychological support: Ningxiang’s shelter employs someone for this purpose, and Jingyuan has a member of Women’s Federation staff stationed in the shelter for this purpose. The levels of professional training of staff appear to differ, and in one case the evaluation team were informed of questionable practices being employed in dealing with domestic violence victims. Greater levels of training / standardisation of procedures appears warranted.

- Maximum length of stay and destinations for victims leaving shelters: Ningxiang report that there is no maximum length of stay in the shelter; stays in Jingyuan are capped at 7 days. It is not clear why stays should be capped. In no county are long stays normal. It does not appear that there are specific systems in place in any of the counties for long-term use of shelters for women who require long-term support. Ningxiang and Jingyuan report that when victims leave the shelter, main destinations are to return home, or to stay with family or friends, and that in some cases shelter staff may help arrange this. Staff report that they carry out follow-up phone calls with victims once they have left the shelter. No specific data were collected for this in Yilong.

- Other management issues: Jingyuan report that certain management issues appear to deter women from using the shelter, including the prohibition on leaving the shelter.

- Jingyuan’s counselling/support centre appears to consist of one member of staff from the Women’s Foundation being located in the county shelter. This appears to have a limited function at present. Consideration could be given as to how to develop this into a more substantive centre within Jingyuan’s ‘5 centre’ model.

- Budgets for the shelters in the different counties appear to differ substantially. Ningxiang stated that the annual operating budget for the shelter was 50,000 Rmb, while Jingyuan stated that the annual operating budget was 6,000 Rmb (neither figure includes staff costs; no figures are available for Yilong). It is unclear why these figures differ so substantially.

- Sustainability: interviewees report that shelters were set up on the requirement of the programme, but that they are funded from local finances. This may have implications for sustainability, though no county currently believes this to be a problem.

Public Security Departments / Legal Aid Centres

The evaluation team carried out meetings with Police and Justice Departments and/or Legal Aid Centres in all pilot counties. Data from the pilot counties indicate that reporting of domestic violence to police hotlines cases is increasing, as is use of legal aid, though there are some differences between county figures. Requests were submitted to the counties for data on a number of indicators regarding the response of the police and justice systems to DV (DV reporting to 110 police hotline; number of uses of written cautions; number of DV victims granted legal aid), but systematic data were not supplied.

Following the establishment of the multi-departmental anti-domestic violence system, different departments have further specified their responsibilities and work processes. According to one police officer in Ningxiang, ”If there is a DV case, after the 110 hotline receives a call for assistance, the local police station will be informed immediately and should attend the scene. If the situation is more complex or serious, they will require the justice department to get involved. They have to monitor the situation  and include the victim into scheduled follow-up household visits ”.

Following the establishment of the multi-departmental anti-domestic violence system, different departments have further specified their responsibilities and work processes. According to one police officer in Ningxiang, ”If there is a DV case, after the 110 hotline receives a call for assistance, the local police station will be informed immediately and should attend the scene. If the situation is more complex or serious, they will require the justice department to get involved. They have to monitor the situation  and include the victim into scheduled follow-up household visits ”.

Main findings from fieldwork are as follows:

- All Public Security Departments / Legal Aid Centres report carrying out large amounts of training within their own systems /with lower level agencies. This is a positive thing.

- Police departments are integrating domestic violence response into the work

of police 110 hotlines, and in many cases are setting targets for response times and/or rates for police attendance at incidents. Police departments report carrying out training with 110 hotline staff on how to handle calls regarding domestic violence.

- Almost all Public Security Departments / Legal Aid Centres report increasing complaints relating to domestic violence, especially following the release of the domestic violence law. The exception to this is Yilong, where interviewees stated that the release of the domestic violence law has led to a reduction in the number of cases as potential perpetrators realise that their behaviour is illegal and desist. Such a sudden change seems unlikely; closer investigation of trends in reporting in Yilong appears warranted.

- A number of interviewees reported DV victims’ lack of willingness to pursue legal recourse against the perpetrators of violence, for a number of common reasons, including customary beliefs that a certain amount of physical violence within the family is expected and/or to be tolerated; fear of the perpetrator (often the husband) being given a custodial sentence, and the repercussions of this on family finances, availability of labour for farming, etc; fear of the repercussions of legal action and/or dissolution of the couple on the family, or children, or on children’s education. Such factors were also raised by other departments and cited as reasons DV victims unwillingness to be referred to legal services. These appear to be challenges to handling of DV cases through official/legal channels.

- In one county, a lack of willingness of DV victims to request use of written cautions (gaojie shu) was reported to the evaluation team. The reason cited for this was that use of a written caution against a parent would be listed on the personal record of a child, and may limit the child’s prospects in certain professions in the future. It is not clear how widespread a concern this should be considered, but it appears to be an institutional constraint to use of warning letters that may deserve further investigation.

- All counties report use of mediation in family-related problems, including domestic violence cases. From interview evidence, it is unclear the extent to which mediation is being used, under what exact circumstances, by whom / what agencies, what qualifications or requirements are for mediators, and whether/how systematic oversight is carried out. From fieldwork, it appears that use of mediation is widespread, though use is almost certain to differ between the three pilot counties. Discussions in the counties tend to indicate that many departments are able to use mediation as a tool in dealing with family-related problems and/or domestic violence cases, and that in some cases this may be the first choice in dealing with such problems. In some cases, the primary aim of mediation was described to the evaluation team as being to ensure that a couple can come back together and not separate. This is worrying if applied in cases of domestic violence. Further investigation appears warranted of the agencies using mediation in DV cases, the criteria for use of mediation versus other approaches, and the process and outcomes of such cases.

- The evaluation team were shown documents in more than one pilot county relating to cases involving domestic violence in the police or justice system. The main kinds of documents presented for our inspection were records of DV cases kept by the Public Security Department and records of DV cases kept by the Justice Department or Legal Aid Centre. Files related to around 30 cases were reviewed across all three counties. Such documents were not systematically collected: in most cases, members of the evaluation team were able to scan through documents during meetings, but not to take them away, copy them, or to make detailed notes. A number of points stood out from examination of these documents:

- Many case files kept by police departments show the use of mediation in cases of domestic violence, supporting evidence from interviews. In some cases, at least, mediation appears to be attempted in even comparatively serious cases of DV.

- No systematic assessment of legal case documents was possible, but the number of cases in which divorce was granted appears to have been small from the cases briefly reviewed by the evaluation team.

- In some cases in which a DV victim sought divorce, despite apparently adequate evidence to support a divorce ruling (including photographic and other evidence of violence), and recommendation for divorce by the lawyer of the DV victim, this was not granted.

- In at least one case seen by the evaluation team, a complaint of DV was raised involving an apparently deliberate use of a car to run over the victim. CCTV evidence was not collected, and the case was apparently not considered for criminal prosecution.

- In at least some cases in which divorce was not granted, the decision appears to have been based on an assessment by the court that marital relations remained functioning/intact, and that it was therefore preferable for the couple to remain together.

Medical system

The health system has become the most important department through which evidence relating to DV cases is being collected and preserved. As one doctor from Yilong Health Bureau said, “Now that we have an anti-DV medical intervention centre, we can provide medical treatment and psychological counselling to DV victims, collect and preserve evidence, make a comprehensive assessment of DV victims, develop intervention plans for DV victims, refer victims to other departments, and carry out follow up ”.

The health system has become the most important department through which evidence relating to DV cases is being collected and preserved. As one doctor from Yilong Health Bureau said, “Now that we have an anti-DV medical intervention centre, we can provide medical treatment and psychological counselling to DV victims, collect and preserve evidence, make a comprehensive assessment of DV victims, develop intervention plans for DV victims, refer victims to other departments, and carry out follow up ”.

The evaluation team visited county-level medical facilities in each of the pilot counties. Facilities visited were all Maternal and Child Health Hospitals, probably reflecting the fact that these have the closest institutional links to the Women’s Federation system, even following the merger of the health and reproductive health systems. The evaluation team was unfortunately not able to visit community or village level facilities.

- Referral within the health system:

- China’s rural health care system includes providers at three levels: village, township, and county. All pilot counties describe the use of vertical referral across the levels of the rural health system in cases of domestic violence, according to the principle that cases that cannot be dealt with at village/township level should be referred to county level, and that cases which require certification of evidence be dealt with in an appointed centre for the recording of medical evidence (jianding zhongxin).

- This should be considered a natural approach to detection, assessment and treatment of domestic violence cases, but also inevitably raises the question of capacity at local levels to correctly detect and refer domestic violence cases, especially in places that should be expected to have overall lower capacity levels (remoter, poorer, rural areas), and given the difficulties of large-scale grassroots-level training.

- There may be instances in which programme-supported agencies are only able to refer to specific hospitals, and these may not be convenient or appropriate. This was cited as a problem in one pilot county. Where this is the case, it is suggested that counties review procedures to allow more appropriate referral.

- Financial barriers to access:

- Of the three pilot counties, only Yilong has a system in place to provide free tests and treatment in cases of domestic violence. This is only available in one hospital (the county Maternal and Child Health Hospital), and is, effectively, underwritten by the hospital itself, rather than being specifically supported by public funds. In Ningxiang and Jingyuan no specific provision is made for this, but it was stated that patients are not charged at the point of treatment, but after the event, in order to reduce barriers to access, and that in some cases costs may be either recouped from the perpetrator of violence and/or waived where there is no ability to pay. In such cases, the hospital may underwrite this cost itself or request reimbursement from public emergency funds. In some cases, it was reported that programme staff may provide funds for treatment from their own pocket.

- In both Ningxiang and Jingyuan, it was stated that costs typically associated with domestic violence cases are limited, and that costs of treatment are not considered a barrier to access. This is possibly the case, but in one instance the evaluation team was told by interviewees from the police system of a woman refusing to seek care for an injury sustained as a result of domestic violence due to concern over the cost. It is likely that financial barriers to treatment require follow-up investigation, especially in cases where the victim is either poor, has gone to the police or a medical facility in an emergency, and/or does not have access to funds due to economic control by a partner.

- Cases of violence, whatever the cause, are not covered by China’s rural health insurance system. Where this was raised (Jingyuan), it was stated that medical costs associated with domestic violence are, for this reason, not covered by the insurance system. While the rural health insurance system was not a focus of the programme, it appears unreasonable to exclude such costs from health insurance coverage. Some research has found that non-inclusion of self-harm and suicide in China’s rural health insurance has reduced reporting of these problems. It is conceivable that a similar phenomenon exists in relation to domestic violence.

Education department

The participation of education departments and institutions in anti-domestic violence work in the pilot counties was not systematically assessed, though all counties state that they are carrying out awareness raising activities in educational institutions [CS/Q24]. In Ningxiang, it was reported that the education department now institutes domestic violence reporting points in schools, attached to a ‘responsibility system’, according to which if an incident is reported in a school but not acted upon, school staff will be held responsible. Although it does not directly/specifically relate to violence against women, this system appears to be a positive development and may warrant further investigation.

Omissions

There appear to be a number of omissions from the current system being trialled in the pilot counties, including the following:

- There appear to be few provisions for long-term shelter for victims in need of this, or differentiated/targeted support for particularly complex DV cases.

- A number of interviewees noted that their counties have limited resources available for psychological support and counselling, and suggested that development of this kind of capacity be supported in future. This may be worth considering.

- Professional social workers are not currently included in the models being piloted in the three counties, but could bring a valuable contribution.

Further actions and recommendations

- Consider assessing best practices among shelters in the pilot counties and developing a checklist of features for DV shelters to be considered during design.

- Consider assessing counselling and psychological support facilities, including capacity of staff engaged in this and approaches used, and developing guidance on best practices.

- Consider whether there is a need for long-term shelters/support, and how this might be met.

- While the evidence available is limited, interviews and documents such as those seen by the evaluation team raise questions regarding the treatment of DV cases in the legal system. Taken together, the above points appear to: support evidence from interviews regarding the use of mediation in DV cases; to indicate that in at least some cases, the seriousness of domestic violence is being downplayed, and to indicate that there are challenges to changing habitual/traditional norms/practices, even within rule-governed systems such as the courts. A number of points merit further, systematic, investigation, including how DV cases are treated in the courts in the pilot counties, and the bases for legal judgements in DV cases / divorce cases involving DV; knowledge, attitudes and behaviour of judges and other legal professionals involved in DV cases; specific training needs of judges and other legal professionals involved in DV cases; evidential requirements in DV cases and the impact of these on outcomes; how oversight and management of DV cases are carried out in courts in the pilot counties.

- The extent to which mediation is being used in DV cases, under what exact circumstances, by whom / what agencies, what qualifications or requirements are for mediators, and whether/how systematic oversight is carried out.

- Investigate possible financial barriers to access to treatment and consider developing guidance for the health and family planning system in the pilot counties on dealing with DV cases where there is no ability to pay.

- Consider investigating the assessment of symptoms that may be linked to domestic violence by grassroots-level health facilities, especially ones that should be considered to have comparatively lower capacity, and what proportion of potential DV cases is likely to be accurately detected under current conditions.

INTERVIEWS WITH DOMESTIC VIOLENCE VICTIMS

Although the main focus of this programme has not been to carry out direct intervention with domestic violence victims, victims are important stakeholders in anti-domestic violence work, and their participation is important in ensuring a successful programme. During fieldwork, the evaluation team carried out interviews with domestic violence victims in the three counties. Yilong introduced three interviewees; Ningxiang and Jingyuan each introduced two interviewees. Interviews were carried out in private and secure locations. Each interview lasted approximately one hour and was carried out by female members of the evaluation team. Main findings are as follows:

In all counties, the domestic violence victims introduced to the evaluation team had suffered from serious/extreme violence. Among them was one woman whose case was a criminal case, and two whose cases appear susceptible of criminal prosecution, according to a legal expert accompanying the evaluation team, but were not treated as such. Aside from two domestic violence victims interviewed in Yilong, all others had divorced. However, as discussed elsewhere in this report, a limited document review carried out in the counties shows that many cases do not end in divorce.

- Of the seven women interviewed, only two suffered violence during the programme period and were given assistance by the Women’s Federation, Justice Department and health agencies. The remaining women were victims of violence prior to the start of the second programme period, but requested and received support for domestic violence. In these cases, the main support received was from the Women’s Federation in the form of counselling and information, and from the Justice Department, in the form of legal advice.

- All seven women stated that the support they received from the range of public agencies they encountered was positive and effective. Not only did it help them escape violence, but it also helped them understand more and increased their awareness. This support equipped them with the knowledge of what they should do if they were to encounter domestic violence again. They have all passed on information and knowledge regarding domestic violence to friends and colleagues who they believe need help.

As one interviewee said, “I was born in 1984 and have been married for 10 years. My husband started abusing me after we had been married for half a year. At first I forgave him, but it became a regular thing later on. My husband and his parents all hit me, and in 2011 the situation became serious. I sought help from the Women’s Federation, village cadres and the police system. After that I left home and rented a room in the town. My husband took my child away, and I didn’t have any money. I wanted to see my child but my husband didn’t let me. I wanted to get divorced but didn’t know how. I learned from the training how to go about getting a divorce. After being abused in 2011, I had my injuries assessed. At first I didn’t want to get divorced, but after the trainings, I came to realise the harm caused by DV and its effect to women in the long run. I learned through this that women facing these problems need to be proactive – we need to actively seek help. I found a job in the town and I got divorced in February 2017.”

As one interviewee said, “I was born in 1984 and have been married for 10 years. My husband started abusing me after we had been married for half a year. At first I forgave him, but it became a regular thing later on. My husband and his parents all hit me, and in 2011 the situation became serious. I sought help from the Women’s Federation, village cadres and the police system. After that I left home and rented a room in the town. My husband took my child away, and I didn’t have any money. I wanted to see my child but my husband didn’t let me. I wanted to get divorced but didn’t know how. I learned from the training how to go about getting a divorce. After being abused in 2011, I had my injuries assessed. At first I didn’t want to get divorced, but after the trainings, I came to realise the harm caused by DV and its effect to women in the long run. I learned through this that women facing these problems need to be proactive – we need to actively seek help. I found a job in the town and I got divorced in February 2017.”

The following are comments and reflections on these interviews and findings:

- Many of the women, when seeking help, were advised to ‘keep going’ (hao hao guo rizi), to think of the importance of family harmony (jia he wan shi xing), and given other similar advice/mediation promoting family reunion. For example, one domestic violence victim in Yilong was the victim of extremely serious violence, amounting to criminal action, in the period before this programme started. Despite this, and in the period covered by this programme, her case was ‘mediated’ by a community-level staff member involved in this programme, who counselled her not to divorce her husband who had perpetrated the violence, and that the couple try to get along together, and that the husband not beat the wife. This shows how some programme staff have not understood or accepted the fundamental principle that domestic violence is an infringement of human rights, and that training has not fundamentally challenged traditional norms reinforcing and preserving the institution of marriage (such as the customary saying that “it is better to knock down a bridge than to break apart a marriage”). Despite the programme, women remain bound in the patriarchal institution of marriage based on traditional ideas and morals, and mediation in cases such as this risks perpetuating the possibility of violence towards women.

- In cases where evidence is unavailable, it appears hard to seek justice and for victims to exercise their right to live without violence. Interviews with domestic violence victims tend to reinforce the assessment of the evaluation team regarding case files reviewed in the counties and discussed in Section 5.

- In some cases, women who have received support from the programme have concluded that improving their economic status in the household is the most basic way to solve the problem of domestic violence. One woman in Yilong, for example, stated that “now I earn money, my status at home is higher than before – he no longer dares to hit me”. While changing women’s economic status is a necessary component of changing the unequal status of women and men, it is not equivalent to equalising relations within marriage and not a substitute for challenging and reforming patriarchal power relations.

- The impression of the evaluation team is that it was not that easy for the three counties to arrange interviews with domestic violence victims. In some cases, women had to take time off work or to travel long distances to attend interviews with the evaluation team, in some cases at their own expense. Given the difficult circumstances of these women, it is disappointing that these factors were not taken into account when the counties were arranging these interviews.

PROSPECTS FOR SCALE UP

This section discusses available evidence for scale up of models developed in the three pilot counties, factors likely to support scale up, and apparent barriers to scale up. In our analysis, ‘scale up’ principally refers to the studying and/or direct use of a pilot county model by a non-pilot county, though analysis also considers cases in which county models or practices appear to have been drawn on by provincial departments in developing anti-DV regulations or policy.

Consolidated findings

In all provinces there appears to be a degree of scale up. This appears strongest in Gansu; at present it appears unlikely that substantial scale up will take place in either Hunan or Sichuan. While feedback on the models at all provincial-level meetings attended by the evaluation team was broadly positive, forms of scale up visible in the three provinces differ, and the provinces clearly attach different degrees of importance to ‘their’ county pilots.

Discussions with provincial officials indicate that increased provincial coordination and promotion will be necessary to support adoption at scale of the pilot county models. On present evidence, Gansu is the province in which the pilot county’s experience is being most strongly promoted. It appears at present that Hunan’s work on domestic violence is comparatively advanced, that there are other local models that the province considers more advanced than Ningxiang’s, and that this will limit the impact of the pilot. Provincial support for Yilong’s model appears weak. Gansu’s relatively strong support for scale up of Jingyuan’s model appears to be linked to a framing of domestic violence in terms of a harmonious society, which is increasing the political importance attached to DV. It is unclear the extent to which this kind of framing is operating in other provinces.

Provincial agencies in the three provinces were given a limited role in the programme. It appears that their main participation was in the dissemination meeting held at the end of the programme. It is possible that low levels of engagement across the programme cycle are linked to relatively limited provincial support for scale up of the pilot county models, though it would likely be hard to substantially engage the multiple provincial government departments needed to effectively promote multi-department cooperation models over a substantial period of time in a county level pilot, for example through trainings, field trips, etc.

The evaluation has identified a number of barriers to effective scale up of pilot county models:

- Promoting multi-department coordination at the county level is possible, but all counties state that leadership support, in the form of strong commitment from county government, financial support, etc, is a necessary precondition. It is likely that the presence of the programme has leveraged this kind of support in the pilot counties and increased their willingness to promote multi-department coordination. Without such a pilot (and the resources and support that it brings), and without support from the provincial or city level, this kind of model may be hard to replicate at scale.

- In the pilot counties, work is led by the Women’s Federation. The relatively weak position of the Women’s Federation in the local administrative structure is likely to be a barrier to replication at scale in other counties, without external support for coordination, as above. As discussed elsewhere in this report, Jingyuan Women’s Federation suggest that the local Public Security Department could lead inter-departmental coordination, and that this might make scale up easier. This may be the case, but it goes against China’s domestic violence law, and the evaluation team are concerned that this could lead to domestic violence becoming even more of a law and order issue, and less of a gender/rights issue.

- Reports summarising county pilots developed by the programme include as annexes county level policies, regulations, etc, as well as standard forms used by the programme, such as risk assessment forms. These materials are likely to provide a useful resource for other counties wishing to study pilot counties’ models, but they are unlikely to constitute a ‘standalone’ resource. Multiple pilot county interviews indicate that use of risk assessment forms, and the five-step method, for example, requires training to be fully effective.

- Training is certain to be important in scale up. The programme has achieved substantial changes in knowledge and attitudes in the pilot counties, and this has clearly been necessary to the development of capacity of the individual departments involved in the pilot, and to the development of multi-departmental systems in the counties. Interviewees also stressed the importance of training in harmonising the thinking of multiple departments in the pilot counties domestic violence, and building effective teams. This indicates strongly that there will be a need for widespread and sustained training if counties are to adopt multi-departmental anti-domestic violence response systems. While the programme has gone some way to training teams in the pilot counties capable of carrying out training locally and, potentially, in surrounding counties, this remains a very limited resource which will need to be strongly built upon if there is to be support for other counties contemplating adopting this kind of approach to DV response. There is a degree of risk in widespread scaling up of a system that falters and lacks legitimacy in non-pilot counties due to limited capacity.

- Reports summarising pilot models were found by the evaluation team to portray the pilot counties’ models as substantially different, and to summarise them with catchphrase-type names. While this may be common practice in summarising sub-national reforms in China, the evaluation team felt that in this case this over-stressed the differences between the counties and downplayed the similarities. If a set of general publicity materials are to be developed summarising counties’ experiences, an approach stressing commonalities, possibly based on a C-M-O (context-mechanism-outcome) framework, could be productive.

The remainder of the section discusses detailed evaluation findings supporting the above analysis.

Data used

Analysis in this section relies principally on the following sources of evidence:

- Documentation provided by UN Women relating to dissemination meetings held in each provincial capital in early 2017

- Reports prepared with the support of UN Women / ACWF summarising the models of the pilot counties

- Multiple stakeholder meetings convened with provincial government departments during fieldwork

- Discussions with pilot counties regarding the possibility of scale up of their models

A separate search for provincial or other policies to corroborate or deny claims made during interviews or discussions was not carried out, due to insufficient time and resources. The remainder of this section discusses the current situation and prospects for scale up in each province, before summarising findings regarding scale up and the processes of scale up.

The following table summarises the position of scale up in each province as understood by the evaluation team at the time of writing.

Table 5: Overview of evidence for scale up

| Province | County-county scale up of pilot experience? | Province directly promoting pilot experience? | Pilot experience informing provincial policy? |
| --- | --- | --- | --- |
| Sichuan | Limited | No | No evidence |
| Hunan | No | No | Some / limited |
| Gansu | Strong | Yes | Yes |

Programme support to scale up

The programme has supported work in the pilot counties since 2014. Little support has been given to the counties’ parent provinces (Sichuan, Hunan, Gansu), though there are indications that a small number of provincial officials have visited the pilot counties to see the pilots first hand. Large-scale dissemination meetings were held in the three provinces in February / March 2017. According to documents provided by UN Women, these meetings brought together officials from a range of different departments and from non-pilot cities/counties in each province (attendees: Jingyuan, 110; Ningxiang, 80; Yilong, 110). At each provincial meeting, a report summarising that province’s pilot county’s model was presented, and officials from the relevant county were invited to present their experience at the meeting. The hope is that this will inform provincial and sub-provincial officials of the model being developed in the pilot county in their province and prompt them to study/copy it.

Sichuan

All provincial departments that attended the meeting discussed the anti-domestic violence work that they are carrying out. Many activities, such as awareness raising (xuanchuan) and training are being carried out by multiple departments within their own vertical systems, including in some cases with county-level agencies. Main findings from the provincial meeting:

- Provincial departments report that many counties are pursuing similar reforms to those being carried out in Yilong, linking multiple local government departments; the Yilong model is believed to be more mature that those of other similar counties, but similar in ends and means.

- Non-pilot counties that attended the meeting apparently stated that it is possible to copy the Yilong model, though there has been no direct feedback regarding other counties’ copying of Yilong’s experience to date.

- It was stated that non-pilot counties argue that the probability of widespread adoption of multi-sectoral models by counties would be strengthened if the province were to increase provincial-level coordination, and mandate county-level coordination.

- The provincial Women’s Federation state that this would be challenging to do; there are apparently no direct plans to issue a document promoting this at this point in time.

Hunan

Representatives of all main departments with a mandate linked to domestic violence attended the meeting. Main findings from the meeting are as follows:

- Few attendees had substantial knowledge of Ningxiang’s model. Most had learned only a limited amount about it at the provincial dissemination meeting, had had no previous exposure, and had not taken part in programme-organised activities. Only on attendee, from the provincial Women’s Foundation, had visited Ningxiang to examine local practice. When questioned about the value of the model for the province or for other counties, most attendees spoke only in general terms.

- Where interviewees commented on the dissemination potential of Ningxiang’s model, they stated that inter-departmental cooperation is necessary to respond to domestic violence, and that it should be possible for other counties to copy this model. It was stated, however, that organic, county-county, scale up is unlikely to achieve widespread coverage, and that widespread scale-up would need to be pushed from the provincial level.

- According to meeting attendees and other interviewees, Liuyang County is perceived as being the leading model in Hunan in developing a multi-sectoral response to domestic violence, with a more mature model than Ningxiang’s. This will almost certainly dilute the possible impact of Ningxiang’s model.

- The province is working on instituting cross-departmental coordination following the domestic violence law, and individual departments are implementing work on domestic violence within their own vertical systems, but the province is currently not specifically promoting copying of Ningxiang’s model, and does not appear to have plans to do so.

- The provincial Women’s Federation stated that they are cooperating with the provincial Public Security Department on regulations regarding use of warning letters and personal protection orders in cases of domestic violence, and that the experience of well-performing counties will be taken into account, including that of Ningxiang.

Gansu

Representatives of all main departments with a mandate linked to domestic violence attended the meeting. Main findings from the meeting are as follows:

- Attendance at the provincial dissemination meeting appears to have been good (more than 110 attendees), with a number of prefecture-level cities, and several counties, in attendance. Jingyuan is described as relatively representative of Gansu’s counties, meaning that a model developed there should be applicable elsewhere. Materials summarising Jingyuan’s model were disseminated at the provincial meeting and fourteen counties in two prefecture-level cities (Baiyin and Qingyang) are said to have already started developing inter-departmental cooperation mechanisms, based on Jingyuan’s model.

- The provincial Women’s Federation state that Gansu is in the process of establishing a multi-sector cooperation model for responding to domestic violence closely linked to Jingyuan’s approach. Coordination is being provided by the provincial General Management Office (Zong Zhi Ban; see note in Table 3). The provincial Women’s Federation and Health and Family Planning department have issued a joint document requiring that health facilities establish points for reporting of domestic violence, that certain social organisations develop capacity to provide counselling services, and that legal agencies take on domestic violence cases and reference Jingyuan’s experience.

- The Women’s Federation state that they hope to promote adoption of the model at the sub-provincial level through linking it to local government work/targets on maintaining stability and developing ‘Peaceful Gansu’, through including it in periodic legal awareness raising (pufa) work, and that they hope to promote provincial legislation to bring Jingyuan’s experience into local level legislation.

- Multiple meeting attendees’ statements show the extent to which, in Gansu, work on domestic violence is being framed as part of developing a harmonious society. Statements from the provincial General Management Office, for example, state that they are working on integrating anti-domestic violence work, including Jingyuan’s experience, into provincial activities to promote development of a ‘Peaceful Gansu’, and that their aim is to integrate targets on domestic violence into performance assessment (kaohe) of sub-provincial governments/departments.

- Provincial interviewees reported other work going on in Gansu that potentially strengthens the work being done in Jingyuan and/or the province’s efforts to promote that, including the apparently active engagement of a number of provincial departments not necessarily involved in other provinces (notably the General Management Office, the provincial Party School, and the provincial High Court). The High Court is also involved in using lessons from a Fujian anti-DV pilot (also supported by UN Women) in a city in Gansu. It was stated at the provincial meeting that this has created awareness of DV and fertile ground for learning from Jingyuan’s pilot.

Further actions and recommendations

- The model for multi-department response to DV that has been developed through this programme is relatively mature but, as discussed above, faces barriers in achieving deep institutional change which will be needed to change many of the outcomes for victims of DV. Under these conditions, there are inevitably questions around how to think about promoting scale up. If, as appears the case, the barriers to this kind of institutional change are systemic, they will require systemic solutions that pilots are unlikely to be able to provide.

- There are questions that will need to be addressed regarding how support can be provided to non-pilot counties during scale up, especially how capacity will be built and how training can be provided. This will require resources and support from provincial and/or central government.

SUPPORT TO NATIONAL-LEVEL LEGISLATION

China’s Family Violence Law was passed on the 27th December 2015, and came into force on the 1st March 2016. The Law is the result of a long period of work and effort on the part of many government agencies, social organisations and scholars. The All China Women’s Federation has provided financial and technical support to the process. One of the goals of this programme is to advance the legislative process, and the programme has played a role in supporting ACWF in providing support to the legislative process. Activities supported by the programme to that end have included the following:

- With support from the programme, ACWF collated and translated a large amount of documentation relating to a number of other countries’ domestic violence legislation into Chinese (France, Germany, Canada, Israel, New Zealand and Bangladesh). The resulting documentation was made available to the Legislative Affairs Commission of the NPC Standing Committee and the Legislative Affairs Office of the State Council. A portion of these appear to have been made use of the process of developing China’s Family Violence Law. For example, following exposure to materials on other countries’ practices, legislators debated expanding the scope of domestic violence to include non-married, cohabiting couples.

- In November 2014, the programme organised a number of national-level officials to take part in a study visit to Canada. The trip included a member of the Legislative Affairs Office of the State Council working on the development of the Family Violence Law, officials from the ACWF and staff from the Supreme People’s Court taking part in the drafting of the law. During the study trip, the officials were mainly exposed to the following two Canadian approaches: The personal protection order used by the Canadian legal system, through which courts can restrain perpetrators of domestic violence; Canada’s use of peace bonds, through which victims can seek police assistance in cases of domestic violence.

- In September 2016, a delegation of eight officials, including the head of the Rights Department of the ACWF, and members of the Supreme People’s Court, the Ministry of Public Security, and UN Women visited the UK to study that country’s practices in dealing with domestic violence. During that visit, the delegation met with the UK Foreign Office, Home Office, the Ministry of Justice, the Crown Prosecution Service and the College of Policing to better understand UK legislation, and the approaches of these agencies to domestic violence work.

- In 2014, UN Women participated in the organisation of a high-level roundtable to promote legislation on domestic violence alongside a number of other UN agencies. The meeting convened more than twenty high-level national and international experts on domestic violence law alongside the Legislative Affairs Office of the State Council, the National People’s Congress, related government departments, members of the family violence network, and civil society organisations to discuss how to best reflect international experience in the process of China’s drafting its Family Violence Law.

The main impacts of the programme in China’s development of the Family Violence Law appear to be as follows:

- Through compiling and translating a wide range of international documentation on domestic violence law and organising study visits, the programme has created a degree of exposure of Chinese legislators to international practice and concepts. Although it is impossible to assess the extent of this, and the evaluation team have not been able to directly interact with individuals involved in these activities, this is likely to have increased these individuals’ awareness and knowledge of other countries’ practices. In the case of the inclusion of personal protection orders in the law, this exposure appears to have played a direct role, and led to specific discussions by legislators regarding the feasibility of implementing personal protection orders in China. Following this exposure, individuals involved in the study tours were involved the process of drafting and revising legislation. The main areas in which this experience appears to have been relevant are as follows:

- During revision of the draft law, the stipulation that women seeking court protection from perpetrators of domestic violence should first apply for divorce was removed. This is a positive revision which should make it easier for victims of domestic violence to seek protection.

- The revised draft of the Family Violence Law included a provision on the use of warning letters and stressed that countering domestic violence is the joint responsibility of the state, society and every family. A number of themes that were the particular object of study during the overseas study trips were the definition of domestic violence, preventive measures (particularly the use of personal protection orders as a standalone measure, the need for information sharing and cross-departmental cooperation in cases of domestic violence.

- UN Women led technical support of the UN system to Chinese government and legislators, and led the writing of a document entitled The Family Violence Law of the People’s Republic of China: An Analysis (UN Task Force for Support National FV Law, 15 March 2016), coordinating the input of other UN agencies and providing technical feedback to government on the content of the law.

- The Family Violence Law Drafting Committee carried out a site visit to Hunan, during which they were exposed to the experience of both Liuyang and Ningxiang counties. Through this route, the programme is likely to have contributed an example of a successful county case to the national legislative process.

Saying this, there are a number of challenges in directly relating the implementation of this programme with China’s Family Violence Law. The most important of these are, first, that China’s legislative processes are not very transparent, making it hard to determine actual links between programme activities and the legislative process. Second, although the programme was able to involve individuals from key government and other agencies in its activities, including in visits to Canada and the UK, it is, inevitably, difficult to involve very high-officials with actual decision-making authority. This is likely to have diluted the influence of such activities. The evaluation team were not able to directly interview individuals who took part in the activities described here, and data collection has had to rely on use of secondary materials (documentation provided by programme stakeholders) and on interviews with UN Women and ACWF officials. This limits our ability to state with confidence the degree of impact of the programme. The analysis above represents our judgement based on information available at the time of writing.

PROGRAMME DESIGN, MANAGEMENT AND SUPERVISION

This section discusses issues of programme design, management and oversight.

Consolidated findings

Programme design and management were well executed, but some aspects could have been stronger and would benefit from more attention in any subsequent programme: for example, better specification of the programme’s expected impact and pathways to impact through development of a theory of change could have been beneficial in understanding some of the barriers to effective change at the level of behaviours and institutions that will be required to ensure better de facto outcomes for domestic violence victims. The programme logframe does not provide a complete description of the programme, and a number of key causal links are not specified. At the level of monitoring/supervision, more attention could have been paid to developing indicator systems to effectively capture real-world changes arising from the programme; broader programme supervision, through field trips, focus groups, etc, could provide better real-time assessment of programme achievements and challenges.

The remainder of the section discusses detailed evaluation findings supporting the above analysis.

Data

Analysis is based on the following main forms of evidence:

- Programme documents collected and reviewed during the inception period

- Meetings with UN Women and staff of the ACWF

- Meetings/discussions carried out during county-level fieldwork

A number of points are raised below. They should be taken as constructive criticisms – they show certain limitations weaknesses in programme design/supervision which, while they do not appear to have substantially damaged this programme, could be addressed in any follow up programme.

Findings

Main findings are as follows:

- It does not appear that a theory of change was developed for the programme, to clearly specify the linkages between programme activities, outputs, outcomes and goals. For example, there are gaps between activities supported by the programme and hoped-for results. Examples include:

- The gap between main activities supported (training) and the development of multi-department systems in the three pilot counties, which has largely been carried out by local government departments. While training supported by the programme has influenced norms, ideas and capacity in the counties that have influenced the development of these systems, the linkage is indirect. Better understanding the linkage between programme activities and local processes could strengthen programme design.

- There is a gap between the focus on training in the current programme and needed institutional reforms in the pilot counties. One example of this is the embeddedness of institutions such as mediation in administrative practice. Such institutions are supported by policies, laws, and other systems, and are unlikely to be reformed simply through training; more direct approaches are needed.

- The logframe does not provide a complete description of the programme, and a number of key causal links are not specified. Examples of how greater specification of the programme logic could have helped programme design/implementation are given below:

Logframe text: 	Output 2 Enhanced capacity of multi-sectoral service providers and community workers to provide coordinated quality services based on the needs of DV survivors in the pilot sites in Ningxiang County of Hunan Province, Jingyuan County of Gansu Province, and Yilong County of Sichuan Province

Comment: 	The link between training and changing behaviours is under-specified. Theories of capacity building and/or behaviour change tend to indicate that there is a chain of activities between exposure to new ideas, changes in norms, to changes in behaviours, and that many institutional and other factors are important in supporting behaviour change – in this case, behaviour change that could result in provision of better services to victims of domestic violence.

Logframe text: 	Output 3 Increased willingness among policy makers at provincial level in Hunan, Sichuan and Gansu to replicate multi-sector model throughout the three provinces.

Comment: 	There is a weak link between the activities carried out by the programme and the hoped-for result of province-wide scale up. A number of factors that may create barriers to scale up are not taken into account. Activity 3.1 in the logframe (“Collect and analyze data and evidence demonstrating the value of the DVPR Model in pilot sites by the external evaluation team” [italics ours]) should not be considered a core programme activity contributing to achievement of logframe outputs/outcomes.

- Outcome-level indicators should be better specified. The outcome-level indicator used by the programme specifies that government will “better address DV in China by adopting international standards and the multi-sectoral model”. This should be considered an intermediate indicator, and a proxy for an actual outcome, rather than a direct measure of changes in outcomes for domestic violence victims. A number of points relating to the treatment of DV victims in the administrative, police and legal systems, as well as the use of mediation in DV cases, could be considered as possible outcome indicators, but would need further work to develop.

- Programme monitoring: Relatively weak monitoring systems were put in place for the programme, requiring reporting of programme activities carried out in the counties. Given the decentralised nature of this programme, where local government agencies put in place systems that are influenced by, but not directly the result of, programme activities, this kind of reporting only provides evidence of activities, not of changes at the output/outcome level. A number of data points could be used to develop a more robust monitoring system that could reflect actual changes in outcomes for victims of domestic violence, some of which are discussed in Section 4. Development and use of such a system would have the potential advantages of both more accurately recording changes brought by the programme, and in encouraging cultures of use of evidence to show the impacts of reforms in the pilot counties.

- Programme supervision: As discussed in Section 3, the evaluation team encountered problems with understandings of domestic violence, particularly where concepts introduced by the programme conflict with dominant and embedded norms. These were most apparent at the community (shequ) level, but also apparent among staff of county-level departments in a substantial number of cases. Strengthened supervision, in the form of short visits / focus groups with communities and/or local officials could be used to rapidly detect such problems and aid course-correction. Such visits could be combined with trainings and/or routine county visits without much expense or addition of time in the field.

Comments, further actions and recommendations

- Consider carrying out theory of change workshops including key programme stakeholders to more fully specify programme logic and spot weaknesses.

- Consider how to develop more robust monitoring mechanisms that can more accurately reflect real world changes, especially at the outcome level.

- Consider how ongoing supervision can be used to detect possible problems in programme implementation during the course of the programme and aid course correction.

SYNTHESIS OF FINDINGS, CONCLUSIONS AND RECOMMENDATIONS

Phase two of the programme of “Preventing and Responding to Domestic Violence in China through a Multi-sectoral Approach” (2014-2017), supported by the EVAW Trust Fund was established to build on phase one (2010-2012) and further develop county models for cross-departmental cooperation to address domestic violence, promote their scale up, and to support the national legislative process and the development of a Family Violence Law. The main forms of support provided by the programme were to training of staff in the three pilot counties, convening of provincial dissemination meetings to promote scale up of the county models developed with support from the programme, and a range of national-level activities supporting development of China’s Family Violence Law (collation and translation of documentation, study tours, etc). This section:

- summarises main findings from the evaluation

- presents findings against the evaluation hypotheses and provides conclusions

- lists recommendations arising from the evaluation

Synthesis of main findings

This section brings together main findings set out in the body of this report. Analysis is set out as follows:

- Training, development of county models

- Dissemination and scale up

- Support to national-level legislation

- Programme design and supervision

    - Training, development of county models

During fieldwork, the evaluation team developed the following graphic representing the pathway of change anticipated as a result of training and support to counties provided by the programme. This was ratified with UN Women.

The graphic provides a useful tool for mapping the impact of training and the extent to which this has translated into changes in norms, behaviour and institutions. Based on this, it is possible to see the following:

- Section three discusses the large-scale training carried out in all pilot counties. This is judged to be well-designed and successful by most training participants and departments involved. Interviewees and survey respondents state that training has given them information on domestic violence in China, the law regarding domestic violence, as well as providing practical information that is of relevance to their work. Survey responses show that overwhelmingly trainees think that the training has given them at least a basic awareness of domestic violence and of the principles and practice of work of their departments in preventing and halting domestic violence. Interviewees report that the training has imparted a lot of legal and practical knowledge regarding domestic violence and that they are able to make use of this in their work and/or impart this to others.

- As well as influencing awareness and knowledge regarding domestic violence, it is possible to see a degree of normative change among survey respondents and interviewees, but there is substantial evidence from fieldwork and survey results that such change coexists with traditional norms and value judgements regarding domestic violence. It appears that entrenched norms are hard to change fundamentally in a relatively short timeframe. Fieldwork indicates that all counties are making progress in improving knowledge and changing norms, but the degree of progress visible at present differs between counties. This should be considered natural, and supports the need for continued and widespread training and awareness raising work.

- At the level of behaviour, a number of interviewees in all counties reported incidents in which they had been able to use knowledge regarding domestic violence in their work or in dealing with others, and many survey responses or interviewees state that practical information imparted during training has been useful in their work.

- The organisation of follow-on training differs in the three programme counties and between different departments in each of the counties, with some reporting relatively strong support for organised follow-on training, and others reporting little such support. Given the progress made by the programme, but also the need for sustained and deepened training, the evaluation team believe that it is important to create more systematic approaches to training in the counties.

- Sections four (Building systems and institutionalising work) and five (Findings on work of participating departments) deal with the changing organisational and institutional responses to domestic violence in the pilot counties. Findings here are broadly positive, but mixed.

- Section four describes the inter-departmental management and referral systems for dealing with domestic violence cases set up in the pilot counties. While there are some differences in the pilot counties’ models, all have put in place functioning and apparently relatively mature systems for convening inter-departmental meetings and for referral. Working-level inter-departmental coordination is progressing in the counties, which appears to be an encouraging indicator of institutionalisation of anti-domestic violence work. Departments involved in anti-DV work in the counties operate within-system referral and coordination procedures, though there are differences between these systems and there are likely to be differences in levels of effectiveness.

- Levels and patterns of referral present an unclear picture, differing from county to county (and between individual departments involved in DV work). No clear explanation for this is apparent from existing data. Nor is it possible from existing data to state what barriers there are to referral or to greater uptake of services. From available data, the incidence of DV in the programme counties appears low, but it is likely that this is due to low levels of reporting and seeking assistance from official agencies, as well as anomalies in how data are recorded and reported.

- Section five describes the work of a number of departments involved in providing services to victims of domestic violence. From interviews in the pilot counties, it is apparent that all departments are building systems to respond to domestic violence. However, fieldwork uncovered a range of practices, some of which provoke concern. At one level, for example, practice in shelters in the pilot counties appears to leave room for improvement, though it should be assumed that many such problems could in principle be resolved with more creative management and a degree more funding. More concerning are more embedded practices linked to prevailing institutions, including the apparent blurring of boundaries between domestic violence and ‘family conflict’ (jiating jiufen). Both these terms are used in administrative language in the counties, and in at least some cases, the evaluation team came across incidents that should be considered domestic violence but were being labelled ‘family conflict’. This blurring of boundaries, and downplaying of the seriousness of individual cases, appears to be replicated in case files seen by the evaluation team during fieldwork. The evaluation team’s interpretation of this is that, although there is a substantial amount of change in levels of knowledge/awareness and (to some extent) in norms and behaviours, it is hard to reform deeply-embedded institutions such as those around the social and institutional definition/construction of family conflict vs. domestic violence and the administrative/legal institutions established to deal with such problems.

- On one level, the assessment of the evaluation team is that this is inevitable: this programme has principally supported training in a number of departments in the pilot counties, the impact of which is visible and positive. Equally, changes in institutional practices are clearly visible – multiple departments in all counties have set up procedures for handling and referral of domestic violence victims. These are positive things and successes of the programme. On another level, however, reforming deeply-embedded social, administrative, and legal institutions is hard and will take time. The programme was not designed to work specifically on reform to the way DV cases are handled in the courts in the pilot counties or to reform actual institutional structures and processes that underpin use of mediation. However, it appears likely that change at the level of institutions that underpin and sustain such practices is necessary to improve outcomes for domestic violence victims. Given the difficulties visible in changing popular perceptions of domestic violence, and the fact that widespread attitudinal/behavioural change is likely to be a long-term process, and one which is dependent, at least in part, on levels of economic and social development and openness, it appears that changes at the level of organisations and institutions are particularly needed.

    - Dissemination and scale up

- In all provinces there appears to be a degree of scale up. This appears strongest in Gansu; at present it appears unlikely that substantial scale up will take place in either Hunan or Sichuan. While feedback on the models at all provincial-level meetings attended by the evaluation team was broadly positive, forms of scale up visible in the three provinces differ, and the provinces clearly attach different degrees of importance to ‘their’ county pilots.

- Discussions with provincial officials indicate that increased provincial coordination and promotion will be necessary to support adoption at scale of the pilot county models. On present evidence, Gansu is the province in which the pilot county’s experience is being most strongly promoted. It appears at present that Hunan’s work on domestic violence is comparatively advanced, that there are other local models that the province considers more advanced than Ningxiang’s, and that this will limit the impact of the pilot. Provincial support for Yilong’s model appears weak.

- Provincial agencies in the three provinces were given a limited role in the programme. It appears that their main participation was in the dissemination meeting held at the end of the programme. It is possible that low levels of engagement across the programme cycle are linked to relatively limited provincial support for scale up of the pilot county models.

- The evaluation has identified a number of barriers to effective scale up of pilot county models, including: (1) There is difficulty in scaling up pilots that rely on coordination of multiple departments, in the absence of strong leadership support from above (from the province, for example). (2) The relatively weak position of the Women’s Federation may hamper scale up efforts. (3) Multiple tools have been developed and popularised through the programme including use of risk assessment forms. These are useful and deserve wider dissemination, but are unlikely to be standalone resources – their use will need to be accompanied by the development of administrative systems and widespread training. (4) Widespread training will be required if county models are to be disseminated widely. This will require commitment of resources and political commitment.

    - Support to national-level legislation

- The programme has provided support to the national-level legislative process culminating in the adoption of the Family Violence Law. Activities supported by the programme have principally been of two kinds – collation and translation of materials on overseas practices/legislation, and study visits to other countries (Canada and the UK).

- It has been challenging to collect evidence on the impact of these activities. The most obvious barrier to this has been the inability of the evaluation team to interview individuals from the key institutions targeted by the programme who were involved in these activities. This is disappointing, but not surprising – access to these institutions should be considered difficult. Given this, data collection relied on use of secondary materials and on interviews with UN Women and ACWF officials, limiting the evaluation team’s ability to state with confidence the degree of impact of the programme on the central legislative process.

- Saying this, it appears that there has been a degree of impact of translated materials and/or overseas learning supported by the programme, including the inclusion of personal protection orders and warning letters in the scope of the law, and the removal of the stipulation that women seeking court protection from perpetrators of domestic violence should first apply for divorce. Although it is not possible to document, the programme is likely to have created a degree of exposure to new ideas and practices for a group of Chinese officials and legislators.

    - Programme design and supervision

- Programme design and management were well executed, but some aspects could have been stronger and would benefit from more attention in any subsequent programme. For example, better specification of the programme’s expected impact and pathways to impact through development of a theory of change could have been beneficial in understanding some of the barriers to effective change at the level of behaviours and institutions that will be required to ensure better de facto outcomes for domestic violence victims. The programme logframe does not provide a complete description of the programme, and a number of key causal links are not specified. At the level of monitoring/supervision, more attention could have been paid to developing indicator systems to effectively capture real-world changes arising from the programme; broader programme supervision, through field trips, focus groups, etc, could provide better real-time assessment of programme achievements and challenges.

    - Gender perspective on domestic violence and programme design

The programme has been informed by a gender perspective on domestic violence, and this in turn has informed the evaluation of the programme. A number of principles underpin the analysis in this report. First, understandings of domestic violence and related practices are moulded by traditional views and value judgements. In China’s traditional patriarchal society, traditional culture (including traditional views and value systems) and political systems have influenced the roles of both sexes, and relations between the sexes in which the position of women is inferior and subordinate to that of men. These value and power systems contribute to the creation and perpetuation of domestic violence through framing women as being at fault, despite being victims of violence; through contributing to a culture of silence around domestic violence, considered a ‘family matter’; and through contributing to women’s silently enduring domestic violence, through gender norms which stress that women should accept their lot. Second, fundamentally, domestic violence is a result of unequal power relations and control in the family/marriage. Perpetrators of violence believe in the primacy of their rights within the family, and that any means (including violence) is legitimate in asserting those rights vis-à-vis other family members or in giving vent to feelings. Victims of violence may also hold such beliefs. Third, design of the programme revolves around meeting actual needs and in changing embedded gender relations. Meeting needs includes providing material and spiritual support to women to solve immediate problems. Changing embedded gender relations involves increasing women’s status and unequal power relations between women and men and through that process ensuring that women’s rights are respected and that all women have freedom for personal development.

Streams of evidence shows that the training and awareness raising work carried out by the programme has included content on changing traditional views and norms; the evidence from most training participants shows the importance of this in changing understandings, though to varying degrees. Substantially changing the traditional culture and ideas of China’s patriarchal society is a long-term and difficult task. Future work should continue to understand how China’s patriarchal society contributes to domestic violence and how to effect systemic change. Second, aside from training, the programme has supported few activities designed to reform unequal family/marriage power relations or to remove the control of perpetrators of violence over victims. Although the programme has worked on creating models for cross-department working and provision of services to help provide for the immediate needs of victims of violence, fundamental change will require more far-reaching changes, including increasing women’s status and reforming gender relations arising from China’s traditional patriarchal system.

Conclusions and findings against DAC criteria

This section provides conclusions regarding EVAW II based on the evaluation hypotheses set out in Section 3.3 and on findings against the DAC criteria. Together these provide both an assessment of the extent to which the programme logic has held, and a consolidated assessment of the relevance, effectiveness, efficiency, sustainability and impact of the programme.

    - Findings against the evaluation hypotheses

Evaluation hypotheses were developed based on the theory of change as a way to test the logic of the intervention. While there are differences in the degree to which the different hypotheses have held, the overall programme logic appears robust and effective.

- Hypothesis 1: Activities supported by the programme, including translation of foreign anti-DV legislation, circulation of materials summarising international best practice on tackling DV, and study trips to countries with notable anti-DV practices contribute to improved understanding among law drafters and key themes are selectively incorporated into national DV law.

- Hypothesis 2: Support provided by the programme to county implementing agencies, principally in the form of training and capacity building, contributes to counties’ strengthening of multi-sectoral anti-DV systems and adoption of international practices.

- Hypothesis 3: Capacity building and advocacy activities supported by the programme, including trainings and workshops, increase national participants’ knowledge of international standards and of the value programme’s multi-sectoral model.

- Hypothesis 4: Support provided by the programme to county implementing agencies, principally in the form of training, improves the ability of multi-sectoral service providers and community workers to provide coordinated quality services based on the needs of DV survivors.

- Hypothesis 5: Dissemination activities supported by the programme, principally dissemination meetings held in the three provinces, increase provincial policy makers’ willingness to replicate models developed in the pilot sites.

The evaluation finds that there is relatively limited evidence to make a case for or against impact of the programme in contributing to improved understanding among law drafters and providing support for national legislative processes (Hypothesis 1). It finds that the direct impact from activities supported by the programme appears limited, but that it is likely that there is a degree of indirect impact in the form of awareness raising and increased understanding.

The evaluation collected good evidence from multiple sources, both quantitative and qualitative regarding the development of anti-DV systems in the counties (Hypothesis 2). Evidence from county-level fieldwork and the surveys implemented by the evaluation team shows that anti-DV systems (both inter-departmental meeting systems and referral systems) have been established and that they are being strengthened and consolidated. Training and capacity building have contributed to this consolidation and strengthening. The evaluation also finds that there is mixed evidence regarding the adoption of good / international practices in county anti-DV systems, as exemplified by concerns regarding shelters, case definition (domestic violence vs. ‘family conflict’), and treatment of cases in the police/legal systems, as well as apparently widespread use of mediation. In the assessment of the evaluation team, the programme underestimates the gap between provision of training and changes in institutions and practices, and that change at deeper, institutional levels necessary to create more substantive change for victims of domestic violence is likely to require sustained work and support.

The evaluation collected good evidence from multiple sources, both quantitative and qualitative regarding the impact of capacity development activities and training on knowledge (Hypothesis 3). Survey evidence shows clearly the extent to which training organised by the programme has influenced attitudes and knowledge, including of international standards, as exemplified by many respondents’ classification of DV as a rights issue. Interview evidence is incontrovertible that there is widespread support among county-level stakeholders for the programme’s multi-sectoral model.

The evaluation has presented partial evidence to substantiate a case for/against impact of support by the programme (principally through training) to provide coordinated quality services based on the needs of DV survivors (Hypothesis 4). Coordinated services are being provided and, as discussed at length in the report, the degree of coordination has increased and coordination mechanisms are becoming embedded and institutionalised. Survey evidence shows that departments in all counties state that they take victims’ needs into account in setting and modifying services, indicating that services should be based on the needs of DV victims, though little or no direct evidence is available from DV victims regarding their experience of these systems and/or individual departments’ services. Set against this, there is some evidence which may contradict this viewpoint, for example the limited use of DV shelters and low rates of seeking support from official agencies may indicate that services are not valued or responding to actual needs. Without further evidence, it is not possible to respond to this point.

The evaluation collected reasonable evidence for support from the provinces for replication of pilot models (Hypothesis 5). Different provinces show a range of outcomes, with some provinces actively supporting dissemination of the county models, and others displaying less support. Reasons for this are likely to include the extent to which provincial stakeholders have been included throughout the programme, the relative significance of county models supported by EVAW versus other existing models in the pilot provinces, and a range of factors relating to the institutional influence of the Women’s Federation in the three provinces. The evaluation finds that there are barriers to replication that will need to be overcome if the county models are to have widespread impact.

    - Findings against DAC criteria

The following table synthesises findings again the DAC criteria of relevance, effectiveness, efficiency, sustainability and impact.

Table 6: Findings against DAC criteria

| DAC criteria | Main findings |
| --- | --- |
| Relevance | - The evaluation finds that the programme’s approach of developing multi-departmental management and referral systems, and of carrying out training of government agencies/staff to respond to the needs of victims of domestic violence, is relevant in the pilot counties and in China more broadly. Work supported by the programme to create awareness of domestic violence and change norms and behaviours is highly relevant to China’s current context. - The evaluation also finds, however, that the focus of the programme has been reactive (dealing with the consequences of domestic violence), rather than proactive (preventing domestic violence), and that the majority of support has been to the above activities and that there has been little focus on prevention, early detection, and other pre-emptive interventions. - The evaluation finds that the programme was designed in a way that is relevant to China’s political and institutional structure, in simultaneously following top-down (supporting legislation) and bottom-up (developing sub-national models) approaches, and that it takes into account the need to engage stakeholders from multiple ministry systems to provide joined up services. - The evaluation also finds, though, that there are likely to be limits to the impact of the approach used in this programme of development and scale up of sub-national models, and that greater work through specific ministry systems to promote ministry-specific regulations, guidance, etc, is likely to be needed in subsequent stages of programming. - The programme demonstrates good fit with UN Women’s mandate and that of the principal partner institution, the All China Women’s Federation, and with UN Women’s mandate and comparative advantage in China as a natural interlocutor for the ACWF, which is de facto the led agency on domestic violence. |
| Effectiveness | - The evaluation finds that outputs/outcomes have been achieved (see Annex 2), but that indicators are limited in their ability to reflect real-world programme achievements. - Effective coordination and management structures were put in place between UN Women, ACWF and the pilot counties to ensure programme implementation. |
| Efficiency | - Evidence available shows that resources have been efficiently used: for a relatively limited budget, the programme has carried out multiple trainings in all pilot counties, and in Beijing, has carried out study trips to two countries, and has collated and translated a substantial amount of documentation into Chinese to serve as a resource for decision makers and legislators. In addition, the programme has catalysed change, and leveraged resources, in the pilot counties. - Programme design, management and supervision measures are adequate to the programme, but would benefit from improvement. Examples include use of a theory of change to underpin programme design, and improved monitoring indicators more capable of reflecting real world changes. |
| Sustainability | - The evaluation finds that multi-department and referral systems established in the pilot counties are relatively institutionalised and should be considered basically sustainable, though individual participating departments in all counties raise a number of challenges relating to their work. Although there is no reason to think at present that these challenges directly undermine the sustainability of the programme’s achievements, it is possible that they may do so if not addressed. - The pilot counties appear to be making judgements regarding sustainability based on current volumes of service delivery. If numbers of reported cases change following introduction of the Family Violence Law, as should be expected, this could create pressure on resources and have an impact on sustainability. - The Family Violence Law provides a good context to ensure the sustainability of the systems established through this programme, with the caveat that changes in policy or in incentive systems in one or more ministry system associated with the models developed in the counties could have an impact on sustainability of the county models. - Scale up and consolidation of the pilot county models should be understood as a way of ensuring the sustainability of these models. From evidence available, it is not clear the extent to which these models will be scaled up or sustained at provincial (or larger) scale without increased support from provincial governments. |
| Impact | - The evaluation finds substantial intermediate impacts on county administrative systems and processes, which are established and functioning. Knowledge and awareness of domestic violence are changing in the three pilot counties (albeit from different starting points), and there is evidence of a degree of normative change, though this is challenged by entrenched norms and attitudes that support traditional gender roles and may condone violence. - The multi-departmental referral system and service provision by individual departments in the pilot counties has reached a large number of victims of domestic violence over the course of the programme (2014-2017), but it is hard to accurately assess impacts for victims. Limitations on data from the counties mean that it is not possible to get a full picture of referral activity, while a systematic assessment of case outcomes for domestic violence victims was outside the scope of this analysis, both in terms of time and data availability. - Findings regarding the work of individual government departments in the pilot counties suggest that, despite the establishment of referral systems and the provision of training to all departments on procedures for providing services to domestic violence victims and/or handling of domestic violence cases, at least a proportion (and possibly a high proportion) of cases are being handled in ways that are not consonant with the norms and standards supported by this programme. As discussed at length in the report, changing embedded institutions and systems is expected to require continued effort, but will likely be important for ensuring better outcomes for victims of domestic violence. |

    - Overall conclusions

EVAW II ran from July 2014 to July 2017 and covered three main strands of work: support to national anti-domestic violence legislation; training and capacity development in three pilot counties chosen to be broadly representative of different levels of development in rural China; and provincial dissemination of models developed in the three counties.

The evaluation team developed a set of hypotheses to guide the evaluation by specifying the logic of the programme, against which fieldwork could provide findings. The evaluation also considered the programme against DAC criteria. The evaluation concludes that EVAW II has been broadly successful its immediate objectives at the output and outcome level, that the implicit theory of change underlying the programme is sound, but that there is a need for more and sustained work both in the pilot counties and more broadly if the broader aims of the programme are to be achieved. The programme performs well as measured against all DAC criteria of relevance, effectiveness, efficiency, sustainability and impact.

China’s Family Violence Law was issued in 2015 (effective from March 2016). EVAW II provided support to translation and compiling of a range of documentation intended to inform legislation and organised visits to Canada and the UK to examine other countries’ practices. We conclude that, while it is likely that these activities will have had some impact, impact appears limited. Examples of possible impact include discussion regarding the use of personal protection orders in China, the removal of the stipulation that women seeking court protection from DV perpetrators should first apply for divorce, and provision on the use of warning letters, which may have been informed by programme-supported activities. This conclusion should be caveated with the statement that interviewing central government departments in China is challenging, and that better access for the evaluation team might have resulted in a different conclusion.

Very substantial progress has been made in increasing capacity in the pilot counties, and in building management systems for coordinating the work of multiple departments on domestic violence, as well as building referral systems able to coordinate services between different government departments, and activities supported by the programme (principally training) are almost universally recognised for their quality and appropriateness. Saying this, however, the evaluation also concludes that training and capacity development are insufficient on their own to achieve deep institutional change, and that this is necessary to change the ways that domestic violence cases are dealt with, and to change final outcomes for victims.

From evidence available at present, it appears that more work is required to better understand the institutional factors that have an influence on cases and outcomes, particularly (though not exclusively) in the police and judicial systems. The evaluation concludes that this points to a need for continued support to anti-DV work in the pilot counties, but that county-level piloting likely has inherent limits due to the ways that system-level incentives impinge on the decisions of county governments and individual government departments. Fundamentally reforming such systems is likely to require work that can promote change in system-level incentives and institutions. It is conceivable that such work could start with explorations at the county level of the challenges to implementing such changes, and possibly piloting specific measures in the pilot counties, that could be built on in provincial, ministerial or other policy or guidelines.

A major objective of the programme was to provide scaleable models that could be rolled out in the pilot provinces. The evaluation concludes, overall, that this has been a mixed success. While the county models are now relatively mature, the current evidence of scale up is limited, and in two of three provinces it doesn’t appear at present that provincial government or agencies is providing the support that will likely be necessary to see these models achieve widespread coverage. An important caveat to this finding is that it remains early days and that more provincial backing or scale up may yet materialise.

At an institutional level, however, the evaluation concludes that support will be needed to more widespread scale up. The pilot counties have benefited from substantial support over the two phases of this programme (EVAW I and II). Although a number of training materials, and reporting and referral forms, etc, have been developed through the programme, and these are universally acknowledged to be useful, other counties are almost certain to require support in building the kinds of systems that the pilot counties have successfully developed. Support to capacity development is likely to be critical.

The programme has worked to develop a cadre of individuals in the three counties with capacity to carry out follow-on training. This appears to be a promising start, but at present these resources are clearly insufficient to the task of carrying out the kind of widespread training that will be needed to broadly disseminate knowledge to, and to support development of coordination and referral mechanisms in, non-pilot counties in the pilot provinces (let alone nationally), while supporting deep institutional change in these non-pilot counties will surely require time and support. Support at this scale clearly exceeds the capability of any one donor organisation, and these conclusions point to the need for government support for widespread capacity development. Presentations at a national dissemination meeting convened by UN Women in June 2017 indicate that some such work is being done in, for example, the police system. Understanding the scope and suitability of work already underway and how this can be supported, improved and made systemic will be important.

Recommendations

This section summarises recommendations provided throughout the report. Following feedback from UN Women, recommendations have been given priority rankings, as indicated by stars (*) in the following table.

Table 7: Recommendations

| Recommendation | Priority* |
| --- | --- |
| Strategic level - EVAW II has been largely reactive, in setting up systems to deal with domestic violence cases, and provide support to victims, after the fact. This is useful, but in future programming, it would be beneficial to consider how to include a greater focus on early detection and prevention in subsequent work, including assessing of at risk women/families. - As the evaluation has shown, training and capacity building appear to be limited in their ability to bring about substantial institutional transformation in the absence of changes in systemic institutions and incentives. In future programming, UN Women should consider what aspects of developing coordinated responses to domestic violence should be addressed through small-scale piloting in counties, and what requires centrally-driven, top-down change through the government and legal systems, and where the strengths of both bottom-up and top-down approaches lie. This could be linked to an assessment of personnel assessment practices in use in the pilot counties (both good practices and practice likely to create inappropriate incentives) as a reference point for other counties during scale up. | *** *** |
| Training, capacity building and raising awareness - Encourage pilot counties to create needs-based, financed and systematic approaches to follow-on training to ensure that training is ongoing, and that it reaches all relevant departments and penetrates to the grassroots. Consider developing targets for training activities. Encourage use of needs analysis by counties/departments and tracking of training needs over time. Encourage pilot counties to explore greater use of cross-departmental training groups, and attempt to gain government backing for the inclusion of training in the work of all government departments. - Programme-provided or supported training should more thoroughly consider the differences between the three pilot counties and the specific needs of participants from different departments. Training design could make use of participatory needs assessment approaches. UN Women / ACWF should consider reviewing the content of training to increase content on how to communicate with domestic violence victims, counselling and related practical skills. - Increase the stress on gender concepts in training. Continue to stress the importance of clearly understanding domestic violence and differentiating it from other phenomena. Consider more clearly defining and specifying the scope and nature of domestic violence, from a narrow focus on close relatives / within marriage to include violence among cohabiting, unmarried couples, and among former partners who have separated or between divorced. - The programme has trained a number of TOT trainees. While this is a positive things, this capacity will need to be strengthened and updated over time, including with content on new legislation and on best practices in other places. Much stronger training capacity will need to be built to underpin scale up of the models developed by EVAW II province- or nation-wide (see comments on scale up, below). Work at this scale is beyond the capacity of any one donor. UN Women and ACWF should consider how they can advocate for the mainstreaming of such training and support work by central government, ministries and/or provincial governments to ensure that training is of high quality and that it reflects the values and concerns of UN Women / ACWF. - At present, many different activities are recorded as ‘training’ by pilot counties. This creates a lack of clarity around the kinds of activities actually carried out. any subsequent programme should consider promoting standardised classification of training activities to avoid too wide a range of activities (e.g. informal discussion of domestic violence at large-scale meetings) being classified as training. This would have the advantage of increasing transparency over extent of ongoing activity. | *** ** ** *** * |
| Building systems and institutionalising work - The evaluation found that systems for recording data on DV in the pilot counties are limited in their ability to clearly show the extent of the problem. Getting a better understanding of incidence is important to guiding the public policy response. UN Women and ACWF should consider carrying out a more in-depth assessment of systems currently in use for recording instances of domestic violence by all relevant departments, and should encourage counties to develop unified recording systems and information sharing systems and/or consider providing technical/financial support for developing cross-departmental, integrated information systems. - The evaluation has found that data provided by the pilot counties regarding referrals is limited in its ability to clearly show flows of people between different government departments. An in-depth analysis of referral patterns and barriers to referral, plus how these can be overcome in subsequent work, would be helpful to inform subsequent programming. - Discuss with counties in more detail the range of challenges raised in response to the evaluation survey, and whether any of these require systemic solutions and/or are amenable to inter-county learning and summarising of experience. | ** * * |
| Work of participating departments - A number of things require systematic investigation: how DV cases are treated in the courts in the pilot counties, and the bases for legal judgements in DV cases / divorce cases involving DV; knowledge, attitudes and behaviour of judges and other legal professionals involved in DV cases and specific training needs of judges and other legal professionals involved in DV cases; evidential requirements in DV cases and the impact of these on outcomes; how oversight and management of DV cases are carried out in courts in the pilot counties; the extent to which mediation is being used in DV cases, under what exact circumstances, by what agencies, what qualifications or requirements are for mediators, and whether/how systematic oversight is carried out. - DV shelters: Consider summarising best practices from the pilot counties on systematically including domestic violence victims in designing services. Consider assessing best practices among domestic violence shelters in the pilot counties and developing a checklist of features for DV shelters to be considered during design. There appear to be few provisions for long-term shelter for victims in need of this, or differentiated/targeted support for complex DV cases. Consider whether there is a need for long-term domestic violence shelters/support, and how this might be met. - Counselling and psychological support facilities available in the counties are limited. Consider assessing the current state of counselling and psychological support facilities, including capacity of staff engaged in this and approaches used, and developing guidance on best practices. Subsequent work should consider how greater and more professional resources can be made available for psychological support and counselling. Consider how professional social workers and/or non-governmental agencies could contribute to tackling domestic violence, possibly through purchasing arrangements with county agencies. - Health facilities: Investigate possible financial barriers to access to treatment in health facilities and consider developing guidance for the health and family planning system in the pilot counties on dealing with DV cases where there is no ability to pay. Consider investigating the assessment of symptoms that may be linked to domestic violence by grassroots-level health facilities, especially ones that should be considered to have comparatively lower capacity, and what proportion of potential DV cases is likely to be accurately detected under current conditions. | *** ** * ** |
| Programme design and supervision - In subsequent programmes, consider carrying out theory of change workshops including key programme stakeholders to more fully specify programme logic and spot weaknesses. If in-house capacity is not available for this, consider contracting external support. - Monitoring mechanisms: In subsequent programmes, consider how to develop more robust monitoring mechanisms that can more accurately reflect real world changes, especially at the outcome level. Examples could include changes in numbers of high / medium / low risk cases, changes in classification of cases as domestic violence vs. ‘family conflicts’, etc. Monitoring frameworks used in EVAW II did not include any assessment of outcomes for DV victims. In subsequent programming, it would be beneficial to investigate more fully outcomes of actual cases through the mediation and court systems and what support is needed to achieve better outcomes. - In subsequent programmes, consider how ongoing supervision can be used to detect possible problems in programme implementation during the course of the programme and aid course correction. - Consider making use of targeted external support in carrying out theory of change workshops, designing reporting and monitoring systems, etc. | * ** * * |
| Note: *** indicates highest priority; * indicates lower priority. |  |

EVALUATION TERMS OF REFERENCE

The evaluation terms of reference are reproduced here for reference.

Terms of Reference

Final Evaluation of the 2nd Phase EVAW Programme: Promote Efforts for National Legislation on Domestic Violence and Upscale the Multi-sector Model in China

Job Code Title:       One international and one national consultant

Type of Contract:		Contract for Consultant

Location:				Beijing with travel to pilot sites in Hunan, Sichuan and Gansu

Duration of Contract:	April 20th –June 23rd 2017

Start Date: 			20th April

Proposal/CV requirements: Please see section VII.

Application Deadline:  March 26th 2017

- Background and Context

In China, as in other countries, domestic violence (DV) presents a significant risk to the health and well-being of women, as well as undermines the social and economic development of communities and the entire country. DV persists and continues to be treated as a family affair despite provisions in the Marriage Law (revised in 2001) and the Law on the Protection of Rights and Interests of Women (amended in 2005), which prohibit DV and explicitly state that violence against women (VAW) is a human rights violation. To support the implementation of these national legislations, 29 provinces have established regulations on the prevention of and response to DV. Moreover, in 2008, the All China’s Women Federation (ACWF) and key government agencies jointly released a national policy document that identifies their roles and responsibilities in addressing DV.

The EVAW Trust Fund supported the UN joint programme “Preventing and Responding to Domestic Violence (DV) in China through a Multi-sectoral Approach” from 2010 to 2012. The expected outcome of this three-year joint programme was to establish an effective DV prevention and response (DPVR) model in three counties and improve relevant DV laws and policies. The external, final evaluation of the programme in 2012 found that the local DPVR models were established and functioning in the three pilot sites in Hunan, Sichuan and Gansu Provinces. The three pilot sites have established preliminary tailored, multi-sectoral cooperation mechanisms at county level, with prevention of DV and response to the multiple needs of DV survivors as top priorities. However, the local DVPR models were still in early stages of development. In particular, the referral mechanism at community level still needed further improvement to ensure services meet the needs of DV survivors. While evaluators observed a moderate increase in DV awareness among the general public, uptake of DV services did not to increase significantly.

The EVAW joint programme highlighted the need for a DV Law that addresses violence against women, children, the elderly and the disabled occurring within the home or within intimate relationships. As this FV Law was already on the National People’s Congress’ (NPC) legislative agenda, it was suggested that more efforts should be made to 1) support the drafting process of the law to incorporate internationally accepted standards and definitions; 2) further develop the multi-sectoral DPVR models in Hunan, Sichuan and Gansu provinces for national scaling-up, based on the pilot model established during the previous EVAW programme.

Programme Description:

Based on the recommendations and lessons learned from the EVAW joint programme, a second phase of the programme “Promote Efforts for National Legislation on Domestic Violence and Upscale the Multi-sector Model in China” was formulated and the programme covers a period of July 14 2014 to July 15 2017. The programme aims to contribute to the DV Law drafting process and further develop the DVPR model in Hunan, Sichuan and Gansu based on the pilot model established during the previous EVAW Joint Programme supported by the EVAW Trust Fund. Following the passing of China’s first DV Law on December 27th 2015 and coming into effect on March 1st 2016, the programme has been working towards the implementation of the law.

Long term objective: Increase the number of women in China that can enjoy their right to a life free from DV.

Overall Goal of the programme is to protect women from DV in China through national legislation and improved and expanded services. The outcome is defined as “Government took measures to better address DV in China by adopting international standards and the multi-sectoral model in the 3 pilot provinces”.

The expected outputs to be achieved during the three years of this programme are as follows:

- Increased knowledge of international standards and of value of the multi-sectoral prevention and response model implemented under the programme among decision-makers at national level.

- Enhanced capacity of multi-sectoral service providers and community workers to provide coordinated quality services based on the needs of DV survivors in the pilot sites in Ningxiang County of Hunan Province, Jingyuan County of Gansu Province, and Yilong County of Sichuan Province.

- Increased willingness among policy makers at provincial level in Hunan, Sichuan and Gansu to replicate multi-sector model throughout the three provinces.

The programme uses the strategy of a rights-based, multi-sectoral approach. Its key activities include advocacy for the DV Law drafting team, capacity building of multi-sector service providers in the pilot sites, male involvement and public advocacy. Community mobilization and individual behavior change activities aim at improving knowledge, attitudes and practices of community members (including men and youth). To respect, protect and fulfill women’s human rights provided under the CEDAW, the programme works to raise women’s awareness of their rights and to conduct advocacy activities targeting policy decision-makers and legislators.

By adopting a rights-based and DV survivors’-centered approach and ensuring survivors’ well-being and safety, the programme continues the work that began in Ningxiang County of Hunan Province, Jingyuan County of Gansu Province, and Yilong County of Sichuan Province, to demonstrate an effective community intervention model through a strengthened multi-sectoral referral mechanism based on the early results produced under the EVAW joint programme.

- Evaluation purpose and use

The overall purpose of this evaluation is to provide a solid assessment of the programme’s relevance, effectiveness, efficiency, impact and sustainability guided by

- Relevance: extent to which the expected results are consistent with beneficiaries’ requirements, country-needs, global priorities, UN Women’s mandate and comparative advantage and partners’ and donors’ policies;

- Effectiveness: extent to which 2nd Phase EVAW outputs/outcomes were achieved, including coordination, management and institutional structure of the programme implementation.

- Efficiency: measures of the programme delivery (monitoring and indicators) and how economically resources/inputs (funds, expertise, time, etc.) are converted to results.

- Sustainability: The probability of continued long-term benefits from the programme results; and

- Impact: change/progress in lives of women and girls suffering violence and possible change/progress in mind set of different stakeholders throughout the programme   implementation in contributing to transformational change for gender equality and women's empowerment.

The evaluation will provide a series of recommendations and proposals for improving programme design and management structure, as well as strategic approaches, in order to inform decisions concerning similar projects and programmes.

The evaluation will also consider:

- Relationships and coordination with national and sub-national stakeholders, decentralized structures and systems, and identify opportunities for improved collaboration and coordination.

- Relevance, efficiency, and sustainability of the convergence approach in line with the OECD-DAC criteria for evaluation, together with integration of human rights, gender equality and environmental sustainability in line with UN Women’s evaluation criteria.

- Evaluation Key Questions

The consultant should be guided but not limited to the scope of the evaluation questions listed below. The consultant should raise and address any other relevant issues that may emerge during the evaluation:

| Evaluation Criteria | Key Questions |
| --- | --- |
| Relevance | - To what extent are the programme objectives consistent with beneficiaries’ needs and the country’s violence against women priorities, global trends and processes and partners’ and donors’ requirements; in other words, are the programme goals relevant in China? - What is UN Women’s comparative advantage in this area of work compared with other UN entities and key partners? - To what extent is the intervention aligned with and contribute to international conventions (e.g. CEDAW, SDG) and related documents (e.g. Concluding Observations), and other relevant international agreements on human rights and gender equality? - To what extent is the intervention informed by substantive and tailored human rights and gender analyses that identify underlying causes and barriers to beneficiaries’ fulfillment of human rights and gender equality? - To what extent is stakeholder participation relevant to the intervention? |
| Effectiveness | - To what extent has the programme made progress towards planned outcomes and outputs? Which areas or outcomes have progress and least progressed and why? - How effective were the programme strategies in achieving expected results? - During the programme implementation, were there systematic and appropriate efforts to include various groups of stakeholders, including those who are most likely to have their rights violated? - To what extent did the programme develop and build capacities of partners to protect women’s human rights and promote gender equality? - How effective has the programme been in establishing ownership? - What are the lessons learned from these partnerships and the possibilities to replicate them? - To what extent has the programme been implemented using a Human Rights based-approach? - Did the programme implementation maximize efforts to build the capacity of rights holders and duty bearers? |
| Efficiency | - Have resources (funds, human resources, time, expertise, etc.) been allocated strategically to achieve results? Have resources been used efficiently? - Have programme funds and activities been delivered in a timely manner? - Assess managerial and work efficiency. Were management capacities adequate? - How effectively did the programme management team monitor programme performance and results? |
| Impact | - What are the positive and negative, primary and secondary long-term effects produced by the Programme, directly or indirectly, intended or unintended? - Have rights holders been able to enjoy their rights? Have duty bearers improved the ability to comply with their obligations? - Has the programme enhanced the international standards in various training, research and advocacy/campaigns planned and implemented? - How effective were the accountability mechanisms operating on anti- DV, human rights and gender equality? - Have there been any good practices, community response model(s) and tenable change produced under the programme that could be up-scaled? |
| Sustainability | - To what extent has the programme supported: - Development of an enabling or adaptable environment for real change on eliminating domestic violence, protecting women’s human rights and gender equality - Institutional change conducive to systematically addressing domestic violence, human rights and gender equality concerns - Establishment of accountability and oversight systems between rights holders and duty-bearers - Capacity development of targeted rights holders (to demand) and duty bearers (to fulfill) rights - Development of appropriate model responses to the violence against women at the community level and its implications for the policy change. - How was exit strategy planned/ addressed during programme implementation? - Can the programme approach or results be replicated or scaled up by national partners? What would support their replication and scaling up? - Any gaps to be further addressed by future programmes to ensure sustainability of the programme models? |

- Scope

The evaluation will look at the UN Women’s “Promote Efforts for National Legislation on Domestic Violence and Upscale the Multi-sector Model in China (2nd Phase EVAW)” programme which has been implemented by ACWF. Under this, the scope of the evaluation is limited to the programme funded by the Government of China, implemented over the period of 3 years (July 14 2014 – Julie 15 2017) with a total budget of USD 500,000.

The evaluation will focus on the 2nd Phase EVAW overall, programme achievements at outcome level, assess the programme impact against its original design where possible; and identify key successes, lessons and experiences arising during programme implementation at national level and in one county in each of the three selected provinces, namely Hunan, Gansu and Sichuan provinces. The evaluation will also assess the management and coordination structure of the programme and analyse its benefits and shortcomings against the achievements and impact of the programme.

The final evaluation of the programme is to be conducted externally by an independent consultants’ team, consisting of one international and one national consultant, both of whom are preferably based in Beijing. UN Women China will provide substantive support, in close consultation with ACWF who is the Responsive Party for the implementation of the programme. The evaluation will be conducted in the period of April to June 2017.

- Methods, Processes and Timeframe

Methodology:

The evaluation will be based on gender and human rights principles, as defined in the UN Women Evaluation Policy. The evaluation will be conducted in accordance with UN Women evaluation guidelines and UNEG Norms, Standards, Ethical Guidelines, Code of Conduct for Evaluations and Integrating Human Rights and Gender Equality in Evaluations in the UN System.

The evaluation will be a transparent and participatory process involving relevant UN Women stakeholders and partners at national and local levels. These are including but not limited to: UN Women staff, staff from UN agencies, and ACWF staff at national, provincial and county levels, multi-sectoral partners, community workers, and/or women who are survivors of domestic violence if appropriate.

The evaluation will examine all the relevant documents of the programme, including programme document with logical framework, annual work plan, progress report by implementing partners, UN Women’s progress reports to the donor, knowledge products produced in the frameworks of the programme, the evaluation report of the UN joint programme conducted in 2012,  etc.

The evaluation methodology will employ mixed methods for data collection. The evaluation will have two levels of analysis and validation of information:

- Level 1: A desk review of information sources, such as, but not limited to: programme documentation, work plans, roles and responsibilities, partnership agreements, progress reports, mission reports, technical products developed, data collected, and any important correspondence between key parties.

- Level 2: In-depth analysis of the programme both by qualitative and quantitative data collection. This will involve visits to project sites in three provinces where the programme has been implemented, and will employ a number of evaluation methods ranging from document reviews, interviews, focus group discussions, surveys, observations.

Evaluation process:

The evaluation will look at the progress made towards the results of the programme and communicate lessons learned and any recommendations for future programming to UN Women and partners. The entire process will take place over a period of April to June 2017, in which collection of field data should be completed over a period of 1 month from the start of data collection.

The evaluation should include the following steps:

Step 1: Desk review: Key documents, reports, policy papers

The evaluation team will attend an inception meeting where orientation on programme objectives will be offered, as well as on progress made. At this stage of the evaluation, the evaluators will have the chance to speak with UN Women staff, as well as with selected stakeholder representatives. The evaluation team will be given key programme documentation for review. The inception meeting, desk review of key programme documents (e.g. programme documentation, contracts, agreements, progress reports, mission reports, etc.), and key stakeholder interviews to understand the scope of the evaluation - will be held to inform the drafting of the inception report. This stage of the process can be home-based.

# Step 2: Inception report

The draft Inception Report should be submitted, with methodology and evaluation design. The inception report will be reviewed by UN Women. The Inception Report will then be finalized based on UN Women’s feedback. The Inception Report should include final evaluation questions, identified stakeholders for interviews and discussions, and the methodology of the evaluation.

# Step 3: Data collection (mixed-methods)

The evaluation team will conduct interviews and meetings in Beijing with UN Women, ACWF and other UN agencies in Beijing on how stakeholders view the programme. Information and data from programme staff at national and local levels, documentation, surveys (pre- and post-training survey) and stakeholder interviews and group discussions are used to determine plausibility of the programme model, i.e. to the extent it is properly implemented, sufficiently developed, and activities appropriate, to reasonably predict that the programme is contributing to the stated results, with a particular emphasis on output level results. This data collection will include both in-country, face-to-face and/or virtual (telephone, video conferencing) interviews.

The evaluation team will conduct field visit to selected programme provinces. A short and simple questionnaire should be complimented by focus group discussion at the field level to collect data facts and information from the implementing partners and beneficiaries for in-depth insights of the programme effectiveness efficiency and sustainability. In the selected programme sites, the evaluation team will

- Attend an initial briefing meeting with all local participating organizations and departments,

- Meet relevant provincial/municipality level key stakeholders (e.g. ACWF, health bureau, public security bureau, bureau of justice, civil affairs departments),

- Visit programme county/communities in the programme provinces according to the detailed schedule and meet relevant stakeholders and beneficiaries, and

- Hold a debriefing meeting with local participating organizations and departments at which preliminary findings will be presented by the consultant.

Step 4: Data analysis and synthesis

Collected data should be analysed, and the Analysis Framework should be clearly explained in the report and also shared during the inception phase.

# Step 5: Sharing of preliminary findings

The evaluation team will share preliminary findings and recommendations with UN Women at the end of the field visit and interviews with stakeholders. The evaluators will draft the report and present the initial report to a group with representatives from UN Women and key stakeholders.

# Step 6: Report writing

The evaluation team makes conclusions and recommendations. Conclusions and recommendations are drawn from the data. The evaluators is encouraged to guard against validity threats, such as personal bias.

# Step 7: Sharing of draft report

The evaluation team finalizes a draft report and share the draft report to stakeholders to validate information. The report structure should follow UNEG’s evaluation report guidance. UN Women will review the report as part of quality assurance and will share it with ACWF for feedback.

# Step 8: Finalization of the Report

The evaluation team will finalize the report. Recommendations will be drafted for Management Response.

# Step 9: Dissemination of Report

UN Women will develop a dissemination and utilization plan following the finalization of the Evaluation Report.

UN Women and ACWF will be responsible for providing logistic support. Detailed itinerary will be developed in consultation with the consultant, UN Women and ACWF.

Timeframe / Work plan:

The timeframe (tentative) for 27 working days for evaluation team spread across the period of April 20 to June 23 2017.

| Items | Responsible Party | No. of working days | Deliverable Deadline | April |  |  |  | May |  |  |  | June |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inception meetings with UN Women and ACWF, desk review and drafting inception report with evaluation methodology | Evaluation team | 5 | 7 May |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of inception report by UN Women/ACWF – 1 week | UN Women ACWF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalization of inception report | Evaluation team | 1 | 12 May |  |  |  |  |  |  |  |  |  |  |  |  |
| Data collection: trip to the programme sites and meeting with stakeholders in Beijing | Evaluation team | 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Presentation of preliminary findings to UN Women | Evaluation team | 1 | 26 May |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit 1st draft report, which summarizes key findings and recommendations | Evaluation team | 5 | 1 June |  |  |  |  |  |  |  |  |  |  |  |  |
| Review 1st draft report by UN Women and ACWF - 1 week | UN Women ACWF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit 2nd draft report | Evaluation team | 3 | 11 June |  |  |  |  |  |  |  |  |  |  |  |  |
| Review 2nd draft report by UN Women and ACWF - 1 week | UN Women ACWF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalization and submission of final report in English and Chinese | Evaluation team | 3 | 23 June |  |  |  |  |  |  |  |  |  |  |  |  |

- Deliverables

# The deliverables of the evaluation are as follows:

- Inception Report: The inception report should detail the evaluators’ understanding of what is being evaluated and why, showing how each evaluation question will be answered by way of: proposed methods; proposed sources of data; and data collection procedures. The inception report should also include an evaluation matrix, proposed schedule of tasks, activities and deliverables. The inception report should also contain a description of the country visits. UN Women guidance on inception reports is available.

- Preliminary Findings: The evaluation team shall share initial findings and recommendations with the UN Women programme team prior to the stakeholders’ consultation.

- Draft Reports: Report structure should follow UNEG evaluation report guidance.

- Review to validate data and provide feedback comments: UN Women China should make share for sharing draft report with ACWF to validate data and provide feedback to the draft report at a timely manner.

- Final Report: The final report will follow UN Women’s Report Guidance, and be submitted in hard and in soft copy in English and Chinese.

# Note: All process should be guided by UNEG’s guidance on human rights and gender equality in evaluation: http://uneval.org/document/detail/1616

- Management arrangement

The evaluation team will work in close collaboration and consultation with UN Women China and programme management structure as per the table below:

| # Actors and accountability | Roles and Responsibilities |
| --- | --- |
| # China Country Programme Manager | - Safeguard of the independence of the evaluation exercise and ensure quality of the evaluation - Prepare a management response to the evaluation |
| # Evaluation Task Manager – Programme Coordinator | - Prepare TOR for the evaluation - Provide all the document information sources the evaluators require - Provide inputs from the programme perspective - Participate in the review of the evaluation methodology - Help identify the Programme sites to be visited - Help arrange the travel to the Programme site and other logistic issues in close consultation with ACWF. - Observe the evaluation process - Facilitate the process by providing available documents, data and contacts - Clarify questions raised during the evaluation - Provide inputs for the evaluation report |
| # Regional Evaluation Specialist | - Support the UN Women China on all stages of evaluation management, in terms of technical evaluation issues |
| # Programme implementation team – UN Women and ACWF | - ACWF will provide logistic support to facilitate the evaluators’ field visits and meetings with partners and individuals at national and local levels at the request of the evaluators - Participate in various steps of the evaluation management process, such as inception meeting and commenting on draft reports |
| # Evaluation Team Leader | - Lead and conduct the evaluation, and be responsible for the relevant deliverables - Communicate with UN Women whenever needed - Oversee field visits and data collection Deliverables and Deadline - First inception report, 7 May - Final inception report, 12 May - Presentation of preliminary findings, 26 May - First draft report, 1 June - Second draft, 11 June - Final report in English, 23 June |
| # Evaluation Team Member | - Conduct the evaluation, and be responsible for the relevant deliverables - Communicate with UN Women whenever needed - Conduct field visits and data collection Deliverables and Deadline - First inception report, 7 May - Final inception report, 12 May - Presentation of preliminary findings, 26 May - First draft report, 1 June - Second draft, 11 June - Final report in Chinese, 23 June |

- Personnel / Qualifications

The evaluation team should consist of one international as team leader and one national consultant as team member to conduct the evaluation process and produce deliverables. The team leader will consult with the national expert on division of labour for specific tasks, but retain the overall responsibility for delivering expected deliverables and evaluation results with the support of the national expert.

An application with both international and national evaluators is highly desirable. Beijing based applications will be prioritized. The evaluation team should clearly detail roles and responsibility, and the number of days each member shall work. CVs of team members have to be attached, with at least 2 references. Sample of previous work should be included, they will be asked for during assessment of proposals. A cover letter confirming availability for the task and the daily consulting rate requested should be included in the application package.

Qualifications for an international evaluator serving as the team leader:

- At least Master’s Degrees in social sciences, evaluation, development studies, gender studies, law studies, sociology, political science;

- Strategic thinking and proven expertise on gender analysis and gender based violence;

- At least 10 years’ experience in programme evaluation and proven accomplishment in undertaking evaluations, preferably gender based violence or/and violence against women evaluation including leading evaluations of multi-stakeholder programmes;

- Experience in conducing complex evaluations in the development field and with international organizations (at least 8 evaluations of which at least one as team leader);

- Knowledge in results-based programming in support of gender based violence, gender justice and human rights;

- Excellent inter-personal and communication skills;

- Excellent written and spoken English and presentational capacities;

- Spoken and presentational capacity in Chinese very strong asset;

- Extensive knowledge of qualitative and quantitative evaluation methods;

- Previous experience of working with the UN, with China experience is a distinct advantage;

- Knowledge of the gender based violence in the context of China and preferably previous experience in anti-DV initiatives in China an asset;

- Excellent drafting and writing skills to produce and present concise and analytical reports and communicate clearly with evaluation stakeholders;

- Excellent interpersonal and teamwork skills;

- Display of integrity, by modelling the UN's values and ethical standards; and

- Cultural, gender, religion, race, nationality and age sensitivity and adaptability are required.

Qualifications for a National evaluator serving as team member:

- At least Master’s Degrees in social sciences, evaluation, development studies, gender studies, law studies, sociology, political science;

- At least 5 year experience in participating in programme evaluations with gender-responsive evaluations is a requirement;

- Experience with programmes and/or evaluations on gender based violence, especially domestic violence;

- Excellent English and Chinese drafting and writing skills to produce and present concise and analytical reports and communicate clearly with evaluation stakeholders

- Excellent understanding and commitment to UN Women’s mandate is a requirement;

- Previous experience of working with the UN, with experience working in China is a distinct advantage;

- Display of integrity, by modelling the UN's values and ethical standards;

- Cultural, gender, religion, race, nationality and age sensitivity and adaptability are required.

- Evaluation Ethics

# Evaluations in the UN will be conducted in accordance with the principles outlined in both UNEG Norms and Standards for Evaluation in the UN System and by the UNEG ‘Ethical Guidelines for Evaluation’. These documents will be attached to the contract. Evaluators are required to read the Norms and Standards and the guidelines and ensure a strict adherence to it, including establishing protocols to safeguard confidentiality of information obtained during the evaluation. Evaluators are also required to be guided by UN Women’s Handbook on Gender-Responsive Evaluations throughout the process.

ANNEX 2: LOGFRAME AND DATA

The following table reports data against logframe indicators. Note that the quality of indicators used by the programme is discussed in Section 9, which should be referred to alongside this table.

Table 8: Findings against logframe indicators

| Logframe outcome/output | Indicator | Data/source | Assessment and/or comment on the indicator |
| --- | --- | --- | --- |
| Outcome: Government took measures to better address DV in China by adopting international standards and the multi-sectoral model in the 3 pilot counties | - Institutionalized standards and operational procedures developed and issued for multi-sector referral system in 3 pilot sites | - A large number of county level documents and operational procedures have been formulated/released by the pilot counties;; main ones are included in reports produced by the programme synthesising the three pilot county models. | - Outcome, as measured by the indicator, has been reached. |
| Output 1: Increased knowledge of international standards and of the value of the multi-sectoral prevention and response model implemented under the programme among decision-makers at national level. | - At least 60% of the national policy-makers participating in programme workshops increased their knowledge as measured by pre- and post-workshop assessments | - No data were collected by programme implementers following workshops with national policymakers as this was thought to be inappropriate. | - No judgement is possible due to absence of data. |
| Output 2 Enhanced capacity of multi-sectoral service providers and community workers to provide coordinated quality services based on the needs of DV survivors in the pilot sites in Ningxiang County of Hunan Province, Jingyuan County of Gansu Province, and Yilong County of Sichuan Province. | - At least 70% of all training participants rated the training as “practical and useful” as measured by pre and post-training assessments - Trained DV service providers and community workers can demonstrate how to address DV in their daily work. | - Progress reports supplied by UN Women to the evaluation team state that in all cases of pre- and post-training assessments, more than 95% of training participants rated the training as “practical and useful” - No systematic data was collected regarding point two through programme monitoring/reporting, but survey and interview data collected during the final evaluation provide evidence of the ability of service providers to address DV in their daily work. | - Output 2, as measured by the indicator, has been reached, with the caveat that data collected by the evaluation indicate that there are discrepancies in the ability of individuals to report on / demonstrate ability to address DV and actual practice as influenced by prevailing norms and institutions. |
| Output 3 Increased willingness among policy makers at provincial level in Hunan, Sichuan and Gansu to replicate multi-sector model throughout the three provinces. | - At least 70% of all training participants rated the training as “practical and useful” as measured by pre and post-workshop assessments | - Information/documentation provided to the evaluation team does not specifically report on training participants’ rating of the training as “practical and useful”, but reports that “100% of the participants agreed that multi-sector service providers have to work together to safeguard the legitimate rights and interests of DV victims” | - The output appears to have been achieved, with the caveat that data collected does not exactly fit the indicator. |
| Source: Progress Reports and Mission Reports provided by UN Women to the evaluation team. |  |  |  |

ANNEX 3: INTERVIEWS AND MEETINGS

| Date | Location | Time | Meeting attendees / format |
| --- | --- | --- | --- |
| 31st May | Beijing | a.m. | Meeting, UN Women: Julia Broussard (head); Guo Ruixiang (programme manager), Henry Li (programme assistant). |
|  | Beijing | p.m. | Meeting with staff from the Rights Department and International Department of the All China Women’s Federation. |
| 1st June | Chengdu, Sichuan | p.m. | Meeting with multiple departments of Sichuan provincial government, convened by Sichuan Provincial Women’s Federation, including Women’s Federation, Police Department, Justice Department, Health and Family Planning, Civil Affairs. |
| 2nd June | Yilong County, Sichuan | a.m. | Individual meetings with Yilong County departments involved in programme: Women’s Federation, Police Department, Justice Department, Health and Family Planning, Civil Affairs. |
|  |  | p.m. | Visits to, and meetings with: maternal and child hospital, Yilong county town; police station; domestic violence shelter. |
| 3rd June | Yilong County, Sichuan | a.m. | Nanmen community visit/meetings; interviews with domestic violence victims. |
| 4th June | Changsha, Hunan | a.m. | Interview with Ouyang Yanwen |
|  | Ningxiang County, Hunan | p.m. | Meetings with representatives of Donggui and Meijiatian communities. |
| 5th June | Ningxiang County, Hunan | a.m. | Joint meeting with Ningxiang County departments involved in programme: Women’s Federation, Police Department, Justice Department, Health and Family Planning, Civil Affairs. |
|  |  |  | Meeting with Ningxiang Women’s Federation. |
|  |  |  | Meeting with two lawyers from Ningxiang Legal Aid Centre. |
|  |  | p.m. | Meeting with two police officers from Baishiqiao police station. |
|  |  |  | Meeting with staff from Ningxiang County maternal and child hospital. |
| 6th June | Ningxiang County, Hunan | a.m. | Visit/meeting, domestic violence shelter. |
|  |  |  | Meeting with Ningxiang trainees. |
|  | Changsha, Hunan | p.m. | Meeting with multiple departments of Hunan provincial government, including Women’s Federation, Police Department, Justice Department, Health and Family Planning, Civil Affairs. |
| 7th June | Lanzhou, Gansu | p.m. | Meeting, multiple departments of Gansu provincial government: including Women’s Federation, Police Department, Justice Department, Health and Family Planning, Civil Affairs, Gansu People’s Court, Gansu Party School. |
| 8th June | Jingyuan, Gansu | a.m. | Joint meeting with Ningxiang County departments involved in programme: Women’s Federation, Police Department, Justice Department, Health and Family Planning, Civil Affairs, law firm. |
|  |  |  | Meeting, Justice Department. |
|  |  | p.m. | Visit/meeting, domestic violence shelter. |
|  |  |  | Meeting, Women’s Federation. |
|  |  |  | Meeting, Jingyuan County maternal and child hospital. |
|  |  |  | Meeting, Police Department. |
| 9th June | Jingyuan, Gansu | a.m. | Interview, victims of domestic violence. |
|  |  |  | Meeting, community representatives. |
| 21st June | Beijing | p.m. | Meeting with UN Women: Guo Ruixiang (programme manager), Henry Li (programme assistant), Wang Qing. Interview with Li Hongtao. |
| 27th June | Beijing | p.m. | Presentation of initial evaluation findings at meeting of national stakeholders and pilot county representatives. |
| 28th June | Beijing | p.m. | Meeting, UN Women: Julia Broussard (head); Guo Ruixiang (programme manager), Henry Li (programme assistant), Wang Qing (programme assistant). |

ANNEX4: PRIVACY STATEMENT

The following privacy statement was used in interviews:

评估小组在访谈中遵循研究伦理，访谈遵循自愿和保密的原则。评估小组明确告知受访者（特别是受暴妇女），此次评估的意义、内容、时长、访谈方式和保密承诺。受访者被告知：访谈将在安全的环境中开展，并遵循自愿的原则，如果觉得不舒服，受访者可以不回答访谈问题，也可以选择在访谈开展的任意时间点终止。受访者的个人信息和在访谈中告诉我们的信息，不会被透露出去。我们会尽最大努力保护受访者的私密信息。

ANNEX 5: COUNTY SURVEY DATA

县级项目实施伙伴机构调查问卷

促进反家庭暴力立法，推广多部门合作模式 （反家暴项目二期）

终期评估

- 基本信息

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 回收问卷数 | 5 | 4 | 5 |
| 问卷填答单位 | 卫计局，妇联，民政局，公安局，司法局 | 卫计局，妇联，公安局，庇护所 | 司法局、县妇联、公安局、民政局、卫计局 |

- 结果、成果和挑战

- 请问贵单位开展的反家暴项目，主要是针对哪些群体？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 遭受家暴的已婚妇女 | / | 2/4 | 1/5 |
| 遭受亲密关系暴力的未婚妇女 | / | / | / |
| 以上两个群体都是 | 5/5 | 2/4 | 4/5 |

- 从 2014年7月，二期项目实施以来，县级是否仍然存在反家暴多部门协调机制，各部门均指定反家暴联络人？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 5/5 | 4/4 | 5/5 |
| 否 | / | / | / |
| 无回答 | / | / | / |

- 多部门反家暴联络人开会的频率为

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 每月一次 | / | / | 4/5 |
| 每季度一次 | 5/5 | 4/4 | / |
| 半年一次 | / | / | / |
| 无固定时间,临时召集 | / | / | 1/5 |
| 其他，请说明 | / | 2/4 卫计：2016年至2017年5月共召开联系会议16次。 妇联：临时重要紧急事项 临时调度 | 县妇联：若有紧急案例，会临时召开 |

- 多部门反家暴联络人会议的主要目的是什么（如：信息共享、解决社区在提供服务过程中遇到的瓶颈、监督案例、后续跟踪）？

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 信息共享；共同探讨对受害者的干预方案。 |
| 妇联 | 通报近期家暴工作信息，分析当前 工作形式，针对工作中的问题寻找解决途径，了解转介案例处理结果和受暴者近况与处境。 |
| 民政局 | 研究反家暴工作存在的问题和困难。 |
| 公安局 | 研讨工作中的困难和问题，推动责任落实和部门合作联动 |
| 司法局 | 通过召开会议，加强多部门的协调配合 |
| 湖南宁乡 |  |
| 卫计局 | 以上都是 |
| 妇联 | 主要目的是解决涉及全县多部门合作反家暴工作中遇到的瓶颈和重要案例的研究与整顿 |
| 公安局 | 一是加强协调沟通解决存在的问题，二是落实反家暴各法律法规并用于实践，三是监督各部门工作进度的情况 |
| 庇护所 | 1 信息共享、发挥作用；2 解决难题，做好衔接；3 及时总结，后续跟踪。 |
| 甘肃靖远 |  |
| 公安局 | 一是研究反家暴工作的共性问题，二是解决个案案例的瓶颈问题，三是开展信息共享，对有关挑战提出解决方案 |
| 司法局 | 及时信息共享，讨论在工作过程中遇到的困难，对重要案例进行后续跟踪 |
| 县妇联 | 及时信息共享，讨论解决提供服务过程中遇到的困难，对重要案例监督、以及后续跟踪 |
| 民政局 | 1.信息共享，解决各部门提供服务过程中遇到的困难、难题、进行沟通，取得最好的解决方案2.对案件进行监督和后期的跟踪 |
| 卫计局 | 主要目的是：定期讨论、分析、研制、分享反家暴工作中的案例和经验，并提出下一阶段的工作措施，对上个月的受家暴者随访情况，对处理的结果做到信息共享。 |

- 县级是否由某一部门总体负责具体家暴案例的案例管理，以确保为家暴受害者提供的服务的及时性和连续性？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 若是，哪个部门？ | 5/5 县妇联 | 4/4 县妇联 | 1/5 县妇联 |
| 否 | / | / | 4/5 |
| 无回答 | / | / |  |

- 请为本地的反家暴多部门协调机制的运行情况打分（5分为最好）。

|  | 1 分 | 2 分 | 3 分 | 4 分 | 5 分 |
| --- | --- | --- | --- | --- | --- |
| 四川仪陇 | / | / | / | / | 5/5 |
| 湖南宁乡 | / | / | / | 2/4 | 2/4 |
| 甘肃靖远 | / | / | / | 3/5 | 2/5 |

- 请简要描述二期项目中，贵单位与其他相关部门之间，反家暴多部门协调机制的成立过程和运作情况。

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 县委政府成立领导小组，相关部门负责人为成员，领导小组下设办公室，在妇联，办公室负责人综合协调反家暴工作，组织召开协商会，互通案件信息。 |
| 妇联 | 从县委、政府的名义出台了一系列反家暴规范性文件并且成立了以县委、县政府领导为正副组长、相关部门负责人为成员的领导小组。领导小组下设办公室，办公室设在妇联。办公室负责综合协调多部门之间工作、互通信息，配合相关部门协同处理。 |
| 民政局 | 以县委政府的名义，出台了一系列反家暴文件，并成立了县委政府分管领导小组组长，相关部门为小组成员，设办公室在妇联，负责综合协调工作，并召开了协调会，互通案件信息，并配合相关部门协调处理。 |
| 公安局 | 县妇联牵头，县委政府制定出台一系列制度文件，我局按照职责要求，建立反家暴工作机制，开展业务培训，与其他部门协同开展宣传预防，矛盾排查化解，警情处置，以受害者为中心的救助维权，定期通报情况，与法院、妇联发布了告诫制度实施办法，依法打击违法犯罪行为。 |
| 司法局 | 县政府出台了一系列文件，成立了领导小组，召开了专题会议。 |
| 湖南宁乡 |  |
| 卫计局 | 1、接受家人、110处警、妇联、庇护所等多部门转介来的受害人；2、转介给家人、110处警、妇联、庇护所等已经康复的受暴者。 |
| 妇联 | 在县领导的统一调度和安排下，建立了县级多部门合作反家暴的工作机制，形成明确了各部门固定的职责，部门之间建立了畅通的转介机制。 在项目的运行过程中，各部门将反家暴工作职能向下级延伸，基层以乡镇和社区（村）为单位，也形成了基层多部门的工作机制，以方便服务受暴妇女个案。 工作人员的反家暴知识与反家暴工作方法都有了很大程度的提高。最主要的是受暴妇女及群众的反家暴常识越来越强，许多多年遭受家暴的老年妇女都纷纷发出声音寻求帮助。 |
| 公安局 | 具体情况如下：如发生一起家暴，在110指挥中心接到救助电话后，第一时间通知案件发生所在地的派出所，出警了解情况并请社区民警上门配合、协调解决问题并宣传相关法律法规，情况较为复杂或严重的，请所在地司法部门协调员出面共同完成协调工作，及时控制事情发生的变化并将其纳入重点上门对象，至少每个季度上门一次，有案件发生的半年内进行每月上门一次了解具体情况。 |
| 庇护所 | 1、召开联席会议，明确第二期项目部门工作任务和职责。2、开展业务培训，组织庇护所负责人和各乡镇民政工作负责人参加专业培训，听取联合国、全国妇联、省市妇联等相关专家授课，学习“五步法”实际操作技能。3、反庇所开展工作人员业务培训，实际操作运用“五步法”成果用于工作实践。 |
| 甘肃靖远 |  |
| 卫计局 | 反家暴二期项目启动实施，卫计局与妇联、公安、检察院、民政、司法、法院等部门对反家暴工作有了全新认识，积极主动开展工作，创新建立了“五中心”联动维权工作机制：依托县公安局110指挥中心建立了110投诉中心、伤情司法鉴定中心，依托县司法局建立了法律援助中心，依托县民政局建立了庇护中心，依托县妇联建立了心理安抚中心。建立了以危险评估为基础的转介制度来实现5个中心之间的合作和家暴干预工作，以整体的干预总结流程和各部门的工作流程来实施反家暴工作。 |
| 公安局 | 在妇联的统一协调之下，我单位和卫计局、民政局、司法局法律援助中心，法院等单位认真应对家庭暴力，对家庭暴力的报案、投诉积极干预，根据受害人的中心诉求开展转介，相互之间逐步形成了合作联动和协调机制。依托县公安局110指挥中心建成反家暴110投诉中心，依托县公安局司法鉴定中心建成反家暴伤情司法鉴定中心。依托县司法局法律援助中心建成靖远县妇女儿童法律援助中心，依托县民政局救助站建成反家暴庇护中心，依托县妇联办公室建立妇女儿童心理抚慰中心。“五中心”联动工作机制的建立，成为反家暴工作的有效途径，成为多部门合作反家暴的“靖远模式”。 |
| 司法局 | 与其他部门密切合作，在实践中积极探索“五中心”联动的反家暴模式，对在自己职权范围内的家暴案件，依法依程序以家暴受害者的需求为他们提供法律服务，对超出本部门职权范围的家暴案件，积极转介相关部门。 |
| 民政局 | 多部门联动，通过相关转介成为联络纽带，我们按照直接责任制的要求，对需要庇护的受暴者进行庇护，需要治疗的受害人转介至医疗机构开展伤情治疗；需要法律援助的也可以转介至法律援助中心提供法律咨询；对需要综合转介的，一般先向妇联转介，再由妇联开展转介。 成立过程：由妇联牵头、部门参与的管理模式，严格落实各自部门的工作职责和工作制度。 |
| 县妇联 | 二期项目开展以后，我单位及时反家暴成员单位沟通，成立领导小组，确保每个成员单位的反家暴工作有人管理，同时在各成员单位制定专门联络员，具体负责此项工作。在近几年的实践中，逐渐探索出“五中心”联动的反家暴模式，首先从“阻止暴力”、“伤情鉴定”、“法律讼诉”、“心理辅导”、“安全庇护”等重要环节入手，因为这是反家暴工作中能提供最重要的服务，受暴者可能最早求助的部门，通过这些重点部门带动其他部门，最终形成反家暴合力，达到共同防治家暴的目的。 |

- 多部门合作机制下，贵部门的主要职责是什么？

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 建立反家暴医疗干预中心，对家暴受害人提供医疗救治、心理疏导，医疗文件的书写，相关证据的收集与留存，对受害妇女进行综合评估，制定干预方案，根据受暴者需要，转介到其他部门，随访。 |
| 妇联 | 妇联职责：切实履行预防和制止家庭暴力工作领导小组办公室职责，牵头做好各成员单位综合协调工作，督导乡镇、县级相关部门开展反家暴工作。 |
| 民政局 | 民政局依托救助站为家庭暴力受害者提供临时性救助。 |
| 公安局 | 将家庭暴力报警纳入“110”接警工作范围，及时查处涉及家庭暴力的案件，协助法院执行人身保护令。 |
| 司法局 | 加强对家庭暴力的普法教育，为符合法律援助条件的受害人提供法律援助。 |
| 湖南宁乡 |  |
| 卫计局 | 1、及时有效地医治受害人身心，直至康复。2、保全受害人在医疗卫生部门就诊相关医疗文书，如门诊病历、住院病例、CT、彩超等检查结果、医疗证据，必要时描写人体图。3、及时准确地为受害人作出司法鉴定。4、履行强制报告制度。 |
| 妇联 | 牵头建立多部门合作机制，牵头组织多部门联席会议解决多部门合作运转中遇到的困难，干预服务部门借贷的家暴案。负责全县反家暴的宣传、培训。深入推动基层多部门反家暴工作机制的建立与完善。 |
| 公安局 | 根据公安机关职能职责，认真履行权利义务。报案后应及时出警，制止家庭暴力，按照有关规定调查取证，协助受害人就医鉴定伤情，及时固定证据。随后，根据公安职责和《反家庭暴力法》相关法律依法开展后续工作。 |
| 庇护所 | 反家暴庇护所工作职责：1、按法律法规规定，为受暴者提供有效临时性生活救助、法律援助及人性化帮助；2、热情接待家暴受害者，安工做程序做好处置及转介等工作；3、做好所内安全庇护、生活安排等；4、协助妇联等部门不断探索和完善反家暴工作方式方法 |
| 甘肃靖远 |  |
| 县妇联 | - 负责反家暴日常工作，指导协调各部门及家暴工作 - 设立家庭暴力投诉站，为家暴受害人提供必要救助，为家暴受害严重者协助申请人身安全保护令 - 积极开展反家暴宣传和培训工作 - 为家暴受害者提供心理抚慰 - 对各乡镇、县直单位的反家暴工作进行指导、考评 |
| 司法局 | - 指导人民调解组织调处家庭暴力纠纷，做好调解记录，调解文书制作及归档工作，对不能达成调解协议的，可以提示受害者向公安机关报案或向人民法院起诉 - 指导、协助有关部门开展反家暴普法宣传和培训 - 组织法律援助机构为符合条件的家暴受害者提供法律援助 |
| 公安局 | 一是接到报警及时处警 二是按照法律程序调查取证 三是协助受害人就医、鉴定伤情 四是通知民政部门安置弱势受害人 五是家庭暴力告诫并监督实施 |
| 卫计局 | - 在卫计系统做好宣传、动员，发放宣传资料 - 做好医务人员的培训 - 在各个医疗机构设立反家暴门诊 - 做好诊断记录及保存证据 - 按照《执业医师法》及《护士管理办法》保护患者隐私 |
| 民政局 | 五中心之一“庇护中心”，对外做好宣传、对内规范运行中心，为受暴者提供“类家庭”的环境，靖远县反家暴庇护中心是反家暴工作的后勤保障机构，其工作核心是为遭受家庭暴力后暂时无法回家居住的受暴者提供的临时庇护。 |

- 您是否认为多部门协调造成了协调困难、权责不清、程序更加繁琐？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | / | 1/4 | / |
| 否 如何避免的？ | 5/5 | 3/4 | 5/5 |
| 无回答 | / | / | / |

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 各部门职责分明，相互配合，通过培训提高了各部门工作人员的业务水平，通过反复合作，逐步探索，多部门合作体系和机制已日趋完善，联络人会议制度得到落实，各部门主动作为，积极作为。 |
| 妇联 | 各司其职，各尽其责，相互配合。 |
| 民政局 | 各司其职，各尽其责，相互配合。 |
| 公安局 | 各司其职,相互配合。 |
| 司法局 | 各司其职，各尽其责，相互配合。 |
| 湖南宁乡 |  |
| 卫计局 | / |
| 妇联 | 明确部门职责。观念上改变对家暴行为的认识，深刻感受家暴危害，重视反家暴工作，基层简化转介文书传递，使用灵活转介，县级部门不涉及法律证据文书也尽量简化。 |
| 公安局 | 这些问题相应存在，主要在于统筹和组织牵头部门对于多部门协调机制自身的权责分配认识不清，业务不熟悉，多部门协调运作，首先要强化各基层与单位自身认识。 |
| 庇护所 | 每个部门单位确定了协调负责人，确保联系畅通，转介及时，为受暴着提供必要周到和安全的庇护和帮助。 |
| 甘肃靖远 |  |
| 卫计局 | 1.县委、县政府高度重视2.各部门职责明确统一、清晰的工作流程3.靖远县反家暴“五中心”统一指挥，建立起了防范、救助、处理和打击家暴行为的多部门的合作模式4.每月召开一次联席会议 |
| 县妇联 | 我们探索出“五中心”联动的模式，就是为了应对家庭暴力工作中遇到的协调困难、程序繁琐等问题。各成员单位均指定一名反家暴联络员，负责做好反家暴工作的上传下达，信息推送等日常工作，同时“五中心”联动共同防治家暴，均指定专人负责家暴工作，这里的专人和联络员是同一个人。 |
| 民政局 | 各部门各司其职，以各部门的工作核心为准，为受暴者提供准确的要求，比如：庇护中心为受暴者提供“类家庭”的临时庇护场所，心理抚慰中心核心是为其提供心理康复咨询，法律援助中心为其提供法律咨询，伤情鉴定中心为其提供暴力后身体伤害的有力证据，110报警投诉中心则是第一时间受暴者选择的维权牵动，之间并不冲突，权责清楚。 |
| 公安局 | 多部门合作要固定人员，避免岗位变动导致工作衔接不够，合作者要有团队意识，以积极的工作态度开展工作 |
| 司法局 | 各部门均有一名反家暴联络员，负责做好反家暴工作的上传下达，信息报送等工作。 |

- 跟以前单一部门的反家暴行动相比，请简要描述反家暴多部门协调机制的主要优势。

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 1、有利于各部门间信息共享，提出一个最优化的干预方案，，让受暴者得到好的归属。2、制度化，规范化，专业化的模式为解决受暴者问题提供了强有力的保障。3、有利于建立家庭暴力的预防、干预、救助长效机制。 |
| 妇联 | 职责明确，流程规范，联动协调，紧密配合。 各部门通过转介能够弥补单个部门职能和责任的缺陷，为家暴者提供一站式服务，避免了对家暴者的二次伤害。 |
| 民政局 | 职责明确，流程规范，联动协调，紧密配合。 |
| 公安局 | 1、职责明确，各部门在职责范围内开展工作，避免陷入孤军奋战的困境。2、联动协调，弥补职能缺陷。如对受害人的伤情鉴定明确为卫生部门的职责，对受害人的临时庇护明确为政府部门的职责等。 |
| 司法局 | 各司其职，流程规范，各尽其责，相互配合。 |
| 湖南宁乡 |  |
| 卫计局 | 1、强化了部门间的协作，实现了从“单打独斗”到“联合作战”的转变；2、实现了从“推诿塞责”到“快速高效”的转变 |
| 妇联 | 部门职责明确，相互之间没有推诿现象发生，部门积极履职，容易形成帮助受害者的合力。部门共同参与，有利于反家暴社会氛围的形成。 |
| 公安局 | 反家暴是一个复杂工程，往往涉及报警、求助就医、伤情鉴定、人身安全权益保障和维护、法律援助等各个方面。应该需要多部门统筹、协调合作。另外，各部门协调机制在其他，很多国家已经有很丰富的运作经验，有很多国外方法可借鉴，结合中国的国情，这个机制如果运行有畅，应该会起到更加有效的协同和成效。 |
| 庇护所 | 1、可采取多种形式，广泛宣传家暴的危害性；2、开展多部门配合，为救助家暴者提供全方位的帮助和支持；3、开展多部门交叉联合培训，有利于实行家暴案例首问制接待要求；4、有利于织就反家暴社会网络，形成合力。 |
| 甘肃靖远 |  |
| 卫计局 | 跟单一部门的反家暴行动相比，反家暴多部门协作机构的主要优势是，能够形成合力，避免家暴受害人投诉之门，能够更好地以受害人需求为中心开展工作，家暴受害人的需求是多元的，单一部门的反家暴行动不能满足受害人多元的需求，只有形成多部门协作机构，才能更好的更快的为受害人提供良好的服务，多部门协调机构之间的相互转介，使受害人一次性投诉就能够得到多元化的服务，使受害人的需求能够多元化的满足，这是单一部门的反家暴行动所达不到的工作优势。 |
| 县妇联 | 部门之间的沟通加强了，尤其是加强了反家暴关键部门之间的联系沟通，促进了部门之间的信息共享，资源共享，各部门在做好本部门份内作用的同时，通过网上通报，电话联系，会议交流等形式，为每一起家暴案例提供全面及时的服务。 |
| 民政局 | 相比：反家暴多部门协调机制的主要优势，为受暴者提供的服务更全面化，更人性化，受暴者遭受伤害后“有家可回”、“有法可依”、“有冤可诉”、真正的维护自己的合法权益免受侵犯，让制造家暴的人受到应有的惩罚。 |
| 公安局 | 单一部门的反家暴行动相比，反家暴多部门协调机构的主要优势是：能够形成合力，避免家暴受害人投诉无门，能够更好地以受害人需求为中心开展工作，家暴受害人的需求是多元的，单一部门的反家暴行动不能满足受害人多类的需求，只有形成多部门协调机构，才能更好的更快捷的为受害人提供良好的服务，多部门协调机制之间的相互转介，使受害人一次投诉就能够得到多元的服务。使受害人的需求能够最大限度的满足，这是单一部门的反家暴行动达到的工作优势。 |
| 司法局 | 各部门在做好本部门职权内工作的同时，通过网上通报电话，微信联系，会议交流等形式，加强沟通，促进资源共享，保证为家暴受害者提供全面及时的服务。 |

- 请简要描述反家暴多部门协调机制遇到的主要挑战

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 1、各部门事多人少，基层反家庭暴力骨干严重缺乏。2、各部门与专项经费用于反家暴工作。 |
| 妇联 | 专业人员缺乏，经费紧张，且缺乏专门从事反家暴工作的机构，有时会出现换人断档的现象。 |
| 民政局 | 人员不够，经费紧张。各部部门无专业人员，缺乏专门专职机构。 |
| 公安局 | 缺乏专职的人员和机构开展专门的工作，基层缺乏相关阵地建设和人员，如救助站，一线警员少，压力巨大。 |
| 司法局 | 缺乏专职人员和专门机构。 |
| 湖南宁乡 |  |
| 卫计局 | 1、受害人不主动求治，甚至反复，证据难以保全；2、同居型受害人不愿意保全证据，甚至提供虚假证据；3、救治过程中，医疗服务经常缺乏合适的陪护人员。 |
| 妇联 | 1、工作量大。妇联与各部门特别是公安与法院原有工作量很大。随着群众维权意识的提高，各部门的工作量显著增加，人手紧导致服务不能达到最理想的效果。2、观念转变难，工作人员与受害人的观念对于受害人走出行动起着很重要的作用，而工作中这部分人观念的转变还是需要比较长的时间。3、救助手段有限，支持资源相对不够。 |
| 公安局 | 反家暴工作宁乡一直以来走在全国前列，总结的“五步法”更是具体而实用。“五步法”具体包括“鼓励受害人诉出实情”——引导受害人收集证据——引导受害人学会向援助机构求助——引导受害人学会相关法律法规——引导受害人建立危险评估意识等。五个环节对于各部门协调机制中主要挑战是多部门的责任分工，责任分工更为具体才能更进一步提高效率。在宣传法律法规的方面，多部门可同时发动，亦可采取专场的形式由妇联牵头组织，先从政府、大型企业开始。所有宣传中，宣传法律法规尤为重要，它整个家暴的核心问题，而在整个的反家暴的工作中，各部门的责任是关键。公安机关日常工作量较大，每次发生家庭暴力的事件后，得分大量的时间和精力在宣传法律法规和找解决问题的方法。如在发生家暴事件后，明确各部门责任及时移交专业部门，更能提高办事效率，遏制事件进一步恶化。 |
| 庇护所 | 我认为，目前多部门协调机制遇到的主要挑战有：1、执法上应细化，更具操作性。取证的进行、举证责任的明确、家暴告诫书和人身保护的法律效果硬进一步确定。2、来自传统和社会观念的影响，“家丑不可外扬”、“清官难断家务事”、“民不举，官不究”等，尚需有效解决。 |
| 甘肃靖远 |  |
| 卫计局 | - 多部门协调机构中的部门还不够多，民众参与度还不够 - 培训和印刷宣传资料的经费保障问题 - 宣传力度不够大，知晓度有待于进一步提高 - 受传统观念的影响，受暴人在医疗机构就诊时不愿意说出实情 - 受害人的维权意识、法律观念淡薄 - 受暴人思想和受暴人家庭的思想变化不够，受暴人随时随地放弃公权力的干预 - 家庭成员之间的经济赔偿难以操作 - 多部门之间的信息共享问题 |
| 县妇联 | - 反家暴人员不够稳定，明确各部门联络员，岗位变动之后，短时间无法开展工作 - 需要一个部门从中协调，妇联多次协调，成立领导小组，领导此项目的开展，执行以及持续发展，但妇联的协调能力有限 - 熟人社会对反家暴工作的影响 |
| 民政局 | 1.家庭暴力的预防机制还不够健全，家庭暴力防治应当坚持“早期干预，预防为主”的原则，现行法律规定的家庭暴力预防机制不足，而多部门面临的更多的是遭受家暴后的受害者主动求助的，而那些家暴后不愿暴露和即将遭受伤害的人无法通过多部门的帮助来摆脱困境。 |
| 公安局 | 多部门机构松散始终困扰在我们左右，今天培训的骨干，明天在本单位的岗位就可能变动，这是我们经常遇到的难题。骨干人员不能持久稳定，长效机构基础不定。 部门之间的相互依靠成为工作的绊脚石，骨干人员工作积极性并不统一，消极思想变成了相互依靠，政出多门反而影响工作成效，需要一个强有力的协调机构。 |
| 司法局 | - 反家暴工作人员紧缺，有的部门工作人员兼职反家暴工作，存在力不从心的状况 - 需要一个部门从中协调 |

- 贵部门是否有记录家暴案例的信息数据库或体系？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 5/5 | 3/4 | 4/5 |
| 否 | / | 1/4 | 1/5 |
| 无回答 | / | / | / |

- 如果是，信息和数据是否有和其他部门分享？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 5/5 | 2/2 | 3/4 |
| 否 | / | 2/2 | 1/4 |
| 无回答 | / | / | / |

2）贵部门是否采取了任何措施，确保信息在需要的时候得到分享，并注意了保密和保护寻求帮助的人的隐私？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 4/5 | 4/4 | 4/4 |
| 否 | / | / | / |
| 无回答 | 1/5(妇联) | / | / |

（三）服务的质量

- 项目启动后，至今贵部门处理过的家暴案例数量。

| 四川仪陇 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 处理过的家暴案例数量 | 跟踪过的家暴案例数量 | 转介到其他部门的案例数量 |  | 从其他部门接到的转接案例数量 |  |
|  |  | 转介给的部门 | 案例数量 | 转介来自部门 | 案例数量 |
| 卫计局：66 | 62 | 妇联 | 25 | 妇联 | 45 |
|  |  | 公安 | / |  |  |
|  |  | 民政 | / |  |  |
| 妇联：134 | / | 公安 | 48 | 公安 | 19 |
|  |  | 医院 | 45 | 医院 | 25 |
|  |  | 司法 | 65 |  |  |
|  |  | 民政 | 8 |  |  |
| 民政局：33 | 22 | 司法 | 13 | 妇联 | 8 |
|  |  | 医院 |  |  |  |
| 公安局：/ | / | 妇联 | 19 | 妇联 | 48 |
| 湖南宁乡 |  |  |  |  |  |
| 处理过的家暴案例数量 | 跟踪过的家暴案例数量 | 转介到其他部门的案例数量 |  | 从其他部门接到的转接案例数量 |  |
|  |  | 转介给的部门 | 案例数量 | 转介来自部门 | 案例数量 |
| 卫计局：/ | / | 法院 | 8 | / | / |
|  |  | 律师事务所 | 5 | / | / |
|  |  | 妇联 | 17 | / | / |
|  |  | 司法所 | 25 | / | / |
|  |  | 综治办 | 11 | / | / |
|  |  | 劝解回家 | 15 | / | / |
| 妇联：502 | 426 | 公安 | 125 | 公安 | 5 |
|  |  | 司法 | 140 | 医院 | 28 |
|  |  | 法院 | 75 | 庇护所 | 13 |
|  |  | 庇护所 | 49 | / | / |
|  |  | 基层妇联 | 37 | / | / |
| 公安局:1537（近三年） | 1537 | 妇联 | 126 | 民政 | 165 |
|  |  |  |  | 妇联 |  |
|  |  |  |  | 法院等 |  |
| 庇护所:58 | 17 | 妇联 | 49 | 公安 | 11 |
|  |  | 司法 | 4 | 妇联 | 6 |
|  |  | 卫计 | 6 | / | / |
| 甘肃靖远 |  |  |  |  |  |
| 处理过的家暴案例数量 | 跟踪过的家暴案例数量 | 转介到其他部门的案例数量 |  | 从其他部门接到的转接案例数量 |  |
|  |  | 转介给的部门 | 案例数量 | 转介来自部门 | 案例数量 |
| 卫计局150 | 85 | 妇联 | 20 | 公安局 | 7 |
|  |  | 公安局 | 24 |  |  |
|  |  | 法律援助 | 79 |  |  |
|  |  | 民政局 | 22 |  |  |
| 县妇联150 | 130 | 卫生医疗机构 | 12 | 卫生医疗机构 | 5 |
|  |  | 公安部门 | 26 | 公安部门 | 7 |
|  |  | 司法部门 | 65 | 庇护中心 | 3 |
|  |  | 庇护中心 | 2 |  |  |
|  |  | 各乡镇妇联 | 25 |  |  |
| 民政局22 | 22 | 县妇联 | 3 | 靖远县中医院 | 1 |
|  |  | 妇联 | 3 | 县妇联 | 2 |
|  |  |  |  | 妇联 | 2 |
| 公安局225 | 46 | 妇联 | 7 | 妇联 | 26 |
| 司法局320 | 146 |  |  | 妇联 | 65 |

14. 贵部门是否有标准操作程序，来进行多部门预防和应对家庭暴力模式下向其他服务部门转介的工作（其他服务如：警察、医疗、法律）？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 5/5 | 4/4 | 5/5 |
| 否 | / | / | / |
| 无回答 | / | / | / |

- 如果是，工作人员是否接受了标准操作程序方面的培训？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 5/5 | 4/4 | 5/5 |
| 否 | / | / | / |
| 无回答 | / | / | / |

- 贵部门经常转介到的服务为：（可多选）

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 医疗服务 | 4/5 | 2/4 | 4/5 |
| 社会福利服务（如妇联） | 5/5 | 3/4 | 4/5 |
| 庇护所 | 5/5 | 2/4 | 3/5 |
| 法律服务 | 5/5 | 4/4 | 4/5 |
| 警察 | 4/5 | 3/4 | 4/5 |
| 其他( 请说明) | / | / | 公安局：民政救助机构 |

- 贵部门在为受暴妇女提供服务的时候，是否会与受暴妇女本人及其亲属开展参与式的交谈？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是（大概说话内容） | 5/5 | 4/4 | 5/5 |
| 否（大概说话内容） | / | / | / |
| 无回答 | / | / | / |

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 受暴者基本情况，疾病情况，向其提供法律等相关知识。 |
| 妇联 | 了解施暴者与受暴者的家庭状况，寻找利于受暴者的可用资源。 |
| 民政局 | / |
| 公安局 | 敢于依法维权，咨询服务，向施暴者予以教育惩戒。 |
| 司法局 | 教育、调解。 |
| 湖南宁乡 |  |
| 卫计局 | 您是怎么受的伤 是谁打了您 用什么打的您? |
| 妇联 | / |
| 公安局 | / |
| 庇护所 | 征求服务对象同意拟订帮扶内容；及时沟通，提供人性化服务 |
| 甘肃靖远 |  |
| 卫计局 | 1.了解家暴的原因2.以患者为中心，询问受害人的需求3.反家暴立法、家暴性质4.家暴的处理流程 |
| 县妇联 | - 首次家暴发生的时间？2.有什么不良生活习惯？3.有没有孩子看到？ 4.上一辈有没有家暴情况？5.以往受暴后，你是怎么做的，比如告诉父母、报警等 |
| 民政局 | 家暴产生的原因，受暴妇女的生活环境，经济，社会地位，家庭中和施暴者的关系 |
| 公安局 | 了解家暴的原因，了解受害人的需求 |
| 司法局 | - 第一次家暴在什么时间？ - 以往受暴后世如何做的？ |

- 您是否知道转介到某种服务时该找哪个部门、具体哪个科室、联系人是谁？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 5/5 | 4/4 | 5/5 |
| 否 | / | / | / |
| 无回答 | / | / | / |

18. 在为寻求帮助的家暴受害人提供连贯服务方面，贵部门应该发挥的作用和工作人员的责任是否明确？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 5/5 | 4/4 | 5/5 |
| 否 | / | / | / |
| 无回答 | / | / | / |

19. 贵部门采取了哪些措施，来保证能以友好的方式提供服务，使包括贫困妇女、少数民族妇女、残疾妇女、边远地区妇女在内的社区弱势群体能够获得服务？

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 1、加强了对各级保健机构的医务人员培训，提高了医务工作者的反家暴意识、能力及沟通技巧。2、县妇幼保健院落实各部门职责，对受暴者进行伤情鉴定、心理疏导、证据收集、随访等，一系列医疗干预，相关制度职责明确、规范，流程清晰，绿色通道畅通。3、根据受暴者综合评估情况，及时转介到妇联、民政、公安等部门，帮助受暴者寻求其他帮助。4、利用县乡村三级妇幼卫生工作服务网络，对贫困妇女等特殊人群进行重点关注。 |
| 妇联 | 1.开通12338维权热线（县内热线：0817-7229566）2.组建反家暴志愿工作队伍，覆盖医疗、法律、公安、民政和心理咨询等领域为受暴者提供尽可能接近的专业水平的服务。3.建立县乡村（社区）三级反家暴网络平台。4.建立反家暴和受暴对象互助微信（QQ）群。5.在有条件的地方设置心理咨询服务平台。 |
| 民政局 | 1、建立庇护场所，抽出专项资金，建立反家暴庇护中心，专业管护人员、医疗保健师，为受暴者提供临时庇护场所。2、与相关部门密切配合，为受暴人提供法律帮助，医疗救助和心理疏导。4、保障进驻庇护中心人员的人身安全。 |
| 公安局 | 建立了110报警平台，派出所报警电话全天24小时接警出警；加强与乡镇、村、社区配合，及时处置各类报警求助；严明了工作纪律，开展相应执法培训。 |
| 司法局 | 在各乡镇成立法律援助工作站，使辖区内弱势群体可以就近获得法律援助。 |
| 湖南宁乡 |  |
| 卫计局 | 1、送医送药下乡；2、对外伤型就诊妇女进行暴力筛查；3、建立健康体检档案；4、进行两癌普查 |
| 妇联 | 1、对社区弱势群体会给予一定金额的资金救济（200-400元）；2、帮助她们申请法律援助；3、安排志愿者进行一对一帮助。’ |
| 公安局 | 在县局的统筹组织下，我们近年来开展了“四心”服务，为社区弱势群众提供了力所能及的帮助。一，开展“放心”服务，协调劳务派遣部门，未就业苦难、家庭苦难人员“一站式”推动就业。二，开展“细心”服务，主动服务心理自卑、身体残疾的弱势群众。三，开展“热心”服务，深入社区，主动宣传法律知识，了解群众疾苦和诉求，积极帮助协调。四，开展“齐心”服务，与相关福利部门建立长期协调机制，搭建资源共享平台，整合社会力量，进行帮助。 |
| 庇护所 | 庇护所的工作做到以下方面保证有效地为受暴着提供友好服务。 1 明确工作职责，要求工作人员共同遵照执行。工作职责是：遵守法律，讲究方法，宣传政策，有效庇护；2 制定了“六不准”工作原则，六不准是：不准言语刺激；不准侵吞财务；不准盘问个人隐私；不准要求从事劳动；不准扣押申诉控告材料；不准阻挠亲属正常来访。3 以人为本，提供服务：接待受暴着，实行首问责任制，针对个体不同情况，提供亲情化『类家庭』服务。 |
| 甘肃靖远 |  |
| 卫计局 | - 在全县各医疗机构设反家暴门诊 - 先诊治后付费 - 首诊负责制 - 门诊大夫要与受暴的弱势群体以及其家属开展参与式交谈 - 根据经验评估量化后转介！维护受害人的合法权利 |
| 县妇联 | - 举办家长学校、母亲讲堂等活动深入各乡镇宣讲反家暴相关知识 - 成立反家暴联谊会，以妇女之家为活动阵地，引导妇女自主学习相关法律 - 举办妇女技能培训班，提高妇女就业、创业能力、提高家庭地位（妇女手工编织、妇女家政服务员、育婴员培训） - 积极落实妇女小额担保贷款政策，鼓励妇女创业就业，增加收入 |
| 民政局 | 庇护中心选择的位置较为隐蔽，更好的来保护受暴者的隐私；庇护中心的入住环境以暖色系设计为主，为她们提供“类家庭”的温馨港湾，消除她们的陌生环境的顾虑；中心工作人员热情大方，以受暴者为中心的工作态度，全心为其提供服务；来庇护中心后根据性别、民族、年龄进行分类分区救助 庇护中心的救助不分年龄、种族、身体健康状况、居住地偏远的因素，我们的核心是为所有遭受家暴后暂时无法回家的受害者提供的临时庇护。 |
| 公安局 | - 对社区民警开展培训，加强执法规范化和职业道德教育 - 出台《依法处置家庭暴力执法指引》规范以受害人需求为中心的工作方法 - 深入开展“五步法”工作指导，加强社区民警在执法家庭暴力中使用正确的方法 - 与妇联、医疗、民政和法律援助中心加强联系，确保弱势群体能在医疗机构“绿色通道”及时就医，获得免费的法律援助，获得必要的民政求助 |
| 司法局 | - 深入乡镇、村委会、居委会宣传反家暴知识 - 对来访的家暴受害者提供一对一咨询和法律服务 - 以家暴受害者为中心，为其提供法律服务 - 保护家暴受害者的隐私 |

- 如何进行改进，来保证服务能以更加友好、及时和连续的方式提供给寻求反家暴服务的人？

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 1、进一步加强业务培训，提高医务人员识别和加强家庭暴力的能力。2、进一步加强信息互通，增强联系频次，深入细致探讨受暴妇女的干预方案。 |
| 妇联 | 以受暴者为中心，站在受暴者的角度考虑问题，接纳受暴者对待事物的方式和态度，引导受暴者寻求自身可用资源和身边资源，并按家暴危害程度分。 |
| 民政局 | 1、加大救助资金的投入，扩大庇护所功能，加大救助力度。2、完善反家暴应急联动机制，密切配合相关部门开展联合救助，确保服务连续性、持久性。 |
| 公安局 | 强化教育培训，使一线民警充分理解家暴妇女的多重困境，以受害人为中心开展工作，不断提高处警民警的执法水平，职业道德水平。 |
| 司法局 | 加强反家暴援助案件的回访力度。 |
| 湖南宁乡 |  |
| 卫计局 | 1、体制保证；2、法律保证 |
| 妇联 | - 向社会购买服务，向社会机构为受害人提供全程的干预服务；2、建立更方便更有自尊感更多功能的为受暴者服务的庇护所；3、从法律上进一步细化对施暴人的惩戒。 |
| 公安局 | 对各部门进行专项考核，明确各部门具体职责，紧密联系，及时处理纠纷。 |
| 庇护所 | 1、注重保护受暴着隐私。我县反家暴庇护所设立城中心公园内，和治安乞讨人员管理的救助管理站在一起，隐蔽性做的不够，受暴者被视为受助对象有一种被歧视感，今后将尽力改进。2、专业工作人员不够。庇护所工作人员由救助站工作人员兼职，虽然对他们进行多次业务培训，但是能够有能力独自处置反家暴工作人员偏少。 |
| 甘肃靖远 |  |
| 卫计局 | - 定期或不定期对各医疗机构反家暴门诊医师进行培训 - 各医机构按月统计反家暴门诊人数 - 定期召开联席会议，信息共享 - 门诊医师做好详细地诊疗记录并保存 - 征求受害本人的志愿转介给相关部门 - 对受暴者提供力所能及的帮助 |
| 县妇联 | - 首先保证反家暴工作人员的专业性，更有专业知识 - 反家暴工作人员的稳定性 |
| 民政局 | 庇护中心工作制度的不断完善，工作人员进行及时的培训、学习、提高自身服务能力，一切以受暴者为核心的工作宗旨来要求自己，提高工作效率 |
| 公安局 | 确保反家暴骨干队伍的相对稳定 不断培训加强反家暴骨干的工作素质 各部门制定反家暴工作行动规范 各部门联动机制转介机制要更加健全 政府对反家暴工作的投入要持续加大 |
| 司法局 | - 扩大宣传的力度，尤其是青壮年男性人群 - 对社会家庭在进行法律知识培训的同时加强人伦道德的培训 |

- 地方能力建设

- 贵部门组织过的培训

| 四川仪陇 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 培训名称和内容 |  |  | 培训材料的制定 | 培训人数 |  |  | 提升比例 |
|  |  |  |  |  | 男 | 女 | 合计 |  |
| 卫计局 | 2015年第二季度，妇幼工作例会；反家暴医疗干预培训会 |  |  | 3次，沟通课件内容及培训方式，面对面沟通 | 125 | 56 | 181 | / |
|  | 2017年仪陇县举办妇女保健，儿童保健暨反家庭暴力业务培训班 |  |  | 2次，沟通课件内容，面对面沟通 | 138 | 22 | 160 | / |
| 妇联 | 2015年“促进反家暴法推广”多部门合作，优化培训 |  |  | / | 175 | 105 | 280 | / |
|  | 促进反家暴法，推广各部门合作模式，“仪陇培训者培训班” |  |  | / | 35 | 15 | 50 | / |
|  | 反家暴基层骨干培训班 |  |  | / | 40 | 30 | 70 | / |
|  | 反家暴妇联干部培训班 |  |  | / | 100 | / | 100 | / |
| 民政局 | 2011年《社会性别意识》《反家暴法律常识》 |  |  | / | 111 | 137 | 250 | 95% |
|  | 2011年多部门合作反家暴民政人员培训，参与式培训 |  |  | / | 77 | / | 77 | 95% |
|  | 2012《反家暴法律常识》《社会性别意识》 |  |  | / | 76 | 179 | 255 | 95% |
|  | 2012年《拓展民政服务职能，救助家暴受害者》 |  |  | / | 15 | 42 | 57 | 95% |
|  | 2015年打造家暴受害者庇护所的意义与作用 |  |  | / | 25 | 45 | 70 | 95% |
|  | 2016年《组织反家暴宣传，推广多部门合作模式》 |  |  | / | 50 | 31 | 81 | 95% |
| 公安 | 反家暴警情处置流程处置规范 |  |  | 1次，沟通教案及教学方式，面对面沟通 | 142 | 18 | 160 | 90%以上 |
| 司法 | / |  |  | / | / | / | / | / |
| 湖南宁乡 |  |  |  |  |  |  |  |  |
|  |  | 培训名称和内容 |  | 培训材料的制定 | 培训人数 |  |  | 认识提升参训人员比例 |
|  |  |  |  |  | 男 | 女 | 合计 |  |
| 卫计局 |  | / |  | / | / | / | / | / |
| 妇联 |  | 如何加强基层妇联信访的证据作用 |  | 1次，沟通教案，电话 |  |  | 50 | 100% |
|  |  | 反家暴工作者能力培训 |  | 2次，沟通教案及方式，电话、电邮 | 100 | 200 | 300 | 100% |
|  |  | 反家暴工作者社区倡导前培训 |  | 2次，沟通教案，电话、电邮 | 29 | 52 | 81 | 100% |
|  |  | 反家暴师资培训 |  | 3次，沟通教案，电话、电邮 | 3 | 48 | 51 | 100% |
|  |  | 反家暴基层社区培训 |  | 3次，电话 |  |  | 1000 | 70% |
| 公安局 |  | 反家暴行动座谈会 |  | 1次，电话沟通及教案教学方式 | 35 | 15 | 50 | 50% |
|  |  | 反家暴取证行动部署会 |  | 2次，电话沟通 | 20 | 33 | 53 | 85%明白怎样运用实践 |
| 庇护所 |  | 民政系统年轻干职工培训 |  | 电话沟通2次，针对民政职责任务进行集中培训 | 15 | 21 | 36 | 90% |
|  |  | 全县乡镇社会事务办公室培训 |  | 3次，集中培训，电话沟通 | 11 | 22 | 33 | 85% |
|  |  | 庇护所反家暴法培训 |  | 1次，集中培训，当面 | 2 | 6 | 8 | 100% |
| 甘肃靖远 |  |  |  |  |  |  |  |  |
|  |  | 培训名称和内容 | 培训材料的制定 |  | 培训人数 |  |  | 认识提升参训人员比例 |
|  |  |  |  |  | 男 | 女 | 合计 |  |
| 卫计局 |  | 多部门预防和反家庭暴力项目卫计系统培训班 | 是，三次面对面，一次电话 |  | 56 | 47 | 106 | 90% |
|  |  | 反家暴医疗项目干预培训班 | 是，面对面沟通3次 |  | 54 | 33 | 87 | 88% |
|  |  | 反家暴项目乡村两级医务人员培训班 | 是，面对面17次，电话5次 |  | 158 | 79 | 237 | 80% |
| 县妇联 |  | 2015多部门合作反家暴培训班 | 2次，电话沟通 |  |  |  | 150 | 80% |
|  |  | 2016多部门合作反家暴培训班（三次） | 3次，电话沟通 |  |  |  | 37 | 83% |
|  |  |  |  |  |  |  | 70 | 83% |
|  |  | 2017全市多部门反家暴培训班 |  |  |  |  | 52 | 85% |
| 民政局 |  | 民政系统反家庭暴力专题培训 | 2次沟通教案及教学方式 |  | 45 | 26 | 81 | 85% |
|  |  | 民政局反家暴知识讲座 | 3次沟通教学方式 |  | 40 | 28 | 68 | 89% |
| 公安局 |  | 社区民警反家暴培训 | 3次 |  | 15 | 176 | 191 | 80% |
|  |  | 派出所执法检查培训 | 12次 |  | 11 | 151 | 166 |  |
| 司法局 |  | 多部门合作反家暴培训（2015） |  |  |  |  |  |  |
|  |  | 多部门合作反家暴培训（2016） |  |  |  |  |  |  |
|  |  | 全市反家暴培训班（2017） |  |  |  |  |  |  |
|  |  | 司法所反家暴及调解员培训 |  |  |  |  | 200人 |  |

- 工作人员在本县开展恰当的家庭暴力预防和应对服务的能力。请填写和贵部门相关的内容。

| 试点医疗机构能够提供恰当的家庭暴力服务（包括常规检查和有效转介）的医务人员的数量： |  |
| --- | --- |
| 四川仪陇 | 卫计局：137 |
| 湖南宁乡 | 卫计局：300多 |
| 甘肃靖远 | 卫计局：221 县妇联：221 |
| 公安部门能够提供恰当的家庭暴力服务（包括有效监督和跟踪报警电话）的警员数量 |  |
| 四川仪陇 | 公安局：160 |
| 湖南宁乡 | 公安局：50 |
| 甘肃靖远 | 县妇联：191 公安局：191 |
| 妇联能够提供恰当的家庭暴力服务的工作人员数量 |  |
| 四川仪陇 | 妇联：300 |
| 湖南宁乡 | 妇联：435 |
| 甘肃靖远 | 县妇联：2 |
| 能够提供恰当的家庭暴力法律服务的法律工作者（如：法官、检察官、法律援助人员）的数量 |  |
| 四川仪陇 | 司法局：80 |
| 湖南宁乡 | / |
| 甘肃靖远 | 县妇联：7 司法局：2 |
| 能够有效传播家庭暴力关键信息的同伴教育员的数量 |  |
| 四川仪陇 | / |
| 湖南宁乡 | 妇联：48 |
| 甘肃靖远 | / |
| 家暴庇护所的数量、床位数（如：1，10） |  |
| 四川仪陇 | 妇联：2+流动庇护 民政局：8 |
| 湖南宁乡 | 庇护所：（1,5） |
| 甘肃靖远 | 县妇联：5 民政局：5 |
| 能够开展社区反家暴培训的培训师的数量 |  |
| 四川仪陇 | 妇联：15 公安局：36 |
| 湖南宁乡 | 妇联：10 卫计局：10 |
| 甘肃靖远 | 县妇联：6 公安局：1 |

（五）公众意识提升

- 贵部门是否在学校或社区，面向儿童开展过反家暴的宣传？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 4/5 | 4/4 | 5/5 |
| 否 | / | / | / |
| 无回答 | 1/5（民政） | / | / |

24. 贵部门在城镇和农村开展过的宣传活动：

| 四川仪陇 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 宣传活动名称和举办地 |  |  | 城镇 |  | 农村 |  | 宣传活动的形式 |  | 受益群体 |  | 直接受众人数 |
| 卫计局 | 妇幼保健院：反家暴咨询活动：新政镇朝天街口 |  |  | √ |  |  |  | 义诊 |  | 广大妇女儿童 |  | 872 |
|  | “拒绝家庭暴力，呵护美好生活”：三蛟镇，天山村 |  |  |  |  | √ |  | 反家暴教育，咨询活动 |  | 农村留守妇女儿童老人 |  | 156 |
|  | 反对家庭暴力共创和谐社会：双昷乡范围沟村 |  |  |  |  | √ |  | 健康教育讲座 |  | 农村留守妇女儿童老人 |  | 108 |
| 妇联 | 家暴立法，推广各部门合作宣传启动 |  |  |  |  | √ |  | 游街,文艺表演 |  | / |  | 13000 |
|  | 当地学校 |  |  |  |  | √ |  | 宣讲，文艺表演 |  | / |  | 1800 |
|  | 每年三八宣传活动 |  |  | √ |  | √ |  | 文艺表演，传单 |  | 学生、教师 |  | 3000 |
|  | 法律知识竞赛 |  |  | √ |  | √ |  | / |  | / |  | 900 |
| 民政 | 参加多部门合作预防应对仪式 |  |  | √ |  |  |  | 电视台 |  | / |  | 2000 |
|  | 没有家暴16日宣传 |  |  | √ |  | √ |  | 现场咨询 |  | / |  | 12000 |
|  | 反对家暴，人人有责：红色经典广场 |  |  | √ |  |  |  | 现场宣传 |  | / |  | 800 |
| 公安 | 法治讲座：学校 |  |  | √ |  |  |  | 大会宣讲 |  | 中小学生 |  | 3万 |
|  | 农民夜校：村委会 |  |  |  |  | √ |  | 座谈，宣讲 |  | 农村群众 |  | 10万 |
|  | 三八妇女节 |  |  | √ |  |  |  | 集中宣传 |  | 妇女儿童 |  | 1万 |
|  | “11.25”反家暴日 |  |  | √ |  |  |  | 集中宣传 |  | 妇女儿童 |  | 1万 |
|  | “12.4”宪法日 |  |  | √ |  |  |  | 集中宣传 |  | 妇女儿童 |  | 2万 |
| 湖南宁乡 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 宣传活动名称和举办地 | 城镇 |  | 农村 |  | 宣传活动的形式 |  | 受益群体 |  | 估计的直接受众人数 |  |
| 卫计局 |  | 2016.11.25 拒绝家庭暴力 呵护美好生活 | √ |  |  |  | 活动 |  |  |  | 1500人 |  |
| 县妇联 |  | 玉潭街道 | √ |  |  |  | 授课 |  | 社区工作者 |  | 80人 |  |
|  |  | 双江口村 |  |  | √ |  | 授课 |  | 社区工作者 |  | 50人 |  |
|  |  | 灰汤镇牛角湾村 |  |  | √ |  | 授课 |  | 群众 |  | 50人 |  |
|  |  | 双凫铺镇双桂村 |  |  | √ |  | 授课 |  | 群众 |  | 50人 |  |
|  |  | 灰汤镇镇政府 |  |  | √ |  | 宣传资料 |  | 群众 |  | 500人 |  |
|  |  | 玉潭镇人人乐广场 | √ |  |  |  | 宣传资料 |  | 群众 |  | 10000人 |  |
| 公安局 |  | “五位一体”宣传行动 4月25日 |  |  |  |  | 展台、发放资料 |  | 普通群众 |  | 3万余人 |  |
|  |  | “110日”宣传活动（玉潭）人人乐 1月10日 |  |  |  |  | 展台、发放资料 |  | 普通群众 |  | 5000余人 |  |
| 庇护所 |  | / | / |  | / |  | / |  | / |  | / |  |
| 甘肃靖远 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 宣传活动名称和举办地 | 城镇 |  | 农村 |  | 宣传活动的形式 |  | 受益群体 |  | 估计的直接受众人数 |  |
| 卫计局 |  | 反对家庭暴力，构建和谐社会（各乡镇文化广场） | × |  | √ |  | 发放宣传折叶、咨询 |  | 农村妇女儿童，参与活动的所有家庭 |  | 2.5万余人（18次） |  |
|  |  | 促进家庭和谐，维护社会稳定（广场、钟鼓楼） | √ |  | × |  | 发放宣传折页、咨询（面对面） |  | 农村及城镇妇女 |  | 6000余人 |  |
|  |  | 反家庭暴力知识讲法（职专礼堂） | √ |  | × |  | 讲座 |  | 干部职工 |  | 700余人 |  |
| 县妇联 |  | 反家暴宣传进校园 | √ |  | √ |  | 发放宣传材料、开办讲座、以案释法 |  | 学生、老师 |  | 4500余人 |  |
| 民政局 |  | 华富光彩小学反家暴知识进校园 | 刘川镇 |  | √ |  | 发放宣传材料 |  | 全体师生 |  | 150人 |  |
|  |  | 慈济小学反家暴知识进校园 | 刘川镇 |  | √ |  | 发放宣传材料 |  | 全体师生、家长 |  | 300人左右 |  |
| 公安局 |  | 法律“七进”宣传 | √ |  | √ |  | 进社区、进企业、进学校深入宣传 |  | 居民学生等 |  | 10万 |  |
|  |  | 国家宪法日宣传 | √ |  | √ |  | 发资料 |  | 居民 |  | 2万 |  |
|  |  | 每年法制宣传日宣传 | √ |  | √ |  | 搞咨询 |  | 居民 |  | 3万 |  |
|  |  | 反家暴专题宣传 | √ |  | √ |  | 展板、彩页发放 |  | 居民 |  | 5万 |  |
| 司法局 |  | 反家暴专门宣讲活动 | √ |  | √ |  | 发放宣传材料、开办讲座、法律咨询 |  | 妇女、老人、儿童 |  | 8000人 |  |

- 媒体对贵部门组织的宣传和其他活动的报道。

| 四川仪陇 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 媒体报道标题 | 报道日期 |  | 媒体名称 |  | 带来的影响 |
| 卫计局 | 珙县赴仪陇县参加反家暴培训班 | 2016.7.4 |  | 珙县新闻网 |  | 网友一致好评 |
| 妇联 | 四川省推广各部门合作反家暴“仪陇模式” | 2007.3.17 |  | 仪陇新闻网 |  | / |
|  | 反家暴“仪陇模式”获肯定 | 2107.3.17 |  | 四川法制报 |  | / |
|  | 全国妇联反家暴项目“仪陇模式”获肯定 | 2017.3.17 |  |  |  | / |
|  | 四川推广各部门合作家暴仪陇模式 |  |  | 人民日报 |  | / |
|  | 联合国多部门合作项目在仪陇启动 | 2011.11.24 |  | 南充日报 |  | 省市妇联领导讲话 |
|  | 联合国项目培训“反家暴”目的 | 2011.12.26 |  | 南充日报 |  | 省妇联领导讲话 |
| 公安 | / | / |  | / |  | / |
| 司法 | / | / |  | / |  | / |
| 湖南宁乡 |  |  |  |  |  |  |
|  | 媒体报道标题 | 报道日期 | 媒体名称 |  | 带来的影响 |  |
| 卫计局 | / | / | / |  | / |  |
| 县妇联 | 促进反家暴法推广多部门合作，宁乡市反家暴五步工作法获推广 | 4.18 | 央视网 |  | / |  |
|  | 促进反家暴法推广多部门合作，宁乡市反家暴五步工作法获推广 | 4.18 | 湖南卫视 |  | / |  |
|  | 敲黑板！遭遇家暴第一时间要做什么？记住这5步，很重要！ | 4.18 | 湘妹子 |  | / |  |
|  | 湖南各地学习宁乡反家暴模式“五步法”打通最后一公里 | 4.18 | 网易新闻 |  | / |  |
|  | 被软禁的女儿 | 2016.4.22 | 湖南公共频道 |  | 群众反响极好 |  |
| 公安局 | “五位一体”宣传成效显著 | 11月25日 | 宁乡公安微信公众号 |  | 公众积极留言 |  |
|  | 警花警草都在干什么？ | 1月10日 | 宁乡公安微信公众号 |  | 公众积极点赞留言 |  |
| 庇护所 | 宁乡县举行『11.25』周际消除对妇女暴力XXX工作者沙龙 | 2015.11.26 | 潇湘女性网 |  | 1促进了反家暴庇护工作制度建设 2提升了社会认知度 |  |
| 甘肃靖远 |  |  |  |  |  |  |
|  | 媒体报道标题 | 报道日期 | 媒体名称 |  | 带来的影响 |  |
| 民政局 | “五中心联动”反家暴接地气落实处 | 2017.3.29 | 中国妇女报 |  | 靖远反家暴实践在“二期推广会”上获好评 |  |
|  | 坚决向家庭暴力说“不” | 2017.3.8 | 法治甘肃网 |  |  |  |
|  | 甘肃靖远试点反家暴项目最佳实践系列 | 2017.5.31 | 联合国妇女署 |  |  |  |
|  | 临夏州妇联调研反家暴“靖远模式”座谈会 | 2017.5.25 | 靖远县妇联 |  | 营造了良好的社会氛围 |  |
|  | 不要暴力 爱的路上有我也有你 | 2017.4.14 | 白银市妇联 |  | 让学员们受益匪浅 |  |
| 县妇联 | “五中心联动”反家暴接地气落实处 | 2017.3.29 | 中国妇女报 |  | 靖远模式获好评，更多人知晓 |  |
|  | 陇上反家暴第一人焦向东 | 2017.5.8 | 华夏文明导报白银周刊 |  |  |  |
|  | 坚决向家庭暴力说“不” | 2017.3.8 | 法治甘肃网 |  |  |  |
|  | 点赞《中国妇女报》有刊登了反家暴“靖远模式”——以“受害人为中心”选择工作法 |  |  |  |  |  |
|  | “五心联动”甘肃靖远反家暴模式走向全国 | 2017.3.8 | 薛长明 |  | 更多人知道了靖远模式 |  |
|  | 不要暴力 爱的路上有我也有你 | 2017.4.14 |  |  |  |  |
|  | 反家暴 维权益 靖远为妇女撑起保护伞 | 2017.4.24 |  |  |  |  |
| 卫计局 | 坚决向家庭暴力说“不” | 2017.3.8 | 法治甘肃网 |  |  |  |
|  | 健康社会 幸福家庭 | 2017.5.15 | 甘肃健康教育 |  |  |  |
|  | “五中心联动”反家暴接地气落实处 | 2017.3.29 | 中国妇女报 |  |  |  |
|  | 健康家庭 健康中国 | 2017.4.7 | 靖远电视台 |  |  |  |
| 公安局 | 主动担当显品质，勇于奉献创佳绩 | 2016.6 | 甘肃妇女 |  |  |  |
|  | 陇上反家暴第一人焦向东 | 2017.5.8 | 华夏文明导报 |  | 阅读5.2万次 |  |
|  | “五心联动”反家暴模式获全国妇联、联合国妇女署肯定 | 2017.4.11 | 兰州晚报 |  |  |  |
|  | 让正义的法槌包含温度 | 2017.5.15 | 白银晚报 |  |  |  |
| 司法局 | 坚决向家庭暴力说“不” | 2017.3.8 | 法治甘肃网 |  |  |  |
|  | “五心联动”甘肃靖远反家暴模式走向全国 | 2017.3.8 | 薛长明 |  | 更多人知道了靖远模式 |  |
|  | “五中心联动”反家暴接地气落实处 | 2017.3.29 | 中国妇女报 |  | 靖远模式走向全国 |  |

- 贵部门制作分发的宣传教育材料的数量

| 四川仪陇 |  |  |  |
| --- | --- | --- | --- |
|  | 宣传材料标题 | 份数 | 在何地、如何分发 |
| 卫计局 | 妇女法律服务手册 | 6000 | 医院门诊现场分发或自取 |
|  | 反家庭暴力，建幸福家庭，构和谐社会 | 5000 | 医院门诊，现场分发 |
| 妇联 | 反家暴宣传袋 | 15000 | / |
|  | 反家暴宣传折页 | 10000 | / |
|  | 反家暴年历 | 300 | / |
|  | 反家暴倡议书 | 10000 | / |
|  | 反家暴画板 | 3000 | / |
| 民政局 | 反家暴庇护中心总做制度宣传单 | 800 | 广场 |
|  | 反家暴庇护工作流程宣传栏 | 20 | 人口密集地等 |
|  | 全国妇联制作的宣传、台历等 | / | / |
|  | 反家暴民政庇护宣传海报 | 700 | / |
| 公安局 | 构建和谐反对家暴宣传折页 | 10万 | 城镇社区，农村乡镇，街道和派出所 |
| 司法局 | 农村实用法律读本 | 10万 | 各村或居委会 |
|  | 法律服务便民卡 | 2万 | 各乡镇 |
| 湖南宁乡 |  |  |  |
|  | 宣传材料标题 | 份数 | 在何地、如何分发 |
| 卫计局 | / | / | / |
| 县妇联 | 宣传《反家庭暴力法》 | 10000 | 乡镇 |
|  | 拒绝家庭暴力 呵护美好生活 礼品 | 3000 | 人人乐广场 |
|  | 维护妇女合法权益 促进男女性别平等 礼品 | 5000 | 人人乐广场 |
|  | 《反家暴法》折页 | 20000 | 人人乐广场 大润发广场 基层政府 |
|  | 遭遇家暴怎么办微电影 |  | 多部门微信公众号 |
|  | 宁乡妇联告诉你 遭遇家暴怎么办 |  | 多部门微信公众号 |
|  | 宁乡县反家暴多机构联系方式 | 2000 | 各部门分发 |
| 公安局 | 家暴相关法律法规 | 2000 | 城区及各大乡镇 |
|  | 反家暴流程和评估细则 | 3000 | 城区及各大乡镇 |
| 庇护所 | 宁乡县反家暴庇护所工作制度（便民公约） | 10000张 | 宣传册分发，平时兄弟县市交流派送，乡镇街道村社区下发 |
|  | 宁乡县就住管理站工作规程（内含反家暴法） | 1500份 | 2016年5月印发 途径如 上 |
| 甘肃靖远 |  |  |  |
|  | 宣传材料标题 | 份数 | 在何地、如何分发 |
| 卫计局 | 向家庭暴力说“不” |  | 钟鼓楼前 |
|  | 反对家庭暴力 促进社会和谐 |  | 会州广场 |
|  | 健康生育相关宣传资料 | 30余万份 | 各乡镇文化广场 各村卫生室向居民分放 |
| 县妇联 | 向家庭暴力说“不” | 1000份 | 钟鼓楼广场向市民分发 |
|  | 中华人民共和国反家庭暴力法 | 20000份 | 靖远县会州广场 靖远二中、一中、靖远八中 |
|  | 反家暴折页 | 20000份 | 各乡镇妇女之家 |
|  | 《中华人民共和国反家庭暴力法》释义及简明读本 | 100本 | 2016年6月、7月培训会教材 |
| 民政局 | 坚决向家庭暴力说“不” | 2000份 | 在县城钟鼓楼前组织工作人员向群众分发 |
|  | 庇护中心——家一样的温馨港湾 | 2500份 | 人民广场向群众宣传并发放 |
|  | 远离家庭暴力——构建和谐社会 | 4000份 | 靖远二中向学生发放 |
| 公安局 | 《反家庭暴力法》宣传材料 | 2万份 | 各乡镇派出所分发 |
|  | 促进家庭和谐 维护社会稳定（展板） | 2个 | 县局长期展板 |
|  | 反对家庭暴力 构建和谐社会（展板） |  |  |
|  | 反对家庭暴力、构建和谐社会宣传折页 | 2000份 | 各种活动分发 |
| 司法局 | 《中华人民共和国反家暴法》 | 1000份 | 钟鼓楼广场 |
|  | 《反家暴法》释义及简明读本 | 1000份 | 钟鼓楼广场 |
|  | 法律援助宣传手册 | 10000份 | 钟鼓楼广场 法律服务大厅 |

（六）地方承诺

- 如果您了解在项目实施期间（2014年7月至2017年7月）有公共资金投入支持项目目标，请提供信息：

| 四川仪陇 |  |  |  |
| --- | --- | --- | --- |
|  |  | 投入（人民币） | 实物或人力投入（请具体说明） |
| 卫计委 | 中央政府 | / | / |
|  | 省政府 | / | / |
|  | 县政府 | / | / |
|  | 部门 | / | / |
|  | 其他 | / | / |
| 妇联 | 中央政府 | / | / |
|  | 省政府 | / | / |
|  | 县政府 | / | / |
|  | 部门 | / | / |
|  | 其他 | / | / |
| 民政局 | 中央政府 | / | / |
|  | 省政府 | / | / |
|  | 县政府 | / | / |
|  | 部门 | 8900 | 解决受暴者庇护所饮食住宿 |
|  | 其他 | / | / |
| 公安局 | 中央政府 | / | / |
|  | 省政府 | / | / |
|  | 县政府 | / | / |
|  | 部门 | / | 大量人力用于家暴警情处置、纠纷调解和案件办理。 |
|  | 其他 | / | / |
| 司法局 | 中央政府 | / | / |
|  | 省政府 | / | / |
|  | 县政府 | / | / |
|  | 部门 | / | / |
|  | 其他 | / | / |
| 湖南宁乡 |  |  |  |
|  |  | 投入（人民币） | 实物或人力投入（请具体说明） |
| 卫计局 | 中央政府 | / | / |
|  | 省政府 | / | / |
|  | 县政府 | / | / |
|  | 部门 | 30万 | 诊室、病房、培训、就诊培训、心理疏导 |
|  | 其他 | / | / |
| 县妇联 | 中央政府 | 306253 | / |
|  | 省政府 | / | / |
|  | 县政府 | 共计29338 | 本部门约有500人参与此项工作 |
|  | 部门 |  |  |
|  | 其他 | / | / |
| 公安局 | 中央政府 | / | / |
|  | 省政府 | / | / |
|  | 县政府 | / | / |
|  | 部门 | 5万 | 制作宣传资料，救助 |
|  | 其他 | / | / |
| 庇护所 | 中央政府 | / | / |
|  | 省政府 | / | / |
|  | 县政府 | 10万-20万 | 财政配套资源用于庇护所建设 |
|  | 部门 | / | // |
|  | 其他 | / | / |
| 甘肃靖远 |  |  |  |
|  |  | 投入（人民币） | 实物或人力投入（请具体说明） |
| 卫计局 | 本部门 | 3万元 | 印刷宣传资料、人员培训 |
| 县妇联 | 中央政府 | 315357 | 宣传资料1万余份 |
|  | 省政府 | 10000 | 宣传资料1万余份 |
|  | 县政府 | 80000 |  |
| 民政局 | 本部门 | 50000 | 庇护中心住宿环境设施的配备，食物的供给 |
| 公安局 | / |  |  |
| 司法局 | / |  |  |

- 联合国二期项目将于2017年7月14日结束，贵部门是否计划继续支持多部门家庭暴力预防和应对活动？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 5/5 | 4/4 | 5/5 |
| 否 | / | / | / |
| 无回答 | / | / | / |

如果是：

- 是否有公共资金（县级和部门资金）投入支持继续开展家庭暴力预防和应对活动？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 估计能获得多少资金数量 | 2/5 (民政：10万) (公安：/) | 4/4 （卫计：15万/年） （妇联：10万） （庇护所：20万） （公安局：/） | 5/5 县妇联：每年1万元 民政局：5万元 公安局：3万元 司法局：每年1万元 |
| 否 | 2/5 | / |  |
| 无回答 | 1/5 | / |  |

- 这些资金将会支持哪些活动？

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | / |
| 妇联 | / |
| 民政局 | 反家暴先传活动，受保人庇护生活、社会救济，医疗救助 |
| 公安局 | 宣传、救助、工作经费 |
| 司法局 | / |
| 湖南宁乡 |  |
| 卫计局 | 1 单独设置诊室及病房 2进行反家暴专项医治培训 3建立数据库、大数据处理家暴 |
| 妇联 | 反家暴法的宣传 反家暴工作人员的继续培训 反家暴工作中对受害人服务的环节（如救助如个案服务向购买社会服务转变） |
| 公安局 | 有利于反家暴 |
| 庇护所 | 1 反家暴庇护所设施设备完善； 2 工作的正常开展 3 工作人员培训和部门间交流合作 4 引进社工组织提供专业服务 5 印制宣传资料 |
| 甘肃靖远 |  |
| 卫计局 | - 制作宣传资料 - 培训各医疗机构反家暴门诊医务人员 - 举行反家暴知识宣传、讲座等活动 |
| 县妇联 | - 人员培训 - 用于宣传 |
| 民政局 | 改善庇护中心受暴人员的居住条件，提高食物供给，提高工作人员办公设施条件，构建庇护网络系统的运营机制、实现多部门信息资源的共享 |
| 公安局 | - 开展反家暴“靖远模式”宣讲活动 - 印刷反家暴宣传材料、开展宣传 - 建立多部门联动网络工作机制 |
| 司法局 | 人员培训、宣传 |

- 项目活动在何种程度上融入了贵部门的常规工作？

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 卫计局将反家暴工作纳入到个下属单位年度绩效考核范畴，各单位将此项纳入内部日常工作开展。 |
| 妇联 | 该项目实施以来，一直作为妇联维权发展工作的重要组成部分，并作为维权工作重点进行日常化管理，纳入单位、科室年度目标考核。 |
| 民政局 | 项目活动在很大程度上融入了民政社会救助工作中。 |
| 公安局 | 提高了全体民警的反家暴意识，反家暴工作已成为“110”与派出所接警处境的日常性工作，将反家暴的能力培训、制度建设纳入工作计划，反家暴工作的信息共享与统计工作的稳步推进。 |
| 司法局 | 主要是与法律援助和法制宣传相结合。 |
| 湖南宁乡 |  |
| 卫计局 | 非常融入 |
| 县妇联 | 各项活动已完全融入了妇联的常规工作 |
| 公安局 | 融入了警察日常工作，形成了反家暴工作流程，并进行考核，在机构设立了家暴投诉点，明确专人负责。 |
| 庇护所 | 1 成为救助站三大板块工作之一（流浪乞讨人员救助管理、流浪未成年人救助保护、反家暴庇护救助）。2 形成了一整套切实可行的工作制度和操作规程。3 部门联动协调机制较有力，庇护所有专业工作人员提供服务。 |
| 甘肃靖远 |  |
| 卫计局 | 救死扶伤是我们医疗卫生系统义不容辞的责任，《执业医师法》《护士管理办法》都明确规定医务人员在执业活动中要关心、爱护、尊重患者和保护患者隐私，不得泄露，以及诊疗记录都有明确规定，这与反家暴多部门协调机构工作中心的职责相辅相成。项目活动完全（或者说基本上）融入了卫生计生部门的常规工作。 |
| 县妇联 | 将家暴工作列入专项工作、指定专人负责 |
| 民政局 | 提高了部门的反家暴服务能力，实现了多部门都是首责部门的共识，将家暴服务工作做到实处。 |
| 公安局 | 矛盾纠纷化解和平安建设是公安机关义不容辞的工作，反家暴工作是矛盾化解和平安社会建设重要的部分，依法开展告诫是预防和制止家暴有效的方式。这些工作已经融入了公安机关的常规工作，且已经成为基本工作的一部分。 |
| 司法局 | 将家暴工作列入专项工作，指定专人负责 |

- 现有的反家暴法规是否为贵县实施多部门家庭暴力预防和应对模式提供了足够的基础？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 3/5 | 4/4 | 5/5 |
| 否 | 2/5(民政、司法) | / | / |
| 无回答 | / | / | / |

（七）良好实践和教训

31. 请描述一个 2014 年 7 月项目实施以来，显示贵县多部门家庭暴力预防和应对模式发挥了作用的家暴事件。请提供事件经过、哪些部门或组织介入处理、有何作为及结果是什么。从该事件中得到了哪些经验和教训，比如，什么因素带来了积极的结果，家庭暴力预防和应对模式中哪些部分可以再加强改进？请对今后需要改变的方面提出建议。

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 曾有一例由县妇联首先接诊的受暴妇女，携带一幼女，丈夫不在身边，经验伤诊断为“多处软组织损伤”，比全面了解情况后进行评估，充分尊重受暴妇女意愿，转介到县妇联，在县妇联介入后分别联系到新政派出所，且救助管理站，分别提供了人身保护和住宿场所，最后在县法律援助中心，根据受暴妇女意愿下成功离婚。 正式由于多部门积极配合和及时干预，制定了合理干预方案，才使受暴妇女成功摆脱受暴环境。 建议：增加各级财政的专项投入。 |
| 妇联 | 案例：2016年5月 陕西妇女阿荣被家暴案 经过：阿荣多年前被拐卖到仪陇阿柴家，因担心女子不愿与自己生活，多次对阿荣实施家暴。致2016年5月阿荣逃至妇联、公安求助。妇联接案后首先登记案件详情，并根据阿荣要求分别转接至：民政（临时庇护）、医院（检查问诊）、公安（调查案件经过，寻找阿荣家，还其真实身份）、司法（提供法律援助）、乡村（提供相关信息，配合相关部门办案）。 结果：阿荣还原真实身份，解除无效婚姻，回山西娘家。 感受：是多部门合作反家暴力量和社会力量在赣榆反家暴中的重要作用 |
| 民政局 | 2016年4月21日，我县某乡十一村三组妇女郭某，因被拐和长期家暴来到妇联申诉，由县妇联转介到庇护中心，临时救助，在庇护期间，我们耐心询问当事人家庭情况，安抚受暴妇女的情绪，联合公安机关对其进行法律援助。 |
| 公安局 | 2014年11月14日13时许，我局110接到报警，在金城镇南街王的盛宴内有人打架，金城派出所民警接110指令后立即赶赴现场，发现一年轻女子倒在地上，地上有鲜血，处置民警立即控制现场，协助120抢救伤员，开展调查。经查受害人李某是嫌疑人袁某的前妻，两人于9月30日协议离婚，袁某一直心存不满，于当日携带刀具将李某面部和颈部划伤。案发后，我局立案侦查，袁某被刑事拘留。妇联介入对受害人进行心理辅导，以后工作中需进一步加强宣传教育，基层组织开展预防工作。 |
| 司法局 | / |
| 湖南宁乡 |  |
| 卫计局 | 2016年11月，水晶丽城小区周某遭丈夫殴打入住宁中医院，为固定证据链，接诊医生上报，在县妇联周建新主席协调下，110处警调取监控，通过询证当事人（周某丈夫）及邻居，为周某重新填写了出警记录，固定了证据链作出了积极贡献。 |
| 县妇联 | 2016年12月底我县廖某因遭受继子的家暴受伤，躺在床上一个星期无人照顾，拨打110，警察出警做好了登记送她去医院治疗，同时发出伤情鉴定信，廖某伤情鉴定为轻伤二级。此时廖某丈夫向她提出了离婚诉讼。廖某在被田易斧子赶出家门，找到县妇联，妇联鉴定案情之后，转介法律援助中心应对离婚诉讼，指导她去检察院就她继子对她的家暴行为提起诉讼。离婚案件开庭后，被调解达成协议，继子赔偿廖某医药费68000元，夫妇达成和解，以保障征收在即的廖某的权益，廖某向继子发出谅解书。 警察、妇联、司法、法院、检察院都为保障廖某的权利作出的保护法定权益的工作及指导，最大程度上保护了廖某的权益。但最终与施暴者达成调解协议，应考虑到离婚后，廖某的土地权益保障受影响难以到位才做出了一定积极的让步。 |
| 公安局 | 2016年8月4日，宁乡县双凫铺村唐某因家庭纠纷，将其公公易某右手食指韧带切断，将其婆婆杨某颅骨砍裂、锁骨砍断。经法医鉴定，易某为轻微伤，杨某为轻伤二级。唐某虽否认违法事实，但公安、检察机关依法检查后，认为证据确凿，依据《刑法》和《刑事诉讼法》有关条款依法移送起诉。从此事件中我们得到了经验，家暴还需多部门合作，责任明确。 |
| 庇护所 | 横市镇妇女隆某，由于经历过一次车祸，精神受到刺激，有时生活中表现的精神恍惚，因此，丈夫经常为此虐待她。隆某经当地村委会介绍，自行来庇护所求助。工作人员从与隆某的交流中得知，隆某的弟弟小隆因隆某丈夫李某经常殴打其姐，表示一定要带着炸药找到姐夫与其拼命。洪金文得知情况后，一方面安抚隆某，安排入住庇护所，另一方面将此情况转介给妇联及当地人民政府，分别找李某和小隆谈话，告知家暴是犯罪，以暴制暴违法，不能解决问题，经过多部门单位的共同努力，李某认识到错误，前来庇护所将妻子接回家后洪金文电话回访，双方已经和好。 启示：1 个案不同采取相应措施 2 多部门同理合作 3 从源头上预防和制止家暴 4 需要司法部门强力介入才能对施暴者行程威慑 5 庇护所除提供安全庇护，还要善于从受暴者方面找到解决问题的背后根源，及有效应对措施 |
| 甘肃靖远 |  |
| 卫计局 | 2016年6月10日，靖远县东湾镇的马某遭丈夫魏某的殴打致左腓骨骨折，派出所民警将受暴者送到县医院诊治，经X光显示左腓骨骨折，并对患者作了详细的诊疗记录，保存了影像检查光片；派出所民警将情况转介到县妇联，县妇联将情况转介给法律援助中心，律师免费为马某提供了法律咨询，经伤情鉴定中心鉴定（结合医院的诊疗记录），马某构成轻伤二级，民警征求马某同意，民警协同检察院作出不起诉处理，最后法院以故意伤害罪判魏某管制两年。 在这个案例中，公安、医疗机构、妇联、援助中心、检察院、法院等机构始终围绕以受害人的需求为中心开展工作，积极转介、协调，维护了受害人的合法权利，多部门协调获得了积极的结果。 |
| 县妇联 | 张红多年前因为家庭暴力而选择了离婚，但是离婚后并没有离家，而是和前夫一同抚养孩子。现在孩子已经成年，经济条件有所改善，前夫平时好逸恶劳，也玩小赌博，一旦赌输了就像张红要钱，遭到拒绝就会殴打她，2016年8月8日将张红打伤，前来求助。并威胁变卖张红的财产。县妇联详细了解案情并进行登记。同时转介至县妇幼保健院，为张红治疗，并保存伤情证据，村委会负责对此案情进行核实，并对其前夫进行批评教育。转介至刘川镇派出所，向其前夫发出告诫，转介至县司法局为张红提供法律援助，对张红的财产进行分割，事后回访再无暴力发生。 |
| 民政局 | 以二期项目实施以来三滩镇一家暴妇女（吴XX）为例 2017年，三滩镇吴XX妇女长期遭受家暴、精神失常、走投无路、准备跳黄河自尽，附近居民发现，及时拨叫三滩镇派出所，派出所民警出警，进行询问，为其备案，帮助其了解需求，及时转介于庇护中心，安全入住庇护中心，在其期间，庇护中心积极联系心理抚慰中心为其提供心理咨询，同时转介医疗机构，对其进行医治，转介于法律援助中心，为其提供婚姻关系上的法律服务，在长期的家暴中，吴XX产生了厌世的情绪，对婚姻关系产生了无望的心理，在抚慰期间，建议其起诉离婚，我们通过律师帮助受害人手机了有关证据，并通过细心细致的劝说，最终协商离婚。法庭上，男方对自己的行为终于有所悔悟，从此案件中，多部门的合作给我们的服务提供了全面性、及时性、应更多的拓宽深度和广度，将多部门的合作更为细致和周全。 |
| 公安局 | 2016年6月10日，靖远县东湾镇的马某遭受丈夫魏某殴打致左腓骨骨折，派出所将情况转介县妇联，县妇联将情况转介法律援助中心，律师免费为马某提供法律咨询，经鉴定马某构成“轻伤二级”，法制民警约见了马某征求意见，马某不希望司法机关处理魏某，法制民警协调检察院作不起诉处理，马某家人阻挠，检察院未做不起诉，审判阶段，马某出具了谅解书，法院以故意伤害罪判处魏某管制两年。 在这个案例中，公安、妇联、法律援助中心、检察院和法院等机构始终围绕受害人的需求为中心开展工作，积极转介，跟进协调，维护了受害人的合法权利。 |
| 司法局 | 2016年3月，由靖远县妇联转介而来的靖远县双龙中学教师王XX，因不堪忍受丈夫长期以来的家庭暴力而咨询，援助律师认真了解了受害者王XX的具体情况后，因其刚刚经历过暴力，于是引导其去医疗部门去进行诊断治疗，经受害者同意后，向医疗机构转介，王XX及时去医疗机构进行了诊断治疗，拍片并保留了相关证据。其后，王XX在法律援助中心律师的援助下，向法院提起离婚诉讼。 从该事件中可以看出，在反家暴案件中多部门合作更能形成合力。 |

- 贵部门是否曾参与将多部门合作的成功经验在其他地区进行推广？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 是 | 4/5 | 4/4 | 5/5 |
| 否 | / | / | / |
| 无回答 | 1/5 | / | / |

注：有三个县选择是，但是在之后的回答中，妇联虽然没有选择，可以分析出是进行了推广的。

- 如果是，在什么级别的地区推广：

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 省级 | 4/5 | 3/4 | 4/5 |
| 市级 | / | 2/4（其中庇护所既选了省级又选了市级） | 3/5 |
| 县级 | / | / | 2/5 |

- 如果是，请描述具体情况：

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | / |
| 妇联 | 反家暴“仪陇模式”在全国范围内推广，先到广元、乐山等地介绍方法、经验。 |
| 民政局 | / |
| 公安局 | 2017年3月，全国妇联，联合国妇女署在成都召开了反家暴二期培训项目四川省推广会，我局在会上发言。同月，我局反家暴工作经验材料被省公安厅、市公安局刊发。 |
| 司法局 | / |
| 湖南宁乡 |  |
| 卫计局 | / |
| 县妇联 | 2017年4月18日，全国妇联、联合国妇女署促进反家庭暴力立法，推广多部门合作模式项目湖南省推广会在长沙召开。省妇联、省公安厅、省民政厅、省卫计委、省政府与政协、湖南大学法学院，各市级妇联权益部部长、部分市州和县市区法院、公安、民政、司法、卫计以及我县相关部门负责人参加了会议，推广了我县项目经验，力争反家暴在湖南落地生根。 |
| 公安局 | 4月份，湖南省协作会在长沙召开。（全国妇联、联合国妇女署促进反家暴法推广多部门合作模式项目） |
| 庇护所 | 1参与甘肃靖远县交流座谈会 2 南京市妇联、岳麓区妇联来庇护所现场观摩 3 西安市多部门交流座谈会 4 长沙市反家暴就住庇护所经验介绍 |
| 甘肃靖远 |  |
| 卫计局 | 2017年2月21日，在兰州召开了家暴二期项目推广会，甘肃省妇联向全省推广了“靖远模式”，全国妇联、联合国妇女署向全国推广这一模式，全省14个市州妇联、公安、卫计、民政、司法等部门负责人参加。 |
| 县妇联 | 2017年2月21日，甘肃省召开全国妇联、联合国妇女署反家暴项目二期甘肃推广会 2017年4月8日，在靖远召开白银市多部门合作预防和制止家庭暴力维权干部培训班 2016年8月1日、8月2日、8月26日我县反家暴骨干焦向东分别在平川区、全宁县、景泰县做反家暴培训讲座。 |
| 民政局 | 1.2017年4.14 不要暴力 爱的路上有我也有你——白银市妇联举办多部门合作预防和制止家庭暴力维权干部培训班 2.2017年5.25临夏州妇联调研反家暴“靖远模式”座谈会 |
| 公安局 | 2017年2月21日，在兰州召开了反家暴二期项目推广会，甘肃省妇联向全省推广了“靖远”模式，全国妇联、联合国妇女署向全国推荐这一模式。全省14个地州市妇联、公安、民政、法院、卫计、司法部门负责人参加。 |
| 司法局 | 2017年2月21日 甘肃省召开全国妇联、联合国妇女署反家暴项目二期甘肃推广法 2017年4月8日 靖远召开白银市多部门合作预防和制止家庭暴力维权干部培训班 2016年8月1日、8月2日、8月26日我县反家暴骨干焦向东分别在平川区、全宁县、景泰县做反家暴培训讲座。 |

- 与一期项目相比，二期项目最大的特色和进展是什么？

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 1.领导更重视2.部门合作更紧密3.相关工作人员态度明显提高4.反家暴基层骨干和志愿者团队在壮大5.从事反家暴工作人员经验更丰富6.参与式的培训方式成效显著并得到广泛推广。 |
| 妇联 | 二期项目培训了地方培训者，并注重参与式的方式，特别是受暴对象的参与显得特别重要。另外，“五步干预法”为干预者提供了简便、高效的工作方法。 |
| 民政局 | 第一期：宣传倡导，能力提升； 第二期：反家暴立法，推动多部门合作。 |
| 公安局 | 制定了《反家暴法》。 |
| 司法局 | 程序简化，便民利民，各部门相互配合。 |
| 湖南宁乡 |  |
| 卫计局 | 1各部门职责更清 2各部门联动更快 |
| 县妇联 | 部分履职更积极、配合支持度更高 工作人员方法掌握得更全面 群众意识进步显著 |
| 公安局 | 多部门的职责更加明确。各机构反家暴的先进模式应用逐步形成。 |
| 庇护所 | - 创立了宁乡工作模式『五步法』，成为部门协调合作工作指南。 2、随着《反家暴法》出台，社会关注度越来越高，部门联动越来越受重视，越来越紧密 |
| 甘肃靖远 |  |
| 卫计局 | 尊重受害人的基本意愿，以受害人为中心开展工作，多部门联合，使受害人的身心得到抚慰，对施暴人给予行为和经济的两重惩罚。有多方的预防和判断家暴的发生；二期项目工作机制健全，工作流程清晰，职责明确、措施得力，以受害人为中心五步法、危险量化评估、转介等。 |
| 县妇联 | 各部门共同防治家暴，加强了各部门之间的联动。各部门各司其职，信息共享，预防和应对家庭暴力形成整体策略——部门联动，形成合力。 |
| 民政局 | - 拓广反家暴的深度和广度，提高了公众的认识率和知晓率，反家暴的服务能力更为周全 - 进展是《反家庭暴力法》的颁布实施，使反家暴工作有法可依，执法有据 |
| 公安局 | 最大的特色是加强了各级别的培训，特别是为试点地区培训了师资和骨干，使之能够开展培训 最大的进展是《反家庭暴力法》的颁布实施，可以说“促进反家庭暴力法宣传”的目标完成，使反家暴工作有法可依、执法有据 |
| 司法局 | 各部门共同防治家暴，加强了各部门之间的联动，各部门各司其职，信息共享、互相转介，部门联动，形成合力。 |

34. 与一期项目相比，二期项目面临的特殊挑战有哪些？

| 四川仪陇 |  |
| --- | --- |
| 卫计局 | 1.人员要求更高2.资金要求更大 |
| 妇联 | 《反家暴法》的颁布实施，现实的操作关键在于法律的执行者和相关部门，如何成立专门的反家暴工作机构，并提升执法者的执行力是值得思考的问题。县级法院在没有高层（如省院）关于反家暴法中人身保护令推行的相关文件通知，执行存在一定难度。 |
| 民政局 | / |
| 公安局 | / |
| 司法局 | 资金保障 |
| 湖南宁乡 |  |
| 卫计局 | 1未建立数据库。 2后续资金支持。 3相关工作人员相对固定 |
| 县妇联 | 受害人为主体的志愿者队伍成长困难 受害人回访接触率低 |
| 公安局 | 专项经费不足，支持力度需要加强，从事专项工作的人员素质和能力参差不齐。 |
| 庇护所 | 1 提升全社会对家暴行为的认识。 2 提高国家社会保障水平，对贫困家庭、贫困妇女等特殊弱势群体给予更多援助 |
| 甘肃靖远 |  |
| 卫计局 | - 多部门参与、加强部门之间合作 - 部门之间的转介效率 - 信息共享 - 经费保障 - 专业的团队 |
| 县妇联 | - 加强部门的合作 - 提高部门转介的效率 - 要有专业的团队来做此项工作 |
| 民政局 | - 如何将预防反家暴的能力适用于各个部门，将反家暴扼杀到萌芽状态 - 宣传不广——每次开展宣传，到场的大部分是老人和妇女，而真正施暴主体——中青年男性很少参加此类活动 - 形式不一，家庭暴力的种类较多，在维护受暴者的权利和义务时难以充分的得到保障 |
| 公安局 | 二期项目面临的特殊挑战是，《反家庭暴力法》实施后，受暴者投诉上升，但政府的救助机构和机制不够，仅有妇联、民政、司法、公安等部门的救助远远不够，在受暴者就业、增加收入、提高经济地位都需要政府加大救助，另外，冷暴力的干预机制仍然空白 |
| 司法局 | - 加强部门的合作 - 提高部门转介的效率 - 要有专业的团队来做此项工作 |

ANNEX 6: TRAINING SURVEY DATA

项目培训活动评估问卷调查

促进反家庭暴力立法，推广多部门合作模式（反家暴项目二期）

终期评估

- 基本情况

| 县 | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 工作部门 | 51 | 33 | 46 |
| 参与培训次数及日期 |  |  |  |

- 培训内容

1. 你目前的工作内容与反家暴的相关程度如何？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 紧密相关 | 17/51 | 16/33 | 14/46 |
| 部分相关 | 32/51 | 14/33 | 26/46 |
| 不太相关 | 0/51 | 2/33 | 6/46 |
| 基本不相关 | 2/51 | 0/33 | 0/46 |
| 无回答 | 0/51 | 1/33 | 0/46 |

2. 你参加的培训中用到的教材包括（可多选）

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 《预防和应对家庭暴力多部门合作工作手册》 | 49/51 | 29/33 | 40/46 |
| 《预防和应对家庭暴力警察工作手册》 | 17/51 | 10/33 | 16/46 |
| 《预防和应对家庭暴力“妇女之家”工作手册》 | 37/51 | 20/33 | 27/46 |
| 其他（请注明） ______________________________ | 0/51 | 1/33 （反家暴法） | 3/46 |
| 无回答 | 0/51 | 0/33 | 0/46 |

3. 通过参加培训， 你是否了解了家庭暴力的本质、形式、特点和产生的原因？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 非常了解 | 24/51 | 16/33 | 14/46 |
| 基本了解 | 15/51 | 14/33 | 27/46 |
| 部分了解 | 3/51 | 2/33 | 5/46 |
| 不太了解 | 0/51 | 0/33 | 0/46 |
| 不了解 | 0/51 | 0/33 | 0/46 |
| 无回答 | 0/51 | 1/33 | 0/46 |

4. 你认为下列哪个/哪些说法是正确的？（可多选）

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 家庭暴力的根本原因是制度与文化中的父权制以及两性间不平等的权力关系 | 38/51 | 26/33 | 39/46 |
| 家庭暴力是对女性人权的极大侵害 | 43/51 | 24/33 | 41/46 |
| 家庭暴力的施暴方和受暴方都有责任 | 25/51 | 11/33 | 5/46 |
| 家庭暴力是是可以通过女性努力维护男性的权益得到解决的 | 15/51 | 6/33 | 0/46 |
| 无回答 | 0/51 | 1/33 | 0/46 |

5. 通过参加培训，你在多大程度上了解了家庭暴力对受暴者、儿童、家庭、施暴者和社会的危害？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 非常了解 | 17/51 | 15/33 | 15/46 |
| 基本了解 | 30/51 | 15/33 | 27/46 |
| 部分了解 | 4/51 | 2/33 | 3/46 |
| 不太了解 | 0/51 | 0/33 | 1/46 |
| 不了解 | 0/51 | 0/33 | 0/46 |
| 无回答 | 0/51 | 1/33 | 0/46 |

6. 通过参加培训， 你在多大程度上了解了本部门在预防和制止家庭暴力方面的基本职责？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 非常了解 | 22/51 | 12/33 | 15/46 |
| 基本了解 | 15/51 | 19/33 | 21/46 |
| 部分了解 | 13/51 | 0/33 | 10/46 |
| 不太了解 | 1/51 | 1/33 | 0/46 |
| 不了解 | 0/51 | 0/33 | 0/46 |
| 无回答 | 0/51 | 1/33 | 0/46 |

7. 通过参加培训，你在多大程度上了解了本部门预防和制止家庭暴力的原则和工作流程？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 非常了解 | 13/51 | 14/33 | 11/46 |
| 基本了解 | 31/51 | 15/33 | 28/46 |
| 部分了解 | 5/51 | 2/33 | 7/46 |
| 不太了解 | 2/51 | 1/33 | 0/46 |
| 不了解 | 0/51 | 0/33 | 0/46 |
| 无回答 | 0/51 | 1/33 | 0/46 |

8. 培训中运用的案例在多大程度上贴合你的工作实际？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 非常贴合 | 25/51 | 13/33 | 12/46 |
| 基本贴合 | 12/51 | 14/33 | 15/46 |
| 部分贴合 | 13/51 | 5/33 | 15/46 |
| 不太贴合 | 1/51 | 0/33 | 4/46 |
| 不贴合 | 0/51 | 0/33 | 0/46 |
| 无回答 | 0/51 | 1/33 | 0/46 |

9. 培训中讲解的工作重点难点， 在多大程度上符合你的工作实际？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 非常符合 | 17/51 | 12/33 | 11/46 |
| 基本符合 | 20/51 | 12/33 | 21/46 |
| 部分符合 | 12/51 | 7/33 | 13/46 |
| 不太符合 | 2/51 | 1/33 | 1/46 |
| 不符合 | 0/51 | 0/33 | 0/46 |
| 无回答 | 0/51 | 1/33 | 0/46 |

10. 你认为受害妇女在服务过程中的参与重要吗？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 非常重要 | 48/51 | 22/33 | 20/46 |
| 重要 | 2/51 | 10/33 | 26/46 |
| 不太重要 | 0//51 | 0/33 | 0/46 |
| 不重要 | 0/51 | 0/33 | 0/46 |
| 无回答 | 1/51 | 1/33 | 0/46 |

11. 通过培训，你了解了哪些预防和制止家庭暴力的法律和政策？（可多选）

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 《宪法》节选 | 40/51 | 19/33 | 38/46 |
| 《婚姻法》节选 | 51/51 | 26/33 | 44/46 |
| 《妇女权益保障法》节选 | 51/51 | 29/33 | 44/46 |
| 《警察法》节选 | 17/51 | 11/33 | 18/46 |
| 《未成年人保护法》节选 | 42/51 | 22/33 | 38/46 |
| 《刑法》节选 | 40/51 | 20/33 | 38/46 |
| 《治安管理处罚法》节选 | 40/51 | 20/33 | 36/46 |
| 其他，请列举_________________ | 4/51 - 《中华人民共和国反家暴法》 - 相关司法解释，《侵权责任法》 - 《反家庭暴力法》 - 相关司法解释、《民事诉讼法》 | 2/33 | 2/46 - 《村民委员会组织法》《城市居民委员会组织法》《人民调解法》 - 《村民委员会组织法》《城市居民委员会组织法》《人民调解法》 |
| 无回答 | 0/51 | 2/33 | 0/46 |

12. 以下培训内容，对你印象最深、启发最大的内容是哪些？请按照最重要到最不重要的次序排序（例如： BCADFEG） _______________

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| A. 家庭暴力产生的原因 B. 家庭暴力对受暴者、儿童和家庭的伤害 C. 对家庭暴力认识的误区 D. 预防和制止家庭暴力的主要方法 E. 预防和制止家庭暴力的工作流程 F. 老师讲的家庭暴力案例 G. 如何与其他部门合作 |  |  |  |

- 培训内容的运用

13. 手册附录中的法律法条，你曾经在工作中运用过吗？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 有 请列举具体名称 | 22/51 | 19/33 | 24/46 |
| 没有 | 28/51 | 9/33 | 21/46 |
| 无回答 | 1/51 | 5/33 | 1/46 |

14. 迄今为止，你在培训中学到知识技能在多大程度上与你的反家暴工作需要相关联？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 高度相关 | 17/51 | 10/33 | 9/46 |
| 基本相关 | 14/51 | 9/33 | 23/46 |
| 部分相关 | 10/51 | 13/33 | 13/46 |
| 不太相关 | 9/51 | 0/33 | 1/46 |
| 不相关 | 0/51 | 0/33 | 0/46 |
| 无回答 | 1/51 | 1/33 | 0/46 |

15. 在以后的培训中，你认为你在培训中学到知识技能在多大程度上与你的反家暴工作需要相关联？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 高度相关 | 22/51 | 13/33 | 15/46 |
| 基本相关 | 12/51 | 11/33 | 18/46 |
| 部分相关 | 9/51 | 8/33 | 12/46 |
| 不太相关 | 4/51 | 0/33 | 1/46 |
| 不相关 | 0/51 | 0/33 | 0/46 |
| 无回答 | 4/51 | 1/33 | 0/46 |

16. 如果你在 14、 15 题中回答了“不太相关”或“不相关”，请解释为什么？

| 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- |

17. 迄今为止，你在多大程度上向自己的同事传递了你在培训中学到的知识技能？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 非常多 | 18/51 | 17/33 | 11/46 |
| 部分 | 29/51 | 15/33 | 32/46 |
| 不太多 | 1/51 | 0/33 | 1/46 |
| 没有 | 1/51 | 0/33 | 0/46 |
| 无回答 | 2/51 | 1/33 | 2/46 |

18. 如果你在 17 题中选择了“不太多”或“没有”，请解释为什么？

| 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- |
| 当前从事的工作与反家暴无太大关联，今后的培训应当从公安局派出所选取人员，因为派出所是涉及反家暴警情处置的第一部门 | / | / |
| 因为乡镇医院编制不够，人员少，一岗多人，根本绝没有时间做其他事项 |  |  |

19. 你认为受害妇女能够在多大程度上共同参与服务的过程？

|  | 四川仪陇 | 湖南宁乡 | 甘肃靖远 |
| --- | --- | --- | --- |
| 高度参与 | 28/51 | 11/33 | 6/46 |
| 部分参与 | 18/51 | 20/33 | 33/46 |
| 不太参与 | 3/51 | 1/33 | 5/46 |
| 不参与 | 0/51 | 0/33 | 1/46 |
| 无回答 | 2/51 | 1/33 | 1/46 |

- 请描述一个工作中的案例，说明你在工作中如何运用了培训中到的知识技能（ 50-100 字） ?

| 四川仪陇：20/51 |  |
| --- | --- |
| 1 | 在派出所接处警，受理、处置过程中充分运用了培训中学到的各项技能，如在2016年2月何某某和李某某因夫妻感情破裂分居，何某某常跑老婆单位宿舍闹事，被依法采用考试，后再未发生纠纷。 |
| 2 | 如有妇女报案受到家暴，我作为接报警中心的工作员，会在情感上给予支持与同情，与其很好的沟通交流，问清真实想法，视情通知医院、妇联等相关部门参与。 |
| 3 | 目前工作中还没有案例。 |
| 4 | 从学习培训后，到现在我还没有遇到一起案例，所以没法描述。 |
| 5 | 暂无案例。 |
| 6 | 与乡镇妇联一起对本地一名受暴妇女进行了救助，对其进行了心理疏导，对其丈夫进行了法律宣传与批评教育，经过调解是双方和解。 |
| 7 | 程女士的丈夫只好喝了酒就殴打自己，考虑孩子受影响经常忍气吞声。在社区宣传反家暴活动中向社区说出自己经历后，社区通过调查取证，帮助受害者收集资料，告诫此行为是违法行为。现在程女士丈夫已改变。 |
| 8 | 有一对夫妇，丈夫经常打妻子，其妻子到镇妇联求助，我作为妇联主席，联系镇民政所、司法所工作人员到其家中协调解决时，其丈夫通过宣传反家暴法等让其丈夫认识到了自己的错误行为，让其知道家暴时是犯法的，后来其丈夫有所转变，不再对其妻子进行家暴。 |
| 9 | 一是组建部门配合较好，加强领导，明确责任。二是在家庭冷暴力中采取疏导、说服教育，让家庭和睦相处。 |
| 10 | “家和万事兴”这是每个中国人气旺的家庭生活状态。然而，面对生活的坎坷，有人心理发生畸变，挥舞着“暴力拳头”打碎了家的温馨。随着家暴入法，反家庭暴力是一项系统工程，为家暴的受害者提供了法律咨询、援助及心里咨询等一站式服务。挽救了很多家庭。例如：小王是两个孩子的妈妈，是一个全职主妇，老公在外做生意，两人经常会因为一些琐事吵架，老公偶尔还会有暴力行为，而大多数的“惩罚”方式是不和她说话，有次看见小王情绪低落，脸上还有被老公打过的伤痕。我一再追问她才想我述说了她的事情。为了帮助小王挽回婚姻，除了每个月定期见面，每隔一个星期就会给小王打一次电话，给她一点夫妻相处的建议，经过一段时间的努力，现在小王和老公的关系密切了，小王也慢慢找到了自己在家庭中的定位。 |
| 11 | 一对夫妻，常年分居，丈夫常年殴打妻子，并在本村另外找情人，妻子怕闲言碎语，坚决不离婚，镇妇联了解情况后，对其丈夫进行了教育，并对其宣传反家暴法，后丈夫有所收敛。 |
| 12 | 今年13岁的小伟（化名），在他很小的时候，父亲病逝，母亲失联，他一直跟着伯伯生活。但伯伯并不喜欢小伟，常因为一些小事动手打他。挨了打得小伟到处跑，连饭也不愿意回家吃。甚至有一段时间在养老院吃饭。因为长时间流浪，接触的人过于复杂，小伟还学会了偷东西。由于从小缺少关爱，他不愿意与人交流。为了减缓小伟的心理负担，缓和他与家人的矛盾，我在当地妇联工作期间，要求其家人带小伟每周到乡妇联对其进行教育，向其宣传我国《未成年人保护法》，禁止父母（长辈）虐代子女，并不定时走访，小伟的情况得到减缓，并回到学校。 |
| 13 | 百锁村上有对新婚夫妇结婚5个月就遇到双方轻度家暴行为，经过镇妇联与村干部的调解，化解了家庭矛盾，平息了家暴行为，促进了家庭和谐。 |
| 14 | 闵某（女）与李某2014年结婚，双方均系再婚，婚后共同于2016年生育一子。闵某怀孕期间曾遭李某殴打两次，产子后不到半年，双方再次因为生活琐事发生打架。遂闵某前来咨询。讲述其在婚姻中遭遇的不幸和生活的不易，以及其对婚姻的向往和对孩子的关爱与不舍；经了解，其夫妻矛盾系婆媳矛盾所引发，打架过程中双方均有受伤，但女方伤情相对严重，且害怕回家；女方咨询的主要目的是如何解除婚姻关系。基于女方的特殊情况，我们建议其先到医院处理伤情（叮嘱其收集和保存受伤的相关证据）；再到公安派出所报警，请求民警对李某作出处罚，或予以告诫；基于经济困难，可到法律援助中心申请法律援助等。 |
| 15 | 没有该方面案例，只是想针对自身工作实际，谈谈想法。曾办理过一个故意伤人案件。该案嫌疑人为一名五十余岁的妇女，因其不堪忍受丈夫的长期施暴，最终采取在其丈夫的面里面投放毒鼠强的极端方法，将其丈夫毒死。因为到了我们这个环节，很多都是矛盾已经激化，以至于产生严重后果。而且已经是到了用道德不能调和，需要上升到法律层面了。所以，在以后工作中，如何各部门联动进行宣传、预防，才是重中之重。 |
| 16 | 张某（女），长期受到老公的殴打，曾起诉到法院离婚，但在法庭开庭前三天，再次被老公殴打，并受到威胁，所以张某不敢到庭诉讼。其后，张某仍然经常受到老公的殴打，且事态更为严重。张某来我所申请给予法律援助，经我所与司法局、公安、妇联、医疗等多部门的工作协调与配合下，取得了大量的证据后，张某再次诉至法院请求判决离婚，并根据婚姻法第46条之规定，张某起诉主张了因家暴给予张某造成的精神损害赔偿金，张某的老公在大量的证据面前不得不低头认错，并承诺痛改前非，张某表示原谅，同时撤回起诉，此后，夫妻俩和好如初。 |
| 17 | 我办理的王某某诉刘某离婚纠纷一案。原告王某某对刘某有殴打行为，我依法指导刘某如何收集证据，并对王某某进行了批评。在案件判决时根据双方提供的证据和考虑刘某的具体情况及要求，依法驳回了原告王某某的离婚诉讼请求。 |
| 18 | 在有家庭暴力存在的家庭，帮助受害妇女联系公安部门和妇联，成功离婚，避免再次伤害。 |
| 19 | 原在司法所工作的时候参与对发生家暴的家庭进行法律宣传和调解。 |
| 20 | 离婚诉讼中，妇女称曾多次受家暴。但举证较少或没有。为了核实情况，主动与当地派出所、妇联、社区等相关部门联系了解情况，取证以维护受害妇女权益。 |
| 湖南宁乡 |  |
| 1 | 玉潭街道某社区一对母子前来庇护所求助，母亲40多岁，儿子21岁，两人均伤痕累累，我在接待过程中，他们先只讲丈夫打孩子妻子，我鼓励他们说出真相，原来好赌，后染毒瘾，经常殴打他们，我迅速将此情况通报公安部门，将其抓获送到戒毒所戒毒，同时，要他们更换手机号码到长沙找工作，暂打工为生。 |
| 2 | 2017年3月，妇女刘某来我办公室投诉，说被丈夫殴打赶出家门，我依法把她送到庇护所，并将此事转介给派出所和乡妇联。 |
| 3 | 女性刘某去年10月一个晚上因小事被丈夫殴打赶出家门，事后政府投诉，我知情，便和乡妇联、司法所的同志一起接待，处理，在得知她丈夫追随而出时，我及时把她送至家暴庇护所安置。 |
| 4 | 2016年12月，我镇界头村一妇女受害者曾某来镇政府投诉，来时可见头部流血，说是被丈夫打伤的，当时我将人员立即送到乡卫生院救治，同时向派出所报案，转介乡妇联协助处理。 |
| 5 | 我是某乡镇民政办工作人员，有一次来了一对夫妻要离婚，离婚原因主要是家庭暴力。我通过对多部门合作模式，请来了乡妇联主席、派出所干警对其丈夫进行了教育，其丈夫通过我们对他家庭暴力教育，认识了错误，夫妻和好。 |
| 6 | 我是某乡镇民政办工作人员，有一次来了一对夫妻要离婚，离婚原因主要是家庭暴力。我通过对多部门合作模式，请来了乡妇联主席、派出所干警对其丈夫进行了教育，其丈夫通过我们对他家庭暴力教育，认识了错误，夫妻和好。 |
| 7 | 2017年3月，刘某被丈夫打后来我所投诉，听取该女同志的投诉后，我认为立即把此案转介到妇联和司法所进行了处理，该同志在我站住了两天后，在派出所、区妇联联合工作下，该同志丈夫向妇女认错后接其回家。 |
| 8 | 有一位受家暴的妇女来我办求助，说其受丈夫打骂，我们将她的基本情况登记，分析家暴发生的原因，了解她受到的伤害，然后给她法律援助，通过《宪法》《妇女权益保障法》告诉她维权，告诉她如何去求助，让她远离家暴。 |
| 9 | 2012年7月宁乡县某乡镇发生一起丈夫殴打妻子的家庭暴力案件，接到受害当事人的报案后，派出所立即处警，并做好当事人的询问调查工作，在当地妇联、村委会、派出所的协调努力下，案件成功处置。 |
| 10 | / |
| 11 | 家庭暴力，大部分施暴方为男性，受暴方为女性，通常女性较为脆弱，大多采用逃避和退缩的方式面对问题，在得知有暴力倾向的家庭时，多了解施暴方的个性，因人而定的方法，防止暴力行为，多与受暴方沟通，教她怎样预防和制止暴力的行动。 |
| 12 | 刘某与王某自五年前结婚以来，感情一直不稳定，多次闹离婚，男方坚决不同意，现有一个2岁多的女儿，今年刘某再次提出离婚，遭到男方的极力反对并威胁及语言攻击，不允许见自己的亲生女儿。此种情况下，受害人可根据《婚姻法》的条例向居民委员会、村民委员会提出请求。 |
| 13 | 某年某日，接110指挥中心出警指令后，立即向领导及相关部门汇报，根据学到的知识，询问基本情况，做询问笔录，填写《接受案件回执单》将其转介至其他机构，后多次回访。 |
| 14 | / |
| 15 | 2016年2月我所受理王玉娇被共同居住的前夫刘建华以铁锹、扫帚、拳头故意伤害案，我们受理报警后，对受害人进行风险评估，要求其进行伤情鉴定，形成受暴询问材料，调请相关知情人及现场证据，依法进行了裁决处理，对违法人员予以行政拘留10日并处罚款伍佰元整。 |
| 16 | 在学习和生活中，经常进行反家暴知识宣传，使广大妇女儿童了解反家暴方面的相关知识、法律条文、举报流程。 |
| 17 | 知识点：为受害人创建温磬安全的环境，让受害人充分自诉。案例：受害人前来就诊，陪诊者即为施暴者，我以为病人检查身体为由，要求施暴者室外等候。关上诊室门那一刻，受害者立刻跪地求我救她。因此我极其印象深刻，所以我们在以后的工作中一定要注意回避加害者，给受害人一个安全的环境。 |
| 18 | 在工作中我通过将学到的反家暴知识，在职工培训过程中进行宣传学习，与同事们共享和学习。 |
| 19 | 丈夫赵某婚后打骂妻子多次，一名受害者某某，35岁。首先，了解具体情况，分析原因，理解并尊重受害者权力，保护受害者隐私，根据具体情况采取相关措施，情节严重，后帮助其求助妇联，保护自己的合法权益 |
| 20 | / |
| 21 | 一位妇女来妇科门诊就诊，说话吞吞吐吐，在做妇检时，发现其身上有多处伤痕。追问再三，才承认是其丈夫殴打所致，予以取证，拍照，留存病例，开导告知可以报警等，患者感谢万分离去。后来追问（电话），其夫很少再次打她，当然和当地妇联上门做工作密切相关。 |
| 22 | 工作中未接触家暴、工作案例 |
| 23 | 帮助联系了姜某所在地办事处人员，一举化解矛盾，密切关注其家庭情况，坚决杜绝再次发生暴力行为。 |
| 24 | 在工作中遇到一个妻子殴打丈夫的家暴，我们从以下几个方面着手解决：1.对受害者进行安抚，对施暴者进行教育。2.及时制止暴力行为。3.遭到家暴时应及时报警求助，配合警方调查。4.帮助联系法律援助和心理援助的专业人员，在专业上帮助受害者。5.帮助联系家庭所在地的街道办事人员进行调解，化解矛盾。6.平时在工作中加强对单位科室人员的宣传教育等。 |
| 25 | 戴某群（女）与戴某良（男）于2005年登记结婚。男方经常暴力殴打女方，女方向妇联投诉，妇联指派宁乡县法院援中心办理，县法援中心起诉到法院，法院依法调解双方离婚。 |
| 26 | 袁某受丈夫家庭暴力，多次干预她喜欢干的工作，让她时刻恐慌，也很无奈。袁某求助妇联，寻找法律援助，向法院申请了人身保护令，较好地维护了她的合法权益。 |
| 27 | 袁某与邓某于1990年4月登记结婚，自1991年起，邓某对袁实施家暴，袁向妇联申请援助，县法援中心介入，代理袁向法院起诉要求离婚，县法院判决允许离婚。 |
| 28 | 在家庭生活中如何与接触的亲人、朋友交流，讲话的技巧，对孩子的教育方法及对家人的关爱。 |
| 29 | 丈夫汤某与刘某均为再婚。汤某经常吸毒，经常无故打骂妻子刘某，并将刘某打伤至轻伤一级。汤某因此受到了处罚，刘某提起离婚诉讼。我认为为维护妇女权利，应在受到家暴时，首先报警，也可找妇联。如果无法长期生活，可依据《婚姻法》和《反家暴法》起诉离婚。 |
| 30 | 居住于新县枫村上上组的周宁珠于2013年与唐寿均结婚后，多次遭受唐寿均的殴打与欺辱，但由于没有报案记录，在我办理本案时，主动找到当地的村委会，请求村委会出面要求出具保证书，该保证书中体现有实施暴力记录，从而佐证唐有家庭暴力的事实。 |
| 31 | 2015年6月，刘某与陈某认识、恋爱并结婚，双方均系再婚。后因家庭琐事发生争执，陈某对刘某实施家暴，刘忍无可忍，向妇联投诉。后在县法律援助中心帮助下，向县法院起诉，解除婚姻。 |
| 32 | 小芳曾受到丈夫小明的家庭暴力长达三年，但给她的心理留下了巨大的创伤，通知心理咨询让她慢慢走出曾经被丈夫伤害的阴影，重新寻找新生活。2016年5月11日，周小玲作为原告向法院起诉，要求与被告谢艳明离婚，并反映被告对其有家暴行为。法院判决不准离婚后，谢艳明对其威胁、恐吓，新县公安局向谢艳明出具了家庭暴力告诫书。 |
| 33 | 2017年4月26日，周小玲第二次起诉离婚时，申请人身安全保护令，本院依然受理，向谢艳明送达了民事裁定书，向其所在派出所及村委送达了民事裁定书和协助执行通知书。 |
| 甘肃靖远：46/46 |  |
| 1 | 我办理过马梅园的案例，均已妥善解救 |
| 2 | 张某和马某是夫妻，育有三个子女均已成年，在共同生活近三十年期间，张某好逸恶劳，多次殴打、威胁马某，甚至用自己的生命威胁马某，但张某仍不满意，起诉法院要求离婚，迫使马某好吃好喝供养他。受理本案后，我们办案组多次全方位向张某和马某宣传男女平等、夫妻之间有相互扶助的义务等相关法律知识，最终马某认识到自己一直被张某控制并已习惯的现实，决然同意和张某离婚，张某也在一定程度上认识到自己的暴力行为。双方解除婚姻后半年，我们办案组回访，张某和马某虽未复婚，但张某一直随马某一起种地干家务，积极帮助马某的生活。 |
| 3 | 2017年1月13日，在靖远县刘川乡金川村，段某与妻子万某因琐事发生争执，段某对妻子拳打脚踢，万某无法忍受，报至派出所解决。接警后，民警首先指出段某殴打他人的行为为违法行为，是触犯法律的，随后对段某讲解家庭琐事与纠纷应协商解决，不能使用暴力。最后对段某与万某耐心劝说，段某承认了自己家暴打人的错误，保证以后不再对妻子使用暴力，万某也原谅了丈夫。 |
| 4 | 对于寻求帮助的受暴妇女，我都会为他讲解反家暴的基本知识，引导他们向相应的部门积极寻求法律帮助，按照维权流程寻找法律保护。 |
| 5 | 朋友的姐姐因为遭受到丈夫多次暴力殴打，他不知道怎么办，我告诉她一定要报警，同时可以通过妇联等多部门寻求帮助及救济，收集证据，诉讼离婚。 |
| 6 | 一日，听到邻居家吵架声，经了解，原来丈夫整日酗酒，无所事事，总是伸手向老婆要钱花，不给钱就骂。发现这是家庭暴力就上前劝说，但仍然不听劝继续实施家暴的，就可以拨打110寻求帮助。 |
| 7 | 在入户工作中，可以给妇女们宣传男人打女人不再是家务事，让妇女们拿起法律的武器，维护自己的合法权益，应培训中学到的理念，更好的为妇女服务。 |
| 8 | 同事的邻居陈某婚后经常因家庭琐事招丈夫殴打，本人却不敢言说，后来在同事的鼓励下找到妇联，在问清楚陈某的意图后，我们找到陈某的丈夫张某，向他讲解了打人是犯法的，并对张某实施的暴力进行了分析、劝解，张某听完当场承认错误，保证以后再不打陈某。 |
| 9 | 在一次行走中，有一位男士在打骂一位女士，经了解原来是夫妻。由于女士没有固定工作，丈夫是一位医生，只要她做的饭莱没有达到他的要求，他就打骂。我上前劝说：这是家庭暴力，如若不听劝，仍然要继续打骂，实施家庭暴力，这位女士你完全可以拨打110报警，要求对他进行告诫。 |
| 10 | 与朋友聊天发现她手臂上的伤情，才知道她经常被丈夫打，我告诉她这是家庭暴力，是什么原因遭到丈夫的毒打，还是因为钱的原因，让他们好好沟通协调，如果还是不听劝就求助110民警，寻求帮助。 |
| 11 | 我接到一个知心电话，一位李女士称丈夫经常打骂她，由于她没有工作，经常在家带孩子，丈夫是一位中学老师，她想让丈夫知道这是家暴，又不想因此影响夫妻关系。我告诉她可以与社区妇联工作人员联系，要求上门向其丈夫宣讲，并且可以宣讲我县的家暴告诫制度，如果宣讲之后其丈夫仍然实施家暴，可以拨打110报警，要求对其进行告诫。 |
| 12 | 李某和婆婆因为家庭琐事争吵并厮打，司法所协同乡妇联前去调解，向双方讲解了家庭暴力的相关知识。 |
| 13 | 2016年6月，马某在家人的陪同下来咨询，经询问得知其是被丈夫施暴多次无法容忍，因看到其伤势较重，我中心立即向公安部门转介并同时通知医疗机构，并告知当事人去就诊。当事人出院后，依照其要求为其提供法律援助，顺利办理了离婚手续。 |
| 14 | 自己的初中同学嫁给了我们一个邻居，婚后不久，丈夫就开始打妻子，婆婆急性子，嫌弃儿媳，经常在她儿子面前埋怨他妻子，丈夫也是个妈宝，什么都听他妈的，以致于我这个同学被打得遍体鳞伤，最严重的一次就是他妻子刚做完节育手术后没几天就打她，还让她做饭、干家务之类的，有一天我们同学家只有她一人，她向我咨询怎么办，我就告诉她有关方面的程序与流程，让她到司法部门了解情况，必要时起诉离婚。我们这同学终于在去年离婚了。 |
| 15 | 我单位附近有一对夫妻，其男方动辄对女方辱骂，甚至多次拳脚相加，多次劝阻无效，后通过对其母亲进行《反家暴法》相关规定告知，经其母亲多次利用法律的约束得以劝诫其子，遂逐渐减少了对妻子的家暴行为。 |
| 16 | 王某某，在靖远县妇幼保健院生女孩儿后，遭到丈夫、婆婆的辱骂。通过培训，我认为这是一种性别歧视，语言行为暴力，冷暴力，对产后妇女伤害很大，严重者会导致产后抑郁症，当遇到这种情况，医务人员常常会尽早疏导，关心照顾，帮助妇女愉快地度过产褥期，批评丈夫婆婆，指出这种做法是不对的，这还算是家庭暴力中较轻的一种，严重的应该寻求相关部门的帮助，共同制止。 |
| 17 | 张某被其公公殴打来所，我告诉她县委拨打110报警，留取证据，然后入院治疗，出院后可以起诉，最后此案和解。 |
| 18 | 我的朋友张某，因为琐事和丈夫发生争吵，被丈夫殴打，来找我哭诉，我建议她到派出所报案，因为是首次家暴，她不愿意去，我告诉她，对家暴一定要零容忍，经我的劝说，她向派出所报案，经过派出所的调解，她的丈夫再没有打过她。 |
| 19 | 王女士来我处就诊。她讲到：经常被丈夫毒打，听完后告诉她有关家庭暴力相关知识。并告诉他可以通过法律途径去解决，从而是自己的权益得以保护。 |
| 20 | 王女士来我处就诊。她讲到：经常被丈夫毒打，听完后告诉她可以保存病例，同时向派出所报案，还可以找妇联 |
| 21 | 半年前，遭受家暴长达十几年的居民小张来到靖远县东升乡卫生院，向工作人员求援。在我认真检查并进行了免费的治疗并出具伤情证明，依托我乡派出所经过调查取证向施暴者发出家庭暴力告诫书，并提供了法律援助进行心理辅导和事后回访，使其远离了家庭暴力。 |
| 22 | 李某婚后不久遭到丈夫的谩骂及殴打后来我院就诊，我认真询问受伤原因，详细、准确、客观地记录了伤情，并对受伤害人进行了如何反家暴的指导。首先要认真对待第一次家庭暴力，如果你容忍了第一次，就会有第二次、第三次甚至更多的家庭暴力，而且一次比一次严重。因此一定要对第一次家庭暴力说“不”，要尽最大的可能保证自己的人身安全，如果有生命危险要大声呼喊，或采取其他有效手段，并在24小时内到当地派出所开出验伤通知书，为今后要求法律援助，保留有力证据，做好自我保护。 |
| 23 | 我镇东宁村有一农户，丈夫偶尔殴打妻子，其妻子向民政部门寻求帮助，通过培训我对其丈夫进行了宣传，告诉他打老婆是违法行为 |
| 24 | 我同事的朋友经常被婆婆殴打，她的丈夫也认为打老婆很正常，我建议她在被打后去派出所报案，让派出所对婆婆和老公进行说服教育，后来她说报案之后，婆婆再没有打过她。 |
| 25 | 我的朋友经常遭到丈夫的殴打，他不知道怎么去救助，我告诉她可以向派出所报案，也可以直接去妇联求助。 |
| 26 | 在工作中没有遇到家暴案例，但是我知道遭受家暴后可以去报警或者去妇联。 |
| 27 | 有一个受暴妇女说被丈夫打了，我告诉她可以去找妇联，寻求帮助。 |
| 28 | 我们婚姻登记处来了一个姓郭的女士，跟我们咨询离婚的事情。我让她详细地说一下情况。她说她娘家是甘肃省武都市的，嫁到我们甘肃省白银市靖远县东升乡。婚后生了一儿一女。女儿在平川区读高中，儿子在靖远县读初中。她男人在甘肃省白银市平川区开煤矿，家庭经济情况非常好，在平川区有一套别墅，靖远县有一套楼房，乡下还有平房。但是几年前，他男人又找了个小老婆，并且和小老婆生了一个儿子。现在她男人带着小老婆，小老婆的儿子，她的女儿一起住在平川区的别墅里，她自己带着儿子在靖远县，她男人已经好几年没有给过她一分钱了，她自己在外面打工挣钱，供儿子读书。她男人动不动就从平川区到靖远县来打她，逼她离婚，离婚条件是不给她一分钱，让她净身出户。最近又打了一次，她实在受不了了，到我们这里咨询，希望我们能给她办理离婚，把她现在居住的一套房子和儿子分给她。正在说话的时候，她男人来了，没说两句话，当着我们办公室工作人员的面，又动手打了郭女士一巴掌，还把她往办公室门外拖，扬言今天要打死她。郭女士吓得一直往后缩。我们办公室的几个工作人员拼命地拉开了郭女士的男人，警告他不能再打人，再打我们就报警了，那个男人才走了。后来我们告诉郭女士，这种情况我们是不能办理协议离婚的，只能上法院诉讼离婚了。我们又告诉她，打人是犯法的，任何人都不能侵犯她的合法权益，她的情况已经属于家庭暴力了。她可以到法院诉讼离婚，也可以向妇联求助，寻求法律援助。 |
| 29 | 2016年12月14日，一名受暴妇女来到办公室向我咨询，我告诉她如果无家可归，向驻我院妇联工作人员处登记，确认后可提供为期7天的庇护，也可以向派出所报警。 |
| 30 | 朋友们平时在一起闲聊时说起某某被丈夫家暴，我都会说出自己的观点，家庭暴力不是家丑，不能容忍，一定要寻求解决办法，可以找妇联，也可以打110报警，向这些部门寻求帮助。 |
| 31 | 我的一个朋友受丈夫的家暴,我告诉她一定要打110报警,我的朋友说是第一次打她,以前没有打过,我告诉她对于第一次家暴尤其不能容忍,因为这是纵容施暴者。打了110之后,民警进行了教育,他的丈夫认识到了错误,也再没有打过她。 |
| 32 | 2017年5月30日,辖区内潘某女拨打110报警称:其夫孙某将其多次殴打,要求派出所处理。派出所接警后当即赶往现场。到达现场后:首先对潘某女进行询问并对其伤情进行拍照固定,收集提供证据。排除危险因素后,帮助潘某女制定安全计划;对乡镇司法、妇联、社区进行通报,跟踪管理。 |
| 33 | 我在工作中受理过子女不养活老人的案例，因为是亲属间矛盾，我认为不能予以处罚，运用反家庭暴力法第二章第十条和第三章第十五条，对其子女进行讲解，并联合乡司法调解组织与妇联对其进行释法教育，让其认识到错误，从而化解矛盾，维护了其家庭和睦相处。 |
| 34 | 2015年，在靖远县北滩镇发生一起因家庭暴力构成的故意伤害案，检察院在审查起诉中，我们及时向受害人李某讲解了反家庭暴力知识，并进行了心理疏导 |
| 35 | 我们邻居，他们夫妻俩多年来一直吵架，甚至打架，一次自己正巧碰见，就用培训中学到的反家庭暴力知识告诉他们，丈夫打妻子是犯法的，现在反家暴法也已出台，它将保护妇女儿童的权益，丈夫在敢打妻子，妻子可以找妇联、司法局等部门申请调节，如果丈夫屡教不改，妻子可以申请公安局出具告戒制度或申请法院出具人生保护令，实在不行起诉离婚。 |
| 36 | 社区的妇女宋某来找我说被丈夫殴打，我通过上门了解，告诉他们打人违法，并及时向乡镇妇联反应，妇联和派出所对其丈夫进行了批评教育，后来丈夫又打了宋某，及时向辖区派出所报案，派出所发了告诫书，其丈夫再没有打过宋某。 |
| 37 | 我社区张某来找到我说自己经常受到丈夫的谩骂，他的心情很烦闷，我告诉她这是家庭暴力，通过多次的上门说教，张某的丈夫认识到了自己的错误，并且建议张某到妇联心理抚慰中心去寻求帮助。 |
| 38 | 王某来请求离婚，原因是经常受到家暴，但是庭审过程中其丈夫不同意离婚，通过和王某了解，丈夫曾于2016年7月份给她写过保证书，并且当时把王某打伤住进了医院，经过努力协调调取了履历，结合保证书，法院最终认定家暴事实成立，准予离婚。 |
| 39 | 我社区万某被丈夫殴打，2016年9月被丈夫打伤，我们了解情况后及时送住医院救治，并且拨打110报警，出院后万某向法院提起诉讼离婚，其丈夫不承认打过万某，万某找到了报警记录和住院病历，最终法院判离。 |
| 40 | 我接待过一个来访妇女，她被丈夫殴打，是因为家庭琐事吵架，我们对她们进行了调解，因为是首次家暴，并说明如果再次殴打，派出所会发告诫书，事后回访再无家暴发生。 |
| 41 | 张某,女,结婚28年,丈夫长期对其实施家暴,在2017年1月份无故殴打张某,施暴后张某去医院挂号诊断,诊断结果是家暴造成张某肋骨打断,张某告诉妇联工作人员,在受到侵害时,宁可在家忍气吞声,忍辱负重,也不愿声张,就是为了自己的孩子,现在孩子上大学了,实在受不了这种生活。长期以来的家暴导致她的身体、精神和心理现在严重抑郁,张某找到妇联,希望维护自己的权益。针对张某的叙述,区妇联工作人员在妇联系统来信来访来电情况登记表上予以登记,告知以后再次发生家暴:第一步收集和固定证据:注意收集暴力伤害的证据。如毁坏的物品,撕裂的衣服,家暴的照片。第二步找警察:在家暴危急时刻,向白银区反家庭暴力110投诉中心报警求助,人民警察会依职到家暴现场,如若发生伤害,可以到白银区反家庭暴力伤情司法鉴定中心申请伤情鉴定。第三步去法院:法院负有维护受暴妇女合法权益的责任,可以选择离婚或寻求保护。第四步找司法行政部门:白银区在司法局成立了白银区反家庭暴力妇女儿童法律援助中心,为制止家庭暴力,可以受害者提供法律援助等。第五步寻求民政部门救助:对面临危害或无处可去的家暴受害者,可以到民政部门成立的白银区反家庭暴力庇护中心寻求帮助,庇护中心可以安排短期的免费庇护居住。第六步:到白银区反家庭暴力妇女儿童抚慰中心,寻求心理开导。 |
| 42 | 对来访的受暴妇女，我都会为他讲解反家暴的基本知识，引导受家暴妇女积极寻求法律帮助，按照维权流程寻找法律保护。 |
| 43 | 朋友的姐姐因为遭受到丈夫多次暴力殴打，我告诉朋友可以通过多部门寻求帮助及救助，收集证据，诉讼离婚等。 |
| 44 | 有一位妇女,经常受到丈夫的辱骂,她无处诉说,到村委会要求村上介入,我们进行劝导,并连同村妇女主任做思想工作,同时,对她丈夫进行思想教育,告知他的行为属于家庭暴力,触犯了《中华人民共和国反家庭暴力法》,如果不及时停止,将会收到公安机关的告诚书。经过我们的劝说和教育,涨幅的行为有历收敛。 |
| 45 | 我的一个朋友受丈夫的家暴,我告诉她一定要打110报警,我的朋友说是第一次打她,以前没有打过,我告诉她对于第一次家暴尤其不能容忍,因为这是纵容施暴者。打了110之后,民警进行了教育,他的丈夫认识到了错误,也再没有打过她。 |
| 46 | 2017年3月张某因被丈夫家暴，我所出面主持调调解，因伤情不严重，对男方进行批评教育，对双方宣传相关法律知识，后经调解和好。 |

Fuller information on findings is available in the Baseline Report. Citation details are as follows: Tan, Can, et al. (2010). Preventing and Responding to Domestic Violence in China through a Multi-sectoral Approach. Baseline Survey Report for UN agencies’ Joint Programme.

See UN Women project proposal, Promote Efforts for National Legislation on Domestic Violence and Upscale the Multi-sector Model in China.

Source: UN Women evaluation ToR, 2017.

See Kirkpatrick, D. L. (1994). Evaluating Training Programs. San Francisco: Berrett-Koehler Publishers, Inc and Kirkpatrick, Jim and Wendy Kayser Kirkpatrick (2009). The Kirkpatrick Four Levels: A Fresh Look After 50 Years, 1959-2009, Kirkpatrick Partners White Paper, April 2009, available here.

Source: UN Women evaluation ToR.

Source: UN Women evaluation ToR.

‘Family-related problem’ is used here as a catch all term to reflect the fact that a number of problems related to families and family conflicts, including domestic violence, appear to be linked in popular conceptions.

See: Pawson, R. (2013). The Science of Evaluation. London: SAGE.