## Slide 1: تقييم مشروع المحطة الواحدة للأعمال ورشة عرض النتائج والتوصيات الرئيسة
عامرماضي
19 حزيران 2017

## Slide 2: العرض المقدم
انشطm التقييم والصعوبات/التحديات
ملخص حول النتائج والاستنتاجات من التقييم
عرض التوصيات
نقاش

## Slide 3: أنشطة التقييم
اجتماع
مرحلة تكوين التقييم
مرحلة العمل الميداني (آذار/نيسان)
  مقابلات وحلقات نقاش
  مراجعة مكتبية
  زيارات للشركات والجمعيات المستفيدة، بما في ذلك معرض الحفل الختامي
مرحلة التحليل وإعداد التقرير (على ثلاثة مراحل)
شكراً جزيلاً للجميع.

## Slide 4: الصعوبات
الوضع الفلسطيني وما يفرضه من محددات على آفاق تطور القطاع الخاص
بعض النقص في البيانات الخاصة بوضع البداية قبل المشروع
الأنشطة في غرة
هل نستطيع أن نعزي أي أثر للمشروع؟
لم تكن جميع الانشطة قد اكتملت، وبعضها لم يمر على انجازه الكثير من الوقت.

## Slide 5: المقاربة
الاستقلالية، الحيادية وحفظ السرية
الاجابة على اسئلة التقييم الستة (حسب الشروط المرجعية)
الأخذ بعين الاعتبار استخدامات التقييم في التحليل والتوصيات
Notes: Theory of Change won’t be central to analytical report, but we’ll refer to the work done during the inception mission and to the design assumptions that it identified.

## Slide 6: الملائمة
متسق مع السياق...
  خطة التنمية الوطنية
  UNDAF
  توجهات المؤسسات الشريكة
  أهداف التنمية المستدامة وخصوصاً SDG1, 5, 8, 10, 17) )
  هدف الصندوق الممول والخاص بالتنمية الشمولية
  الاستراتيجية الوطنية عبر القطاعية للنوع الاجتماعي
  الاستراتيجية الوطنية للتصدير
  احتياجات النساء الرياديات والتعاونيات المستهدفة
Notes: The JP was (and continues to be) relevant in view of national and international commitments and strategic priorities of the Government of the State of Palestine, and the United Nations strategic priorities as identified in the United Nations Development Assistance Framework for the State of Palestine (UNDAF). It is also very well aligned with UN Women’s, FAO’s, and ITC’s corporate and country-level priorities, as well as with the SDGs (particularly SDG1, 5, 8, 10, and 17) and the SDG-F policy goal of inclusive economic growth for poverty eradication and gender mainstreaming.

## Slide 7: الملائمة
ما خطط من انشطة بناء قدرات وتطوير سياسات متسق مع احتياجات المؤسسات المستهدفة/الشريكة، ولكن عند التنفيذ قل مدى الاتساق/الملائمة
التدقيق مع بنك فلسطين وبيرزيت للأدوية مرتبط ارتباط مباشر مع توجهات المؤسستين، واسترايجية البنك.
Notes: Staff of Gender Units within the targeted ministries described the capacity building interventions planned under the JP as being “perfectly aligned” with their needs, and in-tune with their analysis of the capacity building needs for mainstreaming gender within the respective ministries. One informants interviewed by the evaluation made reference to the capacity building on integrating gender in planning and operations that was planned under the programme, describing it as “the best kind of support Gender Units could be provided to be able to discharge their functions more easily, and mobilise the support they need for this purpose.” Trainees in the various ministries that have received training on gender reported that there was a clear need for the type of training and capacity building support that was planned within the framework of the JP, particularly the training on integrating and mainstreaming gender in national policies, plans, and programs.
The two private sector companies reported that the support they received within the framework of the JP to undertake a gender audit was relevant to their overall strategy of creating an equitable and inclusive working environment for their employees.

## Slide 8: التصميم
اشتمل على جميع العناصر الاساسية، ولكن مستوى التفاصيل في العناصر كان متفاوتاً مما أثر على التنفيذ
بعض نقاط الضعف:
  اهداف طموحة ومشكوك في القدرة على تحقيقها في الفترة المتاحة
  مستوى المشاركة في التصميم لم يكن كافي
  تحليل الاستراتيجيات واسباب اختيارها، وكذلك المخاطر
  الاطار المنطقي للمشروع
  استراتيجية الخروج /الاستمرارية
  الفئة المستهدفة تحديداً
  المصادر البشرية المخصصة من حيث العدد وحجم الوقت المخصص
  كيفية استخدام المصادر المخصصة من المشاريع الأخرى
فترة تصميم أطول كان من الممكن أن تعالج نقاط الضعف هذه
Notes: women empowerment at different levels, with and through multiple stakeholders, and from different angles. The joint programme was appropriate for this broad approach, given the needs of the target group and the types of change the programme set out to achieve. The relatively small number of participating UN agencies in the JP also lent itself for enhanced synergies and collaboration. This said, the roles of the UN agencies in the programme did not necessarily reflect their comparative advantages.
The design of JP was in line with SDG-F ToRs and guidance, with joint programming being a particular strength of the programme. The design process was participatory and consultative, thereby facilitating proper identification of needs. The JP’s proposed response to these needs was ambitious, with objectives and indicators that did not seem to be commensurate with the 24 months given by the lifespan of the SDG-F programmes and the context in which the JP was to operate. The JP’s design process itself was a bit rushed, which gave little room for: (i) the participation of some groups of right bearers in the design, and (ii) in-depth analysis of strategies and potential risks. It also seems to have had negative effects on the quality of the results framework, which had a few deficiencies. Overall, however, and despite these limitations, the JP was well designed.

## Slide 9: الفعالية - المخرجات
حقق المشروع مخرجاته، بمستويات متفاوتة
  م 1.1 (السياسات والتدريب) تحقق جزئيا، وليس كما كان مخططاً تماماً
  م 1.2 (التدقيق) تحقق بالكامل
  م 2.1 (التنافسية) تحقق بالنسبة للشركات ولكن بمستوى أقل بكثير للجمعيات
  م 2.2 (المشاركة في التجارة) تحقق كما كان مخطط
  م 2.3 (الترويج الخارجي) تحقق جزئياً
Notes: The project achieved, albeit to varying degrees, all of its envisaged outputs:
Output 1.1, Palestinian public institutions are better able to develop and apply more equitable policies and technical services to support and protect increased economic activity in the private sector, was delivered largely, but not yet entirely, as planned. This was done through, both, building the capacity of partner public sector entities in gender and gender mainstreaming approaches, as well as supporting them –on a relatively limited scale, however- to develop policies that promote inclusive economic development.
Output 1.2, targeted private companies have increased engagement and social responsibility towards inclusion of women in the economic sector based on values of gender equity and promotion of women’s rights, was fully achieved.
Output 2.1, women owned/run MSMEs and cooperatives strengthen their capacity to improve their competitiveness in a sustainable and environmentally responsible way, was largely achieved for MSMEs, but not yet fully for cooperatives.
Output 2.2, women-owned/run MSMEs and cooperatives increase their participation in trade, was delivered as planned,
Output 2.3, promotion of Palestinian products produced by women owned MSME’s and cooperatives in local, regional and international markets is increased, was delivered as planned.

## Slide 10: الفعالية - النتائج
احرز المشروع تقدماً ملحوظاً باتجاه تحقيق نتائجه المتوخاة، محققاً اياها جزئياً.
ساهم المشروع بشكل كبير في تحسين مستوى تنافسية الشركات النسائية، وبشكل أقل –نتيجة لقصر دورة حياة المشروع- ولوجها للأسواق.
النساء المستفيدات تمكنًّ من تعلم معنى القيمة المقدرة واهميتها عند التعامل مع الأسواق، وهو ما أثر ايجابا على طريقة إدارة النساء لشركاتهن
عديد منهن خطين خطوات كبيرة خلال مراحل تطوير المنتج التي نفذت من خلال المشروع، ما كان له أثر على زيادة مبيعاتهن من منتجات شركاتهن داخليا وخارجياً (كم قدر المساهمة؟؟؟).
Notes: The JP made significant progress towards its two planned outcomes, partially achieving both. Particularly strong contributions were noted in relation to enhanced competitiveness of women-owned MSMEs, and, understandably given the JP’s relative short lifetime, to a somewhat lesser extent, their access to markets. Women beneficiaries had the opportunity to learn about the concept of perceived value and how important it is when dealing with markets, which has had a positive impact on their businesses. Several of them have made leaps and bounds in the product development phase and have been able to increase their business both locally and internationally. And, they had a valuable opportunity to learn how long the sampling and development process takes when doing custom work, which has helped them develop a future mind-set in doing business.

## Slide 11: الفعالية - النتائج
من الشركات الـ 43 التي استهدفت قعلياً، 35 (81%) حققت زيادة بلغت 60% قي مبيعاتها.
هذه الزيادة الكبيرة مقارنة بما كان مخطط له أدت لتحقيق المشروع لنتيجته العامة المخطط: 42% من زيادة في المبيعات للشركات المستهدفة؛ ضعف الزيادة المستهدفة.

## Slide 12: الفعالية - النتائج
حققت شركتي الثمار والروزنة (الأخيرة تأسست نتيجة للمشروع) نمواً كبيرأص في مبيعاتها (40 و 68%)، إلا أن هذه الزيادة لم تنعكس في مبيعات الجمعيات بعد.
شركة نيوفارم الوسيطة حصلت على 34% من إمداداتها من سلع ومواد خام من ا13 تعاونية مستهدفة، كانت تتعامل مع معظمها في السابق.
عمل المشروع على دعم تطوير التنافسية والوصول للأسواق للمنشآت النسوية المستهدفة أدى إلى زيادة طاقات هذه المنشآت، والتي لن يثبت مدى الفائدة التي ستحققها سوى الوقت.
Notes: While both companies with which the JP connected its targeted cooperatives witnessed impressive increases in their sales turnover in 2016 compared to the baseline (40% and 68.1%, respectively), the benefits of these increases did not trickle down to the cooperatives in tangible manner. Similarly, While NFC, an export intermediary used by the JP to support cooperatives- reported sourced 34% (US$ 60,294) of its total supplies from 13 cooperatives targeted by the JP, this did not represent a significant increase from the baseline. It is thus concluded that support to competitiveness of and access to markets for women-owned/run cooperatives has materialised in enhanced potential, which the test of time will only prove the extent to which it will be actualised.
Contributions to enhancing the capacities of relevant duty bearers to enhance policies for inclusive socio-economic development were considerable, but varied in their reach, depth and likely sustainability within the respective partner organizations. A greater level of achievement in such a way that reflects itself positively on employment creation in MSMEs and cooperatives as envisaged in the JP’s results framework was unrealistic given the current political and socio-economic realities in Palestine and what was planned by the JP. For policies to induce inclusive growth and employment creation in the MSME and cooperative sectors, three key things were needed: i) a more in-depth assessment of the systemic policy constraints preventing the growth of women-owned MSMEs and cooperatives; ii) focused lobbying and advocacy to affect changes in polices identified under (i); and iii) longer term capacity building and enforcement support. The JP delivered partially on (i) and (ii), but delivering on (iii) was not entirely possible given the 24 months given by the lifespan of the SDG-F programmes.

## Slide 13: الفعالية - النتائج
بالنسبة للنتيجة رقم 1
  ما تم تحقيقه من مخرحات على صعيد الوزارات المستفيدة من التدريب يوعلى صعيد ورقة السياسات يجب البناء عليه حتى يتسني تحقيق النتيجة المرجوة (تمكين المؤسسات من التخطيط وتبني سياسات وبرامج شمولية)
  تشير المشاورات مع المؤسسات إلى حاجة أكبر ونهج مختلف عن الذي تم تبنيه لبناء قدرات الوزارات واللجنة في مجالات تحليل السياسات والتخطيط من منظور النوع الاجتماعي، هذا فضلاً عن التدقيق على مدى إدماج النوع الاجتماعي في المؤسسات العامة.
  ما هو مؤكد أن الشركاء كان لديهم توقعات عالية من تدخلات المشروع، ولكن هذه التوقعات لم يتم تلبى بالشكل المطلوب.

## Slide 14: الكفاءة
نجاح المشروع في تحقيق قدر عالي من الكفاءة كان بتطلب تنفيذ الأنشطة في أوقات مناسبة وتوفير المصادر المختلفة في وقتها المخطط وذلك لارتباط المشروع بمدخلات من أربعة مشاريع أخرى، لكل منها موازنته ودورة حياته,
كان من الضروري للمشروع ايضاً أن يخطط بشكل دقيق لضمان اتساق تدخلاته المتعلقة بتطوير التنافسية ومخرجاتها مع رزنامة المشتريات المعتادة للمشترين.
عانى المشروع من تأخير في التنفيذ لعدة أسباب، كان ممكن أن يتخطى الكثير منها، مما أثر على كفاءه استخدام مصادره من جهة، وأضعاف امكانية الاستفادة من المشاريع الاخرى بفاعلية.
Notes: Joint-programming” was a particular strength, but “joint-implementation” has not fully materialized. Joint-programming contributed to the harmonization of UN support in the sense that UN input was well coordinated. The clear separation of tasks at the design stage prevented overlaps, but also did not encourage joint activities. While inputs converged at the beneficiary level, agencies still worked rather in parallel than jointly.
Programme governance and management did not materialise as planned, leading to some inefficiencies in coordination at the strategic level. The NSC met only once during the entire programme cycle to discuss the JP, while the PMC was never formed. Strategic coordination and coherence suffered as a result, with consequences for the operational “jointness” of the programme. The PMT, which met regularly throughout much of the programme implementation, not only had little remit to fill the gap left by the absence of the PSC and PMC, but itself also needed a higher level management structure for guidance and strategic decision making. Moreover, The PS did not function as expected due to changes in the SDG-F Programme Manager that took place during the implementation of the JP, and the inability of UN Women’s M&E Associate to allocate 50% of his time to the JP as planned due to other competing work demands on the one hand, and, reportedly, lack of authority to fully discharge the M&E function responsibilities vis-à-vis the JP on the other hand.
Generally, with some exceptions, outputs delivered were of good quality, judged by their fitness for use. Beneficiaries were mostly satisfied with the content of equipment they received through the matching funds, the hands-on product development advice provided, and branding and marketing advice. These were the outputs with most utility for the beneficiaries.

## Slide 15: الكفاءة
كان التخطيط المشترك أحد السمات القوية للمشروع، ولم يكن التنفيذ المشترك بنفس القدر من القوى.
لم يتم تشكيل اللجان التوجيهية والإدارية التي كان امن المفترض أن يتم تشكيلها حسب وثيقة المشروع ووفقاً لمعايير الصندوق. هذا الأمر أدى إلى إصعاف كفاءة الادارة والقيادة الاستراتيجية والتنسيق ما جعل المشروع غير قادر على اقبات القيمة المضافة للشراكة بين المؤسسات الأممية الثلاثة.
بشكل عام، ومع وجود بعذ الاستثناءات، طانت جودة مدخلات ومهرجات المشروع مقبولة.
Notes: Joint-programming” was a particular strength, but “joint-implementation” has not fully materialized. Joint-programming contributed to the harmonization of UN support in the sense that UN input was well coordinated. The clear separation of tasks at the design stage prevented overlaps, but also did not encourage joint activities. While inputs converged at the beneficiary level, agencies still worked rather in parallel than jointly.
Programme governance and management did not materialise as planned, leading to some inefficiencies in coordination at the strategic level. The NSC met only once during the entire programme cycle to discuss the JP, while the PMC was never formed. Strategic coordination and coherence suffered as a result, with consequences for the operational “jointness” of the programme. The PMT, which met regularly throughout much of the programme implementation, not only had little remit to fill the gap left by the absence of the PSC and PMC, but itself also needed a higher level management structure for guidance and strategic decision making. Moreover, The PS did not function as expected due to changes in the SDG-F Programme Manager that took place during the implementation of the JP, and the inability of UN Women’s M&E Associate to allocate 50% of his time to the JP as planned due to other competing work demands on the one hand, and, reportedly, lack of authority to fully discharge the M&E function responsibilities vis-à-vis the JP on the other hand.
Generally, with some exceptions, outputs delivered were of good quality, judged by their fitness for use. Beneficiaries were mostly satisfied with the content of equipment they received through the matching funds, the hands-on product development advice provided, and branding and marketing advice. These were the outputs with most utility for the beneficiaries.

## Slide 16: الكفاءة
بالنسبة لكفاءة التنفيذ فيما يتعلق بالرقابة والتقييم:
  منظومة لرقابة على المشروع لم تندمج إلا على مستوى إعداد التقارير الدورية بالرغم من محاولات الإدارة المسؤولة لبناء نظام تقييم أكثر اندماجاُ.
  العناصر الأساسية للتقييم والرقابة تم توفيرها، ولكن لم يتم التعامل معها ولم يتم تطويرها كما يجب أثناء التنفيذ.
  المشروع كان يتطلب جهود رقابة أكبر من تلك التي كان من الممكن توفيرها في سياق المخصصات المخطط لها والمتوفرة من جهة، بالإضافة إلى تمكين أكبر لقيادة دفة الرقابة والتقييم والتعلم.
Notes: The JP monitoring came together only at the level of reporting where the information had to be aligned with the required SDG-F format. The basic elements needed for JP monitoring were developed, but were not fully adhered during implementation. The M&E system envisaged in the SDG-F guidance to enable holistic monitoring, evaluation and learning beyond the JP’s monitoring matrix was only partially developed. The monitoring framework needed to be further developed and revised during implementation to ensure better alignment with the between certain JP activities implemented by specific partner agencies and the framework outcomes, as well as with partner agencies M&E systems. Despite the efforts of the M&E Officer to strengthen joint monitoring and accountability mechanisms, monitoring of the programme seemed to be perceived by partners to be the sole responsibility of UN Women, rather than being the joint and equal responsibility of all three agencies. The JP would have benefitted from a greater role for M&E than what was actually given, and from a stronger system for programme monitoring, oversight and quality assurance. A more assertive and inclusive Programme management would have greatly helped in this regard as well.

## Slide 17: الكفاءة
خطة التواصل والاتصال تم إعدادها وكانت ذات جودة جيدة، إلا أنه لم يتم تنفيذ إلأ جزء يسير منها.
لهذا السبب لم يستطع المشروع تحقيق وعده لكي يكون منصة لحشد التأييد ومناصرة القضايا الاقتصادية التي تعيق مشاريع النساء المستفيدات، ولا أن يكون منصة لرفع الوعي حول أهداف التنمية المستدامة.

## Slide 18: الأثر
كان له أثر على مستوى التأثير في بيئة الأعمال.
أثر ايجاباً من حيث تحسين مستوى الخدمات المقدمة للمنشآت الاقتصادية النسوية وتمكين النساء من استخدام والوصول لهذه الخدمات.
كان للمنح التي حصلت عليها المنشىآت المستفيدة أثر كبير على تجسين كفاءة عمل وتنافسية منتجات هذه المنشآت ما كان له بمساهمة كبيرة في تحقيق الانجازات آنفة الذكر على صعيد المخرجات والنتائج.
مساهمات واضحة باتجاه أهداف التنمية المستدامة SDGs.

## Slide 19: الاستدامة
من المبكر الحكم عليها
هناك عدد من العوامل التي تعزز فرص الاستدامة:
  تحسين البئية الداعمة لاستدامة النتائج
  دعم شعور المستفيدين بملكية المخرجات والنتائج
  بناء قدرات ومعارف يمكن للمستفيدين استخدامها مستقبلاً
  تعزيز العلاقات التجارية المبنية على الفائدة المشتركة بين المؤسسات
  ايجاد محطات بيع والعمل على زيادة قدرتها على الاستدامة
Notes: While the evaluation found that it was too early to judge sustainability of the JP, it also found the JP made appropriate and largely successful efforts to create or strengthen existing conditions likely to foster the continuation and dynamic adaptation of results under Outcome 1, including (i) contributing to strengthening the overall enabling environment for addressing women’s economic rights in the context of the local market for agricultural and cultural products as regards the existing legal and policy frameworks; (ii) supporting national ownership of results; and (iii) demonstrating how, through simple technical support and capacity building, private business could analyse their business performance and operations from a gender perspective, which is likely to be taken up in the future.

## Slide 20: الاستدامة
مع هذا..... هناك مخاطر تهدد فرص الاستدامة
فرص استدامة النتائج المرتبطة بالنتيجة الثانية عالية خصوصاً للشركات النسوية، إلا أنها غير منظورة للتعاونيات النسوية.
العلاقات السوقية التي تم بنائها بين التعاونيات ونيوفارم والروزنة والثمار وبين الشركة والمشترين خارح فلسطين ستستمر طالما توفر من يدعمها.
في حين أن المساحات المستخدمة لعرض المنتجات النسوية سيتم الاستمرر في استخدامها لهذا الأمر، إلا أن استدامة نموذج المحطة الواحدة ستكون ممكنة فقك في حالتين: التمويل الخارجي للاستمرار وقيام منتدى سيدات الاعمال بتطوير نموذج عمل تجاري مستدام يتيح الاستمرارية، وهذا يتطلب الدعم بحد ذاته.
Notes: Sustainability threats exist nonetheless. These include the continued lack of buy-in and support from high-level decision makers in relevant government agencies, including for the policy paper; and the challenging overall socio-economic situation and political instability affecting Palestine. The latter contributes to the existing, (and likely worsening) situation as regards the availability resources for government institutions (and NGOs), many of which are dependent on external donor funding when it comes to gender equality related initiatives.
Sustainability of Outcome 2 results, and particularly vis-à-vis MSMEs, is likely due to the high levels of interest and commitment to continuous improvement. Most but not all MSMEs and cooperatives expressed that they would continue participating in trade fairs, using the know-how they have obtained in the course of the programme. In some cooperatives and MSMEs, there is little evidence that capacities built will be maintained without further external support. The sustainability of market linkages established/facilitated by the JP is uncertain, but would be likely if additional follow-up is provided.
The OSS/BDSH that was created by the JP is currently an integral part of the BWF’s structure. However, while BWF is actively seeking funds to maintain the services the OSS had provided under the JP, it is not yet financially sustainable, and the business model that it could use for this purpose is yet to be developed. Hence, sustainability of the services provided within the framework of the JP through the OSS/BDSH is likely so long BWF is able to fundraise for it, and, over the medium term, develop a business model to sustain it.

## Slide 21: الدروس المستفادة
نجاح المشاريع المشتركة في
Internal risks to the effective implementation of JPs are plentiful, and can sometimes have more serious implications than external risks if not well identified and mitigated during both the design and implementation of JPs.
JPs need to be realistic about their objectives and targets. This requires analysis of the baseline situation, understanding of the operating context, and changes processes.

## Slide 22: التوصيات
متعلقة بالمشروع قيد التقييم
  تعميم نتائج المشروع، بما في ذلك نتائج التقييم
  متابعة انهاء الانشطة التي لم تكن قد انتهت اثناء التقييم قبل انتهاء فترة التنفيذ، وفي حال تعذر ذلك التأكد من وجود مصادر داخلية لمتابعتها.
  وضع خطة لمتابعة العلاقات التي تم بنائها مع المشترين الخارجيين لحين تحقيق نتائج بخصوصها.
  هناك بعذ الجمعيات التي تلت معدات ولم تستخدمها بعد نتيجة لعدم قيام الموردين بتدريبهم عليها. لذا التأكد من قيام الموردين بالتدريب المطلوب.

## Slide 23: التوصيات
عند تصميم وتنفيذ مشاريع مستقبلية شبيهة
  التأكد من توفير وقت ومصادر كافية للتصميم، مع التأكيد على ضرورة اختيار ومشاركة الفئات المستهدفة والمؤسسات الشريكة في التصميم قدر الامكان.
  ضمان صياغة أفضل للنتائج والإطار المنطقي، بما في ذلك التأكد من واقعية الاهداف في سياق محددات التنفيذ المرتبطة بالسياق العام، والمصادر المالية المتاحة، والوقت المتاح.
  التأكد من تشكيل اللجان التوجيهية والإدارية عند فترة التصميم، وادماجها في عملية التصميم.
  وضع آليات عمل تضمن قيام فرق المشروع في المؤسسات الشريكة باجتماعات دورية للتخطيط اوالرقابة المشتركة وذلك لتعزيز التنفيذ المشترك فعلياً.

## Slide 24: التوصيات
في حال الرغبة بتصميم مشروع مستقبلي شبيه أو مرحلة جديدة....
  استثمار الممارسات الجيدة التي تم تنفيذها، التحول من التنفيذ المباشر لأنشطة بناء القدرات التنافسية إلى تيسير وتحفيز بناء العلاقات التجارية بين أطراف الانتاج المختلفة في القطاع الخاص بحيث تحفز الكبرى منها لادماج الصغرى في سلاسل توريداتها وتساعدها لمواكبة الاستجابة لمتطلباتها بطريقة تضمن استدامة هذه العلاقة بين الطرفين.

## Slide 25: شكراً.....