[image: image1.png]United Nations Entity for Gender Equality
and the Empowerment of Women




Terms of Reference

National Evaluation Consultant 
to Support Conducting a Country Portfolio Evaluation for UN Women in Palestine
	Location:
	State of Palestine

	Application Deadline:
	5 February 2017

	Additional Category:
	National Consultant

	Type of Contract:
	Special Service Agreement / SSA

	Languages Required:
	Arabic and English 

	Starting Date:
(date when the selected candidate is expected to start)
	12 February 2016

	Duty Station
	Home Based with frequent travel to West Bank locations (and to Gaza Strip – upon availability of a valid permit)

	Duration of Initial Contract:
	25 working days (within 3 months period)

	Expected Duration of Assignment:
	25 working days (within 3 months period)

	


I Background
UN Women, grounded in the vision of equality enshrined in the Charter of the United Nations, works for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security. Placing women’s rights at the center of all its efforts, UN Women leads and coordinates United Nations system efforts to ensure that commitments on gender equality and gender mainstreaming translate into action throughout the world. It provides strong and coherent leadership in support of Member States’ priorities and efforts, building effective partnerships with civil society and other relevant actors.

UN Women plays an innovative and catalytic role in the State of Palestine since it began its operations in Palestine in 1997 (as UNIFEM).  UN Women’s mandate in Palestine is derived from its global mandate. The Country Office focuses on assisting and consolidating efforts undertaken by the Palestinian Authority, aligning strategies and programs with Palestinian national priorities and harmonizing such work across the UN Country Team. UN Women focuses on strengthening the efficiency and accountability of national institutions as duty bearers and supporting women as rights holders through effective partnerships across civil society. The current SN is connected to the UN Women Global Strategic Plan and aligned with key national and international development priorities including the MDGs, the Palestinian Authority Cross Sector National Gender Strategy, National Strategy to Combat Violence against Women, Palestinian National Plan, and the current UN Development Assistance Framework (UNDAF) for Palestine. During these years, the SN has been modified to take into consideration findings from mid-term reviews, lessons learned and incorporating evolving and new priorities such as the SDGs, UN Women’s Flagship Initiatives, updated national strategies, the ratification of CEDAW in Palestine and the new National Action Plan on Women Peace and Security.

This high-level strategic package (SN/AWP, DRF and OEEF) is the foundation for UN Women’s Country Office program delivery and achievement of development results in Palestine. The Country Office is preparing for its final year in the current strategic note and beginning the planning for the new SN 2018-2020. This strategic process is in alignment with the new UNDAF and other national priorities and strategies that are currently in the planning process as well.  As such,  UN Women Country Office in Palestine is commissioning a Country Portfolio Evaluation (CPE). The CPE is a systematic review and assessment of the contributions made by UN Women to development results with respect to gender equality and women’s empowerment in Palestine. The main point of reference for this evaluation will be the Strategic Note (SN) 2014-2017 and accompanying Annual Work Plan (AWP) including the Development Results Framework (DRF) and the Organization Effectiveness and Efficiency Framework (OEEF). The intended outcomes of this evaluation are to ensure progress toward results and accountability to all stakeholders; provide credible and reliable evidence for decision-making and evidence-based advocacy; and contribute to lessons learned about the normative, operational and coordination work (which are the three key pillars of UN Women’s operational mandate) in relation to gender equality and women’s empowerment for future strategic planning.  This terms of reference is for an external national consultant who will work together with an international national consultant recruited through a separate TOR for conducting the evaluation.   
II Program Objectives and Strategy
The current SN outlines five result areas as outlined in the DRF. The DRF and the OEEF are the basis for the CPE. As such, the following summarizes the outcomes of each result and its key strategies.
Development result framework (DRF)
1. Women’s increased leadership and participation in the decisions that affect their lives 

Through supporting a women’s rights agenda in legal, regulatory and institutional frameworks, UN Women aims to create spaces for women’s participation in decision making processes and engagement in political, economic and social initiatives across Palestine. Complementing the normative focus, UN Women, through effective civil society partnerships, seeks to increase women’s participation and leadership as well as cultivate changes in behaviour about the importance of women’s participation. Key strategies include a focus on working across key political and governing institutions at the national level in combination with support to local community-based organizations that work directly with women and their respective communities across Palestine.
2. Increased economic empowerment of women, especially those most excluded

UN Women aims to secure Palestinian women’s livelihoods as a means to participate in and benefit from economic development. Through improving capacity, knowledge and building of networks, UN Women seeks to foster an enabling economic environment, policies and regular frameworks that strengthen women’s economic rights and security. Key strategies include facilitating gender sensitive services (e.g. financial, market, infrastructure, etc.), policies, and regulations that support women owned businesses.
3. Preventing violence against women and girls and expanding access to services

UN Women aims to improve access to security, protection and justice for Palestinian women and girls who are survivors of violence. The approach is two-fold with a focus on the normative frameworks and support to related institutions, and support through civil society partnerships to accessible quality services. Key strategies include applying international standards and methods as well as utilizing a holistic and multi-sector approach. Additionally, UN Women seeks to focus on collaboration and coordination across actors working on violence including national authorities, civil society and UNCT partners. 
4. Women’s leadership in peace, security and humanitarian response

UN Women aims to effectively integrate gender equality into Palestine’s humanitarian programming response and assistance as well as create space for women’s involvement in all matters related to peace and security. UN Women has supported efforts to this end working with the women’s machinery, national authorities responsible for humanitarian, and peace and security initiatives and facilitating networks of women’s civil society organizations working on these issues across Palestine and in particular Gaza. Key strategies include promoting the use of international humanitarian, legal and human rights instruments and standards related to gender equality in humanitarian work and women’s participation in matters related to peace and security. Additionally, UN Women seeks to position itself as a facilitator for such dialogues.
5. National planning and budgeting process promote stronger institutional accountability to gender equality commitments

UN Women aims to increase the financial commitments (international and domestic) for investments related to gender equality and women’s empowerment. UN Women is working to ensure that mechanisms are in place which can monitor the implementation of gender related commitments by national authorities and facilitate donor coordination to this end. Key strategies include ensuring gender responsive planning, budgeting and financing is utilized by national authorities, accountability mechanisms are in place and civil society organizations are equipped to monitor and advocate for accountability and transparency in relation to financial aid for gender equality.
UN Women’s theory of change is that these results can be achieved if effective gender mainstreaming occurs in national plans, policies, legal frameworks and services; women are endowed with the skills and capacities to make and take decisions impacting their lives; and communities are aware and understand the importance of protecting and advancing women’s rights, participation and gender equality.

Organizational effectiveness and efficiency framework (OEEF)
In addition to evaluating the development results, the CPE will evaluate UN Women’s achievements toward meeting the outputs articulated in the OEEF including the following areas of focus:
· More effective and efficient lead and coordinator on gender equality commitments across the UN Country Team

· Institutionalize a strong culture for results-based management

· Improve internal management and operational functions

· Leverage and manage resources more effectively
SN scope, timeframe and management:
The following points are relevant to the evaluation in relation to the Strategic Note:
· The geographical scope of the SN is across all of Palestine - West Bank (Areas A, B and C), Gaza and East Jerusalem.

· The timeframe is from 2014 through 2017. The original scope was through 2016 but owing to the importance of aligning with the National Development Plan and UNDAF, the SN was extended for one additional year. A mid-term review was conducted on August 2015.

· Stakeholders include: Palestinian Authority (including Ministries, Office of the Prime Minister, Office of the Attorney General, Police and local councils), the UN Country Team and the UN offices that are part of the humanitarian clusters, civil society organizations and community-based organizations, and donor community including the local aid coordination mechanisms.

· The Representative is responsible for the overall management of the SN and its implementation. There is a senior management team in place and all staff members have a corresponding role and responsibility to implementation rooted in their respective AWPs.
UN Women’s program in Palestine is rooted in the above Strategic Note and maintains a main office in East Jerusalem with smaller offices in Ramallah in the West Bank andin Gaza.
III Purpose of the Country Portfolio Evaluation
CPE is an opportunity to ensure the accountability of UN Women to its donors, partners  and  other  stakeholders  and  to  facilitate  learning about what works in different contexts with  a  view to  improving  the  relevance  and performance of  interventions  over time. Additionally, the evaluation findings will inform decision making processes especially for the next strategic planning process which will commence in 2017.
The key principles for gender-responsive evaluation at UN Women are: 1) National ownership and leadership; 2) UN system coordination and coherence with regard to gender equality and the empowerment of women; 3) Innovation; 4) Fair power relations and empowerment; 5) Participation and inclusion; 6) Independence and impartiality; 7) Transparency; 8) Quality and credibility; 9) Intentionality and use of evaluation; and 10) Ethics. 
Country Portfolio Evaluation (CPE) is a systematic assessment of the contributions made by UN Women to development results with respect to gender equality at the country level. The UN Women portfolio responds to its three core mandates, which include normative, program and coordination work. It uses the Strategic Note as the main point of reference.

It is a priority for UN Women that the CPE will be gender-responsive, and will actively support the achievement of gender equality and women’s empowerment.

The primary intended users of the evaluation are the UN Women Country Office team but equally useful for national authorities, civil society partners, UNCT partners and relevant donors.

The evaluation is mainly designed to:
1. Learning and improved decision-making to support the development of new programs.    

2. Accountability for the development effectiveness of the CO Strategic Note.

3. Capacity development and mobilization of national stakeholders to advance gender equality and the empowerment of women.      

IV Evaluation Objectives
The main objectives of the CPE are to:
· Assess the relevance of UN Women contributions to national priorities and alignment with international agreements and conventions on gender equality and women’s empowerment
· Assess effectiveness and organizational efficiency in progressing towards the achievement of gender equality and women’s empowerment results as defined in the Strategic Note including testing the validity of theories of change
· Analyze how human rights approach and gender equality principles are integrated in the design and implementation of the Strategic Note

· Identify and validate lessons learned, good practices and examples of innovation that support gender equality and human rights 

· Provide insights into the extent to which the UN Women has realized synergies between its three mandates (normative, coordination and operations) and on how to leverage the UN system to increase development results on gender equality 

· Provide forward-looking actionable recommendations with respect to the development of the next Strategic Note

· Support the UN Women CO to improve its strategic positioning to better support the achievement of sustained gender equality and women’s empowerment

The evaluation will apply the OECD-DAC evaluation criteria of relevance, efficiency, effectiveness, and sustainability as well as the additional criterion of human rights and gender equality by addressing the following questions (note that the questions are not comprehensive and the national evaluation consultant is expected to ensure alignment of the questions with the context within Palestine):

Relevance: 
The extent to which strategic choices have maximized UN Women’s comparative advantages in addressing priorities for gender equality and women’s empowerment
· How has UN Women positioned itself within the national development/policy space, and what are its strategies in assisting efforts on gender equality and the empowerment of women? 

· What is UN Women’s comparative advantage compared with other UN entities and key partners? 

· Was UN Women responsive to the evolution of development challenges and the priorities in national strategies, or significant shifts due to external conditions? How are the short-term requests for assistance balanced against long-term development needs? 

· Is the portfolio aligned with national policies and international human rights norms? 

· Is the choice of interventions most relevant to the situation in the target thematic areas? 

· Is the choice of partners most relevant to the situation of women and marginalized groups? Are the existing partnerships working?

Efficiency:
The extent to which resources, organizational structures and management processes add to UN Women’s productive capacity
· To what extent does the UN Women country office management structure support efficiency for implementation? 
· Does the organization have access to the necessary skills, knowledge and capacities needed to deliver the portfolio?
· How well have resources and risks been managed to ensure results?
· Has a results-based management system been established and implemented?

· Are UN Women’s knowledge management and communications capabilities and practices relevant to the needs of the portfolio and partners?

· Are the interventions achieving synergies within the UN Women portfolio and the work of the UN country team?
· Is the balance and coherence between programming operational coordination and policy-normative work optimal? 

Effectiveness:
The extent to which UN Women has contributed to achieving planned outcomes and mitigating negative externalities
· To what extent have planned outputs been achieved on time? 
· Are interventions contributing to the expected outcomes? For whom? 
· What unexpected outcomes (positive and negative) have been achieved? For whom? 
· What has UN Women’s contribution been to the progress of the achievement of outcomes? What are the main enabling and hindering factors to achieving planned outcomes? 
· What contribution is UN Women making to UN coordination on gender equality and the empowerment of women? Which roles is UN Women playing in this field? To what extent has gender equality and women’s empowerment been mainstreamed in UN joint programming such as UNDAF? 
· What contribution is UN Women making to implementing global and national norms and standards for gender equality and the empowerment of women?

Sustainability:
The extent to which positive outcomes can be maintained and advanced independently by local actors
· To what extent was capacity developed in order to ensure sustainability of efforts and benefits?
· Is there national ownership and are there national champions for different parts of the portfolio? What local accountability and oversight systems have been established to support the continuation of activities? 
· How did UN Women design to scale-up coverage and effects of its interventions? Did UN Women use and capitalize upon pilot/catalytic initiatives?

Human Rights and Gender Equality:
The extent to which the principles and standards of global human rights norms on gender equality and women’s empowerment are addressed in UN Women’s country portfolio
· Is the portfolio addressing the root causes of gender inequality?
· To what extent is the portfolio changing the dynamics of power in relationships between different groups? 
· Has the portfolio been implemented according to human rights and development effectiveness principles: Participation/empowerment, inclusion/non-discrimination, national accountability/transparency? Which groups is the portfolio reaching the most, and which are being excluded?
The evaluation is expected to take a gender-responsive approach. Gender-responsive evaluations utilize a systematic approach to examining factors related to gender that assesses and promotes gender equality issues and provides an analysis of the structures of political and social control that create gender equality. This technique ensures that the data collected is analyzed in the following ways:

1. Assessing the extent to which the intervention was guided by the relevant international (national and regional) normative frameworks for gender equality and women’s rights, UN system-wide mandates and organizational objectives
2. Determining the claims of rights holders and obligations of duty bearers and identifying trends, common responses and differences between groups of stakeholders
3. Assessing the extent to which participation and inclusiveness was maximized in the interventions planning, design, implementation and decision-making processes
4. Triangulating information to identify similarities and/or discrepancies in data obtained in different ways (i.e., interviews, focus groups, observations, etc.) and from different stakeholders (e.g., duty bearers, rights holders, etc.)
5. Identifying the context behind the numbers and people (using case studies to illustrate broader findings or to go into more depth on an issue) and integrating into the analysis of relationships and power dynamics, and the structures that contribute to inequalities
6. Assessing the extent to which sustainability was built into the intervention through the empowerment and capacity building of women and groups of rights holders and duty bearers

The preliminary findings obtained through this process should be validated through a stakeholder workshop with evaluation management and reference groups towards the end of the primary data collection stage.

V Scope of the Evaluation
The scope of the CPE is based on assessing the 2014-2017 SN and the 2014-2016 AWPs.  A mid-term review was undertaken in August 2015 according to UN Women Program Division guidance and will be used as appropriate to inform the CPE. Considerations should also be given to corporate, thematic, regional and country office evaluation plans. The scope of a CPE is expected to include normative, coordination and operational work in all thematic areas prioritized in the SN and will include joint programs and programming. Where joint programs are included in the analysis, the evaluation will consider both the specific contribution of UN Women, and the additional benefits and costs from working through a joint modality. The intended planning of the CPE does not overlap with other national or international related evaluative process and in fact aligns with processes for upcoming planning in 2017.
The evaluation will apply the Women’s Empowerment Framework (developed by Sara Hlupekile Longwe) as a way to conceptualize the process of empowerment. This will help frame progressive steps towards increasing equality, starting from meeting basic welfare needs to equality in the control over the means of production.

The national evaluation consultant is expected to undertake a rapid evaluability assessment in the Inception. This should include the following:

1. A review of the conduciveness of the context for the evaluation;
The national evaluation consultant will need to undertake an initial assessment of the availability of secondary data necessary for the evaluation in the Country Office. Additionally, in circumstances where constraints are faced – such as limited travel or accessibility to project sites, these limitations should be understood and generalizing findings should be avoided where a strong sample has not been used. In addition, cultural aspects that could impact the collection of data should be analyzed and integrated into data collection methods and tools. 
VI Evaluation Design
Detailed guidance on the Country Portfolio Evaluation (CPE) approach has been developed by UN Women and will be made available to the selected national evaluation consultant in the evaluation inception phase. While the final evaluation methodology and questions will be contextualized and adapted for each country during the inception phase, it is recommended that the evaluations use a theory-based cluster design. The performance of the county portfolio will be assessed according to the theory of change stated in the Strategic Notes. To achieve sufficient depth, the evaluation will cluster programming, coordination, and policy activities of the Country Office around the thematic areas stated in the UN Women Strategic Plan. 

The evaluation will undertake a desk-based portfolio analysis that includes a synthesis of secondary results data for the Development Results Framework and the Organizational Effectiveness and efficiency framework of the Country Office. This will cover all activities undertaken by the Country Office.

The portfolio analysis will be triangulated through a mixed methods approach that will include:

1. Desk review of additional documentary evidence;

2. Consultation with all main stakeholder groups; and

3. An independent assessment of development effectiveness using Contribution Analysis.

The evaluation is expected to apply a gender responsive approach to assessing the contribution of UN Women to development effectiveness. It should identify expected and unexpected changes in target and affected groups. It is anticipated that the evaluation will apply process tracing to identify the mechanisms of change and the probable contributions of UN Women.

The methods should include a wide range of data sources (including documents, field information, institutional information systems, financial records, beneficiaries, staff, funders, experts, government officials and community groups). The evaluation is particularly encouraged to use participatory methods to ensure that all stakeholders are consulted as part of the evaluation process. At a minimum, this should include participatory tools for consultation with stakeholder groups and a plan for inclusion of women and individuals and groups who are vulnerable and/or discriminated against in the consultation process (see below for examples).

The use of participatory analysis, video, photography or other methods are particularly encouraged as means to include rights holders as data collectors and interpreters. The national evaluation consultant should ensure that plans on how protection of participants and respect for confidentiality are relevant to the context of Palestine.   

The evaluations will use a wide range of relevant participatory data collection tools (please refer to the guidance note):

· (Group) Interviews

· Secondary document analysis

· Observation

· Multimedia (photography, drawing)

· Others [See UN Women CPE Guidance]

The evaluation is expected to reconstruct the theories of change using a participatory process during the Inception Workshop. This should be critiqued based on feminist and institutional analysis. The evaluation will apply Contribution Analysis to assess the effectiveness of UN Women’s country portfolio.

The evaluation is expected to apply a purposive sampling design based on the following minimum standards:

· One or two projects per thematic cluster of operational work;

· The most strategically important thematic interventions for the CO:

· Relevance of the subject. Is the project a socioeconomic or political priority of the mandate and role of UN Women? Is it a key priority of the national plan, UN Women strategic note or the AWP? Is it a geographic priority of UN Women, e.g., levels of gender inequality and the situation of women in the country?
· Risk associated with the project. Are there political, economic, funding, structural or organizational factors that present potential high risk for the non-achievement of results or for which further evidence is needed for management decision-making?
· Significant investment. Is the intervention considered a significant investment in relation to the overall office portfolio (more than one-third)?

2. The richest learning opportunities.
· Potential for replication and scaling-up. Would the evaluation provide the information necessary to identify the factors required for the success in a thematic area and determine the feasibility of replication or scaling-up? Does the thematic area include a pilot and/or an innovative initiative?
· Knowledge gap. Will the evaluation help to fill a pressing knowledge gap in relation to achieving gender equality or the empowerment of women?

VII Duties and Responsibilities:

UN Women has hired an International Evaluation Consultant to lead the execution of the Country Portfolio Evaluation. Through this advertisement, UN Women wishes to hire a national consultant to support the execution of the Country Portfolio Evaluation and provide key support to the International Evaluation Consultant. The National Evaluation Consultant will report directly to UN Women Palestine Country Office Evaluation Manager.

The National Consultant is expected to: 

· Provide a quality context analysis for the CPE and support the development of context specific tools and evaluation methods; 

· Ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights; 

· Lead the inception workshops and support and facilitate the data collection process at the national level through organizing and facilitating interviews, focus groups discussions and national round table discussions and workshops with national partners and stakeholders. 

· Identify sample limitations at an early stage and triangulate information to help ensure robust, relevant and reliable results

· Set the field mission agenda in collaboration with the International Consultant – expected to take place in February 

· Report to the UN Women Evaluation Manager and keep them well informed of all actions related to executing the CPE.

The National Evaluation Consultant is expected to discuss during the Inception Workshops how the process will ensure participation of stakeholders at all stages, with a particular emphasis on rights holders and their representatives:
· Design (inception workshop);

· Consultation of stakeholders;

· Stakeholders as data collectors;

· Interpretation;

· Reporting and use.

Key stakeholders of the CPE include governing authorities, civil society actors, donors and UNCT members. The national evaluation consultant will ensure that those key stakeholders are reached out to as related to the UN Women programs integral to the SN. 
The national evaluation consultant is encouraged to further analyze stakeholders according to the following characteristics:
· System roles (target groups, programme controllers, sources of expertise, and representatives of excluded groups);
· Gender roles (intersections of sex, age, household roles, community roles);
· Human Rights roles (rights holders, principal duty bearers, primary, secondary and tertiary duty bearers);
· Intended users and uses of the respective evaluation.

The national evaluation consultant is encouraged to extend this analysis through mapping relationships and power dynamics as part of the evaluation. It is important to pay attention to participation of rights holders—women and vulnerable and marginalized groups—to ensure the application of a gender-responsive approach. It is also important to specify ethical safeguards that will be employed. 

The national evaluation consultant is expected to validate findings through engagement with stakeholders at stakeholder workshops, debriefings or other forms of engagement. 

Furthermore, UN Women will establish an Evaluation Reference Group. The reference group is an integral part of the evaluation management structure and will facilitate the participation of relevant stakeholders in the design and scope of the evaluation, raising awareness of the different information needs, quality assurance throughout the process and in disseminating the evaluation results. The Reference Group will comprise of select UN Women Staff, select staff of responsible parties (government and non-government), and donor representatives and support the processes and methods of the evaluation. 
VIII Timeframe
The following is the suggested timeframe for the national evaluation consultant to accomplish the contractual responsibilities for the CPE. The exact timing will be determined in close consultation with the country office. The expected activities and deliverables in country and the number of work days are listed below:
·  Inception phase: Inception meeting, analysis of contextual background, review and contextualize data proposed data collection tool, review inception report, participate in inception report presentation. 7 days

· Data collection phase: Data collection including initial debriefing evaluation management group; 10 Days

· Debriefing Evaluation Management Group; 1 Day

· Reporting phase: Analysis of data and preparation of draft report in Arabic English; presentation of draft report to reference group.  4 Days

· Follow up and use phase: Finalize report, include management feedback and submit final edited version; 3 Days

IX Expected Deliverables
The following are the expected deliverables for the national evaluation consultant:

Contextual Background Analysis: 23 February 2017
Data collection tools incorporating contextual background in cooperation with the International Consultant: 27 February

2017








Inception workshop and Power Point Presentation of for EMG and ERG in English and Arabic (including refining evaluation uses, framework, stakeholder analysis and theory of change): 27 February 2017







Main Findings Brief Report in high quality English and Arabic: 20 March 2017
Validation and participatory recommendation session presentation including analysis Power Point presentation of preliminary findings in English and Arabic: 27 March 2017
Comments and Feedback on Draft Evaluation Report: 31 March 2017
Final Summary Report in Arabic and English: 20 April 2017
The evaluation will have the following management structures:
· Country Office Evaluation Manager and Regional Evaluation Specialist for coordination and day-to-day management;

· Evaluation Management Group for administrative support and accountability: Special Representative or Deputy Representative, Evaluation Manager, Regional Evaluation Specialist
· Evaluation Reference Group for substantive technical support: UN Women programme staff, National government partners, Development partners/donors, UNCT representatives, Civil Society partners.

The main responsibilities of the CPE Team are as follows:

The International Evaluation Consultant:

The evaluation will be carried out by an International Evaluation Consultant hired by UN Women and who will have the overall responsibility for the assignment. The International Evaluation Consultant will report directly to UN Women’s Evaluation Manager and will be responsible for all logistics requested for carrying the CPE, and the development and dissemination of methodological tools together with the national consultant as specified in this TOR.   

The National Evaluation Consultant

1. To avoid conflict of interest and undue pressure, the National Evaluation Consultant needs to be independent, implying that they must not have been directly responsible for the design, or overall management of the subject of the evaluation, nor expect to be in the near future.
2. The National Evaluation consultant must have no vested interest and must have the full freedom to conduct their evaluative work impartially. They must be able to express their opinion in a free manner.
UN Women’s Country Office Evaluation manager 
1. Conducts a preliminary assessment of the quality of reports and comments for action by the national evaluation consultant
2. Provides substantive comments on the conceptual and methodological approach and other aspects of the evaluation design

3. Initiates timely payment of the national evaluation consultant
4. Coordinates feedback on the draft and final report from the regional evaluation specialist, management and reference groups
5. Maintains an audit trail of comments on the evaluation products so that there is transparency in how the national evaluation consultant is responding to the comments
Evaluation Management and Reference Groups (including the Regional Evaluation Specialist)
1. Provide substantive comments and other operational assistance throughout the preparation of reports.
2. Where appropriate, participates in meetings and workshops with other key partners and stakeholders before finalization of reports. 
In order to maximize stakeholder participation and ensure a gender-responsive evaluation, the evaluation manager will support the national evaluation consultant during data collection in the following ways:
1. Consult partners regarding the evaluation and the proposed schedule for data collection

2. Arrange for a debriefing by the national evaluation consultant prior to completion of data collection to present preliminary and emerging findings or gaps in information to the evaluation manager, evaluation management and reference groups
3. Ensure the stakeholders identified through the stakeholder analysis are being included, in particular the most vulnerable or difficult to reach, and provide logistical support as necessary contacting stakeholders.  
4. Ensure that a gender equality and human rights perspective is streamlined throughout the approach, and that the national evaluation consultant is abiding by the ethical principles outlined below.

XI National Evaluation Consultant, Skills and Experience
The evaluation will be conducted by two external consultants, one international and one national . The National Evaluation Consultant will be recruited by UN Women based on their demonstrated requisite skills needed to carry out the evaluation as identified in this ToR. The National Evaluation Consultant will be engaged under the Special Service Agreement (SSA), for a total number of 25consultancy days in the period between February and April 2017. 
The international evaluation consultant will have the overall responsibility for all deliverables while the national evaluation consultant will have the responsibility for all deliverables described in this TOR.   

The national evaluation consultant recruited by UN Women per this TOR is expected to submit all deliverables under the evaluation as per the approved work plan and schedule for submitting all deliverables. 
CORE VALUES / GUIDING PRINCIPLES:

· Integrity: Demonstrating consistency in upholding and promoting the values of UN Women in actions and decisions, in line with the UN Code of Conduct; 

· Cultural Sensitivity/Valuing diversity: Demonstrating an appreciation of the multicultural nature of the organization and the diversity of its staff. Demonstrating an international outlook, appreciating differences in values and learning from cultural diversity.  

CORE COMPETENCIES:

· Ethics and Values: Demonstrating / Safeguarding Ethics and Integrity; 

· Demonstrate corporate knowledge and sound judgment; 

· Developing and Empowering People / Coaching and Mentoring: Initiative-taking; coaching and mentoring ability; 

· Working in Teams: Acting as a team player and facilitating team work; 

· Communicating Information and Ideas: Facilitating and encouraging open communication in the team, communicating effectively; 

· Self-management and Emotional intelligence: Creating synergies through self-control.

· Conflict Management / Negotiating and Resolving Disagreements: Managing conflict; 

· Knowledge Sharing / Continuous Learning: Learning and sharing knowledge and encourage the learning of other.

FUNCTIONAL COMPETENCIES:

· Proven experience in development of training manuals, review of frameworks and policies, and gender mainstreaming;

· Demonstrated skills as a trainer/facilitator;

· Strong report writing skills; 

· Outstanding knowledge of gender, women’s rights and the different challenges with regard to gender equality and women political participation, especially in Palestine;

· Proven strong coordination and facilitation skills; 

· Proven experience in capacity development;

· Strong communication skills in English and Arabic (oral and written);

· Ability to work under pressure and to deliver on time; and

· Results oriented, flexible and with problem solving skills.
· Knowledge of the role of UN Women and its programming, coordination and normative roles at the regional and country level 

· Technical competence in the thematic areas to be evaluated

· Process management skills, including facilitation and communication skills

· Good understanding of the development context as well as humanitarian work and coordination mechanisms
· Good understanding of the development context as well as humanitarian work and coordination mechanisms
Education
· Master’s degree or equivalent in social science, development studies, gender studies, or equivalent
Experience: 

· At least 7 years of professional experiences in conducting evaluations 
· Documented previous experience in conducting evaluations for gender-responsive projects/programmes; at least 2 evaluations
· Extensive knowledge of and experience in the development context in Palestine; minimum documented experience of 10 years within the development work in Palestine.
· Experience in gender analysis and human-rights based approaches is an asset
Languages: 
· Fluent in English and Arabic. 
XII Ethical Code of Conduct
UN Women has developed a UN Women Evaluation Consultants Agreement Form for evaluators that must be signed as part of the contracting process, which is based on the UNEG Ethical Guidelines and Code of Conduct. These documents will be annexed to the contract. The UNEG guidelines note the importance of ethical conduct for the following reasons:

1. Responsible use of power: All those engaged in evaluation processes are responsible for upholding the proper conduct of the evaluation.
2. Ensure credibility: With a fair, impartial and complete assessment, stake- holders are more likely to have faith in the results of an evaluation and to take note of the recommendations.
3. Responsible use of resources: Ethical conduct in evaluation increases the chances of acceptance by the parties to the evaluation and therefore the likelihood that the investment in the evaluation will result in improved outcomes.
Specific safeguards must be put in place to protect the safety (both physical and psychological) of both respondents and those collecting the data. These should include:

1. A plan is in place to protect the rights of the respondent, including privacy and confidentiality
2. The interviewer or data collector is trained in collecting sensitive information, and if the topic of the evaluation is focused on violence against women, they should have previous experience in this area
3. Data collection tools are designed in a way that are culturally appropriate and do not create distress for respondents
4. Data collection visits are organized at the appropriate time and place so as to minimize risk to respondents
5. The interviewer or data collector is able to provide information on how individuals in situations of risk can seek support

The evaluation’s value added is its impartial and systematic assessment of the programme or intervention. As with the other stages of the evaluation, involvement of stakeholders should not interfere with the impartiality of the evaluation.

If the national evaluation consultant identify issues of wrongdoing, fraud or other unethical conduct, UN Women procedures must be followed and confidentiality be maintained. The UN Women Legal Framework for Addressing Non-Compliance with UN Standards of Conduct, and accompanying policies protecting against retaliation and prohibiting harassment and abuse of authority, provide a cohesive framework aimed at creating and maintaining a harmonious working environment, ensuring that staff members do not engage in any wrongdoing and that all allegations of wrongdoing are reported promptly, investigated and appropriate action taken to achieve accountability. The UN Women Legal Framework for Addressing Non-Compliance with UN Standards of Conduct defines misconduct and the mechanisms within UN Women for reporting and investigating it. More information can be provided by UN Women if required.
XIII Application procedure

This SSA modality is governed by UN Women General Terms and Conditions. UN Women will only be able to respond to applicants who meet the minimum requirements. 

Candidates should be able to quickly submit degree certificates, medical certification (of good health), should they be requested in consideration of this consultancy.

XIV Evaluation of applicants
Candidates will be evaluated using a cumulative analysis method taking into consideration the combination of the applicants’ qualifications mentioned above; and financial proposal. A contract will be awarded to the individual national evaluation consultant whose offer receives the highest score out of below defined technical and financial criteria. Only candidates obtaining a minimum of 70 points in the technical evaluation will be considered for financial evaluation. The financial proposal should be daily lump sum incorporating daily fees, transportation costs and any other logistical expenses.
Technical Evaluation (70%) – max. 70 points:
Relevant education; max 10 points
· Master’s degree in relevant field
Experience; max 60 points

· At least 7 years of professional experiences in conducting evaluations; max 20

· Documented previous experience in conducting evaluations for gender-responsive projects/programmes; at least 2 evaluations; max 20

· Extensive knowledge of and experience in the development context in Palestine; minimum documented experience of 10 years within the development work in Palestine; max 10

· Experience in gender analysis and human-rights based approaches is an asset; max 10

Financial evaluation (30%) – max. 30 points:

The maximum number of points assigned to the financial proposal is allocated to the lowest price proposal. All other price proposals receive points in inverse proportion. A suggested formula is as follows: 

p = 30 (μ/z)

Using the following values:

p = points for the financial proposal being evaluated

μ = price of the lowest priced proposal

z = price of the proposal being evaluated

 

Annex 1 UN Women GERAAS evaluation quality assessment checklist

· Guidance on the UN Women Global Evaluation Reports Assessment and Analysis System (GERAAS) is available at: http://www.unwomen.org/en/about-us/evaluation/decentralized-evaluations

Annex 2 UN Women Evaluation Consultants Agreement Form

· UN Women Evaluation Consultants Agreement Form: http://gate.unwomen.org/

· UNEG Ethical Guidelines and Code of Conduct for Evaluation in the UN system

http://www.uneval.org/document/detail/100

Annex 3 UNEG Norms and Standards for evaluation

· UNEG Norms: UNEG website http://unevaluation.org/document/detail/21

· UNEG Standards: UNEG website http://unevaluation.org/document/detail/22

Annex 4 UN Women Evaluation Handbook

· UN Women Independent Evaluation Office website: 

http://genderevaluation.unwomen.org/en/evaluation-handbook

Annex 5 Resources for data on gender equality and human rights

· UN Office of the High Commissioner for Human Rights (OHCHR) – Universal Human Rights Index:

http://uhri.ohchr.org/en

· UN Statistics – Gender Statistics: http://genderstats.org/

· UNDP Human Development Report – Gender Inequality Index: 

http://hdr.undp.org/en/content/gender-inequality-index-gii

· World Bank – Gender Equality Data and Statistics: http://datatopics.worldbank.org/gender/

· Organization for Economic Co-operation and Development (OECD) Social Institutions and Gender

Index: http://genderindex.org/

· World Economic Forum – Global Gender Gap Report: http://www.weforum.org/issues/global-gendergap
· A listing of UN reports, databases and archives relating to gender equality and women’s human rights can be found at: 
http://www.un.org/womenwatch/directory/statistics_and_indicators_60.htm
[image: image2][image: image3][image: image4][image: image5][image: image6][image: image7][image: image8][image: image9][image: image10][image: image11][image: image12][image: image13][image: image14][image: image15][image: image16][image: image17][image: image18][image: image19][image: image20][image: image21][image: image22][image: image23][image: image24][image: image25][image: image26][image: image27][image: image28][image: image29][image: image30][image: image31][image: image32][image: image33]
1

