Promoting Women’s Political Participation In Sri Lanka [UNWOMEN/MCO/2016/042] The Final Evaluation Report By Dr. Maneesha S. Wanasinghe – Pasqual Consultant 2016

AKNOWLEDGEMENTS

This evaluation would not have been possible without the able support of a number of individuals. First and foremost, I wish to thank the team at UN Women Sri Lanka, UN Women India and UN Women New York for their assistance. The work undertaken by the UN Women Sri Lanka team, ably led by Ms. Ramaaya Salgado, must be mentioned for their unstinting support in conducting the evaluation. Their partners in this endeavor – Association of War Affected Women (AWAW), Search for Common Ground Sri Lanka (SFCG), and Women and Media Collective (WMC) – must also be mentioned with gratitude for providing information and names of stakeholders when requested.

I must also thank all the stakeholders – from women politicians to university youth, from activists to trade union workers – who gave their valuable time to listen to the questions and answer truthfully.

Finally, I wish to thank my team of consultants – Emeritus Professor Y. A. D. S. Wanasinghe, Ms. Marini De Livera, and Mr. Namal Weerasinghe – for their assistance in gathering the data and in the conducting the qualitative research within the given period of time.

Dr. Maneesha S. Wanasinghe – Pasqual

LIST OF ACRONYMS

AWAW	Association for War Affected Women

CADAW	Convention on the Elimination of All Forms of Discrimination Against Women

FGD	Focus Group Discussions

IPU		Inter-Parliamentary Union

KII		Key Informant Interviews

MDG	Millennium Development Goals

MP		Member of Parliament

PC		Provincial Council

PRC		Public Representation Committee

PWC	Parliamentary Women’s Caucus

RA		Research Assistant

SDG	Sustainable Development Goals

SFCG	Search for Common Ground

TOR	Terms of Reference

UN		United Nations

UNEG	United Nations Evaluations Group

UNW/I	UN-Women India

UNW/SL	UN-Women Sri Lanka

WMC	Women and Media Collective

TABLE OF CONTENTS

| ACKNOWLEDGEMENTS | ii. |
| --- | --- |
| LIST OF ACRONYMS | iii. |
| LIST OF ANNEXUTRES | v. |
| LIST OF TABLES | vi. |
| LIST OF FIGURES | vii. |
| LIST OF CHARTS | viii. |
| LIST OF BOXES | ix. |
| LIST OF MAPS | x. |
| - EXECUTUVE SUMMARY | 1 |
| - INTRODUCTION | 4 |
| INTRODUCTION | 4 |
| Theoretical Backdrop | 6 |
| Sri Lankan And Women In Politics | 6 |
| PURPOSE OF EVALUATION | 8 |
| Program Objectives And Scope | 8 |
| - EVALUATION METHODOLOGY | 11 |
| EVALUATION | 11 |
| Evaluation Design | 11 |
| A Focus | 14 |
| LIMITATIONS | 24 |
| FINDINGS | 26 |
| ANALYSIS | 26 |
| Analysis of UN-Women Sri Lanka | 28 |
| Analysis of Partners | 29 |
| Analysis of Activities | 30 |
| Analysis of Workshops | 32 |
| Analysis of Impact | 36 |
| Analysis of Reporting | 40 |
| Analysis of Monitoring by UN-Women | 41 |
| - CONCLUSION | 42 |
| Recommendations | 43 |
| LIST OF ANNEXES | 47 |
| Annex I: UN-Women TOR | 47 |
| Annex II: Guidelines | 82 |
| Annex III: References | 99 |
| Annex IV: Stakeholder Analysis | 102 |
| Annex V: Program Analysis | 105 |
| Annex VI: Summary Findings | 112 |

| LIST OF TABLES |  |  |  |
| --- | --- | --- | --- |
| Table 1: Level of Equality | 12 |  |
| Table 2: Level of Equality in TOR | 13 |  |
| Table 3: Field Research Tools | 17 |  |
| Table 4: Duties and Responsibilities of Partners | 30 |  |

| LIST OF FIGURES |  |
| --- | --- |
| Figure 1: Program Causal Chain | 13 |
| Figure 2: Data | 15 |
| Figure 3: Limitations Matrix | 25 |

| LIST OF BOXES |  |
| --- | --- |
| Box 1: Outcome and Outputs in TOR | 26 |

LIST OF MAPS

| Map 1: Field Research | 15 |
| --- | --- |

EXECUTIVE SUMMARY

This report presents the findings of the final evaluation of the project on Promoting Women’s Political Participation in Sri Lanka on behalf of UN-Women [UNWOMEN/MCO/2016/042]. The evaluation analyzes the contribution of the UN Women Sri Lanka and of three Implementing Partners.

Scope and Approach

Using both a Women’s Empowerment Framework lens and a structural/cultural violence philosophical angle, this evaluation design assessed whether the UN-Women Sri Lanka project to ‘Promote Female Political Participation’ was successful. The evaluation was limited to activities undertaken by the three partners – Association for War Affected Women (AWAW), Search for Common Ground (SFCG), and Women and Media Collective (WMC) along with UN Women Sri Lanka – under the rubric of the specific project, which covered a two-year period from 2015 to end of 2016.

The very existence of a project of this type is proof of how urgent and essential it is to focus on women in politics in the context of Sri Lanka because – despite the major strides in equality that occurred in the fields of education, health, and even life expectancy – women lag behind their male counterpart when it comes to political participation. The election of 2015 elected only 13 women to the Parliament as opposed to 212 males who were elected. Women in the Parliament never increased more than a dismal 6.8% of the entire 225 seat Parliament since the 1980s. This project was formulated under this backdrop. There were two broad objectives and more specific objectives within each.

- Strengthen capacities of women including youth and civil society organisations for greater participation of women in political and institutional mechanisms, at national and provincial levels.

    - Increase women’s influence in national and local governance institutions by strengthening their voice and participation in political and institutional mechanism at national and local level through capacity development

    - Partner with the media in Sri Lanka to build awareness on the issue of under representation of women in national and local governance and advocate for women’s political participation

- Enhance understanding among parliamentarians (both women and men) to support and advocate for greater representation and effective participation of women in Sri Lanka’s governance structures.

  - Advocate with parliamentarians for greater representation of women in Sri Lanka’s governance structures and institutions through a mandatory quota for women.

For each of the Objectives, there was an envisioned Outcome and an Output. For the first Objective, the Outcome was Capacity Development and Attitudinal/Behavioral change and the desired Outputs included capacity development, networking, knowledge, and attitude transformation. The second Objective had an outcome focus that strives to introduce institutional and legal change. This Outcome was coupled with the desired Output of capacity development, knowledge and attitude transformation.

Methodology

The evaluation of the project initiated by UN Women and implemented by UN Women and their partners utilized OECD recommended criteria on relevance, effectiveness, efficiency, sustainability, and impact. Conducting on a tight time constraint, the Consultant was joined with three other experts as well as a Research Assistants. A mixed method design was used to gather qualitative and quantitative data and the evaluation was based on Longwe’s Women’s Empowerment Framework.

Key Findings and Conclusion

-A caveat at the outset: the project targeted specific outcomes and never envisioned extensive changes as the timeframe was only from 2014 – 2016.

| Recommendation |  |
| --- | --- |
| Doing the Right Thing | Continue activism for women through campaigns, having workshops and trainings are essential. They help disseminate knowledge. |
|  | Political participation of women through greater discourse on the best ways of achieving it. |
|  | Voter education to the general public should be undertaken along with women’s activism. |
|  | Encourage the internal democracy in political parties |
|  | Capturing the motivation by women who wish to or are part of the politics of Sri Lanka. |
| Doing it Right (i.e. Best Practice) | Work with the Constitutional Council and the Parliamentary Women’s Caucus. |
|  | Engaging both male and female parliamentarian is vital for changes in attitudes to occur, which in turn would assist in creating new laws that benefit women. |
|  | Use of different methods – from workshop lecture/discussion/group work/presentation to use of social media – to disseminate knowledge is exceptionally useful. |
|  | The focus on analyzing Parliamentary speeches. This should be expanded to include analysis of media-bias, and speeches outside Parliament by politicians. |
|  | The targeting of male and female for workshops/training sessions for journalists, youth, and Plantation sector participants, is an exceptionally good practice which should be extended where possible. |
|  | The use of a number of experts – e.g. Anoma Rajakaruna, Jeeva Kariyawasm – coupled with those with extensive experience (e.g. Sumeeka Perera) help make sessions interesting and insightful. More specialists – male trainers – should be included. |
|  | The fact that the partners with the assistance of UN-Women Sri Lanka were able to coordinate the ‘Vote for Women’ campaign is commendable. Despite each partner (a) working on different Activities in different areas of the island and (b) having other projects along with the UN-Women one, it is vital that such coordination be a part of future projects. |
|  | Encourage the professionalism shown by UN Women Sri Lanka and the partners in their networking. |
|  | UN Women Sri Lanka to continue training partners on budgetary practices |
| Better Ways of Achieving Results | UN Women to train partners on report writing to ensure that a single report format is kept. |
|  | While no irregularities on financial disclosures occurred during this project, transparency in terms of what is disclosed with regard to workshops and other activities must be encouraged. |
|  | Evident that UN Women Sri Lanka was transparent in their interactions and in record keeping. |
|  | A Nationwide Voter education campaign |
|  | Critical discussion on the need for quota |
|  | Internal democratization of political parties |
|  | Creating an anti-sexist Media |
|  | Gathering experts with innovative approaches to get ideas across |

BACKGROUND

INTRODUCTION

The background details presented below, though divided to different sections, are all inter-linked and is inclusive of the positive as well as the critical comments on the project and its beneficiaries.

Theoretical Backdrop

For a country to transform from a war to peace, requires the institutionalization of democracy. Not only does this entail developing rules, but there must also be a socialization of democratic norms. This is especially vital when a country, which experienced decades of war, needs to move from ‘unstable peace’ to ‘stable peace’. As noted by the late Kenneth Boulding, there must be ‘inclusive peace’ in order for a country to transform. However, from a more subtle point of view, it is Galtung’s idea of transforming a country from ‘negative peace’ to ‘positive peace’ through the elimination of ‘structural’ and ‘cultural’ violence that is at the heart of the evaluation presented below. To Galtung, violence is not just what is direct or observed. Direct violence include killing, and maiming among others. There are other forms of violence which are embedded in the socio-economic, political-cultural structure of a society. Paul Farmer defines this as,

Structural violence is one way of describing social arrangements that put individuals and populations in harm’s way… The arrangements are structural because they are embedded in the political and economic organization of our social world; they are violent because they cause injury to people … neither culture nor pure individual will is at fault; rather, historically given (and often economically driven) processes and forces conspire to constrain individual agency. Structural violence is visited upon all those whose social status denies them access to the fruits of scientific and social progress. (Farmer 1999).

Moreover, this structural violence is often not recognized by the people in general (especially those in power or with power) since it is imbued in the culture to such an extent that people are blind to this type of violence. This acceptance of structural violence without questioning is termed ‘cultural violence’, which Galtung himself states as “those aspects of culture, the symbolic sphere of our existence – exemplified by religion and ideology, language and art, empirical science and formal science (logic, mathematics) – that can be used to justify or legitimize direct or structural violence.” (Galtung 1990: 291).

This is at the heart of any and all discrimination against women that exists in a society. Cinfortini summarizes Galtung’s argument:

Galtung argues that violence can also be defined in terms of the kind of harm it produces, in terms of what human needs it limits. Both direct and structural violence hamper the need of bodily and psychological integrity, basic material needs (such as the need for sleep, nutrition, movement, health, love, etc.), classical human rights (freedom of expression, need for mobilization, need for work, etc.), and nonmaterial needs (such as solidarity, friendship, happiness, self-actualization, and so on). (Confortini 2006: 337).

It is not an easy task to include women in politics. There is a power inequality that is inherently part of a patriarchic society. This is evident if one was to re-interpret the ‘Power and Control Wheel’ to look into not just ‘domestic abuse’ but also ‘structural violence’ and ‘cultural violence’ that keep women from achieving their best. According to the ‘Power and Control Wheel’ by Clare Murphy, other than direct physical violence, women face symbolic aggression, one-sided power games, mind games, inappropriate restrictions, isolation, over protection and caring, emotional unkindness and violation of trust, degradation, separation abuse, denial, minimizing and blaming, using the children, economic abuse, and using social institutions (2013). What women face is ‘structural’ and ‘cultural violence’ that requires a political will, a legal basis and norm socialization to transform

There has to be a legal framework, a political party system that nominates women in politics, voter education, among others. Internationally, as signatories to laws, a country should adhere to international standards that guarantee women equality, political and socio-economic rights. These include Article 2, 7, and 21 of the Universal Declaration of Human Rights (1948), Articles 3, 25, and 26 of the International Covenant on Civil and Political Rights, as well as Article 2 and Article 7, subsection (a) and (b) of the Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW), which speaks of the responsibility of states to “take all appropriate measures to eliminate discrimination against women in the political and public life” (CEDAW 1981). Twenty years after the Beijing Declaration and Platform for Action, UN-Women analysis highlights that globally, women continue to be under-represented in politics.

Despite the steady increase in women’s political representation and participation in parliaments, women remain significantly under-represented at the highest levels of political participation as well as across the public and private sectors.

The persistence of discrimination, gender bias, and the threat of violence, harassment and intimidation in political institutions contribute to the low levels of women’s political participation.

Accelerating women’s participation in decision-making requires a comprehensive approach; the implementation of temporary special measures to achieve a gender balance in decision-making bodies and capacity building and training initiatives to support women’s political participation at the local and national levels. (UN-Women 2015).

This is a concern in that “Structural violence feeds off the steady stream of cultural violence … [and] structural violence, more often than not, is left unchanged, and the cycle of violence continues. The invisibility of the structure is frequently a function of our lack of tools to see below the surface.” (Pilisuk and Rountree 2008: 50). The violence faced by women who want to take part in politics is direct and indirect (i.e. structural and cultural). Legal, political, and attitudinal. The project under evaluation – ‘Promoting Women’s Political Participation in Sri Lanka’ – is a way to transform the existing cultural and structural violence that hinder women’s participation in local, provincial and national politics in Sri Lanka.

Sri Lankan and Women in Politics

Sri Lanka presents a unique set of data on women and equality. According to the UNDP data, the life expectancy of females in Sri Lanka is 78 years to male 71.5 years. Females in Sri Lanka even spend more time at school (14 years to 13.3 years) than their male counterparts, with almost 73% of females having ‘some secondary education’. Yet, despite having a healthy and literate female population, female participation in the labor force fall dismally short. This is in terms of both female participation (35% to male 76%) and in terms of earning with male having an income almost three times that of females (Rs. 14,307 to Rs. 5,452). Such statistics is in complete contrast to the fact that Sri Lanka has a commendable position of 73rd among 188 countries and is placed in the ‘High Human Development’ category in the Human Development Report’s Gender Development Index (GDI) of 2015 (UNDP 2015).

The above conflicting insights highlight the complex situation in Sri Lanka where women are accorded equality as a Fundamental Right under the 1978 Constitution (http://www.parliament.lk/files/pdf/constitution.pdf). Moreover, under Millennium Development Goals (MDG), the 2014 Country Report noted that “Overall Sri Lanka is in a strong position. The good performance noted in the 2008/9 MDG Country Report has been sustained and Sri Lanka has already achieved many of the goals and is mostly on track to achieve the others.” (2015). This report noted that the country was on track to gender parity in ‘primary education’, but, further highlighted the fact that

From 1989 to 1994, women comprised only 5.8 percent of parliamentarians; the portion has increased only marginally to 6.8 percent in the present Parliament. Encouraging more female representation would help ensure that women, who often hold different views or face different needs, are adequately represented. (UN Sri Lanka Report 2015).

This issue is reiterated in the Through the Global Gender Gap Report 2014, which provides data on 142 countries. According to that report, the country with the highest number of women in Parliament is Rwanda with 64 % followed by Bolivia (53%) and Cuba (49%), which is commendable. But, other than the former two examples, all other countries fall short of the 50% mark that should be the minimum number since women equal men in terms of population statistics. The disparity between women’s place in politics is stark and disconcerting. It is more discouraging to note that while Sri Lanka is overall 79th under the broad rubric of ‘Gender Gap Index’ in 2014 – with Educational Attainment providing a comfortable 59th position, Health and Survival providing an exceptional rank of 1 – under ‘Political Empowerment’ Sri Lanka’s ‘Women in Parliament’ category places Sri Lanka 130th out of 142 countries. This is despite having over 24 years under female heads of state (under Prime Minister Mrs. Sirimavo Bandaranaike 1960 – 1965, 1970 – 1977 and under President Chandrika Bandaranaike Kumarathunga 1993 – 2005). Women (at least two here) have gone to the highest level of governance. Despite this stellar accomplishments, the category ‘Women is Ministerial Positions’ places Sri Lanka in a dismal place due to having only 3% of the Parliament comprising women.

Another world classification, compiled by the Inter-Parliamentary Union (IPU), looked at the percentage of Women in Parliament. This has Sri Lanka placed 176th out of 186 rankings (with 193 countries being tabulated). Sri Lanka has the lowest ranking out of South Asian countries in this classification, even below Maldives. Sri Lanka is ranked below Iran (174th), Congo (166th), Bhutan (164th) and Myanmar (154th). Only countries ranked below Sri Lanka are some African and Middle Eastern counties. This is due to the fact that out of 225 seats in Parliament, only 13 seats or 5.90% of the seats are occupied by women (2016 statistics from http://www.ipu.org/wmn-e/classif.htm).

This was the situation prior to the inception of the project. It can be assumed that the project designers wanted to increase women’s participation in politics through

- Legislative changes

- Political party action

- Empowering the Women’s Parliamentary Caucus

- Gaining insights into whether there exists gender-bias in the Parliament

The need to increase political participation of women in Sri Lanka is urgent since, as a signatory to the Sustainable Development Goals (SDG), Sri Lanka is duty-bound to “End all forms of discrimination against women and girls” (SDG 2016). But, at the same time, the SDG Index has Sri Lanka in 97th position, with only 149 countries’ information being utilized (SDSN Leadership Council 2016).

PURPOSE OF EVALUATION

According to the UNEG Norms for Evaluation, evaluation is defined as

an assessment, as systematic and impartial as possible, of an activity, project, programme, strategy, policy, topic, theme, sector, operational area, institutional performance, etc. It focuses on expected and achieved accomplishments, examining the results chain, processes, contextual factors and causality, in order to understand achievements or the lack thereof. It aims at determining the relevance, impact, effectiveness, efficiency and sustainability of the interventions and contributions of the organizations of the United Nations system. An evaluation should provide evidence-based information that is credible, reliable and useful, enabling the timely incorporation of findings, recommendations and lessons into the decision-making processes of the organizations of the United Nations system and its members. (UNEG 2005: 5)

In brief, the purpose of this summative evaluation is to answer three questions.

Are we doing the right thing? It examples the rationale, the justification of the undertaking, makes a reality check and looks at the satisfaction of intended beneficiaries. Evaluation is also about Are we doing it right? It assesses the effectiveness of achieving expected results. It examines the efficiency of the use of inputs to yield results. Finally, evaluation asks Are there better ways of achieving the results? Evaluation looks at alternative ways, good practices and lessons learned. (UNEG 2005: 6)

The task assigned to the Consultant was to gather primary and secondary data from multiple sources in the period of 25 working days or five weeks (25th November to 30th December 2016).

Program Objectives and Scope

The overarching objective of the project would be to work

for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security. Placing women’s rights at the center of all its efforts, UN-Women leads and coordinates United Nations system efforts to ensure that commitments on gender equality and gender mainstreaming translate into action throughout the world. (http://www.unwomen-asiapacific.org/docs/tor/2016/IND/20160928_IND_SSA042_Consultant_for_Evaluation_of_RNE_Project_in_Sri_Lanka.pdf)

To be pedantic, this project focused on ‘Elimination of Discrimination’ through ‘Empowerment of Women’ by targeting the achievement of ‘Equality’. This is at the heart of the ‘Sustainable Development Goal 5: Gender Equality’. More specifically, this project falls under Target 5: ‘Ensure Women’s Full and Effective Participation and Equal Opportunities for Leadership at all levels of decision-making in political, economic and public life’ under the broader rubric of Goal 5. The indicator for this target is “Percentage of seats held by women and minorities in national parliament and/or sub-national elected office according to their respective share of the population (modified MDG Indicator)”. While this indicator is limited in that it cannot measure the real-world impact of women in political decision-making, “Participation in elected office is a key aspect of women’s and minorities’ opportunities in political and public life, and is therefore linked to their empowerment. Their presence in decision-making bodies alters dynamics and can help bring to light women’s and minorities’ concerns.” (SDSN 2016). The proposed activities (presented below) also strives to ensure Target 5.c.: ‘Adopt and strengthen sound policies and enforceable legislation for the promotion of gender equality and the empowerment of all women and girls at all levels’. It is also in keeping with the Constitutional guarantees under the Fundamental Rights provision 12(1), which states that “All persons are equal before the law and are entitled to equal protection of the law” and Article 12(4) which stipulates that “Nothing in this Article shall prevent special provision being made, by law, subordinate legislation or executive action, for the advancement of women, children or disabled persons.” (Sri Lanka Constitution, 1978).

The two-year project designed by UN Women Sri Lanka (2014 – 2016) began in the midst of an exciting period – politically speaking – in Sri Lanka. As the TOR inform, this program had two outcomes.

- Strengthened capacities of women including youth and civil society organisations for greater participation of women in political and institutional mechanisms, at national and provincial levels.

- Enhanced understanding among parliamentarians (both women and men) to support and advocate for greater representation and effective participation of women in Sri Lanka’s governance structures.

Under these outcomes, there existed three elements

- Increase women’s influence in national and local governance institutions by strengthening their voice and participation in political and institutional mechanism at national and local level through capacity development;

- Advocate with parliamentarians for greater representation of women in Sri Lanka’s governance structures and institutions through a mandatory quota for women;

- Partner with the media in Sri Lanka to build awareness on the issue of under representation of women in national and local governance and advocate for women’s political participation

EVALUATION METHODOLOGY

THE EVALUATION

The evaluation used a mixed method to gather data and focused on ‘triangulation’ in order to avoid bias and to ensure that all insights were included. Being a gender-responsive evaluation, the focus was on the ‘Women’s Empowerment Framework’ in which the aim was

to incorporate gender awareness, women’s participation, and women’s issues into development programs, with the goal of overcoming inequality. The framework consists of a five-level scale of increasing equality and empowerment.

The framework also identifies three levels of recognition of women’s issues in project objectives: the negative level – ignores women’s issues; the neutral level – recognizes women’s issues but ensures only that women’s positions are not further undermined; and the positive level – focuses on improving the position of women. (Oregon.edu)

Mixed method here entails using both interview/focus group discussions as well as surveys (i.e. qualitative and quantitative methods) to gather data.

Evaluation Design

At the outset, it is pertinent to emphasize that this evaluation strived to be ‘gender-responsive’. The evaluation design is ‘summative’ in that it focuses on outcomes and lessons learnt. But its overarching design is based on Sara Hlupekile Longwe’s Women’s Empowerment Framework. In brief, this

framework is intended to help planners question what women’s empowerment and equality means in practice, and, from this point, to assess critically to what extent a development intervention is supporting this empowerment. Longwe defines women’s empowerment as enabling women to take an equal place with men, and to participate equally in the development process in order to achieve this control over the factors of production on an equal basis. (March, Smyth and Mukhopadhyay 2015: 92).

Longwe’s framework requires initially establishing the specific ‘level of equality’ (Welfare to Access to Conscientisation to Participation to Control) of a project (see Table 1 below). Since the

levels of equality are hierarchical. If a development intervention focuses on the higher levels, there is a greater likelihood that women’s empowerment will be increased by the intervention than if the project focuses on the lower levels. If the intervention concentrates only on welfare, it is very unlikely that women will find the project empowering. (March, Smyth and Mukhopadhyay 2015: 93).

It is under this assumption that this project is evaluated.

Table 1: Level of Equality

| Level of Recognition | Definition | Increase |
| --- | --- | --- |
| Control | “The term denotes women’s control over the decision-making process through conscientisation and mobilisation, to achieve equality of control over the factors of production and the distribution of benefits. Equality of control means a balance of control between men and women, so that neither side dominates.” | Increased equality Increased empowerment |
| Participation | “women’s equal participation in the decision-making process, in policy-making, planning, and administration … Equality of participation means involving women in making the decisions by which their community will be affected, in proportion which matches their proportion in the wider community.” |  |
| Conscien-tisation | “This is understood … as a conscious understanding of the difference between sex and gender, and an awareness that gender roles are cultural and can be changed.” |  |
| Access | “Women’s access to the factors of production on an equal basis with men … equality of access is obtained by applying the principle of equality of opportunity, which typically entails the reform of the law and administrative practice to remove all forms of discrimination against women.” |  |
| Welfare | “Level of women’s material welfare, relative to men.” |  |

Source: March, Smyth and Mukhopadhyay 2015: 94

The target of this project is not ‘Welfare’ or ‘Access’ but rather a better level of equality through ‘Conscientisation’ and ‘Participation’ (see Table 2 below).

This is based on the assumption, inherent in the project design and verified by empirical evidence, that in practice, Sri Lankan women’s empowerment has by-passed ‘Welfare’ and ‘Access’ levels but require extensive assistance in the more daunting levels. This is not to say that women do not face issues in access and welfare. Rather, the emphasis placed by the UN-Women designers was based on the assumption that women have achieved – they have material welfare and do have access under the law – and therefore the next stage is to find ways of gaining inclusivity in the political decision-making process. This assumption also highlights the approach to the ground reality of the project.

Table 2: Level of Equality in Project Design

| Level of Recognition | UN-Women Project | UN-Women Outcomes | UN-WomenProject 3 Elements |
| --- | --- | --- | --- |
| Participation | “creation of a substantive body of knowledge to inform measures including; policy advocacy, training and capacity building, coalition building and lobbying for mainstreaming gender in the governance structure of Sri Lanka.” | - Strengthened capacities of women including youth and civil society organisations for greater participation of women in political and institutional mechanisms, at national and provincial levels. | - Increase women’s influence in national and local governance institutions by strengthening their voice and participation in political and institutional mechanism at national and local level through capacity development; |
|  |  | - Enhanced understanding among Parliamentarians (both women and men) to support and advocate for greater representation and effective participation of women in Sri Lanka’s governance structures. | - Advocate with parliamentarians for greater representation of women in Sri Lanka’s governance structures and institutions through a mandatory quota for women; |
| Conscien-tisation |  |  | - Partner with the media in Sri Lanka to build awareness on the issue of under representation of women in national and local governance and advocate for women’s political participation |

Source: Project Design and adapted from Longwe 2002)

According to the UN Women’s How to Manage Gender-Responsive Evaluation: Evaluation Handbook, there is a clear ‘Program Causal Chain’ (see Figure 1 below) that was kept in mind at evaluation stage. This evaluation combines that causal chain with the analysis on the levels of equality in order to glean whether the inputs were adequate to sufficiently result in positive impacts.

Figure 1: Program Causal Chain

(Source: https://undg.org/wp-content/uploads/2015/01/UNDG-RBM-Handbook-2012.pdf)

These impacts should not be merely token. Rather, the analysis examines whether the Activities envisioned by the partners resulted in a ‘Conscientisation’ or in true ‘Participation’. In other words, whether the Activities resulted in Outputs and Outcomes and Impacts that challenge ‘Cultural’ violence and ‘Structural violence’ that exist to discriminate against women in politics.

- Focus

The research methodology is developed in accordance with the objectives of the final evaluation. This is a mixed method approach strives to focus on the outcome-based approach. It will be guided by four broad questions.

- Will the outputs be achieved by end of 2016?

- Have these contributed to the ‘planned outcomes’?

- Have the outputs produced any intended positive results?

- Have the outputs produced any unintended positive or negative results?

Answers to these questions enabled us subsequently to analyze the project under the six broad areas:

  - Relevance

  - Effectiveness

  - Efficiency

  - Impact

  - Sustainability

  - Gender Equality and Human Rights

Therefore, the evaluation examined the overarching objective of the project and then evaluated whether each of the partners designed appropriate activities and subsequently implemented the activities to the benefit of the UN Women’s objectives. The data collection involved gathering secondary and primary data. The research tools used to gather the data is also presented. This secondary data included all reports by the partners, any documents submitted by the partners on workshop handouts among others. Primary data include the interviews, FGDs, case studies, UN Resolutions, key Conventions, Treaties, the Sri Lankan Constitution, Party Manifestos, as well as any signature/evaluation sheet which holds information on participant names, contact address/phone and their views.

Figure 2: Data

- Systemic manner of the evaluation

Since this project has three partner organizations and is a multi-stakeholder one, data needs to be collected from different stakeholders using different research tools. The initial step was to gather a four specialists/experts to assist the Consultant to conduct the field research. These specialists had extensive experience in conducting field research on women, some with a focus on local government while others on human rights. They in turn worked with Research Assistants (RA) – with previous experience in conducting field research of a similar kind – who were given an intensive training. This training included training on asking sensitive questions and on the ethical component in conducting field research. Where Tamil language is prevalent, the evaluation would require the assistance of the two Tamil-speaking RAs while in other places, the three Sinhala-speaking RAs.

Concurrent to this, the Consultant focused on the desk research, which provided insights into places to conduct field work. The focus then was the determine areas for field work that was in keeping with the project activities and the time constraints of the research itself. The field setting of this evaluation is presented below. Along with this, a decision was made to conduct telephone interviews of university youth who participated in workshops. This was due to the fact that students from universities would be scattered. The Consultant focused on interviewing students from the Universities of Jaffna and Eastern because it was felt that their needs might not often be heard.

Map 1: Field Research

| Field Research: KII, FGDs and Case Studies from - Anuradhapura (Sinhala) - Batticaloa (Tamil) - Colombo (Sinhala/Tamil) - Kurunegala (Sinhala) - Matara (Sinhala) - Nuwara Eliya (Sinhala/Tamil) - Trincomalee (Tamil) Telephone KII conducted from those living in: - Jaffna (Tamil) - Kandy (Sinhala) The KII from Puttalam met the Consultant in Colombo. - Puttalam (Sinhala/Tamil/Muslim) Source: Political Map of Sri Lanka at http://pragmora.com/conflicts/srilanka/maps/ KII also with - UN Women Sri Lanka - National Committee on Women |  |
| --- | --- |

The data collection involved focusing on secondary data and primary data. The research tools used to gather the data include Key Informant Interviews (KII), Focus Group Discussions (FDG), Case Studies, and Survey. The data collection focused on gathering information from multiple stakeholders.

- UN Women

- Partners: AWAW, WMC, and SFCG

- National Level Politicians:

  - Women’s Parliamentary Caucus representative

  - Member of Parliament (current or recent-past)

- Local Level Politicians

  - Female Provincial Council  (current or recent-past)

  - Local Government member (current or recent-past)

- National Committee on Women at Ministry of Women and Child Affairs

- Activists:

  - Government Agent

  - Women working in different sectors

- Trade Union members

- Youth: University Students

The initial desk research resulted in the designing of the ‘field research tools’. This table (see below) not only highlighted the systemic manner of the evaluation but it is also a reflection on the availability of data. It is evident from the list below that there was a lacuna in the reports providing to UN-Women by the partners regarding activities and the details of the beneficiaries.

Table 3: Field Research Tools

| Partner | Outcome | Planned Activity | Activity Conducted | Area | Evaluation Tool |
| --- | --- | --- | --- | --- | --- |
| Association of War Affected Women (AWAW) | OBJECTIVE 1: Greater willingness among Parliamentarians and select Provincial Councils to actively support increased and effective representation of women in politics at the National and Provincial level | 1.1.0: To conduct 1 advocacy meeting each with eight political parties in Colombo to advocate for a 33% quota for women in elected office | Advocacy Campaign - Political parties Meeting with representatives of Political Parties [17 - 26 June 2015 Discussion about the constitutional submission to the constitutional committee | Colombo | KII: Political Party Representatives |
|  |  | 1.4.0: Conduct two two-day workshops for 50 members of Parliament and Trade Union members on gender responsive policy design and implementation | 2 Day Workshop on the National machinery on women – independent Commission on Women; Discriminatory laws; Violence against Women; Lack of Political participation; Women in the informal sector; Gender stereotyping; Health – teen pregnancies and unsafe abortions; Women affected by conflict; Migrant women. - Prepared 2 Action plans a)Trade union members created an action plan for a social media page (Facebook) to highlight issues in the plantation sector, and the page was named “Malayaga kozundu” means “up country tea leaf” - Draft an action plans on “Women peace, security and development” in Central and Eastern initially and then in the rest of the 7 provinces | Colombo, Trincomalee, and Nuwara Eliya | KII: MPs, Provincial Counsellors, Government Agents FGD: Trade Union Members |
|  | OBJECTIVE 2: Increased public awareness and support of women’s political representation and participation at the national and provincial levels. | 2.1.1: Conduct one workshop on identifying themes/messages/issues for advocacy material on women’s political and democratic rights/women in decision-making and ‘vote for women’ with partner organizations and relevant experts | Poster campaign. | Kandy & Jaffna | KII of AWAW Survey: youth / |
|  |  | 2.2.1: Conduct 4 one-day meetings with 100 youth from Universities of Peradeniya, Batticoloa (i.e. Eastern), Jaffna, and Colombo. | Workshops for 76 undergraduates from 4 Universities on the importance of electing women to political bodies. Themes discussed: Women’s political history in Sri Lanka, current status and international experience. | Batticaloa & Jaffna | FGD & Survey: University students |
|  |  | 2.2.2.: Distribution of 10,000 leaflets and posters to reach 10,000 members of the public all-island to advocate for the ‘vote for women’ by University students | Half day Workshops for University Students to distribute the Leaflets and Posters | Batticaloa & Jaffna | Survey: University Students |
|  |  | : Six one day seminars to establish regional women’s caucus with regular networking and knowledge sharing | Networking workshop to build women politician’s caucuses [4 workshops for 77 persons on 20.04.2016 ; 24.05.2016; 31.05.2016 25.06.2016. Covered most of the Districts | Colombo, Batticaloa, Kandy, | KII: Politician AWAW |
|  |  | : One regional women’s summit to jumpstart the process with the participation of members of the WPC and male Parliamentarians and Provincial Counsellors | Conducted in 2016 | Colombo | KII: UNW & AWAW |
| Women and Media Collective (WMC) | OBJECTIVE 1: Greater Willingness among Parliamentarians and select Provincial Councils to actively support increased and effective representation of women in politics at the National and Provincial level | 1.1.2: Conduct one national media briefing to advocate for inclusion of clauses related to increased women’s representation in the 20th Constitutional Amendment. | Press briefing (08 September 2015) to demand for a 30% increase in women’s political representation at Local Government. | Colombo | KII |
|  |  | 1.2.2: Conduct a one-day consultation with 15 provincial council members (including women) from a select Provincial Council on reviewing gender responsiveness of one Provincial Council’s Action Plan. | Organized a round of discussion on the new constitution making process. Discussions conducted in Batticaloa , Kurunegala and Colombo with the participation of women activists, members of CSOs, women affiliated to political parties, Trade unions and Women’s Organizations. | Kurunegala | FGD/Case Study |
|  |  | 1.5.1: Conduct a study (online and on print) on gender-biased statements made in Parliament during the last decade to advocate for gender-equitable political environment. | http://womenandmedia.org/wp-content/uploads/2016/02/Hansard-Research-Study.pdf | Colombo | FGD/KII |
|  |  | 1.5.2: Publish the study on gender-biased Parliament statements in three languages |  |  | book |
|  |  | 1.5.3: Conduct a national level media-briefing to disseminate findings on gender-biased statements made in the Parliament. | Held a national level media briefing to disseminate findings on gender biased statements made in the Parliament. |  | WMC Website |
|  |  | 1.5.4: Conduct meetings with WPC to disseminate the study findings | Lack empirical data |  | N/A |
|  |  | 1.5.5: Monitor Parliamentary speeches for 3 months to evaluate the impact of the dissemination of the study | Lack empirical data |  | N/A |
|  | OBJECTIVE 2: Increased public awareness and support of women’s political representation and participation at the National and Provincial levels | 2.2.1: Conduct one workshop on identifying themes/messages/issues for advocacy material on women’s political and democratic rights/women in decision-making and ‘Vote for Women’ with partner organizations and relevant experts. | Facilitated a discussion on the Local Authorities Elections Amendment Act of 2012 [December 21, 2015]. Focused on increasing representation of women under the mixed electoral system. | Colombo and Kandy | FGD |
|  |  | 2.1.2: Commission the production of three animated sports | Produced animated spots targeting the Parliamentary elections. | Colombo | FGD |
|  |  | 2.1.6: Developing and commissioning the broadcasting of 30 (voice) profiles for a period of 3 months in three languages | Lack empirical data | N/A | N/A |
|  |  | : Constitutional-making | Discussions held with women’s rights activists (WRAs) and Women’s groups (WGs) in appox. 20 Districts on the new constitution making process. | Colombo | FGD/Website |
|  |  | : Social Media Campaign | http://womenandmedia.org |  |  |
|  |  | : Short Film Competition (theme: “Women’s Participation and Representation in politics” | ## WMC Short film competition 2016 http://womenandmedia.org/winners-wmc-short-film-competition-2016/ |  |  |
|  |  | : Publications: focusing on Women, Politics and Constitutional Amendments | http://womenandmedia.org/category/publications/wmc-publications/ |  |  |
|  |  | : Two forums with 15 male Parliamentarians and representatives of the WPC on raising awareness on gender-responsive policies. | National level Consultation led by WMC with contributions from 45 WR advocates to build a consensus on the electoral systems and W’s political participation. | Colombo | KII |
|  |  | : Women’s National Convention on Advocacy Strategies in the current political/constitutional framework |  | Colombo | KII |
| Search for Common Ground (SFCG) | OBJECTIVE 1: Greater willingness among Parliamentarians and select Provincial Councils to actively support increased and effective representation of women in politics at the National and Provincial levels | 1.1: Conduct four stakeholder consultations with women parliamentarians to identify three key interventions from the Country Action Plan of the WPC for gender-responsive planning, design and implementation. Provide follow-up support to secure funds for implementation | SFCG, after consultations with MPs, women’s organizations, women’s activists, Women’s Affairs Ministry officials and Women’s committee members, prepared a draft action plan for the Sri Lanka Women’s Parliamentarians Caucus(February 2016). With amendments from the caucus, this plan was launched on the 10th March in all three languages. | Colombo | KII /Case Study |
|  |  | 1.2: Needs assessment focusing on (1) Women MPs, (2) Officers working at the WPC, and (3) the WPC as an institution/body |  | Colombo | KII/Case Study |
|  |  | 1.3: Developing an action plan for WPC and 2 or 3 project proposals focusing on key priorities. | Lack empirical data | N/A | N/A |
|  |  | 1.4: Building networks for Women Members of Parliament at Provincial and Local Governmental level. | Three meetings held on 6th, 22nd and 28th of September, to raise awareness among local women activists of the Amended LG Act. | Colombo Badulla Kurunegala | KII/Case Study |
|  |  | 1.5: Group and tailor-made training for women MPs, their research assistants, and WPC officers | Lack empirical data | N/A | N/A |
|  |  | 1.6: Communication and monitoring and evaluation technical support | Lack empirical data | N/A | N/A |
|  | OBJECTIVE 2: Increased public awareness and support of women’s political representation and participation at the National and Provincial levels | 2.1.1: Conduct one workshop identifying themes/messages/issues for advocacy material on women’s political and democratic rights/women in decision-making and ‘Vote for Women’ with partner organizations and relevant experts. | The Vote for Women media campaign launch took place from 3:30 – 5.00 p.m. on August 15, 2015 . Joint initiative by SFCG, WMC and AWAW. | Colombo and Kandy | FGD/KII |
|  |  | 2.4: Launching and maintaining a social media campaign designed in activity 2.1 (above) | Introduction of social media platform of the campaign (consists of a Facebook page (facebook.com/VoteWomenSL) ,Twitter page (@vote_women_sl) and Instagram page (votewomensl). | Colombo | KII |
|  |  | 2.5: Conduct two training programs for 25 Sinhala/Tamil radio journalists on ‘Common Ground approach’ and script writing. Those who followed this would then be invited to - Half-day coaching session on ‘women empowerment’ - Developing a drama script that focuses on ‘Women’s empowerment and gender’ - One day script finalizing workshop | Training programmer held for journalists from Tamil, Sinhala and Muslim communities. The participants represented media organizations such as Vasantham FM ,Ruhunu Sevaya, Kathurata Sevaya, and Sri Lanka broadcasting cooperation. This was the second training programme conducted for them. | Colombo | KII |
|  |  | 2.6: Conduct a three-day training workshop for 25-30 journalists in English medium on ‘Gender Sensitive and Responsive Journalism | Professional Training Course on Radio Drama for Social Advocacy (18-20,Sept. 2015). A 3 day training program to develop the skills and knowledge of radio journalists to develop the capacities of these journalists to ensure that they can produce radio programs that are conflict sensitive while at the same time being attractive and interesting to the local audience. |  |  |
|  |  | : Building profiles of WPC members. | Book | Colombo | KII |

Source: Based solely on Partner reports submitted to UN-Women Sri Lanka

While it is possible to be critical of the fact that some Partners had not complete their initially submitted Activities. However, due to the complex political transformation that occurred during the period 2014 – 2016, it is understandable that there was a shift in the focus. This is clearly indicated by Dr. Kotagoda.

“The proposal was for increasing women in local. For that, in 2015, we had this digital animation spots. “But our whole idea was based on local government. We canvassed but then in 2015 it was cancelled. We designed a poster. We campaigned to increase voting for women. Therefore, it was difficult to complete everything for what we applied for in 2014. [Suddenly] When we got funding, we were bang in the middle of the General Election. In 2015, we wanted to check how women were spoken about in Parliament. Then we realized that there was another aspect that needed crucial focus and that was on Constitutional change. So we spoke to UN-Women [Sri Lanka], and they said ok … So most of 2016 was supporting women to make representation to the Representation Committee that was part of the new Constitutional making process.” (Dr. Sepali Kotagoda (WMC, recorded with permission).

- Ethical considerations in the evaluation

Ethical considerations for this evaluation included areas listed below.

- Independence and Impartiality through Triangulation

The data gathered for the evaluation included review of existing documentations from UN-Women, the partner reports; Interviews which were conducted by the Consultant and experts (on women in local government) and by trained Research Assistants (RAs); Focus Group sessions (only with the partners and mainly by the Consultant); Case Studies; and Survey. It was understood that there were inherent strengths and weaknesses in this endeavor. The documentations were limited in nature and there were instances where the contents did not fully illustrate the amount of work completed by the partners. In conducting interviews, while the information was rich, and in-depth, it was also very time consuming. Moreover, the survey was limited to University students who participated in one activity by one partner. They were interviewed via telephone so there was a limitation in terms of numbers and in terms of visually observing the responses.  In brief, there was triangulation of data – interviews, surveys, and focus group discussions, coupled with case studies and documentary evidence – which ensured lacuna in one would be compensated by the other. It also prevented skewed analysis as data flow was from diverse sides.

The training of the RAs, conducted in two sessions – 3rd December and 16th December 2016 – provided the core investigative team to ensure that the RAs would work under these strict requirements. This meant triangulation of investigator as a method of research to ensure validity and reliability. Two triangulations – method and investigator – along with the use of qualitative and quantitative data analytical tools meant that

- The researcher’s bias was avoided since both the RAs and the core researcher specialists/experts would conduct interviews – one observing whilst interviewing, the other writing and observing – in order to provide a clear picture of the different opinions expressed by the participants.

- It also provided a means of fact-checking of sorts, whereby the key informants’ statements were examined for validity through observation of their practices and through their attitudes.

The qualitative and quantitative approaches also meant that a more comprehensive picture of the reality among people who dealt with disability on a daily basis. Triangulation, of method and investigator ensured transparency of the whole process since each statement in the evaluation has empirical evidence backing it.

- Understanding power relations in order to promote participation

The Consultant was mindful of the power asymmetry in dealing with women. This was very evident in women in the Plantation sector. Women are marginalized under technical, social and political dimensions. However, to compensate, the Consultant took three steps: i.) Interviewed women by themselves where possible, ii.) Interviewed men separately, and iii.) Used the ‘levels of severity of gender problem’ as a lens to make sense of the power disparity and the focus of this evaluation. In Sri Lanka, there is a sever type of gender problem. The data on women in politics emphasize the reality of a ‘gender gap’. The statement made by former Member of Parliament (MP) Ms. Rosy Senanayake, for example, can be taken to highlight gender concerns.

It is unfortunate that in general women are not considered strong enough to be in the political arena. Being a woman itself is a challenge to enter into politics. I myself had gone through a long list of barriers, which could be discouraging. I have been in politics for over 28 years but I worked for the party for 20 to 22 years before I actually got nominations.

I was not taken seriously and my decisions were also not taken seriously. They often do not consider giving responsibility or a key position in the party to a woman.  However, majority of people who work in politics at the grassroots level are women and there are plenty who have the capacity to come into local councils, then to provincial and national politics. (2014).

The structural and cultural violence against women who wish to enter politics in Sri Lanka is evident. The statement illustrate the existence of the ‘gender gap’, ‘gender discrimination’, and ‘patriarchal control’.

LIMITATIONS

The evaluation faced a number of limitations, which had to be overcome by the Consultant in order to complete the task on time, effectively and efficiently. The matrix (Figure 3 below) summarizes the limitations faced by the Consultant (inner circle) and the methods used to overcome/compensate for those limitations (outer squares).

- The Evaluation process

  - Time Constraint: more than the period given (25 working days, from November 25th to December 30th 2016) was the fact that there were a number of holidays during the evaluation period in Sri Lanka. This resulted in the unavailability of some stakeholders/beneficiaries. Moreover, those in the government (i.e. local and provincial government level) sectors were busy with end-of-year work that had to be completed by 31st December 2016. They therefore were reluctant to take time off to meet the Consultant and/or Specialists. The trade-off for both these was to allow these individuals to set the time for meetings. This resulted in a number of interviews taking place after 20th December. There were times when the Consultant had to return on another day (as in returning to Batticaloa) to ensure that the all relevant information was gathered. On one occasion, the stakeholder from Puttalam was interviewed in Colombo.

  - Methodology was such that the Consultant had to gather four specialists/experts to assist in conducting the field research (i.e. KII, Survey, FGDs, and Case Studies). Each of the specialists had extensive experience conducting field research and, more importantly, had a background in conducting research on gender sensitive issues and on local government elections. They, along with the RAs provided the relevant material on time.

- Partner Reporting

  - Documentation/reporting was not adequate. The partners’ reports (see Table 2 above) lacked in-depth insights and analysis. The reports were not framed under formal framework and were not presented in a similar fashion. This lacuna was overcome by interviewing the partners, the trainers, the beneficiaries, and UN-Women Sri Lanka members. The UN-Women staff also provided copies of names and addresses from the signature lists of all participants.

  - Activities in workshops: The structure of all workshops was similar with a large amount of time focused on lectures followed by group discussions and presentations. This format, while commendable in that it provides information vital to the participants, can often re-affirm issues and not challenge them. Moreover, information on how those who did not participate fully were included in the workshop sessions was not adequately presented in reports.

  - Level and target group: Some of the workshops target specific groups but lacked cohesiveness in the depth of the contents. According to an interview (26th December 2016), the introduction to journalists on ‘gender’ sensitivity included young journalists as well as veterans. Whilst commendable that veterans can be used to guide the novices, reports on how that was done was not clearly indicated.

- Lacked Monitoring and Evaluation. Teaching a group to create a drama, whilst very impactful, was never evaluated by interviewing or by observing the participants’ use of the knowledge/techniques.. This was overcome by the Consultant by interviewing a selected number of the participants. In Nuwara Eliya, for example, the impact on Plantation sector Workers’ views on gender equality and importance of political education had been tremendous (KII 22nd and 23rd December 2016) but was never included in the reports provided by the partners since there was no follow-up.

- Gender Awareness: From the perspective of Women’s Empowerment Tool 1, which analyzes levels of equality, it is apparent that the focus was on Conscientiation and Participation. However, what was not clear from the initial documentation was whether the workshops, awareness campaigns, etc. targeted men and women equally. Moreover, there existed a lacuna on the methods used to ensure gender awareness (for journalists for example). Follow-up interviews compensated for this lacuna.

Figure 3: Limitations Matrix

FINDINGS

ANALYSIS

This section intends to present a summarized version of the findings and then, below, illustrate with empirical evidence the reasons for certain conclusions. The analysis begins from the Project design itself. As noted at the outset, the project was designed pre-2014 but came into effect between 2014 and 2016. During this period there was a political change that was never anticipated. As a result of the Presidential elections of 2015, a new President (Maithreepala Sisirena) with a different agenda came to the forefront. An unforeseen outcome was the postponement of local elections. Thus, the Tables 4 and 5 below provides an analysis of the project (proposal to implementation) itself. It examines the Outcomes and Outputs as envisioned in 2014 (see Box 1).

Box 1: Outcome and Outputs

Outcome 1: Capacity Development and Attitudinal/Behavioral change - Strengthened capacities of women including youth and civil society organisations for greater participation of women in political and institutional mechanisms, at national and provincial levels. - Increase women’s influence in national and local governance institutions by strengthening their voice and participation in political and institutional mechanism at national and local level through capacity development - Partner with the media in Sri Lanka to build awareness on the issue of under representation of women in national and local governance and advocate for women’s political participation Outputs 1.1 and 1.2: capacity development, networking, knowledge and attitude transformation Outcome 2: Institutional and Legal Change - Enhanced understanding among parliamentarians (both women and men) to support and advocate for greater representation and effective participation of women in Sri Lanka’s governance structures. - Advocate with parliamentarians for greater representation of women in Sri Lanka’s governance structures and institutions through a mandatory quota for women. Output 2.1 and 2.2: capacity development, knowledge and attitude transformation

The proposed Outcomes mentioned here include changes to institutional (Parliamentary), legal (the Constitution), and behavioral (awareness lead to change in perception) capacities that can transform the structural violence prevalent when looking at women in politics (see Box 1 above and Annex V). The findings regarding the completion of activities:

- Relevance: With the exception of one activity (Activity 2.1.1: Conduct one workshop on identifying themes/messages/issues for advocacy material on women’s political and democratic rights/women in decision-making and ‘vote for women’ with partner organizations and relevant experts), which had a broad focus, all activities were specifically targeting gender equality and human rights as it pertained to the project design in the UN-Women Sri Lanka project. The exception here was a two-day workshop which had examined human rights, good governance, and gender-responsive budgeting and had come out with two action plans. They had however included aspects of ‘health-teen pregnancies, unsafe abortions, migrant women among others. This means that all – with the exception of the above small divergence – were very focused on the relevance of their activities.

- Efficiency and Effectiveness: The tasked taken over by UN Women, including working with the National Committee on Women, supervision of partner activities, and organizing meetings with key stakeholders, were also completed, albeit in 2016.

- Sustainability: The UN Women Sri Lanka, for example, provided unstinting support for organizing events, such as the one for National Committee on Women. Their support would ensure sustainability.

- Impact: Training ‘English medium’ journalists on drama might have limited impact to Sri Lanka. Sri Lankans predominantly listen to their native language radio programs (including radio-plays) and only the urban class listens to the English medium radio. Also, there is no follow-up so it is uncertain whether this training reached the general public and if so, how.

The impact of activities is often not measureable for a two-year project. However, it is also important to mention that some activities may have had some measurabe impact.

- WMC: Activity 1.5.1. and 1.5.2 resulted in the publication of a book (available online as well) on Parliament’s Representation of Women: A Selective Review of Sri Lanka’s Hansards from 2005-2014 was commendable. Letters have come from Parliamentarians to WMC thanking them for the work. At the same time, other Parliamentarians commented that

“I have never heard about this document. And I check whether this book is available to us as MPs.” (16th December 2017).

Yet, the publication of the speeches itself had brought on a discussion on what is insulting to women. This was evident when Hon. Minister added that “We men never insult women. We treat them with respect. As members of different parties [in Parliament] men and men argue and fight among themselves. But we never insult women.“

Another caveat in the analysis is that some activities were transformed to accommodate the changing post-2015 election environment of Sri Lanka. WMC: Activity 1.2.2., for example, was a  plan to conduct a one-day consultation with 15 Provincial Council members by WMC, which was not done as expected. What they did was to focus on women activists (see Annex V). To reiterate, the flexibility afforded to the partners by UN Women is not a negative factor. This allowed the partners to effective when there were many changes.

Analysis of UN-Women Sri Lanka

The UN-Women Sri Lanka appears to do a herculean task whilst being under-staffed. The UN Women Sri Lanka contribution can be analyzed from two lenses. The first is as the coordinator of the activities of the partners (AWAW, SFCG, and WMC). The second is as an entity that designed and implemented activities under the broad rubric of ‘Women’s Political Participation’.

- Sustainability: UN Women Sri Lanka provided the initial introduction of the partners to each other, provided basic training on budgeting, and conducted discussions for all partners (for which some did partners sent representatives but did not personally attend). The documentation of the project in December 2016 is also commendable.

- Efficiency and Effectiveness: The positive takeaways include the fact that they continuously kept the partners informed and allowed flexibility in terms of activity, submission (in terms of a single format) of reports and evidence. It appears that the UN-Women Sri Lanka team had set out criteria for assessment and budgeting (i.e. trained through ‘gender-responsive’ budgeting workshop) but still allowed the partners to submit reports and expenses in slightly different formats. Whilst commendable since this flexibility allows partners to submit information on time, it also hinder evaluation since reports provide different depths in terms of insights. Other than collecting the documents submitted to the UN-Women Sri Lanka by partners on workshops and campaigns, they have had limited opportunity to observe the partners in action. The names of the UN-Women staff appear only in one workshop.

At the same time, UN Women Sri Lanka team provided funding and helped organize events that impacted women’s empowerment.

- Relevance: A rough video of all their activism provided information on the activism, networking, and organizational skills utilized the staff members. They constantly interacted with the Women’s Caucus at Parliament, the Ministry of Women and Child Affairs, the National Committee on Women, male politicians, activists, and trainers. The lacuna in activism was due to staff limitations rather than interest.

- Efficiency: UN Women Sri Lanka provided a certain amount of freedom for the partners in report writing and submission of expenses. At the same time, when they took over the organizing of events, their skills were evident. “The UN Women took over all aspects of organizing the event. They paid for everything. We just did the programme” noted Ms. Sumanasekara, the Chairperson of the National Committee on Women.

- Sustainability: A positive aspect of this analysis is the fact that UN Women Sri Lanka successfully coordinated a number of events, including the ‘Round-table discussion on women’s political participation’ where activists and specialists were brought together on 14th December 2016 to examine future training programs and voter education campaigns. Ms. Swarna Sumanasekara, the Chairperson of the National Committee on Women, praised the assistance given to their activities.

Analysis of Partners

According to Bartsiotas and Prom-Jackson in the Review of the Management of Implementing Partners in United Nations System Organizations, parties responsible and accountable to UN-Women to manage individual programs and projects. Each project has one implementing partner. In this relationship with the partner, there are some ‘Duties’ and ‘Responsibilities’ that the UN system expects of a Partner.  These do not appear to have been taken into consideration during the initial period or in subsequent monitoring and evaluation periods. The ideas adapted from Bartsiotas and Prom-Jackson (2013) are listed below:

Analysis of Activities

To reiterate, the overarching attempt of this project is to ensure the self-actualization of women who want to enter into politics. In other sense, it is possible to state that the project envisioned the reduction of cultural violence and the end of structural violence against women in politics. It is because of this that a good analysis must be made to understand how they hoped to ensure that the outcomes and outputs were positive.

- The most significant activity for all three partners was the ‘Vote for Women’. This in some sense was a success in that the partners used their own skill-set to disseminate knowledge. At the same time, without voter education as the foundation, the impact of such a campaign might not be as successful.

- The work with the Parliamentary Women’s Caucus was also important. According to Mr. Abdul Majeed Nzamuddin, the Coordinator of Parliamentary Caucus noted that the Caucus members work without political affiliation. Since it works to empower women parliamentarians, partner networking with this caucus is crucial. The Caucus was able to help pass the Local Government Amendment Act, which enables 25% female representation at Local Government elections. The Caucus designed an Activity plan for 2017 and its four objectives are:

- To enhance the capacity of the caucus and it is individual members

- To contribute towards the ongoing and proposed governance, economic and political reforms

- To increase women’s active participation and political representation at local, provincial and parliamentary level

- To focus on women affected by disasters and others recovering from conflicts.

The activity plan that was drafted was assisted by SFCG, although other activists not related to UN Women project was also involved. .

- Another crucial activity was the creating of a Regional Caucus. As will be discussed below, while the idea of such a caucus is good, it needs follow-up sessions with networking between grassroots and decision makers being at the heart of the workshop sessions.

- While a great deal has been analyzed below on activism by and for women, the focus here should also be on the youth from Universities who were included in the poster campaign conducted by AWAW. The focus on youth is important as they – both male and female – are new to the idea of women’s participation and therefore, it is possible to assess/evaluated the impact of poster campaigns on their attitudes (see Box 2 in Annex IV).

These 10 students spoke of their understanding of the aim of the workshop (see Chart 1, Annex IV).

- Impact: It was one day workshop. Most of the participants do not recall the names of the resource persons and few remembered a woman lecturer’s name, Mrs. Barathi since the evaluator interviews were months after the workshops. However, it is apparent that youth – whilst not ignorant of women’s rights – retained information.

- Relevance: Most of them have heard of the topics/issues raised in the workshop, but they could earn more knowledge in the subject area through the workshop. However, few stated that some areas, specifically rights and issues of women, are new for them and they came to know them through the workshop. All of them told that the workshop was fruitful for them. They mentioned that at the end of the workshop, they were given a group work. In that assignment, they were categorized into groups and asked them to present the outcome of the group work (See Chart 3 in Annex IV). While the students appear to have understood the barriers, they do not appear to have knowledge on what is sought by women in joining politics, nor on discriminations, insecurities, and hardships of women in politics (See Chart 4, Annex IV).

- Sustainability: The youth did not appear to be interested in campaigning for nominations for women. Thus, while knowledge was gained, that appears not to have created advocates, nor has it embolden them to join politics.

A more in-depth discussion on youth from the Eastern University provided clearer answers (see Charts 5 to 8 in Annex IV; Box 3 below). A caveat; the above interviews were conducted via telephone (see Box 3 in Annex IV). The analysis (in Chart 5 in Annex IV) illustrate that:

- Relevance: The youth from Eastern University were far more critical than their University of Jaffna counterparts since they wanted different insights and information from the workshop. At the same time, whether it is a direct impact of this workshop is hard to decipher but it is apparent that the students had some innovative and interesting ideas (see Chart 6, Annex IV). But at the same time, acknowledged the reality that women are often discouraged from becoming active participants in politics.

- Efficiency and Effectiveness: As the diagram (in Annex IV) illuminate, the futility of a single workshop was expressed by all participants. “A single workshop won’t give us knowledge and tools to change the situation. You need us to become activist but we are without tools” noted one participant. They further noted that the reality faced by women was dire in Batticatoa (see Chart 7 and 8 in Annex IV).

- Sustainability: All the female students (5 out of the 10 interviewed) stated that they will never become politically active under the current status quo. They did not relish the criticisms, discriminations, sexism, and threats they might face. They also commented that they felt their future husbands will oppose such a venture.

The Plantation Sector participants who had a history of working with women and had previous workshop experiences provided a different set of answers. At Nuwara Eliya, for example, seven took part in a FGDs. The coordinator who gathered the participants was Hon. Sivaguru Saraswathi, a member of the Central Provincial Council (see Box 4 in Annex IV).  It is apparent that these individuals were not plantation workers who toil in the fields (see Chart 9 in Annex IV). They however gained some knowledge of women and their political empowerment (see Box 5 in Annex IV). The participants requested that in future, “Bring new trainers so that it will be more successful” noted one participant. To these individuals, there was strong impact (see Box 6 in Annex IV).

- Relevance: The FGD participants reiterated that these changes to knowledge, practice and attitudes was essential in order to help women. This was mainly due to the reality of the issues faced by women (see Chart below).

- Impact: the Plantation workers who participated in workshops conducted by AWAW, the participants noted that there was trickle-down effect. They had to explain their ideas to the villagers, which in turn helped impart knowledge to the villagers as well.

- Effectiveness: These individual would like to go on study tours to areas where women volunteerism/social work/ activism is strongest to learn from those lessons. At the same time, parents do not like young girls from attending or 3 day workshops. So better to have workshops in Nuwara Eliya or any other place close to the Estates (Chart 10 in Annex V).

Analysis of the workshops

- Training methods:

“By the time you understood the contents of the lecture, it was over” noted a Participant on a one-day workshop.

  - Lecture method: some of the lecturers/trainers are well known (e.g. Cyrene Siriwardane and Anoma Rajakaruna). However, there were others who were not only not well known but, due to the lacuna in the report content, it was difficult to assess their abilities to impart knowledge. However, as Annex V illuminated, some participants like the lecture format while others were less enthusiastic about the method/style of imparting knowledge.

  - Discussions: all were free to talk and in their own language. This meant that no one felt intimidated. The participants were happy on that aspect.

  - Practical method: women were trained to give speeches. Once they are on stage, their public speaking was critiqued and advise given to gain confidence. This was greatly appreciated as those who did not have the opportunity to go for this workshop fervently wished that they could also be taught this way.

A finding is that workshops which focuses on lectures alone is not adequate to inculcate knowledge. What is needed include handouts, case study analysis (by partners), and practicing skills with the assistance of a facilitator, forum theatre, plenary discussions, among others (British Council and Action for Development 2015).

- Training content:

  - An analysis of the reports and participant comments indicate that there is little information or agreement on what should be included in a training manual/package.

  - The content of training sessions differed. Some focused on training women to speak in public, others on getting the participants to write a drama. More others focused on imparting knowledge on ‘Women’s Rights’ and on barriers faced by women interested in entering politics. This is in keeping with the reality faced by women, even those who otherwise were well known such as Rosy Senanayake.

  - It was evident that some workshops provided a lot of introductory training. While this is required, the partners did not conduct follow-up sessions for these individuals. If there had been time, this would have resulted in assessing ‘impact’ by examining how knowledge transformed the participants’ (both female and male in some workshops) attitudes (i.e. ‘conscientisation’) which in turn influence their practice (i.e. enable the women to participate in politics with confidence).

  - While the proposed workshop/training for a tailor-made training for women MPs, their research assistants, and the WPCs, it also highlights the fact that politicians who are in places of power face different challenges and therefore require more specific trainings. Moreover, as was made apparent by two MPs, the politicians themselves go for trainings.

“We have had trainings and trainings. Substance and content is useless. Whether it is new or not, most NGO trainers talk of ‘experiences’. We need to know about the Laws. The Local Government Act, Election Laws, Constitutions, Women Rights Laws, and machinery to implement these laws. This is never done by the government or the NGOs.” (Chandrika de Soysa)

“There are training sessions under Education Committees within the Hela Urumaya. We talk about our ideology, we discuss world trends, give leadership training. In addition to which, we send people for trainings such as these. We even have a media coordinator. ” (N. Siri Waranasinghe)

Findings

- Training should include aspects of ‘values’, ‘leadership qualities’, ‘gender and accountability, commitments and required standards’, ‘public expenditure tracking’, ‘participatory budgeting’, ‘advocacy and lobbying’, the ‘structure of local government/provincial councils’ among others (British Council and Action for Development 2015).

- Networking is essential. The UN Women Sri Lanka and the current and any future partners must have this aspect for any project targeting women in politics to be a success.

- Trainers:

  - Some of the trainers were men. While this is commendable, there were some complaints by participants on why this is so. It would have been beneficial to explain the importance of not excluding men in the discussion to the participants.

  - Some complained that they meet the same set of trainers for every workshop.

A finding is that it is vital that the trainers become ‘facilitators’ in order to impart knowledge and transform attitudes. Some have done this effectively (e.g. WMC) while others appear to have pleased the participants at workshops but at the same time, appear not to have inculcated in-depth knowledge.

- Participants

  - There were three types of ‘beneficiaries’ (see Annex V) who have different requirements in terms of Project Activities.

    - Those who are women’s rights activists who have been working for the advancement of women, some for over 20 years. They have experience, some their own associations and networks. These individuals lobbied, canvased at meetings and therefore had the experience. The case study of Ms. Sumeeka Perera presented below in one such example of someone who needs to gain further and extensive knowledge on how to use tools for advocacy than anything basic/introductory.

    - Those who are young, whose parents/grandparents were from the political arena who had knowledge of issues related to women’s political participation. Ms. Sujeewa Chandrasiri, (DATE) the granddaughter of Somaweera Chandrasiri is the enthusiastic young SLFP organizer for the Colombo District. She is also the Chairman for the Somaweera Chandrasiri Cultural Foundation. She is a young activist, just as Ms. Jeevani Kariyawasm, both of whom fall into a category of those with extensive knowledge.

    - Those who have no knowledge on women’s participation issues but are eager to learn. These include participants of sessions in Kurunegala, Kandy, Batticaloa, among other places. They (as the Beneficiary Analysis in Annex IV illuminate) attend the sessions to gain knowledge. They are content with the knowledge but understand from experience the reality of the discrimination against women in politics. These women must be trained for working at village level.

A crucial finding is that it is imperative to tailor-make the training sessions/workshops for the different needs to the participants. The training given by the partners is commendable but could have been more focused, more professional (some), and better organized in that they are designed based on the abilities/needs of the participants.

- Frequency of Training

  - The reports highlighted the fact that the partners had had only a few sessions where the same participants were invited to attend a more advance training/workshop session.

An interesting finding was that since the participants were part of a long-term commitment to enhancing the political power of women, trainings were a continuation of previous workshops done under different projects.

- Duration and Venue

  - There were half-day, one day and two or three day residential workshops. There are benefits for all these. However, as noted by one (male) participant interviewed, in Nuwara Eliya, there was a reluctance to sending girls to even Kandy for a residential workshop. These men commented on the safety of the girls issue but also of the fact that women had responsibilities which could not be shunned even for two-days.

A finding was that all three types of workshop sessions had benefits. The partners were adapt at organizing and conducting workshops.

- Impact of Training

Impact should include changes to ‘knowledge’, ‘attitudes’ and ‘practice’ in keeping with the Levels of Equality. It is evident from the FGDs and KII of youth that they felt that a single workshop – whether spanning one day or three-days – while enough to impart knowledge, is not enough to provide tools and create advocates. These students were critical of the fact that there was no needs assessment in know of their level of knowledge. They felt that what they were taught was inadequate.

Finding include:

- Voter education, advance human rights discussions were not included in training. There must be a progressive increase in the knowledge gained in order to make informed decisions on women and political empowerment.

- The evaluation of the workshops/training sessions/practical sessions all hinged on the capabilities of the trainer/organizer and the knowledge/experience/expectations participants. There is a lacuna in information on the reasons for choosing both the ‘trainers’ and the ‘participants’. The abilities of the trainer, their skill-level at creating enthusiasm, and their suitability for the task of imparting knowledge and skills, have not been explained in the reports.

- Workshops/training sessions that were designed for particular groups provided the most effective due to the choice of relevant information being imparted in a creative manner. According to Anoma Rajakauna, for example, noted that the workshop for journalists specifically targeted young journalists, both men and women. She added that interspersed with these youth were veteran journalists who were role models for the young electronic, print, and social media journalists.

Analysis of Impact

## According to politicians and government agents interviewed, impact in terms of UN Women Sri Lanka activities is positive. The relationship is developing and there is belief, especially by members of the Women’s Caucus in the Parliament and the Chairperson from the National Committee for Women, that UN Women Sri Lanka has a good reputation for organizing. At the same time, it is apparent that the impact can be difficult to gage (see Annex V) since the period of the project was limited and the evaluation was conducted prior to understanding a long-term ‘impact’. However, it is possible to infer impact. In some cases, when the Partner has done an excellent job (e.g. WMC’s book Parliament’s Representation of Women: A Selective Review of Sri Lanka’s Hansards from 2005-2014) there appeared to be a lack of interest by the people it was targeted for. As one participant at the launched on 30th January 2016 noted,

## “The launch was a grand reception at the Galadari Hotel. A lot of food but few attendees. Hardly anyone from the Parliament. There was only one person I remember who left after a short time.”

## “If there are such incidents of verbal abuse, there is a sub-committee of women to whom the women MPs could complain to. There is a complain mechanism. But it has not received any complaints so far.” (Participant).

Therefore, it is apparent that the dissemination of the knowledge was inadequate. Therefore, the impact of such hard work is meager.

Findings include:

    - To get women candidates, they must be trained over a long period of time on different aspects that will ensure that they are articulate, knowledgeable and have the necessary management expertise to lead. This is not to say that male politicians have all these attributes. But this was the overall idea presented by all stakeholders, from partners to politicians to trainers to beneficiaries.

    - It is an interesting fact that no one has questioned why a quota is needed but a number of those interviewed commented that providing a quota won’t guarantee that the best candidates will be able to come forward. As note dishearteningly by one individual, “Politician’s family members will then be able to come for nominations”. (see Annex IV for further quotations).

    - According to some politicians, setting aside a quota for women to enter into politics should be at the political party nomination level and not at the Parliament level. The lack of internal democracy within the political party system is the issue. Inexperienced or those with family ties are nominated at present because the ‘name’ can get a person elected.

    - Accordingly, the entrance to politics should be skewed in favor of women. There are women who work voluntarily since the 1980s who have the local knowledge and the contacts at local level but have had no opportunity to lead as they are not given nominations.

A FGD summarized the frustration felt by female politicians: Some noted that while the party does call for nominations, they were not nominated despite having extensive experience.

“At the last minute they did not give a chance.  So women went as independent candidates because of this. Sometimes, because they are given information late, at mid-night, some women don’t even have a chance to go as independent candidates.” (Sumitha Perera, Kurunegala).

This aspect is rationalized by another political party decision-maker.

“Any political party, as a party we focus on whether a person can win. We already have two female members in the Central Committee. The Chairperson of the Legal Sub-committee is also a women, Dr. Nirmala Perera. Candidates such as Vishaka Athukorala had a large voter-base and she is a new member. These women have come to these positions through their own endeavor. The Media Coordinator, who is also a lady, plays a major role. Even inside the Party, at District and National level, women play a great role, even acting as Electoral Organizers in some Districts. The Party’s philosophy, the Buddhist philosophy, is that you can rise to any position based on your abilities, knowledge, perseverance and skills. So, women can do this even without a quota. Women have not been granted quotas for education or in any other sector, even jobs. Women in administration, in all places where women shine, they are not given quotas. So why a quota here? If there is one, it is possible that relatives will come.” (Hon. Sri Warnasinghe KII)

With regard to the ‘Regional Caucus’, women who participated in sessions, including  T. Thangavel and K. Konalakanthi from Trincomalee and G. Santhimathi, A. Hansa, and M. Christian from Batticaloa commented on the lack of progress. They noted that the workshop provided knowledge on gender in politics. A crucial finding here is that:

- Political parties should be forced to provide a quota for women candidates. Only then will women be able to come to positions of power.

- CSOs, especially civil forums, have to work to select and support a single woman candidate to win elections.

- Parties must extend financial and physical assistance to women candidates to support their progress in politics.

- On Women

Women from different background were interviewed for the evaluation. While the initial idea for the project occurred prior to the political changes of 2014/2015 and therefore was designed to target a local government election, the partners expanded or altered their Activities in order to rally behind the newly evolving political needs. In the process, it is apparent that the partners targeted women from different sectors (Plantation sector workers, Provincial Council members, MPs, among others).

Findings include

- Some workshops – according to the reports submitted to UN-Women – were specifically designed for the participants while others lacked information on the practical application of the ideas imparted. In one session, for example, a workshop/training conducted by WMC targeted the women participants by training them on public speaking. This was an example of correct targeting. At the same time, there were workshop sessions in which the basic background information was not imparted prior to a discussion on a knowledge-heavy topic such as constitutional changes. Moreover, the village level concerns appear not to be part of the training. This was reiterated by a participant who noted sadly that in practice some of the ideas imparted did/would not work.

- There is no indication as to whether the target group are the women who participated in the workshops or women in the area which such participants represent. Training the enthusiastic female political participant on human rights in itself is inadequate if dissemination of knowledge (i.e. “Strengthened capacities of women including youth and civil society organisations for greater participation of women in political and institutional mechanisms, at national and provincial level”) into practice and attitudes is to be successful.

- Though participants were genuinely interested in the advancement of women in politics, they also require skills and knowhow on how to impart knowledge gained at workshops to their supporters.

- Another problem was that there were workshop where men and women were both included (e.g. AWAW at Nuwara Eliya; Journalist workshop SFCG) but in the majority of the workshops, only female participants were included. The men constitute a vote base whose attitudes towards women must be transformed.

- The participants lamented on the difficulty in meeting members of the Parliamentary Women’s Caucus. There was a concern that women do not actually help women. This is reiterated by a Politician: “Local government politicians are invited to the Parliamentary Caucus on rare occasions, like the Women’s Day or for some useless training program. Or to talk about the Local Government Acts. Nothing else.”

- On Media

According to one politician, the media stereotypes women.

“They show women bathing, using various products, looking after kids, eating and drinking. These advertisements waste people’s time. Why can’t they portray women as role models in the villages and the cities? Women who have taken the initiative and have thought out of the box, done something spectacular. You never see this. They can interview such people [women] once a week.”

This finding is reiterated by the Hon. Dr. Sudarshani Fernandopulle, the Chairperson of the Parliamentary Women’s Caucus commented on the fact that media does not do justice to women. There is a lack of interest in how to capture the media, ensure peace journalism and media monitoring.

It is possible to have a social media campaign on ‘name it, change it’ (as done by Women and Media Centre http://www.womensmediacenter.com/pages/media-monitoring-education) along with tracking sexual harassment can provide different lenses to reporting of women. Women, as noted by a journalist, portrays women as either victims or naggers. But, as emphasized by UN-Women in the Asia Pacific region, media is crucial as

Media plays a very important role in our daily life. Media helps form our social values. Partnering with private sector organizations, UN Women has been promoting the use of media, especially social media, as a powerful tool to advocate for elimination of violence against women and promote gender equality”. (http://asiapacific.unwomen.org/).

The team from WMC has focused on twitter, youtube and facebook to bring attention to women’ issues including vote for women campaign. They have uploaded the best short films (of 2014) that highlight the needs of women in politics. Moreover, they have incorporated news spots in local television. Such innovative approaches can help transform attitudes and impart knowledge (see Case Study in Annex V).

- On Youth

Youth as noted above, were knowledgeable but were reluctant to become activists or politicians. They felt that the knowledge gained was inadequate for them to become active for women’s rights (see above Charts 1-8 and the analysis).

Analysis of Reporting

There does not appear to be a pre-set criteria for evaluating performance. The lack of a performance indicator is an issue in understanding the ‘impact’ of each of the activities. The reporting requirements appear to be lax in that most of the work carried out by partners is not highlighted adequately.

Analysis of Partner Monitoring and Evaluation

It is evident that monitoring and evaluation criteria is not given. This is a major concern in the evaluation process. There are two examples of post-workshop evaluation (WMC and AWAW) but these were done immediately after the sessions. What has been neglected is the importance of evaluation several months after the workshop/training to understand the impact. WMC does have an analysis of those who watched their short films on YouTube and who commented on twitter/Facebook. This is a good approach.

Findings include

- UN Women Sri Lanka was detailed oriented with regard to their own activities. They provide detailed activity sheets and budgets. It is apparent that, whilst late in initiative the activities (since most occurred in 2016), they are impactful.

- There is a need to include workshop training modules in order to comprehend the depth of what is being taught and whether such knowledge/skills are required for the specific audience (see Annex V).

- The partners often provided information on the Resource Persons but not their qualification to conduct such workshops.

- Monitoring appeared stringent with regard to fund allocation.

- Partners require further training on how to work inside the UN system. As noted by one member of UN-Women, sometimes reimbursement was delayed because the partners did not forward their financial information in accordance with the exacting standards of UN. This despite UN-Women having had a training session on budgeting with all three members.

- The fact that a baseline was never done is a concern. However, there is enough existing data (some verifiable while other not) on the reality faced by women who wish to enter into politics.

CONCLUSION

RECOMMENDATIONS

The project design envisioned a mainstreaming of gender equality in politics in Sri Lanka. To some extent, the partners and UN Women have done a herculean task in the short period of the project.

- It is possible to change sexist attitudes of the populous by ‘Re-Framing’ the argument. Instead of Women Empowerment, etc. term it “Partnership for Democracy”.

- Strategizing

  - Promote women’s participation but focus on the obstacles and the advances made by women

    - Obstacles such as those faced by rural women; advocates; activists; and men who support women’s empowerment.

    - Advances can be presented by proposing workshops for each level

      - Parliamentary level:

        - Awareness: Constitution, Rules and Regulations within Parliament;

        - Activism: areas where women have to be vocal (all)

        - Visibility: media attention (build rapport with specific media personnel/organizations. Get invitations for discussions/talks; invite media for events etc.)

      - Potential nominees for national/local government level

        - Knowledge/Awareness: Constitution, Rules and Regulations at national/local government level

        - Skills: public speaking; organizing; administrative; leadership.

        - Visibility: training of the use of traditional and non-traditional media.

        - Funding: how to find funding.

  - Challenge the ‘Boy’s Club’ mentality

    - Media campaign on role of male Parliamentarians

      - Their responsibilities as citizens/elected representatives (half of whom would have been voted in by women)

      - Their language

      - Their actions

      - Their family life and how it impacts vs. women’s

    - Highlight the family as integral

      - Role of women and men (paternity leave)

    - Male and Female Parliamentarians together focus on a crucial issue

      - Combatting Alcoholism and Drug addiction through Rehabilitation

      - Childcare and Women’s Employment

      - Increase Migration of Educated men and women

    - Be a mentor/role model to the people

- Learn from others

  - South Asia

  - Rwanda

- Highlight that having a quota for women in politics does not do away with corruption/nepotism. Accountability, transparency, and integrity should be attributes to be inculcated.

Recommendations

- Promoting a focus

- Activism for Women

Holding campaigns, having workshops and trainings are essential. They help disseminate knowledge. This focus must be sustained in for future projects.

- Political participation of women

While political participation of women is essential, there must be a greater discourse on the best ways of achieving this. These include a discussion on the validity of demanding special provisions for women through a quota system when (a) no quota system has been set aside for women in other sectors and they have excelled in those areas; and (b) the quota system highlights the fact that women are a group to be protected (i.e. Article 12(4), Sri Lanka Constitution 1978) and therefore not equal to men; and (c) a quota system is required at nomination from party level as this might make the political parties more democratic.

- Voter Education

Voter education to the general public should be undertaken along with women’s activism. This is clearly not part of this project as it stands. However, it is possible to fill this lacuna in future proposals, as highlighted by the suggestion made by the Ms. Swarna Sumanasekara, the Chairperson of the National Committee on Women. It is possible to train women who are politically active to go back to their respective Districts to educate the populous. This has to include education on the Constitution and the need for Constitutional reform. As Hon. Dr. Fernandopulle noted,

“In the Constitution, Article 12 (4) women have been lumped with disabled people and children. Because of that, that it is established that special laws should be enacted by them. Women should not be treated as a vulnerable group”

- Internal democracy in political parties

As long as there is no transparency and accountability in the nomination process in the political parties, it is unlikely that a quota alone will ensure that the best female candidate is selected. There is a shortfall in terms of party support for female candidates as noted both by the elite in the party and by those who want to get into mainstream politics. For example, Dr. Sudharhani Fernandopulle, Chairperson of the Parliamentary Women’s Caucus, noted that

“Party structure from top to bottom are not open to women leaders. This structure has to change if we are to give effect to democratic ideals. Therefore we have to attract able women to support the party … Women’s Wing have not promoted and protected women’s rights as expected of them. Instead, they have been utilized in canvassing and gaining more votes for the parties.”

Moreover, the demand for a set of criteria for female candidates has resulted in the creation of a document by the National Committee on Women. As this set of criteria is presented only for women. It is vital to enhance the internal democracy of political parties through systematic campaigns and continued discussions.

- Capturing the Motivation of Women

It is possible to capture motivation by women who wish to or are part of the politics of Sri Lanka. It is difficult to find out, as one politician noted, whether “Women in the country are not ready and women in the parties still not interested.” A gendered evaluation can highlight the lacuna in protection or motivation, which then can be filled.

- Right Method/Best Practice

  - Best Practices:

- All attempted to work with the Constitutional Council and the Parliamentary Women’s Caucus. Engaging both male and female parliamentarian is vital for changes in attitudes to occur, which in turn would assist in creating new laws that benefit women. However, it is vital to stress that the partners did not find it easy to get the politicians involved. As noted by partners, this was a difficult task as it is was next to impossible to get all 13 female MPs together. But, it is crucial that these female politicians be encouraged to participate and that they be given assistance/knowledge/skills that are not of the norm.

- Use of different methods – from workshop lecture/discussion/group work/presentation to use of social media – to disseminate knowledge. The workshop that was praised the most had the female participants learn public speaking. The workshops that were most criticized was those that were half/one-day where a lot of information was crammed into the short time-span but with little practical tools provided.

- The focus on analyzing Parliamentary speeches. This should be expanded to include analysis of media-bias, and speeches outside Parliament by politicians. Only by highlighting the words used, can the blind acceptance of sexist/discriminatory/demeaning references to women be challenged. Only with that can cultural violence be extinguished and structural violence faced head-on. Only then would it be possible to achieve true participation of women.

- The targeting of male and female for workshops/training sessions for journalists, youth, and Plantation sector participants, is an exceptionally and should be extended where possible.

- The use of a number of experts – e.g. Anoma Rajakaruna, Jeeva Kariyawasm – coupled with those with extensive experience (e.g. Sumeeka Perera) help make sessions interesting and insightful. More specialists – male trainers – should be included.

  - Coordination

The fact that the partners with the assistance of UN-Women Sri Lanka were able to coordinate the ‘Vote for Women’ campaign is commendable.

- Despite each partner (a) working on different Activities in different areas of the island and (b) having other projects along with the UN-Women one, it is vital that such coordination be a part of future projects.

- It is vital to remove replication, provide peer evaluation, and allow for nuanced methods for disseminating knowledge.

- While some of the partners appear to have made use of this project by UN-Women to expand their existing projects, UN-Women should fund projects where long-term commitment for an activity exists.

  - Professionalism:

On paper and in talking with the partners, it was apparent that these individuals were very articulate, knowledgeable and experienced. Yet, the report were (a) not based on a single format, (b) had numerous repetitions, (c) lacked crucial information (e.g. names of partners, modules used to train, examples of laws discussed, names of trainers, etc.), (c) appeared to have been spliced from different reports and/or inception reports. Professionalism, however, was evident in their networking.

  - Accountability and Transparency

According to UN-Women Sri Lanka, there does not seem to be any irregularities in terms of financial disclosure. Transparency is a concern in terms of what is disclosed with regard to the workshops. The Partners should provide the relevant information to the UN-Women for recording purposes.  These include:

- The names of resource persons are included in the Reports but why they were chosen is not apparent. The CVs of trainers and specialists are missing.

- The pre-requisite evaluation by participants at the time of the workshop and later, it is difficult to think of transparency and accountability. While one partner did mention that “It is difficult to check on ‘impact’ in such a short period of time”, it is still possible to evaluate at least the short term impact (positive or negative).

- Are there better ways of achieving the results?

  - A Nationwide Voter education campaign

  - Critical discussion on the need for quota

  - Internal democratization of political parties

  - Creating an anti-sexist Media

  - Gathering experts with innovative approaches to get ideas across

ANNEXES

Annex I: TOR

Date of Issue: 27 September 2016 Closing Date: 03 October 2016 SSA Announcement No. UNWOMEN/MCO/2016/042 - POSITION INFORMATION Title; Consultant for Final Evaluation of Project - ‘Promoting Women’s Political Participation in Sri Lanka’*. Duty Station; Colombo, Sri Lanka (Home-based). Type of Contract; SSA. Contract Duration; October to December 2016 (25 working days). No of Positions; 1. Contract Supervision; Monitoring and Evaluation Unit, MCO and Programme Analyst, Sri Lanka. *Open to Sri Lankan Nationals only - CONTEXT UN Women, grounded in the vision of equality enshrined in the Charter of the United Nations, works for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security. Placing women’s rights at the centre of all its efforts, UN Women leads and coordinates United Nations system efforts to ensure that commitments on gender equality and gender mainstreaming translate into action throughout the world. It provides strong and coherent leadership in support of Member States’ priorities and efforts, building effective partnerships with civil society and other relevant actors. In Sri Lanka, UN Women promotes women’s political leadership and gender responsive governance, based on enhanced capacities of women, youth, female and male parliamentarians and the media through its project on Promoting Women's Political Participation. The project supports the creation of a substantive body of knowledge to inform measures including; policy advocacy, training and capacity building, coalition building and lobbying for mainstreaming gender in the governance structure of Sri Lanka. The two-year project (2014-2016) is implemented in coordination with three local partner organisations. Financial support for the implementation of the project is provided by the Government of Norway, amounting to a total budget of USD 300,000. In Sri Lanka, the percentage of women in Parliament since the 1930s has never exceeded 6%. Though a majority of women exercise their political rights as voters or campaigners during election periods, less than 5.8% of women were elected in to Parliament at the recently concluded General Elections in 2015. Women’s representation at the municipality and local governments’ level was poorer at 2 % for the period 2008-2012. Further, the lack of opportunity for political training and skills development creates a vicious cycle, impeding women’s participation in politics. There are various factors inherent in Sri Lankan politics which impede women’s political participation. Socio-economic barriers, limited access to resources coupled with a deeply patriarchal society impedes women to participate fully in public life. Gender stereotyping, the lack of financial resources to sponsor election activities, the lack of child care support system at the community level particularly restrict women’s ability to engage in public discourse and social networking, critical to political representation. The gender intensive preferential vote electoral system has further discouraged women’s participation in elections. In Sri Lanka, politics is regularly interspersed with violence, particularly during election periods further discouraging women from engaging in the political sphere. In response to the socio-political background, UN Women developed the two-year project in 2014 to enhance political will for creating an enabling environment for women’s representation and participation in politics at national and provincial levels. The programme works to contribute to the achievement of the following outcomes: - Strengthened capacities of women including youth and civil society organisations for greater participation of women in political and institutional mechanisms, at national and provincial levels. - Enhanced understanding among parliamentarians (both women and men) to support and advocate for greater representation and effective participation of women in Sri Lanka’s governance structures. There are three main elements to the programme: - Increase women’s influence in national and local governance institutions by strengthening their voice and participation in political and institutional mechanism at national and local level through capacity development; • Advocate with parliamentarians for greater representation of women in Sri Lanka’s governance structures and institutions through a mandatory quota for women; • Partner with the media in Sri Lanka to build awareness on the issue of under representation of women in national and local governance and advocate for women’s political participation The project has envisaged the final evaluation of the project during October-December 2016. The final evaluation is expected to assess the results of the project at different levels (output, outcome and impact), analyse lessons learnt, document good practices and to provide recommendations for a future course of action for enhancing women’s leadership and political participation in Sri Lanka. It is in this context that UN Women intends to commission an independent evaluation of the ‘Promoting Women’s Political Participation in Sri Lanka’ Project. The Evaluation shall take into account and should also refer to the guiding documents for evaluation at UN Women, including the Evaluation Policy, Evaluation Chapter of the POM, the GERAAS evaluation report quality checklist, the United Nations System-wide Action Plan Evaluation Performance Indicator (UN-SWAP EPI) and the Evaluation Handbook. These documents serve as the frame of reference for the Evaluation Manager and the evaluation consultant(s) for ensuring compliance with the various requirements and assuring the quality of the evaluation report. Objectives The overall purpose of the end-of-programme evaluation is to assess programmatic progress (and challenges) at the outcome and impact level, with measurement of the achievement of programme outputs, including identification of factors that affected the implementation, assessing gaps and extracting lessons learnt. The findings of evaluation, especially the lessons learnt, good practices and recommendations will be of paramount importance for strengthening the efforts towards gender equality in gender responsive governance. It will consist of a desk review, field visits, in-depth interviews with UN Women staff, and in-depth interviews with key stakeholders and beneficiaries. It will contribute to results-based management that documents results achieved, challenges to progress, and contributions to the creation of a more conducive environment for women’s political participation in Sri Lanka. The specific evaluation objectives are to: a) Analyse the relevance/appropriateness of the project design, strategy and approaches; b) Assess achievement of outcomes and outputs, with a critical examination of how/to what extent the project supported efforts to promote women’s political participation and strengthened the capacities of beneficiaries, d) Analyse and document lessons learned, best practices, success stories that can be up‐scaled for enhancing Women’s political participation e) Document and analyse possible weaknesses, constraints, challenges and opportunities in project design and implementation f) Provide recommendations to the UN Women and partners regarding specific strategies and approaches for sustaining the gains of the project when designing and implementing similar projects in future. Key evaluation questions to consider (including but not limited to): Relevance - To what extent is the project relevant to the needs and priorities as defined by beneficiaries (individuals, institutions and communities)? - To what extent is the project aligned with relevant normative frameworks for gender equality and women’s empowerment? - What is UN Women’s comparative advantage in this area of work compared with other UN entities and key partners? Effectiveness - To what extent were the expected outcomes achieved and how did UN Women contribute towards these? - What strategies where adopted to achieve the expected outcome? What was UN Women’s comparative advantage in each of the strategy area? Assess the success of these strategies and provide recommendations to scale up and to inform future work of UN Women in similar area. Efficiency - To what extent does the management structure of the project support efficiency for programme implementation? Impact - To what extent was gender equality and women’s empowerment advanced as a result of the project? - What were the unintended effects, if any, of the project? Sustainability - To what extent was capacity developed in order to ensure sustainability of efforts and benefits? Gender Equality and Human Rights - To what extent has gender and human rights considerations been integrated into the programme design and implementation? - How has attention to/integration of gender equality and human rights concerns advanced the area of work? These questions are not considered final and it is expected that the evaluation consultant will refine and develop these together with UN Women. Scope of Work The end-of-project evaluation will assess the collective performance and implementation of all project partners, including UN Women, within the entire project lifespan (December 2014 to November 2016). The evaluation will cover the national and local levels through which the project operated and will assess all aspect of the project. The Consultant will specifically perform the following responsibilities under this assignment: Desk Review: - Conduct a desk review of project documents, progress reports, other assessment and monitoring reports relating to the project. - Conduct a desk review of relevant project and government documents to reconstruct baseline data. Data Collection for reconstructing baseline data and final evaluation: - Conduct interviews and focus group discussions with the concerned stakeholders and key informants at the national and provincial levels. Analysis - Progress Against Objectives: - Assess the extent to which the project strategies have contributed in achieving the project activities, outputs and outcomes. Sustainability, Replication and Scale up: - Review the contextual factors which are important in the sustaining and replicating the project interventions and its impact - Assess the factors required to scale up initiatives in each of the two project outcomes and strategy to do so if required. Project Management: - Review the capacities (technical, administrative and advocacy skills) of the Partners to deliver the project objectives and how they can be strengthened to improve impact - Review the M&E Framework including log frame indicators, tools and processes the Partners use to monitor and report their activities. Review the processes used to systematically document any advocacy initiatives that were undertaken. Partnership Management: - Assess the level of engagement between the Partners and key Stakeholders at all levels and the ability to leverage the partnership process to inform the project strategy. - Assess the value of addition of UN Women in terms of the resources, oversight and technical support Cost Effectiveness: • Assess the level of investment, both human and financial resources, committed for implementing the project. Analyse the Budget and Expenditure over the two-year period. - Review the degree to which project strategies are cost effective in making an impact on the ground and at various levels. Evaluation Design/Methodology The evaluation is expected to have a summative (backwards looking) perspective, to support enhanced accountability for development effectiveness and learning from experience. The evaluation will be results-oriented and provide evidence of achievement of expected outputs through the use of quantitative and qualitative methods. In the lack of baseline data the final evaluation will also entail reconstructing the baseline data through secondary data, recall techniques, key informants and group interview techniques. The methodology will be developed by the Evaluation Consultant and presented for approval by UN Women during the inception phase along with a detailed work plan for the evaluation. The methodology should detail the data collection methods and tools for consultations with the different stakeholders. III. ROLES AND RESPONSIBILITIES The Consultant will carry out the following suggested steps for the Final Evaluation: Inception (October 2016) - Conduct a preliminary desk review of all relevant documents including the project document, LogFrame, implementation plan, monitoring reports, donor reports, project publications, etc. - Conduct preliminary discussions with UN Women to refine the evaluation scope, questions and methodology. - Draft an Inception Report with detailed and refined evaluation scope, methodology and plan including time schedules, sampling and data analysis framework with tools for review by UN Women. - Refine the evaluation methodology/question matrix based on UN Women’s feedback. Data Collection (October – November 2016): - Conduct in-depth review of all relevant programme and project documents and reports - Conduct in-depth interviews with main stakeholders (national/regional public authorities, UN staff, implementing staff, donors, and others as necessary) - Conduct programme field visits. Conduct interviews and focus group discussions with the concerned stakeholders at the national and provincial levels, ensuring the collection of quantitative and qualitative data and case studies. Individual and group discussions, in-depth interviews with key partners and a series of focus groups with the project management team, national partners, counterparts, beneficiaries are envisaged to be conducted under this stage. Both qualitative and quantitative data should be collected in order to triangulate and provide the context behind the numbers. Reporting (December 2016): - Review and analyze all available data. - Prepare and submit a first draft of the report for comments. - Deliver a PowerPoint Presentation of key findings, lessons learned, good practices and initial recommendations to UN Women. - Revise report based on feedback from implementing partners and UN Women. - Submit final report. Deliverables The expected outputs of the assignment include: • Inception Report with details on Scope of Work, Methodology, Tools and Timeframes • A presentation on the draft evaluation findings • Detailed Final Evaluation Report with concrete recommendations to inform future strategy of UN Women. Timeframe The Consultancy is expected to begin in October 2016. The first draft of the Evaluation Report will be submitted by 01 December 2016 and the revised, final Report by 15 December 2016. The Consultant will be expected to provide inputs over a period of 10 weeks from October to December 2016. Action; By When; Who. Signing of Consultancy Contract; October 2016; UN W and Consultant. Desk Review of Secondary Documents; 2 weeks post contract signing; Consultant. Inception Report. Data Collection (Field visits, focus group discussions, interviews); October - November 2016; UN W and Consultant. Analysis/Presentation on initial draft findings; November 2016; Consultant. Submission of Draft Report; December 2016 (1 week post presentation); Consultant. Revision of report following feedback from UN Women, partners; December 2016 (1 week for review of draft report); Consultant. Submission of Final Report; December2016 (1 week post UNW/partner feedback); Consultant. Reporting The Evaluation will be commissioned UN Women MCO. The Consultant will report to the Monitoring & Evaluation Unit, UN WOMEN MCO, and the Programme Analyst, Sri Lanka. IV. COMPETENCIES Core Values / Guiding Principles: Integrity: - Demonstrate consistency in upholding and promoting the values of UN Women in actions and decisions, in line with the UN Code of Conduct. Professionalism: - Demonstrate professional competence and expert knowledge of the pertinent substantive areas of work. Cultural sensitivity and valuing diversity: - Demonstrate an appreciation of the multicultural nature of the organization and the diversity of its staff; - Demonstrate an international outlook, appreciating difference in values and learning from cultural diversity. Core Competencies: Ethics and Values: - Demonstrate and safeguard ethics and integrity. Organizational Awareness: - Demonstrate corporate knowledge and sound judgment. Work in teams: - Demonstrate ability to work in a multicultural, multi ethnic environment and to maintain effective working relations with people of different national and cultural backgrounds. Communicating and Information Sharing: - Facilitate and encourage open communication and strive for effective communication. Self-management and Emotional Intelligence: - Stay composed and positive even in difficult moments, handle tense situations with diplomacy and tact, and have a consistent behaviour towards others. Conflict Management: - Surface conflicts and address them proactively acknowledging different feelings and views and directing energy towards a mutually acceptable solution. Continuous Learning and Knowledge Sharing: - Encourage learning and sharing of knowledge. Functional Competencies: - Consistently approaches work with energy and a positive, constructive attitude; - Demonstrates good oral and written communication skills; - Focuses on impact and result for the partners and responds positively to feedback. V. QUALIFICATIONS & APPLICATION Education: - Minimum Masters’ degree in gender studies, social sciences, statistics, population sciences or other relevant subject Experience: - Minimum 8 years of professional working experience in international development with specialization in Monitoring & Evaluation and quantitative and qualitative data analysis; - Extensive experience of working on projects related to Issues of Women Empowerment and Inclusion; - Good writing and documentation skills; - Proven track record of work in a multi-cultural and multi-disciplinary environment; - Knowledge and familiarity with countries in South Asia would be an advantage. Language: - Fluency in English and Sinhalese/Tamil (both writing and oral). Interested applicants should apply to this announcement through UNDP jobs site: jobs.undp.org Interested individual consultants must submit the following documents/information to demonstrate their qualifications in one single PDF document: - All applications must include (as an attachment) the completed UN Women Personal History form (P-11) which can be downloaded from http://www.unwomen.org/about-us/employment; - Kindly note that the system will only allow one attachment, please combine all your documents into one (1) single PDF document. Applications without the completed UN Women P-11 form will be treated as incomplete and will not be considered for further assessment; - Applications received after the close date will not be accepted; - Only short-listed candidates will be contacted. Evaluation and Selection Criteria Criteria for shortlisting of CVs will be based on the following assessment: - Required Degree and Qualification (5 points); - Minimum Experience relevant to the assignment (5 points); - Experience in M&E (5 points); - Working knowledge and use of computers and its programmes / applications. Experience in the usage of computers and office software packages (MS Word, Excel, etc.) and advance knowledge of spread sheet and database packages (5 points). The evaluation process for selection of the candidate will be based on the following assessment: The technical proposal should include: - Detailed methodology - Previous experience in a similar capacity - Experience working with UN agencies or other international organizations - Skills and competencies related to the assignment - Availability The financial proposal should include: - Fees - The financial proposal shall specify the consultancy fees and all costs (printing, stationary, telephone, internet etc.) in relation to the scope of work of the consultancy. - Travel - All envisaged travel costs (local travel, living allowance, terminal expenses etc.) must be included in the financial proposal. UN Women will not accept travel costs exceeding those of an economy class ticket. - In the case of unforeseeable travel, payment of travel costs including tickets, lodging and terminal expenses shall be agreed upon, between UN Women and Individual Consultant, prior to travel and will be reimbursed. The financial offer will be required at a later stage once the evaluation of the technical proposal is complete. The individuals who achieve the maximum score in technical evaluation will be requested to provide the financial proposal. Only candidates obtaining a minimum of 70% in the technical evaluation will be considered for the financial evaluation. Note: In July 2010, the United Nations General Assembly created UN Women, the United Nations Entity for Gender Equality and the Empowerment of Women. The creation of UN Women came about as part of the UN reform agenda, bringing together resources and mandates for greater impact. It merges and builds on the important work of four previously distinct parts of the UN system (DAW, OSAGI, INSTRAW and UNIFEM), which focused exclusively on gender equality and women’s empowerment.

Annex II: Guidelines

Presented below are guidelines for Key Informant Interviews (KII), Focus Group Discussions (FGD) and Case Studies.

GUIDELINE FOR UN WOMEN PARTNERS - BASIC INFORMATION - What is your organization’s focus with regard to work with women? - Since when? - Why did you want to focus on these aspects? - Which areas of the island? - How is this related to the work you have done with UN Women here? - Your organization’s strengths/weakness with regard to this specific project? - BACKGROUND - What were the broad areas of your focus under this project? - Why did you focus on these specific activities in this project? - Due to observable - Due to reality of the situation - Due to what was told - Other - ACTIVITIES - Steps taken for each of the activities? - How many were conducted - Trainers - Who are they? - What are their qualifications? - What did they use to conduct the training sessions? - Participants - Who were the participants? - How were they chosen? - What was their views on the activities? - MEASURING SUCCESS - How do you measure ‘success’? - How did you measure the impact? - How did you ensure - Reliability - Efficiency - Effectiveness - Sustainability - Gender Sensitivity - OBSTACLES - What was the most difficult thing to accomplish?

GUIDELINES FOR ELECTED REPRESENTATIVES NATIONAL AND LOCAL (MC/UC/PS) - BACKGROUND INFORMATION - Name, Age, Ethnicity - Civil Status - Unmarried - Married (If Married, name and profession of husband) - Divorced (name and profession of the former husband) - Widowed (name and profession of former husband) - Family - Number of Dependent Children - Number of Adult Children in Politics - Number of family members in Politics - Level of Education - Pre-O/Level - Passed O/Level - Passed A/Level - University Graduate - Professional Qualification (Lawyer, Architect) - Other - Professional Qualifications - Occupation - Employed - Primary (Agriculture/Dairy farming) - Part time/Fulltime - Formal/Informal sector - Secondary (Industry) - Part time/Fulltime - Formal/Informal sector - Tertiary (Service Sector) - Part time/Fulltime - Formal/Informal sector - Politics (fulltime) - Unemployed - Fluency in Sinhala, Tamil and English Language (Reading, Writing and Speaking) - POLITICAL BACKGROUND - Number of years in Politics - Career path - From Local to National (how and why) - National (how and why) - In what capacity did you serve? - What is the main reason for entering politics - Self-motivation - To keep Family seat - Have time to devote to politics - Other (specify) - How many times were you re-elected? - Did you have any political or related experiences (welfare society, CBO, Trade Union, etc.) before you entered politics? - What do you hope to accomplish as a politician? (explain) - Do you consider participation of women in politics as important? - If yes, why? - If no, why not? - TASKS OF ELECTED OFFICIALS - How did you serve - Your electorate? - The nation? - What were your most proud achievements which benefitted your constituents? - What are the most common complaints made by the general public regarding - Efficiency - Effectiveness - Did not focus on the target/needs - Other (specify) - GENDER SENSITIVITY - Were you given an induction training? - If yes, what was the training on? - If no, why not? - Were you introduced to - Human Rights - Gender - Women’s Rights - CEDAW - Other - Did you design any programs that focus on women? - As a women, what is the most significant contribution you can do - Improve livelihoods of women - Work for women’s rights - Create political awareness of women - Represent women’s perspectives - Empower marginalized communities - a) Explain why women are under-represented in politics in SL - Lack of political connections - Traditional roles and decision-making patterns (culturally prescribed domestic roles and traditions) - No support from family - Inability to balance family and profession - Persistent stereotypes of women being less capable than men - Lack of confidence - Economic reasons - Low level of education - Educated women are reluctant to come forward - Other (specify) b) Explain how this situation be changed. - Is the media gender sensitive? - If Yes, how was that achieved? (through Civil Society activities) - If No, why not? - SUPPORT - Did you receive any support at the start of your political career - From the political party - From the political party women’s wing - From the Parliamentary Women’s Caucus - From Civil Society - Type of support since - Political education - How to design a budget - How to administer - How to write and give speeches - How to conduct research - How to delegate - How to advertise your work - Other (specify) - Do you know of any Civil Society Group that does provide such support - If Yes, if so whom - If No, why not? - Have you worked with - AWAW - What is their focus? - SFCG - What is their focus? - WMC - What is their focus? - In what capacity? - They Provided Education - On what - You Went for training - On what? - Joined in a ‘Vote for Women’ campaign - Went on field visits abroad - Other (specify) - Did you take part in specific activities of - AWAW - SFCG - WMC - In your dealings with one/all of the organizations, was there - In-depth understanding of the issues at stake - Long-term changes to K-A-P - Short-term changes only - No changes what-so-ever - Replication of activities - Other (specify) - Did you - Read the documents provided to you by the above 3 organizations? - Watch the Animated Video of WMC? - Go to the social media platform to use your voice? - Other (specify) - WORKSHOP/TRAINING SESSION - Name of the Organizing/Implementing partner? - How many workshops did you attend? - If more than one, name them - What type of programs did you attend? - What were the objectives? - Selection - Were you selected or did you hear of this and volunteer your name? - Why were you selected? - Why other were selected? - Who selected you? - How were you informed of the selection? - What remunerations were given to help you to attend? - How did you leave your family/job to attend the workshop? - What was the type of program? - Lectures - Hands on participation - Group discussions/presentations - Other (specify) - Objectives - When you heard of these and initially attended, what did you expect? - What specific outcome do you think these organizers wanted to impart to yo? - Other subjects discussed - Method of Instruction (lecturer-centered lecture/student-centered/discussion/group work/presentations) - If you were divided into groups at any of the sessions, what was discussed in your group? - What were the findings/results of that discussion? - Outcomes of the workshop - Most useful aspect of the workshop/s - Knowledge - Attitudes - Skills - Ways to convert ideas into practice - Challenges faced in implementing the ideas/knowledge gained - Ideas were too simple/not clear enough/hard to understand - Awareness program was not adequate - The workshop did not result in increasing support for my cause/aspirations - Other (specify) - What did they learn (in regard to the subject of women representation) - Empowered more - Increased the dedication of my participation - IMPROVEMENTS - What improvements need to be made to increase the political participation of women in politics? - In your own words, what can be improved in terms of your dealings with (any of these) civil society organizations?

GUIDELINES FOR WOMEN (including ESTATE WOMEN) PARTICIPANTS - BACKGROUND INFORMATION - Name, Age, Ethnicity - Civil Status - Unmarried - Married (If Married, name and profession of husband) - Divorced (name and profession of the former husband) - Widowed (name and profession of former husband) - Family - Dependence - Does the husband work? - Number of Dependent Children - Number of adult family members who are not working - Politics - Number of Adult Children in Politics - Number of family members in Politics - Occupation - Employed - Primary (Estate worker/Agriculture/Dairy farming) - Part time/Fulltime - Formal/Informal sector - Secondary (Industry) - Part time/Fulltime - Formal/Informal sector - Tertiary (Service Sector) - Part time/Fulltime - Formal/Informal sector - Politics (fulltime) - Unemployed - Fluency in Sinhala, Tamil and English Language (Reading, Writing and Speaking) - POLITICAL BACKGROUND - What is ‘political activism’? - Are you allowed to actively take part in protests/discussions/workshops by - Husband - Family (e.g. Father) - Employer - Other (specify) - Are you an active member of a political party or any other civil organization? - What is the main reason for entering politics - Self-motivation - Because I faced discrimination - Because I was asked to - I have time to devote to politics - Other (specify) - Do you consider participation of women in politics as important? - If yes, why? - If no, why not? - KNOWLEDGE ON THE TASKS OF ELECTED OFFICIALS - Why does the Constitution need changes? - Obsolete - Needs new amendments - Don’t know - Other (specify) - How can the Constitutional changes impact you in the Estates? - What is expected of an elected official? - At National/Local level - From Estate region - From Women politicians - What are the most common complaints made by people in the Estates regarding certain politicians? - Not Efficient - Not Effective - Did not focus on the target/needs - Nepotism - Other (specify) - Can you become politically active? - If Yes, Where and How? - In Trade Unions - In CBOs/Welfare societies - At Local/National Level? - If No, why not? - GENDER SENSITIVITY - Do the men in the Estate allow for women to participate in workshops? - Yes, how - No, why not - Were you given any training on political rights? - If yes, what was the training on? - If no, why not? - What is your understanding on - Human Rights - Gender Issues - Women’s Rights - CEDAW - Worker’s Rights - Other - Have anyone (government/political party/Civil Society organization) designed any programs that focus on women in your area? - If Yes, on What? - Childcare and Motherhood - Employability and Career advancement - Empowerment and Entrepreneurship - Other (specify) - If No, Do You Think Someone Needs to? - If Yes, On What? - If No, Why Not? - As a women, what is the most significant contribution you can do - Improving livelihoods of women - Work for women’s rights - Create political awareness for women - Represent women’s perspectives - Empower marginalized communities - Explain why women are under-represented in politics in SL - Lack of political connections - Traditional roles and decision-making patterns (culturally prescribed domestic roles and traditions) - No support from family - Inability to balance family and profession - Persistent stereotypes of women being less capable than men - Lack of confidence - Economic reasons - Low level of education - Educated women are reluctant to join - Other (specify) 7. What can you do to change this situation? 8. Is the media gender sensitive? - If Yes, how was that achieved? (through Civil Society activities) - If No, why not? - CIVIL SOCIETY PARTNERS - Do you know of any Civil Society Group that does provide such support - If Yes, if so whom - If No, why not? - Name of the Organizing/Implementing Partner - Name of the Coordinator - Name of Resource Persons - Have you participated in any activity with - AWAW - What is their focus? - SFCG - What is their focus? - WMC - What is their focus? - In what capacity? - They Provided Education - On what - You Went for training - On what? - Joined in a ‘Vote for Women’ campaign - Was interviewed by them - Other (specify) - Did you take part in specific activities of - AWAW - SFCG - WMC - In your dealings with one/all of the organizations, was there - In-depth understanding of the issues at stake - Long-term changes to K-A-P - Short-term changes only - No changes what-so-ever - Replication of activities - Other (specify) - Did you - Read the documents provided to you by the above 3 organizations? - Watch the Animated Video of WMC? - Go to the social media platform to use your voice? - See any comments in social media - Other (specify) - IMPROVEMENTS - What improvements need to be made to increase the political participation of women in politics? - In your own words, what can be improved in terms of your dealings with (any of these) civil society organizations?

GUIDELINES FOR PARTICIPANTS ESTATE TRADE UNION - BACKGROUND INFORMATION - Name, Age, Ethnicity - Civil Status - Unmarried - Married (If Married, name and profession of spouse) - Divorced (name and profession of the former spouse) - Widowed (name and profession of former spouse) - Family - Dependence - Does the husband work? - Number of Dependent Children - Number of adult family members who are not working - Politics - Number of Adult Children in Politics - Number of family members in Politics - Occupation - Employed - Primary (Agriculture/Dairy farming) - Part time/Fulltime - Formal/Informal sector - Secondary (Industry) - Part time/Fulltime - Formal/Informal sector - Tertiary (Service Sector) - Part time/Fulltime - Formal/Informal sector - Politics (fulltime) - Unemployed - Fluency in Sinhala, Tamil and English Language (Reading, Writing and Speaking) - POLITICAL BACKGROUND - What is ‘political activism’? - Trade Union - What is a Trade Union? - How long have you actively taken part in Trade Unions? - What is the Function of a Trade Union? - Are you allowed to actively take part in protests/discussions/workshops by - Family (e.g. Spouse/Parent) - Employer - Other (specify) - What is the main reason for entering politics - Self-motivation - Because I faced discrimination - Because I was asked to - I have time to devote to politics - Other (specify) - Do you consider participation of women in politics as important? - If yes, why? - If no, why no? - KNOWLEDGE ON THE TASKS OF ELECTED OFFICIAL - Why does the Constitution need changes? - Obsolete - Needs new amendments - Don’t know - Other (specify) - How can the Constitutional changes impact you in the Estates? - What is expected of an elected official? - At National/Local level - From Estate region - From Women politicians - What are the most common complaints made by people in the Estates regarding certain politicians? - Not Efficient - Not Effective - Did not focus on the target/needs - Nepotism - Other (specify) - Can you become politically active? - If Yes, Where and How? - In Trade Unions - In CBOs/Welfare societies - At Local/National Level? - If No, why not? - GENDER SENSITIVITY - Do the men in the Estate allow for women to participate in workshops? - Yes, how - No, why not - Were you given any training on political rights? - If yes, what was the training on? - If no, why not? - Were you introduced to - Human Rights - Gender - Women’s Rights - CEDAW - Worker’s Rights - Other - Have anyone (government/political party/Civil Society organization) design any programs that focus on women? - If Yes, on What? - Childcare and Motherhood - Employability and Career advancement - Empowerment and Entrepreneurship - Other (specify) - If No, Do You Think Someone Needs to? - If Yes, On What? - If No, Why Not? - What is the most significant contribution a women can make in Politics? - Improving livelihoods of women - Work for women’s rights - Create political awareness for women - Represent women’s perspectives - Empower marginalized communities - Women cannot effectively participate in politics - Other (specify) - Explain why women are under-represented in politics in SL - Lack of political connections - Traditional roles and decision-making patterns (culturally prescribed domestic roles and traditions) - No support from family - Inability to balance family and profession - Persistent stereotypes of women being less capable than men - Lack of confidence - Economic reasons - Low level of education - Educated women are reluctant to join - Other (specify) - Is the media gender sensitive? - If Yes, how was that achieved? (through Civil Society activities) - If No, why not? - CIVIL SOCIETY PARTNERS - Do you know of any Civil Society Group that does provide such support - If Yes, if so whom - If No, why not? - What is the name of the - Organizer/Key point person - Resource persons in workshops - Have you participated in any activity with - AWAW - What is their focus? - SFCG - What is their focus? - WMC - What is their focus? - In what capacity? - They Provided Education (On what) - You Went for training (On what) - Joined in a ‘Vote for Women’ campaign - Focused on Constitutional Reform discussions - Was part of the poster campaign - Looked at social media - Was interviewed by them - Other (specify) - Did you take part in specific activities of - AWAW - SFCG - WMC - In your dealings with one/all of the organizations, was there - In-depth understanding of the issues at stake - Long-term changes to K-A-P - Short-term changes only - No changes what-so-ever - Replication of activities - Other (specify) - Did you - Read the documents provided to you by the above 3 organizations? - Watch the Animated Video of WMC? - Go to the social media platform to use your voice? - See any comments in social media - Other (specify) - IMPROVEMENTS - What improvements need to be made to increase the political participation of women in politics? - In your own words, what can be improved in terms of your dealings with (any of these) civil society organizations?

GUIDELINES FOR PARTICIPANTS LAWYERS/UNIVERSITY STUDENTS/JOURNALISTS - BACKGROUND INFORMATION - Name, Age, Ethnicity - Civil Status - Unmarried - Married (If Married, name and profession of spouse) - Divorced (name and profession of the former spouse) - Widowed (name and profession of former spouse) - Family - Number of family members in Politics - Number of Dependents (Children below 18, unemployed/elderly family members) - Level of Education - Pre-O/Level - Passed O/Level - Passed A/Level - University Graduate - Professional Qualification (Lawyer, Architect) - Other (specify) - Professional Qualifications - Occupation - Employed - Primary (Agriculture) - Part time/Fulltime - Formal/Informal sector - Administrative position - Secondary (Industry) - Part time/Fulltime - Formal/Informal sector - Administrative position - Tertiary (Service Sector) - Part time/Fulltime - Formal/Informal sector - Politics (fulltime) - Unemployed - Fluency in Sinhala, Tamil and English Language (Reading, Writing and Speaking) - POLITICAL BACKGROUND - What is ‘political activism’? - What are your political rights? - Are women allowed to actively take part in protests - Family (e.g. Spouse/Parent) - Employer - Other (specify) - What is the main reason for women to enter into politics? - Self-motivation - Faced discrimination - Was requested by friends and relations - Retired and have time to devote to politics - Other (specify) - Do you consider participation of women in politics as important? - If yes, why? - If no, why not? - KNOWLEDGE ON THE TASKS OF ELECTED OFFICIALS - Why does the Constitution need changes? - Obsolete - Needs new amendments - Don’t know - Other (specify) - How can the Constitutional changes impact - You specifically? - On Women’s Representation? - On Rights of People? - On the balance of power in the Parliament? - On gender-sensitivity of policies? - Other (specify) - What is expected of an elected official? - At National/Local level - By people in estates and villages - By Women politicians - In your view, what are the most common complaints made by people regarding certain politicians? - Not Efficient - Not Effective - Do not focus on the target/needs - Nepotism - Corruption - Other (specify) - In your view, what is the most common complaint made by people regarding female politicians in particular? - Not Efficient - Not Effective - Did not focus on the target/needs - Nepotism - Not confident - Other (specify) - GENDER SENSITIVITY - Were you given an induction training at the outset of your education/career? - If yes, what was the training on? - Human Rights - Gender - Women’s Rights - Specific Documents (CEDAW/Rights of the Child/etc.) - Other (specify) - If no, why not? - Did you design any programs that focus on women? If ‘Yes’ explain in detail. - What is the most significant contribution a woman elected representative can do to - Improve livelihoods of women - Work for women’s rights - Create political awareness of women - Represent women’s perspectives - Empower marginalized communities - Explain why women are under-represented in politics in SL - Lack of political connections - Traditional roles and decision-making patterns (culturally prescribed domestic roles and traditions) - No support from family - Inability to balance family and profession - Persistent stereotypes of women being less capable than men - Lack of confidence - Economic reasons - Low level of education - Educated women are reluctant to join - Other (specify) - Is the media gender sensitive? - If Yes, how was that achieved? (through Civil Society activities) - If No, why not? - SUPPORT - a) Did you receive any support to enhance your - Political education - How to design a budget - How to administer - How to write and give speeches - How to conduct research - How to delegate - How to advertise your work - Other (specify) b) From whom did you get this support? - Do you know of any Civil Society Group that does provide such support - If Yes, if so whom - If No, why not? - Have you worked with - AWAW - What is their focus? - SFCG - What is their focus? - WMC - What is their focus? - In what capacity? - They Provided Education - On what - You Went for training - On what? - Joined in a campaign (on what) - Went on field visits abroad - Checked their social networking - Was a resource person (specify) - Other (specify) - Who is the organizer/point-person/key resource person for that organization? - Did you take part in specific activities of - AWAW - SFCG - WMC - In your dealings with one/all of the organizations, was there - In-depth understanding of the issues at stake - Long-term changes to K-A-P - Short-term changes only - No changes what-so-ever - Replication of activities - Other (specify) - Did you - Read the documents provided to you by the above 3 organizations? - Watch the Animated Video of WMC? - Go to the social media platform to use your voice? - Other (specify) - WORKSHOP/TRAINING SESSION - Name of the Organizing/Implementing partner? - How many workshops did you attend? - If more than one, name them - What type of programs did you attend? - What were the objectives? - Were you a participant or a resource person - Resource Person (selection) - What specialty ensured you be selected as a Resource Person? - What preparations did you do? - How much information were you given on the - Overall objective of the project - Overall objective of the workshop/training session - Basic background of the participants (to know the level of knowledge) - Your tasks - When was the session/s held? - How many participants - What was the level of their understanding - Was there a Q&A/Evaluation after the session - If Yes, what did they ask? - If No, what could encourage them to have asked? - Participant (Selection) - Were you selected or did you hear of this and volunteer your name? - Why were you selected? - Why other were selected? - Who selected you? - How were you informed of the selection? - What remunerations were given to help you to attend? - How did you leave your family/job to attend the workshop? - What was the type of program? - Lectures - Hands on participation - Group discussions/presentations - Other (specify) - Objectives - When you heard of these and initially attended, what did you expect? - What specific outcome do you think these organizers wanted to impart to yo? - Other subjects discussed - Method of Instruction (lecturer-centered lecture/student-centered/discussion/group work/presentations) - If you were divided into groups at any of the sessions, what was discussed in your group? - What were the findings/results of that discussion? - Most useful aspect of the workshop/s - Knowledge - Attitudes - Skills - Ways to convert ideas into practice - Challenges faced in implementing the ideas/knowledge gained - Ideas were too simple/not clear enough/hard to understand - Awareness program was not adequate - The workshop did not result in increasing support for my cause/aspirations - Other (specify) - What did they learn (in regard to the subject of women representation) - Empowered more - Increased my dedication to the cause. - Was there a follow-up session/discussion? - Do you need more information? (Specify) - IMPROVEMENTS - What improvements need to be made to increase the political participation of women in politics? - In your own words, what can be improved in terms of your dealings with (any of these) civil society organizations?

Focus Group Discussion Guidelines

FGD GUIDELINES FOR UN WOMEN - BASIC INFORMATION - How long has the project been in the discussion process before it was implemented in 2015? - Why was the decision taken to focus on Women in Politics? - How were the needs identified? - BACKGROUND - What were the broad areas of your focus under this project? - Why did you focus on these specific activities in this project? - DATA - How did you empirically understand the issue? - If there was no baseline data, how was success measured? - What are the empirical data provided by you to the Norwegian donor? - FOCUS - How important was SDGs in designing the Objectives/Goals? - How did national goals (Mahinda and Maithree mandates) in determining the areas of focus? - PARTNERS - How were the implementing partners chosen? - Advertisement - Other (specify) - What qualities/qualifications resulted in their selection? - What documentation did the partners provide you with? - Concept note - List of Activities - Other (specify) - How are the partners’ activities linked to the overall objective of the project? - Who were the targets of these projects? - How are they to ensure sustainability - Coordination - Were partners introduced to one another? - Were partners activities designed to prevent replication? - Were partners given a training to assist them in their projects? - How was their progress evaluated? - Activity-wise: start, mid-stage and completion - Impact - Other (specify) - How satisfied are you with the progress made by the partners?

Case Studies

CASE STUDY GUIDELINES FOR MEMBERS OF PROVINCIAL COUNCILS/GOVERNMENT AGENTS - BACKGROUND INFORMATION - Name, Age, Ethnicity - Civil Status - Unmarried - Married (If Married, name and profession of spouse) - Divorced (name and profession of the former spouse) - Widowed (name and profession of former spouse) - Family - Number of family members in Politics - Number of Dependents (Children below 18, unemployed/elderly family members) - Level of Education - Pre-O/Level - Passed O/Level - Passed A/Level - University Graduate - Professional Qualification (Lawyer, Architect, other) - Other (specify) - Professional Qualifications - Occupation - Employed - Primary (Agriculture) - Part time/Fulltime - Formal/Informal sector - Administrative position - Secondary (Industry) - Part time/Fulltime - Formal/Informal sector - Administrative position - Tertiary (Service Sector) - Part time/Fulltime - Formal/Informal sector - Politics (fulltime) - Unemployed - Fluency in Sinhala, Tamil and English Language (Reading, Writing and Speaking) - CHALLENGES FACED BY WOMEN AS A MEMBER OF A PROVINCIAL COUNCIL/GOVERNMENT AGENT 1. What was it like being a women working in your line of work? As a member of the Provincial Council or the GA? 2. How did you overcome stereotypes? 3.What was the most challenging part of working among people and getting their support? 4.How have the political parties assisted/hindered your projects? 5.Have female politicians been supportive or uncooperative? - TRAINING/ENHANCEMENT OF KNOWLEDGE - Were you given a training on Women’ Rights and information on laws and conventions on women? - Have you attended a session/workshop of the partners (AWAW/WMC/SFCG) - How would you assess its long-term and short term impact? - What are the themes/subjects about which you need training?

PERCEPTION ANALYSIS SURVEY: University Students

      - Why were your chosen for the workshop?

- Politically active

- Subject specialist

- Focus of my research

- interest

- Due to my gender

- Ethnic Group

- Don’t’ know

- What did you expect from it?

  - Knowledge

  - Tools

  - Don’t know

- What did you know of 				Pre-Workshop                Post Workshop

| - Sri Lankan Constitution |  |  |
| --- | --- | --- |
| - New [peace] Constitution being written |  |  |
| - Women’s place in society |  |  |
| - What rights to they have to enter into politics |  |  |
| - Why do women enter into politics |  |  |
| - What are should be the concern |  |  |
| - Women issues only |  |  |
| - Women and Children only |  |  |
| - Migrant female workers |  |  |
| - All aspects, irrespective of gender |  |  |

- Challenges faced by female politicians

  - Social-Cultural

  - Financial

  - Responsibilities

  - Lack of experience

  - Economic issues

  - Discrimination

- What were the real results of the workshops

  - None

  - Became an activist

  - Learnt a bit

  - Learnt a lot

| Date | Day |
| --- | --- |
| 25th November 2016 | Literature Survey |
| 26th November 2016 |  |
| 27th November 2016 |  |
| 28th November 2016 | Meeting with UN-Women Sri Lanka |
| 29th November 2016 | Desk research of partner reports |
| 30th November 2016 | Partner meeting with UN-Women representative |
| 1st December 2016 | Desk research of partner activity reports. Emailing, Telephoning |
| 2nd December 2016 |  |
| 3rd December 2016 | Training RAs |
| 4th December 2016 | Designing Guidelines & Writing Inception Report |
| 5th December 2016 |  |
| 6th December 2016 | KII, Mr. Abdul Maheed Nzamuddin |
| 7th December 2016 | Pilot Survey, Trincomalee/ Re-design guidelines |
| 8th December 2016 |  |
| 9th December 2016 | Submission of Inception Report |
| 10th December 2016 | Skype talk with Madhulika and Nishtha, UN WOMEN India |
| 11th December 2016 | Preparation of guidelines for FGDs for UN Women |
| 12th December 2016 |  |
| 13th December 2016 | - KII/FGDs of UN Women members |
|  | - Changes to KII Guidelines |
| 14th December 2016 | Field Research: Matara |
| 15th December 2016 |  |
| 16th December 2016 | - Telephone/Email requests for appointments to meet - Political leadership (women, party representatives) - Participants - Partners - Review of Field notes with RAs - Field Research Anuradhapura |
| 17th December 2016 | KII with Chandraika De Soysa Deputy Chairperson of the SLFP Women's fórum |
| 19th December 2016 | KII with - Participants from Matara - Trainer: Ms. Kariyawasam (AWAW Consultant/Trainer) - Nishantha Sri Warnasinghe from Hela Urumaya Field Research: Kurunegala |
| 20th December 2016 | Field Research: Kurunegala KII: WMC and Sumike Perera KII: Dr. S. Fernandopulle MP/Women’s Parliamentary Caucus |
| 21st December 2016 | Field Research: Nuwara Eliya |
| 22nd December 2016 | Field Research: Nuwara Eliya/ KII: A. Rajakaruna (via phone) |
| 23rd December 2016 | Field Research: Batticaloa |
| 24th December 2016 | Field Research: Trincomalee |
| 25th December 2016 | Field Research: Batticaloa Analyze data and Write Evaluation report |
| 26th December 2016 |  |
| 27th December 2016 |  |
| 28th December 2016 |  |
| 29th December 2016 | Submission of Evaluation |
| 30th December 2016 | Make changes and Presentation |

Annex III: References

Karunarathne, Waruni (2014) “Some Get Nominated for Lineage, Popularity, Money – Rosy Senanayake UNP MP” in Sunday Leader, 02.03.2014. http://www.thesundayleader.lk/2014/03/02/some-get-nominated-for-lineage-popularity-money-rosy-senanayake-unp-mp/

Longwe, Sara Hlupekile (2002) “Addressing Rural Gender Issues: a framework for leadership and mobilisation” http://www.sarpn.org/documents/d0000055/P60_Rural_Gender_Issues.pdf

March, Candida, Ines A. Smyth and Maitrayee Mukhopadhyay (1999) A Guide to Gender-Analysis Frameworks. Dorset: Oxfam.

n.a. (n.d.) “Women’s Empowerment Framework” in n.a. Gender Equality: implementing gender-focused development. http://pages.uoregon.edu/aweiss/Intl640/CEDPA_Week5_1.pdf

SDSN (2016) SDG Index & Dashboards: a global report. Paris: Sustainable Development Solutions Network.

Sri Lanka Parliament Secretariat (2015) The Constitution of the Democratic Socialist Republic of Sri Lanka. Colombo: Sri Lanka Parliament Secretariat. http://www.parliament.lk/files/pdf/constitution.pdf

UNDG (2011) Results-based Management Handbook: harmonizing RBM concepts and approaches for improved development results at country level. https://undg.org/wp-content/uploads/2015/01/UNDG-RBM-Handbook-2012.pdf

UNDP (2015) Human Development Report 2015. http://hdr.undp.org/en/countries/profiles/LKA#

UNDP (2015) Sustainable Development Goals. http://www.undp.org/content/undp/en/home/sustainable-development-goals.html

UNEG (2005) Norms for Evaluation in the UN System. New York: UNO.

UNGA (2005) Resolution Adopted by the General Assembly on 16 September 2005: 2005 World Summit Outcome A/RES/60/1. New York: UNO.

UNGA (2009) Resolution Adopted by the General Assembly on 18 December 2009: Fellow-up to the Fourth World Conference on Women and full implementation of the Beijing Declaration and Platform for Action and the outcome of the twenty-third special session of the General Assembly A/RES/64/141. New York: UNO.

UNO (2006) United Nations system-wide policy on gender equality and the empowerment of women: focusing on results and impact CEB/2006/2. New York: UNO.

UNO (2016) “Goal 5: Achieve gender equality and empower all women and girls” http://unstats.un.org/sdgs/files/metadata-compilation/Metadata-Goal-5.pdf

UNW (2012) Executive Board of the United Nations Entity for Gender Equality and the Empowerment of Women: evaluation policy of the United Nations Entity for Gender Equality and the Empowerment of Women UNW/2012/12. New York: UNO.

UNW (2016) UN-Women Annual Report 2015-2016. http://www2.unwomen.org/-/media/annual%20report/attachments/sections/library/un-women-annual-report-2015-2016-en.pdf?v=1&d=20160629T203016

UNWomen (2015) How to Manage Gender-Responsive Evaluation: evaluation handbook. http://www2.unwomen.org/~/media/headquarters/attachments/sections/library/publications/2015/unwomen-evaluationhandbook-web-final.pdf?v=1&d=20150423T183815

Annex IV: Stakeholders Analysis

Stakeholder Analysis (of a selected number of beneficiaries)

| Who | Place and Date | What (their role in this project) | Previous Experience | Why (what is gained by participating) | How (was this achieved) | What Next (What else is needed) |
| --- | --- | --- | --- | --- | --- | --- |
| S. Wijeratne | Kurunegala | Participant at workshop | Activist; Treasurer, Women’s Society; Coordinating Secretary, Preschool Voluntary Society. | Hoping for nomination so want to get as much knowledge as possible. Already had previous training but despite the training at Sri Sampath Centre, which lasted for 3 years and training at SLILG, she still wants to gain knowledge. | - Women’s Rights - Speaking articulately: a practical training on how to speak at an even. “First time I spoke on a stage. [WMC/SFCG] people helped highlight my strengths and weaknesses. Got confidence. No fear now. Ms. Anoma Rajakaruna was great.” - “I gained so much confidence that I gave a voice cut fir the Wayamba Radio service” after this. | - Some workshops are not challenging while others are. - Practical exercises are essential. |
| - Pushpakumari | Kurunegala | Participant at workshop | Canvassing for the party. Went as an observer (election monitoring) at election centers. | Needed basic data on how to help the villages. Needed confidence in speaking. | - Gained insights into all barriers faced by women – from getting nominations to facing violence pre and post elections. - Learnt how to get funds for rural/village development. Used this to get funds. - How to speak: “style, content, voice modulation, and structure of speeches”. | - Gone to many workshops and similar contents in some of them. |
| A. Maheshika | Kurunegala | Participant at workshop | Was nominated but not selected by the party. Only two women went from the District from the party however. | Despite training and experience, party officials don’t want us to be part of the nominations list. Wanted to find ways to | - Confidence and knowledge on women’s rights. | - While the content of the workshops were good, it is difficult to recall the names of the trainers. Would appreciate a short bio of the trainers. - Some of what is taught in workshops cannot be done in the real world. |
| W. Balasooriya | Kurunegala | Participant at workshop | In politics since 1998. Worked in the informal sector. Created a SLFP Women’s Society. Sameeka Perera helped. Participated in workshops since 2007. Went for ‘pocket meetings’ workshops where she attained the skill for 2-minute speeches. | Wanted to gain knowledge to become an independent candidate as her nomination was rejected by the SLFP. | Want knowledge in order to help her in her work with the village. Wanted to learn on - Good governance | Now more and more middle-class people are coming forward as candidates for elections. We are now somewhat left out. |

The in-depth analysis of the workshop targeting youth and estate workers is presented through a series of Charts (see pages 31 - 34). The Charts 1 to 4 focus on the views of youth from Jaffna University.  Moreover, Box 2 below also provide insights into the youth interviewed for this evaluation.

Box 2: Youth (Jaffna) Opinion of Activities

| Ms. K. Suganya Kaluthavalai Mr. M. Jegatheesh Kaluthavalai Mr. M. Tharaka Jaffna Mr. P. Kajendren Jaffna Mr. P. Vinorathan Kalmunai Ms. R. Naguleswari Jaffna Ms. S. Durga Dehiwala Ms. S. Theepa Jaffna Ms. T. Dorin Kowsalya Jaffna Ms. V. Sulakshan Sunnagam | Most of the participants don’t know on what basis they were selected to the workshop. All of them believe that since the workshop was targeted for university students they were selected. Participants are university students from various fields of study such as agriculture, science and arts. |
| --- | --- |

Chart 1: Aim of the Workshop for University Students, held in Jaffna

Chart 2: Content of the Workshop (Jaffna)

Chart 3: Knowledge of Barriers (Jaffna)

Chart 4: Reality of Women in Politics (Jaffna)

Charts 5 to 8 and Box 3 focus on the views of youth from the Eastern University.

Box 3: Youth (Batticaloa) Opinions of Activities

| - Ms. Janani Manoharan - Ms. Kokularaj Sanjeeva - Mr. A. C. Irunadhanaraj - Mr. T. Kuhan - Mr. K. Sanjeev - Ms. M. Pavithra - Ms. K. Sarmik - Mr. J. Vipulanan - Mr. K. Pradanath - Ms. K. Sumangala | All these students were from the Eastern University. They were interviewed together in a FGD. All of these students live in Batticaloa. |
| --- | --- |

Chart 5: Content of the Workshop (Batticaloa)

Chart 6: View of Participation of Women (Batticaloa)

Chart 7: Impact of Workshop (Batticaloa)

Chart 8: Reasons for Women in Batticaloa not being able to join politics

Finally, Charts 9 and 10 as well as Box 4, 5, and 6 examine the views of the Plantation sector.

Box 4: Plantation Workers who attended workshop

- Political Activist and Member, Provincial Council Hon. Sivaguru Saraswathi - Political Activist, Ms. Shashikala (Watawala) - Political Activist, Mr. L. Pushparaj (Kandapola) - Political Activist, Mr. S. Kumara (Hatton) - Political Activist and School teacher Mr. Udayakumaran (Thalawakele) - Political Activist, Mr. Shanmugarathnam (Pathana) - Political Activist, Mrs. Sujikala (Walapane)

Chart 9: Reasons why the workshop was a success (Nuwara Eliya)

Box 5: Knowledge Gained by Nuwara Eliya Participants

- Women and children’s rights - Why women should participate in politics - Constitutional reforms and the quota system - Attributes of a leader - Identification of issues among the plantation sector population - Ways of solving problems

Chart 10: Reality of why women don’t participate in politics (Nuwara Eliya)

Box 6: Impact of Knowledge on Women & Men (Nuwara Eliaya)

| The impact of the knowledge gained at workshop on women | The impact of the knowledge gained at workshop on men |
| --- | --- |
| - Knowledge: Retained ideas presented. - Practice: Gained confidence - Attitudes: Enhanced their political will | - Knowledge: Understood why women should engage in politics - Practice: Would “speak on behalf of women and their needs for political participation anywhere.” - Attitudes: Realized that women deserve respect |

The views of politicians on the project itself and the different activities is presented below.

Politicians

  - Hon. Chandrika De Soysa (SLFP) highlighted the fact that she and the SLFP understood the political hurdles/barriers women in politics had to overcome

    - “We have to do this because women do not have rights and do not enjoy these rights. The organizers in different districts ignore women. It through Women’s Wing we as women get our rights. This is a form of collective bargaining where we [can] get our rights in a peaceful way.”

“Parties don’t consider women’s expertise and ability … There are lots of young women leaders emerging from the villages, from different Unions … where they have proven to be excellent leaders. Not given a chance.”

Summary: No funding, no support from spouse, politically marginalized; too many responsibilities, child-care are barriers. Moreover, the pre and post-election violence hinders even the ardent female political activist.

  - According the Hon. Minister of Irrigation, Duminda Dissanayake, SLFP Secretary.

    - “Sri Lanka Freedom Party encourages and supports the enactment of legislation and their implementation.”

    - “[Women don’t enter Local or National level politics because] few women come forward. Politics is difficult for them and dirty. They participate in other ways effectively in election - Helping out in canvassing.”

  - The Hon. Dr. Fernandopulle commented that she was satisfied with the training she underwent when attending a workshop conducted by SFCG. She moreover noted how UN Women Sri Lanka was working tirelessly through different agencies.

It is apparent that the men and women politicians understand the issues. The AWAW even met the political representatives of the Communist party, the Hela Urumaya Party and the Democratic National Party. Whether they took up the cause for quotas from these partners is not clearly evident. However, it is evident that the partners’ activism at the Parliamentary Representation Committee on Constitutional Reform was influenced. This is evident especially in the report submitted by SFCG. Some politicians noted that while it is good to have equality, there should not be a quota. Moreover, as one noted,

“We are culturally different from Western nations. It is not equally we need for women but their due place (nisi thana) such as mother and wife. This role is vital and they are placed in an exalted position in Sri Lanka … In Sri Lanka women enjoy something more than equality.”

Another politician noted that women in Sri Lanka have equal opportunities.

“They excel at interviews, in Law College entrance exams, universities. They don’t lack anything.”

Hon. Sri Waranasinghe commented that

“women do face a lot of obstacles, not from the family or neighbors. There is a lot of tension from within the party as men and women compete to get nominations. Sometimes insults other times it is political thuggery”.

Another issue seen by a number of participants of workshops was why some focus on women’s issues only.

Hon. Chandrika De Soysa (SLFP) highlighted the fact that she and the SLFP understood the political hurdles/barriers women in politics had to overcome

    - “We have to do this because women do not have rights and do not enjoy these rights. The organizers in different districts ignore women. It through Women’s Wing we as women get our rights. This is a form of collective bargaining where we [can] get our rights in a peaceful way.”

“Parties don’t consider women’s expertise and ability … There are lots of young women leaders emerging from the villages, from different Unions … where they have proven to be excellent leaders. Not given a chance.”

Summary: No funding, no support from spouse, politically marginalized; too many responsibilities, child-care are barriers. Moreover, the pre and post-election violence hinders even the ardent female political activist.

According the Hon. Minister of Irrigation, Duminda Dissanayake, SLFP Secretary.

    - “Sri Lanka Freedom Party encourages and supports the enactment of legislation and their implementation.”

    - “[Women don’t enter Local or National level politics because] few women come forward. Politics is difficult for them and dirty. They participate in other ways effectively in election - Helping out in canvassing.”

The Hon. Dr. Fernandopulle commented that she was satisfied with the training she underwent when attending a workshop conducted by SFCG. She moreover noted how UN Women Sri Lanka was working tirelessly through different agencies.

It is apparent that the men and women politicians understand the issues. The AWAW even met the political representatives of the Communist party, the Hela Urumaya Party and the Democratic National Party. Whether they took up the cause for quotas from these partners is not clearly evident. However, it is evident that the partners’ activism at the Parliamentary Representation Committee on Constitutional Reform was influenced. This is evident especially in the report submitted by SFCG. Some politicians noted that while it is good to have equality, there should not be a quota. Moreover, as one noted,

“We are culturally different from Western nations. It is not equally we need for women but their due place (nisi thana) such as mother and wife. This role is vital and they are placed in an exalted position in Sri Lanka … In Sri Lanka women enjoy something more than equality.”

Another politician noted that women in Sri Lanka have equal opportunities.

“They excel at interviews, in Law College entrance exams, universities. They don’t lack anything.”

Hon. Sri Waranasinghe commented that

“women do face a lot of obstacles, not from the family or neighbors. There is a lot of tension from within the party as men and women compete to get nominations. Sometimes insults other times it is political thuggery”.

Another issue seen by a number of participants of workshops was why some focus on women’s issues only.

    - As Hon. Rosy Seneanayake noted in an interview done in 2014,

I have noticed that many young women who have received nominations this time have a popular face in their respective fields. Some think that they have a popular face and now they need a power face. They need to understand politics is not a glamorous industry like a piece of colourful art. That is a misconception. It is a 24 hour, 7 days a week, full-time job with lot of hard work where you undergo many difficulties and face barriers. In the Sri Lankan context, politics is a risky job with the prevailing system of assassinations, gun culture and with enormous money engaged. This is a tough game.

Most of these women nominees have not at least participated in a single protest or have gone house-to-house to meet people. Besides, when popular figures who are interested in the power face with no dedication contest election, they tend to get higher numbers of votes at the election and top the list wiping out most senior worthy members – which is a shame. Most of them are not sincere to the party, as they have not embraced party ideologies or principals and therefore tend to cross over. (2014).

The idea that women are often seen as pawns of their family is wrong, according to Hon. Rosy Senanayake, who commented that

Not every woman has played the sympathy card to win votes to get into politics. However, those women who have come into politics after the death of their fathers, brothers or husbands may have been benefited by the voter-base created by those deceased.

They may reap the benefit of somebody else’s hard work for the first time but in order to sustain their position, they need to work for the people. Otherwise, they will not get re-elected the next time.

I am happy to say that there are women such as Thalatha Athukorala, Chandrani Bandara, Pavithra Wanniarachchi, Sumedha Jayasena, etc. who had come into politics with the support of the voter-base of their deceased ones and have managed to get re-elected and some for the third or fourth time. Amara Piyaseeli stayed in politics since 1977 until she decided to retire from politics. By being elected over and over again, these women have proven that they are sincerely committed and dedicated to serve the people and are capable of sustaining their voter-base – and worthy of being nominated. (Rosy Senanayake 2014).

Moreover, commenting on Constitutional Changes, Hon. Dr. Fernandopulle,

“The Committee has been progressive and has included most of the recommendations suggested by women’s groups.”

Annex V:

Output and Outcome Analysis based on Inputs

| Outcomes | Output | Internal to the portfolio |  |  |  | External to the portfolio |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Facilitate (f) |  | Hinder (h) |  | Facilitate |  | Hinder |  |
|  |  | At Proposal and Design | At Implementation |  | When Providing Resources | At Proposal and Design | During Implementation |  | When Providing Resources |
| 1. | 1.1 | f: Proposal is not strict in Activities; f: Achievable Objectives h: no baseline survey h: no performance criteria for assessment h: UNW/I designed project; found partners. | f: Flexibility on methods used by partners h: Partner capabilities & resources not similar (AWAW vs. WMC vs. SFCG) h: Delay in beginning the project. |  | f: Norwegian grant f: Sum provided for activities h: funds allocated for each activity not justified; h: Delay in fund allocation. | f: At Design stage, SL was to have Local Government elections so women capacity development was vital. | h. Change in government, resulting in postponement of local/ provincial elections. |  | h. A comment by partners was that there was a time laps in getting the funding. h. UNW/SL noted that not all invoices were submitted according to the exacting standards of the UN despite numerous discussions |
|  | 1.2 |  |  |  |  | f: Media focus did not change from design stage to implementation stage. Possible to then examine ‘impact’ in 2016. |  |  |  |
| 2. | 2.1 |  |  |  |  | f: Flexibility of proposed activities allowed for major changes of 2015. h. Elected women remained low, even in 2015 elections. Strong voices (Rosy Senanayake, etc.) ousted |  |  |  |
|  | 2.2 |  |  |  |  | h: Idea existed but parliamentarians did not champion it. | f: Idea for quota championed by PM Wickramasinghe |  |  |

Program Analysis

| Partner | Activities | Outcomes | Output | Relevance | Effectiveness | Efficiency | Sustainability | Impact* | Gender Equality & Human Rights |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SFCG | 1.4: Building networks for Women Members of Parliament at Provincial and Local Governmental level. | Three meetings held on 6th, 22nd and 28th of September, to raise awareness among local women activists of the Amended LG Act. | Approx. 80 women leaders and Caucus members attended. Preparation of proposals from a gender perspective to be incorporated into the Constitution. | √ | √ | √ | X∆ * | X∆* | √ |
|  | 2.6: Conduct a three-day training workshop for 25-30 journalists in English medium on ‘Gender Sensitive and Responsive Journalism’ | Professional Training Course on Radio Drama for Social Advocacy (18-20,Sept. 2015). 3 day training program to develop the skills and knowledge of radio journalists to develop the capacities of these journalists to ensure that they can produce radio programs that are conflict sensitive while at the same time being attractive and interesting to the local audience. | 14 participated of whom 4 were women. Participants gained knowledge in writing scripts for a radio drama. Participants created characters, story arch, and storyline and wrote a script for a radio drama based on gender based violence (GBV). | √ | X∆* | √ | X* | X∆ * | √ |
|  | 2.1.1: Conduct one workshop identifying themes/messages/issues for advocacy material on women’s political and democratic rights/women in decision-making and ‘Vote for Women’ with partner organizations | The Vote for Women media campaign launch took place from 3:30 – 5.00 p.m. on August 15, 2015. Joint initiative by SFCG, WMC) and AWAW | To change voter attitudes towards female politicians, encourage more women to seek nominations in the future, and enhance political discourse and culture in Sri Lanka by improving women’s representation and participation in parliament. Material developed to promote women participation ie social media campaign, dialogue-free animated spots offered free of charge to TV stations, social media forums and female candidates political affiliation, encouraging the public to vote for capable female representation in politics. Theme song “Chandeta Aruthak,” broadcast on radio and on television, accompanying the animated spot. Distributed free of charge to any female politician. Introduction of the poster calling Sri Lankans to cast their vote for a woman. | √ | √ | √ | X * ∆ | X ∆* | √ |
|  | 2.4: Launching and maintaining a social media campaign designed in activity 2.1 (above) |  | Regardless of political affiliation, encouraging the public to vote for capable female representation in politics, bi-lingual theme song, and posters | √ | √ | √ | X∆* | X∆ * | √ |
|  | 2.5: Conduct two training programs for 25 Sinhala/Tamil radio journalists on ‘Common Ground approach’ and script writing. Those who followed this would then be invited to - Half-day coaching session on ‘women empowerment’ - Developing a drama script that focuses on ‘Women’s empowerment and gender’ - One day script finalizing workshop | Training programmer held for journalists from Tamil, Sinhala and Muslim communities. The participants represented media organizations such as Vasantham FM ,Ruhunu Sevaya, Kathurata Sevaya, and Sri Lanka broadcasting cooperation. This was the second training programme conducted for them. | Objectives of the training were to; Sensitize journalists on women’s participation and representation Encourage them to portray women in a more positive light when they are writing various scripts to bring gender perspective into the writing of the participants | √ | √ | √ | X* | X* | √ |
|  | 2.6: Conduct a three-day training workshop for 25-30 journalists in English medium on ‘Gender Sensitive and Responsive Journalism’ |  | Professional Training Course on Radio Drama for Social Advocacy (18-20,Sept. 2015). A 3 day training program to develop the skills and knowledge of radio journalists to develop the capacities of these journalists to ensure that they can produce radio programs that are conflict sensitive while at the same time being attractive and interesting to the local audience. | √ | √ | √ | X*∆ | X*∆ | √ |
| WOMEN AND MEDIA COLLECTIVE | 1.1.2: Conduct one national media briefing to advocate for inclusion of causes related to increased women’s representation in the 20th Constitutional Amendment | Discussions held with women’s rights activists (WRAs) and Women’s groups (WGs ) in appox. 20 Districts on the new constitution making process. | Press briefing (08 September 2015) to demand for a 30% increase in women’s political representation at Local Government. 15 submissions made to PRC [Jan-Feb.2016] | √ | √ | √ | X∆ * | X∆ * | √ |
|  | 1.2.2: Conduct a one-day consultation with 15 provincial council members (including women) from a select Provincial Council on reviewing gender responsiveness of one Provincial Council’s Action Plan. | Organized a round of discussion on the new constitution making process. Discussions conducted in Batticaloa, Kurunegala and Colombo with the participation of women activists, members of CSOs, women affiliated to political parties, Trade unions and Women’s Organizations. | Topics discussed: Principals of a Constitution; Current process of constitution making; what should be included, esp. with regard to protecting women’s rights. | √ | √ | X | X* | X* | √ |
|  | 1.5.1: Conduct a study (online and on print) on gender-biased statements made in Parliament during the last decade to advocate for gender-equitable political environment. | http://womenandmedia.org/wp-content/uploads/2016/02/Hansard-Research-Study.pdf | ## Parliament’s Representation of Women: A Selective Review of Sri Lanka’s Hansards from 2005-2014, launched on 30th January 2016. | √ | √ | X∆ | X∆ | X*∆ | √ |
|  | 1.5.2: Publish the study on gender-biased Parliament statements in three languages |  |  | √ | √ | X∆ | X∆ | X*∆ | √ |
|  | 2.2.1: Conduct one workshop on identifying themes/messages/issues for advocacy material on women’s political and democratic rights/women in decision-making and ‘Vote for Women’ with partner organizations and relevant experts. | Facilitated a discussion on the Local Authorities Elections Amendment Act of 2012 [December 21, 2015]. Focused on increasing representation of women under the mixed electoral system. | ## Vote for Women Campaign Launch 12 Aug, 2015 online. http://womenandmedia.org/vote-for-women-campaign-launch/ | √ | √ | √ | √ | √ ∆ | √ |
|  |  |  | http://womenandmedia.org/category/publications/wmc-publications/ [In Sinhala only] |  |  |  |  |  |  |
|  | : Two forums with 15 male Parliamentarians and representatives of the WPC on raising awareness on gender-responsive policies. | National level Consultation led by WMC with contributions from 45 WR advocates to build a consensus on the electoral systems and women’s political participation. | Submissions published on WMC web, Facebook and Twitter https://sway.com/DtcdC5T40Cy30B5V | √ | √ | √ | √ | X∆ | √ |
| AWAW | 1.1.0: To conduct 1 advocacy meeting each with eight political parties in Colombo to advocate for a 33% quota for women in elected office | Advocacy Campaign - Political parties: Meeting with representatives of Political Parties | Between 17 - 26 June 2015, met representatives from - National Labor Front - Democratic party; - Communist Party; - Jathika Hela Urumaya - All Ceylon Muslim Congress. Also met - Hon. Prime Minister Ranil Wickramasinghe - Election Commissioner Wrote to - Mr. Susil Premajayantha, - Anura Priyadarshana Yapa of UPFA and SLFP, - Mr. Anura Kumara Dissanayake of the JVP. | √ | √ | √ | X* | X* | √ |
|  | 1.4.0: Conduct two two-day workshops for 50 members of Parliament and Trade Union members on gender responsive policy design and implementation | Prepared ‘Action plan’ | Trade union members created an action plan for a social media page (Facebook) to highlight issues in the plantation sector, and the page was named “Malayaga kozundu” means “up country tea leaf” Promoting women’s political participation – a two day residential workshop [28-29 Nov.2015] on Gender responsive policy design and implementation. 24 participants (politicians, lawyers, TU members). Session 2 -‘Making Rights a Reality’. Sector b) a draft action plans on “Women peace, security and development” in Central and Eastern initially and then in the rest of the 7 provinces. 24 participants (politicians, lawyers, TU members). Session 2 -‘Making Rights a Reality’. Sector b) a draft action plans on “Women peace, security and development” in Central and Eastern initially and then in the rest of the 7 provinces. | √ | √ | √ | √ | √ | √ |
|  | 2.2.1: Conduct 4 one-day meetings with 100 youth from Universities of Peradeniya, Batticoloa (i.e. Eastern), Jaffna, and Colombo. | Between 1st August to 31st December 2015, conducted workshops for 76 undergraduates from 4 Universities on the importance of electing women to political bodies. Themes discussed: Women’s political history in Sri Lanka, current status and international experience. | - Session 1- Lecture on CEDAW and Fundamental Rights, Basic Principles and Provisions, Principal areas of concern in Sri Lanka - Group work - Challenges and opportunities for W. to be in politics and benefits to society, Advocacy on women’s participations – quota systems, Themes for advocacy and Discussions on how to build up the campaign. | √ | √ | √ | X* | X* | √ |
|  | 2.1.1: Conduct one workshop on identifying themes/messages/issues for advocacy material on women’s political and democratic rights/women in decision-making and ‘vote for women’ with partner organizations and relevant experts | 2 Day Workshop on the National machinery on women – independent Commission on Women; Discriminatory laws; Violence against Women; Lack of Political participation; Women in the informal sector; Gender stereotyping; Health – teen pregnancies and unsafe abortions; Women affected by conflict; Migrant women. | Recommendations. Group Work Objective: to ensure that potential members of trade unions and politicians develop clear perspectives on socio-economic, political and cultural issues. To ensure that they are Guided by the overall policy framework of CEDAW Recommendations and methods to resolve the issues Session 02 :Making Rights a Reality. Lecture and Group work. Presentations and discussions on ‘What media should do to protect women’s human rights; What parliament should do to protect women’s basic human rights? What court should do to protect women’s Rights? Discussion about the constitutional submission to the constitutional committee, Day 2 Session 3 Good Governance and Democracy- components of Good Governance. Session 04 Gender responsive Budget preparation Group Work Discussions and submission of Action Plans: Action plan 01: Drafted by members of trade unions on creating a Facebook page to discuss on the issues faced by plantation sector women Action Plan 02: Drafted by politicians, members of trade unions and lawyers. They drafted a provincial action plan for women’s peace and security and development | X | √ | √ | X∆ | X* | X* |
|  | 2.2.2.: Distribution of 10,000 leaflets and posters to reach 10,000 members of the public all-island to advocate for the ‘vote for women’ by University students | Half day Workshops for University Students to distribute the Leaflets and Posters | Recommendations: To prepare a road map where civil societies contributions can be obtain to increase the participation at all levels of governance | √ | √ | √ | X | X | √ |
|  | : Six one day seminars to establish regional women’s caucus with regular networking and knowledge sharing | Networking workshop to build women politician’s caucuses [4 workshops for 77 persons on 20.04.2016 ; 24.05.2016; 31.05.2016 25.06.2016. Covered most of the Districts].Objective is to build regional women politician’s caucuses for former and present provincial and local government women political members. | Outcomes Identified the importance of Women Caucuses, Challenges faced and Solutions. Appointed a nation level coordinator; established regional women’s caucuses; Enhanced women’s political participation; Appointed Regional coordinators to every caucus to coordinate the network work; Appoint two advisors / consultants. Identified women’s networking issues. | √ | √ | √ | √ | X* | √ |

*Difficult/Impossible to measure impact with current data and/or due to it being too short a period since Activity.

∆Whether the target audience truly influences

The focus of the Activity is either too broad or not in keeping with the TOR of the project.

Annex VI: Summary of Findings

Overall Analysis of the Project

Major issues that need to be tackled in future activities

- Voter Education

Voter education to the general public should be done hand-in-hand with women’s activism. This is clearly not part of this project. It is possible to train women who are politically active to go back to their respective Districts to educated the populous. This has to include education on the Constitution and the need for Constitutional reform. As Hon. Dr. Fernandopulle noted,

“In the Constitution, Article 12 (4) women have been lumped with disabled people and children. Because of that, that it is established that special laws should be enacted by them. Women should not be treated as a vulnerable group”

- Internal democracy in political parties

As long as there is no transparency and accountability in the nomination process in the political parties, it is unlikely that a quota lone will ensure the best female candidate is selected. There is a lack of support by the party official. This is noted both by the elite in the party and by those who want to get into mainstream politics.

For example, Dr. Sudharhani Fernandopulle, Chairperson of the Parliamentary Women’s Caucus – who was interviewed on the …. noted that

Party structure from top to bottom are not open to women leaders. This structure has to change if we are to give effect to democratic ideals. Therefore we have to attract able women to support the party … Women’s Wing have not promoted and protected women’s rights as expected of them. Instead, they have been utilized in canvassing and gaining more votes for the parties.

- Capturing Motivation of Women

It is possible to capture motivation by women who wish to or are part of the politics of Sri Lanka. It is difficult to find out, as one politician noted, whether “Women in the country are not ready and women in the parties still not interested.”