Meta-Analysis

of Six Women Peace and Security Programme Evaluations in Nepal UN Women Country Office

February 2018

Kate Butcher

TABLE OF CONTENTS

EXECUTIVE SUMMARY	iii

INTRODUCTION	1

Background	1

Purpose of the Meta-Analysis	2

Methodology	2

Limitations	4

EVALUATION FINDINGS AND CONCLUSIONS ON OECD/DAC CRITERIA	4

Relevance	5

Effectiveness	6

Efficiency	9

Sustainability	10

Impact	11

Gender equality	12

LESSONS LEARNED, GOOD PRACTICES & PROMISING APPROACHES	13

EVALUATION FINDINGS ON OPERATIONAL PRINCIPLES AND APPROACHES	14

Partnerships	14

Knowledge management	15

Capacity Development	15

Replication and “Up-scaling”	16

Results Based Management	16

CONCLUSION	17

RECOMMENDATIONS/WAY FORWARD	18

REFERENCES	20

ANNEX 1. Terms of Reference	21

ANNEX 2. Detailed scores of each Evaluation report against OECD/DAC sub criteria	33

ANNEX 3. Analytical framework	34

LIST OF TABLES

Table 1:  Aggregate scores of each evaluation repor against criteria…10

LIST OF ACRONYMS

BASE			Backward Society Education

CAW			Conflict Affected Women

CDS			Creative Development Society

CEDAW 		Convention on the Elimination of All Forms of Discrimination Against

Women

CSO			Civil Society Organization

CSP			Community Security Plan

DADO			District Agriculture Development Office

DCC			District Co-ordination Committee

DDC			District Development Committee

DHS			Dalit Help Society

DLSO			District Livestock Service Office

DWC			Department of Women and Children

EPST			Ensuring Participatory and Secure Transition

FE			Final Evaluation

GATE			Global Accountability and Tracking of Evaluations

GERAAS		Global Evaluation Reports, Assessments and Analysis System

GPI-CT		Localizing the Women Peace and Security Agenda in Central Terai

GRB			Gender Responsive Budgeting

GRRSP		Gender Responsive Recovery for Sustainable Peace

HQ			Headquarters

IEO			Independent Evaluation Office

IPWA			Inter-Party Women Alliance

MoWCSW		Ministry of Women, Children and Social Welfare

MTR			Mid-term Review

NAP			National Action Plan

NCO			Nepal Country Office

NGO			Non-Governmental Organization

OECD/DAC	Organisation for Economic Co-operation and Development Assistance Committee

RBM			Results Based Management

SIWPSAN	Strengthening Implementation of the Women Peace and Security Agenda in Nepal

ToC			Theory of Change

ToT			Training of Trainers

UNDAF		United Nations Development Assistance Framework

UNSCR		United Nations Security Council Resolution

VAW			Violence against Women

VDC			Village Development Committee

WCO			Women and Children Office

WPS			Women Peace and Security

# EXECUTIVE SUMMARY

UN Women Nepal Country Office (NCO) commissioned a meta-analysis of six Women’s Peace and Security (WPS) programme evaluations which took place between 2014-17, within the period of the UN Women Nepal Strategic Note. The Terms of Reference state the purpose of the analysis is to gather lessons learned across the programmes both to inform the Nepal Country Office ongoing strategic planning process for 2018-22, and to provide partners with greater insight into the effectiveness of UN Women’s work. The analysis took place between 31st October 2017 and 3th January 20187.

The six evaluation reports were commissioned by the UN Women Independent Evaluation Office (IEO) using the Global Evaluation Report Assessment and Analysis System (GERAAS). Two quality assessments were conducted by UN Women IEO itself while the remaining four were assessed by independent teams. All the reports were rated satisfactory or above and posted on the GATE system

The six evaluations are:

- Mid-Term Evaluation (Jul 2015) Strengthening Implementation of the Women, Peace and Security Agenda in Nepal SIWPSAN. (Jun 2012-Dec 2016)

- Final Evaluation (Dec 2016) Strengthening Implementation of the Women, Peace and Security Agenda in Nepal (Jun 2012-Dec 2016)

- Final Evaluation Ensuring Participatory and Secure Transition (2013-2015)

- Final Evaluation of Localizing Women Peace and security agenda in Central Terai Districts of Nepal Project (Jan 2015-Oct 2016)

- Mid-Term (Dec 2014) Evaluation of Gender Responsive Recovery for Sustainable Peace (GRRSP)

- Final (2015) Evaluation of Gender Responsive Recovery for Sustainable Peace (GRRSP) Oct 2012-Dec 2015.

The analysis employed a three-step approach; i) desk review, harvesting 311 key statements clustered around Organisation for Economic Co-operation and Development/ Development Assistance Committee (OECD/DAC) criteria of relevance, effectiveness, efficiency, sustainability, impact including gender equality and women’s empowerment ii) aggregation and mapping of data onto a colour coded matrix according to pre agreed sub criteria attached to each main criterion to enable a visual overview of patterns occurring; iii) analysis and presentation of the findings.

Overall the analysis found that the portfolio had performed well over three key criteria relevance, effectiveness and sustainability. Efficiency was found to require greater attention and impact, too, scored fairly low scores but this is largely the result of relatively short time frames.

Efforts have been highly relevant showing clear alignment with national and international policies and commitments and responding to the need of beneficiaries. Geographic site selection has been appropriate and further consideration is now needed to ensure that beneficiary selection correctly reflects the social context.

UN Women has played to its comparative advantage in Nepal and can demonstrate through its projects that it has made a difference to beneficiaries’ lives at an individual and collective level.  Its effectiveness is further demonstrated by the fact that the Women Peace and Security agenda is becoming institutionalized in collaborating Districts and more women are participating in and leading peacebuilding initiatives.  The majority of objectives have been achieved and some changes in programming and policy have been noted, for example the development of guidelines on rolling out the National Action Plan (NAP) on United Nations Security Council Resolutions (UNSCR) 1325 and 1820 and for undertaking Gender Audits.

Efficiencies can be improved; while activities were largely found to be cost and resource efficient, co-ordination and communication require more attention particularly where multiple partners are involved. Findings demonstrate that it is important to distinguish between technical assistance and management functions where UN Women places staff at District level.

Sustainability of interventions was perceived to be moderate although attention is drawn to the relatively short time frame of most projects. Nevertheless, promising examples have already emerged, where non-participating Village Development Committees (VDCs) have been motivated to adopt approaches to WPS implementation because of positive feedback from project participants elsewhere. Some examples of enduring impact have been provided, particularly in terms of improved community cohesion and non-violent conflict resolution based on community dialogue.

Key lessons learned on UN Women organizational drivers.

All interventions were implemented in partnerships either with other UN agencies or Civil Society Organisations (CSO) and all worked through government systems thus maximising ownership and sustainability.  A central plank of all interventions is capacity development and where this is delivered through training sessions and workshops attention is drawn to the need for regular follow-up and mentoring to ensure that knowledge and skills are retained.  Knowledge management was found to be an implicit aspect of work and would benefit from higher visibility given that valuable lessons are being learned from this work. Results Based Management is not explicitly addressed in the evaluation reports although attention is paid to the relative value of Theories of Change (ToC) governing projects; these demonstrate that more attention is needed to ensure that ToCs are, i) regularly updated to remain relevant as contexts change, ii) where there are ToC attached to different outcomes in a project they should be consolidated to ensure that linkages across outcomes are maximised and iii) accompanied by risk management strategies.

Recommendations

For NCO and the Strategic Plan

Strengthen UNW intersectional responses to WPS by:

- Ensuring conflict affected survivors are integrated as one of the target groups throughout UN Women Nepal’s thematic area. This will further support their recovery efforts.

- Investing in translating all relevant tools on addressing sexual and gender based violence and its prevention and response into local languages to ensure local engagement and sustainability. Translations and long-term capacity building should be prioritized over the repetitive production of new tools, strategies, guidelines and advocacy campaigns.

- Supporting the establishment of an independent monitoring mechanism run by women’s civil society groups and women’s human rights defenders in future peacebuilding programs to track implementation of the national action plan implementation.

- Further refining selection protocols for projects which ensures identification of appropriate beneficiaries who are representative of their communities.

Strengthen approaches to gender mainstreaming by:

  - Commit to gender parity among project staff (that is 50 per cent women) and to the training of all staff in gender equality programming and the protection of women’s human rights, identifying and responding to the early warning specially with regards to emerging conflict and tension.

  - Continue advocating for local level allocation of funds for GEWE as part of National Level Gender Responsive Budget allocation. The budget should be allocated to address women’s leadership at all levels, addressing violence against women, addressing peace, security and humanitarian efforts, increasing gender responsive local planning and implementation.

  - Ensuring that UN Women is a member of all relevant inter-agency forums on peace, security and humanitarian response, including the relevant Advisory Group on peace and security, to ensure a gender perspective is mainstreamed throughout the UN’s response in conflict, disaster, early warning and emergencies.

  - Consider either applying only for funding with longer than 2-year duration or lobbying donors to extend the duration and funding of projects which address WPS

Strengthen coordination of WPS efforts by:

  - Strengthening existing management committees for gender equality in project locations to address lack of intra-ministerial, coordination, Federal, Provincial, Local Government coordination, timely budget release, effective documentation, reporting and institutional memory, ownership among local authorities.

  - Considering expanding reference to all eight WPS resolutions along with other international instrument in UN Women work related to participation, protection, prevention and peacebuilding.

For Project Implementers

- Engage beneficiaries in all stages of project cycle.

  - Where projects are jointly implemented, ensure clarity of roles, and encourage joint planning and monitoring of projects to enhance ownership and increase efficiency.

  - Ensure systems and procedures are commonly understood by all stakeholders.

  - Ensure consolidated Theories of Change are developed for each project accompanied by risk management and contingency strategies.

  - To enhance the sustainability of efforts, UN Women should ensure its projects focus on enhancing the capacity of existing mechanisms and networks, both across government and Civil Society, rather than initiating new ones.

  - Consider greater attention to engaging men as advocates of gender equality.

  - Continue to build on comprehensive packages which address economic recovery and psycho social support.

# INTRODUCTION

UN Women Nepal Country Office (NCO) commissioned a meta-analysis of six Women’s Peace and Security (WPS) programme evaluations that were conducted between 2014 and 2017, within the period of the UN Women Nepal Strategic Note,  and which were rated as ‘satisfactory’ or above by the UN Women Independent Evaluation Office (IEO) using the Global Evaluation Report Assessment and Analysis System (GERAAS). Two quality assessments were completed by UN Women’s IEO while the remaining four were assessed by independent teams.

The purpose of the analysis is to gather lessons learned across the programmes, both to inform the ongoing strategic planning process for 2018-2022 and to provide partners with insights into the effectiveness of Un Women’s work. The analysis was conducted between October and December 2017.

## Background

Grounded in the vision of equality enshrined in the Charter of the United Nations, UN Women works for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security. Placing women’s rights at the centre of all its efforts, UN Women leads and coordinates United Nations System efforts to ensure that commitments on gender equality and gender mainstreaming translate into action throughout the world. It also provides strong and coherent leadership in support of national priorities and efforts, building effective partnerships with government, civil society and other relevant actors.

In Nepal, UN Women focuses on strengthening women’s voice, agency and leadership across sectors to advance women’s rights, provide space for women’s meaningful participation and to demonstrate tangible differences in their lives. The agency’s programme adopts a holistic and integrated approach across UN Women’s five thematic priorities. It is guided by Nepal’s stated priorities (including those from the Three-Year Plan 2016-2019) and its commitments to relevant normative frameworks, the country’s United Nations Development Assistance Framework (UNDAF) 2013-2017, the CEDAW Concluding Observations (2011) and UN Women’s Corporate Strategic Plan 2014-2017. The programme promotes national ownership, capacity development and institutionalization, inclusiveness, coordination and partnerships, and knowledge generation and management, and seeks to prioritize engagement with and support to key duty bearers who are responsible for advancing women’s human rights and with rights holders so they can exercise voice and agency. UN Women is in process of developing UN Women’s Corporate Strategic Plan 2018-2021.

Nepal witnessed a decade-long armed conflict (1996-2006) between the Government of Nepal (GoN) and the Communist Party of Nepal (CPN-Maoist) which concluded with the

signing of the Comprehensive Peace Agreement (CPA) between an alliance of the seven political parties and the CPN (Maoist). Although women were not included in the development of the 2006 peace agreement, the transition to secular democratic governance witnessed a push from women's groups for equal participation and protection in the constitution during the post conflict period. It was in the post-conflict period of transformation, recovery and reconstruction, that Nepal launched its National Action Plan (NAP) on the implementation of the UNSCRs 1325 and 1820, internationally to coincide with the 55th Commission on the Status of Women in New York, and nationally on 17 February 2011 in Kathmandu. The NAP was contextualized within a broader set of government policies and demonstrated the political commitment and high priority of the Government of Nepal to issues related to women, peace and security in the post-conflict context of Nepal.

Nepal was the first country in South Asia and second in Asia to adopt a 5-year NAP.

This meta-analysis considered six decentralized evaluation reports. All reports were rated as ‘satisfactory’ or above by the UN Women IEO using GERAAS and posted on the GATE system.

The six evaluations are:

| Name of Project | Implementation period | Budget (USD) | Type and date of Evaluation / |
| --- | --- | --- | --- |
| Strengthening Implementation of the Women, Peace and Security Agenda in Nepal SIWPSAN | Jun 2012-Dec 2016 | 2,047,428.00 | Mid-Term Evaluation 15 June 2015 |
| Strengthening Implementation of the Women, Peace and Security Agenda in Nepal | Jun 2012-Dec 2016 | 1,973,574.00 | Final Evaluation December 2016 |
| Ensuring Participatory and Secure Transition | 2013-2015 | 625,000.00 | Final Evaluation 30 November 2015 |
| Localizing Women Peace and security agenda in Central Terai Districts of Nepal Project | Jan 2015-Oct 2016 | 576,602.00 | Final Evaluation October 2016 |
| Gender Responsive Recovery for Sustainable Peace (GRRSP) | Oct 2012-Dec 2015 | 898,800.00 | Mid-Term Evaluation December 2014 |
| Gender Responsive Recovery for Sustainable Peace (GRRSP) | Oct 2012-Dec 2015 | 898,000.00 | Final Evaluation May 2015 |

## Purpose of the Meta-Analysis

The primary purpose of the meta-analysis is to capture key insights into how the NCO’s WPS interventions achieved their goals and outcomes together with related lessons learned. The analysis synthesises key findings, conclusions and recommendations from six evaluation reports that meet UN Women quality requirements. The full Terms of Reference can be found at Annex 1.

## Methodology

The analysis consisted of desk review of the evaluation reports, initial analysis and preparation of a draft report presented (virtually) at a validation workshop for major stakeholders and members of the Reference Group. The Reference Group, included members of the Ministry of Peace and Reconstruction, National Planning Commission, 1325 Action group, Conflict Victims Common Platform, Development Partners, UN Agencies, representatives from the relevant department of Kathmandu University and UN Women.

The report considers the five OECD/DAC evaluation criteria of relevance, effectiveness, efficiency, sustainability, and impact.  Gender equality was also considered in order to determine lessons learned with regard to gender transformative work.

The analysis is grounded in the UN Women principles and approaches:

- national ownership

- inclusion

- advocacy

- partnership

- knowledge management

- capacity development

- replication and ‘up-scaling’

- results based management (RBM)

A three-step approach was employed as follows:

- Systematic, in-depth desk review of each report

Each report was reviewed and statements relevant to each of the OECD/DAC criteria harvested from the sections on findings, conclusions, recommendations and lessons learned. A total of 311 such statements were harvested.

- Data Mapping

A matrix (Annex 2) was developed summarising the performance of each evaluation report against the five OECD/DAC criteria, which are further broken down into sub-criteria based on those used in the Meta-Analysis of evaluations managed by UN Women in 2016.

Harvested statements were considered specifically in relation to the sub-criteria. Scoring was based upon the degree to which each of the individual sub-criteria were matched by corresponding statements. Thus, a maximum of three or four points were available for each criterion.

The data and scores were then mapped onto the framework in Table 1, with a colour-coded ‘traffic light’ system facilitating visual reference:

- green strong (3)

- orange moderate (2)

- red weak (1)

This provides an overview of the data, highlighting patterns, commonalities, strengths and weaknesses across the six evaluations.

- Analysis, interpretation and presentation

The final step involved analysis and interpretation to identify key insights and recommendations for future programming, highlighting the NCO’s main strengths and weaknesses and comparative advantage in terms of addressing WPS in the country.

## Limitations

The six evaluation reports differ in their presentation, focus and structure and as such, limit the extent to which comparisons can be made. Thus, while trends are suggested in this report, they should be considered illustrative rather than conclusive.

Furthermore, while the qualitative synthesis process attempted to apply structured analysis (by classifying all individual statements from reports), a degree of interpretation was required in terms of identifying the main findings in each report, interpreting these findings and their implications, and determining what particular combinations of findings from the different reports represent reliable patterns.

# EVALUATION FINDINGS AND CONCLUSIONS ON OECD/DAC CRITERIA

Overall, as Table 1 shows, the analysis found that the portfolio performed well over three of the five key criteria but that efficiency required greater attention. Impact was found to score poorly due to short time frames. For a breakdown of scoring see Annex 3.

Table 1. Aggregate scores of each evaluation report against Criteria

| Evaluations | OECD/DAC Criteria |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Relevance | Effectiveness | Efficiency | Sustainability | Impact |
| SIWPSAN (MTR) | 4/4 | 2/3 | 2/3 | 2/3 | 2/3 |
| SIWPSAN (Final) | 3/4 | 3/3 | 2/3 | 3/3 | 2/3 |
| EPST | 3/4 | 2/3 | 1/3 | 2/3 | 2/3 |
| GPI-CT | 4/4 | 2/3 | 2/3 | 2/3 | N/A |
| GRRSP (MTR) | 4/4 | 3/3 | 2/3 | NA | N/A |
| GRRSP (Final) | 4/4 | 3/3 | 3/3 | 2/3 | 2/3 |
| Total | 22/24 (92%) | 15/18 (83%) | 12/18 (67%) | 11/15 (73%) | 8/12 (67%) |

## Relevance

Key messages

- UN Women WPS interventions in the NCO have mostly been aligned with relevant national and international development goals and policies including UN Women global and national strategies.

- Appropriate partnerships are evident across all evaluations both with government bodies at national and sub-national levels, with UN agencies and CSOs.

- Interventions have been suited to their target group and appropriate Districts selected for implementation.

- Better prioritization of beneficiaries is needed with greater attention to highly marginalized groups including Dalit and Janajati and more proportional representation to ensure equitable engagement.

- The need for consultation with project beneficiaries during the project design was highlighted.

In the Peace and Security agenda UN Women seeks to strengthen women’s leadership and participation by supporting the development and implementation of national commitments, specifically the implementation and monitoring of the National Action Plan (NAP) on United Nations Security Council Resolutions (UNSCR) 1325 and 1820 and in supporting the implementation of the plan as per its UNDAF (2013-2017) mandate under Outcome 9. It works at national and local levels, addressing the rights and agency of conflict-affected women so they can influence local decision-making processes to demand accountability and contribute to a sustainable peace.

The NAP is built on five pillars namely: i) participation, ii) protection and prevention, iii) promotion, iv) relief and recovery and v) resource management & monitoring and evaluation (M&E) and aims for the participation and leadership of women at all levels of decision-making, conflict transformation and peacebuilding processes.

All interventions under this meta-analysis related to one or more of the five pillars of the NAP.

Overall, as Table 1 illustrates, relevance was strong across the portfolio. All reports highlighted that interventions had responded to the needs and priorities of their target groups, noted strong alignment with Nepal’s NAP, and with one exception, highlighted linkages to international commitments.

All reports cited strong working partnerships with joint implementing partners such as the UN Development Programme (UNDP), the International Labour Organisation (ILO), and the Food and Agriculture Organisation (FAO), government departments at national, district and local level and CSOs. Geographic coverage was considered appropriate and site selection made in consultation with key stakeholders, government funders and implementing agencies.  However, attention was sometimes drawn to the need to pay closer attention to the issue of beneficiary selection.

While all programmes had criteria for beneficiary selection, one programme (GRRSP) noted the need for greater clarity around the definition of ‘Conflict Affected Women’. A theme emerged across two evaluations (SIWPSAN Final Evaluation 2016 and GRRSP Final Evaluation 2015), namely the need to focus more on the most marginalised populations in the project area, in order to achieve more proportional representation:

‘Though there are beneficiaries from multiple exclusions, the project did not pay special consideration to select the beneficiaries from most marginalized groups such as Dalit in proportion of their presence in the population. Rather the proportion of privileged group such as Chhetri was higher in the project intervention than their presence in the population’ (SIWPSAN Final Evaluation 2016, Finding 8. p29).

Opportunities exist in the future to fine-tune selection criteria so that survivors of VAW and Conflict Affected Women are better represented and UN Women can better demonstrate its commitment to inclusiveness.

There was clear evidence of UN Women working to its comparative advantage across the portfolio: particularly with regard to women’s leadership and enhanced participation in decision-making, community capacity for peace, community peacebuilding, gender responsive transitional justice, economic recovery of conflict victims, addressing issues of conflict related sexual violence (CRSV), UN coordination and reporting on women, peace and security agenda and Gender-Responsive Budgeting (GRB).

Although not included as a sub criterion, two of the evaluations (EPST 2015, GPI-CT 2016) highlight the need to include beneficiaries in project design:

‘While the project is relevant, the design process appears to be "top-down" with limited joint analysis and consultations with actual project beneficiaries’ (EPST 2015 p25).

This was raised as an issue of principle, rather than practicality, since the reports also noted that interventions met beneficiary needs. Nevertheless, in the future, more attention should be afforded to ensuring that projects are based on ‘bottom up’ planning, so that beneficiaries are meaningfully involved at all stages of the project cycle.

## Effectiveness

Key messages

- The portfolio of work has largely been effective at achieving its objectives

- There is strong evidence of concrete benefits for beneficiaries, although this is not evenly distributed.

- Effectiveness depends to some extent on the operating context of interventions.

- Projects with short timeframes were most challenged in achieving results.

- There is evidence that programming has become more gender responsive and inclusive as a result of the work.

- Guidelines have been developed to improve and institutionalize programing for WPS.

- Effectiveness could be improved with clearer definition of roles and responsibilities for each partner and with more effective co-ordination among them.

- Work through existing networks of women and structures where possible.

Overall, the portfolio performed strongly under Relevance as Table 1 shows. Most of the interventions achieved their objectives and results, or else were on track to doing so. Those with the shortest time frame were most challenged in terms of achieving results (EPST 2015, GPI-CT 2016). While this situation is often donor –driven and beyond the control of UN Women, it raises issues of whether or not funding with short time frames should be accepted in the future particularly where longer term transformative change is sought.

UN Women support to building awareness of WPS issues within the framework of the NAP and including VAW, human rights, and UNSCRs 1325 and 1820 was successful in building momentum for more gender- responsive planning and implementation. As a result of UN Women’s technical and advocacy support to government stakeholders at national and district levels, enhanced capacity was noted in terms of the application of normative frameworks for gender equality and women’s empowerment, gender-responsive planning, zero tolerance of sexual violence, GRB, NAP implementation and localization of the women, peace and security agenda.

However, the importance of context was also highlighted as a critical factor affecting effectiveness:

‘…the project districts had unfavourable environment with low level of inputs from women groups and networks in local planning and budgeting processes, slow pace of government procedures, top-down decision-making process, and limited resources available at the DDCs and MCs for implementation and monitoring of NAP on UNSCRs 1325 and 1820. Under such conditions, the project duration was inadequate to achieve the desired outcomes. The Madhesh movement and border closures affected the project’s effectiveness in those project activities such as trainings and capacity development of targeted networks and groups was constrained. Achieving the project outputs was hindered due to the absence of GRB software which made it difficult to implement the GRB process at the district and community levels’ (GPI-CT 2016 p22).

Some of these issues could have been better anticipated. More rigorous risk management strategies attached to projects in the future may help both to ensure that risks are planned for and to calibrate expected results of projects.

All interventions demonstrated some changes in practice, if not in policy. This ranged from budget allocations for gender-responsive initiatives, to development and implementation of community security plans (CSP).

‘Ministry of Agricultural Development, through its district level offices (DADO and DLSO) has allocated more than 30 percent of the total programme budget (which is more than NPR 6.0 million per district) for gender responsive initiatives’ (GRRSP. Final Evaluation 2015 p11).

The collective effort was successful in building capacity of stakeholders and beneficiaries: by simultaneously building the capacity of both duty-bearers and rights-holders and supporting interaction between them.

The interventions have succeeded in increasing women’s participation in peacebuilding and local decision making and in securing closer attention to NAP at District and Local levels.  Psychosocial counselling has enabled women to manage the trauma of conflict and engaged more actively in community affairs and/or livelihoods. Support for collaborative leadership and dialogue has succeeded in changing beneficiaries’ perceptions toward resolving differences non-violently,

‘while the project has made notable contribution to improve community security in the project districts. Increased women’s participation in peacebuilding and local decision making and enhancing the capacity of national and district level government agencies in implementing NAP are another notable contribution (EPST 2015 p8).

Guidelines have been developed to i) inform effective roll out of the NAP at District level together ii) support the establishment of partnerships with CSOs for implementation of UNSCR 1325 and 1820 iii) support the establishment and management of Safe Houses and iv) conduct gender audits.

Training on UNSCRs 1325 and 1820, and support in developing women’s shared voice have resulted in one site, in the submission of a memorandum to district level government line agencies urging the inclusion of women in planning and budgeting processes.

Every report noted that partnering with government bodies, whether at central, district or local level enhanced the effectiveness of interventions. Increased effectiveness was also cited where project planning was inclusive and bottom-up, rather than top down.

Three issues emerged across the portfolio as influencing effectiveness:

- Women’s collectives: two reports cited the importance of building a group identity among women as a pre-requisite for meaningful participation in peacebuilding and decision making: "After the skill development training, we were organized in a group. Before the project we were alone and didn’t realise our collective strength’ (GRRSP. Mid Term Evaluation 2014 p20).

‘[conflict affected women] (CAW) being one of the main beneficiaries of the project is not yet organized or institutionalized as other groups of women and therefore their involvement was not as effective as expected’ (GPI-CT 2016 p7).

- Need for greater clarity in collaborating partners’ roles and responsibilities. All interventions were collaborative efforts, either with UN partners or with CSOs. Three evaluations noted lack of clarity about partners’ respective roles and responsibilities, together with the need for joint planning and improved synchronicity (see Efficiency). One evaluation highlighted confusion about the role of UN Women field staff, which – while appreciated - was not sufficiently clear to implementing partners and stakeholders.

- Need for more attention to project design and results frameworks (see also RBM). Two evaluations were constrained by the fact that there was no baseline data against which to measure progress. Some activities were not included in the Results Framework. Flexibility of instruments was noted as positive in that beneficial activities were implemented (for example, seed funding for women’s enterprise activities) but since these were not included in the project design, progress and impact was difficult to track.

## Efficiency

Key messages

- Activities have been partially resource efficient, and innovative cost-saving mechanisms have been designed.

- Not all reports reflect timeliness of interventions

- Short project timeframes and relatively long preparatory periods reduce time for implementation and thus reduce efficiency.

- Greater co-ordination among partners, consolidated monitoring and reporting systems together with greater clarity in operating procedures are all necessary to improve efficiency.

- Creating parallel structures challenges local resource mobilization and longer-term efficiencies.

Overall, interventions were reported to have been both cost- and resource-efficient and budgets accounted for in a transparent manner. Joint programmes shared costs, and judicious selection of project sites, for example in adjacent districts, was also found to reduce costs. Outsourcing capacity development to local partners was found to be particularly efficient, since such organisations were both cost-effective and familiar with local cultures and mores. Innovative approaches to cost saving were also found:

‘such as reducing the number of days in residential training by increasing number of hours per day, conducting skill development training in VDC cluster and organising skill examination test during the residential training period rather than conducting separately’ (SIWPSAN Final Evaluation 2016 Finding 21 p44).

Some reports do not address the extent to which activities were completed on time. Others argued for more time to be devoted to specific activities. For example, the time allocated for provision of psychosocial counselling was found to be inadequate. Furthermore, attention is drawn to the importance of the context within which projects occur:

‘The time-period of one and a half year for achieving the project outcome was too short, especially in the context of the project districts that had high prevalence of Gender Based Violence (GBV), gender inequity and inequality, low participation of women in local planning processes, poor knowledge on NAP on UNSCRs 1325 and 1820.’ (GPI-CT 2016 p23).

The overall efficiency score of 67% (Table 1) was adversely affected by reference to weak systems and procedures across three reports; where systems and procedures relate to project management, implementation and personnel systems.  SIWPSAN mid-term report acknowledges the value and added efficiencies afforded by the placement of UN Women staff within the Women and Children’s Office (WCO). At the same time, it notes a degree of confusion at District level:

‘Lack of clarity of roles and responsibilities of UN Women Project staff to the WCO, and lack

of ownership of this particular position among WCO are some of issues observed at the

district level. For example, in some project districts, Women Development Officers weren’t clear on exact role of the UN WOMEN project staff and were of the opinion that the position was to support solely SIWPSAN project instead of support to the WCO’(SIWPSAN Midterm  Evaluation 2015 p28).

The same report also calls for better utilisation of existing women’s community structures rather than the establishment of new ones. The creation of parallel structures is reiterated in EPST where the project created Multi Stakeholder Dialogue Forums which at times overlapped with existing and formally recognised Local Peace Committees in terms of members and agendas. This led to confusion at times and the report concludes that attention to strengthening the LPCs would be a more efficient way forward. In the same vein, the project created Community Security Committees which, as non-registered entities, had limited legality and accountability. The report concludes that a more efficient approach would be to work with the existing Community Police Service Centres set up by the Nepal Police.

The GRRSP Mid-term and Final reports describe a high degree of efficiency between the three UN partners in line with UNDAF, achieved by synergistic planning and monitoring systems aligned with government processes. The SIWPSAN final report also notes that the Project Steering Committee played an important and efficient coordination role. Conversely, efficiency is constrained where co-ordination and consolidated reporting systems are afforded too little attention (EPST 2015).

Three further challenges were identified in relation to efficiency: delays in budgets reaching district level, the result of slow government procedures, frequent staff turnover, particularly among government counterparts necessitating repeated training and capacity development events, and lack of preparedness for external events affecting project implementation.

## Sustainability

Key messages

- It is critical to use existing systems and structures at government and civil society level where possible.

- Some evidence of continued activity after phase-out due to the ripple effect of successful interventions.

- Activity tends to decline in line with reduced support.

- Psychosocial counselling is showing sustainable benefits with recipients more able to participate in community life and income generation.

- Transformative work such as community dialogue has demonstrably improved relations both within communities and between communities and the police.

- Gender Responsive Budgeting has been important in securing consideration of gender equality in central and district planning processes.

Five of the reports consider sustainability which was found to be more likely when local government budget allocation was approved for WPS issues:

‘Many VDCs have allocated budget for community security planning which is highly notable from sustainability because even if the project is phased out, VDCs can continue to support community security planning’ (EPST 2015 p9).

Likewise, where existing mechanisms have been employed to drive project goals – e.g. District Coordination or Development Committees, Interparty Women’s Alliance -  prospects of sustained benefits were found to be higher. Furthermore, integrating peacebuilding initiatives into local government systems enhances sustainability. GRRSP Final Evaluation notes that sustainability for CAW entrepreneurs and women owned small businesses were enhanced because the project ensured that beneficiaries were formally registered with the Cottage and Small industry office, thus legitimizing their work in the longer term.

All reports describe capacity development, for example, training of trainers (ToT), workshops and NAP/WPS agenda awareness raising sessions, as well as skills training. One evaluation notes that establishment and support to the IPWA was perceived by non-participating VDCs to be a successful strategy and was thus emulated (SIWPSAN Midterm Evaluation 2015 p7). This ‘ripple effect’ shows promise for the wider sustainability of project goals.

While the benefits of capacity development benefits were deemed to increase the likelihood of sustainability, the need for monitoring and follow up was cited.

‘Within one year, we have just learned how to crawl. Such a project needs to continue for at least 2-3 years to enable us to be independent and attain economic prosperity and social development’ (GRRSP Final Evaluation 2015 p40).

Three reports observed that as project input declines so too does beneficiary action.

‘In regards to women leaders and other women groups/networks, the project has ignited them to establish a collective voice for advocacy and demand to include women agendas in local planning and budgeting process. It has also motivated them to increase their participation in local planning and budgeting process but they need continue support of the GPI-CT project to build their capacity for their meaningful participation and to influence local planning and budgeting process’ (GPI-CT 2016 p33).

All reports highlight a degree of ownership, particularly at the local level. One report (EPST) points to the fact that, while several line agencies were involved as partners, no one agency was nominated as the lead agency and this resulted in weak overall ownership. The same report notes the absence of a clear sustainability strategy. It was felt that local and national ownership, and thus sustainability, could be enhanced if key stakeholders had been involved at all stages of the project cycle

## Impact

Key Messages

- None of the reports claim national policies have changed as a result of their input.

- Positive changes in beneficiaries’ lives were noted in the four reports which considered impact.

- Evidence of improved community cohesion was provided for example in relations between community and the police.

- Project inputs were of a relatively short duration limiting realistic chances of impact.

The four reports that attempt to measure direction towards impact note that the relatively short duration of the projects makes assessing impact challenging. Nevertheless, specific examples of impact are recorded anecdotally. For example, EPST cites evidence of communities using dialogue as a tool to reduce community tension in Banke and Nepalgunj and a jointly-funded and newly constructed bridge as evidence of improved community- police relations.

SIWPSAN Mid Term Evaluation (2015) provides evidence of increased reporting of VAW in project sites, a likely consequence of enhanced awareness of VAW systems and rights issues. GRRSP Final Evaluation suggests that through bringing different groups of people together -  including women from opposing sides of the conflict – the project has developed self-confidence and community cohesion.

## Gender equality

Gender equality and women’s empowerment is the cornerstone of UN Women support and this portfolio of work has made important contributions to women’s participation and leadership in peacebuilding initiatives as well as their economic empowerment. Nevertheless, it was deemed useful to examine the degree to which reports reflected contributions to gender transformative work, for example by addressing underlying causes of gender inequality, and transforming the social and political mores that perpetuate them. This was based on the justified assumption that all of the work across this portfolio was explicitly adopting a gender responsive approach.

Two of the reports provide examples of social and cultural change in perceptions of men toward women, which touch on a change in personal power relations between men and women:

‘Evidence of this success was noted during the evaluation study when women expressed their ability to convince their husbands that they could work together. Thus, understanding gender roles in the family was found to be one of the major impacts on the lives of conflict affected women and men’ (GRRSP Final Evaluation 2015 p37).

GPI-CT explores the cultural context within which the project took place and notes that:

‘Women’s participation in GRB is low because it is also guided by strategies that mainly constitutes head of government line agencies where women at the positions is very low’ (GPI-CT 2016 p32).

Two reports note the importance of involving men in the WPS agenda and suggest that targeted interventions with male gender advocates would be worth considering:

‘more frequent awareness raising for concerned government and civil society stakeholders based on the findings of the Women’s Safety Audit involving women as well as boys and men would have more impact on preventing violence against women’ (EPST 2015 p37).

A need is emerging for programmes to take an intersectional approach to their work with women as highlighted by GRRSP in terms of future targeting for livelihoods work since:

‘There were a few CAW families without land, or with very little land, for whom agricultural production had little or no meaning. Alternative livelihood options should have been planned for these families’ (GRRSP Final Evaluation 2015 p32).

While securing land for the landless is beyond the mandate of UN Women it remains a key message for advocacy.  Overall there were few examples of gender transformative work. This is likely because of the relatively short time frames of the projects but it highlights the need for longer term or sustained engagement if WPS investments are to be both sustainable and cost effective. This includes the need for consolidated attention to mainstreaming gender equality across projects and programmes both internally as a Human Resource issue, and externally through policy advocacy and across the project cycle.

# LESSONS LEARNED, GOOD PRACTICES & PROMISING APPROACHES

The portfolio offers a range of lessons learned, good practice and promising approaches. These include the importance and the value of participatory approaches that engage beneficiaries throughout the project cycle. Those interventions with the greatest degree of collaboration and participation recorded greater prospects of sustainability.

Since gender equality cuts across social political and resource conflicts, the WPS agenda provides an excellent entry point to peacebuilding. UN Women has played a key role in Nepal in ensuring that WPS is on the central and district governance agenda, building on comparative advantages and relationships in country. This momentum has paid dividends at district level, where increased awareness has led to greater commitment to institutionalize gender issues.

GRB is perceived to be an excellent tool for GPI-CT the NAP but, to be effective, GRB-related capacity development must be synchronised to coincide with government’s budgeting timeframe.

Where multiple agencies were involved in project implementation, there was a need for clear roles and responsibilities, effective co-ordination mechanisms (vertical and horizontal) together with joint monitoring and reporting systems. GRRSP demonstrated how an effective project steering committee with joint monitoring mechanism successfully managed a diverse portfolio of activities.

Building the capacity of rights holders simultaneously with that of duty bearers is an effective of securing the WPS agenda at district level. By building on the power of networks, whether through VDC networks or women’s networks, for example the revived Inter Party Women’s Alliance (IPWA), women’s rights have become an institutionalized issue on the local development agenda. However, the evaluations also repeat the importance of using existing networks rather than creating parallel structures.

Economic empowerment goes hand in hand with social and political empowerment and has a synergistic effect.  Economically empowered women are shown to benefit from wider psychosocial empowerment and practically, by being economically empowered, are better able and motivated to become more engaged in decision making at community level.

Only one evaluation noted that more work had been expended on UNSCR 1325 than 1820 (SIWPSAN Final Evaluation 2016). On further scrutiny, none of the other five evaluation reports distinguish between 1325 and 1820, citing them always simultaneously. It is not clear therefore, whether each substantive issue e.g. participation or VAW has been equally addressed or not and this merits further consideration.

Constraint of time was a common theme. Much of the WPS work, changing social and individual attitudes and behaviours as well as government and CSO governance processes and practices cannot be sustainably achieved within a short time frame but requires ongoing nurturing and support.

# EVALUATION FINDINGS ON OPERATIONAL PRINCIPLES AND APPROACHES

## Partnerships

These project evaluations demonstrate that partnerships are essential for effective approaches to implementing the WPS agenda and that chances of sustainability are increased with effective government partners both at national and local level. However, the concept of a ‘partnership’ remains ill-defined across the portfolio: some reports view all those engaged in the intervention as partners while others refer largely to co-implementers as partners. For the purpose of this report partnership is used to refer to co-operating entities while stakeholders refer to both beneficiaries, communities and government agencies where relevant.

Four of the six reports refer to  UN agencies: UNDP, FAO and ILO, while the two SIWPSAN reports cite variously that the project has 10 partners or is managed by UN Women through different partners including Ministry of Women, Children and Social Welfare (MoWCSW), Department of Women and Children (DWC) at central level and three local NGO partners, namely Dalit Help Society (DHS) in Bhajhang, Creative Development Society (CDS) in Doti and Backward Awareness Society (BASE) in Kailali with occasional technical support from Training Centre Nepal (TCN) Search for Common Ground (SfCG), Local Development Training Centre (LDTA), SAATHI, Krishna Consultancy, IOM, UNDP and 1325 Action Group’.

The partnership for GRRSP between UN Women, ILO and FAO was found to work particularly well because each agency had a clear working niche. For example, UN Women supported gender awareness and psychosocial counselling, while FAO and ILO supported livelihoods and economic empowerment. This multifaceted intervention was found to be effective because it responded simultaneously to the broad spectrum of needs of conflict affected women and worked synergistically.

Likewise, where roles and responsibilities were clearly defined activities ran most smoothly. Without this clarity ownership and efficiency of the project was undermined. Given that all of the interventions were partnerships and are likely to be in the future, greater attention to the practicalities of partnerships is required.

Nonetheless, to be effective these multiple partner programmes demand both horizontal and vertical coordination mechanisms that are sufficiently credible, authoritative and acceptable. It is also necessary to ensure that multi-layered partnerships do not inhibit ownership by local stakeholders and beneficiaries. Effective partnerships also require acknowledgment (and ideally harmonisation) of their respective organisational procedures and requirements and associated strengths and challenges.

## Knowledge management

Few of the reports focus on knowledge management, although one (GPI-CT 2016 p6) specifically notes the need to share lessons from the local level up to the national level to inform policy decisions. The same report refers to ToT on GRB and NAP as a contribution ‘to the knowledge hub on GRB and national action plan on UNSCRs 1325 and 1820 at national and sub-national level.’

Given the frequent mention of high staff turnover of government officials, at a local level, consideration needs to be given to ensuring that relevant project communication is accessible, dynamic and shared, rather than top-down and one directional. Similarly, training and capacity development materials (e.g. on UNSCRs 1325 and 1820) need to be adapted to ensure they are consistent with the educational levels and languages of the diverse participants. None of the reports shed light on the degree to which this is happening.

Clearly UN Women is contributing to the collective knowledge on implementing the WPS agenda in Nepal through these projects; ‘UN Women Nepal to a great extent correctly analysed and interpreted the on-going needs of the women’s leadership and participation in peace, security and governance process at the local and country level (SIWPSAN Final Evaluation Finding 3 p26).

## Capacity Development

Capacity development has been identified as a key intervention in the reviewed documents. As well as specific skills and practice-oriented training for individual beneficiaries (such as in economic empowerment), capacity-building has also contributed to strengthening specific structures and mechanisms, including those at village level.

All reports refer to training and ToT as well as awareness raising as key strategies for capacity development. However, a note of caution: trainings and awareness sessions are alone insufficient to lead to long term change as many development efforts will attest to. As noted by GRRSP, the foundations may have been laid but ongoing support will still be required to maintain levels of confidence, markets and to troubleshoot as and when problems occur. To this end, a longer-term presence in selected districts will maximise investments to date.

Capacity development for women’s leadership was considered successful and reflected in increased community participation, leadership, and decision-making as well as access to support for survivors of conflict and violence. Moreover, capacity development and empowerment can have generalised as well as specific benefits. For example, economic empowerment was found to be associated with enhanced participation in household and community levels.

Ensuring the local implementation of Nepal’s NAP requires capacity development among both duty bearers and right holders. Capacity development also needs to be sufficiently flexible to accommodate the frequent staff turnover among government personnel. Two reports note the need for monitoring and follow up post training to ensure that messages are fully absorbed and understood.

Finally, capacity development of government partners is already paying dividends ‘The enhanced capability of MoWCSW can be judged from their quality of reporting and response on incorporating relationship between the project and international conventions (Universal Periodic Review by HRC, CEDAW CC, CRC Committee) on women/girls affected by conflict, violence against women, women’s participation in political and public life. They were better equipped in organising meetings and monitoring project activities. (SIWPSAN Final Evaluation 2016 p32).

## Replication and “Up-scaling”

Limited attention was given to replication and up scaling apart from recommendations that interventions be repeated. However, some positive examples have been provided. The SIWPSAN Mid-term Evaluation cites:

‘Project has supported the capacity development of the project partners to enhance the managerial, technical capacity of the DCC members and local partners to amplify, replicate project agenda and gains, and the partner commitment to take forward the NAP agenda at the local level is visible, and this has further led to strengthening them for potential scale-up in other VDCs as well’ (SIWPSAN Mid-term Evaluation 2015 p7).

Together with concerns over sustainability, replication relies to some extent on continued input:

‘it seems that level of participation of target groups in local organisations goes down if no further support is provided, further capacity development is necessary to enhance the existing skills of entrepreneurs (for some economic activities such as tailoring, beautician, cooking and mobile repair) and there is need for continuous advocacy for replication and scaling up with the focus on wider VDC coverage as well as coverage of excluded groups.’ (GRRSP Final Evaluation 2015 p16

The instance of non-project VDCs replicating the establishment of IPWA based on the positive examples from project VDC is worthy of closer investigation to determine a) how the project communicated its good practice across non-project VDCs and b) what conditions in non-project VDCs were present to enable this ripple effect to take place. This knowledge could then be deployed in future project planning.

An insight provided by GRRSP final report was that the approach of working with stakeholders ‘as experts, alongside DADO and DLSO staff, establishing

linkages with the market through local partner organisations has not only benefitted individuals but also partner organisations and can easily be replicated elsewhere.

GRRSP notes a further area for replication is the expertise developed for right place right business with proper training. The selection of activities was based on locally available natural resources and raw materials, thereby avoiding the risk of importing raw materials and goods from outside. Most of the products developed by businesses were based on market demand focusing on the competitive advantage of the locality and value chain upgrading of agriculture products.’ (GRRSP Final Evaluation Finding 8 p30)

## Results Based Management

None of the reports provide clear reference to RBM. Theories of Change (ToC) were examined in four of the six evaluations. SIWPSAN found the ToC to have been effective in achieving results, whereas the EPST found that the ToCs attached to each of the three project outcomes did not describe a coherent overall project approach and that a consolidated ToC was deemed to have been more appropriate. None of the ToC examined included risks and assumptions.  Based on some of the challenges to activities, for example high turnover of staff, more attention should be paid to integrating risk management into projects’ logic models. It is understood that this is already gaining greater attention.

One report notes that some activities, while successful, were not included in the Results Framework challenging the evaluation process:

‘some of the activities along this line were added later (for example, GRB in outcome area III), it is recommended to integrate this approach in the project from the project design phase so that the project will strongly link peacebuilding with development and reflect this in the project's theory of change’ (EPST 2015p10).

This represents a potential missed opportunity in learning for UN Women. There is considerable value in the development of a contingency or risk management plan that anticipates and addresses possible social, administrative and political risks to project implementation: for example, frequent staff turnover and delays in budgets arriving at District level should be an anticipated and therefore manageable risk.

# CONCLUSION

The portfolio of evaluations demonstrates that UN Women has played to its comparative advantage in Nepal and through its projects has made a difference to beneficiaries’ lives at an individual and collective level.  The Women Peace and Security agenda is becoming institutionalized in collaborating Districts and more women are participating and leading in peacebuilding initiatives. Efforts have been highly relevant showing clear alignment with national and international policies and commitments and responding to the need of beneficiaries. Geographic site selection has been appropriate and further consideration is now needed to ensure that beneficiary selection correctly reflects the social context.

Using gender equality as a vehicle for linking WPS with governance structures is shown to be an effective strategy. The approach of building duty bearers’ and rights holders’ capacity simultaneously has also proven to be effective both at increasing women’s engagement in peacebuilding and increasing government attention to the issue of Gender Equality. However, this analysis identifies several opportunities for NCO to enhance its effectiveness in the future: Greater attention to intersectionality and inclusion will ensure programmes are meeting the need of all women affected by conflict; Strengthened coordination at all levels of government will support timely budget release and build institutional memory and ownership among local authorities moving forward for NAP II phase.

the focus on UNSCRs 1325 and 1820 should be expanded to (i) integrate the areas of the WPS agenda (either the five pillars of the NAP or the four traditional pillars of the agenda), and (ii) disaggregate results across each of these areas of work.

Finally, those projects with short durations were less effective at achieving results than those of longer timelines. Given this finding, it may be worth considering which projects UN Women decides to pursue in the future focusing on those of a longer duration or building in to shorter projects the possibility of coaching and mentoring after the main project work has ceased.

Efficiencies can be improved; while activities were largely found to be cost and resource efficient, co-ordination and communication require more attention particularly where multiple partners are involved. It is important to distinguish between technical assistance and management functions where UN Women places staff at District level.

NCO could gain efficiencies in the future from translating existing training and project materials developed across the portfolio of work examined here into local languages for wider application. Materials which focus on sexual and gender based violence would address the need for a raised profile of these issues.

Sustainability of interventions was perceived to be moderate although attention is drawn to the relatively short time frame of most projects some positive examples have emerged where non- project VDCs are adopting project VDC practices.

To maximise on the learning gained from these interventions UN Women would benefit from more rigorous attention to project management and systems, and to make knowledge gained from them more visible.

# RECOMMENDATIONS/WAY FORWARD

For NCO and the Strategic Plan

Strengthen UNW intersectional responses to WPS by:

- Ensuring conflict affected survivors are integrated as one of the target groups throughout UN Women Nepal’s thematic area. This will further support their recovery efforts.

- Investing in translating all relevant tools on addressing sexual and gender based violence and its prevention and response into local languages to ensure local engagement and sustainability. Translations and long-term capacity building should be prioritized over the repetitive production of new tools, strategies, guidelines and advocacy campaigns.

- Supporting the establishment of an independent monitoring mechanism run by women’s civil society groups and women’s human rights defenders in future peacebuilding programs to track implementation of the national action plan implementation.

- Further refining selection protocols for projects which ensures identification of appropriate beneficiaries who are representative of their communities.

Strengthen approaches to gender mainstreaming by:

- Commit to gender parity among project staff (that is 50 per cent women) and to the training of all staff in gender equality programming and the protection of women’s human rights, identifying and responding to the early warning specially with regards to emerging conflict and tension.

- Continue advocating for local level allocation of funds for GEWE as part of National Level Gender Responsive Budget allocation. The budget should be allocated to address women’s leadership at all levels, addressing violence against women, addressing peace, security and humanitarian efforts, increasing gender responsive local planning and implementation process.

- Ensuring that UN Women is a member of all relevant inter-agency forums on peace, security and humanitarian response, including the relevant Advisory Group on peace and security, to ensure a gender perspective is mainstreamed throughout the UN’s response in conflict, disaster, early warning and emergencies.

- Consider either applying only for funding with longer than 2-year duration or lobbying donors to extend the duration and funding of projects which address WPS

Strengthen coordination of WPS efforts by

  - Strengthening existing management committees for gender equality in project locations to address lack of intra-ministerial, coordination, Federal, Provincial, Local Government coordination, timely budget release, effective documentation, reporting and institutional memory, ownership among local authorities.

  - Considering expanding reference to all eight WPS resolutions along with other international instrument in UN Women work related to participation, protection, prevention and peacebuilding.

For Project Implementers

- Engage beneficiaries in all stages of project cycle.

- Where projects are jointly implemented, ensure clarity of roles, and encourage joint planning and monitoring of projects to enhance ownership and increase efficiency.

- Ensure systems and procedures are commonly understood by all stakeholders.

- Ensure consolidated Theories of Change are developed for each project accompanied by risk management and contingency strategies.

- To enhance the sustainability of efforts, UN Women should ensure its projects focus on enhancing the capacity of existing mechanisms and networks, both across government and Civil Society, rather than initiating new ones.

- Consider greater attention to engaging men as advocates of gender equality.

- Continue to build on comprehensive packages which address economic recovery and psycho social support.

# REFERENCES

Asian Academy for Peace Research and Development (2015). Ensuring Participatory and Secure Transition (EPST).  Final Evaluation.

Nepal Institute for Development Studies (2015).  Gender Responsive Recovery for Sustainable Peace (GRRSP). Final Evaluation.

http://gate.unwomen.org/Evaluation/Details?EvaluationId=5023

Ojha, GP. (2014) Gender Responsive Recovery for Sustainable Peace (GRRSP). Mid-Term Evaluation.

http://gate.unwomen.org/Evaluation/Details?EvaluationId=4783

Ojha GP et al. (2016) Strengthening Implementation of the Women, Peace and Security Agenda in Nepal. Final Evaluation.

http://gate.unwomen.org/Evaluation/Details?EvaluationId=8123

Right Direction Nepal (2016). Localizing Women Peace and Security Agenda in Central Terai Districts of Nepal. Final Evaluation.

http://gate.unwomen.org/Evaluation/Details?EvaluationId=8124

Scott Wilson Nepal Pvt. Ltd. (2015) Strengthening Implementation of the Women, Peace and Security Agenda in Nepal (SIWPSAN). Mid-Term Evaluation. July 2015

http://gate.unwomen.org/Evaluation/Details?EvaluationId=5022

UN Women Corporate Strategic Plan 2018-2021.

http://www.unwomen.org/-/media/headquarters/attachments/sections/executive%20board/2017/second%20regular%20session%202017/unw-2017-6-strategic%20plan-en-rev%2001.pdf?la=en&vs=2744

# ANNEX 1. Terms of Reference

##### Background

Grounded in the vision of equality enshrined in the Charter of the United Nations, UN Women works for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security. Placing women’s rights at the center of all its efforts, UN Women leads and coordinates United Nations System efforts to ensure that commitments on gender equality and gender mainstreaming translate into action throughout the world. It also provides strong and coherent leadership in support of national priorities and efforts, building effective partnerships with government, civil society and other relevant actors. In Nepal, UN Women focuses on strengthening women’s voice, agency and leadership across sectors to advance women’s rights, provide space for women’s meaningful participation and to demonstrate tangible differences in their lives. The agency’s programme adopts a holistic and integrated approach across UN Women’s five thematic priorities. It is guided by Nepal’s stated priorities (including those from the Three-Year Plan 2016-2019) and its commitments to relevant normative frameworks, the country’s United Nations Development Assistance Framework (UNDAF) 2013-2017, the CEDAW Concluding Observations (2011) and UN Women’s Corporate Strategic Plan 2014-2017. The programme promotes national ownership, capacity development and institutionalization, inclusiveness, coordination and partnerships, and knowledge generation and management, and seeks to prioritize engagement with and support to key duty bearers who are responsible for advancing women’s human rights and with rights holders so they can exercise voice and agency. UN Women is in process of developing UN Women’s Corporate Strategic Plan 2018-2021. UN Women is dedicated to the achievement of gender equality and the empowerment of women. The mandate and functions of UN Women call for the promotion of organizational and UN system accountability on gender equality through evaluation, strengthening evaluation capacities and learning from evaluation, and developing systems to measure the results and impact of UN Women with its enhanced role at the country, regional and global levels. The purpose and role of evaluation in UN Women is to contribute to learning on best ways to promote gender equality and women’s empowerment, enhance UN Women’s accountability, and inform decision-making. By providing evidence-based information, evaluation contributes to UN Women’s role to generate knowledge on what works to advance gender equality and women’s empowerment. To address the organizational demands for enduring good quality and credible evaluations particularly at decentralized level, the UN Women’s Independent Evaluation Office (IEO) has designed a Global Evaluation Oversight System (GEOS) and a Global Evaluation Reports Assessment and Analysis System (GERAAS) driven by similar good practices enforced by other UN entities and consistent with the UNEG Norms and Standards. The system is serving as a key instrument to increase the application of sound approaches and methods to continuously improve the quality and credibility of evaluation methods and reports within UN Women. As part of this process, the IEO assesses the quality of the oversight system on a quarterly basis and corporate and decentralized evaluations on a yearly basis and made available assessment findings to senior managers, programme units and the UN Women Executive Board. In addition to the quality assessment of individual reports, the GERAAS system requires a meta-analysis of evaluations to capture the key insights from evaluation reports – rated satisfactory or above according to UN Women standards. This is required to develop constructive lessons for future system strengthening of programming, organizational effectiveness and the evaluation function. Whereas the meta-evaluation provides a rating of the quality of evaluation reports according to UN Women standards, meta-analysis synthesizes the key findings conclusions and recommendations for the body of evaluation reports that meet UN Women quality requirements. UN Women Nepal (NCO) is seeking a consultant to conduct a meta-analysis of the evaluation reports produced by the NCO for Women Peace and Security (WPS) projects from the period 2014-2017. The selected consultant will review the evaluation reports produced by the NCO for WPS projects, as well as analyze trends, results, contributions, strengths and weaknesses across the NCO. It should also synthesize the recurrent findings, recommendations, conclusions and, and lessons learnt for all evaluation reports completed in the given years. The findings of meta-analysis of the evaluation reports will contribute to the development of the NCO’s Strategic Plan 2018 – 2022.

##### Duties and Responsibilities

Since 2012, UN Women Nepal Office has commissioned six evaluations of its projects/programmes covering mainly WPS projects from 2014 to 2016. The meta-analysis will be conducted by an external consultant from 1 September 2017 to 16 November 2017. The consultant will work under the overall supervision of the Unit Manager of the PSH Unit and in close coordination with the M&E officer and other programme units. METHODOLOGY: This meta-analysis will be carried out solely based on desk review of six programme evaluation reports completed between 2014-2016. By aggregating the recurrent findings, conclusions, lessons learned, good practices and recommendations, the synthesise will provide a better understanding and insight of NCO’s WPS programme interventions and operational effectiveness of NCO interventions as it transitions into a new Strategic Note cycle (2018 - 2022). The synthesis of this information will also support the use of evaluation findings by the NCO and its key stakeholders for its Strategic Planning process. It will also inform donors and other development partners about the effectiveness of the interventions supported by the NCO’s intervention on WPS projects in the last four years. Usability will be ensured through different strategies, including tailoring of the deliverables to ensure that the results of the MA are captured in a way that stimulates sharing and understanding of knowledge. META-ANALYSIS QUESTIONS: The meta-analysis should be guided but not limited to the guiding questions illustrated below. The consultant is encouraged to be innovative in the analysis and presentation of the insights to address any other relevant issues that may emerge during the analysis. The analysis is guided by the following core questions: - What are the strengths that emerge from the evaluations of the NCO’s WPS projects? - Which types of efforts/strategies being implemented have shown high degrees of relevance, effectiveness, sustainability, efficiency and impact? - Are there any patterns and lessons to be learnt regarding results produced by the NCO’s WPS projects in general? - Are there findings and conclusions that point in the same direction? - What strengths and challenges do the evaluations expose? - What are the lessons learnt? DUTIES AND RESPONSIBILITIES: - To examine the quality of the past evaluation reports of the NCO’s WPS projects by providing a summary of reports to the Senior Managers and staff in the NCO; - To analyze the impacts of the NCO’s projects on WPS; - To provide better understandings and insights into the NCO’s performance; - To capture experiences and lessons learnt from the evaluations to enhance organizational learning and knowledge management. KEY DELIVERABLES: The three main deliverables of the consultancy will be the following: Deliverable 1: Aide Memoire The aide memoire will be completed after an initial desk review of the completed evaluations of the six WPS projects. It will be 2-3 pages’ maximum in length and will include: - Introduction - Background to the meta-analysis: objectives and overall approach of both phases of this exercise. - Description of meta-analysis methodology/methodological approach. - Work Plan with dates and deliverables (Annex). Expected Duration: 2 weeks Management Notes: - This report will be used as an initial point of agreement and understanding between the consultant and the Evaluation Manager (Unit Manager, Peace and Security and Humanitarian Action Programme) & Reference Group. Payment schedule: 40% of total on approval of deliverable. Deliverable 2: First and Second Draft Meta-Analysis Report with Report Validation Workshop The first draft report will analyze and synthesize the findings, conclusions, recommendations and lessons learned and good practices from the six WPS evaluations conducted. It will be a maximum of 25-page report that will help to paint a perspective of the achievement of the NCO’s WPS projects vis-à-vis its organizational goals. The Meta-analysis is poised to provide a basis to better understand the NCO’s WPS interventions and achievement of its goal and outcomes. The content of the report will be discussed with the consultant in detail prior to the meta-analysis phase. The consultant should cover all the required sections and contents in the first draft and share it to the management group and reference group for their inputs. The second draft report will be presented in the validation workshop organized by the consultant in close consultation with management team of the NCO after incorporating the inputs received from relevant experts/stakeholders. It will be a 25-page report that will help to paint a perspective of the achievement of NCO’s WPS programmes and projects vis-à-vis its organizational goals. The NCO will provide support to the consultant to make sure wide-ranging stakeholders, including partners and beneficiaries attend the meeting. The consultant will submit several key products namely; - One validation workshop; - Power point presentation of the meta-analysis; - A ten-page summary report (e-copy and 100 copies printed) in Nepali and English language. Expected Duration: 2 weeks (First draft) Expected Duration: 1 week (Second draft) Expected Duration: 2 weeks (Validation Workshop) Management Notes: - The first draft report will be reviewed and commented on by the management team. - Once the inputs from management group are incorporated in the first draft, the agency will share the second draft to the reference group. - The second draft will be shared with the reference group and presented in the validation workshop after the review and comments from the management team of the NCO and the Reference Group. Payment schedule: 30% of total on approval of deliverable. Deliverable 3: Final Meta-Analysis Report and Dissemination of Report The consultant will finalize and submit the meta-analysis report by incorporating the comments from the NCO and the relevant stakeholders. The final meta-analysis report shall include the following chapters: - Executive Summary - Background and context of the analysis - Purpose - Approach and methodology - Findings – from the desk review of the six evaluations - Conclusions and lessons learnt - Recommendations - Annexes (relevant documents) The consultant will in close coordination with the NCO prepare a dissemination strategy and disseminate the report among the project partners and stakeholders at national level by sharing the published report. The consultant will organize a national level workshop for the dissemination of this report and present on the findings and recommendations. Expected Duration: 2 weeks Management Notes: - The final Meta-Analysis report will go through a process of review and approval. Final approval of findings will be done by the Representative, UN Women Nepal. Payment schedule: 30% of total on approval of deliverable. SUGGESTED WORKPLAN: - Aide Memoire: Weeks 1 and 2 - First and second draft meta-analysis Report with Report Validation Workshop: Weeks 3 to 7 - Final Meta-Analysis Report and Dissemination of Report: Weeks 8 and 9 EVALUATION MANAGEMENT: The Meta-Analysis Management Group will comprise of the NCO Representative, Deputy Representative, Unit Manager - Peace and Security and Humanitarian Action Programme, M&E Officer and Women, Peace and Security Consultant and will be in charge of the direct management of the meta- analysis. At the technical level, this group will provide technical feedback and support essential decision making during the whole evaluation process. The Reference Group will comprise of members of the Ministry of Peace and Reconstruction, National Planning Commission, 1325 Action group, Conflict Victims Common Platform, Development Partners, UN Agencies, representatives from the relevant department of Kathmandu University and UN Women. Who: Actors and Accountability - Reference Group What: Roles and Responsibilities - Safeguard the independence of the meta-analysis exercise and ensure quality of evaluations; - Participate in inception meeting and comment on draft meta-analysis report; - Ensure the quality of the management response and follow- up actions. Who: Actors and Accountability - Meta-Analysis Management Group What: Roles and Responsibilities - Provide relevant information to the consultant. - Provide comments and feedback on the draft meta-analysis report in consultation meeting. Who: Actors and Accountability - Country Representative, UN Women Nepal What: Roles and Responsibilities - Safeguard the independence of the meta-analysis exercise and ensure its quality. - Responsibility of approving management responses to the meta-analysis in the GATE system and ensure the follow- up actions. Who: Actors and Accountability - Unit Manager - Peace and Security & Humanitarian Action Programme What: Roles and Responsibilities - Coordinate overall process of the meta-analysis; - Provide overall guidance to the meta-analysis process to ensure the quality of the meta-analysis; - Coordinate administrative and logistics support to the consultant; - Ensure timely submission of the meta-analysis report by the consultant to the NCO; - Facilitate a management response to meta-analysis and ensure the implementation of committed actions in the management response; - Disseminate the meta-analysis findings and ensure the follow-up. Who: Actors and Accountability - The Consultant What: Roles and Responsibilities - Lead the whole meta-analysis process and produce quality deliverables in timely manner; - Effectively communicate with the NCO, reference group and other stakeholders. ETHICAL CODE OF CONDUCT: The meta-analysis shall be conducted in accordance with the principles outlined in both UNEG Norms and Standards for Evaluation in the UN System and the UNEG ‘Ethical Guidelines for Evaluation’. Evaluators are required to read the Norms and Standards and the guidelines and ensure a strict adherence to it, including establishing protocols to safeguard confidentiality of information obtained during the evaluation. The UNEG Ethical Guidelines can be found here: http://uneval.org/papersandpubs/documentdetail.jsp?doc_id=102. The UNEG Code of Conduct for Evaluation in the UN system can be found here: http://uneval.org/document/detail/100 All documents produced during the course of this meta-analysis will remain the property and copyright of UN Women.

##### Competencies

Functional Competencies: - Excellent programme formulation, implementation, monitoring and evaluation skills; - Excellent knowledge of results based management principles and approaches; - Ability to develop detailed operational plans, budgets, and deliver on the development results; - Outstanding knowledge working in post-conflict and transitioning scenarios; - Ability to lead formulation of strategies and their implementation; - Excellent networking skills.

##### Required Skills and Experience

Education - Masters or higher-level degree in social science/ research monitoring and evaluation is required, preference will be given to holders of PhD degree. Experience - A minimum of 10 years’ relevant experience undertaking evaluations is required including proven practical professional experience in designing and conducting evaluations; - Experience of conducting meta-evaluation and meta-analysis preferably with UN agencies, is an asset; - Quantitative and qualitative data analysis skills; - Proven ability to produce coherent, clear and analytic reports of high quality is a requirement; - Experience of facilitating workshops for initiating evaluation and for sharing evaluation findings; - Substantive experience in leading evaluation with a strong gender focus is preferred; - Detailed knowledge of the role of the UN and its programming is desirable; - Working experience in Nepal will be an asset. Language skills - Excellent command of written and oral English. EVALUATION AND SELECTION CRITERIA: UN Women applies a fair and transparent selection process that takes into account both the technical qualification and the financial proposals submitted in support of consultant applications. Candidate applications will be evaluated using a cumulative analysis method taking into consideration the combination of applicant qualifications and financial proposal. The contract will be awarded to the individual consultant whose offer has been evaluated and determined as: - Responsive/compliant/acceptable; and - Having received the highest score out of below defined technical/interview and financial criteria. Only candidates obtaining a minimum of 70 per cent in the technical evaluation will be considered for further evaluation process. The maximum number of points assigned to the financial proposal will be allocated to the lowest price proposal among the qualified candidates. All other price proposals receive points in inverse proportion. Technical evaluation criteria (including a minimum qualification and experience): - Masters or higher-level degree in social science/ research monitoring and evaluation is required, preference will be given to holders of PhD degree (10 points); - 10 years’ relevant experience undertaking evaluations including proven practical professional experience in designing and conducting evaluations (25 points); - Experience of conducting meta-evaluation and meta-analysis for UN Agencies (20 points); - Ability to produce coherent, clear and analytic high-quality reports- based on the writing sample (20 points); - Substantive experience in leading evaluation with a strong gender focus (15 points); - Experience of facilitating workshops for initiating evaluation and for sharing evaluation findings (10 points). Technical Evaluation – documents based/interview (70%). Financial Evaluation (30%); Evaluation of submitted financial offers will be done based on the following formula: S = F min / F * 30 - S - Score received on financial evaluation; - F min - the lowest financial offer out of all the submitted offers qualified over the technical evaluation round; - F - financial offer under the consideration. The candidate who scores highest cumulative score will be considered for the service. HOW TO APPLY? Interested individual/consultants must submit the following documents: - Cover letter; - UN P11 form (blank form can be downloaded from: http://www.unwomen.org/en/about-us/employment/) or curriculum vitae in any standard format; - A separate page of lump-sum financial proposal including consultant fee, translation/ editing and proof reading, and other relevant cost to undertake the above deliverables; - A recent (within three years) written sample with min. 3000 words where the applicant is the lead evaluator. Note: Please upload the required document as on attachment. TRAVEL AND ACCOMODATION EXPENSES: - UN Women will bear the travel and accommodations costs beyond commuting distance from the consultant’s usual place of residence for UN Women authorized travel as per the UN Women standard guidelines.

For all reports go to

http://gate.unwomen.org/EvaluationUnit/FullDetails?EvaluationUnitId=169

# ANNEX 2. Detailed scores of each Evaluation report against OECD/DAC sub criteria

| Criteria | Relevance | Effectiveness | Efficiency | Sustainability | Impact |
| --- | --- | --- | --- | --- | --- |
| Sub Criteria | 1.Respond to needs and/or priorities of target group. 2.Aligned with relevant international/national development goals, policies commitments 3.Effective partnerships for planning, coordination and implementation with governments, bilateral/ multilateral /development humanitarian partners and NGOs 4.Clear and appropriate selection criteria for locations and beneficiaries | 1.Objectives and results achieved 2. Positive benefits for target group members 3.Significant changes in development policies and programmes | 1.Activities are cost/resource efficient 2.Achieved on time 3.Efficient systems and procedures | 1.Benefits likely to continue beyond completion 2.Sustainable in terms of institutional/ community capacity 3.Government ownership at national or district level | 1.Changes in national level policy 2.Changes in lives of beneficiaries 3.Community cohesion has improved |
| SIWPSAN (MTR) | 1√2√3√4√ | 1√2√3× | 1√2√3× | 1√2√3× | 1×2√3√ |
| SIWPSAN (Final) | 1√2√3√4× | 1√2√3√ | 1√2√3× | 1√2√3√ | 1×2√3√ |
| EPST | 1√2x3√4√ | 1√2√3× | 1√×2×3× | 1√2√3× | 1×2√3√ |
| GPI-CT | 1√2√3√4√ | 1√2√3× | 1√2√3× | 1√2√3× | N/A |
| GRRSP (MTR) | 1√2√3√4√ | 1√2√3√ | 1√2√3× | NA | N/A |
| GRRSP (Final) | 1√2√3√4√ | 1√2√3√ | 1√2√3√ | 1√2√3× | 1×2√3√ |

# ANNEX 3. Analytical framework

| Project Reports | Relevance - Respond to needs and/or priorities of target group. - Aligned with relevant international/national development goals, policies commitments - Effective partnerships for planning, coordination and implementation with governments, bilateral/ multilateral /development humanitarian partners and NGOs - Clear and appropriate selection criteria for locations and beneficiaries | Effectiveness - Objectives and results achieved - Positive benefits for target group members - Significant changes in development policies and programmes | Efficiency - Activities are cost/resource efficient - Achieved on time - Efficient systems and procedures | Sustainability - Benefits likely to continue beyond completion - Sustainable in terms of institutional/ community capacity - Government ownership at national or district level | Impact - Changes in national level policies - Changes in lives of beneficiaries - Community cohesion has improved advocacy |
| --- | --- | --- | --- | --- | --- |
| Mid Term Evaluation (Jul 2015) SIWPSAN | - Working in 3 districts highly affected by conflict - Beneficiaries are those affected by and survivors of conflict & violence - Effective partnerships with govt. and CSOs - Aligned with national and international goals - Some beneficiaries not directly affected Score: 4 | - Progress on track to achieve - Capacity built among beneficiaries have - Field presence of UNW staff supports capacity development and monitoring - Need for better coordination of 10 national and local partners - Need for better clarity of roles and responsibilities Score: 2 | - Activities cost and resource efficient - Achieved on time - Added value of UNW staff in field - Good use of relevant expertise in capacity development - Need greater clarity of roles between UNW and WCO at field level Score:2 | - Increased by capacity development of DCC members and local partners - Using existing mechanisms (e.g. IPWA) to sustain gains - Not linking initiatives to existing community structures - Frequent transfer of govt. personnel Score: 2 | - Revival of IPWA at district and VDC levels - Observable changes in leadership and awareness - Enhanced social harmony - Policy change not relevant or achievable in timeframe Score:2 |
| Final Evaluation Strengthening Implementation of the Women, Peace and Security Agenda in Nepal. 2016 | - Relevant to needs - Aligned with relevant normative frameworks and GoN priorities - All recs of MTE were acted upon - Selection criteria could have been clearer in securing participation of former women combatants and survivors of VAW Dalits, Janajati/Tharu and those from remote locations - Greater rep of Chhetri women than their presence in population - Did not appear to consider causes of discrimination e.g. age, disability, language Score: 3 | - All 3 outcomes achieved, including - Economic and social empowerment of women - Appropriate guidelines developed Score: 3 | - Resources strategically allocated to outcomes and transparently managed - Consistency between inputs and results - Delays in budget delivery and insufficient cost saving mechanisms Score: 2 | - Capacity built among MoWCSW (central) and local WCOs, DCCs and IPWGs - NAP (and budget allocation) implemented at national, district and village level plans - Continued (after phasing out) media interest in relevant social issues - Capacity built (e.g. among entrepreneurs) may not be sufficient to ensure sustainability - Need for further scaling up and replication to widen VDC coverage and include excluded groups Score: 3 | - Capacity built among govt institutions and other stakeholders to implement NAP - CSO and local govt stakeholders collaborating - CAW, IPWN and former women combatants assuming leadership positions in local organisations - Improved economic status of some CAW and former women combatants - No evidence of national policy change Score: 2 |
| Final Evaluation Ensuring Participatory and secure transition (2015) | - Highly relevant to national peace efforts - Strengthened relevance through addressing several related issues??? - Highly relevant to needs of beneficiaries in most affected locations but they were not involved in design ? no explicit reference to national and global policy commitments Score: | - Satisfactory achievement at output and outcome levels - Positive benefits in terms of capacity development and enhanced community security - Capacity built among national and district level govt. Score: 3 | - Activities completed on time - Lack of consolidated monitoring and reporting system - Creating parallel structures Score: 1 | - Dialogue increasingly seen as suitable method of conflict resolution and reflected in documented examples - Improved relations between community and police - NAP and GRB are structural changes are addressing women’s equality and inclusion Score: 2 | - Exit strategy developed - Several VDCs have allocated budget for community security planning - Sustainability not discussed fully with local stakeholders - Variable degrees of local and national ownership Score: 2 |
| Final Localizing the women peace and security agenda in the central Terai districts of Nepal (Jan 2015-Oct 2016) | - Aligned with normative frameworks on gender, human rights, etc. - Implementation of NAP on women, peace & security - Aligned with Gov. 14 step planning process on women, peace and security - Relevant to beneficiaries needs and geographical concentrations - District level stakeholders and beneficiaries not involved in design Score:4 | - Partial achievement of outcome indicators: - functional GRBC in DDCs and MCs - Capacity built among members and others in GRB planning and lobbying - Meaningful participation in planning and budgeting - Unable to measure adoption of GRB as software not used in current year or monitoring reports not yet completed - Community security plan is gender sensitive and inclusive but implementation slow and allocated budget used for other purposes (contradicted by perception survey) - While participation has increased in Bara district, in Parsa women not participating or included in MC and DDC councils Score: 2 | - Activities deemed cost efficient and made use of local resources - Strategic allocation of resources - UNDP/UN Women collaboration beneficial - Timeliness unclear Score: 2 | - Capacities built - Mechanism established - GRB principles to be followed in planning and budgeting from 2017/18 - Partial ownership Score: 2 | N/A |
| Mid-term Evaluation Gender Responsive Recovery for Sustainable Peace (GRSSP). Dec 2014 | - Responsive to beneficiaries prioritised needs - Ethically and technically sound and aligned with national policy - Targeting of beneficiaries appropriate - However most needy missed out on economic recovery - Psychosocial counselling needs to be of longer duration - Need to expand inclusion of beneficiaries beyond those who participated in baseline Score: 3 | - Some outputs achieved in full others in part (output level results 71.2% and outcome level 43.4%) Beneficiaries have access to psychosocial support and economic empowerment - Project capitalised on partners comparative advantages - Stakeholders gender sensitised - Govt officials have begun resourcing gender responsive initiatives Score: 3 | - Activities are considered cost/resource efficient - Cost saving mechanisms used (sharing financial, human and physical resources internally and from other projects) - No written MoUs between partners - Limited updating of incoming DCC and LPC members - Training materials too advanced for users - Timeliness not reported Score: 2 | N/A | N/A |
| Final Evaluation Gender Responsive Recovery for Sustainable Peace (GRSSP). May 2015 | - Appropriate mix of interventions, locations and beneficiaries - Aligned with relevant national policy and plans Score 3: | - Effective partnership by three UN agencies - Local resource use and cost sharing contribute to sense of ownership by women - Capacity development implemented prior to locally relevant technical training Score: 3 | - Cost sharing and savings among 3 UN agencies - Use of open call for proposals and bidding process - Playing to comparative strengths of local organisations and partners - Collective monitoring by the 3 UN agencies - On time Score: 3 | - Successfully promoting cooperation and collaboration between groups of beneficiaries (including former enemies) - Increased self-confidence among beneficiaries - Increased economic opportunities for beneficiaries through training and support - Relatively short implementation time may be insufficient to ensure sustainability without provision of additional support Score:2 | - With few exceptions, project partners are already established in project locales and will continue to work - Some savings groups will continue beyond the end of the project - Registration of local groups has created a potentially lasting link between local people and government service providers (esp. since this entitles them to certain financial benefits) - Economic advantages provided to women through training are potentially sustainable Score:2 |

Strong= meets all criteria (3), Moderate=meets 2 (2), Weak =meets 0-1 (1)

Criteria and sub-criteria

1. Relevance

1.1 Programmes and projects are suited to the needs and/or priorities of the target group.

1.2 Projects aligned with relevant international/national development goals, policies and commitments: national ownership

1.3 Effective partnerships exist with governments, bilateral and multilateral development and humanitarian organisations, and

non-governmental organisations for planning, coordination and implementation of support to advance GEEW

1.4 Extent the interventions have applied appropriate basis for selecting (a) programme beneficiaries, (b)implementing regions

2. Effectiveness

2.1 Projects achieved their stated objectives and attain expected results

2.2 Projects resulted in positive benefits for target group members: capacity development, inclusiveness

2.3 Projects contributed to significant changes in development policies and programmes knowledge management

3. Efficiency

3.1 Project activities evaluated as cost/resource efficient.

3.2 Activities achieved on time (given the context).

3.3 Systems and procedures efficient (including financial/human resource management, partnerships and co-ordination).

4 Sustainability of results/benefits

4.1 Benefits judged likely to continue after project or programme completion.

4.2 Projects reported as sustainable in terms of institutional and/or community capacity.

4.3 Government ownership at national or district level

5. Impact

5.1 Policies changed as a result of the project at national level

5.2 Beneficiaries lives changed as a result of the project

5.3 Community cohesion has improved advocacy

6. Gender Equality

6.1 Enhanced participation of women in decision making: inclusiveness & intersectionality

6.2 Empowerment of women economically/socially

6.3 Gender Equality addressed through transformative interventions

asiapacific.unwomen.org/en/countries/nepal/about-un-women-nepal

asiapacific.unwomen.org/en/countries/nepal/about-un-women-nepal

UNSCR 1325 affirms the importance of the participation of women and inclusion of gender perspectives in peacebuilding, peace keeping operations, post conflict peacebuilding and governance and humanitarian planning. UN resolution 1820 recognizes sexual violence as a tactic of war and a matter of international peace and security that necessitates a security response.

The Madhesh movement and blockade delayed some project activities in the Terai