TERMS of REFERENCE

UN Women Paraguay Country Portfolio Evaluation

# I. Background

The Country Office (CO) Strategic Note (SN) is the main planning tool for UN Women’s support to normative, coordination and operational work in Paraguay. The CO has been operational in Paraguay since 2013. Before this, it was preceded by UNIFEM Programme Office, dependent of the Sub-regional Office for Brazil and Southern Cone. This evaluation will consider the Strategic Note covering the period 2015-2019. A new Strategic Note is due to be developed starting in July 2019 for the period 2020-2024.

The Strategic Note is linked to the UN Women Global Strategic Plan 2014-2017, aligned to the recently approved UN Women Global Strategic Plan 2018-2021, the III National Plan for Equal Opportunities between Women and Men 2008-2017 and the Paraguay UNDAF 2015-2019. The CO Strategic Note supports the following Goals contained in UN Women’s Strategic Plan 2014-2017: - SG1: Women’s leadership and political participation - SG2: Women’s economic empowerment - SG3: Ending violence against women - SG5: Mainstreaming gender in national governance systems

The Strategic Note is aligned with the results of the UNDAF, specifically the following 3 development effects:

UNDAF Result 1.1: Paraguay will have progressed in the protection and guarantee of rights for all people, especially on those groups who are discriminated and excluded. UNDAF Result 1.3: Paraguay will have advanced in the empowerment of women and their effective participation in public life and in politics. UNDAF Result 2.1: Paraguay will have significantly reduced the level of poverty, will established decent work and will guarantee the improvement of income for the working population and discriminated and excluded groups. The Strategic Note is grounded in the standards, principles and obligations of the Convention to Eliminate All Forms of Discrimination Against Women (CEDAW), Beijing Declaration and Platform for Action, Concluding Observations of the Commission on the Status of Women, Security Council Resolution 1325, and Sustainable Development Goals. The description of the country context, including economic context and inequity between social groups is the following: • Government: Representative Democratic Republic. • Total population: 6.775.786. • MIC with sustained growth rates, second most unequal country in the region (GINI coefficient 0,48 - 2016). • GDP: USD 24.8 billion (2016), GDP per capita: USD 4,077.7 (2016). • Poverty: 28.8 per cent of inhabitants (1.949.272 people) live in poverty, and 5.7 per cent (387.242 people) live in extreme poverty. • Paraguay’s rural and indigenous population is most affected by both poverty and extreme poverty: poverty 39,7% and extreme poverty 12,1%. • Country of young people (over 60% in working-ages 15 to 64). • Birth-rates and high levels of teenage pregnancy (20% of all pregnancies with highest figures between ages 10 and 14). • High rates of feminicide: 49 women murdered in 2017 in a small country. • Tax system: Paraguay collects 57% through indirect taxes and has a limited application of personal income tax (0.5% of taxpayers). In response to the economic and social challenges faced by the country, the government prepared the first 2030 National Development Plan (NDP) around three pillars: Poverty reduction and social development, Inclusive economic growth and Inclusion of Paraguay in global markets. The Government linked the NDP with the SDGs for the implementation of the 2030 Agenda. The Presidential elections and General elections that took place in April 2018 increases important institutional changes with a new government that will take office on 15 August 2018. Paraguay, is a MIC with limited resource mobilization opportunities. The country largely stopped receiving resources from traditional donors. This situation equally affects other United Nations agencies while government itself does not contribute to UN funding in country. Moreover, Paraguay remains as a non-priority country of gender equality focused aid in the region and globally and the country does not possess a large private sector with most national and multinational companies offering in-kind contributions rather than financial resources.

The situation of women in Paraguay can be described as follows:

While legal and normative contexts for women's rights and gender equality have improved in recent years, high gender gaps remain in all areas and the implementation of legal and policy measures is slow and under-resourced. In addition, gender stereotypes and social norms constitute serious bottlenecks to women and girls' empowerment and rights in public and private spheres. The cultures of "machismo" and violence/discrimination against women and girls remain widespread. In terms of indicators, the following are the most important: # Women are under-represented in decision making in all spheres of development: Paraguay remains one of the three Latin-American countries with the lowest female political representation (16.8% in Congress; 16.6% in the Executive; 10% of Mayors and 20% of City Councillors). After the General Elections of April 2018, the electoral mission of the OAS and EU reiterates their concern over the law level of female representation in the legislative bodies, a situation generated in part due to deficient quota legislation. The Missions recommended the approval of the Parity Bill, currently being debated in the Congress, as an important possibility of improvement in the conditions of equality in elections and in access to representation for women. # Persistent gaps between men and women in the economic sector: Female headed households represent a total of 30% of all HHs and their poverty level reaches 38.3%; rural and indigenous women remain the face of extreme poverty in the country, occupied in small scale agriculture with no labour rights or social protection, low access and control of resources (13 % of land), credit and assets. In the formal economy, women’s salaries are 77.8% of men’s yet women`s employment remains concentrated in domestic work where the legal minimum wage is 60% of the minimum wage in other sectors. # Violence against women: The Comprehensive Law to protect women against all forms of violence came into force in December 2017. The new normative introduces for the first time the penal figure of feminicide among other advances in legislation. The situation of physical, psychological and sexual violence suffered by indigenous women puts women and girls in a particular scenario of vulnerability to HIV, particularly in areas like Boquerón, one of the poorest departments in the country, with the second highest indigenous population (21.2 per cent), where the incidence of HIV is 29.7 new cases per 100,000 inhabitants, much higher than the national or Chaco region rates.

# II. Description of the programme

The total planned budget of the Strategic Note 2015-2019 was USD 5.367.291. As of 2018, the total resources mobilized were USD 724,260. UN Women undertakes interventions across its three mandate areas: - Normative work: to support inter-governmental bodies, such as the Commission on the Status of Women (CSW) and the General Assembly, in their formulation of policies, global standards and norms; - Operational work: to help Member States to implement international standards and to forge effective partnerships with civil society; and - Coordination work: entails both work to promote the accountability of the United Nations system on gender equality and empowerment of women (GEEW), including regular monitoring of system-wide progress, and more broadly mobilizing and convening key stakeholders to ensure greater coherence and gender mainstreaming across the UN.

The main interventions undertaken under the Strategic Note are: Normative; Coordination; National programmes; Regional programmes; Global programmes. Political and technical assistance for the design of the Law on Integral Protection for Women against all forms of violence (Law No. 5777/16); UN Women CO is a member of Paraguay´s UNCT and leads the UN Gender Focal Points (GTG); Campaign to eradicate the violence against women; International colloquium: To govern the land in equality, within the framework of the regional initiative “Women’s access to land: economic autonomy, equal rights and food security“ with FAO/Regional inter-agency work plan being implemented with FAO, UNDP, IOM and WFP.; Global Action Programme on Migrant Domestic Workers and their Families. Technical assistance and advocacy for the approval of the Law 5407/15 for domestic workers; Boosted strategic actions to raise people’s awareness about VAW, in the framework of the UNITE’s Campaign; Strengthening capacities of political women, civil society advocates, among others.. Political and technical assistance for the design and approval of the Parity Bill.; Production of sex-disaggregated data and gender analysis on women´s situation (including the first time use survey) and to monitor the National Development Plan and Sustainable Development Goals with the General Directorate of Statistics, Surveys and Censuses (DGEEC).. Inclusion of gender indicators in public-private suppliers contracting with UN WOMEN`s technical support..; Fostered coordination to the creation of a national working group for the design of a National Care Policy.. Assistance for the establishment of the Democratic Parity Group for the approval of the Parity Bill.; Incorporated the gender perspective into the Tenondera program. Also approved by Resolution No. 1074/2017 its own manual to address violence against women from SAS programs..

A draft stakeholder analysis has been undertaken by the CO. This is expected to be reviewed and updated by the evaluator as part of the inception phase.

In line with UN Women’s commitment to Results Based Management, a Development Results Framework (DRF) was developed with performance indicators. This includes basic assumptions, but a full theory of change will need to be reconstructed by the evaluation team through a participatory process.

The Strategic Note also includes an Organisational Effectiveness and Efficiency Framework (OEEF) with performance indicators. The evaluation is expected to use this to assess organizational performance. The Country Office is based in Asuncion, Paraguay with a total of 9 people working.

# III. Purpose (and use of the evaluation)

The work of UN Women is framed by the Convention on the Elimination of All Forms of Discrimination Against Women (CEDAW), which is often called the “international bill of women’s rights”, and the Beijing Platform for Action, which sets forth governments’ commitments to enhance women’s rights. The spirit of these agreements has been affirmed by the Sustainable Development Goals; UN Security Council resolutions on women, peace and security and on sexual violence in conflict; Economic and Social Council agreed conclusions 1997/2 and resolution 2011/5; and the UN System Chief Executives Board for Coordination policy on gender equality and women’s empowerment and its corresponding system-wide action plan.

Evaluation in UN Women is guided by these normative agreements to be gender-responsive and utilizes the entity’s strategic plan as a starting point for identifying the expected outcomes and impacts of its work and for measuring progress towards the achievement of results. The UN Women Evaluation Policy and the UN Women Global Evaluation Strategy 2018-2021 are the main guiding documents that set forth the principles and organizational framework for evaluation planning, conduct and follow-up in UN Women. These principles are aligned with the United Nations Evaluation Group (UNEG) Norms for Evaluation in the UN System, Standards for Evaluation in the UN System and Ethical Guidelines. The key principles for gender-responsive evaluation at UN Women are: - National ownership and leadership; - UN system coordination and coherence with regard to gender equality and the empowerment of women; - Innovation; - Fair power relations and empowerment; - Participation and inclusion; - Independence and impartiality; - Transparency; - Quality and credibility; - Intentionality and use of evaluation; - Ethics.

A Country Portfolio Evaluation (CPE) is a systematic assessment of the contributions made by UN Women to development results with respect to gender equality at the country level. The UN Women portfolio is a set of interventions that includes normative, operational and coordination work. The CPE focuses on their individual and combined success in advancing gender equality in Paraguay. It uses the Strategic Note as the main point of reference. This CPE has been primarily commissioned by the Country Office (CO) as a formative (forward-looking) evaluation to support the CO and national stakeholders’ strategic learning and decision-making for the next Strategic Note, due to be developed in July 2019. The evaluation is expected to have a secondary summative (backwards looking) perspective, to support enhanced accountability for development effectiveness and learning from experience. It is a priority for UN Women that the CPE will be gender-responsive, and will actively support the achievement of gender equality and women’s empowerment.

The primary intended users of this evaluation are: - UN Women Paraguay CO, UN Women ACRO and other internal UN Women stakeholders - Target groups, their households and community members programme/project partners - National government institutions - Civil society representatives - Donors and development partners - UN Country Team

The primary intended uses of this evaluation are: - Learning and improved decision-making to support the development of the next Strategic Note 2019-2024; - Accountability for the development effectiveness of the CO Strategic Note 2015-2019 in terms of UN Women’s contribution to gender equality and women’s empowerment; - Capacity development and mobilisation of national stakeholders to advance gender equality and the empowerment of women.

# IV. Objectives (evaluation criteria and key questions)

The evaluation has specific objectives: - Assess the relevance of UN Women contribution to the intervention at national level and alignment with international agreements and conventions on gender equality and women’s empowerment. - Assess effectiveness and organizational efficiency in progressing towards the achievement of gender equality and women’s empowerment results as defined in the Strategic Note. - Enable the UN Women Paraguay CO to improve its strategic positioning to better support the achievement of sustained gender equality and women’s empowerment. - Analyse how human rights approach and gender equality principles are integrated in the design and implementation of the Strategic Note. - Identify and validate lessons learned, good practices and examples of innovation that supports gender equality and human rights. - Provide insights into the extent to which the UN Women CO has realized synergies between its three mandates (normative, coordination and operational). - Provide actionable recommendations with respect to the development of the next UN Women Paraguay CO Strategic Note 2019-2024.

The evaluation will apply four OECD/DAC evaluation criteria (relevance, effectiveness, efficiency, and sustainability) and 11 sub-criteria. Human Rights and Gender Equality is mainstreamed as a sub-criterion. The evaluation will not consider impact (as defined by UNEG) as it is considered too premature to assess this. The evaluation will seek to answer the following key evaluation questions and sub-questions: Key Criteria; Key Questions; Sub Criteria; Sub Questions. Relevance; Are we doing the right things?; Alignment; Is the portfolio aligned with national policies and international human rights norms?. Human Rights and Gender Equality; Is the choice of partners most relevant to the situation of women and marginalised groups? Is the choice of interventions most relevant to the situation in the target thematic areas? Do interventions target the underlying causes of gender inequality?. Efficiency; Are we doing things right?; Organizational Efficiency; To what extent does the UN Women CO management structure support efficiency for implementation? Does the organisation have access to the necessary skills, knowledge and capacities needed to deliver to portfolio? Has a Results Based Management system been established and implemented?. Coherence; Are the interventions achieving synergies within the UN Women portfolio and the work of the UN Country Team? Is the balance and coherence between programming-operational, coordination and policy-normative work optimal? What is UN Women’s comparative advantage in this area of work compared with other UN entities and key partners?. Human Rights and Gender Equality; Which groups is the portfolio reaching the most, and which are being excluded?. Effectiveness; Are the things we are doing working?; Achievements; To what extent have planned outputs been achieved on time? Are interventions contributing to the expected outcomes? For who? What unexpected outcomes (positive and negative) have been achieved? For who? What has been UN Women’s contribution to the progress of the achievement of outcomes? What are the main enabling and hindering factors to achieving planned outcomes?. Human Rights and Gender Equality; Is the portfolio addressing the root causes of gender inequality? To what extent is the portfolio changing the dynamics of power in relationships between different groups? Has the portfolio been implemented according to human rights and development effectiveness principles: - Participation/empowerment - Inclusion/non-discrimination - National accountability/transparency. UN Coordination; What contribution is UN Women making to UN coordination on GEEW in Paraguay? Which roles is UN Women playing in this field? To what extent has gender equality and women’s empowerment been mainstreamed in UN joint programming such as UNDAF?. Normative; To what extent have lessons learned been shared with or informed global normative work and other country offices? What contribution is UN Women making to implementing global norms and standards for gender equality and the empowerment of women in Paraguay?. Sustainability; Will the changes last?; Capacity development; To what extent was capacity developed in order to ensure sustainability of efforts and benefits?. Ownership; Is there national ownership and are there national champions for different parts of the portfolio? What local accountability and oversight systems have been established to support the sustainability of activities?.

The evaluation is expected to take a gender-responsive approach. Gender-responsive evaluations use a systematic approach to examining factors related to gender that assesses and promotes gender equality issues and provides an analysis of the structures of political and social control that create gender equality. This technique ensures that the data collected is analysed in the following ways: - Determining the claims of rights holders and obligations of duty bearers - Assessing the extent to which the intervention was guided by the relevant international (national and regional) normative frameworks for gender equality and women’s rights, UN system-wide mandates and organizational objectives - Comparing with existing information on the situation of human rights and gender equality in the community, country, etc. - Identifying trends, common responses and differences between groups of stakeholders (disaggregation of data), for example, through the use of graphs or illustrative quotes (that do not allow for identification of the individual) - Integrating into the analysis the context, relationships, power dynamics, etc. - Analysing the structures that contribute to inequalities experienced by women, men, girls and boys, especially those experiencing multiple forms of exclusion - Assessing the extent to which participation and inclusiveness (with respect to rights holders and duty bearers) was maximized in the interventions planning, design, implementation and decision-making processes - Triangulating information to identify similarities and/or discrepancies in data obtained in different ways (i.e., interviews, focus groups, observations, etc.) and from different stakeholders (e.g., duty bearers, rights holders, etc.) - Identifying the context behind the numbers and people (using case studies to illustrate broader findings or to go into more depth on an issue) - Comparing the results obtained with the original plan (e.g., through the application of the evaluation matrix) - Assessing the extent to which sustainability was built into the intervention through the empowerment and capacity building of women and groups of rights holders and duty bearers The preliminary findings obtained through this process should be validated through a stakeholder workshop with evaluation management and reference groups towards the end of the field mission.

# V. Scope of the evaluation

The timing of this Country Portfolio Evaluation is intended to assess the effectiveness and lessons learned as we approach the end of the current Strategic Note. The period covered by the evaluation will be 2015-mid 2018. The CPE will focus on all activities undertaken by the CO under the Strategic Note, including general support to normative policy and UN coordination. Programme work will be considered based on the thematic areas established by the UN Women Strategic Plan 2014-2017.

The evaluator is expected to establish the boundaries for the evaluation, especially in terms of which stakeholders and relationships will be included or excluded from the evaluation. These will need to be clearly described and justified during the Inception Phase. UN Women organisational structures and systems outside of the CO (such as regional architecture) are not within the scope of this evaluation, and should be referenced only where there is a clear implication for the design and implement of the CO Strategic Note.

The evaluation is expected to consider the main cultural, religious, social and economic differences between the different regions/ provinces covered by the evaluation when analysing the contributions of UN Women.

The evaluator is expected to undertake a rapid evaluability assessment at the inception stage. This should include the following: - An assessment of the relevance, appropriateness and coherence of the implicit or explicit theory of change, strengthening or reconstructing it where necessary; - An assessment of the quality of performance indicators in the DRF and OEEF, and the accessibility and adequacy of relevant documents and secondary data; - A review of the conduciveness of the context for the evaluation; - Ensuring familiarity with accountability and management structures for the evaluation.

The evaluation is expected to face the following logistics constraints: - Budget and time constraints. - The Presidential elections and General elections that took place in April 2018 increases important institutional changes with a new government that will take office on 15 August 2018. Some institutions of the Executive Branch could already have movements and new officials could not know about UNW programme. Where these constraints create limitations in the data that can be collected, these limitations should be understood and generalizing findings should be avoided. In addition, cultural aspects that could impact the collection of data should be analysed and integrated into data collection methods and tools. The evaluator is expected to include adequate time for testing data collection tools.

# VI. Evaluation design (process and methods)

The evaluation will use a theory-based design. The performance of the country portfolio will be assessed according to the theory of change stated in the Strategic Note 2015-2019. To achieve sufficient depth, the evaluation will analyze programming, coordination, and normative activities of the Country Office around the thematic areas stated in the UN Women Strategic Plan 2014-2017. The evaluation will undertake a portfolio analysis that includes a synthesis of secondary results data for the Development Results Framework (DRF) and the Organizational Effectiveness and Efficiency Framework (OEEF) of the Country Office. This will cover all activities undertaken by the Country Office. The portfolio analysis will be triangulated through a mixed methods approach that will include: - Desk review of additional documentary evidence; - Consultation with all main stakeholder groups; and - An independent assessment of development effectiveness.

The method should include a wide range of data sources (including documents, field information, institutional information systems, financial records, beneficiaries, staff, funders, experts, government officials and community groups). The evaluation is particularly encouraged to use participatory methods to ensure that all stakeholders are consulted as part of the evaluation process. At a minimum, this should include participatory tools for consultation with stakeholder groups and the inclusion of women and individuals and groups who are vulnerable and/or discriminated against in the consultation process. The consultant should guarantee the protection of participants and respect for confidentiality.

The evaluation is encouraged to use the following data collection tools: - Interviews - Focus Groups - Secondary document analysis - Survey - Observation - Multimedia (video, photography, drawing) The evaluator should take measures to ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights.

The evaluation is expected to reconstruct the theory of change using a participatory process during the inception stage. This should be analyzed based on feminist and institutional analysis.

The evaluation will apply Contribution Analysis to assess the effectiveness of UN Women’s country portfolio. The evaluation will also include a basic analysis of risk in the country portfolio. Given the small size of the portfolio, the evaluation is expected to cover interventions in all thematic areas in addition to UN coordination and normative work.

# VII. Stakeholder participation

The consultant is expected to discuss during the inception phase how the evaluation will ensure participation of stakeholders at all stages, with a particular emphasis on rights holders and their representatives.

Stakeholders should include: - Target groups, their households and community members; - Programme and project partners; - National government institutions; - Internal UN Women stakeholders; - Civil society representatives; - Political leaders and representatives - Private sector and trade unions representatives; - Donors and development partners; - UN Country Team.

The consultant is encouraged to extend this analysis through mapping relationships and power dynamics as part of the evaluation. It is important to pay particular attention to participation of rights holders—in particular women and vulnerable and marginalized groups—to ensure the application of a gender-responsive approach. It is also important to specify ethical safeguards that will be employed.

The evaluator is expected to validate findings through engagement with stakeholders at stakeholder workshops, debriefings or other forms of engagement.

# VIII. Time frame

The evaluation is expected to be conducted according to the following time frame, with the Inception Phase commencing in July. The estimated number of person-days required for the evaluation is 40 Task; Time frame; Responsible party. Inception phase (desk review to prepare for evaluation); 15 days (post contract signing); Evaluator. Inception Workshop and preparation of Aide Memoire; 2 days; Evaluator, task manager and UN Women staff. Data collection stage (field mission); 5 days; Evaluator. Reporting stage (analysis and presentation of draft Final Report); 12 days (post final data collection); Evaluator. Evaluation Reference Group feedback to draft Final Report; 5 days; UN Women evaluation reference group. Findings validation and participatory recommendations workshop; 1 day; Evaluator, task manager and UN Women staff. Presentation of Final Report; 5 days; Evaluator. TOTAL (Evaluator); 40 days.

The evaluator is expected to design and facilitate the following events: - Participatory inception workshop (including refining the evaluation framework, stakeholder map, and theory of change); - In-country entry and exit briefs for UN Women staff and key stakeholders; - Findings validation and participatory recommendations workshop.

# IX. Expected deliverables

This section describes the type of products (reports, briefs or other) that are expected from the evaluation, who will use them and how they will be used. Deliverable; Time frame for submission; Person responsible; Payment schedule. Work plan (Word format) in Spanish.; 5 days (post contract signing); Evaluator; 20%. Inception Aide Memoire (Word format) in Spanish.; During Field Mission; Evaluator (task manager and RES feedback); 20%. Draft Final report (Word format) (including 2 rounds of revision) in Spanish.; 2 weeks after field mission; Evaluator (reference group feedback); 30%. Final report (PDF/Word formats) in Spanish.; 1 week once consolidated inputs are received; Evaluator; 30%. Management Response; Within 6 weeks once the report is cleared; CO Representative- Evaluation task manager; N/A. Development of knowledge products.; Within 8 weeks once the once the report is cleared; CO Representative- Evaluation task manager – Communication Associate; N/A.

A model Final Evaluation Report will be provided to the evaluator based on the following outline. The evaluation task manager and the Regional Evaluation Specialist will quality assure the evaluation report. The draft and final evaluation report will be shared with the evaluation reference group for quality review. The final report will be approved by the Evaluation Management Group. 1) Title and opening pages 2) Executive summary 3) Background and purpose of the evaluation 4) Programme/object of evaluation description and context 5) Evaluation objectives and scope 6) Evaluation methodology and limitations 7) Findings: relevance, effectiveness (normative, coordination, operational), efficiency, sustainability, and gender and human rights 8) Conclusions 9) Recommendations 10) Lessons learned ANNEXES: • Terms of Reference • Documents consulted • Lists of institutions interviewed or consulted and sites visited (without direct reference to individuals) • Analytical results and methodology related documentation, such as evaluation matrix • List of findings and recommendations

# X. Management of the evaluation

This evaluation will have the following management structures: - UN Women Evaluation Task Manager for coordination and day-to-day management; - Evaluation Management Group for decision-making: Country Representative, Evaluation Task Manager, Regional Evaluation Specialist - Evaluation Reference Group for substantive technical support: UN Women programme staff, National government partners, Development partners/donors, UNCT representatives, Civil Society Advisory Group.

The main roles and responsibility for the management of the evaluation are: Evaluator; - To avoid conflict of interest and undue pressure, the evaluator need to be independent, implying that he/she must not have been directly responsible for the design, or overall management of the subject of the evaluation, nor expect to be in the near future. - Evaluator must have no vested interest and must have the full freedom to conduct the evaluative work impartially. He/she must be able to express his/her opinion in a free manner. - The evaluator prepares all evaluation reports, which should reflect an agreed- upon approach and design for the evaluation from the perspective of the evaluator, the evaluation manager and RES.. Evaluation manager (supported by the Regional Evaluation Specialist); - Conducts a preliminary assessment of the quality of reports and comments for action by the evaluator - Provides substantive comments on the conceptual and methodological approach and other aspects of the evaluation design - Manages logistics for the field mission - Initiates timely payment of the evaluator - Coordinates feedback on the draft and final report from the evaluation management and reference groups - Maintains an audit trail of comments on the evaluation products so that there is transparency in how the evaluator is responding to the comments. Evaluation management and reference groups; - Provide substantive comments and other operational assistance throughout the preparation of reports. - Where appropriate, participates in meetings and workshops with other key partners and stakeholders before finalization of reports..

# XI. Evaluator skills and experiences

UN Women are seeking to appoint a qualified national/regional consultant to undertake the evaluation.

The evaluator is expected to be able to demonstrate evidence of the following capabilities: - At least five (5) years of experience in conducting evaluations, desirable experience in conducting gender-responsive evaluation. - Extensive knowledge of, and experience in applying, qualitative and quantitative evaluation methods. - Proven experience in gender analysis and human-rights based approaches. - Data analysis skills - Excellent ability to communicate with stakeholders - Technical competence in the thematic areas to be evaluated - Process management skills, including facilitation and communication skills - Knowledge of the role of UN Women and its programming, coordination and normative roles at the regional and country level - Proficiency in Spanish and working knowledge of English - Desirable working experience and proven knowledge of the context in Paraguay.

# XII. UN Core values and competencies

Core Values: * Respect for Diversity * Integrity * Professionalism Core Competencies: * Awareness and Sensitivity Regarding Gender Issues * Accountability * Creative Problem Solving * Effective Communication * Inclusive Collaboration * Stakeholder Engagement * Leading by Example

# Application process

# All applications must include only one attachment that consists in an updated CV/UNDP P11 (Personal History) duly signed and economic offer in accordance with the indicated products. Applications without complete and duly signed P11 will not be considered for evaluation and will be treated as incomplete. The P11 form can be found at the following link: http://www.unwomen.org/en/about-us/employment.

Only the candidates selected for the short list will be contacted. Applications received after the deadline will not be considered.

UNDP and UN Women are committed to achieving workforce diversity in terms of gender, nationality and culture. Individuals from minority groups, indigenous groups and persons with disabilities are equally encouraged to apply. All applications will be treated with the strictest confidence.

If you are experiencing difficulties with online job applications, please contact jobs.help@undp.org

# Annex 1 UNEG Quality Checklist for evaluation reports and

http://uneval.org/document/detail/607

# Annex 2 UN-SWAP Evaluation technical note and Scorecard

http://uneval.org/document/detail/1452

# Annex 3 UNEG Ethical Guidelines

http://uneval.org/document/detail/102

# Annex 4 UNEG Code of Conduct for Evaluation in the UN system

http://uneval.org/document/detail/100

# Annex 5 UNEG Norms and Standards for evaluation

http://uneval.org/document/detail/21

http://uneval.org/document/detail/22

# Annex 6 UN Women Evaluation Handbook

http://genderevaluation.unwomen.org/en/evaluation-handbook

General Directorate of Statistics, Surveys and Censuses - DGEEC, National Integrated Household Survey (Encuesta Permanente de Hogares), 2016.

General Directorate of Statistics, Surveys and Censuses - DGEEC, National Integrated Household Survey (Encuesta Permanente de Hogares), 2016.

World Bank national accounts data, and OECD National Accounts data files, 2016.

General Directorate of Statistics, Surveys and Censuses - DGEEC, National Integrated Household Survey (Encuesta Permanente de Hogares), 2016.

General Directorate of Statistics, Surveys and Censuses - DGEEC, National Integrated Household Survey (Encuesta Permanente de Hogares), 2016.

General Directorate of Statistics, Surveys and Censuses – DGEEC, Aprovechar ahora la juventud: un análisis del bono demográfico del Paraguay. Período 2000 – 2025, 2016.

: National Demographic Survey, Sexual and Reproductive Health (ENDSSR 2008), CEPEP and official data from the Ministry of Public Health (MSPyBS).

Ministry of Women with support of the Public Ministry, January 2018.

World Bank national accounts data, 2017.

Superior Court of Electoral Justice (TSJE), 2017.

General Directorate of Statistics, Surveys and Censuses - DGEEC, National Integrated Household Survey (Encuesta Permanente de Hogares), 2016.

Kuña ha yvy · Desigualdades de género en el acceso a la tierra en Paraguay, UN Women Paraguay – Oxfam in Paraguay, July 2017.

General Directorate of Statistics, Surveys and Censuses - DGEEC, National Integrated Household Survey (Encuesta Permanente de Hogares), 2015.

Ministry of Health (MSPBS)/ General Directorate of Strategic Information on Health (DIGIES). Health Basic Indicators. Paraguay 2015.

UN Security Council resolutions on women, peace and security and on sexual violence in conflict include: 1325 (2000), and 1820 (2008), 1888 (2009), 1889 (2009), 1960 (2010), 2106 (2013), and 2122 (2013);

UNEG, “Norms for evaluation in the UN system”, 2005, available online at: http://www.unevaluation.org/document/detail/21, and “Standards for evaluation in the UN system”, 2005, available online at: http://www.unevaluation.org/document/detail/22

UNEG, “Ethical guidelines”, 2008, available online at: http://www.unevaluation.org/document/detail/102

A theory based-design assesses the performance of the Strategic Note based upon its stated assumptions about how change happens. These assumptions can be challenged, validated or expanded upon by the evaluation.

The regional evaluation specialist participates in the country visit including data collection in an active advisory and quality assurance role, ensuring that learning stays within the organization.