# Corporate Thematic Evaluation of

# UN Women’s Contribution to Humanitarian Action

# Report - Annexes (Unedited)

# 11 July 2019

External Evaluation Team – DARA:

Angélica Arbulú (Co-Team Leader)

Silvia Hidalgo (Co-Team Leader)

Dorian LaGuardia (Senior Evaluator)

Alesia O’Connor (Team Member)

Ana Rodriguez (Team Member)

Table of Annexes

1.	Terms of Reference	3

2.	Inception Phase Report	4

3.	HACRO Organigram	5

4.	Analytical Framework	6

5.	Evaluation Questions	20

6.	Demographic Information of Evaluation Respondents	23

7.	Demographic Data of Focus Group Discussions	31

8.	Stakeholder analysis.	32

9.	Evaluation Survey Results & Protocol	35

10.	Semi-structured Interview Protocol	40

11.	Self-Assessment Protocol	47

12.	Portfolio Review- High level findings	55

13.	Enabling and limiting factors (internal and external) that contribute to the achievement of results.	61

14.	Partnership Attributes & Enabling Factors	63

15.	List of knowledge products produced by UN Women	65

16.	Revised Theory of Change	66

17.	Bibliography	72

## Terms of Reference

Find the evaluation Terms of Reference clicking on the icon below.

## Inception Phase Report

Find the Evaluation Inception Report clicking here.

## HACRO Organigram

## Analytical Framework

| Evaluation Questions | Evaluation sub-questions | Evaluation Level | Indicators | Analytical Strength/ Process | Cohorts | Data Sources | Analytical Tools/ Approaches | Constrain-ts/ Depend-encies |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Is UN Women's work relevant to gender responsive humanitarian action including DRR? |  | Relevance | Evidence that UN Women is contributing to: - gender analysis of the crisis conducted - gender analysis updated - indication that gender analysis informed response to the crisis UNW, and/or the humanitarian community as whole - Extent of gender integration in humanitarian coordination structures and work, such as for example gender sensitive clusters/sectors’ guidance material developed and disseminated; gender dimensions of each cluster well-articulated and reflected in the discussions and work of cluster members; gender addressed as a priority by the HCT | Mix of comparative best practices and qualitative trends amongst respondents | UN Women (ALL); UN Women Partners (ALL); Other Humanitarian Actors; UNCT/HCT; HC/RC; Donors; Others | Semi-structured interviews; Survey; UN Women Documentation; Comparative; Evaluator Expertise Review of HNOs and HRPs in countries visited and comparison with data from three randomly selected countries with large humanitarian emergencies where UN Women is not present | Contribution Analysis; Qualitative Trend Analysis; Comparative Analysis Feminist Theory/Nature of Gender Equality; Stakeholder Interest mapping | None |
|  | - To what extent has UN Women’s humanitarian action complemented and added value to ensure that women and girls are better served within the broader response? | Relevance | - Extent to which consultation and communication with affected populations, and men and women of various age and diverse backgrounds therein, have been used to inform programme design and implementation | Mix of comparative best practices and qualitative trends amongst noted cohorts. | UN Women (Regional); UN Women (Country); UN Women Partners (Country); Other Humanitarian Actors; UNCT/HCT; HC/RC; Civil Society; Affected Populations; Others | Semi-structured interviews; Group discussions; Survey; UN Women Documentation; Comparative; Evaluator Expertise Portfolio review Country missions |  | None. |
|  | 1.2 Given expertise and capacities on the ground, is UN Women concentrating its efforts in the right places to ensure a gender responsive humanitarian response? | Relevance | - Stakeholder perception of UN Women capacity - Stakeholder perception of appropriateness of areas of focus |  | UN Women (Regional); UN Women (Country); UN Women Partners (Country); Other Humanitarian Actors; UNCT/HCT; HC/RC; Civil Society; Affected Populations; Others | Semi-structured interviews; Group discussions; Survey; UN Women Documentation; Comparative; Evaluator Expertise Portfolio review Country missions |  | None |
| 2. To what extent has UN Women’s response been appropriate in the context of the needs and priorities of the affected populations, particularly those left furthest behind in humanitarian contexts? |  | Appropriateness | - Stakeholder perception of level of appropriateness - Evidence of UN Women undertaking and using needs assessments - Evidence of needs assessments targeting those worst off/furthest left behind and enabling a response to their needs and priorities and ensuring a comprehensive gender approach (inclusion of men as relevant) | Need to have tangible/practical links to broader humanitarian action planning (HRP) and targeting with corresponding convergence of qualitative trends between UN Women staff and other humanitarian actors. | UN Women (ALL); UN Women Partners (Country); Other Humanitarian Actors; Civil Society; Affected Populations; Others | Semi-structured interviews; Group Discussions; Survey; UN Women Documentation; UN Women Evaluations; Other Qual Data; Standards & Frameworks; Comparative; Evaluator Expertise | Contribution Analysis; Qualitative Trend Analysis | Appropriate' needs to be based on terms of art and common definitions of what this entails. Respondent information may not abide by these strict definitions. |
| 3. Has UN Women adhered to the principles of humanitarian action? |  | Appropriateness | - Has the protection of life, health and dignity been prioritised by strategies and actions? - How does UN Women ensure their actions are (and are perceived as) neutral within a conflict? - Are UN Women staff familiar with the humanitarian principles and the code of conduct - To what degree has UN Women considered the context and conflict when deciding where and how to intervene to ensure neutrality and impartiality - Is UN Women speaking with all actors? - Is UN Women ensuring clear distinction between its actions and that of national actors. | Need to have tangible/practical links to broader humanitarian action planning (HRP) and targeting with corresponding convergence of qualitative trends between UN Women staff and other humanitarian actors. | UN Women (local); UN Women Partners (local); Other Humanitarian Actors; HC/RC; Donors; Others | Semi-structured interviews; Group Discussions; Survey; UN Women Documentation; UN Women Evaluations; Other Qual Data; Evaluator Expertise |  |  |
| 4. How successful has UN Women been in designing and implementing its humanitarian work to contribute to longer term development and sustainability, taking into account the humanitarian – development nexus? |  | Connectedness | - Stakeholder perception of UN Women’s effectiveness in its HA contributing to longer-term sustainability - Evidence of consideration of longer-term development and sustainability factors in design, implementation and M&E - Evidence of linkage/handover to longer term initiatives/teams / partners | Subject matter and comparative expertise will be primary and then tested through qualitative trend analysis amongst noted cohorts and measured against tangible examples/proof of how this work contributes to the humanitarian/development nexus. | UN Women (Global); UN Women Partners (Global); Other Humanitarian Actors; HC/RC; Donors; Others | Semi-structured interviews; UN Women Documentation; Standards & Frameworks; Comparative; Evaluator Expertise | Contribution Analysis; Qualitative Trend Analysis; Partnership Assessment Framework; GEM Framework | May be highly subjective given how different cohorts/respondents describe and think about the humanitarian-development nexus. |
| 5.0 Is UN Women investing in the right partnerships in humanitarian action in the right way? |  | Partnerships | - Partnerships are sustained, renewed, expanded - Evidence of partnerships on the ground. | Identification of specific activities to which have benefitted from partnerships followed by an analysis of how/if these contribute to greater results. Will test this through qualitative information from noted cohorts and related programme/activity documentation. Comparative analysis and subject matter expertise will be used to assess the implications of these results in relation to the inclusion of gender equality and women's empowerment elements. | UN Women (Global); UN Women (Regional); UN Women (Country); UN Women Partners (Global); UN Women Partners (Country); Other Humanitarian Actors; UNCT/HCT; HC/RC; Civil Society; Affected Populations; Donors; Others | Documentation with a focus on partnership agreements; Semi-structured interviews with partners; Evaluator Expertise | Partnership Assessment Framework; Contribution Analysis; Qualitative Trend Analysis | Will need access to internal documentation and discussions to understand bottlenecks and flows |
|  | 5.1 What are the key partnerships that can support UN Women to achieve its mandate? | Partnerships | - Partnerships identified are able to benefit from UN Women’s strengths and expertise - Partnerships identified are able to strengthen UN Women’s work, either in reach or quality | Identification of specific partnerships to which UN Women has contributed followed by an analysis of how/if these contribute to greater results. | UN Women (Global); UN Women (Regional); UN Women (Country); UN Women Partners (Global); UN Women Partners (Country); Other Humanitarian Actors; UNCT/HCT; HC/RC; Civil Society; Affected Populations; Donors; Others | Comparative analysis; Analysis Semi structured interviews with partners and UN Women KII; analysis of documentation; Evaluator Expertise | Partnership Assessment Framework; Contribution Analysis; Qualitative Trend Analysis | Given that partnerships include other actors and their own priorities, limitations, etc… there may be factors outside UN Women’s control (and outside the evaluation team’s reach) that may be affecting effective partnerships |
|  | 5.2 What are the enabling factors and challenges to effective partnerships? | Partnerships | - Changes and amendments to existing partnerships will help identify enabling factors and challenges - Specific examples that show the added value of the partnerships | Comparative analysis and subject matter expertise will be used to assess the implications of these results | UN Women (Global); UN Women (Regional); UN Women (Country); UN Women Partners (Global); UN Women Partners (Country); Other Humanitarian Actors; UNCT/HCT; HC/RC; Civil Society; Affected Populations; Donors; Others | Analysis of successful examples; Live observation; analysis of existing documentation as well as partner’s mandate and other corporate and strategic information; semi-structured interviews; Comparative; Evaluator Expertise | Partnership Assessment Framework; Contribution Analysis; Qualitative Trend Analysis | In some instances it may be too early to asses |
| 6.0 To what extent is UN Women effective in integrating gender equality and women’s empowerment in humanitarian action through its normative, coordination, and operational work? |  | Effectiveness | - Progress on indicators in IASC GEEW Accountability Framework that measures in how far the standards all actors have committed to in the Policy have been addressed in joint products or actions. - Evidence of gender considerations in humanitarian response (including plans, guides, checklists, etc) reported to be derived from UN Women’s actions - Extent of gender integration in humanitarian coordination structures and work, such as for example gender sensitive clusters/sectors’ guidance material developed and disseminated; gender dimensions of each cluster well-articulated and reflected in the discussions and work of cluster members; gender addressed as a priority by the HCT - Evidence of UN Women contributing to effective gender integration in HA (e.g. indicators from UN Women M&E efforts, production, dissemination and use of tools and guidance, results of training and outreach efforts, tracking progress at HNO and HRP level, outcomes of participation and efforts in major initiatives and progress of key indicators against targets as for example agenda for humanity gender commitments tracking including financial data, parity in HCs and other key positions, etc. ) - Evidence/ measure on whether efforts are systematic, and as part of a strategy, with real strategic planning behind, rather than being discretionary, and based on personal capacity or relationships. | Identification of specific activities to which UN Women has contributed followed by an analysis of how/if these contribute to greater results. Will test this through qualitative information from noted cohorts and related programme/activity documentation. Test will be in the demonstrable links between UN Women contributions and expected results and how/if this is recognised by noted cohorts. Comparative analysis and subject matter expertise will be used to assess the implications of these results in relation to the inclusion of gender equality and women's empowerment elements. | UN Women (Global); UN Women (Regional); UN Women (Country); UN Women Partners (Global); UN Women Partners (Country); Other Humanitarian Actors; UNCT/HCT; HC/RC; Civil Society; Affected Populations; Donors; Others | Semi-structured interviews; Group Discussions; Survey; UN Women Statistics; UN Women Documentation; UN Women Evaluations; Other Quant Data; Other Qual Data; Standards & Frameworks; Comparative; Evaluator Expertise | Contribution Analysis; Complex Adaptive Systems; Qualitative Trend Analysis; Feminist Theory/Nature of Gender Equality; Stakeholder Interest mapping; Partnership Assessment Framework; Counterfactual | Will be dependent on sufficient level of documentation across all areas. May require high level CAS analysis. |
|  | 6.1. To what extent has UN Women contributed to more women and girls playing a greater role in humanitarian response and recovery efforts, including disaster risk reduction (DRR)? | Effectiveness | - Evidence of UN Women contributing to women and girls playing a greater role (e.g. inclusion of women’s associations/NGOs in humanitarian coordination architecture and efforts, women and girls included in needs assessments, design and aid delivery) - Stakeholder perception of greater inclusion and consideration, emphasis on rights holders (women’s and girls’ perception on their role) | In relation to activities identified/analysed according to EQ7.0, assess how many more women may have played a greater role due to UN Women efforts. Programme/activity documentation will be key. | UN Women (Country); UN Women Partners (Country); Other Humanitarian Actors; Civil Society; Affected Populations | Semi-structured interviews; Group Discussions; Survey; UN Women RBM; UN Women Statistics; UN Women Documentation; UN Women Evaluations; UN Women structures & processes; Other Quant and Qual Data; Standards & Frameworks; Comparative; Evaluator Expertise | Contribution Analysis; Complex Adaptive Systems; Qualitative Trend Analysis; Counterfactual | Need sufficient quantitative data associated with noted programmes and/or results-based documentation, e.g. monitoring and evaluation reports. |
|  | 6.2. To what extent has UN Women contributed to more women and girls being better served by humanitarian response and recovery efforts, including disaster risk reduction (DRR)? | Effectiveness | - Coverage of women and girls and relevant vulnerable populations (e.g. host communities, men as appropriate) - Indication of quality and responsiveness of assistance received, e.g. dignified treatment, safe and accessible services and distribution; more appropriate design and implementation, e.g. without overburdening, not putting them at further risk, culturally sensitive, for e.g. male and female outreach workers, etc. - Stakeholder perception, M&E |  |  |  |  |  |
|  | 6.3. To what extent does UN Women work with affected populations and civil society in ways that enable them to influence a humanitarian response? | Effectiveness | - Evidence of UN Women consideration of women’s empowerment, capacity strengthening of civil society in HA advocacy efforts - Evidence of efforts to create opportunities for participation and input from civil society | In relation to activities identified/analysed according to EQ7.0, will include qualitative trend analysis from affected populations/civil society compared with relevant programme/activity documentation. | UN Women (Country); UN Women Partners (Country); Other Humanitarian Actors; Civil Society; Affected Populations | Semi-structured interviews; Group Discussions; UN Women Documentation; UN Women Evaluations; Other Qual Data; Comparative | Contribution Analysis; Complex Adaptive Systems; Qualitative Trend Analysis | Access to purposeful sample of people from civil society and affected populations with facilitation/participatory techniques sufficient to solicit reliable information. |
|  | 6.4. To what extent is UN Women contributing to making coordination mechanisms for humanitarian response more gender-sensitive and ensuring accountability for integrating gender equality across the response? | Effectiveness | - Evidence of increased use/effectiveness of accountability frameworks for coordination UN Women’s contribution to making coordination mechanisms for humanitarian response more gender-sensitive and ensuring accountability for integrating gender equality across the response - Evidence of UN Women’s role in this process - Use of HCT Scorecard - Stakeholder perception on UN Women’s contribution | Qualitative trend analysis amongst noted cohorts measured against tangible examples/proof of how gender equality has been integrated. Test will be number/level of examples where this has been the case and whether these are replicable/scalable. | UN Women (Regional); UN Women (Country); UN Women Partners (Country); Other Humanitarian Actors; UNCT/HCT; HC/RC | Semi-structured interviews; UN Women Documentation; Standards & Frameworks; Comparative; Evaluator Expertise HCT and cluster documentation and groups in countries covered by missions and 3 countries with humanitarian responses where UN Women is not present | Contribution Analysis; Complex Adaptive Systems; Qualitative Trend Analysis; Feminist Theory/Nature of Gender Equality; Stakeholder Interest mapping; Partnership Assessment Framework; GEM Framework; Counterfactual; Statistical; Business Process Engineering | Need enough tangible examples that illustrate accountability. |
|  | 6.5 To what extent and how are the different areas of the mandate reinforcing each other | Effectiveness | - Stakeholders perception - Evidence of achievements/progress in one area of mandate resulting from work on another (or vice versa) - Opportunities for scaling up or strengthening UN Women’s position | Qualitative trend analysis amongst noted cohorts measured against tangible examples/proof of how different areas reinforce each other. Test will be number/level of examples where this has been the case and whether these are replicable/scalable. | UN Women (Regional); UN Women (Country); UN Women (global), UN Women Partners (Country); Other Humanitarian Actors; UNCT/HCT; HC/RC | Semi-structured interviews; Survey; UN Women Documentation; UN Women Evaluations; UN Women structures & processes; Comparative RO Self-assessment questionnaire | Contribution Analysis; Complex Adaptive Systems; Qualitative Trend Analysis; Partnership Assessment Framework; | Need enough tangible examples that illustrate complementarity between areas |
| 7.0 Is UN Women effectively managing knowledge and learning to strengthen its results and further its mandate? |  | Effectiveness | - Stakeholder perception on feedback loops - Evidence of learning feeding into global approach | Qualitative inputs from noted cohorts tested through the existence of different practices, e.g. in coordination for a, documentation, et. al. number, type, and scalability/ replicability of examples will provide basis for conclusions | UN Women (Global); UN Women (Regional); UN Women (Country); UN Women Partners (Global) | Semi-structured interviews; Survey; UN Women Documentation; UN Women Evaluations; UN Women structures & processes; Comparative RO Self-assessment questionnaire | Contribution Analysis; Complex Adaptive Systems; Qualitative Trend Analysis; Kirkpatrick analysis of learning | Will depend on practical examples of how UN Women has learned something new and then put that learning into practice. May not get past reaction/satisfaction in Kirkpatrick model. |
|  | 7.1 To what extent is learning from the field feeding into the global approaches to gender equality and women’s empowerment and vice-versa? | Effectiveness | - Stakeholder perception on feedback loops - Evidence of learning feeding into global approach and field | Qualitative inputs from noted cohorts tested through the existence of different practices, e.g. in coordination for a, documentation, et. al. number, type, and scalability/ replicability of examples will provide basis for conclusions | UN Women (Global); UN Women (Regional); UN Women (Country); UN Women Partners (Global) | Semi-structured interviews; Survey; UN Women Statistics; UN Women Documentation; UN Women Evaluations; UN Women structures & processes; Comparative RO Self-assessment questionnaire | Contribution Analysis; Complex Adaptive Systems; Qualitative Trend Analysis; Kirkpatrick analysis of learning | Will depend on practical examples of how actors have learned something new and then put that learning into practice. May not get past reaction/satisfaction in Kirkpatrick model. |
| 8.0 What are enabling and limiting factors (internal and external) that contribute to the achievement of results and what actions need to be taken to overcome any barriers that limit progress? Are there any opportunities and entry points for further scaling up? |  | Effectiveness | - Stakeholder perception of enabling and limiting factors (internal and external) and any evidence that may be available to support these perceptions - Evidence of limiting factors being overcome (e.g. successful fundraising, partnerships, deployments, projects) | Analysis from all other effectiveness questions will contribute to answering this with a focus on those that have the most potential negative/positive impact and/or cost implications. | UN Women (Regional); UN Women (Country); UN Women Partners (Global); UN Women Partners (Country); Other Humanitarian Actors; Others | ALL, except survey | TBD; all Force field analysis/SWOT Comparative | Dependent on other areas of inquiry and analysis. |
| 9.0 Do UN Women’s institutional arrangements and mechanisms support efficient and timely humanitarian response? |  | Efficiency | - Evidence of policies, strategies, processes and procedures in place and being used supporting effective and efficient humanitarian work (e.g. timeliness and capacity indicators associated with roster of gender experts for quick deployment in emergencies; activation and rapid response mechanisms for e.g. in relation to resource mobilization; stand-by capacities in place, etc.); SOPs - Total number of participations of UN Women in PDNA exercises and % of participants - Timeliness and number of rapid deployments - Timeliness of procurement on emergency items - Use of fast-track procedures and number of days for decision-making and disbursements to partners etc. - Stakeholder perception - Clarity of decision-making structures | Subject matter expertise, especially in relation to business process engineering, efficiency, results based management, etc. Will be supported through qualitative evidence from relevant stakeholders. | UN Women (ALL) | Semi-structured interviews; UN Women RBM; UN Women Statistics; UN Women Documentation; UN Women structures & processes; email trails; Financial information; Standards & Frameworks; Evaluator Expertise | Business Process Engineering; financial ratio analysis | Requires specific data/financial information. |
|  | 9.1. To what extent do UN Women’s institutional arrangements (including lines of communication, decision making and support structures), operational mechanisms, and financial resources support an effective and efficient response? | Efficiency |  | Same as for EQ 14 with the inclusion of UN Women partners perceptions of effective and efficient institutional arrangements, etc. | UN Women (ALL); UN Women Partners (ALL); UN Women Partners (Country) |  |  |  |
| 10.0 Does UN Women have the appropriate expertise and capacities to support gender equality and women's empowerment in humanitarian action? |  | Efficiency | - Stakeholder perception of UN Women’s internal expertise on how to apply/mainstream gender in HA and of HA context - Level of HA capacity/resources in HQ, ROs, COs (positions, budget) | Analysis from all other effectiveness questions will contribute to answering this with a focus on those that are replicable/scalable or that have exceptional potential for compelling results even in sui generis contexts. | UN Women (Global); UN Women (Regional); UN Women (Country); UN Women Partners (Global); UN Women Partners (Country); Other Humanitarian Actors | Semi-structured interviews; Survey; UN Women RBM; UN Women Statistics; UN Women Documentation; UN Women structures & processes; Other Quant Data; Other Qual Data; Standards & Frameworks; Comparative | Qualitative Trend Analysis; Partnership Assessment Framework; GEM Framework; Counterfactual; Business Process Engineering | May be subjective; depends on sufficient data from multiple sources. |
|  | 10.1 Does UN Women have adequate surge capacity to be able to respond rapidly to emergencies? | Efficiency | - Level of HA capacity/resources in HQ, ROs, COs (positions, budget) - UN Women presence at the early stages of an emergency |  | Government, Donors, UN Women (all), Partners (ALL) | Semi structured interviews, survey, UN Women Documentation; | Qualitative Trend Analysis; | May be subjective; depends on sufficient data from multiple sources. |
|  | 10.2 Does UN women ensure adequate and up-to-date capacity and skills (training, etc.) of staff working in humanitarian action? | Efficiency | - Stakeholder perception of UN Women’s internal expertise on how to apply/mainstream gender in HA and of HA context - Level of HA capacity/resources in HQ, ROs, COs (positions, budget) | Analysis from all other effectiveness questions will contribute to answering this with a focus on those that are replicable/scalable or that have exceptional potential for compelling results even in sui generis contexts. | Government, Donors, UN Women (all), Partners (ALL) | Semi structured interviews, survey, UN Women Documentation; | Qualitative Trend Analysis |  |
| 11.0 How has UN Women's humanitarian work addressed the underlying causes of gender inequality and discrimination? |  | Gender Equality and Human Rights | - differentiated strategies in relation to underlying causes of discrimination | All other related data, analysis, and information will contribute to impact questions. Relies on high degree of triangulation between different sources, using contribution analysis as a model. Analysis will include the evidentiary strength of any findings/conclusions and will often cite models for measuring different aspects of impact going forward. | ALL | ALL, except survey | TBD; all | Dependent on other areas of inquiry and analysis. |
|  | 11.1 To what extent does the humanitarian action work undertaken by UN Women address the underlying causes of inequality and discrimination, including those experienced by the LGBTQI community and women with disabilities? | Effectiveness | - Evidence of UN Women humanitarian action response addressing root causes of discrimination; consideration of these in assessments, programme design, M&E; management response, etc - changes in the gender dynamics at the household and community levels such as for e.g. growing number of women in leadership position in recovery efforts; at policy level, increased recognition of women’s role in emergency preparedness, response and recovery efforts, including in policies documents/strategies, approaches, and so on; - Stakeholder perceptions on UN Women HA work addressing underlying causes and including persons with disability, LGBTQI |  |  |  |  |  |
|  | 11.2 To what extent were a human rights based approach and gender equality incorporated in the design and implementation of UN Women’s humanitarian action? | Gender Equality and Human Rights | - Evidence of HRBA and GE approach included in HA: consideration of contribution to the development of the capacities of ‘rights holders’ to claim their rights - contribution to the development of the capacities of ‘duty bearers’ to meet their obligations - Use of disaggregated data - AAP - # of indicators developed in consultation with affected community - % of female and % of male actively participating in the conception and implementation of M&E of programmes. - % of those who participated directly in decision making about assistance interventions who are women - Evidence of discussions organized with affected girls, women, boys and men that have been used to influence decisions made on design of assessments, programmes, standards, selection criteria, etc. - Feedback and complaints mechanisms incorporated in UN Women’s HA |  |  |  |  |  |
| 12. To what extent is UN Women's work in humanitarian action sustainable, including DRR, recovery, and other aspects along the humanitarian - development nexus? |  | Sustainability | - Stakeholder perceptions on level of sustainability - Evidence of UN Women’s strategies integrating sustainability factors - Evidence of UN Women accessing multi-year-funding for its activities in HA - Evidence of UN Women’s HA work linking into UNDAF - Handover of activities to other actors | Qualitative trend analysis amongst noted cohorts, citing convergence and divergence with the latter a possible sign of a lack of sustainability. Such issues will be further assessed through subject matter expertise. | UN Women (Country); UN Women Partners (Country); Other Humanitarian Actors; Civil Society; Affected Populations | ALL | TBD; all | Dependent on other areas of inquiry and analysis. |

## Evaluation Questions

As based on the original set of questions included in the TOR and the analysis conducted as part of the inception phase, including a revised theory of change, the following questions were agreed to as part of the Inception Phase.

Relevance

1.0 	Is UN Women's work relevant to gender responsive humanitarian action including DRR?

  - To what extent has UN Women’s humanitarian action complemented and added value to ensure that women and girls are better served within the broader response?

  - Given expertise and capacities on the ground, is UN Women concentrating its efforts in the right places to ensure a gender responsive humanitarian response?

Appropriateness

2.0 	To what extent has UN Women’s response been appropriate in the context of the needs and priorities of the affected populations, particularly those left furthest behind in humanitarian contexts?

3.0 	Has UN Women adhered to the principles of humanitarian action?

Connectedness

4.0 	How successful has UN Women been in designing and implementing its humanitarian work to contribute to longer term development and sustainability, taking into account the humanitarian – development nexus?

Partnerships

5.0 	Is UN Women investing in the right partnerships in humanitarian action in the right way?

5.1 	What are the key partnerships that can support UN Women to achieve its mandate?

5.2 	What are the enabling factors and challenges to effective partnerships?

Effectiveness

6.0 	To what extent is UN Women effective in integrating gender equality and women’s empowerment in humanitarian action through its normative, coordination, and operational work?

6.1 	To what extent has UN Women contributed to more women and girls playing a greater role in humanitarian response and recovery efforts, including disaster risk reduction (DRR)?

6.2 	To what extent has UN Women contributed to more women and girls being better served by humanitarian response and recovery efforts, including disaster risk reduction (DRR)?

6.3 	To what extent does UN Women work with affected populations and civil society in ways that enable them to influence a humanitarian response?

6.4 	To what extent is UN Women contributing to making coordination mechanisms for humanitarian response more gender-sensitive and ensuring accountability for integrating gender equality across the response?

6.5. 	To what extent and how are the different areas of the mandate reinforcing each other?

7.0 	Is UN Women effectively managing knowledge and learning to strengthen its results and further its mandate?

7.1 	To what extent is learning from the field feeding into UN Women’s global approaches to gender equality and women’s empowerment (GEWE) and vice-versa?

8.0 	What are the enabling and limiting factors (internal and external) that contribute to the achievement of results and what actions need to be taken to overcome any barriers that limit progress? Are there any opportunities and entry points for further scaling up?

Efficiency

9.0 	Do UN Women’s institutional arrangements and mechanisms support efficient and timely humanitarian response?

9.1 	To what extent do UN Women’s institutional arrangements (including lines of communication, decision making and support structures), operational mechanisms, and financial resources support an effective and efficient response?

10.0 	Does UN Women have the appropriate expertise and capacities to support gender equality and women's empowerment in humanitarian action?

10.1 	Does UN Women have adequate surge capacity to be able to respond rapidly to emergencies?

10.2 	Does UN women ensure adequate and up-to-date capacity and skills (training, etc.) of staff working in humanitarian action?

Gender Equality & Human Rights

11.0 	How has UN Women’s humanitarian work addressed the underlying causes of gender inequality and discrimination?

11.1 	To what extent does the humanitarian action work undertaken by UN Women address the underlying causes of inequality and discrimination, including those experienced by the LGBTQI community and women with disabilities?

11.2 	To what extent were a human rights-based approach and gender equality incorporated in the design and implementation of UN Women’s humanitarian action?

Sustainability

12. 	To what extent is UN Women's work in humanitarian action sustainable, including DRR, recovery, and other aspects along the humanitarian - development nexus

## Demographic Information of Evaluation Respondents

| Bangladesh field mission |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date | Role/Title | Organisation |  | Type | Gender | # of respondents |
| 03/02/2019 | Programme Specialist, DRR, Climate Change and HA | UN Women |  | KII | W | 1 |
| 03/02/2019 | Operations Manager | UN Women |  | KII | W | 1 |
| 03/02/2019 | Country Representative | UN Women |  | KII | W | 1 |
| 03/02/2019 | Senior Researcher | BCAS |  | KII | M | 1 |
| 03/02/2019 | BNPS staff | BNPS |  | KII | M | 1 |
| 03/02/2019 | Executive Director | Green Hill |  | KII | M | 1 |
| 03/02/2019 | BRAC Staff | BRAC |  | KII | M | 1 |
| 03/02/2019 | Additional Secretary | Ministry of Disaster Management & Response |  | KII | W | 1 |
| 03/02/2019 | Deputy Secretary | Department of Women's Affairs |  | KII | M | 1 |
| 03/02/2019 | GiHA Focal Point | Department of Women's Affairs |  | KII | W | 1 |
| 04/02/2019 | Head of Sub Office, Cox's Bazar | UN Women |  | KII | W | 1 |
| 04/02/2019 | Gender Programme Analyst | UN Women |  | KII | W | 1 |
| 04/02/2019 | Protection Sector Coordinator | UNHCR |  | KII | W | 1 |
| 04/02/2019 | Protection Officer - SGBV | UNHCR |  | KII | W | 1 |
| 04/02/2019 | GiHA WG | Oxfam |  | KII | W | 1 |
| 04/02/2019 | Senior Coordinator | ISCG |  | KII | M | 1 |
| 04/02/2019 | Operational and Thematic Coordination Team Lead | ISCG |  | KII | W | 1 |
| 04/02/2019 | Lead, Gender Community Based and Legal Protection | BRAC |  | KII | W | 1 |
| 04/02/2019 | Head of Sub Office, Cox's Bazar | UNFPA |  | KII | W | 1 |
| 04/02/2019 | Emergency Programme Coordinator | FAO |  | KII | M | 1 |
| 04/02/2019 | Head of Sub Office, Cox's Bazar | WFP |  | KII | M | 1 |
| 04/02/2019 | Emergency Coordinator | IOM |  | KII | M | 1 |
| 05/02/2019 | Head of Sub Office, Cox's Bazar | UNDP |  | KII | M | 1 |
| 05/02/2019 | Women's Centre Staff | ActionAid |  | FGD | M | 6 |
| 05/02/2019 | Beneficiaries FGD | Beneficiaries |  | FGD | M | 15 |
| 05/02/2019 | Beneficiaries FGD | Beneficiaries |  | FGD | M | 8 |
| 05/02/2019 | Programme Management Advisor | UNDP |  | KII | M | 1 |
| 05/02/2019 | Staff | ActionAid |  | KII | M | 1 |
| 05/02/2019 | Technical expert | ECHO |  | KII | M | 1 |
| 06/02/2019 | PSEA Network Coordinator | ISCG |  | KII | W | 1 |
| 06/02/2019 | Refugee Relief & Repatriation Commissioner | RRRC |  | KII | M | 2 |
| 06/02/2019 | Camp in Charge | RRRC |  | KII | M | 1 |
| 06/02/2019 | Gender Focal Point | WFP |  | KII | M | 2 |
| 06/02/2019 | Head of Sub Office, Cox's Bazar | UNHCR |  | KII | M | 1 |
| 07/02/2019 | Humanitarian Affairs Specialist | UN RCO |  | KII | M | 1 |
| 07/02/2019 | Assistant Country Director | UNDP |  | KII | M | 1 |
| 07/02/2019 | Country Manager | UNOPS |  | KII | M | 1 |
| 07/02/2019 | Director | Dept of Environment |  | KII | W | 1 |
| 07/02/2019 | Humanitarian Advisor | DFID |  | KII | M | 1 |
| Cameroon field mission |  |  |  |  |  |  |
| Date | Role/Title |  | Organisation | Type | Gender | # of respondents |
| 17/01/19 | UNW CO Staff |  | UNW | KII | M | 1 |
| 17/01/19 | Program manager EVAWG |  | UNW | KII | M | 1 |
| 17/01/19 | Representative and focal point |  | UNESCO | KII | M | 2 |
| 17/01/19 | Protection, communities, GVB focal points |  | UNHCR | KII | M | 3 |
| 17/01/19 | UNFPA Staff |  | UNFPA | KII | W | 1 |
| 18/01/19 | NGO Staff |  | Aldepa | KII | M | 4 |
| 18/01/19 | UNFPA Staff |  | UNFPA | KII | M | 0 |
| 18/01/19 | Gender desk officer and boss |  | Local government | KII | W | 2 |
| 18/01/19 | Implementing partner |  | ALVF | FGD | M | 7 |
| 19/01/19 | Gender desk officer |  | police | KII | M | 1 |
| 19/01/19 | Magistrate |  | local GoV | KII | W | 1 |
| 19/01/19 | Education officer and OIC |  | UNICEF | KII | M | 2 |
| 19/01/19 | Director |  | Improff | KII | W | 1 |
| 19/01/19 | Director and department delegate |  | Women’s Empowerment Center | KII | M | 2 |
| 19/01/19 | Relay staff |  | relay | FGD | M | 6 |
| 20/01/19 | Sub office representative |  | OCHA | KII | M | 1 |
| 20/01/19 | Head of mission in Maroua |  | UNDP | KII | M | 1 |
| 20/01/19 | UNW CO Staff |  | UNW | KII | W | 1 |
| 21/1/19 | Camp administrator |  | UNHCR | KII | M | 3 |
| 21/1/19 | Camp manager |  | UNHCR | KII | M | 1 |
| 21/1/19 | FGD |  | Minawao partners | FGD | M | 8 |
| 21/1/19 | Zamay community leader |  | Beneficiaries | KII | M | 1 |
| 21/1/19 | Programme policy officer |  | WFP | KII | M | 1 |
| 22/1/19 | NGO Staff |  | plan | KII | M | 2 |
| 22/1/19 | GBV officer |  | UNW | KII | M | 1 |
| 22/1/19 | Livelihoods officer |  | UNW | KII | M | 1 |
| 22/1/19 | Ministry Staff |  | MINPROFF | KII | M | 1 |
| 22/1/19 | Gender focal points |  | UNICEF and OCHA | KII | M | 3 |
| 23/01/19 | M&E |  | UNW | KII | W | 1 |
| 23/01/19 | ECHO Staff |  | ECHO | KII | M | 2 |
| 23/01/19 | MINPROFF |  | government counterpart | KII | M | 6 |
| 23/01/19 | National security |  | national security | KII | M | 2 |
| 23/01/19 | OCHA Staff |  | OCHA | KII | W | 1 |
| 23/01/19 | OIC Country Representative |  | UNW | KII | W | 1 |
| 24/01/19 | second chance education |  | UNW | KII | W | 1 |
| 24/01/19 | Japan cooperation staff |  | Japan Government | KII | M | 2 |
| Colombia field mission |  |  |  |  |  |  |
| Date | Role/Title |  | Organisation | Type | Gender | # of respondents |
| 18/02/2019 | United Nations Resident Coordinator's Office |  | UN RCO | KII | W | 2 |
| 18/02/2019 | Staff |  | OCHA | KII | M | 1 |
| 18/02/2019 | Staff |  | NRC | KII | M | 2 |
| 18/02/2019 | Staff |  | WFP | KII | M | 2 |
| 18/02/2019 | HA team |  | UNW | KII | M | 3 |
| 18/02/2019 | M&E team |  | UNW | KII | M | 5 |
| 18/02/2019 | UNHCR Office Representative |  | UNHCR | KII | W | 1 |
| 18/02/2019 | Protection cluster focal point |  | protection cluster meeting | KII | M | 1 |
| 18/02/2019 | UNMASS. Aldeas |  | puntos focales de genero | FGD | M | 4 |
| 19/02/2019 | Staff Defensoria del Pueblo |  | Defensoria del pueblo | KII | W | 2 |
| 19/02/2019 | beneficiaries |  | Tejedoras de vida putumayo | FGD | M | 12 |
| 19/02/2019 | women's organisation |  | Tejedoras de vida putumayo | KII | M | 2 |
| 19/02/2019 | Staff |  | UNICEF | KII | W | 2 |
| 19/02/2019 | Staff |  | ONUDC | KII | W | 2 |
| 19/02/2019 | Staff |  | NRC | KII | W | 1 |
| 19/02/2019 | GIFMM |  | UNHCR | KII | M | 1 |
| 19/02/2019 | Staff |  | OIM | KII | M | 2 |
| 19/02/2019 | Staff |  | ECHO | KII | M | 1 |
| 20/02/2019 | Staff Defensoria del Pueblo |  | Defensoria del pueblo | KII | M | 4 |
| 20/02/2019 | Staff Defensoria del Pueblo |  | Defensoria del pueblo | KII | W | 1 |
| 20/02/2019 | Staff Unidad Nacional de Gestión del Riesgo |  | Unidad Nacional de Gestión del Riesgo | KII | M | 4 |
| 20/02/2019 | Staff ONIC |  | ONIC | KII | W | 1 |
| 20/02/2019 | Staff UNHCR |  | UNHCR | KII | W | 1 |
| 20/02/2019 | UN System in Riohacha |  | UN UNICEF, UNHCR, FAO, UN Women | FGD | M | 6 |
| 20/02/2019 | Pastoral Luteran NGO - Maicao staff |  | Pastoral Luteran NGO | KII | W | 1 |
| 21/02/2019 | UNFPA Staff |  | UNFPA | KII | M | 0 |
| 21/02/2019 | Staff USAID |  | USAID | KII | W | 1 |
| 21/02/2019 | Staff Cruz Roja Internacional |  | Cruz Roja Internacional | KII | M | 1 |
| 21/02/2019 | GBV subgroup representative |  | GBV subgroup | KII | W | 1 |
| 20/02/2019 | Maicao shelter |  | Beneficiaries | FGD | M | 12 |
| 21/02/2019 | Independent consultant |  | Independent Consultant | KII | M | 1 |
| Geneva mission |  |  |  |  |  |  |
| Date | Role/Title |  | Organisation | Type | Gender | # of respondents |
| 18/03/2019 | Director, Coordination Division |  | OCHA | KII | M | 1 |
| 18/03/2019 | Manager: Inclusion, Protection and Engagement |  | IFRC | KII | M | 1 |
| 19/03/2019 | Head, Partnership and Coordination Service at UNHCR |  | UNHCR | KII | W | 2 |
| 19/03/2019 | Humanitarian Affairs Officer |  | IASC | KII | M | 2 |
| 19/03/2019 | Humanitarian Affairs Officer |  | OCHA | KII | M | 1 |
| 19/03/2019 | Global Protection Cluster |  | UNHCR | KII | W | 1 |
| 20/03/2019 | Director |  | ICVA | KII | M | 1 |
| 20/03/2019 | Gencap Unit |  | OCHA | KII | W | 1 |
| 20/03/2019 | HACRO staff |  | UNW | KII | W | 1 |
| 20/03/2019 | HACRO staff |  | UNW | KII | W | 1 |
| Jordan field mission |  |  |  |  |  |  |
| Date | Role/Title |  | Organisation | Type | Gender | # of respondents |
| 03/03/2019 | Recovery Specialist |  | UNW | KII | W | 1 |
| 03/03/2019 | Programme Associate |  | UNW | KII | M | 1 |
| 03/03/2019 | UN Coordination and Civil Society Affairs Junior Specialist |  | UNW | KII | W | 1 |
| 03/03/2019 | Director |  | JWU | KII | W | 1 |
| 03/03/2019 | Gender Advisor |  | UNW | KII | W | 1 |
| 03/03/2019 | Operations Manager |  | UNW | KII | M | 0 |
| 03/03/2019 | Head of programmes |  | WFP | KII | W | 1 |
| 04/03/2019 | Deputy |  | OCHA | KII | M | 1 |
| 04/03/2019 | Second secretary, Humanitarian Officer |  | Australian Embassy | KII | W | 2 |
| 04/03/2019 | Resident Coordinator |  | UNCT | KII | M | 1 |
| 04/03/2019 | Secretary General |  | JNCW | KII | W | 1 |
| 04/03/2019 | humanitarian relief coordination unit |  | Ministry of Planning and International Cooperation | KII | M | 2 |
| 05/03/2019 | project manager |  | Education for Employment - Jordan | KII | M | 1 |
| 05/03/2019 | Food Security Gender focal point |  | WFP | KII | W | 1 |
| 05/03/2019 | Deputy |  | UNFPA | KII | W | 2 |
| 05/03/2019 | Director of Policies and Strategies |  | Ministry of Social Development | KII | M | 1 |
| 05/03/2019 | Country Representative |  | UNW | KII | M | 1 |
| 05/03/2019 | Advocacy Policy and Communications Coordinator |  | Jordan INGO Forum | KII | W | 1 |
| 05/03/2019 | Cooperation officer |  | France | KII | W | 1 |
| 05/03/2019 | Director, Humanitarian Assistance |  | Iceland | KII | W | 1 |
| 05/03/2019 | Institutional Capacity Development Specialist |  | UNW | KII | M | 1 |
| 05/03/2019 | Education Specialist |  | UNW | KII | W | 1 |
| 05/03/2019 | Operations Manager |  | UNW | KII | W | 1 |
| 05/03/2019 | Head of Sub office |  | UNICEF | KII | W | 1 |
| 06/03/2019 | Beneficiaries (women) Zaatari -Oasis 1 |  | Beneficiaries | FGD | M | 5 |
| 06/03/2019 | Beneficiaries (men) Zaatari -Oasis 1 |  | Beneficiaries | FGD | M | 6 |
| 06/03/2019 | Beneficiaries (women) Zaatari -Oasis 2 |  | Beneficiaries | FGD | M | 13 |
| 06/03/2019 | Beneficiaries (men) Zaatari -Oasis 2 |  | Beneficiaries | FGD | M | 4 |
| 06/03/2019 | Focus groups (women) Azrak refugee camp |  | Beneficiaries | FGD | M | 5 |
| 06/03/2019 | Focus groups (women) Azrak refugee camp |  | Beneficiaries | FGD | M | 4 |
| 06/03/2019 | Focus groups (women) Azrak refugee camp |  | Beneficiaries | FGD | M | 8 |
| 06/03/2019 | Focus groups (men) Azrak refugee camp |  | Beneficiaries | FGD | M | 5 |
| 06/03/2019 | Gender focal points |  | UNHCR, NGO | FGD | M | 5 |
| 06/03/2019 | Azrak camp staff |  | World Vision | KII | M | 1 |
| 06/03/2019 | Head of Azrak Sub office |  | WFP | KII | M | 2 |
| 06/03/2019 | VAF Coordinator |  | UNHCR | KII | M | 1 |
| 07/03/2019 | Focus group -Karak governorate- out of camp |  | Beneficiaries | FGD | M | 20 |
| 07/03/2019 | Karak Women's NGO |  | NGOs | KII | W | 1 |
| New York missions |  |  |  |  |  |  |
| Date | Role/Title |  | Organisation | Type | Gender | # of respondents |
| 03/11/2018 | Director HARCO |  | UNW | KII | M | 1 |
| 03/11/2018 | OCHA Staff |  | OCHA | KII | W | 1 |
| 03/11/2018 | Humanitarian and Gender Specialist |  | UNW | KII | W | 1 |
| 03/11/2018 | Human Resource Specialists |  | UNW | KII | M | 2 |
| 03/11/2018 | Humanitarian and Gender Specialist |  | UNW | KII | W | 1 |
| 03/12/2018 | OCHA Senior Humanitarian Affairs |  | OCHA | KII | M | 1 |
| 03/12/2018 | Gender Adviser |  | OCHA | KII | W | 1 |
| 03/12/2018 | Head of Office and Humanitarian Affairs |  | IASC | KII | W | 1 |
| 03/12/2018 | Special Advisor to Change |  |  | KII | W | 1 |
| 03/12/2018 | Director of Gender and Policy |  | Save the Children | KII | W | 1 |
| 03/12/2018 | Policy and Partnerships Lead |  | DPKO | KII | W | 1 |
| 13/03/2019 | Senior Program Advisor |  | UNDP | KII | W | 1 |
| 13/03/2019 | Humanitarian Officer |  | CERF | KII | W | 1 |
| 13/03/2019 | Chief Humanitarian Action and Transition Team |  | UNICEF | KII | M | 1 |
| 13/03/2019 | Deputy Director |  | UNICEF | KII | W | 1 |
| 13/03/2019 | Humanitarian Director of Practice |  | Care USA | KII | W | 1 |
| 14/03/2019 | Humanitarian Officer |  | UNW | KII | M | 1 |
| 14/03/2019 | Director Program Division |  | UNW | KII | W | 1 |
| 14/03/2019 | Acting Chief Humanitarian Branch |  | UNFPA | KII | W | 1 |
| 14/03/2019 | Policy Specialist |  | UNW | KII | W | 1 |
| 14/03/2019 | Operations Advisor |  | UNW | KII | M | 1 |
| 15/03/2019 | Japan cooperation staff |  | Japan Government | KII | W | 1 |
| 15/03/2019 | Director Gender Interview |  | WFP | KII | W | 1 |
| South Sudan field mission |  |  |  |  |  |  |
| Date | Role/Title |  | Organisation | Type | Gender | # of respondents |
| 11/02/2019 | UN Women Deputy Representative |  | UNW | KII | W | 1 |
| 11/02/2019 | UN Women Gender and Humanitarian Action Team |  | UNW | FGD | M | 6 |
| 11/02/2019 | Implementing Partner |  | SSWEN, SPEDAP, IPCA, SSWEA, CEPO, Grand Debaters | FGD | M | 12 |
| 11/02/2019 | Gender Focal points |  | NGOs | KII | M | 2 |
| 11/02/2019 | Director General |  | Ministry of Humanitarian and Disaster Management | KII | W | 1 |
| 12/02/2019 | Director General and Acting DG |  | Ministry of Gender, Child and Social Welfare | KII | W | 1 |
| 12/02/2019 | Director General |  | Ministry of Agriculture and Food Security | KII | W | 1 |
| 12/02/2019 | Strategic planning advisor and team leader |  | RC | KII | M | 1 |
| 12/02/2019 | Sr programme advisor, programme support and partnerships and M&E |  | UNDP | KII | M | 2 |
| 12/02/2019 | Assistant Representative |  | UNHCR | KII | M | 2 |
| 12/02/2019 | Representative |  | OCHA | KII | M | 1 |
| 13/02/2019 | WFP Representative |  | WFP | KII | M | 1 |
| 13/02/2019 | Head of Cooperation |  | Embassy of Germany | KII | W | 1 |
| 13/02/2019 | Representatives |  | UNESCO | KII | M | 4 |
| 13/02/2019 | Gender Focal Point |  | UNFPA | KII | W | 1 |
| 14/02/2019 | Field visit to PoC and meeting with UN Women beneficiaries - Beads and Liquid soap making |  | POC – CECP UN House | FGD | M | 5 |
| 14/02/2019 | Field visit to meet UN Women beneficiaries – Agriculture group – VSAL and Group discussion |  | IPCA Field Office | FGD | M | 6 |
| 14/02/2019 | Cluster Gender Focal Points |  | Lozoh Women Development Org, Titi Foundation, Rural Women for Development, Crown the Women, Nile Hope, Women's Enterprise Fund, Plan International, Oxfam, UNICEF, Norwegian People's Aid | KII | M | 9 |
| 14/02/2019 | Head of Cooperation/Humanitarian |  | Embassy of Japan | KII | M | 1 |
| 14/02/2019 | Representative |  | Oxfam | KII | W | 1 |
| 14/02/2019 | HA programme officer |  | UN Women | KII | M | 1 |
| Remote interviews |  |  |  |  |  |  |
| Date | Role/Title |  | Organisation | Type | Gender | # of respondents |
| 11/08/2018 | PS regional advisor LAC |  | UNW | KII | M | 1 |
| 10/09/2018 | Policy Advisor |  | UNW | KII | W | 1 |
| 10/09/2018 | Director of HACRO |  | UNW | KII | M | 1 |
| 11/09/2018 | DRR Geneva, HACRO |  | UNW | KII | W | 1 |
| 04/01/2019 | Co-Chair Gender Reference Group IASC |  | IASC | KII | W | 1 |
| 04/01/2019 | On resources mobilization |  | UNW | KII | M | 1 |
| 04/01/2019 | Country Representative, Egypt |  | UNW | KII | W | 1 |
| 31/01/2019 | GenCap Advisor |  | GenCap | KII | M | 1 |
| 31/01/2019 | Regional HA Advisor & HOO Myanmar |  | UN Women | KII | W | 1 |
| 20/02/2019 | Former Deputy HoSO and Senior Protection Coordinator |  | UNHCR | KII | W | 1 |
| 04/03/2019 | Regional Director, ECA, UN Women |  | UNW | KII | W | 1 |
| 07/04/2019 | Country Representative Barbados MCO (Huracan) |  | UNW | KII | W | 1 |
| 07/04/2019 | Country Representative, Iraq (Yemen), UN Women |  | UNW | KII | W | 1 |
| 13/11/2018 | PS regional advisor LAC |  | UNW | KII | W | 1 |
| 13/3/2019 | SIDA staff |  | SIDA | KII | M | 4 |
| 16/10/2018 | Assistant Secretary General, Policy and Programme |  | UNW | KII | W | 1 |
| 16/10/2018 | Policy Specialist on Gender, Governance and Crisis Prevention, UNDP |  | UNDP | KII | W | 1 |
| 17/10/2018 | Chief, HACRO. Now on detailed assignment |  | UNW | KII | M | 1 |
| 18/03/2019 | Assistant Executive Director, and Operations, WFP |  | WFP | KII | W | 1 |
| 18/3/2019 | Assistant Executive Director |  | WFP | KII | W | 1 |
| 22/3/2019 | Chief Policy Advisor, Women, Peace and Security Section, UN Women |  | UNW | KII | W | 1 |
| 25/03/2019 | ECHO, European Commission |  | ECHO | KII | W | 1 |
|  | UNW Policy specialist |  | UNW | KII | W | 1 |
|  |  |  | OXFAM | KII | W | 1 |
|  | Gender and Protection Specialist, Fiji MCO |  | UNW | KII | W | 1 |
|  | WPS and HA Advisor for Arab States, UN Women (former Jordan) |  | UNW | KII | W | 1 |
|  | UN Woman staff |  | UNW | KII | W | 1 |
| 06/05/2019 | UNW Change management (male) |  | UNW | KII | M | 1 |
| 07/05/2019 | Preliminary findings debriefing - online with UNW /HACRO |  | UNW | FGD | M | 12 |
| 06/05/2019 | SIDA staff |  | SIDA | KII | M | 2 |
| 06/05/2019 | ECHO staff |  | ECHO | KII | W | 1 |

## Demographic Data of Focus Group Discussions

| Country | No. Focus Group Discussions | No. of Interviews | Female participants | Male participants |
| --- | --- | --- | --- | --- |
| Cameroon | 3 | 33 | 35 | 41 |
| Bangladesh | 3 | 36 | 46 | 21 |
| Colombia | 3 | 27 | 63 | 18 |
| South Sudan | 3 | 17 | 26 | 23 |
| Jordan | 10 | 28 | 68 | 38 |
| New York | 0 | 23 | 19 | 5 |
| Geneva | 0 | 10 | 7 | 5 |
| Skype | 1 | 30 | 38 | 8 |
| Total | 23 | 204 | 302 | 159 |

## Stakeholder analysis.

Figure 1 Key stakeholders for Normative Mandate, as identified by HACRO

NOTE: Blue for HACRO NY, Yellow for HACRO Geneva. NY stakeholders have been weighted to reflect relative importance; Geneva stakeholders have not been weighted

Figure 2: Key stakeholders for Coordination Mandate, as identified by HACRO*

NOTE: Blue for HACRO NY, Yellow for HACRO Geneva. NY stakeholders have been weighted to reflect relative importance, Geneva stakeholders have not been weighted

Figure 3: Key stakeholders for Operational Mandate, as identified by HACRO*

NOTE: Blue for HACRO NY, Yellow for HACRO Geneva. NY stakeholders have been weighted to reflect relative importance, Geneva stakeholders have not been weighted

## Evaluation Survey Results & Protocol

#### On-line global survey protocol

Overview

Purpose
The purpose of the survey is to better understand different aspects of UN Women’s contribution to humanitarian action.

Who is being asked to complete the survey?

The survey is directed toward UN Women staff working on HA, UN agencies, INGOs, national NGOs and donors.

What is it going to be used for?

The survey results will be treated as a specific data set in how the evaluation answers different questions. The data will remain anonymous and raw data will be administered by DARA, results will be shared with UN Women so that the data can potentially be used as a data point for other IEAS exercises later in time, before sharing the information data will be anonymized.

Completing the Survey

The survey consists of 21 questions that are answered by all respondents and then separate sections for different respondent types. In the below list of questions, those to be answered by UN Women staff are denoted with an  ( I) for internal and those to be answered by other cohorts are denoted with an ( E ) for external. We expect that the survey will take between 20 - 25 minutes to complete.

Summary

Thank you for participating in the Global Corporate Thematic Evaluation of UN Women's Contribution to Humanitarian Action (HA). This survey is directed toward UN Women staff working on Humanitarian Action, UN agencies, INGOs, national NGOs and donors.

The purpose of the survey is to better understand different aspects of UN Women’s contribution to humanitarian action. This questionnaire is designed to ensure you are able to contribute to the full range of questions that will be covered in this evaluation. We appreciate your time and consideration of the issues included in this questionnaire and ask that you complete the survey by Thursday 28th February 2019.

The information collected will remain anonymous and raw data will be administered by DARA, results will be shared with UN Women so that the data can potentially be used as a data point for other IEAS exercises later in time, before sharing the information data will be anonymized.

Your participation will be highly appreciated as we analyse the results of the UN Women’s contribution to humanitarian action. We estimate that the survey will take between 20 - 25 minutes to complete. Thank you very much for your time and support. Please start the survey now by clicking on the button below.

Demographics

Name:

Title:

Gender:

Organisation:

Country:

Type of Office (HQ; Regional; Country; Sub-office, Programme Presence)

Time in Position:

Respondent Type

UN Women (Global)

UN Women (Regional)

UN Women (Country Office)

UN agency

International NGO

IFRC

The Inter-Agency Standing Committee (IASC)

National NGO

Donor

Independent Gender Specialist

The Gender Standby Capacity Project (GenCap)

Government

Other (please specify)

If working in an UN agency, please select:

International Organization for Migration (IOM)

Food and Agriculture Organization (FAO)

International Fund for Agricultural Development (IFAD)

International Labour Organization (ILO)

International Maritime Organization (IMO)

Joint United Nations Programme on HIV/AIDS (UNAIDS)

Office of the United Nations High Commissioner for Refugees (UNHCR)

UN Women (UN Women)

United Nations Children's Fund (UNICEF)

United Nations Development Programme (UNDP)

United Nations Environment Programme (UNEP)

United Nations Framework Convention on Climate Change (UNFCCC)

United Nations Human Settlements Programme (UN-Habitat)

United Nations International Strategy for Disaster Reduction (UNISDR)

United Nations Office for the Coordination of Humanitarian Affairs (OCHA)

United Nations Population Fund (UNFPA)

United Nations Relief and Works Agency for Palestine Refugees in the Near East (UNRWA)

United Nations Research Institute for Social Development (UNRISD)

United Nations University (UNU)

World Bank Group (World Bank Group)

World Food Programme (WFP)

World Health Organization (WHO)

General

- How long have you worked with UN Women? 
(Scale: . 0 - 6 months; . 6 – 12 months; . 1 – 3 years; 3 – 5 years; more than 5 years)

- UN Women’s work in humanitarian action is important for effective and principled humanitarian action.  
(Scale: 1. Strongly disagree to 10. Strongly Agree.)

- (E) In a few words please describe your work with UN Women.  (Open ended)

- (I) In a few words please describe your work within UN Women. (Open ended)

1--Not at all    2-- Somewhat    3 --Significantly 	4—Completely	Don’t Know (DK)/Not relevant (NR)

1      2       3     4       DK

Relevance

- (I/E) Is UN Women’s role in humanitarian action relevant to ensuring HA is more gender responsive? (1.0)

(I /E)Does UN Women concentrate its efforts in the right areas to ensure gender responsive humanitarian action? (1.2)

- (I/E) Please rate the relative importance you would give to the different areas and activities in which UN Women focuses its work:

(1: Not at all important; 2: Slightly Important; 3: Fairly Important; 4: Very Important)

a. Provide gender expertise to global humanitarian coordination mechanisms

b. Provide gender expertise to field level humanitarian coordination mechanisms

c. Provide technical gender in humanitarian action input into the formulation of humanitarian normative policy, standards, guidance resources etc.

d. Ensure gender is integrated throughout all stages of humanitarian assessments, planning, implementation and monitoring

e. Ensure availability and use of sex-disaggregated data and gender analysis in the development of humanitarian action response plans

f. Ensure accountability on mainstreaming gender across humanitarian action

g. Contribute to women’s organizations playing a leadership role in humanitarian response and recovery effort

h. Enable women and women’s groups to contribute to disaster risk management plans

i. Implement projects enabling women to access the information, skills and resources they need to secure livelihood opportunities in humanitarian contexts to build their self-reliance and resilience through empowerment

j. Efforts to prevent and respond to SGBV

k. Ensuring accountability on IASC gender in humanitarian action policy and helping roll out the IASC Policy (and Accountability Framework) on Gender Equality and the Empowerment of Women and Girls in Humanitarian Action

l. Work on ensuring women and girls leadership and participation in humanitarian action

m. Strengthening assessments of the gender dimensions of disaster risk

n. Promotion of gender-responsive National Disaster Risk Management Policies and Governance

o. Contribution to resource mobilization efforts for resilience approaches that include gender equality and women/girls empowerment.

p. Strengthening the capacity of women to prevent, prepare for, and recover from climate and conflict related shocks

- (I/E) How else is UN Women’s work important to humanitarian action? (open ended)

Coordination & Coherence

(I/E)

Does UN Women contribute to making coordination mechanisms for humanitarian response more gender-sensitive? (4.0)

(I/E)

Does UN Women enhance coherence amongst humanitarian actors on gender equality and women's empowerment? (5.0)

Effectiveness

- (I/E) How useful for effective humanitarian action are UN Women’s guidance in relation to knowledge on gender-responsive humanitarian action and with respect to accountability frameworks? (NORMATIVE)

(I/E) How effective is UN Women’s work to enhance gender-responsive policies for humanitarian action? (7.0)

(I) Does UN Women contribute to more women and girls playing a greater role in humanitarian response and recovery efforts, including disaster risk reduction (DRR)?  (7.1)

(I)Does UN Women contribute to more women and girls being better served by humanitarian response and recovery efforts, including disaster risk reduction (DRR)? (7.2)

(I/E) Does UN Women ensure that accountability mechanisms are effective for integrating gender equality across a response?  (8.0)

- (I /E) Please categorise the following into enabling or limiting factors in UN Women’s work in humanitarian action (Categorise each of the following):

  - Funding

  - Prioritization of humanitarian action within UN Women

  - Expertise in humanitarian action

  - UN Women experience in humanitarian action

  - UN Women Internal procedures (such as procurement, recruitment, disbursement of funds, etc…)

  - Internal human capacity

  - UN Women organizational flexibility

  - UN Women mandate

- (I) To what extent is learning from the field feeding into UN Women’s global approaches to gender equality and women’s empowerment and vice-versa? (open ended)

Efficiency

- (I) Are UN Women’s processes and procedures efficient in the context of a humanitarian response? “(such as procurement, recruitment, disbursement of funds, etc…) (14.0)

- Does UN Women have the right capacity in place for humanitarian action?

(Open ended)

Closing

- (I/E) Do you have any other comments about UN Women’s work in humanitarian action? (Open ended)

- Are there any issues that this survey has neglected or that deserve more attention?

Thank you very much for completing this survey.

#### Survey results and analysis.

The complete analysis of the survey can be found here.

## Semi-structured Interview Protocol

Name: 					Title:

Organisation:

Time/Date:

UN Women Humanitarian Strategy (2014 – 2017)

OVERALL GOAL OF UN WOMEN’S HUMANITARIAN STRATEGY: Integration of gender equality and women’s empowerment considerations in the development and implementation of normative, policy and procedures in humanitarian action.

From UN Women’s Strategic Plan (2014-17):

Outcome 4.3: Gender equality and women’s empowerment commitments adopted and implemented throughout humanitarian action including preparedness, disaster risk reduction, response and early recovery.

Output 4.3.1: Evidence-based knowledge on gender-responsive humanitarian action including performance measurement and accountability frameworks, is accessible to policy-makers, practitioners and decision-making bodies.

Output 4.3.2: Enhanced national and regional capacity of institutions and partners to develop and implement gender-responsive policies and measures for humanitarian action.

Output 4.3.3: Existing coordination mechanisms are more gender-responsive and better analyse and address the distinct needs of women, girls, men and boys.

Strengthening of UN Women’s capacity in humanitarian action will be done through a multifaceted approach:

- Recruitment of staff where demand for dedicated technical expertise cannot be met by the current office structure in humanitarian contexts;

- Developing strategic partnerships with key humanitarian stakeholders, offering stand-by personnel through technical rosters; and

- Continued capacity building of its senior national staff to create a pool of cadre that could be deployed on detail assignments.

Purpose & Objectives

Evaluator will describe evaluation’ objectives how these relate to UN Women’s strategy, and the specific purpose, process, outputs and expected outcomes of the interview. This protocol is based on a semi-structured approach to interviews, implying that while there will be standard questions, as included here, there will also be adequate time to explore issues related to specific respondents’ experiences.

The primary purpose of the evaluation is to assess UN Women’s approach to humanitarian action at the global, regional and country levels, as well as the integration of human rights approaches and gender equality principles into its humanitarian work. The Evaluation will inform UN Women´s strategic decisions regarding its approach to Humanitarian Action. The Evaluation’s objectives include:

- Assess the relevance / appropriateness of UN Women’s humanitarian action across its tripartite mandate (normative, coordination, operational) in addressing local needs and priorities and increasing ownership and accountability on integrating gender into humanitarian action.

- Assess the effectiveness and efficiency of UN Women’s contributions in prevention, preparedness, response, recovery and resilience.

- Assess the extent to which UN Women’s interventions are connected to longer-term and development efforts and support sustainable approaches to recovery and disaster risk reduction.

- Analyse how human rights approaches and gender equality principles are integrated into humanitarian action.

- Identify and validate innovations and an optimal set of services, as well as lessons learned and good practice examples, in UN Women’s humanitarian work.

- Provide actionable recommendations with a view to solidify UN Women’s work in humanitarian action.

Qualitative Evidence

As a primary means for collecting qualitative evidence, the evaluation team will ask standard questions of all respondents from UN Women and other humanitarian actors.  We do this to examine patterns across different groups of respondents rather than being overly biased by the responses of any single respondent.

In practice, the interview will focus on 1 or 2 questions per evaluation criteria. These will be selected as based on the respondents’ roles and responsibilities. Questions may be also tailored for specific respondents. Specific examples will be elicited as often as possible. References to specific evaluation questions are included.

As noted in the analytical framework, some questions are meant to be exploratory and/or to solicit examples of best/emerging practices or challenges. Others are specific to our Qualitative Data Trend Analysis, the latter of which are identified by an “*”.

| QUESTIONS | Government | Donors | Affected Populations | UN Women Staff | International NGOs | Partners /National NGOs | UN Agencies |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Overall |  |  |  |  |  |  |  |
| - Please describe your role and the primary aspects of your work that relate to how UN Women contributes to humanitarian action (normative, coordination/policy, and operational activities). | X | X |  | X | X | X | X |
| Relevance |  |  |  |  |  |  |  |
| - Describe the relevance of UN Women’s normative, coordination, and operational work in humanitarian action as it relates to your work? (1.0) * | X | X |  | X | X | X | X |
| - Given your work with UN Women/Other humanitarian organisation, is it working in the right places to ensure a gender effective humanitarian response? Please provide examples and other areas where it could work. (1.2) * |  | X |  | X | X | X | X |
| Appropriateness |  |  |  |  |  |  |  |
| - What does UN Women do, if anything, to ensure that its work in humanitarian action meets the needs and priorities of affected populations (Men and women of different age and diverse background)? What else might it be doing? (2.0) * |  |  | X | X | X | X |  |
| - Does UN Women adhere to the humanitarian principles of humanity, neutrality, impartiality and independence in its humanitarian action efforts? (3.0) |  | X |  | X | X |  | X |
| Connectedness & Coherence |  |  |  |  |  |  |  |
| - How does UN Women’s work in humanitarian action complement the ways in which women and girls are served by other humanitarian actors, civil society, and local and national government? Please provide examples and areas where it could do more or less. (4.0) * | X | X |  | X | X | X | X |
| - To what extent does UN Women's work in humanitarian action contribute to longer term development, taking into account the humanitarian – development nexus? (Purposefully asks for respondents to cite their own opinion on the matter.) (4.0) * | X | X |  | X | X |  | X |
| Partnerships |  |  |  |  |  |  |  |
| - Is UN Women investing in the right partnerships in humanitarian action in the right way? (5.0) | X | X |  | X | X | X | X |
| - What are the key partnerships that can support UN Women to achieve its mandate? (5.1) | X | X |  | X | X | X | X |
| - What are the enabling factors and challenges to effective partnerships for UN Women? (5.2) |  | X |  | X | X | X | X |
| - To what extent do partnerships enable UN Women to maximise gender equality and women's empowerment in humanitarian action? (Practical examples are needed here.) | X | X |  | X | X | X | X |
| Effectiveness |  |  |  |  |  |  |  |
| - Please describe how UN Women’s activities support women and girls during a humanitarian response? (6.0) |  |  | X | X | X | X | X |
| - How has UN Women contributed to more women and girls playing a greater role in humanitarian response and recovery efforts, including disaster risk reduction (DRR)? (6.1) |  |  | X | X | X | X | X |
| - To what extent has UN Women contributed to more women and girls being better served by humanitarian response and recovery efforts, including disaster risk reduction (DRR)? (6.2) |  |  | X | X | X | X | X |
| - To what extent does UN Women work with affected populations and civil society in ways that enable them to be active in a humanitarian response? (6.3) * |  |  | X | X | X | X | X |
| - How does UN Women contribute to making coordination mechanisms for humanitarian response more gender-sensitive? (6.4) * |  | X |  | X | X |  | X |
| - To what extent and how are the different areas of the mandate reinforcing each other? (May need to define ‘accountability” and then seek tangible examples.) (6.5) * |  |  |  | X |  |  | X |
| - How do UN Women staff and other actors leverage quantitative and qualitative evidence towards expected outcomes and goals at the field level? (Practical examples are needed here.) (7.0) |  |  |  | X |  |  | X |
| - To what extent is learning from initiatives implemented in the field feeding into the global approach and vice-versa? (Practical examples are needed here.) (7.1) |  |  |  | X |  |  |  |
| - What are the enabling and limiting factors that contribute to achieving results? Are there any opportunities and entry points for scaling up? (Practical examples are needed here.) (8.0) |  | X |  | X | X |  | X |
| Efficiency |  |  |  |  |  |  |  |
| - In consideration of specific activities, were some more efficient and/or cost effective than others toward achieving broader objectives? if so, what contributed to these differences? (9.0) |  |  |  | X | X |  | X |
| - To what extent has UN Women’s institutional arrangements, operational mechanisms and financial resources advanced an effective and efficient response? (May relate to a limited number of respondents.) (9.1) |  |  |  | X | X | X | X |
| - Does UN Women have the appropriate expertise and capacities to support gender equality and women’s empowerment in humanitarian action? (10.0) | X | X |  | X | X | X | X |
| - Does UN Women have adequate surge capacity to respond rapidly to emergencies? (10.1) | X | X |  | X | X | X | X |
| Gender Equality & Women’s Empowerment |  |  |  |  |  |  |  |
| - How has UN Women humanitarian work addressed the underlying causes of gender inequality and discrimination? (Purposefully broad and open ended. Will be drawn from how respondents have thought through preceding questions. Will be used to add nuance to more direct analysis.) (11.0) | X | X | X | X | X | X | X |
| - To what extent does the humanitarian action work undertaken by UN Women address the underlying causes of inequality and discrimination, including those experienced by the LGBTQI community and women with disabilities? (Purposefully broad and open ended. Will be drawn from how respondents have thought through preceding questions. Will be used to add nuance to more direct analysis.) (11.1) | X | X | X | X | X | X | X |
| - To what extent were a human rights-based approach and gender equality incorporated in the design and implementation of UN Women’s humanitarian action? (Purposefully broad and open ended. Will be drawn from how respondents have thought through preceding questions. Will be used to add nuance to more direct analysis.) (11.2) |  | X |  | X | X |  | X |
| Sustainability |  |  |  |  |  |  |  |
| - To what extent is UN Women's work in humanitarian action sustainable, including DRR, recovery, and other aspects along the humanitarian - development nexus? (12.0) * | X | X |  | X |  |  | X |
| - What needs to be done to ensure the sustainability of UN Women’s normative, coordination, and operational work in relation to humanitarian action at the global, regional, and country levels? (Practical examples are needed here.) | X | X |  | X |  |  | X |
| Exploratory Questions |  |  |  |  |  |  |  |
| The evaluation team will then ask any follow-up questions where additional detail or more clarity would be useful. | X | X | X | X | X | X | X |
| Closing |  |  |  |  |  |  |  |
| - Do you have any recommendations for UN Women to improve its contribution to humanitarian action? | X | X | X | X | X | X | X |
| - Is there anything we haven’t discussed that you expected we would discuss? Any other points you’d like to raise? | X | X | X | X | X | X | X |
| - What are your expectations for this evaluation? | X | X | X | X | X | X | X |

## Self-Assessment Protocol

Regional Self-Assessment Questionnaire for Humanitarian Advisors

February 2019

The evaluation recognises that Humanitarian Advisors play a key role in UN Women’s contribution to humanitarian action. This questionnaire is designed to ensure you are able to contribute to the full range of questions that will be covered in this evaluation. The questionnaire may be followed by further substantive discussion with you and other key stakeholders in your region. Through this self-assessment the evaluation seeks to:

- Offer regional Humanitarian Advisors an opportunity to be further involved in the evaluation and share any issues of concern;

- Reflect on UN Women’s HA efforts, the quality, results and internal and external factors that have influenced its impact

We appreciate your time and consideration of the issues included in this questionnaire and ask that you return the survey to us by email before [date]. All information provided will remain strictly confidential and will not be shared outside the DARA team. Your participation will be highly appreciated as we analyse the results of the UN Women’s contribution to humanitarian action.

- Name (optional): 					Country/Region:

- Gender:

- Position:

- Starting date as Humanitarian Advisor/current position:

| Consultant |  |
| --- | --- |
| UN Women staff |  |

- Contract:

| Full-time |  |
| --- | --- |
| Part-time |  |
| Other distribution of time (please specify) |  |

- Time allocated to Humanitarian Advisor role/other areas of work:

- Previous position:

EQ 1. Is UN Women's work relevant to making humanitarian action more gender responsive?

  - How relevant are different aspects of UN Women's normative, coordination, and operational work to the needs of women and girls in different humanitarian contexts in your region?

Please explain/comment:

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t Know |
| --- | --- | --- | --- | --- | --- | --- |
| Normative |  |  |  |  |  |  |
| Coordination |  |  |  |  |  |  |
| Operational |  |  |  |  |  |  |

  - In the context of New Way of Working (NWOW), UN reform, and the Grand Bargain, is UN Women positioned to integrate gender equality in humanitarian action in your region?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |

Please provide your comments on the following;

- In what ways is UN Women well-positioned to achieve this?

- Are there any gaps?

EQ 2. To what extent has UN Women’s response been appropriate in the context of the needs and priorities of the affected populations, particularly those left furthest behind in humanitarian contexts in your region?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

2.1. Can you provide an example of an appropriate humanitarian response (either current or past) undertaken by UN Women in your region?

a. How was it appropriate to the needs and priorities of the affected populations?

b. How was it appropriate to those left furthest behind?

EQ3. How successful has UN Women been in designing and implementing its humanitarian work in your region to contribute to longer term development and sustainability, taking into account the humanitarian – development nexus?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all successful; 2: Minimally successful; 3: Somewhat successful; 4: Mostly successful; 5: Very successful, and add narrative comments as appropriate]

|  | Very successful | Mostly successful | Somewhat successful | Minimally successful | Not at all successful | Don’t Know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

3.1. In what ways has UN Women engaged across the humanitarian-development-peace continuum to complement and enhance UN efforts in your region to move away from a short-term, service provision model to one that contributes to sustainable development?

3.2 Was the assistance provided in a way that took account the longer-term context?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Strongly disagree; 2: Disagree; 3: Somewhat agree; 4: Agree; 5: Strongly agree, and add narrative comments as appropriate]

|  | Strongly agree | Agree | Somewhat agree | Disagree | Strongly disagree | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

3.3 How would you rate UN Women’s ability to design and implement its humanitarian work overall?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Very poor; 2: Poor; 3: Fair; 4: Good; 5: Very good, and add narrative comments as appropriate]

|  | Very good | Good | Fair | Poor | Very poor | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

EQ4. To what extent is UN Women effective in integrating gender equality and women’s empowerment in humanitarian action through its normative, coordination, and operational work?

4.1 To what extent has UN Women contributed to more women and girls playing a greater role in humanitarian response and recovery efforts, including disaster risk reduction (DRR) in your region?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

4.2 To what extent has UN Women contributed to more women and girls being better served by humanitarian response and recovery efforts, including disaster risk reduction (DRR) in your region?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

4.3 To what extent does UN Women work with affected populations and civil society in ways that enable them to be active in a humanitarian response?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

  - Can you provide one or more successful example(s) of this in your region?

4.4 To what extent has UN Women contributed to strengthened norms and standards on gender equality in humanitarian action (GiHA) in your region?

To what extent has UN Women supported the implementation of norms and standards on GiHA in humanitarian response?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

4.5 How would you rate UN Women’s contribution to making coordination mechanisms for humanitarian response more gender-sensitive in your region?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Very poor; 2: Poor; 3: Fair; 4: Good; 5: Very good, and add narrative comments as appropriate]

|  | Very good | Good | Fair | Poor | Very poor | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

4.6 How have these efforts translated into changes in humanitarian response at the regional and country level?

a. What are the major challenges in doing this?

b. Can you provide any examples of success in your region?

EQ5. To what extent is learning from the field feeding into UN Women’s global approaches to gender equality and women’s empowerment and vice-versa?

5.1 What are the processes used to provide feedback to HQ staff on learning from the field?

a. How is knowledge shared between HQ, regional and country offices?

b. How are decision-making processes communicated and managed?

5.2 How would you rate the effectiveness of the feedback loops at country, regional and HQ level?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Very poor; 2: Poor; 3: Fair; 4: Good; 5: Very good, and add narrative comments as appropriate]

|  | Very good | Good | Fair | Poor | Very poor | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Knowledge |  |  |  |  |  |  |
| Decision-making |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

EQ6. Does UN Women have the appropriate expertise and capacities to support gender equality and women's empowerment in humanitarian action?

6.1 How would you rate the appropriateness of the expertise in your office to support gender equality and women’s empowerment in humanitarian action?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Very poor; 2: Poor; 3: Fair; 4: Good; 5: Very good, and add narrative comments as appropriate]

|  | Very good | Good | Fair | Poor | Very poor | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

6.2 How adequate is the capacity (including human and programmatic resources) in your regional and country offices to support gender equality and women’s empowerment in humanitarian action?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Very poor; 2: Poor; 3: Fair; 4: Good; 5: Very good, and add narrative comments as appropriate]

|  | Very good | Good | Fair | Poor | Very poor | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

EQ7. What are enabling and limiting factors (internal and external) that contribute to the achievement of results and what actions need to be taken to overcome any barriers that limit progress?

7.1 What factors (internal and external) enable UN Women to achieve intended results in humanitarian action?

7.2 What factors (internal and external) limit UN Women’s ability to achieve intended results in humanitarian action?

7.3 What actions are required to overcome any barriers that limit progress?

7.4 Are there any opportunities and entry points for further scaling up?

EQ8. Do UN Women’s institutional arrangements and mechanisms support efficient and timely humanitarian response?

8.1 To what extent has UN Women’s institutional arrangements, operational mechanisms, and financial resources advanced an effective and efficient response in your region?

Note: Institutional arrangements refer to the policies, systems, and processes that organizations use to legislate, plan and manage their activities efficiently and to effectively coordinate with others in order to fulfil their mandate. (UNDP definition)

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Institutional arrangements |  |  |  |  |  |  |
| Operational mechanisms |  |  |  |  |  |  |
| Financial resources |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

8.2 How would you rate UN Women’s contribution to ensuring accountability for integrating gender equality across the response?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Very poor; 2: Poor; 3: Fair; 4: Good; 5: Very good, and add narrative comments as appropriate]

|  | Very good | Good | Fair | Poor | Very poor | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

EQ9. How has UN Women’s humanitarian work addressed the underlying causes of gender inequality and discrimination?

9.1 To what extent does the humanitarian action work undertaken by UN Women in your region address the underlying causes of inequality and discrimination, including those experienced by the LGBTQI community and women with disabilities?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

9.2 To what extent were a human rights-based approach and gender equality incorporated in the design and implementation of UN Women’s humanitarian action?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

EQ10. To what extent is UN Women's work in humanitarian action sustainable, including DRR, recovery, and other aspects along the humanitarian - development nexus?

10.1 To what extent has UN Women enhanced national and local ownership, overall and in your region?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Not at all; 2: Minimally; 3: Partially; 4: Mostly; 5: Completely, and add narrative comments as appropriate]

|  | Completely | Mostly | Partially | Minimally | Not at all | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Overall |  |  |  |  |  |  |
| Region |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

10.2 How often does programming take into account the sustainability of UN Women’s work on humanitarian action in your region?

[Please fill with an “X” in the table below on a scale from 1 to 5 - 1: Never 2: Rarely; 3: Sometimes; 4: Mostly; 5: Always, and add narrative comments as appropriate]

|  | Always | Mostly | Sometimes | Rarely | Never | Don’t know |
| --- | --- | --- | --- | --- | --- | --- |
| Rating |  |  |  |  |  |  |
| Comment |  |  |  |  |  |  |

Closing questions:

What does UN Women have to prioritise in the future to be more effective in its humanitarian action efforts?

Are there any other comments you would like to make and/or suggestions that the evaluation team should take into account? Is there anything you expected us to ask about that we didn’t?

Please remember to complete Annex I – List of Projects, which was sent to you with this questionnaire.

THANK YOU!

## Portfolio Review- High level findings

#### Summary

The portfolio review analysed documents across 40 countries, including strategic notes, annual reports, quarterly RMS monitoring reports and past evaluations. The process sought to determine the types of humanitarian activities undertaken at the country and regional level, active partnerships, engagement in coordination mechanisms, and UN Women’s participation across the humanitarian programme cycle. In addition, the portfolio review conducted financial analysis of UN Women’s humanitarian programming and its incorporation into relevant humanitarian response plans. Due to limitations in the way humanitarian budgets are identified in UN Women’s systems (i.e. under the same outcome as WPS, sometimes covered under other outcomes for simplicity of reporting), the evaluation reviewed financial data for activities across 40 countries and determined, based on the output description and quarterly monitoring data, whether to include this in the below summary of humanitarian budgets.

#### Key Findings

In 2018, UN Women has funded humanitarian action activities in 27% of the countries in which it has a presence although only 14 countries, or 15% of the countries where it works, had HA budgets over $500,000. This compares with 28 countries with HRPs, the average appeal of which is $963,273,184. Of the 3 countries with the largest HRP appeals in 2018 (Yemen, Lebanon & Turkey), UN Women’s actual HA budget accounts for 0.03% of the appeal in Yemen, 0.06% of the appeal in Lebanon, and 0.16% of the appeal in Turkey.

Table 1 Countries with HA budget and activities

|  | Number of countries with HA budget | Number of countries with HA activities | Number of countries where UNW is present |
| --- | --- | --- | --- |
| 2018 | 25 | 27 | 90 |
| 2017 | 27 | 30 | 107 |
| 2016 | 26 | 32 | 93 |

Note: Sometimes activities are recorded although no budget is allocated.

UN Women’s actual humanitarian budget increased by $2,873,653 or 14% in the 2 years from 2016 to 2018.

Table 2 Actual Humanitarian Budget 2016-2018

|  | Total HA budget identified | Average HA budget per country | Largest budget | Smallest budget |
| --- | --- | --- | --- | --- |
| 2018 | $23,037,508 (25 countries) | $921,500 | $4,616,121 (Jordan) | $20,212 (Mozambique) |
| 2017 | $19,062,568 (27 countries) | $706,021 | $3,199,160 (Lebanon) | $20,084 (WCARO) |
| 2016 | $20,163,855 (27 countries) | $775,533 | $4,209,425 (DRC) | $10,036 (Colombia) |

UN Women’s growth in humanitarian action has occurred almost entirely from non-core resources:

Table 3 Comparison of core and non-core resources available for humanitarian action

| Year | DRF (core) | DRF (non-core available) | Total | Non-core/sum of core and non-core (%) |
| --- | --- | --- | --- | --- |
| 2018 | $ 951,133.00 | $ 15,741,293.00 | $ 16,692,426.00 | 94% |
| 2017 | $ 726,432.00 | $ 19,768,202.00 | $ 20,494,634.00 | 96% |
| 2016 | $ 892,986.00 | $ 17,948,201.81 | $ 18,841,187.81 | 95% |

This is based on the DRF databased on humanitarian action which includes indicative figures (not certified figures) available on RMS. It does not include any resource allocated to HQ units or OEEF.

UN Women’s participation in HRPs has declined in the 3 years from 2016-2018, going from 16/41 HRPs in 2016 (39%) to 8/27 in 2018 (29%).

2017 was the most successful year for UN Women’s participation in HRPs, with almost 42% of their overall appeal amount funded. This was largely due to the positive result in Cameroon, with 31% of UN Women’s HRP amount receiving funding.

Table 4 UN Women Participation in HRPs 2016-2018

|  | 2016 | 2017 | 2018 |
| --- | --- | --- | --- |
| Number of countries with HRP appeals | 41 | 37 | 27 |
| Countries with HRP where UNW has presence | 32 | 27 | 24 |
| Countries with HRP where UNW has HA budget | 18 | 18 | 17 |
| Number of countries where UNW included in appeal | 16 | 10 | 8 |
| UNW total funds requested in appeals | $36,342,314 | $17,863,074 | $27,984,559 |
| Average size of UNW ask as % of total appeal | 0.94% | 0.76% | 0.74% |
| Number of appeals where UNW received funding | 5 | 3 | 3 |
| UNW total funds received from appeals | $2,896,241 | $7,490,798 | $2,422,104 |
| Percentage of UNW appeal funded | 7.97% | 41.93% | 8.66% |

Trends from 2016 to 2018 show a decrease in successful resource mobilisation, with 2017 being particularly low at 49%.

Table 5 Yearly evolution of HA budget (2016-2018).

|  | 2018 | 2017 | 2016 |
| --- | --- | --- | --- |
| Total planned HA budget | $33,907,197 | $38,652,967 | $28,010,418 |
| Actual HA budget mobilized | $23,037,508 | $19,062,568 | $20,163,855 |
| % of planned HA budget mobilized | 68% | 49% | 72% |

Figure 1 UN Women humanitarian budget (Planned vs. actual)

The below table shows the 10 largest HRP appeals in 2018, the UN Women humanitarian budget for each country (actual) and what percentage of the HRP each budget represents;

Table 6 UN Women HA budget as % of HRP

|  | HRP Amount 2018 | UNW HA Budget 2018 | UNW budget as % of HRP |
| --- | --- | --- | --- |
| Yemen | $3,108,067,800 | $997,508 | 0.03% |
| Syria 3RP - Lebanon | $2,291,098,474 | $1,486,190 | 0.06% |
| Syria 3RP - Turkey | $1,743,677,229 | $2,713,208 | 0.16% |
| Republic of South Sudan | $1,717,890,485 | $375,131 | 0.02% |
| Democratic Republic of the Congo | $1,675,200,000 | $156,010 | 0.01% |
| Somalia | $1,542,514,570 | $105,000 | 0.01% |
| Ethiopia | $1,177,218,620 | $0 | 0.00% |
| Nigeria | $1,047,768,587 | $658,303 | 0.06% |
| Syria 3RP - Jordan | $1,043,346,938 | $4,616,121 | 0.44% |
| Sudan | $1,007,555,093 | $1,319,375 | 0.13% |

The table below shows the most common types of activities by year, including the number of countries that reported conducting each type of activity.

Table 7 Most common types of activities by year

| 2018 | # of countries | 2017 | # of countries | 2016 | # of countries |
| --- | --- | --- | --- | --- | --- |
| Technical assistance | 21 | Technical assistance | 23 | Technical assistance | 23 |
| Capacity building of HA actors | 18 | Capacity building of HA actors | 16 | Capacity building of HA actors | 20 |
| SGBV prevention & response | 11 | Livelihoods | 11 | SGBV prevention & response | 16 |
| Livelihoods | 11 | Women’s centre | 11 | Livelihoods | 13 |
| Coordination | 9 | SGBV prevention & response | 10 | Women’s centre | 11 |

Note: DRR capacity building was captured as a separate activity

The total number of countries with DRR activities (response, preparedness, normative, capacity building) were 9 in 2016; 11 in 2017; and 8 in 2018. The below table shows a breakdown of countries recording different types of DRR activities;

Table 8 Number of countries with DRR activities by type

| DRR Activity | # of Countries 2018 | # of Countries 2017 | # of Countries 2016 |
| --- | --- | --- | --- |
| DRR Preparedness | 1 | 7 | 4 |
| DRR Response | 2 | 9 | 2 |
| DRR Capacity Building | 6 | 5 | 8 |
| DRR Normative/ Standard Setting | 4 | 6 | 7 |

The below table shows the actual HA budgets by region, from 2016 to 2018. The Arab States region has consistently been responsible for more than a third of UN Women’s humanitarian budget. Both African regions have seen a decline in their budgets between 2016 and 2018.

Table 9 HA budgets by region

|  | 2016 | % of total HA 2016 | 2017 | % of total HA 2017 | 2018 | % of total HA 2018 | Budget variance 2016 vs 2018 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Americas & Caribbean | $335,977 | 2% | $659,408 | 3% | $1,119,504 | 5% | 233% |
| Arab States | $7,124,139 | 35% | $7,421,097 | 39% | $8,298,911 | 36% | 16% |
| Asia Pacific | $1,712,186 | 8% | $1,615,655 | 8% | $5,610,903 | 24% | 228% |
| East & Southern Africa | $3,105,761 | 15% | $4,213,782 | 22% | $2,716,804 | 12% | -13% |
| Europe & Central Asia | $195,523 | 1% | $1,180,763 | 6% | $2,713,208 (all Turkey) | 12% | 1288% |
| West & Central Africa | $7,690,269 | 38% | $3,971,863 | 21% | $2,578,178 | 11% | -66% |

The table below shows the countries in which the humanitarian budget accounted for 50% or more of the total CO budget between 2016 and 2018.

A total of 6 countries had a humanitarian budget of $500,000 or more for 3 consecutive years (2016-2018), namely Jordan, Iraq, Nigeria, Lebanon, Cameroon and Uganda. Three further countries had humanitarian budgets of $500,000 or more for 2 consecutive years: DRC, South Sudan and Turkey.

Table 10 Countries with 50% or more of total budget allocated to HA.

|  |  | 2016 |  |  | 2017 |  |  | 2018 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Country | Region | Actual CO Budget | Actual Budget (HA) | HA Budget as % of CO Budget | Actual CO Budget | Actual Budget (HA) | HA Budget as % of CO Budget | Actual CO Budget | Actual Budget (HA) | HA Budget as % of CO Budget |
| Jordan | Arab States | $ 5,257,018 | $ 2,739,575 | 52% | $ 4,241,411 | $ 1,875,253 | 44% | $ 6,629,089 | $ 4,616,121 | 70% |
| Turkey | Europe and Central Asia | $ 569,230 | $ - | 0% | $ 1,770,774 | $ 959,059 | 54% | $ 3,612,362 | $ 2,713,208 | 75% |
| Lebanon | Arab States | $ 1,779,541 | $ 1,321,155 | 74% | $ 3,752,523 | $ 3,199,160 | 85% | $ 2,252,998 | $ 1,486,190 | 66% |
| Sudan | East and Southern Africa | $ 252,328 | $ - | 0% | $ 709,857 | $ 48,000 | 7% | $ 1,402,041 | $ 1,319,375 | 94% |
| Cameroon | West and Central Africa | $ 1,832,648 | $ 794,181 | 43% | $ 2,074,125 | $ 855,761 | 41% | $ 1,944,476 | $ 1,118,629 | 58% |
| Yemen | Arab States | $ 212,605 | $ - | 0% | $ 1,078,938 | $ - | 0% | $ 1,893,216 | $ 997,508 | 53% |
| Iraq | Arab States | $ 3,387,184 | $ 2,487,307 | 73% | $ 2,229,705 | $ 1,793,956 | 80% | $ 3,005,914 | $ 873,461 | 29% |
| Nigeria | West and Central Africa | $ 3,354,378 | $ 1,709,155 | 51% | $ 3,848,209 | $ 2,028,309 | 53% | $ 4,744,481 | $ 658,303 | 14% |
| South Sudan | East and Southern Africa | $ 4,046,379 | $ 2,503,077 | 62% | $ 2,768,116 | $ 2,122,535 | 77% | $ 2,471,774 | $375,131 | 15% |
| DRC | West and Central Africa | $ 7,094,053 | $ 4,209,425 | 59% | $ 1,826,295 | $689,963 | 38% | $329,914 | $156,010 | 47% |
| Sierra Leone | West and Central Africa | $ 419,208 | $22,593 | 5% | $ 180,185 | $ 102,551 | 57% | $ 848,071 | $ - | 0% |
| CAR | West and Central Africa | $ 647,200 | $329,921 | 51% | $ 496,032 | $ - | 0% | $ 1,002,178 | $ - | 0% |

#### Portfolio review database

A full database of the portfolio review was developed in the data collection and analysis phase. It can be consulted clicking here.

## Enabling and limiting factors (internal and external) that contribute to the achievement of results.

Internal Factors

- The limited capacity for leading in gender in humanitarian action (see efficiency section) and the related difficulty of many UN Women COs to be accepted into the HCT, as described in the section above.

- A more systematic participation of UN Women in humanitarian coordination structures and processes, as a key point for creation and oversight of policy, and the cluster system at country level, which would significantly facilitate coherence and UN Women’s ability to play a consistent role in crisis situations.

- Current monitoring mechanisms focus on outputs and not outcomes or results. As such, the portfolio review conducted as part of this evaluation was not able to provide any insights beyond number of women that have attended certain activities. However, this is not an appropriate measure of effectiveness as the goal is not attendance but empowerment and protection. Current M&E systems do not measure this. Lack of thorough assessments and weak indicators are also insufficient to meet key donor requirements and limit UN Women’s access to funding.

- Similarly, there is limited results-based reporting. The RMS informs at the output level, with some indication of outcomes and results. Results have also been documented for various reports, such as for donors or for the HACRO annual reports, however these tend to focus on successful experiences with limited detail and analysis of the underlying factors.

- Lack of a resource mobilisation strategy in HA and better understanding of key humanitarian donors and processes has often led UN Women to pursue opportunities with less impact, to the detriment of where it can most add value. UN Women can better contribute to HNO processes, assessing GEWE needs for the overall response and define and include its needs in the HRP.

- Lack of an advocacy strategy that recognises UN Women’s key efforts at all levels and engages with donors and other key actors to influence outcomes.

External Factors

- There continues to be a misconception among many humanitarian actors that gender is a development issue that does not need to be prioritised. The evaluation team was aware of examples where even internal gender focal points were shut out of an emergency response. This highlights the need for UN Women to be more systematic about building up the evidence base and piloting examples that can showcase how and why the consideration of gender is a necessary part of an effective response.

- Competition. Gender is everyone’s mandate and UN Women is a relatively new agency with a limited track record in HA. Other agencies, like OCHA and UNHCR among others, have coordination mandates and are relied upon to also integrate gender. Lack of clarity and competition and mistrust in some occasions with UNFPA has also undermined GEWE in HA.

- In some instances, there were parallel coordination structures which made coordination less effective. For example, in Colombia, where you have the traditional cluster structure side-by-side with the structure created for the Venezuela response. While the “back-to-back” approach seeks to minimise impact, it still translates into higher demands on UN Women staff time. In Cameroon, UN Women is the GBV cluster lead in the north but not in the rest of the country. This creates confusion for partners and a lack of coherence.

## Partnership Attributes & Enabling Factors

Before entering a partnership, a clear vision and purpose of the partnership, commitment, capacity and resources are needed. These could include the following:

| Vision and Purpose | UN Women at the field, country, regional and global level needs a clear sense of why it is entering into a partnership, what it can contribute and how the partnership will be beneficial for the organisation and for shared humanitarian objectives. |
| --- | --- |
| Commitment | There has to be a strong mutual desire within UN Women and potential partners, at all levels of the organisation, to be willing to learn and share towards common goals. |
| Time | UN Women has to be prepared to devote the time necessary to make the partnership work and understand that these key partnerships are long-term in nature. |
| Capacity | UN Women needs to have the capacity to enter a partnership. UN Women has the flexibility to welcome new ideas when funding is involved but needs to first and foremost focus on strengthening its identity and capacity in strategic areas. |
| Resources | UN Women has to understand that partnerships may require effort and initial additional expenses for UN Women. Realistic budgets need to be defined and a better understanding of, where relevant, donors and their potential questions and how these will be addressed. |
| Outcomes/results | Partnerships need to define outcomes or results that will be achieved in the short term and the long term, and how success will be measured. Crafting indicators that respond to both mutual and individual goals is important. Partnership success can be defined quite differently by different partners. |

Important enablers and challenges to partnership, depending on their presence or absence, were mentioned by key UN agencies throughout the evaluation. These include:

- Similar organisational culture

- Reputation

- Respected leadership

- Shared vision, common goals and objectives

- Clear division of roles and responsibilities

- Possessing skills and capacity needed for humanitarian response

- Solutions-oriented

- Effective communication,

- Flexibility and capacity to adapt

- Willingness to share resources

- Commitment

- Value added

- Openness, transparency and trust

UN Women may consider the 12 Dynamics of Collaboration and Partnerships that build on the foundation laid by the Principles of Partnership:

Table 11. The 12 Dynamics of Collaboration and Partnerships.

12 Dynamics of Collaboration and Partnerships

1. Prioritising trust: Once trust is built amongst collaborating institutions it is much easier to agree on joint action processes, investments and tools.

2. Shared vision: Evidence from coordinated efforts and partnerships shows that groups benefit from developing a shared vision for wider influence.

3. Accepting time and transaction costs: Building partnerships takes time. Results require commitment, patience and persistence.

4. Shared risks and costs: Partnering agencies need to demonstrate financial, staffing and organisational commitment.

5. Deciding when to form partnerships: Not all circumstances call for coordination and partnership initiatives. It is neither necessary nor desirable to insist on collaboration for its own sake.

6. Ground rules for engagement: A documented TOR/MoU ensures that all parties understand the purpose and structure of engagement.

7. Prioritizing best leadership: Real partnership requires putting the best leadership forward on the basis of adequate capacity.

8. Fertile ground for growth: Partnership done well promotes innovation and growth.

9. Equality of members and balance of power: The size or influence of agencies ought not to affect equity in shared leadership and decision-making; equality is key if members are to remain willing to invest their best.

10. Benefits for all: Investments will grow if partners can see clear incentives and outcomes valuable to their agency.

11. Results-oriented action approach: Success is built when skilled implementers link conceptual tools with global field realities in pursuit of measurable goals.

12. Perpetuating a Learning Culture: Successful partnerships and collaboration encourage a learning culture.

## List of knowledge products produced by UN Women

- UN Women Humanitarian Programmes Review (internal) 2014

- Institute of Development Studies (IDS) at the University of Sussex “The effect of gender equality programming on humanitarian outcomes” (2015)

- Promoting the rights, needs and agency of women and girls in humanitarian action (2015) covering Humanitarian action; Crisis response and recovery; Disaster risk reduction; Migration

- Placing Women and Girls at the Centre, (IASC) 2015

- Promoting the Rights, Needs and Agency of Women and Girls in Humanitarian Action, 2016

- Un women, empowerment and accountability for gender equality in Humanitarian action and crisis response, 2017

- Humanitarian Programme report, Oct 11, 2017

- IASC Gender Handbook for Humanitarian Action, 2017

- IASC Reference Group on Gender and Humanitarian Action, Policy Gender Equality And The Empowerment Of Women And Girls In Humanitarian Action, November 2017

## Revised Theory of Change

UN Women’s Theory of Change underlying its contribution to Humanitarian Action

Adapted from Theory of Change underlying the development results of UN-Women’s Strategic Plan (2018-2021)

Women and girls contribute to and benefit equally from humanitarian action (shortened outcome 5 statement) and Thematic priority 11: More women play a greater role and are better served by humanitarian response and recovery efforts (Output 14)

UN Women’s engagement in Humanitarian Action

#### Assessment

At a time when crises are becoming more widespread, complex and protracted, humanitarian action needs to be more effective than ever. In 2019 an estimated 132 million people are affected by different types of crises. Women and girls continue to bare a disproportionate toll and crises often exacerbate underlying human rights abuses. When the distinct needs and capacities of crisis-affected girls, boys, women and men are not taken into account, humanitarian action may fail to reach the most vulnerable and actually lead to further harm. Despite efforts, the humanitarian community has not consistently and sufficiently prioritized and ensured gender sensitive responses and culturally relevant gender equality programming approaches that are critical in humanitarian action. Experience suggests that work on gender in humanitarian response is often the first thing which donors ask agencies to cut when decreasing programme funding. Similarly, many actors are quick to put aside gender programming to respond quickly to emergencies. Specific gendered humanitarian needs are also persistently underfunded. Routinely, there are:

- Insufficient gender analysis and evidence to inform humanitarian response planning and practice;

- Low technical capacity in gender in emergencies across sectors and organizations;

- A lack of coordination on gender across different agencies and sectors;

- Weak participation and inclusion of women and girls and distinct needs and priorities in humanitarian response;

- Lack of accountability for implementation of gender-related standards within organizations and across the humanitarian system (including donor commitments).

UN Women was specifically created to respond to these recognized gaps and as a means to strengthen and accelerate progress on GEEWG. Humanitarian action cannot be effective without the protection and empowerment of women and girls. The systematic and substantive participation, voice and agency of women and girls in humanitarian action will enable more lives to be saved, and better preserve the dignity of people in times of crisis. Engagement in humanitarian action not only enables UN Women to focus on women and girls in greatest need but ensures that as an agency it is able to take a holistic approach that encompasses the entire continuum of situations embedding the need for GEEWG solutions at the centre of its response. In doing this, UN Women can work in strong partnership with the people it serves, as well as with likeminded agencies, actors engaged in humanitarian response. By engaging in humanitarian action, UN Women is also better able to deliver on its development commitments of leaving no one behind and responding to the needs of the furthest behind first.

#### Goal

The overall goal / impact of UN Women’s contribution is effective principled humanitarian action that saves lives, alleviates suffering and maintains human dignity during and after man-made crises and natural disasters, as well as that strengthening prevention and preparedness to mitigate the impact when such situations occur. Ultimately the goal is to achieve gender equality and empower all women and girls, especially the most disadvantaged, so that they are able to benefit from the full enjoyment of their human rights.

#### Outcomes and overarching approaches

Outcomes:

Outcome 1: Gender-equality programming contributes to more effective humanitarian action; gender, age and diversity analysis informs response. Better humanitarian response based on evidence of the needs and priorities of women and girls affected by humanitarian disasters.

Outcome 2: Increased accountability, coordination and partnerships on gender in humanitarian action lead to better response.

Outcome 3: Women and girls are empowered and able to participate in humanitarian action.

Outcome 4: Gender equality is treated as an objective in humanitarian response.

Outcome 5: Enhanced solutions for women and girls, gender sensitivity and women and girl’s empowerment and protection across the humanitarian-development spectrum.

Outputs:

- Gender-responsive Humanitarian Programme Cycle processes are supported

- Emergency preparedness on GEEWG is strengthened

- Inclusion of gender analysis in planning, response and monitoring tools, including Humanitarian Needs Overviews and Humanitarian Response Plans is strengthened

- Roll-out of IASC Gender accountability framework

- Field-level humanitarian leadership on gender-equality programming by HCs, HCTs and inter cluster/sector working groups is strengthened

- Coordination on GiHA

- Advocate gender equality and women’s empowerment, the prevention of SGBV

- Advocate for women’s participation in humanitarian action

- Facilitate participation of women and girls in humanitarian action

- Rally local women’s organizations, specialised agencies, NGOs and other actors working on gender equality.

- Track progress on and ensure that humanitarian financing is gender responsive through GAM and other means

- Support evidence based principled and pragmatic approaches to the challenges of GEEWG in humanitarian action

- Capacity on gender is strengthened across agencies and sectors through training and supports operationalising guidance

- Meaningful participation of women and girls in humanitarian decision-making is facilitated

- AAP and CwC are gender sensitive and tailored to needs of women and girls

- Inter-agency partnerships on gender-equality programming are established

- Female focused interventions and efforts targeting women and girls are enhanced and better resourced

- Promote positive attitudes and behaviours of boys and men to gender equality

- Linkages between GEEWG in humanitarian action and development are strengthened

Change strategies (how):

Act as a strong, principled and persuasive advocate for the rights and needs of women and girls affected by humanitarian disasters. Humanitarian principles — humanity, neutrality, impartiality and independence — and “do no harm” are essential in humanitarian action. For that reason, governments that are directly part of a conflict cannot generally be relied upon to provide aid in an impartial and neutral manner. In these circumstances, neutral and independent parties are needed to ensure that assistance is provided according to humanitarian principles. UN Women needs to better understand and position its response in these contexts. When UN Women is present in these contexts, further guidance and oversight are needed so that humanitarian principles are not compromised, and UN Women’s reputation and credibility negatively affected.

At a time when increasing numbers of women and girls affected by crises live in a situation of long-term marginalisation, UN Women can encourage their inclusion in national services and economies, reducing their dependency on aid, enabling the progressive realisation of their rights and better preparing them for eventual solutions through advocacy efforts and by identifying partners that can support this process.

Undertake strategic, evidence-based advocacy and outreach to mobilise support for GEEWG in humanitarian action and the most disenfranchised women and girls, including through constructive engagement with boys and men and community level approaches.

Engage in creative, principled and pragmatic approaches to the challenges of GEEWG in humanitarian action that are solutions-oriented, based on an understanding of opportunities and trends, and supported by research, analysis and a strong evidence base. Contribute to advancing GEEWG policy and practical solutions for the protection of people affected by the effects of climate change and natural disasters, recognising humanitarian needs associated with events of this kind. Contribute to any inter-agency response to emergencies resulting from natural disasters, providing leadership on GEEWG, where the three criteria of field presence and capacity, a government request and inter-agency agreement are met.

Engage more decisively and predictably in humanitarian contexts based on predefined criteria, undertaking concerted operational, advocacy and strategic efforts to achieve better GEEWG in humanitarian response. Prioritise maintaining and building UN Women capacity to mobilise rapidly, reliably and effectively in response to emergencies, and strengthen emergency preparedness to become a more predictable actor, committing human, technical and financial resources to make gender equality programming the norm in all humanitarian settings. As part of a broader inter-agency response, engage in a more consistent, predictable and sustainable way in key contexts, making every effort to ensure that key needs are met and focusing on the most vulnerable. Bolster UN Women’s capacity to respond to emergencies in a rapid and effective way, mainstreaming HA throughout the organisation in order to ensure that lives are not lost, that responses are not gender blind, further harm is avoided, and protection needs and capacities not overlooked.

Strengthen gender sensitivity and women and girl’s empowerment and protection across the whole spectrum of humanitarian response, ensuring that a GEEWG perspective is central to all aspects of UN Women’s work and guides broader humanitarian action and engagement by others, strengthening operational capacity for the delivery of GEEWG in humanitarian response, prioritising measures to protect and empower the most affected women and girls.

Reinforce UN Women’s contribution to GiHA within UN/ Humanitarian Country Teams, providing GEEWG expertise and gender analysis of protection risks and needs, and driving and supporting the development of related response strategies, especially across sectors historically less sensitive to gender, and ensuring that consultation with girls and women extends to every stage of the humanitarian programming cycle, as an ongoing process.

Leverage the opportunities - created by the IASC Gender Handbook and associated accountability framework, the newly established GAM, the increasing recognition of the need to include gender equality as an outcome of humanitarian response, donors making gender analysis and SADD a funding requirement, accountability commitments on women and girls’ empowerment at the WHS - to define and champion operational partnerships and coalitions of actors, and progressively mobilise key sources of support and funding for UN Women’s critical added value in providing capacity on GEEWG.

Lead coordination of responses on GEEWG in close collaboration with other actors, working to optimise coherence within the United Nations system and engaging a broad range of actors in the context of humanitarian action; maintain technical capacity on gender in HA in key assistance sectors such as WASH, education, health, shelter, and livelihoods, and work to set policies and standards on women and girl’s participation; female-focused interventions, such as women’s centres in camps; and engage effectively in related partnerships and the coordination of responses, prioritising the most vulnerable.

Empowerment and accountability/participation, AAP and CwC: At a time when a larger than ever number of women and girls affected by crises are left in a state of dependency, UN Women can take all possible steps to ensure that women and girls can participate in decisions that affect them as agents with the potential to determine and build their own future and contribute to the development of the communities where they live. UN Women can help ensure that women and girls have access to the information they need and are able to effectively communicate their needs and priorities. UN Women, as other agencies, can hold itself accountable to the women and girls it intends to serve in all aspects of its work, by involving them in identifying and analysing their needs and the risks they face, and in designing, implementing and evaluating humanitarian response; this should include ensuring that confidential feedback mechanisms are in place for people who are unable, or prefer not to, air their concerns and grievances openly, or who wish to report abuse.

Organizational performance enablers

- Mainstream humanitarian action across UN Women. HACRO could undertake a Headquarters review, aimed at redefining and validating the structure and mix of functions provided at central level, to better support country level HA and strengthen UN Women’s ability to provide oversight and a results-based management (RBM) system to better reflect its overall goals and enable better measurement of progress in key outcome areas of GEEWG. The system should allow for analysis and learning to serve as the basis for the policies it develops, the advocacy it undertakes and the proposals it puts forward, promoting the exchange of lessons across operations and regions and cross-fertilization of ideas and experiences and peer reviews within and outside the organisation. UN Women will could invest in monitoring and accurate reporting to generate the evidence for this system, leading to evidence-based assessments, informed policy and practice, and demonstrating transparency and accountability.

- Attract capacity in HA and adapt and support UN Women’s staff: improve the human resource strategy in HA, recognising the need for dedicated, competent and diverse staff, and a more decentralised approach. Improving outreach for new talent, expanding the roster, streamlining UN Women’s assignment system, improving security management and introducing measures to better address critical gaps through enhanced workforce planning, encouraging experience, learning, interpersonal skills, commitment and innovative thought.

#### Risks and assumptions

Potential risks that can affect UN Women’s effective implementation of its humanitarian action strategy include: (i) resource mobilisation and stakeholders’ management; (ii) capacity and commitment within the agency to humanitarian action; and iii) limited buy-in by traditional actors on the need to incorporate gender and competition for limited resources.

Key assumptions include:

- There is sufficient commitment to supporting women in in crises within the organisation to develop capacity and allocate increased resources

- UN Women will engage in robust partnerships and be able to leverage opportunities and mandate

- Willingness of actors to support GEEWG in humanitarian action

| Goal | Effective principled humanitarian action saves lives, alleviates suffering and maintains human dignity during and after man-made crises and natural disasters, and prevention and preparedness mitigate the impact when such situations occur. Achieve gender equality and empower all women and girls, especially the most disadvantaged, so that they are able to benefit from the full enjoyment of their human rights. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Goal TOC statement | If women and girls are protected and empowered and meaningfully participate, then humanitarian action is more effective, more lives will be saved, and the dignity of people in times of crisis better preserved. If there is focus on women and girls in greatest need in crisis-affected areas and GEEWG solutions are central, then gender equality can be achieved, and women and girls can enjoy their rights |  |  |  |  |
| Outcomes | Outcome 1: Gender equality programming across the cycle contributes to more effective humanitarian action for all, based on evidence of the needs and priorities of women and girls affected by humanitarian disasters. | Outcome 2: Increased capacity, accountability, coordination and partnerships on gender in humanitarian action leads to better response | Outcome 3: Women and girls are empowered and able to participate in humanitarian action | Outcome 4: Gender equality is treated as an objective in humanitarian response | Outcome 5: Enhanced solutions for women and girls, gender sensitivity and women and girl’s empowerment and protection across the humanitarian-development spectrum |
| Outputs (multipurpose, serving various intersecting outcomes) | Gender-responsive Humanitarian Programme Cycle processes are supported. Gender, age and diversity analysis informs response. Inclusion of gender analysis in planning, response and monitoring tools, including Humanitarian Needs Overviews and Humanitarian Response Plans, is strengthened. Track progress on and ensure that humanitarian financing is gender responsive through GAM and other means. Capacity on gender is strengthened across agencies and sectors through training and support operationalising guidance. | Emergency preparedness on GEEWG is strengthened. Roll-out of IASC Gender accountability framework. Field-level humanitarian leadership on gender-equality programming by HCs, HCTs and inter cluster/sector working groups is strengthened. Coordination on GiHA. Rally local women’s organizations, specialised agencies, NGOs and other actors working on gender equality. AAP and CwC are gender sensitive and tailored to needs of women and girls. Inter-agency partnerships on gender-equality programming are established. | Advocate for women’s participation in humanitarian action. Facilitate meaningful participation of women and girls in humanitarian decision-making. | Advocate gender equality and women’s empowerment, the prevention of SGBV. Track progress on GEEWG humanitarian financing. Female-focused interventions and efforts targeting women and girls are enhanced and better resourced. Support evidence-based principled and pragmatic approaches to the challenges of GEEWG in humanitarian action. Promote positive attitudes and behaviours of boys and men to gender equality | Linkages between GEEWG in humanitarian action and development are strengthened Advocacy and partnerships are supported |
| Strategies | 10 Change strategies (how) |  |  |  |  |
| Key assumptions | - There is sufficient commitment to supporting women in in crises within the organisation to develop capacity and allocate increased resources - UN Women will engage in robust partnerships and be able to leverage opportunities and mandate - Willingness of actors to support GEEWG in humanitarian action |  |  |  |  |
| Risks | - Resource mobilization and stakeholders’ management - Capacity in and commitment within the agency to humanitarian action. - Limited buy-in by traditional actors on the need to incorporate gender - Competition for limited resources |  |  |  |  |

## Bibliography

#### Evaluation Report

- Assistant Secretary-General for Humanitarian Affairs and Deputy Emergency Relief Coordinator, Ursula Mueller. “Moving Forward on Gender Equality and Women’s Participation.” Remarks at the Humanitarian Networking and Partnerships Week event. International Conference Center, Geneva, 6 February 2019.

- IASC Reference Group for Gender in Humanitarian Action. “Review of IASC 2008 Policy Statement on Gender Equality in Humanitarian Action.” IASC. 18 May 2015. https://interagencystandingcommittee.org/system/files/2._review_iasc_gender_policy_final_report_narrative_report2_1.pdf

- IASC. “Commitments on Accountability to Affected People and Protection from Sexual Exploitation and Abuse.” IASC. 11 Dec 2017. https://interagencystandingcommittee.org/accountability-affected-populations-including-protection-sexual-exploitation-and-abuse/documents-56

- Janz, Mark R., Soi, Noelle, and Russel, Rebecca. “Collaboration and Partnership in Humanitarian Action.” Humanitarian Practice Network. December 2009.

- Mowjee, Tasneem, Donata Garrasi and Lydia Poole. “Coherence in Conflict: Bringing humanitarian and development aid streams together”. DANIDA. Nov 2015.

- OCHA. “2014-2017 Humanitarian Action Plan” 2013. https://www.unocha.org/sites/unocha/files/OCHA%20SF%202014-2017%20Strategic%20Plan_0_1.pdf

- OCHA. “2017 Humanitarian Annual Report” 2017.

- Transgender Europe. “The Yogyakarta Principles – How International Human Rights Protect LGBTI People.” TGEU: Transgender Europe. 31 January 2018. https://tgeu.org/yogyakarta-principles/

- UN Women Nepal. “Mainstreaming Gender Equality in the 2015 Earthquake Humanitarian Response of Nepal.” UN Women. 2017.

- UN Women. "2014 Colombia RMS". UN Women, 2014.

- UN Women. “2017-18 Annual Report.” 2018. http://annualreport.unwomen.org/en/2018

- UN Women. “Coordinating for Gender Equality Results: Corporate evaluation of UN Women’s contribution to UN system coordination on gender equality and the empowerment of women.” UN Women’s Independent Evaluation Office. 2016

- UN Women. “Empower Women and Girls and Gender as a Cross-Cutting Issue: Analytical Paper on WHS Self-Reporting on Agenda for Humanity Transformation 3D.” Action Aid, UN Women: Women’s Refugee commission. 2017.

- UN Women. “Flagship programme initiatives.” UN Women. Accessed May 2019. http://www.unwomen.org/en/how-we-work/flagship-programmes

- UN Women. “Gender in Humanitarian Action Asia Pacific Working Group. Integrating Gender into Humanitarian Action: Good Practices from Asia-Pacific” ADPC, OCHA, UN Women. 6. Dec 2017.

- UN Women. “Mozambique Annual Report.” UN Women. 2017.

- UNFPA. “New Ebola outbreak hits women and girls hardest in the Democratic Republic of the Congo.” UNFPA. 10 September 2018. https://www.unfpa.org/news/new-ebola-outbreak-hits-women-and-girls-hardest-democratic-republic-congo

- UNHCR. “UNHCR Emergency Handbook”. Accessed May 2019. https://emergency.unhcr.org/

- United Nations. “Transforming Out World: the 2030 Agenda for Sustainable Development”. United Nation’s Sustainable Development Summit. 25 Sept 2015. https://sustainabledevelopment.un.org/content/documents/21252030%20Agenda%20for%20Sustainable%20Development%20web.pdf

- Women’s Peace & Humanitarian Fund. http://wphfund.org/

#### Case Studies

Partnerships Case Study:

- “Assistant Secretary-General for Humanitarian Affairs and Deputy Emergency Relief Coordinator, Ursula Mueller – Remarks at the Humanitarian Networking and Partnerships Week event: Moving Forward on Gender Equality and Women’s Participation.” International Conference Centre, Geneva, 6 February 2019

- “Mainstreaming gender through the work of the agencies and envisaged collaboration with UN-Women.” Joint Meeting of the Executive Boards of UNDP/UNFPA, UNICEF, UN-Women and WFP. 4 and 7 February 2011

- UN Women. “Corporate Evaluation on Strategic Partnerships for Gender Equality and the Empowerment of Women.” UN Women. 2017.

- UNDP. “UNDP Third Gender Equality Strategy 2018-2021.” UNDP, September 2018. https://www.undp.org/content/undp/en/home/librarypage/womens-empowerment/undp-gender-equality-strategy-2018-2021.html

- UNFPA “UNFPA Humanitarian Response in Iraq 2018-2019.” UNFPA. https://iraq.unfpa.org/sites/default/files/pub-pdf/UNFPA%20Iraq_Humanitarian%20Response%202018-2019_0.pdf

- UNICEF. “Executive Board focuses on gender equality in UNICEF programming.” UNICEF.14 June 2018. https://www.unicef.org/about/execboard/index_102908.html

- Wess, T. “What’s Wrong with the UN and How to Fix it?” Polity: 2009.

- Wess, T. “Would the World be better without the UN?” Polity: 2018.

- WFP. “WFP Gender Policy (2015-2020)”. WFP. 2015. https://www1.wfp.org/publications/2015-wfp-gender-policy-2015-2020-0

Disaster Risk Reduction Case Study:

- Bahadur, A. V., Ibrahim, M. & Tanner, T. “The Resilience Renaissance? Unpacking of Resilience for Tackling Climate Change and Disasters.” Strengthening Climate Resilience Discussion; Institute of Development Studies, University of Sussex; 10 August 2012.

- CARE, Humanitarian Networks and Partnerships Week Event: “Moving forward on gender equality and women’s participation.”  February 2019 Geneva, Switzerland

- CERF. “Emergency Gender Responsive Protection Services to Survivors of Hurricane Irma in the Caribbean.” CERF proposal. 4 October 2017. (17-rr-WOPM-002).

- FAO. “A gender-responsive approach to disaster risk reduction (DRR) planning in the agriculture sector: Guidance for supporting rural women and men to build resilience in the face of disasters” FAO; 2016. (I6531EN/1/11.16)

- GFDRR et al. “Gender Equality and Women’s Empowerment in Disaster Recovery.” GFDRR, UNISDR, IRP, The World Bank, & UN Women.

- Leaning, Jennifer, and Debarati Guha-Sapir; “Natural Disasters, Armed Conflict, and Public Health.” The New England Journal of Medicine. 7 November 2013. (369:1836-1842)

- Lee, Jason Brown; “Complex Adaptive Systems.” CTS Technical Report, March 2007.

- Levine, Simon & Irina Mosel, “Supporting Resilience in Difficult Places.” Overseas Development Institute, April 2014.

- Martin-Breen, Patrick and J. Marty Anderies; “Resilience: A Literature Review.” The Rockefeller Foundation, September 2011.

- OCHA/UN “South Sudan Humanitarian Response Plan: January – December 2019.” OCHA/UN; December 2018.

- OCHA/UN. “Iraq Humanitarian Response Plan: January – December 2019.” OCHA/UN; February 2019.

- OCHA/UN. “Syria Humanitarian Response Plan: January – December 2019.” OCHA/UN; December 2018.

- Pain, Adam & Simon Levine, “A Conceptual Analysis of Livelihoods and Resilience: Addressing the ‘Insecurity of Agency’.” Humanitarian Policy Group Working Paper, November 2012.

- Pingali, Prabhu; Luca Alinovi & Jacky Sutton, “Food Security in Complex Emergencies: Enhancing Food System Resilience.” Disasters, Vol. 29, Issue Supplement 1; June 2005.

- Shrader, Elizabeth and Delaney, Patricia L. “Gender and Post-Disaster Reconstruction: The Case of Hurricane Mitch in Honduras and Nicaragua.” LCSPG/LAC Gender Team: The World Bank Group; 2000. 20-Point Checklist on Making Disaster Risk Reduction Gender Sensitive. UNISDR. “20-Point Checklist on Making Disaster Risk Reduction Gender Sensitive.” UNISDR.

- UN Women. “Disaster Management in Bangladesh: What Women Need.” UN Women; 2015.

- UN Women. “Restoring Dignity and Building Resilience: Monitoring Report on UN Women’s Programming in Za’atari Refugee Camp.” UN Women; June – October 2015.

- UN Women. “UN Women 2014 - 2017 Humanitarian Strategy.” UN Women; 6/20/2014; June 2014.

- UN Women. “UN Women Strategic Note 2018-2021; Barbados MCO Country Office SN Report.” UN Women; September 2019.

- UNDP and UN Women. “Gender and Disaster Risk Reduction in Europe and Central Asia: Workshop Guide for Facilitators.” UNDP & UN Women; 2018.

- UNISDR. “Policy and Practical Guidelines: Making Disaster Risk Reduction Gender Sensitive.” UNISDR, UNDP, and IUCN; 2009.

- UNISDR. “Sendai Framework for Disaster Risk Reduction 2015 – 2030.” UNISDR; (UNISDR/GE/2015 - ICLUX EN5000 1st edition) 2015.

- World Bank. “Gender Equality and Women’s Empowerment in Disaster Recovery.” GFDRR, UNISDR, IRP, The World Bank, & UN Women.

- World Bank. “Handbook for Estimating the Socio-Economic and Environmental Effects of Disasters.” The World Bank; 2003.

Humanitarian Response Case Study:

- Assistant Secretary-General for Humanitarian Affairs and Deputy Emergency Relief Coordinator, Ursula Mueller. “Moving Forward on Gender Equality and Women’s Participation.” Remarks at the Humanitarian Networking and Partnerships Week event. International Conference Center, Geneva, 6 February 2019.

- BHP. “A Second Chance through Education.” YouTube. 9 Sep 2018. https://www.youtube.com/watch?v=3jN_OZHVQzA

- BHP. “UN Women’s Second Chance Education and Vocational Learning Programme.” BHP. 17 Dec 2018. https://www.bhp.com/community/community-news/2018/12/un-womens-second-chance-education-and-vocational-learning-programme

- Global Acceleration Instrument. “Global Acceleration Instrument for Women, Peace and Security and Humanitarian Action.” GAI. 20 March 2017. http://mptf.undp.org/document/download/17816

- SIDA. “Gender Equality in Humanitarian Assistance.” SIDA. Mar 2015. https://www.sida.se/contentassets/3a820dbd152f4fca98bacde8a8101e15/gender-tool-humanitarian-assistance.pdf

- UN General Assembly. “Resolution 64/289.” UN. 2 Jul 2010. https://undocs.org/en/A/RES/64/289

- UN Women. “About UN Women.” UN Women. Accessed May 2019. http://www.unwomen.org/en/about-us/about-un-women

- UN Women. “Barbados MCO 2018 Report.” UN Women. 2018.

- UN Women. “Colombia 2014 RMS Report.” UN Women. 2014.

- UN Women. “Flagship programme initiatives.” UN Women. Accessed May 2019. http://www.unwomen.org/en/how-we-work/flagship-programmes

- UN Women. “Humanitarian Framework.” UN Women. 2018.

- UN Women. “Mozambique Annual Report 2017.” UN Women. 2017.

- UN Women. “Strategic Plan 2018-2021.” UN Women. 2017. http://www.unwomen.org/en/digital-library/publications/2017/8/un-women-strategic-plan-2018-2021

- UN Women. “UN Women WPHF 2019 Funding Board meeting presentation.” UN Women. 29 March 2019.

- UNHCR. Livelihoods and Economic Inclusion. UNHCR. Accessed May 2019. https://www.unhcr.org/4ad2e7d26.html

- Women’s Peace and Humanitarian Fund. “Our Mission.” WPH Fund. http://wphfund.org/our-mission/

- WPFH. “2019 Funding Board meeting presentation.” WPFH. 29 March 2019.

Normative Case Study:

- 3D) and Gender as a Cross-Cutting Issue.” Agenda for Humanity. 1 May 2017. https://www.agendaforhumanity.org/sites/default/files/AP_3D&Gender_0.pdf

- Action Aid, UN Women, and WRC, “Empower Women and Girls (Transformation

- Action Aid. “Empower Women and Girls and Gender as a Cross-Cutting Issue.  Analytical Paper on WHS Self-Reporting on Agenda for Humanity Transformation 3D.” UN Women Women’s Refugee commission. 2017

- Action Aid. “Getting gender into the Grand Bargain.” ActionAid Discussion Paper, 19 June 2016

- ADPC, OCHA, and UN Women. “Gender in Humanitarian Action Asia Pacific Working Group. Integrating Gender into Humanitarian Action: Good Practices from Asia-Pacific” United Nations. 6 Dec 2017.

- Agenda for Humanity. “Initiative: Grand Bargain.” Agenda for Humanity. Accessed May 2019. https://www.agendaforhumanity.org/initiatives/3861

- Bastagli, Francesa, Hagen-Zanker, Jessica, Harman, Luke, Sturge, Georgina, Barc, Valentina, Schmidt, Tanja and Pellerano, Luca. “Cash transfers: what does the evidence say? A rigorous review of impacts and the role of design and implementation features, research reports and studies.” UKAID. July 2016. https://www.odi.org/sites/odi.org.uk/files/resource-documents/10749.pdf

- CARE. “Not what she bargained for? Gender and the Grand Bargain.” CARE International. Jun 2018. https://insights.careinternational.org.uk/publications/not-what-she-bargained-for-gender-and-the-grand-bargain

- CEB. “Aide-Memoire on Integrating Gender Equality in the UN Plan of Action on DRR for Resilience.” UN. 2017. https://www.preventionweb.net/publications/view/53087

- Humanitarian Networks and Partnerships Week Event: “Moving forward on gender equality and women’s participation” RECOMMENDATIONS. 6 February 2019. Geneva, Switzerland

- IASC Gender Reference Group, Annual Report - January 2018-December 2018

- IASC Reference Group for gender in Humanitarian action – HUMANITARIAN CRISIS IN WEST AFRICA (EBOLA) GENDER ALERT: February 2015

- IASC Reference Group for gender in Humanitarian action HUMANITARIAN CRISIS IN SOUTH SUDAN GENDER ALERT 2 (May 2014)

- IASC Reference Group for gender in Humanitarian action HUMANITARIAN CRISIS IN YEMEN GENDER ALERT (July 2015)

- IASC Reference Group for gender in Humanitarian action HUMANITARIAN CRISIS IN CENTRAL AFRICAN REPUBLIC (CAR) GENDER ALERT (June 2014)

- IASC Reference Group for gender in Humanitarian action HUMANITARIAN CRISIS IN IRAQ GENDER ALERT: SEPTEMBER 2014

- IASC Reference Group for gender in Humanitarian action HUMANITARIAN CRISIS IN NEPAL GENDER ALERT (May 2015)

- IASC Reference Group for gender in Humanitarian action HUMANITARIAN CRISIS IN THE CARIBBEAN GENDER ALERT (Sept 2017)

- IASC Reference Group for Gender in Humanitarian Action, Review of IASC 2008 Policy Statement on Gender Equality in Humanitarian Action. https://interagencystandingcommittee.org/system/files/2._review_iasc_gender_policy_final_report_narrative_report2_1.pdf

- IASC Reference Group for Gender in Humanitarian Action, Review of IASC 2008 Policy Statement on Gender Equality in Humanitarian Action. https://interagencystandingcommittee.org/system/files/2._review_iasc_gender_policy_final_report_narrative_report2_1.pdf

- IASC Reference Group for Gender in Humanitarian Action, Review of IASC 2008 Policy Statement on Gender Equality in Humanitarian Action. Https://interagencystandingcommittee.org/system/files/2._review_iasc_gender_policy_final_report_narrative_report2_1.pdf

- IASC Reference Group on Gender and Humanitarian Action. https://interagencystandingcommittee.org/gender-and-humanitarian-action

- IASC Reference Group on Gender and Humanitarian Action. https://interagencystandingcommittee.org/gender-and-humanitarian-action

- IASC Reference Group on Gender and Humanitarian Action. https://interagencystandingcommittee.org/gender-and-humanitarian-action

- IASC. “Accountability Framework for the IASC Policy on Gender Equality and the Empowerment of Women and Girls in Humanitarian Action.” IASC. 2018. https://interagencystandingcommittee.org/system/files/iasc_accountability_framework_with_adjusted_self_assessment_0.pdf

- IASC. “Grand Bargain (Hosted by IASC). IASC. Accessed May 2019. https://interagencystandingcommittee.org/grand-bargain-hosted-iasc

- IASC. “Grand Bargain.” IASC. Accessed May 2019. https://interagencystandingcommittee.org/system/files/nn_-_ grand_bargain_report_final.pdf

- IASC. “IASC Reference Group on Gender and Humanitarian Action” IASC. Accessed May 2019. https://interagencystandingcommittee.org/gender-and-humanitarian-action

- IASC. “Women, Girls, Boys and Men Different Needs – Equal Opportunities.” UNHCR. Dec 2006. https://www.unhcr.org/protection/women/50f91c999/iasc-gender-handbook-humanitarian-action.html

- Independent draft Report on the Grand Bargain (2018)

- INTER-AGENCY STANDING COMMITTEE POLICY ON GENDER EQUALITY AND THE EMPOWERMENT OF WOMEN AND GIRLS IN HUMANITARIAN ACTION, 3rd November 2017

- Inter-Agency Standing Committee. “Guidance from the Inter-Agency Standing Committee.” IASC. Accessed May 2019. http://www.globalprotectioncluster.org/tools-and-guidance/guidance-from-inter-agency-standing-committee/

- Inter-Agency Standing Committee. “IASC Policy (and Accountability Framework) on Gender Equality and the Empowerment of Women and Girls in Humanitarian Action, 2017.” IASC. Accessed May 2019. https://interagencystandingcommittee.org/gender-and-humanitarian-action/documents-public/iasc-policy-gender-equality-and-empowerment-women

- International Council of Voluntary Agencies. “Informal Friends of Gender group for the Grand Bargain: Aide-Memoire on Gender Mainstreaming in the Grand Bargain.” ICVA. 23 Feb 2017. https://reliefweb.int/report/world/informal-friends-gender-group-grand-bargain-aide-memoire-gender-mainstreaming-grand

- Islamic Relief, LEARNING PAPER 1 Leave no one behind in humanitarian programming: An approach to understanding intersectional programming . Age, Gender and Diversity Analysis, 2018  https://reliefweb.int/sites/reliefweb.int/files/resources/Learning-paper-1-Leave-no-one-behind-in-humanitarian-programming-An-approach-to-understanding-intersectional-programming_web.pdf

- Konyndyk, Jeremy. “Rethinking the Humanitarian Business Model.” May 2018

- PRM Progress report “Addressing Gender-Based Violence and enhancing Gender Equality and the Empowerment of Refugee, Displaced and Other Crisis-Affected Women and Girls through the Grand Bargain, January 2019

- PRM Progress report “Addressing Gender-Based Violence and enhancing Gender Equality and the Empowerment of Refugee, Displaced and Other Crisis-Affected Women and Girls through the Grand Bargain, January 2019

- REVIEW OF IASC 2008 POLICY STATEMENT ON GENDER EQUALITY IN HUMANITARIAN ACTION, executive summary.

- Sendai Framework for Disaster Risk Reduction. https://www.unisdr.org/we/coordinate/sendai-framework

- Sustainable Development Goals. https://sustainabledevelopment.un.org/sdgs

- UN General Assembly. “One humanity: shared responsibility on the WHS.” United Nations. 2 Feb 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/Secretary-General%27s%20Report%20for%20WHS%202016%20%28Advance%20Unedited%20Draft%29.pdf

- UN OCHA (2017) No Time to Retreat – First Annual Synthesis Report on Progress since the World Humanitarian Summit

- UN Security Council Resolution 2242. http://peacewomen.org/SCR-2242

- UN women “Addressing Gender-Based Violence and enhancing Gender Equality and the Empowerment of Refugee, Displaced and Other Crisis-Affected Women and Girls through the Grand Bargain” full proposal

- UN Women and Action Aid, 2017. Analytical paper on WHS self-reporting on Agenda for Humanity transformation 3D and Gender as a cross-cutting issue.

- UN Women and Action Aid, 2017. Analytical paper on WHS self-reporting on Agenda for Humanity transformation 3D and Gender as a cross-cutting issue.

- UN WOMEN Asia Pacific Annual Report 2016-2017

- UN Women Draft Project Document “Gender Hub to strengthen Gender-Responsiveness of the Rohingya Crisis Response”

- UN Women IES, Universalia “COORDINATING FOR GENDER EQUALITY RESULTS. Corporate evaluation of UN Women’s contribution to UN system coordination on gender equality and the empowerment of women”

- UN Women, COORDINATING FOR GENDER EQUALITY RESULTS. Corporate evaluation of UN Women’s contribution to UN system coordination on gender equality and the empowerment of women, May 2016

- UN Women. “Beijing Platform for Action”. UN Women. 1995. http://www.un.org/womenwatch/daw/beijing/platform/

- UN Women. “HACRO 2018 reporting.” UN Women. 2018.

- UN Women. “IASC e-learning on Gender Equality in Humanitarian Action.” UN Women. Accessed May 2019. https://trainingcentre.unwomen.org/portal/product/iasc-e-learning-on-gender-equality-in-humanitarian-action/

- UN Women. “The Centrality of Gender Equality and Women’s Empowerment for the Formulation of the Global Compact on Refugees.” UNHCR. Accessed May 2019. https://www.unhcr.org/events/conferences/59ddff717/paper-centrality-gender-equality-empowerment-women-formulation-global-compact.html

- UNDG “EIGHT CASE STUDIES ON INTEGRATING THE UNITED NATIONS’ NORMATIVE AND OPERATIONAL WORK” September 2015.

- UNDRR. “Gender.” UNISDR. Accessed May 2019. https://www.unisdr.org/we/advocate/gender

- UNFPA. “New Ebola outbreak hits women and girls hardest in the Democratic Republic of the Congo.” UNFPA. 10 Sep 2018. https://www.unfpa.org/news/new-ebola-outbreak-hits-women-and-girls-hardest-democratic-republic-congo

- UNISDR, 2017. Special Event on Women Leadership in Disaster Risk Reduction for Resilience, https://www.unisdr.org/conferences/2017/globalplatform/en/programme/special-events/view/808

- United Nations “Convention on the Elimination of All Forms of Discrimination against Women (CEDAW).” UN General Assembly. Accessed May 2019. http://www.un.org/womenwatch/daw/cedaw/

- United Nations Entity for Gender Equality and the Empowerment of Women (UN-Women), Strategic Plan 2018-2021. UNW/2017/6/Rev.1

- WHS Commitments to Action (2016). https://www.agendaforhumanity.org/sites/default/files/resources/2017/Jul/WHS_Commitment_to_Action_8 September2016.pdf

- WHS Commitments to Action (2016). https://www.agendaforhumanity.org/sites/default/files/resources/2017/Jul/WHS_Commitment_to_Action_8 September2016.pdf

#### Country Portfolio Review:

Humanitarian Response Plans:

- 3RP. “3RP: Regional Response & Resilience Plan 2016.” 3RP. 2018. (http://www.3rpsyriacrisis.org/.)

- 3RP. “3RP: Regional Response & Resilience Plan 2017.” 3RP. 2018. (http://www.3rpsyriacrisis.org/.)

- 3RP. “3RP: Regional Response & Resilience Plan 2018.” 3RP. 2018. (http://www.3rpsyriacrisis.org/.)

- UNOCHA. “Afghanistan Flash Appeal.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/afg_2016_flash_appeal_web.pdf

- UNOCHA. “Afghanistan Humanitarian Response Plan 2016.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/afg_2016_hrp_final_20151224.pdf

- UNOCHA. “Afghanistan Humanitarian Response Plan 2017.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/afg_2017_hrp_english.pdf

- UNOCHA. “Afghanistan Humanitarian Response Plan 2018-2021.” UNOCHA. 2018. https://www.humanitarianresponse.info/sites/www.humanitarianresponse.info/files/documents/files/afg_2018_2021_hrp_revision_drought_31_may_2018.pdf

- UNOCHA. “Burundi Plan de Réponse Humanitaire 2016.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/HRP_Burundi_2016_Final_FR.pdf

- UNOCHA. “Burundi Plan de Réponse Humanitaire 2017.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/hrp_burundi_2017_fr_small.pdf

- UNOCHA. “Burundi Plan de Réponse Humanitaire 2018.” UNOCHA. 2018. https://reliefweb.int/sites/reliefweb.int/files/resources/hrp_burundi_2018_fr.pdf

- UNOCHA. “Cameroun Humanitarian Response Plan 2016.” UNHCR. 2016. https://www.humanitarianresponse.info/sites/www.humanitarianresponse.info/files/documents/files/2016_cameroun_hrp.pdf

- UNOCHA. “Cameroun Humanitarian Response Plan 2017-2020.” UNHCR. 2018. https://www.humanitarianresponse.info/sites/www.humanitarianresponse.info/files/documents/files/cmr_hrp18_summary_v1.1_light.pdf

- UNOCHA. “Cameroun Humanitarian Response Plan 2017-2020.” UNHCR. 2017. https://www.humanitarianresponse.info/sites/www.humanitarianresponse.info/files/documents/files/2017_hrp_cmr_2.pdf

- UNOCHA. “Democratic Republic of the Congo Humanitarian Response Plan 2017-2019: 2018 Update.” UNOCHA. 2018. https://reliefweb.int/sites/reliefweb.int/files/resources/MAJ_DRC_HRP_2017_En.pdf

- UNOCHA. “Democratic Republic of the Congo Humanitarian Response Plan 2017-2019.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/DRC_HRP_2017.pdf

- UNOCHA. “Democratic Republic of the Congo Humanitarian Response Plan 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/drc_hrp_2016.pdf

- UNOCHA. “Djibouti Humanitarian Response Plan 2016.” UNOCHA. 2016. https://www.humanitarianresponse.info/sites/www.humanitarianresponse.info/files/documents/files/ocha_hrp_djibouti_hr_250416.pdf

- UNOCHA. “Djibouti Humanitarian Response Plan 2017.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/HRP%20Djib%202017.pdf

- UNOCHA. “Dominica Flash Appeal 2017.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/Dominica_FlashAppeal_EN_20170929%20%281%29.pdfç

- UNOCHA. “Ecuador Flash Appeal: Earthquake of 16 April 2016.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/Ecuador%20Flash%20Appeal.pdf

- UNOCHA. “Ethiopia Humanitarian and Disaster Resilience Plan 2018.” UNOCHA and the Government of Ethiopia. 2018. https://reliefweb.int/sites/reliefweb.int/files/resources/ethiopia_2018_humanitarian_and_disaster_resilience_plan.pdf

- UNOCHA. “Fiji Flash Appeal: Tropical Cyclone Winston.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/Fiji%20TC%20Winston%20Flash%20Appeal%20FINAL.pdf

- UNOCHA. “Flash Appeal: Emergency Response Plan for Mozambique: Cyclone Dineo.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/Mozambique%20Flash%20Appeal_FINAL.pdf

- UNOCHA. “Guatemala/Honduras Humanitarian Action Plan.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/Guatemala%20Honduras%202016%20Humanitarian%20Response%20Plan.pdf

- UNOCHA. “Haiti Flash Appeal.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/Haiti%20Flash%20Appeal%20-Hurricane%20Matthew%20Oct%202016.pdf

- UNOCHA. “Haiti Humanitarian Response Plan 2016.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/hti_hrp_060416_final_0.pdf

- UNOCHA. “Haiti Humanitarian Response Plan 2017-2018.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/hrp_2017_20181.pdf

- UNOCHA. “Haiti Humanitarian Response Plan 2017-2018: Revised 2018.” UNOCHA. 2018. https://reliefweb.int/sites/reliefweb.int/files/resources/2018_haiti_revised_hrp_2.pdf

- UNOCHA. “Iraq Humanitarian Response Plan 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/final_iraq_2016_hrp.pdf

- UNOCHA. “Iraq Humanitarian Response Plan 2017.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/2017_hrp_irq_final_2.pdf

- UNOCHA. “Iraq Humanitarian Response Plan 2018.” UNOCHA. 2018. https://reliefweb.int/sites/reliefweb.int/files/resources/IRQ_2018_Full_HRP_0.pdf

- UNOCHA. “Iraq: Mosul Flash Appeal.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/mosul_flash_appeal_final_web.pdf

- UNOCHA. “Kenya Flash Appeal 2017.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/Kenyan_Flash_%20Appeal_15%20March%202017%20final.pdf

- UNOCHA. “Libya Humanitarian Response Plan 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/libya_hrp_final_19_11_2015.pdf

- UNOCHA. “Libya Humanitarian Response Plan 2017.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/2017%20Libya%20Humanitarian%20Response%20Plan%20%28EN%29.pdf

- UNOCHA. “Libya Humanitarian Response Plan 2018.” UNOCHA. 2018. https://reliefweb.int/sites/reliefweb.int/files/resources/2018_HRP_Libya.pdf

- UNOCHA. “Madagascar Flash Appeal 2017.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/2017_Flash_Appeal_MG_eng.002.002.pdf

- UNOCHA. “Mali Humanitarian Response Plan 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/hrp_mali_final.pdf

- UNOCHA. “Mali Humanitarian Response Plan 2017.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/MALI_HRP_final_2017.pdf

- UNOCHA. “Mali Humanitarian Response Plan 2018.” UNOCHA. 2018. https://reliefweb.int/sites/reliefweb.int/files/resources/hrp-2018_mali_en_20180222_vf_0.pdf

- UNOCHA. “Mauritanie Plan de Réponse Humanitaire 2014-2016.” UNOCHA. 2015. https://www.humanitarianresponse.info/sites/www.humanitarianresponse.info/files/documents/files/hrp_2016_mauritanie.pdf

- UNOCHA. “Myanmar Humanitarian Response Plan 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/2016_myanmar_hrp_final.pdf

- UNOCHA. “Myanmar Humanitarian Response Plan 2017.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/2017_myanmar_hrp_final.002.pdf

- UNOCHA. “Myanmar Humanitarian Response Plan 2018.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/2018%20Interim%20Humanitarian%20Response%20Plan_%20Myanmar.pdf

- UNOCHA. “Niger Plan de Réponse Humanitaire 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/hrp_niger_proof5_final_version_13012016.pdf

- UNOCHA. “Niger Plan de Réponse Humanitaire 2017.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/ner_hrp_2017_09122016.pdf

- UNOCHA. “Niger Plan de Réponse Humanitaire 2018.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/F_NRE_HRP_2018_FINAL_LR.pdf

- UNOCHA. “Nigeria Humanitarian Response Plan 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/nigeria_2016_hrp_11012016.pdf

- UNOCHA. “Nigeria Humanitarian Response Plan 2017.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/ocha_nga_hrp_2017_19122016.pdf

- UNOCHA. “Nigeria Humanitarian Response Plan 2018.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/2018_hrp_v5.4.pdf

- UNOCHA. “North Coast of Peru Flash Appeal 2017.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/-PE-Flash_Appeal_ENG_1000_hrs_%28PUBLIC%29-20170410-CV-20519.pdf

- UNOCHA. “Occupied Palestine Territories Humanitarian Response Plan 2018-2020.” UNOCHA. 2017. https://www.ochaopt.org/content/2018-2020-humanitarian-response-plan-hrp

- UNOCHA. “Occupied Palestine Territories Humanitarian Response Plan 2017.” UNOCHA. 2016. https://www.ochaopt.org/content/2017-humanitarian-response-plan-occupied-palestinian-territory

- UNOCHA. “Occupied Palestine Territories Humanitarian Response Plan 2016.” UNOCHA. 2015. https://www.ochaopt.org/content/2016-humanitarian-response-plan-occupied-palestinian-territory

- UNOCHA. “République Centrafricaine Plan de Réponse Humanitaire 2018.” UNOCHA. 2018. https://reliefweb.int/sites/reliefweb.int/files/resources/rca_ocha_2018_hrp-1.pdf

- UNOCHA. “République Centrafricaine Plan de Réponse Humanitaire 2017-2019.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/rca_ocha_2017_hrp_revise_.pdf

- UNOCHA. “République Centrafricaine Plan de Réponse Humanitaire 2016.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/hrp_car_2016.pdf

- UNOCHA. “Sahal: A Call for Humanitarian Aid 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/sahel_hrp_2016_-_en.pdf

- UNOCHA. “Senegal Humanitarian Response Plan 2016.” UNOCHA. 2015. https://www.humanitarianresponse.info/sites/www.humanitarianresponse.info/files/documents/files/2016_senegal_hrp_2.pdf

- UNOCHA. “Sirt Flash Appeal.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/SIRT%20Flash%20Appeal_16Sept_En.pdf

- UNOCHA. “Somalia Humanitarian Response Plan 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/2016%20Somalia_HRP_FINAL.pdf

- UNOCHA. “Somalia Humanitarian Response Plan 2017.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/2017_somalia_humanitarian_response_plan_final.pdf

- UNOCHA. “Somalia Humanitarian Response Plan 2018.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/2018_somalia_hrp_final_draft_18122017_0.pdf

- UNOCHA. “South Sudan Humanitarian Response Plan 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/2016_hrp_SS_Final_WEB.pdf

- UNOCHA. “South Sudan Humanitarian Response Plan 2017.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/South_Sudan_2017_Humanitarian_Response_Plan.pdf

- UNOCHA. “South Sudan Humanitarian Response Plan 2018.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/SS_2018_HumanitarianResponsePlan.pdf

- UNOCHA. “Sudan Humanitarian Response Plan 2016.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/Sudan_2016_Humanitarian_Response_Plan.pdf

- UNOCHA. “Sudan Humanitarian Response Plan 2017.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/Sudan_2017_Humanitarian_Response_Plan.pdf

- UNOCHA. “Sudan Humanitarian Response Plan 2018.” UNOCHA. 2018. https://reliefweb.int/sites/reliefweb.int/files/resources/Sudan_2018_Humanitarian_Response_Plan.pdf

- UNOCHA. “Syrian Arab Republic Humanitarian Response Plan 2015.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/2016_hrp_syrian_arab_republic.pdf

- UNOCHA. “Syrian Arab Republic Humanitarian Response Plan 2017.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/syr_wos_operational_plan_hrp_2017.pdf

- UNOCHA. “Syrian Arab Republic Humanitarian Response Plan 2018.” UNOCHA. 2018. https://reliefweb.int/sites/reliefweb.int/files/resources/2018_2018_hrp_syria.pdf

- UNOCHA. “Tchad Plan de Réponse Humanitaire 2016.” UNOCHA. 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/tchad_hrp_2016_final_0.pdf

- UNOCHA. “Tchad Plan de Réponse Humanitaire 2017.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/tcd_str_hrp2017_fr_20161228.pdf

- UNOCHA. “Tchad Plan de Réponse Humanitaire 2018.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/tcd_str_hrp2018_20180208.pdf

- UNOCHA. “The Gambia Humanitarian Response Plan 2015.” UNOCHA. 2015. https://www.humanitarianresponse.info/sites/www.humanitarianresponse.info/files/documents/files/2016_gambia_hrp_7.pdf

- UNOCHA. “Ukraine Humanitarian Response Plan 2016.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/2016_hrp_ukraine_english.pdf

- UNOCHA. “Ukraine Humanitarian Response Plan 2017.” UNOCHA. 2016. https://reliefweb.int/sites/reliefweb.int/files/resources/humanitarian_response_plan_2017_eng.pdf

- UNOCHA. “Ukraine Humanitarian Response Plan 2018.” UNOCHA. 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/ukraine_humanitarian_response_plan_2018_en_20171201.pdf

- UNOCHA. “Yemen Humanitarian Response Plan 2016.” UNOCHA.2016. https://reliefweb.int/sites/reliefweb.int/files/resources/2016%20Yemen%20Humanitarian%20Response%20Plan.pdf

- UNOCHA. “Yemen Humanitarian Response Plan 2017.” UNOCHA.2017. https://reliefweb.int/sites/reliefweb.int/files/resources/2017_HRP_YEMEN.pdf

- UNOCHA. “Yemen Humanitarian Response Plan 2018.” UNOCHA.2018. https://reliefweb.int/sites/reliefweb.int/files/resources/20180120_HRP_YEMEN_Final.pdf

- UNOCHA. “Zimbabwe Humanitarian Action Plan.” UNOCHA. 2016. https://www.humanitarianresponse.info/sites/www.humanitarianresponse.info/files/documents/files/4_may_zim-hrp-2016_03_pm_002.pdf

UN Women internal documents.

- Action Aid, WRC, UN Women. "Analytical Paper-Agenda for Humanity Transformation 3D and Gender as a cross-cutting issue". Action Aid, WRC, UN Women, 2017.

- Bangladesh Country Office. "Development  Results  Framework." Bangladesh Country Office 2014-16

- Bill and Melinda Gates Foundation. "A Conceptual Model of Women and Girls’ Empowerment". Bill and Melinda Gates Foundation, 2017

- Bishop, Jo-Anne, “Advancing gender equality and the empowerment of women in Asia and the Pacific. Meta-analysis of 2011-2016 evaluation reports”. UN Women Regional Communications Unit. 2017

- Bishop, Jo-Anne,” UN Women Regional Office for Asia and The Pacific .Interactive Annual Report 2015” UN Women Regional Office for Asia and The Pacific. 2016.

- Call to Action on Protection from GBV in Emergencies. "Road Map 2016-2020". Call to Action, 2015. https://reliefweb.int/sites/reliefweb.int/files/resources/Call-to-Action-Roadmap.pdf

- Care International. "Intersections of violence against women and girls with state-building and peace-building: Lessons from Nepal, Sierra Leone and South Sudan". Care International, 2018

- Care International. Policy Brief, "A call to action on gender and humanitarian reform From the Call to Action on Violence Against Women and Girls in Emergencies to the World Humanitarian Summit", Care International, September 2014. (https://www.care-international.org/files/files/CARECalltoactionongenderandhumanitarianreform.pdf)

- Care. "Empowering women and girls affected by Crisis". Care, 2016

- Care. "Gender in Emergencies. She is a humanitarian." Care, 2017. https://reliefweb.int/sites/reliefweb.int/files/resources/CARE_She-is-a-humanitarian-report_Feb-2017_high-res.pdf

- Care. "Gender Marker". Care, undated. http://gender.care2share.wikispaces.net/file/view/CARE_Gender%20Marker_External%20Comms.pdf/

- Daponte, Beth & Simigianis Rea. "Evaluability Assessment of Annual Work Plan 2012-2013." Final Report for UN Women Pacific Multi-Country Office 2013

- DARA. "Humanitarian Response Index 2011: Addressing the Gender Challenge". DARA, 2011

- Davies, R. "Planning Evaluability Assessments: A Synthesis of the Literature with Recommendations." Report of a Study Commissioned by the Department for International Development. 2013

- FAO KORE. "Knowledge Sharing Platform on Resilience". FAO, undated. http://www.fao.org/in-action/kore/protracted-crises-and-conflicts/en/

- Haider, Dilruba. "2018 Outcomes." 2018 Outcomes 2018

- High-Level Committee on Management (HLCM). "Final Programme Criticality Framework. Chief Executives Board for Coordination, 22nd session". HLCM, Sept 2011. (Dropbox: Corporate - Security & Programme Criticality)

- IASC GRG. "ISC Gender Reference Group - Draft Work Plan 2015-2016". IASC GRG, 2015. )

- IASC GRG. "Progress Report - January 2016-December 2016". IASC GRG, 2016. )

- IASC. "ACCOUNTABILITY FRAMEWORK FOR THE INTER-AGENCY STANDING COMMITTEE POLICY ON GENDER EQUALITY AND THE EMPOWERMENT OF WOMEN AND GIRLS IN HUMANITARIAN ACTION". IASC, 2017

- IASC. "Cluster Coordination Reference Module at Country Level". IASC, July 2015. )

- IASC. "Draft Inter-Agency Standing Committee Policy on Gender Equality and Women’s and Girls’ Empowerment". IASC, November 2017

- IASC. "Gender Handbook for Humanitarian Action". Inter-Agency Standing Committee (IASC) 2017

- IASC. "Gender Handbook in Humanitarian Action". IASC, Dec 2006. )

- IASC. "IASC Gender Marker". IASC, Aug 2012. )

- IASC. "IASC Gender SWG Guidance Note on Gender and Resilience". IASC, Sep 2013. )

- IASC. "IASC policy on gender equality and the empowerment of women and girls in humanitarian action". IASC, Nov 2017. )

- IASC. "Introduction to Humanitarian Action: A brief guide for Resident Coordinators". IASC, Oct 2015. )

- IASC. "Review of IASC 2008 policy statement on gender equality in humanitarian action, Detailed analysis". IASC, May 2015. )

- IASC. "Review of the IASC 2008 Gender Equality in Humanitarian Action Policy Statement". IASC, 2015

- IASC. "Revised Accountability Framework - Gender Equality and the Empowerment of Women and Girls in Humanitarian Action". IASC, Nov 2017. )

- Lee Esser, Andrea “UN Women Regional Office for Asia and The Pacific Annual Report 2014“.UN Women Regional Office for Asia and The Pacific. 2015.

- Luchsinger, Gretchen  “UN Women. Annual Report Asia and the Pacific  2016-2017." UN Women Regional Office for Asia and The Pacific. 2018.

- Margie Buchanan-Smith, John Cosgrave & Alexandra Warner; “Evaluation of Humanitarian Action Guide.” ALNAP 2016.

- OCHA. "Global Humanitarian Overview 2018". OCHA, 2018

- Office Bangladesh. "Quarterly Monitoring Report (2015). Impact Area: Women lead and participate in decision making at all levels." Office Bangladesh 2015 Office Bangladesh. "Quarterly Monitoring Report (2016). Impact Area: Women lead and participate in decision making at all levels." Office Bangladesh 2016

- Office Bangladesh. "Quarterly Monitoring Report (2017). Impact Area: Peace and security and humanitarian action are shaped by women leadership and participation." Office Bangladesh 2017

- Office Bangladesh. "Quarterly Monitoring Report (2018). Impact Area: SP Outcome 5 : Women and girls contribute and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action." Office Bangladesh 2018 UN Women Bangladesh. "Strategic Note." UN Women Bangladesh 2016

- Robert Picciotto. “Evaluation Independence in Organizations.” Journal of Multidisciplinary Evaluation; Volume 9, Issue 20, 2013.

- SIDA. "Gender Equality in Humanitarian Assistance. Gender Tool Box." SIDA, March 2015 https://www.sida.se/contentassets/3a820dbd152f4fca98bacde8a8101e15/gender-tool-humanitarian-assistance.pdf

- The Ford Foundation. "The Ford Foundation Grant Reporting Instructions". The Ford Foundation, 2017.

- The Nielsen Company (Bangladesh) Limited. “Final Report on Final Project Evaluation - Reducing Vulnerability of Women Affected by Climate Change through Viable Livelihood Options”. UN Women.2015.

- UN General Assembly. "A/RES/72/279, 72nd session, agenda item 24 (a) Repositioning  of  the  United  Nations  development  system  in  the context  of  the  quadrennial  comprehensive  policy  review  of operational activities  for  development  of  the  United Nations  system". UNGA, 2018.

- UN OCHA. "No Time to Retreat – First Annual Synthesis Report on Progress since the World Humanitarian Summit". UN OCHA, 2017

- UN Secretary-General. "Final draft, Secretary-General's implementation plan for the inception of the reinvigorated Resident Coordinator system". UNSG, Aug 2018.

- UN Secretary-General. "SG letter to UNDS Principals". UNSG, Jun 2018.

- UN Sustainable Development Group. "Joint letter of the UNSDG Chair and Vice-Chair to UN RCs". UNSDG, Jun 2018.

- UN Women “2014 2017 UN Women Regional Office for Asia and The Pacific Development (ROAP) Results Framework (DRF)”. UN Women.2018.

- UN Women “2014 2017 UN Women Regional Office for Asia and The Pacific Development (ROAP) Organizational effectiveness and efficiency (OEE)” UN Women.2018.

- UN Women “Women at the forefront of disaster response in the Pacific. Impact Story”. UN Women. Undated. BANGLADESH

- UN Women ”UN Women Regional Office for Asia and the Pacific: Strategic Note 2014-2017” UN Women.2014.

- UN Women Afghanistan Country Office, “UN Women Strategic Note 2014-2020. SN REPORT 2018. Organizational effectiveness and efficiency (OEE)”. UN Women, 2018

- UN Women Afghanistan Country Office, “UN Women Strategic Note 2014-2020. SN REPORT 2018. Development Results Framework (DRF)”. UN Women, 2018

- UN Women Afghanistan Country Office, “UN Women Strategic Note 2014-2020. SN REPORT 2017. AWP Cover Note ”. UN Women, 2017

- UN Women Afghanistan Country Office, “UN Women Strategic Note 2014-2020. SN REPORT 2018. Narrative”. UN Women, 2018

- UN Women Afghanistan Country Office, “UN Women Strategic Note 2014-2020. SN REPORT 2018. Development results framework (DRF) and Organizational effectiveness and efficiency (OEE)”. UN Women, 2018

- UN Women Afghanistan Country Office, “UN Women Strategic Note 2014-2020”. UN Women, 2014

- UN Women Asia Pacific Section. “Prodoc 80556 Bangladesh. Annexes”. UN Women 2012.

- UN Women Asia Pacific Section. “Prodoc 80556 Bangladesh. Reducing vulnerability thru livelihoods”. UN Women 2012

- UN Women Asia Pacific Section. “Prodoc 80556 Bangladesh”. UN Women 2012.

- UN Women Asia Pacific Section. “Standard MoU for the national Resilience Programme in Bangladesh using pass-through fund management”. 2017

- UN Women Bangladesh Country Office. "UN Women Strategic Note 2017-2020." UN Women Bangladesh Country Office 2018

- UN Women Bangladesh Country Office. "UN Women Strategic Note 2017-2020." UN Women Bangladesh Country Office 2018

- UN Women Bangladesh Country Office. "UN Women Strategic Note 2017-2020. Narrative." UN Women Bangladesh Country Office 2018

- UN Women Bangladesh, UNDP Bangladesh, UNOPS Bangladesh. “National Resilience Programme. Joint Programme Document.( Signed)”. UN Women Bangladesh, UNDP Bangladesh 2017

- UN Women Bangladesh, UNDP Bangladesh, UNOPS Bangladesh. “Prodoc 12231 Bangladesh. National Resilience Program”. UN Women Bangladesh, UNDP Bangladesh, UNOPS Bangladesh 2017

- UN Women Bangladesh: OEEF.  "(No title)." UN Women Bangladesh: OEEF 2016

- UN Women Country Programmes Review on Gender Equality and Women´s Empowerment in Humanitarian Action. "Country Report: Bangladesh." UN Women Country Programmes Review on Gender Equality and Women´s Empowerment in Humanitarian Action 2014.

- UN Women Independent Evaluation Office. "How to Manage Gender-Responsive Evaluations, Evaluation Handbook". UN Women, 2015

- UN Women Independent Evaluation Office. "Strengthening Organizational Structure for Delivering Gender Results, Corporate Evaluation of the Regional Architecture of UN Women". UN Women, 2016.

- UN Women Regional Office for Asia and The Pacific “2014 ANNUAL WORK PLAN HUMAN RESOURCE TABLE in USD”. UN Women Regional Office for Asia and The Pacific. 2014

- UN Women, UN Environment. "Strengthening Human Rights and Gender Equality through Climate Change Action and Disaster Risk Reduction. Project Proposal. (Signed)". UN Women, UN Environment 2018

- UN Women. ""Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex I - STATEMENT  Made  by  women  participants  of  the  South  Caucasus  Women’s  Expert  Group  Meeting  in  Tbilisi,  16-19  December,  2016". UN Women, 2016

- UN Women. "2011 Progress Report." UN Women, 2012.

- UN Women. "2012 Data Companion." UN Women, 2013.

- UN Women. "2012 Progress Report." UN Women, 2013.

- UN Women. "2013 Data Companion." UN Women, 2014.

- UN Women. "2013 Progress Report." UN Women, 2014.

- UN Women. "2014 Data Companion." UN Women, 2015.

- UN Women. "2014 Progress Report." UN Women, 2015.

- UN Women. "2015 Data Companion." UN Women, 2016.

- UN Women. "2015 Progress Report." UN Women, 2016.

- UN Women. "2016 Data Companion." UN Women, 2017.

- UN Women. "2016 Progress Report." UN Women, 2017.

- UN Women. "2016 UN Women Humanitarian Programme Report." UN Women, 2017.

- UN Women. "2017 Data Companion." UN Women, 2018.

- UN Women. "2017 HACRO Report." UN Women, 2018.

- UN Women. "2017 Progress Report." UN Women, 2018.

- UN Women. "2017 Report on Strengthening Resilience and Protection of Women and Youth in Host Communities - Lebanon". UN Women, 2017.

- UN Women. "2018 Report, LEAP Egypt, Iraq, Jordan". UN Women, 2018.

- UN Women. "Afghanistan AWP Monitoring Report 2017". UN Women, 2017

- UN Women. "Afghanistan AWP Monitoring Report 2018".UN Women, 2018

- UN Women. "Afghanistan RMS 2017-18". UN Women, 2018.

- UN Women. "Agency Project Proposal, Rapid Response". UN Women, May 2016.

- UN Women. "Agreement with Government of Japan". UN Women, 2014.

- UN Women. "An Examination of Jordanian Women's Experiences in the Garment Industry, Final Report". UN Women, Sept 2016.

- UN Women. "Annex 1 to Final Report on Community Mobilization and Economic Empowerment of Women and Youth in crisis affected communities-Lebanon". UN Women, 2017.

- UN Women. "Annex 2 to Final Report on Community Mobilization and Economic Empowerment of Women and Youth in crisis affected communities-Lebanon". UN Women, 2017.

- UN Women. "Annex 3 Development Results Framework, UN Women Strategic Plan 2014-17." UN Women, 2013.

- UN Women. "Annex A for Final Progress Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Annex A for Final Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Annex A to Progress Report on Utilizing Digital Tools to Promote Human Rights and Create Inclusive Public Spaces in the Gaza Strip". UN Women, 2018.

- UN Women. "Annex B for Final Progress Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Annex B for Final Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Annex B to Progress Report on Utilizing Digital Tools to Promote Human Rights and Create Inclusive Public Spaces in the Gaza Strip". UN Women, 2018.

- UN Women. "Annex C for Final Progress Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Annex C for Final Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Annex D for Final Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Annex E for Final Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Annex F for Final Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Annex G for Final Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Annex I for Palestine Strategic Notes and Annual Work Plan (2014 - 2016)". UN Women, Dec 2013.

- UN Women. "Annex II for Palestine Strategic Notes and Annual Work Plan (2014 - 2016)". UN Women, Dec 2013.

- UN Women. "Annex III for Palestine Strategic Notes and Annual Work Plan (2014 - 2016)". UN Women, Dec 2013.

- UN Women. "Annex IV for Final Report on Improving Holistic Protection Services for Women and Girls in the Conflict Affected Context of the Gaza Strip”. UN Women, 2016.

- UN Women. "Annex IV for Palestine Strategic Notes and Annual Work Plan (2014 - 2016)". UN Women, Dec 2013.

- UN Women. "Annexes to evaluation report: UN Women’s contribution to UN system coordination on GEEW." UN Women, 2016.

- UN Women. "Annexes to evaluation report: UN Women's contribution to increasing women's leadership & participation in peace & security & humanitarian response." UN Women, 2013.

- UN Women. "Annual  Review  Report  and  Final  to  Government  of  Sweden  through  the  Swedish  International  Development  Cooperation  Agency, Strategic  Partnership  Framework  2011-2016". UN Women, 2017

- UN Women. "Annual Progress Report for Improving Human Security Through Neighborhood Upgrading and Economic Empowerment of Vulnerable Refugees and Host Communities". UN Women, Aug, 2016.

- UN Women. "Annual Report 2011-12." UN Women, 2012.

- UN Women. "Annual Report 2012-13." UN Women, 2013.

- UN Women. "Annual Report 2013-14." UN Women, 2014.

- UN Women. "Annual Report 2014-15." UN Women, 2015.

- UN Women. "Annual Report 2015-16." UN Women, 2016.

- UN Women. "Annual Report 2016-17." UN Women, 2017.

- UN Women. "Annual Report 2017-18." UN Women, 2018.

- UN Women. "Arab States Annual Work Plan (2014 - 2017)". UN Women, 2014.

- UN Women. "Arab States Strategic Note, Narrative (2018 - 2022)". UN Women, 2018.

- UN Women. "Arab States Strategic Note, Organisational Effectiveness and Efficiency (2018 - 2022)". UN Women, 2018.

- UN Women. "Arab States Strategic Notes and Annual Work Plan (2012 - 2013)". UN Women, 2012.

- UN Women. "Arab States Strategic Notes and Annual Work Plan (2018 - 2022)". UN Women, 2018.

- UN Women. "Arab States Strategic Notes, Development Results Framework (2018 - 2022)". UN Women, 2018.

- UN Women. "ASRO AWP Monitoring 2015". UN Women, 2015.

- UN Women. "ASRO AWP Monitoring 2016". UN Women, 2016.

- UN Women. "ASRO AWP Monitoring 2017". UN Women, 2017.

- UN Women. "ASRO RMS". UN Women, date unknown

- UN Women. "Barbados AWP Monitoring Report 2018". UN Women, 2018.

- UN Women. "Barbados RMS 2018". UN Women, 2018.

- UN Women. "Barbados Strategic Note 2014-17". UN Women, 2014.

- UN Women. "Barbados Strategic Note 2018-21". UN Women, 2018.

- UN Women. "Booklet: Flagships Programming Initiative." UN Women, 2015.

- UN Women. "Brazil - Budget 126804 revised 01092016 (Portuguese)". UN Women, 2016.

- UN Women. "Brazil 2014 Annual Work Plan Human Resource Requirements in USD". UN Women, 2014.

- UN Women. "Brazil AWP Monitoring Report 2016". UN Women, 2016.

- UN Women. "Brazil AWP Monitoring Report 2017". UN Women, 2017.

- UN Women. "Brazil AWP Monitoring Report 2018". UN Women, 2018.

- UN Women. "Brazil CO Annual Workplan 2014 - DRF". UN Women, 2014.

- UN Women. "Brazil CO SN - Annual Work Plan 2018". UN Women, 2018.

- UN Women. "Brazil RMS 2016-2018". UN Women, 2018.

- UN Women. "Brazil SN Narrative Report". UN Women, Sept 2018.

- UN Women. "Brazil Strategic Note 2014-2016". UN Women, 2014.

- UN Women. "Brief: Mainstreaming of Security". UN Women, undated. (Dropbox: Corporate - Security & Programme Criticality)

- UN Women. "Brief: Security Risk Management". UN Women, undated. (Dropbox: Corporate - Security & Programme Criticality)

- UN Women. "Case studies: UN Women's contribution to increasing women's leadership & participation in peace & security & humanitarian response." UN Women, 2013.

- UN Women. "Colombia 2014 Annual Work Plan Human Resource Table in USD". UN Women, 2014.

- UN Women. "Colombia 2014 Annual Work Plan". UN Women, 2014.

- UN Women. "Colombia AWP Monitoring 2015". UN Women, 2015.

- UN Women. "Colombia AWP Monitoring 2016". UN Women, 2016.

- UN Women. "Colombia AWP Monitoring 2017". UN Women, 2017.

- UN Women. "Colombia AWP Monitoring 2018". UN Women, 2018.

- UN Women. "Colombia RMS". UN Women, date unknown.

- UN Women. "Colombia Strategic Note (2014 - 2017)". UN Women, 2014.

- UN Women. "Community Mobilization and Economic Empowerment of Women and Youth in crisis-affected areas in Lebanon". UN Women, Apr 2016.

- UN Women. "Country Report: Haiti". UN Women, 2014.

- UN Women. "Country Report: Occupied Palestinian Territory". UN Women, 2014.

- UN Women. "Cover letter - Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF)". UN Women, June 2017

- UN Women. "Cover Letter for Building Business Bridges Programme". UN Women, Apr 2018.

- UN Women. "Cover Letter for Jordan Final Narrative Report". UN Women, 2016.

- UN Women. "Cover Letter to Final Report on Community Mobilization and Economic Empowerment of Women and Youth in crisis affected communities-Lebanon". UN Women, 2017.

- UN Women. "Cover Letter to Progress Report on Utilizing Digital Tools to Promote Human Rights and Create Inclusive Public Spaces in the Gaza Strip". UN Women, 2018.

- UN Women. "Cover Letter, Final Report LEAP Iraq & Jordan". UN Women, Sept 2017.

- UN Women. "Cover letter, First progress report for Strategic Partnership Framework II 2017-2020". UN Women, June 2018

- UN Women. "DAMS List of Projects." UN Women, 2018.

- UN Women. "Development Outcome Reports WPSHA 2016." UN Women, 2016.

- UN Women. "Development Outcome Reports WPSHA 2017." UN Women, 2017.

- UN Women. "Development Outcome Reports WPSHA 2018." UN Women, 2018.

- UN Women. "Development Results Arab States Regional Office (2014 - 2017)." UN Women, 2014.

- UN Women. "Draft Agenda Kampala (Training)." UN Women, 2017.

- UN Women. "Draft Humanitarian Framework 2017." UN Women, 2018.

- UN Women. "Economic Empowerment of Syrian Women Refugees and Host Communities in the Arab Region, Final Evaluation of UN Women Regional Project (2014 - 2016). UN Women, 2017.

- UN Women. "Economic Empowerment of Syrian Women Refugees and Host Communities in the Arab Region, Final Evaluation of UN Women Regional Project Annexes (2014 - 2016). UN Women, 2017.

- UN Women. "Ecuador 2015 Annual Work Financial Resource Table in USD". UN Women, 2015.

- UN Women. "Ecuador AWP Monitoring 2016". UN Women, 2016.

- UN Women. "Ecuador AWP Monitoring 2017". UN Women, 2017.

- UN Women. "Ecuador RMS". UN Women, 2018.

- UN Women. "Ecuador Strategic Note (2015 - 2018), UN Women, 2015.

- UN Women. "Evaluation report: Evaluation of the From Communities to Global Security Institutions (FC2GSI)Programme." UN Women, 2014.

- UN Women. "Evaluation report: Evaluation of UN Women SIDA Strategic Partnership Framework 2011–16." UN Women, 2016.

- UN Women. "Evaluation report: Joint Evaluation of JPs on GE in UN system." UN Women, 2013.

- UN Women. "Evaluation report: UN Women’s contribution to UN system coordination on GEEW." UN Women, 2016.

- UN Women. "Evaluation report: UN Women's contribution to increasing women's leadership & participation in peace & security & humanitarian response." UN Women, 2013.

- UN Women. "External brief: What the UN Development System Repositioning means for UN Women". UN Women, 2018.

- UN Women. "Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex A - Citations Global Study". UN Women, 2017

- UN Women. "Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex B - Image of UN Women's supported response to emergencies in Mosul, Iraq". UN Women, 2017

- UN Women. "Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex C - Penn Law, Mapping the Impact of Gender Equality Provisions". Penn Law, May 2016

- UN Women. "Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex D - Pacific Consultation Background Paper 'Innovating for Impact: A Pacific Regional Consultation on Women's Political Empowerment and Leadership'". UN Women, Sept 2016

- UN Women. "Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex E - Political Dialogues Paraguay". UN Women, Oct 2016

- UN Women. "Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex F - EMB Guidebook (Vietnamese)". UN Women, 2015

- UN Women. "Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex G - Picture from Jordan candidate training Credit RASED". UN Women, undated

- UN Women. "Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex H - Image, UN Women ED meets women survivors in Marinilla, Colombia". UN Women, undated

- UN Women. "Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex J - Validation  Meeting  of  The  Mapping  Report  on  Country  Progress  on  The  Implementation  of  United  Nations  Security  Council  Resolutions  on  Women,  Peace  and  Security  in  East  and  Southern  Africa". UN Women, Sept 2016

- UN Women. "Fifth and final report for the UN Women 'Strategic Partnership Framework 2011-2016 (SPF), Annex K - Consolidated report, Inter-agency Gender Assessment of Refugee Camps in Rwanda". UN Women, 2016

- UN Women. "Final Cover Page for Economic Empowerment of Syrian Women". UN Women, Aug 2014.

- UN Women. "Final Donor Report, LEAP Iraq & Jordan". UN Women, 2017.

- UN Women. "Final Evaluation of Expanding Syrian Women Refugees͛ Access to Economic Recovery Opportunities and Meaningful".  Engagement in Community Life". UN Women, Dec 2015

- UN Women. "Final Evaluation of UN Women Project on Social Cohesion, Service Delivery and Gender Equality". UN Women, Aug 2016.

- UN Women. "Final Financial Statement for Building Business Bridges Programme". UN Women, Dec 2017.

- UN Women. "Final Narrative Report for Economic Empowerment of Syrian Women Refugees Regional Project Implemented in Five countries: Jordan, Iraq, Lebanon, Egypt, Syria". UN Women, 2016.

- UN Women. "Final Progress Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Final Report 2017, LEAP Egypt, Iraq & Jordan". UN Women, 2017.

- UN Women. "Final Report on Community Mobilization and Economic Empowerment of Women and Youth in crisis affected communities-Lebanon". UN Women, 2017.

- UN Women. "Final Report on Engendering Humanitarian Action in Palestine". UN Women, 2016.

- UN Women. "Final Report on Improving Holistic Protection Services for Women and Girls in the Conflict Affected Context of the Gaza Strip”. UN Women, 2016.

- UN Women. "Final Report, Palestine Country Portfolio Evaluation". UN Women, Mar 2017.

- UN Women. "FPI Brief-GIR V2". UN Women, 2016.

- UN Women. "FPI Brief-LEAP_v5." UN Women, 2015.

- UN Women. "GAI 2 pager." UN Women, 2017.

- UN Women. "GAI 2016 Consolidated Narrative and Financial Report." UN Women, 2017.

- UN Women. "GAI Operations Manual." UN Women, 2016.

- UN Women. "Gender and Conflict Analysis in ISIS Affected Communities of Iraq". UN Women, May 2017.

- UN Women. "Gender Inequality of Risk. Gender-responsive disaster risk reduction and resilience building". UN Women, 2018.

- UN Women. "HACRO Overview". UN Women, undated.

- UN Women. "Haiti 2014 Annual Work Plan Human Resource Table in USD". UN Women, 2014.

- UN Women. "Haiti 2014 Annual Work Plan". UN Women, 2014.

- UN Women. "Haiti 2018 Annual Work Plan". UN Women, 2018.

- UN Women. "Haiti AWP Monitoring 2015". UN Women, 2015.

- UN Women. "Haiti AWP Monitoring 2016". UN Women, 2016.

- UN Women. "Haiti AWP Monitoring 2017". UN Women, 2017.

- UN Women. "Haiti AWP Monitoring 2018". UN Women, 2018.

- UN Women. "Haiti RMS". UN Women, date unknown.

- UN Women. "Haiti Strategic Note (2014 - 2016)". UN Women, 2014.

- UN Women. "Haiti Strategic Note and Annual Work Plan (2012 - 2013)". UN Women, Jan 2012.

- UN Women. "Haiti Strategic Note, Development Results Framework (2018 - 2021)". UN Women, 2018

- UN Women. "Haiti Strategic Note, Organisational Effectiveness and Efficiency (2018 - 2021)". UN Women, 2018.

- UN Women. "HQ RMS 2016-2018 (Outcomes, Outputs, Activities)." UN Women, 2018.

- UN Women. "Human Security Leaflet - Improving Human Security Through Neighborhood Upgrade and EE". UN Women, date unknown

- UN Women. "Humanitarian Portfolio Analysis." UN Women, 2018.

- UN Women. "Increasing Human Security to Disaster Risk in Haiti". UN Women, Sept 2015.

- UN Women. "Interim Financial Donor Report, LEAP Jordan, Egypt & Iraq". UN Women, Dec 2016.

- UN Women. "Interim Progress Report, LEAP Egypt, Iraq & Jordan". UN Women, 2017.

- UN Women. "Iraq 2014 Annual Work Plan Human Resource Table in USD". UN Women, 2014.

- UN Women. "Iraq 2014 Annual Workplan". UN Women, 2014.

- UN Women. "Iraq Annual Work Plan 2016". UN Women, 2016.

- UN Women. "Iraq AWP Monitoring 2015". UN Women, 2015.

- UN Women. "Iraq AWP Monitoring 2016". UN Women, 2016.

- UN Women. "Iraq AWP Monitoring 2017". UN Women, 2017.

- UN Women. "Iraq DRF Report". UN Women, date unknown.

- UN Women. "Iraq RMS". UN Women, date unknown.

- UN Women. "Iraq Strategic Note (2014 - 2017)". UN Women, 2014.

- UN Women. "Iraq Strategic Note, Development Results Framework (2016 - 2019)". UN Women, 2016

- UN Women. "Iraq Strategic Note, Narrative (2016 - 2019)". UN Women, 2016.

- UN Women. "Iraq Strategic Note, Organisational Effectiveness and Efficiency (2016 - 2019)". UN Women, 2016.

- UN Women. "Jordan AWP Monitoring 2015". UN Women, 2015.

- UN Women. "Jordan AWP Monitoring 2016". UN Women, 2016.

- UN Women. "Jordan AWP Monitoring 2017". UN Women, 2017.

- UN Women. "Jordan AWP Monitoring 2018". UN Women, 2018.

- UN Women. "Jordan RMS". UN Women, date unknown

- UN Women. "Jordan Strategic Note and Annual Work Plan (2012 - 2013)". UN Women, 2012

- UN Women. "Jordan Strategic Note Report (2011 - 2012)"

- UN Women. "LEAP ProDoc Guidance Note." UN Women, date unknown.

- UN Women. "LEAP: UN Women's global humanitarian response program". UN Women, 2018.

- UN Women. "Lebanon AWP Monitoring 2015". UN Women, 2015.

- UN Women. "Lebanon AWP Monitoring 2016". UN Women, 2016.

- UN Women. "Lebanon AWP Monitoring 2017". UN Women, 2017.

- UN Women. "Lebanon AWP Monitoring 2018". UN Women, 2018.

- UN Women. "Lebanon RMS". UN Women, date unknown.

- UN Women. "Management Response, Evaluation of UN Women contribution to the United Nations system coordination". UN Women, 2015. http://gate.unwomen.org/ManagementResponse/ViewManagementResponse?evaluationId=8093

- UN Women. "MetaAnalysis Report 2013." UN Women, 2014.

- UN Women. "MetaAnalysis Report 2014." UN Women, 2015.

- UN Women. "MetaAnalysis Report 2014-15." UN Women, 2016.

- UN Women. "MetaAnalysis Report 2016." UN Women, 2017.

- UN Women. "Monitoring Report on UN Women's Programming in Za'atari Refugee Camp: Restoring Dignity and Building Resilience". UN Women, 2015.

- UN Women. "Northern Iraq Livelihood Assessment, Synthesis Report". UN Women, Mar 2017.

- UN Women. "Organization brief: The security framework of accountability". UN Women, undated. (Dropbox: Corporate - Security & Programme Criticality)

- UN Women. "Overview of UN Women’s Cash-based Intervention Strategy and Cash Guidance Note". UN Women, Sept 2018.

- UN Women. "Palestine AWP Monitoring 2015". UN Women, 2015.

- UN Women. "Palestine AWP Monitoring 2016". UN Women, 2016.

- UN Women. "Palestine AWP Monitoring 2017". UN Women, 2017.

- UN Women. "Palestine AWP Monitoring 2018". UN Women, 2018.

- UN Women. "Palestine Case Study: Joint Evaluation of JPs on GE in UN system." UN Women, 2013.

- UN Women. "Palestine RMS". UN Women, date unknown.

- UN Women. "Palestine Strategic Note, Narrative (2018 - 2022)". UN Women, 2018.

- UN Women. "Palestine Strategic Note, Organisational Effectiveness and Efficiency (2018 - 2022)". UN Women, 2018.

- UN Women. "Palestine Strategic Notes and Annual Work Plan (2012 - 2013)". UN Women, 2012.

- UN Women. "Palestine Strategic Notes and Annual Work Plan (2014 - 2016)". UN Women, Dec 2013.

- UN Women. "Palestine Strategic Notes, Development Results Framework (2018 - 2022)". UN Women, 2018.

- UN Women. "Preliminary analysis of the financial and other implications of General Assembly resolution 72/279 for UN Women". UN Women, 2018.

- UN Women. "Presentation, IASC Coordination". UN Women, 2017. )

- UN Women. "Programme Criticality: Why it is critical to the organization". UN Women, 2018. (Dropbox: Corporate - Security & Programme Criticality)

- UN Women. "Programme Framework, Strategic  Partnership Framework between the Government of Sweden (represented by SIDA) and UN Women 2017-2020". UN Women, 2017

- UN Women. "Progress Report on Utilizing Digital Tools to Promote Human Rights and Create Inclusive Public Spaces in the Gaza Strip". UN Women, 2018.

- UN Women. "Progress Report, year 1. Promoting women's human rights in the context of the Zika epidemic". UN Women, Jan 2018.

- UN Women. "Project: Promoting women's human rights in the context of the Zika epidemic". UN Women, 2016.

- UN Women. "Promoting the Rights, Needs and Agency of Women and Girls in Humanitarian Action." UN Women, 2015.

- UN Women. "Provisional Financial Donor Report for Period ended 31 March 2016". UN Women, 2016.

- UN Women. "Provisional Financial Donor Report, LEAP Jordan, Egypt & Iraq". UN Women, March 2017.

- UN Women. "Provisional Financial Report for Humanitarian Assistance for Middle Eastern Countries Programme". UN Women, 2017.

- UN Women. "PSH Gender Inequality of Risk and Community Resilience in a Changing Climate External." UN Women, date unknown.

- UN Women. "PSH LEAP in Crisis Response External." UN Women, date unknown.

- UN Women. "Q & A, Change Management". UN Women, Sept 2018 vol. 1.

- UN Women. "ROAS Organizational  Effectiveness  and  Efficiency  Framework (2014 - 2017). UN Women, 2014.

- UN Women. "Second Chance Education - Leaving no-one behind". UN Women, 2018.

- UN Women. "Security Mainstreaming: Enhanced personnel security for improved programme delivery". UN Women, Sept 2015. (Dropbox: Corporate - Security & Programme Criticality)

- UN Women. "Self-Report for 2017 on World Humanitarian Summit Commitments and Initiatives". UN Women, 2017

- UN Women. "SP 2011-2013, Development Results Framework Revised 9 August 2012." UN Women, 2012.

- UN Women. "SP 2011-2013, Management Results Framework (Institutional Budget)." UN Women, date unknown.

- UN Women. "SPF 2017-2020 Risk Register". UN Women, 2017.

- UN Women. "Strategic  Partnership  Framework  between  the  Government  of  Sweden  (represented  by  SIDA)  and  UN  Women  2011-2016,  Progress  on  Outcome/Output  Indicators". UN Women, 2017

- UN Women. "Strategic Partnership Framework 2011-2016, Provisional  Financial  Statement  for  Period  ended  31  December  2016". UN Women, 2017

- UN Women. "Strategic Partnership Framework 2011-2016, Provisional  Financial  Donor  Report  for  Period  ended  31  May  2017". UN Women, 2017

- UN Women. "Strategic Partnership Framework between the Government of Sweden (represented by SIDA) and UN Women 2017-2020 - Budget and Expenses as of December 31st, 2017 - in USD". UN Women, 2018

- UN Women. "Strategic Partnership Framework II 2017-2020, First  Progress Report  to  Government  of  Sweden through  the  Swedish  International  Development  Cooperation  Agency". UN Women, 2018.

- UN Women. "Strategic Partnership Framework II 2017-2020, Interim  Financial  Donor  Report  for  Period  ended  31  December  2017". UN Women, 2018

- UN Women. "Strategic Partnership Framework II 2017-2020, Log frame Progress on Outcome/ Output Indicators". UN Women, 2018

- UN Women. "Strategic Plan 2011-13." UN Women, 2011.

- UN Women. "The effect of gender equality programming on humanitarian outcomes." UN Women, 2015.

- UN Women. "Thematic Evaluation of UN Women’s Humanitarian Action in the Arab States Region Final Evaluation Report". UN Women, 2017.

- UN Women. "Thematic Evaluation of UN Women’s Humanitarian Action in the Arab States Region Evaluation Report Annexes". UN Women, 2017.

- UN Women. "Towards Gender Equality in Humanitarian Response Guidebook (Gaza)". UN Women, date unknown

- UN Women. "Training Manual - Web Version." UN Women, 2017.

- UN Women. "UN Agency to UN Agency Contribution Agreement (Amendment One) for Utilizing Digital Tools to Promote Human Rights and Create Inclusive Public Spaces in the Gaza Strip". UN Women, 2017.

- UN Women. "UN Agency to UN Agency Contribution Agreement for Utilizing Digital Tools to Promote Human Rights and Create Inclusive Public Spaces in the Gaza Strip". UN Women, 2017.

- UN Women. "UN Reform: How can UN Women prepare for, manage and influence change at country and regional level?". UN Women, 2018.

- UN Women. "UN Women and Humanitarian Action." UN Women, 2016.

- UN Women. "UN Women Annual Report, Haiti". UN Women, April 2017.

- UN Women. "UN Women Commitments for the World Humanitarian Summit". UN Women, 2016.

- UN Women. "UN Women Humanitarian Programmes Review 2014." UN Women, 2014.

- UN Women. "UN Women Humanitarian Strategy 2014-17." UN Women, 2014.

- UN Women. "UN Women Strategic Plan 2014-17." UN Women, 2013.

- UN Women. "UN Women Strategic Plan 2018-2021 IRRF." UN Women, 2017.

- UN Women. "UN Women Strategic Plan 2018-2021." UN Women, 2017.

- UN Women. "United Nations Entity for Gender Equality and the Empowerment of Women, UN Women as Executing Agency for the United Nations Trust Fund for Human Security, Increasing Human Security to Disaster Risk in Haiti". UN Women, October 2017.

- UN Women. "UNW 2016 Self Report". UN Women, 2016.

- UN Women. "UNW 2017 WHS Commitments Annual Report". UN Women, 2017.

- UN Women. "UNW Brazil OEEF SN Report". UN Women, Sept 2018.

- UN Women. "UNW Brazil Strategic Note 2017-2021. SN Report 2018". UN Women, Sep 2018.

- UN Women. "UNW Strategy to Leverage Innovation & Technology." UN Women, date unknown.

- UN Women. "Women’s  Leadership,  Empowerment,  Access  &  Protection  in  Crisis  Response  (LEAP)  –  Yemen". UN Women, Apr 2018.

- UN Women. "Women's Access to Basic Services in Irbid and Zarqa Governorates". UN Women, 2016.

- UN Women. "WPHF 2017 annual consolidated report." UN Women, 2018.

- UN Women. "Yemen AWP Monitoring 2015". UN Women, 2015.

- UN Women. "Yemen AWP Monitoring 2016". UN Women, 2016.

- UN Women. "Yemen AWP Monitoring 2017". UN Women, 2017.

- UN Women. "Yemen AWP Monitoring 2018". UN Women, 2018.

- UN Women. "Yemen RMS". UN Women, date unknown

- UN Women. "Yemen Strategic Note, Narrative (2017 - 2019)". UN Women, 2017.

- UN Women. "Yemen Strategic Note, Organisational Effectiveness and Efficiency (2017 - 2019)". UN Women, 2017.

- UN Women. "Yemen Strategic Notes, Development Results Framework (2017 - 2019)". UN Women, 2017.

- UN Women. TOR for GAI." UN Women, 2016.

- UN. "Backgrounder: UN Development System Repositioning". UN, May 2018.

- UN. "Frequently Asked Questions: UN Development System Repositioning". UN, May 2018.

- UN. "Key Messages: Reforming the UN Development System". UN, May 2018.

- UNDP. "Gender Equality Strategy 2014-2017: The Future We Want: Rights and Empowerment". UNDP, 2014

- UNDP. "Note to the UNDP Executive Board: Preliminary analysis of the financial and other implications of resolution 72/279 for UNDP". UNDP, 2018.

- UNDP. "What does it mean to LEAVE NO ONE BEHIND?  A UNDP discussion paper and framework for implementation". UNDP, July 2018

- UNEG. "Norms and Standards for Evaluation.” UNEG, 2017.

- UNFPA. "Strategic Framework for Gender Mainstreaming and Women's Empowerment 2008-2011". UNFPA, 2007

- UNHCR. "Figures at a glance (June 2018)". UNHCR, 2018. http://www.unhcr.org/figures-at-a-glance.html

- UNHCR. "UNHCR: Sector Gender Focal Points Network - Jordan". UNHCR, Dec 2017. http://www.refworld.org/docid/5a38e1534.html

- UNICEF, “Towards implementing a human rights-based approach to programming in Humanitarian action”, UNICEF.

- UNICEF. "UNICEF Gender Action Plan, 2018-2021. Executive Board, 2nd regular session 2017." UNICEF, 2017. http://www.unicefinemergencies.com/downloads/eresource/docs/1.8%20Gender%20equality%20in%20humanitarian%20action/2017-16-Gender_Action_Plan-2017.07.14-Rev.1.pdf

- UNICEF. "Working for an Equal Future, UNICEF Policy on Gender Equality and the Empowerment of Girls and Women". UNICEF, May 2010

- UNISDR. "Policy on gender mainstreaming in disaster risk reduction". UNISDR, 2011

- UNSG. "UNSG report on UN Reform. A/73/63-E/2018/8". UNSG, 2018.

- World Humanitarian Summit. "Women and Girls: Catalysing Action to Achieve Gender Equality. High-level leaders' roundtable". WHS, 2016

This will include looking at Knowledge Management strategies at different levels (including flows between HQ and the field, within regions, across countries); the generation of tools, analysis and programmatic guidance as a means to help identify gaps and opportunities?

If “strongly disagree” or “strongly agree”, will discount other responses by ½ the standard deviation associated with all questions and as established in the final quantitative analysis.

This is related to cognitive focus, e.g. giving people a pause to think about UN Women’s work in somewhat more detail but without having to go into specific examples. This will enable respondents to provide more thoughtful responses to subsequent questions. We will collect the answers from this question and create a word-bubble graph to gauge the frequency of different responses.

May need to define these for different respondents and/or select only those relevant to their work.

May need to define relevant coordination mechanisms, e.g. HCT, clusters, etc.

All references to budget amounts are taken from UN Women RMS, specifically the Quarterly Monitoring data and the Development Activities reports.

HA budget in 25 of the 90 countries where UN Women is present, according to UN Women’s 2017-18 Annual Report, pg. 45.

As per Financial Statements provided in UN Women Annual Reports, 2016-2018.

Lebanon, Myanmar, South Sudan, Jordan, Iraq, Turkey, Cameroon, Democratic Republic of Congo, Thailand-APRO, Fiji (MCO), Bangladesh, Mali, Brazil, Kenya, Palestine, Haiti, Colombia, Sudan, Somalia, Yemen, Nigeria, Uganda, Barbados MCO, Afghanistan, Mozambique

Lebanon, South Sudan, Nigeria, Jordan, Uganda, Iraq, Turkey, Cameroon, Democratic Republic of Congo, Thailand-APRO, Fiji (MCO), Bangladesh, Egypt- ROAS, Nepal, Mali, Ecuador, Brazil, Kenya, Ukraine, Palestine, Haiti, Sierra Leone, Colombia, Tajikistan, Sudan, Somalia, Senegal-WCARO

Democratic Republic of Congo, Jordan, South Sudan, Iraq, Nigeria, Lebanon, Cameroon, Nepal, Mali, Uganda, Palestine, Pakistan, Bangladesh, Central African Republic, Fiji (MCO), Ecuador, Ukraine, Egypt- ROAS, Kenya, Brazil, Haiti, Thailand-APRO, Senegal-WCARO, Sierra Leone, Tajikistan, Colombia

Based on budgets identified using UN Women’s RMS system and Quarterly Monitoring data.

Average budget size for the countries with HA budget identified.

UN OCHA Financial Tracking Service. https://fts.unocha.org/

UN Women RMS data, 2016-2018.

UN OCHA Financial Tracking Service. https://fts.unocha.org/

UN Women RMS data 2018.

The types of activities captured were: Technical assistance, coordination, normative, support women’s organisations to participate in the response, livelihood opportunities, GBV prevention and response, capacity building, women’s cohesion/safe spaces and emergency response. DRR activities were captured separately and identified as either disaster response, disaster preparedness, capacity building or normative/standard setting. This data was identified through UN Women RMS, specifically the quarterly monitoring data.

The ‘Actual Budget (HA)’ was identified through analysis of the quarterly monitoring data and budget information provided in UN Women RMS.

The ‘Actual CO Budget’ was identified through the UN Women Global Dashboard.

Mark R. Janz with Noelle Soi and Rebecca Russell, World Vision International, Collaboration and Partnership in Humanitarian Action. Humanitarian Practice Network, December 2009.