TERMS OF REFERENCE

END OF PROJECT EVALUATION FOR THE IBSA PROJECT: Eliminating Child Marriages in Malawi and Zambia and Offering Scholarships to Child Marriage Survivors – pilot project

Commissioned by Un Women Malawi, Zambia, and Ethiopia offices

- Background Information

UN Women Malawi office has been implementing a one-year pilot project on eliminating child marriages and offering scholarship to child marriage survivors. The project was implemented with support from the India, Brazil and South Africa Facility for Poverty and Hunger Alleviation (IBSA Fund), which aims to enhance South-South cooperation for the benefit of the neediest nations of the South

The project comes to end in September 2020 and the Country Office, with support from the UN Women Regional Office, intend to conduct an end of project evaluation for purposes of learning, accountability and decision-making. Findings and lessons drawn from the evaluation will be used to inform the design of the next phase of the project and share knowledge to other countries in the Global South. Implementation of the evaluation will be guided by the following key UN Women documents: Evaluation Policy; UNW Global Evaluation Reports Assessment and Analysis System (GERAAS) evaluation quality checklist UNW Evaluation Handbook; UN SWAP EPI; United Nations Evaluation Group (UNEG) Norms and Standards for Evaluation in the UN System and UNEG Ethical Guidelines.

- Description of the Project

The government of Malawi has been lead champions at continental and global levels in the effort to eradicate child marriage, with demonstrable progress at the national and the community.  Malawi has one of the highest rates of child marriage in the world, with approximately 1 in 2 girls married by the age of 18. One of the main challenges to ending child marriage in Malawi is traditional and engrained attitudes that makes the practice accepted across the society.

The overall goal of the project was to contribute to the elimination of child marriage in Malawi. Ethiopia and Zambia and offer scholarships to child marriage survivors. Through the project, UN Women intended to contribute to and accelerate implementation of the African and global commitments to ending child marriages as a way of achieving the broader development goals of gender equality, freedom from poverty and creating a just world  thereby contributing to the implementation of Agenda 2063 and the Sustainable Development Goals (SDGs), among others. In so doing, the project will promote sharing of experiences and lessons learned through African Union (AU) policy advocacy platforms to enhance South-South Cooperation (SSC) in Africa region from end child marriage programming in Malawi and Zambia. This further contributes to strengthening accountability and efficiency in the efforts to eliminate child marriages in Malawi and Zambia.

The theory of change of the project intended to reposition young women and girls who have experienced child marriage at the center of a social movement while leveraging the transformative power of traditional institutions. Through coordination and capacity building of both government and civil society the project will strengthen accountability and efficiency in the efforts to eliminate child marriages. This was to be achieved through delivering on the four outcomes:

- The Governments of Malawi and Zambia are enforcing the national legislation to eradicate child marriages at national and local level

- Strong communities prevent child marriage through social movements

- Girls and young women, who experienced child marriage, are re-integrated into society and the education system and

- Reposition the outcomes from the project into strategic communication, convening and documentation to share best practice through the African Union for making this a regional approach.

- Purpose of the Evaluation

The overall objective of the evaluation is to assess outcome results and lessons learned from the implementation of the project. The evaluation will contribute to accountability, learning and decision-making and inform design of the new phase of the project. It will also contribute in knowledge sharing to other countries in the Global South. This is a project specific evaluation to be conducted at the end of the intervention’s life cycle. Main key users of the evaluation are UN Women, the IBSA Fund, UN Women Partners, and donors.

In line with UN Women Evaluation Policy, the final evaluation report together with the UN Women management response will be disclosed publicly on the UNW ‘Global Accountability and Tracking of Evaluation Use (GATE) System’ at http://gate.unwomen.org

- Objectives of the Evaluation

The main objective of the evaluation is to assess outcomes and draw lessons from the IBSA fund project in relation to the intended 4 outcomes of the project. This evaluation will provide answers to the following key evaluation questions:

- Was the project relevant to the needs of the target population?

- To what extent has UN Women contributed to achieving the expected changes?

- How can UN Women improve the efficiency of implementing the project in future?

- What was UN Women’s added value to this area of work?

- How have human rights approach and gender equality principles are integrated in implementation?

- What extent the results achieved by the project contributed in promoting the principles of South-South cooperation?

- What lessons have been learnt, good practices and innovations that can be used to support gender equality and human rights in future projects?

The project interventions will be assessed based on criteria of relevance, effectiveness, efficiency, impact, coherence, and sustainability as below. It will also assess the project using the selected evaluation questions related to principle of South-South cooperation. The evaluation questions will also have to be streamlined to fit into each country specific interventions and contexts.

Relevance

- To what extent is the intervention relevant to the needs and priorities as defined by beneficiaries?

- To what extent is the intervention aligned with relevant normative frameworks for gender equality and women’s empowerment?

- What are UN Women’s comparative advantage in this area of work compared with other UN entities and key partners?

Effectiveness

- To what extent are the expected outputs and outcomes achieved and how did UN Women contribute towards these?

- What unexpected results (positive and negative) have been achieved? For who?

- What are the main enabling and hindering factors to achieving planned outcomes?

Efficiency

- To what extent does the management structure of the intervention support efficiency for programme implementation?

- How well have resources and risks been managed to ensure results?

- Can the offices demonstrate that they comply with good financial management practice?

- What are UN Women’s comparative advantage compared with other UN entities and key partners?

Impact

- To what extent is gender equality and women’s empowerment advanced because of the intervention?

- What are the unintended effects, if any, of the intervention?

Sustainability

- To what extent is capacity developed to ensure sustainability of efforts and benefits?

- How will the benefits of the intervention be secured for rights holders (i.e. what accountability and oversights systems were established)?

Consistency

- To what extent did other interventions (particularly policies) support or undermine the project intervention, and vice versa.

- What were synergies and interlinkages between the intervention and other interventions carried out by the UN Women/government, as well as the consistency of the intervention with the relevant international norms and standards to which UN Women/government adheres?

- How consistent were the project intervention with other actors’ interventions in the same context?

Gender Equality and Human Rights

- To what extent has gender and human rights considerations been integrated into the programme design and implementation?

- To what extent have the projects been implemented according to human rights and development effectiveness principles: Participation/empowerment; Inclusion/non-discrimination; National accountability/transparency.

- To what extent have the projects changed the dynamics of power in relationships between different groups?

South-Cooperation

- National Leadership and Ownership: Was the project sourced through a demand-driven approach? How did the host governments demonstrate their ownership to the project?

- Mutual Benefit: What extent the project supported for mutual benefits through sharing of knowledge, experiences, training, technology transfer, among others? Are there mutual gains?

- Equality and Horizontality: What extent the project utilized mutual exchange between developing countries? What extent partners cooperate as peers; consider each other as equals and their relationship as horizontal (nonhierarchical)?

- Complementarity to North-South Cooperation: what extent the project served as complementary to North-South cooperation?

- Scope of the Evaluation

The evaluation will be a combined single assessment of all IBSA initiatives in Zambia, Malawi, and Ethiopia. The evaluation will cover the period between September 2019 to December 2020.

UN Women intends to recruit an international consultant and two national consultants to conduct this evaluation on individual basis. The international consultant (team leader) will be responsible for conducting interviews with relevant staff and partners in Ethiopia including the AU and producing a consolidated final evaluation report covering the three countries. The two national consultants will each be responsible for conducting interviews with relevant staff and partners in Malawi and Zambia and write country case studies for the two countries, respectively. Due to the COVID 19 situation, it is expected that most of the data collection will be conducted virtually.

- Evaluation Design

The approach will be formative (forward-looking). The evaluation will be gender-responsive and it will apply mixed-methods (quantitative and qualitative data collection methods and analytical approaches) to account for complexity of gender relations and to ensure participatory and inclusive processes that are culturally appropriate. The key principles for gender-responsive evaluation at UN Women are: 1) National ownership and leadership; 2) UN system coordination and coherence with regard to gender equality and the empowerment of women; 3) Innovation; 4) Fair power relations and empowerment; 5) Participation and inclusion; 6) Independence and impartiality; 7) Transparency; 8) Quality and credibility; 9) Intentionality and use of evaluation; and 10) Ethics.

The following key phases will be implemented

- Preparation: Establishment of the reference group, and recruitment of the evaluation team and development of data collection and reporting tools

- Conduct: Inception report, data collection and analysis

- Reporting: Presentation of preliminary findings, draft, and final reports

- Use	and	follow	up:	Management response, dissemination of the report, and follow up to the implementation of the management response.

Methodology

The approach will be gender-responsive and highly participatory to ensure all stakeholders are consulted as part of the evaluation process. The methods should include a wide range of data sources, participatory tools for consultation with stakeholders and a plan for inclusion survivors of gender based violence, girls that dropped from early marriages and individuals and groups who are vulnerable and/or discriminated against in the consultation process. Due to possible travel restrictions, it is expected that the methods include creative options for virtual/online participation and data collection. The evaluation team will develop an evaluation matrix explaining the rationale and approach for data collection.

The evaluation team will be expected to do the following:

- Use a wide range of data sources (for example documents, institutional information systems, financial records, field information, consult beneficiaries, staff, NGOs, UN, AUC, experts, government officials and community groups)

- Data collection methods and analysis: conduct interviews, focus group discussions virtually and if possible, surveys as data collection method and identify most significant change case study that will address gender equality and human rights issues; the evaluator will elaborate on the final rationale for selection and their limitations.

- Suggest a plan for inclusion of girls, women, individuals, and groups who are vulnerable and/or discriminated against in the consultation process and a plan for translation, as necessary.

- Detail a plan on how protection of participants and respect for confidentiality will be guaranteed, mitigated against, and addressed.

- Specify a sampling frame (area and population represented, rationale for selection, mechanics of selection, limitations of the sample) and specify how it will address the diversity of stakeholders in the intervention.

- Specify measures to ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights.

- The preliminary evaluation findings should be validated through a debriefing workshop with Evaluation Management and Evaluation Reference groups at the end of the primary data collection stage

- Time Frame

| Task | Time Frame | Person Responsible |
| --- | --- | --- |
| Final ToR (after consultations with reference group and management group) | 2 weeks (20th September 2020) | Evaluation Manager |
| Recruitment of evaluator(s) | 2 weeks post circulation (4th October 2020) | Evaluation Manager and Regional Evaluation Specialist |
| Inception phase | 2 Weeks after signing of contract (17th October 2020) | Local Consultants & International Consultant |
| Delivery of draft and revised evaluation inception report | 2 Weeks after signing of contract (15th October) | Local Consultants & International Consultant |
| Conduct stage (data collection | 2-3 weeks after submission of inception report (30th October) | Local Consultants |
| Reporting stage (analysis and presentation of preliminary findings) | 2-3 weeks after final data collection (15th November) | Local Consultants |
| Consolidation of Reports and Findings | 2-3 weeks after submission of In Country Reports (30th November) | International Consultant |
| Presentation of Consolidated Findings | 2 weeks after submission of In Country Reports | International Consultant |
| Submission of Final Report | 2 weeks after submission of In Country Reports | International Consultant |
| Use and follow-up | 6 weeks after submission of the final report | Evaluation Manager and Regional Evaluation Specialist |

- Expected Deliverables

- Local Consultants

- Evaluation inception report

- A summary report on key findings based on the evaluation criteria and the evaluation questions (Raw) for Malawi and Zambia respectively.

- Country case studies for Malawi and Zambia respectively

Both the inception report, the summary report and the Country Case Studies will be reviewed by the Evaluation Management Group (EMG) and Evaluation Reference Group (ERG) within two weeks of submission.

- International Consultant

- Evaluation inception report

- Final list of evaluation questions: Based on the desk review (s)he will have the overview on what set of evaluation questions can/ should be asked across the 3 countries, and which evaluation questions need to be adapted to the country context

- A consolidated final evaluation report (incorporating findings from Malawi, Zambia, and Ethiopia) upon meeting the GERAAS quality standards, as appreciated by the Evaluation Reference Group and the Evaluation Management Group.

Both the inception report, the list of evaluation questions and consolidated final report will be reviewed by the Evaluation Management Group (EMG) and Evaluation Reference Group (ERG) within two weeks of submission.

- Management of the Evaluation

Evaluation Management Group (EMG) and Evaluation Reference Group (ERG). comprising of UN Women Programme Officers and MER Specialists representing the three countries and from the UN Regional Office will provide oversight and guidance to the process. With oversight from the Un Women Regional Office, the UN Women Malawi MER Specialist will be a focal person for the evaluation.

Payments are tied with assurance that deliverables are deemed to be of satisfactory quality by the Evaluation Reference Group and the Evaluation Management Group

- Consultants Qualifications, Skills, Experience, and competencies

A: International Consultant

Qualifications, experience, and skills. Preference will be given to applicants meeting the following requirements:

- At least a master’s degree, in any social science, preferably including gender, youth, evaluation or social research.

- Proven experience in evaluations, including 10 years of working experience in carrying out evaluations.

- Demonstrated understanding of the Gender Based Violence.

- Good understanding of gender and GBV contextual issues in Malawi, Zambia, and Ethiopia.

- Demonstratable experience in producing well written, analytical reports in English essential

- Both quantitative and qualitative data analysis skills

The consultant should submit a proposal no longer than 7 pages, excluding CVs, budget, and example piece of work.

B. Local Consultant

Qualifications, experience, and skills. Preference will be given to applicants meeting the following requirements:

- At least a master’s degree in social sciences, Development studies and other related fields.

- Technical knowledge in Gender Equality, SGBV, Harmful Cultural practices.

- At least 5 years relevant and professional experience in conducting evaluation.

- Demonstrated ability to design and plan the research approaches and research methodologies. This should include skills and expertise required to design, plan, and conduct and analyze qualitative data

- Ability to design, manage and implement primary research in potentially challenging project environments. This may include the design of surveys, in-depth interviews, focus group and other research approaches.

- Ability to work both independently and as part of a team

- Fluency in English (written and spoken) with excellent drafting and communication skills.

- Ability to communicate in local language in the country in which one is applying for.

Core Values:

- Respect for Diversity

- Integrity

- Professionalism

Core Competencies:

- Awareness and Sensitivity Regarding Gender issues

- Accountability

- Creative Problem Solving

- Effective Communication

- Inclusive Collaboration

- Stakeholder Engagement

- Leading by Example

- Ethical code of conduct

UN Women has developed the UN Women Evaluation Consultants Agreement Form for evaluators that must be signed as part of the contracting process, which is based on the UNEG Ethical Guidelines and Code of Conduct. The signed Agreement will be annexed to the consultant contract.

The evaluators are expected to provide a detailed plan on how the following principles will be ensured throughout the evaluation (see UNEG Ethical Guidance for descriptions): 1) Respect for dignity and diversity; 2) Right to self-determination; 3) Fair representation; 4) Compliance with codes for vulnerable groups (e.g., ethics of research involving young children or vulnerable groups); 5) Redress; 6) Confidentiality; and 7) Avoidance of harm.

Specific safeguards must be put in place to protect the safety (both physical and psychological) of both respondents and those collecting the data. These should include:

1.	A plan is in place to protect the rights of the respondent, including privacy and confidentiality

2.	The interviewer or data collector is trained in collecting sensitive information, and if the topic of the evaluation is focused on violence against women, they should have previous experience in this area

3.	Data collection tools are designed in a way that are culturally appropriate and do not create distress for respondents

4.	Data collection visits are organized at the appropriate time and place so as to minimize risk to respondents

5.	The interviewer or data collector can provide information on how individuals in situations of risk can seek support

The evaluation’s value added is its impartial and systematic assessment of the programme or intervention. As with the other stages of the evaluation, involvement of stakeholders should not interfere with the impartiality of the evaluation.

The evaluator(s) have the final judgment on the findings, conclusions and recommendations of the evaluation report, and the evaluator(s) must be protected from pressures to change information in the report.

Additionally, if the evaluator(s) identify issues of wrongdoing, fraud or other unethical conduct, UN Women procedures must be followed, and confidentiality be maintained. The UN Women Legal Framework for Addressing Non-Compliance with UN Standards of Conduct, and accompanying policies protecting against retaliation and prohibiting harassment and abuse of authority, provide a cohesive framework aimed at creating and maintaining a harmonious working environment, ensuring that staff members do not engage in any wrongdoing and that all allegations of wrongdoing are reported promptly, investigated and appropriate action taken to achieve accountability. The UN Women Legal Framework for Addressing Non-Compliance with UN Standards of Conduct defines misconduct and the mechanisms within UN Women for reporting and investigating. More information can be provided by UN Women if required.

This TOR is cleared by

Signature      ________________________________

Name and Designation:     Yemi Falayajo

Head of Programme UN Women Malawi Office

Date of signing ___________________________________

This TOR is approved by

Signature      ________________________________

Name and Designation:     Clara Anyangwe

Country Representative UN Women Malawi Office

Date of signing ___________________________________

https://www.unwomen.org/en/about-us/accountability/evaluation/governance-and-policy

https://www.unwomen.org/en/digital-library/publications/2015/4/un-women-evaluation-handbook-how-to-manage-gender-responsive-evaluation

https://www.unwomen.org/en/about-us/accountability/evaluation/un-coherence

http://www.unevaluation.org/document/detail/1914

http://www.unevaluation.org/document/detail/102

IBSA Project document 2018

https://www.oecd.org/dac/evaluation/revised-evaluation-criteria-dec-2019.pd