# Mid-Term Evaluation

# Promoting Women and Girls’ Effective Participation in Peace, Security and Recovery in Mozambique

# UN Women Mozambique

# Inception Report

# 20 January 2021

#### Lead Researcher: 		Lina Marcela González-Piñeros

#### Local Research Team: 	Roberto Luis

## Table of Contents

Introduction	2

Background	2

Context	3

Purpose, objectives and scope of the evaluation	4

Purpose	4

Objectives	5

Scope	5

Theory of Change or Programme Theory	6

Methodological Approach	7

Evaluation criteria and elaboration of key questions	7

Indicators for measuring results	8

Evaluation design	8

Phase 1: Inception Phase/Documentary Review	8

Phase 2: Primary data collection	9

Phase 3: Data analysis and Consolidation of the report.	10

Sample and sampling design	10

Facts and assumptions to consider	11

Sampling for women beneficiaries Output 1.1.	12

Sampling table beneficiaries	13

Sampling for all other stakeholders, including beneficiaries of output 2 and 3	13

Limitations, risks and Challenges	16

Ethical/Safeguarding considerations	17

Ethical Considerations	17

Locations and Safety of the interviews and FGDs	17

Data Management	17

Evaluation matrix	18

Stakeholder Analysis	23

Workplan	28

Responsibilities, logistics and support	29

Task distribution until data collection	29

Annexes	30

A.	Documents Reviewed	30

B.	Draft Data Collection Instruments	31

Tool 1. KII – Government stakeholders -national, provincial and district level	31

Tool 2. KII/FGDS – CSOs, women national organizations, national/international direct or indirect partners, and other secondary partners (Universities, private sector)	32

Tool 3. KII with UN Women Teams -programme and policy	33

Tool 4. FGDs questionnaires women beneficiaries at district level	34

Tool 5. FGDs/case studies men/women beneficiaries (Men for Women Training, Police/ Defense Forces WPS Training)	35

Tool 6. Surveys Police/ Defense Forces WPS Training	36

C.	Terms of Reference	37

D.	Evaluation Management and Reference Group Members	44

## Abbreviations

ADEL	Agência de Desenvolvimento Económico Local

BPFA 	Beijing Platform for Action

CAI	Integrated Service Centers

CECAGE 	Coordination Center for Gender Affairs

CEDAW	Convention on the Elimination of All Forms of Discrimination against Women

COREM 	Conselho Religioso de Moçambique

CSO	Civil Society Organisations

DHD 	Direitos Humanos e Desenvolvimento Asociation

EC/KEQ	Evaluation Criteria / Key Evaluation Questions

EE	Efficiency Evaluation Criteria

EF	Eficacy Evaluation Criteria

FDC 	Foundation for Community Development

FES 	Friedrich Ebert Stiftung Foundation

FGDs	Focal Discussion Groups

FGM	Female Genital Mutilation

GBV	Gender Based Violence

GERAAS 	Global Evaluation Reports Assessment and Analysis System (UN Women)

GMPIS 	Sofala Group of Women Sharing Ideas

GN	General Evaluation Criteria

HRGE 	Human Rights and Gender

IDPs	Internally Displaced People

IM	Impact Evaluation Criteria

IPAJ	Legal Aid and Sponsorship Institute

KII	Key Information Interviews

KEQs	Key Evaluation Questions

MDN	Ministry of National Defense

MGCAS	Ministry of Gender, Child and Social Action

MINT	Ministry of Interior

MTE	Mid-Term Evaluation

MULEIDE	Women, Law and Development Association

NAFEZA	Zambezia Feminist Associations Group

NFETE 	Tete Women's Associations Group

NGOs	Non-Governmental Organizations

OECD/DAC	Organisation for Economic Co-operation and Development/ Development Assistance Committee

NPA WPS	National Action Plan on Women Peace and Security in Mozambique

ProPaz 	Peace Promotion Institute of Mozambique

RL	Relevance Evaluation Criteria

SS	Sustentability Evaluation Criteria

TL 	Team Leader

ToR 	Terms of Reference

UEM 	Eduardo Mondlane University

UJC 	Joaquim Chissano University

UN 	United Nations

UNSC 	United Nations Security Council

UNEG 	United Nations Evaluation Group

UNFPA	United Nations Population Fund

GBV	Gender-Based Violence

VSLA	Association of Savings and Credit Villages

WPS	Women Peace and Security

# Introduction

## Background

Enhancing women’s engagement for sustainable peace requires an integrated approach that simultaneously addresses conflict prevention, resolution and recovery, while strengthening national accountability and ensuring women’s protection from all forms of human rights violations, including sexual and gender-based violence. The work of the UN Women on Women, Peace and Security (WPS) is governed by a series of commitments on the rights of women. These include United Nations Security Council (UNSC) landmark Resolution 1325 (2000) and nine successive resolutions - 1820, 1888, 1889, 1960, 2106, 2122, 2242, 2467 and 2493 as well as the Beijing Platform for Action (BPFA) and the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) including the CEDAW General Recommendation No. 30 on conflict prevention, conflict and post-conflict situations.

Since the ratification of the CEDAW in 1997 and the adoption of BFPA, as well as the gender equality as a constitutional principle, Mozambique has made significant progress at political, legal and institutional level. The main milestones include the existence of a National Policy and Implementation Strategy (2018), the National Plan for the Advancement of Women (2010-2014), the Law on Domestic Violence Against Women (29/2009), the Ministry of Gender, Children and Social Action, the National Council for Women's Advancement (MGCAS), the National Council for the Advancement of Women (CNAM), represented at both provincial and district level, the adoption and implementation of an integrated multi-sectoral approach to assist victims of violence against women, National Action Plan (NAP WPS) on WPS, and the National Strategy and law to Prevent and Combat Premature Unions (19/2019).

In this context, the actions of UN Women in Mozambique are aligned with two strategic objectives: 1) consolidate national unity, peace and sovereignty and 2) develop human and social capital in accordance with the government´s Five Year Plan and the National Plan for the Advancement of Women. The project under evaluation in this report aims to contribute to the implementation of the National Plan for the Advancement of Women and the National Action Plan on Women, Peace and Security (2018-2022) (NAP 1325), which was created with the support of UN Women. The project is also part of the larger UN Women Programme on Women, Peace and Security and is being implemented within the framework of the UNDAF and will contribute towards the achievement of the Agenda 2030 for Sustainable Development and Agenda 2063: The Africa We Want.

Based on international experiences, the NAP 1325 has been formulated around three strategic areas: the integrated response to violence against women and girls, the promotion of women ́s economic empowerment and strengthening enabling environments for effective implementation of global, regional and national commitments on WPS at all levels. This approach responds to the strong perception that in Mozambique, as in any part of the world, conflicts exacerbate violence against women and girls and their insecurity, destroy their means of survival, undermine prospects for socioeconomic empowerment and reinforce the exclusion of women from decision-making processes due to their low representation in formal conflict resolution platforms.

As form of operationalizing the NAP, UN Women in partnership with the MGCAS and support of the Governments of Iceland and the Kingdom of Norway, is implementing the project denominated: “Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique”. This project focuses on four interrelated pillars in line with the NAP 1325:

- Enhance security for women and providing integrated multi-sectorial response services to victims of violence;

- Promote and facilitating the socioeconomic recovery of women;

- Strengthen women’s capacity and women’s organizations to participate in conflict prevention and resolution, in particular at community level; and

- Strengthen national capacity to coordinate, monitor and account for the implementation of global commitments on women, peace and security.

## Context

Mozambique has seen positive developments in terms of gender equality and women’s empowerment during the 20 years of relative peace and stability post the 1992 Peace Accords between the government of Mozambique and the former rebel movement RENAMO. For example, women's participation in politics has increased over time, both at the central level and provincial, district and community level. However, progress has not been enough to challenge deeply rooted sociocultural norms at the local level. These sociocultural norms, for example, contribute to the high rates of all forms of violence against women and girls and socio-economic disparities between women and men, which are exacerbated in situations of conflict, and limited participation of women in conflict resolution processes.

Furthermore, the political situation remains fragile with demobilization and reintegration of former rebel armed forces following cease fire between the government and the National Mozambican Resistance (RENAMO) reached in March 2018 and part of the recently definitive peace agreement signed definitive and comprehensive Peace and Reconciliation Agreement by the Government and RENAMO in August 2019. Furthermore, since 2017, the province of Cabo Delgado (in north of Mozambique-one of the provinces with a growing extractive industry) has been affected by attacks by armed group said to be linked to extremist religious groups, which is resulting in social instability. Political-military tensions as well as increasing violent extremism in the northern region threaten the already precarious peace and security of women and girls in Mozambique.

In addition, other factors, such as macroeconomic instability, health crises (including COVID-19, HIV/AIDS, Tuberculosis, etc), natural disasters and the emergence of conflicts, raise further threatens the peace and security of women. For example, cyclones Idai and Keneth damaged or destroyed thousands of homes, hospitals, roads, schools, and farms. Safe water and sanitation were compromised, resulting in a subsequent cholera outbreak; health services were severely disrupted and remain limited or non-existent; households lost food, legal documents, and other assets; with particular protection risks increased for women and girls (CARE, Sep 2020). In CARE’s rapid gender analysis following Cyclone Idai in Mozambique in 2019, all women respondents stated that they did not own the land they worked on. If their husbands died, women told CARE, the land would pass to his family – and faced eviction (CARE, 2019).

Project evaluations of the responses to these emergencies also found that during the recovery phase, shelter and gender activities were no longer integrated, thus risking the possibility to reinforce negative masculinities and reversing gains in fully integrating women to household and community decision making (CARE, Sep 2020). Furthermore, the COVID-19 crisis brought new challenges to women and girls around the world and many countries recorded a surge in domestic violence, resulting from confinement and increased tensions in the household. In Mozambique, economic pressure, loss of livelihoods and disruption in access to health, social and protection services placed an added burden on women and girls (Spotlight Initiative, 2020).

For example, lockdown confinement, economic stress and anxiety about infection make it very likely that prevalence GBV rates will rise. For survivors of violence, lockdowns have trapped them in their homes with their abusers and isolated them from people and resources of support. Furthermore, UNFPA also warned of a potential rise in FGM as well as child or forced marriages at this time of restricted movement, poor visibility and weakened protection systems. For Mozambique, specific alerts were given in regard to an increase in the prevalence of child marriages (with Mozambique having the highest percentage in the near region at 53%) given poverty and economic instability being the major reported cause (CARE, Abr 2020).  The overlap of conflict and climatic shocks with pre-existing vulnerabilities in the region—including poverty, marginalization and harmful social and gender norms—significantly heightened protection risks. Women and children are at particular risk of exploitation and abuse, including forced recruitments and sexual violence, in addition to lack of access to education for girls and boys (OCHA, Oct 2020).

Under this context, and using adaptative programming, UN Women has implemented so far two thirds of the “Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique”. The project is being supported by the Government of Iceland and the Kingdom of Norway, and complementing efforts previously funded also by these donors as well as other international and national initiatives. With a duration of five years, the project started in December 2017 and will end in December 2021 (as a result of an extension of the initial timeframe ending in December 2020). It is currently being implemented in 14 districts and 7 provinces of the country with a total budget of approximately 4.5 million dollars.

The project’s rationale stems from the need to promote the active and full participation of women and girls in peace, security and recovery processes in Mozambique at all levels. It has a national scope in the area of disseminating the NAP 1325 and strengthening MGCAS ́ technical capacity to promote and monitor the implementation of the NAP 1325 in all provinces of the country and complementing previous and current efforts. The intervention specifically aims to strengthen the capacity of national institutions to provide integrated services for women and girls who are victims of violence and support the economic recovery of women and girls, including those resulting from the exploitation of natural resources and emerging religious fundamentalisms.

Furthermore, it complements the institutional support to the MGCAS at central level provided by the Government of Iceland by enabling the recruitment of technical expertise and thus enhance the capacity of the WPS Unit as well as administrative and financial assistance. Furthermore, it provides and strengthens capacity at provincial and district levels to lead, contribute to and monitor the implementation of NAP 1325. Finally, the project also aims strengthen the capacity of organizations of women and gender activists, to enable them to play a more active role in implementing the NAP 1325 at the provincial, district and community levels, including in the areas of conflict prevention and management.

## Purpose, objectives and scope of the evaluation

### Purpose

The mid-term evaluation is taking place during the 2.5 year of implementation and UN women commissioned the MTE to inform future direction of the project. Therefore, it aims at improving implementation, use of resources, accountability as well as aims to identify the lessons learnt and good practices in order for the project to grow and adapt accordingly in order to achieve the intended results. In this perspective, the evaluation will be used for both accountability and learning purposes, as well as contributing to inform future implementation and decision-making. The evaluation will also serve to sharpen and/or re-align results to new national development indicators, the challenges of the protracted instability in Manica and Sofala Provinces, growing violence in Cabo-Delgado and extreme climate events (Manica, Sofala), in project implementation areas and the tension between emergency and development interventions.

The target audience of the evaluation will be the UN Women project management, its country office and regional management; the donor of the project, other donors interested in UN Women’s portfolio, UN Women’s partners (including the national government and the provincial governments); other stakeholders engaged stakeholders engaged in promotion of WPS agenda, in and out of Mozambique.

### Objectives

Considering the mandates to incorporate human rights and gender equality in all UN work and the UN Women Evaluation Policy, which promotes the integration of women’s rights and gender equality principles, these dimensions will have a special attention in this evaluation. A specific evaluation objective on human rights and gender equality is included as well as considered under each evaluation criterion.

The overall objectives of this evaluation are to:

- Analyse how Human Rights Approach and gender equality principles are integrated in the interventions.

- Assess the relevance of the project at national level including alignment with international agreements and conventions on WPS and other gender equality and women’s empowerment.

- Assess the effectiveness and organizational efficiency in achieving expected results, including the effectiveness of programming strategies in implementing global commitments within national priorities for in working toward to achieve expected results, with a special focus on innovative, scalable and replicable interventions.

- Assess the initial impact of the intervention on the lives of beneficiaries, communities, and institutions involved in the project.

- Assess the potential sustainability of the interventions in achieving gender equality and women’s empowerment in the context of WPS.

- Assess the functioning and efficacy of the Monitoring, Evaluation and Knowledge Management system, identifying and validating lessons learned, good practices and examples of innovation. The evaluation should also investigate the contextual factors that are enabling or restricting the achievement of results, including financial management and human resource investment; and

- Provide actionable recommendations with respect to improving the project and similar programmes in the future.

This inception report intends to put forward the methodological design of the project’s mid-term evaluation, on the basis of the current context and needs. The evaluation team is aiming to finalise and present actionable recommendations by mid-March 2021 and thus informing programming for the last year of implementation.

### Scope

The main scope of this mid-term evaluation relates to the current delivery and achievement of the project Theory of Change and Results Framework indicators as included below. Yet, as a Mid Term Evaluation it will only consider project delivery and reports by December 2020, and will formulate recommendations for the last year of delivery of the project.

The deliverables expected are as below, with the workplan explained in detail in the next sections.

- Evaluation Inception report and debriefing.

- Data collection debriefings, to be done immediately after field data collection is completed, with the aim to present and discussion preliminary findings in primary data collection and determine possible gaps in the analysis.

- Draft assessment report.

- Final assessment report.

- Presentations to stakeholders.

## Theory of Change or Programme Theory

The project is guided by the following theory of change: 1) if a facilitating environment is created for the implementation of WPS commitments, 2) if women participate in decision-making processes on prevention, management and conflict resolution in an effective way, and 3) if the protection, physical and mental health and economic security of women and girls is guaranteed, their human rights respected and their specific needs in the process of peacebuilding and recovery fulfilled. Then, societies will be more peaceful and fairer, because evidence shows that women are the driving forces of peace and security and inclusive societies are more likely to be stable.

Furthermore, post-conflict scenarios are opportunities to link to the root causes of gender inequality barriers. The expected results of the project are the following:

Outcome 1. Women and girls’ safety, physical and mental health and security are enhanced, and their human rights protected.

Output 1.1: Women and girls affected by violence have access to comprehensive services to redress - including appropriate protection, health and psychosocial and legal services in resettlement, returning areas and in disaster affected areas.

Outcome 2: The socio-economic recovery of women and girls is increased in the post conflict setting.

Output 2.1: Women and girls have increased access to economic opportunities in the context of recovery from conflict and cyclone IDAI.

Outcome 3: The enabling environment for sustainable implementation of WPS commitments is strengthened.

Output 3.1: Women and girls’ capacity to participate meaningfully in conflict prevention/resolution strengthened.

Output 3.2: Capacity of the Ministry of Gender to coordinate and monitor implementation of NAP and fulfil UN reporting requirements strengthened.

Output 3.3: National capacity to implement and generate knowledge on WPS enhanced

# Methodological Approach

As mentioned above, this evaluation aims at improving implementation, use of resources, accountability as well as aims to identify the lessons learnt and good practices in order for the “Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique” project to grow and adapt accordingly in order to achieve the intended results.

As the project covers a variety of activities covering both  qualitative and quantitative results, the evaluation team will use a variety use non-experimental assessment tools and extensive data triangulation through the 'mixed methods' approach. These will include: i) a review of project results from documentary means, ii) in-situ assessment of results and practices through various tools and methods (Focal Group Discussion, Key Informative Interviews (KIIs) with external and internal stakeholders, Surveys and Case Studies), and iii) triangulation of the information through comparison of information collected and validation meetings with the HiH team.

Given the impossibility of doing direct field work as a result of the current restrictions with international travel, the lead consultant was assigned one local consultants based in Mozambique. The local consultants were assigned to work across all areas of work as descrived in the Task distribution until data collection section.

Human rights and gender (HR & GE) considerations will be integrated into the evaluation process and products, in line with the UNEG Guidance “Integrating Human Rights and Gender Equality in Evaluation” by:

- Using UN Women’s stakeholder analysis template/criteria as a basis for the stakeholder analysis performed. The Stakeholder analysis  includes a diverse group of stakeholders, including women and men, as well as those who are most affected by rights violations and groups who are not directly involved in the intervention. Both direct and indirect duty bearers and right-holders have been identified, as well as relevant actors that might have been excluded from the project delivery and which can limit the effectivity of the evaluation and programme delivery.

Specific criteria was added to address HR & GE considerations, within the Evaluation matrix. This criteria is specific to the context of the intervention to be evaluated, including specific questions to evaluate results in conflict and disaster-affected areas.

The evaluation methodology employs a mixed methods approach, appropriate to addressing HR & GE. Specific data collection tools and methodological approaches have been formulated for each different stakeholder, with detailed information included in the Stakeholder analysis, Evaluation matrix and the below Sampling Framework. The evaluation methodology also detailed triangulation mechanisms to be used during data analysis.

Safeguarding and ethic principles have been added to this inception report, as well as an analysis of key contextual challenges, risks and limitations.

Additional analysis on how the above plan is implemented during data collection and reporting, will be added in the draft and final reports, including a summary checklist.

## Evaluation criteria and elaboration of key questions

The evaluation will be guided by OECD/DAC, UN Evaluation Group (UNEG) and UN Women Evaluation and Gender-Responsive Evaluation guidelines, and thus aligned with the above-mentioned Evaluation Criteria (Relevance, Impact, Effectiveness, Efficacy, Sustainability and Human Rights Approach and gender equality) and in accordance with above-mentioned evaluation objectives. A full explanation of the updated OECD evaluation criteria has been added within the Evaluation matrix.

The evaluation Terms of Reference (ToR) proposed thirty evaluation questions and seven evaluation criteria as the basis for this research (ToR are available in Annex C). Based on introductory conversations with the UN Women and MGCAS project team and Evaluation Reference Group, and the limitations and context now created by the response to the COVID-19 pandemic, these questions were reduced to twelve Key Evaluation Questions (KEQ) and six evaluation criteria to coincide with the objectives set in the Terms of Reference and alignment with OECD/DAC and UNEG Evaluation Criteria. Additional detail is now provided in the KEQ to specify the project areas of work or outputs to be analysed.

The KEQs were further analysed in accordance with Tool 8 of the UN Women Evaluation Guidance for Gender-Response Evaluations and includes:

classification of each KEGs against OECD/DAC evaluation criteria they were meant to respond to,

specific guiding questions (sub-questions) to guide data collection against each KEG,

the relevant indicators and stakeholder that can help analysing/responding to the question, this is linked with the specific Stakeholder analysis also included in this report.

the relevant data collection method and source of information to be used to collect the responses,

and assumptions expected in terms of data collection and analysis.

This final Evaluation Criteria and KEQ are included in the section Evaluation matrix.

## Indicators for measuring results

All Evaluation Criteria and KEG, but particularly impact and effectiveness criteria, will be measured against the project’s log frame indicators and targets. These indicators and targets are below:

- Output 1.1 Number of people who increase their skills and knowledge in assisting victims of violence in line with the multisectoral integrated services mechanism Baseline: 0	Target: 200

- Output 2.1 Number of women and girls in need who benefited from support to access to economic opportunities Baseline: 0 Target: 8000

- Output 3.1 Number of women trained to engage in conflict prevention/resolution at community level Baseline: 0 Target: 130

- Output 3.2 Number of sectors which implement NAP related actions Baseline:0 Target:2

- Output 3.3 Number of government officials directly engaged in a WPS course in an academic institution Baseline:0 Target: 10

Specific indicators for all other criteria are included in the Evaluation Matrix.

## Evaluation design

As mentioned above, this evaluation applies a mixed methods approach, using multi-pronged participatory and phase approaches for the consultations and data collection, ensuring triangulation of primary information for validation purposes. The proposed phased approach for this evaluation is as follows:

### Phase 1: Inception Phase/Documentary Review

Relevant documents have already been provided and have started to be studied. These include:

UN Women strategy documents, policies, implementation, gender, environment and guidelines, specifically all members of the Evaluation Team have already completed the “How to Manage Gender-responsive Evaluation” mandatory training;

National guiding policies, particularly the National Action Plan on Women, Peace and Security;

Project design and evidence-based documents including project concept note and scoping studies;

Project’s assessment reports and its annexes, including programme implementation plans, evidence of project delivery and financial reports.

Most of the documentary review has been carried out during the inception phase and guided the detailed design of the evaluation.  Additional documents obtained during the field visits will be reviewed as they come, and documentation will be reviewed again during the data collection phase to clarify or verify any disagreements in data collection.

This report also includes a stakeholder analysis and full consolidation of evaluation questions and tools. These two tools and the WorkPlan were presented and discussed with members of the Evaluation Reference Group in order to review possible gaps and provide additional time for review of the inception report. A time of no less than a week has been given to review and comment on the report.

### Phase 2: Primary data collection

This phase includes:

- Desk-based/remote primary data collection: Key Informant semi-structured Interviews (KIIs) and Focal Group Discussions (FGDs) will be conducted remotely with:

- Programme Teams, MGCAS and donors (Specific information on which partners are included in the sampling analysis).

- Partners and actors directly involved in project delivery and monitoring that can be contacted via phone and online (Specific information on which partners are included in the sampling analysis, but this include partner universities, local CSOs and NGO organisations, which in some cases are also direct or indirect beneficiaries of the project).

- In-field primary data collection: Through the Evaluation local consultants, the evaluation teams will consolidate face-to-face KIIs, case studies, surveys and FGDs with all stakeholders in the field. These include:

- Project partners, direct and indirect beneficiaries of the project not interviewed online.

- Community and women leaders which may have been part of the project but only at local levels.

For this, this mid-term evaluation will use a non-experimental mix-method approach. The stakeholder analysis revealed that information on the different Evaluation Criteria is shared across various stakeholders, and that these stakeholders need to be engaged differently through different tools, as follows. Thus, the evaluation will use combination of quantitative and qualitative research methods which will be tailored to the different stakeholders and Key Evaluation Questions. Both the Evaluation Matrix and Stakeholder Analysis include specific references to the specific tools that will be used. In summary the Evaluation Design and tools to be used (draft data collection tools are included in Annex B) will be:

Documentary evidence and analysis will guide the first part of the analysis. An initial review of documentary evidence has already been conducted and guided this

Key Informant Interviews (KIIs) and/or Group Interviews (GIs) will be used primarily for primary and secondary duty bearers, including national, provincial and district Government partners, national and international project partners and associated CSOs/local NGOs (detalhes específicos abaixo na seção de amostragem).

Focal Group Discussions (FGDs) and case studies will be used mainly for rights holders (individually or through the civil society organizations acting on their behalf) who are the intended and unintended beneficiaries of the intervention.

FGDs that can allow unexpected positive and negative outcomes, context dynamics, unknown stories and interests, and potential new ideas and recommendations to arise from group conversations and sharing/comparison of multiple experiences. At the end of each FGD a short survey to all of its participants will be undertaken in order to consolidate additional quantitative information.

Online or face to face surveys and short interviews to collect quantifiable information on specific project result (e.g. satisfaction, limitations and gaps of judicial redress mechanisms).

The complete proposition on sampling and distribution is mentioned in the following subsection. The online platforms used will depend on the availability of the specific stakeholder, but the range includes (Zoom, Teams, WhatsApp, GoogleMeet, Skype, SkypeCalls). Others will be appropriate if necessary.

### Phase 3: Data analysis and Consolidation of the report.

Data analysis will be based on the Evaluation Criteria and include primary and secondary data. Quality control mechanisms will be built in through triangulation and regular feedback loops. A briefing meeting will be done after the end of the secondary data collection in order to ensure that any doubts are solved, highlight any limitations/changes and share/validate the main findings. For the analysis of qualitative data, each of the questions within each tool was assigned a corresponding EKQ and will be analyzed in relation to all data collected for the EKQ. Quantitative data will be limited to the levels of compliance with the target indicators. Therefore, they will be used mainly to measure performance against project indicators. Other quantitative data will include levels of satisfaction with the services offered in the product 1.1. and will be used to also evaluate the effectiveness of that intervention (and therefore used only against EKG in the effectiveness criteria). A data collection tool was developed to consolidate all the corresponding information in the same evaluation question. The table is not included in this report due to its size, but will be sent completed to the UN Women team, to allow direct data verification.

The evaluation report will be structured using the quality standards and elements outlined in the UNW Global Evaluation Reports Assessment and Analysis System (GERAAS).The related deliverable of this phase is the draft evaluation report whose structure is proposed below, and based on the UN Women Evaluation Handbook: How to manage gender-responsive evaluation:

- Title and opening pages

- Executive summary (maximum 4 pages).

- Introduction (5 pages as in this report), including

  - Background and purpose of the evaluation

  - Programme/object of evaluation description and context

  - Evaluation objectives and scope

- Evaluation methodology and limitations (summarized version of this report, 3 to 4 pages)

- Findings (maximum 15 pages)

- Conclusions (maximum 2 pages)

- Recommendations (maximum 2 pages)

- Lessons learned (maximum 2 pages)

- Annexes: as those in this report, but including additional detail on:

  - Lists of institutions interviewed or consulted and sites visited (without direct reference to individuals)

  - Analytical results and methodology related documentation, such as evaluation matrix and stakeholder matrix

After delivery, the Evaluation Team will organise and lead a debriefing session with the Evaluation Reference Group. The presentation will focus on presenting the main findings and recommendations and validating information. Based on any feedback provided during this presentation and corrections to the report, the Evaluation Team will consolidate changes within the draft Evaluation report and present a final one before 30 March 2020.  The final evaluation report and evaluation management responses will be publicly disclosed in the UNW GATE system.

## Sample and sampling design

An initial stakeholder analysis is shown in detail in the next sections. The target sampling was consolidated based on two main categories. Direct women and girls benefiting from services and economic opportunities offered in output 1 and 2 of the project which required a more ample and statistically significant sampling, are reflected in the first subsection. Other project stakeholders, including partners, women leaders and representatives of women and girls’ partner and beneficiary organisations.

The reason for this dual approach is merely creating a representative evaluation which takes into account both the voices of women benefiting from services and interventions aiming to improve the access to redress and socio-economic development services (with focus on conflict-affected areas), and have a separate approach to consider the individual experiences of women leaders that have had a higher said in project implementation or who represent women organisations that are part of the efforts of implement the WPS NAP in Mozambique and were benefited directly or indirectly in this project, as well as other relevant stakeholders.

In general, our proposition is to do primary data collection in 4 out of the 7 provinces, and 7 to 8 of the 17 districts where work was implemented, which is based on the time available for analysis and the number of local researchers assigned to the analysis (two weeks and a local consultant).

### Facts and assumptions to consider

Sampling was based on the following facts and assumptions:

- The project focuses in provinces and areas affected currently or in the past by violent conflict as a result of political tensions, grievances resulting from the exclusion of local economies in the benefits in the extractive industries and increasing religious-based violent.

- In the case of the districts of Mocimboa da Praia and Palma, women and girls were forced to seek refuge in other safer locations mainly Pemba and Nampula province.

- Mocimboa da Praia and Palma districts cannot be reached by road due the insecurity resulting from the clashes between the defence and security forces (on one side) and the insurgents’ activities (on the other).

- It is not safe traveling by road also to Gorongosa, Chibabava and Machaga, in Sofala Province, due to some armed attacks to vehicles by a Renamo dissident group. The large effect of cyclone Elouse in Buzi has also elimitated the possibility of collecting information in those areas.

- Currently, the safe sites to visit are Pemba and Montepuez (Cabo Delgado), Morrumbala (Zambezia) Moatize (Tete), Mabote, Funhalouro and Panda (all in Inhambane), Dondo and Beira (Sofala) and Chigubo and Chibuto (Gaza).

- In Q3 and Q4 2020, the MGCAS, with the support of UN Women, finalized a series of monitoring missions to most of the districts in which the safe spaces and referral centers were established in 2019 (the only 2 not directly monitored were Mocimboa da Praia and Palma due to the lack of safe access as result of the raising violent extremism in Cabo Delgado). Some of the key issues registered and areas of improvement identified include: technical difficulties in filling out the “ficha unica” (the singular incident report used by all sectors (health, police, justice, etc.) and need of more practical learning in the use of the “ficha unica”, lack of in-depth understanding of some of the concepts of the he multisectoral mechanism of assistance, lack of planning and coordination between the different sectors, lack of regular coordination meetings. Some information is thus already existing in most of those districts and we will focus on beneficiaries.

- Activities in output 2.1. on “livelihood support and facilitation of access to sustainable economic opportunities to women affected by conflict and cyclone IDAI” have started, with beneficiaries identified and activities in VSLA, Poultry farming and Apiculture starting or on-going but only from Q1 of 2021. As a result, we feel beneficiaries are not yet in a position to provide feedback on delivery, so we would focus on interviewing the implementing partner(s) to identify the ways in which the beneficiaries were selected (relevance), and how they are planning to measure results and get beneficiary feedback (efficiency, efficacy) in the following months to prepare for the final evaluation.

- As a consequence, we propose to directly visit 4 of the 7 provinces and 7 to 8 of the 17 districts benefited by the project, mainly focusing on Cabo Delgado (with research in Pemba and maybe Montepuez -depending on security), Sofala (Beira, Buzio and/or Dondo), Inhambane (Inhambane, Panda and Funhalouro), and Zambezia (Morrumbala). We will also speak remotely with district/police and/or defens-e officials in three districts of the remaining 9 to 10, and provincial representatives in all other three remaining provinces.

- The evaluation shall try to avoid re-victimization of any of the users of CAI Safe spaces and referral services and thus we will review with CAIs and organizations supporting women victims in every district, what the best way for data collection will be. Based on previous experience we feel that FGDs organized by women support groups will yield the best safeguarding results. Planning below might change as a result.

- As a result of the above assumptions, a total of 395 to 466 direct and indirect beneficiaries will be interviewed, surveys or engaged in this analysis. The minimum sample represent 8% of direct and indirect beneficiaries as per achieved numbers reported in the latest report, and 67% of the original targets. It will thus, correspond to a margin of error of 4,64%, with 95% confidence level, and population proportion of 60%. Detail provided below.

| Output | Target | Achieved | Sample | Details |
| --- | --- | --- | --- | --- |
| Output 1.1 Number of people who increase their skills and knowledge in assisting victims of violence in line with the multisectoral integrated services mechanism | Initial: 200 -government and civil society institutions from 7 provinces, police and defense officials enhanced their knowledge and exchanged experiences on the protection of human rights of women and girls | 3728 | 355 | Surveys to police and defence officials that participated in training (which are easy to identify), and KIIs with CSOs and women organisations, and indirect beneficiaries |
| Output 2.1: Number of women and girls in need who benefited from support to access to economic opportunities | Initial: 200 - new target of 8000 for socio-economic activities starting in Q1 2021 | 350 | 6 | We will interview delivery partners and participants of the Solidarity camps and partner of new activities. |
| Output 3.1: Number of women trained to engage in conflict prevention/resolution at community level | Initial: 200 intially - representatives from grass-roots and civil society organizations were trained on the WPS agenda and NAP, including organisations that participated in Solidarity Camps, also included in above output | 1500 | 31 | Mainly grass-root and CSOs and national, provincial and local level, some being part of the Solidarity Camps as well. |
| Output 3.2: Number of sectors which implement NAP related actions | 2 sectors, MGCAS and the MDN, engaged in NAP dissemination and implementation | 2 | 2 | Also to interview members of training centres |
| Output 3.3: Number of government officials directly engaged in a WPS course in an academic institution | 6 professionals from the training academies of the Ministry of National Defence, and Ministry of Interior as well as Eduardo Mondlane University that completed a post-graduate with a focus on WPS | 6 | 5 | Also interviewing representatives from training organisations |
| Totals | 608 original target | 5586 | 399 |  |

### Sampling for women beneficiaries Output 1.1.

This sample is focused on women beneficiaries from the first project outputs namely: Women and girls affected by violence that were given have access to comprehensive services to redress-including appropriate protection, health and psychosocial and legal services in areas affected by Conflict and Cyclone IDAI (output 1.1).

Output 2.1. is not included here, as the project has only started to implement activities directly (in January 2021), with activities being implemented over the first and second quarter of 2021. Thus, we don’t propose direct interviews with the beneficiaries of this output yet, as the activities are just rolling in and this might increase the risk of creating false expectations or distractions from beneficiaries. This output would thus be evaluated on the basis of its relevance and efficiency so far, and interviews with delivery partners are included in the next sampling section.

As a result, women beneficiaries to be contacted in this area will be women and girls affected by violence that were given have access to comprehensive services to redress-including appropriate protection, health and psychosocial and legal services. A separate sampling of these beneficiaries is provided here because these women may not have direct knowledge of the programme, but access services created by them. Thus, only the evaluation criteria of impact and effectiveness will be mainly applicable, by measuring their level of satisfaction and access. Beneficiaries for output 3, who were more direct beneficiaires of programme activities, such as trainings, workshops and camps are included in the next section.

Furthermore, these indirect women beneficiaries need to be consulted by following stronger safeguarding methodologies, which follow Do Not Harm principles and practices. According to recommendations from our initial engagement with the Evaluation Reference Group, our plan is to reach these women through local organizations working with survivors of SGVB. In order to set alternative plans and follow the best safeguarding practices, we will contact local government institutions and organizations to determine other mechanisms to reach beneficiaries/survivors which are appropriate to local context and without risking the revictimization of those we will contact.

Each FGD will include at most eight participants and we will focus on ensuring participation of at least (i) 2 women and 1 girl (primarily between the ages of 16-55) affected by conflicts and cyclone IDAI; (ii) 1 Women and 1 girl from households without income; (iii) 1 Household headed by people with disabilities; (iv) 1 Women and girls with disabilities; (v) 1 Households led by elderly. Where women and girls with disabilities or an elderly head of a household cannot come to the meeting location, the field work team will visit them to ensure their participation.

The number of 8 participants per FGD is intended to ensure fruitful participation in the discussion as well to mitigate possible risks associated to COVI-19. We propose that the field evaluation team should have some spare masks to distribute to those participants who may not have any. The field evaluation team will need an average of 2 days per districts/site to be visited outside the provincial capitals (one day for a return trip and a day for the actual field work). Where flexibility allows, the team will also work on Saturdays to collect data with participants available.

#### Sampling table beneficiaries

| Province | District | Description | Target | Total |
| --- | --- | --- | --- | --- |
| Cabo Delgado | Montepuez and Pembe | FGDs with women displaced from Mocimboa da Praia and Palma in Accommodation Centres/ Resettled in Pemba (mixed) FGD with users of CAI Safespaces and referral services in Montepuez | 8 people per FGDs maximum 1 to 2 FGD in Pemba with women only group, and mixed group 1 to 2 FGDs or 16 online anonymized surveys in Montepuez | 16 to 32 |
| Sofala | Beira, Buzio and Dondo | FGD with users of CAI Safespaces and referral services in Beira and Buzi or Dondo | 8 people per FGDs maximum 3 FGDs or 24 online anonymized surveys in Beira and Buzi or Dondo (1 to 2 per district) | 24 to 48 |
| Zambezia | Morrumbala | FGD with users of CAI Safespaces and referral services | 8 people per FGDs maximum 2 FGD in with women only group and mixed group | 16 |
| Inhambane | Funhalouro, Panda | FGD with users of CAI Safespaces and referral services | 8 people per FGDs maximum 4 FGDs or 32 online anonymized surveys in Beira and Buzi or Dondo (2 per district) | 32 |
| 4 | 8 | Totals |  | 88 to 128 |

### Sampling for all other stakeholders, including beneficiaries of output 2 and 3

The sample for all other stakeholders was drawn from the stakeholder analysis of those institutions involved in the project. These include:

- women trained to engage in conflict prevention/resolution at community and national levels (output. 3.1)

- government representatives at central, provincial and district levels (relevant to all outputs);

- representatives of academia, police and military forces trained under output 3;

- UN Women Teams, UN partners, donors (embassies of Norway and Iceland) and any other international stakeholders considered relevant (relevant to all outputs);

- academy and local partners counting grassroots, women’s and civil society organisations and movements, academic institutions (relevant to all outputs).

In principle, at least one person will be interviewed at least in each participating institution, although at least two participants will be interviewed in institutions such as MGCAS, MINT and MDN due to their relevance to the project.

The evaluation team will seek to conduct KIIs and FGDs to no less than 87 stakeholders as detailed on the table below, depending on the availability of their project contact people. The KIIs will be face to face in institutions that deliberately decide to do so, although the preferred method will be online KIIs. This should help shorten the time for the field work and reduce risks associated with COVID-19. If possible, we will ensure even split in genders or at least a 30% representation of men in this sample and no less than 50% of women.

The table below shows a tentative sample of participants and their location to be involved from each stakeholder.

| Stakeholder | Tools/method | Target | Total # | Location/Site |
| --- | --- | --- | --- | --- |
| Representatives of MGCAS | KII - face to face or online interviews to the technical project team will be conducted | 2 persons per government agency at least | 2 | Maputo City |
| Representatives of MINT |  |  | 2 | Maputo City |
| Representatives of MDN/Defense officials |  |  | 3 | Maputo City |
| DPGCAS | KII - - face to face in the 4 provices to be visited (Cabo Delgado, Sombala, Inhambane, and Zambezia) and online interviews with at least one of these stakeholders in every single of the locations mentioned (covering all 7 provinces) | 1 to 2 persons in each location, if possible, ensure even split in genders. | 7 to 21 | Pemba, Beira, Inhambane, Quelimane (direct) Tete, Chimioio or Xai-Xai (online) |
| Comando Provincial da Polícia/ Gabinete de Atendimento a Vítimas de Violência Doméstica |  |  |  |  |
| Comando Provincial do Exército |  |  |  |  |
| District Services of Health, Women and Social Action | KII - face to face in the 4 provinces to be visited (Cabo Delgado, Sombala, Inhambane, and Zambezia) and online interviews to at least one of these stakeholders in three of the remaining 9 locations. Focus on those that received training from the project | 1 to 2 persons in each location, if possible, ensure even split in genders | 10 to 21 | Pemba and/or Montepuez, Beira, Buzio, Dondo, Panda and Funhalouro and Morrumbala (direct), Palma, Moatize, Gorongosa, Chibabava, Machanga, Vanduzi, Mabote, Chigubo, Chibuto (online in at least three) |
| District Police Department for Victims of Violence |  |  |  |  |
| Sofala Association of Women Sharing Ideas (GMPIS) | KII - online interview/answers to the project contact persons will be conducted | At least 1 person per organisation, key contact person | 1 | Sofala |
| Young Women Leaders |  |  | 1 | Maputo |
| Rise Woman |  |  | 1 | Manica |
| Follow Your Path (LeMusica) |  |  | 1 | Chimoio |
| Nucleus of Women's Association of Tete (NFETE) |  |  | 1 | Teté |
| Associacao de Mulheres Paralegais de Moatize – Maria Cussaia |  |  | 1 | Teté |
| MULEIDE Cabo-Delgado – Julia Wachave |  |  | 1 | Cabo Delgado |
| Foundation for Community Development (FDC) |  |  | 1 | Maputo |
| Agência de Desenvolvimento Económico Local (ADEL) Sofala and Marica |  |  | 1 | Sofala, Manica |
| Nucleus of Feminist Associations of Zambezia (NAFEZA) |  |  | 1 | Zambezia |
| Other partners and collborators: Friedrich Ebert Foundation (FES) Human Rights and Development Association (DHD), Council of Religions of Mozambique (COREM). Women, Law and Development Association (Muleide), Institute for the Promotion of Peace in Mozambique (ProPaz) | FGO or KII, online interview/answers to the project contact persons will be conducted | At least 3 of these organizations with at least 1 person per organisation, key contact person | 3 | Maputo |
| National Civil Society Platform on Women, Peace and Security | FGD- with any members not interviewed directly before | At least 1 person per organisation, key contact person | 1 | Maputo |
| Other local and district-level CSOs and NGOs members that were part of the Women Solidarity Camps or other project activities | WhatsApp online FGDs or surveys with local level organisations that benefited from trainings as provided by the project | We are assuming at least 3 FGDs with at least 2 to 6 participants, one of each with male participants if available | 6 to 18 | In each district where needed |
| Men for women engaged on the promotion of the active participation of women in conflict resolution and peace building and consolidation | FGD- online FGD and case studies, 200 men engaged according to reports for output 2 | 2 online FGD or group discussion with maximum 10 participants. 2 case studies to be developed with specific participants to be chosen by training organisation | 10-15 | All 7 provinces |
| Other professionals from the training academies of MDN, MINT and UEM trained on the protection of human rights of women and girls as well as on the promotion of gender equality and peace and security policies in security organ ́s strategies/NAP | Surveys and case studies. According to project reports over 3,000 police and defence officials enhanced their knowledge and exchanged experiences. | Online survey distributed with a sample of at least 250 personnel with online surveys to be distributed by training centres. 7 case studies (one per province) to be developed with specific participants to be chosen by training organisation | 250 | All 7 provinces |
| Embassies of Norway and Iceland | KII - online interview to the technical project team will be conducted | At least 1 person per embassy, key contact person | 2 | Maputo |
| UN University Gender Equality Studies and Training Programme (UN-GEST) | KII - online interview/answers to the project contact persons will be conducted | At least 1 person per organisation, key contact person | 1 | Maputo |
| Eduardo Mondlane University (UEM) Coordination Centre for Gender Issues (CECAGE) |  |  | 2 | Maputo |
| Joaquim Chissano University (UJC) |  |  | 1 | Maputo |
| Representatives of organisations considered by the project as affected or opposed to the project | KII or FGD – Stakeholders under identification | TBD | TBD |  |
| Total Number of participants |  |  | 307-338 |  |

## Limitations, risks and Challenges

| Challenges risks and Limitations | Mitigations/Responses proposed |
| --- | --- |
| Number of cases and status of the COVID-19 lockdown does not allow for direct interviews of local partners, authorities or communities. | Data collection methodology is built around both remote and direct data collection. In the cases where direct data collection has been planned but a change in local circumstances does not allow it, local consultants will then proceed with primary data collection through online and telephonic means. FGDs might have to be significantly reduced in total number and number of participants, or completely removed, but they will be replaced with a higher number of KIIs and when possible short telephonic surveys with beneficiaries when this does not create risks for the beneficiaries or data collection. On the basis of the stakeholder analysis, the Evaluation Team will consolidate a list of telephonic and email contacts to enable the planning of the visits, and that can be used for data collection when required. |
| Insecurity and armed conflict in the Northern Areas of Mozambique restrict access and insight on delivery and results in the Cabo Delgado province | Direct data collection in Cabo Delgado has been restricted to Montepuez and Pemba and the stakeholders identified in those areas. To collect information from conflict-affected areas, and when available, we will contact locally-based organisations and government stakeholders via telephonic and online mechanisms. |
| Insecurity and natural disasters (cyclones and heavy rains) in other areas of the central region restrict access and insight on delivery and results in provinces as Sofala, Manica, Zambézia, Inhambane, and Gaza | Data collection in Sofala has been proposed, but final decision on conducting it will be based on communication with local authorities. Data collection on Buzi has been already removed from initial plan, and data collection in Beira and Dondo will be reviewed prior to travel. If travel to Sofala is not possible, we will increase data collection in Gaza (Chigubo and Chibuto) and/or Teté (Moatize) and concentrate exclusively in online data collection and documentary review for Sofala. Remote data collection in Sofala might also be narrowed to avoid taking taime from government functionaries, local ogranisations and beneficiaries whose focus is at the moment in the response to the effects of cyclone Eloyse. |
| Stakeholders to be interviewed do not have sufficient time to cover all interview questions or have a limited availability. | The number of KIIs questions in all data collections have been kept lower purposely be able to use them for remote and direct data collection, and to respond to a likely reduced amount of time available. Besides this, when setting interviews (online or face-to-face) we will agree in advance the amount of time to be taken, and when necessary reduce the number of questions by prioritizing the areas where information from such stakeholder is more required. |
| Results shown in desk review documentation are inconsistent in some or high degree with the information collected through primary data collection | Data triangulation will be a key part of the primary data collection and report writing process. All KIIs will be done by two members of the team, including an international and a local consultant to ensure greater independence in data collection and the possibility for different views to be discussed and validated. When information is inconsistent, these inconsistencies will be discussed with the involved partners to understand possible reasons behind and discard misunderstandings. |
| Time limitation does not allow for all relevant stakeholders to be consulted, creating gaps in the analysis. | An initial plan to ensure consultation with all relevant stakeholders is set above and a revision of gaps in the analysis will be done in a weekly basis to ensure that no relevant stakeholder or information is left out. Having a reduced local research team will limit the possibility to increase the sample, but the international and local consultant will do data collection in parallel when needed. Also in line with recommendations from previous studies conducted by the programme, we tried to adopt a more simplified vocabulary in the tools and the permanence of local consultants for at least a day in each of the sites where direct data collection will be done. |

## Ethical/Safeguarding considerations

### Ethical Considerations

Data gathering will happen in alignment with standard ethical principles for evaluation, with a particular emphasis on confidentiality. All interviewees will be treated with utmost respect. Further, confidentiality will be ensured and will be stressed before asking any question.

In compliance with best standards on data and information management, safeguarding and gender/conflict sensitivity, evaluation participants will be provided with information about the project/programme being evaluated and the methodology used, in an accessible, plain language format. Participants will be provided with sufficient time to consider the information and raise any queries before deciding on their involvement. A consent form is included within each of the tools presented.

The KEG will have particularly account for complexity of gender relations and to ensure participatory and inclusive processes that are culturally appropriate. These methods should be responsive to human rights and gender equality principles and facilitate the engagement of key stakeholders. The team will adhere to several basic principles for the data collection besides the above mentioned:

The questions asked are appropriate and adapted to age, level of education and culture of the participants.

The questions are formulated to reflect the sensitive nature of the topics.

Sampling will be both systematic, but also flexible: access and safety in each location will determine the sampling method used.

The team will ensure triangulation of data by collecting views from different stakeholder groups on the same issue.

### Locations and Safety of the interviews and FGDs

Throughout the research, the team will put the safety and security of participants first. Among others, the team will respect the participants´ preferred location for the interview and taken into account the current limitations on mobility and group meetings due to COVID 19, and the need to ensure outmost safety for the evaluation team and the stakeholders consulted in the ground. Districts for data collection are proposed above and have been selected in consultation with UN Women and be approved by the Evaluation Reference Group, following duty of care and public health guidances.

Furthermore, the teams will strive to accommodate interview times/locations that ensure women’s participation, and to ensure that best practices and recommendations (either set by the WHO and those additional mandated by the local and national government in Mozambique) are followed. The above is in line with UNW Pocket tool for managing evaluation during the COVID-19 pandemic: https://www.UN Women.org/en/digital-library/publications/2020/05/pocket-tool-for-managing-evaluationduring-the-covid-19-pandemic

### Data Management

Given that most of the information will be managed online, we will ensure that we are working through end-to-end encrypted information management systems, without personally identifiable data, which will be returned in full to HiH focal points at the end of the process and deleted from our databases.

FGDs and/or surveys with women and girls’ survivors of sexual based violence who have been beneficiaries of redress services, will be done in smaller groups and only with women and under the guidance of supporting local women organisations.

# Evaluation matrix

| Q# | Evaluation Criteria | Key Evaluation Questions | Sub-questions | Indicator(s) data | Relevant Stakeholder | Collection method(s) | Data source | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | RELEVANCE | To what extent is the intervention relevant to the needs and priorities as defined by beneficiaries, partners and policies? | • How were needs and priorities identified? By whom? • Are there beneficiairy feedback mechanisms included within the project, so new priorities can be identified? • Do beneficiaries feel that the project is attending to their needs? • Are priorities at district, provincial and country level coordinated, or do they differ? If so, what are the key differences? • Did the programme consultations with national counterparts in the formulation and implementation of the programme lead to integration of national priorities? | • Alignment with scoping study, beneficiary feedback mechanisms • Type of studies/analysis done to determine the needs and priorities (scoping study) • Alignment between national plan and provincial and district level priorities. • Number of women trained to engage in conflict prevention/resolution at community level | UN Women Team/Delivery partners Beneficiaries, women organisations/CSOs Government partners (national and subnational level) | • Document analysis • Monitoring records • Interviews (KIIs with delivery partners and CSOs, FGDs with beneficiary groups -face to face or WhatsApp groups) • Surveys to beneficiaries | • National government website • UN Women programme staff • National counterparts • Scoping study/Mapping • Beneficiary groups discussions and surveys | •Information is available • National counterparts are willing/able to meet • Discussions with beneficiaries are able to be held either directly or online. |
| 2 | RELEVANCE | To what extent the intervention has responded to key changes: - humanitarian challenges, such as the cyclones Idai and Kenneth and Covid-19 and conflict in specific districts? - changes in the WPS and recovery policy? | • Did the project have a risk and incident register with proper mitigations and response mechanisms? • What processes were followed to adapt to Covid-19, natural disasters and any other humanitarian challenges? What was the timeframe to implement the adaptation? • Were there any changes in national policy/strategy during project implementation? How does the programme ensure that new priorities are included and taken into consideration? • Do partners/beneficiaries feel that the adaptations were sufficient? | • Existance of risk and issue register. • Number of response plans consolidated against programme/humanitarian challenges. • Number and quality of the adaptations done to the project to respond to the changes. | UN Women Team/Delivery partners Beneficiaries, women organisations/CSOs Government partners (national and subnational level) | • Document analysis • Monitoring records • Interviews (KIIs with delivery partners and women organisations) • Survery or FGD with women beneficiaries) | • KIIs with national counterparts • Risk Register, project reports. • Beneficiary groups discussions and/or surveys |  |
| 3 | IMPACT AND OUTCOME ACHIEVEMENT | Is the project likely to achieve the project aims and results as set on the logframe, ToC and project design? | • What changed in the lives of the beneficiaries (both direct and indirect beneficiaries)? (Assess scenarios of before and after the project). • What are the social changes the intervention contributed for at community level? (attitudes, behaviour, knowledge, socio-cultural practices & norms related to GE) • What institutional changes did the intervention achieve in the partners organizations? • How did the project change the availability of data on WPS and gender equality to guide policy and programming? | • Current achievement against of project's outcome and output indicators (see Section Indicators for Measuring Reports) • Evidence of changes amongst key partners, beneficiaries and their communites • Evidence of unintended effects of UN Women (positive or negative), including on excluded/more vulnerable groups and men/boys | UN Women Team/Delivery partners Beneficiaries, women organisations/CSOs Government partners (national and subnational level) | • Document analysis • Monitoring records • Interviews (KIIs with delivery partners and women organisations) • Survery or FGD with women beneficiaries • Case studies | • Project reports and logframe • KIIs, FGDs and case studyes with all relevant stakeholders | • Information is available • National counterparts are willing/able to meet • Discussions with beneficiaries are able to be held either directly or online |
| 4 | EFFECTIVENESS | To what extent do the activities being carried contribute to the intended outputs and outcomes and how did UN Women contribute towards them? | • Is there evidence that the ToC is being implemented and valid? • What is the level of engagement between the Partners and key Stakeholders at all levels and the ability to leverage the partnership process to inform the advocacy strategy? • What is the value addition of UN Women in terms of the resources oversight and technical support? How can they be strehgten to improve impact? • Did UN Women effectively coordinate with relevant partners to achieve results? • How can this be improved within the partners and UMWomen? | • Evidence of contribution to results as outlined in the programme/project plan and articulated in the theory of change • Use of Most Significant Change techniques for contribution analysis • Evidence of contribution by UN Women to delivery, monitoring and coordination. • Evidence of contribution by other partners to the project deliverables and identification of duplications and gaps- | UN Women Team/Delivery partners Beneficiaries, women organisations/CSOs Government partners (national and subnational level) | • Document analysis • Monitoring records • Interviews (KIIs with delivery partners and women organisations, FGDs with women beneficiaries) • Case studies | • KIIs with national counterparts • Project reports • Beneficiary groups discussions and/or surveys | • Information is available • National counterparts are willing/able to meet • Discussions with beneficiaries are able to be held either directly or online • Partners are willing to be honest about their weaknesses. |
| 5 | EFFECTIVENESS | What are the enabling, limiting factors and risks that are contributing to the achievement of results and what actions need to be taken to overcome any barriers that may limit the progress? | Same as key question: • Identify key enables and challenges • Identify whether this have been considered during project design and delivery, and how they are responded to (particularly in Risk register). | • Qualitative analysis of enablers and challenges, possible SWOT analysis or light touch political economy analysis | UN Women Team/Delivery partners Associated CSOs and women organisations | • Document analysis • Monitoring records, reports • Interviews (KIIs with delivery partners and UM Women project team) | • KIIs with national counterparts • Project reports • Beneficiary groups discussions |  |
| 6 | EFFICIENCY | To what extent are project strategies cost-effective in making an impact on the ground, district and provincial levels? (analysing the budget and project expenditure over the two- and half-year period of the project)? | • What are the key cost drivers of the project? • Are those key cost drivers connected with the main project outcomes? • What has been done to ensure VfM? | • Identificartion of key cost drivers analysis and cost associated • Evidence of implementers use of cost-efficiency mechanisms during implementation | UN Women Team/Delivery partners | • Budget analysis • Monitoring reports • Interviews (KIIs with delivery partners and UN Women project team) | • KIIs with relevant stakeholders • Project reports -financial and narrative | • Financial reports have sufficient detail to determine key cost drivers • Partners are able to identify key areas of economy and efficiency |
| 7 | EFFICIENCY - MONITORING, EVALUATION AND KNOWLEDGE MANAGEMENT | How efficient have been the project management and monitoriing structures been and how can they be improved? | • Is there a need to improve the Monitoring & Evaluation Framework including logical frame indicators, tools and processes used to monitor and report activities, outputs? • Is the knowledge produced by the project being used? (e.g. studies and KP produced during the implementation) • Is the project documentation (donor reporting, activity reporting, KM and communication products) adequate, disseminated and sufficient? | • Qualitative analysis of project reports and monitoring records and analysis against its use | UN Women Team (including regional if applicable)/Delivery partners | • Monitoring reports • Interviews (KIIs with delivery partners and UN Women project team -including regional/international teams that receive and use reports for cross-learning) | • KIIs with relevant stakeholders • Narrative project reports and evidence of learning adaptation and sharing | • Information is available • Stakeholders are willing to be honest about their weaknesses. |
| 8 | EFFICIENCY- MONITORING, EVALUATION AND KNOWLEDGE MANAGEMENT | Which are potential good practices, challenges and lessons from the interventions and recommend forms to improve project strategies in the remaining implementation period? | • What have been the main lessons in terms of design, delivery and monitoring? • What best practices have been consolidated? • What has been done well and what can be improved? | • Qualitative analysis of main challenges and learning (What would you do differently?) • Evidence of good practices and learnings being shared with others. | UN Women Team (including regional if applicable)/Delivery partners | • Monitoring reports • Interviews (KIIs with delivery partners and UN Women project team -including regional/international teams that receive and use reports for cross-learning) | • KIIs with relevant stakeholders • Narrative project reports and evidence of learning adaptation and sharing |  |
| 9 | SUSTAINABILITY | What is the likelihood of long-term benefits and impact from the project? Or To what extent is it expected that the benefits from the project will continue after project completion? Can we detect project ownership from beneficiaries and partners? OWNERSHIP | The project has a sustainability strategy? • What is the project sustainability plan (does it exist)? And how is being implementing it? • How will the benefits of the intervention be secured for rights holders in the long term? • Did the programme enhance local ownership and capacity to influence policy? | • Qualitative analysis of sustainability plans and mechanisms • Evidence of a sustainability plan being developed and implemented • Qualitative evidence of ownership by beneficiaries | UN Women Team/Delivery partners Beneficiaries, women organisations/CSOs Government partners (national and subnational level) | • Document analysis • Monitoring records • Interviews (KIIs with delivery partners and CSOs). • FGDs with beneficiary groups -face to face or WhatsApp groups) | • Project reports and logframe • KIIs, FGDs with relevant stakeholders | • Information is available • National counterparts are willing/able to meet • Discussions with beneficiaries are able to be held either directly or online. |
| 10 | SUSTAINABILITY | To what extent did the organisation build institutional capacity of local partners and communities and their willigness to implement WPS agenda? ACCOUNTABILITY | • To what extent was capacity developed in order to ensure sustainability of efforts and benefits? • To what extent have duty bearers (goverrnment partners, civil society organizations and women´s organizations/associations/movement) committed to promote the WPS agenda and promote peace and security at central provincial and distric levels (accountability)? • What accountability and oversights systems were established or strengthened? | • Qualitative analysis and evidence of capacity being built and used • Qualitative evidence of accountability and oversight systems | UN Women Team/Delivery partners Government partners (national and subnational level) | • Document analysis • Monitoring records • Interviews (KIIs with delivery partners and associated CSOs and women organisations). | • Project reports and logframe • KIIs, FGDs with relevant stakeholders |  |
| 11 | SUSTAINABILITY | What are the contextual factors for sustaining and replicating the project interventions and its impact at national level? | • Light touch PEA/Stakeholder Analysis • What have been the key factors of success? What are the key enablers? • What have been the key factors of failure? What are the key spoilers? | • Qualitative analysis of factors of success and failure that can determine the sustainability of the project. | UN Women Team/Delivery partners Beneficiaries, women organisations/CSOs Government partners (national/ subnational level) | • Document analysis • Monitoring records • Interviews (KIIs with delivery partners and CSOs). • FGDs with beneficiary groups -face to face or WhatsApp groups) | • Project reports and logframe • KIIs, FGDs with relevant stakeholders |  |
| 12 | HUMAN RIGHTS AND GENDER EQUALITY | To what extent has gender and human rights considerations been integrated into the programme design and implementation? Has that allowed progress int he area of work? | (Questions from UNEG Guidance Integrating Human Rights and Gender Equality in Evaluations pp77-92) • To what extent did the processes and activities implemented during the intervention focus on promoting changes in social relations and power structures? • Did the project allowed women to consolidate a stronger role in national and regional peace-building and peace and reconciliation processes? • What gender equality results have been achieved, were power imbalances changed? • How power groups opposed to change be managed? • Has the intervention to any extend led to unforeseen adverse effects on the four cross-cutting issues (gender, human rights, corruption, environment & climate change)? | • Qualitative evidence of changes in political economy and power dynamics, particulalr yin favour of marginalized and/or discriminated groups. • Qualitative analysis of potential spoilers of these expected changes, and evidence of how these risks have been avoided or mitigated. | UN Women Team/Delivery partners Beneficiaries, women organisations/CSOs Government partners (national and subnational level) | • Document analysis • Monitoring records • Interviews (KIIs with delivery partners and CSOs). • FGDs and case studies with beneficiary groups -face to face or WhatsApp groups) | • Project reports and logframe • KIIs, FGDs with relevant stakeholders • Case studies for specific cases where these changes have been observed | • Information is available • National counterparts are willing/able to meet • Discussions with beneficiaries are able to be held either directly or online. |

# Stakeholder Analysis

| Categories | Who? (Name of the Stakeholder) | What (their role in the intervention) | Why are they part of the evaluation | How are they being involved | When will they be involved | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| Duty bearers who have decision-making authority over the intervention such as governing bodies | Representatives of Ministry of Gender, Children and Social Action (MGCAS) | Coordinate, monitor implementation of the NAP and fulfil United Nations reporting requirements strengthened - Lead the coordination and monitoring of NAP initiatives being implemented by different actors in the country. Through technical support and coordination MGCAS contributed to the active engagement of the Police, Justice and health sectors at the provincial and district level towards the establishment of the integrated services for women and girls who experience physical and sexual violence. | Key for the achievement of NAP ownership and project implementation at the district and provincial level. They can provide some insights/reflections on how the project is being implemented and suggestions for improvement. | ERG?/ Data collection (KIIs) | Data Collection, dissemination and possibly as part of RF through-out all phases -TBC | High |
|  | Representatives of Ministry of Interior (MINT) | Coordinate, monitor implementation of the NAP and fulfil United Nations reporting requirements strengthened -focused on police and judiciary. Partners in the provision of tools and material related to gender mainstreaming within the police forces, training module for police training academies at a national level focused on the WPS Agenda, training for police forces in conflict affected areas, such as Cabo Delgado, Sofala, and Manica provinces, on how to protect the human rights of vulnerable groups and adequately serve the differentiated needs of women and girls. | They are key to the implementation/success of the project as part of the implementation efforts of the NAP on WPS. They can provide some insights/reflections on how the project is being implemented and suggestions for improvement. | ERG?/ Data collection (KIIs) | Data Collection, dissemination and possibly as part of RF through-out all phases -TBC | High |
|  | Representatives of Ministry of National Defense (MND) | Coordinate, monitor implementation of the NAP and fulfil United Nations reporting requirements strengthened in regards to the defence sector bodies. | They are key to the implementation/success of the project as they are expected to ensure the of the armed forces observe an acceptable behaviour in conflict situations towards women and girls. They can provide some insights/reflections on how the project is being implemented and suggestions for improvement. | ERG?/ Data collection (KIIs) | Data Collection, dissemination and possibly as part of RF through-out all phases -TBC | High |
| Duty bearers who have direct responsibility for the intervention, such as programme managers and associated partners that do not have decision-making authority over the intervention | Representative from Department of Social Action at district level | Beneficiaries of training and equipment. Direct duty bearers in assisting the needs of SGBV survivors and potential victims. Entity responsible to coordinate the provision of integrated assistance and referal services for women and girls at risk or survivors of violencre | They can provide some insights/reflections on how the project is being implemented and suggestions for improvement, specifically review of the Integrated Multisectoral Mechanism of Assistance to Women Victims of Violence. | ERG?/Data collection (KIIs and/or FGDs) | Data Collection, dissemination and possibly as part of RF through-out -TBC | High |
|  | Police and Defence Officials trained on gender equality and WPS agenda | Beneficiaries of trainings on the multisectoral mechanism of assistance to women and girls at risk of and survivors of violence. To specifically include some of the beneficiaries of post-graduate facilitated by UNU-GESTs Gender Equality Studies and Training Programme as part of a case study, and police forces from conflict affected areas. | Ensure implementation of the NAP in terms of protection and assistance to women survivors and women at risk. They can provide some insights/reflections on how the project is being implemented and suggestions for improvement, specifically on how to conduct training and gaps in the mechanisms to implement what was learned. | Data collection (KIIs or FGDs), dissemination | Data collection (KIIs/FGDs and case studies), dissemination | Medium-High |
|  | Representatives from grassroot women ́s networks: Sofala Association of Women Sharing Ideas (GMPIS), Rise Woman; Follow Your Path (LeMusica); Nucleus of Women’s Associations of Tete (Nafete); and Nucleus of Feminist Associations of Zambezia (NAFEZA) | Partner in charge of reaching out and engage grassroots women in the project targeted provinces and across the country in the implementation of the WPS agenda at the community level through organization of solidarity camps. Carry out a prevention campaign against COVID-19 and the promotion of WPS at community level-specially risks increased by COVID-19. | They are key to the implementation/success of the project as part of dissemination of message across network members and support in identifying women leaders to be trained at local levels. They can provide some insights/reflections on how the project is being implemented and suggestions for improvement. | ERG?/Data collection (KIIs and/orFGDs) | Data Collection, dissemination and possibly as part of RF through-out all phases -TBC | High |
|  | Representatives from Human Rights and Development Association (DHD), Council of Religions of Mozambique (COREM) | DHD and COREM received technical assistance in the conceptualization of The National Platform which seeks to create a united women ́s voice on peace and security issues in Mozambique and demand women voices in the ongoing peace talks and peace agreements, as well as, the post-conflict development strategies and programmes. | They can provide some insights/reflections on how the project is being implemented and suggestions for improvement particularly in terms of implementation for output 3. | ERG?/Data collection (KIIs) | Data Collection, dissemination and possibly as part of RF through-out -TBC | Medium-High |
|  | Government of Norway | Provide funding, support advocacy and partnership building. | Hold strategic decision-making and can support advocacy. If funding is retired project is no longer possible. | ERG?/Data collection (KIIs) | Data collection, dissemination and possibly as part of RF through-out -TBC | High |
|  | Government of Iceland | Provide funding, support advocacy, resource mobilization and partnership building | Hold strategic decision-making and can support advocacy. If funding is retired project is no longer possible. | ERG?/Data collection (KIIs) | Data collection, dissemination and possibly as part of RF through-out -TBC | High |
|  | UN Women | Programme formulation, Management/Monitoring and Learning, technical support to MGCAS, advocacy, partnership building and resources mobilization | Hold strategic decision-making through-out the whole project cycle. | Management Group?/Data collection (KIIs) | All phases. | High |
|  | Representatives from district Governments | Beneficiaries, monitoring and Quality assurance of services provided in their districts. | They provide leadership and hold very strong convening power amongst the different district services involved in the project. Provide access and ability to produce change. | Data collection (KIIs or FGDs), dissemination | Data collection, dissemination | Medium-High |
| Secondary duty bearers, such as the private sector or parents | Representatives from United Nations University Gender Equality Studies and Training Programme (UNU-GEST) and Universidade Eduardo Mondlane (UEM) | Develop and implemented a training of trainers course for the defence and security sector. | They can provide some insights/reflections on how the project is being implemented and suggestions for improvement particularly in terms of implementation for output 3. | Data collection (KIIs), dissemination | Data collection, dissemination | Medium-High |
|  | Representatives from Joaquim Chissano University (UJC) | Implemented debates and reflections on contemporary issues relating to the WPS Agenda, including on- growing violent extremism and terrorism in Mozambique. Supported capacity building of personnel from Government, CSOs and women-led organizations, academic institutions, private sector and media through short-term in-depth trainings on WPS | They can provide some insights/reflections on how the project is being implemented and suggestions for improvement particularly in terms of implementation for output 1 and 2. | Data collection (KIIs), dissemination | Data collection, dissemination | Medium-High |
|  | Other private-sector receptors of training from any of the other outputs | To review: Are there other receptors of training, are they key for the MTR or Final evaluation? | TBC | TBC | TBC | TBC |
|  | Representatives from national and international associated partners: Friedrich Ebert Foundation (FES), the Foundation for Community Development (FDC), Women, Law and Development Association (Muleide and Institute for the Promotion of Peace in Mozambique (ProPaz) | Associated partners in terms of consolidating and coordinating efforts in the promotion of WPS in Mozambique under the overarching umbrella of the NAP. | They can provide some insights/reflections on how the project is being implemented and suggestions for improvement particularly in terms of implementation for output 3. | Data collection (FGDs), dissemination | Data collection, dissemination | Medium |
|  | Representatives from "Men for Women/Harmful Masculinities" initiatives | Men trained under output 3 to be engaged on the promotion of the active participation of women in conflict resolution and peace building and consolidation at the community level through dialogues community | They can provide some insights/reflections on how the project is being implemented and suggestions for improvement particularly in terms of implementation for output 3. | Data collection (FGDs and/or surveys), dissemination | Data collection, dissemination | Medium |
| Rights holders (individually or through the civil society organizations acting on their behalf) who are the intended and unintended beneficiaries of the intervention | Representatives from women and girl survivors of conflict and violence and at risk receiving psychosocial or legal support from CAIs | Direct beneficiaries of the project, particularly output 1. We suggest either to collect voluntary surveys at the entrance of selected CAIs or to send anonymous/voluntary surveys using contact list from CAIs, or announce voluntary FGDs in the CAIs. | They are the beneficiaries and subjects of the entire project. They can provide some insights/reflections on how the project is being implemented and suggestions for improvement particularly in regards to gaps in service provision from the CAIs. | Data collection (FGDs and/or surveys), dissemination | Data collection, dissemination | High |
|  | Representatives from Women that participated in South-South, North-South solidarity WPS workshops | Direct beneficiaries of the project, particularly output 3. Produced position paper that will serve as advocacy tool for women ́s organizations to monitor and evaluate the implementation of national policies and plans in order to ensure that women and girls benefit, and can coordinate best practices with other women leaders in other regions/countries. | They can provide some insights/reflections on how the project is being implemented and suggestions for improvement particularly in regards to international best practices or gaps in the NAP or implementation of the NAP. | Data collection (FGDs), dissemination | Data collection, dissemination | High |
|  | Women representatives of community-based women’s organizations that received trainings on conflict prevention, mediation and resolution provided by the project | Direct beneficiaries and aimed to consolidate National Civil Society Platform on Women, Peace and Security, a platform which seeks to create a united women ́s voice on peace and security issues in Mozambique and use this united voice to demand that the perspective of women and girls is adequately reflected in the ongoing peace talks and peace agreements, as well as, the post-conflict development strategies and programmes | They can provide some insights/reflections on how the project is being implemented and suggestions for improvement particularly in regards to international best practices or gaps in the NAP or implementation of the NAP. | Data collection (FGDs), dissemination | Data collection, dissemination | High |
|  | Women representatives from grass-roots and civil society organizations were trained on the WPS agenda and NAP, or part of consultations to establish a socioeconomic strategy or that will potentially help to implement the strategy | Representatives from potential direct beneficiaries of outputs 2 and 3. Participated in scoping and discussions. | They can provide some insights/reflections on how the project is being implemented and suggestions for improvement particularly in regards to international best practices or gaps in the NAP or implementation of the NAP. | Data collection (FGDs), dissemination | Data collection, dissemination | High |
|  | Women that received or are receiving support in terms of socioeconomic empowerment | Likely to be only in starting point, but important to receive feedback from any early beneficiaries. TBC | They can provide some insights/reflections on how the project is being implemented and suggestions for improvement particularly in regards to output 3. | Data collection (survey), dissemination | Data collection, dissemination | Medium-High |
| Rights holders (individually or through the CSOs on their behalf) who should be represented in the intervention but are not, or who are negatively affected by the intervention -potential spoilers | Representatives from women organisations or other women leaders (women parliamentarians) that are informed of the project but where not part of any of the activities | None, but might have been observers | They may become barriers if they perceive that their are being excluded intentionaly. We need to know their perceptions of the project in order to respond to potential harmful perceptions. They are also normally good observers of the potential gaps of the project. | KIIs and/or FGDs depending on the number | Data collection, dissemination | Medium |
|  | Local conservative leaders including religious leaders and traditional healers | They may hinder the changes the project/ intervention attemps to promote if they percieve any threat in traditional power balance | We need to know their perceptions of the project in order to identify adequate responses to potential harmful perceptions | Interviews/FGDs | Data collection, dissemination | Medium |

# Workplan

The work plan below is indicative and will be adapted depending on circumstances during the implementation of the evaluation. Changes in the workplan will all be approved by the UN Women Evaluation Group.

| ACTIVITY | January 2021 |  |  |  | February 2021 |  |  |  | March 2021 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Week of project | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 |
| Inception Phase |  |  |  |  |  |  |  |  |  |  |  |  |
| Kick-off, inception calls, clarification meetings, information sharing (data sharing started 11 Jan) | X |  |  |  |  |  |  |  |  |  |  |  |
| Stakeholder Mapping and Literature Review |  | X | X |  |  |  |  |  |  |  |  |  |
| Development of data collection tools and evaluation questions/criteria |  | X | X |  |  |  |  |  |  |  |  |  |
| Drafting inception report, delivery and briefing session (1) |  | X | X |  |  |  |  |  |  |  |  |  |
| Reception of comments from Evaluation’s Reference Group |  |  |  | X (2) |  |  |  |  |  |  |  |  |
| Data collection phase |  |  |  |  |  |  |  |  |  |  |  |  |
| Remote and in field primary data collection (3) |  |  |  |  | X | X | X |  |  |  |  |  |
| Review of additional secondary data from field collection |  |  |  |  | X | X | X |  |  |  |  |  |
| De-briefing on main findings from primary data collection to intended beneficiaries (4) |  |  |  |  |  |  |  | X |  |  |  |  |
| Data Analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Consolidation and analysis of information |  |  |  |  |  |  |  | X | X |  |  |  |
| Draft Research Report, presentation and briefing sessions (5) |  |  |  |  |  |  |  |  | X | X |  |  |
| Review/consolidation of feedback, including comments from intended users (6) |  |  |  |  |  |  |  |  |  |  | X | X |
| Final Research Report (7) |  |  |  |  |  |  |  |  |  |  |  | X |
| Dissemination and Presentation of the report |  |  |  |  |  |  |  |  |  |  |  |  |
| Dissemination sessions recommendations | April 2021 |  |  |  |  |  |  |  |  |  |  |  |

- Proposed revised delivery on 21 January

- Proposed deadline to receive comments to Evaluation Team -27 January

- Proposed start of data collection 1st February

- Proposed presentation of key findings from the field 26 February

- Proposed delivery of draft report and presentation – 18 March/20 March (presentation)

- Proposed deadline for providing comments to Evaluation Team -27 March

- Proposed delivery of final report -31 March

# Responsibilities, logistics and support

The Evaluation Team Leader (TL) will be ultimate responsible for the preparation of all deliverables outlined in the TOR. Thanks to her experience in remote management, the TL will coordinate actions of other evaluators to ensure the best performance of activities performed in Mozambique.

Under her technical supervision, the Local Researcher (LR) will be responsible for data collection in the field (4 provinces, 7/8 districts) and other interviews as distributed below. Each team members will be responsible to input information into the data collection table for each of the KEQ.  The Team Leader is the lead in the design of the data-collection and analysis tools and will be in charge of quality control.

The evaluation team will hold frequent meetings and be in daily contact through various means of communication to ensure that the required flow of information is shared within the team.

Field work will require the following logistics and communication support from the UN Women Team:

- Contacts (telephone and email) for all stakeholders listed on the sampling tables;

- Communication to be sent to all stakeholders listed on the table above informing about the evaluation (purpose, dates, participants to involved, etc.);

- Presentation letters of the fieldwork evaluation team;

- Arrangements (directly or through partners) for places where people can meet for the FGDs and KIIs;

- Air and road transport to and from the project sites to be visited;

- Hotel and subsistence allowance for the evaluation team while in the field, this will include purchase of masks to provide to beneficiaries and other stakeholders for KIIs/FGDs in case they don’t have them.

## Task distribution until data collection

| Task | TL-LG | LR-RM |
| --- | --- | --- |
| Inception Report |  |  |
| Initial consolidation of Evaluation Matrix, Methodological Plan, structure and Anexes of Inception report | X |  |
| Initial consolidation of Stakeholder Analysis and data collection tools |  | X |
| Translation of the inception report to Portuguese | X |  |
| Review of the translation |  | X |
| Quality Review of all sections | X |  |
| Documentary Data Analysis | X | X |
| Field Data Collection and input in Data Analysis Database |  | X |
| Online Data Collection |  |  |
| National Government Stakeholders | X |  |
| Provincial and District Government Stakeholders in 3 other districts and 3 remaining provinces | X |  |
| CSOs, Women organisations based in areas different to the areas where fieldwork is based | X |  |
| Survey and FGDs to men, police/defence service men that benefited from training (surveys will require the support from training agencies and Ministries) | X | X |
| Data Analysis and Draft of Final Report (specific tasks to be disaggregated later) | X | X |

# Annexes

### Documents Reviewed

UN Women Evaluation Handbook.

Estudo sobre as Oportunidades de Recuperacao Socio-Economica das Mulheres (Content Approved, Layout being finalized)

Brochura Boas praticas Boas Práticas em Organizações de Mulheres para a Promoção da Agenda Mulheres, Paz e Segurança, e Recuperação Socioeconómica em Moçambique, Abril 2020

Final Version Scooping Study Report: “Promotion of the Women, Peace and Security Agenda and Socioeconomic Recovery in Mozambique (WPS Mozambique)”, Fevereiro 2019

NAP on Women, Peace and Security for Mozambique/Plano Nacional de Acção sobre Mulher, Paz e Segurança (2018-2022)

Promotion of the Women, Peace and Security Agenda and Socioeconomic Recovery in Mozambique (WPS Mozambique) Project Document, Avril 2017.

Promotion of the Women, Peace and Security Agenda and Socioeconomic Recovery in Mozambique (WPS Mozambique) First Donor Report, June 2018

Promotion of the Women, Peace and Security Agenda and Socioeconomic Recovery in Mozambique (WPS Mozambique) Second Donor Report, June 2019 e Anexos:

- Interim Donor Report 30 June  2019 PID 105572  Donor  -00130

- Interim Donor Report 30 June 2019  Project 108139 Norway -187

- Iceland and Norway Cover Letter Second Donor Report and Request for 1 year Project Extension

- Annex B Situational Analysis on WPS in the Context of Post-Conflict Recovery in Mozambique .pdf

- Annex D Grassroots’ Women´s Organizations Inputs to the implementation of the National Action Plan about Women, Peace and Security

- Annex E Declaration of the International Solidarity Camp of Women´s and Feminists Movements on Peace, Security and Women´s Economic Empowerment

- Annex F WPS Conflict Prevention, Mediation and Resolution Training Brief

- Annex G National Action Plan on Women, Peace and Security Provincial Launch and Dissemination Brief

Promotion of the Women, Peace and Security Agenda and Socioeconomic Recovery in Mozambique (WPS Mozambique) Third Donor Report, June 2020 e Anexos:

- Cover Letter_ICE_3rd Progress ReportRepsign.pdf

- Cover Letter_NOR_3rd Progress ReportRepsign.pdf

- Interim  Donor Report 30 June  2020 PID 105572  Donor  -00130

- Interim  Donor Report 30 June 2020  Project 108139 Norway -187

- A Study on the Opportunities for Women´s Socioeconomic Recovery and Sustainable Livelihoods for Women Affected by Conflicts

- Documentation on Good Practices in Women’s Organizations for the Promotion of the Women, Peace and Security Agenda and Socioeconomic Recovery in Mozambique

- Regional Policewomen Training Conference Brief.

### Draft Data Collection Instruments

#### Tool 1. KII – Government stakeholders -national, provincial and district level

The Evaluation Team and UN Women would like to thank you and appreciate the time and information you are sacrificing to participate in this important and valuable study under the Promoting the Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique (WPS Mozambique) project. The mid-term evaluation is aimed at improving implementation, use of resources, accountability as well as aims to identify the lessons learnt and good practices in order for the project to grow and adapt accordingly in order to achieve the intended results. This research is being developed by myself ________________ _______________ , as a local researcher and expert, and lead by Lina Gonzalez-Pineros. You can contact us in our emails _______________________ and linagonzalezp@gmail.com, in case of any doubt.

Please be aware that you can refuse to answer any of the below questions and our stop the interview at any point. If you feel uncomfortable around any of the questions, you want me to reframe it/explain it in any other way, please let me know and I will do. By allowing us to continue you agree with us using the information for the purposes outlined below only. Your personal data won’t be shared with any other person

Interview Date: _____________   Location (District):_______________ 	Province: _________________

Respondent Identification (DateInstitutionNumber): ______________________________________

Gender:  F   M  Other  Prefer not to say	Age: 	 Below 30  30-65  65+

| EC/KEQ | SPECIFIC INTERVIEW QUESTION |
| --- | --- |
| GN.0 | What was your role in the project? |
| RL.1 | Do you feel this intervention relevant to the needs and priorities as defined by the institution you represent or current policies on WPS? |
| RL.2 | Do you feel the intervention has effectively responded to key changes in the context (e.g. humanitarian challenges - cyclones Idai and Kenneth and Covid-19 and conflict in specific districts) or changes in the WPS and recovery policy? |
| RL.2 | Do you think WPS priorities at different levels of the government (national, provincial, district) are similar and/or coordinated? If so, how they are being coordinated? |
| IM.3 and HRGE.12 | What have been the main results of the project within the institution? (Note for interviewer: Search for examples in terms of capacity, attitudes, behavior, knowledge, availability of information on WPS, power imbalances within the institution) |
| IM.3 and HRGE.12 | What have been the main results of the project for you personally? |
| SS.9/11 | What you consider as elements that contribute to the sustainability of the project results? What is needed to ensure that the results of the project are maintained/sustained? What was done so far? What else do you feel that needs to be done in the remaining period of project implementation? |
| SS.9/10 | Do you feel commitment from Government institutions to the WPS/NAP agenda has been strengthen as a result of the project? If so how? |
| EF.4 | Do you feel the project has effectively been able to influence the WPS agenda and delivery of the NAP? If so, how? |
| EF.4 | What is the level of engagement/coordination between you and the UN Women team? Has it been effective? How the relationship can be improved? |
| EF.4 | What has been the value addition of UN Women in terms of the resources oversight and technical support within the project? |
| EF.5 | What have been the key factors of success and failure for the project? What do you think are or have been the main obstacles? Or What are the enabling and limiting factors that are contributing to the achievement of results and what actions need to be taken to overcome any barriers that may limit the progress? |
| EE.8 | In terms of engagement/coordination with UN Women, what do you think has work well and what can be improved and how? |
| HRGE.12 | Has the intervention to any extend led to unforeseen adverse effects on the four cross-cutting issues (gender, human rights, corruption, environment & climate change)? |
| All -classify accordingly | What could have been done better, more of or different? Do you have any additional information or recommendation that could be helpful for the future implementation of the project? |

#### Tool 2. KII/FGDS – CSOs, women national organizations, national/international direct or indirect partners, and other secondary partners (Universities, private sector)

The Evaluation Team and UN Women would like to thank you and appreciate the time and information you are sacrificing to participate in this important and valuable study under the Promoting the Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique (WPS Mozambique) project. The mid-term evaluation is aimed at improving implementation, use of resources, accountability as well as aims to identify the lessons learnt and good practices in order for the project to grow and adapt accordingly in order to achieve the intended results. This research is being developed by myself ________________ _______________ , as a local researcher and expert, and lead by Lina Gonzalez-Pineros. You can contact us in our emails _______________________ and linagonzalezp@gmail.com, in case of any doubt.

Please be aware that you can refuse to answer any of the below questions and our stop the interview at any point. If you feel uncomfortable around any of the questions, you want me to reframe it/explain it in any other way, please let me know and I will do. By allowing us to continue you agree with us using the information for the purposes outlined below only. Your personal data won’t be shared with any other person

Interview Date: _____________   Location (District):_______________ 	Province: _________________

Respondent Identification (DateInstitutionNumber): ______________________________________

For FGDs or Group interviews a line for each participant:

Gender:  F   M  Other  Prefer not to say	Age: 	 Below 30  30-65  65+

| EC/KEQ | SPECIFIC INTERVIEW QUESTION |
| --- | --- |
| GN.0 | What was your role in the project implementation? |
| RL.1 | Do you feel this intervention relevant to the needs and priorities defined in the NAP for WPS? Do you feel there are areas that this project is not attending to which need to be attended to? |
| RL.2 | Do you feel the intervention has effectively responded to key changes in the context (e.g. humanitarian challenges - cyclones Idai and Kenneth and Covid-19 and conflict in specific districts) or changes in the WPS and recovery policy? |
| RL.2 | Do you think WPS priorities at different levels of the government (national, provincial, district) are similar and/or coordinated? If so, how they are being coordinated? |
| IM.3 and HRGE.12 | What do you think have been the main results of the project for your organization or the women/groups of women you represent? (Note for interviewer: Search for examples in terms of capacity, attitudes, behavior, knowledge, availability of information on WPS, power imbalances within the institution, participation of women in peace and reconciliation) |
| SS.9/11 | What you consider as elements that contribute to the sustainability of the project results? What is needed to ensure that the results of the project are maintained/sustained? What was done so far? What else do you feel that needs to be done in the remaining period of project implementation? |
| IM.3 and HRGE.12 | What have been the main results of the project for you personally? |
|  | In what areas do you still feel more effort is needed and why? |
| EF.4 | Do you feel the project has effectively been able to influence the WPS policy? If so, how? |
| EF.4 | What is the level of engagement/coordination between you/your organisation and the UN Women project team? Has it been effective? How the relationship can be improved? |
| EF.4 | What has been the value addition of UN Women in terms of the resources oversight and technical support? |
| EF.5 | What have been the key factors of success and failure for the project? What do you think are or have been the main obstacles? How can these obstacles be solves/can the project do anything about them? |
| EE.8 | In terms of engagement/coordination with UN Women, what do you think has work well and what can be improved and how? Do you feel the way they monitor progress has been adequate? |
| SS.9/10 | Only if not covered before/in IM3: Do you feel commitment from Government institutions to the WPS/NAP agenda has been strengthen as a result of the project? If so how? |
| SS.9/10 | Only if not covered before/in IM3: Do you feel the project has done sufficiently to build capacity of local partners and communities to be able to meet WPS objectives? (Note for interviewer: Please specifically focus on issues like ability to participate in decision-making/peace and reconciliation processes) |
| CC.12 | Only if not covered before/in IM3: Did the project allowed women to consolidate a stronger role in national and regional peace-building and peace and reconciliation processes? If yes, how? If no, why? What more is needed in this area? |
| HRGE.12 | Has the intervention to any extend led to unforeseen adverse effects on the four cross-cutting issues (gender, human rights, corruption, environment & climate change)? |
| All -classify accordingly | What could have been done better, more of or different? Do you have any additional information or recommendation that could be helpful for the future implementation of the project? |

#### Tool 3. KII with UN Women Teams -programme and policy

The Evaluation Team would like to thank you and appreciate the time and information you are sacrificing to participate in this important and valuable study under the Promoting the Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique (WPS Mozambique) project. The mid-term evaluation is aimed at improving implementation, use of resources, accountability as well as aims to identify the lessons learnt and good practices in order for the project to grow and adapt accordingly in order to achieve the intended results. This research is being developed by myself ________________ _______________ , as a local researcher and expert, and lead by Lina Gonzalez-Pineros. You can contact us in our emails _______________________ and linagonzalezp@gmail.com, in case of any doubt.

Please be aware that you can refuse to answer any of the below questions and our stop the interview at any point. If you feel uncomfortable around any of the questions, you want me to reframe it/explain it in any other way, please let me know and I will do. By allowing us to continue you agree with us using the information for the purposes outlined below only. Your personal data won’t be shared with any other person

Interview Date: _____________   Location (District): ______________ 	Province: _________________

Respondent Identification (DateInstitutionNumber): ______________________________________

For FGDs or Group interviews a line for each participant:

Gender:  F   M  Other  Prefer not to say	Age: 	 Below 30  30-65  65+

| EC/KEQ | SPECIFIC INTERVIEW QUESTION |
| --- | --- |
| GN.0 | What was your role in the project implementation? |
| RL.1 | Do you feel this intervention relevant to the needs and priorities defined in the NAP for WPS? Do you feel there are areas that this project is not attending to which need to be attended to? If so why? Are others attending to those priorities? |
| RL.2 | Do you feel the intervention has effectively responded to key changes in the context (e.g. humanitarian challenges - cyclones Idai and Kenneth and Covid-19 and conflict in specific districts) or changes in the WPS and recovery policy? If so how did you adapt (processes, activities)? |
| RL.2 | Do you think WPS priorities at different levels of the government (national, provincial, district) are similar and/or coordinated? If so, how they are being coordinated? |
| IM.3 and CC.12 | What do you think have been the main results of the project for your organization or the women/groups of women you represent? (Note for interviewer: Search for examples in terms of capacity, attitudes, behavior, knowledge, availability of information on WPS, power imbalances within the institution) |
| SS.9/11 | What you consider as elements that contribute to the sustainability of the project results? What is needed to ensure that the results of the project are maintained/sustained? What was done so far? What else do you feel that needs to be done in the remaining period of project implementation? |
| IM.3 and CC.12 | What have been the main results of the project for you personally? |
|  | In what areas do you still feel more effort is needed and why? |
| EF.4 | Only if not covered before/in IM3: Do you feel the project has effectively been able to influence government institutions? If so, how? |
| EF.4 and EE8 | In terms of coordination with partner organizations: - What has worked well and why? Can this be replicated? - What can be improved and how? |
| EF.5 | What have been the key factors of success and failure for the project? What do you think are or have been the main obstacles? How can these obstacles be solves/can the project do anything about them? |
| EF.6 | What are the key cost drivers of the project? What has been done to ensure VfM (diminish costs, make the project more cost-efficient? |
| EE.7 | Do you feel the logframe and ToC effectively represent all areas covered by the project? Do you see the need for any changes? Have any changes been done to the logframe (outputs, indicators and/or targets)? And If so why? |
| EE.7 and 8 | What has been the monitoring strategy for the project? What have been the main challenges in implement it? |
| EE.8 | How do you ensure capturing best or bad practices? How do you share best practices with UN Women teams in other countries in the region (or outside)? |
| EE.8. | Is there a UN WPS strategy under this project is being implemented? How do you coordinate with others partners/projects implementing programmes in the same areas? |
| EE.8 | Is there a UN Women WPS regional strategy? How is it been coordinated? |
| SS.9/10 | Only if not covered before/in IM3: Do you feel commitment from Government institutions to the WPS/NAP agenda has been strengthened as a result of the project? If so how? |
| SS.9/10 | Only if not covered before/in IM3: Do you feel the project has done sufficiently to build capacity of local partners and communities to be able to meet WPS objectives? |
| CC12. | How are you promoting changes in social relations and power structures in the favour of women/girls? |
| HRGE.12 | Has the intervention to any extend led to unforeseen adverse effects on the four cross-cutting issues (gender, human rights, corruption, environment & climate change)? |
| All -classify accordingly | What could have been done better, more of or different? Do you have any additional information or recommendation that could be helpful for the future implementation of the project? |

#### Tool 4. FGDs questionnaires women beneficiaries at district level

The Evaluation Team and UN Women would like to thank you and appreciate the time and information you are sacrificing to participate in this important and valuable study under the Promoting the Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique (WPS Mozambique) project. The mid-term evaluation is aimed at improving implementation, use of resources, accountability as well as aims to identify the lessons learnt and good practices in order for the project to grow and adapt accordingly in order to achieve the intended results. This research is being developed by myself ________________ _______________ , as a local researcher and expert, and lead by Lina Gonzalez-Pineros. You can contact us in our emails _______________________ and linagonzalezp@gmail.com, in case of any doubt.

Please be aware that you can refuse to answer any of the below questions and our stop the interview at any point. If you feel uncomfortable around any of the questions, you want me to reframe it/explain it in any other way, please let me know and I will do. By allowing us to continue you agree with us using the information for the purposes outlined below only. Your personal data won’t be shared with any other person but you can refuse to provide any of the information below.

Interview Date: _____________  Location (Town): ________________ 	Province: _________________

Number of participants: _______          Group identifiable: ______________________________

| Initials | Age Below 30, 30-65, 65+ | Gender F, M, Other, prefer not to say |
| --- | --- | --- |

| EC/KEQ | SPECIFIC INTERVIEW QUESTION |
| --- | --- |
| GN.0 | What kind of services, training/capacity building or activities have you benefited from? Be as specific as possible please? (e.g. trainings on WPS, training on participation on peace/reconciliation trainings, workshops, roundtables, access to redress service, socioeconomic support) |
| RL.1 | Do you feel this intervention relevant to the needs and priorities of women and girls in your communities? If so how? |
| RL.2 | Do you feel the intervention has effectively responded to key changes in the context (depending on region, please choose: humanitarian challenges - cyclones Idai and Kenneth and Covid-19 and conflict in specific districts)? |
| IM.3 | What have been the main results of the project for you personally? (e.g. improvement in redress services, access to socio-economic activities -please specify) |
| IM.3 | Are there any other additional results for your community/socio-economic group? |
| CC.12 | Do you feel this project is empowering you as a woman within your household or community/nationally? Do you feel the project is empowering other women and girls? |
| IM.3 and CC.12 | What more results would you expect to see in the future? In what areas do you still feel more effort is needed and why? |
| SS.9/10 | Do you feel commitment from Government institutions to respond to the needs of women and girls? Do you know what the NAP for WPS is and/or what is included within? |
| HRGE.12 | Has the intervention to any extend led to unforeseen adverse effects on the four cross-cutting issues (gender, human rights, corruption, environment & climate change)? |
| All -classify accordingly | What could have been done better, more of or different? Do you have any additional information or recommendation that could be helpful for the future implementation of the project? |

#### Tool 5. FGDs/case studies men/women beneficiaries (Men for Women Training, Police/ Defense Forces WPS Training)

The Evaluation Team and UN Women would like to thank you and appreciate the time and information you are sacrificing to participate in this important and valuable study under the Promoting the Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique (WPS Mozambique) project. The mid-term evaluation is aimed at improving implementation, use of resources, accountability as well as aims to identify the lessons learnt and good practices in order for the project to grow and adapt accordingly in order to achieve the intended results. This research is being developed by myself ________________ _______________ , as a local researcher and expert, and lead by Lina Gonzalez-Pineros. You can contact us in our emails _______________________ and linagonzalezp@gmail.com, in case of any doubt.

Please be aware that you can refuse to answer any of the below questions and our stop the interview at any point. If you feel uncomfortable around any of the questions, you want me to reframe it/explain it in any other way, please let me know and I will do. By allowing us to continue you agree with us using the information for the purposes outlined below only. Your personal data won’t be shared with any other person but you can refuse to provide any of the information below.

Interview Date: _____________  Location (Town): ________________ 	Province: _________________

Number of participants: _______          Group identifiable: ______________________________

| Initials | Age Below 30, 30-65, 65+ | Gender F, M, Other, prefer not to say |
| --- | --- | --- |

| EC/KEQ | SPECIFIC INTERVIEW QUESTION |
| --- | --- |
| GN.0 | What kind of services, training/capacity building or activities have you benefited from? Be as specific as possible please? |
| RL.1 | Do you feel this intervention relevant to the needs and priorities of women and girls in your communities? If so how? |
| RL.2 | Do you feel the intervention has effectively responded to key changes in the context (depending on region, please choose: humanitarian challenges - cyclones Idai and Kenneth and Covid-19 and conflict in specific districts)? |
| IM.3 | What have been the main results of the project for you personally? (e.g. improvement in redress services, access to socio-economic activities -please specify) |
| IM.3 / CC.12 | What have you been able to do with the training obtained? Are there specific projects you are developing at the local/institutional level? How are you promoting changes in social relations and power structures in the favour of women/girls? |
| SS.9 /EE.5 | Do you see any key challenges/obstacles to the projects/activities do you want to implement at local or institutional levels? In what areas do you still feel more effort is needed and why? |
| SS.9/10 | Do you feel commitment from Government institutions to respond to the needs of women and girls? Do you know what the NAP for WPS is and/or what is included within? |
| HRGE.12 | Has the intervention to any extend led to unforeseen adverse effects on the four cross-cutting issues (gender, human rights, corruption, environment & climate change)? |
| All -classify accordingly | What could have been done better, more of or different? Do you have any additional information or recommendation that could be helpful for the future implementation of the project? |

#### Tool 6. Surveys Police/ Defense Forces WPS Training

To be based on above questions, but to be designed with Training Centers and  corresponding Ministries.

## Terms of Reference

MID-TERM EVALUATION OF UN WOMEN PROJECT- ‘“Promoting Women and Girls´ Effective Participation in Peace, Security and Recovery in Mozambique”

I. Background

A. UN Women´s Mandate for the Project

The work of the UN Women on Women, Peace and Security (WPS) is governed by a series of commitments on the rights of women.

These include United Nations Security Council (UNSC) landmark Resolution 1325 (2000) and nine successive resolutions - 1820, 1888, 1889, 1960, 2106, 2122, 2242, 2467 and 2493 as well as the Beijing Platform for Action (BPFA) and the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) including the CEDAW General Recommendation No. 30 on conflict prevention, conflict and post-conflict situations.

UN Women supports women’s full and equal representation and participation in all levels of peace processes and security efforts.

Enhancing women’s engagement for sustainable peace requires an integrated approach that simultaneously addresses conflict prevention, resolution and recovery, while strengthening national accountability and ensuring women’s protection from all forms of human rights violations, including sexual and gender-based violence. In order to achieve transformative change, UN Women works in the following areas: (1) increasing women’s meaningful participation in formal, and informal peace negotiations; (2) promoting women’s participation in peacebuilding and recovery planning, women’s economic empowerment within recovery efforts, and the establishment of gender responsive post-conflict institutions; (3) increase women´s participation and safety in peacekeeping; (3) ending impunity conflict-related sexual and gender-based violence; (4) promoting a gender-sensitive approach to preventing and countering violent extremism; and (5) create an enabling environment for the implementation of national commitments to women, peace and security (including the implementation of National Action Plans on WPS). In addition, UN Women promotes research initiatives, data collection, learning exchanges, and documentation of good practices on women, peace and security to inform policy and programming.

The actions of UN Women in Mozambique are aligned with two strategic objectives: 1) Consolidate national unity, peace and sovereignty and 2) Develop human and social capital in accordance to the government´s Five Year Plan and the National Plan for the Advancement of Women. The project being implemented will contribute to the implementation of the National Action Plan for the Advancement of

Women and the National Action Plan on Women, Peace and Security (2018-2022) (NAP), which was created with the support of UN Women. The project is part of the larger UN Women Programme on Women, Peace and Security and is being implemented within the framework of the UNDAF (the framework for comprehensive programme cooperation between the UN and the Government of Mozambique) and will contribute towards the achievement of the Agenda 2030 for Sustainable Development and Agenda 2063: The Africa We Want.

B. Context in Mozambique

Following the 1992 Peace Accords between the government of Mozambique and the former rebel movement RENAMO, Mozambique knew almost 20 years of relative peace and stability. This allowed for significant democratic advances in the country, including gender equality and women's empowerment.

Since the ratification of the CEDAW in 1997 and the adoption of Beijing Declaration and Platform for Action as well as the gender equality as a constitutional principle, Mozambique has made significant progress at political, legal and institutional level. The main milestones include the existence of a National Policy and Implementation Strategy, the National Plan for the Advancement of Women, a Law on Domestic Violence Against Women (29/2009), the Ministry of Gender, Children and Social Action, the National Council for Women's Advancement, represented at both provincial and district level, the adoption and implementation of an integrated multi-sectoral approach to assist victims of violence against women, National Action Plan on Women Peace and Security, and the law to Prevent and Combat Premature Unions (19/2019).

Women's participation in politics has increased over time, particularly on central level and women's participation over all sectors of government reached 32.4% in 2016. [1] This is even more visible at provincial, district and community level: there are 36% women provincial governors from previous 22,7%, 18% district administrators from previous 11% and 17% of the heads of administrative posts compared to less than 5%. However, progress has not been enough to challenge deeply rooted sociocultural norms on local level.

The political situation remains fragile with demobilization and reintegration of former rebel armed forces following cease fire between the government and the National Mozambican Resistance (RENAMO) reached in March 2018 and part of the recently definitive peace agreement signed definitive and comprehensive Peace and Reconciliation Agreement by the Government and RENAMO in August 2019.

However, since 2017, the province of Cabo Delgado (in north of Mozambique-one of the provinces with a growing extractive industry) has been affected by attacks by armed group said to be linked to extremist religious groups, which resulting in social instability.

While political-military tensions as well as the increasing violent extremism in the northern region threaten the already precarious peace and security of women and girls in Mozambique. In addition, other factors, such as macroeconomic instability, health crises (including COVID-19, HIV/AIDS, Tuberculosis, etc), natural disasters and the emergence of conflicts, raise further threatens the peace and security of women. Several women and girls have directly endured or are still enduring the impact of conflicts and attacks, live in a constant state of fear of violence, have lost their livelihoods, and have been displaced. This further aggravated by the ongoing political tensions between the leading political parties (despite the signing of the Peace Agreement in 2019) and as the conflicts in the northern region of the country continues to expand and escalate.

II. Description of the Project

The project rationale stems from the need to promote the active and full participation of women and girls in peace, security and recovery processes in Mozambique at all levels. To respond to challenges faced in the promotion of gender equality in peace and security processes at all levels in Mozambique, since 2016 the Government of Mozambique, through the Ministry of Gender, Children and Social Action and with the support of UN Women, began the formulation of the National Action Plan on Women, Peace and Security for the national implementation of UN Security Council Resolution 1325 and the related resolutions. In May 2018, the Government of Mozambique approved the National Action Plan on Women, Peace and Security (2018-2022) (NAP) which seeks to promote women´s and girls´ human rights in armed conflict and post conflict contexts.

As form of operationalizing the NAP, UN Women in partnership with MGCAS and support of the Governments of Iceland and the Kingdom of Norway, is implementing a project denominated: “Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique.” The project focuses on:

Enhancing security for women and providing integrated multi-sectorial response services to victims of violence;

Promoting and facilitating the socioeconomic recovery of women;

Strengthening women’s capacity and women’s organizations to participate in conflict prevention and resolution, in particular at community level;

Strengthening national capacity to coordinate, monitor and account for the implementation of global commitments on women, peace and security.

With a duration of five years, it started in December 2017 and will end in December 2021, the project is currently being implemented in 14 districts and 7 provinces of the country (please refer to the graphic below for specifications) with a total budget of approximately 4.5 million dollars. It is important to note that the project duration had been extended by one year from December 2020 to December 2021. Its direct beneficiaries are women and local government authorities.

The project is guided by the following theory of change: 1) if a facilitating environment is created for the implementation of WPS commitments, 2) if women participate in decision-making processes on prevention, management and conflict resolution in an effective way, and 3) if the protection, physical and mental health and economic security of women and girls is guaranteed, their human rights respected and their specific needs in the process of peacebuilding and recovery fulfilled. Then, societies will be more peaceful and fairer, because evidence shows that women are the driving forces of peace and security and inclusive societies are more likely to be stable. Furthermore, post-conflict scenarios are opportunities to link to the root causes of gender inequality barriers.

The expected results of the project are the following:

Outcome 1: Women and girls’ safety, physical and mental health and security are enhanced, and their human rights protected

Output 1.1: Women and girls affected by violence have access to comprehensive services to redress – including appropriate protection, health and psychosocial and legal services in resettlement, returning areas and in disaster affected areas

Outcome 2: The socio-economic recovery of women and girls is increased in the post conflict setting

Output 2.1: Women and girls have increased access to economic opportunities in the context of recovery from conflict and cyclone IDAI

Outcome 3: The enabling environment for sustainable implementation of WPS commitments is strengthened

Output 3.1: Women and girls’ capacity to participate meaningfully in conflict prevention/resolution strengthened

Output 3.2: Capacity of the Ministry of Gender to coordinate and monitor implementation of NAP and fulfil UN reporting requirements strengthened

Output 3.3: National capacity to implement and generate knowledge on WPS enhanced

The project counts with the following Key stakeholders: Ministry of Gender, Children and Social Action; the Governments of Iceland and the Kingdom of Norway, Ministry of Interior, Ministry of National Defence, Civil Society organizations, especially women-led organizations/associations, the provincial governments and the governments of the target districts. Some of these partners are part of the project Advisory Group.

The project management structure is composed of:

a programme specialist, based in Maputo, who is responsible for the overall supervision of all programmatic management, partnership building and staff management in the project;

a Programme Officer, based in Maputo, who is responsible for the overall project and financial management and technical support in the project;

a Project Officer, based in Ministry of Gender, Children and Social Action, responsible for providing technical support to the Ministry of Gender, Children and Social Action in created WPS unit, as well as responsible for the project coordination and implementation with local government partners at provincial and district levels.

III. Duties and Responsibilities

A. Purpose (and use of the evaluation)

The evaluation will take place during the 2.5 year of implementation and UN women commissioned the MTE to inform future direction of the project. Therefore, it aims at improving implementation, use of resources, accountability as well as aims to identify the lessons learnt and good practices in order for the project to grow and adapt accordingly in order to achieve the intended results. In this perspective, the

evaluation will be used for both accountability and learning purposes, as well as contributing to inform future implementation and decision-making. The evaluation will also serve to sharpen and/or re-align results to new national development indicators, the challenges of the protracted instability and growing violence in project implementation areas and the tension between emergency and development

interventions.

The target audience of the evaluation will be the UN Women project management, its country office and regional management; the donor of the project, other donors interested in UN Women’s portfolio, UN Women’s partners (including the national government and the provincial governments); other stakeholders engaged stakeholders engaged in promotion of WPS agenda, in and out of Mozambique.

B. Objectives (evaluation criteria and key questions)

Considering the mandates to incorporate human rights and gender equality in all UN work and the UN Women Evaluation Policy, which promotes the integration of women’s rights and gender equality principles, these dimensions will have a special attention in this evaluation. A specific evaluation objective on human rights and gender equality is included as well as considered under each evaluation criterion.

The overall objectives of this evaluation are to:

Analyse how Human Rights Approach and gender equality principles are integrated in the interventions;

Assess the relevance of the project at national level including alignment with international agreements and conventions on WPS and other gender equality and women’s empowerment

Assess the effectiveness and organizational efficiency in achieving expected results, including the effectiveness of programming strategies in implementing global commitments within national priorities for in working toward to achieve expected results, with a special focus on innovative, scalable and replicable interventions. The evaluation should also investigate the contextual factors that are enabling or restricting the achievement of results, including financial management and human resource investment;

Assess the initial impact of the intervention on the lives of beneficiaries, communities, and institutions involved in the project;

Assess the potential sustainability of the interventions in achieving gender equality and women’s empowerment in the context of WPS;

Assess the functioning and effectiveness of the Monitoring, Evaluation and Knowledge Management system, identifying and validating lessons learned, good practices and examples of innovation; and

Provide actionable recommendations with respect to improving the project and similar programmes in the future.

C. Key Evaluation Questions

The following draft evaluation questions serve as first reference point for the inquiry. The specific evaluation questions, performance criteria and relevant evaluation instruments will be determined during the inception stage and in close consultation with the Evaluation Reference Group.

Relevance

To what extent is the intervention relevant to the needs and priorities as defined by beneficiaries?

To what extent is the intervention contributing to districts, provincial and country priorities for gender equality and the promotion of the active participation of women in peace, security and recovery in Mozambique?

To what extent the intervention was relevant to beneficiaries to respond the new humanitarian challenges, such as the cyclones Idai and Kenneth and Covid-19 and conflict in specific districts?

What are the current priorities for gender equality, promotion of the participation of women and girls in peace, security and recovery in Mozambique at districts, provincial and country level? Is the project responding to them?

Effectiveness

To what extent do the activities being carried contribute to the intended outputs and outcomes and how did UN Women contribute towards them? Is there area for improvement? If so, how can UN Women improve?

Did UN Women effectively contribute to the outputs?

What are the enabling and limiting factors that are contributing to the achievement of results and what actions need to be taken to overcome any barriers that may limit the progress?

Organizational efficiency

To what extent are project strategies cost-effective in making an impact on the ground, district and provincial levels? (analysing the budget and project expenditure over the two- and half-year period of the project);

To what extent is the Budget and Expenditure over the two and half -year period contributing to desired project results?

What have been the capacities (technical, administrative and advocacy skills) of the project management structure to deliver the project objectives and how could they be strengthened to improve impact?

Contribution to the Intended Outcomes and Impacts

Is the project likely to contribute to long-term social, economic, technical, environmental changes for individuals, communities, and institutions (government and civil society – women’s organizations) and women’s movement related to the project?

What changed in the lives of the beneficiaries (both direct and indirect beneficiaries)? (Assess scenarios of before and after the project).

What are the social changes the intervention contributed for at community level? (attitudes, behaviour, knowledge, socio-cultural practices & norms related to GE)

What institutional changes did the intervention achieve in the partners organizations?

How did the project change the availability of data on WPS and gender equality to guide policy and programming?

Sustainability

To what extent was capacity developed in order to ensure sustainability of efforts and benefits?

How will the benefits of the intervention be secured for rights holders (i.e. what accountability and oversights systems were established or strengthened)?

What are the contextual factors for sustaining and replicating the project interventions and its impact at national level;

To what extent have civil society organizations and women´s organizations/associations/movement committed to promote the WPS agenda and promote peace and security for all at district level;

Do beneficiaries demonstrate skills with potential for long term impact on their wellbeing?

To what extent have Government Partners committed to promoting the WPS agenda at central, provincial and district level?

Human Rights approach and Gender Equality principles

To what extent has gender and human rights considerations been integrated into the programme design and implementation?

How has attention to/integration of gender equality and human rights concerns advanced the area of work?

Strategic positioning

What is the level of engagement between the Partners and key Stakeholders at all levels and the ability to leverage the partnership process to inform the advocacy strategy?

How has the project aligned UN Women’s position to the regional and global context?

What is the value addition of UN Women in terms of the resources oversight and technical support?

Monitoring, Evaluation and Knowledge Management

Is there a need to improve the Monitoring & Evaluation Framework including logical frame indicators, tools and processes used to monitor and report activities, outputs?

Is the knowledge produced by the project being used? (e.g. studies and KP produced during the implementation)?

Is the project documentation (donor reporting, activity reporting, KM and communication products) adequate, disseminated and sufficient?

Which are potential good practices, challenges and lessons from the interventions and recommend forms to improve project strategies in the remaining implementation period.

D. Scope of the evaluation

The scope of the evaluation is national (concentrated at central level as well as in the 14 target districts in the 7 project provinces) and will include all dimensions of the project, namely how it contributes to the overall UN Women mandate to support normative and intergovernmental, operational and coordination work at provincial and national levels. It will assess the implementation from 2018 to the current implementation. In an effort to identify and assess WPS linkages with other thematic areas, the evaluation scope includes also other UN Women impact areas such as the elimination of violence against women and girls, women´s socioeconomic empowerment, and global norms and institutional support. In addition, it will shed light on key relevant issues and emerging project risks, including but not limited to, the increase in violence in Cabo Delgado, the increase in humanitarian and public health crises.

E. Evaluation design (process and methods)

The evaluation will be carried following UN Evaluation Group (UNEG) Norms and Standards (see http://www.UN Women.org/aboutus/ accountability/evaluation/), UN Women Evaluation Policy, UN Women Evaluation Handbook on Gender-Responsive Evaluation, it is already referenced with link in the Annex, UNEG Technical Note on the SWAP Evaluation Performance Indicator, (see https://www.UN Women.org/en/about-us/accountability/evaluation/un-coherence) as well as the Ethical Guidelines for evaluations in the UN system, see Annex to this TOR. Once finalized the evaluation report will be quality-assessed based on the UN Women Global Evaluation Reports Assessment and Analysis System (GERAAS). GERAAS standards and GERAAS rating matrix are available at http://www.UN Women.org/en/about-us/evaluation/decentralized-evaluations.

The formative evaluation will be based on the explicit theory of change already formulated by stakeholders at the beginning of the programme. It will test its validity against the evidence collected so far regarding key programme results. It is also important to mention that both qualitative and quantitative methods are expected to be utilised. The evaluation process will be transparent and involving various stakeholders and partners.

The evaluation type will be non-experimental, and follow these phases:

- Preparation: This includes the stakeholder analysis and establishment of the reference group, development of the ToR, and recruitment of the evaluation team

- Conduct: Inception report, stakeholder workshop, data collection and analysis

- Reporting: Presentation of preliminary findings, draft and final reports

- Use and follow up: Management response, dissemination of the report, and follow up on how to positively shape future programme design.

F. Methodology

The evaluation methodology will be developed by the Evaluation Consultants and presented for approval to the Evaluation Reference Group. The methodology should use a combination of quantitative and qualitative research methods that are appropriate to address the main evaluation questions and account for complexity of gender relations and to ensure participatory and inclusive processes that are culturally appropriate. These methods should be responsive to human rights and gender equality principles and facilitate the engagement of key stakeholders. Measures will be taken to ensure the quality, reliability and validity of data and data collection tools. Limitations with respect to the sample (representativeness) should be stated clearly.

Primary data collection could be undertaken through observations, site visit, individual key informant interviews and focal group discussions with representatives of relevant government institutions (duty bearers), development partners, beneficiaries (right holders) and key community players seeking to address gender equality and human rights issues. Data collection methods such as appreciative inquiry, most significant change, case study, survey could also be implemented. The evaluator will develop a sampling frame (area and population represented, rationale for selection, mechanics of selection, and limitations of the sample) and specify how it will address the diversity of stakeholders in the intervention.

However, given the current COVID-19 context and the increase in insecurity and violence context, there may be some restrictions in the collection of primary data in the field and the evaluation methodology needs to take into account the current COVID-19 and insecurity in Cabo Delgado and other provinces, which will require the application of remote / virtual/ online methods for data collection and stakeholder engagement. For more details, please see UNW Pocket tool for managing evaluation during the COVID-19 pandemic: https://www.UN Women.org/en/digital-library/publications/2020/05/pocket-tool-for-managing-evaluationduring-the-covid-19-pandemic

The evaluator should take measures to ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights; for example, the limitations of the sample (representativeness) should be stated clearly, and the data should be triangulated (cross-checked against other sources) to help ensure robust results. All the data collected should be gender-responsive (including disaggregated by sex and age). The final evaluation report, its quality rating and the evaluation management response will be publicly disclosed in the UNW GATE system.

Stakeholder participation

The Evaluators will collaborate with the Project Management to convene and coordinate meetings with the Evaluation Reference Group (ERG). Ideally, the ERG will include the members of the WPS Advisory Group: The Ministry of Gender, Children and Social Action; the Governments of Iceland and Norway; sister UN agencies, UN Women staff from national and Regional level, local governments and civil society organizations (specially women-led organizations/associations/groups). They will be playing liaison, technical advisory and quality assurance roles, including the validation and dissemination of results. In this sense, rural women and their associations are key rights holders — their views, challenges and progress need to be highly reflected in the process and results of this evaluation.

## Evaluation Management and Reference Group Members

The evaluation reference group will be composed by the project's technical advisory group, namely:

- Government of Mozambique

  - Ministry of Gender, Children and Social Action

  - Ministry of Defense

  - Ministry of the Interior

  - National Institute of Statistics

- Cooperation Partners

  - Embassy of Norway

  - Embassy of Iceland

  - Embassy of Canada

  - Embassy of Sweden

- Academic institutions

  - Joaquim Chissano University

  - CECAGE-EMU

- Civil Society Organizations

  - MULEIDE

  - WLSA

  - ASCHA

  - AMMMCJ

  - PROPAZ

  - GMPI Sofala

  - 17. HOPEM Network

- United Nations

  - UN Women Mozambique and Regional Office (members of the evaluation management team)

Represented at the provincial level by the Provincial Services for Gender, Children and Social Action; and at the district level, by the Health, Women and Social Action Services,

The framework for comprehensive programme cooperation between the UN and the Government of Mozambique.

UN Women, Project’s design document, 2016: “Women's participation over all sectors of government reached 32.4% in 2016”.

UN Women, Project’s design document, 2016: “There are 36% women provincial governors from previous 22,7%, 18% district administrators from previous 11% and 17% of the heads of administrative posts compared to less than 5%”.

CARE, Lessons Learnt from CARE’s Shelter Responses to Cyclone Idai in Malawi, Mozambique and Zimbabwe, September 2020. https://www.careevaluations.org/wp-content/uploads/Lessons-Learnt-from-CARE%E2%80%99s-Shelter-Responses-to-Cyclone-Idai-in-Malawi-Mozambique-and-Zimbabwe.pdf

CARE, Rapid Gender Analysis for Cyclone Idai Response, Sofala Province, Mozambique, Abril 2019. https://insights.careinternational.org.uk/images/in-practice/RGA-and-measurement/RGA-Sofala-Mozambique_April-2019-Final.pdf

Sportlight Initiative. Mozambique responds to gender-based violence in the context of COVID-19, article September 2020. https://spotlightinitiative.org/press/mozambique-responds-gender-based-violence-context-covid-19

CARE, Rapid Gender Analysis for COVID 19  East, Central and Southern Africa, April 2020.  http://www.careevaluations.org/wp-content/uploads/ECSA-RGA-_-FINAL-30042020.pdf

OCHA Situation Report 2020. https://reports.unocha.org/en/country/mozambique

Mocímboa da Praia, Palma, and Montepuez in Cabo Delgado (3), Chibabava, Machanga, Gorongos, Beira, Buzio and Dondo in Sofala (6), Morrumbala in Zambezia (1), Moatize in Teté (1), Vanduzi in Manica (1), Funhalouro, Panda and Mambote in Inhambane (3), Chigubo and Chibuto in Gaza (2)

Particular attention will be paid to ensuring that the mixed participation of women and young women does not result in the lack of participation by either group.

We will ensure at least one person from the  Estado Maior General is included and 1 of the national professionals who successfully completed the UNU GEST 5 month Gender Equality Studies and Training Programme, acquiring a post-graduate diploma with a focus on WPS.

Members from Chibabava and Gorongoza/Maringoe will be interviewed if possible.

We will aim to include the national professional who successfully completed the UNU GEST 5 month Gender Equality Studies and Training Programme, acquiring a post-graduate diploma with a focus on WPS and those responsible for the future MDN academy course on WPS.

The DAC Network on Development Evaluation recently approved an updated set of definitions and principles for use for its evaluation criteria. This adaptation follows a Global Consultation on the Evaluation Criteria. The purpose of the evaluation criteria is linked to the purpose of evaluation. Namely, to enable the determination of the merit, worth or significance of an intervention. The criteria play a normative role. Together they describe the desired attributes of interventions: all interventions should be relevant to the context, coherent with other interventions, achieve their objectives, deliver results in an efficient way, and have positive impacts that last. Definitions for each criteria are provided below. https://www.oecd.org/dac/evaluation/daccriteriaforevaluatingdevelopmentassistance.htm

The extent to which the intervention objectives and design respond to beneficiaries’* , global, country, and partner/institution needs, policies, and priorities, and continue to do so if circumstances change.

The extent to which the intervention has generated or is expected to generate significant positive or negative, intended or unintended, higher-level effects.

The extent to which the intervention achieved, or is expected to achieve, its objectives, and its results, including any differential results across groups.

The extent to which the intervention delivers, or is likely to deliver, results in an economic and timely way.

The extent to which the net benefits of the intervention continue, or are likely to continue.

Includes 88/128 beneficiaries, and organisations (government stakeholders, CSOs, women organisations) based in those locations: Cabo Delgado (with research in Pembe and maybe Montepuez -depending on security), Sofala (Beira, Buzio and/or Dondo), Inhambane (Inhambane, Panda and Funhalouro), and Zambezia (Morrumbala).

The abbreviations included below correspond to the question number and evaluation criteria, thus corresponding to General Notes (GN), RL (Relevance), IM (Impact), SS (Sustainability), EF (Effectiveness), EE (Efficiency), HRGE (Human Rights and Gender). For questions where information can be classified in different areas we added a final questions?