Final Evaluation

of the Project “Promoting Women and Girls´ Effective Participation in Peace, Security and Recovery in Mozambique” (April 2017 – March 2022)

UN Women Mozambique

Inception report

2nd version: 20/04/2022

Lead consultant: Dr. Roberta Pellizzoli

Local evaluation expert: Julio Langa

Index

Introduction	4

Scope and objectives of the inception report	4

UN Women work on Women, Peace and Security in Mozambique	4

Context	5

Purpose, objectives and scope of the evaluation	9

Theory of change or programme theory	10

Methodology	12

Evaluation criteria and elaboration of key questions	12

Stakeholders mapping	14

Indicators for measuring results	20

Evaluation design (method of data collection and analysis)	21

Sample and sampling design	23

Ethical considerations and limitations	30

Evaluation matrix	32

Work plan	37

Responsibilities, logistics and support	38

Annexes	39

Annex I - Internal documents reviewed	39

Annex II - Draft data collection instruments	40

Consent form	45

Tool 1. KII or GI – Government stakeholders at national, provincial and district level	46

Tool 2. KII/ GI – CSOs, women national organizations, national/international partners, and other secondary stakeholder	47

Tool 3. GI with UN Women Team	48

Tool 4. FGDs questionnaires women beneficiaries at district level	49

Tool 5. FGDs questionnaires for participants in trainings on WPS	50

Annex III - Terms of reference	51

Annex IV - Evaluation management and reference group members	59

Abbreviations

ADEL – Local Economic Development Agency

BPFA Beijing Platform for Action

CAI - Integrated Service Centres

CECAGE - Coordination Centre for Gender Affairs

CEDAW Convention on the Elimination of All Forms of Discrimination against Women

COREM – Council of Religions of Mozambique

CSO Civil Society Organisations

DHD – Association for Human Rights and Development

DPGCAS – Provincial Directorate of Gender, Children and Social Action

DTM – Displacement Tracking Matrix

FDC - Foundation for Community Development

FES - Friedrich Ebert Stiftung Foundation

FGDs Focus Group Discussion

GBV - Gender Based Violence

GI – Group interviews

GMPIS - Sofala Group of Women Sharing Ideals

GRO-GEST UN University Gender Equality Studies and Training Programme

IEO – Independent Evaluation Office

KEQs Key Evaluation Questions

KII Key Informants Interviews

LR – Local Researcher

MDN - Ministry of National Defence

MGCAS Ministry of Gender, Children and Social Action

MINT - Ministry of Interior

MMAIMVV - Multisectoral Mechanism for Integrated Assistance to Women Victims of Violence

MULEIDE - Women, Law and Development Association

NAFETE – Nucleus of Tete’s Feminists Associations

NAFEZA - Nucleus of Zambezia’s Feminists Associations

NAP 1325 1325 - National Action Plan on Women Peace and Security in Mozambique

NGOs - Non-Governmental Organizations

NSAG - Non-armed state groups

OECD/DAC - Organisation for Economic Co-operation and Development/Development Assistance Committee

ProPaz - Peace Promotion Institute of Mozambique

Res 1325 - Resolution 1325 of the United Nations Security Council

TL - Team Leader

ToR - Terms of Reference

UEM Eduardo Mondlane University

UJC Joaquim Chissano University

UN United Nations

UNEG - United Nations Evaluation Group

WPS - Women Peace and Security

## Introduction

### Scope and objectives of the inception report

This inception report is intended as a road map for managing the overall evaluation process of the project “Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique”. This document is the result of the outcomes of the inception phase, that included: inception meetings with the project management team, review of project documentation as well as of third parties relevant literature, review of the ToR vis-a-vs the project documentation, presentation of the draft report to the reference group and incorporation of comments received both from the UN Women management team and the reference group members.

Therefore, this document aims to define what is going to be evaluated, how, and with whom, providing a broader discussion on and presentation of: context in which the project has been implemented, and how it has changed since project’s inception; stakeholders’ analysis; proposed approach and methodology made by the evaluation team; and data collection procedures and sources; workplan, deliverables, timetable, roles and responsibilities and proposed travel and logistic arrangements.

A prior rapid evaluability assessment was realized to determine the feasibility of the evaluation based on: clarity of the theory of change, existence and availability of relevant information and documentation, conduciveness of the context for carrying out the evaluation, including the degree of stakeholders’ involvement.

### UN Women work on Women, Peace and Security in Mozambique

The work of UN Women on Women, Peace and Security (WPS) is governed by a series of commitments on the rights of women. These include Resolution 1325 of the United Nations Security Council (Res 1325) and eight successive resolutions - 1820, 1888, 1889, 1960, 2106, 2122, 2242, 2467 and 2493 as well as the Beijing Platform for Action (BPFA) and the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW), the CEDAW General Recommendation No. 30 on conflict prevention, conflict and post-conflict situations.

In Mozambique, the UN Women Country Office has been working in the area of WPS since 2010, advocating for the implementation of the United Nations Resolutions on Women, Peace and Security. The national approach to the implementation of Res 1325 in Mozambique has been evolving over the years. The National Plan for the Advancement of Women 2010-2014 made a general reference to WPS, with an outwards looking perspective: "Integration of more women in peacekeeping missions, mediation and cooperation". The National Plan for the Advancement of Women 2015-2020, supported by UN Women, expanded the scope of intervention of Res 1325 and considered "Women's participation in internal processes of mediation and conflict resolution". At the same time, the Government of Mozambique, through MGCAS and with the technical support of UN Women, formulated the National Plan on Women, Peace and Security (2018-2022) (NAP 1325) for the implementation of Res 1325.

Based on international experiences, NAP 1325 pursues the following objectives:

(i) Create a favourable environment for the implementation of the legislation on women, peace and security; (ii) Integrate a gender perspective in all actions and strategies on conflict prevention and management ; (iii) Guarantee the participation of women in decision making structures in peace and security processes; (iv) Promote mechanisms to secure increased recruitment , retention and promotion of women in defence and security, and justice bodies; (v) Reinforce the fight against all forms of violence against women and girls in armed and non-armed conflict contexts; (vi) Expand efforts for the security, physical and mental health and dignity of women and girls; and (vii) Secure the rights of women and girls in conflict and post-conflict situations.

This approach responds to the strong perception that in Mozambique, as in any part of the world, conflicts exacerbate violence against women and girls and their insecurity, destroy their means of survival, undermine prospects for socioeconomic empowerment and reinforce the exclusion of women in decision-making processes due to their low representation in formal political and conflict resolution platforms.

As form of supporting the operationalization of the NAP 1325, UN Women in partnership with the MGCAS and support of the Governments of Iceland and the Kingdom of Norway, has designed and implemented a project denominated: “Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique” that started in April 2017 and was completed in March 2022.

The overall objective of the project was to ensure that peace and security and recovery processes contribute to gender equality and women´s empowerment in Mozambique. The project aimed to contribute to i) enhance security for women and providing integrated multisectoral response services to survivors of violence; ii) promote and facilitate women´s socioeconomic recovery; iii) strengthen the capacity of women and their organizations to participate in conflict prevention and resolution, particularly at the community level; and iv) strengthen national capacity to coordinate, monitor and account for the implementation of the global commitments on women, peace and security.

### Context

In Mozambique, the institutional and legal frameworks promoting gender equality and the rights of women and girls have advanced significantly since the first democratic elections held in 1994. Parts 2 and 3 of the Constitution lay out the fundamental rights, duties and freedoms of all Mozambicans and Article 66 prohibits discrimination based on colour, race, sex, ethnic origin, place of birth, religion, educational level, social position, the legal status of their parents, or their profession. Article 57 specifically addresses gender equality between men and women, recognizing and encouraging the participation of women in the political, economic, social and cultural activities of the country (Constitution Act, 1994). The country has ratified all the relevant international conventions protecting and promoting women’s and girls’ rights and, after the latest elections, has more than 40% women members of Parliament. Relevant legislation and policies promoting and protecting women’s rights are in place, including the Family Law (2004), the National Plan for Preventing and Combating Gender-Based Violence 2018-2021,; the Law on Domestic Violence against Women (Law 29/2009); the Multisectoral Mechanism for Integrated Assistance to Women Victims of Violence (MMAIMVV, 2012), the Gender Inclusion Strategy of the Health Sector (2018-2023), the Gender Policy and the Strategy for Implementation (2018), the Law to Prevent and Combat Child Marriages (2019).

The 2018 Gender Policy and its Strategy for Implementation identifies a list of gender mainstreaming objectives that cuts across sectors (such as education, health, employment, access to and use of natural resources, political participation), and includes a specific objective aimed to “develop actions that ensure equal participation of women and men in prevention, conflict mediation and peace building”.

To realize these objectives, the implementation strategy defines a series of “intervention axes”, among which is “conflict mediation and peace consolidation” with its related activities:

- To garantee the inclusion, access and permanence of women in the defence and security forces equal opportunities in career progression and in higher ranks

- Include women in peace and conflict resolution processes;

- To ensure that the needs of women combatants and civilians are protected and addressed during and after armed conflict;

- To ensure access to justice for women and girls who are victims of armed conflict and criminal accountability of perpetrators, with a view to ending impunity;

- To encourage conflict prevention and promotion measures and programmes that adopt a gender perspective, including non-violence education for men and boys at different levels and sectors; and

- To encourage the inclusion of women in conflict prevention and mediation.

The recognition of the rights of women and girls within an armed conflict and the importance of including them in conflict prevention and resolution, while ensuring the adoption of a gender perspective in peace and security has been further reinforced by the approval of the NAP 1325, that was developed with the support of UN Women, as discussed in the above section. In order to fully understand the relevance of the UN Women project within the Mozambican context, it is critical to stress that the preparation of NAP 1325 took place at a critical juncture in Mozambique, in a highly sensitive political, economic and humanitarian situation. In fact, the political-military tensions in Central Mozambique threatened the precarious safety and rights of women and girls, that were further exacerbated by other factors such as macroeconomic instability, the effects of drought and floods and the emergence of conflicts resulting from the exploitation of natural resources.

These political-military tensions can be linked to how the Peace Process unfolded in the country since the signature of the Peace Agreement in 1992, that brought to important achievements such as multi-party elections, the adoption of a new Constitution in 1994 and the demobilisation process. Nevertheless, the Peace Agreement full implementation faced several challenges, including an unequal distribution of power, lack of follow-up of the implementation and absence of immediate gains for RENAMO's ex-fighters and the entire population, leading to social and economic exclusion and eventually to a resurgence of the conflict in 2012, that particularly affected the Central Provinces of the country. An indefinite cease-fire was announced in December 2016, and a partial constitutional reform was unanimously adopted by Parliament in early June 2017. In October 2017, negotiations between Frelimo and RENAMO started and on the 6th of August 2019, the Mozambican President and Chairperson of the Frelimo Party, Felipe Nyusi and the new RENAMO Leader, Osufo Momade, signed the National Accord for Peace and Reconciliation. However, notwithstanding the steps taken towards enhancing the decentralisation process in the country, the 2019 Peace Accord did not result in the end of violent incidents in the Central Provinces, with the Junta Militar, a RENAMO splinter group, continued to carry out sporadic attacks in the Central Provinces at least until 2021.

When the negotiations between Frelimo and RENAMO were ongoing to put an end to the conflict in Central Mozambique,an increasingly violent conflict started to erupt in Cabo Delgado, with attacks on local communities carried out by non-state armed groups (NSAGs) and subsequent military interventions that caused widespread violence against civilians as well as destruction of homes, schools, health centres, and government offices. More than 784,000 people are estimated to be internally displaced in Mozambique due to the conflict in Cabo Delgado by February 2022 according to IOM’s Displacement Tracking Matrix (DTM) Baseline Assessment Round 15. Children account for 59 per cent of displaced people, while more than half (52 per cent) of displaced people are women and girls.

The way in which the conflict in Cabo Delgado has evolved is clearly reflected in the WPS project yearly reports: while the project document only briefly mentioned “the re-emergence of cultural and religious extremities throughout the world (including the northern provinces of Mozambique) and […] the pervasive impact of mining and gas exploration in the province of Cabo Delgado,” the first project report (covering implementation until June 2018) highlighted “the recent rise and expansion of armed violence in Cabo Delgado”. The second project report mentions “[continuing] armed violence in Cabo Delgado, affecting the security especially of women and girls, and [undermining] their opportunities to engage in economic activities; with the third report, covering activities until June 2020, highlights how the escalation in violence in Cabo Delgado and the deterioration of the humanitarian situation created “significant challenges to reach and support vulnerable women and girls in conflict affected districts”.

As highlighted in a recent study carried out by the London School of Hygiene and Tropical Medicine, “the conflict in Cabo Delgado has had a devastating impact, especially for women and girls who are experiencing ongoing and new forms of gender-based violence (GBV). The crisis has compounded multiple forms of GBV including intimate partner violence, physical and sexual violence, abduction, sexual trafficking, sexual exploitation and abuse, early and forced marriage, and economic violence. Existing support structures and prevention measures have been widely compromised by conflict and displacement, leaving the urgent needs of GBV survivors overwhelming unaddressed.”

Compared to the country context described in the project document, two other phenomena have to be taken into account in preparing for the evaluation of the WPS project: the increased occurrence of climate-related hazards and natural disasters and the COVID-19 pandemic, and how these impact on women’s and girls’ rights and livelihoods.

With regards to the former, Mozambique is one of Africa’s most vulnerable countries to climate change. Climate-related hazards such as droughts, floods and cyclones are occurring with increasing frequency, with a devastating impact on the population resulting from the combination of the effects of these event and chronic poverty, inadequate basic services and households reliance on subsistence agriculture that further exacerbate existing inequalities. In 2017, when the UN Women project started, the Southern part of the country was suffering from the effects of El Niño, that resulted in severe food insecurity related to drought and subsequent crops failure. In March 2019, Cyclone Idai killed at least 603 people in Central Mozambique. Combined with cyclone Kenneth, that hit the Northern Province of Cabo Delgado a few weeks later, they injured nearly 1,700 people; damaged or destroyed more than 277,700 homes; fully or partially destroyed more than 4,200 classrooms; devastated around 85% of agricultural production in a country where agriculture provides subsistence for 94% of the poor (Mozambique Humanitarian Response Plan 2019).

At the beginning of 2020, the spread of the COVID-19 pandemic, and the measures taken to prevent it, were expected to deepen pre-existing inequalities, across every sphere. The UN Secretary General expressed concern that the socio-economic impact of COVID-19 could be felt especially by women and girls who are generally earning less, saving less, and holding insecure jobs or being more affected by multidimensional poverty; access to health could be negatively affected, and restricted movement and social isolation measures might increase gender-based violence and limit social services capacity to deliver assistance to women’s victims of violence, as well as of women seeking for help.

A thorough understanding of these events, and of how inequalities can become drivers of conflict in fragile contexts, is considered extremely relevant for the evaluation of the UN Women project. The exacerbation of the conflict in Cabo Delgado, extreme climate events, and the COVID-19 pandemic, as highlighted in the UN Women annual reports, have created some setbacks for the project (i.e. the limitations caused by the COVID-19 pandemic in organizing events). Nevertheless, framing the evaluation within this broader picture is important as it will allow to highlight how the good practices and lessons learned during the WPS project implementation can guide future interventions aimed at gender-responsive conflict prevention, post-crisis recovery and peacebuilding in contexts affected by multiple vulnerabilities.

### Purpose, objectives and scope of the evaluation

The final evaluation is taking place after the end of the project implementation. It was commissioned by UN Women to assess the design, implementation, management, and outcomes of the WPS project in order to identify lessons learned and good practices that can guide the design and improve future initiatives managed by the UN Women Mozambique Country Office.

In this perspective, the evaluation will be used for accountability, learning and decision-making purposes, as well as to ensure that future planning of UN Women Mozambique action in the country is aligned to the current WPS context, the challenges of the protracted instability in the North and the trends of reconciliation and recovery interventions that, at the time of submission of this report, are being planned.

The primary target audience of the evaluation will be the UN Women project management, the Mozambique country office and regional management; the donors of the project; UN Women’s partners (including the national government and the provincial governments) in the project; as well as women and other vulnerable groups. As the primary audience, the duty bearers and rights holders of the UN Women project will be directly involved in the evaluation as described in the methodology section below.

The secondary target audience are other relevant stakeholders, which include other donors interested in UN Women’s portfolio; UN Women partners in non-WPS interventions; national and international stakeholders engaged in the promotion of WPS agenda.

The overall objectives of this evaluation are to:

- Analyse how human rights approach and gender equality principles are integrated in the interventions;

- Assess coherence (internal and external) of the project on how well the intervention fit and its compatibility with others in the Country Office and Country in general.

- Assess the relevance of the project at national level including alignment with international agreements and conventions on WPS and other gender equality and women’s empowerment

- Assess the effectiveness in achieving expected results, including the effectiveness of programming strategies in implementing global commitments within national priorities for in working toward to achieve expected results, with a special focus on innovative, scalable and replicable interventions. The evaluation should also investigate the contextual factors that are enabling or restricting the achievement of results;

- Assess the organizational efficiency of the project, in terms of financial management and human resource investments;

- Assess the potential sustainability of the interventions in achieving gender equality and women’s empowerment in the context of WPS.

- Assess the functioning and effectiveness of the Monitoring, Evaluation and Knowledge Management system, identifying and validating lessons learned, good practices and examples of innovation; and

- Provide actionable recommendations with respect to improving the project and similar programmes in the future.

The scope of this final evaluation relates to the delivery and achievement of the project Theory of Change and Results Framework indicators until the end of the project, as per the table below:

Table 1: Scope of the evaluation

| Promoting Women and Girls´ Effective Participation in Peace, Security and Recovery in Mozambique |  |
| --- | --- |
| Timing | End of program |
| Time frame | Entire programme life (2018-2022) |
| Geography | National (concentrated at central level as well as in the 17 target districts in the 7 project provinces) |
| Coverage | Whole project, and esuring analysis of linkages with other UN Women impact areas such as the elimination of violence against women and girls, women´s socioeconomic empowerment, and global norms and institutional support |
| Thematic coverage | All dimensions of the project (Ending violence against women, Socio-economic empowerment, Women, Peace and Security – see following table) |

### Theory of change or programme theory

As per the project document, the project is guided by the following theory of change:

IF a facilitating environment is created for the implementation of WPS commitments, AND

IF women participate in decision-making processes on prevention, management, and conflict resolution in an effective way, AND

IF the protection, physical and mental health and economic security of women and girls is guaranteed, their human rights respected and their specific needs in the process of peacebuilding and recovery fulfilled.

THEN

Societies will be more peaceful and fairer, because evidence shows that women are the driving forces of peace and security, and inclusive societies are more likely to be stable.

AND

Post-conflict scenarios are opportunities to link to the root causes of gender inequality barriers.

The table below resumes the project’s outcomes, outputs, and planned activites as per the original project document:

Table 2: Synthesis of project logic

| OUTCOMES | OUTPUTS | ACTIVITIES |
| --- | --- | --- |
| Women and girls’ safety, physical and mental health and security are enhanced and their human rights protected | Output 1.1: Women and girls affected by violence have access to comprehensive services to redress - including appropriate protection, health and psychosocial and legal services in resettlement and returning areas | 1.1.1: Implement the integrated and multisectorial mechanism of assistance to women and girls at risk of and survivors of violence in refugees and displaced people camps and return areas. 1.1.2: Support the operationalization of safe spaces and referral services (Centres of Integrated Assistance) for women and girls at risk or survivors of violence in the selected districts. 1.1.3: Train the MGCAS, police forces, defence forces and other sectors on Resolution 1325 and the UN Framework on WPS. |
| The socio-economic recovery of women and girls are increased in the post conflict setting | Output 2.1: Women and girls have increased access to economic opportunities in the context of recovery from conflict | 2.1.1: Organize country-level consultations with women’s organizations and government counterparts to identify suitable approach to support women’s socio-economic recovery 2.1.2: Provide livelihood and access to sustainable economic opportunities to women (professional training, entrepreneurship development, financing and extension services). |
| The enabling environment for sustainable implementation of Women, Peace and Security commitments is strengthened | Output 3.1: Women and girls’ capacity to participate meaningfully in conflict prevention/resolution strengthened Output 3.2: Capacity of the Ministry of Gender to coordinate and monitor implementation of NAP 1325 and fulfil UN reporting requirements strengthened Output 3.3: National capacity to implement and generate knowledge on WPS enhanced | 3.1.1: Awareness raising of women’s organizations on the UN normative framework on WPS 3.1.2: Support to women’s organizations to organize forums and advocacy with national and international decision-making bodies on WPS (including high-level representatives, rapporteurs, and relevant experts, wherever appropriate) 3.1.3: Address gender stereotypes and masculinity in WPS, by working with leaders, mediators, men, media 3.1.4: Organize reflections/ analyses on new threats to women's rights in Mozambique and propose preventive actions to relevant actors 3.1.5. Build the capacity of women in conflict mediation 3.1.6. Support community based women’s initiatives to promote conflict resolution 3.1.7. Organize South-South and North-South exchanges of experiences with reference countries on the implementation of the UN Res 1325 3.2.1: Conduct nationwide dissemination of the NAP 1325 and popularization of the UN Normative Framework on WPS 3.2.2: Coordinate and monitor the implementation of NAP 1325 3.2.3: Fulfil reporting obligations as per UN guidelines and participate in related platform 3.2.4: Institutional support to the MGCAS (Technical assistance, office equipment, transportation, operational costs) 3.2.5: Organize 1 annual joint monitoring field visit, annual project review of the technical advisory group and a final national project meeting 3.3.1. Sponsor post graduate training for core team of nationals from academic institutions to lead capacity building on WPS 3.3.2. Sponsor the participation of national professionals from the academia, women's organizations and security sector to short term courses on WPS 3.3.3. Facilitate partnership and organize short term training on WPS in academic institutions 3.3.4 Conduct research including project scoping study and academic debates on topics related to WPS 3.3.5: Identify, document and disseminate good practices emerging from the implementation of the project in all aspects |

## Methodology

### Evaluation criteria and elaboration of key questions

The evaluation Terms of Reference (ToR) proposed that the evaluation is carried out on the basis of five evaluation criteria established by the Development Assistance Committee of the Organisation for Economic Co-operation and Development (OECD/DAC): relevance, coherence, effectiveness, efficiency and sustainability, as well as a specific criterion on human rights and gender equality.

The following table presents a synthesis of the main guiding questions for the OECD-DAC and for the UN Women Independent Evaluation Office (IEO) as related to the six key evaluation criteria:

Table 3: Criteria and guiding questions

| Criteria | OECD-DAC guiding questions | UN Women IEO guiding questions | ToC-related questions |
| --- | --- | --- | --- |
| Relevance | Is the intervention doing the right thing? | Is UN Women contribution to the intervention relevant at national level? | To what extent has the project contributed to create a facilitating environment for the implementation of WPS commitment at the different levels and for different institutions and organizations? |
| Coherence | How well does the intervention fit? | Is the intervention aligned with international agreements and conventions on gender equality and women’s empowerment? |  |
| Effectiveness | Is the intervention achieving its objectives? | Is the intervention effective and efficient in progressing towards the achievement of gender equality and women’s empowerment results as defined in the theory of change? | Are the enhanced protection, health and psychosocial and legal services provided by government and civil society organizations adequately addressing women’s and girls’ needs for safety, physical and mental health and security? |
| Efficiency | How well are resources being used? |  | Has the project effectively contributed to the socio-economic recovery of women in contexts affected by conflict and cyclone IDAI? |
| Sustainability | Will the benefits last? | Is the intervention achieving sustained gender equality and women’s empowerment? |  |
| Human rights and gender equality | Is the intervention based on human rights principles? | How human rights approach and gender equality principles are integrated in implementation? | What is needed in order to ensure sustainability and consolidate the concrete adoption of WPS principles in post-conflict scenarios in Mozambique? |

These criteria have been declined into twentytwo key evaluation questions (KEQ), that are included in the Evaluation Matrix in section III. The Evaluation matrix is the guiding evaluation tool including:

- the definition of each KEQs against OECD/DAC evaluation criteria they are meant to respond to;

- specific subquestions to guide data collection against each KEQ,

- the relevant indicators and stakeholders that can help analysing/responding to the question as per the stakehplder mapping;

- the relevant data collection method to be adopted

- assumptions expected in terms of data collection and analysis.

### Stakeholders mapping

| Categories | Stakeholder | What (their role in the intervention) | Why (gains from involvement in the evaluation) | How (informational, reference group, management group, data collection, etc.) | When (in what stage of evaluation) | Priority (importance of involvement in evaluation process) |
| --- | --- | --- | --- | --- | --- | --- |
| Duty bearers who have decision-making authority over the intervention such as governing bodies | Representatives of Ministry of Gender, Children and Social Action (MGCAS) | Coordinate, monitor implementation of the NAP 1325 and fulfil United Nations reporting requirements. Lead the coordination and monitoring of NAP 1325 initiatives being implemented by different actors in the country. Through technical support and coordination MGCAS contributed to the active engagement of the Police, Justice and health sectors at the provincial and district level towards the establishment of the integrated services for women and girls who experience physical and sexual violence. | Their role was key for the achievement of NAP 1325 ownership and project implementation at sub-national level. They can provide insights on the implementation process and dynamics of change promoted by the project at institutional level (national and sub-national) as well as on perceived needs in terms of institutional strengthening with regards to WPS | Data collection (KIIs) | Data Collection and dissemination of evaluation report | High |
|  | Representatives of Ministry of Interior (MINT) | Coordinate, monitor implementation of the NAP 1325 and fulfil United Nations reporting requirements - focused on police and judiciary. Partners in the provision of tools and material related to gender mainstreaming within the police forces, training module for police training academies at a national level focused on the WPS Agenda, training for police forces in conflict affected areas, such as Cabo Delgado, Sofala, and Manica provinces, on how to protect the human rights of vulnerable groups and adequately serve the differentiated needs of women and girls. | Their role was key for the implementation of the NAP 1325 1325. They can provide insights on the implementation process and dynamics of change promoted by the project at institutional level (national and sub-national) as well as on perceived needs in terms of institutional strengthening with regards to WPS | Data collection (KIIs) | Data Collection and dissemination of evaluation report | High |
|  | Representatives of Ministry of National Defence (MND) | Coordinate, monitor implementation of the NAP 1325 and fulfil United Nations reporting requirements in regard to the defence sector bodies. | Their role was key as they were expected to ensure the armed forces observe an acceptable behaviour in conflict situations towards women and girls. They can provide insights on the implementation process and dynamics of change promoted by the project at institutional level (national and sub-national) as well as on perceived needs in terms of WPS mainstreaming within the armed forces. | Data collection (KIIs) | Data Collection and dissemination of evaluation report | High |
| Duty bearers who have direct responsibility for the intervention, such as programme managers and associated partners | Representatives from Provincial Directorates and District Departments of Social Action | Beneficiaries of training and equipment. Direct duty bearers in assisting the needs of SGBV survivors and potential victims. Entity responsible to coordinate the provision of integrated assistance and referral services for women and girls at risk or survivors of violence | They can provide insights on the project effectiveness in improving District capacity to assist SGBV survivors and implement the Integrated Multisectoral Mechanism in order to guarantee the physical security of women; as well reflect on remaining challanges | Data collection (KIIs and /or GIs depending on officers’ availability) | Data Collection and dissemination of evaluation report | High |
|  | Police and Defence Officials trained on gender equality and WPS agenda | Beneficiaries of trainings on the multisectoral mechanism. | They can provide insights and reflect on the relevance of the NAP 1325 to provide protection and assistance to women survivors and women at risk, and how they assess their capacity to implement the NAP 1325 after the training | Data collection (KIIs and /or GI depending on officials’ availability) | Data Collection and dissemination of evaluation report | Medium- High |
|  | Representatives from grassroot women ́s networks: GMPIS, LeMusica, Nafete, Nafeza, PROMURA, MuLeiDe | Partners in charge of reaching out and engage grassroots women in the project targeted provinces and Districts in the implementation of the WPS agenda, including through organization of solidarity feminist camps. Carry out a prevention campaign on COVID-19 and the promotion of WPS at community level. | These partners played a key role as they ensured that the project topics reached out to beneficiaries at community level, and introduced a key implementation method with the solidarity camps. They can share their view on women’s perception at local level with regards to WPS and its relevance for their lives, highlight needs and challenges, including for this kind of organizations to be able to consolidate their role at local level | Data collection (KII and GI) | Data Collection and dissemination of evaluation report | High |
|  | Representatives from Human Rights and Development Association (DHD), Council of Religions of Mozambique (COREM) | DHD and COREM received technical assistance in the conceptualization of the National Platform which seeks to create a united women’s voice on peace and security issues in Mozambique and demand women voices in the ongoing peace talks and peace agreements, as well as the post-conflict development strategies and programmes. | These partners played a key role for the implementation of Output 3, in particular with regards to the creation of a conducive environment for WPS | Data collection (KIIs) | Data Collection and dissemination of evaluation report | Medium- High |
|  | Government of Norway | Provide funding, support advocacy and partnership building | Holds strategic decision-making and support advocacy | Data collection (KIIs) | Data Collection and dissemination of evaluation report | High |
|  | Government of Iceland | Provide funding, support advocacy, resource mobilization and partnership building | Holds strategic decision-making and can support advocacy | Data collection (KIIs) | Data Collection and dissemination of evaluation report | High |
|  | UN Women | Programme formulation, Management/Monitoring and Learning, technical support to MGCAS, advocacy, partnership building and resources mobilization | Hold strategic decision-making throughout the whole project cycle. | Data collection (KIIs) | All phases | High |
|  | Representatives from target District Governments | Beneficiaries, monitoring and quality assurance of services provided in their districts. | They provide leadership and hold very strong convening power amongst the different district services involved in the project. Provide access and ability to produce change. | Data collection (KIIs or GIs) | Data Collection and dissemination of evaluation report | Medium- High |
|  | Partner organizations for the economic empowerment component: ADEL Sofala, AENA, Livaningo, NAFEZA, UN Habitat | Partners in charge of implementing the economic empowerment activities in the targeted Districts | They can provide insights on the economic empowerment activities and their coherence with the overall WPS and NAP 1325 priorities, as well as on dynamics of change that the project might have promoted | Data collection (KIIs or GIs) | Data Collection and dissemination of evaluation report | High |
|  | Representatives from United Nations University Gender Equality Studies and Training Programme (GRÓ-GEST) and | Developed and implemented a training of trainer’s course for the defence and security sector. | They played a role in the definition of knowledge products that supported the implementation of the WPS and can provide reflections on how to strategically enhance dissemination of these products | Data collection (KIIs) | Data Collection and dissemination of evaluation report | Medium- High |
| Secondary duty bearers | Representatives from Universidade Eduardo Mondlane (UEM) and Joaquim Chissano University (UJC) | UEM (CeCAGE) conducted a situational analysis on WPS, produced evidence and support capacity building on WPS related issues at national level. UJC Implemented debates and reflections on contemporary issues relating to the WPS Agenda, including on growing violent extremism and terrorism in Mozambique. Supported capacity building of personnel from Government, CSOs and women-led organizations, academic institutions, private sector and media through short-term in-depth trainings on WPS | They played a role in the definition of knowledge products that supported the implementation of the WPS and can provide reflections on how to strategically enhance dissemination of these products and capacity building on these topics | Data collection (KIIs) | Data collection and dissemination of evaluation report | Medium- High |
|  | Representatives from national and international associated partners: FES, FDC, WLSA, Muleide, ProPaz, Forum Mulher, Rede Hopem | Associated partners for consolidating and coordinating efforts in the promotion of WPS in Mozambique under the overarching umbrella of the NAP 1325. | They can provide insights on the perceptions with regards to the promotion of WPS in the country from the civil society point of view, as well as remaining challenges and proposals for way forward | Data collection (GIs) | Data collection and dissemination of evaluation report | Medium |
|  | Representatives from "Men for Women/Harmful Masculinities" initiatives | Men trained under output 3 to be engaged on the promotion of the active participation of women in conflict resolution and peace building and consolidation at the community level | They can provide reflection on their perception with regards to the relevance / impact of the training in terms of increased women’s participation | Data collection (GIs) | Data collection | Medium |
|  | Humanitarian partners who are members in the Protection and GBV Clusters in Cabo Delgado and at national level | None, but they are considered relevant for the final evaluation as the NAP 1325 could be mainstreamed in a variety of emergency response and recovery interventions in Cabo Delgado | They can provide insights on their understanding of WPS and how they are integrating or intend to integrate these issues within their interventions / planning | Data collection (GI) | Data collection and dissemination | Medium |
| Rights holders (individually or through the civil society organizations acting on their behalf) who are the intended and unintended beneficiaries of the intervention | Women and girl survivors of conflict and violence and at risk receiving psychosocial or legal support from CAIs | Direct beneficiaries of the project, particularly output 1. | They are the beneficiaries of the project. They can provide some insights/reflections on how they perceive changes in service provision | Data collection through voluntary FGDs at CAIs | Data collection | High |
|  | Women that participated in South- South, North-South solidarity WPS workshops | Direct beneficiaries of the project, particularly output 3. Produced position paper intended as advocacy tool for women ́s organizations to monitor and evaluate the implementation of national policies and plans in order to ensure that women and girls benefit and can coordinate best practices with other women leaders in other regions/countries. | They can provide reflections with regards to international best practices or gaps in the implementation of the NAP 1325, and possible follow up. | Data collection (FGDs) | Data collection and dissemination of evaluation report | Medium-high |
|  | Members of community-based women’s organizations that received training on conflict prevention, mediation and resolution provided by the project | Direct beneficiaries and aimed to consolidate National Civil Society Platform on Women, Peace and Security, a platform which seeks to create a united women ́s voice on peace and security issues in Mozambique and use this united voice to demand that the perspective of women and girls is adequately reflected in the ongoing peace talks and peace agreements, as well as the post-conflict development strategies and programmes | They can provide their perception with regards to how women’s voice is being heard, and how this has changed over the years of implementation of the project | Data collection (FGDs) | Data collection | High |
|  | Women representatives from grassroots and civil society organizations that were trained on the WPS agenda and NAP 1325, or part of consultations to establish a socioeconomic strategy | Representatives from potential direct beneficiaries of outputs 2 and 3. | They can provide some insights/reflections on how the activities to which formulation they contributed were actually reflected in the field | Data collection (FGDs) | Data collection | High |
|  | Women that received support in terms of socioeconomic empowerment | Beneficiaries of the activities focusing on enhanced access to economic opportunities | They can provide their perception with regards to the relevance of the opportunities they had access to to in terms of improving livelihoods | Data collection (FGDs) | Data collection | High |
| Rights holders (individually or through the CSOs on their behalf) who should be represented in the intervention but are not, or who are negatively affected by the intervention | Members from women organisations or other CSOs that are informed of the project but where not part of any of the activities | None | They can provide their perception with regards to the project and how they were indirectly informed about its outcomes. | KIIs | Data collection | Medium |
|  | Local leaders in targeted communities | None | They can provide their perception with regards to the project and if they changes in the way in which women engage with decision-making at community level | KIIs | Data collection | Medium |

### Indicators for measuring results

Two sets of indicators will be used to measure results: (i) the set of indicators as per the project logical framework, resumed in the table below, and (ii) the set of indicators specifically related to the evaluation questions designed by UN Women in the ToR (see Annex), that can be found in the evaluation matrix in Section III.

Table 4: Key indicators

|  | Formulation | Indicator |
| --- | --- | --- |
| Outcome | 1. Women and girls’ safety, physical and mental health and security are enhanced and their human rights protected | Proportion of women with adequate and safe access to integrated assistance services |
|  | 2. The Socio-economic recovery of women and girls are increased in the post conflict setting | Number of women and girls in need who benefited from support to access to economic opportunities |
|  | 3. The enabling environment for sustainable implementation of Women, Peace and Security commitments is strengthened | Level of compliance with UN Res 1325 reporting obligations |
| Output | 1.1 Women and girls affected by violence have access to comprehensive services to redress - including appropriate protection, health and psychosocial and legal services in resettlement and returning areas | Increased skills and knowledge in assisting victims of violence for staff of the multisectorial integrated services mechanism |
|  | 2.1: Women and girls have increased access to economic opportunities in the context of recovery from conflict | Number of women and girls in need who benefited from support to access to economic opportunities |
|  | 3.1: Women and girls’ capacity to participate meaningfully in conflict prevention/resolution strengthened | Number of women trained to engage in conflict prevention/resolution at community level |
|  | 3.2: Capacity of the Ministry of Gender to coordinate and monitor implementation of NAP 1325 and fulfil UN reporting requirements strengthened | Number of sectors which implement NAP 1325 related actions |
|  | 3.3: National capacity to implement and generate knowledge on WPS enhanced | Number of government officials directly engaged in a WPS course in an academic institution |
|  |  | Existence of a course in WPS in an academic institution |

### Evaluation design (method of data collection and analysis)

This evaluation applies a mixed methods approach, that derives insights from the different levels at which the project has been implemented and from its different beneficiaries and stakeholders. A participatory and phased approach for in-depth documentary review, consultations and data collection, and data analysis ensures triangulation of primary information for validation purposes. The three phases of the evaluation include:

##### Phase 1: In-depth documentary analysis

Relevant documents have already been received and have started to be studied during the inception phase (see Annex 1, internal documents reviewed). These include UN Women strategy documents and policies; national guiding policies, particularly the National Action Plan on Women, Peace and Security (2018-2022); project design and evidence-based documents including project document and scoping studies; project’s assessment reports and annexes, including programme implementation plans, evidence of project delivery and financial reports; partners’ reports; and knowledge products produced during the project implementation.

Most of the documentary review has been carried out during the inception phase and guided the detailed design of the evaluation. Additional documents obtained during the field visits will be reviewed as they come, including relevant academic and technical literature on the project’s main topics of relevance, and documentation will be reviewed again during the data collection phase to clarify or verify any disagreements in data collection.

##### Phase 2: Primary field data collection

This phase includes:

1) Desk-based/remote primary data collection: Key Informant semi-structured Interviews (KIIs) and Group Interviews (GIs) will be conducted remotely with:

- Project Team, donors and partners; including the collection / verification of quantifiable information on specific project result

- Partners and actors directly involved in project delivery and monitoring that can be contacted via phone and online.

2) In-field primary data collection: through the Evaluation local consultant, the evaluation team will conduct face-to-face KIIs, case studies, and FGDs with beneficiaries and stakeholders in the field. These include:

- Direct beneficiaries of the project

- Project partners and institutional stakeholder at District / Province level

- Community leaders and key local actors that are informed about the project but have not been involved directly

For this, this final  evaluation will use a non-experimental mixed-method approach, that responds to the need to engage different type of stakeholders through different qualitative tools that will allow to respond to the KEQs. Both the Stakeholder Analysis and the Evaluation Matrix include specific references to the specific tools that will be used. In summary, the tools to be used for data collection (draft data collection tools are included in Annex 2) include:

- Key Informant Interviews (KIIs) and/or Group Interviews will be used primarily for primary and secondary duty bearers, including national, provincial and district Government partners, national and international project partners and associated CSOs/local NGOs.

- Focal Group Discussions (FGDs) will be used mainly for rights holders (individually or through the civil society organizations acting on their behalf) who are the intended and unintended beneficiaries of the project. At the end of each FGD a short survey will be submitted to all of its participants in order to consolidate relevant quantitative information for sample verification of targets.

- Case studies / individual stories will be identified either during FGDs or through KIIs and GIs with partners responsible for the implementation at local level and will be collected through in-depth interviews

##### Phase 3: Data analysis and consolidation

The data analysis process, through triangulation, will provide a comprehensive picture that will enable to fully address the objectives of the Final Evaluation. It will be possible to assess the achievements–measured both through primary and secondary data – with the initial plan. It will be possible to assess if the intervention filled a clear need, to identify most successful activities and the ones that posed a challenge, to tackle the management of time and other available resources; and to identify the means to sustain the achievements in the near future while identifying possible future steps.

Quality control mechanisms will be built in through triangulation and regular feedback cycle with the UN Women team and key partners. In particular, a briefing meeting will be requested after the end of the data collection in order to ensure that any doubts are addtessed, highlight any limitations/changes and share/validate the main findings.

The related deliverable of this phase is the draft evaluation report, with the following structure:

I) Title and opening pages

II) Executive summary

III) Background and purpose of the evaluation

IV) Programme/object of evaluation description and context

V) Evaluation objectives and scope

VI) Evaluation methodology and limitations

VII) Findings against evaluation criteria

VIII) Conclusions

IX) Recommendations

X) Lessons learned

After delivery of the draft report, the Evaluation Team will organise and lead a debriefing session with the Evaluation Reference Group. The presentation will focus on presenting the main findings and recommendations and validating information. Based on any feedback provided during this presentation and corrections to the report, the Evaluation Team will consolidate changes within the draft Evaluation report and present a final version before 30 May 2022.

The evaluators team shall take measures to ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights; for example, the limitations of the sample (representativeness) should be stated clearly, and the data should be triangulated (crosschecked against other sources) to help ensure robust results. All the data collected should be gender responsive (including disaggregated by sex and age). The final evaluation report, its quality rating and the evaluation management response will be publicly disclosed in the UNW GATE system.

### Sample and sampling design

The target sampling was consolidated based on two main categories:

- Women and girls benefiting from training, services, awareness and economic opportunities offered under output 1, 2 and 3 of the project, which require a more ample and statistically significant sampling.

- Project stakeholders, including partner institutions, implementing partners, beneficiary organisations.

The following sections present the sampling methodology and a broad overview of data collection tools (see Annex II for details) for each category, as well as a table showing the methodology to be used for each target group, and how the data collection will be implemented (in presence or in remote). The consultants’ team aims to realize primary data collection in 5 out of the 7 Provinces and Provincial capitals, and in 10 out of the 18 districts where activities were implemented, as per the following table:

Table 5: Locations for primary data collection

| Province | Provincial capital | Targeted District |
| --- | --- | --- |
| Gaza | Xai-Xai | Chibuto, Chigubo |
| Inhambane | Inhambane | Mabote, Funhalouro, Panda |
| Sofala | Beira | Dondo, Chibabava |
| Tete | Tete | Moatize |
| Cabo Delgado | Pemba | Montepuez, Ancuabe |

Remaining Provinces (2) and Districts (8) will be targeted via remote tools.

#### Women beneficiaries

The sample for organization of primary data collection in the field is focused on women beneficiaries from the first three project outputs, namely:

- Women and girls affected by violence that were given access to comprehensive services - including appropriate protection, health and psychosocial and legal services in areas affected by conflict and cyclone IDAI (Output 1.1);

- Women and girls that have been given increased access to economic opportunities in the context of recovery from conflict and cyclone IDAI (Output 2.1);

- Women and girls whose capacity to participate meaningfully in conflict prevention/resolution has been strengthened (Output 3.1).

The main method to be used to collect data from the women beneficiaries will be the focus group discussions comprising primarily groups of women, up to a maximum of 10 each in each location. Particular attention will be paid in order to ensure a range of participants from different backgrounds, including ensuring presence of: women and girls (primarily between the ages of 16-55) affected by conflicts and cyclone IDAI (in the Central Provinces); women and girls that are household heads or from vulnerable households (i.e. with persons living with disabilities); women and girls with disabilities; elderly women (above 55). It is expected that

Geographical sampling was based on the following criteria, facts and assumptions:

Criteria for selecting Districts for primary data collection

- Intensity of interventions in the target Districts (see table 7);

- Different approaches to interventions depending on the Districts;

- Coverage of areas affected by conflict (currently and in the recent past)

- Coverage of the main regions of Mozambique (North, Center and South);

- Significant involvement of direct beneficiaries and stakeholders thanks to engagement with local partners.

Facts and assumptions

- The conflict has escalated in Cabo Delgado in 2021. While the situation remains extremely volatile, many actors are now starting to plan for recovery of the affected populations; collecting primary data in the Province is intended as extremely relevant for developing recommendations for potential future interventions to support women’s participation in WPS;

- In Central Mozambique, attacks have come to an end, and the DDR process has been completed. Assessing women’s beneficiaries’ perceptions with regards to their involvement in WPS in a post-conflict context is relevant for drawing lessons and sistematize good practices.

- Women and girls from Mociboa da Praia and Palma were forced to flee because of insecurity; returning has only recently started, and the two District are not considered safe for travelling.

- The other target Districts are safe to access. Field work is expected to start at the beginning of the dry season; while weather patterns have been irregular, rain is not considered a limiting factor for carrying out field work.

- During the mid-term evaluation, beneficiaries of ativities under output 2.1. on “livelihood support and facilitation of access to sustainable economic opportunities to women affected by conflict and cyclone IDAI” were not yet in a position to provide feedback on delivery- Specific attention will be therefore given to realizing FGDs with this group of right-bearers.

- As a consequence, we propose to directly visit 4 of the 7 provinces and 6 of the 17 districts targeted by the project, mainly focusing on Cabo Delgado (Montepuez and Pemba), Sofala (Beira, Dondo and Gorongosa), Tete (Moatize) and Gaza (Chibuto). The selected Districts also allow to cover areas that hadn’t been included in the mid-term evaluation.

- Provincial and District representatives of the three reminaing Provinces will be interviewed remotely.

- A similar approach to the mid-term evaluation will be adopted for FGDs with the users of CAI Safespaces and referral services, proposing FGDs organized by women support groups as ensuring the best safeguarding results.

- As a result of the above assumptions, a total of 395 to 466 will be contacted for the evaluation

- through KIIs, FGDs or surveys.

#### Project stakeholders

The sample for all other stakeholders was drawn from the stakeholder mapping exercise presented above. These broadly include:

- women trained to engage in conflict prevention/resolution at community and national levels (output 3.1)

- government representatives at central, provincial and district levels (relevant to all outputs);

- representatives of police and military forces trained under output 3;

- UN Women team, donors (embassies of Norway and Finland) and any other international stakeholders considered relevant (relevant to all outputs);

- academy and local partners, including grassroots, women’s and civil society organisations and

movements engaged in the project with different roles (relevant to all outputs).

In principle, at least one person will be interviewed for each participating institution, although at least two participants will be interviewed in institutions such as MGCAS, MINT and MDN due to their relevance to the project. Online meetings will be proposed whenever possible, including in order to save time. The consultants will pay attention to ensure that at least 50% of participants in the data collection are women. Interviews with local partners / civil society organization will preferably be realized through in presence meetings during field visits (see table above); however, online meetings are also planned in case in presence meetings are not feasible and for the Provinces / Districts not targeted by the primary collection of data. Table 6 shows a tentative sample of participants and their location to be involved from each stakeholder.

| Table 6: Data collection strategy |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Level | Stakeholder | Tools | Target | Total # | Location/Site |
| National | Representatives of MGCAS | KII - face to face or online interviews to the technical project team will be conducted | 2 persons per government agency at least | 6 | Maputo / remote |
|  | Representatives of MINT |  |  |  | Maputo / remote |
|  | Representatives of MDN/Defense officials |  |  |  | Maputo /remote |
| National | UN Women | GI - remote | Evaluation management team from the Maputo office | 4 | Maputo / remote |
| National | Representatives from Friedrich Ebert Foundation (FES), Foundation for Community Development (FDC), Human Rights and Development Association (DHD), Council of Religions of Mozambique (COREM), Women, Law and Development Association (Muleide), Institute for the Promotion of Peace in Mozambique (ProPaz) | KII or GI - online (separate) | At least 1 person per organization | 6 to 12 | Remote |
| National | National Civil Society Platform on Women, Peace and Security | GI | At least 3 persons, from organizations different from those above | 3 to 5 | Remote |
| National | Men for women engaged on the promotion of the active participation of women in conflict resolution and peace building and consolidation | FGD - online | 2 online FGD or group discussion with maximum 10 participants. | 16 to 20 | Remote |
| National | Humanitarian partners from the protection cluster | Online GI | At least 5 persons from different organizations / positions | 5 to 8 | Remote |
| National | Embassies of Norway and Finland | KII - online interview to the technical project team will be conducted | At least 1 person per embassy, key contact person | 2 | Remote |
| National | UN University Gender Equality Studies and Training Programme (UN-GEST) | KII / GI - online interview | At least 1 person per organisation, ideally 2 | 3 to 6 | Remote |
|  | Eduardo Mondlane University (UEM) |  |  |  |  |
|  | Joaquim Chissano University (UJC) |  |  |  |  |
| National | Beneficiaries of training courses provided by UJC | Online FGD with (a) women’s CSOs; (b) women from the military | 5 persons per focus group | 10 | Remote |
| Provincial | DPGCAS | KII or GI in presence in 5 Provincial capitals and online interviews with at least one of these stakeholders from remaining 2 Provinces | 1 to 2 persons in each location, if possible, ensure even split in genders. | 7 to 21 | In presence in Xai-Xai, Inhambane, Beira, Tete and Pemba; remote in Manica and Zambezia |
|  | WPS Focal Point |  |  |  |  |
|  | Comando Provincial da Polícia/ Gabinete de Atendimento a Vítimas de Violência Doméstica |  |  |  |  |
|  | Comando Provincial do Exército |  |  |  |  |
| Provincial | Sofala Association of Women Sharing Ideas (GMPIS) | GI - online or in presence group interview (separate) | 2 persons per organization | 10 | Sofala / in presence |
|  | PROMURA |  |  |  | Cabo Delgado / in presence |
|  | Follow Your Path (LeMusica) |  |  |  | Chimoio / remote |
|  | Nucleus of Women's Association of Tete (NAFETE) |  |  |  | Tete / in presence |
|  | Nucleus of Feminist Associations of Zambezia (NAFEZA)* |  |  |  | Zambezia / remote |
| Provincial | ADEL | GI - online or in presence group interview (separate) | 2 persons per organization | 8 | Sofala, in presence |
|  | AENA |  |  |  | Tete and Inhambane, in presence |
|  | Livaningo |  |  |  | Gaza, in presence |
|  | NAFEZA (see above) |  |  |  | Tete, in presence |
|  | UN-Habitat |  |  |  | Cabo Delgado, remote |
| District | District Services of Health, Women and Social Action | KII – GI In presence in 10 Districts and online interviews to at least one of these stakeholders in three of the remaining locations. Focus on those that received training from the project | 1 to 2 persons in each location, if possible, ensure even split in genders | 13 to 23 | In presence in Chibuto, Chigubo (Gaza); Mabote, Funhalouro, Panda (Inhambane); Dondo, Chibabava (Sofala); Moatize (Tete); Montepuez, Ancuabe (Cabo Delgado) + remote in at least 3 other remaining Districts |
| District | District Police Department for Victims of Violence |  |  |  |  |
| District | Women users of CAI Safe spaces and referral services | FGD In presence in 9 Districts | 8 to 10 persons per FGD | 72 to 90 | In presence in Chibuto, Chigubo (Gaza); Mabote, Funhalouro, Panda (Inhambane); Dondo, Chibabava (Sofala); Moatize (Tete); Montepuez (Cabo Delgado) |
| District | Women beneficiaries supported in financial literacy, small businesses management, vocational training and income generation activities | FGD In presence in 8 Districts | 8 to 10 persons per FGD | 64 to 80 | In presence in Chibuto, Chigubo (Gaza); Mabote, Funhalouro, Panda (Inhambane); Dondo, Chibabava (Sofala); Moatize (Tete) |
| District | Women beneficiaries of training in conflict prevention, mediation and resolution | FGD In presence in 10 Districts | 8 to 10 persons per FGD | 80 to 100 | In presence in Chibuto, Chigubo (Gaza); Mabote, Funhalouro, Panda (Inhambane); Dondo, Chibabava (Sofala); Moatize (Tete); Montepuez, Ancuabe (Cabo Delgado) |
| District | Women users of CAI, beneficiaries of income generating activities, training in conflict prevention | KII / case study / personal history | At least 2 per District | 20 to 30 | In presence in Chibuto, Chigubo (Gaza); Mabote, Funhalouro, Panda (Inhambane); Dondo, Chibabava (Sofala); Moatize (Tete); Montepuez, Ancuabe (Cabo Delgado) |
| District | Women targeted by resilient housing component | FGD in presence in one District | 10 persons | 10 | Ancuabe (Cabo Delgado) |
| District | Other local and district-level CSOs and NGOs that received training provided by the project | GI / KII – in presence in 10 Districts | At least 1 organizations per District, 2 persons per organization | 20 to 30 | In presence in Chibuto, Chigubo (Gaza); Mabote, Funhalouro, Panda (Inhambane); Dondo, Chibabava (Sofala); Moatize (Tete); Montepuez, Ancuabe (Cabo Delgado) + remote in at least 3 other remaining Districts |
| District / Province | Representatives of organisations considered by the project as affected or opposed to the project OR that are informed of the project but where not part of any of the activities | KII or GI | At least 5 (2 in presence, 3 in remote) | 5 to 10 | In presence (location tbc) and remote |
| District | Local leaders in targeted communities / Districts | KII or GI | At least 10, one per District targeted by fieldwork | 10 to 20 | Presential in Chibuto, Chigubo (Gaza); Mabote, Funhalouro, Panda (Inhambane); Dondo, Chibabava (Sofala); Moatize (Tete); Montepuez, Ancuabe (Cabo Delgado) + remote in at least 3 other remaining Districts |
|  |  |  |  | 374 to 505 |  |

### Ethical considerations and limitations

The study, including the data collection process, is grounded in the ethical research frameworks on protecting human subjects. The consultant will adhere to the UNEG Ethical Guidelines for evaluation, the UNEG Code of Conduct for Evaluation and the RESPECT Framework Monitoring and Evaluation Guidance to ensure that the rights of individuals involved in an evaluation are respected. The following aspects will be taken into specific consideration during the realization of Focus Groups with project beneficiaries at community level:

Informed Consent: Informed consent of the participants in the fullest meaning, including genuine choice, is central to the evaluation. The participants in the data collection process will be clearly communicated that they have the absolute right to refuse to participate or to answer certain questions. The informed consent form emphasizes that the decision to participate (or not) will not have any negative consequences. The informed consent forms will be in Portuguese and will be read aloud to all prospective participants. Consenting participants will sign the consent form, two copies will be made and one copy of the form will be provided to the participant.

Privacy and Confidentiality: Privacy and confidentiality are critical considerations in the ethical collection of data on individuals. The consultants’ team will ensure confidentiality of all collected data and anonymity of the participants in the focus groups. Given that most of the information will be managed online, the consultants will ensure that they are working without personally identifiable data. FGDs with women and girls’ survivors of sexual based violence who have been beneficiaries of services, will be done in smaller voluntary groups and only with women, and under the guidance of supporting local women organisations. In line with RESPECT guidelines, the evaluators:

- Never record names of CAI safe spaces beneficiaries in FGDs, and rather use unique ID codes

- When using tablets or other digital devices for data collection, ensure that tablets are password protected and all data is encrypted.

- Ensure that all data is kept in password protected files.

- Seek consent of participants before audio recording them and delete recordings after transcription.

- Take care during reporting that data is aggregated sufficiently so that no specific community or individual can be identified.

Respect and Justice: The principle of respect implies valuing humans and their lived realities. It requires recognition that their decisions exist within broader personal, relational, social, cultural, legal and environmental contexts. In FGDs, participants will be invited to talk about what they feel comfortable with. In addition, we will emphasize that those who decide to participate can choose to withdraw from the FG at any time, or refrain from answering a specific question. This will be ensured by:

- Ensuring informed participant consent is obtained, including on an ongoing basis in longitudinal evaluation or research.

- Conducting interviews in private settings.

- Presenting the objective of the evaluation to the respondents, and clarify to women users of CAI safe spaces that no question about experience or perpetration of violence are asked.

Benefits to Participants: During field work it will be emphasized that the objective is to generate evidence and knowledge with regards of the WPS project, to inform the donors about the beneficiaries’ perception with regards to the project and to provide recommendations to UNWomen for potential future initiatives.

Safety and security: the team  will strive to accommodate interview times/locations that ensure women’s participation, and to ensure that best practices and recommendations to prevent COVID-19 transmission are followed by adopting adequate measure. This is in line with UNW Pocket tool for managing evaluation during the COVID-19 pandemic: https://www.unwomen.org/en/digital-library/publications/2020/05/pocket-tool-for-managingevaluationduring-

the-covid-19-pandemic

Limitations will be further developed in the final report. At this stage, the following is to be considered:

- Geographical sample selection is affected by security concerns in certain areas of Cabo Delgado;

- No control / comparison groups are involved; however, some evidence might be drawn from reports of other cooperation partners implementing activities in the same areas;

- Availability of stekholders might be limited. For this reason, particular attention will be paid in the preparation of the interview, including by clarifying the main topics to be discussed, the number of questions and expected duration;

## Evaluation matrix

Evaluation Matrix: The evaluation matrix aims to ensure that all quantitative and qualitative data are collected consistently at all levels of implementation. The evaluation tools contains manners to grasp less tangible or quantifiable indicators such as changes in women perceptions that might be linked to the project environment, changes in the institutional culture or dynamics around gendered power relations. The evaluation matrix will also serve the purpose to review the findings and recommendations made by the mid-term evaluation of the project.

| Evaluation criteria | Key questions | Sub-questions | Indicators | Collection methods | Data source |
| --- | --- | --- | --- | --- | --- |
| Relevance | R1. To what extent was the intervention relevant to the needs and priorities as defined by beneficiaries? R2. To what extent was the intervention aligned with country priorities for gender equality and the promotion of the active participation of women in peace, security, and recovery in Mozambique, at regional and global level? R3. To which the extent the project was able to adjust to respond to emerging needs, especially in the context of the COVID crisis, violent extremism, among other emerging issues? R4. What was the level of engagement between the Partners and key Stakeholders at all levels and the ability to leverage the partnership process to inform the advocacy strategy? | Did the programme consultations with national counterparts in the formulation and implementation of the programme lead to integration of national priorities? | Alignment with scoping study; Alignment with national plan on gender equality and key strategic documents; Number of meetings with national and sub-national counterparts / partners; Perception of national and sub-national counterparts / partners with regards to their ownership of the project | Document analysis Monitoring records KII | National government website UN Women programme staff National counterparts and partners reports and documents |
| Coherence | C1. Internal coherence: were there synergies and interlinkages between the intervention and other interventions carried out by Un Women? C2. External coherence: was the intervention consistent with other actors’ interventions in the same context. Did it include complementarity, harmonisation and co-ordination with others, and the extent to which the intervention added value while avoiding duplication of effort? C3. Coherence to standards and norms: was the intervention consistent with the relevant international norms and standards to which UN Women and the government adhere? | To what extent the project overlapped / coordinated with other interventions in the field focusing on WPS and women’s economic empowerment? What kind of coordination mechanisms were put in place to avoid overlapping and enhance coordination? To what extent is the project in line with international norms and standards? | Alignment with UNWomen country strategy and coherence with country portfolio Perception of external stakeholders with regards to the WPS project; evidence of coherence and synergies with other projects Evidence of coherence with standards and norms | Document analysis Monitoring records KII | National government website UN Women programme staff National counterparts and partners reports and documents Reports and documents from external stakeholders |
| Effectiveness | E1. To what extent did the activities carried out achieve the intended outputs and contribute to intended outcomes and how did UN Women contribute towards them? Is there area for improvement? If so, how could have UN Women done differently? E2. How effective was the Monitoring & Evaluation Framework in including logical frame indicators, tools and processes used to monitor and report activities, outputs? E3. Which were potential good practices, challenges and lessons from the interventions and recommend forms to improve similar project strategies and Un Women programming? | What were the enabling and limiting factors that have contributed to the achievement of results and what actions have been taken to overcome any barriers that could have limited the progress? Was monitoring data, knowledge products and lessons learned adequately used to adjust performance and implementation? | Evidence of contribution to results as outlined in the programme/ project plan and articulated in the theory of change Evidence of effective consultation with key partners Evidence of unintended effects of UN Women (positive or negative), including on excluded/more vulnerable groups and men/boys | Document analysis (annual and donor reports, etc.) Monitoring records Interviews Case study | All key stakeholders and partners UN Women programme staff Project implementation sites Beneficiaries |
| Efficiency | Ef1. To what extent were project strategies cost-effective in making an impact on the ground, district, and provincial levels? (Analysing the budget and project expenditure over the four years period of the project) | Was the project implemented within the planned timeline? If not, what were the challenges and how the project and results were affected? Were resources redirected as needs changed? To what extent were the capacities (technical, administrative and advocacy skills) and project management structure (including of the national counterparts) adequate to deliver the project objectives and how could they be strengthened to improve impact? | Evidence of implementers use of cost efficiency mechanisms during implementation Evidence of budget reviews / amendment to respond to identified challenges / risks Evidence of strategies to mitigate delays | Document analysis (annual and donor reports, etc.) Monitoring records Interviews | UN Women programme staff Key national counterparts |
| Sustainability | S1. To what extent was capacity developed to ensure sustainability of efforts and benefits? And how beneficiaries demonstrate skills with potential for long term impact on their wellbeing? S2. To what extent have civil society organizations and women´s organizations/associations committed to promote the WPS agenda and promote peace and security for all at district level; S3. To what extent have Government Partners committed to promoting the WPS agenda at central, provincial and district level? | How would the benefits of the intervention be secured for rights holders (i.e. what accountability and oversights systems were established)? What were the contextual factors for sustaining and replicating the project interventions and its impact at national level? Are there ongoing projects focusing on WPS from other partners with which coordination will be required to maximize results and ensure sustainability? | Evidence of exit and sustainability strategy drafted and agreed with partners Evidence of unplanned by-products that can contribute to sustainability Perceptions of beneficiaries of WEE activities with regards to support received Evidence of civil society commitment to the WPS agenda (publications, social media posts, events, internal documents, etc) | Document analysis (annual and donor reports, etc.) Monitoring records Interviews Case studies FGD reports | All key stakeholders and partners UN Women programme staff Project implementation sites WEE beneficiaries |
| Gender and human rights | HR1. To what extent has gender and human rights considerations been integrated into the programme design and implementation? HR2. How has attention to/integration of gender equality and human rights concerns advanced the area of work? HR3. To which extent the project reached the most vulnerable groups considering the current context in the country (ex. People with disability, Internal displaced women, women affected by conflict and humanitarian disasters, among others). | To what extent did the processes and activities implemented during the intervention focus on promoting changes in social relations and power structures? Did the project allowed women to consolidate a stronger role in national and regional peace-building and peace and reconciliation processes? What gender equality results have been achieved, were power imbalances addressed? How power groups opposed to change were managed? | Evidence of disaggregation of beneficiaries into reports (gender, age, health and economic status, in line with Leave n one behind principles) Evidence of gender and human rights considerations in project design, implementation and knowledge products | Document analysis with focus on knowledge products Monitoring records | UN Women programme staff UNWomen and partners’ websites |
| ToC-related questions | ToC1. To what extent has the project contributed to create a facilitating environment for the implementation of WPS commitment at the different levels and for different institutions and organizations? |  | Level of compliance with UN Res 1325 reporting obligations ; Number of women trained to engage in conflict prevention/resolution at community level; Number of government official directly engaged in a WPS course in an academic institution | Document analysis (annual and donor reports, etc.) Monitoring records Interviews Case studies FGD reports | All key stakeholders and partners UN Women programme staff Project implementation sites |
|  | ToC2. Are the enhanced protection, health and psychosocial and legal services provided by government and civil society organizations adequately addressing women’s and girls’ needs for safety, physical and mental health and security? |  | Proportion of women with adequate and safe access to integrated assistance services; Increased skills and knowledge in assisting victims of violence for staff of the multisectorial integrated services mechanism | Document analysis (annual and donor reports, etc.) Monitoring records Interviews Case studies FGD reports | All key stakeholders and partners UN Women programme staff Project implementation sites CAI |
|  | ToC3. Has the project effectively contributed to the socio-economic recovery of women in contexts affected by conflict and cyclone IDAI? |  | % of resources allocated for economic empowerment at local level (such as District Funds, local financial mechanisms, public-private partnerships) which benefit women opportunities in the selected districts; % of women and girls in need who benefited from support to access to economic opportunities | Document analysis (annual and donor reports, etc.) Monitoring records Interviews Case studies FGD reports | All key stakeholders and partners UN Women programme staff Project implementation sites WEE beneficiaries |
|  | ToC4. What is needed in order to ensure sustainability and consolidate the concrete adoption of WPS principles in post-conflict scenarios in Mozambique? |  |  |  |  |

## Work plan

| Project Plan | Activity | Milestone | Deliverable | 2022 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |
|  |  |  | Weeks | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| PHASE 1: INCEPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft Inception Report with data collection tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Meeting with the evaluation reference group to discuss IR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development of tools for field work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Field research preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Inception Report based on comments from UNWomen and ERG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PHASE 2: DATA COLLECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In-depth review of project documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data collection at field level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data collection from remote |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PHASE 3: DATA ANALYSIS & WRITE UP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preliminary report providing overview of the desk review, initial findings etc. and clearly specifying the contribution of the paper |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Presentation of the preliminary report to UNWomen and ERG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Responsibilities, logistics and support

The Evaluation Team Leader (TL, Roberta Pellizzoli) will be ultimate responsible for the preparation of all deliverables outlined in the ToR. Under her technical supervision, the Local Researcher (LR, Julio Langa) will be responsible for data collection in the field (4 provinces, 8 districts) and other interviews as distributed below. Each team members will be responsible to input information into the data collection table for each of the KEQ. The Team Leader is the lead in the design of the data-collection and analysis tools and will be in charge of quality control.

The evaluation team will hold frequent meetings and be in daily contact through various means of communication to ensure that the required flow of information is shared within the team, as well as with the UN Women evaluation officer and team regularly.

| Task | TL | LR |
| --- | --- | --- |
| Inception Report |  |  |
| Initial consolidation of Evaluation Matrix, Methodological Plan, structure and Annexes of Inception report | X | X |
| Initial consolidation of Stakeholder Analysis and data collection tools |  | X |
| Quality Review of all sections | X |  |
| Documentary Data Analysis | X | X |
| Field Data Collection and input in Data Analysis Database |  | X |
| Online Data Collection |  |  |
| National Government Stakeholders | X | X |
| Provincial and District Government Stakeholders in 5 other districts and 3 remaining provinces | X | X |
| CSOs, Women organisations and any other stakeholders based in areas different to the areas where field work is based | X | X |
| Data Analysis and Draft of Final Report (specific tasks to be disaggregated later) | X | X |

Field work will require the following logistics and communication support from the UN Women Team:

- Contacts (telephone and email) for all stakeholders listed on the sampling tables;

- Communication to be sent to all stakeholders listed on the table above informing about the  evaluation (purpose, dates, participants to involved, etc.);

- Presentation letters of the fieldwork evaluation team;

- Arrangements (directly or through partners) for places where people can meet for the FGDs and  KIIs;

- Air and road transport to and from the project sites to be visited;

- Hotel and subsistence allowance for the LR while in the field, this will include purchase of masks to provide to beneficiaries and other stakeholders for KIIs/FGDs in case they don’t have them.

## Annexes

### Annex I - Internal documents reviewed

Promoting Women and Girl´s Effective Participation in Peace, Security and Recovery in Mozambique – Project proposal

National Action Plan on Women, Peace and Security (2018-2022)

Donors reports

First Progress Report to the Governments of Iceland and Norway, April 2017 – June 2018

Second Progress Report to the Governments of Iceland and Norway, July 2018 – June 2019

Third Progress Report to the Governments of Iceland and Norway, July 2019 – June 2020

UNWomen Quarterly reports 2018, 2019, 2020, 2021

Financial reports

Interim financial donor report for the period ended 31 December 2021 / Government of Norway and Government of Iceland

Knowledge products

Estudo de oportunidades para a recuperação socioeconómica de mulheres e raparigas no contexto pos-conflito;

Promoção da participação efetiva das mulheres e raparigas nos processos de paz, segurança e recuperação em Moçambique;

Declaração do acampamento solidário internacional das mulheres feministas e dos movimentos sociais sobre paz, segurança e empoderamento económico;

Women’s engagement in conflict mediation is key to achieve sustainable peace in Mozambique – WPS

Good practices in women’s organizations for the promotion of women, peace and security and socioeconomic recovery in Mozambique;

Regional Policewomen training conference (CR19) – Brief

Partners’ reports

ADEL Sofala – Primeiro relatorio de progresso

ADEL Sofala – Relatorio de progresso relative aos meses de Abril a Junho de 2021

ADEL Sofala – Segundo relatório de progresso

UN-Habitat – Mid-term report WPS

UN-Habitat – Progress report WPS

### Annex II - Draft data collection instruments

This section provides a presentation of the tools and methodologies to be used during the course of the evaluation, both in the desk research and with:

- Women beneficiaries at District level

- Institutional partners and counterparts, including academic partners

- Civil society partners

- Project staff and reference group

Data will be collected both by the team leader and the national consultant through field visits (for women beneficiaries) and meetings in presence or in remote, according to the stakeholder availability and preference.

Stakeholders Mapping (adapted from: GTZ)

Stakeholders mapping is a crucial tool to identify who has had an influence on the implementation of the project, to understand in retrospect the role they have played and to visualize the connections among the different stakeholders. Overall, the stakeholder landscape varies a lot and different actors might be crucial in certain phases or with regards to specific issues and disappear – or play a minor role - in others. Also, stakeholders that at the beginning were not considered relevant might have been involved in the project at later stages or might have played a behind-the-scenes role: indeed, this tool aims at capturing the variety of stakeholders that have been involved in the WPS project at different stages, understanding their role, strengths and weaknesses as well as identifying key partners / actors for sustainability, follow up, as well as future initiatives. The two steps presented below aim at capturing this complexity.

Step 1 - Stakeholders identification: Moving from the information collected from the project documents provided by UNWomen project team, this tool aims at reflecting with the project staff on who have been the key actors and stakeholders for the WPS project, what kind of role have they played (for example in terms of changes promoted or, on the other side, of creating obstacles / bottlenecks) and how they influenced the project thanks to their position, capabilities, knowledge, connections and scope of influence.

- Starting from the list of stakeholders mentioned above, the project staff identifies those who have been critical in the implementation of the project;

- The stakeholders identified are then positioned into the matrix below, that takes into account their (1) legitimacy, (2) resources, (3) connections, and (4) position on gender issues  and measures them as weak, medium, strong.

| Key stakeholder for WPS project | Stakeholder short description | Stakeholder position |  |  |  | Involvement in the WPS project |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Legitimacy | Resources | Connections | Gender issues | Role | Impact | Timing |
| Stakeholder 1 |  |  |  |  |  |  |  |  |
| Stakeholder 2 |  |  |  |  |  |  |  |  |
| Stakeholder 3 |  |  |  |  |  |  |  |  |
| Stakeholder … |  |  |  |  |  |  |  |  |

Step 2 - Stakeholders mapping: Moving from the stakeholders’ identification and validation in step 1, this second step aims at understanding – through a visualization - the position of each stakeholder regarding each indicator selected in the previous chapter and among each other.

This exercise is useful for:

- Having a broader understanding of how the different actors played a role with regards to the key issues at stake in the project (identified with project indicators) and of the relationships among them (including those existing before the project and those facilitated by WPS)

- Identify virtuous alliances as well as problematic relationships among stakeholders and the power relations among them

- Identify those stakeholders that played a powerful role in the realization of the project objectives

- Reveal gaps in information and areas where stakeholders’ participation has been insufficient

- Identify the critical actors for follow-up initiatives as well as the areas where more information and connections are needed

Focus Group Discussions and Key Informants Interviews

Focus Group Discussions (FGD) and Key Informants Interviews (KII) are standard qualitative tools used in evaluations. In this context, the former is used for collecting qualitative information in a short time from women beneficiaries involved in the project activities, as well as with the project team and with civil society partners (in particular when the partner is a women’s group). KII will be used with selected institutional, academic and civil society partners. Two methodologies will be adopted during FGD and KII: the Living Mirror, and the Most Significant Change, as per the following sections.

Living Mirror (adapted from CARE)

The objective of this tool, to be used during FGDs with civil society partners and project staff and KIIs with institutional partners / counterparts is to understand changes in women’s empowerment and overall knowledge about NAP 1325 through the perceptions of the stakeholders involved in the project. In this context, it is used for three groups of actors that have been involved at different levels and in different activities. The facilitator first asks to what extent the group is aware of the project (except project staff) and of its objectives and related activities, then the focus shifts on the interviewee perceptions of changes occurred among women beneficiaries.

A. General questions about the project (except for project staff):

- In general, what do you know about the project, and how have you been involved (in which role, for how long?)?

- At the beginning, what were your impressions about this initiative. Have your views changed during the implementation of the project?

- Have you been involved before in initiatives aiming at women’s empowerment and gender equality? How? What was your impression then?

- What are the drivers and obstacles for the success of initiatives such as this project, from your own perspective?

- What have been the changes (positive or negative) that the project has brought for you, if any?

  - And for the women beneficiaries?

  - In terms of access to integrated assistance services?

  - In terms of increased skills and knowledge regarding WPS?

  - Within their communities?

  - In their relationship with local institutions?

  - And for the trainees?

  - In terms of knowledge regarding WPS?

  - In terms of knowledge and capacity to assist victims of violence?

Responses may be brought back to women beneficiaries to contribute to the discussion while paying attention to avoid influencing their position, as well as discussed with the project team and reference group to reflect on the different perceptions that institutional partners and civil society partners have with regards to the project.

Most Significant Change (adapted from: CARE)

The objective of this tool is to reflect on what changes have happened over a certain period of time and to explore why these changes happened, as well as analyse implications for future interventions. In this context, it is used in FGDs and KIIs with three groups of actors (women beneficiaries at District level, institutional partners and civil society partners) - those who either have benefited directly from the project (beneficiaries at District level) or might have increased their knowledge, capacity, skills, understanding of gender-related issues (institutional partners and civil society partners) and use these to improve their practices on WPS and increase their accountability.

The “most significant change” tool implies asking one main question: “Looking back at your involvement in the WPS project, what do you think was the most significant change in terms of”, as per the following table:

| MOST SIGNIFICANT CHANGE |  |
| --- | --- |
| Looking back at your involvement in the WPS project, what do you think was the most significant change in terms of |  |
| STAKEHOLDER GROUP | CHANGE |
| Beneficiaries at District level | Access to adequate and safe integrated assistance health / GBV services Knowledge about, and access to economic opportunities Knowledge about conflict prevention and resolution at community level |
| Institutional partners (national and District level, incl. University) | Increased skills and knowledge in assisting victims of violence for staff of the multisectorial integrated services mechanism; Institutional capacity to advocate for and allocate resources for women’s economic empowerment at local level; Mainstreaming of NAP 1325 priorities across different sectors / institutions Involved government officers’ knowledge about WPS Institutional capacity to comply with UN1325 resolution Institutional capacity to implement NAP 1325 related actions |
| Civil society partners | Civil society capacity to advocate for, manage and allocate resources for women’s economic empowerment at local level; Civil society knowledge about NAP 1325 and its priorities; Mainstreaming of NAP 1325 priorities at local level through civil society action |

The participants, from their different perspectives, are requested to provide examples of concrete changes (what happened, who was involved, where and when, as well as why it can be described as a change, including a negative one) that occurred for them or that they have seen occurring. The stories of changes collected from the different groups of actors are revised by the project team with the consultants and, if appropriate, discussed during the presentation of the draft final report to collectively develop concrete recommendations and proposals for next steps.

## Consent form

The Evaluation Team and UN Women would like to thank you and appreciate the time and information you are sacrificing to participate in this important and valuable study under the Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique project.

The final evaluation will be used for accountability, learning and decision-making purposes, as well as to ensure that future planning of UN Women Mozambique is aligned to the country context and the needs of UN Women key target groups.

This research is being developed by myself, Julio Langa, and Roberta Pellizzoli, respectively local evaluation expert and lead consultant.

You can contact us on our emails: julioalanga27@yahoo.com.br and rpellizzoli@gmail.com in case of any doubt.

Please be aware that you can refuse to answer any of the below questions and stop the interview at any point. If you feel uncomfortable around any of the questions, you want me to reframe it/explain it in  any other way, please let me know and I will do. By allowing us to continue you agree with us using the information for the purposes outlined below only. Your personal data won’t be shared with any other person.

Interview date:

Location:

District:

Province:

## Tool 1. KII or GI – Government stakeholders at national, provincial and district level

Respondent Identification (Date Institution Number):

Gender: □ F □ M □ Other □ Prefer not to say	Age:	□ Below 30 □ 30-65 □ 65+

| KEQ | SPECIFIC INTERVIEW QUESTIONS |
| --- | --- |
| Gen | In general, what do you know about the project, and how have you been involved (in which role, for how long?)? |
| R | At the beginning, what were your impressions about this initiative. Have your views changed during the implementation of the project? |
| C2 | Have you been involved before in initiatives aiming at women’s empowerment and gender equality, and specifically focusing on women, peace and security issues? How? What was your impression then? How does this project differ? |
| E | What are the drivers and obstacles for the success of initiatives such as this project, from your own institutional perspective? |
| E. – Ef. | To what extent has the project contributed to create a facilitating environment for the implementation of WPS commitment at the different levels and for different institutions and organizations?* |
| Ef | Are the enhanced protection, health and psychosocial and legal services provided by government and civil society organizations adequately addressing women’s and girls’ needs for safety, physical and mental health and security?* |
| Ef.1 | Has the project effectively contributed to the socio-economic recovery of women in contexts affected by conflict and cyclone IDAI?* |
| S3 | What is needed in order to ensure sustainability and consolidate the concrete adoption of WPS principles in post-conflict scenarios in Mozambique? |
| E. – GH. | What have been the changes (positive or negative) that the project has brought for your institution? And for you? And for the beneficiaries? (Search for examples in terms of capacity, attitudes, behavior, knowledge, availability of information on WPS, power imbalances within the institution) |
| S. | What can be done to make sure that these changes are maintained / addressed? What do you feel should be done, in practice? Who are the key actors to be involved? |
| E | What has been the level of engagement/coordination between you and the UN Women project team? Has it been effective? |
| ALL | What could have been done better, more of or different? Do you have any additional information or recommendation that could be helpful planning future initiatives? |

## Tool 2. KII/ GI – CSOs, women national organizations, national/international partners, and other secondary stakeholder

Respondent Identification (Date  Institution  Number):

Gender: □ F □ M □ Other □ Prefer not to say	Age:	□ Below 30 □ 30-65 □ 65+

| KEQ | SPECIFIC INTERVIEW QUESTIONS |
| --- | --- |
| Gen | In general, what do you know about the project, and how have you been involved (in which role, for how long?)? |
| R | Have you been involved before in initiatives aiming at women’s empowerment and gender equality, and specifically focusing on women, peace and security issues? How? What was your impression then? How does this project differ? |
| E | What are the drivers and obstacles for the success of initiatives such as this project, from your own perspective and experience? |
| E-Ef. | To what extent has the project contributed to create a facilitating environment for the implementation of WPS commitment at your level of work? |
| Ef. | Are the enhanced protection, health and psychosocial and legal services provided adequately addressing women’s and girls’ needs for safety, physical and mental health and security?* How? |
| Ef.1 | Has the project effectively contributed to the socio-economic recovery of women in contexts affected by conflict and cyclone IDAI?* How? |
| S. | What is needed in order to ensure sustainability and consolidate the concrete adoption of WPS principles in post-conflict scenarios in Mozambique? What should UN Women do? And what should the government do? And what is the role of an organization like yours? |
| E-GH. | What have been the changes (positive or negative) that the project has brought for your organization? And for you? And for the beneficiaries? (Search for examples in terms of capacity, attitudes, behavior, knowledge, availability of information on WPS, power imbalances within the institution) |
| S. | What can be done to make sure that these changes are maintained / addressed? What do you feel should be done, in practice? Who are the key actors to be involved? |
| E. | What has been the level of engagement/coordination between you and the UN Women project team? Has it been effective? |
| ALL | What are you proud of in this project, and what could have been done better, more of or different? Do you have any additional information or recommendation that could be helpful for the future implementation of the project? |

## Tool 3. GI with UN Women Team

Respondent Identification (Date  Institution  Number):

Gender: □ F □ M □ Other □ Prefer not to say	Age:	□ Below 30 □ 30-65 □ 65+

| EC/KEQ | SPECIFIC INTERVIEW QUESTIONS |
| --- | --- |
| R | To what extent has the project contributed to create a facilitating environment for the implementation of WPS commitment at your level of work? |
| Ef | Are the enhanced protection, health and psychosocial and legal services provided adequately addressing women’s and girls’ needs for safety, physical and mental health and security?* Can you make examples? |
| E. Ef. | Has the project effectively contributed to the socio-economic recovery of women in contexts affected by conflict and cyclone IDAI?* Can you make some examples? |
| S. | What is needed in order to ensure sustainability and consolidate the concrete adoption of WPS principles in post-conflict scenarios in Mozambique? What should UN Women do? And what should the government do? Who do you see as the key actors, and how has this changed since the kickoff of the project? |
| E.-GH | What have been the changes (positive or negative) that the project has brought for your organization? And for you? And for the beneficiaries? (Search for examples in terms of capacity, attitudes, behavior, knowledge, availability of information on WPS, power imbalances within the institution) |
| S | What can be done to make sure that these changes are maintained / addressed? What do you feel should be done, in practice? Who are the key actors to be involved in possible future initiatives? |
| S | What is your biggest concern in terms of ensuring that the results of the Project are maintained/sustained? Is there a sustainability plan? How is being implemented, what are the main challenges? |
| E | In terms of coordination with partner organizations: What has worked well and why? Can this be replicated? What can be improved and how? |
| ALL | What are you most proud of in this project, and what could have been done better, more of or different? |

## Tool 4. FGDs questionnaires women beneficiaries at district level

Number of participants:	            Location:

| Initials | Age group | Gender | Notes |
| --- | --- | --- | --- |

| EC/KE | SPECIFIC INTERVIEW QUESTIONS |
| --- | --- |
| GEN | What kind of services, training/capacity building or activities have you benefited from? Be as specific as possible please? Who has implemented the activities you benefited from? (e.g. trainings on WPS, training on participation on peace/reconciliation trainings, workshops, roundtables, access to redress service, socioeconomic support) |
| E.- Ef- GH. | What have been the changes (positive or negative) that the project has brought for you, if any? - In terms of access to integrated assistance services? - In terms of increased skills and knowledge regarding NAP1325? - In terms of economic empowerment? - Within your community and family? - For other women you know that have been involved? Has the benefit been the same for everyone? Please explain |
| R. | Do you feel that this intervention was relevant given the needs and priorities of women and girls in your community? If yes, how? If not, why? |
| E. | How was the relationship with the organization that implemented the activities? Do you feel your voice was heard? |
| S. | How have local institutions been involved in the project? |

## Tool 5. FGDs questionnaires for participants in trainings on WPS

Number of participants:	    Location:

| Initials | Age group | Gender | Notes |
| --- | --- | --- | --- |

| EC/KE | SPECIFIC INTERVIEW QUESTIONS |
| --- | --- |
| GEN | What kind of training/capacity building have you benefited from? Be as specific as possible please? Who has implemented the activities you benefited from? |
| GEN | What do you know about the project under which these training have been realized? Have you been involved in other activities under this project? |
| E. GH. | What have been the changes (positive or negative) that the project has brought for you, if any? - In terms of increased skills and knowledge regarding NAP1325? - For your organization? - For the target group of your organization? - Can you make examples of how you have used the knowledge gained in the training? |
| R. | Do you think WPS / NAP 1325 are relevant issues in the current debate in Mozambique? Can you make examples? Who are the key actors in this debate? |
| E.-EF. | How was the relationship with the organization that implemented the training? Do you feel the training was tailored to your training needs? |

### Annex III - Terms of reference

| International Consultant on FINAL EVALUATION OF UN WOMEN PROJECT- ‘“Promoting Women and Girls´ Effective Participation in Peace, Security and Recovery in Mozambique |  |
| --- | --- |
| Location : | Maputo, MOZAMBIQUE |
| Application Deadline : | 10-Nov-21 (Midnight New York, USA) |
| Additional Category : | Gender Equality |
| Type of Contract : | Individual Contract |
| Post Level : | International Consultant |
| Languages Required : | English Portuguese |
| Starting Date : (date when the selected candidate is expected to start) | 10-Jan-2022 |
| Duration of Initial Contract : | 40 working days |

##### Background

A. UN Women´s Mandate for the Project The work of the UN Women on Women, Peace and Security (WPS) is governed by a series of commitments on the rights of women. These include United Nations Security Council (UNSC) landmark Resolution 1325 (2000) and nine successive resolutions[1] - as well as the Beijing Platform for Action (BPFA) and the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) including the CEDAW General Recommendation No. 30 on conflict prevention, conflict, and post-conflict situations. UN Women supports women’s full and equal representation and participation in all levels of peace processes and security efforts. Enhancing women’s engagement for sustainable peace requires an integrated approach that simultaneously addresses conflict prevention, resolution, and recovery, while strengthening national accountability and ensuring women’s protection from all forms of human rights violations, including sexual and gender-based violence. In order to achieve transformative change, UN Women works in the following areas: (1) increasing women’s meaningful participation in formal, and informal peace negotiations; (2) promoting women’s participation in peacebuilding and recovery planning, women’s economic empowerment within recovery efforts, and the establishment of gender responsive post-conflict institutions; (3) increasing women’s participation and safety in peacekeeping; (3) ending impunity conflict-related sexual and gender-based violence; (4) promoting a gender-sensitive approach to preventing and countering violent extremism; and (5) creating an enabling environment for the implementation of national commitments to women, peace and security (including the implementation of National Action Plans on WPS). In addition, UN Women promotes research initiatives, data collection, learning exchanges, and documentation of good practices on women, peace, and security to inform policy and programming. The actions of UN Women in Mozambique are aligned with two strategic objectives: 1) Consolidate national unity, peace and sovereignty and 2) Develop human and social capital in accordance with the government´s Five Year Plan and the National Plan for the Advancement of Women. The project being implemented contributes to the implementation of the National Action Plan for the Advancement of Women and the National Action Plan on Women, Peace and Security (2018-2022) (NAP 1325), which was created with the support of UN Women. The project is part of the larger UN Women Programme on Women, Peace and Security and is being implemented within the framework of the Mozambique UNDAF 2017-2021 (United Nation Development Assistance Framework) and it is also expected to contribute towards the achievement of the Agenda 2030 for Sustainable Development and Agenda 2063: The Africa We Want. B. Context in Mozambique Following the 1992 Peace Accords between the government of Mozambique and the former rebel movement RENAMO, Mozambique enjoyed nearly 20 years of relative peace and stability. This allowed for significant democratic advances in the country, including gender equality and women's empowerment. Since the ratification of the CEDAW in 1997 and the adoption of Beijing Declaration and Platform for Action as well as the gender equality as a constitutional principle, Mozambique has made significant progress at political, legal and institutional level. The main milestones include the adoption of a Gender National Policy and its Implementation Strategy, the National Plan for the Advancement of Women, a Law on Domestic Violence Against Women (29/2009), the National Council for Women's Advancement, represented at both provincial and district level, the adoption and implementation of an integrated multi-sectoral approach to assist victims of violence against women, National Action Plan on Women Peace and Security, and the approval of the Law to Prevent and Combat Premature Unions (19/2019). Women's participation in politics has increased over time. Mozambique has had six general elections (1994, 1999, 2004, 2009, 2014 and 2019) and five municipal elections (1998, 2003, 2008, 2013, 2018, and the mid-term elections of Nampula in 2017). Presidential, legislative, and assembly elections for provincial councils took place in October 2019. As a result of the general election in 2019 elections, women make 41.2 per cent of MPs (103 out of 250) and at local level as a result of the 2018 elections there are 6 presidents’ women out of 53 presidents of municipal councils (11.3%), and 8 are represented as Presidents of the Municipal Assemblies (15,1%). The Speaker of Parliament has been a woman in the last 3 elections (2009, 2014, 2019). At national level, women’s participation over all sectors of government reached 32.4% in 2016. [2] However, progress has not been enough to challenge deeply rooted sociocultural norms such as discrimination against women, lack of education especially in rural areas, limited participation in public spaces. The political situation remains fragile with demobilization and reintegration of former rebel armed forces following cease fire between the Government and the National Mozambican Resistance (RENAMO) reached in March 2018 and part of the recently definitive peace agreement and comprehensive Peace and Reconciliation Agreement by the Government and RENAMO in August 2019. However, since 2017, the province of Cabo Delgado (in north of Mozambique-one of the provinces with a growing extractive industry) has suffered attacks perpetrated by armed group said to be linked to extremist religious groups, resulting in social instability. Although there is at times the appearance of stability, there is high probability that these attacks and violent extremism will persist, given the fact that the purpose and provenience of these group is still rather unexplained, and they remain active in the northern region of Mozambique. Given that the country currently faces an immensely sensitive political, economic, and humanitarian situation, this scenario is likely to further undermine the prospects of achievement of gender equality by 2030. While political-military tensions as well as the increasing violent extremism in the northern region threaten the already precarious peace and security of women and girls in Mozambique. In addition, other factors, such as macroeconomic instability, health crises (including COVID-19, HIV/AIDS, Tuberculosis, etc), natural disasters and the emergence of conflicts, further threatens the peace and security of women. Women continue to suffer physical and psychological harm from both armed and other conflicts, economic exclusion, environmental degradation, and masculinised politics and militarism, which have only compounded gendered insecurity. These harms are generally not accompanied by a reparation process that includes the provision of opportunities for social, phycological and economic recovery after the conflict.

##### Duties and Responsibilities

The project rationale stems from the need to promote the active and full participation of women and girls in peace, security and recovery processes in Mozambique at all levels. To respond to challenges faced in the promotion of gender equality in peace and security processes at all levels in Mozambique, since 2016 the Government of Mozambique, through the Ministry of Gender, Children and Social Action and with the support of UN Women, began the formulation of the National Action Plan on Women, Peace and Security for the national implementation of UN Security Council Resolution 1325 and the related resolutions. In May 2018, the Government of Mozambique approved the National Action Plan on Women, Peace and Security (2018-2022) (NAP 1325) which seeks to promote women´s and girls´ human rights in armed conflict and post-conflict contexts. To support the operationalization of the NAP 1325, UN Women in partnership with MGCAS and support of the Governments of Iceland and the Kingdom of Norway, is implementing a project denominated: “Promoting Women and Girl’s effective participation in peace, security and recovery in Mozambique.” The project focuses on: - Enhancing security for women and providing integrated multi-sectorial response services to victims of violence; - Promoting and facilitating the socioeconomic recovery of women; - Strengthening women’s capacity and women’s organizations to participate in conflict prevention and resolution, in particular at community level; - Strengthening national capacity to coordinate, monitor and account for the implementation of global commitments on women, peace and security. With a duration of four years, it started in December 2017 and will end in December 2021, the project is currently being implemented in 17 districts located in 7 provinces of the country (please refer to the graphic below for specifications) with a total budget of approximately 4.5 million dollars funded by the Governments of Norway and Iceland. It is important to note that the project duration has been extended (non-cost extension agreement) by one year from December 2020 to December 2021. Its direct beneficiaries are women and local government authorities. And at national level, building the capacity of government institutions to implement the UNSCR 1325. The project is guided by the following theory of change: 1) if a facilitating environment is created for the implementation of WPS commitments, 2) if women participate in decision-making processes on prevention, management, and conflict resolution in an effective way, and 3) if the protection, physical and mental health and economic security of women and girls is guaranteed, their human rights respected and their specific needs in the process of peacebuilding and recovery fulfilled. Then, societies will be more peaceful and fairer, because evidence shows that women are the driving forces of peace and security, and inclusive societies are more likely to be stable. Furthermore, post-conflict scenarios are opportunities to link to the root causes of gender inequality barriers. The expected results of the project are the following: - Outcome 1: Women and girls’ safety, physical and mental health and security are enhanced, and their human rights protected - Output 1.1: Women and girls affected by violence have access to comprehensive services to redress - including appropriate protection, health and psychosocial and legal services in resettlement, returning areas and in disaster affected areas - Outcome 2: The socio-economic recovery of women and girls is increased in the post conflict setting - Output 2.1: Women and girls have increased access to economic opportunities in the context of recovery from conflict and cyclone IDAI - Outcome 3: The enabling environment for sustainable implementation of WPS commitments is strengthened - Output 3.1: Women and girls’ capacity to participate meaningfully in conflict prevention/resolution strengthened - Output 3.2: Capacity of the Ministry of Gender to coordinate and monitor implementation of NAP 1325 and fulfil UN reporting requirements strengthened - Output 3.3: National capacity to implement and generate knowledge on WPS enhanced The project counts with the following Key stakeholders: Ministry of Gender, Children and Social Action; the Governments of Iceland and the Kingdom of Norway (donors), Ministry of Interior, Ministry of National Defence, Civil Society organizations, especially women-led organizations/associations, the provincial governments and the governments of the target districts. And the project Advisory Group aiming at providing technical advice to the project implementation, including oversight of overall project The project management structure is composed of: - a programme specialist (part-time), based in Maputo, who is responsible for the overall supervision of all programmatic management, partnership building and staff management in the project; - a Programme Officer, based in Maputo, who is responsible for the overall project and financial management and technical support in the project; - a Project Officer, based in Ministry of Gender, Children and Social Action, responsible for providing technical support to the Ministry of Gender, Children and Social Action in created WPS unit, as well as responsible for the project coordination and implementation with local government partners at provincial and district levels. Purpose (and use of the evaluation) The final, end-of-programme evaluation will serve to evaluate the design, implementation, management, and outcomes of the WPS project to identify lessons, good practices that can improve future such initiatives managed by the UN Women Country Office, including accountability, learning and decision-making purposes. Moreover, the evaluation is expected to provide forward-looking and actionable recommendations, based on previous work conducted and the current positioning of UN Women in this area. The intended end users of this evaluation are UN Women project management, UN Women country office and regional senior management; the donors of the project, other donors interested in UN Women’s portfolio, UN Women’s main partners (including the national government and the provincial governments); other stakeholders engaged stakeholders engaged in promotion of WPS agenda, in and out of Mozambique. Aligned with United Nations Evaluation Group (UNEG) Norms and Standards, this evaluation will have an explicit focus on utility. The evaluation will be shared with key stakeholders, donors, and partners. In line with UN Women Evaluation Policy a management response will be prepared for this evaluation as practical means to enhance the use of evaluation findings and follow-up to the evaluation recommendations. The management response will identify who is responsible, what are the action points and the deadlines. It will be posted on the online UNW ‘Global Accountability and Tracking of Evaluation Use (GATE) System’ at http://gate.unwomen.org/. IV. Objectives (evaluation criteria and key questions) Considering the mandates to incorporate human rights and gender equality in all UN work and the UN Women Evaluation Policy, which promotes the integration of women’s rights and gender equality principles, these dimensions will have a special attention in this evaluation. A specific evaluation objective on human rights and gender equality is included as well as considered under each evaluation criterion. The overall objectives of this evaluation are to: - Analyse how human rights approach and gender equality principles are integrated in the interventions; - Assess Coherence (internal and external) of the project on how well the intervention fit and its compatibility with others in the CO and Country in general. - Assess the relevance of the project at national level including alignment with international agreements and conventions on WPS and other gender equality and women’s empowerment - Assess the effectiveness in achieving expected results, including the effectiveness of programming strategies in implementing global commitments within national priorities for in working toward to achieve expected results, with a special focus on innovative, scalable and replicable interventions. The evaluation should also investigate the contextual factors that are enabling or restricting the achievement of results; - Assess the organizational efficiency of the project, in terms of financial management and human resource investments; - Assess the initial impact of the intervention on the lives of beneficiaries, communities, and institutions involved in the project; - Assess the potential sustainability of the interventions in achieving gender equality and women’s empowerment in the context of WPS. - Assess the functioning and effectiveness of the Monitoring, Evaluation and Knowledge Management system, identifying and validating lessons learned, good practices and examples of innovation; and - Provide actionable recommendations with respect to improving the project and similar programmes in the future. Key Evaluation Questions The evaluation will address the following OECD-DAC[1] evaluation criteria, namely: Relevance, Coherence, Effectiveness, Efficiency, Impact and Sustainability. A specific criterion on Human rights and gender equality will also be assessed. The evaluation will not consider impact (as defined by UNEG) as it is considered too premature to assess this. The evaluation will also, to the extent possible, analyse Value for Money (VFM) and good use of resources by establishing a link between the use of funding and the performance and results of the country office. The evaluation will seek to answer the following key evaluation questions and sub-questions: Relevance - To what extent was the intervention relevant to the needs and priorities as defined by beneficiaries? - To what extent was the intervention aligned with country priorities for gender equality and the promotion of the active participation of women in peace, security, and recovery in Mozambique, at regional and global level? - At the extent to which the project was able to adjust to respond to emerging needs, especially in the context of the COVID crisis, violent extremism, among other emerging issues. - What was the level of engagement between the Partners and key Stakeholders at all levels and the ability to leverage the partnership process to inform the advocacy strategy? Coherence - Internal coherence: were there synergies and interlinkages between the intervention and other interventions carried out by Un Women and other institutions, such as the government, as well as the consistency of the intervention with the relevant international norms and standards to which UN Women and the government adheres? - External coherence: was the intervention consistent with other actors’ interventions in the same context. Did it include complementarity, harmonisation and co-ordination with others, and the extent to which the intervention added value while avoiding duplication of effort. Effectiveness - To what extent do the activities carried out achieved the intended outputs and contributed to achieved outcomes and how did UN Women contribute towards them? Is there area for improvement? If so, how could have UN Women done differently? - What were the enabling and limiting factors that have contributed to the achievement of results and what actions would have been taken to overcome any barriers that could have limited the progress? - How was Monitoring & Evaluation Framework including logical frame indicators, tools and processes used to monitor and report activities, outputs? - Was monitoring data, knowledge products and lessons learned adequately used to adjust performance and implementation? - Which were potential good practices, challenges and lessons from the interventions and recommend forms to improve similar project strategies and Un Women programming? Efficiency - To what extent were project strategies cost-effective in making an impact on the ground, district, and provincial levels? (Analysing the budget and project expenditure over the four years period of the project) - Was the project implemented within the planned timeline? If not, what were the challenges and how the project and results were affected? - To what extent were the capacities (technical, administrative and advocacy skills) and project management structure adequate to deliver the project objectives and how could they be strengthened to improve impact? Sustainability - To what extent was capacity developed to ensure sustainability of efforts and benefits? And how beneficiaries demonstrate skills with potential for long term impact on their wellbeing? - How would the benefits of the intervention be secured for rights holders (i.e. what accountability and oversights systems were established)? - What were the contextual factors for sustaining and replicating the project interventions and its impact at national level; - To what extent have civil society organizations and women´s organizations/associations committed to promote the WPS agenda and promote peace and security for all at district level; - To what extent have Government Partners committed to promoting the WPS agenda at central, provincial and district level? Human Rights approach and Gender Equality principles - To what extent has gender and human rights considerations been integrated into the programme design and implementation? - How has attention to/integration of gender equality and human rights concerns advanced the area of work? - To which extent the project reached the most vulnerable groups considering the current context in the country (ex. People with disability, Internal displaced women, women affected by conflict and humanitarian disasters, among others). Scope of the evaluation The scope of the evaluation is national (concentrated at central level as well as in the 17 target districts in the 7 project provinces) and will include all dimensions of the project. The evaluation will cover the entire project implementation from 2018 to 2021. In effort to identify and assess WPS linkages with other thematic areas, the evaluation scope includes also other UN Women impact areas such as the elimination of violence against women and girls, women´s socioeconomic empowerment, and global norms and institutional support. The evaluation will also review the findings and recommendations made by the mid-term evaluation of the project. VI. Evaluation design (process and methods) The evaluation will be carried following UN Evaluation Group (UNEG) Norms and Standards (see http://www.unwomen.org/about-us/accountability/evaluation/ ), UN Women Evaluation Policy as well as the Ethical Guidelines for evaluations in the UN system, see Annex to this TOR. Once finalized the evaluation report will be quality-assessed based on the UN Women Global Evaluation Reports Assessment and Analysis System (GERAAS). GERAAS standards and GERAAS rating matrix are available in the annexes. The formative and summative evaluation will be based on the explicit theory of change already formulated by stakeholders at the beginning of the programme. It will test its validity against the evidence collected so far regarding key programme results. It is also important to mention that both qualitative and quantitative methods are expected to be utilised. The evaluation process is expected to be transparent and involve various stakeholders and partners. The evaluation type will be non-experimental, and follow these phases, being phase 1 and 4 under UN Women direct responsibility: - Preparation: This includes the stakeholder analysis and establishment of the reference group, development of the ToR, and recruitment of the evaluation team. - Conduct: Inception report, stakeholder workshop, data collection and analysis. - Reporting: Presentation of preliminary findings, draft and final reports. - Use and follow up: Management response, dissemination of the report, and follow up on how to positively shape future programme design. Methodology The evaluation methodology will be developed by the Evaluation Consultants and presented to the Evaluation Reference Group and approval of the evaluation management team. The methodology should use a combination of quantitative and qualitative research methods that are appropriate to address the main evaluation questions and account for complexity of gender relations and to ensure participatory and inclusive processes that are culturally appropriate. These methods should be responsive to human rights and gender equality principles and facilitate the engagement of key stakeholders. Measures will be taken to ensure the quality, reliability, and validity of data. Limitations with respect to the sample (representativeness) should be stated clearly. Primary data collection could be undertaken through observations, site visit, individual key informant interviews and focal group discussions with representatives of relevant government institutions (duty bearers), development partners, beneficiaries (right holders) and key community players seeking to address gender equality and human rights issues. Data collection and analysis methods such as appreciative inquiry, most significant change, case study, survey could also be implemented. The evaluator will develop a sampling frame (area and population represented, rationale for selection, mechanics of selection, and limitations of the sample) and specify how it will address the diversity of stakeholders in the intervention. However, given the current COVID-19 context and the increase in insecurity and violence context, there may be some restrictions in the collection of primary data in the field as well as observation which can cause some methodological limitations. To mitigate this risk, remote data collection may be adopted. The evaluator should take measures to ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights; for example, the limitations of the sample (representativeness) should be stated clearly, and the data should be triangulated (cross-checked against other sources) to help ensure robust results. All the data collected should be gender-responsive (including disaggregated by sex and age). The evaluator should also consider other recent evaluations conducted in the CO, such as the WPS MTE and the Country Portfolio Evaluation covering the period of 2017-2021. Stakeholder participation The Evaluators will collaborate with the CO evaluation manager to convene and coordinate meetings with the Evaluation Reference Group (ERG). Ideally, the ERG will include the members of the Advisory Group: The Ministry of Gender, Children and Social Action; the Governments of Iceland and Norway; sister UN agencies, local governments, and civil society organizations (specially women-led organizations/associations/groups). They will be playing liaison, technical advisory, and quality assurance roles, including the validation and dissemination of results. In this sense, rural women and their associations are key rights holders — their views, challenges and progress need to be highly reflected in the process and results of this evaluation.

### Annex IV - Evaluation management and reference group members

The Evaluation is commissioned by UN Women Mozambique Country Office. The Consultants will report to the Country Representative and will benefit from technical support of the UN Women Programme Specialist, UN Women Programme Officer (Women, Peace and Security), and UN Women M&E Officer (who will be the main liaison person), and from the Regional Evaluation Specialist based in the UN Women Regional Office in Kenya. The evaluation team will also benefit of support from the Evaluation management group and reference group established by the CO with specific ToRs highlighting their responsibilities and role during the evaluation.

The members of the evaluation management group include:

- Country Representative

- UN Women Programme Specialist

- UN Women Programme Officer (Women, Peace and Security)

- UN Women M&E Officer (main liaison person)

- Regional Evaluation Specialist based in the UN Women Regional Office in Kenya

The members of the reference group include:

| # | Organization | Relation with the Project | Member | Position | Contact/Email |
| --- | --- | --- | --- | --- | --- |
| 1 | Ministry of Health | Government | Felisbela Gaspar | Advisor to the Minister for Gender | gfelisbela1963@gmail.com |
| 2 | Ministry of Gender, Children and Social Action | Partner | Sansão Buque | Deputy Gender Director | kiyabuque@yahoo.com.br |
| 3 | Joaquim Chissano University | Responsible Partner/ Academia | Egna Sidumo | Researcher Center for International Strategic Studies | esidumo@gmail.com |
| 4 | Sócio Cultural Horizonte Azul Association | CSO | Dalila Macuacua | Executive Director | dalilamacuacua@yahoo.com.br |
| 5 | Center of Coordination of Gender Issues (CeCAGe) | Academia | Gracinda Mataveia | Director of Center of Coordination of Gender Issues | uemcecage@gmail.com |
| 6 | SWEDEN Embassy | Corporate Development Partner | Pia Oste | Program Specialist - Democracy, Human Rights and Gender Equality | pia.oste@gov.se |
| 7 | REDE HOPEM | Implementing Partner | Jorge Cuinhane | HOPEM National Coordinator | jorgecuinhane@hotmail.com |
| 8 | PROPAZ | CSO | Jacinta Jorge | Executive Director | jacintajorge.59@gmail.com |
| 9 | ICELAND Government (Donor) | Project Donor | Pétur Waldorff | Deputy Permanent Representative | petur.skulason@utn.is |
| 10 | Norway | Project Donor | Denise Wetela | Gender Adviser | Denise.Cuamba.Wetela@mfa.no |
| 11 | JUSTA PAZ | CSO | Telma Tonela | Executive Director | ttonela20@justapaz.org.mz |
| 12 | FORUM MULHER | CSO | Nzira de Deus | Executive Director | nzira.deus@gmail.com |
| 13 | Women's Group for the Sharing of Ideas in Sofala - GMPS | Implementing Partner | Jessica Salomão | Project Official | jessicasalomao2014@gmail.com |

Roles and responsibilities of different groups engaged in the evaluation:

| Team | Responsibilities |
| --- | --- |
| Management Evaluation Group | • Participate in any meetings of the management group • Approve the consultant/firm selected to conduct the evaluation • Participation in any inception meeting/s and quality assure the evaluation inception report • Facilitate access to information by the evaluation team • Review and quality assure the draft evaluation report • Disseminate and promote the use of the evaluation findings and recommendations. |
| Evaluation Reference group | • Facilitating the participation of the key stakeholders in the evaluation design, defining the objectives, the evaluation scope and the different information needs. • Providing input on the evaluation products: a) ToR, which defines the nature and scope of the evaluation; b) inception report, which defines the approach and methodology of the evaluation team; c) preliminary findings, which identify the key findings from preliminary analysis; and d) draft and final reports, to identify factual accuracy, errors of interpretation or omission of information. • Providing relevant information (i.e., via surveys, interviews, etc.) and documentation to the evaluation team. • Disseminating evaluation results. • Implementing evaluation recommendations as appropriate. |

The Security Council adopted resolution (S/RES/1325)resolution (S/RES/1325)resolution (S/RES/1325) on women and peace and security on 31 October 2000. The resolution reaffirms the important role of women in the prevention and resolution of conflicts, peace negotiations, peace-building, peacekeeping, humanitarian response and in post-conflict reconstruction and stresses the importance of their equal participation and full involvement in all efforts for the maintenance and promotion of peace and security.

https://tbinternet.ohchr.org/_layouts/15/TreatyBodyExternal/Treaty.aspx?CountryID=118&Lang=EN

https://data.ipu.org/content/mozambique?chamber_id=13469

http://forumulher.org.mz/wp-content/uploads/2018/09/POLITICA-DE-GENERO-e-Estrategia-Implementacao-APROVADA-CM-11.09.2018ooo.pdf

The UN Women project was drafted in this period, and formally released in October 2017.

https://maputoaccord.org/en/resources/

https://dtm.iom.int/mozambique

Source: Humanitarian Needs Overview 2022.

D’Odorico G, Hossain M, Jamal E, Scarpassa do Prado D, Roberts C, Palmer J (2021). The gender-based violence (GBV) situation and response in Cabo Delgado, Mozambique: A rapid assessment. UK: London School of Hygiene & Tropical Medicine. Mozambique: United Nations Refugee Agency.

https://climateknowledgeportal.worldbank.org/country/mozambique/vulnerability and https://thinkhazard.org/en/report/170-mozambique

https://www.unwomen.org/en/digital-library/publications/2020/04/policy-brief-the-impact-of-covid-19-on-women

KII: Key informant interview

GI: Group Interview

FGD: Focus Group Discussion

The consultant will engage with key decision makers and stakeholders within the partner and targeted institutions and organizations to understand the perception of these actors with relation to the project, as well as to assess future areas of intervention based on needs. Based on detailed stakeholder mapping exercise (using the stakeholder analysis template), further stakeholders from relevant fields of research, civil society, government, international organization will also be mapped and interviewed as key-informants. KII will be realized in order to specifically assess (i) the relevance of the initiative, (ii) its sustainability in the framework of similar ongoing interventions, and (iii) to provide actionable recommendations for follow up.

Identification of FG participants will require an extended dialogue with the Evaluation Reference Group to define the stratification criteria that will allow a proper coverage of the different typologies of beneficiaries and of the different targeted areas; nevertheless, a preliminary sample proposal is presented in the following section. Focus groups are aimed at engaging with women beneficiaries to assess their perceptions with regards to the project, using methods such as the “most significant change.” In selected districts, women’s associations that have been targeted by the project will serve as reference for the development of ad hoc case studies.

The number of 10 participants per FGD is intended to ensure fruitful participation in the discussion as well to mitigate possible risks associated to COVID-19, though at the time of submission of this report most restrictions have been eased. It is proposed that the local evaluator should have some spare masks to distribute to those participants who may not have any.

https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2020/RESPECT-implementation-guide-Monitoring-and-evaluation-guidance-en.pdf

http://www.fsnnetwork.org/sites/default/files/en-svmp-instrumente-akteuersanalyse.pdf

The term “stakeholder” cam be used with different meanings. Here it includes target groups (the beneficiaries of the WPS project), local and national institutional actors, researchers, development partners, civil society organizations, influential individuals.

Legitimacy has to do with their institutional position in relation to the project or their ascribed role in the project. The key question is: Does the stakeholder hold an influential institutional position with strong legitimacy?

Resources include knowledge, expertise and capabilities as well as material resources. The key question is: Did the stakeholder dispose of specific material and immaterial resources that allowed him to influence the project?

Connections are the key relationships that each actor has with other stakeholders or with other actors (limited to the scope of intervention of WPS project). The question is: Is the stakeholder well interconnected with other influential actors?

This dimension aims at clarifying the stakeholder’ position on gender issues: what is the experience that the stakeholder has in promoting GEWE? What is its strategy? Are there specific connections that the stakeholders have developed in this dimension? In case it is neutral or opposed to the promotion of GEWE, how has this impacted on WPS? Have there been relevant changes in its position during the project implementation?

Types of involvement include information, consultation, involvement in decision-making, as coordination partner, as cooperation partner, as beneficiary, etc. This section also aims at capturing for how long the stakeholder has been involved in the project.

http://gendertoolkit.care.org/Pages/living%20mirror.aspx

http://gendertoolkit.care.org/Pages/Most%20significant%20change.aspx