“Promoting Resilience, Self-Reliance And Social Cohesion Among Displaced Populations And Host Communities With Focus On Women And Girls In South Sudan and Mali”

January 2016 – June 2020

Final Evaluation

Final Report

Dirk Hansohm

Johnny Okeny

12 June 2022

Executive summary

This is a report on the final, independent, evaluation of a UN Women (UNW) project, financed by the Federal Republic of Germany, executed in May 2022. The report only covers South Sudan. After the background and basic information on the project, the third section, the second section presents the evaluation approach and methodology. The main section reports on the findings of the evaluation, structured by evaluation criteria and evaluation question. The final section presents lessons and recommendations.

South Sudan, independent in 2022, faces stark development problems due to its geographical land-locked location, history, climate, difficult business environment, weak governance, fragility and conflict. Women are on the lower rungs of the social hierarchy ladder than men and have fewer resilience assets and rely more on natural resources, but the conflict redefines gender roles.

In order to be useful and relevant, the evaluation takes account of the country context and regional and local situation. The application of best practices from elsewhere is only useful if and when adapted to the concrete country context.

With a budget of €3 million, sponsored by the Government of Germany, UN Women (UNW) implemented the project “Promoting Resilience, Self-Reliance And Social Cohesion Among Displaced Populations And Host Communities With Focus On Women And Girls In South Sudan and Mali” over the period January 2016 – June 2020. Overall objective of the project was to promote self-reliance and social cohesion for internal displaced persons (IDPs) and their host communities, with a focus on areas of South Sudan and Mali affected by the ongoing conflicts. The two strategic outcomes were to improve access to sustainable livelihood and income generation opportunities for women and girls among IDPs and host communities, and to alleviate the risk of sexual and gender-based violence among IDPs and host communities.

The project was implemented using four key strategies: providing vocational and income generation skills along with literacy and numeracy, providing access to productive resources, raising awareness and education about the rights of women and girls against GBV and allowing GBV survivors to access multi-sectoral services, and identifying and training GBV community activists.

The project was implemented by six implementing partners in Juba, Rumbek, Mundri, Nimule, Awerial-Mingkaman, and Yambio.

The main purpose of this evaluation is to assess the achievement of project results and performance of the above-described intervention. Field research was carried out in South Sudan over a period of 15 working days, in Juba and in the selected implementation locations.

Findings of the evaluation are to inform UNW South Sudan’s future work in humanitarian and resilience response, especially on women’s economic empowerment (WEE), ending violence against women and girls (EVAW).

The evaluation objectives are addressed in the 18 evaluation questions in the evaluation matrix (see Appendix).

The Evaluation addresses five criteria:

- Design and implementation of the project

- Relevance

- Effectiveness

- Efficiency

- Sustainability

The definition of the criteria is informed by the OECD/DAC evaluation criteria definitions. Also important are gender equality and human rights. This dimension is mainstreamed – its different dimensions are assessed under the five evaluation criteria. This has been regarded as more useful than adding a separate criteria of gender equality.

On the basis of this, the report provides the lessons learned, best practices, success stories and challenges. The evaluation identifies challenges and gaps in the implementation of the project for future improvement.

This evaluation covers the full implementation period of January 2016 – June 2020. The evaluation methodology is mixed: Quantitative and qualitative research methods and analytical approaches are combined. Data from different sources are combined and cross-checked (triangulated). The evaluation was participatory, including beneficiaries, implementing agencies, cooperating government agencies, and the funder.

In the given time frame, it was not possible to undertake a truly representative evaluation. Instead, an evaluation could be done that gives a good coverage of the regional differences, including all the strategies, and including a wide range of stakeholders.

In addition to Juba, two other implementation areas were visited: Rumbek and Yambio. These were selected according to reachability, representing different geographical areas, implementation of all the four strategies, and presence of IDPs and host communities. On this basis, Rumbek, Juba, and Yambio have been selected.

The examination of the design and project implementation evaluation criterion finds logical key links between the overall objective, outcomes and outputs. However, there was limited context analysis, while assumptions and risks were not spelled out. The absence of an overall baseline study and few needs assessments qualified the quality of the analysis and base-line data. Further, reports on implementation and monitoring were incomplete. The results framework is SMART (specific, measurable, achievable, relevant, and time-bound), as well as clear and logical. However, because of a lack of quantified targets for most outputs there are deficits in specificity and measurability.

The evaluation of the relevance evaluation criterion finds that the objectives and design responded to the needs of the target groups. The project was also aligned to national structures, plans and programmes. Further, it was also well aligned with South Sudan’s international obligations, including on those on WEE and EVAW. The project was also consistent with the country’s specific situation, taking account of conflict, vulnerabilities, gender aspects, and weak governance. Ownership by stakeholders was very high. The beneficiaries committed to the project and its activities. Local community leaders were strongly involved. There were also signs of ownership by local government, even though limited by their low capacities.

Effectiveness is mainly defined by the progress achieved towards the project objectives and expected results. 67.4% of those trained started small businesses (compared to a target of 70%). The target of women gaining training was highly overachieved (136%), like the target on beneficiaries gaining access to productive resources (118%). The targets on GBV awareness raising was also highly exceeded. More community activists were engaged than planned (30%).

The criterion efficiency is mainly concerned with the economic and timely delivery of project outcomes. In a very difficult environment start-up kits were mostly timely delivered, while at times there were delays in payments of approved budgets. Short funding phases led to interruptions of activities and endangered the sustainability of the implementation partners. Numerous information blockages undermined efficiency. Reports on monitoring were incomplete. Stakeholder involvement in the project was high.

Sustainability was evaluated by five questions. A strong link between capacities and ownership was found. The project increased personal capacities of women to earn their own incomes. Professional empowerment of implementation partners and local leaders was found, while that of local government remained limited due to frequent staff movement and limited capacity.

Sustainably improved lives were reported at all places. Training and start-up capital of women led to economic empowerment outliving project duration. Local leaders and state ministries gave and received support. IDP and host communities gained equitably. The situation on SGBV improved because awareness, information, and support to the referral path for survivors. All these factors contributed to sustainability.

The observation of the project areas almost two years after project end allowed a view on maintenance of results over the longer term. Many women businesses continued to operate. Many implementing partners also continued to operate, monitor and support beneficiaries, although on a reduced scale. The positive effects on SGBV were also largely retained in view of interviewees. However, gains remain exposed to risks.

There is scope and need for continued and enhanced support to grow the economy. Many examples for social promotion of the role of women in society are the most prominent unforeseen effects of the project. The key complementarity of this project to other interventions exist to support to agriculture, the backbone of the mainly rural economy.

Overall, the project approach to combined WEE and GBV alleviation has proven viable, even under very challenging conditions. This is a feasible and important approach to promote WEE with great potential to replicate.

Regular monitoring will be critical for success. Effective project coordination with stakeholders will be vital for ownership and sustainability. The engagement of local leaders for the selection of beneficiaries has proven effective. Community GBV activists were found to have played a very active role as agents for change.

The formation of VSLA has shown not only a high potential to raise savings and consumption levels, but also a great effect on reducing GBV. Constant field presence of implementing partners has promoted good relationships with all. The short funding phases have reduced effectiveness and efficiency. The absence of professional GBV staff in places has hindered service provision and increased harm.

The report concludes by listing a number of recommendations that arise from the evaluation.

- Creating a firm basis of project implementing through a baseline survey and analytic study is vital.

- Systematic reporting and rigorous monitoring for accountability should be an integrated part and basis for follow-up projects. Monitoring should be systematically used to adapt and improve implementation.

- The scope and potential for learning from each other among implementation partners should be enhanced through support.

- Local leaders can be empowered to take a lead in enlightening their communities.

- Linking VSLAs to micro-finance institutions holds great potential to raise savings, consumption, and welfare.

- More focus should be given to strengthening functional literacy and numeracy as basis for development as freedom.

- Training on business management and entrepreneurship has also potential.

- The links of local small business and smallholder agriculture should be strengthened.

- More focus, beyond addressing consumption needs as tailoring and hairdressing, should be given to raising productivity in agriculture through new technologies (as animal ploughs) and new crops and improved seeds. There is a great opportunity in these areas to and they will open a way to diversify the agriculture and for the economy and welfare to grow.

- More focus can also be given on climate smart agriculture amd renewable technologies. This will also add value and create welfare on local basis.

- Awareness raising on GBV needs to be continued and broadened.

- Support to referral paths need to be strengthened and broadened.

- In particular, capacities of the police and judicial systems need to be strengthened.

- All these measures will contribute to WEE and improve gender equality.

Contents

Executive summary	2

1	Introduction	7

2	Background	7

3	Evaluation approach and methodology	10

4	Findings	13

4.1	Design and project implementation	14

4.2	Relevance	16

4.3	Effectiveness	20

4.4	Efficiency	27

4.5	Sustainability	29

5	Conclusions	32

5.1	Lessons learnt	32

5.2	Recommendations	33

Annexes	34

Terms of Reference	34

Evaluation matrix	43

Interview instruments	46

Interview partners	67

References and background documents	70

Project reports	70

Abbreviations	72

# Introduction

This is a report on the final, independent, evaluation of a UN Women (UNW) project (limited to South Sudan), financed by the Federal Republic of Germany, executed in May 2022. After the background and basic information on the project, the third section presents the evaluation approach and methodology. The main fourth section reports on the findings of the evaluation, structured by evaluation criteria and evaluation questions. The final section concludes with lessons and recommendations.

# Background

The Republic of South Sudan became the world’s newest nation and Africa’s 55th country on July 9, 2011. Renewed conflicts in December 2013 and July 2016 have undermined the development gains achieved since independence and worsened the humanitarian situation. As a consequence, South Sudan remains caught in a web of fragility, economic stagnation, and instability a decade after independence. Poverty is ubiquitous and is being reinforced by ongoing intercommunal conflict, displacement, and external shocks. The signing of the latest truce in September 2018 and subsequent formation of a unity government in February 2020 have provided a large measure of hope for recovery and peace building.

Women are on the lower rungs of the social hierarchy ladder than men and have fewer resilience assets and rely more on natural resources. Their high rates of illiteracy, limited skills and limited access to professional employment make them more vulnerable to climate change calamities than men, and households headed by females are more vulnerable to disasters such as famine.

South Sudan’s conflict redefines gender roles. While the direct actors and victims of conflict are mostly men, the indirect costs fall heavily on women and children. While women traditionally play a limited role in public life and their economic contribution is largely invisible, conflict also promotes their emancipation. Women play an active role in peacebuilding and an increasing role in society. Women are particularly vulnerable to the effects of climate change.

In order to be useful and relevant, the evaluation has to take account of the country context and regional and local situation. The application of best practices from elsewhere is only useful if and when adapted to the concrete country context.

The context of South Sudan has to be taken into account for the project evaluation. Particularly relevant are:

- As a land-locked country, South Sudan has a weak infrastructure.

- While the peace process continues, deep political and social conflicts dominate.

- The economy is ridden by inefficiencies and incomplete markets.

- The private sector, vital for economic recovery and development, is weakly organised.

- The business environment is very difficult for all on many aspects, and in particular for small and informal businesses. Besides limited education and training, access to finance, inputs, markets, energy, land, as well as legal insecurity, are important.

- Governance is weak and institutions are infant, they are also subject to frequent changes.

- The resource-based economy contributes to weak governance.

- Transparency is generally low and the quantity and quality of data is low.

- There are wide regional income and development disparities. In addition, the urban bias towards Juba is huge.

- While a rapid social change is happening in South Sudan, the position of women is still problematic. Despite many initiatives and legal reforms, gender inequality is still high and women’s empowerment is limited.

- Climate change has also started to affect the country and project areas strongly and to an increasing scale.

- In order to resolve ongoing conflicts, raising incomes of broad parts of the population will be vital. The project thus addresses a key issue.

- There are high degrees of instability and unpredictability, as well as security concerns. South Sudan also witnesses a regional and international rapidly changing context. The country with its infant institutions and incomplete markets and crisis mode is hardly able to cope with these. In this context, increasing the resilience is vital.

- The crisis is added to by the direct and indirect impacts of Covid-19 in the country, including the project areas. The impacts of the Omicron variant are still unclear.

With a budget of €3 million, sponsored by the Government of Germany, UN Women (UNW) implemented the project “Promoting Resilience, Self-Reliance And Social Cohesion Among Displaced Populations And Host Communities With Focus On Women And Girls In South Sudan and Mali” over the period January 2016 – June 2020. This evaluation covers activities in South Sudan. Further information will be limited to South Sudan.

Overall objective of the project was to promote self-reliance and social cohesion for internal displaced persons (IDPs) and their host communities, with a focus on areas of South Sudan and Mali affected by the ongoing conflicts.

The project had two strategic outcomes, namely, to:

- Improve access to sustainable livelihood/income generation opportunities for vulnerable women and girls among the IDP population and host community in the targeted geographic locations;

- Alleviate the risk of sexual and gender based violence (SGBV) among IDP population and host communities.

The project was implemented using four key strategies, namely:

- Provision of marketable vocational/income generational skills along with literacy and numeracy skills through informal trainings and skills building sessions to IDP and their host communities.

- Provision of access to productive resources including finance and start-up kits to allow the women to establish viable livelihood/income generation activities.

- Raise awareness and provide community education about the rights of women and girls against GBV; and allowing GBV survivors to access to multi-sectoral services via referral pathways.

- Identification of community activists to be engaged in a community-based protection mechanism to assist survivors to access critical response services available to them.

According to the two strategic outcomes and the related four key strategies, two outcomes with each two outputs (one output per key strategy) were defined:

Outcome 1: Women and adolescent girls among displaced population and their host communities have acquired income generating skills and livelihood assets to engage in sustainable livelihood activities to enhance their resilience

- Output 1.1 – women and adolescent girls displaced by the crisis and their host communities have acquired marketable vocational/income generation skills along with literacy and numeracy skills through informal training.;

- Output 1.2: Women and girls displaced by conflict and their host communities have access to productive resources including finance and/ start-up kits to establish viable livelihood/income generation activities.

Outcome 2: The risk of SGBV is alleviated among IDP population and host communities

- Output 2.1 – Targeted women and girls from the displaced population and host communities are informed of their rights against GBV and are provided with access, via referral pathway, to multi-sectoral GBV survivor services available their vicinity.

- Output 2.2:  Community activists engaged in a community-based protection mechanism to assist survivors to access critical response services

The project was implemented in close cooperation with the government. The key coordinating ministry was the Ministry of Gender, Child and Social Welfare (MGCSW). Further important institutions were the Ministries of Education and Agriculture, at federal level and in the states of implementation.

Through UN Women South Sudan partners, the project was implemented by six agencies:

- Community Integrated Rural Development Initiative (CIRDI),

- Change Agent Association/Organization (CAO),

- Initiative for Peace Association (IPCA),

- Support for Peace and Education Development Program (SPEDP),

- Grand Debaters and

- South Sudan Women Network (SSWEN)

Activities were implemented in Juba, Rumbek, Mundri, Nimule, Awerial-Mingkaman, and Yambio.

# Evaluation approach and methodology

The approach chosen to evaluate this project took account of the context of the specific country circumstances of South Sudan. As the desk review indicates, the project addresses several of these challenges and has made substantial progress to alleviate them. The evaluation assesses the extents and challenges and proposes how to build on its successes in a sustainable way to contribute to resilience.

The main purpose of this evaluation is to assess the achievement of project results and performance of the above-described intervention. Field research was carried out in South Sudan over a period of 15 working days, in Juba and in the selected implementation locations.

Findings of the evaluation are to inform UNW South Sudan’s future work in humanitarian and resilience response, especially on women’s economic empowerment (WEE) and ending violence against women and girls (EVAW).

Specific evaluation objectives (and how they are addressed) include:

- Assess the relevance of the implementation strategy and approaches: the evaluation assessed the extent to which the project’s implementation strategy and implementation approaches responded to beneficiaries, global, country, and partner/institution needs, policies, and priorities, and continued to do so if circumstances changed.

- Assess organizational efficiency: the evaluation in particular assessed the extent to which the intervention delivered results in an economic and timely way.

- Validate the project results: the evaluation confirmed if and how the planned and reported project results have been achieved.

- Assess the potential for sustainability: the evaluation assessed if the benefits are likely to last – it will assess if the net benefits of the intervention will continue, or likely to continue.

- Document lessons learned, best practices, success stories and challenges: the evaluation documents the lessons learned by implementors, beneficiaries, and government. Further, it points out any best practices and success stories and their potential and conditions to be replicated elsewhere. In addition, the evaluation explains the challenges the project implementation met and that future interventions in its areas are likely to meet.

- Identify strategies for replication and up-scaling: based on the evaluation results, the report identifies areas where and ways how to replicate and up-scale interventions of the project. This includes identifying the conditions that must be met or created to make replication and up-scaling possible.

- Provide actionable recommendations: based on the evaluation results, the report lists concrete recommendations that can be implemented.

- Assess how the project and its results relate to SDGs: the evaluation report specifies to which SDGs and how the project results relate.

These evaluation objectives are addressed in the 18 evaluation questions in the evaluation matrix (see Appendix).

The Evaluation addresses five criteria:

- Design and implementation of the project

- Relevance

- Effectiveness

- Efficiency

- Sustainability

The definition of the criteria is informed by the OECD/DAC evaluation criteria definitions. Design and implementation of the project is added. Also important are gender equality and human rights. This dimension is mainstreamed – its different dimensions are assessed under the five evaluation criteria. This has been regarded as more useful than adding a separate criteria of gender equality.

On the basis of this, the report provides the lessons learned, best practices, success stories and challenges. The evaluation identifies challenges and gaps in the implementation of the project for future improvement. Key target group is the UNW project planning and implementation staff, especially in the area of WEE. Beyond this, the report should also be of interest to other stakeholders concerned with WEE.

This evaluation covers the full implementation period of January 2016 – June 2020. The evaluation methodology is mixed: Quantitative and qualitative research methods and analytical approaches are combined. Data from different sources are combined and cross-checked (triangulated).

The evaluation was participatory, including beneficiaries, implementing agencies, cooperating government agencies, and the funder.

The UN Women Evaluation Policy and the Evaluation Strategy to Transform Women’s and Girls’ Lives 2018-2021 are the main guiding documents that set forth the principles and organizational framework for evaluation planning, conduct and follow-up in UN Women.

The evaluation approach taken here is informed by the UNDP frameworks and by the rich experience of the national and international experts. Relevant UNDP frameworks include the Global Evaluation Report Assessment and Analysis System (GERAAS) and its Guidance Note, the UN Evaluation Group (UNEG) Norms and Standards for Evaluation in the UN System

. The UN Women Evaluation Policy and the Evaluation strategy to transform womens’ and girls’ lives 2018-21 have also been taken as guiding documents.

The evaluation strives to meet the norms of:

- Internationally agreed principles, goals and targets

- Utility

- Credibility

- Independence

- Impartiality

- Ethics

- Transparency

- Human rights and gender equality

- National evaluation capacities

- Professionalism

In particular, the evaluation is aligned to the UN Women Strategy to transform Women’s and Girl’s lives 2018-2021. It has to be noted that the systematic and comprehensive way of evaluation had to be adapted to the environment of limited data availability and time budget.

Ethical safeguards

Ethical considerations and safeguards are an important part of the UNEG’s norms and standards for evaluation. They are stipulated in its Ethical Guidelines for Evaluation (UNEG 2020). The ethical principles of integrity, accountability, respect and beneficence were upheld in the conduct, management, and governance of this evaluation.

Integrity in evaluation requires honesty and truthfulness in communication and action, professionalism based on competence, commitment, ongoing reflective practice and credible and trustworthy behaviour, as well as independence, impartiality, and incorruptibility.

Accountability in evaluation requires transparency, responsiveness, taking responsibility for meeting the evaluation purpose, and justifying and fairly and accurately reporting to stakeholders decisions, actions and intentions.

Respect in evaluation requires access to the evaluation process and products by all relevant stakeholders in the evaluation process, meaningful engagement and fair treatment of all relevant stakeholders in the entire evaluation process, and fair representation of different voices and perspectives in the evaluation products.

Beneficence in evaluation requires explicit and ongoing consideration of risks and benefits from the evaluation process and products, maximising benefits at systematic, organizational and programmatic levels. Ensuring evaluation makes an overall positive contribution to human and natural systems.

These safeguards have been carefully considered by the evaluation team throughout their mission. In the beginning of the interviews background and purpose of the evaluation were explained. Statements of the respondents were carefully listened to. All questions and concerns were taken note of. The interviews were framed by pre-discussions and post-discussions of the two evaluators.

Data sources, data collection methods and evaluation management

Data sources were:

- the project documentation and reports from UNW and the six implementing agencies – these provide quantitative data on project activities, outputs and outcomes, plus own assessments;

- reports and other documents by government, relevant cooperation partners, research bodies and other non-state actors that illuminate the situation of the target groups and their environment;

- qualitative interviews by the two consultants with key informants: project coordinator, implementing agencies, government, beneficiaries, and other key informants (guided by the questions guideline);

- focus group discussions with beneficiaries: women livelihoods groups, VSLA beneficiaries, women and girls on GBV, and community activists (also guided by the questions guideline).

Because of changing methodologies of the annual reports it was not possible to determine exactly which activities were implemented by which agency and in which location. The first step in the field work was to establish the distribution of activities in order to establish a fuller picture, allow an in-depth analysis of the project impact.

Through cross-checking the consultants confirm the validity of information in a process of matching and comparing information collected from different sources (from documents, from interviews and/or from stakeholders). The main objective of crosschecking was to spot contradictions between information sources. A further analysis of the degree of reliability of these information sources was carried out in order to validate the most objective conclusion.

The evaluation was Human Rights and Gender responsible and an Evaluation Reference Group (ERG) was established. The ERG was an integral part of the evaluation management structure and was constituted to facilitate the participation of relevant stakeholders in the design and scope of the evaluation, raising awareness of the different information needs, quality assurance throughout the process and in disseminating the evaluation results. The ERG was engaged throughout the process. Its advice was given both during the inception stage and at the presentation of the field work presentation.

The two consultants worked flexibly together, mainly jointly in meetings with key informants or foal group discussions. Primary responsibilities are divided by criteria: design and project implementation, efficiency, sustainability (International consultant), relevance and effectiveness (national consultant). Overall responsibility is with the international consultant. The consultants will meet daily, discuss and exchange notes. The interaction of their respective experience will be a key instrument to cross-check and triangulate information.

Data have been organized, categorized, summarized and analysed along the evaluation questions. The results on each evaluation question from the different sources and cross-checked, are presented by evaluation question in the report.

Limitation and mitigation strategies

An evaluation of this project in a tight frame of three weeks of field research was very demanding and the consultants have worked in a time conscious manner. The project has an impressive record of delivered activities and outputs. It has a high degree of complexity as it involved five locations in different regions, involved six implementing agencies, and worked on four strategies in quite divergent areas.

In the given time frame (15 work days), it was not possible to undertake a truly representative evaluation. Instead, an evaluation was done that gives a good coverage of the regional differences, including all the strategies, and including a wide range of stakeholders.

In addition to Juba, two other implementation areas were visited: Rumbek and Yambio. These were selected according to reachability, representing different geographical areas, implementation of all the four strategies, and presence of IDPs and host communities. On this basis, Rumbek, Juba, and Yambio were selected.

# Findings

The field research could validate activities and results in all four strategies at all visited places. Overall, the following outcomes were achieved:

- 2607 beneficiaries (2320 of them women) were trained in vocational skills

- 3537 beneficiaries (2594 of them women) accessed start-up kits and grants

- 2382 beneficiaries (2345 of them women) established small businesses

- Increased knowledge on GBV led to increased and improved reporting

- Improved referral of GBV cases to leaders, police, courts, hospitals

- Substantial reduction of GBV cases over the project duration

- Enhanced social cohesion between IDPs and host communities at implementation locations

The overall evaluation of the project is very positive, under challenging conditions. Some concerns are noted on reporting, monitoring, efficiency.

The following sub-sections report the evaluation results according to evaluation criteria and evaluation question.

## Design and project implementation

This section captures basic elements of the planning and organisation of the project that are important for an implementation at quality level. These concern the logical model of reality and intervention, quality analysis and the base-line data, and the nature of the results framework.

Does the project have a clear theory of change/logic model?

A theory of change is a method that explains how a given intervention, or set of interventions, are expected to lead to a specific development change, drawing on a causal analysis based on available evidence. In addition to spelling out logical relationships between action and results, the theory of change has to analyse and spell out assumptions and risks.

The project document of this project is brief. Its situational analysis contextualizes the problems of displaced populations and particular women in conflict situations. It provides a clear theory of change with logic key links between the overall objective, outcomes and outputs.

The overall objective of the project to promote self-reliance and social cohesion for IDPs and their host communities affected by ongoing conflicts is to be attained by improved access to sustainable livelihood/income generation opportunities for both groups and by alleviation of risks of SGBV among both groups. Provision of vocational skills along with literacy and numeracy are to enable the target group to engage in sustainable livelihood activities to enhance their resilience.

Awareness raising and information about their rights as well as engagement of community activists are to alleviate the risk of SGBV among both target groups (IDPs and host communities).

These two causal relationships are logical and important. This is well documented in typical comparable settings. Such evidence is also available for South Sudan. However, this evidence does not seem to have been analysed.

The context analysis is very brief. Assumptions and risks are not spelled out. This would be important to monitor conditions of success and ensure minimizing risks to success.

Does the project design base on quality analysis and base-line data?

It is important for a project to define a base line of the situation at the start of the project so that results of the project interventions can be measured. This was also envisaged in the project document as a first step of implementation.

Output one stipulates a baseline assessment to identify woman friendly vocational skills that are in demand within the local markets in the areas where the IDPs are located. Output two requires a participatory needs and capacity assessment of the target beneficiaries and a market survey to define target market needs.

The project document does not refer to base-line data and a quality analysis. No documentation was available to the consultants that provide base-line data and a quality analysis. However, the implementing agencies undertook basic baseline assessments to identify vocational skills in demand and participatory needs assessments. The latter have been undertaken with the beneficiaries.

The assessments meet minimum standards. The identified skills in demand are limited to few skills directly and presently in demand, as tailoring and hair dressing. While clothing is among the most basic demand, hair dressing is less. More importantly, meeting these skills do not stimulate connected other needs and does not enlarge the economy through raising productivity.

It has to be recognized that the project operates in an extreme environment with data scarcity, existing or looming conflicts, and risks of rapid changes. In such an environment the expected standards of quality analysis and data provision need to be lowered.

The reports on implementation and monitoring are incomplete. No implementation matrix was used.

Overall, is the results framework SMART (specific, measurable, achievable, relevant, time-bound), clear and logical?

Each element of the SMART framework works together to create a goal that is carefully planned, clear and trackable. A smart framework is specific, measurable, assignable, realistic, and time-related. A specific framework targets a specific area for improvement. A measurable output quantifies or at least suggests an indicator of progress. An assignable framework specifies who will implement. Realistic targets state what results can realistically be achieved, given available resources. Time-bound targets specify when the results can be achieved.

Output 1 defines as specific result the completion of 3 months vocational training by 3,000 women and adolescent girls by end of 2019. No targets are defined for the literacy, numeracy, or entrepreneurial skills. No specific results are also defined for the establishment of women empowerment centres and women friendly centres. Thus, the progress on these activities cannot be measured.

Output 2 sets a target of 3,000 targeted beneficiaries to receive start-up capital to establish group or individual activities by end 2019. Activities to support target women groups to access land for commercial vegetable production and marketing (1.2.3.), provision or greenhouse/drip irrigation technologies to beneficiaries engaged in commercial vegetable production, and provision of energy and resource saving technology to targeted beneficiaries do not define targets. Thus, progress in these areas cannot be measured against a specific indicator.

The results framework does not fully meet the requirements of specificity and measurability.

## Relevance

This criterion considers the extent to which the intervention objectives and design respond to beneficiaries, global, country, and partner/institution needs, policies, and priorities, and continue to do so if circumstances change.

Do the intervention objectives and design respond to the needs of the target groups, including the disabled, and target areas and continue to do so if circumstances change?

The evaluation established that the project was consistent with the needs of the target groups and the target areas, both IDPs and the host communities. FGD with beneficiaries indicated that training provided by the project on vocational skills dovetailed with the provision of start-up kits to graduating trainees, and was in line with their needs. The project often coupled vocational skills training with adult literacy training. The adult functional literacy programme was relevant to the needs of most members of the VSLA who could neither read nor write. One participant of the FGDs, 68 old women, and a member of a VSLA in Nimule indicated “we used to hire people to come and calculate our savings from Village Savings and Loans Associations and to record our transactions. However, with literacy skills acquired through the project, we are able to do it for ourselves. Using the reading skills, we are also able to access market information and marketable value chains”. The needs of women and girls in livelihoods are immense and have not be completely addressed by the project and hence the importance of training more women in various vocational skills as the new needs and priorities arise.

The project aimed at alleviating the risk of SGBV among IDP population and host communities. Targeted women and girls from the displaced populations and the host communities were informed of their rights concerning GBV. They were also provided with access, via referral pathways, to multi-sectoral GBV survivors services available in their vicinity. The program activities are in line with needs of women and girls who bear the brunt of sexual and gender based violence (SGBV). The project contributed to alleviating the risk of SGBV among the IDPs and host communities through awareness meetings and radio talk shows. Nonetheless there is the need to carry out more awareness and sensitization of the communities to sustain the gains made by the project.

Do the intervention objectives and design match with the national structures, policies, plans, programmes, and decision-making processes?

The project is expressly aligned with national priorities expressed in the economic development objective of the Republic of South Sudan National Development Strategy (SSNDS) July 2018-June 2021. The Economic Development Cluster Goal is “to improve food security and livelihoods, and revitalize the national economy” with the objective of a “diversified private sector-led economic growth and sustainable development” that improves livelihoods and reduces poverty. The project is also in line with the natural resources sector objective which seeks “To ensure food security and improve livelihoods and income generation for the people of South Sudan, through sustainable use of natural resources and land management”.

The South Sudan Vision 2040 was translated into the South Sudan Development Plan 2011-13, which has gender equality as one of the issues cutting across the four pillars of the plan, being; (i) Governance; (ii) Economic Development; (iii) Social and Human Development; and, (iv) Conflict Prevention and Security. The UN Women project is in line with the Social and Human Development pillar of the SSDP plan 2011-2013, especially the program area of enhancing literacy and alternative education, with the development objective of increased literacy and functional skills for youth and adults and provide alternative and accelerated learning opportunities for out of school children. Similarly, the UN Women project is in line with the programme area of “increasing youth access to vocational training”.

The project is in line with the Ministry of Gender, Child and Social Welfare (MGCSW) Strategic Plan 2013-2018 whose strategies and objectives focus on gender equality and women empowerment, effective support services and the cross-cutting issues related to counselling. The scope of the mandate of the Ministry covers gender and women's empowerment, child and social welfare functions. The findings of the evaluation indicate that the UN Women project successfully trained women in vocational skills (tailoring, hair dressing and bread making, etc), provide them with start-up kits that enabled them to start individual or group businesses.

Do the intervention objectives and design reflect and align with South Sudan’s international obligations and commitments, incl. in the field of WEE, EVAW and humanitarian action?

Globally the project embraced components of the Sustainable Development Goals (SDGs) particularly Goal 2, Goal 4 and Goal 5.

Goal 2: “End hunger, achieve food security and improved nutrition and promote sustainable agriculture” and its corresponding targets, especially Target 2.3 that states that “By 2030, double the agricultural productivity and incomes of small-scale food producers, in particular women, indigenous peoples, family farmers, pastoralists and fishers, including through secure and equal access to land, other productive resources and inputs, knowledge, financial services, markets and opportunities for value addition and non-farm employment.” Female farmers in Lakes, Western Equatoria and Central Equatoria State were trained in improved farming technologies including modern vegetables production and provided with seeds enabling them to produce vegetables for home consumption and for the market.

For example, on access to land for farming, KII with the Programme Manager from IPCA in Juba mentioned that the Central Equatoria State Ministry of Agriculture and Forestry allocated a land area of 2 Feddans (8,400 square meters) to a women vegetable group in Luri Payam (Juba County) for vegetables production. While in Juba Nabari, a member of a women vegetable group allowed the group to use two Feddans of his land for group vegetables farming.

The project contributed to SDG 4: “Ensure inclusive and equitable quality education and promote lifelong learning opportunities for all” especially Target 4.4 which states that “By 2030, substantially increase the number of youth and adults who have relevant skills, including technical and vocational skills, for employment, decent jobs and entrepreneurship” and to the objectives of the Sphere Standards and the minimum Standards of Education in Emergency (INEE) that highlights the need to provide education related to livelihoods and employment such as small business development, financial literacy, technical and vocational education and training to young men and women particularly those from vulnerable groups, who do not complete formal school.

During a FGD with 6 members Wulu County Women Hairdressing Group, they said CIRDI trained them on hair dressing for 3 months and were refreshed for another one month. Similarly, a female tailor in Muniki Payam of Juba County mentioned that she was trained by UNW/IPCA on tailoring for about 3 months and provided with a start-up kit comprising sewing machine, fabrics and tool box which enabled her to establish a tailoring business at her residence.

According to the UNW Fourth Annual Progress Report 2019, in Nimule and Yambio, 286 project participants (242 women and 44 men) acquired reading and writing skills thus enabling them to read, calculate their savings and record their business transactions which according to them have benefitted them greatly

Similarly the UN Women project contributed to SDG 5 that is to “Achieve gender equality and empower all women and girls” and its corresponding targets, especially Target 5.2, “Eliminate all forms of violence against all women and girls in the public and private spheres, including trafficking and sexual and other types of exploitation, and Target 5.3, “Eliminate all harmful practices, such as child, early and forced marriage and female genital mutilation”

The UN Women Project (Outcome 2) aims to alleviate the risk of SGBV among IDP population and host communities. FGD with two female community activities in Juba County (Jebel and Luri) revealed that the most important forms of SGBV are domestic violence (beating of wives by husbands), rape, forced marriages and early marriages of girls and unwanted pregnancies. Through the public awareness meetings and radio talk shows conducted by community GBV activists and the Protection/Gender Officers from the implementing partners, the UN Women project has greatly contributed to Ending Violence against Women (EVAW) from IDPS and host communities in the targeted locations.

The project is aligned to the UN Women Strategic plan 2018-2021 strategic priority Outcome 3 that seeks the economic empowerment of women, ensuring that, “more women own, launch and/or better manage small, medium and large enterprises” and that “more rural women secure access to productive resources and engage in sustainable agriculture”. Similarly, the project addresses the issue of ending violence against women (EVAW). Outcome area 4 strives to ensure that “more countries and stakeholders are better able to prevent violence against women and girls and deliver essential services to victims and survivors” and that “more cities and other settings have safe and empowering public spaces for women and girls”.

The evaluation findings established that the project promoted sustainable livelihood activities for women and worked towards the reduction of sexual and gender based violence among the displaced population and host communities in South Sudan. Similarly the UN Women project established four woman friendly spaces in the targeted locations in Rumbek Yambio, Mundri and Nimule

Are the intervention objectives and design consistent with the country’s specific situation?

The onset of conflict in South Sudan in 2013 and 2016 led to the displacement of many people, some of who sought refuge in neighbouring countries, while others settled in relatively secure areas in South Sudan. Most households, the majority of who are women who lost their main sources of livelihoods and had to resort to coping strategies such as disposal of productive and non-productive assets such as small ruminants, kitchen sets, jewellery, tools and equipment. The project objective and design aimed at enabling women and adolescent girls among displaced population and their host communities to acquire income generating skills and livelihood assets to engage in sustainable livelihood activities to enhance their resilience to future shocks. Displaced women needed access to productive resources including start-up kits and financial resources to enable them start their own business and earn income to sustain their livelihoods and desist from disposal of assets and engaging in risky coping strategies.

Due to the social and economic impact of the war, some women and girls reportedly resorted to risky behaviour such as transactional sex to secure income to support themselves and their families. In addition to the loss of livelihoods and family members, and the burden of caring for their children, women are subjected to horrendous human rights violations and atrocities including rape, abduction, forced marriage, and sexual exploitation, abuse and harassment. In this respect the project was designed to alleviate the risk of SGBV among IDP population and host communities by making them aware on their rights against GBV and providing them with access to multi-sectoral GBV survivor services available their vicinity.

Have the stakeholders taken ownership of the project concept?

The involvement of community leaders and the local authorities has contributed to stakeholders’ sense of ownership of the process of development of activities and the project achievements that resulted. At the state level in Rumbek and Yambio, there is a monthly Gender Cluster Coordination meeting chaired by the Director General in the State Ministry of Gender, Child and Social Welfare (SMGCSW) and co-chaired by an INGO. Similarly, KII with the Director for Gender in the SMGCSW in Yambio revealed that the ministry staffs were also involved in the selection of beneficiaries, conducting outreach activities on GBV together with the implementing partner staff and monitoring the activities of the women VSLAs. The active participation of the state ministry is an important aspect of taking ownership in that it takes the lead to ensure that the project results and outcomes are owned by the community.

In general, there were good working relationships of the project with community leaders and local government authorities. The chiefs mobilized communities and participated in the community needs assessment and the planning of the project activities together with IPCA staff and the communities. The community leaders including chiefs, sub chiefs and headmen, were involved in the identification and mobilization of beneficiaries. The community leaders allocated land for cultivation to the VSLA and the vegetables groups. In addition, the chiefs supervised the VSLA for sustainability by ensuring they function as per their bylaws and constitutions. In this respect the involvement of local community structure in the UN Women Project was an important aspect of local ownership of the project that greatly contributed to the success of the project in visited locations.

## Effectiveness

Effectiveness addresses the extent to which the intervention achieved, or is expected to achieve, its objectives, and its results, including any differential results across groups. Key evaluation questions concerns the progress made towards the achievement of the project’s objectives and results. Some detail is provided on this.

What has been the progress made towards achievement of the project’s objectives and expected results?

Effectiveness of End of Project Outcome-1

Outcome 1: Displaced women and adolescents and host populations have developed IGA skills and engaged in sustainable livelihood activities

Under outcome 1, the project achieved a score of 67.37% on its outcome indicator; 2,383 out of 3,537 women/girls and men from displaced and host communities started small businesses leading to improved livelihoods of their families. The project largely achieved the outcome that it set for itself as women/girls and men were enabled to start, expand and diversify their businesses enterprises in tailoring and hair dressing salon. As illustrated in the below Table, high achievements of 90.4% were scored in the areas of women and girls who started small business leading to improved livelihoods of their families. However, a lower score of 4% was noted in the outcome area of men who started small businesses. The much lower participation of men in the project reflects the strong project focus on women and WEE.

Table: Achievement of Outcomes and Short-term Impacts

| Indicator | Target Value |  | Achieved Jan 2016-June 2020 | Achieved against Target value |
| --- | --- | --- | --- | --- |
| Outcome 1: Displaced women and adolescents and host populations have developed IGA skills and engaged in sustainable livelihood activities |  |  |  |  |
| Percent of trained beneficiaries/groups who started small businesses leading to improved livelihoods of their families |  | 3,000 | Women/girls and men (2,383 out of 3,537 Women and girls (2,345 out of 2,594) Men (38 out of 943) | 67.37% 90.4% 4% |

According to the UN Women Final Project Report, January 2026-June 2020, through the VSLAs about 18.8% (1,003) out of the 5,339 members started their own business enterprises, owing to the saving and lending skills and the start-up grants provided by the project. Of the 1,003 members who started own businesses, 96.2% (965) were women and 3.8% (38) were men.  Each VSLA received a startup grant of worth average of $400 that has enabled women to increase their savings and expand their businesses.

Effectiveness of End of Project Outcome-2

Outcome 2: The risk of SGBV is alleviated among IDP population and host communities

Under outcome 2, the project achieved an average outcome performance of 94.9% on its outcome indicators. As illustrated in the below Table, high achievements were scored in the areas of women beneficiaries demonstrating awareness on GBV (100%) and men demonstrating awareness on GBV (89.83%)

Table: Achievement of Outcome 2 and Short-term Impacts

| Indicator | Target Value |  | Achieved Jan 2016-June 2020 | Achieved against Target value |
| --- | --- | --- | --- | --- |
| Outcome 2: The risks of gender-based violence are reduced among displaced populations as well as in host communities |  |  |  |  |
| % of targeted beneficiaries demonstrating awareness on GBV |  | 80% of women beneficiaries 60% of male beneficiaries | 61 out of 61 women 53 out of 59 men *Samples from the target communities | 100% 89.83% |
| Average Outcome Performance |  |  |  | 94.9% |

According to the UN Women Final Progress Report 2016-2020, there has been an increase in the number of GBV cases that were reported in all the project target locations from 0 in 2016 to 397 in 2020. A total of 397 SGBV cases were reported for the period 2016-2020 as follows: 2016-2017 (0 cases), 2017-2018 (0 cases), 2018-2019 (96 cases), 2019-2020(108 cases) and 2020 (193 cases). The community mobilization interventions through community awareness meetings and TV/radio messages focused on providing communities with knowledge on GBV, where to report and how to care for the survivors. Improved understanding of GBV has resulted in increased reporting of GBV cases in the target project locations.

The UN Fourth Annual Progress Report 2019 mentioned that in Yambio, in 2019, three rape cases were reported and referred to responsible authorities. Through intensification of the use of mobile courts, all the survivors of GBV have accessed to justice as all perpetrators have received jail sentences.

The findings of the final evaluation were that the establishment of community women action/or activist teams has been a big potential to draw up better approaches and strategies for the protection of GBV survivors. FGD with two community activity groups in Juba County revealed that there has been a decrease in the overall incidences of GBV in the communities and this could be to a large extent attributed to the awareness conducted by them. “Yes, our GBV outreach activities/services in the communities resulted in improved reporting of cases to us and subsequent referral to the chiefs and to the police for legal recourse and to the health facilities for examination and treatment” said one of the female community GBV activists.

The involvement of traditional and religious leaders in the fight against GBV has also enabled effective handling of the GBV cases in all the project target locations. In Matangai Payam, Rumbek Center County, a paramount chief who participated in GBV awareness meetings conducted by the community GBV activists in his community said that through the training he acquired more knowledge that helped him to deal with cases of GBV that frequently arise in his community. Now he handles rape cases in the community; cases are reported to him, and hearings takes place in the traditional court. The survivors are referred to Matangai PHCU for medical examination and treatment. When found guilty for raping a girl the perpetrator is fined 5 head of cattle and sentenced to 5 years in prison. If the victim is a married woman the culprit pays 7 heads of cattle and is imprisoned for 2 years.

Progress made towards achievement of expected results/outputs

Output 1.1: Displaced women acquired vocational/income generation skills along with literacy and numeracy skills

The project was able to convert its resources into activities and output with an estimated effectiveness of 136.1% a total of 4,083 women and adolescent girls successfully completed a 3 months vocational training supported by the project.

Vocational skills training

The UNW Fourth Annual Progress Report 2019 indicated that, 342 beneficiaries (332 women and 10 men) in all the project target locations acquired skills in tailoring, hair dressing, saloon, soap making, bee keeping and computer with support of this project. The women acquired tailoring skills in effective use of the machines, measuring, sketching, sewing, hemming of bed sheets, and buying materials. In Rumbek and Yambio (Anika Women Group), 49 persons (32 women and 17 men) enhanced bee keeping skills through training organised by Community Integrated Rural Development Initiative (CIRDI) and Change Agency Organization (CAO) respectively.

Literacy and numeracy and entrepreneurship skills

The UNW Fourth Annual Progress Report 2019 indicated that in Nimule and Yambio, 236 beneficiaries (192 women and 44 men) were trained on functional literacy/numeracy skills training supported by this project.

SPEDP established five Functional Adult Literacy (FAL) centers in Magwi County in Eastern Equatoria State, from January 2020- May 2020, SPEDP provided functional Adult Literacy (FAL) to 102 individual (2 males and 100 females) drawn from VSLAs, agriculture and vocational skill training center to build their capacities on literacy and numeracy. On the other hand Change Agency Organization (CAO) conducted training for 150 direct beneficiaries including 20% of men on VSLA basic and entrepreneurship skills; 120 in Yambio and 30 in Nzara.

Agronomic Skills

The UN Women project successfully trained farmers in Lakes, Western Equatoria and Eastern Equatoria State in improved farming technologies including modern vegetables production, Smart agricultural practices, integrated pests and control and diseases management. According to the UN Women Third Annual Report 2018, in Mundri and Yambio, 220 women have improved their skills in production of new and climate resilient varieties for vegetables as they gained access to agricultural extension services in modern vegetable production. In Matangai Payam, 50 women from vegetables production groups were selected and trained on vegetables production.

Livelihood groups

UN Women Final Report, for the period January 2016- June 2020, indicated that 180 VSLAs with total membership of 5,339 persons (3,915 women and 1,424 men) were formed in the target project locations. Each group consists of 30 members and the inclusion of men in all groups according to the project documents was deliberate to ensure men were not left behind and enhance men’s understandings of women’s economic empowerment.

CAO facilitated the formation of 31 VSLA in Yambio and Nzara Payams. The project provided lockable cash boxes to the VSLA groups and one meeting hall have been constructed to women of Gangura Centre in Yambio County.

Output 1.2: Displaced women have access to productive resources including start-up kits and financial resources

Under output 1.2 the project was able to convert its resources into activities and output with an estimated effectiveness of 117.9% as detailed in below Table. A total of 3,537 (2,594 women/girls and 943 men) beneficiaries out of the target 3,000 received start-up capital, cash grant or micro-finance to establish groups or individual businesses through project support, thus surpassing the 3,000 beneficiaries’ target.

Tailoring and hair dressing kits

KII with a former Project Manager for UN Women project implemented by CIRDI indicated that 9 women (6 in Wulu County and 3 in Matangai Payam in Rumbek Center Payam) were trained in tailoring skills and provided with startup kits comprising sewing machines, tool box and rolls of fabrics of their choices. A female beneficiary in Muniki Block B in Juba town said that she was idle before her participation in the UN Women project implemented by IPCA. Because of the training in tailoring and provision of startup kits by the project she established a tailoring business. Now she said, she is able to earn income which she uses to feed her family. She mentioned that she cannot miss getting money on a daily basis from her business. From savings from her business she was able to buy a new sewing machine.

A FGD with Wulu County Women Hairdressing Group revealed that they received from the project through CIRDI 2 large looking mirrors, curtain, hair wigs and needles, scissors, assorted hair treatment chemicals and CIRDI paid a rent of six months for a shop where they could conduct their business. The training and hair dressing startup kits provided by the project enabled them to start and operate a group hair dressing saloon in Wulu town. The earned incomes are saved and the accumulated profits are distributed among members. Though the earned incomes, the members said that they were able to feed their families, pay schools for their children and meet other essential households’ needs as well as save some of the money.

Bee Keeping and honey production inputs

The findings of the final evaluation were that in 2019 CIRDI trained a bee keeping group in Rumbek and provided them with 30 modern bee hives. Similarly, according to Change Agency Organization (CAO) Quarterly Report for the period February to April, 2020, ten bee hives have been handed over to Anika women association. The members of Tivura honey processing group in Yambio Payam said there have been great changes in their living standards now compared to before joining the VSLA in that now they are able to save money, loan money and invest in IGAs. The incomes they earned from their individual small businesses were used to buy bicycles, shoes and clothing, and food from the market for the households. The women said that they have seen improvements in their lives and living standards socially and economically. According to the women, their husbands are very happy in that they are able to take some responsibility of running the household together with them.

Farming inputs

According to the UN Women Third Annual Report for 2018 in Yambio CAO facilitated the formation of 7 groups comprising 210 rural women farmers. The groups acquired access to new agricultural technologies such as improved climate resilient ground nut, maize, vegetable, tomatoes, onion, eggplant, okra, and cabbage seeds, most of which are resilient to drought, early maturing, highly nutritious and with a high germination rate.

A vegetables group in Juba Nabari in Juba County during a FGD said that they received from IPCA vegetable seeds (okra, kale, eggplant, tomatoes, green pepper and onions) and tools and equipment (2 watering cans, 2 wheelbarrows, 2 rakes, 2 Slashers). Similarly a FGD women vegetables group in Matangai Payam in Rumbek Centre revealed that the project provided them with vegetables seeds (kale, okra, amaranthus, eggplant, parsley and onions) and tools and equipment (23 watering cans, 23 rakes, 23 Slashers and 1 wheelbarrow).

Output 2.1 Women are informed of their rights in GBV provided with access to multi-sectoral GBV survivor services available their vicinity.

Under output 2.1, the project was able to convert its resources into activities and outputs with an average effectiveness of 203.9%. Out of the project target of 8,000, a total of 23,227 persons (14,521 women and 8,706 men) participated in GBV awareness/sensitization sessions and community dialogues. The target was overachieved by 290.3%. About 62.5% (14,521) of women and girls and 37.5% (8,706) of men out of the total of 23,227 community members participated in GBV awareness/sensitization sessions and community dialogues.

On the other hand, 8,861 men and boys out of the target 4,000 participated in GBV awareness/sensitization sessions. Thus the target was overachieved by 221.5%. All four of the planned women friendly spaces were established in Rumbek, Yambio, Mundri West and Nimule. The Yambio Women Empowerment Center was constructed by UN Women, while the Mingkaman Women Empowerment Center was rehabilitated by UN Women. The facility can accommodate up to 600 women/participants.

GBV awareness/sensitization

The community awareness meetings organized by the Community GBV Activists have focused on raising awareness on SGBV including child marriages, excessive dowry, forced marriages of adolescent girls, early marriages of adolescent girls, domestic violence, rapes of adolescent girls and women, the rights of girls to education, unequal treatment of women before the law, denial of access to justices to women, and prevention of women from inheriting property.

The findings of the evaluation were that UN Women through the support of implementing partners such as IPCA, CIRDI, and CAO conducted radio and TV talk shows which focused on educating communities on the negative impacts of SGBV and also providing referral channels for reporting and handling SGBV cases. For instance, IPCA has produced IEC materials such as T-Shirts and leaflets to raise awareness on GBV. From February to April 2020, 41 members (16 men and 25 women) from Nakofo Nzara County participated in gender based violence /conflict mitigation awareness sessions conducted by CAO. Similarly 70 community members (14 men, 56 women) from Kuzee in Yambio County were awared on GBV and conflict mitigation by CAO staff.

Similarly, CAO trained beneficiaries (71 in Yambio and 32 in Nzara), including GBV focal persons, VSLA members, community and church leaders on conflict mitigation.

GBV case management and psychosocial support

The project trained 123 young men in Psychosocial counseling, and thus has improved GBV case management, as the young men provided support to GBV survivors and refer cases to responsible authorities such as police.

GBV reporting system and referral pathway

During the reporting period February to April 2020, CAO in Yambio, received 56 GBV cases: 9 rape cases, 8 cases of psychological violence, 23 physical violence, 4 other GBV, 8 domestic violence and 4 attempted rape cases. The rape cases had been referred to health facilities for treatment and medical review. In the month of April 2020, CAO received 4 serious rape cases two girls were raped by their step fathers one girl was raped by the father and one pregnant lady was raped by a soldier. Only one perpetrator had been arrested and only two girls have been admitted to CTC Directorate of Social Welfare.

Women empowerment centers and women friendly spaces

The project has established two Women Empowerment Centers (WEC) in Mingkaman in Lakes State and in Yambio in Western Equatoria State. Four women friendly spaces were constructed in four project locations including Rumbek, Mundri West, Nimule and Yambio. The centers provide safe spaces for women to receive counseling support, vocational training and other economic empowerment interventions. Since the inception of the project, over 12,800 women have benefitted from the WECs and women friendly spaces through training, which has provided women in vocational skills, and psychosocial counseling. The women friendly spaces also offer women and girls access to free space for discussions on rights, GBV prevention and access to multi-sectoral GBV services, and transformational leadership training.

Output 2.2: Community Activists engaged in a community based sensitization, advocacy and promotion of protection mechanism

Under output 2.2, the project was able to convert its resources into activities and output with an estimated effectiveness of 128.3%. A total of 260 community activists out of the target 200 were trained and mentored in advocacy, and promotion skills. Thus the project scored an achievement of 130% above the target value. Similarly the community activities reached 8,861 men and boys out of the target of 7,000; thus the project over-achieved its target by 126.6%.

Community activists trained in community outreach and referral skills

The UN Women Final Progress January-June 2020 states that 260 community activists were trained and acted as male champions on reducing GBV. These community activists have played a leading role in transforming social norms, and negative masculinities. Using community dialogues, awareness and sensitization campaigns including radio talks, discussions, debates, and sports to prevent violence against women, community activists have reached out to 8,861 men and boys including traditional and religious leaders.

During the period February to April 2020, Change Agency Organization (CAO) trained a total of 29 Community GBV focal persons (11 men and 18 women) from Nzara to play the role of local GBV activists.

How adaptable and rapidly did the project react to crises and changing situations?

The UN Women Final Progress Report 2016-2020 indicated that the hyperinflation experienced by South Sudan has resulted in the unavailability of some materials on the market and where available, prices became astronomical. UN Women has addressed the situation by making disbursements to implementing partners in US dollars instead of SSP, making it easier for supplies to be procured in neighbouring countries. Insecurity due to non-state armed groups operations in some of Western Equatoria Counties and other project locations was resolved by UN Women by ensuring that in all the project locations, field missions and transportation of materials were conducted by air. UN Women has worked closely with UNMISS (United Nations Mission to South Sudan) to provide security, and the state ministries supported the UN Women interventions by ensuring safety in the project target locations.

The project realised that there were high rates of illiteracy among the VSLA members and thus responded to this by initiating adult numeracy and literacy classes. In addition, all training was conducted in local language to facilitate understanding by all participants. To a certain extent, some cultural practices and norms affecting the behaviour and attitudes of men towards women resulted in widespread practices of early and forced marriages. However, the project identified those challenges and built the capacities of the Community GBV Activists to work with men and traditional leaders in order to change the social norms, and address attitudes that increase GBV such as forced and early marriages.

IPCA reported that in 2018, due to the insecurity in Mundri, the State Government changed the protocols of Operations for Non-governmental Organizations (NGOs). Any workshops or trainings must be cleared by the National Security Services. As a result, scheduled trainings could not start early. Instead whole two days were used for seeking security clearance. Similarly, access to Mundri by road was a challenge and the flight bookings for departure to Mundri for the implementation proved hard as it took two weeks for a flight to get fully reserved. Nonetheless, the State, County authorities and local community leaders were supportive during the entire project process from mobilization, sensitization and selection of beneficiaries.

Systematic monitoring and documentation of progress in implementation would have provided a basis for a higher degree of project reaction to crises and changing environments.

Has the project achieved any unforeseen results, either positive or negative? For whom?

The most notable unforeseen project result is the elevation of women in traditional structures, but also the wider society.

For instance, during a FGD with five VSLA groups in Yambio, it was mentioned that the VSLA have empowered women socially and unexpectedly elevated some of them to leadership positions in their communities as well as in the state. A few VSLA females’ members have been elected to leadership and decision making positions in their communities as headpersons, sub chiefs and secretaries in the traditional courts. There is a female member from one of the VSLA who was appointed as a member of the National Assembly.

Women have also being empowered economically, one of the female VSLA member in Yambio saved money which she used to pay for her education, now, and she obtained a diploma in clinical medicine. The evaluation collected numerous comparable examples.

## Efficiency

Efficiency refers to the extent to which the intervention delivers, or is likely to deliver, in an economic and timely way. The first evaluation question relates to this issue, while the second evaluation question relates to the extent of stakeholder involvement.

Were resources (financial, human, technical) allocated and outputs delivered in an economic and timely way to deliver the project outcomes?

The environment for project implementation was very difficult over the entire implementation period. Conflicts, a political crisis, and shocks in the international economic, political and social environment, notably the Covid-19 pandemic, further increased the challenges to implementation. These led to the project extension until end June 2020. The pandemic was also among the causes of the delay of this end project evaluation to May 2020.

All actors and stakeholders in implementation are obviously aware of these difficult circumstances. Under these circumstances, best efforts were undertaken to deliver finance and outputs in economic and timely way, as appreciated by the beneficiaries.

However, there were instances of delays in payments on approved funding applications by implementing partners. These were due to the practice of payments by UNW via UNDP.

Beneficiaries reported timely receipt of the start-up kits (incl. tailoring machines, tool kits, fabrics, mirrors, wax, etc., seeds).

Another reason for interruptions of project implementation was the need for applying anew for funding after a funding phase was ended, reported on and evaluated. For example, the reported implementation gaps between the four funding phases of CAO in Yambio were 2, 3 and 7 months.

Notable information blockages on different levels limited the ability of the project to deliver on its planned targets. For example, in one case the director of one IP did not circulate the results of a market needs assessment undertaken for the project. The project manager was thus not able to make use of this report.

In another development, the final project manager of UNW for the project was not in possession of the project documentation of the previous project manager.

An important instrument to check the progress of the project implementation are the monitoring reports of the implementing partners, the UNW project manager and the M&E department of UNW. The German embassy, representing the donor, the development ministry of Germany, was also expected to monitor the project.

Some monitoring visits were reportedly done, by the UNW project manager, by the UNW evaluation department and by the implementing agencies. However, very limited reporting is available and there are no signs of systematic monitoring. This would be necessary as a basis to systematically learn and improve project implementation.

To what extent were relevant stakeholders and actors included in the project planning and implementation?

The project achieved a high degree of stakeholder involvement. In particular the beneficiaries have been highly involved in the needs assessments and intervention planning. Their needs, requirements, and ideas on solutions were starting points. This has been reported in all visited areas, both by implementing agencies and beneficiaries. Traditional leaders and government officials also confirmed this. At the same time, the abilities of the beneficiaries to articulate themselves and their needs and interests are different between the visited project areas. This led necessarily to different degrees of effective participation. The capacities of beneficiaries to articulate themselves appears to be the higher, the higher the level of overall development and exposure to outside influences.

The implementing agencies develop their proposed projects in the framework stipulated by UNW. They play the key role in planning and implementation. The visits at the three implementing partners visited in Juba, Rumbek and Yambio validated that these roles have been played. The fact that in case of Rumbek, the implementing partner CIRDI had to close down its office because of lack of funding for new projects testifies to the severe problems of sustainability of the implementing NGOs that have in most cases no core funding for their organisations. They depend entirely on project funding that provides generally only an overhead charge of 10% of project budgets. In case of CIRDI the former project manager was able and willing to provide the required information and organisation of the programme to visit beneficiaries, local leaders and local government.

Local leaders were in all areas involved in project implementation. They were not only well informed about the project plans and implementation, but also played a role in the selection of beneficiaries, and resolution of disputes. They displayed a high degree of ownership and saw the project as positive or very positive for their areas.

The degree of government participation in planning, implementation and monitoring the project differed by location. The key level of government engagement was at local level. The key ministry at national level was the MGCSW in Juba. The MGCSW played a key role in securing funding of the project and in setting the overall framework. However, it was not involved in project implementation. The gender ministries at local level were the direct counterparts. Their knowledge of the project and involvement differed by region and was highly determined by their own capacity.

The agriculture ministries are the most relevant to the project. However, their actual involvement has been limited.

Generally, the capacities of public administration (both personally and institutionally) at local level has been extremely limited, in particular the gender ministries. They have not been in a position to contribute effectively either to planning, implementing, or monitoring and evaluating the project and its implementation.

## Sustainability

Sustainability refers to the extent to which the net benefits of the intervention continue, or are likely to continue. This includes different aspects, including capacities and ownership, sustainable improvements in the lives of beneficiaries, a likelihood of continuation of benefits, perspectives of replication, and complementary effects on other development efforts. The fact that the project ended almost two years before the end evaluation allows a perspective on sustainability.

Have capacities and ownership (individual, institutional) been increased, in particular on the state level?

Both capacity and ownership by beneficiaries, implementing agencies and government are vital to strengthen the chances of longer term effects beyond the project implementation period. Both are closely interrelated: Without increased capacities ownership can hardly develop. Vice versa, capacity building requires ownership. The two necessitate each other.

Capacities of beneficiaries have been increased as a result of project implementation, often substantially. Proximity of larger markets and better developed infrastructure, especially in Juba, but also to some degree in Yambio, provided a more conducive environment for capacity development.

In most reported cases they have increased their capacities to earn own incomes and to lead an own life. The training in financial literacy played a key role. This resulted in often high levels of ownership. Even after almost two years after project end, many interviewees remember vividly their experience and are eager to know about plans to continue the activities.

Capacities of the implementing partners in terms of higher levels of training and institutional management have been enhanced. However, the economic sustainability of the agencies has in most cases not increased, because of their very limited overhead incomes through the UNW finance, not added to by any core finance.

According to numerous local leaders, the project activities supported their own efforts and enhanced their capacities to lead and develop their areas.

Local government has reportedly least gained in terms of institutional capacity building. However, government officials often benefited from participation in training sessions.

To what extent have lives sustainably improved economically and in terms of SGBV, in particular for women/girls and among IDPs and in host communities (incl. leaders)?

Various beneficiaries in all the visited areas report that their lives have been changed due to enlightenment and in particular due to their abilities to lead a more self-determined life because of their chance to earn incomes with vocational and business training, sometimes supported by additional training in literacy and numeracy. The project has considerably contributed to a rapid process of social change.

In terms of economic empowerment, project efforts have been successful in all visited areas. At the same time, the extent of sustainable life improvements was highly dependent on the economic environment, political stability, absence of conflict, and personal leadership. For instance, personal leadership of a new governor was noted as providing a more conducive environment for project success in Rumbek. On the other hand, the economic environment, in particular proximity of markets, was more positive in Juba and Yambio. Each of these frame conditions was highly fragile, limiting sustainability. These factors are independent of the project design and implementation. Close interaction with the various stakeholders were important to make use of opportunities as well as to mitigate challenges.

Due to the project activities, notably the vocational and business management training, and the resulting ability of women to contribute to the household incomes, the social position of women has also been enhanced. As reported in the visited areas, women are generally not any more regarded as mere housewives with household duties, but also as contributors to income welfare. As reported, most husbands welcomed this change, relieving them of part of their responsibilities.

As reported in all areas, project management and local leaders have taken care to ensure that the benefits have been equally allocated to both IDPs and to their host communities.

In the specific area of SGBV, the lives of women has also improved. Due to the awareness raising and information of women’s rights among both women and men, the minds have been broadened and attitudes have started to change. Many local leaders have actively supported this process. Through the activities of the GBV local activists, survivors of SGBV have been better able to cope in the referral path.

What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time after the project phases out?

Due to the almost two year gap between project end and this evaluation the evaluators could assess to which degree effects continued to exist.

Women have been provided with training and in most cases with cash amounts of material start-up kits with production/service instruments (e.g. tailoring machine) means of income generation. Many or most have been reportedly been able to continue operating after project end.

In many cases, implementation partners have continued visiting the supported beneficiaries also beyond the project end on a voluntary basis, even though on a limited scale.

Among the staff of implementing partners, many continue, either on the basis of new other projects, or as volunteers supported by their savings or family support. Others, however, are leaving the system. One reports now training as a midwife.

This testifies to a degree of economic self-sustaining. However, there are high risks to the sustainability of the improvements of economic and social welfare because of existing or imminent conflicts. It is likely that the social empowerment and socially enhanced role of women will be maintained, as it is part of a wider process of social change that is supported by a multiplicity of additional factors.

Does the project have an exit strategy and are there perspectives of replication?

The project was designed to enable women and adolescent girls to be capacitated to manage business and agriculture as well as to generate more income to sustain themselves. For example, village savings loan associations and agriculture groups support the members to access cash, seeds, tools, and lands to start new business and agriculture while they can also increase their savings and assets. The project helped beneficiaries to sustain their lives, to have better positions in their families and societies and to gain self-respect.

At the same time, more men and young men understand women are equal to men as well as gender-based violence is a violation of human rights and not accepted. In terms of co-existence of the host communities and IDPs, both host communities and IDPs participated in the project, and the project contributed significantly both groups to understand and support each other. In this sense, the project included an exit strategy, and the assumption of this process has largely been born out. Degrees of economic resilience have strengthened.

At the same time, the economic systems as a whole, in all three visited areas, remain subject to high risks of conflict, climate and other.

In order to ensure longer term sustainability by growing the economy by increasing productivity a continued support to beneficiaries through monitoring and assistance as well as training for and provision of production tools for increased productivity will be vital for future project success and sustainability. There is in particular scope in intensifying agriculture.

This project to empower women has been one of the first projects of its kind in South Sudan. Other projects have learned from its experience and taken up its lessons for subsequent projects.

Are there innovative good practices, unforeseen results, complementary and synergistic effects on UNW and other development interventions?

The most reported unforeseen result of the project has been the alleviation of women leaders of the project to position in traditional leadership in executive and judicial systems. The most prominent example is the appointment of a women leader as a member of the national assembly.

Some more than others, project implementors have become part of networks that exchange experience and learn from each other.

In general, the project activities with its outcomes and outputs has been complementary to other project activities, most notably on support to agriculture.

# Conclusions

The following conclusions consist of two parts: lessons learnt and recommendations. These follow from the evaluation according to the evaluation questions, and the discussions of the two experts. Another source were suggestions by the interviewed stakeholders.

## Lessons learnt

As stated above, because of limited data availability and the complex nature of the project, it has not been possible to examine a representative sample. The selected sample is illustrative. Thus, the following lessons do not have a firm basis of evidence, but rest on an illustrative sample. At the start of follow-up interventions in this field, a firm baseline study and analysis will have to be undertaken as a basis for project implementation.

Nevertheless, the following lessons can be formulated:

- The overall project approach, combining WEE and SGBV alleviation, has proven feasible and promising, even under very challenging conditions. This approach has potential for replication.

- The project set a clear focus on gender equality and WEE. Women have been the main beneficiaries.

- Disability has also been taken care of.

- To set it on a firm basis, a more systematic data and analytic base should be created as a start, than has been possible for this evaluated project.

- Regular and systematic monitoring, based on a monitoring matrix, should be institutionalized.

- There is a strong link between ownership and sustainability. These are mutually dependent and strengthen each other.

- Effective project coordination with stakeholders (beneficiaries, local leaders and local authorities) has proven vital for ownership and sustainability.

- The engagement of local leaders has shown to be effective for the selection of beneficiaries.

- Community GBV activists have played a very positive role as agents of economic and social change.

- The formation of VSLA has a great impact on reducing GBV.

- Constant field presence of implementing partners promoted good relationships with all.

- Short phases of funding has reduced both effectiveness and efficiency of the project.

- The absence of GBV professional staff hinders the service provision for GBV survivors and increases their harm from GBV.

## Recommendations

As stated above, the lessons and recommendations arising from this project evaluation do not have a strong and firm basis. With this limitation in mind, the following recommendations can be provided:

- Creating a firm basis of project implementing through a baseline survey and analytic study is vital.

- Systematic reporting and rigorous monitoring for accountability should be an integrated part and basis for follow-up projects. Monitoring should be systematically used to adapt and improve implementation.

- The scope and potential for learning from each other among implementation partners should be enhanced through support.

- Local leaders can be empowered to take a lead in enlightening their communities.

- Linking VSLAs to micro-finance institutions holds great potential to raise savings, consumption, and welfare.

- More focus should be given to strengthening functional literacy and numeracy as basis for development as freedom.

- Training on business management and entrepreneurship has also potential.

- The links of local small business and smallholder agriculture should be strengthened.

- More focus, beyond addressing consumption needs as tailoring and hairdressing, should be given to raising productivity in agriculture through new technologies (as animal ploughs) and new crops and improved seeds. There is a great opportunity in these areas to and they will open a way to diversify the agriculture and for the economy and welfare to grow.

- More focus can also be given on climate smart agriculture amd renewable technologies. This will also add value and create welfare on local basis.

- Awareness raising on GBV needs to be continued and broadened.

- Support to referral paths need to be strengthened and broadened.

- In particular, capacities of the police and judicial systems need to be strengthened.

- All these measures will contribute to WEE and improve gender equality.

Annexes

Terms of Reference

| International Consultant / Evaluator for the final evaluation of the “Promoting Resilience, Self-Reliance And Social Cohesion Among Displaced Populations And Host Communities With Focus On Women And Girls In South Sudan and Mali” |  |
| --- | --- |
| Location : | Home-based with travel to South Sudan |
| Application Deadline : | 20-April 2021 (Midnight New York, USA) |
| Additional Category : | Gender Equality |
| Type of Contract : | Individual Contract |
| Post Level : | International Consultant |
| Languages Required : | English, French |
| Starting Date : (date when the selected candidate is expected to start) | 30-May 2021 |
| Duration of Initial Contract : | 30 working days |
| Expected Duration of Assignment : | 30 working days in the period of 30 May – 30 June 2021. |

Background

In June 2020, UN Women – the United Nations Entity for Gender Equality and the Empowerment of Women – with the generous support from the Government of Germany, has been implementing a project titled “Promoting Resilience, Self-Reliance And Social Cohesion Among Displaced Populations And Host Communities With Focus On Women And Girls In South Sudan and Mali” with the budget of EUR 3,000,000. The project has been implemented in South Sudan and Mali, and in South Sudan it has been implemented in Rumbek, Mundri, Nimule, Awerial-Mingkaman, Juba and Yambio through UN Women South Sudan partners, Community Integrated Rural Development Initiative (CIRDI), Change Agent Association/Organization (CAO), Initiative for Peace Association (IPCA), Support for Peace and Education Development Program (SPEDP), Grand Debaters and South Sudan Women Network (SSWEN). The project was expected to be implemented for 3 years from 2016 to 2019. However, with the conflict that broke in Mid-2016, which interrupted project implementation for a better part of that year, implementation was extended to June 2020.

The overall objective of the project was to promote self-reliance and social cohesion for   internal displaced persons (IDPs) and their host communities, with a focus on areas of South Sudan and Mali affected by the ongoing conflicts. The project had two strategic outcomes, namely, to:

- Improve access to sustainable livelihood/income generation opportunities for vulnerable women and girls among the IDP population and host community in the targeted geographic locations;

- Alleviate the risk of sexual and gender based violence (SGBV) among IDP population and host communities.

The project was implemented using four key strategies, namely;

- Provision of marketable vocational/income generational skills along with literacy and numeracy skills through informal trainings and skills building sessions to IDP and their host communities.

- Provision of access to productive resources including finance and start-up kits to allow the women to establish viable livelihood/income generation activities.

- Raise awareness and provide community education about the rights of women and girls against GBV; and allowing GBV survivors to access to multi-sectoral services via referral pathways.

- Identification of community activists to be engaged in a community-based protection mechanism to assist survivors to access critical response services available to them.

Evaluation purpose, objectives and use

The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. The specific evaluation objectives are as follows:

- Analyze the relevance of the implementation strategy and approaches of the project;

- Assess organizational efficiency in progressing towards the achievement of the project’s results as defined in the intervention;

- Validate the project results in terms of achievements and/or weaknesses toward the outcome and outputs;

- Assess the potential for sustainability of the results achieved by the project;

- Document lessons learned, best practices, success stories and challenges to inform future work of UN Women and the German Government in addressing resilience, self-reliance and social cohesion especially focus on women’s economic empowerment (WEE) and violence against women in humanitarian and fragile contexts;

- Identify strategies for replication and up-scaling of the project’s best practices;

- Provide actionable recommendations for future programmatic developments and maximize ownership by partners;

- To assess how the project and its results relate and contribute to commitments and achievement of Sustainable Development Goals (SDGs).

Findings of the evaluation will inform UN Women South Sudan’s future work in the area of humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW). The external evaluation will further identify lessons learned, best practices and challenges of the  project and will greatly inform the development of the follow-up programmatic interventions. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area.

Evaluation Scope, Methodology, criteria and Key Evaluation Questions:

Scope and methodology

The final evaluation of the project is to be conducted externally by an international external consultant/evaluator in a team with national consultant/assistant evaluator. It is planned to be completed in 27 working day in the period of 25 November 2019 – 04 January 2020. The evaluation will cover the full project implementation period from January 2016 to December 2019. The evaluation will be conducted in South Sudan, where the project has been implemented, in the capital Juba with a travel to selected project target states and communities to collect data as defined by the evaluation plan.

The evaluation methodology will be mixed (quantitative and qualitative research methods and analytical approaches) to account for complexity of gender relations and to ensure participatory and inclusive processes that are culturally appropriate. The consultant is expected to reconstruct, validate and identify the gaps in the project’s results framework.

Assumptions should be tested and explain both the connections between early, intermediate and long term project outcomes and the expectations about how and why the project has brought them about. The evaluation team is also expected to identify challenges and gaps in the implementation of the project for future improvement. Hence, an eventual next phase of the project will benefit from the findings. The evaluation team should develop a sampling frame (area and population represented, rationale for selection, mechanism of selection, limitations of the sample) and specify how it will address the diversity of stakeholders in the intervention. The evaluation team should take measures to ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights; for example, the limitations of the sample (representativeness) should be stated clearly and the data should be triangulated (cross-checked against other sources) to help ensure robust results.

Criteria and key questions

The evaluation will address the criteria of Design and implementation of the Project, Project Relevance, Effectiveness, Efficiency, and Sustainability. More specifically, the evaluation will address the key evaluation questions:

- Design and implementation of the Project: A) Does the project have a clear theory of change/logic model? B) Overall, is the results framework SMART, clear and logical? C) Are the formulated outputs and outcomes clear and realistic? D) Are they measurable and do they respond to the needs identified? E) Do all results have sufficient, clearly defined and measurable indicators? F) Does baseline information exist, or what are the provisions to generate baseline information? G) Does the project have an M&E Framework with tools?

- Relevance: A) How does the project design match with the complexity of national structures, systems and decision-making processes? B) How does the project reflect and align with national strategic plans and normative frameworks as well as South Sudan’s international obligations and commitments in the field of WEE, EVAW and humanitarian action? C) Is the project design based on quality analysis, including gender and human rights-based analysis, risk assessments, socio-cultural and political analysis? D) Were the programmatic strategies appropriate to address the identified needs of beneficiaries? E) To what extent is the project results consistent with beneficiary requirements that is promoting resilience, self-reliance, peaceful co-existence, empowering women and promoting gender equality F) Has the project addressed the relevant needs in the target areas? G) Have new, more relevant needs emerged that the project should address? F) Have the stakeholders taken ownership of the project concept?

- Effectiveness: A) What has been the progress made towards achievement of the expected outcomes and expected results? What are the results achieved? B) What are the reasons for the achievement or non-achievement of the project results? C) Does the project have effective monitoring mechanisms in place to measure progress towards results? D) What is the influence of the specific country context and circumstances on the achievement of results and operational effectiveness? F) How adaptable and rapidly does the project react to changing situations?  G) Has the project achieved any unforeseen results, either positive or negative? For whom? H) What are the good practices and the obstacles or shortcomings encountered? How were they overcome? I) to what extent have capacities of relevant duty-bearers and rights-holders been strengthened? J) What -if any- types of innovative good practices have been introduced in the project for the achievement of WEE, EVAW and humanitarian action results? K) Has the project led to complementary and synergistic effects on broader UN Women efforts to promote WEE and EVAW in South Sudan?

- Efficiency: A) Have resources (financial, human, technical support, etc.) been allocated strategically to achieve the project outcomes? B) Have the outputs been delivered in a timely manner? C) To what extend were relevant stakeholders and actors included in the project planning and implementation?

- Sustainability: A) How effectively has the project been able to contribute to the generation of national ownership of the project outputs? B) What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time after the project phase out? C) To what extend has the project identified strategic partners that could pick up on supporting continued government and non-governmental action when the project comes to an end? D) Do national/local institutions demonstrate leadership commitment and technical capacity to continue to replicate some project activities? E) To what extend have the project’s exit strategy been well planned and successful? F) To what extend has the UN Women been able to promote replication of project successes?

The questions outlined above are preliminary and are expected to be revised and refined by the evaluation team during the inception phase of the evaluation.

Phases of the evaluation process

The evaluation process is divided in five phases: 1) Preparation, mainly devoted to structuring the evaluation approach, preparing the TOR, compiling project documentation, and hiring the evaluation team; 2) Inception, which will involve evaluability assessment, inception meetings, inception report and finalization of evaluation methodology; 3) Data collection and analysis, including desk research and preparation of field missions, visits to project sites 4) Data analysis and synthesis stage, focusing on data analyzed, interpretation of findings and drafting of an Evaluation Report; and 5) Dissemination and follow-up, which will entail the development of Management Response, uploading it into UN Women GATE system.

The consultant will be responsible for inception, data collection and data analysis and synthesis phases.

- Inception phase: At the beginning of the consultancy, the consultant will be provided with key sources of information for an initial desk review. At the end of this phase an inception report that will include the refined evaluation methodology will be delivered. The inception report will be validated and approved by UN Women.

- Data collection phase: Based on the inception phase, the consultant will carry out further in-depth desk review, and field missions will be conducted to complete data collection and triangulation of information. Interviews and focus group discussions with key stakeholders, as relevant, will take place.

- Data analysis and synthesis phase: The collected information will be analyzed, and final evaluation report will be delivered. A validation meeting will be organized where the consultant will validate the final report with UN Women and the evaluation reference group (ERG) and approved by UN Women.

UNW follows a systematic process to assess the quality of all completed evaluations on a yearly basis. This external quality assessment is based on the ‘Global Evaluation Report Assessment and Analysis System’ (GERAAS) and closely aligned with UN Evaluation Group quality standards. All evaluations in UN Women are annually assessed against the framework adopted in GERAAS and hence the consultant should be familiar with GERAAS quality standards. Evaluation in UN Women is guided by normative agreements to be gender-responsive and utilizes the entity’s Strategic Plan as a starting point for identifying the expected outcomes and impacts of its work and for measuring progress towards the achievement of results. The UN Women Evaluation Policy and the Evaluation Strategy to Transform Women’s and Girls’ Lives 2018-2021 are the main guiding documents that set forth the principles and organizational framework for evaluation planning, conduct and follow-up in UN Women. These principles are aligned with the United Nations Evaluation Group (UNEG) Norms and Standards for Evaluation in the UN System and the UNEG Ethical Guidelines. In addition, UN Women is an UN-SWAP reporting entity and the consultant will take into consideration that all the evaluation in UN Women are annually assessed against the UN-SWAP Evaluation Performance Indicator and its related scorecard.

Stakeholders Participation and Evaluation Management Structure

The evaluation will be a consultative, inclusive and participatory process and will ensure the participation of stakeholders engaged in the implementation of the project. The evaluation will be Human Rights and Gender responsible and an ERG will be established.

The Evaluation Reference Group (ERG) is an integral part of the evaluation management structure and is constituted to facilitate the participation of relevant stakeholders in the design and scope of the evaluation, raising awareness of the different information needs, quality assurance throughout the process and in disseminating the evaluation results. The ERG will be engaged throughout the process and will be composed of relevant representatives of state and non-state stakeholders. The ERG group will review the draft evaluation report and provide substantive feedback to ensure quality and completeness of the report and will participate in the inception and validation meeting of the final evaluation report.

The UN Women South Sudan Monitoring and Evaluation Focal Point will serve as the Evaluation task manager, who will be responsible for day-to-day management of the evaluation. UN Women East and Southern Africa will support the evaluation process.

Coordination in the field including logistical support will be the responsibility of UN Women. Within six weeks upon completion of the evaluation, UN Women has the responsibility to prepare a management response that addresses the findings and recommendations to ensure future learning and inform implementation of relevant projects. This is a consultative/participatory final project evaluation with a strong learning component. The management of the evaluation will ensure that key stakeholders are consulted.

##### Duties and Responsibilities

Duties and responsibilities of the International Consultant are: - To elaborate and submit the detailed inception report which contains evaluation objectives and scope, desk review, description of evaluation methodology/ methodological approach, data collection tools, data analysis methods, key informants/agencies, evaluation questions, performance criteria, issues to be studied, work plan and reporting requirements. It should include a clear evaluation matrix linking all these aspects; - To elaborate and finalize the data collection methodology such as guides, questioners/tools to be used with the key informants/interviewees; - To conduct field visit combined with individual interviews and focus groups discussions with the relevant stakeholders; - To prepare a Power Point Presentation and an outline on preliminary findings and present to ERG and reflect the feedback shared at this presentation in the final report; - To produce and submit the draft and final evaluation reports in English. Format of the final evaluation report shall include the following chapters: Executive Summary (maximum five pages), Project description, Evaluation purpose, Evaluation methodology, Findings, Lessons learnt, Recommendations and Annexes (including interview list- without identifying names for confidentiality, data collection instruments, key documents consulted, Terms of Reference). Deliverables: - Detailed Inception Report, which contains evaluation objectives and scope, findings from inception meetings with all relevant stakeholders, initial desk review, description of evaluation methodology/methodological approach, data collection tools, data analysis methods, key informants/agencies, evaluation questions, performance criteria, issues to be studied, work plan and reporting requirements. It should include a clear evaluation matrix linking all these aspects - by 12 December 2019 (7 working days, home-based); - Data collected through completed field visit and key informant interviews and focus group discussions - by 21 December 2019 (15 working days, in South Sudan); - Data analyzed and Power Point Presentation on preliminary findings conducted to highlight key evaluation findings and conclusions, lessons learnt and recommendations- by - 25 December 2019 (2 working days, in South Sudan); - Draft and Final Evaluation report & Evaluation brief that reflects key findings, conclusions and recommendations and deployed methodology (indicative samples will be provided by UN Women) in English taking into consideration comments and feedback collected from the presentation of preliminary findings. The report shall include the following chapters: Executive Summary (maximum five pages), Introduction and Background, Evaluation approach and methodology, Findings, Conclusions, Lessons learnt, Recommendations and relevant Annexes - by 04 January 2020 (9 working days, home based). The evaluation team has to submit the initial draft of the evaluation report to Evaluation Reference Group after 7 working days and use the additional 2 days to address ERG comments/feedback and resubmit the final version to the Evaluation task manager);

##### Competencies

Core Values: - Respect for Diversity - Integrity - Professionalism Core Competencies: - Awareness and Sensitivity Regarding Gender Issues - Accountability - Creative Problem Solving - Effective Communication - Inclusive Collaboration - Stakeholder Engagement - Leading by Example Please visit this link for more information on UN Women’s Core Values and Competencies: http://www.unwomen.org//media/headquarters/attachments/sections/about%20us/employment/un-women-employment-values-and-competencies-definitions-en.pdf

##### Required Skills and Experience

Education: - At least a master’s degree in Agriculture, sociology, international development, gender/women studies or related areas; Experience: - At least 7 years practical experience in conducting evaluations of strategies, policies and programmes; - Experience and knowledge on gender equality and women’s empowerment, violence against women and domestic violence; - Experience/knowledge of gender equality and violence against women issues in South Sudan; - Excellent analytical, facilitation and communications skills and ability to negotiate amongst a wide range of stakeholders; - Knowledge of human rights issues, the human rights based approach to programming, human rights analysis and related mandates within the UN system will be considered an asset; Language: - Proficiency in English, and French Evaluation procedure: The candidates will be evaluated against the following technical and financial criteria: - At least a master’s degree in sociology, international development, gender/women studies or related areas (max 40 ponts); - At least 7 years practical experience in conducting evaluations of strategies, policies and programmes (max 70 points); - Knowledge on gender equality and women’s empowerment, violence against women and domestic violence (max 70 points); - Experience/knowledge of gender equality and violence against women issues in South Sudan (max 70 points); - Excellent analytical, facilitation and communications skills and ability to negotiate amongst a wide range of stakeholders (max 70 points); - Proficiency in English (max 30 points). Knowledge of human rights issues, the human rights based approach to programming, human rights analysis and related mandates within the UN system will be considered an asset. Maximum total technical score amounts to 350 points. Only candidates who have passed over the minimum qualification criteria and have accumulated at least 245 points out of maximum 350 under technical evaluation will qualify for the next stage i.e. evaluation of their financial proposals. Evaluation of submitted financial offers will be done based on the following formula: S = Fmin / F * 150 S – score received on financial evaluation; Fmin – the lowest financial offer out of all the submitted offers qualified over the technical evaluation round; F – financial offer under consideration. The winning candidate will be the candidate, who has accumulated the highest aggregated score (technical scoring +financial scoring). Management arrangements: The UN Women M&E Focal Point in South Sudan will serve as the evaluation task manager. The evaluation task manager will be responsible for day-to-day management of the review. Coordination in the field including logistical support will be the responsibility of the Project Team. Financial arrangements: Payment will be disbursed upon submission and approval of deliverables and certification by UN Women Component Manager that the services have been satisfactorily performed as specified below: - Deliverable 1 (7 working days) – 30% - Deliverables 2,3,4,5 (20 working days) – 70% Application submission package: - CV; - Duly filled Personal History Form PHF11 that can be downloaded from http://www.unwomen.org/en/about-us/employment - A sample of previously conducted / most relevant evaluation report - Financial Proposal - lump sum proposal/offer* in USD (including breakdown of this lump sum amount, indicating all necessary costs to complete this assignment)...

Evaluation matrix

| Evaluation questions | Methods and sources | Indicators |
| --- | --- | --- |
| Design and implementation of the project |  |  |
| Does the project have a clear theory of change/logic model? | Document review of project document | logic, inclusiveness and clarity of underlying theory of change |
| Does the project design base on quality analysis and base-line data? | Review of project documentation Key informant interviews (KII) with project staff | existence and logic of baseline data, quality of situation analysis at project start |
| Overall, is the results framework SMART (specific, measurable, achievable, relevant, time-bound), clear and logical? | Review of project document, KII with project staff | extent to which results framework is specific, measurable, achievable, relevant, time-bound, clear and logic |
| Relevance |  |  |
| Do the intervention objectives and design respond to the needs of the target groups, including the disabled, and target areas and continue to do so if circumstances change? | Review of project documentation, KII, FGD with beneficiaries | Satisfaction of beneficiaries Human development indicators |
| Do the intervention objectives and design match with the national structures, policies, plans, programmes, and decision-making processes? | Review of project documentation, government development plans and relevant documents, relevant documents of development partners and research bodies | Project objectives and design versus government, development partners structures and plans |
| Do the intervention objectives and design reflect and align with South Sudan’s international obligations and commitments, incl. in the field of WEE, EVAW and humanitarian action? | Review of project objectives and design, reports on relevant government commitments | project objectives and plans versus government commitments |
| Are the intervention objectives and design consistent with the country’s specific situation? | Review of project documentation, analyses of country situation | Project objectives and design characteristics versus key characteristics of South Sudan (as identified above in ‘country context’) |
| Have the stakeholders taken ownership of the project concept? | Project documentation (implementation reports), KII and FGD | Indicator: feedback from stakeholders on ownership and engagement |
| Effectiveness |  |  |
| What has been the progress made towards achievement of the project’s objectives and expected results? | Review of project document and implementation reports KII, FGD with beneficiaries, implementors, government | Project objectives and expected results versus actual progress towards these |
| How adaptable and rapidly did the project react to crises and changing situations? | Review of project implementation reports KII, FGD with implementors, beneficiaries, government | Instances of reactions by project implementors |
| Has the project achieved any unforeseen results, either positive or negative? For whom? | Review of project implementation reports KII, FGD with implementors and beneficiaries | Evidence of unforeseen results and reactions |
| Efficiency |  |  |
| Were resources (financial, human, technical) allocated and outputs delivered in an economic and timely way to deliver the project outcomes? | Review of project implementation reports KII and FGD with implementors and beneficiaries | Project expenditures with staff and technical resources versus results |
| To what extent were relevant stakeholders and actors included in the project planning and implementation? | Review of project implementation reports KII and FGD with implementors, beneficiaries, government (especially on local level) | Evidence on stakeholder involvement Perceptions of stakeholders |
| Sustainability |  |  |
| Have capacities and ownership (individual, institutional) been increased, in particular on the state level? | Review of documentation of capacities (project and other reports) KII, FGD with project implementors, beneficiaries, government | Increased individual and institutional capacity and ownership |
| To what extent have lives sustainably improved economically and in terms of SGBV, in particular for women/girls and among IDPs and in host communities (incl. leaders)? | Review of project reports and other reports on the specific KII, FGD with implementors, beneficiaries, local government | State of relevant human development indicators |
| What is the likelihood that the benefits from the project will be maintained for a reasonably long period of time after the project phases out? | KII, FGD with project implementors, beneficiaries, development partners | Projected human development indicators for future periods |
| Does the project have an exit strategy and are there perspectives of replication? | Review of project documentation, KII with implementors | documentation of exit strategies |
| Are there innovative good practices, unforeseen results, complementary and synergistic effects on UNW and other development interventions? | Review of project documentation KII, FGD with implementors, beneficiaries, development partners | evidence of good practices, unforeseen results, synergies |

Interview instruments

UN Women Final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan”

Appendix 1 _FGD Community Activists

| Introduction Hello, my name is -----------and I am here on behalf of UN Women, South Sudan. We are conducting a final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. You have been selected by chance from all stakeholders in the area for this interview. The survey is voluntary and you do not have to participate, and can withdraw consent at any time – and that there will be no consequences for doing so. The information that you give will be fed into an evaluation report, this will be share with the Government of Germany as the donor, the Ministry of Agriculture and Food Security, the Ministry of Gender, Child and social welfare, the six national NGOs involved in the implementation of the project and other relevant National/State Ministries and other government institutions, NGOs and CBOs, local community leaders and local authorities in South Sudan. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area. We hope you will participate in the interview since your views are important. Could you please spare some time (around 30 minutes) for the interview? Can we begin now? 1.Yes 2.No |  |
| --- | --- |
| Section 1:Assessment details. Interviewer Name. Date of Interview:; ¦__¦__¦ / ¦__¦__¦ / 2022 Day Month. Town/Boma; Payam:. County:; State:. Number of participants:; Total: Male: Female:. Focal person (Name); Gender (male/female)-. Phone number. |
| 1 | As community activists what activities did you carry out in the targeted community during the project period? Since the close of the project in June 2020 to date what have and/or are you doing in the targeted community? |
| 2 | What types of training did you receive from the Un Women project? If so, in what areas/topics? How relevant were the trainings to your work as community activists? |
| 3 | Which forms of sexual and gender based violence have you identified as the most important to address in this community? Who are most affected? Give reasons for your choice? |
| 4 | As community activists what did you do to try to end the risk of SGBV on women and girls in your community? What were the results of your interventions, if any? |
| 5 | To what extent do you think the understanding of GBV among the project target populations has improved through community awareness meetings and TV/radio messaging conducted by you? How was the level of participation of i) women and adolescent girls, and ii) men and boys on those occasions? |
| 6 | 2) Did the improved understanding of GBV have any effect on the frequency of reporting of GBV cases among women and girls in the target project locations? 3) Which cases of GBV are most reported by women and girls in your location? |
| 7 | Do you think increased awareness among men and boys on the rights of women and girls against GBV changed their perception, attitude and behaviour towards women and girls? Has this in any way resulted in deceased rates of domestic and other form of violence by men on women and girls? |
| 8 | Do you think that improved reporting and management of GBV cases has resulted from the important roles you as community activists played in providing community outreach and referral outlets. Please elaborate? |
| 9 | Are services available to help survivors of violence and abuse (e.g. medical, psychosocial, material, legal, community based) in your location? Who provided each of these services? To what extent do you think women and girls benefitted from these services? |
| 10 | What do you think the situation of women and girls in relation to risk of gender based violence are now compared to before the project intervention? What has changed so far? Reasons for the changes? |
| 11 | In your opinion what has been the main challenges you faced in carrying out your activities in the communities? How did you cope with these challenges? What did the project done to minimize the constraints you faced? To what degrees of success? |
| 12 | What have you learnt from the UN Women project (the way the project was planned, implemented, coordinated and its achievement)? What did you think went well? What was not done well? |
| 13 | Are you currently continuing with your activities since the funding of the UN Women project came to an end in 2020? What type of activities are you undertaking? Is any NGO or government institution assisting you to sustain your activities? |
| 14 | In your opinion in which area should a future UN Women project focus on (give reasons for your choice).in relation to human rights and gender, SGBV and women empowerment? What would you like to be done differently? |

UN Women Final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan”

Appendix 2_FGD Targeted Women and Girls on GBV

| Introduction Hello, my name is -----------and I am here on behalf of UN Women, South Sudan. We are conducting a final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. You have been selected by chance from all stakeholders in the area for this interview. The survey is voluntary and you do not have to participate, and can withdraw consent at any time – and that there will be no consequences for doing so. The information that you give will be fed into an evaluation report, this will be share with the Government of Germany as the donor, the Ministry of Agriculture and Food Security, the Ministry of Gender, Child and social welfare, the six national NGOs involved in the implementation of the project and other relevant National/State Ministries and other government institutions, NGOs and CBOs, local community leaders and local authorities in South Sudan. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area. We hope you will participate in the interview since your views are important. Could you please spare some time (around 30 minutes) for the interview? Can we begin now? 1.Yes 2.No In case you want to raise any issues you may contact: Partner------------ Contact------------------------------------- |  |
| --- | --- |
| Section 1:Assessment details. Interviewer Name. Date of Interview:; ¦__¦__¦ / ¦__¦__¦ / 2022 Day Month. Town/Boma; Payam:. County:; State. Number of participants:; Total: male: female:. Focal person (Name); Gender (male/female)-. Phone number. |
| 1 | Are there problems in your community because of physical or sexual violence on women and girls; either in the community or in their homes? Which forms of violence have you identified as the most important to address in this community? Who are most affected? |
| 2 | Where do you think the majority of the violence against women and girls take place? Who are the perpetrators of the different types of violence and abuse done on women and girls in your community? What are the reasons? |
| 3 | To whom do women and girls most often go for help when they’ve been victims of some form of violence and abuse? What are some of the reasons why women and girls do not report and/or seek help for GBV cases? |
| 4 | Have you been informed by the UN Women project of you rights against gender based violence? If so, to what extent have you benefitted from the messages? |
| 5 | Do you think increased awareness among men and boys on the rights of women and girls against GBV changed their perception, attitude and behaviour towards women and girls in your location? To what extent do you feel that violence and abuse on women and girls by men have reduced? |
| 6 | Did the UN Women provide services to help survivors of violence and abuse (e.g. medical, psychosocial, material, legal, community based)? Which services were available to women and girls? Which ones were and are being used by women? |
| 7 | What was the quality of the services for GBV survivors? To what extent do you think women survivors of GBV benefitted from these services? |
| 8 | Are appropriate security measures for the prevention and punishment of sexual and gender-based violence taken in the community? Do victims of crime, including Sex and Gender Based Violence survivors, have access to judicial recourse? (Police and courts etc.). To what effect? |
| 9 | Are you aware of the services provided to women at the women friendly spaces in your location? What are they? In what ways do you think women and girls benefitted from the services of the women friendly spaces? |
| 10 | Did the project provide women with access to training in trauma healing and counseling? In what ways do you think you benefitted from the training? |
| 11 | What do you think the situation of women and girls in relation to risk of gender based violence are now compared to before the project intervention? What has changed so far? Reasons for the changes? |
| 12 | In your opinion what has been the main challenges or gaps of the UN Women project in reaching out and addressing the problems of violence and abuse on women? How did the project cope with these challenges? |
| 13 | Any reflection on what the project could have done differently/additionally with regards to alleviating the risk of SGBV among women and girls in your community. Any lessons learnt? What worked well? What did not work well? |
| 14 | In your opinion in which area should a future UN Women project focus on (give reasons for your choice) in relation to human rights and the alleviating the risk of GBV on women and adolescent girls and empowering women and girls in your location? |

UN Women Final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan”

Appendix 3_FGD VSLA Beneficiaries

| Introduction Hello, my name is -----------and I am here on behalf of UN Women, South Sudan. We are conducting a final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. You have been selected by chance from all stakeholders in the area for this interview. The survey is voluntary and you do not have to participate, and can withdraw consent at any time – and that there will be no consequences for doing so. The information that you give will be fed into an evaluation report, this will be share with the Government of Germany as the donor, the Ministry of Agriculture and Food Security, the Ministry of Gender, Child and social welfare, the six national NGOs involved in the implementation of the project and other relevant National/State Ministries and other government institutions, NGOs and CBOs, local community leaders and local authorities in South Sudan. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area. We hope you will participate in the interview since your views are important. Could you please spare some time (around 30 minutes) for the interview? Can we begin now? 1.Yes 2.No |  |
| --- | --- |
| Section 1:Assessment details. Interviewer Name. Date of Interview:; ¦__¦__¦ / ¦__¦__¦ / 2022 Day Month. Town/Boma; Payam. County:; State. Number of participants:; Total: Male: Female:. Focal person (Name); Gender (male/female)-. Phone number. |
| 1 | When was the Village Savings and Loan Association formed? What is the composition of the VSLA (men/women)? Do you think the VSLA address the developmental issues in the area? |
| 2 | What do you think were the main objectives and purposes of establishing the VSLA? What do you think are the benefits the members realized from the VSLA? How did the community in general benefit from the FSLA? |
| 3 | Was there any training provided to boards/committee members and ordinary members? What types of training was provided? To what extent have they benefitted from the training? In what ways? |
| 4 | To what extent were the knowledge and skills you acquired from the project on vocational/income generating skills and entrepreneurship relevant to you? In what ways have they benefitted from the training? |
| 5 | Did any of your members receive any training in literacy and numeracy skills? To what extent they benefit from the training provided by the UN Women project? |
| 6 | Did you receive any material support from the project in the past 24 months? Types and quantities received? Were these appropriate and relevant to your needs and priorities? |
| 7 | Was the VSLA provided with start-up grants by the project? What was the amount disbursed by the project? Do you feel the grant was sufficient enough to cover members borrowing requirements? |
| 8 | To what extent have the material and financial support you received from the project built your capacity to manage the VSLA and provide services to members? What services were provide to members? |
| 9 | What activities are you engaged in as a group? How do you finance the operations of the VSLA? Do you think the VSLA address the needs and priorities of members? |
| 10 | Did the VSLA save some money from its operations? How much was saved in the last cycle? Where did you keep the money? |
| 11 | Did members take any loans from the VSLA? What was the average amount borrowed per member? What were the main purposes for taking of loans by members? |
| 12 | What are some of the income generating activities started by members through the loans from the VSLA? Which types of income generating activities were successful? Which ones were successful and which ones were less successful? Why? |
| 13 | Has there been any change in your livelihoods and standards of living mow compared to before the joining the VSLA? What has changed? In what ways? |
| 14 | As an organization what are some of the challenges you encountered in running the VSLA? Did you receive any support from the project to resolve the challenges? What type of support? |
| 15 | How are you currently sustaining the activities of the VSLA? What is the future plan of your group? What type of support would you want to enable the group to sustain itself? From whom? |
| 16 | Any reflection on what the project could have done differently/additionally? Any lessons learnt? What have you as an organization learnt from this project? (the way the project was planned, implemented, coordinated and its achievement) What worked well? What did not work well? |
| 17 | What are your recommendations to UN Women for future interventions in promoting sustainable livelihoods and enhanced resilience for your community? What would you like to be done differently? |

UN Women Final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan”

Appendix 4_ FGD Livelihoods Group

| Introduction Hello, my name is -----------and I am here on behalf of UN Women, South Sudan. We are conducting a final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. You have been selected by chance from all stakeholders in the area for this interview. The survey is voluntary and you do not have to participate, and can withdraw consent at any time – and that there will be no consequences for doing so. The information that you give will be fed into an evaluation report, this will be share with the Government of Germany as the donor, the Ministry of Agriculture and Food Security, the Ministry of Gender, Child and social welfare, the six national NGOs involved in the implementation of the project and other relevant National/State Ministries and other government institutions, NGOs and CBOs, local community leaders and local authorities in South Sudan. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area. We hope you will participate in the interview since your views are important. Could you please spare some time (around 30 minutes) for the interview? Can we begin now? 1.Yes 2.No |  |
| --- | --- |
| Section 1:Assessment details. Interviewer Name. Date of Interview:; ¦__¦__¦ / ¦__¦__¦ / 2022 Day Month. Town/Boma; Payam. County:; State. Number of participants:; Total: Male: Female:. Focal person (Name); Gender (male/female)-. Phone number. |
| 1 | What is the name of the livelihood group? Number of members (male and females)? Why was it formed? Purpose of the group? Is the group still functional to date? |
| 2 | What types of vocational/income generation skills did your receive from the UN Women project? How relevant to you were the skills you acquired? In what ways did you benefit? |
| 3 | Did any of you receive training on literacy and numeracy skills from the project? To what extent have you benefitted from the skills you acquired through the project? |
| 4 | What types of livelihood activities are you carrying out as a group? What type of financial and material support did you receive from UN Women project for the establishment of your group business enterprise? Do you keep written records of the activities in the group enterprise? |
| 5 | To what extent do you think you have benefitted from the support provided by the project? In What ways? |
| 6 | Have you ever needed any loan since the establishment of your business? What were the main reasons why you needed the loan? |
| 7 | Did you ever take any loan for your business? If yes, how much? From which sources? What did you do with loan? |
| 8 | Is access to credit is a key constraint in this location? If so, what potential do you see in a Village Savings and Loans Association? What services could they provide to you? |
| 9 | What were the greatest challenges you faced in operating and maintaining your businesses? What type of help or support would you need the most if you were going to go into a new field of business? |
| 10 | What are the types of products and/or services which you produce and trade/sell? Where do you sell your produce (farm-gate, middlemen, market place, cooperatives and contracts etc.?)? Who are your main customers? |
| 11 | Did you face any difficulties in finding buyers for your products? If your answer is yes, what are the reasons? |
| 12 | Tell me about your life before you joined the group and how has that changed since you became a member of the livelihood group? In what ways has your life and behavior changed since you joined the group? |
| 13 | What are some of the challenges and limitations your group faces? How did you as a group resolve the constraints? What did the project do to help you with challenges you face? |
| 14 | How are you currently sustaining the activities of the livelihood group? What is the future plan of your livelihood group? What type of support would you want to enable the group to sustain itself? |
| 15 | What have you learnt from the UN Women project (the way the project was planned, implemented, coordinated and its achievement) implanted in your location? What do you think went well? What was not done well? Give reasons for your observations? |
| 16 | What are your recommendations to UN Women to enable more women and girls and men to start and sustain viable individual or group livelihood/income generation activities? What would you like to be done differently? |

UN Women Final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan”

Appendix 5_KII State/County Department of Gender, Child and Social Welfare

Introduction Hello, my name is -----------and I am here on behalf of UN Women, South Sudan. We are conducting a final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. You have been selected by chance from all stakeholders in the area for this interview. The survey is voluntary and you do not have to participate, and can withdraw consent at any time – and that there will be no consequences for doing so. The information that you give will be fed into an evaluation report, this will be share with the Government of Germany as the donor, the Ministry of Agriculture and Food Security, the Ministry of Gender, Child and social welfare, the six national NGOs involved in the implementation of the project and other relevant National/State Ministries and other government institutions, NGOs and CBOs, local community leaders and local authorities in South Sudan. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on women economic empowerment (WEE), ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area. We hope you will participate in the interview since your views are important. Could you please spare some time (around 30 minutes) for the interview? Can we begin now? 1.Yes 2.No

Section 1:Assessment details. Interviewer Name. Date of Interview:; ¦__¦__¦ / ¦__¦__¦ / 2022 Day Month. Town/Boma; Payam. County; State. Name of Institution/organization:. Name of respondent:; Male/Female:. Position :. Mobile phone.

| 1 | What is your role in the State/County Department of Gender, Child and Social Welfare? For how long have you been in this position? |
| --- | --- |
| 2 | To what extent were you involved in the UN Women project implemented in your location? (Reference may be made to needs assessment, mobilization, sensitization, training, capacity building linkages, etc.)? Were you personally involved in the project? If so in what role? |
| 3 | Were gender and human rights and specific needs of women/girls considered during the needs assessment, project design and implementation? Are human rights and gender objectives clearly stated in the project results framework? |
| 4 | Do you feel that the project proposed and implemented specific activities to allow women inclusion and to address their gender and human rights concerns/needs? What are the activities? Success rate? |
| 5 | To what extent do you think there was clarity of differentiation, in the project description, between the interests/priorities of women, adolescent girls, men and boys and potentially vulnerable groups? |
| 6 | Was the State Ministry/County Department of gender technically involved in project implementation? In what ways? The extent did you benefit from your participation in the project? |
| 7 | Did the UN Women project carry out any capacity building interventions for the State Ministry/Departments and its staff? To what extent do you think the support enhanced your capacity to contribute effectively towards the achievement of project outcomes? |
| 8 | What cluster coordination mechanisms are in place for organizations working in gender, child and social welfare? Extent to which State/County level coordination mechanisms/arrangements are functional and effective? If not, what are the reasons? |
| 9 | How was your working relationship and cooperation with UN Women project implementing partners in your location? To what extent do you think the working relationship contributed to or hindered the success of the project in your location? |
| 10 | Do you feel the project achieved the outcomes that it set for itself in informing women and girls against gender based violence and alleviating the risk of sexual and gender based violence (SGBV)in your location? Extent to which rates of violence against women and adolescent girls in targeted communities has been reduced due to UN Women project interventions |
| 11 | Which enabling factors do you feel contributed most to the achievement of expected outcomes in reducing the risks of gender based violence on women and girls in your location? And which constraining factors contributed most to the non-achievement of expected outcomes? |
| 12 | Do you think there were any unintended outcomes/results that arose during the implementation of the UN Women project in your location? Please give details? In what ways, if any, did they affect the different stakeholders? Did you contribute in any way to mitigate the negative outcomes/impacts on beneficiaries? |
| 13 | Are you aware of any types of innovative good practices that have been introduced in the project for the achievement of Women Economic Empowerment (WEE), Ending Violence Against Women (EVAW) EVAW and humanitarian action results? What types of relevant interventions were implemented? |
| 14 | Do you think the project led to complementary and synergistic effects on broader UN Women efforts to promote WEE and EVAW in your State and in South Sudan? Please elaborate |
| 15 | Do you think that national/local institutions demonstrate leadership commitment and technical capacity to continue to replicate some project activities? Please elaborate? What support do you think they will require to effectively carrying out their mandates? |
| 16 | Are you aware of any appropriate sustainability and exit strategy designed by UN Women and local implementing partners to ensure sustainability of the project’s results beyond the funding period? Was the exit strategy put into effect? If so, please give details. What have been the results of this strategy to date? |
| 17 | As a result of your involvement in different aspects of the project intervention implementation do you feel that you have the capacity (e.g. financial, staff, time, etc.) to maintain and /or continue to generate the project outcomes? |
| 18 | Any reflection on what the project could have done differently/additionally? Any lessons learnt? What have you as an organization learnt from this project? (the way the project was planned, implemented, coordinated and its achievement) What worked well? What did not work well? |
| 19 | What are your recommendations to UN Women for future interventions in Women Economic Empowerment (WEE), Ending Violence Against Women (EVAW) and gender and human rights for women and adolescent girls in South Sudan? What would you like to be done differently? |

UN Women Final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan”

Appendix 6 _KII State Ministry /County Department of Agriculture

Introduction Hello, my name is -----------and I am here on behalf of UN Women, South Sudan. We are conducting a final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. You have been selected by chance from all stakeholders in the area for this interview. The survey is voluntary and you do not have to participate, and can withdraw consent at any time – and that there will be no consequences for doing so. The information that you give will be fed into an evaluation report, this will be share with the Government of Germany as the donor, the Ministry of Agriculture and Food Security, the Ministry of Gender, Child and social welfare, the six national NGOs involved in the implementation of the project and other relevant National/State Ministries and other government institutions, NGOs and CBOs, local community leaders and local authorities in South Sudan. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area. We hope you will participate in the interview since your views are important. Could you please spare some time (around 30 minutes) for the interview? Can we begin now? 1.Yes 2.No

Section 1:Assessment details. Interviewer Name. Date of Interview:; ¦__¦__¦ / ¦__¦__¦ / 2022 Day Month. Town/Boma; Payam. County; State. Name of Institution/organization:. Name of respondent:; Male/Female:. Position :. Mobile phone.

| 1 | What is your role in the State Ministry/County Department of Agriculture? How long have you worked in this position? |
| --- | --- |
| 2 | What is your role in the UN Women project? Was the Ministry/County Department consulted/involved during the project design and at the inception and implementation phases (such as selection of target locations, technical support to implementing partners’ staff and beneficiaries, etc.)? To what extent do you feel the project addressed the felt needs and priorities of targeted populations in livelihoods promotion and enhanced resilience? |
| 3 | To what extent was the State Ministry/County Departments technically involved in project implementation? (Reference may be made to, mobilization, sensitization, training, capacity building linkages, etc.)? The extent did the Ministry/County Department benefit participation in the project? |
| 4 | Did the UN Women project carry out any capacity building interventions for the State Ministry/Departments and its staff? To what extent do you think the support enhanced your capacity to contribute effectively towards the achievement of project outcomes? |
| 5 | What cluster coordination mechanisms are in place for organizations working in agriculture, food security and livelihoods? Extent to which State/County level coordination mechanisms/arrangements are functional and effective? If not, what are the reasons? |
| 6 | How was your working relationship and cooperation with UN Women project implementing partners in your location? To what extent do you think the working relationship contributed to or hindered the success of the project in your location? |
| 7 | Discuss assistance to farmers regarding seeds and tools, and the trainings they receive? Do you think the UN Women project is addressing the correct issues in food security and livelihoods? To what extent do you think farmers and framers groups benefitted from the activities and outputs of the project? |
| 8 | Do you feel the project achieved the outcomes that it set for itself in promoting sustainable livelihood activities to enhance the resilience of women, girls, men and boys in your location? Extent to which targeted population had access knowledge and skills and to means of production including start up kits and financial resources, and established successful group or individual businesses? |
| 9 | Which enabling factors do you feel contributed most to the achievement of expected outcomes in sustainable in livelihood activities and enhanced resilience of beneficiaries? And which constraining factors contributed most to the non-achievement of expected outcomes? |
| 10 | Do you think there were any unintended outcomes/results that arose during the implementation of the UN Women project in your location? Please give details? In what ways, if any, did they affect the different stakeholders? Did you contribute in any way to mitigate the negative outcomes/impacts on beneficiaries? |
| 11 | Do you think that national/local institutions demonstrate leadership commitment and technical capacity to continue to replicate some project activities? Please elaborate? What support do you think they will require to effectively carrying out their mandates? |
| 12 | What is the current situation of women, girls, men and boys in relation to livelihoods and resilience? Do you think there has been any improvement or decline in their livelihoods now compared to before the project intervention? Which groups do you feel benefitted the most? Why? |
| 13 | Has the project addressed the relevant needs of women and girls, men and young boys in this location? To what extent? Do you think that new, more relevant needs emerged that the project should address? |
| 14 | Are you aware of any appropriate sustainability and exit strategy designed by UN Women and local implementing partners to ensure sustainability of the project’s results beyond the funding period? Was the exit strategy put into effect? If so, please give details. What have been the results of this strategy to date? |
| 15 | As a result of your involvement in different aspects of the project intervention implementation do you feel that you have the capacity (e.g. financial, staff, time, etc.) to maintain and /or continue to generate the project outcomes? |
| 16 | Any reflection on what the project could have done differently/additionally? Any lessons learnt? What have you as an organization learnt from this project? (the way the project was planned, implemented, coordinated and its achievement) What worked well? What did not work well? |
| 17 | What are your recommendations to UN Women for future interventions in promoting equitable access to sustainable livelihood/income generation opportunities and enhanced resilience for vulnerable communities in South Sudan? What would you like to be done differently?? |

UN Women Final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan”

Appendix 7: _KII_ implementing partner staff

Introduction Hello, my name is -----------and I am here on behalf of UN Women, South Sudan. We are conducting a final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. You have been selected by chance from all stakeholders in the area for this interview. The survey is voluntary and you do not have to participate, and can withdraw consent at any time – and that there will be no consequences for doing so. The information that you give will be fed into an evaluation report, this will be share with the Government of Germany as the donor, the Ministry of Agriculture and Food Security, the Ministry of Gender, Child and social welfare, the six national NGOs involved in the implementation of the project and other relevant National/State Ministries and other government institutions, NGOs and CBOs, local community leaders and local authorities in South Sudan. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area. We hope you will participate in the interview since your views are important. Could you please spare some time (around 30 minutes) for the interview? Can we begin now? 1.Yes 2.No

Section 1:Assessment details. Interviewer Name. Date of Interview:; ¦__¦__¦ / ¦__¦__¦ / 2022 Day Month. Town/Boma; Payam. County; State. Name of Institution/organization:. Name of respondent:; Male/Female:. Position :. Mobile phone.

| 1 | What is your role in the UN Women project implemented in your location? How long have you been involved with the project? |
| --- | --- |
| 2 | Are human rights and gender objectives clearly stated in the project results framework? Extent to which the interest/priorities of women adolescent girls, men and boys and vulnerable groups differentiated in the project document |
| 3 | The extent to which the M&E staff used tools to collect, classify, analyze and provide monitoring reports for management decision making and control. Were the reporting schedules to UN Women observed? |
| 4 | Were the budget approved and disbursed for the project adequate enough for implementation of project activities? How timely were the disbursements of funding? If there were any delays, what were the main causes of delays? |
| 5 | Types of project inputs and timeliness of delivery to project sites/beneficiaries. Adequacy and quality of inputs provided to beneficiaries. Were available resources channeled in a coordinated manner towards achievement of the strategic objectives? |
| 6 | What were the planned and actual numbers and category of staff recruited for project implementation (classify by categories)? Were all key staffs in post within 6 months of start up? Were they maintained through project life? What were their experiences? |
| 7 | How was your working relationship with relevant local community/traditional leaders and local government authorities in the target location? Did you get good cooperation from them? To what extent do you think the working relationship contributed to or hindered the success of the project in your location? |
| 8 | Which state line ministry/county departments were involved in the implementation of the project? Any financial, material, capacity building and/or any other types of support provided to them by the project? To what extent do you think the support provided to them enhanced their capacity to implement the UN Women project? |
| 9 | How satisfactory do you feel were the UN Women procedures that were implemented at each phase of the project cycle? [design/preparation – approval – implementation (including monitoring and reporting/disbursement of funds/approval of expenses) – evaluation] What aspects could have been better? |
| 10 | Did the UN Women project undertake any capacity building activities for your staff? What types of capacity building activities were undertaken? Extent to which the capacity building interventions enhanced the staff capacity in implementation of the project? |
| 11 | To what extent do you think the project outcomes achieved contributed to addressing the challenges to sustainable livelihoods for vulnerable groups as well as the disabled? Presence of key results achieved by the intervention towards the realization of human rights and gender equity. |
| 12 | To what extent do you think the project outcomes achieved contributed to addressing the challenges to gender empowerment and SGBV among women and adolescent girls in the targeted locations? Presence of key results achieved by the intervention towards the realization of human rights and gender equity? |
| 13 | Did the project generate any unintended outcomes/results? How did they affect the different stakeholders? How adaptable and rapidly did the project react to changing situations? |
| 14 | To what extent, were innovative good practices introduced in the project for the achievement of Women Economic Empowerment (WEE) and Ending Violence Against Women (EVAW) and humanitarian action results? What types of relevant interventions were implemented? To what degree of success? |
| 15 | To what extent do you feel that the project led to complementary and synergistic effects on broader UN Women efforts to promote Women Economic Empowerment (WEE) and Ending Violence Against Women and Girls (EVAW) in South Sudan? Please elaborate |
| 16 | Any reflection on what the project could have done differently/additionally? Any lessons learnt? What have you as an organization learnt from this project? (the way the project was planned, implemented, coordinated and its achievement) What worked well? What did not work well? |
| 17 | What are your recommendations to UN Women for future interventions in i) WEE, EVAW, gender and human rights, and ii) access to sustainable livelihood/income generation opportunities and enhanced resilience for communities in South Sudan? What would you like to be done differently? |

UN Women Final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan”

Appendix 8 _KII-IGA operator

Introduction Hello, my name is -----------and I am here on behalf of UN Women, South Sudan. We are conducting a final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. You have been selected by chance from all stakeholders in the area for this interview. The survey is voluntary and you do not have to participate, and can withdraw consent at any time – and that there will be no consequences for doing so. The information that you give will be fed into an evaluation report, this will be share with the Government of Germany as the donor, the Ministry of Agriculture and Food Security, the Ministry of Gender, Child and social welfare, the six national NGOs involved in the implementation of the project and other relevant National/State Ministries and other government institutions, NGOs and CBOs, local community leaders and local authorities in South Sudan. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area. We hope you will participate in the interview since your views are important. Could you please spare some time (around 30 minutes) for the interview? Can we begin now? 1.Yes 2.No

Section 1:Assessment details. Interviewer Name. Date of Interview:; ¦__¦__¦ / ¦__¦__¦ / 2022 Day Month. Town/Boma; Payam. County; State. Name of Institution/organization:. Name of respondent:; Male/Female:. Position :. Mobile phone.

| 1 | What is the name of your business? What type of income generating activity are you engaged in? For how long have you been running the business? What type of financial and material support did you receive from UN Women project for the establishment of your business enterprise? |
| --- | --- |
| 2 | What types of vocational/income generation and entrepreneurship skills did your receive from the UN Women project? How relevant to you were the skills you acquired? In what ways did you benefit? |
| 3 | Did any of you receive any training on literacy and numeracy skills from the project? To what extent have you benefitted from the skills you acquired through the project? Do you keep written records of the activities in your business enterprise? |
| 4 | Have you ever needed any loan since the establishment of your business? What were the main reasons, why you needed the loan? |
| 5 | Did you ever take any loan for your business? How much? From which sources? To what extent do you think you have benefitted from the support provided by the project? |
| 6 | Is access to credit is a key constraint in this location? If so, what potential do you see in a Village Savings and Loans Association? What services could they provide to you? |
| 7 | What were the greatest challenges you faced in operating and maintaining your businesses? Did you receive any material and financial support from any sources after the closure of the UN Women project? |
| 8 | What are the types of products and/or services which you produce and trade/sell? Where do you sell your produce (farm-gate, middlemen, market place, cooperatives and contracts etc.)? Who are your main customers? |
| 9 | Did you face any difficulties in finding buyers for your products? If your answer is yes, what are the reasons? How were the difficulties resolved, if any? |
| 10 | Tell me about your life before you established your business with support from UN Women Project? How have your life changed since you acquired relevant skills and received financial and other productive resources from the project? |
| 11 | How are you currently sustaining the activities of the livelihood group? What is the future plan of your livelihood group? What type of support would you need to enable the group to sustain itself? |
| 12 | What have you learnt from the UN Women project (the way the project was planned, implemented, coordinated and its achievement) implanted in your location? What do you think went well? What was not done well? Give reasons for your observations? |
| 13 | What are your recommendations to UN Women for strengthening the capacity of women and youth to start and sustain profitable income generating activities in their communities? What would you like to be done differently? |

UN Women Final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan”

Appendix 9: _KII Local Community Leader/Paramount Chief

Introduction Hello, my name is -----------and I am here on behalf of UN Women, South Sudan. We are conducting a final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. You have been selected by chance from all stakeholders in the area for this interview. The survey is voluntary and you do not have to participate, and can withdraw consent at any time – and that there will be no consequences for doing so. The information that you give will be fed into an evaluation report, this will be share with the Government of Germany as the donor, the Ministry of Agriculture and Food Security, the Ministry of Gender, Child and social welfare, the six national NGOs involved in the implementation of the project and other relevant National/State Ministries and other government institutions, NGOs and CBOs, local community leaders and local authorities in South Sudan. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area. We hope you will participate in the interview since your views are important. Could you please spare some time (around 30 minutes) for the interview? Can we begin now? 1.Yes 2.No

Section 1:Assessment details. Interviewer Name. Date of Interview:; ¦__¦__¦ / ¦__¦__¦ / 2022 Day Month. Town/Boma; Payam. County; State. Name of Institution/organization:. Name of respondent:; Male/Female:. Position :; Mobile phone.

| 1 | To what extent did the UN Women project involve the local community leadership structure? (Reference may be made to mobilization, sensitization, dialogue, beneficiaries’ selection, linkages, etc.)? In what role? |
| --- | --- |
| 2 | How was your relationship with the project implementation team in your location? To what extent have benefitted from the activities and outputs of the UN Women project? |
| 3 | Did you receive any training on rights of women against gender based violence and other related topics from the UN Women project? How relevant were the trainings to you? In what ways do you think you have benefitted from the training? |
| 4 | Which forms of violence have you identified as the most important to address in this community? Who are most affected? What did you as a local community leader do to try to end the risk of SGBV on women and girls in your community? |
| 5 | If a woman of girl has been raped in this community, what did you as a local community leader do to help the survivor? How successful was your intervention? What more could be done to help those who have been raped? |
| 6 | Are you aware of cases of young school girls forced into early marriages in your community? Who were the perpetrators of the gender based violence against girls? In what ways have you intervened in such situations? |
| 7 | Have there been cases of physical domestic violence by men on women in your location? Have the affected women reported to you? If yes, in what ways did you intervene? |
| 8 | To what extent do you think men and boys benefitted from the SGBV awareness and sensitization promotions organised by the community activists in your location? Extent to which rates of violence against women and adolescent girls in targeted communities has been reduced? |
| 9 | Do you feel that the project is addressing the correct issues in alleviating sexual and gender based violence against displaced and host community women and girls in this location? Have you noticed any reductions in the incidences of SGBV on women and girls in your community? |
| 10 | To what extent do you think the reporting on cases of domestic violence, physical assault, rape and other SGBV by women and girls have increased in your community? To whom do women and girls survivors of SGBV mostly report the incidences? If so, what are the possible reasons for increased reporting by women and girls? |
| 11 | To what extent has the reporting of incidences of violence and abuse by women increased or decreased in your community? What are the reasons for your observation? Have any of the culprits apprehended and punished? |
| 12 | In your opinion what have been the main challenges/gaps of the UN Women project in relation to alleviating the risk of GBV in your community? How did you as a community leader contributed to resolving some of the challenges? |
| 13 | Any reflection on what the project could have done differently/additionally in alleviating the risk of gender based violence in your community? Any lessons learnt? What worked well? What did not work well? |
| 14 | What are you as a community leader doing to maintain and /or continue to ensure that the rights of women and girls against GBV are observed and enforced in your community? Has any NGO or government body assisted you in this regards? |
| 15 | What are your recommendations to UN Women for future interventions in gender and human rights, SGBV and women empowerment in this location? What would you like to be done differently? |

UN Women Final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan”

Appendix 10: _KII UN Women Programme Staff/ Coordinator_ Project 0009879/BMZ-No.2015.4079.8

Introduction Hello, my name is -----------and I am here on behalf of UN Women, South Sudan. We are conducting a final evaluation of the “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” The main purpose of this final evaluation is to assess the achievement of project results and performance of the above-described intervention. You have been selected by chance from all stakeholders in the area for this interview. The survey is voluntary and you do not have to participate, and can withdraw consent at any time – and that there will be no consequences for doing so. The information that you give will be fed into an evaluation report, this will be share with the Government of Germany as the donor, the Ministry of Agriculture and Food Security, the Ministry of Gender, Child and social welfare, the six national NGOs involved in the implementation of the project and other relevant National/State Ministries and other government institutions, NGOs and CBOs, local community leaders and local authorities in South Sudan. The information generated by the evaluation will be used by different stakeholders to contribute to building of the evidence base on effective strategies for humanitarian and resilience response especially on WEE, ending violence against women and girls (EVAW) in South Sudan, and to facilitate UN Women’s strategic reflection and learning for programming in the area. We hope you will participate in the interview since your views are important. Could you please spare some time (around 30 minutes) for the interview? Can we begin now? 1.Yes 2.No

Section 1:Assessment details. Interviewer Name. Date of Interview:; ¦__¦__¦ / ¦__¦__¦ / 2022 Day Month. Town/Boma; Payam. County; State. Name of Institution/organization:. Name of respondent:; Male/Female:. Position :. Mobile phone.

| 1 | What is your role in the UN Women “Promoting Resilience, Self-Reliance and Social Cohesion among Displaced Populations and Host Communities with Focus on Women and Girls in South Sudan” project implemented in South Sudan? How long have you been involved with the project? |
| --- | --- |
| 2 | To what extent is the UN Women project results framework SMART, clear and logical? Are the formulated outputs and outcomes clear and realistic? Extent to which the results framework of the intervention integrated human rights and gender? |
| 3 | Was the project design based on quality analysis, including gender and human rights-based analysis, risk assessments, socio-cultural and political analysis? Extent to which the interest/priorities of women adolescent girls, men and boys and vulnerable groups and the disabled differentiated in the project document. |
| 4 | Does the UN Women project have an M&E framework with appropriate tools (including reporting methods and formats, field monitoring visits, and the use of Risk Management System (RMS)? To what extent has the M&E system produced regular and quality monitoring reports for management control and decision making? |
| 5 | How satisfactory do you feel were the UN Women procedures that were implemented during the implementation phase of the project including monitoring and reporting/disbursement of funds/approval of expenses and evaluation? What aspects could have been better? |
| 6 | To what extent did you build the organizational and technical capacities of the implementing partners? In what ways do you think the capacity building efforts for local implementing partners contributed to or hindered the success of the project in targeted locations? |
| 7 | Which state line ministries/county departments were involved in the implementation of the project? What were their roles? Any financial, material, capacity building and/or any other types of support provided to them by the project? |
| 8 | To what extent do you think the capacity building efforts for the line ministries and county departments contributed to successful implementation of the UN Women project in the various project locations? Please elaborate. |
| 9 | Were any technical supervisory visits to project location undertaken by M&E and other senior programme staff? To what extent did the meetings and supervisory visits enhance the NGOs capacity to implement the project? |
| 10 | Do you feel the project achieved the outcomes that it set for itself in relation to i) improved sustainable livelihoods and enhanced resilience of targeted populations and ii) reduced risks of SGBV? |
| 11 | What were the enabling factors (internal and external) that influenced the achievement and non-achievement of the expected outcomes? What level of effort was made by you to overcome these challenges |
| 12 | To what extent, were innovative good practices introduced in the project for the achievement of Women Economic Empowerment (WEE) and Ending Violence Against Women (EVAW) and humanitarian action results? What types of relevant interventions were implemented? To what degree of success? |
| 13 | To what extent do you feel that the project led to complementary and synergistic effects on broader UN Women efforts to promote Women Economic Empowerment (WEE) and Ending Violence Against Women and Girls (EVAW) in South Sudan? Please elaborate. |
| 14 | Has the project addressed the relevant needs of women and girls, men and young boys in this location? To what extent? Do you think that new, more relevant needs emerged that the project should address? |
| 15 | Did the project design include an exit strategy/plan for sustainability of results? Was the exit strategy put into effect to ensure sustainability of the project’s results beyond the funding period? If so, please give details. What have been the results of this strategy to date? |
| 16 | To what extent do you think the UN Women project benefits/results are likely to be sustained and generate the outcomes both ensuring livelihoods sustainability and social equity after donor funding ceases? What are the key factors facilitating/limiting the sustainability of the project benefits – especially financial, institutional, social, environmental, economic and political aspects? |
| 17 | Do you think that national/local institutions demonstrate leadership commitment and technical capacity to continue to replicate some project activities? Please elaborate? What support do you think they will require to effectively carrying out their mandates? |
| 18 | Any reflection on what the project could have done differently/additionally? Any lessons learnt? What have you as an organization learnt from this project? (the way the project was planned, implemented, coordinated and its achievement) What worked well? What did not work well? |
| 19 | What are your recommendations to UN Women for future interventions in i) WEE, EVAW, gender and human rights, and ii) access to sustainable livelihood/income generation opportunities and enhanced resilience for communities in South Sudan? What would you like to be done differently? |

Interview partners

| S/N | Name | Position | Organization& Location |  |
| --- | --- | --- | --- | --- |
| 1 | Dunstan Mubangizi | Monitoring, Evaluation & Reporting Specialist | UN Women Country Office, Juba | 0929 277 827 |
| 2 | Edfas Mkandawire | Program Specialists on Women Economic Empowerment | UNW Women Country Office, Juba | 0926 008 702 |
| 3 | Lado Jackson | Project Manager | IPCA Head Office, Muniki Block B, Juba | 0927 062 608 |
| 4 | Blantine Loice | Women Protection& Empowerment Officer | IPCA Head Office, Muniki Block B, Juba | 0925 888 138 |
| 5 | Edna Tabu | Community GBV Activist | IPCA Head Office, Muniki Block B, Juba | 0980071043 |
| 6 | Juan Jessica | Community GBV Activist | IPCA Head Office, Muniki Block B, Juba | 0923633092 |
| 7 | Julia Kapuki | Business Owner/Restaurant | Juba Nabari Luri Payam, Juba County | 0920 788 556 |
| 8 | Helen Joseph | Tailor | Muniki Block B | 0922 920 778 |
| 9 | Martin Ngule Simon | Project Manager (former) | CIRDI, Rumbek Lakes State |  |
| 10 | Peter GUM | Director General | State Ministry of Gender, Child and Social Welfare, Rumbek Lakes State | 0925 254 498 |
| 11 | Peter Rech Mathet | Deputy Executive Director | Wulu County Head Office, Wulu, Lakes State |  |
| 12 | Isaac Juma Mading | Payam Administrator | Wulu Payam, Wulu, Lakes State |  |
| 13 | Mary Philip Abdalla | Tailor | Wulu County Wulu , Lakes State | 092 812 006 |
| 14 | Kueng Maring Machar | Deputy Payam Administrator | Rumbek Center County, Rumbek, Lakes State | 0920 708 576 |
| 15 | Santino Laat Kuc | Payam Administrator | Rumbek Center County, Rumbek, Lakes State | 0922 373 180 |
| 16 | Makuet Thokrial | Paramount Chief | Matangai Payam, Rumbek Center county, Lakes State | 0923 661 232 |
| 17 | Maliir Matueng | Community GBV Activist | Rumbek Center County, Rumbek, Lakes State | 0924 084 004 |
| 18 | Deng Makueth | Community GBV Activist | Rumbek Center County, Rumbek, Lakes State | 0921 243 143 |
| 19 | Sarah Akoi | Community GBV Activist | Rumbek Center County, Rumbek, Lakes State | 0928 481 507 |
| 20 | Emanuel Ismail Ariminio | Programme Coordinator | CAO, Yambio, Western Equatoria State | 0928 302 916 |
| 21 | Francis Philomon | Adm& Finance | CAO, Yambio, Western Equatoria State | 0925 109 795 |
| 22 | Isaac Alex | Livelihood Officer | CAO, Yambio, Western Equatoria State | 0928 357 980 |
| 23 | Clement Bullen | Community GBV Activist | Yambio Payam, Yambio County, Western Equatoria State | 0920 700 551 |
| 24 | Hipai Suzan | Community GBV Activist | Yambio Payam, Yambio County, Western Equatoria State | 0927 397 403 |
| 25 | Lina Luciano | Community GBV Activist | Yambio Payam, Yambio County, Western Equatoria State |  |
| 26 | Suzan Simon | Community GBV Activist | Yambio Payam, Yambio County, Western Equatoria State | ,0920 790 688 |
| 27 | Livia Constantino | Director for Gender | State Ministry of Gender, Child and Social Welfare, Yambio | 0924 873 904 |
| 28 | Madelena Juani Samson | Deputy Director for Gender | State Ministry of Gender, Child and Social Welfare, Yambio | 0925 042 158 |
| 29 | Daniel Nlathoga | Director General | State Ministry of Agriculture and Forestry, Yambio | 0920 703 287 |
| 30 | Susan Angelo | Tailor | Yambio Payam Yambio County | 0929 108 042 |
| 31 | Justin Ebere | Chairperson Board of Directors | CAO, Yambio, Western Equatoria State | 0928887017 |
| 31 | Victor Diko | Secretary, Board of Directors | CAO, Yambio, Western Equatoria State | 0926056667 |
| 31 | Sila Lomus | Treasurer , Board of Directors | CAO, Yambio, Western Equatoria State | 0925615803 |
| 32 | Aya Benjamin Libo Warilla | Minister of Gender | MGCSW |  |
| 33 | Esther Ikere | Undersecretary | MGCSW |  |
| 34 | Regina Ossaluma | Director General for Gender and Child Welfare | MGCSW |  |
| 35 | Emmanuel Ladu Lako | Acting Director Planning and Research | MGCSW |  |
| 36 | Rosemarie Hille | Women Peace & Security, Stabilization, Humanitarian Aid | German Embassy Juba | 0918 924 698 |

References and background documents

GERAAS Guidance Note, Aug 2019

Independent Evaluation Office (IEO) ‘Global Evaluation Report Assessment and Analysis System’ (GERAAS), Jan 2015

Narrative implementation reports by SPEDP, CAO, IPCA, CIRDI

United Nations Evaluation Group (UNEG) Norms and Standards for Evaluation in the UN System

UNW Terms of reference: International consultant/Evaluator for the final evaluation of the ‘Promoting resilience, self-reliance and social cohesion among displaced populations and host communities with focus on women and girls in South Sudan and Mali

UNW, Evaluation Strategy to Transform Women’s and Girls’ Lives 2018-2021, Jan 2018

Project reports

UNW, Final Project Report. Sustainable livelihood activities for women and reduction of sexual and gender based violence among displaced population and host communities in South Sudan and Mali

UNW, First – Fourth Project Progress Reports

CHANGE AGENCY ORGANIZATION (CAO), Quarterly report, Yambio 290420

CAO, Summary report to evaluators, Yambio

CIRDI Child marriage training message

CIRDI End of Project Report women IDP South Sudan Wulu Jan-May 2020 280820

CIRDI Final Report Wulu March to May 2019

CIRDI INTERIM ANNUAL Report_Wulu – mAY 2020 150520

CIRDI Interim report Wulu county May 2020 150520

CIRDI Report Rapid Market Assessment in Wulu County

IPCA - UNWOMEN Partner FINAL Narrative REPORT Mundri Mungkaman 2020 150520

IPCA-DRAFT Partner Narrative REPORT Mundri-West 2020 150520

IPCA-Final_Narrative_Report Mundri-West_2019_15_08_2019

IPCA, UNWOMEN partner final narrative report 2020

IPCA, Final report: IPCA-RWSS Humanitarian Assistance Programme Mundri-West county, submission date 8th May 2018

Report on the Awerial Project 120520

Support for Peace and Education Development Program (SPEDP), Effect of Covid-19 on UNWomen project

Support for Peace and Education Development Program (SPEDP), Final Narrative Report, April-June 2019

Support for Peace and Education Development Program (SPEDP), Final Narrative Report, 300620

Support for Peace and Education Development Program (SPEDP), List of VSLA groups in Magwi

Support for Peace and Education Development Program (SPEDP), Mid-Year Report 2020

Support for Peace and Education Development Program (SPEDP), Narrative report start to April 2020

Support for Peace and Education Development Program (SPEDP), Success stories from SPEDP UN-Women Nimule project area

UNW, Partner narrative report, Strengthening capacities of women peace networks to coordinate local peace initiatives in Wau, Yambio and Juba counties, 11.1.2021

UNW, Final Project Report. Sustainable livelihood activities for women and reduction of sexual and gender based violence among displaced population and host communities in South Sudan and Mali

UNWomen First Progress Report to Germany women IDP South Sudan Jan-Dec_2016

UNWomen Second Progress Report to Germany women IDP South Sudan Jan-Dec 2017

UNWomen Third Annual Progress Report to Germany women IDP South Sudan Jan-Dec 2018

UNWomen Fourth Progress Report to Germany women IDP South Sudan Jan-Dec 2019

Abbreviations

CAO		Change Agent Association/Organisation

CIRDI		Community Integrated Rural Development Initiative

ERG		Evaluation Reference Group

EVAW		ending violence against women and girls

FAL

FGD		focal group discussion

GBV 		gender-based violence

GERAAS	Global Evaluation Report Assessment and Analysis System

PHCU

IDP		internal displaced person

INGO		international non-government organisation

IPCA		Initiative for Peace Association

KII		key informant interview

MGCSW 	Ministry of Gender, Child and Social Welfare

OECD/DAC	Organisation for Economic Cooperation and Development / Development Assistance Committee

SGBV		sexual and gender based violence

SMART 	specific, measurable, achievable, relevant, and time-bound

SMGCSW	State Ministry of Gender, Child and Social Welfare

SPEDP	Support for Peace and Education Development Programme

SDG		Sustainable Development Goal

SSDP		South Sudan Development Plan 2011-13

SSNDS	South Sudan National Development Strategy 2018-2021

SSWEN	South Sudan Women Network

ToT		trainers for trainers

UNEG		United Nations Evaluation Group

UNW		United Nations Women

VAWG	violence against women and girls

VSLA		Village Savings and Loan Association

WEC		Women Empowerment Centre

WEE		women economic empowerment