TERMS OF REFERENCE

Country Programme Evaluation (CPE) of UN Women Malawi Country Office (CO) Strategic Note (SN) 2016-2021.

| Location: | Malawi |
| --- | --- |
| Languages Required: | Fluent English |
| Duration of Initial Contract: | 45 working days |
| Expected Duration of Assignment: | 6 months |

# Introduction and purpose of the CPE

A Country Portfolio Evaluation (CPE) is a gender-responsive systematic assessment of the performance and contributions made by a Country Office for the achievement of gender equality results in the country they serve. The CPE utilizes the entity’s strategic plan as a reference for measuring progress towards the achievement of expected outcomes and impacts. Similar, to other evaluations, the CPE is compliant with UN Women Evaluation Policy and aligned with the United Nations Evaluation Group (UNEG) Norms and Standards for Evaluation in the UN System and Ethical Guidelines. The CPE is being led by the Independent Evaluation Service (IES) of the Independent Evaluation and Audit Services of UN Women (IEAS).

The evaluation will serve a dual and mutually reinforcing learning and accountability purpose as it provides an opportunity to: (i) consolidate learning from what worked and what could be done differently; and (ii) offer evidence-informed insights to support the development of a new Strategic Note covering the period 2022 to 2027. In general, the CPE will examine UN Women’s integrated mandate, its comparative and collaborative advantages, and the synergies among thematic areas to establish a trajectory of results and analysis of medium- to long-term changes along the development and humanitarian nexus over the five -year period.

Specifically, the CPE will assess the UN Women Malawi’s strategic positioning, and the relevance, effectiveness, efficiency, and sustainability of the portfolio with reference to the Strategic Note cycle of 2016-2021. The CPE will target programmes and projects that the CO has implemented during the past 5 years, with a special focus on the Women Empowerment Programme implemented with funding from the Royal Norwegian Embassy. The CPE focuses on their individual and combined success in advancing gender equality in Malawi. It uses the Strategic Note as the main point of reference.

In particular, the evaluation will examine:

- the level of efficiency, effectiveness, and sustainability of UN Women thematic areas and integrated mandate and explanations for these results (including factors beyond UN Women’s control).

- the level of synergy and multiplying effect between the various thematic areas and the integrated mandate including leveraging opportunities with partners (joint programmes, contribution to UNDAF (UNSDCF), national capacity, legislative frameworks etc).

- the level of organizational effectiveness and efficiency results including risk mitigation measures, resources stewardship, organizational structure, results-based management) to understand these drivers of strategy and how they were considered and managed; and

- identify and validate lessons learned, good practices and examples of innovation that support gender equality and women’s empowerment and provide actionable recommendations to feed into     to the forthcoming Strategic Note and its engagement in system-wide initiatives and review processes including UNSDCF annual and mid-term reviews.

The proposed CPE will be a transparent and participatory process. To achieve this the evaluation methodology will involve all relevant UN Women Malawi CO staff, stakeholders, and partners at national and sub-national levels. The CPE will be based on gender and human rights principles, as defined in the UN Women Evaluation Policy, and adhere to the UN norms and standards for evaluation in the UN System.

# Background (programme/project context)

UN Women's mandate (GA resolution 64/289) is to lead, coordinate and promote accountability of the UN system to deliver on gender equality and women empowerment with the primary objective of enhancing country-level coherence, ensuring coordinated interventions, and securing positive impacts on the lives of women and girls, including those living in rural areas.

The Country Office (CO) Strategic Note (SN) is the main planning tool for UN Women’s support to normative, coordination and operational work in Malawi. The SN is aimed at ensuring that Women and girls enjoy their full rights and positively contribute to, and benefit from, social economic and political development in Malawi by December 2021. The SN has largely been implemented through the Women Empowerment Programme which consists of three thematic components namely, Gender and governance: Women and Youth empowerment through enterprise development and Elimination of Violence against women and girls.

The UN Women portfolio is focused around its three-fold mandate, which includes normative, operation and coordination work.

- Normative work: to support inter-governmental bodies, such as the Commission on the Status of Women (CSW) and the General Assembly, in their formulation of policies, global standards and norms. The Strategic Note 2016 – 2021 is grounded in the standards, principles, and obligations of the Convention to Eliminate all forms of Discrimination Against Women (CEDAW), Beijing Declaration and Platform for Action, Concluding Observations of the Commission on the Status of Women, UNSCR 1325, CEDAW Concluding Observations on the combined 4th and 5th periodic reports. The SN is designed in support of the international commitments and national strategies and in support of efforts led by governments and CSOs. The SN is aligned to UN Women Global Strategic Plans 2014 – 2017 and 2018 – 2021.

- Operational work: to help Member States to implement international standards and to forge effective partnerships with civil society; and

- Coordination work: entails both 1) work to promote the accountability of the United Nations system on gender equality and women empowerment (GEWE), including regular monitoring of system-wide progress, and more broadly 2) work to mobilize and convene key stakeholders to ensure greater coherence and gender mainstreaming across the UN.

The main interventions undertaken across three mandate areas under the Strategic Note 2016 – 2021 are:

Normative; Coordination; Impact Areas as per the Annual Workplan. Enhanced dialogue among the Gender machinery on implementation of Gender equality related national, regional, and international normative and policy frameworks. Support implementation and tracking progress of SDG 5, CEDAW. Support to Beijing +20 and +25 national Review Support to CEDAW and Istanbul Convention national and shadow reports; Member of the UNCT Lead of UNCT Gender Theme Group (GTG) Lead of Results Group on Gender Equality (RGEW) Co-lead of International Working Group on Gender Equality Consultations with Civil Society Advisory Group (CSAG) Quarterly coordination with Gender mechanisms; Impact Area 6: A comprehensive and dynamic set of global norms, policies and standards on gender equality and women & girls’ empowerment is strengthened and implemented. Impact Area 1: Women lead, participate in, and benefit equally from governance systems. Impact Area 3: Women and girls live a life free of violence. Impact Area 2: Women have income security, decent work, and economic autonomy. Impact Area 4: Peace, security, transitional justice, and humanitarian action shaped by women leadership and participation..

Development Results; Annual Budgets. 2018; 2019; 2020; 2021. Impact Area 1: Women lead, participate in, and benefit equally from governance systems.; 672,993; 1,112,611; 957,656; 239,000; 590,000. Impact Area 3: Women and girls live a life free of violence.; 732,947; 996,398; 3,387,895; 5,243,165; 4,785,934. Impact Area 2: Women have income security, decent work, and economic autonomy.; 929,000; 857,722; 909,218; 797,117; 330,232. Impact Area 4: Peace, security, transitional justice, and humanitarian action shaped by women leadership and participation.; 250,000; 600,163; 170,000; 1,217,203. Global norms policies and standards; 459,480; 561,660; 269,299; 260,000.

In line with UN Women’s commitment to Results Based Management, a Development Results Framework (DRF) was developed with performance indicators. The Strategic Note includes an Organisational Effectiveness and Efficiency Framework (OEEF) with performance indicators on coordination and strategic partnership, organizational effectiveness, communications, and financial management. The evaluation is expected to use this to assess organizational performance.

# Evaluation objectives, criteria, and questions

This CPE is commissioned as a primary formative (forward-looking) evaluation to support the Country Office (CO) and national stakeholders’ strategic learning and decision-making for the next Strategic Note, due to be developed in 2021. The evaluation is expected to have a secondary summative (backwards looking) perspective, to support enhanced accountability for development effectiveness and learning from experience.

The primary intended users of this evaluation are:

- UN Women Malawi CO, Regional Office, and UN Women HQ

- Target groups, their households and community members, programme/project partners

- National government institutions

- Civil society representatives

- Donors and development partners

- UN Country Team and GTG

Primary intended uses of this evaluation are:

- Learning and improved decision-making to support the development of the next Strategic Note 2022-2027.

- Accountability for the development effectiveness of the CO Strategic Note 2022-2027in terms of UN Women’s contribution to gender equality and women’s empowerment.

- Capacity development and mobilisation of national stakeholders to advance gender equality and women empowerment.

The specific evaluation objectives include:

1.	Assess the relevance of UN Women contribution to the intervention at national levels and alignment with international agreements and conventions on gender equality and women’s empowerment.

2.	Assess effectiveness and organizational efficiency towards the achievement of gender equality and women’s empowerment results as defined in the Strategic Note.

3.	Support the UN Women Malawi CO to improve its strategic positioning to better support the achievement of sustained gender equality and women’s empowerment.

4.	Analyse how human rights approach and gender equality principles are integrated in the design and implementation of the Strategic Note.

5.	Identify and validate lessons learned, good practices and examples of innovation that supports gender equality and human rights.

6.	Provide insights into the extent to which the UN Women Malawi CO has realized synergies between its three mandates (normative, coordination and operations).

7. 	Provide actionable recommendations with respect to the development of the next UN Women Malawi CO Strategic Note.

The evaluation will apply four OECD/DAC evaluation criteria [relevance, effectiveness (including normative, and coordination mandates of UN Women), efficiency, human rights and gender equality, coherence, and sustainability] and Human Rights and Gender Equality as an additional criterion. The evaluation will seek to answer the following key evaluation questions and sub-questions:

| Key Criteria | Key Questions | Sub Criteria | Sub Questions |
| --- | --- | --- | --- |
| Relevance | Are we doing the right things? | Alignment and positioning | Is the portfolio and the Women Empowerment Programme aligned with national policies and international human rights norms? What is UN Women’s comparative advantage in this area of work compared with other UN entities and key partners? |
| Efficiency | Are we doing things, right? | Organizational Efficiency | To what extent does the management structure support efficiency for implementation? Does the organization have access to the necessary skills, knowledge and capacities needed to deliver to the portfolio? Has a Results Based Management system been established and implemented? |
|  |  | Coherence | Are the interventions achieving synergies within the UN Women portfolio and the work of the UN Country Team? Is the balance and coherence between programming- operational, coordination and policy‐normative work optimal? |
|  |  | Human Rights and Gender Equality | Which groups is the portfolio reaching the most, and which are being excluded? Has the portfolio been implemented according to human rights and development effectiveness principles: - Participation/empowerment. - Inclusion/non-discrimination. - National accountability/ transparency. |
| Effectiveness | Are the things we are doing working? | Operational mandate | To what extent have planned outputs/outcomes been achieved on time? Are interventions contributing to the expected outcomes? What unexpected outcomes (positive and negative) have been achieved? What are the main enabling and hindering factors behind observed outcomes? |
|  |  | UN Coordination | What contribution is UN Women making to UN coordination on GEWE? To what extent has gender equality and women’s empowerment been mainstreamed in UN joint programming such as UNSDCF? |
|  |  | Normative | What contribution is UN Women making to implementing global norms and standards for gender equality and women empowerment? |
| Sustainability | Will the changes last? | Capacity development | To what extent was capacity developed to ensure sustainability of efforts and benefits? |
|  |  | Ownership | Is there national ownership and are there national champions for different parts of the portfolio? What local accountability and oversight systems have been established? |
| Human Rights and Gender Equality | Are the things we are doing working? | Human Rights and Gender Equality | Is the choice of partners most relevant to the situation of women and marginalized groups, including women with disabilities? Is the choice of interventions most relevant to the situation in the target thematic areas? Do interventions in general and particular for the WEP program contribute to target the underlying causes of gender inequality? Is the portfolio addressing the root causes of gender inequality? To what extent is the portfolio changing the dynamics of power in relationships between different groups? |
| Coherence | Are the things we are doing working? | compatibility | Are the key interventions implemented through various programmes or projects compatible with other interventions in the country? Is there any potential duplication of efforts in this area? |

As part of the inception meeting the evaluation team will review agreed indicators for answering each evaluation question.

The evaluation is expected to take a human right and gender-responsive approach in identifying how the Strategic Note tackles factors and structures of political and social control that maintain gender inequality. This ensures that the data collected is analysed in relation to relevant international normative frameworks, human rights and gender equality, inclusiveness – Leaving No one behind and disability, power relations and sustainability. The preliminary findings obtained through this process should be validated through a stakeholder workshop with evaluation management and reference groups towards the end of the primary data collection stage.

# Scope of the evaluation

This evaluation will consider the current Strategic Note covering the period 2016 – 2021. A new Strategic Note is due to be developed in 2021, for the period 2022 – 2027. The period covered by the evaluation will be 2016-2021. The CPE will focus on all activities undertaken by the CO under the Strategic Note, including general support to normative policy and UN coordination. Programme work will be considered in relation to the thematic areas established by the UN Women Strategic Plan 2021-2027.

As most of the CO work takes place around the country, including remote districts, the evaluators are expected to visit several sites during the field mission to Malawi. All COVID preventive measures will be adhered to and these include wearing of face masks, maintaining social distance, limiting participants during meetings in line with the guidelines.

VI. Evaluation design (process and methods)

The evaluation team is expected to undertake a rapid evaluability assessment in the Inception. This should include the following:

- An assessment of the relevance, appropriateness, and coherence of the implicit or explicit theory of change, strengthening or reconstructing it where necessary through a stakeholder workshop.

- An assessment of the quality of performance indicators in the DRF and OEEF, and the accessibility and adequacy of relevant documents and secondary data.

- A review of the conduciveness of the context for the evaluation.

- Ensuring familiarity with accountability and management structures for the evaluation.

The evaluation will be carried out following the UN Evaluation Group (UNEG) Norms and Standards (see http://www.unevaluation.org/document/detail/1914), as well as the Ethical Guidelines for evaluations in the UN system. The evaluation will also apply the UN Women GERAAS evaluation report quality checklist and the UNEG Technical Note on the SWAP Evaluation Performance Indicator. In line with Norms and Standards a management response will be prepared for this evaluation as practical means to enhance the use of evaluation findings and follow-up to the evaluation recommendations. The management response will identify who is responsible, what are the action points and deadlines.

The evaluation will use a theory-based cluster design. The performance of the country portfolio will be assessed according to the theory of change stated in the Strategic Note 2016-2021. To achieve sufficient depth, the evaluation will cluster programming, coordination, and policy activities of the Country Office around the thematic areas stated in the UN Women Strategic Plan 2015-2020. It will provide special focus on the Women Empowerment Programming which comes to an end in March 2021.

The evaluation will undertake a desk-based portfolio analysis that includes a synthesis of secondary results data for the Development Results Framework (see Annex [X]) and the Organizational Effectiveness and Efficiency Framework (see Annex [X]) of the Country Office. This will cover all activities undertaken by the Country Office.

The portfolio analysis will include:

- Desk review of documentary evidence. The method should include a wide range of data sources (including documents, field information, institutional information systems, financial records, beneficiaries, staff, funders, experts, government officials and community groups).

- Consultation with main stakeholders; and

- An independent assessment of development effectiveness using Contribution Analysis.

The evaluation will identify expected and unexpected changes in target and affected groups. It is anticipated that the evaluation will apply process tracing to identify the mechanisms of change and the probable contributions of UN Women. It is suggested that mixed qualitative/quantitative cases of different target groups be developed, compared, and contrasted. The evaluation team will identify which factors, and which combinations of factors, are most frequently associated with a higher contribution of UN Women to expected and unexpected outcomes.

The CPE is being led by the Independent Evaluation Service (IES) of the Independent Evaluation and Audit Services of UN Women (IEAS). The evaluation will use participatory methods to ensure that all stakeholders are consulted as part of the evaluation process. At a minimum, this should include participatory tools for consultation with stakeholder groups and a plan for inclusion of vulnerable and/or marginalized women and individuals and groups who are in the consultation process (see below for examples).

The use of participatory analysis, video, photography, or other methods are particularly encouraged as means to include rights holders. The evaluator should specify how protection of participants and respect for confidentiality will be guaranteed.

The evaluation will use the following data collection tools:

- Interviews.

- Secondary document analysis.

- Observation.

- Multimedia (photography, drawing).

- Others.

The evaluators should take measures to ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights; for example, the limitations of the sample (representativeness) should be stated clearly, and the data should be triangulated (cross-checked against other sources) to help ensure robust results.

The evaluation is expected to reconstruct the theories of change using a participatory process during the evaluation. This should be critiqued based on feminist and institutional analysis.

The CPE will sample programmes and projects that the CO has implemented during the past 5 years. Special attention will be given to the WEP in a case study as described below.

VII. Case Study

A deep-dive case study model will be employed purposively on the three thematic areas of the Women Empowerment Programme and on selected thematic or sub-thematic areas of other programmes/projects. The selected thematic or sub -thematic areas will be discussed and confirmed with the CO management and programme staff to ensure adequate coverage and representation of intervention areas. The WEP constituted the largest share of programme resources during the SN period. Other criteria for selecting the case study include interventions were advanced enough that results had emerged; the holistic approach would allow assessment of synergy, complementarities, and impact across different thematic areas; a mix of investment across the CO’s composite mandate; and geographical concentration of interventions will facilitate data collection in selected districts and local sites. Baseline benchmarks are also available to track progress over time.

In general, with the use of the case study, the CPE will seek to unpack the degree to which the project/s have catalysed and accelerated progress towards GEWE through influence of wider programme strategies or policies or through adoption of innovative approaches. Performance will also be examined through the lens of cost efficiency analysis / gains regarding operations, procurement, implementation modalities, execution of advocacy campaigns/communication activities and capacity development interventions particularly workshops/training     . The approach and methods for cost consciousness analysis will be further elaborated in the evaluation matrix.  Data will be collected from secondary and primary sources including stakeholders and beneficiaries at different levels (national, state, UN partners, CSOs/CBOs, and local governments). The number and location of field visit sites for the case study/ies will be determined in consideration of having a good mix of the portfolio.

# Stakeholder participation

The evaluators are expected to detail how the evaluation will ensure participation of stakeholders during the design, consultations, data collection, analysis and interpretation and reporting writing. It is expected that the evaluation will target community members, Civil Society Implementing Partners, government institutions, Private sector, Political leaders, and representatives, Donors and development partners, UN Country Team, and others.

The evaluators are encouraged to further analyse stakeholders according to the following characteristics: System roles (target groups, programme controllers, sources of expertise, and representatives of excluded groups), Gender roles (intersections of sex, age, household roles, community roles), Human Rights roles (rights holders, principal duty bearers, primary, secondary, and tertiary duty bearers).

They are expected to validate findings through engagement with stakeholders at stakeholder workshops, debriefings, or other forms of engagement.

VI	Intended users and uses of the evaluation.

The evaluators are encouraged to extend this analysis through mapping relationships and power dynamics as part of the evaluation. It is important to pay particular attention to participation of rights holders—women and vulnerable and marginalized groups—to ensure the application of a gender-responsive approach. It is also important to specify ethical safeguards that will be employed.

# VII	Time frame for Senior Evaluator and Three Evaluators-Team Members

The evaluation is expected to be conducted within a period of 66 days of which 45 days are billable for the International Consultant and 30 days for each of the two national consultants (preliminary estimations):

| Task | Time frame (Nr. of days) | Effort (Nr. of days) – International Consultant | Effort (Nr. of days) – National Consultants | Responsible party |
| --- | --- | --- | --- | --- |
| Desk review and preparing the inception meeting (reviewing UN Women Malawi 5-year programming) | 10 | 7 | 7 |  |
| Virtual inception meeting/workshop between evaluators, CO, and stakeholders | 1 | 1 | 1 | Evaluators / UN Women CO |
| Drafting Inception report | 7 | 3 | 3 | Evaluators ERG, EMG |
| Evaluation Reference Group and Evaluation Management Group Comments | 3 | 0 | 0 |  |
| Inception report revision | 2 | 2 | 1 |  |
| Data collection | 18 | 14 | 14 | Evaluators |
| Presentation of preliminary findings (post data collection) | 3 | 1 | 1 | Evaluators |
| Draft Report | 22 | 14 | 7 |  |
| Evaluation Reference Group and Evaluation Management Group Comments | 6 | 0 | 0 | ERG and EMG |
| Report revision and Final Report submission | 8 | 3 | 1 | Evaluator |
| Sub-Total | 66 | 45 | 35 |  |
| Use and follow-up post final report | 6 weeks | — |  | UN Women |

Under the guidance of evaluation team leader, the evaluators are expected to design and facilitate the following processes:

- Virtual inception workshop (including refining evaluation questions, the evaluation framework, stakeholder map, and theories of change).

- In-country participatory data collection mission for UN Women staff and key stakeholders.

- Findings, validation, and participatory recommendations session.

# Expected deliverables.

The following are the deliverables expected from the evaluation. The consultants will be accountable for the portion of deliverable assigned by the Team Leader.

| Deliverable | Time frame for submission | Person responsible |
| --- | --- | --- |
| Inception report Word format (including rounds of revision) | 2 Weeks after signing of contract | Evaluation team leader (EMG and ERG feedback) |
| Preliminary findings presentation | 2-3 weeks after final data collection |  |
| Draft report Word format (including rounds of revision) | 4 weeks after final data collection | (Evaluation team leader EMG and ERG feedback) |
| Final report | 4 weeks after submission of draft report | Evaluation team leader (EMG and ERG feedback) |
| Management Response | 2-3 weeks after final report | Malawi CO Representative |

The evaluation manager and the regional evaluation specialist will quality assure the evaluation report. The draft and final evaluation report will be shared with the evaluation reference group, and the evaluation management group for quality review. The final evaluation report will be independently assessed using quality standards outlined in the UNW Global Evaluation Reports Assessment and Analysis System (GERAAS). The final evaluation report and evaluation management responses will be publicly disclosed in the UNW GATE system. The final report will be approved by the evaluation management committee.

# Management of the evaluation

The management structure for this evaluation will include:

- WCA Regional Evaluation Specialist (RES) will be the evaluation team leader for this evaluation and will be supported by the UN Women MWI CO M&E Sp during the evaluation process.

- Evaluation Management Group for administrative support and accountability will include: the Regional Evaluation Specialist (IES), a Programme Manager delegated by the CO, the M&E Officer.

- Evaluation Reference Group for substantive technical support: Representatives from Malawi Government – Ministry of Gender; Civil Society Advisory Group; Academia; representative of the UNCT, and from Civil Society Organizations implementing partners.

The main roles and responsibility for the management of the evaluation reports are:

| Evaluation team leader (UN Women WCA RES) | - Leads the conceptual and methodological approach and other aspects of the evaluation design. - Leads the preparation of deliverables. - Ensures team members have the full freedom to conduct their evaluative work impartially and can express their opinion in a free manner. - Coordinates feedback on the draft and final report from the management and reference groups. - Maintains an audit trail of comments on the evaluation products so that there is transparency in how the evaluation team is responding to the comments. |
| --- | --- |
| Evaluation team (senior evaluator and evaluator-team members) | - To avoid conflict of interest and undue pressure, the members of the evaluation team need to be independent. - Under the guidance of the evaluation team leader, the evaluation team works together with the team leader in preparing all evaluation products, which should reflect an agreed- upon approach and design for the evaluation from the perspective of the evaluation team and the evaluation team leader. |
| The M&E Specialist | - will manage document retrievals and access. - facilitate contacts with evaluation participants. - organize logistics for the field mission. |
| Evaluation Reference groups | - Provide substantive comments and other operational assistance throughout the preparation of reports. - Where appropriate, participates in meetings and workshops with other key partners and stakeholders before finalization of reports. |

To maximize stakeholder participation and ensure a gender-responsive evaluation, the evaluation team leader will support the evaluator(s) during data collection in the following ways:

- Coordinate gathering and filing of documents related to the 5-year programme period for desk review.

- Consult partners regarding the evaluation and the proposed schedule for data collection.

- Arrange for a debriefing by the evaluator(s) prior to completion of data collection to present preliminary and emerging findings or gaps in information to the evaluation manager, evaluation management and reference groups.

- Ensure the stakeholders identified through the stakeholder analysis are being included, the most vulnerable or difficult to reach, and provide logistical support as necessary contacting stakeholders and arranging for transportation.

- Ensure that a gender equality and human rights perspective is streamlined throughout the approach, and that the evaluator(s) is abiding by the ethical principles outlined below.

All payments are subject to the approval of deliverables by the evaluation management group. The approval of each deliverable will be based on assessment of deliverables against GERAAS evaluation parameters. Payments will be done upon approval of the following outputs:

- 20%: upon approval of the inception report. The consultant will be accountable for the portion of deliverable assigned by the Team Leader.

- 30%: upon appreciation that the draft reports / case studies meets minimum requirements

- 50%: upon approval of the evaluation report / case studies.

# Evaluation team composition, skills, and experiences

A team of four consultants one Senior Evaluator, and three other National Evaluators and Experts on (1) Gender Based Governance and Humanitarian) (2) Violence Against Women and Girls (3) Women Economic Empowerment will work together and undertake the evaluation. The estimated number of person-days required for the evaluation is 45 days for the Senior Evaluator and 35 days for the Evaluators / Team Members.

The Senior Evaluator must possess the following qualifications:

Education:

- At least a master’s degree in sociology, international development, gender/women studies, or related area

Experience:

- At least 15-years practical experience in conducting gender-responsive evaluations of development strategies, policies and programs.

- Extensive knowledge of, and experience in applying, qualitative and quantitative evaluation methods.

- A strong record in designing and leading evaluations.

- Proven knowledge of the role of UN Women and its programming, coordination, and normative roles at the regional and country level

- Country or regional experience in the region.

- Excellent analytical, facilitation and communications skills and ability to interact with a wide range of stakeholders.

- Process management skills, including facilitation presentations and communication skills.

- Experience on women peace and security is considered a strong asset.

- Experience in conflict and post conflict countries is considered a strong asset.

The Three Evaluators/Team members must possess the following qualifications:

Education:

- At least a Master’s degree in sociology, gender, international development, social sciences, or another related area

Experience:

- Minimum 7 years of professional experience on relevant development GEWE related issues, including substantive support to several evaluation processes.

- Experience in evaluation any of the three thematic components namely, Gender and governance: Women and Youth empowerment through enterprise development and Elimination of Violence against women and girls.

- Technical knowledge in monitoring and evaluation

- Experience of gender analysis and human rights-based approaches

- Process management skills, including facilitation and communication skills with stakeholders.

- Data analysis skills

Evaluators should have proven commitment to the core values of the United Nations, in particular respecting differences of gender, ethnicity, religion, culture, nationality, language, age, HIV status, disability, and sexual orientation, or other.

XII. Ethical code of conduct

UN Women has developed a UN Women Evaluation Consultants Agreement Form for evaluators that must be signed as part of the contracting process, which is based on the UNEG Ethical Guidelines and Code of Conduct. These documents will be annexed to the contract. The UNEG guidelines note the importance of ethical conduct for the following reasons:

1.	Responsible use of power: All those engaged in evaluation processes are responsible for upholding the proper conduct of the evaluation.

2.	Ensuring credibility: With a fair, impartial, and complete assessment, stake- holders are more likely to have faith in the results of an evaluation and to take note of the recommendations.

3.	Responsible use of resources: Ethical conduct in evaluation increases the chances of acceptance by the parties to the evaluation and therefore the likelihood that the investment in the evaluation will result in improved outcomes.

The evaluators are expected to provide a detailed plan on how the following principles will be ensured throughout the evaluation (see UNEG Ethical Guidance for descriptions): 1) Respect for dignity and diversity; 2) Right to self-determination; 3) Fair representation; 4) Compliance with codes for vulnerable groups (e.g., ethics of research involving young children or vulnerable groups); 5) Redress; 6) Confidentiality; and 7) Avoidance of harm.

Specific safeguards must be put in place to protect the safety (both physical and psychological) of both respondents and those collecting the data. These should include:

- Ensuring that data collection and interviews abide by guidelines set by the Malawi Government on prevention of COVID.

- Ensuring excluded and marginalized groups are not further excluded from participating in the CPE.

- A plan is in place to protect the rights of the respondent, including privacy and confidentiality.

- The interviewer or data collector is trained in collecting sensitive information, and if the topic of the evaluation is focused on violence against women, they should have previous experience in this area.

- Data collection tools are designed in a way that are culturally appropriate and do not create distress for respondents.

- Data collection visits are organized at the appropriate time and place to minimize risk to respondents.

- The interviewer or data collector can provide information on how individuals in situations of risk can seek support.

The evaluation’s value added is its impartial and systematic assessment of the programme or intervention. As with the other stages of the evaluation, involvement of stakeholders should not interfere with the impartiality of the evaluation.

The evaluator(s) have the final judgment on the findings, conclusions and recommendations of the evaluation report, and the evaluator(s) must be protected from pressures to change information in the report.

Application process

Interested candidates should apply online following relevant instructions and deadline indicated in the call for applications. Candidates should submit:

- a letter of interest with indication of availability during the period of four consecutive months May to August 2021.  The letter of intent should include a declaration of any involvement with any UN-Women work over the period, or potential partners, and that the candidate declare that there is no potential conflict of interest.

- a personal CV, not exceeding three pages. The candidate is highly encouraged to provide information in relation to relevant experience to the evaluation in her/his CV.

- a sample evaluation report authored recently by the applicant which will be assessed against UN Women’s GERAAS parameters.

Shortlisted candidates will be requested to take a short oral interview, and share references,

Annex 1 Key references

- Guidance on Country Portfolio Evaluations in UN Women:

At UN Women Independent Evaluation Office website:

https://www.unwomen.org/en/digital-library/publications/2016/3/guidance-on-country-portfolio-evaluations-in-un-women

- UN Women GERAAS evaluation quality assessment checklist.

UN Women Independent Evaluation Office website at

http://www.unwomen.org/en/about-us/evaluation/decentralized-evaluations

- UN Women Evaluation Consultants Agreement Form.

UN Women Evaluation Consultants Agreement Form http://gate.unwomen.org/ , UNEG Ethical Guidelines and Code of Conduct for Evaluation in the UN system http://www.uneval.org/document/detail/100

- UNEG Norms and Standards for evaluation.

At UNEG website http://www.unevaluation.org/document/detail/1914

- UN Women Evaluation Handbook

At UN Women Independent Evaluation Office website: http://genderevaluation.unwomen.org/en/evaluation--‐handbook

- Resources for data on gender equality and human rights.

At UN Office of the High Commissioner for Human Rights (OHCHR) – Universal Human Rights Index: http://uhri.ohchr.org/en

At UN Statistics website– Gender Statistics: http://genderstats.org/

- UNDP Human Development Report – Gender Inequality Index:

At UNDP website: http://hdr.undp.org/en/content/gender-inequality-index-gii

- World Bank – Gender Equality Data and Statistics:

At World Bank website: http://datatopics.worldbank.org/gender/

- Organisation for Economic Co-operation and Development (OECD) Social Institutions and Gender Index

At OECD website: http://genderindex.org/

- World Economic Forum – Global Gender Gap Report

At world Economic Forum website:  http://www.weforum.org/issues/global-gender-gap

- A listing of UN reports, databases and archives relating to gender equality and women’s human rights can be found at: http://www.un.org/womenwatch/directory/statistics_and_indicators_60.htm

The key principles for gender-responsive evaluation at UN Women: 1) National ownership and leadership; 2) UN system coordination and coherence regarding gender equality and women empowerment; 3) Innovation; 4) Fair power relations and empowerment; 5) Participation and inclusion; 6) Independence and impartiality; 7) Transparency; 8) Quality and credibility; 9) Intentionality and use of evaluation; and 10) Ethics.

UNEG, “Norms for evaluation in the UN system”, 2005, available online at: http://www.unevaluation. org/document/detail/21, and “Standards for evaluation in the UN system”, 2005, available online at: http://www.unevaluation.org/document/detail/22.

UNEG, “Ethical guidelines”, 2008, available online at: http://www.unevaluation.org/document/detail/102.

Three specific criteria will be used for the analysis of the strategic positioning: strategic alignment, responsiveness and added value.

Guidance on a gender-and human rights responsive evaluation approach is available in the UN Women Evaluation Handbook and in the UNEG Guidance on Integrating Human Rights and Gender Equality in Evaluations

A theory based-design assesses the performance of the Strategic Note based upon its stated assumptions about how change happens. These assumptions can be challenged, validated or expanded upon by the evaluation.

A cluster evaluation assess a large number of interventions by ‘grouping’ similar interventions together into ‘clusters’, and evaluating only a representative sample of these in depth.