Program Evaluation

“Preventing Violence Against Women and Girls and Delivering Essential Services to Survivors in Ethiopia”

Submitted by:

Leonard Maveneka (International Consultant) &

Martha Nemera (National Consultant)

December 19/2022

Addis Ababa

Ethiopia

United Nations Entity for Gender Equality and Empowerment of Women

UN Women

Inception Report

Version-2 Second Draft

Table of Contents

List of Tables	iii

List of Acronyms	iv

1.Background and Contexts	1

1.1 Introduction	1

1.2 Context of violence against women and girls (VAWG)	1

1.3 Overview of the program	8

1.4 Theory of program change	10

1.5 Purpose and objectives	11

1.6 Scope of the program evaluation	13

1.7 Expected use of the program evaluation	13

2. Methodology	13

2.1 Evaluation criteria and elaboration of key questions	13

2.2 Indicators for measuring results	18

2.3 Evaluation design	22

2.3.1 Evaluation Approach and Method	22

2.3.2 Evaluation process	23

2.3.3 Data Collection Tools	26

2.4 Gender and Intersectionality	28

2.5 Sample and sampling design	29

2.6 Data Analysis, Quality Assurances and Reporting	35

2.6.1 Data Analysis and Synthesis	35

2.6.2 Quality Assurance	36

2.6.3 Program Evaluation Reporting	37

2.7 Limitations to the evaluation	39

2.8 Evaluation Ethics and safety consideration	40

3. Evaluation Matrix	43

4. Work Plan and milestones for deliverables	53

5. Responsibilities, logistic and support	56

6. Annexes	60

6.1 Proposed Data Collection Tools 	60

Tool-1: Key Informant Interview Guide	60

Tool-2: Focused Group Discussion Guide	76

Tool-3: In-depth interview guide	80

Tool-4: Checklist for observation	80

Tool-5: Guiding questions for documentation Most significant change stories	81

6.2 List of documents reviewed	82

6.3 Terms of References (TOR)	85

6.4 Evaluation management and reference group members	85

# List of Tables

Table 1: Evaluation Criteria and Questions	10

Table 2: Program expected results and indicators of measures	11

Table 3: List of program implementation actors	15

Table 4: List of Key Informant Sampling	16

Table 5: List of Focused Group Discussion Sampling	17

Table 6: List of samples for In-depth Interview Respondents	17

Table 7: Qualitative data transcription template	18

Table 8: Proposed program evaluation reporting  outline	18

Table 10:Risk assumption for potential limitations and mitigation measures	19

Table 11: Evaluation Matrix	22

Table 12: Program evaluation work plan and time schedule	29

Table 13: Role and responsibilities of evaluation team	30

Figure 1: Program Theory of change	8

# List of Acronyms

AWSAD	Association of Women Sanctuary and Development

BoE		Bureau of Education

BoJ		Bureau of Justice

BoWCSA	Bureau of Women Children and Social Affairs

CEDAW	Convention on the Elimination of Discrimination against Women

EDHS		Ethiopian Demographic and Health Survey

EMERDA	Ethiopia Muslims Relief and Development Association

EOC-DICAC	Ethiopian Orthodox Church Development and Inter-Church Aid Commission

FGC		Female Genital Cut

FGD		Focused Group Discussion

FGM		Female Genital Mutilation

FOAG		Federal Office of the Attorney General

VAWG		Violence Against Women and Girls

HTP		Harmful Traditional Practices

IDI		In-depth Interview

IPV		Intimate Partner Violence

KII		Key Informant Interview

MoE		Ministry of Education

MOWSA	Ministry of Women, Children and Social Affairs

UNEG		United Nations Evaluation Group

VAWC		Violence Against Women and Children

VAWG		Violence Against Women and Girls

# 1.Background and Contexts

## 1.1 Introduction

An external team of two consultants was hired to evaluate the program independently using UN Women evaluation guidelines, and an Evaluation Reference Group (ERG) was formed to provide quality assurance of the evaluation process. This Inception report describes in detail how the program "Preventing Violence Against Women and Girls and Delivering Essential Services to Survivors in Ethiopia" will be evaluated. Several activities were carried out during the development of this inception report, including an initial meeting with the UN Women team, an internal meeting of the consulting team, and document review. The activities carried out during the inception phase allowed us to better understand the quality expectations, roles, and responsibilities of the consulting team, and to pool the necessary documents for review.

This inception report provides background information on Violence Against Women and Girls (VAWG) in Ethiopia, the proposed methodology, detail work plan as well as the tools that will be used for the program evaluation.

## 1.2 Context of violence against women and girls (VAWG)

lobally, an estimated 736 million women—almost one in three—have been subjected to physical and/or sexual intimate partner violence, non-partner sexual violence, or both at least once in their life (30 per cent of women aged 15 and older). This figure does not include sexual harassment. The rates of depression, anxiety disorders, unplanned pregnancies, sexually transmitted infections and HIV are higher in women who have experienced violence compared to women who have not, as well as many other health problems that can last even after the violence has ended.

Gender-based violence (GBV) is the fourth leading cause of death worldwide for people aged 15-44 years (WHO, 2014). More than 1.3 million people die each year as a result of GBV, accounting for 2.5 percent of global mortality (WHO, 2014). It is estimated that one in three women experiences physical or sexual abuse in their lifetime (WHO,2014). Further, one in five women is sexually abused as a child (Mikton et al., 2016).

In Ethiopia, violence against women and girls is still a serious problem that is fueled by persistent gender-biased attitudes and practices. Domestic violence, child marriage, and female genital cutting (FGC) are among the most common forms of VAWG that women face in Ethiopia. Spousal violence is very high in Ethiopia. The 2016 EDHS found that 34 percent of ever-married women age 15-49 have  experienced physical, sexual, or emotional violence by their current or former husband/partner, while 27 percent of ever-married women had experienced physical, sexual, or emotional violence.

VAWG nd Harmful Traditional Practices (HTP) against women in Ethiopia have their roots in the gender inequalities between men and women. Although violence against women has begun to receive more attention nationally over the last two decades, it is still largely hidden. According to UNECA and ACGS (2010), there are a number of reasons for this, including the predominance of the patriarchal system, the acceptance of violence against women as the cultural norm, the stigma attached to female victims of violence, and the very low rate of reporting by female victims of violence.

Female Genital Mutilation/Cutting (FGM/C) is a form of VAWG which, although it is still highly prevalent, has decreased in recent years, due in part to the legal efforts being taken against it. The prevalence of FGM/C varies greatly by region, with the highest prevalence being in Somali (99%) and the lowest in Tigray (23%) The prevalence of FGM/C has decreased in Ethiopia over the past 16 years, from 80% in 2000, 74% in 2005, and 65% in 2016.9  The decline is particularly evident among younger women, ages 15-19, since circumcision has decreased by 24% from 2005-2016 in this group. Data from 2013 indicate that more than 23.8 million girls and women have undergone the practice, placing Ethiopia among the top ten countries in Africa with the highest rates of circumcised women.

FGM and child marriage are inextricably linked. Both are complex, traditional practices based on entrenched gender norms that seek to control girls and their sexuality. In many areas, FGM is either seen as a prerequisite or precursor to a good marriage.

Although marriage before the age of 18 years is illegal in Ethiopia, it is still widely practiced across the country. However Afar and Somali are unique among the country’s regions in that they have not yet revised their family codes to outlaw child marriage (McGavock, 2021). Reluctance to do so is evident in the very high rates of child marriage in both regions. Of women aged 20–24 years at the time of the 2016 DHS, UNICEF reports that 67 percent of those in Afar and 55 percent of those in Somali were married before the age of 18, compared to only 40 percent nationally. While the incidence of child marriage among girls aged 15–17 is declining on a national basis, it appears to be climbing in Afar and Somali. In 2000, at the national level, 20% of girls aged 15–17 was married. By 2016, that figure had dropped to 11%. In Afar and Somali, on the other hand, the rate of child marriage had climbed by six and seven percentage points respectively.

Recent survey data highlights how much Afar and Somali girls and women have in common in terms of voice and agency. Not only are they more likely than their peers in other regions to be completely uneducated, to have undergone FGM/C, to be at increasing risk of child marriage and adolescent motherhood, and to lack access to productive assets, but they also have less input in decisions that affect their lives at the individual, household and community levels.

UN Women in partnership with the Ministry of Women, Children and Youth (MOWCY) commissioned an assessment on the Socio-economic status of women and girls in Somali and Afar regions and barriers hindering the adoption of Family Law. The assessment confirmed that women and girls in the two regions have very low socio-economic status compared to other regions such as access to education and employment, reproductive health rights and women’s decision-making power. The finding also established the key barriers and controversial areas for adopting the law are marriageable age, bigamy, period of widowhood, irregular union, child adoption and paternity.

Sexual violence against women and girls is devastating as it can result in reproductive health issues, poor academic performance, lack of self-esteem, impaired social relationships, depression, eating disorders, substance abuse, suicide attempts, and risky sexual behaviours. According to the 2016 DHS data, 33 percent of women ages 15-49 had ever experienced physical or sexual violence. Domestic violence is the most common form of violence that women experience, which includes physical, sexual, and emotional violence. Among women aged 15-49, 10 percent reported having ever experienced sexual violence at some point in their lives . Community-based cross-sectional studies performed at universities or high schools have found that the rates of students reporting being sexually harassed or experiencing other types of sexual violence is as high as 74%. ,.

## The legal framework on VAWG

The government of Ethiopia has ratified international and regional conventions and normative frameworks that protect and promote the rights of women and gender equality. These include the Convention on the Political Rights of Women (CPRW) in 1953, the Convention on the Elimination of All Forms of Discrimination against Women (CEDAW) in 1981, and adoption of the principles of the 1995 Beijing Platform for Action and the Beijing +5 in 2000. The Government has also ratified the African Charter on Human and Peoples’ Rights in 1998; the African Charter on the Rights and Welfare of the Child in 2000 and the African Charter on Human and Peoples’ Rights on Rights of Women in Africa (Maputo Protocol) in 2018. The Maputo Protocol guarantees the rights of women, including rights to participate in political processes, sexual and reproductive healt rights and an end to violence and discrimination against women and girls, including female genital mutilation/cutting (FGM/C).

Ethiopia has established specific legal measures and actions to address violence, including the Revised Family Law in 2000 and the Revised Criminal Code in 2005 (UN Women 2016). The government has also put in place the requisite institutional mechanisms at federal and regional levels, including the establishment of (1) The Ministry of Women, Children and Youth Affairs Offices MOWCYA, (2) Child and Women Protection Units within the various police units, and (3) a Special Bench for violence Ethiopia’s second Growth and Transformational Plan (GTP II 2015) included ending violence against women as a priority.

Although Ethiopia does not have a single, consolidated law on VAWG, there are various provisions related to specific forms of VAWG, general violence protections for women, and sweeping declarations of equality that can be interpreted as protecting women against VAWG. On FGM, for instance, one of the most important pieces of legislation is the 2005 Revised Criminal Code which outlaws the practice and sets the penalties for transgressors based on the severity of the FGM. There are also various national strategies in Ethiopia that set goals and make plans for the elimination of FGM, including Growth and Transformation Plan, National Alliance to End Child Marriage and FGM, and National Strategy and Action Plan on HTPs against Women and Children in Ethiopia.

The legal structures to deal with VAWG in Ethiopia include the formal legal systems at national and local levels as well as community-based and religious legal structures. However, these systems often do not operate in tandem, which complicates the enforcement of VAWG laws. Because of this complication, formal Woreda courts are increasingly trying to work with these informal justice systems so that both can be more effective

One of the most important federal legislation on VAWG in Ethiopia is the 2005 Revised Criminal Code. It includes prohibitions and penalties against most types of VAWG.  However, laws alone often do not result in behavioral change, normative change, or even effective enforcement at the local levels. Often, it is the more targeted and local policies that have more of an impact on people’s lives.

#### Gaps in the fight against VAWG

Although acts of sexual violence, domestic violence, sexual harassment and harmful practices are illegal under the law, government enforcement of such laws is inconsistent. The challenge for VAWG survivors is access to justice, as cases of domestic violence and rape are often given a low priority in the justice system and face significant delays due, in part, to poor documentation and inadequate investigation.

At national level, Ethiopia has many laws that guarantee equal rights for women and prohibit most forms of VAWG, including female genital mutilation (FGM), child marriage, most forms of rape, and some Intimate Partner Violence (IPV). However, for a variety of reasons, including the often-discordant levels of the formal and informal legal systems, the general culture of acceptance of VAWG the poor training of law enforcement officers and judges, and the lack of institutional support behind the enforcement of the bans, the policies are widely ineffective at preventing violence.

The existing national legal framework in Ethiopia fails to comprehensively address all forms and determinants of violence against women including the scattered provisions found in different pieces of legislation and inadequacy of existing provisions to deal with all forms of violence in a comprehensive manner including domestic violence and sexual harassment.

On early marriage, for instance, one of the main issues that has historically prevented the effectiveness of child marriage laws has been a lack of knowledge of the policies among average people (specifically poor, rural, uneducated populations). Fortunately, the knowledge that child marriage is illegal under national law is increasing across all populations, but many people still prioritize the tradition and the social and economic benefits of the practice.

But ending the practice of early marriage is still difficult since, in many areas, the practice is not seen as harmful. It is seen as a way to expand girls’ reproductive years and secure advantageous spouses that can help them climb the socioeconomic ladder. Therefore, many people ignore the law, and due to poor enforcement, they do so with impunity.

In relation to FGM, many laws at different levels within Ethiopia now forbid the practice and impose penalties on transgressors. However, the coordination among the different levels of society and law enforcement is often far from effective. Studies also indicate that in societies which still firmly believe in the value of FGM, the new legal penalties may have caused the practice to go underground, making it more dangerous and harder to track.,

Another impediment is the low health seeking behaviour among women who have experienced violence in Ethiopia. Overall, only 23 percent of women aged 15-49 who have ever experienced any type of physical or sexual violence by anyone have sought help. Notably, 66 percent have never sought help nor told anyone about the violence. Women who have experienced both physical and sexual violence are more likely to have sought help (27 percent) than women who have experienced only sexual violence (7 percent) or only physical violence (23 percent),

Furthermore, the CSO legislation shrinked the space for civil society organizations to engage in right-based approaches and limited their advocacy work on human rights in general. This posed significant challenges, particularly in terms of policy advocacy for the proper enforcement of legal provisions concerning VAWG and women's rights in general.

It is against this background that UN Women Ethiopia sought the services of a team of  consultants to evaluate its Programme “Preventing Violence Against Women and Girls and Delivering Essential Services to Survivors in Ethiopia”

## 1.3 Overview of the program

The four- year program “Preventing Violence Against Women and Girls and Delivering Essential Services to Survivors in Ethiopia” that aim  women and girls living a life free of violence is a continuation of a previous programme (2015-2017).

The Programme responds to the Convention on Ending All Forms of Discrimination Against Women (CEDAW) general recommendation 35 (2017) which builds on general recommendation 19 (1992) and the concluding observations of the Committee on the Elimination of Discrimination against Women (forty-ninth session 11-29 July 2011). It also adheres to sustainable Development Goal 5 through the specific target on “Eliminate all forms of violence against all women and girls in the public and private spheres, including trafficking and sexual and other types of exploitation.”

At the global level, it is in alignment with UN Women Strategic Plan, in particular the achievement of Impact 3 of the UN Women Strategic Plan 2017-2021 (i.e., that women and girls live a life free from violence), at the country level it si aligned to the UN Women Strategic Note 2017-2021, the United Nations Development Assistance Framework (UNDAF) 2017-2020, and United Nations Sustainable Development Cooperation Framework (UNSDCF) 2020-2025; as well as the ten years development plan 2020/21-2029/30 where “eliminating violence against women and children and harmful practices” was an area of focus.

To contribute to its ultimate goal “women and girls living a life free of violence” the programme gave du focus for preventing VAWG and supporting women and girls' survivors of violence and their access to justice, protection and quality essential services. The Program aim to achive three different but interlinked below outcomes:

- Outcome 1: An enabling legislation and policy environment in line with international standards on EVAWG and other forms of discrimination is in place and translated into action;

- Outcome 2: Favourable social norms, attitudes and behaviours are promoted at community and individual levels to prevent VAWG;

- Outcome 3: Women and girls who experience violence can use available, accessible and quality essential services so the impacts of violence are addressed, and perpetrators are held accountable

The program has deployed the following strategies: Knowledge generation, policy advocacy, and data collection and analysis, Capacity development, Community mobilization and Multi-sectoral coordination.

The program has been implemented in partnership and collaboration of virous actors among Ministry of Women and Social Affairs, regional Bureaus of women and children affairs, Ministry of Justice, regional Bureaus of Justices, Ethiopian Police University, Ministry of Education and Central Statistics Agency are key partners representing government stakeholders.   The program’s partnership with the Civil Society Organizations (CSOs) includes  Association for Women's Sanctuary and Development (AWSAD), Agar Ethiopia Charitable Society, Ethiopia Orthodox Church-Development and Inter-Church Aid Commission (faith-based organization), Norwegian Church Aid, and Setaweet Yebego Adiragot Dirijit.

The program is a multi  donors funded project  and the main funder of the program are:

- Government of Denmark, through the Royal Danish Embassy in Ethiopia

- Government of Sweden, through  the Swedish International Development Agency (SIDA)

- Government of Norway, through the Royal Norwegian Embassy in Ethiopia

- Government of Netherlands, though the Embassy of Netherlands in Ethiopia

- Irish Aid/the Embassy of Ireland in Ethiopia.

The programme has been implemented starting  from 01 January 2019 with an end date of 31 December 2021 followed by a no cost extension until 31 December 2022. The total estimated budget was for the four years was 4,488,140 USD and actual expenditure as of April 2022 was 4,270,723 USD.

The program intervention covered federal  level and selected regions of Ethiopia: Afar, Amhara, Oromia, Gambella, Sidama, and Somali. During its implementation period, major unforeseen events had happened such as the COVID 19 pandemic and the ongoing armed conflict that broke out on November 2022 and this had resulted   changes in the geographic coverage and accordingly programme was not implemented in Tigray, Diredawa and Gambela regions as per original plan while new regions like Afar and SNNPR were targeted.

## 1.4 Theory of program change

The program hypothesizes that if (1) an enabling legislative and policy environment in line with international standards on EVAWG, including for ending impunity and other forms of discrimination is in place and translated into action;  if policies and programmes are informed by the evidence of what works and quality and comparable data on violence against women and girls;  if favorable social norms, attitudes and behaviors are promoted at institutional, community and individual levels to prevent VAWG;  if women and girls who experience violence can use available, accessible and quality essential services so the impacts of violence are addressed and perpetrators of VAWG are duly prosecuted; then (2) there will be a substantial reduction in violence against women and girls; because (3) better responses to VAWG are available, violence is being prevented before happens, or before it re-occurs, and those experiencing violence, as well as their dependents, can recover and rebuild their lives with appropriate assistance and support. The program theory of change is illustrated in figure -1 below.

Figure 1: Program Theory of change

## 1.5 Purpose and objectives

The overall purpose of the evaluation will be to assess the contributions made by the programme towards ending violence against women and girls in Ethiopia. The evaluation is also expected to provide an in-depth assessment of the results against the three outcomes of the programme and performance in terms of relevance, effectiveness, efficiency, sustainability, impact, inclusiveness, coherence, participation, equality, non-discrimination, and social transformation.

Specific Objectives

The specific objectives of the evaluation will be to:

- Identify and document good practices and lessons learnt to inform the next phase, including future programming and initiatives on EVAWG and support strategic policy decisions;

- Assess the extent to which the results of the programme were achieved, including unintended results and examine to what extent the programme responded to the country’s international commitments, national needs, government priorities as well as with the UNDAF/UNSDCF and UN Women pervious Strategic Plan and UN Women Ethiopia’s pervious Strategic Note.

- Examine the programme’s contribution to strengthening federal and regional normative frameworks and enforcement mechanisms to prevent and respond to VAWG

- Assess the relevance of the contribution of the programme to the protection of women and girls, prevention of VAWG and provisions of services for VAWG survivors.

- Review the programme design, implementation strategy, institutional arrangements as well as management and operational systems.

- Aanalyze and reflect on the overall progress of the programme and the validity of its TOC and identified strategies.

- Assess the effectiveness and organizational efficiency in progressing towards the achievement of gender equality and women’s empowerment results as defined in the intervention.

- Assess the sustainability of the intervention in achieving sustained prevention and response to VAWG.

- Determine the impact of the intervention in terms of ending violence against women and girls.

## 1.6 Scope of the programme evaluation

## The end of programme evaluation will cover the implementation of the programme from 01 January 2019 - 31 December 2022. This includes the no cost extension period. The final evaluation is expected to highlight the achievements as well as come up with actionable recommendations for sustainability and improvement of future programme implementation.      The evaluation will focus on all activities undertaken and geographical locations covered by during the period both at  Federal and Regional levels.  The evaluation will be undertaken with the following key stakeholders in mind:  Federal, Regional and district level government sector offices, project implementing CSO partners.

## 1.7 Expected use of the program evaluation

The UN Women Ethiopia Country Office will be the primary users of the evaluation, with the findings feeding into the new planning cycle for the period 2023-2025. The evaluation will also be used by national stakeholders, including implementing partners, to learn what worked well and what needs to be improved. The evaluation will also inform development partners on how and where they should continue to invest to achieve better results in terms of creating a life free of violence for Ethiopian women and girls.

# 2. Methodology

## Evaluation criteria and elaboration of key questions

The consultants will use the  Organization for Economic Co-Operation and Development (OECD) and Development Assistance Committee (DAC) evaluation criteria to assess all project components from conceptualization, implementation processes and proposed outcomes (results). The evaluation will also follow the United Nations Evaluation Group's (UNEG) Norms and Standards for Evaluation in the UN System and the UN Women Evaluation policy. The evaluation criteria to be used include relevance, effectiveness, efficiency, sustainability, impact, coherence, participation (inclusiveness equality, non-discrimination, and social transformation) The consultants will specifically look at the project

The consultants will specifically look at the project

- Relevance: Relevance will assess how successfully project objectives and implementation strategies are aligned with beneficiary      needs and priorities, overall organizational priorities, and levels of alignment to national and global (VAWG) agendas. The Relevance component will investigate how well project activities were linked to the current Ethiopian context and how well they adapted to the country's changing situation. To what extent the programme aligned with and contributes to the relevant national, regional and international policies and normative frameworks on human rights, gender equality and women’s empowerment such as the  Convention  on  Elimination  of  all forms  of  Discrimination  Against  Women  (CEDAW),  the  Beijing  Platform for  Action, the SDGs  including Ethiopia country development priorities, GTP, 10 year development plan, UN Women SN 2018-2021, UNDAF Ethiopia 2016-2022 and UNSDCF 2022-2025

- Effectiveness: This refers to the extent to which objectives of the programme were met. This will measure achieved results against the result that the project expected to achieve. It will further analyze enablers and obstacles for achievement or non-achievement of project objectives. The section will document progress against benchmarks as initially set out in the logframe particularly progress made towards achievement of the expected outcomes in terms of preventing and responding to VAWG in Ethiopia; extent to which the expected outcomes were achieved and how UN Women contributed to the achievement of the outcomes;  how other stakeholders were involved in the programme implementation, and how the programme has been monitored and reviewed. The analysis will outline levels of progress and dynamics that influenced achievement of results.

- Efficiency: The evaluation will investigate how well resources were translated into results. This will focus on the management and institutional arrangements, risk analysis, the quality of technical assistance as well as the quality of monitoring and evaluation.

- Impact: This will focus on the measurable changes in the lives of women, girls, boys, and men, including VAWG survivors, which can be directly and indirectly linked to the project thus far. The analysis will focus on positive and negative as well as intended and unintended changes. Impact analysis will determine changes attributable to the programme and changes for which the programme contributed (attribution and contribution).

- Sustainability: Sustainability will determine the extent to which programme design and implementation ensured continuation, ownership, maintenance and replication of project activities beyond the supported phase. A four-tier sustainability analysis will be employed focusing on programmatic organizational, technical and financial sustainability.

- Coherence: Coherence will assess the compatibility of the UN Women  Preventing Violence Against Women and Girls and Delivering Essential Services to Survivors in Ethiopia" with other interventions in Ethiopia focusing ending VAWG.  It will also assess the extent to which EVAWG program interventions by other players (particularly policies) support or undermine the Programme and vice versa

Participation: Participation and inclusiveness will assess how the program engaged the multiple groups of actors and considered equality and non-discrimination in the participations and engagements.

Table 1: Evaluation Criteria and Questions

| Criteria | Key Evaluation Questions |
| --- | --- |
| Relevance | - To what extent did the programme target and reach poor and marginalized women and children? - To what extent did the programme mainstream gender equality in the design and delivery of activities? - To what extent did the programme factor in the changes brought in by the resumption of hostilities in Ethiopia during the implementation period? - How well did the programme respond to the needs of target beneficiaries, including how these needs evolved over time? - What is the relevance in relation to the UN-Women Strategic Plan, the Human Rights-Based Approach to Programming and Results-Based Management? |
| Effectiveness | - To what extent are the results that are reported a fair and accurate record of achievement? - To what extent has the programme delivered results that are value for money? - How well did the programme apply value for money principles of effectiveness, economy, efficiency in relation to delivery of its outcome; - To what extent has the programme used learning to improve delivery? - What were the key drivers and barriers affecting the delivery of results for the programme? |
| Efficiency- Approaches used by UN Women | - To what extent did UN Women Ethiopia deliver results on time and on budget against agreed plans - To what extent did the programme understand cost drivers and manage these in relation to performance requirements? - Did the actual or expected results (outputs and outcomes) justify the costs incurred? Were the resources effectively utilized? - What factors contributed to implementation efficiency? - Were there more efficient ways and means of delivering more and better results (outputs and outcomes) with the available inputs than were used? - Could a different approach have produced better results? How efficient were the management and accountability structures of the programme? |
| Impact- What difference has the programme made to lives of beneficiaries (what, who, where, when)? | - What changes (long term and short term) in the lives of women and children can be directly attributed to the programme? - To what extent and how did the programme impact on the lives of beneficiaries - To what extent did the programme build the capacity of implementing partners? - How many people received support from the programme that otherwise would not have received support? - To what extent and how has the programme affected people in ways that were not originally intended? |
| Sustainability | - To what extent has the programme leveraged additional resources (financial and in-kind) from other sources? - What effect has this had on the scale, delivery or sustainability of activities? - What evidence is there to show that the benefits delivered by the programme will be sustained after the fuinding ends? - What is the capacity of the IPs to sustain the programme beyond the funded period? |
| Coherence | - To what extent was the UN Women VAWG Programme compatible with similar interventions by the government or by CSOs - Did the Programme duplicate interventions by other players in the VAWG arena - To what extent did the Programme fit in with similar VAWG interventions being carried out at the global and at the local level. |
| Participation | - To what extent was the programme inclusive and engaged different actors? - What strategy was used by the programme to target and reach out to the most vulnerable? |

## 2.2 Indicators for measuring results

Table 2: Program expected results and indicators of measures

| Program Expected Results | Result indicators | Data Quality Verification |
| --- | --- | --- |
| Goal: Women and Girls live a life free of violence | Indicator: Percentage of women and girls aged 15-49 who have experienced violence in the past 12 months |  |
| Outcome 1 An enabling legislation and policy environment in line with international standards on EVAWG and other forms of discrimination is in place and translated into action | 1A: Number of regional family laws that are aligned with international Human Rights Standards, namely Maputo Protocol and CEDAW General Recommendation 35 on VAW. | Results collected from desk review and key informants will be verified with the project monitoring report. The regional family laws will be verified against the international human right standards. |
|  | 1B: Percentage of cases of violence against women and girls filed in courts that have a verdict reached. | Information collected from KII from justice system regarding cases reported and got decision and will be verified with the records in the system. |
| Output 1.1: Somali and Afar regions’ legislation framework enabled through advocacy on identified attitudes and barriers to adopt family laws in line with the Federal Family Code and international instruments on women's rights, namely Maputo Protocol and CEDAW | 1.1A: Number of women groups and parliamentarians with increased capacity through training to advocate for the adoption of family law in Somali and Afar regions. | Information and data collected from key informants will be verified with the project records and any advocacy agenda and plan developed by the parliamentarians. |
| Output 1.2: Evidence-based data, information and analysis on VAWG and women's access to justice available | 1.2A: Number of evidence-based research studies and/or analyses of Ethiopian women's access to justice and prevalence and incidence of VAWG across regions produced | Information and data will be collected from KII and the documents produced by the program collected and reviewed and crossed check for the quality of the data collected |
| Output 1.3: Capacity of law enforcement bodies strengthened to implement legislation on EVAWG and other forms of discrimination | 1.3A: Percentage of reported VAWG cases investigated and prosecuted in targeted areas | Information from the, KII and ex- VAWG Survivors will be verified against the records of VAWG |
|  | 1.3B: Number of police officers, prosecutors, judges and health officers trained in gender-sensitive service delivery to survivors of violence | Information form KII received the training verified against the training registration and reports. |
| Outcome 2: Favorable social norms, attitudes and behaviors are promoted at community and individual levels to prevent VAWG | 2A: % of women and men in SASA! Kebeles that change attitude towards spousal violence | Information from FGD and KII will be verified with the records of SASA, studies conducted by the project and an in-depth interview made by the program evaluations |
| Output 2.1: Women, girls, men and boys at community and individual levels are mobilized in favors of respectful relationships and gender equality | 2.1A: Number of national media guide on gender responsive and sensitive reporting with a section on VAWG reporting produced and endorsed | Information form KII will be verified with the program monitoring and records and document from the media agency. |
|  | 2.1.B: Percentage of people in communities that apply SASA! are mobilized in favors of respectful relationships and GE | Information from KII and FGD of SASA participants will be verified against the studies conducted on SASA |
| Output 2.2: Increased capacity of traditional and religious leaders in addressing VAWG | 2.2. A Number of religious and traditional leaders advocating for the promotion and protection of women's rights | Information from the religious key informants will be verified with the community FGD, project records |
| Output 2.3: Educational curricula and programmes addressing gender equality and VAWG are developed and integrated into formal and non-formal education | 2.3A: Number of Standard teachers training manual on VAWG in schools developed | Information from key informants of teachers and school administrators will be verified with the developed manuals and guidelines |
|  | 2.3.B Number of Formal and non – formal education institutions that integrate standard teachers training manual | Information for the key informant will be verified with the standards teacher training manual developed |
| Outcome 3: Women and girls who experience violence use available, accessible and quality essential services | 3A: Number of VAWG survivors who have accessed comprehensive services | Information from the service providers centers verified against the key informants of VAWG Survivors |
| Output 3.1: Strengthened capacity of service providers in providing quality coordinated and accessible essential services to women and girl’s survivors of violence in accordance with global essential services package | 3.1A: Number of joint standard operating procedure in line with global standards on essential services is developed | Information form KII and FGD and existing project developed Standard Operating procedures of the safe house will be verified with the global standards. |
|  | 3.1B: Number of members of the Network of Ethiopian women shelters that are using standardized operating procedure | Information from the Network members interview will be verified against the standardized operating procedures expected to be received. |
| Output 3.2: Availability and accessibility of quality essential services for women and girls’ survivors increased | 3.2A: Number of shelters available and providing quality, accessible, multi sectoral survivors-based services for women and girl survivors of violence | Information from KII will be verified against the records of Shelter network coordinators and against the quality standards operating procedures. |
|  | 3.2B: Number of shelters using the Essential Services package | Information from observation and KII with the shelter staff will be verified with the VAWG Survivors and standards operative procedures and service packages provided. |

## 2.3 Evaluation design

### 2.3.1 Evaluation Approach and Method

To inform and direct the evaluation design the evaluation will follow a “Programme Theory of Change (Toc) Evaluation approach”, the ToC is found in figure -1, and developed, pathways to program goal focusing on the assumptions and risks stated in the program document. The ToC outlines the program system of concepts, assumptions, expectations, beliefs, the presumed relationships among them and what is going on with these things and why. The approach helps to analyze the program evaluation findings. Meaning, the approach helps us to see the programme impact, the cross-cutting issues across the program, thereby showing the links between causes and effects, to see the program wider effect at higher level, extract learning and make recommendations.

Furthermore, the approached is designed to answer the question of what worked (by measuring or assessing the changes brought about by program), but also why and how it worked (by examining the processes that led to those changes). This also helps to generally examine wider contributions to change, such as the actions of other interventions or changes in the wider vision of VAWG free environment, the approach work with an explicit theory, a theory of change or logic model that underpins the program

In summary, the approach is based on two distinct parts: a conceptual part, which concentrates on developing the theory of change or logic model and using it to guide the evaluation; and a second part that involves collecting evidence to establish whether and/or how a program intervention produced the desired changes.

Besides ToC framework that helps for analysis, to further organize the data and information and to better understand the change at programme level, a “Program evaluation framework” will also be used. The framework organizes the project data and findings to programme strategic components. The framework is found in table-11.

The evaluation will promote a participatory approach that engages multiple stakeholders who were involved in the programme design and implementation. The Consultants recognize that incorporating multiple methods into a single evaluation often results in a stronger, more comprehensive evaluation than conventional evaluation approaches that rely on only one method, hence the use of a mixed method approach in this evaluation.

The Evaluation will therefore use qualitative method predominately and quantitative data from the project MEL documentation to substantiate the qualitative data. The strengths of qualitative aspect of the Evaluation include providing contextual data to explain complex issues and complementing quantitative data by explaining the “why” and “how” behind the “what.” The qualitative component will provide stories of success and failure, stories of change in implementation communities as well as provide narrative accounts (based on focus group discussions and key informant interviews) of how the project impacted on lives of beneficiaries and their surrounding

### 2.3.2 Evaluation process

In general, the program evaluation will have five different but interconnected phases and each phase and expected deliverables at each phase is elaborated below:

Phase-1: Start up meeting

Following the signing of the contracts the consultants held a meeting  with UN- Women, whose purpose was to better understand their expectations of the evaluation regarding the deliverables and the timelines. The consultants were also provided with the available documents and were made aware of the support that UN Women and project partners would provide.  This phase was accomplished before the development of the  inception report.

Phase-2: Inception report

Phase  involved the development of the inception report which will guide the remaining phases of the evaluation process. Two major deliverables were expected at this phase elaborated below:

Deliverable 1: Draft Inception Report: The inception report was developed following the structure agreed with UN-Women. The inception report includes all annexes (evaluation matrix, evaluation instruments /tools and list of actors for consultation, operational plan and data collection tools). Before developing the inception report, the consultants systematically reviewed the documents provided by UN Women, which included national and international documents pertinent to VAWG. Following the documents review the consultants developed and refined evaluation questions.

Deliverable 2: Final Inception Report: the draft report was submitted to UN-Women on the agreed timeline. The consultants received comments and made the appropriate amendments to the draft inception report. The consultants also developed a “trail of comments” indicating in writing how they had addressed the comments. The trail of comments documents wasd submitted together with the final inception report.

Phase-3: Data collection

This phase will involve primary and secondary data collection and expected deliverables at this phase are elaborated below:

Deliverable 3: Primary and secondary data set: Data collection will be undertaken according to the inception report once it is approved by UN-Women. This phase will also see an in-depth secondary document review and analysis such as review of the financial reports and other monitoring and studies conducted by partners. This phase will also include field visits, interviews with Programme beneficiaries, (through representative sampling), discussions and consultations with key actors like government officials, CSOs etc. The consultants will gather primary and secondary data for qualitative and qualitative analysis.

Deliverable 4: Data analysis  and debriefing meeting with UN Women

Once the data collection is completed the consultants will analyse the report. Qualitative data will be analysed using content analysis. A draft report written the consultants will make an initial  presentation of their initial findings to UN women in person or virtually as appropriate. The purpose of the briefing at this stage will be identify gaps in the draft report that can still be addressed.

Phase-4: Draft report Presentation

Deliverable 4: Draft Report:  following the debriefing, the consultants will prepare the  draft evaluation report based on the agreed evaluation report outline in the UN Women Evaluation Handbook (Box 18). The consultants will ensure that the draft report conforms to the UNEG (2017) Norms and Standards for Evaluation or the OECD/DAC (2010) Quality Standards for Development Evaluation and follows the structure and instructions as set out in Annex 3.

Prior to the submission of the draft report to the EMT, the consultants will undergo an internal quality control process through the Consultant’s Evaluations Quality Assurance System (EQAS). If the quality of the draft evaluation report is deemed satisfactory by EMG UN Women will circulate the report to key stakeholders for their comments.

Phase-5 Evaluations Communication and presentation:

Deliverable: 5 Final Report: the consultants will address all the relevant comments in the draft report and produce the final report along with the “trail of comments” using the format set out in Annex 2, indicating how each comment was addressed. The consultants will submit the final report with the trail of comments document for the review of ETM.

Deliverable 6: Final presentation: once the final evaluation report is approved by the EMG the consultants will prepare and facilitate a workshop to present the findings, conclusions, recommendations and lessons of the program evaluation in Addis Ababa in person or virtually as appropriate.

Deliverable 7: Evaluation Communication: the consultants will develop a power point presentation and a 2-pager summarising the final key findings, lessons learnt and recommendations in line with UN Women’s corporate branding guidelines.

### 2.3.3 Data Collection Tools

1. Desk Review: desk review will continue in all phases of the evaluation and will include a review of the programme document, assessment report, progress reports, annual reports, baseline report, study report, labeling of data for analysis, looking/aggregating indicators for meta-synthesis of a wide range of UN Women’s evaluations and audits to help answer the key evaluation questions. The meta-synthesis will include all UN Women programme evaluations findings; information on the Key Evaluation Questions, placed within an analytical framework based on the theory of change. Desk Review will also attempt to further refine the Theory of change and assumptions to be tested, which will inform the evaluation’s analysis. The review will provide an assessment of the potential range and quality of the secondary data available for use by the evaluation, including identification of gaps to be addressed with additional data collection. It will also help to determine the extent and coverage of evaluative evidence available for the design of the evaluation case studies. This phase also includes finalizing the inception report after incorporating the feedback and comments received from UN Women.

2. Key Informant Interviews (KII):  It will be important to interview a broad range of key stakeholders to allow the evaluation to capture varying perspectives and underlying issues or      problems.  Key informant interviews will therefore be conducted with a broad range of stakeholders, including UN Women Programme staff, Federal, regional and district government officials and CSOs implementing the Programme and other relevant UN agency focal persons and service providers (see table-4 with detailed list below).  The interviewers will use both face to face and remote interview techniques. UN Women team will help in setting up the interviews     .  Questions for the KIIs will be open ended and framed in such ways as to ensure that respondents participate in more dialogue and provide as much information as possible.  The KII guiding questions will be first approved by the UN Women before the interviews start. The selection of Key Informants will be gender-sensitive, conflict-sensitive, and respect the principles of Do No Harm and Leave No One Behind.

3. Focused Group Discussion: Focus group discussions (FGDs) will allow exploration of participants' views and exposure to programme components. It will give participants an opportunity to share their views on VAWG services provided and gaps in service provision, in a context where they can consider their own views in relation to the views of others.  Focus group discussions (FGDs) will be conducted among programme beneficiaries, community members, women and men, boys and girls, religious leaders and VAWG survivors. The FGD guiding questions will be first approved by the UN Women before the data collection process starts. The selection of FGD participants will be gender-sensitive, conflict-sensitive, and respect the principles of Do No Harm and Leave No One Behind.

4. In Depth Interview: In-depth interviews will be conducted with selected women and men programme participants to extract the programme’s most significant change stories on the lives of individuals building agency, community transforming social norms and institutions responsive to gender.

5. Observation: During the field qualitative data collection, both quantitative and qualitative observations will be made. The qualitative observations will be on the agency of women and girls and functionality of the established systems, while the quantitative observation will be on the quantity of services improved. A checklist will be developed to inform the evaluation team on what to observe and what questions to ask during observations.

2.3.4 Learnings and Most Significant Change Stories

Learning has been defined by different institutions in different ways, in the UN definition learning encompasses “acquiring” “new” or modifying and reinforcing existing: knowledge, skills, values or preferences which may lead the programme participants to change the way they work now and, in the future, depth of their knowledge, attitude or behaviors relative to the type and range of experience they have before implementing the programme.

Learning is therefore a method or techniques or approach or a system that has shown results superior to those achieved with other means. It may encompass a whole programme delivery, or it may simply refer to a single method or a way of looking at things or addressing a problem.

Learning and most significant change stories in this program evaluation, considered as an individual's or group's acquisition or modification of information, knowledge, understanding, attitudes, values, skills, competencies or behaviors as a result of the Programme idea and practices that brought about changes in the life of the individual, their household, their community, and their institutions. And these practices must be participatory and inclusive, replicable and scalable, acceptable and adaptable, cost-effective, innovative or new to the area.

In line with the above criteria mentioned the programme evaluation will document learnings and Most Significant Change Stories. During the data collection participants will be asked to identify major learnings from the programme via key informant and focused group discussions. A learning documenting checklist will be created and used during the key informant and focus group discussions.  Cases will thus be identified and further in-depth studies will be made on the programme strategies that brought about the changes and stories and most significant change stores developed and annexed to the programme evaluation report.

## 2.4 Gender and Intersectionality

To ensure that no one is left behind, the program evaluation will take gender sensitivity and social inclusion principles into account. Women are a diverse group of people who experience the world in a variety of ways because the world does not treat them all the same. As a result, the experiences of all women can never be crammed into a single experience. The evaluation will therefore take due regard of gender and intersectionality to ensure that those who face multiple forms of discrimination as a result of being women, youth, disabled, ultra-poor etc participate in the programme evaluation and their views are taken on board.

Due focuses will be made for gender sensitivity, intersectionality and social inclusion disaggregation will be made accordingly during respondents’ identification, data collection, data analysis, and reporting.

## 2.5 Sample and sampling design

The programme evaluation team will make sure fair sampling strategies that avoid unfair or unjustified targeting and inclusion of specific groups and avoid unfair or unjustified exclusion of specific groups.  A rprsnetative sample size will be dround from the sampling frame  with due consideration of contextis  and diversity of target groups

Sample Design: The non-probability sampling design will be used, meaning that some members of programme participants will have a higher chance of being included in the response than others based on their participation and knowledge of  the programme implementations.

Sampling Method: the programme evaluations will use qualitative sampling methods mostly purposive and convenience sampling methods.

- Purposive Sampling:  Purposive sampling will help to attract people who can provide extensive information on the topic under inquiry. Purposive sampling will assist in clustering programme evaluation regions based on the key gender issues pertinent to the region and respondents to include people representing a diverse range of opinions and who participated in program implementations.

- Convenience Sampling:  another nonprobability sampling strategy that the evaluation will employ is convenience sampling. To draw a convenience sample, the evaluation team will  collect data from program participants or other relevant elements and convenience sample made to which the interviewer and the interviewee have the most convenient access. In particular this strategy is very helpful for interviewing VAWG survivors and caregivers

Sample Size: samples for the evaluation are drawn from the programme key actors under each outcome area of the programme taking into consideration representations across the different regions and contexts. The key actors per outcome and region are listed in Table-3 below. The actual sample size will be determined flexibly in the field based on the saturations of the obtained data.

The program intervention covered the federal level and selected regions of Ethiopia, including Afar, Amhara, Oromia, SNNPR, Sidama, and Somali. To generate a representative sample, the evlaution team carefully examined the context of each region as well as the program focus in each region. Somalia and Afar are grouped together among the total program operation regions due to their similarities in context and pervalance of similar  forms of VAWG. Morover the program interventions are similar in the Somali and Afar regions, the evaluation team grouped the two regions, and Somalia is included in the study sample. Accordingly, the program evaluation sample districts where the responses will be drowned in addition to the Federal level are Amhara, Oromia, SNNPR, Sidam, and Somali.

The initial sample size for each qualitative approach is drawn from the key actors list using purposive sampling and presented in the subsequent tables below:

Table 3: List of program implementation actors

| Outcome | Regional Focus | Key Actors |
| --- | --- | --- |
| Outcome-1: |  |  |
| Output 1.1 | Somali and Afar | - Bureau of Justice - Regional Supreme Court and Sharia Court - Women Parliamentarian - Religious and Cultural leaders - Norwegian Church Aid (NCA) - EWLA Grass root Women’s groups - Bureau of Women and Social Affairs |
| Output 1.2 | Federal, Afar and Somali | - Ministry of Justice - Somali bureaus of women and social affairs - Central Statistical Services (CSS) - Ministry of Women and Social Affairs - Setaweet Yebego Adragot Dirijit |
| Output 1.3 | Amhara, Sidam and Oromia | - Education Office - Health Office, One Stop Centers - Police, Prosecutors, Judiciary - AWSAD - Agar Ethiopia |
| Outcome-2 |  |  |
| Output 2.1 | Oromia, Amhara and Addis Ababa | - SASA Group - EOC - AWSAD - Ethiopian Broadcasting Agency - Local Media in Oromia (Adama Segele) and Amhara (Debereberhan FM) |
| Output 2.2 | Amhara Oromia, Sidama and Somalia | - Norwegian Church Aid (NCA) - The Ethiopian Orthodox Church Development and Inter-Church Aid Commission (EOC-DICAC) |
| Output 2.3 | Oromia, Sidama and Amhara | - Yellow Movement and Male Engagement (Sidama) - Targeted Schools (Teachers and Administrators) - Police College - Bureau of Education - AWSAD |
| Outcome-3 |  |  |
| Output 3.1 | Amhara and Oromia | - Ethiopian Network of Women Shelters (ENWS) - ENWS Members Organizations - VAWG Coordination Body (National Coordination Body) |
| Output 3.2 | Amhara, Sidama and Oromia | - AWSAD - In Adama/Oromia, Sidam, Addis Ababa Shelter - Agar Ethiopia – Bahir Dar Shelter - Good Samaritan Association – Gonder Research Institutions - One Stop VAWG service centers and other key stakeholders working closely with the Shelters (police, prosecutors, regional bureau of women and social affairs, survivors of violence, ex- residents of shelter, ENWS members |

Table 4: List of Key Informant Sampling

The sampling for each region purposively drowns form table-3 above based on their participation in the different output of the project as specified.

| List of key Informants | Addis Ababa | Amhara | Oromia | Sidama | Afar | Somalia |
| --- | --- | --- | --- | --- | --- | --- |
| Federal Government Stakeholders |  |  |  |  |  |  |
| - Ministry of Women, and Social Affairs | 1 | - | - | - | - | - |
| - Ministry of Justice | 1 | - | - | - | - | - |
| - Central Statistical Service (CSS ) | 1 | - | - | - | - | - |
| - Ministry of Education | 1 | - | - | - | - | - |
| - Ethiopia Police University |  |  |  |  |  |  |
| Region / district stakeholders |  |  |  |  |  |  |
| - Regional Supreme Court and Sharia Court | - | - | - | - | - | 1 |
| - Bureau of Justice (Police, Prosecutors Judiciary) |  | 3 | 3 | 3 | - | 3 |
| - Women parliamentarian/Women Caucus | 2 | - | - | - | - | 3 |
| - CBOs (Religious and cultural leaders) |  | 3 | 3 | 3 | - | 4 |
| - Grass root women’s groups leaders |  | 3 | 3 | 3 | - | 3 |
| - Bureau of Women and Children Affairs |  | 1 | 1 | 1 | - | 1 |
| - Yellow Movement and male engagement | 1 | - | - | 1 | - | - |
| - Bureau of Education |  | 1 | 1 | - | - | - |
| - Bureau of Health |  | 1 | 1 | 1 | - | - |
| - Schools |  | 1 | 1 | - | - | - |
| Implementing CSOs |  |  |  |  |  |  |
| - Ethiopian Broadcasting agency | 1 | - | - | - | - | - |
| - Oromia Media | - | - | 1 | - | - | - |
| - SASA Groups Leaders | 2 | 3 | 3 | - | - | - |
| - Shelter Ex- resident | 3 | 3 | 3 | 3 | - | - |
| - EOC-DICAC | 1 | 1 | 1 | 1 | - | - |
| - NCA, | 1 | - | 1 | 1 | - | - |
| - Shelter Network Chair | 1 | - | 1 | - | - | - |
| - VAWG Coordination Body | 1 | - | 1 | - | - | - |
| - AWSAD | 1 | 1 | 1 | 1 | - | - |
| - Agar Ethiopia |  | 1 | - | - | - | - |
| - WLA |  | - |  |  | - | 1 |
| - UN Women | 3 | - |  |  | - | - |
| - Good Samaritan Association – Gonder Research Institutions | - | 1 | - | - | - | - |
| Total | 22 | 22 | 25 | 18 | - | 16 |

Table 5: List of Focused Group Discussion Sampling

| List of Focused Group | Addis Ababa | Amhara | Oromia | Sidama | Afar | Somalia |
| --- | --- | --- | --- | --- | --- | --- |
| Community project participants (6 to 12) - participants |  |  |  |  |  |  |
| Women Group (6 to 12)- participants |  | 2 | 2 | 2 |  | 2 |
| Men Group- (6 to 12) participants |  | 2 | 2 | 2 |  | 2 |
| Girls Group- (6 to 12) participants |  | 2 | 2 | 2 |  | 2 |
| VAWG Survivors- (3 to 6) participants |  | 1 | 1 |  |  |  |
| SASA group participants- (6 to 12) participants |  | 1 | 1 |  |  |  |
| Total |  | 8 | 8 | 7 |  | 8 |

Table 6: List of samples for In-depth Interview Respondents

| List of In-depth Interview | Addis Ababa | Amhara | Oromia | Sidam | Afar | Somalia |
| --- | --- | --- | --- | --- | --- | --- |
| Women Shelters ex-residents |  | 3 | 3 | 3 | - | 3 |
| VAWG survivors in the safe house |  | 3 | 3 | 3 | - | 3 |
| Community representative |  | 3 | 3 | 3 | - | 3 |
| Total: |  | 9 | 9 | 9 | - | 9 |

## Data Analysis, Quality Assurances and Reporting

### 2.6.1 Data Analysis and Synthesis

A qualitative data transcription Excel template will be used for the analysis of qualitative data collected from different sources. The triangulated evidence will be organized into key findings using a systems approach to report on the key evaluation questions and also referencing the value added of the UN Women strategic plan in comparison with the baseline values aggregated from the program documents; and also assessing th extent to which the recommendations of different UN Women evaluations have been implemented. The overall approach to the evaluation data analysis will be a mixed approach with a focus on utilization-focused, gender responsive approach. The consultants will use a mix of qualitative and quantitative methods of data-collection and analysis. Qualitative methods will allow for an in-depth understanding of key issues, while quantitative approaches (collected and aggregated from the desk review, evaluation reports, monitoring reports) will help to identify overall trends and ensure the programme effectiveness to outcomes target. During analysis the evaluation team will specify the programme impact on gender response; here the team will follow UN Women gender action/strategy documents embedded in the strategic document. The evaluation team will pay particular attention to the extent to which the program   benefitted rights-holders (stakeholders, project beneficiaries), and how it strengthened the capacity of duty-bearers or other actors to fulfill obligations and responsibilities. In summary, the evaluation team will apply:

1) Contextual analysis, here the consultants will carry out a systematic analysis of  the qualitative data after identifying, sorting, organizing, interpreting, consolidating, to better understand the programme and

2) Comparative Analysis, here the quantitative data will be aggregated, summarized and analyzed depending on the data type; this will help to clarify the programme the changes the programme brought about.

The Synthesis of the analysis will feed conclusions in response to the evaluation questions and forward-looking recommendations.

Table 7: Qualitative data transcription template

| Evaluation Criteria | Evaluation Sub Questions | Respondents Direct Response |  |  |  |  | Thematic Analysis |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desk Review | KII | FGD | IDI | Observation |  |

### 2.6.2 Quality Assurance

For quality assurance the evaluation team will be independent from UN Women and the evaluation reference groups at all times and adhere to the UN Evaluation Group (UNEG) Norms and standards and undertake regular consultations with the evaluation reference group.  The draft report will be first peer reviewed by the consultants themselves. It will then be reviewed by the UN Women team at different levels – Evaluation Task Manager. The final report will make clear disclaimers proclaiming that the views in the report are those of the evaluation team, and not necessarily of UN Women- who may articulate their voice through a Management Response.

### 2.6.3 Program Evaluation Reporting

Factual corrections and comments will be provided by the UN Women evaluation task manager and then Evaluation Reference groups as they review the draft report. The draft evaluation report will be structured as per the proposed reporting format indicated in the table below

Table 8: Proposed programme evaluation reporting outline

Executive Summary (Max 5 pages) - Brief description of programme - Purpose and scope of the evaluation; - Summary of the evaluation methodology; - Major findings and conclusions; - Key recommendations; - Summary of lessons learned and best practices Acknowledgements Tables of Contents List of Acronyms and Abbreviations 1.Introduction 1.1 Context 1.2 Background and description of the three-years programme including underlying rationale, stakeholders and beneficiaries, conceptual model 1.3 Evaluation objectives and evaluation criteria considered in the evaluation 2. Evaluation Methodology 2.1 Applied techniques and methodology 2.2 Major limitations of the study 3. Analysis of data and findings of the evaluation as per criterions 3.1 Relevance 3.2 Effectiveness 3.3 Efficiency 3.4 Impact 3.5 Sustainability 3.6 Coherence 4. Lessons learnt with wider relevance that can be generated beyond the three years’ program 5.Conclusion and Recommendations (based on evidence and insights) classified according to the criterion 6. Annex including 6.1 Terms of reference of the evaluation 6.2 Technical proposal 6.3 List of Document reviewed 6.4 List of people consulted

## 2.7 Limitations to the evaluation

The proposed evaluation tools have an appropriate balance between standardization and flexibility to be adapted for different needs without compromising data efficacy and analysis. At the same time, there are some risks and assumptions that will pose potential limitation of the program evaluation must be understood from the outset:

Table 10: Risk assumption for potential limitations and mitigation measures

| Types of Risk /Challenges | Potential Limitation | Mitigation Measure |  |
| --- | --- | --- | --- |
| Timing Delays | - Delays in scheduling of meetings and field visits due to government competing priorities, - In some case, difficult to schedule key informant interviews with-time constraints and distance; | - The evaluation team will pre-inform stakeholders before field work, will develop a list of key informant actors during inception report so that interviews can be set up before hand. ` |
| Reports/Data Availability | - Stakeholders/ Actors (example police, Justice offices) might not provide quality data against our measurement variables; | - As a mitigation measure, all data and information will be triangulated with UN Women and partners CSO data source |
| Contextual/Attribution constraints | - Many organizations are working in the project areas from other source of funding which will need to be taken into account as it might affect some of the evaluation findings; | - As a mitigation measure, the evaluation team will probe-more, triangulate findings, review other actors working in the area with similar modalities |

## 2.8 Evaluation Ethics and safety consideration

3.1 Evaluation ethical standards

To safeguard the research participants, the consultants will follow the WHO Ethical and Safety Recommendations for Research on Domestic Violence Against Women. The consultants will align to the Ethical code of conduct of the UN Evaluation Group. The following ethical standards will be considered in the programme evaluation process:

- Safety of evaluation participants: The safety of respondents and the evaluation participants is paramount, the physical safety of respondents and interviewers from potential retaliatory violence by the perpetrator or perpetrators of violence is of prime importance. Women and girls participants experiencing violence, may provoke further violence, or place the respondent or the interview team at risk by the perpetrators through their participation in the evaluation. Therefore, the evaluation team will consider the following:

- Conduct interviews only in a private setting where the respondents and the interviewer are safe

- During the interview, frame the study as a study on women’s health, life experiences or family relations than VAWG.

- Only one woman per household should be interviewed about her experiences of domestic violence

- When interviewing in the context of a household survey, interviewers should be trained to terminate or change the subject of discussion if an interview is interrupted by anyone.

- Sound Methodology: due to the sensitive issues under discussion, there will be a tendency by participants to underplay their experiences. Therefore, the evaluation team will give due concern to the appropriateness of the evaluation methodology.

- Protecting Confidentiality: preserving personal information is one of the fundamental principles involving the collection of data on individuals. The program evaluation team will adhere to UN Women and Partners Code of Ethics, and Safeguarding Policy when addressing concerns about consent, confidentiality, anonymity and the potential impact of the program evaluation data collection on those being consulted. Any personal information that an individual discloses during information collection exercise will be considered as confidential and handled confidentially.

Ethical and Safety Recommendations for Domestic Violence Research:

- The safety of respondents and the research team is paramount, and should guide all the decisions

- Prevalence studies need to be methodologically sound and to build upon current research experiences about how to minimize the under-reporting of violence

- Protecting confidentiality is essential to ensure both women’s safety and data quality

- All research team members should be carefully selected and receive  specialized training and on-going support

- The study design must include actions aimed at reducing any possible distress caused to the participants by the research

- Fieldworkers should be trained to refer women requesting assistance to available local services and sources of support. Where few resources exist , it may be necessary for the study to create short-term support mechanisms

- Researchers and donors have an ethical obligation to help ensure that their findings are properly interpreted and used to advance policy and intervention development

- Violence questions should only be incorporated into surveys designed for other purposes when ethical and methodological requirements can be met.

Sources: WHO Ethical and Safety Recommendations for Research on Domestic Violence Against Women

The evaluation team will obtain individual and group written and oral consent as appropriate to the data collection tools that will be used.  At the start of the interviews, the consultants will explain the purpose of the programme evaluation to each participant and will obtain informed consent. The standard concet form for VAWG survivors will be used in consultation of the program evlatuion team and implementing partners of the safe houses.

Moreover respondents will be informed that there is no perceived potential risk or adverse events as well as anticipated costs to be incurred by participants as they will be interviewed at their location; Furthermore, they will be informed there will be no compensation or rewards for responding to KII and FGD questions.

For confidentiality of VAWG Survivors, the FGDs and KII discussions will be managed by the female consultant

- Research team: all the data collectors will be carefully selected and receive specialized training and on-going support.

- Prevent possible distress: the evaluation team will consider actions aimed at reducing any possible distress caused to the evaluation participant by the evaluation team. Here the evaluation team will give due focus for clarity and understanding on the purpose of the evaluation and the team will provide an introduction on the purpose of the evaluation for respondents and ask if they have any issues or questions that need clarification before proceeding to the discussions.

- VAWG referral system and managing sensitive issues: The evaluation team will be trained to refer women VAWG survivors requiring and requesting assistance from local support services e.g. counseling services, shelters or legal services during the programme evaluation. Prior to data collection activities, the evaluation team will identify potential providers of support or services to whom women can be referred, including health, justice and social services, or women’s organizations.

As the programme has been supported the one stop service centers and safe houses, this will be an opportunity  to reduce the gaps on the spot support and ensure adequate services are available for women.

# 3. Evaluation Matrix

Table 11: Evaluation Matrix

| Evaluation Questions | Indicators | Data Sources | Data Collection Methods | Targets | Baseline value | Program Evaluation Value |
| --- | --- | --- | --- | --- | --- | --- |
| Goal Women and Girls live a life free of violence |  |  |  |  |  |  |
| To what extent did the program contribute to women and girls living a life free from violence | % of women and girls aged 15-49 who have experienced violence in the past 12 months | EDHS Project progress reports National assessment on cases of VAWG investigated, prosecuted and adjudicated | Desk Review | 20% | 23% |  |
| Outcome 1 : An enabling legislation and policy environment in line with international standards on EVAWG and other forms of discrimination is in place and translated into action Output 1.1: Somali and Afar regions’ legislation framework enabled through advocacy on identified attitudes and barriers to adopt family laws in line with the Federal Family Code and international instruments on women’s rights, namely Maputo Protocol and CEDAW Output 1.2: Evidence-based data, information and analysis on VAWG and women’s access to justice available Output 1.3: Capacity of law enforcement bodies strengthened to implement legislation on EVAWG and other forms of discrimination |  |  |  |  |  |  |
| Relevance: To what extent is the programme and the outcome on enabling legislation and policy environment aligned to government national priorities and needs, improving the social norms restrictive of gender equality? Effectiveness: What have been achieved so far? What helped the achievement of the outcomes? Are there still gaps, and if so, where? What was most effective in making progress towards : an enabling legislation and policy environment in line with international standards on EVAWG Efficiency: How efficient the resources used to achieve lobbying for the reversion of regional family lows in Afar and Somali Regions and enabling legislation and policy environment in line with international standards on EVAWG in general ? Impact: What changes brought as a result of the intervention in lobby for aligning the regional family laws to the international human right standards and enabling legislation and policy environment in line with international standards on EVAWG? Sustainability: To what extent will the project result be likely to sustain What will contribute to this? What factors will constrain it? What specific strategies, approaches and activities has UN Women used to build the sustainability? What evidence is there of positive shifts? Lessons Learned: What are the lessons learned through enabling legislation and policy environment in line with international standards on EVAWG? What is needed to enhance the effectiveness, efficiency and sustainability of Ethiopia’s prevention and response to VAWG? What improvements could be made in the next phase of the programme? | # of regional family laws that are aligned with international Human Rights Standards, namely Maputo Protocol and CEDAW General Recommendation 35 on VAW. | Reports from MoWCA and Somali and Afar Regional Government | FGD, KII and Desk review | 9 | 7 |  |
|  | % of cases of violence against women and girls filed in courts that have a verdict reached. | National assessment on cases of VAWG investigated, prosecuted and adjudicated | FGD, KII and Desk review | TBD | TBD |  |
|  | # of women groups and parliamentarians with increased capacity through training to advocate for the adoption of family law in Somali and Afar regions. | Program Report Program Participants | FGD, KII, Desk Review | TBD | TBD |  |
|  | # of evidence-based research studies and/or analyses of Ethiopian women’s access to justice and prevalence and incidence of VAWG across regions produced | National assessment on cases of VAWG investigated, prosecuted and adjudicated, EDHS further analysis and EDHS 2021 | FGD, KII and Desk Review | 4 | 1 |  |
|  | % of reported VAWG cases investigated and prosecuted in targeted areas | Report from FOAG national assessment on cases of VAWG investigated | FGD, KII and Desk review | TBD | TBD |  |
|  | # of police officers, prosecutors, judges and health officers trained in gender-sensitive service delivery to survivors of violence | Training reports, pre and post assessments | FGD, KII and Desk review | 4,000 | 1,000 |  |
| Outcome 2: Favorable social norms, attitudes and behaviors are promoted at community and individual levels to prevent VAWG Output 2.1: Women, girls, men and boys at community and individual levels are mobilized in favor of respectful relationships and gender equality Output 2.2: Increased capacity of traditional and religious leaders in addressing VAWG Output 2.3: Educational curricula and programmes addressing gender equality and VAWG are developed and integrated into formal and non-formal education |  |  |  |  |  |  |
| Relevance: To what extent is the programme and this outcome aligned to government national priorities and needs, improving the social norms restrictive of gender equality? Effectiveness: What have been achieved so far? What helped the achievement of the outcomes? Are there still gaps, and if so, where? What was most effective in making progress towards: improving social norms, attitudes and behaviours Efficiency: How effect the resources used to achieve improving social norms, attitudes and behaviors around VAWG? Impact: What changes brought as a result of the intervention in improving social norms, attitudes and behaviors arund VAWG? Sustainability: To what extent will the project result on social norms, attitudes and behaviors be likely to sustain What will contribute to this? What factors will constrain it? What specific strategies, approaches and activities has UN Women used to build the sustainability? What evidence is there of positive shifts? Lessons Learned: What are the lessons learned through improving social norms, attitudes and behaviors VAWG? What is needed to enhance the effectiveness, efficiency and sustainability of Ethiopia’s prevention and response to VAWG? What improvements could be made in the next phase of the programme? | % of women and men in SASA! Kebeles that change attitude towards spousal violence | Program assessment report of UN Women supported SASA! And Non-SASA! Kebeles in targeted provinces | FGD, KII and Desk review | 70% | Amhara (52% F and 46% Male) and Oromia (40% F and 51% Male) |  |
|  | # of national media guide on gender responsive and sensitive reporting with a section on VAWG reporting produced and endorsed | Copy of the media guideline | FGD, KII and Desk review | 1 | 0 |  |
|  | % of people in communities that apply SASA! Are mobilized in favor of respectful relationships and GE | Assessment report of UN Women supported SASA! | FGD, KII and Desk review | 50% | Oromia (35%F and 10%M) and Amhara (20%F and 22%M) |  |
|  | # of religious and traditional leaders advocating for the promotion and protection of women’s rights | training Reports Study participants voice | FGD, KII and Desk review | 1000 | 100 |  |
|  | # of Standard teachers training manual on VAWG in schools developed | Ministry of Education | FGD, KII and Desk review | 1 | 0 |  |
|  | # of Formal and non – formal education institutions that integrate standard teachers training manual | Ministry of Education | FGD, KII and Desk review | 10 | 0 |  |
| Outcome 3 Women and girls who experience violence use available, accessible and quality essential services Output 3.1: Strengthened capacity of service providers in providing quality coordinated and accessible essential services to women and girl’s survivors of violence in accordance with global essential services package Output 3.2: Availability and accessibility of quality essential services for women and girls’ survivors increased |  |  |  |  |  |  |
| Relevance: To what extent is the programme and this outcome aligned to government national priorities and needs, improving the social norms restrictive of gender equality? Effectiveness: What have been achieved so far? What helped the achievement of the outcomes? Are there still gaps, and if so, where? What was most effective in making progress towards: Efficiency: How efficient the resources used to make VAWG services available, accessible and quality Impact: What changes brought as a result of the intervention in improving essential services of VAWG? Sustainability: To what extent will the project result essential services of VAWG be likely to sustain? What will contribute to this? What factors will constrain it? What specific strategies, approaches and activities has UN Women used to build the sustainability? What evidence is there of positive shifts? Lessons Learned: What are the lessons learned improving essential services of VAWG What is needed to enhance the effectiveness, efficiency and sustainability of Ethiopia’s prevention and response to VAWG? What improvements could be made in the next phase of the programme? | # of VAWG survivors who have accessed comprehensive service | Report from the Ethiopian Network of Shelters and justice bodies | FGD, KII , IDI and Desk review | TBD | TBD |  |
|  | # of joint standard operating procedure in line with global standards on essential services is developed | Ethiopian Network of Shelters annual report | FGD, KII and Desk review | 1 | 0 |  |
|  | # of members of the Network of Ethiopian women shelters that are using standardized operating procedures | Ethiopian Network of Shelters annual report | FGD, KII and Desk review | 9 | 2 |  |
|  | # of shelters available and providing quality, accessible, multi sectoral survivors-based services for women and girl survivors of violence | Report from the Ethiopian Network of Shelters | FGD, KII and Desk review | 16 | 14 |  |
|  | # of shelters using the Essential Services package | Report from the Ethiopian Network of Shelters | FGD, KII and Desk review | 12 | 2 |  |

# 4. Work Plan and milestones for deliverables

Table 12: Program evaluation work plan and time schedule

| Evaluation Phase and Activities | Timeline From December 2022 to February 2023 |  |  |  |  |  |  |  |  |  |  |  | Deliverables |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 |  |
| Phase-I: Literature review and Inception Report |  |  |  |  |  |  |  |  |  |  |  |  | Draft Inception Report- December 2 Final Inception Report- December 19 |
| 1.1 Develop inception report and submit for review | Dec,2 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 Discussion with UN Women team on draft inception report | Dec,7 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 Address comments on the draft inception report & submit the final | Dec,19 |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase-2: Literature Review and Field data collection |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Recruit and train filed assistants |  |  |  | Dec 26 |  |  |  |  |  |  |  |  | Field data collection update report -December 26 |
| 2.2 Communicate field offices and arrange |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 Data Collection in Addis |  |  |  |  | Jan1-5 |  |  |  |  |  |  |  |  |
| 2.4 Travel to Amhara and Oromia |  |  |  | Dec,26-31 |  |  |  |  |  |  |  |  |  |
| 2.5 Travel to Sidama |  |  |  |  |  | Jan9-12 |  |  |  |  |  |  |  |
| 2.6 Travel to Somali |  |  |  |  |  |  | Jan17-21 |  |  |  |  |  |  |
| 2.6 Interview- UN Women team |  |  |  |  |  | Jan,16 |  |  |  |  |  |  |  |
| Phase-3 Data analysis and draft reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Qualitative Data Analysis |  |  |  |  |  |  |  | Jan23-Jan 31 |  |  |  |  | Draft Report February 15/2023 |
| Draft Report |  |  |  |  |  |  |  |  | Feb1-15 |  |  |  |  |
| Communicate the Draft Report |  |  |  |  |  |  |  |  | Feb15 |  |  |  |  |
| Incorporate comments |  |  |  |  |  |  |  |  |  | Feb25 |  |  |  |
| Phase-4: Validation and Final Report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Validation workshop |  |  |  |  |  |  |  | Feb15 |  |  |  | Feb 24 | Validation PPT-February 24/2023 Final Report February 28/2023 |
| Final Evaluation Report |  |  |  |  |  |  |  |  |  |  |  | Feb 28 |  |

# 5. Responsibilities, logistic and support

Table 13: Role and responsibilities of evaluation team

| Program Evaluation Phases | Lead of the Assignment | Communication liaison with UN Women and stakeholders | Role and Responsibilities |  |
| --- | --- | --- | --- | --- |
| - Phase-1 - Inception Report | Martha Nemera | Martha Nemera | International Consultant | National Consultant |
|  |  |  | - Ensure the quality of the inception report and data collection tools - Make the quality clearance before submission of the inception report to UN Women Evaluation Task Manager | - Communicate UN Women on the inception report - Undertake desk review - Develop the inception report with data collection tools and submit to UN Women Evaluation Task Manager for review and approval; - Attend meeting with UN Women on queries on the inception report |
| Phase-2 Data Collection | Martha Nemera | Martha Nemera | - Make a supervision of field data collection in selected regions - Ensure data quality management and assist at office level, validate and triangulate the data with secondary sources. | - Communicate with UN women regarding the data collection - Coordinate data collection plan and communication - Conduct qualitative data collection with divers’ group of KII and FGD - Conduct field debriefing after data collection is completed - Provide update report on field data collection for UN Women Evaluation Task Manager - Transcribe the qualitative data and develop qualitative data filed report |
| Phase-3 Data Analysis | Mr. Leonard Maveneka | Mr. Leonard Maveneka | - Conduct regress data analysis, and in-depth desk review; - Conduct data triangulation and quality assurances | - Support in the qualitative data analysis and triangulation of the data collected from different sources |
| Phase-4 Draft Report | Mr. Leonard Maveneka | Mr. Leonard Maveneka | - Liaison with UN Women in communication with draft report - Undertake literature review - Develop draft report - Address comments on draft report | - Assist the international consultant in draft report - Assist the international consultant in addressing comments on the draft report |
| Phase-5 Validation and Final Report | Mr. Leonard Maveneka | Mr. Leonard Maveneka | - Liaison with UN Women in communication with validation and final report - Validation of the draft report - Incorporate comments and submit final report | - Participate in validation workshop - Address comments in the final report |

# 6. Annexes

## 6.1 Proposed Data Collection Tools

Tool-1: Key Informant Interview Guide

| ### Tool-1.1: KII Interview guide for trained teachers |  |
| --- | --- |
| ### Evaluation Criteria | ### Guiding Question |
| Participation | - What is your role in the program? Tell us about activities that you have participated in? |
| Relevance | - What aspects of the training did you find most useful and why? |
| Effectiveness | - What difference has the VAWG training made in the way you address school VAWG? - Were you provided with a training manual to use in cascading the training? - What were the key drivers and barriers affecting the delivery of results for the Movement activities? - What do you think can be done to improve the quality of the training? - Have you carried out a risk mapping exercise for your school? - What risks did you identify and how are you dealing with them? - Can you explain the referral chain that you have developed for your school and how effective has it been in responding to school violence? |
| Efficiency | - To what extent has the Movement used learning to improve delivery? - Do you think that the support and resources used is adequate? |
| Impact | - Do you think that the program activity brought changes in your work? If yes, what changes? If not, why? |
| Sustainability | - How have you cascaded the training to other teachers at the school? - Apart from teachers, who else do you think should undergo the training and why? |
| Learnings | - What specific lessons were learnt during implementation? - Do you have any recommendations for similar programs? |

| ## Tool-1.2: Key Informant Interview Guide National Coordination Body (NCB) |  |
| --- | --- |
| ## Evaluation Criteria | ## Guiding Questions |
| Participation Coherence and Partnership | - What do you see as your most critical coordination functions? - UN coordination platform on violence against women and children (VAWC) was established bringing together, UNFPA and UNHCR, UNICEF and UN Women. As the NCB, (a) what is your relationship with this platform? (b) Do you see any scope for synergies between the two coordinating bodies (c) is there no duplications in the coordination functions |
| Relevance | - How do you see the relevance of the program in the context of Ethiopia? - How broad do you consider your mandate i.e.Which critical VAWG players do you think need coordination? |
| Effectiveness | - `How effective are NCB’s coordination structures at district level? Are the linkages with the center strong and functional? - What capacities have been built within the NCB to improve your coordination functions? - To what extent have functional NCB coordination structures been established at district level? How effective are they? Can you explain how the coordination functions from the district to the national level? (coherence/effectiveness/ relevance) - The NCB has coordination structures that stretch to the district and regional level. How effective are these structures? What do you think should be done to strengthen the structures, especially at district and regional levels? |
| Efficiency | - To what extent has the improved coordination of the GBVVAWG response from your office resulted in improved quality of VAWG service delivery? If the answer is yes, please explained how this has been achieved? |
| Impact | - Do you think that the program activity brought changes in your work? If yes, what changes? If not, why? |
| Sustainability | - In the past the NCB ceased operations because of financial viability issues. What do you think can be done to make it a more financially viable and sustainable institution in the long term? - Apart from support from UN Women to what extent has the NCB leveraged resources from other sources to ensure its continued sustainability after the grant period? (sustainability) |
| Learning | - What is your key learning from the program? - Do you have any suggestions for a similar program? |

| ## Tool-1.3: Key Informant interview with Ministry of Women and Social Affairs (MOWSA) |  |
| --- | --- |
| ## Evaluation Criteria | ## Guiding Questions |
| Participation, partnership and collaboration, | - As the Ministry is mandated to deal with VAWG, what do you see as your key role(s)? And how effectively have you been able to carry this out? - You work closely with UN Women in your VAWG work. What form has that collaboration taken? (What value has UN Women brought to your work on VAWG? |
| Relevance | - In your opinion, are the three outcomes sufficiently broad to cover the most critical VAWG intervention areas for Ethiopia? If not, what issues are not covered and should have been included? |
| Effectiveness | - The GBVVAWG National Coordination Body is housed in the Ministry of Justice. How closely does your Ministry work with the NCB and do you share the coordination functions between you? Do you think the NCB would be more effective if it was housed in your Ministry? - What elements of the UN Women-supported VAWG interventions were most effective over the programme period? What do you attribute their effectiveness to? - The Family Law has still not been adopted in Somali and Afar. (a) what are some of the underlying reasons that it has still not been adopted (b) what strategies is the government putting in place to facilitate the adoption of the Law (c) what has been the impact of the failure to adopt the law on the well-being of women in the two regions? |
| Efficiency | - What has been the quality of UN Women’s technical support? - In what way has the financial support through UN Women enhanced your capacity to deliver on your mandate? - Which of the interventions were cost-effective and why? |
| Impact | - Several policy dialogues have been held in Afar and Somali involving key stakeholders such as the regional parliament, police, judges, BoJ, BoWCA and Islamic council representatives to influence the adoption of the Family Law. What impact did these interventions have in swaying public opinion in the two states in favor of the Family Law? |
| Sustainability | - How do you see the sustainability of the project results? |
| Learnings | - What is your key learning from the program? - Do you have any suggestion for similar programs? |

| ## Tool-1.4: Key Informant Interview Guide for Ethiopian Women Lawyers' Association (EWLA) |  |
| --- | --- |
| ## Evaluation Criteria | ## Guiding Questions |
| Participations | - What was your key role in the program? How is the partnership with the UN Women in implementing the program? |
| Relevance | - With support from UN Women, your organization established two legal aid centers in Afar and Somali regions. Why were these specific regions chosen? - What have you identified as the barriers to access to What are the most pressing legal issues that the legal aid centers have had to deal with in the two regions? justice for women in the two regions? - Are these the same or similar barriers experienced in other regions of the country? If they are different, what are the major differences and what can you attribute the differences to? |
| Effectiveness | - Can you briefly explain how the legal aid centers work? - How effective have the Legal Aid Centers been in increasing women’s access to justice? - How many women have the legal centers assisted and with what success (in terms of cases that have been handled successfully)? - Based on your experience running legal aid centers in the two regions, what do you see as some of the challenges facing women who want to access legal aid services? - Legal aid is only one of the many services that VAWG survivors need. Can you please explain the referral chain of the other services that the women need and also indicate their availability in the two regions? - UN Women commissioned the “Perception study on women and community’s attitude towards survivors of Violence Against Women and Girls (VAWG) accessing rehabilitation and reintegration services, in Afar and Somali Regions’. Has the study been completed and can we have a copy. If the study has not been completed, can you explain some of the issues emerging from the draft report? |
| Efficiency | - Are the Legal Aid Centers manned by lawyers or by paralegals? How cost efficient are the Legal Aid Centers compared to other means that could have been used to increase women’s access to justice? E.g., the use of a pool of independent lawyers providing services to EWLA. |
| Impact | - According to one of the reports, a total of 40 women were assisted through the Legal Aid Centers. What do you think has been the impact of this intervention on the women in Afar and in Somali? |
| Sustainability | - How sustainable is the concept of Legal Aid Centers? What could be done to make them sustainable within the regions? |
| Learnings | - What is your key learning from the program? - Do you have any suggestions for similar programs? |

| ## Tool-1.5: Key Informant Interview Guide for Church/Faith Leaders using the SASA Faith |  |
| --- | --- |
| ## Evaluation Criteria | ## Guiding Questions |
| Participation and partnership, collaborations, coherence | - What is your role as Church leaders in the implementation of the SASA Faith? - Are there other institutions or organizations carrying out similar interventions to what you are doing and if so, what are the synergies between what they are doing and what you are doing? |
| Relevance | - What do you see as the biggest strength of the SASA Faith Approach in fighting VAWG? (Relevance, effectiveness) |
| Effectiveness | - How effective has SASA Faith been in addressing cultural and religious beliefs that promote GBVVAWG? (effectiveness) - What Church structures have you found to be most effective/conducive to addressing VAWG issues? (effectiveness) - SASA Faith is being implemented through Sermons, theology and Bible Colleges. Out of these, which are (a) the most sustainable methods (sustainability) (b) the most effective methods (effectiveness) (c) the most cost-effective methods? (efficiency) - How many people are participating in the programme that you are implementing? How long does it take to go through the whole cycle? - Compared to other awareness raising and behavior change strategies, what are the advantages of the SASA Faith over other behavior Change strategies? |
| Efficiency | - What are the major financial outlays in implementing SASA if any? Is this a programme you can implement without external funding? (Efficiency, sustainability) |
| Impact | - You have been implementing the SASA Faith for a while now, what impact would you say it has made on the lives of beneficiaries? |
| Sustainability | - The SASA Faith has been implemented with UN Women’s support. How sustainable do you think it will be after the end of the funding period? (sustainability) |
| Learnings | - What is your key learning from the program? - Do you have any suggestions for similar programs? |

| ## Tool-1.6: KII guide for Ministry of Education Official involved in curriculum development |  |
| --- | --- |
| ## Evaluation Criteria | ## Guiding questions |
| Participation, Coherence, Partnership | - What is your role in the project? How is the collaboration and partnership with UN Women in the program? |
| Relevance | - As the Ministry of Education, what benefits do you see in promoting a gender equal, respectful, and non-violent culture among students and teachers? (relevance) - As the Ministry of Education, you must have a vision of what you want to see happening in schools in relation to gender equality and equity as well as in the fight against VAWG in schools. Can you please explain this vision and how you think it would transform the education sector in Ethiopia. (relevance) - How relevant do you think the curriculum development initiative is as a strategy to address VAWG in schools and in society at large? (relevance) - Why do you think the education sector should be involved in the fight against VAWG? (relevance) |
| Effectiveness | - What steps are you taking to promote that culture? And with what success? (effectiveness) - How effective has UN Women’s support in your programme to promote gender equality through the curriculum? (effectiveness) You have been working with UNICEF to engender the educational curricula for some time now. What have been the major milestones in this journey? (effectiveness) What have been some of the major successes in this journey? (impact) What have been the major challenges? (effectiveness/impact, unexpected outcomes) - As the Ministry of Education, what do you consider your priority fighting VAWG in schools or fostering a culture where young people will grow up shunning violence? (Relevance, effectiveness) - What do you see as the education sector’s comparative advantage in fighting VAWG in schools and in the broader society through influencing values and norms from an early age? (effectiveness) - In relation to regions such as Amhara, Tigray and Somali, to what extent are your interventions in those areas factoring in the increased vulnerability of women and girls to GBVVAWG as a result of the conflict? If you are, please give examples and how successful these have been. |
| Efficiency | - What elements of the programme were implemented in a cost effective way? If there are please explain |
| Impact | - Are there any special regions of Ethiopia where you want to see the most change? (Effectiveness, impact) Please explain. |
| Sustainability | - The Ministry has a programme of gender integration in primary education curriculum. To what extent have the capacities of relevant staff in the Ministry been built to enable them to carry on the work even after the UN Women project ends? (sustainability) - To what extent is the Ministry able to sustain the curriculum development initiative even after the end of the UN Women support? (sustainability) |
| Learnings | - What is your key learning from the program? - Do you have any suggestions for similar programs? |

| ## Tool-1.7: Key Informant Interview Guide UN Women |  |
| --- | --- |
| ## Evaluation Criteria | ## Guiding Questions |
| Participation, Coherences, Partnership | - The programme had a broad range of partners both in the government and in civil society. In relation to the CSO partners, what criteria was used in selecting partners? (Partnership and collaboration) - Among UN agencies, UNFPA appears to be the lead on VAWG. UNICEF also has GBVVAWG programmes focusing on children. UN Women also has GBVVAWG programmes such as the one being evaluated. What are the special skills that UN Women brings to the table that makes it particularly suited to focus on VAWG? To what extent does UN Women collaborate with the other two UN agencies on VAWG? (One UN, Coherence, partnership and collaboration |
| Relevance | - What are some of the major highlights in the EVAWG your VAWG programme in Ethiopia? (Effectiveness, impact, relevance) |
| Effectiveness | - Ethiopia has some intractable VAWG proproblems including FGM and child marriages and abductions. Strong cultural beliefs and practices as well as some conservative religious beliefs and practices make the problems even more difficult to address. What tailored interventions have you designed that you believe will shift people’s behavior and practices positively? (effectiveness) - The concept of a code of conduct for teachers and other school staff is noble but (a) how will it be enforced and by who and (b) what are the proposed sanctions for those who break it? (effectiveness) - In addressing GBVVAWG, several external factors are considered important to fight it such as (a) keeping girls in school to reduce early marriages (b) educating girls to make them less vulnerable to GBVVAWG (c) economically empowering women to reduce their dependence on men and less vulnerable to GBVVAWG (d) support to adolescent sexual reproductive rights (ASRHR) programmes to equip girls and young women with information on reproductive health and to be able to access the services. However, in looking at the programme theory of change, such accompanying interventions are not visible. Was this an omission or did the programme leave these interventions to other more specialized agencies? - To what extent do you see synergies in the three outcome areas that the programme was focusing on? If there are synergies, - (a) to what extent were these explored (b) with what success (c) did partners also work to exploit the synergies and (d) how did these strengthen the national VAWG response? (Coherence, effectiveness, efficiency |
| Efficiency | - In terms of resource share, what percentage of UN Women resources in the programme went to prevention compared to response. - What is considered the ideal resource split between the two? In the long term, how would the way the resources are shared reflect on programme sustainability? (e.g., the response such as shelter, access to justice etc. needs constant resources while prevention is about equipping people with knowledge and influencing behavior change and this can be sustained with minimal external resources) (efficiency) |
| Impact | - In the last couple of years since your programme started, conflict has worsened in the regions of Amhara, Tigray, Somali and Afar. To what extent have you redesigned your interventions to take cognizance of the heightened vulnerability of women as a result of the conflict? Please explain (impact) - Drafting a gender sensitive curriculum can work at two levels: reducing VAWG in schools and also grooming young people to be gender sensitive adults who abhor VAWG. Which of the two is your program focus? Please explain why.(impact) |
| Sustainability | - How is the sustainability of the results obtained? In your opinion? - which strategies of the project contributed to sustainability? |
| Learnings | - What is your key learning from the program? What changes stories that the program brought? |

| Tool-1.8: Key Informant Interview Guide, Ministry of Justice |  |
| --- | --- |
| Evlaution Criteria | Guiding Questions |
| Participation, Coherences, Partnership | - There are several VAWG response structures in Ethiopia, which include the police special VAWG unit; the special VAWG courts; social services; counseling services, One Stop Centers and VAWG shelters. How are these different structures coordinated and how has the coordination assisted in creating a seamless and intgrated national VAWG response, (snergies, coherence and coordination). ‘ - Justice delivery and policing are only two functions in relation to VAWG while the bulk of interventions relate more to prevention through awareness raising and behavior change as well as psycho-social support. Is the Ministry of Justice equipped with the necessary skills to address these more important components or to coordinate them? - In your opinion, what other areas should the UN Women programme have focused on to achieve greater impact? And why? |
| Relevances | - The National GBV Coordinating body is housed in the Ministry of Justice. Please explain why this is the case instead of it being housed in the Ministry of Women’s Affairs, which is focused much more on VAWG? (relevance, Coherence) |
| Effectivenes | - There are some VAWG manifestations that are steeped in culture and religious practices rightfully or wrongly, such as FGM/C and early marriages although there are clear laws against them. What are the challenges that the government faces, particularly your ministry, in enforcing compliance with the laws? Going forward, what do you see as the most effective strategy that could be used to enforce compliance? (effectiveness) - The UN Women Programme focuses a lot on the creation of “An enabling legislation and policy environment in line with international standards on EVAWG and other forms of discrimination is in place and translated into action”. What do you see as some of the major legislative and policy gaps that merited this focus by the programme? To what extent have these been addressed? (relevance, effectiveness, |
| Efficency | - In your opinion, to what extent is VAWG prioritized within the government? What are the indications that it is? Is this reflected in the resources allocated to the response? The resources are scattered across various ministries and institutions including Justice, Health, Social services, Ministry of Women and even education. Has an estimate been made in calculating the spending on the various interventions? (efficiency) |
| Impact | - In your opinion, what has been the impact of the programme on the lives of beneficiaries – women and girls – and also on the broader community? Please explain |
| Sustainability | - How sustainable will this programme be after the end of UN Women funding? To what extent is the government prioritizing funding VAWG initiatives? - In your experience, is it easy to attractfunding for VAWG programmes? |
| Learnigns | - What is your key learning from the program? - What do you suggest for similar programs? |

| Tool-1.9: Key Informant Interview Guide, Implementing partners for the Safe Cities |  |
| --- | --- |
| Evaluation Criteria | Guding Questions |
| Participation, Partnership and Coherence | - What is your role in the program? What was the partnership model with UN Women? |
| Relevance | - The concept of safe cities is relatively new in Ethiopia, how relevant is the intervention in the two places where it is being implemented – Addis Ababa and Hawassa? What specific safety challenges is the programme trying to address and with what success? - Hawassa has specific problems because of its high female factory workers population that has already been experiencing high levels of violence, especially among the women working night shifts. To what extent has the project taken the contextual factors into account and what are the specific interventions that have been designed to address these issues and with what success? - Currently Ethiopia is experiencing conflict in several regions. In terms of prioritization, would it not have been more strategic to invest in violence prevention in those areas because of the higher vulnerability of women to war-related violence? |
| Effectivness | - What laws and policies have been developed under the programme to fight VAWG in public places? - How effective has the project been in (a) identifying areas of intervention e.g. street lighting; influencing behavior change among men in their attitude to women in public spaces?To what extent has the project invested in capacity building of town planners to ensure more gender-friendly infrastructure and as part of ensuring the sustainability of the project? |
| Efficiency | - In terms of resource allocation, what percentage has been allocated to prevention of violence against women and girls in public places and what percentage to response. What form has the response taken? How sustainable are the interventions currently in place? |
| Impact | - The programme is still a pilot, what positive changes has it brought into the lives of women and girls in the two cities in terms of reducing their vulnerability to violence in public places? |
| Sustainability | - The concept of safe cities is relatively new, In what ways do you think local authorities can sustain the services after the end of funding? |
| Learning | - What lessons have been learnt from the pilot phase of the project that you think should be taken on board going forward? |

| Tool-1.10: Key Informant Interview Guide, Implementing partners Safe House |  |
| --- | --- |
| Evaluation Criteria | Guiding Questions |
| ## Participation, Partnership and Coheren | - What is your role in the program? How is the partnership with UN Women? - There are several partners who provide a variety of services to survivors. In your opion are their services well coordinated and integrated? If not, what do you think needs to be done to provide seamless services to survivors? |
| ## Relevance | - Compared to the number of women requiring shelter services, what percentage are you able to accommodate? |
| ## Effectiveness | ## How is the Standard Operating procedure is implemented and impacted interventions, ## How is do you work with other stakeholders, referral linkages, and what is achievement of the project in this regard? ## What are the key challenges of shelter services? |
| ## Efficiency | - The provision of shelter for VAWG survivors is critical but also seen as a response to violence that has already been committed and therefore not contributing to VAWG reduction. Under the UN Women grant: - how much of the resources are dedicated to prevention? - what activities fall under the ambit of prevention? - how successful has been the prevention component - what are the linkages between the prevention activities and the service provision components? |
| ## Impact | - According to the Impact Assessment of AWSAD’s Shelter programme, the concept of economic empowerment for VAWG survivors seem to have largely flopped partly because of the mismatch between the skills trained and the requirements of the job market. At the same time, it is acknowledged that there is need to economically empower the women to make them less vulnerable to VAWG. What strategies are being put in place to make the programme more effective and viable? |
| ## Sustainability | - Given the high levels of VAWG in Ethiopia, how sustainable is the concept of institutionalized shelters for VAWG survivors compared to the concept of community-based shelters for instance? |
| ## Learning | ## What lessons have you learnt from implementing the shelter project that can be taken into the next phase of the project? - What do you suggest for similar programs? |

| Tool-1.11: Key Informant Interview Guide for Shelter Coordination Network |  |
| --- | --- |
| Evaluation Criteria | Guiding Questions |
| ## Participation, Partnership and Coherences | - What is the role of the Shelter Coordination Network? |
| ## Relevance | ## What is the revance of the program? |
| ## Effectiveness | - How is the VAWG service provisions? What are the main services and challenges - What support provided by the program? How effective the support provided? |
| ## Efficiency | - How are the resources allocated for the Coordination? |
| ## Impact | ## What permanent changes have you observed among some of the women who have been through the shelter (Improved self-confidence etc)? |
| ## Sustainability | ## Besides current funding from UN Women, what are your other sources of funding to run the shelters? |
| ## Learnings | ## What are the major lessons that you have learnt that you feel can inform how shelters are run in the future (management, activities and programmes that are most beneficial to inmates etc)? |

| Tool-1.12: Key Informant Interview Guide government stakeholders- Regional Cabinets and Women Standing Committee Parliamentarians |  |
| --- | --- |
| ## Evaluation Criteria | ## Guiding Questions |
| Participation, Partnership and Coherences | - What is your role in the program activity? - What support provided by UN Women? |
| Relevance | - In what ways is the programme addressing the VAWG priorities of Ethiopia as articulated in various national documents? |
| Effectiveness | - What was most effective in making progress towards policy ask regarding VAWG and Family law bill in Afar and Somali regions? - How was the training provided for women parliamentarians and women’s groups in Somali and Afar regions to advocate for the adoption of family law in Somali and Afar regions? - How is the effectiveness of the initiative to lobbies the policy influences and decision makers for ending VAWG and improving the normative framework? |
| Efficiency | - What you think that the resources and support provided in this regard were sufficient to achieve the objective? |
| Impact | - What permanent changes do you think this programme has made on the lives of women? - What changes have you observed in community members (men and boys) in their attitude to women and to VAWG that you feel can be attributed to the programme, please explain? |
| Sustainability | - Do you think that the initiative to lobby policy influencers and decision makers for ending VAWG and improving the normative frameworks will continue in the future? If yes how? If not why? |
| Learnings | - What is you key learning form the program activities? - Do you have any suggestions for similar program? |

| ## Tool-1.13: Key Informant Interview Guide government stakeholders- CSA |  |
| --- | --- |
| ## Evaluation Criteria | ## Guiding Questions |
| Participation and Coherences | - What is your role in the program? - What support provide by UN Women? |
| Relevance | - What is the relevance of the activities to your programme to national prioritioes on VAWG? |
| Effectiveness | - What was most effective in making progress towards considering the VAWG in the EDHS? - Do you think that the technical support and capacity building on VAW module provided were sufficient to achieve the objective? |
| Efficiency | - How is the adequacy of the resources supported? For example, expenses to cover data collectors cost etc |
| Impact | - What are the results or changes you have seen as the result of the program support in your work? |
| Sustainability | - Do you think that the initiative supported by the program that is consideration of VAWG indicators in the EDHS will continue in the future? If yes how? If not why? |
| Learnings | - What is your key learning participating in the program? - Do you have any suggestion for similar program? |

| ## Tool-1.14: Key Informant Interview Guide government stakeholders- Federal Office of Attorney General |  |
| --- | --- |
| ## Evaluation Criteria | ## Guiding Questions |  |
| Participation, Partnership and Coherences | - What is your role in the program? How is the partnership and collaboration with UN Women? |
| Relevance | - How relevant are your activities to the national agenda on VAWG? |
| Effectiveness | - How effective was the support provided for FOAG in the undertaking of a national assessment on cases of VAWG reported, investigated, prosecuted and adjudicated in all regions. |
| Efficiency | - Have the programme’s resources been sufficient and appropriate to achieve its outputs and outcomes? - Are there models or alternative approaches/modes of delivering the programme that could work as well in achieving the same results? |
| Impact | - Do you think that the support improved the practice of VAWG cases reported, investigated and prosecuted |
| Sustainability | - Is there any evidence that the outcomes have been/will be sustained? (Please give examples) What facilitates and constrains sustainability? - To what extent will you be likely to sustain the knowledge, capacity, systems, and other benefits of UN WOMEN’s support? What will contribute to this? What factors will constrain it? - Are there particular priorities for support that would What specific strategies, approaches and activities has UN Women used to build the sustainability of programme benefits? What evidence is there of positive shifts? - enhance sustainability? |
| Learnings | - Are there any lessons you/your organization have learned through your engagement with the UN Women PRVAWG programme that you want to share? What is needed to enhance the effectiveness, efficiency and sustainability of Ethiopia’s prevention and response to VAWG? - What improvements could be made in the next phase of the programme? - Are there any other comments you would like to make that we didn’t cover in this interview? |

| ## Tool-1.15: Key Informant Interview Guide with One Stop Center |  |
| --- | --- |
| ## Evaluation Criteria | ## Guiding Questions |
| Participation and Coherences | - Is there any support you received from UN Women and its implementing partners? |
| Relevance | - How is the relevance of the support provided? |
| Effectiveness | - What service are you providing in the center? - What referral mechanisms are in place? - What is your relation with the safe houses established? - How is the effectiveness of the support provided? - What are the key challenges that the center is currently facing? |
| Efficiency | - Do you think that the resources provided are sufficient addressing the need? |
| Impact | - What changes do you observe as a result of the program support? |
| Suitability | - How do you see the sustainability of the services? What contribute for the sustainability What is the constraints for the sustainability |
| Learnings | - What are your key learnings working with the UN Women Program? - Do you have any suggestions for similar programs? |

| ### Tool-1.16: Ethiopian Broadcasting Agency |  |
| --- | --- |
| ### Evaluation Criteria | ### Guiding Questions |
| Participation, Partnership and Coherences | - What is your role in the program? - Do you think that the initiative supported by the project that is considering gender equality in media will continue in the future? If yes, how? If not, why? |
| Relevance | - What is the relevance of your broadcasts to the fight against VAWG? |
| Effectiveness | - What support is provided by UN Women? - What was most effective in making progress towards considering VAWG in media broadcasting? |
| Efficiency | - Do you think that the resources and support provided were sufficient to achieve the objective? |
| Impact | - What lasting changes do you think have come about as a result of your broadcasts? |
| Sustainability | - Do you think your programmes can be sustained after the end of external funding? If yes how? If not why? |
| Learnings | - What is your key learning participating in the program? |

### Tool-2: Focused Group Discussion Guided

| Tool-2.1: FGD guide for Women of Faith (Amhara -Debre Birhan and Ankober), and Somali regions) |  |
| --- | --- |
| Evaluation Criteria | Guiding Questions |
| Participation | - As Women of Faith, what do you see as your role in VAWG prevention and response? |
| Relevance | - What elements of the training did you find particularly relevant to you and your community? - What are the main VAWG issues in your community? - Which of these have been most difficult to deal with and why? - To what extent has the programme been able to deal with them and with what results |
| Effectiveness | - What skills did you gain from the gender training specifically in how to handle VAWG in your community? - How have you used the skills that you acquired from the training - The programme also trained men on VAWG prevention and response. - What is the level of collaboration between the men and women who were trained? - Beside Women of Faith, who else do you think should undergo the training - In your opinion, how effective has it been? the training and deploying of Women of Faith in addressing the VAWG issues in your community? Can you give examples of cases where you have intervened and with what results |
| Efficiency | - How is the resources efficiency for the trainings and other supports? |
| Impact | - Are there any improvements that you would like to see in the way the training programme was designed and executed? |
| Sustainability | - Do you think the programme can be sustained after the end of UN Women support? |
| Learnings | - What is your key learning from the program activities? Do you have any suggestions for similar program? |

| ### Tool-2.2: FGD guide with members of the Yellow Movement |  |
| --- | --- |
| ### Evaluation Criteria | ### Guiding Questioons |
| Participation | - What is your role in the program? In which activities you patriciate with UN Women? |
| Relevance | - What do you see as the benefit of having the Yellow Movement at the University - What VAWG issues have you dealt with at the university |
| Effectiveness | - What difference has the Movement made to the lives of female students at the University? - How well did the Movement respond to the needs of female students, including how these needs evolved over time? - Apart from financial support, has UN Women Ethiopia providdo you ted any technical support to the Movement and if so, what form has this support taken? In what ways has the technical support improved project implementation? - What advocacy issues has the Movement been working on and with what success? How effective have been your Weekly Table Day Activism in (a) raising awareness about campus VAWG (b) in changing attitudes and practice among students and lecturers? |
| Efficiency | - Did you think that the resources you have were used most efficiently? If not, what do you think could have been done better - Given your situation, do you think more could have been achieved with the resources at your disposal than was achieved? |
| Impact | - What changes (long term and short term) in the lives of female students can be directly attributed to the work of the Movement |
| Sustainability | - As an activist Movement, how broad is your funding base and how sustainable is it? |
| Learnings | - One of the Movement’s founders Halina has gone through harrowing experiences of sexual harassment in the workplace. What lessons can you say were learnt from this that can inform the way the Movement deals with VAWG going into the future? - Do you have any suggestion for similar programs? |

| ### Tool-2.3: FGD interview guide for community members (men) |  |
| --- | --- |
| ### Evaluation Criteria | ### Guiding Questions |
| Participation | - What is your role in the program? In which activities do you participate? |
| Relevance | - What are some of the biggest VAWG issues facing this community - What do you consider to be the underlying causes of VAWG - Are there any ways in which the VAWG awareness raising conducted in your community contradicts the beliefs and cultural practices that you value as a people in this region |
| Effectiveness | - How are they being addressed? By whom? With what success - What do you think needs to change to reduce the level and severity of VAWG in the community - What do you think the role of men in prevention and response of VAWG - What institutions are you working with to address VAWG in your community? How effective are they? |
| Efficiency | - How is the resources efficiency I the activities you participated in? |
| Impact | - What difference have they made in the way you understand VAWG and respond to it |
| Sustainability | - Do you think that the awareness on VAWG made by the project will sustain? If yes how? If not why? |
| Learnings | - What needs to be done more to prevent and respond to VAWG |

| ### Tool-2.4: Focused Group Discussion Guide -Survivors of VAWG |  |
| --- | --- |
| ### Evaluation Criteria | ### Guiding Questions |
| Participation | - In what activities you participate in the safe house? |
| Relevance | - How is the relevance of the activities in the prevision and response of VAWGs in your community? |
| Effectiveness | - What are the main VAWG issues in your community? Which of these have been most difficult to deal with and why? - How did you come to this Shelter? Where did you get the information? - What support did you receive from these Shelters? How effective is the service provided - Do you think that the support you received is helpful? How? If not, why |
| Efficiency | - Are there any improvements that you would like to see in the way the service was designed and executed? |
| Impact | - What changes brought in your life after joining the safe houses? |
| Sustainability | - Do you think these changes will be sustained? |
| Learnings | - What elements of the training did you find particularly relevant to you and your community? And why? - What is your advice for service providers around VAWG? |

| ### Tool-2.5: Focused Group Discussion Guide - Guide for Church/Faith Leaders using the SASA Faith |  |
| --- | --- |
| ### Evaluation Criteria | ### Guiding Questions |
| Participation | - What is your role as Church leaders in the implementation of the SASA Faith? - How many people are participating in the SASA programme that you are implementing? How long does it take to go through the whole cycle? |
| Relevance | - What do you see as the biggest strength of the SASA Faith Approach in fighting VAWG? |
| Effectiveness | - SASA Faith is being implemented through Sermons, theology and Bible Colleges. Out of these, which are (a) the most sustainable methods (b) the most effective methods (c) the most cost-effective method? - What Church structures have you found to be most effective/conducive to addressing VAWG issues? - How effective has SASA Faith been in addressing cultural and religious beliefs that promote VAWG? |
| Efficiency | - Compared to other awareness raising and behavior change strategies, what are the advantages of the SASA Faith over other behavior Change strategies |
| Impact | - You have been implementing the SASA Faith for a while now, what impact would you say it has made on the lives of beneficiaries |
| Sustainability | - What are the major financial outlays in implementing SASA if any? Is this a programme you can implement without external funding? - The SASA Faith has been implemented with UN Women’s support. How sustainable do you think it will be after the end of the funding period? |
| Learnings | - What are your key learnings implementing the SASA? - What suggestions do you have for similar program running SASA? |

### Tool-3: In-depth interview guide

| ## Tool-3.1: In -Depth Interview Guide – Selected women and men |  |
| --- | --- |
| ## Evalaution Criteria | ## Guiding Questions |
| Context and Relevance | - Tell us about your life experiences? Are there any challenges that you have been facing regarding VAWG? Have you ever experienced any forms of VAWG? If you please tell me about (if you are comfortable telling)? - How is your participation in the program? How are you selected for the program support? Where do you get the information? |
| Effectiveness | - What services are provided by the program? - How is the effectiveness of the services? - What are the mechanisms for prevention and response of VAWG? How effective are the mechanisms? How accessible are the mechanisms? Are they used extensively by women survivors of VAWG and if not, what is the reason that they are not used as much (could be attitudes of officers; stigmatization of VAWG ; distances to facilities; lack of facilities; lack of knowledge of the existence of facilities) |
| Efficiency | - How is the efficiency and adequacy of the resources in the activities you participated in? |
| Impact | - Do you think that the program supported has brought changes in your life? If yes what? If not, why? - How do you see the changes in your life as a result of the support received from the program? |
| Sustainability | - Do you think that the services provided will be sustained in the future? - Do you think that you will continue with the changes that brought in your life after the project support? If yes how? If not why? |
| Learnings | - What are your key learnings participating in the program? - What do you recommend for prevention and response of VAWG? |

### Tool-4: Checklist for observation

## Tool-4.1: In -Depth Interview Guide – Selected women and men

- Observe the adequacy of the materials in Safe House? - Observe the management of the Safe House - Observe how the Women and Children friendly courts operate? - Observe separate benches for women in police stations

### Tool-5: Guiding questions for documentation Most significant change stories?

## Guiding Questions Tool-5.1 Documentation most significant change stories Guide – Checklist

- What was the situation before? - What support was provided by the programme? - What change have you seen as a result of the support (a) to you as an individual or (b) to the community at large?? - Do you think that the results brought by the project will be sustained? If yes, how? If not, why not?

## List of documents reviewed

- Kh Abrokwah (2021) Addressing gender-based violence against women and children in Africa

- K Abrokwah (2021) Addressing gender-based violence against women and children in Africa

- UNODC (2020) Addressing violence against women and girls in Ethiopia

- Cordon M et al (2018) Systematic Literature Review of Gender Based Violence in Ethiopia Magnitude, Policies, and Interventions Cordon M et al (2018) Systematic Literature Review of Gender Based Violence in Ethiopia Magnitude, Policies, and Interventions

- Gebre T et al (2020) The Prevalence of Gender-based Violence and Harmful Traditional Practices against Women in the Tigray Region, Ethiopia

- Cordon M et al (2018) Systematic Literature Review of Gender Based Violence in Ethiopia Magnitude, Policies,

- and Interventions

- UNICEF. The dynamics of social change: Towards the abandonment of female genital Mutilation/Cutting in five African countries. 2010.

- Fite MD. The Ethiopia’s legal framework on domestic violence against women: A critical perspective. International journal of gender and women’s studies. 2014;2(1):49-60

- Gordon M et al (2018) Systematic Literature Review of Gender-Based Violence in Ethiopia Magnitude, Policies, and Interventions  UN Women Donor Report (2021) Preventing and Responding to Violence against Women and Girls in Ethiopia for the agreement with the Government of Denmark: ‘Combating Violence Against Women and Girls in Ethiopia

- Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016. https://dhsprogram.com/pubs/pdf/FR328/FR328.pdf.

- Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016.. https://dhsprogram.com/pubs/pdf/FR328/FR328.pdf.

- Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016.. https://dhsprogram.com/pubs/pdf/FR328/FR328.pdf

- Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016.

- Jones N, Gupta T, Tefera B. Evaluation of Norway’s support to women's rights and gender equality in development cooperation: Ethiopia case study report. NORAD. 2015.

- Jones N, Tefera B, Stephenson J, Gupta T, Pereznieto P. Early marriage and education: The complex role of social norms in shaping Ethiopian adolescent girls’ lives. ODI. 2014. https://www.odi.org/sites/odi.org.uk/files/odi-assets/publications-opinion-files/9183.pdf. Lelieveld M. Child protection in the Somali region of Ethiopia. Save the Children, Mercy Corps, and Islamic Relief.

- Jones N, Gupta T, Tefera B. Evaluation of Norway’s support to women's rights and gender equality in development cooperation: Ethiopia case study report. NORAD. 2015.

- Jones N, Tefera B, Stephenson J, Gupta T, Pereznieto P. Early marriage and education: The complex role of social norms in shaping Ethiopian adolescent girls’ lives. ODI. 2014. https://www.odi.org/sites/odi.org.uk/files/odi-assets/publications-opinion-files/9183.pdf.

- UNFPA-UNICEF. Joint programme on female genital Mutilation/Cutting: Accelerating change. 2014. UNFPA-UNICEF. Joint programme on female genital Mutilation/Cutting: Accelerating change. 2014. UNFPA-UNICEF. Joint programme on female genital Mutilation/Cutting: Accelerating change. 2014.

- Presler-Marshall E (et al) 2022, Girls and women’s social and economic empowerment in Ethiopia’s Afar and Somali regions: challenges and progress A review of the evidence

- Presler-Marshall E (et al) 2022, Girls and women’s social and economic empowerment in Ethiopia’s Afar and Somali regions: challenges and progress A review of the evidence

- Alemu B (2007) Early marriage in Ethiopia: Causes and health consequences

- Gordon M et al (2018) Systematic Literature Review of Gender-Based Violence in Ethiopia Magnitude, Policies, and Interventions  Presler-Marshall E (et al) 2022, Girls and women’s social and economic empowerment in Ethiopia’s Afar and Somali regions: challenges and progress A review of the evidence

- UN Women (2019) Annual Report to the Royal Danish Embassy and Government of the Republic of Ireland January to December 2019

- Jones N, Tefera B, Stephenson J, Gupta T, Pereznieto P. Early marriage and education: The complex role of social norms in shaping Ethiopian adolescent girls’ lives. ODI. 2014.

- Cordon M et al (2018) Systematic Literature Review of Gender-Based Violence in Ethiopia Magnitude, Policies, and Interventions

- ora A. Assessment of sexual violence against female students in wolaita sodo university, southern Ethiopia. J Interpers Violence. 2013;28(11):2351-2367

- Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016. https://dhsprogram.com/pubs/pdf/FR328/FR328.pdf.

- Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016 Jones N, Gupta T, Tefera B. Evaluation of Norway’s support to women's rights and gender equality in development cooperation: Ethiopia case study report. NORAD. 2015.

- UNFPA. Endline evaluation of the UNFPA support prevention and management of gender based violence in Ethiopia. 2017

- Mekuria A, Nigussie A, Abera M. Childhood sexual abuse experiences and its associated factors among adolescent female high school students in Arbaminch town, Gammo Goffa zone, southern Ethiopia: A mixed method study. BMC International Health and Human Rights. 2015;15.

- Programme Document, Preventing and Responding to VAWG in Ethiopia, UN Women, 2019

## 6.3 Terms of References (TOR)

## 6.4 Evaluation management and reference group members

(*) Tables, figures, graphs and diagrams should be numbered and have a title.

World Health Organization, on behalf of the United Nations Inter-Agency Working Group on Violence Against Women Estimation and Data (2021)

Gebre T et al (2020) The Prevalence of Gender-based Violence and Harmful Traditional Practices against Women in the Tigray Region, Ethiopia

Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016. https://dhsprogram.com/pubs/pdf/FR328/FR328.pdf.

Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016.. https://dhsprogram.com/pubs/pdf/FR328/FR328.pdf.

Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016.. https://dhsprogram.com/pubs/pdf/FR328/FR328.pdf

. Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016.

Jones N, Tefera B, Stephenson J, Gupta T, Pereznieto P. Early marriage and education: The complex role of social norms in shaping Ethiopian adolescent girls’ lives. ODI. 2014.

Presler-Marshall E (et al) 2022, Girls and women’s social and economic empowerment in Ethiopia’s Afar and Somali regions: challenges and progress A review of the evidence

Presler-Marshall E (et al) 2022, Girls and women’s social and economic empowerment in Ethiopia’s Afar and Somali regions: challenges and progress A review of the evidence

Presler-Marshall E (et al) 2022, Girls and women’s social and economic empowerment in Ethiopia’s Afar and Somali regions: challenges and progress A review of the evidence

UN Women (2019) Annual Report to the Royal Danish Embassy and Government of the Republic of Ireland January to December 2019

Tora A. Assessment of sexual violence against female students in wolaita sodo university, southern Ethiopia. J Interpers Violence. 2013;28(11):2351-2367

Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016. https://dhsprogram.com/pubs/pdf/FR328/FR328.pdf.

Ethiopia Demographic and Health Survey. Central Statistical Agency. 2016

Jones N, Gupta T, Tefera B. Evaluation of Norway’s support to women's rights and gender equality in development cooperation: Ethiopia case study report. NORAD. 2015.

UNFPA. Endline evaluation of the UNFPA support prevention and management of gender-based violence in Ethiopia. 2017

Mekuria A, Nigussie A, Abera M. Childhood sexual abuse experiences and its associated factors among adolescent female high school students in Arbaminch town, Gammo Goffa zone, southern Ethiopia: A mixed method study. BMC International Health and Human Rights. 2015;15.

Preliminary Gender Profile of Ethiopia, 2014. European Union/UN Women: Addis Ababa, Ethiopia, p. 19.

Central Statistical Agencyu (2016) Ethiopia Demographic Health Survey

Lelieveld M. Child protection in the Somali region of Ethiopia. Save the Children, Mercy Corps, and Islamic Relief.

Jones N, Gupta T, Tefera B. Evaluation of Norway’s support to women's rights and gender equality in development cooperation: Ethiopia case study report. NORAD. 2015.

Jones N, Tefera B, Stephenson J, Gupta T, Pereznieto P. Early marriage and education: The complex role of social norms in shaping Ethiopian adolescent girls’ lives. ODI. 2014. https://www.odi.org/sites/odi.org.uk/files/odi-assets/publications-opinion-files/9183.pdf.

UNFPA-UNICEF. Joint programme on female genital Mutilation/Cutting: Accelerating change. 2014. UNFPA-UNICEF. Joint programme on female genital Mutilation/Cutting: Accelerating change. 2014. UNFPA-UNICEF. Joint programme on female genital Mutilation/Cutting: Accelerating change. 2014.

Cordon M et al (2018) Systematic Literature Review of Gender Based Violence in Ethiopia Magnitude, Policies,

and Interventions

UNICEF. The dynamics of social change: Towards the abandonment of female genital Mutilation/Cutting in five African countries. 2010.

Fite MD. The Ethiopia’s legal framework on domestic violence against women: A critical perspective. International journal of gender and women’s studies. 2014;2(1):49-60

Gordon M et al (2018) Systematic Literature Review of Gender-Based Violence in Ethiopia Magnitude, Policies, and Interventions

Programme Document, Preventing and Responding to VAWG in Ethiopia, UN Women, 2019.

Cordon M et al (2018) Systematic Literature Review of Gender Based Violence in Ethiopia Magnitude, Policies, and Interventions

UN Women Donor Report (2021) Preventing and Responding to Violence against Women and Girls in Ethiopia for the agreement with the Government of Denmark: ‘Combating Violence Against Women and Girls in Ethiopia

Alemu B (2007) Early marriage in Ethiopia: Causes and health consequences

Gordon M et al (2018) Systematic Literature Review of Gender-Based Violence in Ethiopia Magnitude, Policies, and Interventions

Jones N, Gupta T, Tefera B. Evaluation of Norway’s support to women's rights and gender equality in development cooperation: Ethiopia case study report. NORAD. 2015.

Jones N, Tefera B, Stephenson J, Gupta T, Pereznieto P. Early marriage and education: The complex role of social norms in shaping Ethiopian adolescent girls’ lives. ODI. 2014. https://www.odi.org/sites/odi.org.uk/files/odi-assets/publications-opinion-files/9183.pdf.

Central Statistical Agencyu (2016) Ethiopia Demographic Health Survey