Annex 1: Terms of Reference

STATEMENT OF NEED:

UN Women is seeking the services of a consultancy firm to conduct a final evaluation of UN Women’s regional programme ‘Men and Women for Gender Equality’ – Phase I (2015–2019) and Phase II (2019–2022). The evaluation is expected to have more focus on Phase II – the implementation timeframe of which will end by February 2022, given that Phase II builds upon results and lessons learned from Phase I. The evaluation process will be initiated in April 2021 and completed by 31 December 2021.

Background and context

UN Women works to promote behavioural and social norm change for gender equality and women’s empowerment (GEWE) as a cross-cutting issue across its developmental outcomes, identified in the UN Women’s Strategic Plan 2018–2021. UN Women’s regional programme ‘Men and Women for Gender Equality’ (MWGE) speaks to several outcomes of the Strategic Plan, especially Outcome 4:

‘Ensuring that all women and girls live a life free from all forms of violence’.

The entity believes that the best way to stop violence against women and girls is to prevent it from happening in the first place, including through the engagement of men and boys. In its support to Member States, UN Women places emphasis on the prevention of violence against women and girls in private and public spaces, e.g. through transforming negative behaviours and social norms and by advocating for and institutionalising gender transformative policy and legislative reforms.

A number of internationally agreed norms and standards relate specifically to UN Women’s work on promoting gender equality, ending violence against women and catalysing changes in social norms and normative/legislative frameworks for GEWE:

Declaration on the Elimination of Violence against Women, 1993.

International Conference on Population and Development drawing links between gender equality and reproductive health and rights, 1994.

Beijing Platform for Action identifying specific actions for governments to take to promote gender equality and prevent and respond to violence against women and girls, 1995.

The UN Human Rights Council’s resolution on accelerating efforts to eliminate all forms of violence against women, 2012.

64th session of the Commission on the Status of Women, at which leaders pledged to ramp up efforts to fully implement the Beijing Declaration and Platform for Action, including ending all forms of violence and harmful practices against women and girls, 2020.

Regional overview

Many countries across the Arab States region have taken strides in the last two decades to advance gender equality and combat discrimination and violence against women. Nevertheless, inequalities in power, influence and access to/control over resources between men and women remain challenging in the region. The region continues to score the lowest globally on both women’s political and economic participation, according to the Global Gender Gap Reports. Moreover, the region has seen a decrease in gross domestic product and gross national incomes, increases in poverty and youth unemployment, and a widening gap between rural and urban areas and between the rich and poor. While both men and women have been impacted by these macroeconomic developments, women remain disproportionally affected, owing to gender inequalities. Many women and girls face multiple and intersecting forms of discrimination. The most vulnerable women live in rural areas below the poverty line without formal employment, and many of those are heads of households. Women with disabilities are further marginalised.

Gender discriminatory behaviours and challenging social norms that are conducive to gender inequality, violence and discriminatory practices in families and communities are mostly reinforced through social institutions – such as faith-based institutions, the media and the education system – and discriminatory laws and policies existing across the Middle East and North Africa (MENA) region. These gender inequalities are exacerbated by conflict and displacement in the region. Several policies also contribute to and reinforce gender discrimination. The majority of personal status and family codes that exist in the MENA region discriminate against women and girls. For example, many of these codes confer upon women the status of a dependent and/or minor; consider fathers the sole guardians of their minor children; qualify a woman’s testimony as being worth half the evidentiary value of a man before a court; deprive women of their inheritance rights; and require women to go to court to obtain a divorce, while a husband can divorce through verbal renunciation.

Research findings also demonstrate how traditional attitudes around concepts of qiwamah and wilayah, which are commonly understood to legitimise men’s authority over women, can be misused as justification for rigid gender roles and to legitimise personal status laws and Convention on the Elimination of all Forms of Discrimination Against Women (CEDAW) reservations, on the basis that certain articles of CEDAW are contrary to Islamic teachings or Sharia.

Economic and social policies in the region often lack a clear gender dimension. For example, there is an absence of family-friendly policies that promote the equal division of unpaid childcare and household work, which is a significant hindrance to women’s participation in the workforce.

Given the context, and given also that 80% of the indicators for gender equality across the Sustainable Development Goals (SDGs) lack data, concerted efforts are required for evidence-based policy formulation and interventions that ensure that no woman or girl is left behind.

On a positive note, the region has been committed in the last two decades to gender equality and its collective fight against discrimination and violence against women. Egypt, Jordan, Lebanon and Morocco have each ratified CEDAW; however, they have entered reservations concerning articles that are fundamental to the full and effective implementation of the Convention, often justifying this on the grounds that the provisions are contrary to Sharia. Conversely, the State of Palestine and Tunisia have ratified CEDAW with no reservations. All these countries also adopted the Beijing Platform for Action. They have also translated their international commitments to gender equality into constitutional, legislative and political reforms. For more details about the six countries of the MWGE – Phase II implementation please refer to Annex III A: Phase I ProDoc and Annex III C: Phase II ProDoc.

Programme overview

In 2015, UN Women Regional Office for the Arab States initiated the programme ‘Men and Women for Gender Equality’ – funded by Sweden – to understand how best to tackle the root causes of gender inequality and discrimination and address them through a bottom-up approach. The programme focused on engaging men and boys to achieve gender equality in partnership with women and girls, while also promoting the rights of women in the family by providing alternative interpretations of religious texts. Phase I demonstrated the need to continue effective development approaches to address the root causes of gender equality, to create new and innovative approaches, and to continue supporting social movements that tackle inequalities and unfavourable social and gender norms. The programme implementation countries were Egypt, Palestine, Lebanon and Morocco, where the International Men and Gender Equality Survey (IMAGES) studies were conducted.

It is against the above background that UN Women initiated the second three-year phase of the ‘Men and Women for Gender Equality’ programme (MWGE Phase II) in March 2019, with the overall goal of catalysing social norm change to enable men and women to exercise their rights and opportunities equally in six countries: the four countries of Phase I and two new additions, Jordan and Tunisia, which were added to MWGE Phase II due to strong interest from national counterparts in conducting the IMAGES researches in order to contribute to data availability on the topic of understanding masculinities and social gender norms in both countries.

Programme goal

With the overall goal of creating communities where men and women in the Arab States societies are able to exercise their rights and opportunities equitably as active citizens in their communities and countries, the programme intends more specifically to contribute to the following:

Create communities that have more gender equitable attitudes and behaviours.

Integrate and promote gender responsive practices in key regional and national institutions (governments, academia, faith-based institutions, media) and regional networks.

Advocate for and support the drafting, revision and/or approval of laws, policies and strategies that promote gender equality.

Duration of the programme and budget

MWGE Phase I was a four-year programme that was implemented between January 2015 and February 2019 and funded by the Government of Sweden through the Swedish International Development Cooperation Agency (Sida) with SEK 86.12 million (around USD 10,386,500). The second phase is a three-year programme, from March 2019 to February 2022, with a budget of SEK 90 million (around USD 10,839,690). The second phase needs to fill a funding gap of around USD 3 million and efforts are underway for resource mobilisation, which have resulted in some additional funds mobilised by UN Women from other donors and programmes at country level.

Programme management and implementation arrangements

The UN Women Regional Office implements the regional activities and has the overall responsibility for the coordination and implementation of the programme and works in close collaboration with the country offices, who implement country-level activities.

The current programme team in Phase II is made up of 13 professionals and consists of a Regional Programme Manager (international staff), two Regional Programme Analysts (one international and one national) and six National Programme Coordinators (at country level). In addition, there are four Project Assistants in Egypt, Lebanon, the State of Palestine and Morocco; a regional communications consultant, with capacities in campaigning and communications; and a regional monitoring and evaluation consultant. The team works in close collaboration with UN Women’s regional and country teams, thematic advisors and programme staff at regional and country levels, for the effective implementation of the MWGE programme and to influence the design and the implementation of other UN Women programmes. Please see Annex III A: Phase I ProDoc and Annex III C: Phase II ProDoc for more information about the management arrangements of the programme.

The programme has a Regional Advisory Committee (RAC) that meets once a year to inform the planning and strategic directions for the programme and to monitor and support progress on implementation, based on the report of the Regional Programme Manager and the National Programme Coordinators. The country advisory groups are set up at country level in the four countries which are in Phase II, to advise the country programmes. These groups are chaired by UN Women Country Representatives – or their alternates.

Project beneficiaries and key stakeholders

The programme targets the following four groups:

A diverse population of men, women, boys and girls at community level, with a special focus on the marginalised populations, to promote and strengthen the principle of Leave No One Behind in accordance with the 2030 Agenda.

The public, with a focus on young men and young women, reached through awareness raising interventions and campaigns.

Key institutions (governments, academia and the private sector), mobilised through workshops and other targeted interventions.

Policymakers, through policy and advocacy dialogues through civil society actors.

The programme works with a wide range of partners and stakeholders at regional and national levels, including government institutions (including intergovernmental institutions such as the League of Arab States), international organisations working on related issues such as masculinities and evidence building, civil society organisations (CSOs), the private sector, and UN agencies such as UNFPA, UNICEF, UNESCO and ILO. For a complete list of the community-based organisations (CBOs) and the partner organisations with a contractual relationship with UN Women, and the list of other stakeholders that cooperate with UN Women for the MWGE programme implementation, please see Annex II A: MWGE Phase II – First Annual Progress Report 2019. For the Phase I of the project, the list of partners is included in Annex I – E: Final Narrative 2015 – 2019.

Theory of Change or intervention logic

The programme in Phase II builds upon the results and lessons learned from Phase I. It is based on a set of assumptions and preconditions to create a pathway for change: If (1) communities demonstrate more gender equitable behaviours; if (2) key institutions (academia, faith-based institutions, media, governments) and networks integrate/promote gender responsive practices; and if (3) laws, policies and strategies promoting gender equality are drafted, revised and/or approved; then (4) men and women in Arab societies can equally exercise their rights and opportunities as active citizens in their communities and countries, because (5) equality will be promoted at all levels of society through positive behavioural change and through a favourable legislative environment.

Annex III C: Phase II ProDoc includes the Theory of Change (ToC) figure.

The programme uses three key strategies: (a) address main root causes of gender inequality e.g. patriarchal structures, by tackling negative attitudes, behaviours and social norms; (b) promote gender responsive institutional practices; and (c) strengthen advocacy for policy and legal change.

Based on the proposed goal and ToC, the programme in Phase II has three outcomes, with two to three outputs each:

| Outcome 1 Communities have more gender equitable behaviours. Women, men, girls and boys develop positive behavioural change toward gender equality and are supported to take action to promote gender equality (GE) within their communities. | Outcome 2 Key regional and national institutions (government, academia, faith-based institutions, media) and regional networks integrate/ promote gender responsive practices. | Outcome 3 Laws, policies and strategies promoting gender equality drafted, revised and/or approved on (a) gender discriminatory laws; (b) gender-based violence; (c) paternal/parental leave; and (d) gender strategies promoting male engagement. |
| --- | --- | --- |
| Associated Outputs |  |  |
| 1.1 Interventions for challenging social norms and promoting gender equality are implemented and replicated. | 2.1 Key institutions commit to more gender responsive practices. | 3.1 Civil society organisations have greater capacity to advocate for legal and policy change based on the research findings. |
| 1.2 A regional model for engaging fathers in gender equality exists. | 2.2 Networks commit to GE and male engagement through replication of programme practices and material developed through the programme. | 3.2 Increased availability of research and knowledge products on gender equality and masculinity in the region. |
|  |  | 3.3 Strengthened capacity of key government decision makers to develop laws, policies and strategies. |

The programme results and resource framework and Programme Management Framework in Phases I & II are presented as Annex III B and D.

Key programmatic interventions

Research and data: the programme generates cutting-edge evidence and data to fill the existing evidence gap in the region. A few examples include:

The International Men and Gender Equality Survey (IMAGES), which is the first multi-country study in the MENA region carried out in partnership with Promundo and local research partners to take a wide-angle lens to the lives of women and men and their attitudes towards gender equality. IMAGES was conducted in Egypt, Palestine, Morocco and Lebanon in Phase I, while it is being developed in Tunisia and Jordan during Phase II.

Knowledge products and tools on women’s rights in Muslim families to promote gender equitable interpretations of religious texts and legal reforms for gender equality, in collaboration with Musawah.

Other knowledge products developed under the programme that were replicated and used to inform other programmes, research initiatives and capacity building activities that promote GEWE.

Evidence-based advocacy:

Advocacy for development of national policies and programmes on: fatherhood and caregiving; gender socialisation; promoting the engagement of youth, with a focus on young men; ending violence against women; and family-friendly workplace policies and equitable workplace practices, advocating for a unified Personal Status law and granting nationality rights to women across the implementing countries.

The institutionalisation of Program P (fatherhood programme) and advocacy for paternal leave.

Cooperation and partnership with national governments and intergovernmental organisations such as the League of Arab States, the Swedish Agency of International Development (Sida), and in-country government and national women organisations in Egypt, Palestine, Morocco, Lebanon, Tunisia and Jordan to strengthen policy and legal structures and processes for GEWE.

Community engagement, capacity development and youth networks: engagement with communities to test, replicate and scale up innovative interventions, including:

community and national-level action grants implemented by local CSOs and CBOs to engage young men and women in gender equality initiatives, and fathers and men in general in violence prevention and childcare.

gender transformative parenting programmes rolled out in Egypt, Morocco and Palestine (Phase II) and informed by Program P, conducted in Lebanon (Phase I), which was an intervention for engaging fathers in caregiving and maternal and child health. These parenting programmes use a gender transformative methodology which provides concrete strategies and activities to engage men in active fatherhood, starting from their partners’ pregnancies through to their children’s early years, while promoting broader gender equality through parenting and within marriage and the family.

the #Because_I_am_a_man regional campaign, launched in 2017, using the key findings of the IMAGES research and other communications materials to challenge gender stereotypes and raise awareness on the positive roles men can play in achieving gender equality.

enhance capacity of women’s rights advocates and networks to promote gender equality in the family context by using gender-equal interpretations of Islam.

media outlets, journalists and media students are being engaged by the programme to promote gender sensitive reporting and monitoring.

At regional level

Regional networking and communities of practices to promote collaboration, cross-learning, and dissemination of best practices to promote gender equality, including through the engagement of men and boys. In addition, cooperation with regional and global institutions and networks such as the Anna Lindh Foundation and the Regional Accountability Framework of Action to End Child Marriage in the Middle East and North Africa (MENA)/Arab States region (RAF). One additional regional partnership with the Arab Scouts has been pursued by the programme in order to reach out to young people across the region to promote their awareness and behavioural change for gender equality.

The programme supports the establishment of the UN Women Regional Office for Arab States’ Gender Innovation Agora as a platform for youth advocates across the region to promote GEWE in their national context.

At global level

Collaboration with MenEngage Alliance, UN Women’s HeForShe initiative and UN Women’s Communications Department at Headquarters is being maintained by the MWGE programme on an ongoing basis in order to disseminate and share knowledge and experiences generated by the programme in the Arab States region.

Some additional details about the programme can be found here.

Implementation status

The following description provides a snapshot of the current status of implementation and key achievements of the programme in Phase II:

Under Outcome 1:

In 2019–2020, over 15,000 men and women have been targeted by local interventions implemented by 25 CBOs in Egypt, Lebanon, Morocco and Palestine to promote behavioural change for gender equality and take actions in favour of gender equality within their own communities. Preliminary evidence already confirms positive shifts in behaviours of some men, who because of the CBOs initiatives are increasingly taking their share in unpaid care and domestic work. Impact has also been observed in indirect beneficiaries (i.e. children, family members and neighbours), who have benefited from direct beneficiaries’ involvement to challenge gender stereotypes and harmful practices such as early marriage.

The three gender transformative parenting programmes that will engage around 800 fathers and mothers in Palestine, Morocco and Egypt in 2021 are well advanced in their implementation. The programme design was finalised in Palestine, Morocco and Egypt after formative research was conducted by local CSOs in each country. Furthermore, in Palestine curriculum development and training for 20 trainers was undertaken. The three programmes will be further implemented and completely rolled out in 2021. Program P was also adapted during Phase I in Lebanon and is now being institutionalised by the Ministry of Social Affairs.

Since April 2020, more than 16 million people were reached by the ‘Because I am a Man’ regional campaign, which produced and disseminated over 200 different materials, including social media videos, short documentary-style videos, caricatures, billboards in prominent locations, TV programme production, radio adverts and radio drama series, songs and music videos, animations, and other stories of change published online. The campaign generated a social media engagement surpassing 20 million people, 45% of them male.

Under Outcome 2:

A new regional partnership with the Arab Scouts has been formalised and the development of a first-ever regional strategic plan for gender equality of the Arab Scouts has been initiated, with technical support from UN Women. Some initiatives of the programme with the scouts to raise awareness on gender equality (e.g. a photo competition on gender equality in social media) also started implementation, reaching out virtually to many of the five million Scout members present in the MENA region.

Institutionalisation of programme’s knowledge products and tools by government institutions continued in the countries of implementation. For example:

In Lebanon, the programme supported three military and security agencies to roll out the gender curricula and trainings on gender equality to military officers.

In Lebanon, the Ministry of Social Affairs adopted Program P as its fatherhood module for Social Development Centers. In Egypt, the Ministry of Youth was engaged in the contextualisation of the programme’s ‘youth advocacy toolkit for gender equality’ and negotiated with UN Women its integration in the Ministry’s programmes and rollout.

Under Outcome 3:

Relevant evidence has been made available and extensively utilised by stakeholders (e.g. in government reports, academic papers, policy briefs and project documents). In 2020, the development process of IMAGES in Jordan and Tunisia has resulted in the finalisation of the questionnaires of the quantitative and qualitative research components in both countries, after a comprehensive process led by local research partners in both countries, facilitated by UN Women and supported by Promundo.

In 2020, 13 online capacity building sessions and one webinar were delivered with technical support from Musawah to strengthen the capacity of 151 regional advocates to campaign in favour of feminist interpretations of Islamic teachings. As a result, some of them took initiatives within their organisations to advocate family law reforms within their national contexts across the MENA region. Further, two policy briefs on the topics of ‘Muslim Family Law Reform’ and ‘Child Marriage’ were also launched and disseminated to the public, and one video and other audio-visual materials were disseminated in social media to promote reforms of the laws that are inspired or based in Islam. These audio-visual materials were viewed 52,208 times in social media and received positive feedback from public audiences.

The increased capacity of CSOs supported by the programme and the ongoing support for the implementation of advocacy strategies with CSOs and governments in Phase II have resulted in the approval of a law against sexual harassment by the Lebanese Parliament in December 2020. Other advocacy efforts continued in Lebanon in favour of a law on equal nationality rights and a unified personal status law; in Egypt for paternity leave and to improve the provisions of maternity leave; and in Palestine for the inclusion of paternity leave in the labour law and within institutions’ policies/bylaws, as well as for the endorsement of the Family Protection Bill.

Key challenges

The main challenges experienced by the programme in Phase II are described as follows:

Overall, the COVID-19 pandemic and the subsequent lockdowns and restrictions put in place by the governments across the region presented a challenge to the logistics of planned programme activities. This was particularly relevant for the engagement of/advocacy with governments and governmental institutions at both regional and national levels. The process of IMAGES also experienced delays in Jordan and Tunisia due to COVID-19, resulting in an extension of the IMAGES implementation timeframe until 2022 in both countries.

The COVID-19 pandemic also obliged the programme and the CBOs to adjust/adapt some interventions to fit the new context, while new opportunities were also pursued by the programme. For example, a stronger focus was given to media and social media campaigning to promote men's engagement in unpaid care and domestic work and in prevention of violence against women.

Engaging men in the gender transformative programmes and, in general, working with and encouraging the participation of married men that have financial and economic responsibilities to provide for their families has been challenging.

Obtaining the support of the community leaders to work on a non-service-related project that challenges prevalent social norms was especially difficult at the beginning of implementation.

Targeting men from disadvantaged groups, such as those with disabilities and with diverse sexual orientations, has been challenging owing to the lack of capacity, proper resources, and the cultural practices that discriminate against them and that then to influence behaviours of key stakeholders involved. Further, the lockdowns due to COVID-19, copmbined with the obligation to conduct certain CBOs activities remotely/online, resulted in the exclusion of some of the most disadvantaged remote populations who did not have access to IT and the Internet.

The political instability in some countries has affected the work of the CBOs and/or the normal course of programmes’ implementation. This has been the case in Lebanon and Tunisia, for example. Further, the tragic blast in Beirut in August 2020 also impacted the CBOs both in terms of material and human losses.

Past reviews, evaluations and lessons

- The midterm review (in August 2017) of Phase I found the programme to be very relevant, unique and innovative in addressing gender equality challenges and power relations between men and women in the region. There was an overall consensus on the pertinence of the theme of masculinities and engaging men and boys, the need to address a knowledge gap through the various research in the programme, and the relevance of targeting new and emerging CSOs. Key lessons learned for the future programme were:

It is necessary to engage and involve potential national partners early in all aspects of the programme design. This ensures greater ownership and enhances the linkage of the different components: research, capacity development and advocacy.

There could be more meaningful consultation with country offices in the design of the programme, the logframe and the selection of regional partners. In Lebanon, a country of no UN Women presence at the time, more careful attention should have been paid to engagement and ownership of the partners, including the main government counterpart of UN Women in the country.

It helps to have more openness with regional partners in terms of sharing the overall framework submitted to the donor (Sida) during the formulation process. This enables partners to see how their work fits into it.

Full reports of Phases I & II can be accessed in Annex I A, B, C, D, E, and Annex II A.

- Formative Evaluation of Community-Based Solutions and National-Level Grants for Promoting Gender Equality and Engaging Men and Boys, covering the period 2015–2018 in Lebanon, Morocco, and Palestine. The evaluation started in 2018 and completed in January 2019, and made the following key recommendations:

- UN Women and its partners should expand their engagement strategy to include more segments of the community and multiple stakeholders, influencers and role models to further strengthen and formalise the multiplier effect of its current programming.

There should be greater emphasis on placing interventions within a broader human rights framework in future programming, ensuring that gender equality and women’s rights and issues of intersectionality are firmly embedded in that framework.

UN Women could expand its capacity building of partner organisations and individuals with whom it is working on engaging men and boys for GEWE, in terms of institutional capacity as well as capacity on GEWE.

To support and see more meaningful and sustained social change, increase the duration of community-based grants to two years. Also ensure that grants have a clear ToC – linked to the broader programme ToC – and stronger monitoring, with closer linkages between national and community-based grants.

It is worth continuing to support and expand non-traditional activities to promote GEWE, as this has contributed to changing traditional stereotypes.

The full report and the management response can be accessed here: Formative Evaluation: Community Based Solutions and National Level Grants for Promoting Gender Equality and Engaging Men and Boys

- There are also 14 cases where men, women and youth took actions that promote gender equality across the communities targeted by the programme and that were documented in stories written following the Most Significant Change (MSC) technique. The MSC is a participatory monitoring and evaluation method that involves the collection of significant change (SC) stories emanating from the field level and the systematic selection of the most significant of these stories by panels of designated stakeholders or staff. Due to the complex nature of the project, the MSC technique was better suited to capture social change. For more information, please refer to Annex VI: Phase I MSC Stories.

Evaluation purpose and objectives

The purpose of this final evaluation is twofold; (a) accountability, to assess the overall performance of the programme and achievement against the planned results; (b) learning, by studying the nature and processes of interventions to determine which strategies and elements worked well, in which context and why, and potential for replicating or scaling up the successful innovations. At the same time, it will contribute towards building a body of evidence around engaging men and women for GEWE for other UN Women partners and sector players.

Therefore the evaluation is both summative and formative in nature.

Specifically, the objectives of this evaluation are to:

analyse the relevance of the programme objectives, intervention logic, strategy and approach at national and regional levels, as well as UN Women’s comparative advantage/added value in this area as compared with key partners.

assess organisational efficiency, partnerships and coordination mechanisms in progressing towards the achievement of the programme results.

assess the connectedness and sustainability of the results and the intervention in advancing gender equality in the target countries.

assess effectiveness and the likelihood of impact of the programme intervention on the target individuals, groups, communities and institutions.

identify and document lessons learned, good practices and innovations, success stories and challenges within the programme, to inform future work of UN Women to transform negative behaviours and challenge prevalent gender social norms, including by engaging men and boys.

Use and users of the evaluation

The findings will be used to inform future programmatic decisions, organisational learning and accountability, as well as for the identification of good practices to strengthen UN Women’s strategies and programmes to transform negative behaviours and challenge gender social norms, including through the engagement of men and boys in the targeted countries, region and beyond.

Targeted users of the evaluation: The targeted users of the evaluation are UN Women Senior Management at regional and country levels, programme staff, current and potential donors (Sida) and other key stakeholders (government partners, other regional actors, UN system).

Evaluation scope

The evaluation shall cover all aspects of the programme’s implementation of Phase I and Phase II and the programme period from January 2015 to May 2021.

It will include six countries where activities are being implemented: Egypt, Lebanon, Morocco, Palestine, Jordan and Tunisia. It will also include the regional initiatives taking place at Arab States regional level. Due to the complex, interconnected, multifaceted nature of the programme, the evaluation will also cover a few selected themes/interventions in order to develop case studies to provide in-depth analysis of the selected themes/interventions.

The evaluation will be conducted between April 2021 and December 2021.

Evaluation criteria, questions and methodology

Evaluation criteria:

The evaluation will use the OECD/DAC evaluation criteria, including relevance, effectiveness, efficiency, connectedness and sustainability and contribution to impact (likelihood of), and will answer evaluation questions related to these criteria. Considering the mandates to incorporate human rights and gender equality in all its work and the UN Women Evaluation Policy, which promotes the integration of women’s rights and gender equality principles, these dimensions will have a special attention in this evaluation and will be considered under each evaluation criterion.

Furthermore, the evaluation is to be conducted in line with: UNEG Norms and Standards for evaluation; the UNEG Code of Conduct for Evaluations in the UN System; UN Women evaluation guidelines, including Evaluation Policy; GERAAS evaluation report quality checklist; and UN Women’s ‘How To Manage Gender-Responsive Evaluation’ handbook. The evaluation shall also be guided by the UN Women Pocket tool for managing gender responsive evaluation during COVID-19.

At inception stage, the evaluation team is expected to develop an evaluation matrix summarising key questions, indicators, sources of information and methodology to guide the analysis and triangulation. The final evaluation matrix will be validated by the evaluation task managers and the evaluation reference group constituted in the framework of this evaluation processes and will be approved in the evaluation inception report.

The evaluation will, in general, seek to answer the follow key questions:

Relevance

How relevant and evidence-informed is the programme intervention logic and Theory of Change (ToC) to bring and sustain gender transformative changes in behaviours and challenge social norms, institutions, policies and practices at national and regional levels? To what extent are the ToC’s underlying assumptions still valid?

To what extent do the intervention strategies and activities respond to the regional and country contexts and specific needs/priorities of the target individuals and groups, including those who are most vulnerable?

To what extent did the programme adapt to the emerging crises across the region and continue to be fit for purpose?

What is the comparative advantage of UN Women in leading this programme? Is the value addition of UN Women well understood and recognised among the regional and national stakeholders, including the UN partner agencies?

Effectiveness

To what extent and in what ways has the programme been effective in designing and implementing interventions for promoting positive behaviours and challenging social norms that underpin gender inequality and its various manifestations, such as gender-based violence?

How effectively has the programme been able to create and share evidence base and knowledge products that can support in advocacy efforts for GEWE?

To what extent and in what ways has the programme been effective in creating an enabling environment for policy-level changes to promote gender equality? To what extent did the community-level interventions influence policy and vice versa?

How relevant and effective have capacity building initiatives been for the national authorities, CSOs, feminist groups, and other targeted institutions to bring forth legal and policy-level changes as a result of the programme interventions?

How effective is the programme’s innovation and scaling-up strategy and practice? What are some of the key successes, as well as not so successful stories in scaling up innovative initiatives and associated learning? Are there any opportunities and entry points for further scaling up?

How effective has the programme been in achieving results, given the impact of the COVID-19 pandemic? Were the adaptations and adjustments undertaken by the programme to respond to the COVID-19 context adequate to achieve the expected results and impact?

Efficiency

Is the programme management structure ‘fit for purpose’ with the regional and country-level institutional arrangements to deliver the results in a cost effective and efficient manner?

Is the regional arrangement successfully leveraging the combined effects of the multi-country programme?

Have the financial resources been optimally deployed and used to achieve the results?

Have the strategic partnerships been optimally developed and utilised to contribute towards the programme results and for gaining economies of scale?

Does the programme have an effective monitoring and evaluation framework and systems to measure complex transformations such as positive behavioural changes, as well as to capture discernible, reliable evidence of UN Women’s contribution to changed social norms, institutions and policy/legal frameworks?

How successful has the programme been in its resource mobilisation efforts, taking the COVID-19 crisis into consideration? How has the funding gap been resolved by the programme to achieve the agreed results?

Gender and human rights

How has the programme addressed the underlying causes of gender inequality and discrimination and to what extent has it successfully transformed negative behaviours and challenged the negative social norms?

To what extent does the programme incorporate the principle of Leave No One Behind, providing special focus on the marginalised groups and individuals?

To what extent was a human rights-based and gender transformative approach incorporated in the design and implementation of the programme?

How effective was the programme in identifying and addressing the differentiated needs of disadvantaged groups and individuals?

Sustainability

What indications are there that the outcomes will be sustained, e.g. through requisite capacities, systems, structures, community of practices, etc.? Will the relevant activities continue in the same or modified format after funding reduces or is withdrawn?

To what extent did the programme invest/result in strategic partnerships?

To what extent are policy and regulatory frameworks in place that will support the continuation of gender transformational work?

To what extent was capacity of national government and other programme partners developed in order to ensure sustainability of efforts and benefits, including the capacity to raise funding (or allocate national budget) for financial sustainability?

To what extent are the models/innovative approaches implemented by the programme to achieve GEWE outcomes institutionalised in the targeted countries and at regional level?

Is it recommended to pursue a follow-up programming (new programme phase or new programme) after MWGE Phase II? If so, what would be the overall design and adjustments needed for this future programming to maximise effectiveness and impact? What could be the overall design of a future programme, according to what has worked and what has not worked so far?

Impact (likelihood of)

What were the positive (and negative) changes in the lives of the target group that occurred directly or indirectly due to the programme activities?

To what extent is the programme changing the power dynamics in relationships between men and women at individual, family, community and systems levels?

Did the programme influence policy and legal changes to promote GEWE outcomes?

Evidence, learning and knowledge management

Has the programme contributed towards increased availability of evidence, research and knowledge products on gender equality and masculinity in the targeted countries and region?

How effective are the learning and knowledge management strategy and practices? To what extent do they support promotion of cross-country, cross-regional learning?

To what extent do the data, evidence and lessons systematically feed into learning and programmatic decision making?

What are some of the key lessons learned that can be shared beyond the concerned specific programme?

Evaluation design and methodology

This will be a theory-based, utilisation-focused evaluation, based on participation and involvement of relevant stakeholders and partners in the countries throughout the evaluation process. The evaluation will be based on gender and human rights principles and adhere to the United Nations Evaluation Group (UNEG) Norms and Standards and Ethical Code of Conduct and UN Women Evaluation Policy and guidelines.

It will have to adopt more systems thinking and complexity-responsive design and apply a feminist approach to evaluation to examine issues of power and to understand and evaluate whether and how the programme has contributed or led to changes in the root causes of gender inequalities and power structures. It will apply a mixed-method approach, using qualitative as well quantitative methods and using triangulation to validate the various sources of information.

The evaluation will be applying relevant gender-analytical frameworks such as the Social Relations Framework or Gender and Work framework to assess how gender discriminations and inequalities created, maintained and reproduced in institutions (i.e. the household, community, market and states) are being challenged and transformed through the programme. The Gender Results Effectiveness Scale can be used to measure the effectiveness of the programme and rate it against the five-point ratings scale, moving from gender negative to gender transformative, measuring results that contributed to changes in norms, cultural values, power structures and the roots of gender inequalities and discrimination.

The programme uses a diverse range of means of implementation/interventions to achieve the programme results, such as campaigns, community engagement, capacity building, policy advocacy, etc. The evaluation will therefore be comprised of a selection of relevant evaluation methods and tools to evaluate the programme and address the evaluation questions.

A list of suggested methods and tools are presented below; however, these are indicative, and interested bidders are expected to choose, and present relevant methods and tools based on their interpretation of the evaluation assignment.

- The evaluation could adopt and apply the Social Norms Analysis Plot (SNAP) Framework developed by CARE to develop story vignettes to measure changes in behaviour and social norms over time, and to inform ways that interventions can be further tuned for greater impact. Other relevant methods could also be suggested and used, depending on the evaluator’s assessment of the context and data availability.

- Contribution analysis and robustness of the ToC to assess the overall contribution of the programme towards the gender equality outcomes using the existing or reconstructed programme ToC and results chain to gain an understanding of the conditions that affect results; to identify those strategies that are effective; to collect information that helped adaptation or lack thereof; and, should the desired results not materialise, to ascertain whether this was because of programme design, implementation or external factors beyond the control of the programme.

- Evaluate the policy advocacy and normative work using relevant methods such as the Bellwether method, Intense Period Debriefs, Policymaker Ratings, Outcome mapping, System Mapping, Process Tracing, etc. and evaluate the work related to networks and institutional change for GEWE using methods such as network analysis, MSC, etc.

- Established methods for evaluating training and capacity building initiatives such as the Pact’s Capacity Development Evaluation framework and the Kirkpatrick model.

This is a regional programme, so the main report will focus on how results brought together under the programme ToC have been delivered efficiently and are likely to be sustainable. However, the evaluation will also present country-specific findings and recommendations in the form of six country summary reports. In addition, the evaluation will deliver at least three thematic case studies to present an in-depth analysis about the intervention, as suggested below:

One case study on behavioural and social norms change, covering an in-depth analysis of the initiatives engaging males, such as the interventions focused on fatherhood.

Programme’s contribution in advocacy to pursue legal and policy reform in favour of GEWE.

Evidence and learning portfolio of the programme to fill the evidence gap and utilisation by stakeholders of the evidence, knowledge products and good practices undertaken by the programme.

The evaluation team is encouraged to review these at the inception stage, to validate these or present alternate case study themes.

The evaluation will use a wide stream of multiple quantitative and qualitative data collection and analysis methods, which include a combination of portfolio analysis, desk-based review, a series of online and onsite interviews and survey with relevant stakeholders, target groups and individuals, coordinators of the programme, and country case studies in the programme countries.

Methodological rigour and report quality will be ensured specifically through the Regional Evaluation Specialist (RES) as well as through the Evaluation Management Group, Evaluation Reference Group and Evaluation Steering Committee.

The evaluation design will have to take into consideration the challenges presented by the COVID-19 pandemic and shall be guided by the UN Women Pocket tool for managing gender responsive evaluation during COVID-19.

Evaluation time frame

The implementation of Phase I of the programme began in January 2015, and Phase II will be completed by February 2022. The evaluation process will run from April 2021 to December 2021, inclusive of the preparation phase.

The intended evaluation calendar includes:

Evaluation inception phase (completed by end of May 2021)

Virtual data collection from the field (completed by mid- August 2021)

Data analysis and draft report writing (completed by end of September 2021)

Submission of final report (completed by mid of November 2021)

Final dissemination workshop and other evaluation products (By December 2021).

Data collection will be conducted in Egypt (including with the regional stakeholders), Palestine, Lebanon, Morocco, Jordan and Tunisia in coordination with UN Women staff in the regional and country offices and key relevant stakeholders in the implementation of the project.

Evaluation governance structure and process

The evaluation will be a consultative, inclusive and participatory process and will include a threefold management structure which consists of an Evaluation Steering Committee, an Evaluation Management Group and Evaluation Reference Group.

In addition to the three bodies mentioned above, the RES UN Women Regional Office for Arab States (ROAS) will support the evaluation process technically. Relevant country offices will closely support the coordination for the field visits, including logistical support.

The evaluation will be carried out by an external independent evaluation company. Under the guidance of the Evaluation Management Group (EMG), the evaluation team will ensure that the evaluation is conducted in accordance with the UNEG Ethical Guidelines and Code of Conduct for Evaluation in the United Nations system and other key relevant guidance documents in UN Women.

Function and composition of the different bodies

Evaluation Management Group (EMG) will be led by the RES of the UN Women Arab States Regional Office. The EMG will be responsible for the overall management of the process, including the recruitment of the evaluation team, the coordination of field missions and the quality assurance of the evaluation deliverables. The RES is a member of the UN Women Independent Evaluation Service (IES) of the Independent Evaluation and Audit Services (IEAS) and will ensure the greatest degree of independence during the entire evaluation process. The EMG will liaise with the Evaluation Steering Committee and the Evaluation Reference Group to obtain final endorsement and approval of the evaluation deliverables.

Evaluation Reference Group (ERG) facilitates the participation of relevant stakeholders in the design and scope of the evaluation, raising awareness of the different information needs, maintaining quality assurance throughout the process and disseminating the evaluation results. The ERG is composed of key national stakeholders from government and CSOs in the six countries, Sida (and other potential donor partners), key MWGE programme staff members (MWGE Regional Programme Manager, MWGE Regional Programme Analysts, MWGE Regional Communications consultant, and MWGE national coordinators from the six countries of implementation), UN Women relevant thematic experts from ROAS and HQ, and relevant regional and national programme partners.

Evaluation Steering Committee (ESC) will be the key accountable body that will ultimately endorse the evaluation report and will be responsible for the development of an evaluation Management Response (MR) to address the recommendations included in the report. The ESC will be chaired by the Regional Director, ROAS, and will include Sida, the Deputy Regional Director, ROAS, and the six UN Women's country representatives (or their alternates) from the six countries of implementation.

Detailed terms of reference (ToR) of the above groups are presented in Annex VII: ToR of evaluation groups.

Phases of the evaluation process

The evaluation process will include the following stages:

- Preparation: gathering and analysing programme data, conceptualising the evaluation approach, internal consultations on the approach, preparing the ToR, establishment of the evaluation governance structure and selection of the evaluation team.

Inception: consultations between the evaluation team and the EMG, inception meetings with the ERG and ESC, programme portfolio review, light evaluability assessment and scoping exercise, finalisation of stakeholder mapping, review of the result logics, analysis of information relevant to the initiative, finalisation of evaluation methodology and preparation and validation of inception report.

Data collection and analysis: in-depth desk research, in-depth review of the programme documents and monitoring frameworks, in-depth online interviews as necessary, staff and partner survey/s, and onsite data collection. Debriefing sessions with the key in-country stakeholders will be organised to present emerging trends/preliminary findings and to build ownership of the findings with programme counterparts. The team leader may be asked to debrief the EMG at the end of the country visits. This helps to obtain a sense of the evaluation team’s preliminary findings ahead of the draft reporting phase.

Analysis, validation, and synthesis stage: analysis of data and interpretation of findings and drafting and validation of an evaluation report and other communication products.

Dissemination and follow-up: once the evaluation is completed, UN Women is responsible for the development of a Management Response to evaluation recommendations within six weeks of the final approval of the evaluation report, publishing the evaluation report, uploading the final evaluation report on the UN Women GATE website and disseminating evaluation findings among key stakeholders.

The evaluation team will be responsible for Phases II, III and IV with the support of UN Women, while UN Women is entirely responsible for Phases I and V.

Expected deliverables and time frame

The evaluation team is responsible for the following deliverables:

Draft inception report: The evaluation team will present a refined scope, a detailed outline of the evaluation design and methodology with evaluation matrix, stakeholder mapping and stakeholder selection for data gathering, a sampling strategy for more in-depth analysis of various aspects of the performance of the programme, and a strategy for collecting, analysing and aggregating different sources of data. The report will include an evaluation matrix and a detailed workplan with finalisation of the schedule for country visits and stakeholder interviews (see UNEG Guidelines on inception reports).

Final inception report: addressing comments and feedback from the EMG and ERG.

In-country briefings: The team will present preliminary data to in-country key stakeholders for discussion after completing the data collection phase in the field. The in-country debrief is needed to review data with selected key stakeholders, increase the evaluation team’s understanding of data accumulated so far, and identify data issues or gaps that may be addressed/collected/revisited before leaving the country. The in-country debrief is not to be used to present preliminary findings, as the data analysis is not yet completed and could mislead stakeholders. Presentation material is to be submitted to the EMG prior to the debriefing session.

Presentation of preliminary findings to EMG and internal ERG members: A PowerPoint file detailing the emerging findings of the evaluation will be presented for validation and feedback with the EMG and internal ERG members. The evaluation team will incorporate the feedback received into the draft report.

Presentation to external members of ERG: The revised presentation will be delivered to the reference groups for comment and validation.

Draft evaluation report: The first draft report includes background, methodology, limitations, findings, conclusions, lessons learned and recommendations sections.

Final evaluation report: The final report will include a concise Executive Summary and annexes detailing the methodological approach/analytical products developed during the course of the evaluation, and a (maximum) 10-page synthesis of findings from each country visited and case studies. An Arabic copy of the report will be provided after finalising the English version.

Evaluation communication products: A PowerPoint/Prezi presentation of the final key evaluation findings and recommendations, and a two-pager/infographics on the final key findings, lessons learned and recommendations.

All completed tools and datasets making up the different lines of evidence should be made available to the Regional Evaluation Specialists upon request (including field notes, transcribed highlights from interviews and focus group discussions, and details from quantitative analysis).

All products – such as inception, draft and final reports – will be validated by the ERG. The evaluation team will maintain an audit trail of the comments received and will provide a response on how the comments were addressed in the final inception report. The final evaluation report will be approved by the ESC.

Evaluation time frame

The evaluation team will be expected to complete the tasks within the indicative time frame:

| Tasks/deliverables | Expected delivery date |
| --- | --- |
| Inception phase |  |
| Desk review of background documentation | April 2021 |
| Inception meeting with ERG and EMG | April 2021 |
| Inception report (including three rounds of revision) | End of May 2021 |
| Data collection phase |  |
| Additional documents review, (online) interviews and FGDs for data collection | by mid-August 2021 |
| Analysis and reporting phase |  |
| Presentation of preliminary findings (2) | Mid-September 2021 |
| Draft report with country summary and thematic case studies | End of September 2021 |
| Final report (including three rounds of revision), final country and thematic case studies | Mid of November 2021 |
| Final dissemination of the evaluation, 2-page evaluation Brief with infographics, and evaluation communication products (PPT) | By December 2021 |

Evaluation team composition and requirements

To ensure independence and fulfilment of UN evaluation standards, the IES of the IEAS Regional Evaluation Specialists in the Arab States Region will assume overall responsibility for the design and oversight of this evaluation. Within this arrangement, an external independent evaluation firm with a combination of the requisite expertise in evaluation, and relevant thematic area(s) expertise will be contracted to undertake this evaluation.

The evaluation is to be conducted by a company which is expected to propose a team composed of the following categories:

- Core Evaluation Team;

Additional non-specialised personnel.

The core evaluation team

This team is expected to consist of:

- Team leader/senior international evaluation consultant (who would assume a team leader role and be the main responsible person for the coordination of the whole spectrum of the evaluation process and quality deliverables listed in the ToR);

- An international evaluation specialist;

- Thematic expert(s); and

- National consultants.

The evaluation team itself should strive for gender balance in its composition and possess background knowledge/expertise in the countries covered by this evaluation.

Additional non-specialised personnel

The core evaluation team may draw upon other non-specialised expertise as necessary. These resources may include, but are not limited to:

- Researchers;

- Editorial and communications staff;

- Administrative and logistical assistance personnel; and

- Translators.

Overall, the team should be familiar with feminist evaluation approaches, mixed‐methods, theory‐ based, utilisation‐focused, participatory, and gender and human rights-focused evaluations in the context of negative gender behavioural transformation, advocacy and policy work.

The selected firm should make every effort to ensure that the original members of the evaluation team that begins the project will work on the project through to its completion.

Quality assurance

The firm must have an Evaluation Quality Assurance System (EQAS) that will be used throughout the evaluation process. The team leader will ensure the quality assurance for evaluation deliverables before submitting the evaluation deliverables to UN Women.

The team/firm should take measures to ensure data quality, reliability and validity of data collection tools and methods and their responsiveness to gender equality and human rights. (COVID-19-related scenario and link to the resources).

Duties and responsibilities of the international evaluator team leader:

Assume sole responsibility in ensuring the consistency, quality and timely delivery of expected products, and overall coordination with UN Women Regional Evaluation Specialists;

Lead preparation of the inception report outlining design, approach and methodology of the evaluation and workplan of the evaluation team;

Direct and supervise the work of the international and national consultants;

Lead meetings with the reference groups and other stakeholders;

Lead the preparation of the draft and final evaluation reports and evaluation communication products.

Duties and responsibilities of the international evaluation specialist:

Provide overall support and work under the overall leadership and guidance of the evaluation team leader;

Support evaluation preparatory phase including synthesising information for the inception report;

Lead data collection missions in selected country;

Support the preparation of all evaluation deliverables, including the analyses and synthesis of evaluation evidence and reports drafting;

Lead the preparation of evaluation communication products.

Duties and responsibilities of the thematic expert(s):

Act as an advisor on key thematic areas covered in the programme;

Lead the thematic case studies, including report writing under the supervision of the team leader;

Provide technical and strategic inputs into the evaluation process and key evaluation products: inception report, case studies, preliminary/emerging findings, and the draft evaluation report.

Duties and responsibilities of the national consultants:

Support inception phase through initial desk review, analysis of available reference material and in-depth stakeholder analysis based on agreed criteria;

Assist in the preparation of missions with UN Women offices as relevant;

Participate in country data collection missions;

Conduct interviews and collect data as advised by the team leader;

Attend and support the preparation of all meetings and presentations;

Support the analysis of the evidence at country level for the synthesis report and contribute towards the country case studies.

Qualifications and requirements of the team leader

At least a master’s degree in social sciences, gender studies, development studies, economics, international relations, or a relevant social science-related area;

At least 10 years of relevant experience of periodically conducting evaluations of strategies, policies and/or development programmes preferably focused on gender equality, women's empowerment and social transformation;

Seven years of experience in leading complex, multi-country evaluations, including team supervision and management;

Proven experience of designing and leading or participating in gender responsive and human rights-based evaluations utilising participatory approaches and methodologies;

Proven knowledge and experience in GEWE, gender mainstreaming and gender analysis and the related mandates within the UN system, and particularly UN Women;

Demonstrated facilitation and communications skills, experience in participatory approaches and ability to negotiate among a wide range of stakeholders;

Ability to produce well-written analytical reports and apply feminist analysis to them;

Previous experience working in Arab States region will be considered an asset;

Experience with the United Nations system will be considered an asset;

Proficiency in English;

Knowledge of any of the languages of the countries involved in this evaluation (Arabic and/or French) will be considered an asset.

The international evaluation specialist:

At least a master’s degree in social sciences, gender studies, development studies, economics, international relations, or a relevant social science-related area;

At least seven years of relevant experience of periodically conducting evaluations of strategies, policies and/or development programmes focused on GEWE, of which four years are of conducting evaluations focused on GEWE themes such as involvement of men for gender social transformation, gender-based violence, gender and policy advocacy, social/feminist movements, innovative approaches to GEWE, etc.;

Proven experience of designing and leading or participating in gender responsive and human rights-based evaluations utilising mixed methods, participatory approaches and methodologies;

Proven knowledge and experience in GEWE, gender mainstreaming and gender analysis and the related mandates within the UN system, and particularly UN Women;

Demonstrated facilitation and communications skills, experience in participatory approaches and ability to negotiate among a wide range of stakeholders;

Ability to produce well-written analytical reports and apply feminist analysis to them;

Previous experience working in Arab States region will be considered an asset;

Experience with the United Nations system will be considered an asset;

Proficiency in English;

Knowledge of any of the languages of the countries involved in this evaluation (Arabic and/or French) will be considered an asset.

Qualification and requirements of the international thematic experts:

At least a master’s degree in social sciences, gender studies, development studies, economics, international relations, or a relevant social science-related area;

Over 10 years of relevant experience of work in GEWE focused on themes such as behavioural and social norms change, involvement of men for GEWE, prevention of gender-based violence, gender and policy advocacy, social/feminist movements, innovative approaches to GEWE, etc.;

Knowledge of the region/countries covered by the intervention is an asset;

Previous experience participating in gender responsive and human rights-based evaluations utilising feminist and participatory approaches and methodologies will be considered a strong asset;

Experience with the United Nations system is an asset;

Proficiency in English, knowledge of any of the languages of the countries involved in this evaluation (Arabic and French) will be considered an asset.

Qualifications and required expertise of local consultants:

At least a master’s degree related to one or more of the following: gender studies, economics, social sciences, development studies or a related area;

Five years of relevant experience in GEWE, particularly focused on gender and policy/normative work, gender mainstreaming and gender analysis, gender and grass roots movements, gender-based violence;

Knowledge and experience of gender responsive and human rights-based approaches to evaluation;

Experience of conducting gender responsive evaluations and/or applied research utilising a wide range of approaches and methods;

Ability to produce well-written reports;

Demonstrated facilitation and communications skills, experience in participatory approaches and ability to negotiate among a wide range of stakeholders;

Experience within the United Nations system will be considered an asset;

Proficiency in local language(s) of the target countries and English.

Competencies and core values for international and local consultants:

Strong analytical, writing and reporting abilities;

Strong interpersonal and communication skills, ability to lead a team and negotiate among a wide range of stakeholders;

Commitment to quality products and deadlines;

Builds strong relationships;

Focuses on impact and results and responds positively to feedback;

Approaches work with energy and a positive, constructive attitude;

Demonstrates/safeguards ethics and integrity;

Demonstrated corporate knowledge and sound judgement;

Acts as a team player and facilitates teamwork;

Facilitates and encourages open communication in the team, communicating effectively;

Learns and shares knowledge and encourages learning of others;

Demonstrates integrity and fairness by modelling UN values and ethical standards;

Demonstrates professional competence and is conscientious and efficient in meeting commitments, observing deadlines and achieving results;

Displays cultural, gender, nationality, religion and age sensitivity and adaptability.

References

- Engaging men and boys in preventing violence against women: applying a cognitive-behavioural model, Claire V Crooks. https://pubmed.ncbi.nlm.nih.gov/17322269/

- Policy approaches to engaging men and boys in achieving gender equality and health equity, World Health Organization, July 2010 Policy approaches to engaging men and boys in achieving gender equality

- Shifting Social Norms to tackle Violence Against Women and Girls (VAWG), DFID, Jan 2016 Shifting Social-Norms-tackle-Violence-against-Women-Girls

Annexes

Annex I – Programme Reports for Phase I

Annex II – Programme Reports for Phase II

Annex III – ProDoc and PMF for Phase I & II

Annex IV – Midterm and Formative Evaluations for Phase I

Annex V – Baseline Report for Phase II

Annex VI – Phase I – MSC stories

Annex VII – ToR of evaluation groups

- DELIVERABLE SCHEDULE

| Deliverable | Payment amount | Time frame |
| --- | --- | --- |
| Desk review of background documentation | 5% | April 2021 |
| Inception meeting with ERG and EMG | 5% | April 2021 |
| Inception report (including three rounds of revision) | 10% | End of May 2021 |
| Additional documents review, (online) interviews and FGDs for data collection | 5% | by mid-August 2021 |
| Presentation of preliminary findings (2) | 10% | Mid-September 2021 |
| Draft report with country summary and thematic case studies | 15% | End of September 2021 |
| Final report (including three rounds of revision), final country and thematic case studies | 30% | Mid of November 2021 |
| Final dissemination of the evaluation, 2-page evaluation brief with infographics, and evaluation communication products (PPT) | 20% | By December 2021 |

Annex 2: Targets and Achievements per Country and Year

|  | 2019 |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Egypt | Jordan | Lebanon | Morocco | Palestine | Tunisia | RO | Egypt | Jordan | Lebanon | Morocco | Palestine | Tunisia | RO |
| Outcome 1: Communities have more gender equitable behaviours |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 Interventions (including the engagement of men in violence prevention, fatherhood, the engagement of young men and young women in gender equality, and the engagement of men in addressing gender discriminatory practices and laws) for challenging social norms and promoting gender equality are implemented and replicated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.1.1 Number of women, men, young women and young men participating in community interventions Target: 5000 Achieved: 122,768 | 205 |  | 67 | 800 | 52 |  |  | 93,032 |  | 935 | 18,496 | 9,181 |  |  |
| Indicator 1.1.2 Percentage of young men and young women who report positive change in attitudes toward gender equality Target: +15% Achieved: n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |
| Indicator 1.1.3 Number of times programme good practices and tools are replicated Target: 20 Achieved: 24 |  |  | 3 | 1 | 3 |  |  | 6 |  | 2 | 5 | 4 |  |  |
| Output 1.2 A regional model for engaging fathers in gender equality exists |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 1.2.1 Percentage of participating fathers and mothers in Program P who have more positive attitudes towards gender equality and fathers’ involvement in childcare Target: + 10% Achieved: n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |
| Indicator 1.2.2 Percentage of parents under Program P who report to have used at least 1 parenting technique in the past 3 months Target: +10% Achieved: n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |
| Indicator 1.2.3 Number of men and women reached by the fatherhood campaign Target: 200,000 Achieved: 35,493,445 | 160 |  |  | 300 |  | 300[1] |  | 7,000,000 |  | 1,417,658 | 13,800,000 | 3,500,000 |  | 9,755,027 |
| Outcome 2: Key regional and national institutions (academia, faith-based institutions, media) and regional networks integrate/promote gender responsive practices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 Key institutions commit to more gender responsive practices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.1.1 Number of universities/schools sensitised who commit to use teaching material promoting gender equality Target: 8 Achieved: 6 |  |  |  |  |  |  |  | 4 |  | 2 |  |  |  |  |
| Indicator 2.1.2 Number of media who commit to develop more gender sensitive context Target: 4 Achieved: 5 |  |  |  |  |  |  |  |  |  | 3 | 2 |  |  |  |
| Indicator 2.1.3 Number of sensitised government institutions who commit to integrate programme practices and material Target: 6 Achieved: 8 |  |  | 2 |  |  |  |  | 2 |  | 3 | 1 |  |  |  |
| Output 2.2 Networks commit to GE and male engagement through replication of programme practices and material developed through the programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.2.1 Number of innovative technological tools promoting GE developed by youth members of networks and institutions Target: 1 Achieved: 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 2.2.2 Number of regional and national networks who commit to GE and engagement of men and boys by using programme practices and material developed through the programme Target: 12 Achieved: 6 |  |  | 1 |  |  |  | 2 |  |  |  |  |  |  | 3 |
| Outcome 3: Laws, policies and strategies to promote gender equality are drafted, revised and/or approved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 Civil society organisations (CSOs) have greater capacity to advocate for legal and policy change based on the research findings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 3.1.1 CSOs score on advocacy capacity assessment tools Target: + 20% Achieved: XX | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |
| Indicator 3.1.2 Number of CSOs and NGOs who advocate against/for (a) gender discriminatory laws (b) gender-based violence, (c) paternal/ parental leave, (d) gender strategies promoting male engagement (disaggregated by area of focus) Target: 10 Achieved: 28 |  |  | 1 |  | 6 |  | 1 | 7 |  | 6 | 6 | 7 |  |  |
| Output 3.2 Increased availability of research and knowledge products on gender equality and masculinity in the region |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 3.2.1 Number of knowledge products available based on research conducted under the programme Target: 10 Achieved: n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |
| Indicator 3.2.2 Number of times programme partners used knowledge products to advocate for gender equality and women's empowerment Target: 8 Achieved: 24 |  |  | 2 | 5 | 10 |  |  |  |  | 7 |  |  |  |  |
| Indicator 3.2.3 Number of times media cites/ links to data on gender equality and masculinity produced under the programme Target: 20 Achieved: 20 |  |  |  |  |  |  |  |  |  |  | 20 |  |  |  |
| Output 3.3 Strengthened capacity of key government decision makers to develop laws, policies, strategies on (a) gender discriminatory laws, (b) gender-based violence, (c) paternal/parental leave, (d) gender strategies promoting male engagement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Indicator 3.3.1 Number of decision makers influenced by the programme with an improved capacity to draft, revise and/or approve laws, policies and strategies on (a) gender discriminatory laws, (b) gender-based violence, (c) paternal/parental leave, (d) gender strategies promoting male engagement (disaggregated by area of focus and by sex) Target: 16 Achieved: 6 |  |  |  |  |  |  |  | 6 |  |  |  |  |  |  |

[1] In the report, around 600 in Tunisia and Morocco is mentioned – so I divided it into 300 per country.

Annex 3: List of References

Synthesis Report

Abualsameed (2021) UNW Regional review engaging males in Arab states.

Arab Development Portal. Gender. Available at: Gender | Arab Development Portal

Committee on the Elimination of Discrimination Against Women (CEDAW) (2018) Contribution to the 2030 Sustainable Development Goals in response to a call for inputs by the High-Level Political Forum on Sustainable Development (HLPF). Available at: OHCHR | Committee on the Elimination of Discrimination against Women

Grieg A (2021) Beyond Engaging Men: Review and Recommendations for UN Women’s Gender Equality Work with Men and Boys: Briefing Note.

Grieg A and Flood M (2020) Work with Men and Boys for Gender Equality: A Review of Field Formulation. The Evidence Base and Future Directions.

Guskey et al. (2002) Gauge impact with five levels of data. Available at: https://tguskey.com/wp-content/uploads/Professional-Learning-1-Gauge-Impact-with-Five-Levels-of-Data.pdf

International Labour Organization (ILO) (2018). Available at: Home - ILOSTAT - The leading source of labour statistics

Marrar S (2019) Community Based Solutions and National level Grants for Promoting Gender Equality and Engaging Men and Boys.

National Strategy for Women in Lebanon 2011-2021, National Action Plan (2017-2019). Available at: The National Strategy for Women in Lebanon (2011-2021) | Civil Society Knowledge Centre (civilsociety-centre.org)

NCW (2017) Egypt’s National Strategy for the Empowerment of Egyptian Women 2030: Vision and Pillars. Available at: final-version-national-strategy-for-the-empowerment-of-egyptian-women-2030.pdf (ncw.gov.eg)

NCW (2020) Final report engaging men and boys in gender equality programme national grant.

OHCHR (2017) Accelerating efforts to eliminate violence against women: engaging men and boys in preventing and responding to violence against all women and girls. Available at: Human Rights Documents (ohchr.org)

Peace Women (2018) Outside the box a training manual on gender and masculinities and strategy of engaging men and boys in combating gender discrimination and violence. Available at: Outside the Box a training manual on gender & masculinities & strategies of engaging men and boys in combating gender discrimination & violence | PeaceWomen

Plan Gouvernemental pour l’égalité. Initiative Concertée pour le Renforcement des Acquis des Marocaines (ICRAM) 2017–2021. Available at : icram-2-fr.pdf (social.gov.ma)

Promundo. Program P. Available at: Program P | Promundo (promundoglobal.org)

Tarazi R (2017) Men and Women for Gender Equality, Mid-Term Review report.

The Jordanian National Commission for Women (2020), National Strategy for Women in Jordan 2020-2025. Available at: The National Strategy for Women 2020 - 2025 01122021 (2).pdf

The World Bank (2019) Sustainable Development Goals database. Available at: Sustainable Development Goals (SDGs) | DataBank (worldbank.org)

The World Bank (2019) World Development Indicators. Available at: World Development Indicators | DataBank (worldbank.org)

UN (2017) United Nations Development Assistance Framework Morocco 2017-2021. Available at: Morocco, UN System Sign 2017-2021 UNDAF | Maroc.ma

UN (2018) United Nations Development Assistance Framework State of Palestine 2019-2022. Available at: UNDP-papp-research-undaf_2018-2022.pdf

UN (2018) United Nations Strategic Development Framework Jordan 2018-2022.

UN (2018) United Nations Strategic Framework Egypt 2018-2022.

UNDP. Gender Development Index. Available at: Gender Development Index (GDI) | Human Development Reports (undp.org)

UNDP. Gender Development Index: Indicators. Available at: | Human Development Reports (undp.org)

UNDP, The Gender Results Effectiveness Scale (GRES): A Methodology Guidance Note. Available at: GRES_English.pdf (undp.org)

UNFPA (2019) Study about Violence against older people in Palestine.

UNSDG (2021) Plan-Cadre de Cooperation Des Nations Unies Pour Le Développement Durable 2021-2025. Available at : FR_UN Sustainable Development Cooperation Framework Guidance.pdf

UNSF (2017) United Nations Strategic Framework Lebanon 2017-2020. Available at: United Nations Strategic Framework (UNSF) LEBANON (2017-2020) | United Nations in Lebanon

UNW (2008) Convention on Elimination of All forms of Discrimination Against Women (CEDAW). Available at: Convention on the Elimination of All Forms of Discrimination against Women (un.org)

UNW (2015) Development results framework 2015-2017. Available at: Annex II - Revised Results Framework.pdf (unwomen.org)

UNW (2015) The Beijing Declaration and Platform for Action. Available at: Beijing Declaration and Platform for Action, Beijing +5 Political Declaration and Outcome | UN Women – Headquarters

UNW (2017) MWGE Annual Report 2017.

UNW (2018) UN Women Strategic Plan 2018-2021. Available at: UN Women Strategic Plan 2018–2021 | UN Women – Headquarters

UNW (2018) Understanding how to engage men in gender transformative approaches to end violence against women. Available at: Understanding How to Engage Men in Gender Transformative Approaches to End Violence Against Women | UN Women – Arab States

UNW (2019) Evaluation of the National Strategy for Women and Situational Analysis of Women’s Rights and Gender Equality in Jordan. Available at: 20190601 UN Women Evaluation Final Report.pdf

UNW (2019) Men and Women for Gender Equality Phase II – First Annual Progress Report.

UNW (2020) Second Annual Progress Report.

UNW (2020) Lebanon’s Feminist Civil Society Platform calls for ensuring a fair and equitable space for women in the political sphere. Available at: Lebanon’s Feminist Civil Society Platform calls for ensuring a fair and equitable space for women in the political sphere | UN Women – Arab States

UNW (2020) Morocco MWGE Annual Report.

UNW (2020) MWGE Annual Report 2020.

UNW (2020) Rapid Assessment: The effects of COVID-19 on violence against women and gendered social norms. A snapshot from nine countries in the Arab States. Available at: Draft 7_Rapid Assessment of the effects COVID19_EN_11820 (unwomen.org)

UNW (2021) Baseline/Endline Summary – Evaluation of Community-Based Interventions in Morocco, “Men and women for Gender Equality” Regional Programme – Phase II (March 2019-February 2022), November 2021.

UNW (2021) Men and Women for Gender Equality. UN Women ROAS. Regional Review Report. Available at: Men and Women for Gender Equality | UN Women – Arab States

UNW (2021) Virtual Monitoring of Community Grants in Palestine. Report of Findings, Challenges and Recommendations, p. 3.

UNW (2022) Engaging Men and Woman for Gender Equality. Available at: Men and Women for Gender Equality | UN Women – Arab States

UNW (2022) Quantitative Evaluation of Community-based interventions in Egypt, Lebanon, Morocco and Palestine.

UNW (2022) Quantitative Evaluation of Community-Based Interventions in Egypt, Lebanon, Morocco and Palestine.

UNW (2022) Quantitative Evaluation of Community-Based Interventions in Egypt, Lebanon, Morocco, and Palestine. UN Women’s Regional Programme ‘Men and Women for Gender Equality – Phase II’, February 2022.

UNW (2022) UN Women Strategic Plan 2022-2025. Available at: Publications | UN Women – Headquarters

UNW and the Palestinian Ministry of Women’s Affairs. Partners in Development: The National Cross-Sectoral Strategy to Promote Gender Equality and Equity and the Empowerment of Women, 2017-2022

UNW. Commission on the Status of Women 48th Session. Available at: CSW 48th session, Thematic Issue: "The role of men and boys in gender equality" (un.org)

UNW, National Strategy to Combat Violence Against Women 2011-2019. Available at: PalestinianAuthorityNationalStrategytoCombatpdf.pdf (unwomen.org)

Walker D, Engle O and Beckert S (2019) Positioning GAGE evidence on masculinities. A mapping of stakeholders and policies relating to the engagement of boys and men for gender equality. London: Gender and Adolescence: Global Evidence.

World Economic Forum (2020) Global gender Gap Report 2020. Available at: WEF_GGGR_2020.pdf (weforum.org)

Transforming Patriarchal Masculinities Programming: A Comparator Study

Coalition of Feminists for Social Change (COFEM) (2017) “Feminist perspectives on addressing violence against women and girls: How a lack of accountability undermines work to address violence against women and girls”.

COFEM (2017) “How a lack of accountability undermines work to address violence against women and girls”. Feminist Perspectives on Addressing Violence Against Women and Girls. Paper No. 1.

COFEM (2018) “Staying accountable to women and girls, Feminist Pocketbook Tip Sheet 4”. Available at: https://cofemsocialchange.org/wp-content/uploads/2018/11/TS4-Staying-accountable-to-women-and-girls.pdf

Cowan P A et al. (2009) “Promoting fathers’ engagement with children: Preventive interventions for low income families”. Journal of Marriage and Family.

Doyle K, Levtov R G, Barker G, Bastian G G, Bingenheimer J B, Kazimbaya S et al. (2018) “Gender-transformative Bandebereho couples’ intervention to promote male engagement in reproductive and maternal health and violence prevention in Rwanda: Findings from a randomized controlled trial”. PLoS ONE.

Dunkle K, Stern E, Chatterji S and Heise L (2019) “Effective prevention of intimate partner violence through couples training: a randomised controlled trial of Indashyikirwa in Rwanda”. BMJ Global Health.

Edström J, Hassink A, Shahrokh T and Stern E (2015) “Engendering Men: A Collaborative Review of Evidence on Men and Boys in Social Change and Gender Equality”. Institute of Development Studies.

Gibbs A, Jewkes R and Sikweyiya Y (2015) “‘I Tried to Resist and Avoid Bad Friends’: The Role of Social Contexts in Shaping the Transformation of Masculinities in a Gender Transformative and Livelihood Strengthening Intervention in South Africa”. Men and Masculinities 21, no. 4.

Greene M E and Perlson S M (2016) “Gender synchronization: updating and expanding the concept”. PowerPoint presentation. Available at: https://www.igwg.org/wp-content/uploads/2017/06/IGWG_Plenary2016_GenderSynch_Greene.pdf

Greig A and Flood M (2020) “Work with Men and Boys for Gender Equality: A Review of Field Formation, The Evidence Base and Future Directions”. United Nations Women Discussion Paper.

Hartmann A and Linn J F (2008) “Scaling up. A framework and lessons for development effectiveness from literature and practice.” Wolfensohn Center for Development working paper 5.

Jain S, Greene M, Douglas Z, Betron M and Fritz K (2011) “Allowing Men to Care—Fatherhood and Child Security Project: A Program to Engage Men on HIV, Violence, and Caregiving in South Africa. Case Study Series”. USAID’s AIDS Support and Technical Assistance Resources, AIDSTAROne, Task Order 1.

Kimball E, Edleson J L, Tolman R M, Neugut T B and Carlson J (2013) “Global Efforts to Engage Men in Preventing Violence Against Women: An International Survey”. Violence Against Women.

Makusha T, Van den Berg W, Khoza G and Lewaks A (2019) “Engaging South African Fathers: The MenCare Childcare and Protection programme”. Sonke Gender Justice and UNICEF SA.

Namy S, Heilman B, Stich S, Crownover J, Leka B and Edmeades J (2015) “Changing what it means to ‘become a man’: participants’ reflections on a school-based programme to redefine masculinity in the Balkans”. Culture, Health & Sexuality.

OECD (2019) “Engaging with Men and Masculinities in Fragile and Conflict-Affected Settings”. OECD Development Policy Papers. No. 17.

Peacock D (2013) “South Africa's Sonke Gender Justice Network: Educating men for gender equality”. Agenda.

Peacock D and Barker G (2014) “Working with Men and Boys to Prevent Gender-based Violence: Principles, Lessons Learned, and Ways Forward”. Men and Masculinities.

Pino A (2017) “Engaging men and boys for gender equality... What do women have to do with it?” GREAT Insights Magazine, Volume 6, Issue 2.

Ricardo C (2014) “Men, Masculinities, and Changing Power: A Discussion Paper on Engaging Men in Gender Equality From Beijing 1995 to 2015”. MenEngage Alliance and UN Women.

Shefer T, Kruger L and Schepers Y (2015) “Masculinity, sexuality and vulnerability in ‘working’ with young men in South African contexts: ‘you feel like a fool and an idiot … a loser’”. Culture, Health & Sexuality.

Singizi Consulting Africa (2021) “Progress Evaluation of The MenEngage Alliance For The Period 2017 – 2020”. Available at: https://menengage.org/wp-content/uploads/2021/09/MenEngage-Alliance-2017-2020-Evaluation-Executive-Summary.pdf

Slegh H, Barker G, Kimonyo A, Ndolimana P and Bannerman M (2013) “‘I can do women's work’: reflections on engaging men as allies in women's economic empowerment in Rwanda”. Gender & Development.

Sonke Gender Justice (2009) “Summary of Research Findings on Sonke Gender Justice Network’s ‘One Man Can’ Campaign”.

Sonke Gender Justice (2019a) “Sonke Gender Justice Strategic Plan: 2020 – 2024”. Available at: https://genderjustice.org.za/publication/sonke-gender-justice-strategic-plan-2020-2024/#:~:text=Our%20Strategic%20Goal%202020%2D2024,and%20gender%20justice%20in%20Africa.

Sonke Gender Justice (2019b) “RIGHTS, ACTION AND ACCOUNTABILITY: A Case Study on Community Mobilisation & State Accountability in Sierra Leone & Zimbabwe”. Available at: https://genderjustice.org.za/publication/rights-action-and-accountability-2/

Sonke Gender Justice (2019c) Sonke Gender Justice Annual Report 2019”. Available at: https://genderjustice.org.za/publication/sonke-annual-report-2018-2019/

Stern E, Batista M, Shannon G, Heise L and Mannell J (2021) “A case study comparison of engaging community activists to prevent gender-based violence in Peru and Rwanda”. Global Public Health.

Stern E (2020) “Indashyikirwa: Lessons Learned from Engaging Men”. PowerPoint Presentation.

The Equality Institute (2020) “MenEngage Online Survey: Report on findings”. Unpublished.

The Equality Institute (2020) “Revising MenEngage Principles, Code of Conduct, and Accountability Standards Research Brief: Findings from Key Informant Interviews”. Unpublished.

The MenEngage Alliance (2014) “Accountability Standards and Guidelines”. Available at: https://menengage.org/resources/accountability-standards-guidelines/

The MenEngage Alliance (2016) “Critical Dialogue on Engaging Men And Boys in Gender Justice – Summary Report”. Available at: https://menengage.org/resources/a-critical-dialogue-on-engaging-men-and-boys-in-gender-justice-summary-report/

The MenEngage Alliance (2020) “Contexts and Challenges for Gender Transformative Work with Men and Boys. A Discussion Paper”. Available at: https://menengage.org/resources/contexts-and-challenges-work-with-men-and-boys/

The MenEngage Alliance (2021) Discussion papers of the 3rd MenEngage Global Symposium”. Available at: https://menengage.org/wp-content/uploads/2022/02/MenEngage-Ubuntu-Symposium-Discussion-Papers-Ebook-EN.pdf

The Prevention Collaborative (2019) “Study Summary: Bandebereho Couples’ Intervention to Promote Male Engagement in Reproductive and Maternal Health and Violence Prevention in Rwanda”.

Wakefield S and Koerppen D (2017) “Applying Feminist Principles to Program Monitoring, Evaluation, Accountability and Learning”. Oxfam Discussion Papers.

Walker D, Engle O and Beckert S (2019) “Positioning GAGE evidence on masculinities. A mapping of stakeholders and policies relating to the engagement of boys and men for gender equality”.

Thematic Case Study Report: Social Norms and Behaviour Change

Cislaghi B and Heise L (2018) Theory and practice of social norms interventions: Eight common pitfalls. Globalisation and Health. Available at: https://doi.org/10.1186/s12992-018-0398-x

Cislaghi B et al. (2019) Changing Social Norms: the Importance of "Organized Diffusion" for Scaling Up Community Health Promotion and Women Empowerment Interventions. Prevention Science. Available at: https://pubmed.ncbi.nlm.nih.gov/30747395/

Moghadam V M (2021) COVID-19 and female labour in the MENA Region. Available at: COVID-19 and Female Labor in the MENA Region | Middle East Institute (mei.edu)

Promundo-UN Women (2017) Understanding Masculinities: Results from the International Men and Gender Equality Survey (IMAGES) – Middle East and North Africa Egypt, Lebanon, Morocco, and Palestine.

Promundo-UN Women (2017) Understanding Masculinities: Results from the International Men and Gender Equality Survey (IMAGES) – Middle East and North Africa Egypt, Lebanon, Morocco, and Palestine.

The social norms learning collaborative (2021) Getting practical: Integrating social norms into social and behaviour change programs.

UNW (2020) ‘Because I am a man’ – Phase II Campaign Strategy.

UNW (2020) The Impact of COVID-19 on Violence against Women and Girls in the Arab States through the Lens of Women's Civil Society Organizations.

UNW. Concept Note: Adaptation of the ‘Because I Am a Man’ Campaign to #COVID19 Outbreak.

Voices for Change (2017) Using social marketing to shift discriminatory gender norms. Available at: https://www.sddirect.org.uk/media/1922/1624-v4c-lp-social-marketing-web.pdf

Thematic Case Study Report: Knowledge Management and Learning

Cislaghi B and Heise L (2018) Theory and practice of social norms interventions: Eight common pitfalls. Globalisation and Health. Available at: https://doi.org/10.1186/s12992-018-0398-x

Cislaghi B et al. (2019) Changing Social Norms: the Importance of "Organized Diffusion" for Scaling Up Community Health Promotion and Women Empowerment Interventions. Prevention Science. Available at: https://pubmed.ncbi.nlm.nih.gov/30747395/

Moghadam V M (2021) COVID-19 and female labour in the MENA Region. Available at: COVID-19 and Female Labor in the MENA Region | Middle East Institute (mei.edu)

Promundo-UN Women (2017) Understanding Masculinities: Results from the International Men and Gender Equality Survey (IMAGES) – Middle East and North Africa Egypt, Lebanon, Morocco, and Palestine.

Promundo-UN Women (2017) Understanding Masculinities: Results from the International Men and Gender Equality Survey (IMAGES) – Middle East and North Africa Egypt, Lebanon, Morocco, and Palestine.

The social norms learning collaborative (2021) Getting practical: Integrating social norms into social and behaviour change programs.

Together and Equal (2020) A summary of the qualitative interaction with the social media campaign.

UNW (2018) Toolkit for youth on advocating and achieving gender equality by 2030. Available at: Toolkit for Youth on Advocating and Achieving Gender Equality by 2030 - Egypt | UN Women – Egypt

UNW (2020) ‘Because I am a man’ – Phase II Campaign Strategy. Section 8: The Brand.

UNW (2020) Second Annual Progress Report.

UNW (2020) The Impact of COVID-19 on Violence against Women and Girls in the Arab States through the Lens of Women's Civil Society Organizations.

UNW. Concept Note: Adaptation of the ‘Because I Am a Man’ Campaign to #COVID19 Outbreak.

Voices for Change (2017) Using social marketing to shift discriminatory gender norms. Available at : https://www.sddirect.org.uk/media/1922/1624-v4c-lp-social-marketing-web.pdf

Case Study Report: Jordan

The Jordanian National Commission for Women (2020) The National Woman Strategy in Jordan 2020-2025. Available at: الاستراتيجية الوطنية للمرأة في الأردن 2020-2025 (3)_0.pdf (women.jo)

UNW (2015) Annual Report 2015-2019.

UNW (2020) Annual Progress Report Jordan.

Case Study Report: Palestine

Kuttab E, Awwad N A, Meari L and Hammami R (2020) Formations of Masculinities and Gender Dynamics in the Palestinian Colonial Context. Available at: Formations of masculinities and gender dynamics.pdf (birzeit.edu)

Ministry of Women’s Affairs. State of Palestine the Second National Action Plan on Women, Peace and Security for the implementation of United Nations Security Council Resolution 1325 and Subsequent resolutions. 2020-2024.

UN. Achieve gender equality and empower all women and girls. Available at: Goal 5 | Department of Economic and Social Affairs (un.org)

UNFPA (2019) Study about violence against older people in Palestine.

UNW (2019) Annual report 2015-2019.

Cast Study Report: Egypt

Government of Egypt (2014) Egypt’s Constitution of 2014, Article 11. Available at: https://www.constituteproject.org/constitution/Egypt_2014.pdf

Government of Egypt (2021) National Human rights Strategy. Available at: https://sschr.gov.eg/media/gapb5bq4/national-human-rights-strategy.pdf

Ministry of Health and Population [Egypt], El-Zanaty and Associates [Egypt], and ICF International (2015) Egypt Demographic and Health Survey 2014. Available at: https://dhsprogram.com/pubs/pdf/fr302/fr302.pdf

NCW (2018) National Strategy for the Empowerment of Egyptian Women 2030. Available at: http://ncw.gov.eg/wp-content/uploads/2018/02/final-version-national-strategy-for-the-empowerment-of-egyptian-women-2030.pdf

NCW (2020) Final Report Engaging Men and Boys in Gender Equality Programme National Grant.

NCW and World Bank (2021) The Post Covid-19 Pandemic: New Normal for Egyptian Women. Available at: https://en.enow.gov.eg/Report/The%20Post%20Covid-19%20Pandemic.pdf

OECD (2021) Evaluation Criteria. Available at: https://www.oecd.org/dac/evaluation/daccriteriaforevaluatingdevelopmentassistance.htm

Promundo. Available at: Promundo (promundoglobal.org)

Tarazj R (2017) Mid Term Review, Men and Women for Gender Equality.

UN Women (2019) Violence Against Women and the SDGs in Egypt Factsheet. Available at: https://egypt.unwomen.org/sites/default/files/Field%20Office%20Egypt/Attachments/Publications/2019/03/VAW%20optimized.pdf

UNFPA (2020) Violence against Women and Girls and COVID-19 in the Arab Region. Available at : https://arabstates.unfpa.org/sites/default/files/pub-pdf/violence_against_women_and_covid19_in_the_arab_states_region_-_english_version_2.pdf

United Nations Population Fund (UNFPA), Central Agency for Mobilization and Statistics (CAPMAS) and NCW (2015) Egypt Economic Cost of Gender-based Violence Survey. Available at : https://egypt.unfpa.org/sites/default/files/pub-pdf/Costs%20of%20the%20impact%20of%20Gender%20Based%20Violence%20%28GBV%29%20WEB.pdf

UNPDF (2013) UN Partnership Development Framework with the Government of Egypt for 2013-2017. Available at: UNDAF 2013-2017.pdf

UNPDF (2018) UN Partnership Development Framework with the Government of Egypt for 2018-2022. Available at: United Nations Partnership Development Framework (UNPDF) 2018-2022 | United Nations in Egypt

UNW (2013) Strategic Plan 2014-17: Making this the century for women and gender equality. Available at: Publication: Strategic Plan 2014–17: Making this the century for women | UN Women – Headquarters

UNW (2015) Development results framework 2015–2017.

UNW (2018) South to South visit-Action Plan, Egypt Team.

UNW (2019) Development results framework 2019–2021.

UNW (2021) ROAS MWGE Regional Report.

UNW (2021) Virtual Monitoring of Community Grants in Egypt.

UNW and NCW (2020) Women and Covid-19. Available at: https://arabstates.unwomen.org/sites/default/files/Field%20Office%20Arab%20States/Attachments/Publications/2020/05/Egypt%20COVID19%20Brief/women%20%20covid19%20en.pdf

UNW and Promundo (2017) Understanding Masculinities: Results from the International Men and Gender Equality Survey (IMAGES). Available at: https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2017/IMAGES-MENA-Multi-Country-Report-EN.pdf

UNW. The Youth Advocacy Toolkit. Available at: Advocacy Toolkit | UN Women – Arab States

Case Study Report: Lebanon

ESCWA (2020) Lebanon population trapped in poverty. Available at: https://www.unescwa.org/news/lebanon-population-trapped-poverty

https://www.youtube.com/watch?v=gu1QIMRMfMs&list=PLt6Jq6O7V3eRwp4IHc0MUX2uJpm7EQ7by&index=73

https://www.youtube.com/watch?v=SvELmI7TcXM&list=PLt6Jq6O7V3eRwp4IHc0MUX2uJpm7EQ7by&index=55

Lebanon’s Feminist Civil Society Platform (2021) Charter of Demands. Available at: https://www.fe-male.org/wp-content/uploads/2021/08/charter-document-2021_english-final.pdf

National Commission for Lebanese Women (2019) National Action Plan for an inclusive implementation of United Nations Security Council Resolution 1325. Available at: file:///C:/Users/doaa.arafa/Documents/Consultancy/MWGE/LEBANON/PEACE%20BUILDING%2022%20H%20ENG%20p08.pdf

National Commission for Lebanese Women (2021) National Strategy for Women in Lebanon. Available at: https://nclw.gov.lb/wp-content/uploads/2017/02/2-National-strategy-for-women-in-Lebanon-2011-2021-in-3-languages.pdf

National Commission for Lebanese Women (2021) National Strategy for Women in Lebanon. Available at : https://nclw.gov.lb/wp-content/uploads/2017/02/2-National-strategy-for-women-in-Lebanon-2011-2021-in-3-languages.pdf

NCLW website. Available at: https://nclw.gov.lb/en/mission-and-vision-2/

OECD (2021) Evaluation Criteria. Available at : https://www.oecd.org/dac/evaluation/daccriteriaforevaluatingdevelopmentassistance.htm

RDFL (2017) The Attitude of Lebanese Society on Child Marriage: An Opinion Poll. Available at: https://www2.unwomen.org/-/media/field%20office%20arab%20states/attachments/publications/2019/02/rdfl%20poll%20booklets%20high.pdf?la=en&vs=2302

Tarazi R (2017) Mid Term Review - Men and Women for Gender Equality.

UN (2017) UN Strategic Framework Lebanon. Available at: https://lebanon.un.org/sites/default/files/2021-05/UNStrategicFrameworkLebanon2017-2020-021856.pdf

UN Women (2017) Strategic Plan 2018-2021. Available at: https://undocs.org/en/UNW/2017/6/Rev.1

UN Women (2019) Understanding the Role of Women and Feminists Actors in Lebanon’s 2019 Protests. Available at: gendering lebanons 2019 protests.pdf (unwomen.org)

UN Women (2020) Gender Based Violence, Access to Justice and the economy. Available at : https://arabstates.unwomen.org/en/digital-library/publications/2020/04/gender-alert-on-covid-19-lebanon

UN Women (2020) Women’s Needs and Gender Equality in Lebanon’s Covid-19 Response. Available at : https://www.alnap.org/system/files/content/resource/files/main/gender%20and%20covid_un%20women%20lebanon_march%202020.pdf

UN Women (2020) Women’s Needs and Gender Equality in Lebanon’s Covid-19 Response. Available at : https://www.alnap.org/system/files/content/resource/files/main/gender%20and%20covid_un%20women%20lebanon_march%202020.pdf

UN Women and Promundo (2017) Understanding Masculinities: Results from the International Men and Gender Equality Survey (IMAGES). Available at: https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2017/IMAGES-MENA-Multi-Country-Report-EN.pdf

UN Women and Promundo (2017) Understanding Masculinities: Results from the International Men and Gender Equality Survey (IMAGES). Available at : https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2017/IMAGES-MENA-Multi-Country-Report-EN.pdf

UN Women, RAOS (2021) Trend Analysis of UN Women ROAS: On the Thematic Area Social Norms Change for GEWE and Positive Masculinities in the Arab State; Lebanon.

UN Women (2019) Country Advisory Committee for Lebanon.

Understanding masculinities in Lebanon – Adnan’s story. Available at:

Understanding masculinities in Lebanon: A drama. Available at:

UNW (2015) Development results framework 2015-2017.

UNW (2017) Men and Women for Gender Equality Mid Term Review Full Report.

UNW (2019) development Results Framework 2019-2021.

UNW (2019) Lebanon Country Office, Strategic Notes Report 2019-2021.

UNW, Baseline-Endline Lebanon (2021) EVALUATION OF COMMUNITY-BASED INTERVENTIONS IN LEBANON “Men and Women for Gender Equality.” Regional Programme - Phase II (March 2019–February 2022).

World Economic Forum (2021) Global Gender Gap Report. Available at: https://www3.weforum.org/docs/WEF_GGGR_2021.pdf

Annex 4: List of NGOs/CBOs (Amount Received in USD1/Length of Contract)

Note: For those highlighted in yellow, information regarding length of contract was not available.

|  | Egypt | Jordan | Lebanon | Morocco | Palestine | Tunisia | RO |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 12 |  |  |  |  |  |  |  |
| Umbrella organisation | CARE Egypt (172,000/9 months) |  | Save The Children (275,000/14 months) | Quartiers du Monde (208,000/12–14 months) | NGO Development Center (NDC) in partnership with Women’s Affairs Technical Committee (WATC) (197,507.18/18 months) |  |  |
| CSOs | Sohbet el kheir for social development and health awareness (7,000/6 months) |  | Abnaa Saida Balad (20,208/9 months) | Ayadi al amal (17,648/12 months) | The Palestinian Association for Empowerment and Local Development (REFORM) (12,162/12 months) |  |  |
|  | El Amani elgamila for community development (12,000/2 months) |  | Akkarouna (18,760/9 months) | Khouloud (16,914/12 months) | Youth For Jerusalem Association (YJA) (12,162/11 months) |  |  |
|  | Al mostafa for development and sustainability (12,000/6 months) |  | Al Jaleel for Development (16,336/9 months) | AESD (10,725/12 months) | Palestinian Entrepreneurship Creative woman (15,532/12 months) |  |  |
|  | Youth association for local community-El Akhmyin (14,000/6 months) |  | Common Effort (15,045/9 months) | Al Anouar (14,945/12 months) | Al Ofoq Foundation for Youth Development (23,723/12 months) |  |  |
|  | Youth association for women welfare and environment improvement (12,000/2 months) |  | Fe-Male (18,242/9 months) | Citoyens de rue (15,062/12 months) | Future Brilliant Association (16,993/11 months) |  |  |
|  | Al gawda for development (14,000/6 months) |  | Lebanese Youth Network (LYN) (15,846/9 months) | Mhasshas (16,286/12 months) | The Palestinian youth volunteer center (12,131/11 months) |  |  |
|  |  |  | Midal (16,951/9 months) | Maroc Volontaires (16,462/12 months) | Benaa youth center (14,959/11 months) |  |  |
|  |  |  | Musawat (18,003/9 months) |  | Al Waleed Charity association (12,162/11 months) |  |  |
|  |  |  | Youth Development Organization (16,979/9 months) |  |  |  |  |
| National grants/NGOs | National Council for Women (NCW) (91,000/12 months) |  | Care (50,000/13 months) | Association Marocaine pour les Droits des Femmes (AMDF) (93,000/12 months) | Aisha Association for Woman and Child protection – Gaza (102,314.91/18 months) |  |  |
|  |  |  | The Collective for Research and Training on Development-Action(CRTD.A) (50,000/14 months) | Rêves de plumes (collectif zan9a bla violence) (35,505/12 months) | 2 Sharek Youth Forum-Ramallah-West Bank (78,971.67/18 months) |  |  |
|  |  |  | Lebanese Women Democratic Gathering (RDFL) (50,000/14 months) | Association Theatre de l’Aquarium (90,000/12 months) | Palestinian Counselling Center (PCC) –Jerusalem (120,628.25/16 months) |  |  |
|  |  |  | Promundo-AUS and ABAAD (205,085/14 months) |  |  |  |  |
| Subtotal (USD) | 334,000 |  | 786,455 | 534,547 | 619,246.01 |  |  |
| Phase II3 |  |  |  |  |  |  |  |
| Umbrella organisation | CARE International (225,000/18 months) |  | Kafa (425,680/11 months) | Moroccan Institute for Local Development (IMADEL) (387,468/29 months) | NGO Development Center (NDC) in partnership with Women’s Affairs Technical Committee (WATC) (424,243.24/27 months4 |  | Promundo (517,812/ 13 months) |
| CSOs | El-Shabab Association for Developing Communities – ElAkhmin (XXXXX/XX months) | Center for Strategic Studies (CSS) (196,893/17 months) | Abnaa Saida El Balad Association (40,000/8 months) | Association des Echos pour la solidarité et le développement (AESD) (29,236/10 months) | Future Youth Arms Forum (SAED) (53,869.39/23 months) | Arab Institute for Human Rights (AIHR) and National Institute of Statistics (NIS) (114,000/16 months) / (30,000/XX months) | Musawah (444,820/ 11 months) |
|  | Youth association for women welfare and environment improvement – Mansheyet Nasser (XXXXX/XX months) | Information and Research Center King Hussein Foundation (IRCKHF) (136,432/18 months) | Fe-Male (40,000/8 months) | Al Intilaka pour le développement et l’environnement et la culture (AIDECA) (29,248/10 months) | Al –Ofoq (51,983.26/23 months) | Beity (75,000/18 months) |  |
|  | Ma’an Association for Development – Sohaj (XXXXX/XX months) |  | Al Jaleel Organization for Development (40,000/8 months) | Ayadi Al Amal (29,256/10 months) | Palestinian Association for Empowerment and Local Development (REFORM) (43,636.36/20 months) |  |  |
|  | Sohbit El-Khair Association (XXXXX/XX months) |  | Mousawat (40,000/8 months) | Afro-Med centre des études stratégiques et développement durable (29,564/10 months) | Benaa Youth Centre (53,030.50/22.5 months) |  |  |
|  | Better Life Association – Asyut (XXXXX/XX months) |  |  | Chourouk pour l’intégration des femmes en situation difficile (29,226/10 months) | Brilliant Future Association (51,818.18/20 months) |  |  |
|  | Al Salah Association for Community Development (XXXXX/XX months) |  |  | Khouloud pour le développement (27,220/8 months) |  |  |  |
|  | ATC (30,000/XX months) |  |  | Tidat pour le développement et la solidarité (29,327/10 months) |  |  |  |
|  | Axeer (20,000/XX months) |  |  | Association Theatre Aquarium (30,244/10 months) |  |  |  |
|  | 360 Experiential solutions (5,000/XX months) |  |  |  |  |  |  |
| Other grants and partners | National Council for Women (NCW) (50,000/6 months) |  | ABAAD (36,429/7 months) | Medias et cultures (269,500 Moroccan Dh/9 months) | Palestinian Counselling Center (PCC) in partnership with Aisha Association for Women and child protection (224,999.92/28 months) |  |  |
|  | Wellspring (243,000/8 months) |  | Daraj Media (10,000/6 months) | Quartiers du Monde (QDM) (252,221/14 months) | SHAREK Youth Forum in partnership with Haya Joint Programme funded by GAC (9,166.82/14 months) (from MWGE) |  |  |
|  | Centre for Development Studies (50,000/XX months) |  | UNDP Accelerator Lab (4,900/5 months) |  |  |  |  |
|  |  |  | CIBLW (42,812.57/ 4 months) |  |  |  |  |
| Subtotal (USD) | 350,000 | 333,325 | 592,599 | 873,684 | 635,340 | 144,000 | 5,153,716 |
| Total (USD) | 670,000 | 333,325 | 1,378,854 | 1,398,631 | 1,228,906 | 144,000 | 5,153,716 |

Annex 5. Selection Numbers of CSOs and NGOs/National Grants1

|  | Phase I |  |  | Phase II |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Number of CSOs that were mapped2 | Number of CSOs that were selected to build their capacity | Number of CSOs that were selected to be funded | Number of CSOs that were selected for Phase II |  | Total CSOs funded in Phase II |
| Country CSOs |  |  |  |  |  |  |
|  |  |  |  | Number of CSOs that are the same as in Phase I | Number of CSOs that are new in Phase II |  |
| Egypt | 1,000 | 15 | 6 | 2 | 7 | 9 |
| Lebanon |  | 15 | 9 | 4 | 3 | 4 |
| Morocco |  | 15 | 7 | 4 | 4 | 8 |
| Palestine |  | 23 | 8 | 5 | 0 | 5 |
| Total CSOs |  | 68 | 30 | 15 | 14 | 26 |
| Country NGOs/National grants |  |  |  |  |  |  |
| Egypt |  |  | 1 | 1 | 1 | 2 |
| Lebanon |  |  | 4 | 0 | 4 | 4 |
| Morocco |  |  | 3 | 0 | 2 | 2 |
| Palestine |  |  | 3 | 2 | 2 | 2 |
| Total |  |  | 11 | 3 | 9 | 10 |

Annex 6. Mapping of Support to Policies and Organisations/Institutions/Networks in Phase II

Outcome 3. Strengthened capacity of key government decision makers to develop laws, policies and strategies on: (a) gender discriminatory laws; (b) gender-based violence; (c) paternal/parental leave; and/or (d) gender strategies promoting male engagement.

|  | Policies/legal framework1 | Organisations/Institutions/ Networks |
| --- | --- | --- |
| Egypt | - NCW Vision 2030 – mainstreamed across 4 pillars (women’s political empowerment and leadership; women’s economic empowerment; women’s social empowerment; and women’s protection) - Labour law (paternity leave, CBO petition/campaign) | - Ministry of Social Solidarity (AR 2020) - Ministry of Education - Ministry of Youth and Sports (MoYS) - NCW - Dar el Ifta - Beit Al Ella |
| Jordan | - National Strategy for Women's Empowerment Limited information currently (IMAGES study yet to launched) | - Jordanian National Commission for Women (JNCW) |
| Lebanon | - Sexual harassment law (passed in December 2020) - Personal status law (ongoing) - Parental leave law (ongoing) - National Action Plan on child marriage (Annual report 2019) - Law on equal nationality rights (Annual report 2019) - National Action Plan (NAP) on UN Security Council Resolution 1325 on Women, Peace and Security (AR 2019 – linked to issues of early marriage and personal status) - Gender transformative fatherhood programme (MoSA, AR 2020) | - The Lebanese Armed Forces (LAF), not the Ministry of Defence - The internal Security Forces (ISF) and General Security (GS), not the Ministry of Interior - The Ministry of Social Affairs (MoSA) - Arab Institute for Women/LAU (only during Phase I, then coordination of parental leave law during Phase II) - National Council for Lebanese Women (NCLW) - Network of CSOs which was established in Lebanon after the Beirut Blast with support from MWGE and which developed a Feminist Charter of Demands |
| Palestine | - Advocacy for inclusion of paternity leave in the labour law and within institutions (select labour unions) policies/bylaws in Palestine (annual report 2019) - Family Protection Bill (AR 2019) - Amendment of the age of marriage to 18 years for both sexes (AR 2019) - Paternity leave in selected CSOs | - Ministry of Women’s Affairs - Palestinian Labour Union (paternity leave) - Reform group (conducting peer advocacy and media-based campaigning on positive masculinity) - Sharia Court judges - The Youth Agora Network (Palestine chapter) |
| Morocco | - Decree of law 103.13 on violence against women (VAW) (AR 2019) - Partial withdrawal, in April 2011, of the reservations relating to key CEDAW provisions (Articles 9 and 16) - Launch of the Optional Protocol ratification process, mainstreaming of gender equality in several policy and institutional reforms, including the advanced regionalisation project, justice reform, budgetary reform and public spending, and administrative reform - Governmental Plan for Equality (2012–2016) - Institutionalisation of gender in the areas of education, communication, public service, employment and vocational training, and elimination of violence against women - Readiness explicit to improve public policies governance at both local and national levels (convergence, transparency, monitoring/evaluation), resources and basic social services | - Creation of the ‘National Commission for Protection of Women Victims of Violence’ and requesetd line ministries and departments (AR 2019) - Economic, Social and Environmental Council (AR 2020) - Ministry of Health |
| Tunisia | - Not applicable | - Not applicable |
| Regional | - Youth Call to Action to End Violence Against Women and Girls in the Arab States - Regional MENA Muslim Family Law Reform campaign (Musawah) with JNCW and Equality Now - Arab Scouts’ regional strategic plan for gender equality 2022–2025 - The Youth Agora Network | - UN Women Gender Innovation Agora network of youth activists - Jordanian National Council for Women, JNCW (regional partner for the regional Muslim Family Law workshop and network) - Arab Scouts |

Annex 7: Knowledge Products

|  | # | Title | Year published | Author (organizations, e.g., Musawah, Promundo, etc) | Regional/ Country | Used by whom (country, name of organization, date) | Type |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | 1 | Knowledge building briefs – 01: Shari’ah, Fiqh and State Laws | 2016 | Musawah | Regional | All audiences with focus on advocates, CSOs, religious institutions, scholars, lawyers, Intl orgs & policymakers | Toolkit |
|  | 2 | Knowledge building briefs – 02: Muslim family laws | 2016 | Musawah | Regional | All audiences with focus on advocates, CSOs, religious institutions, scholars, lawyers, Intl orgs & policymakers | Toolkit |
|  | 3 | Musawah vision for the family | 2016 | Musawah | Regional | All audiences with focus on advocates, CSOs, religious institutions, scholars, lawyers, Intl orgs & policymakers | Toolkit |
|  | 4 | Women’s Stories, Women’s Lives: Male Authority in Muslim Contexts | 2016 | Musawah | Global1 | All audiences with focus on advocates, CSOs, religious institutions, scholars, lawyers, Intl orgs & policymakers | Research |
|  | 5 | Outside the box: A training manual on gender & masculinities & strategies of engaging men and boys in combating gender discrimination and violence | 2017 | ABAAD & UN Women | Regional | Training of trainers amongst CSOs | Toolkit |
|  | 6 | Understanding masculinities: Results from the International men and gender equality services (IMAGES) – Middle East & North Africa | 2017 | Promundo and UN Women | Regional | All | Research |
|  | 7 | Understanding masculinities: Results from the International men and gender equality services (IMAGES) – Middle East & North Africa. Executive summary | 2017 | Promundo and UN Women | Regional | All | Research |
|  |  | Understanding masculinities: Results from the International men and gender equality services (IMAGES) Egypt | 2017 | Promundo and UN Women | Egypt | All | Research |
|  |  | Understanding masculinities: Results from the International men and gender equality services (IMAGES) Lebanon | 2017 | Promundo and UN Women | Lebanon | All | Research |
|  |  | Understanding masculinities: Results from the International men and gender equality services (IMAGES) Morocco | 2017 | Promundo and UN Women | Morocco | All | Research |
|  |  | Understanding masculinities: Results from the International men and gender equality services (IMAGES) Palestine | 2017 | Promundo and UN Women | Palestine | All | Research |
|  | 8 | Knowledge building briefs – 03: Islam and the question of gender equality | 2017 | Musawah | Regional | All audiences with focus on advocates, CSOs, religious institutions, scholars, lawyers, Intl orgs & policymakers | Toolkit |
|  | 9 | Capacity building toolbox for emerging CBOs and youth groups | 2017 | UN Women | Regional | CBOs and youth groups | Toolkit |
|  | 10 | Across divides to advance women’s rights through dialogue: experiences from the ground | 2017 | SFCG & UN Women | Regional | Policy makers, UN actors, CSOs | Policy brief |
|  | 11 | Who provides who cares? Changing dynamics in Muslim families | 2018 | Musawah | Regional | All | Toolkit |
|  | 12 | Le concept de la Qiwamah | 2018 | The Center for Studies and Research on Women in Islam (CERFI) & Rabita mohammadia des oulémas | Morocco | CSOs and UN actors in Morocco | Research |
|  | 13 | The attitude of Lebanese Society towards Child Marriage: An opinion poll | 2018 | The Lebanese Women Democratic Gathering (RDFL) in partnership with UN Women and Save the Children | Lebanon | All | Research |
|  | 14 | A guide to online campaigning: A companion to the toolkit for youth on advocating and achieving gender equality by 2030 | 2018 | UN Women | Regional | Youth-led groups and community-based organisations generally | Toolkit |
|  | 15 | Facilitators manual: An accompanying resource to the toolkit for youth on advocating and achieving gender equality by 2030 | 2018 | UN Women | Regional | Facilitators | Toolkit |
|  | 16 | Toolkit for youth on advocating and achieving gender equality by 2030 | 2018 | UN Women | Regional | Youth-led groups and community-based organisations generally | Toolkit |
|  | 17 | Engaging men in gender-transformative approaches to end violence against women | 2018 | UN Women & Promundo | Regional | Policy makers, UN actors, CSOs | Policy brief |
|  | 18 | Engaging young men in advancing gender equality | 2018 | UN Women & Promundo | Regional | Policy makers, UN actors, CSOs | Policy brief |
|  | 19 | Promoting men’s caregiving to advance gender equality | 2018 | UN Women & Promundo | Regional | Policy makers, UN actors, CSOs | Policy brief |
|  | 20 | Raising children more gender equitably | 2018 | UN Women & Promundo | Regional | Policy makers, UN actors, CSOs | Policy brief |
|  | 21 | Understanding the business case for gender equality in the workplace | 2018 | UN Women & Promundo | Regional | Policy makers, Business leaders, CSOs, UN actors | Policy brief |
|  | 22 | Gender Sensitive Media Content: Media Monitoring Toolkit | 2018 | Ahead of the Curve | Regional | Media producers | Toolkit |
|  | 23 | BRIEF: 10 strategies to engage men and boys in partnership with women and girls to achieve gender equality | No date | UN Women | Regional | CSOs and UN actors | Lessons learned brief |
| Phase 2 | 24 | Pursuing equality in rights and representation: women’s experiences running for parliament in Lebanon’s 2018 elections | 2020 | UN Women | Lebanon | CSOs and UN actors in Lebanon | Research |
|  | 25 | Violences faites aux femmes et aux filles en temps de crise – l'expérience du confinement au Maroc – French & Arabic | 2020 | UN Women | Morocco | All | Research |
|  | 26 | Musawah Policy brief #1: Why Muslim family law and why now? | 2020 | Musawah | Regional | Advocates and Policy makers | Policy brief |
|  | 27 | Musawah Policy brief #2: Ending Child Marriage in Muslim Family Laws | 2020 | Musawah | Regional | Advocates and Policy makers | Policy brief |
|  | 28 | Positive Parenting guide (in Arabic only) | 2021 | CARE Egypt | Egypt | Youth-led groups and community-based organisations generally | Toolkit |
|  | 29 | Executive workshop on the implementation of law no. 205 (anti sexual-harassment law): Toolkit for employers | 2021 | Center for Inclusive Business and Leadership (CIBL) for Women at the Olayan School of Business, American University of Beirut, and our partners UN Women, UNDP, the Lebanese League for Women in Business, ABAAD, and SEEDS | Lebanon | Employers | Toolkit |
|  | 30 | What gets men interested in home-care duty? Accelerator lab experiment | 2021 | UNDP Lebanon | Lebanon | All | Research |
|  | 31 | Comparative Study of Violence against Female Reporters and Male Reporters during Lebanon’s 2019 Protest Movement - Violence against Women in Public Life | 2021 | UN Women | Lebanon | CSOs and UN actors in Lebanon | Research |
|  | 32 | Adaptation of Toolkit for youth on advocating and achieving gender equality by 2030 to the Egyptian context | 2021 | UN Women Egypt | Egypt | Youth-led groups and community-based organisations generally | Toolkit |
|  | 33 | Musawah Policy brief #3: Ending Polygamy in Muslim Marriages | 2021 | Musawah | Regional | Advocates and Policy makers | Policy brief |
|  | 34 | Musawah Policy brief #4: Divorce rights in Muslim family law | 2021 | Musawah | Regional | Advocates and Policy makers | Policy brief |
|  | 35 | Musawah Policy brief #5: Fair and Just Financial Rights Upon Divorce | 2021 | Musawah | Regional | Advocates and Policy makers | Policy brief |
|  | 36 | Musawah Policy brief #6: Upholding the Best Interests of the Child in Custody and Guardianship | 2021 | Musawah | Regional | Advocates and Policy makers | Policy brief |
|  | 37 | Musawah Policy brief #7: Marriage as a Partnership of Equals | 2021 | Musawah | Regional | Advocates and Policy makers | Policy brief |
|  | 38 | How to become a feminist ally in 30 days (Arabic) | 2021 | UN Women Morocco & Médias et Cultures | Morocco | Youth | Toolkit |
|  | 39 | The necessity of childcare services during economic empowerment programming in Lebanon | 2021 | UN Women | Lebanon | Programme implementers for women’s economic empowerment initiatives | Research |
|  | 40 | Women’s Experiences of Harassment in Taxis: A Case Study of Tripoli, Lebanon August 2021 | 2021 | UN Women | Lebanon | Advocates and Policy makers | Research |
| Projected | 40 | Understanding masculinities: Results from the International men and gender equality services (IMAGES) Jordan – Report, executive summary and policy brief | 2022 | Promundo and UN Women | Jordan | All | Research |
|  | 43 | Understanding masculinities: Results from the International men and gender equality services (IMAGES) Tunisia – Report, executive summary and policy brief | 2022 | Promundo and UN Women | Tunisia | All | Research |
|  | 46 | Media code of conduct | 2022 | UN Women & UNESCO | Palestine | All | Toolkit |
|  | 47 | Media Monitoring research | 2022 | UN Women & UNESCO | Palestine | All | Research |
|  | 48 | Handbook on engaging men as allies | 2022 | KAFA & UN Women | Lebanon | All | Toolkit |
|  | 49 | Research on Knowledge, Perceptions, Attitudes, and Practices of Institutional Actors on Men’s Caregiving and Paternity Leave in the MENA Region | 2022 | UN Women and AWRAD | Regional | All | Research |
|  | 50 | Analytical report of the national violence prevalence survey 2019 | 2022 | MWGE & SAWASYA II programme | Palestine | All | Research |
|  | 51 | Success Stories & Best Practices | 2022 | CARE | Egypt | All | Lessons learned brief |
|  | 52 | Gender Transformative Parenting Manual | 2022 | WellSpring | Egypt | CSOs | Toolkit |

Annex 8: UN Women Because I am a Man Campaign

Mapping of countries, activities, media, audiences and dates

| Country | Campaign title and media | Messages | Dates |
| --- | --- | --- | --- |
| Regional: Egypt, Morocco, Lebanon, Palestine, Tunisia Sources: ROAS Annual Report 2020, pp. 20–21; ‘Because I am a man’ – Phase II Campaign Strategy | Because I Am a Man: regional campaign Online and mass media: videos, billboards, TV programmes, radio advertisements and drama series, songs and music videos, animations, and stories of change Via celebrities and social media influencers Web banners, GIFS Infographics – 5 things men can do about the home | Shared childcare and domestic work Men who share responsibilities are happier and more successful Gender equity leads to more prosperous societies Men and boys have a role to play in preventing violence against women | Phase I and Phase II – ongoing |
| Egypt | BIAM Phase I campaign Celebrities and social media influencers, videos BIAM Football League Campaign 3 videos made in partnership with WellSpring Working with 10 celebrities/ influencers and producing 2 PSAs currently | Raising men’s awareness of gender equality | Phase I Phase II: Launched February 2020 Ongoing, 2022 |
| Tunisia (data from Tunisia Diffusion Plan) | Because I Am A Man Engaging male Tunisian influencers to promote GE 10 video testimonials from men spread across the campaign TV and radio debates Tunisian Scouts campaign videos Online GIFs/banners | Engaging men and showing alternative positive masculinity Combating violence against women Men should capitalise on COVID-19 lockdowns to share childcare responsibilities Economic and mental health benefits to more gender equality male roles | February–April 2021 |
| Lebanon (data from Annual Report, p. 21, and Together and Equal campaign summary) | Together and Equal Social media – YouTube, Facebook 17 videos with social media influencers | Shared domestic responsibilities and household chores | Launched May 2020 |
| Lebanon ROAS Annual Report 2020, pp. 17–18 | CBO-led online campaigns Partnership with MTV on social media | Gender equality and positive masculinity Importance of reporting GBV | Phase II |
| Morocco | Because I Am a Man Phase I Range of activities including theatre, graphics, regional fatherhood photography competition |  | Phase 1 |
| Morocco ROAS Annual Report 2020, P15 | Phase II Artistic competitions on social media CBO-led campaigns using local radio stations and online videos | Positive masculinity Gender equality | 2020 |
| Morocco, Hit Ana Rajel (Because I am A Man) Source: Hit Ana Rajel Rapport (campaign report, September 2020) | Phase II 10 short videos of male role models on theme of shared domestic duties UN Women social media channels and 2M TV | Shared domestic duties during lockdown | April–August 2020 |
| Palestine Source: Partner Productions Spreadsheet | A range of videos, a play, radio debates and short films produced by CBO and NGO partners | Men participating in household chores Addressing non-traditional gender roles Men’s roles in tackling GBV Testimonials from men who took part in interventions saying how it impacted their lives | Phase II |

Annex 9. Stakeholder Analysis

The following list provides the main stakeholders to be engaged per location. The evaluation team will consult with national consultants to prioritise this list down to approximately 60 key organisations (from a total of 120) in order to align with the sampling expectations.

| Type of stakeholder | Egypt | Jordan | Lebanon | Morocco | Palestine | Tunisia | Regional level | Global |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Advisory/Strategic Group Committees | Advisory Committee Members | Strategic Group Members | Advisory Committee Members | n/a (Morocco did not establish an Advisory Group) | Advisory Committee Members | Strategic Group Members |  |  |
| UN Women | Country Director/ Deputy MWGE programme staff | Country Director/ Deputy MWGE programme staff | Country Director/ Deputy MWGE programme staff | Country Director/ Deputy MWGE programme staff | Country Director/ Deputy MWGE programme staff | Country Director/ Deputy MWGE programme staff | ROAS Youth portfolio and Gender Youth Innovation Agora ROAS EVAW regional programme specialist ROAS regional programme manager of Decent Work 4 Women ROAS communications unit | HeForShe initiative EVAW unit in HQ HQ Communications Department |
| Government/ Intergovernmental | Ministry of Youth & Sports (MoYS) National Council for Women (NCW) Al Azhar | National Commission for Women | Ministry of Social Affairs (MoSA) National Council for Lebanese Women (NCLW) Lebanese Internal Security Forces (LISF) Lebanese Armed Forces (LAF) Parliamentary Commission | High Commission for Planning | Ministry of Women’s Affairs Ministry of Social Development | Centre de Recherches, d’Etudes, de Documentation et d’information sur la Femme (CREDIF) Ministry of Women, Family and Childhood Affairs National Institute of Statistics (NIS) | Jordanian National Council for Women, JNCW (regional partner for the regional Muslim Family Law workshop and network) |  |
| UN agencies | UNFPA UNICEF | UNFPA UNICEF | UNFPA UNICEF UNDP Accelerator Lab | UNFPA UNICEF | UNFPA UNICEF | UNFPA UNICEF | UNICEF UNFPA ESCWA RAF |  |
| Donors | USAID EU | UK Government |  | EU | Australian Department of Foreign Affairs Swiss Development Cooperation | Canadian International Development Agency EU | Swiss Development Cooperation Global Affairs Canada | Sida |
| Umbrella organisations | CARE |  | Kafa | Institut Marocain Pour le Développement Local (IMADEL) | NGOs Development Centre (NDC)/Women’s Affairs Technical Committee (WATC) |  |  |  |
| NGOs/FBOs | Wellspring |  | ABAAD Abnaa Saida El Balad Association Fe-Male Al Jaleel Organization for Development Mousawat | Association des Echos pour la solidarité et le développement (AESD) Ayadi Al Amal Al Intilaka pour le développement et l’environnement et la culture (AIDECA) Afro-Med centre des études stratégiques et développement durable Chourouk pour l'integration des femmes en situation difficile Khouloud Pour le développement Tildat Pour le développement et la solidarité Association Théâtre Aquarium Ayadi Al Amal Quartiers du Monde (QdM) | Future Youth Arms Forum (SAED) SHAREK Youth Forum Al-Ofoq Palestinian Association for Empowerment and Local Development (REFORM) Benaa Youth Centre Brilliant Future Association Palestinian Counselling Center (PCC)/Aisha Association for Women and Child Protection | Beity Arab Institute for Human Rights (AIHR) | Promundo Musawah Advocates supported by Musawah under the MWGE, who are CSO and university/academia people Anna Lindh Foundation Arab Scouts Equality Now | MenEngage Alliance Sonke Gender Justice |
| Private sector | 360 Experiential Solutions Axeer ATC CDS |  |  |  |  |  | HSBC |  |
| Media |  |  | Daraj media Al Mayadeen online MTV Lebanon | Radio Moussawat 2M Channel |  |  |  |  |
| Other (e.g. Academia, INGOs) | Helwan and Sohag Universities Al-Zuhour and Al-Salam Schools | Information and Research Center King Hussein Foundation (IRCKHF) Center for Strategic Studies (CSS) | American University of Beirut (Center for Inclusive Business for Women) Lebanese American University (Arab Institute for Women) International Centre for Migration Policy Development (ICMPD) | Henrich Böll Foundation Association Démocratique des femmes du Maroc (ADFM) | Birzeit University |  | Former MWGE Regional Programme Manager in Phase I Consultant who undertook a regional desk review of the MWGE programme in 2021 |  |

Annex 10: Evaluation Matrix

| Evaluation criteria | Key question(s) | Sub-question(s) | Indicator(s) data | Collection method(s) | Data source | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Relevance | EQ 1. To what extent are UN Women’s MWGE interventions aligned with regional and country contexts and addressing the priorities of stakeholders? | Did the programme hold consultations with key stakeholders to identify key priorities and guide the design? To what extent is the programme aligned with regional strategies? To what extent is the programme aligned with national priorities? | Existence of assessments to guide design Number of meetings with national counterparts Alignment with regional strategies Alignment with national plans on gender equality Changes made to programme to respond to crises | Document analysis KIIs | National government websites UN Women website UN Women programme staff National counterparts | Information is available National counterparts are willing/able to meet |
|  | EQ 2. How relevant is the intervention logic of the programme and to what extent did UN Women’s MWGE programme adapt to respond to changing contexts? | To what extent did the programme adapt to the changing political/security crises across the region and continue to be fit for purpose? To what extent did the programme adapt to the COVID-19 pandemic? | Evidence of change in design, modality of delivery, etc. | Document analysis KIIs | UN Women programme staff National counterparts | National counterparts are willing/able to meet |
|  | EQ 3. What is the comparative advantage of UN Women in leading the MWGE programme? | Is the value addition of UN Women well understood and recognised among the regional and national stakeholders, including the UN partner agencies? | Number of countries in which UN Women interventions achieve strong synergies with other actors Perception of key partners on UN Women value addition | Document analysis KIIs | National counterparts UN agencies Implementing partners (regional and national levels) | National counterparts are willing/able to meet |
|  | EQ 4. How relevant are the programme intervention logic and Theory of Change (ToC)? To what extent are the ToC’s underlying assumptions still valid? | Degree to which intervention logic is aligned with country contexts | Change in context which requires new assumptions | KIIs | All key stakeholders | National counterparts are willing/able to meet |
| Effectiveness/ Impact | EQ 5. To what extent has the MWGE programme contributed to behaviour and policy change, institutional and national capacity development, information and knowledge sharing to promote GEWE across different settings? | To what extent and in what ways has the programme been effective in promoting positive behaviours and challenging negative social norms? To what extent and in what ways has the programme been able to create and share evidence base and knowledge products? To what extent and in what ways has the programme been effective in creating an enabling environment for policy-level changes to promote gender equality? How relevant and effective have capacity building initiatives been for national authorities, CSOs, etc.? How effective is the programme’s innovation and scaling-up strategy and practice? What are the programme’s unintended consequences (positive or negative)? | Number and type of positive behaviour changes in relation to GEWE Number of knowledge products utilised for challenging gender and social norms Number of policy changes introduced Number of CSOs demonstrating increased capacities and able to influence policy change Existence and analysis of unplanned effects generated from the interventions carried out Analysis of the mitigation strategies of the negative effects | Thematic case studies (SBCC and Knowledge) Questionnaire with CSOs KIIs Document review Country case studies | All key stakeholders Programme documents | High response rate for questionnaire Information is available National counterparts are willing/able to meet |
| Efficiency | EQ 6. Has MWGE been efficient, achieving high-impact work in a cost effective way, while using processes and systems to enable sufficient resources to be made available in a timely manner to achieve planned results? | Is the regional arrangement successfully leveraging the combined effects of the multi-country programme? To what extent have the human resources been adequate to achieve the expected products and results? Have the financial resources been optimally deployed and used to achieve the results? How successful has the programme been in its resource mobilisation efforts? How has the funding gap been resolved to achieve the agreed results? Did the programme experience any delays, and what were the causes? Does the programme have an effective monitoring & evaluation framework and systems to measure complex transformations? | Processes put in place to manage programme (regional management, procurement, risk management) Ratio of financial resources used per type of activity/country Number of partnerships established Indicators used in the M&E framework Amount of resources mobilised | KIIs Document review | UN Women staff Financial reports M&E reports | Availability of documentation |
| Gender and human rights | EQ 7. To what extent was a human rights-based and gender transformative approach incorporated in the design and implementation of the programme? | To what extent was a human rights-based and gender transformative approach incorporated in the design and implementation of the programme? To what extent does the programme incorporate the principle of Leave No One Behind providing special focus on the marginalised groups and individuals? | Number of regional/country interventions that developed a gender analysis in the design phase Number of regional/country interventions with specific design features intended to reduce discriminatory barriers and focus on the inclusion of marginalised/ disadvantaged individuals and groups Number of countries that have a functioning feedback and complaint handling mechanism | Desk review KIIs Country case studies | UN Women staff NGOs/CSOs | Availability of documentation |
| Sustainability | EQ 8. What are the indications that MWGE’s interventions and approaches will be sustained? | To what extent is there national ownership of the MWGE programme? To what extent did the programme result in strategic partnerships? To what extent are policy and regulatory frameworks in place that will support the continuation of gender transformational work? To what extent was capacity of national government and other programme partners developed in order to ensure sustainability of efforts and benefits? To what extent have financial resources been mobilised and/or budget lines allocated for addressing GEWE at national level? | Frequency of and participation in National Steering Group Meetings Number of strategic partnerships established Number of policy and legal frameworks put in place Number and institutional affiliation of persons whose capacity has been developed Amount of funding allocated and/or raised to continue implementation of GEWE activities | KIIs Document review CSO questionnaire Country Case studies | Government counterparts Regional institutions UN Women staff | Information is available National counterparts are willing/able to meet |
| Evidence, learning and knowledge management | EQ 9. How is the programme generating, utilising and sharing lessons and knowledge? | To what extent do they support promotion of cross- country, cross-regional learning? To what extent do the data, evidence and lessons systematically feed into learning and programmatic decision making? What are some of the key lessons learned that can be shared beyond the specific programme? | Evidence of cross-regional learning and sharing of experiences Evidence of programmatic changes due to evidence/ knowledge generation (e.g. changes introduced as a result of the MTR) | KIIs Document review Country case studies Thematic study | UN Women staff Partners (global, regional, national) | Availability of documentation |

Annex 11: KII Interview Protocol

Note 1: It is expected that the interviews with donors and other UN agencies will last approximately 1 hour (60 minutes). In the cases of UN Women staff directly involved in the interventions and of the counterparts (civil society and public institutions), the interviews are estimated to last for 90–120 minutes. In the case of some other actors (M&E officer and finance/administration staff) they will not last longer than 30 minutes.

Note 2: The team does not identify any risk or discomfort that may result from participating in it beyond the fatigue of talking for 60–120 minutes.

Note 3: The Matrix (in Annex 13) includes the questions which will be asked to each type of stakeholder following the introduction.

Acknowledgments and presentation of the team

Hello, my name is _______________ and I work with Itad. We want to thank you for accepting the invitation to participate in this conversation, which will be of great importance for the evaluation we are conducting.

The interview with you will take about [time; see Note 1 above] to complete.

Presentation of the evaluation

Itad, an international consulting company headquartered in the UK, has been hired by the regional office of UN Women in Cairo, Egypt to carry out a multi-country evaluation which covers Egypt, Jordan, Lebanon, Morocco, Palestine and Tunisia. The objective of this study is to analyse interventions implemented through the regional programme ‘Men and Women for Gender Equality’.

We will also be looking at how the programme has engaged men and boys to achieve gender equality in partnership with women and girls. We also would like to know if there have been any positive and negative effects in terms of enhancing gender equality. For this, it is essential to know the opinion of different actors who have participated, directly or indirectly, in their implementation.

Presentation of the interview and work methodology

We would like to clarify that by participating in this evaluation there will be no immediate benefit, although in the long term it is expected that the results of the evaluation may favour the improvement of the living conditions of women in the country. Nor will any incentive be offered for participating in this interview.

All interviews are confidential. The information will be used only in an aggregate form in our report and the appointments that can be made cannot be related to the people interviewed, i.e. no interviewee will be identified, except as part of a relationship or list of people interviewed; this will be included at the end of the evaluation document.

Participation is completely voluntary. You have every right to decide to participate or not. You will be asked the following question before starting the survey: ‘are you willing to participate?’

In case of questions or complaints about this evaluation, you can contact Mr Rodrigo Montero, UN Women Regional Programme Manager, rodrigo.montero@unwomen.org.

I have some questions to guide our conversation. If there is something that you feel is beyond your experience or knowledge, please let me know. To help the evaluation team remember our conversation today, I will be taking some handwritten notes. However, I will not be audio-recording the meeting and will not take any photos.

Before we begin, do you have any questions or concerns related to the assessment or this interview?

Annex 12: Evaluation Sub-Questions per Category of Stakeholder

| Evaluation criteria | UN Women RD/DRR/CD | UN Women MWGE staff | UN Women programme staff | Regional/ global partners | Government | Donors | UN Agencies | Umbrella NGO | CBOs | Media | Private Sector | Academia |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RELEVANCE |  |  |  |  |  |  |  |  |  |  |  |  |
| EQ 1. To what extent are UN Women’s MWGE interventions aligned with regional and country contexts and addressing the priorities of stakeholders? |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Did the programme hold consultations with key stakeholders to identify key priorities and guide the design? |  | X | X |  | X |  | X | X |  |  |  |  |
| 1.2 To what extent is the programme aligned with regional strategies? | X |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 To what extent is the programme aligned with national priorities? |  |  |  |  | X |  |  | X |  |  |  |  |
| EQ 2. To what extent did UN Women’s MWGE programme adapt to respond to changing contexts? |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 To what extent did the programme adapt to the changing political/security crises across the region and continued to be fit for purpose? |  | X |  |  | X |  |  | X |  |  |  |  |
| 2.2 To what extent did the programme adapt to the COVID-19 pandemic? |  | X |  |  |  |  |  | X | X |  |  |  |
| EQ 3. What is the comparative advantage of UN Women in leading the MWGE programme? |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 Is the value addition of UN Women well understood and recognised among the regional and national stakeholders, including the UN partner agencies? |  | X |  | X | X | X | X | X |  |  |  | X |
| 4. How relevant are the programme intervention logic and Theory of Change (ToC)? To what extent are the ToC’s underlying assumptions still valid? |  | X | X |  |  |  |  | X | X |  |  |  |
| EFFECTIVENESS/IMPACT |  |  |  |  |  |  |  |  |  |  |  |  |
| EQ 5. To what extent has the MWGE programme contributed to behaviour and policy change, institutional and national capacity development, information and knowledge sharing, to promote GEWE across different settings? |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 To what extent and in what ways has the programme been effective in promoting positive behaviours and challenging social norms? |  | X | X |  |  |  |  | X | X |  | X |  |
| 5.2 To what extent and in what ways has the programme been effective in creating an enabling environment for policy-level changes to promote gender equality? |  | X |  |  | X |  |  | X |  |  |  | X |
| 5.3 To what extent and in what ways has the programme been able to create and share evidence base and knowledge products? |  | X |  | X |  |  | X | X |  | X | X | X |
| 5.4 How relevant and effective have capacity building initiatives been for national authorities, CSOs, etc.? |  |  |  |  | X |  |  | X | X |  |  |  |
| 5.5 How effective is the programme’s innovation and scaling-up strategy and practice? |  | X |  | X |  |  |  | X |  | X | X | X |
| 5.6 What are the programme’s unintended consequences (positive or negative)? |  | X |  |  | X |  |  | X | X |  |  |  |
| EFFICIENCY |  |  |  |  |  |  |  |  |  |  |  |  |
| EQ 6. Has MWGE been efficient, achieving high-impact work at the lowest possible cost, while using processes and systems to enable sufficient resources to be made available in a timely manner to achieve planned results? |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 Is the regional arrangement successfully leveraging the combined effects of the multi-country programme? | X | X | X | X |  |  |  | X |  |  |  |  |
| 6.2 To what extent have the human resources been adequate to achieve the expected products and results? |  | X |  | X |  |  |  |  |  |  |  |  |
| 6. 3 Have the financial resources been optimally deployed and used to achieve the results? |  | X |  |  |  | X |  |  |  |  |  |  |
| 6.4 How successful has the programme been in its resource mobilisation efforts? How has the funding gap been resolved to achieve the agreed results? |  | X |  |  |  | X |  |  |  |  |  |  |
| 6.5 Did the programme experience any delays, and what were the causes? |  | X |  | X | X |  |  | X | X |  |  | X |
| 6.6 Does the programme have an effective monitoring & evaluation framework and systems to measure complex transformations? |  | X |  |  |  |  |  | X | X |  |  |  |
| GENDER AND HUMAN RIGHTS |  |  |  |  |  |  |  |  |  |  |  |  |
| EQ 7. To what extent was a human rights-based and gender transformative approach incorporated in the design and implementation of the programme? |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 To what extent was a human rights-based and gender transformative approach incorporated in the design and implementation of the programme? |  | X |  | X |  |  |  | X | X |  |  | X |
| 7.2 To what extent does the programme incorporate the principle of Leave No One Behind, providing special focus on the marginalised groups and individuals? |  | X |  | X |  |  |  | X | X |  |  |  |
| SUSTAINABILITY |  |  |  |  |  |  |  |  |  |  |  |  |
| EQ 8. What are the indications that MWGE’s interventions and approaches will be sustained? |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.1 To what extent is there national ownership of the MWGE programme? |  | X |  |  | X |  |  | X |  |  |  |  |
| 8.2 To what extent did the programme result in strategic partnerships? |  | X |  | X | X |  | X |  |  | X | X | X |
| 8.3 To what extent are policy and regulatory frameworks in place that will support the continuation of gender transformational work? |  | X | X |  | X |  |  |  |  |  |  | X |
| 8.4 To what extent was capacity of national government and other programme partners developed in order to ensure sustainability of efforts and benefits? |  | X |  |  | X |  |  | X | X |  |  |  |
| 8.5 To what extent have financial resources been mobilised and/or budget lines allocated for addressing GEWE at national level? |  |  |  |  | X | X |  |  |  |  |  |  |
| EVIDENCE, LEARNING AND KNOWLEDGE MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |
| EQ 9. How is the programme generating, utilising and sharing lessons and knowledge? |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.1 To what extent do they support promotion of cross-country, cross-regional learning? |  | X |  | X | X |  |  | X |  |  |  |  |
| 9.2 To what extent do the data, evidence and lessons systematically feed into learning and programmatic decision making? | X | X | X |  |  |  |  |  |  |  |  |  |
| 9.3 What are some of the key lessons learned that can be shared beyond the specific programme? |  | X |  | X | X |  |  | X |  |  |  | X |

Annex 13: CBO Capacity Building Questionnaire

Purpose: to obtain evidence regarding the advocacy capacity building support provided by umbrella organisations1 to the CBOs/CSOs2 engaged in the UNW MW4GE programme.

Approach: using SurveyMonkey, we will target the advocacy focal points (and related staff as necessary) in relevant CBOs/CSOs that have continued to engage in advocacy activities in Phase II of the programme.

Dear all

Thank you for participating in this short survey for the regional evaluation of UN Women’s Regional Programme on Men and Women for Gender Equality. The voice of the CBOs and CSOs involved in the programme will be critical in providing lessons and guidance to your umbrella organisation to improve advocacy support in both current and future programming activities in the MENA region and beyond.

This survey will take approximately 20 minutes to complete. The survey focuses on the capacity building support provided by UN Women, with a specific focus on the capacity support for advocacy. We define advocacy as ‘targeted interventions using evidence (research, programme findings, persuasive argument, and beneficiary voices) to inform specific national policy or legislature statements or processes’.

All information provided in this survey will be anonymised and will remain confidential. All participant names and organisational affiliations will be removed in the dataset. If any quotes are used in the final regional evaluation report, they will not be attributed to any person or organisation.

GENERAL INFORMATION

- How long have you been working with the CBO/CSO?

- joined less than 1 year ago

- joined between 2019 and 2020

- joined before 2019

- Gender:

- Female

- Male

- Other

- Country:

(a) Egypt

(b) Lebanon

(c) Morocco

(d) Palestine

- Length of training:

(a) 1 day or less

(b) 2–5 days

(c) more than 5 days

TECHNICAL/THEMATIC FOCUS

- In which gender-focused areas did your CBO/CSO receive the most support from the umbrella organisation?

(Yes, no, somewhat, cannot recall)

- The differences between gender harmful, gender blind, gender neutral, gender sensitive and gender transformative

- Global policy statements relating to gender (CEDAW, Beijing, Council Resolution 1325, etc.)

- Definitions and approaches that promote gender equality that focus on the engagement of men and boys (masculinities)

- Definitions and types of feminism

- Typologies of violence (domestic violence, intimate partner violence, sexual assault, physical assault, economic violence, psychological violence, etc.) harmful practices (child marriage, female genital mutilation/cutting, etc.) or forms of discrimination (unequal work burdens, unequal pay, inequality of opportunity, etc.)

- In which gender-focused areas does your CBO/CSO need more support from the umbrella organisation?

(please select up to 3 priority areas, if any) (same list as above)

- In which technical area did you CBO/CSO receive most support from the umbrella organisation?

- Research and analysis

- Developing an advocacy strategy/plan/campaign

- Implementation of advocacy strategy/plan

- Advocacy and communications tools/social media advocacy campaigns

- M&E For advocacy

- Networking

- Community mobilisation

- In which technical areas does your CBO/CSO need more support from the umbrella organisation?

(please select up to 3 priority areas, if any) (same list as above)

TOOLS AND APPROACHES PROVIDED

- Were the advocacy capacity development tools provided by your umbrella organisation easy to use?

- The tools were easy to apply to different situations

- The tools were fairly easy to use, but there were elements that were complicated

- The tools were complicated and a challenge to adapt to different situations

- We did not use the tools

- To what extent was the advocacy capacity building support a key factor in contributing to any policy or legislature changes achieved by your CBO/CSO?

- The advocacy capacity building support provided by your umbrella organisation was a major factor in contributing to specific policy or legislature changes or successes

(please describe how and why, and please name the policy or legislature change)

- The advocacy capacity building support provided by your umbrella organisation was a fairly important factor in contributing to specific policy or legislature changes or successes

(please describe how and why, and please name the policy or legislature change)

- The advocacy capacity building support provided by your umbrella organisation was a minor factor in contributing to specific policy or legislature changes or successes

(please describe how and why, and please name the policy or legislature change)

- If your CBO experienced increased capacity to advocate as a result of your umbrella organisation’s support, where was this capacity used or directed? (please tick all that apply)

- Government level

(please describe which stakeholder, and why they were targeted)

- Sub-national government level (district authorities)

(please describe which stakeholder, and why they were targeted)

- Local-level government

(please describe which stakeholder, and why they were targeted)

- Other CBOs/NGOs

(please describe which stakeholder, and why they were targeted)

- If you answered ‘yes’ to any of the above, please describe the experience: what worked well and why (what factors enabled your CBO/CSO), and what did not work very well (what barriers did your CBO/CSO experience)?

- What changes or results has your CBO/CSO helped to enact as a result of increased advocacy activities?

  - No change or very little change (please describe)

  - Small or incremental changes such as increased access, recognition, and influencing decisions (please describe)

  - Intermediate change, such as getting actors to change the way they work or think (please describe)

  - Transformative changes, such as being able to influence the language or framing of policies, laws and legislation, or other rules (please describe)

- In addition to increased financial resources, what type of support does your CBO/CSO need from your umbrella organisation in order to improve the changes or results that your CBO/CSO would like to see in advocacy activities? (Select all that apply)

- More regular advocacy training

- More context or issue-specific advocacy training

- Tools that are easier to use

- The use of your umbrella organisation as a facilitator in advocacy initiatives

- Other (please describe)

- To what extent has your umbrella organisation supported on building, facilitating and sharing knowledge exchange and learning between CBOs/CSOs to improve collective action in advocacy?

- Your umbrella organisation has provided transformative support to CBOs/CSOs and has greatly facilitated the sharing of strategies, materials and information to improve advocacy results

- Your umbrella organisation has provided significant ongoing support to CBOs/CSOs and has facilitated the sharing of strategies, materials and information to improve advocacy results

- Your umbrella organisation has provided a little support to CBOs/CSOs and has facilitated a small amount of sharing of strategies, materials and information to improve advocacy results

- Your umbrella organisation has not provided support to CBOs/CSOs and has not facilitated the sharing of strategies, materials and information to improve advocacy results

OPEN-ENDED

- How can your umbrella organisation improve the selection, engagement and ongoing management (inc. monitoring and learning) with CBOs in order to improve advocacy results?

(Please describe)

- Is there anything else you would like to tell us about your experience with your umbrella organisation’s advocacy capacity building support provided to your CBO/CSO?

(Please describe)

# Annex 14: Theory of Change – with EQs Mapped to Appropriate Levels

Annex 15: Evaluation Committees

Evaluation Steering Committee (ESC)

Chair: UN Women ROAS Regional Director: Susanne Mikhail susanne.mikhail@unwomen.org

Sida Regional Head at MENA: Maria Selin maria.selin@gov.se

Sida Regional First Secretary: Rasmus Rodhe rasmus.rodhe@gov.se

UN Women ROAS Deputy Regional Director: Janneke Kukler janneke.kukler@unwomen.org

UN Women Egypt Country Office Representative: Christine Arab christine.arab@unwomen.org

UN Women Lebanon Country Office Representative: Rachel Dore-Weeks rachel.weeks@unwomen.org

UN Women Jordan Country Office Representative (or alternate): Ziad Sheikh ziad.sheikh@unwomen.org

UN Women Palestine Country Office Representative: Maryse Guimond maryse.guimond@unwomen.org

UN Women Morocco Country Office Representative: Leila Rihawi leila.rhiwi@unwomen.org

UN Women Tunisia Country Office Representative: Maria Begona Lasagabaster Olazabal begona.lasagabaster@unwomen.org

Evaluation Management Group (EMG)

UN Women ROAS Regional Evaluation Specialist: Chaitali Chattopadhyay c.chattopadhyay@unwomen.org

UN Women MWGE Regional M&E Consultant: Nicola Musa nicola.musa@unwomen.org

UN Women Egypt M&E Focal Point: Shatha Al-Monthri shatha.almonthri@unwomen.org

UN Women Lebanon M&E Focal Point: Olivia Schmitz olivia.schmitz@unwomen.org

UN Women Jordan M&E Focal Point: Ola Jundi ola.jundi@unwomen.org

UN Women Palestine M&E Focal Point: Alla Eddin Ayesh allaa.ayesh@unwomen.org

UN Women Morocco M&E Focal Point: Meryem Nassif meryem.nassif@unwomen.org

UN Women Tunisia M&E Focal Point: Hela Skhiri hela.skhiri@unwomen.org

Evaluation Reference Group (ERG) – UNW staff members

MWGE programme:

MWGE Regional Programme Manager: Rodrigo Montero rodrigo.montero@unwomen.org

UN Women Egypt MWGE National Coordinator: Rasha Abouelazm rasha.abouelazm@unwomen.org

UN Women Lebanon MWGE National Coordinator: Jumanah Zabaneh jumanah.zabaneh@unwomen.org

UN Women Jordan MWGE National Coordinator: Isadora De Moura isadora.demoura@unwomen.org

UN Women Palestine MWGE National Coordinator: Hadeel Abdo hadeel.abdo@unwomen.org

UN Women Morocco MWGE National Coordinator: Zineb Chebihi zineb.chebihi@unwomen.org

UN Women Tunisia MWGE National Coordinator: Boutheina Hammami boutheina.hammami@unwomen.org

ROAS and HQ

HQ – Policy Specialist, EVAW Section: Khamsavath Chanthavysouk khamsavath.chanthavysouk@unwomen.org

HQ – Head of HeForShe: Edward Wageni edward.wageni@unwomen.org

Evaluation Reference Group (ERG) – External partners

Regional – Sida Regional First Secretary: Rasmus Rodhe rasmus.rodhe@gov.se

Regional – Sida HQ Gender Advisor: Anna Widestam anna.widestam@sida.se

Regional – Musawah Regional MENA Advisor: Marwa Sharafeldin msharafeldin@googlemail.com

Regional – Arab Scouts Regional Director: Dr Amr Hamdy amr.hamdy@scout.org

Lebanon

Lebanon – KAFA, MWGE Project Coordinator: Majd Ghraizi majd.ghraizi@kafa.org.lb

Lebanon – National Commission for Lebanese Women: Cynthia Chidiac cynthia.chidiac@gmail.com

Egypt

Egypt – CARE, Women’s Rights Program Director: Sandra Azmy Sandra.Azmy@care.org

Egypt – Egyptian National Council for Women (NCW), Head of the Complaints Office: Amal Tawfik (TBC)

Palestine

Palestine – NDC (NGOs Development Centre), Program director: Ala’ Ghalayini aghalayini@ndc.ps

Palestine – Ministry of Social Development, Deputy Minister: Daoud Al-Deek ddeek@mosa.gov.ps

Morocco

Morocco – IMADEL, Project Manager: Amina Fennane fannaneamina1@gmail.com

Morocco – Head of Division of the National Observatory of Women – Ministry of Family, Solidarity, Equality and Social Development: Amina Slimani Houari slimaniamina1@gmail.com

Tunisia

Tunisia – Beity: Marta Luceno Moreno m.lucenomoreno@gmail.com

Tunisia – IADH: Esraa Attia esraa.attia94@gmail.com

Jordan

Jordan – CSS: Dr Zaid Eyadat z.eyadat@css-jordan.org

Jordan – IRCKHF: Dr Aida Essaid aida.essaid@irckhf.org

Annex 16. List of KIIs – scoping and evaluation phase

Scoping:

| Last name | First name | Title | Organisation | Sex |
| --- | --- | --- | --- | --- |
| Mikhail | Susanne | ROAS Regional Director/ESC | UN Women (ROAS) | F |
| Kukler | Janneke | ROAS Deputy Regional Director/ESC | UN Women (ROAS) | F |
| Chattopadhyay | Chaitali | ROAS Regional Evaluation Specialist/EMG | UN Women (ROAS) | F |
| Montero | Rodrigo | MWGE Regional Programme Manager/ERG | UN Women (ROAS) | M |
| Musa | Nicola | MWGE Regional M&E Consultant/EMG | UN Women (ROAS) | M |
| Tanani | Ola | Because I am a Man Campaign Leader – International Communications Consultant | UN Women (ROAS) |  |
| Fokaidou | Lemonia | Programme Analyst | UN Women | F |
| Tarek | Radwa | Programme Analyst | UN Women (ROAS) | F |
| Abouelazm | Rasha | MWGE National Coordinator/ERG | UN Women (Egypt) | F |
| Al-Monthri | Shatha | M&E Focal Point/EMG | UN Women (Egypt) | F |
| De Moura | Isadora | MWGE National Coordinator/ERG | UN Women (Jordan) | F |
| Jundi | Ola | M&E Focal Point/EMG | UN Women (Jordan) | F |
| Zabaneh | Jumanah | MWGE National Coordinator/ERG | UN Women (Lebanon) | F |
| Schmitz | Olivia | M&E Focal Point/EMG | UN Women (Lebanon) | F |
| Abdo | Hadeel | MWGE National Coordinator/ERG | UN Women (Palestine) | F |
| Ayesh | Alla Eddin | M&E Focal Point/EMG | UN Women (Palestine) | M |
| Chebihi | Zineb | MWGE National Coordinator/ERG | UN Women (Morocco) | F |
| Nassif | Meryem | M&E Focal Point/EMG | UN Women (Morocco) | F |
| Hammami | Boutheina | MWGE National Coordinator/ERG | UN Women (Tunisia) | F |
| Skhiri | Hela | M&E Focal Point/EMG | UN Women (Tunisia) | F |
| Rodhe | Rasmus | First Secretary/ESC/ERG | Sida (Regional) | M |
| Dohmen | Sofia | Senior Advisor on Conflict and Gender | Sida (HQ) | F |
| Widestam | Anna | Gender Advisor | Sida (HQ) | F |

Evaluation

| Last name | Organisation |
| --- | --- |
| Heba Salah | Al-Azhar, House of Verdict / Owner and Founder of “Women's Voice for Peace” Initiative |
| Amal Tawfick | NCW |
| Rasha Abou El Azm | UNWomen |
| Gilian al Misiri |  |
| Maha | UNWomen |
| Maged Tawfik | Well Spring |
| Mina Moawad | CARE |
| Amr Yuness | Shehab |
| Nihal Sharara | ATC |
| Ali Mokhtar | CDS |
| Christine Arab | UN Women |
| Abdel Razak abou Ala | Youth Association |
| Nada Nashat | Egypt CSO |
| Alan Grieg | Independent |
| Laxman Belbase | MenEngage Alliance |
| Brian Heilman | Promundo |
| Zulaikha Shihab | Musawah |
| Abby Fried | Promundo |
| Dr Marwa Sharaf ElDin | Musawah |
| Aida Essaid, PHD | IRCHKHF |
| Jumanah Zabaeh | UN Women |
| Abir Chebaro | Advisory Committee-NLCW |
| Rachel Dore-Weeks | UNWomen |
| May Ghanem | UNWomen |
| Colonel Marwa Saoud | LAF |
| Zoya Rouhana | Kafa |
| Majd Ghraizi | kafa |
| Ghida Anani | ABAAD |
| Hayat Mershad | Fe-male |
| Mahmoud Charary | al Jaleel Org. |
| Mohamad Younis | Musawat |
| Sarah Al Bitar | Abnaa Saida al Balad Association |
| Dr. Charlotte Karam | American University of Beirut (Center for Inclusive Business for Women) |
| Vanessa Wahbe | Internal Security Forces |
| Victor Makai | International Centre for Migration Policy Development (ICMPD) |
| Myriam Sfier | Lebanese American University |
| Maryse Guimond | UNWomen-Palestine |
| Hadeel Abdou | UNWomen-Palestine |
| Afaf Zebdeh | Women’s Affairs Technical Committee (WATC) |
| Azhar Besaiso ( Gaza) | Development Centre -NDC |
| Ala' Ghalayini | development Centre -NDC |
| Amin Khalf | Future Youth Arms Forum (SAED) |
| Haitham Abu Teir | Brilliant Future Association |
| Rawan Sharqawi | Palestinian Association for Empowerment and Local Development (REFORM) |
| Khaled Jame' | Benaa Youth Centre |
| Eileen Kuttab | Bir Zeit University |
| West Bank FGD3 | future Youth Arms Forum (SAED) |
| West Bank FGD2 | future Youth Arms Forum (SAED) |
| West Bank FGD | Future Youth Arms Forum (SAED) |
| Gaza FGD | Brilliant Future Association |
| Gaza FGD 2 | Brilliant Future Association |
| Gaza FGD 3 | Brilliant Future Association |
| Hanan Kamar | UNW |
| Lemonia Fokaidu | UNW |
| Radwa Tarek | UNW |
| Rodrigo Montero | UNW |
| Nicola Musa | UNW |
| Begonia Lasagabaster |  |
| Yosra Zbiss | UN Women |
| Israa Attia Tunisia | IADH |
| Francesca Malaguati | 12/02/2021 |
| Hedia Belhaj youssef | Cawtar |
| Imen Brahem | 09-Dec-21 |
| Marta Lucenom | Beity |
| Laxman Belbase & Oswaldo Montoya | MenEngage Alliance |
| Dean Peacock | Sonke Gender Justice |
| Fidele Futayisre, Jonathan Munyanziza & Emmanuel Karamage | RWAMREC |
| Erin Stern | Independent |
| Ola Tanani | UN Women |
| Marta Luceño Moreno | Beity- Partenaire d’implémentation de l’étude IMAGES |
| Asma Nouira | IADH- Partenaire d’implémentation de l’étude IMAGES |
| Monia Gari | Observatiore national pour la luttes contre la violence a l'egard des femmes |
| Yosra Zbiss | UN Women |
| Maria Begona | UN Women |
| Dr. Salma Al Nimis | Jordanian National Committee for Women (JNCW) |
| Isadora De Moura | UNWOMEN Jordan |
| Mr Ziad Sheikh | UNWOMEN Jordan |
| Prof. Zaid Eyadat | The Centre for Strategic Studies (CSS) |
| Maria Ardaji | Consulate General of Sweden in Jerusalem |
| Asem Khamis | Ministry of Social Sevelopment |
| Amin Khallaf | Musawah CBO Training |
| Leila Rouhi | UN Women |
| Moudni Abdelamjid | Media and culture CSO |
| Kouis Said | Tildat |
| Sadaoui Hamed | AIDECA |
| Amina Lotfi | Association Démocratique des femmes du Maroc (ADFM) |
| Amina fenane | Institut Marocain Pour le Développement Local (IMADEL) |
| Fatna Bouih | QDM |
| Abedlghani Elhamdaoui | Chourouk CBO |
| Amina Houari Slimani | Minstry of women affaires |
| noura mounim | Ayadi Elamal |
| Youssef Belouafi | Khouloud |
| Khadija Dellero | UN Women |

Annex 17: ‘Because I am a Man’ Campaign – Methodological recommendations for evaluation

Introduction and Background

Background for evaluating an element of the Men and Women for Gender Equality programme, specifically the ‘Because I am a Man’ campaign, which is being implemented by UN Women in the following six countries: Morocco, Tunisia, Jordan, Egypt, Lebanon and Palestine. The campaign has involved a mix of traditional (radio and TV) and social media (Facebook, Twitter and Instagram) channels.

The target audience of the campaign is 18–30-year-olds in each of the six countries.

The Challenge Where Face-to-Face Research is Often Next to Impossible

There is already some data on reach and, to a lesser extent, engagement. However, there is no data on effectiveness of the campaign, such as: proven recall by media/execution; attitude towards the campaign in general and specifics; how the campaign makes them feel; and how the campaign has changed their behaviour or prompted other actions (the issues that could be covered are outlined below).

The additional complication is the challenge of face-to-face fieldwork in some of these countries owing to safety concerns, although it may be possible at extortionate cost and very long timescales. Pragmatically, an online survey of 18–30-year-olds can be conducted in each of the six countries, using a 10-minute translated questionnaire with validated campaign evaluation questions. Using well-constructed panel samples and applying weighting post-fieldwork as necessary means that a representative sample in each country can provide robust effectiveness and attitudinal data by country, which will not only be of benefit in the evaluation but will also help inform the development of the campaign in the future.

The Research Solution

Having dismissed a purist and possibly unachievable face-to-face methodology (the cost of which would be likely to run into at least six figures sterling), we would recommend a well-designed online panel sample of 500 18–30-year-olds in each country with a questionnaire of 10 minutes (approximately 2500 words) that will be translated into modern Arabic in each country as appropriate. A long and detailed questionnaire would suffer from low response, high dropout and completion fatigue, which would undermine the quality of the data.

Such an approach will need the following in terms of timings:

Set-up – 1 day

Translations on a 2500-word 10-minute questionnaire – 3 days

Fieldwork – 10 days

Tables – 1 day

Topline report – 3 days.

It should be noted that costs do vary by country, with Palestine, Lebanon and Jordan the most expensive; for the other three the costs are substantially less, and across all six countries it should average out at just over £5000 per country, including a topline report.

The Questionnaire

The efficacy of this study will depend on a set of succinct and validated questions that can cover the key metrics in 10 minutes, principally using closed pre-coded questions. Any open-ended questions will add to coding costs, but it is anticipated that the only open-ended question that may be needed relates to proven recall of the campaign.

Drawing on my experience of campaign evaluation research, a summary of the issues to be covered would be as follows, although this is very much a starting point and dependent on the number of different channels and executions by each country:

Unprompted awareness of campaign

Proven recall of campaign or any specific executions (optional open-ended)

Prompted recall of campaign and specific executions

Attitudes towards overall campaign:

Relevance to them/people like them

Messages drawn from campaign (positive and negative)

Specific descriptors of campaign

Interest to know more

Actions taken from having seen campaign

Attitudes towards specific executions/channels:

Relevance to them/people like them

Messages drawn (positive and negative)

Specific descriptors

Interest to know more

Actions taken from having seen

Overall satisfaction/dissatisfaction towards the campaign

Changes to improve its impact

Annex 18: Because I Am a Man Campaign

A brief review of selected communications products, 28 February 2022

Introduction

This document presents reflections on a selection of communications products from the Because I Am a Man (BIAM) campaign. The document is based on a brief review of selected communications products on the BIAM playlist on YouTube, and it compares these with the BIAM Communications Strategy1 and with international best practice on social and behaviour change communications.2, 3 It is not comprehensive or systematic, nor is it based on beneficiary feedback, and these ideas should been seen as hypotheses for UN Women’s consideration.

The BIAM strategy and international best practice in SBCC

The BIAM Phase II campaign strategy contains recommendations for behaviour change communications and brand identity. These include:

using role models of successful couples who the target audience can relate to

demonstrating the benefits of gender equality in people’s lives to make it appealing and attractive

creating a brand personality which is successful, inspirational and friendly

focusing on fun and engaging activities through social media

including a specific call to action in communications products.

These principles are consistent with international best practice in social and behaviour change, which also emphasises that publicising the prevalence of harmful practices can reinforce inequality and make things worse.

Review of a selection of communications products

We can now review a selection of BIAM communications products taken from the BIAM YouTube playlist4 against these principles.

| Video title | Brief description | Review | Views at 28.02.2022 |
| --- | --- | --- | --- |
| Palestinian Men Speak Up For Gender Equality5 | Palestinian men speaking up in favour of gender equality | - Presents a range of positive role models - Suggests benefits of gender equality for men and women Lacks a clear call to action | 408 |
| Understanding Women’s Economic Empowerment In Morocco: A Drama6 | A conversation between two men, one more conservative and one more liberal | - Presents likeable and relatable characters - Shows the arguments in favour of women’s economic empowerment - Likely to prompt for further discussion | 207 |
| Understanding Masculinities In Lebanon – Adnan’s Story7 | Adnan speaks about the benefits of gender equality for his family | - Shows a positive role model - Demonstrates benefits of gender equality - Acknowledges challenges - Contains a call to action to other men | 173 |
| Learning Basic Homecare In Less Than Seven Minutes8 | Shows a man doing basic household chores in a light-hearted manner | - Has a fun and engaging tone - Shows a positive role model - Contains practical information and a call to action | 57 |
| Understanding Gender Norms In Palestine: A Drama9 | Story of a young boy who is ridiculed for failing to confirm to macho gender roles | - Shows a child being ridiculed and verbally abused - Highlights negative`x attitudes and behaviours - Risks reinforcing discriminatory practices - Lacks a call to action | 619 |
| Because I Am A Man (Hit Ana Rajel) Morocco10 | Ten videos on themes such as rape, sexual violence, etc. | - Shows negative, harmful and insulting behaviours - Highlights prevalence of negative behaviours - Likely to reinforce harmful gender norms - Lacks a call to action | Varies: averages 200–300, but 28,000 for marital rape |
| Understanding Masculinities In Lebanon: A Drama11 | A story of couple being criticised by the husband’s parents for engaging in gender equal behaviours | - Highlights discriminatory attitudes and behaviours - Shows couple being ridiculed for gender equal behaviours - Likely to reinforce negative practices - Lacks a call to action | 693 |

Conclusion

This brief review suggests that the BIAM strategy and brand identity are not consistently implemented across the range of BIAM communications. Some videos show positive role models, demonstrate the benefits of gender equality and have a clear call to action. Others highlight negative behaviours, publicise the prevalence of harmful practices and lack a call to action. We believe that the effectiveness of the campaign would be substantially enhanced by a more consistent implementation of the communications and brand strategy.

http://www3.weforum.org/docs/WEF_GGGR_2020.pdf

Women still have less access, to economic resources, ownership and control over land and other forms of property, inter alia.

Musawah, Who Provides? Who Cares? Changing Dynamics in Muslim Families, and Le concept de la Qiwamah du point de vue du referentiel. Religieux et des mutations societales au Maroc. Rapport d’analyse. Coordination: Aicha el Hajjami, 2018.

Jurists developed the concept of qiwamah as a set of obligations and rights for men and women in marriage: husbands protect and provide; wives in turn obey. Source: Musawah (2018) Who Provides? Who Cares? Changing Dynamics in Muslim Families, 2018.

Ibid. Jurists understood wilayah to refer to the right and duty of fathers or male family members to exercise guardianship over their dependent wards (female or male).

https://data.unwomen.org/sdg-monitoring

Amount converted into USD on 14 February 2021.

Amount converted into USD on 14 February 2021. It is worth mentioning that this amount is not reflective of the exact total amount received by UN Women after disbursements from Sida, because these depend on the SEK-USD exchange rate at the time of each bank transfer.

Promundo works to promote gender equality and prevent violence by engaging men and boys in partnership with women and girls. https://promundoglobal.org/work/

Musawah ('equality' in Arabic) is a global movement for equality and justice in the Muslim family https://www.musawah.org/about/

Phase II of the programme has a three-year implementation phase from March 2019 to February 2022. However, the evaluation will commence in April 2021, so will be able to cover the period to May 2021.

Social Relations Approach

https://genderatwork.org/analytical-framework/

Evaluation of UNDP’s Contribution to Gender Equality and Women’s Empowerment (2008–2013)

Applying Theory to Practice: CARE’s Journey Piloting Social Norms Measures for Gender Programming

Measuring Gender-related social norms, LSHTM &STRIVE

PACT_capacity_development

Kirkpatrick's Four-Level Training Evaluation Model

Field visits to three countries where the intervention is implemented are foreseen.

Tool 8. Evaluation matrix template

http://www.uneval.org/document/detail/608

Tool 14. GERAAS evaluation report quality assessment Guidance Note (2019) and EQA Matrix (2019)

Tool 7. Evaluation product comment template

Indicative and will be finalised during the inception phase.

As part of the inception phase, a more detailed evaluation timeline will be charted out by the evaluation team for the countries to be visited as part of onsite data collection in consultation with the EMG and programme staff.