End-term Evaluation of the Protection Component

of UN Women’s 2020-2021 “Women’s Economic Empowerment” (WEE) Interventions in Lebanon

Final Report

Table of Contents

List of Acronyms	2

List of Tables	3

Executive Summary	3

Background and Purpose of the Evaluation	4

Methods	4

Findings and Conclusions	4

Main Recommendations	5

1.	Background and context of the evaluation	6

1.1 Social, Political, Operational, and humanitarian context of Violence Against Women in Lebanon	7

1.2 Implementation of the integrated Women’s Economic Empowerment and protection interventions	8

1.1.	Theory of Change (TOC) and Logical Framework	8

2.	Evaluation Purpose, Objectives, Criteria and Scope	10

2.1.	Purpose of the Evaluation	11

2.2.	Evaluation Objectives	11

2.3.	Evaluation Criteria and Questions	11

2.4.	Scope of the Evaluation	12

2.4.1 Overall Scope	12

2.4.2 Integration of Human Rights and Gender Equality	12

2.5.	Intended Users	13

3.	Evaluation Methodology	13

3.1.	Data Collection Methods	14

3.2.	Sampling Strategy	15

3.3.	Data Compilation and Analysis	17

3.4.	Ethical Considerations	17

3.5.	Limitations	18

3.6.	Evaluation Management	18

4.	Evaluation Findings	19

4.1.	Relevance	20

4.2.	Effectiveness	22

4.3.	Coherence	27

4.4.	Efficiency	29

4.5.	Emerging Impact	30

4.6.	Sustainability	34

4.7.	Human Rights & Gender Equality	36

5.	Conclusions, Lessons Learned and Recommendations	38

5.1.	Conclusions	39

5.2.	Lessons Learned	40

5.3.	Recommendations	41

Annex 1: Evaluation TOR	44

Annex 2: List of documents consulted	54

Annex 3: List of Key Informant Interviews	55

Annex 4: Research Tools	56

Annex 5: Evaluation Matrix	74

Annex 6:  GRES Scale	79

Annex 7:  Partners Monitoring Tools	81

Annex 8:  Project Progress Report	89

Annex 9:  Project Expenditures Face forms	92

# List of Acronyms

| AWP | Annual Work Plan |
| --- | --- |
| CATI | Computer Assisted Telephone Interviews |
| COVID-19 | Corona Virus Disease of 2019 |
| CSO | Civil Society Organization |
| EMG | Evaluation Management Group |
| EQM | Evaluation Question Matrix |
| ERG | Evaluation Reference Group |
| ERP | Emergency Response Plan |
| ESC | Evaluation Steering Committee |
| ETM | Evaluation Task Manager |
| EVAW | End Violence Against Women |
| FGD | Focus Group Discussion |
| GBV | Gender-Based Violence |
| GBVIMS | Gender-Based Violence Information Management System |
| GERAAS | UN Women Global Evaluation Report Assessment and Analysis System |
| INGO | International Non-Governmental Organization |
| KI | Key Informant |
| KII | Key Informant Interviews |
| LEAP | Women’s Leadership, Empowerment, Access and Protection in Crisis Response |
| M&E | Monitoring & Evaluation |
| MHPSS | Mental Health and Psycho-Social Support |
| MOSA | Ministry of Social Affairs |
| MR | Management Response |
| NGO | Non-Governmental Organization |
| ODK | Open Data Kit Software |
| OECD-DAC | Organisation for Economic Co-operation and Development's Development Assistance Committee |
| PSEA | Prevention of Sexual Exploitation and Abuse |
| PSS | Psycho-Social Support |
| RGA | Rapid Gender Assessment |
| SDC | Social Development Center |
| SGBV | Sexual and Gender-Based Violence |
| SN | Strategic Note |
| SPSS | Statistical Package for the Social Sciences |
| TOC | Theory of Change |
| TOR | Terms of Reference |
| TVETC | Technical and Vocational Education Training Centers |
| UN WOMEN | United Nations Entity for Gender Equality and the Empowerment of Women |
| UNEG | United Nations Evaluation Group |
| USD | United States Dollar |
| VAW | Violence Against Women |
| WEE | Women’s Economic Empowerment |
| WHO | World Health Organization |

# List of Tables

Table 1- List of activities conducted under project (2021/2022) Outcome 1	12

Table 2- Women Economic Empowerment (WEE) Theory of Change (ToC)	13

Table 3- FGDs Distribution	19

Table 4 - Survey Quota Distribution	19

# Executive Summary

## Background and Purpose of the Evaluation

Violence against women (VAW) is a long-standing challenge in Lebanon, underpinned by patriarchal social norms and structural inequalities that manifest in a legal framework highly unfavourable to women. The situation of gender-based violence has worsened due to the combination of crises currently faced by Lebanon, from the financial and economic crisis to the health crisis caused by the COVID-19 pandemic.

UN Women works for the empowerment of women and the achievement of equality between women and men and has an established presence in Lebanon since 2017. In the current context, UN Women recognized the need to scale up protection services to meet the growing protection needs in the country. This evaluation stems from UN Women’s recognition of the need to assess its resilience and recovery response projects amid Lebanon’s new landscape, and aims to support UN Women Lebanon’s strategic learning, decision-making and positioning for future work and programming regarding the protection intervention of the Women’s Economic Empowerment (WEE) programme in Lebanon.

## Methods

The evaluation is utilization-focused and gender responsive. It followed the Organisation for Economic Co-operation and Development's Development Assistance Committee’s (OECD-DAC) criteria. The evaluation took place via a mixed methodological approach, consisting of both quantitative and qualitative primary and secondary data collection. The primary data was aimed at collecting a range of viewpoints from a sample of 15 interviews with key informants (KIs), including UN Women, implementing partners, and other local and international non-governmental organization (NGO) partners; three focus group discussions (FGDs) and 150 computer assisted telephone interview (CATI) surveys with target beneficiaries. The sampling methodology was purposive to facilitate access to the key stakeholders, and because of its better compatibility with the limitations caused by the COVID-19 pandemic and the ensuing lockdowns. The evaluation followed the World Health Organization’s (WHO) Ethical and Safety Recommendations for Research on Domestic Violence Against Women.

## Findings and Conclusions

Amidst the combined crises in Lebanon, protection needs are growing; at the same time, acute financial and economic needs emerged, sometimes overshadowing the search for psychosocial support and protection. In this context, both projects implemented by UN Women and its partners responded adequately to protection and psychosocial needs. The response was highly relevant to beneficiaries’ needs because the projects was built on evidence and through a particpatory approach with community-based organisations.

The projects underwent some adaptations following the COVID-19 pandemic and the Beirut port explosion on 4th August 2020. The most significant one being the shift to an online delivery modality approach.

The evaluation data confirmed the psychosocial support sessions and the legal counselling to be the most effective components of the projects, helping the beneficiaries find concrete solutions to their problems. At the same time, the awareness campaign was seen as less effective because it did not have a direct effect on its audience. However, the short timeline and the exclusion of men might have left the projects short of yielding optimal outcomes.

The projects had a positive influence on beneficiaries’ lives. The positive change happened at different levels: improved psychology and mindset of women, increased ability at emotional regulation and the social support network the women built through the project. Moreover, the positive influence extended to women’s relationship with their children and changed their perception of child raising. Regarding the women’s relationship with their partners, however, the project in some cases did not have an impact or, in other cases, worsened the relationship by causing more confrontations resulting from women demanding their rights.

Two projects run by UN Women and its implementing partners were mostly cost-efficient, and the teams were able to complete the activities on time, using the available resources. Further constraints faced by the projects were external in nature and originated from two sources: the health and economic situation in Lebanon, and the governmental bureaucracy, but UN Women’s and implementing partners’ flexibility helped in mitigating these challenges.

The project had a short timeline and did not have a clear sustainability plan. Nevertheless, several results emanating from the project indicated that sustainability could be ensured beyond the end of the project duration. At the national level, the collaboration with government and the long-term funding (including for retaining of NGO staff) were two key steps needed to achieve sustainability in protection projects. The evaluative evidence also indicated that the inclusion of men in protection projects represented an important factor for the achievement of sustainability.

Finally, the projects were able to promote gender responsive changes but did not succeed well at extending protection services to women with disability.

## Main Recommendations

- Include a cash component – unconditional cash or cash for work – in all current and near-future protection projects, to accommodate beneficiaries’ urgent financial needs. The cash component can last as long as the economic crisis persists or until UN Women might deem appropriate.

- Integrate psychiatrists in protection projects and/or in the staff of organizations working on gender-based violence in general to respond to the needs of beneficiaries having dire mental health problems.

- Work on the interpersonal level of the gender socio-ecological model, by raising the awareness of and empowering the beneficiaries’ direct environment. This applies to the beneficiaries’ children, but especially to the male figures in their family – husband, brother, etc.

- Continue the advocate for a change of the legal framework to render it in line with gender equality principles and continue to push for the application or reinforcement of laws and policies that protect women and girls from gender-based violence.

- Design longer-term projects to allow for more time to fully respond to beneficiaries’ protection needs, and better shape the recovery and sustainability aspects. Develop a sustainability/exit strategy as a part of the programme design, implement and monitor.

- Use advocacy to mainstream gender-based violence aspects into the projects of partners working in the livelihood sector. UN Women is in a strong position to use the advocacy tool, given that it is chairing the Gender Working Group and the LGBTIQ+ Task Force, and co-chairing the Child Protection and Sexual and gender-based violence sector under the Emergency Response Plan (ERP).

- Include beneficiaries in the design of the project, through consultations with women from the targeted communities, to have the community perspective considered and increase community ownership of the projects.

- Following the experience acquired from the implementation of remote delivery due to the COVID-19 pandemic, use online interventions in parallel to face-to-face interventions to extend protection projects to harder-to-reach categories, such as women living in remote areas or adolescent girls confined at home and in need of awareness sessions.

# Background and context of the evaluation

## 1.1 Social, political, operational, and humanitarian context of Violence Against Women in Lebanon

Violence against women is a long-standing challenge in Lebanon, underpinned by patriarchal social norms and structural inequalities that manifest in a legal framework highly unfavourable to women. This has worsened due to the combination of crises currently faced by Lebanon, from the financial and economic crisis to the health one caused by the COVID-19 pandemic. The crises coerced the women to be locked at home with their abusers and further reduced their ability to negotiate their rights and to access protection services.

Lebanon has long suffered from structural gender inequalities. In reference to the European Union and UN Women’s report “European Union Sector Specific Gender Analysis: An In-depth Sectoral Examination of Feminist and Women’s Rights Issues in Lebanon”, three main issues restrict women’s access to rights and gender-based violence related services: a) the gender inequality enshrined in the law and institutions, b) the patriarchal social and cultural norms, and c) the under-resourced and limited-service provision. In the lockdown period imposed because of the COVID-19 pandemic, the gender-based violence situation worsened, jeopardizing women’s and girls’ sense of safety even more.

Since 2019, Lebanon started facing an unprecedented multi-faceted crisis comprising of the economic, financial and health aspects. The combination of crises caused a dramatic change in the macro-economic framework that reflected on all social standings in the country, but especially on the already poor and vulnerable households among the Lebanese and refugee communities. Already struggling to make ends meet, these households found themselves with further reduced income generating opportunities, lower wages, worsening working conditions, and a more limited access to basic public services (health, social services, infrastructure, etc.) which, as a result of the crisis, became increasingly dysfunctional.

The overwhelming and devastating conditions have forced many parts of the population to resort to negative coping strategies, engendering harmful consequences on their livelihoods and health. In the case of women, be Lebanese or Syrian, or from different nationalities living in Lebanon, the negative coping strategies affected their ability to negotiate equal treatment, rights and protection from violence.

## 1.2 Implementation of the integrated Women’s Economic Empowerment and protection interventions

UN Women works for the empowerment of women and the achievement of equality between women and men and has an established its presence in Lebanon since 2017. Since the establishment of UN Women’s office presence in Lebanon, it has worked to empower women and girls at micro, meso, and macro levels. The Women’s Economic Empowerment programme predominantly focused on increasing the resilience of vulnerable women and girls in Lebanon through the provision of economic opportunities and the improvement of women’s and girls’ access to protection services from violence. In partnership with local actors providing protection services, UN Women has also been supporting vulnerable women and women at increased risk of sexual and gender-based violence.

In response to the combination of crises in Lebanon, between 2020-2022, UN Women and its partners implemented two projects titled: “Addressing Economic and Protection Challenges faced by Women and Girls (refugees and host community nationals) in Lebanon’s Host Communities and Country” (2020 to 2021) and “Crisis Response: Supporting Women Protection and Economic Recovery Lebanon” (2021 to 2022). Both projects aimed to contribute towards the empowerment of vulnerable women and girls within Syrian and Palestinian refugee and Lebanese host communities through increased economic opportunities, improved access to protection services, and increased resilience in the context of Lebanon’s multidimensional development challenges. The services addressing gender-based violence ranged from a broad awareness raising campaign to more targeted awareness raising sessions, individualized psycho-social and emotional support sessions, case management and the provision of shelters and safe spaces.

Both projects were funded by the government of Japan. The financial investment made for the protection component amounts to a total of 636,563 USD. This was divided between 449,819 USD for the “Addressing Economic and Protection Challenges faced by Women and Girls (refugees and host community nationals) in Lebanon’s Host Communities and Country” project, and 186,744 USD for the “Crisis Response: Supporting Women Protection and Economic Recovery Lebanon”.

## Theory of Change (TOC) and Logical Framework

In all its livelihood programming, UN Women Lebanon incorporates a protection component through the provision of proper protection information, awareness and referrals (when needed) to the targeted women. The overall theory of change (TOC) of the WEE programme at UN Women in Lebanon is as follows:

“If women are well equipped with market-based skills and resources,

If women are supported in accessing the local labour market,

If women are provided with information and access to protection services and practical skills on self-protection,

Then there will be a more protective and enabling environment for women’s economic participation,

Then women will be more resilient amidst the economic crisis and protected refugee crisis because women will be more engaged in public life and better able to access decent work.”

The projects were aligned with and contributed towards the theory of change (TOC) of the WEE programme at UN Women in Lebanon.

The interventions were also directly linked to the development results of UNW’s Strategic Plan (SP, 2018-2021), outcome four: “Outcome 4: All women and girls live a life free from all forms of violence”.

Furthermore, the projects also aligned with the below output 2.3.5 under the outcome 2.3. of UN Women Lebanon’s 2021 Annual Work Plan that is connected to the UN Women’s global Strategic Plan 2022-2025 Outcome 3:

- Impact 2: UN Women Strategic Plan Outcome 3: Women have income security, decent work, and economic autonomy

  - Outcome 2.3: National authorities, private sector and CSOs are engaged in and actively support gender equality and women’s economic empowerment and protection

    - Output 2.3.5: Women and girls are supported with essential protection services, including to respond to increased needs as a result of the Covid-19 epidemic.

Project one:

In collaboration with the Ministry of Social Affairs (MoSA), CARE International in Lebanon (CARE) and ABAAD, UN Women implemented the protection component of the project “Addressing Economic and Protection Challenges faced by Women and Girls (refugees and host community nationals) in Lebanon’s Host Communities and Country” from June 2020 until the end of February 2021.

The purpose of this project was to promote agency for women (both national and refugees), increase marginalized women’s access to assets and resources, improve women’s access to protection and childcare services and challenge structural inequalities to their economic participation. “Women’s access to childcare and protection services improved” was the project’s desired output which falls under the protection component.

The direct beneficiaries of the project account to a total of 3,657 women and girls; 41 per cent were Syrian refugees and 59 per cent were Lebanese and other nationalities. Of these 3,435 accessed direct protection services such as protection referrals, psycho-social counselling, legal aid, and social cohesion activities while the remaining attended awareness sessions.

Project two:

UN Women and its partner, KAFA started the implementation of the “Crisis Response: Supporting Women Protection and Economic Recovery Lebanon” one-year project by March 2021. The main goal of this project was to provide support to women affected by Lebanon’s crises (economic crisis, COVID-19 and the Syria crisis) and to their families, to recover and contribute to broader economic growth. The project addresses women’s urgent economic and protection needs, while also working on the macro-economic issues with women’s cooperatives and the private sector to support an enabling environment for women’s economic empowerment.

Under the protection component, two activities were conducted, which fall under the programme output “Women’s access to childcare and protection services improve”:

Table 1- List of activities conducted under project (2021/2022) Outcome 1

- Providing protection services and awareness raising for women and girls affected by the Blast and the economic crisis including case management, mental health, prevention of sexual exploitation and abuse (PSEA) and psychosocial support (Mental health and psychosocial support) services, gender-based violence related services, and comprehensive legal assistance, including legal representation. Indicator: # of women and girls reached through protection services and awareness raising. Baseline: 0. Target: 500 beneficiaries

- Rehabilitation of two social development centers (SDCs) to become safe spaces – Under implementation by time evaluation occurred- Indicator: # of SDCs rehabilitated. Baseline: 0. Target: 2

# Evaluation Purpose, Objectives, Criteria and Scope

## Purpose of the Evaluation

The main purpose of the end-term evaluation is to support UN Women Lebanon’s strategic learning, and decision-making and positioning for future work and programming on the protection intervention of the Women’s Economic Empowerment programme in Lebanon. More specifically, the purpose of this evaluation was to:

- Draw lessons learned and recommendations for future work and programming on the protection component of the Women’s Economic Empowerment programming in Lebanon;

- Have a forward looking or formative focus and provide key recommendations for the implementation and scaling up opportunities of future work, based on the lessons learned identified through this evaluation; and

- Provide forward looking recommendation on the roles of all key stakeholders to ensure linkages and mutual synergies of the different stakeholders.

## Evaluation Objectives

The evaluation had the following objectives:

- To provide a detailed assessment of the extent to which the protection services achieved their intended results in line with the project’s theory of change;

- Identify and validate lessons learned, promising practices and innovations of protection work supported by Women’s Economic Empowerment Programme;

- Provide actionable recommendations with respect to the development of the protection component of the future programming of the Women’s Economic Empowerment programmes;

- Support the UN Women Country Office to improve its strategic positioning to better support the achievement of sustained gender equality and ending violence against women.

## Evaluation Criteria and Questions

The evaluation utilized the OECD-DAC evaluation criteria of Relevance, Effectiveness, Coherence, Efficiency, Impact, Sustainability, and Human Rights & Gender Equality. The specific evaluation questions were as follows:

Relevance:

- To what extent did the projects reach out and respond to the needs and priorities of the beneficiaries?

- To what extent was the project ToC, design, implementation strategy and approaches relevant to the needs and priorities in Lebanon?

Effectiveness

- To what extent did the project increase the protection and awareness about what rights of the targeted women?

- What were the main successes of the project interventions?

- What are the limiting factors that might have hindered the achievement of the intended results and what needs to be done to overcome these limiting factors?

- How effective was the online interventions that replaced the face-to-face interventions during COVID 19?

Efficiency

- To what extent did UN Women’s allocated resources (human and financial) enable the effective implementation of the project interventions?

- What is UN Women’s comparative advantage for the implementation of protection services in Lebanon?

- What improvement in resources, institutional setup and arrangement is required for the efficient implementation and the achievement of results?

Coherence

- To what extent were the project interventions coherent with interventions with similar objectives of other stakeholders?

Impact

- To what extent the results achieved have contributed to changes (positive and negative) in beneficiaries' lives as a result of the intervention.

Sustainability

- To what extent did the project interventions contribute to the creation of sustainable results (both on the individual and the institutional level)

Human rights & Gender Equality

- To what extent was the human rights-based approach and gender equality incorporated in the design and implementation?

- To what extent has UN Women been able to identify and address the challenges to bring forth gender transformative changes within the framework of the project?

For a detailed evaluation matrix, please refer to Annex 5: Evaluation Matrix

## Scope of the Evaluation

### 2.4.1 Overall Scope

The evaluation looked at the protection components of two UN Women projects funded by the Government of Japan and covered the period from June 2020 till March 2022, with focus on lessons and evidence of the achieved outputs and activities.

The geographical scope of the evaluation focused on the project’s three implementation areas (Beirut, Akkar and Tripoli).

The evaluation assessed how the project was designed considering the Beirut blast and the economic crisis, and how it adapted its activities to the COVID-19 pandemic.

### 2.4.2 Integration of Human Rights and Gender Equality

The evaluation was guided by the United Nations Evaluation Group (UNEG) Guidelines on Human Rights and Gender Equality in Evaluations, specifically, UNEG Ethical guidance and norms, as well as UN Women’s Guide on Gender-Responsive Evaluations. As such, a focus on human rights and gender equality was integrated into all the phases of the evaluation in the following manner:

- Dedicated evaluation criteria on human rights and gender equality was included in the evaluation questions.

- The language and cultural issues were carefully assessed in the interview questions, as well as through the survey questions. The survey was piloted prior to the official launch with project beneficiaries to assess user-friendliness and cultural/language appropriateness. Interviews with key stakeholders were almost always carried out in Arabic, or a combination of Arabic and English.

- Informed consents were obtained in each of the data collection components, and it was made explicit that the names of individuals consulted during evaluation data collection will not be made public.

- In constituting Focus Group Discussions (FGDs), the consultant and UN Women’s implementing partners who facilitated this process paid attention to ensuring that members of the FGDs felt safe to participate and communicate their ideas, by making participation in the FGDs voluntary, holding the meetings in the language participants were comfortable with, as well as inviting participants from stakeholders that are homogeneous and compatible together.

- When preparing the sampling strategy, ten per cent of the surveys were planned to be conducted with the most marginalised groups (i.e. women with disabilities), however the response rate was very low.

- A gender analytical lens was applied to analyse and interpret data

## Intended Users

The main users of this evaluation are the UN Women Lebanon Country Office and project stakeholders, who will use the findings of the evaluation to feed into UN Women Lebanon Country Office’s Strategic plan for the coming three years (2022-24) and in formulating new protection programming and Women’s Economic Empowerment programming with protection components in Lebanon.

- Evaluation Methodology

The evaluation is utilization focused, gender responsive, and used the principle of participation through stakeholders’ involvement across the evaluation cycle. A stakeholders analysis map was prepared to inform the evaluation design, methodology and sample size.

The evaluation included gender analysis across the report and followed UN Women’s Global Evaluation Reports Assessment and Analysis System (GERAAS). UNDP Gender Results Effectiveness Scale (GRES)was used as the gender analytical framework for the evaluation to assess if the projects were gender negative, blind, targeted, responsive and transformative in nature. For more details, please refer to the evaluation matrix (ref. Annex 5: Evaluation Matrix)

## Data Collection Methods

The evaluation employed a mixed methodological approach, consisting of both quantitative and qualitative primary and secondary data collection.

Primary Data Collection

Primary data collection aimed to assess whether the projects met their objective, and in that scope, a wide range of viewpoints was collected from a sample of 15 KIIs conducted with UN Women Lebanon staff, implementing partners staff, staff from local and international NGOs and experts in the field of protection; three FGDs with beneficiaries in the three regions of intervention covering total 25 stakeholders; and 150 CATI surveys with beneficiaries residing in the projects’ three implementation regions.

- Key Informant Interviews (KIIs): The interviews were semi-structured, yet flexible to allow for targeting the questions according to the key informant’s level of familiarity and engagement with the project(s). Due to the COVID-19 pandemic, the KIIs were conducted virtually, with online platforms such as WhatsApp, Skype, or Zoom utilized for the purpose.

- Focus Group Discussions (FGDs): FGDs were primarily with project beneficiaries thereby ensuring inclusiveness of target population. A total of three FGDs were held covering total 25 stakeholders.

- Computer Assisted Telephone Interviews (CATI): The quantitative survey was conducted in Arabic with beneficiaries residing in the projects three implementation areas (Beirut, Akkar, and Tripoli).  A total of 150 CATI surveys were conducted.

The survey was conducted through CATI because of the COVID-19 pandemic. Consequently, it did not exceed 15 minutes in length. A database especially conceived for the processing of the collected data, using Open Data Kit (ODK), was developed.

Before the start of the survey, a pilot test was conducted to test the smooth transition between questions and whether the questions were clear and met the time frame for the tool.

Secondary Data Collection

The secondary data collection consisted of a review of around 20 reports and documents shared by UN Women Lebanon’s team, and a compilation of existing literature, documentation, studies and reports carried out on the related topics under study.

## Sampling Strategy

In all evaluation components (KIIs, FGDs, CATI survey), a purposive sampling was followed reflecting the profile of participants. The data collection looked to target primarily all the actors involved in the project, i.e., UN Women’s staff, implementing partner’s staff, government representatives and beneficiaries of the projects. To complement the analysis and evaluate the project with respect to other initiatives taking place in the protection sector, especially at the coherence and sustainability levels, a consultation with staff from external NGOs and with experts from the protection sector also took place.

A total of 15 KIIs, 3 FGDs, and 150 CATI Surveys were conducted.

Due to the limits imposed by the COVID-19 pandemic, the consultations were done virtually with most of the stakeholders.

The sampling and survey demographics details are described below.

- Distribution of Key Informant Interviews (ref Annex 3: List of Key Informant Interviews):

Table 2- KII distribution

| # Interviews | Participants |
| --- | --- |
| 3 | Staff from UN Women management involved in the programme |
| 6 | Staff from UN Women implementing partners involved in the programme (Care International Lebanon, ABAAD and KAFA) |
| 3 | Staff from other international and national NGOs working on protection in Lebanon |
| 3 | other project stakeholders as applicable (Experts, governmental institutions and others). |

- Distribution and profile of FGDs participants:

Table 3- FGDs Distribution

| Area | Implementing Partner | Number of Attendees | Nationality | Current Marital Status | Children | Age Groups |
| --- | --- | --- | --- | --- | --- | --- |
| Beirut/ Mount Lebanon | KAFA | 10 | Lebanese | Married and Non-Married | With and Without | Adults (30+) |
| Akkar | ABAAD | 10 | Non-Lebanese | Married and Non-Married | With and Without | Adults (30+) |
| Akkar | Care International | 5 | Non-Lebanese | Non-Married | Without | Youth (18 to 29 years) |

- CATI survey quota Distribution

Table 4 - Survey Quota Distribution

| Area Under Study | Target Population | Implementing Partner | Quota Distribution |
| --- | --- | --- | --- |
| Beirut/ Mount Lebanon | Female Beneficiaries | KAFA | 50 |
| Akkar and Tripoli | Female Beneficiaries | CARE/ABAAD | 100 |
| Total |  |  | 150 |

- CATI Survey Demographics:

- Almost equal split between age groups with youth (15 to 29 years) at 46% and adults (30+) at 54%.

- Average age of total sample is 36 years.

- Nationality of surveyed females:

| Nationality | Count | Percentage |
| --- | --- | --- |
| Lebanese | 107 | 71.3% |
| Non-Lebanese | 43 | 28.7% |
| Total | 150 | 100% |

- Marital status of surveyed females:

| Marital Status | Count | Percentage |
| --- | --- | --- |
| Single | 24 | 16% |
| Married with children | 84 | 56% |
| Married without children | 3 | 2% |
| Divorced/ Separated/ Widowed with Children | 37 | 25% |
| Divorced/ Separated/ Widowed without Children | 2 | 1% |
| Total | 150 | 100% |

v)              Services received by surveyed females:

| Services by Partners |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Grand Total |  | ABAAD and Care International | KAFA |
|  |  | Total | % | Count | Count |
| Services Received | Protection services - Case Management | 26 | 17.3% | 0 | 26 |
|  | Protection services – Prevention of Sexual Exploitation and Abuse Services* | 9 | 6.0% | 9 | 0 |
|  | Protection services - Mental Health and Psycho-Social Support Services | 52 | 34.7% | 23 | 29 |
|  | Protection services - GENDER-BASED VIOLENCE Services | 3 | 2.0% | 3 | 0 |
|  | Protection services - Legal Assistance | 12 | 8.0% | 0 | 12 |
|  | Protection services - Legal Representation | 23 | 15.3% | 1 | 22 |
|  | Protection awareness sessions | 87 | 58.0% | 87 | 0 |
|  | Other non-protection services (included trainings on jobs and cash assistance) | 61 | 40.7% | 59 | 2 |

*PSEA services included In-kind distribution and share of information

vi) Inclusiveness: 10 per cent of the total CATI surveys were planned to be conducted with the most marginalised groups (i.e., women with disabilities). However, only one female with disability was available and able to participate in the survey.

## Data Compilation and Analysis

To retain the integrity of the data, all transcripts and all information pertaining to the study were stored on a secured, password-protected computer. For the KIIs and FGDs, information was coded compiled and summarized using NViVo qualitative data analytical software, whereas the survey data was analysed using SPSS.

Results of the desk review segment, the KIIs, the FGDs, and the surveys were triangulated to validate the data and ensure its quality.

Following the data collection and data analysis, the consultant held a workshop with UN Women team to discuss the findings and validate the data and the analysis. The evaluation recommendations were drafted using a participatory approach to achieve optimal buy-in and utilisation of the evaluation.

## Ethical Considerations

The evaluation was conducted in line with United Nations Evaluation Group (UNEG)’s ethical guidelines and the code of conduct for evaluators in the UN system. By signing the UN Women Code of Conduct, which is based on the UNEG code of conduct, the consultant committed herself to abide by the requirements for integrity, accountability, respect, and beneficence.

The evaluation also followed the WHO Ethical and Safety Recommendations for Research on Domestic Violence Against Women. Particularly, the data collection team made sure to maintain strict confidentiality and to create a safe space for sharing perspectives and experience in order to avoid participants discomfort, embarrassment or emotional distress.

## Limitations

- The COVID-19 pandemic as well as the fuel crisis in Lebanon (February 2022) were the main limitations of this evaluation. They restricted travel and in-person interviews, leading to informant interviews being conducted online and the quantitative survey being conducted by phone.

- The FGDs, were conducted in-person while adhering to COVID-19 precautionary measures. The preference was for FGDs to be conducted in person for a better management of the group format and a possibility to probe and induce a deeper discussion.

- Ten per cent of the total surveys were also planned to be conducted with the most marginalised groups (i.e. women with disabilities). However, only one female with disability was available and able to participate in the survey.

## Evaluation Management

Representing a consultative, inclusive, and participatory process, the evaluation included a twofold management structure, an Evaluation Management Group (EMG) and Evaluation Reference Group (ERG). Furthermore, an Evaluation Steering Committee (ESC) was established.

The EMG was established to oversee the evaluation management, make key decisions, quality assure different deliverables and maintain highest degree of independence during the entire evaluation process. Under the overall guidance of the EMG and the Evaluation Task Manager (ETM), the evaluation was carried out by an independent evaluation consultant, who coordinated closely with UN Women Lebanon’s team and the EMG on all steps of the evaluation. The preliminary findings were shared with UN Women’s team.

The ERG was established to facilitate a comprehensive review of the evaluation products and to ensure the participation of key stakeholders in the evaluation. The ERG comprised of UN Women Staff, key humanitarian stakeholders in Lebanon, duty bearers and right holders. It served as an integral part of the evaluation management structure and was constituted to facilitate the participation of relevant stakeholders in the design and scope of the evaluation, raising awareness of the different information needs, quality assurance throughout the process and in disseminating the evaluation results.

The ESC was established as the key accountable body to endorse the evaluation report and will be responsible for the development of an Evaluation Management Response (EMR) to address the recommendations included in the report.

# Evaluation Findings

## Relevance

Finding 1: Amidst the COVID-19 pandemic, the Lebanese economic crisis and the Beirut Blast, protection needs were growing and a necessity to be addressed. At the same time, strong financial and economic needs emerged due to the acute deterioration of the economic situation in the country. In this context, the projects were relevant to the needs of the women and responded adequately to their protection and psycho-social needs.

Gender-based violence has been a critical challenge in Lebanon, raising protection needs among Lebanese and migrant women, as well as women from the refugee community. The combination of the Lebanese economic crisis, the COVID-19 pandemic and the Beirut blast exacerbated these needs while creating new financial and economic ones. Specifically, the COVID-19 pandemic triggered a higher number of gender-based violence cases because “women were confined at home with their abusers”, as put by one of the interviewed stakeholders, leading to increased protection and psycho-social needs. Simultaneously, the economic crisis and the Beirut blast created acute financial needs, especially for the women who came from vulnerable households.

The evaluation respondents shared that for beneficiaries, financial needs sometimes overshadowed the needs for psycho-social support and protection. They explained that the economic crisis had put basic needs, such as food or rent payment, at the top priorities of women victims of gender-based violence, thus relegating their search for support regarding the violence to a secondary place. This applied specially to married women with children, as their primary concern became “to provide their family with food”, according to one interviewee. According to the implementing partners staff respondents, women were also more reluctant to act against violence due to the lack of financial support from jobs or from their parents.

The projects were built on evidence and , were considered to identify the needs related to women’s protection in Lebanon. assessments of needs of the beneficiaries, making the project design relevant. The country and beneficiary needs in terms of protection services were identified by UN Women and its implementing partners through desk research of the latest studies done by different relevant organizations on gender-based violence status in Lebanon. Reports such as Vulnerability Assessment of Syrian Refugees in Lebanon (VASyR), “Strengthening access to protection, participation and services for women refugees, IDPs and host communities” baseline assessment produced under the EU Madad funded projects, reporting data from the Internal Security Forces on gender-based violence cases, as well as data from the gender-based violence information management system (GBVIMS)

In addition, a rapid gender analysis21 performed by UN Women in the aftermath of the Beirut Blast, as well as an assessment done by UN Women’s implementing partner, ABAAD, of the areas and services affected by the Beirut Blast, were taken into consideration for designing the programme. This helped the projects to better understand the priorities of women and girls at that time.

Moreover, UN Women’s implementing partners’ grass root experience and in-depth knowledge of protection issues, women’s situation and needs were also taken into consideration.

As the COVID-19 pandemic intensified, and the Beirut Blast occurred, the project underwent some adaptations to remain relevant and continue the services. The major adaptation was regarding the delivery approach which shifted to an online modality. Awareness sessions, case management and training took place in an online format. For example, a safety and self-defence training was recorded on video and distributed to beneficiaries.

In the context of the Beirut Blast, the adaptation mainly occurred by shifting part of the psycho-social sessions to focus on issues of trauma or first aid, and to include children in the sessions, or help parents deal with their children’s psychological or emotional challenges. This, however, always took place in the frame of the psycho-social support provided originally in the projects to keep it relevant to the projects’ objectives and to beneficiaries’ needs.

Most of the stakeholders considered the projects’ design relevant to the emerging needs of the beneficiaries. In their opinion, protection and awareness raising services were always relevant, given the persistence of gender-based violence challenges in the country. The services also included the distribution of dignity and/or hygiene kits, that interviewees considered very relevant and important given both the confinement situation and the financial challenges women were facing.

In addition, the psycho-social support sessions focused, among other topics, on questions relevant to the economic crisis, such as household management, financial management and time management. Given that the economic challenges were pre-existing, related questions were included in the projects design, for example, questions regarding electricity availability, internet and gas costs to hear about beneficiaries’ means of communication and transportation.

The CATI Survey results showed that almost all beneficiaries (92 per cent) were either extremely satisfied or satisfied with the relevance of the services to their needs. Further, when asked about needs which were not fulfilled by the interventions, 78 per cent of survey respondents reported receiving all needed support with no exceptions, while the remaining highlighted their additional need for financial assistance and courses/classes to improve practical skills needed in the labour market.

Table: Level of Satisfaction of beneficiaries with the relevance of the service to their needs

|  |  | Level of Satisfaction of beneficiaries with the relevance of the service to their needs |  |  |
| --- | --- | --- | --- | --- |
| Service(s) Received | Count | Neutral | Satisfied | Extremely Satisfied |
| Protection services - Case Management | 26 | 7.7% | 23.1% | 69.2% |
| Protection services - PSEA Services* | 9 | 11.1% | 22.2% | 66.7% |
| Protection services - MHPSS Services | 52 | 5.8% | 32.7% | 61.5% |
| Protection services - GENDER-BASED VIOLENCE Services | 12 | 16.7% | 41.7% | 41.7% |
| Protection services - Legal Representation | 23 | 13% | 44% | 44% |
| Protection awareness sessions | 87 | 3% | 58% | 39% |

Source: CATI Surveys total sample: 150 female beneficiaries

*PSEA services included In-kind distribution and share of information

The project outcomes were also relevant to UN Women’s Economic Empowerment Programme Theory of Change. The Theory of Change stated that a combination of protection and livelihood improvement in women’s lives will enhance women’s protective and enabling environment. UN Women indicated that they were working on merging the protection and livelihood components in such a way to have mandatory protection awareness sessions given to women enrolled in livelihood programmes on one hand, and to assist women enrolled in protection services who are searching for jobs on the other.

To conclude, the projects were built on the evidence and assessments of the needs of the beneficiaries and designed following a participatory approach taking into account the implementing partners’ perspective. This helped to make the projects highly relevant and responsive to the needs of the beneficiaries.

## Effectiveness

Finding 2: The projects fulfilled their intended objectives, with psychosocial support and legal counselling as the two most effective components.

The protection components of both projects consisted of a set of activities aimed at increasing the protection and awareness of the women beneficiaries about gender-based violence and their legal rights. Based on the evaluation evidence, the projects reached their intended objectives, with results indicating that women had an increased knowledge about their rights and about reach-out methods, referral pathways, and self-defence methods. This was validated by the evidence generated through the programme monitoring data and beneficiary feedback tools, employed by implementing partners, such as the pre/post-tests tied to awareness sessions, satisfaction surveys tied to training or psychosocial support sessions, wellbeing surveys tied to case management, and the focus groups and phone calls follow-ups, (ref. annex7: Partners M&E Tools). However, concerns were expressed by the implementing partners regarding the short life span of the projects as a result of which they were not able to measure the long-term impact of the interventions (i.e. the status of the beneficiaries six months after the end of a project activities). As a part of the data and results verification process, the outcomes from the M&E tools were corroborated by UN Women and implementing partners’ observations during regular field visits.

According to an implementing partner's staff, the increase in the number of women filing complaints “without being afraid” from 299 to 1371 calls during March-Aug 2020, demonstrated that women were more aware of their rights and of the existence of a protection system that could support them in their fight against violence. Besides the gained knowledge and awareness, the fostering of a sense of community, support, self-love and self-esteem represented other attainments of project,. However, evaluation data revealed that the monitoring framework of interventions needed to include more detailed indicators for measuring program’s longer-term impact.

The project effectiveness was also confirmed by the beneficiaries during their evaluation interviews wherein most of the interviewed beneficiaries stated that the provided services fulfilled their needs, whether psychosocial or legal. The emotional regulation, self-confidence and psychological strength gained as a result of the psychosocial sessions were among the top benefits cited by beneficiaries during FGDs, in addition to the feelings of being heard and supported, and knowledge acquired about their rights. Project’ beneficiaries in particular talked about the legal counselling service, with many seeing it as an important need that was fulfilled through the project, especially since most of the women were not able to afford a lawyer’s fees on their own. Some stated being disappointed with the outcomes of the legal procedures but recognized that this was due to the national legal framework regarding gender-based violence rather than the project’s performance. Overall, the beneficiaries rated the benefits from the assistance provided by the projects between 75% and 100%, once again highlighting the effectiveness of the project in achieving its objectives.

The psychosocial support sessions and the legal counselling came across as the most effective components of the projects according to evaluation data. Beyond being perceived as such by the beneficiaries, the legal support proved to be essential in teaching women about their rights and showing them that a solution to their situation exists. As one implementing partner’s staff put it, “when you have domestic violence, you don’t only need a psychosocial support, you also need a way in order to end this violence”. This does not exclude, however, the high effectiveness and importance of psychosocial support in preparing the women for the journey out of gender-based violence.

On the other hand, the awareness media campaign was viewed as the least effective component by interviewed stakeholders. The awareness campaign did not have a direct effect on its audience, hence reported to be not concretely contributing to increasing beneficiaries’ protection and awareness.

Most of the interviewed stakeholders said they would not change details in the project but suggest that the projects put an increased focus on the legal component by providing more legal assistance and counselling, integrate psychiatrists in protection projects and/or in the staff of organizations working on gender-based violence in general to respond to the needs of beneficiaries having dire mental health problems and involve work with men and communities

Overall, the evaluation data showed that the project outcomes were met. Interviews with implementing partners’ staff revealed that exceeding the project’s target (initially established at the beginning of the project) constituted a proof of the project’s success and of the importance of the issues it was tackling (ref Annex8: Project Progress Report). Women’s empowerment, overall, was mostly satisfying, almost to a 70% rate, as estimated by one of the implementing partners.

“Usually when you seek help outside your environment means that no one was standing by you, till you reached a point where you had to contact someone for help. The most important thing is that you feel you are taken care of, even though they don’t know you. They can really know what you are thinking about since they had lot of women who went through the same thing.” – FGD participant

“They have the determination to follow up with you and contact you, which made me discuss social and mental matters. I don’t care about legal consultation anymore, because I understood that you need to get on your feet and have self-confidence first, then the other things come along. If I want to demand my rights for the kids’ custody and I don’t feel okay, how would my relationship with my kids be like? So this mental and social help I am getting is so important.”

– FGD participant

Finding 3: The exclusion of men constituted an important limitation to project results, in addition to the short life span of the projects.

Evaluation data confirms that the projects’ results were coherent, logical, and valid with regard to the beneficiaries’ needs, with some limitations. However, the main limitation concerned the absence of men’s involvement. For a number of interviewed stakeholders, protection projects that do not address men – often the other party in gender-based violence cases – remain incomplete and do not yield the best outcomes. Raising men’s awareness represented an important component in women’s empowerment journey, because under the current system in Lebanon, men enjoy significantly more power compared to women and hence, empowering women can sometimes result in confrontations between them, and the male members of their households potentially end up harming them. Therefore, organizing awareness sessions for men about women’s rights, or including men in stress management or relationship management sessions was essential for the success of the outcomes of protection projects.

Another limitation concerned the length of the project. Different implementing partners’ staff viewed that ten months was a short timeline for a protection project. The recovery of women and the change of mindsets that should emanate from such projects are long-term processes that require more time and a longer accompaniment of women.

“Since the beginning of the crisis till now, the work with men is so little. We need to work on both sides, on the beater and the beaten, but we are not working on the one behind [gender-based violence] which increases the stress between [women and men]. So, in a way we are telling her about her rights, and when she goes to demand for it, we are causing her more harm.”

– Partner Representative.

Finding 4: The projects put beneficiaries on the path of recovery, but full recovery, in addition to depending on a multitude of factors, requires longer-term project that regularly follow-up on women’s status. The protection interventions were also not well aligned with the economic empowerment components.

While the projects put the women on the path of recovery, evidence of full recovery is not guaranteed. As pointed by interviewed implementing partners, full recovery would require longer-term projects that include more recovery sessions, personal work with the beneficiaries, monitoring and follow-up. UN Women’s implementing partner organizations underlined that they continued accompanying women, after the end of the projects, to help them on their recovery path. However, 65 per cent of CATI survey respondents and some focus group participants indicated that they had not received any post-project follow-up. The beneficiaries stressed that continuing the provision of emotional and psychological support by the organizations is essential for them to feel supported in the recovery process.

In addition, there was a need for financial assistance stemming from the situation of economic crisis, which the livelihood component did not always succeed at alleviating. The stakeholders shared that women’s full recovery depended on several factors. First, her choices played an important role in her recovery. It depended on her making a personal decision to continue her journey and her fight out of the gender-based violence situation. Second, beneficiaries pointed out that receiving financial and economic support was an important condition for their recovery, indicating that such support could be achieved by granting women jobs or a financial contribution towards their children’s education.

Finding 5: Implementation challenges encountered by the projects were mostly exogenous, and mitigation strategies were employed to overcome them. The major mitigation strategy consisted of a shift to online modality due to the COVID-19 pandemic. While having brought good results, its level of effectiveness could not be equated with face-to-face implementation.

Logistical issues, governmental procedures regarding Social Development Centers (SDCs) and the inability to implement face-to-face activities due to COVID-19 pandemic were the main obstacles during the project implementation. Logistical challenges included transportation challenges, where women were unable to reach the implementing partners’ Centers due to either the mounting costs, triggered by the currency devaluation, or due to the road blockages caused by the protests that were taking place periodically in Lebanon. UN Women’s implementing partners tried to facilitate transportation by providing buses for the beneficiaries to bring them to the centers. Evaluation data showed that this flexibility was needed because “it is very difficult for a woman to make the decision of talking about violence, so we appreciate her effort, and we have to support her and motivate her”.

Another logistical challenge was related to the internet, both in terms of availability and cost. Given that the internet became an essential condition for the implementation of activities during the COVID-19 period, UN Women and its implementing partners took the decision to cover the internet expenses and offered the beneficiaries internet bundles to enable a constant communication between the staff and the beneficiaries. The shift to the online modality, indeed, was fundamental in keeping the projects running, in the absence of the possibility to continue with face-to-face activities. Implementing partners’ staff mainly used WhatsApp as the means of online communication, either individually or in groups, to implement activities such as case management, awareness sessions or training.

The Social Development Center (SDCs), on the other hand, represented a major challenge for the implementing agency, KAFA, as their project included the rehabilitation of two SDCs and their transformation into safe spaces. This activity required an approval from the director general of the Minister of Social Affairs (MOSA) which was constantly delayed due to governmental bureaucracy but was granted at the end. However, due to this delay it was not possible to properly evaluate this programme component as the rehabilitation and trainings of the SDCs’ staff were conducted during March 2022. However, KAFA with the support of UN Women kept an open communication channel with the Ministry of Social Affairs, in addition to a continuous follow-up, to resolve the delay issue.

While the online modality was vital for the projects’ continuity, its effectiveness was lower compared to face-to-face implementation. Evaluation data highlighted the importance of face-to-face interaction in the protection domain, first because of the body language which helped the staff to analyse the beneficiaries’ situation, and second because of the trust that is easier established when the interlocutor is seen. Moreover, some high-risk cases cannot be dealt with only on an online basis as the situation of the woman might pose a threat to her safety. In that case, the implementing partners were able to keep their centers open and host these women. For the rest of the cases, while the quality of the services might have been slightly affected due to the online delivery method, this did not however, eliminate the effectiveness of the services. Indeed, as per the previous analysis in Section 5.1, the projects were able to achieve positive results even by working in an online format, and the implementing partners’ staff were able to circulate their intended message and to register a high participation of beneficiaries in remotely held sessions.

Finally, an important gap in protection projects’ effectiveness in general, that was underlined by interviewed experts, concerned mental health. The experts emphasized the lack of coverage of mental health in protection projects, arguing that addressing mental health is not limited to psychosocial support, and should include dedicated psychiatrists who follow beneficiaries in need. The supply of psychiatrists in the humanitarian domain is still low and limited to a small number of organizations, which slows down referral processes and can have negative effects on the beneficiaries. Improving the mental health coverage is hence important for the improvement of protection services in general.

In addition, evaluation data revealed that the online modality helped reaching some of the most unreachable people and communicated with them in simple ways (via voice messages) without the need for them to know how to read or write. This applies especially for women living in remote areas (far from implementing partner’s Centers), or who may face restrictions on their movements from their families or spouses. The lack of literacy of these women might make it harder for them to physically find the directions for the implementing partner's Centers. The use of this alternative virtual method can thus help bring support to these women in their place of living.

## Coherence

Finding 6: The projects were characterized by smooth communication and effective coordination between all stakeholders, with no major challenges noted, but there is scope for improvement.

The projects were characterized by an effective and smooth communication between various stakeholders, an element that contributed to their successful outcomes. The relationship between UN Women and its partners was positive, based on constant communication and coordination. No major challenges were recorded, and the division of roles and responsibilities was clear.

As indicated by the stakeholders, the communication between UN Women and the partners was regular without micro-management by UN Women. This allowed partners to work independently while being able to count on the support of UN Women when the need arose. The communication took mostly the form of weekly updates sent via email, a periodic report and a monthly meeting with the UN Women focal point. UN Women staff were satisfied with the communication, although there was specific feedback that one implementing partner was less responsive highlighting the need to improve the monitoring and oversight over their performance.

Partners, beyond their communication with UN Women, had to also communicate with other partners, with beneficiaries and with project donors. The communication between partners was frequent, generally amounting to a meeting per week to discuss implementation of activities. While the relationship between ABAAD, Care International Lebanon and the other stakeholders they worked with (such as municipalities or local NGOs) was trustworthy and fruitful, KAFA faced some challenges with MOSA regarding the SDCs, and resorted to the support of UN Women to act as an interlocutor with the Ministry, which proved fruitful for the component’s full implementation in the end. The contact with donors was less frequent, generally limited to a meeting per month, whereas the communication with the beneficiaries was on a regular basis.

As for beneficiaries, the results of the evaluation CATI survey showed a high satisfaction with their interaction with project staff. On average, 93 per cent of surveyed respondents reported good and very good communication with project staff across all services received, and 87 per cent described the staff, who provided them with the services, as professional and extremely professional. This applied to all services received as well. In addition, the Women’s Economic Empowerment Monitoring of Quality Protection Service exercise conducted directly by UN Women staff with beneficiaries of KAFA’s services, pointed out that partner staff were appreciated by the sample group as being a very professional team that respected all beneficiaries regardless of their background and ensured a close follow-up on the cases they are assigned.

No particular challenges stood in the way of communication and coordination in the projects. Delays in the planning and implementation of the activities were rare. In case they occurred, they were due to the prevailing external crisis situation rather than being caused by the stakeholders.

The smooth running of the projects was helped by a clear division and understanding of roles and responsibilities, as confirmed by the different stakeholders. At the start of partners’ on-boarding, a small training was held with the focal persons from the partners’ end to clarify the expectations of UN Women from them, such as weekly updates, quarterly reporting, budget approvals, etc. This helped in having a precise and clear understanding of roles and responsibilities. Furthermore, the frequent coordination between partners in the field avoided overlap in activities.

Finding 7: The projects built on UN Women’s previous initiatives and their lessons learned, which resulted in constant improvements. However, a weak national coordination arrangement for gender-based violence response did not support optimal use of the project's models and successes.

At the national level, building on other national initiatives or other donor-supported projects is a challenge due to a weak coordination by the government. Although synergies and task forces were built between organizations to coordinate efforts, for instance through the gender-based violence task force, duplication of efforts remained a substantial issue. This also affects funding that, instead of being directed towards two similar services, could be channelled to other complementary ones.

Another point raised by various respondents was the overreliance on external funding and the competition over funding, especially at the national or local organizations’ level. Both practices put the protection projects (and NGOs’ projects in general) in a state of constant precariousness. In this sense, receiving funding for different projects offering similar services in a common geographical target area becomes even more problematic.

In this context, although UN Women took into consideration previous experience and lessons to inform the design of these projects, strengthening the project coherence and synergies, the existing limitations of the overall gender-based violence response system did not support an optimal use of the project models and successes. The stakeholders interviewed stated that given the limited involvement of the government to address gender-based violence issue despite repeated efforts by the NGOs to invite ministries to the instituted task forces, UN Women along with other UN institutions should have exerted more pressure on the Lebanese government to change its way of dealing with gender-based violence, while also increasing cooperation between the NGOs.  According to them, the referral networks of the NGOs at the regional levels were playing an important role in complementing the work needed at protection level, yet there was a huge need – and gap in that sense – for the state to collect nationwide data, regulate the services, oversee their quality, and start delivering them through qualified public workers. In this regard, even though the projects concerned met the protection needs of the target beneficiaries, its successful intervention models could not be scaled-up to cover the entirety of needs in Lebanon.

## Efficiency

Finding 8: Despite some constraints in resources and restrictions caused by the health and economic situation, the projects were managed in a cost-efficient manner.

Two projects run by UN Women and its partners were mostly cost-efficient, and the teams were able to complete the activities on time using the available resources. For UN Women, the challenge lied mainly in the human resources, given the conjunction of the small size of the team and the high number of projects (besides the projects under study). UN Women staff had to work extra hours on the projects to ensure an on-time delivery since none of the staff was allocated full-time work on the projects.

For partners, the evaluation found that the overhead costs were sufficient and the partners’ professionalism, experience and diligence in work allowed them to manage the resources adequately. UN Women had four implementing partners. Care International Lebanon allocated seven staff to the project, as did Safadi Foundation and KAFA, while ABAAD allocated five staff. The implementing partners were supported by UN Women through the provision of follow-up, the display of a flexible attitude in adapting to challenges and the sharing of expertise. This last component mainly translated in the provision of guidance, based on UN Women’s extensive experience in the domain of gender equality that allowed the organization to advise on best practices and strategies. The support provided by UN Women was confirmed by a partner staff who said:

“[UN Women] are so understanding, they follow-up a lot, they provide a huge support, and guide us throughout the project, such as periodic reports.”

In addition, a regular monitoring of the budget took place. The total budget for both projects was of 636,563 USD, divided between 449,819 USD for the “Addressing Economic and Protection Challenges faced by Women and Girls (refugees and host community nationals) in Lebanon’s Host Communities and Country” project, and 186,744 USD for the “Crisis Response: Supporting Women Protection and Economic Recovery Lebanon”. A review of the financial documents and the narrative reports happened on a quarterly basis, according to a UN Women staff. In some instances, budget adaptations occurred – upon need and as per the partner’s request – mainly as a result of the COVID-19 pandemic, where the expenses originally dedicated to in-person meetings and conferences (such as premises rental, coffee breaks, etc.) were redirected to the purchase of recharge cards, offered to beneficiaries, that would allow them to keep attending the project activities. However, these adaptations were minor and did not have a serious negative affect on the components of the budget.

The donor reporting (submitted to the Government of Japan) was always done on time. Under both projects, an interim report and a final report were submitted. For the project “Addressing Economic and Protection Challenges faced by Women and Girls (refugees and host community nationals) in Lebanon’s Host Communities and Country”, an interim report was submitted on 31/12/2020 and a final report on 31/12/2021. As for the project “Crisis Response: Supporting Women Protection and Economic Recovery Lebanon”, an interim report was submitted on 31/12/2021, and a final report is expected to be submitted on 31/09/2022. UN Women and its partners did not receive any negative feedback from the donors on their good-quality reports.

The constraints faced by the projects were external in nature and originated mainly from the health and economic situation. Beside the COVID-19 pandemic, which affected the efficient implementation of some activities, logistical issues related to the economic crisis, such as the challenges with money withdrawal or conversion, delayed the implementation but only to short amounts of time.

## Emerging Impact

Finding 9: The projects had an overwhelmingly positive impact on beneficiaries’ lives, which manifested at the psychological, emotional and social levels.

The impact of the projects on beneficiaries’ lives has been prevalently positive, according to evaluation data. As evident from the CATI data, nearly 40 percent of surveyed beneficiary reported they felt supported by people and network; 28 percent reported an improvement in their knowledge regarding their right to have a violence free life, and 13 percent reported they felt safer.

Source: CATI Surveys total sample – 150 Female Beneficiaries

The positive change in beneficiaries’ lives happened at different levels, the first one relating to the psychology and mindset of the women. An increase in confidence, development of independence and a stronger character were reported. This reflected on the ability of beneficiaries to solve problems, “stand up for themselves” as expressed by one of the focus group respondents and withstand societal pressure (“not being afraid of people’s opinions”, in the words of a beneficiary).

A second aspect reported to have improved due to the projects’ interventions was the emotional composition of the women. Beneficiaries said that they were able to forge an emotional regulation ability that helped them to control their behaviour in case of negative emotions, and to adopt strategies to cope with stress and deal with anxiety.

Finally, a recurrent third positive aspect was the social contact women built through these projects, the support they felt through the sharing of experiences and emotions, and the safety given by the space (whether physical or virtual) created in the projects. Through their participation, women became aware of having resources and, most importantly, options. Based on this, some made the commitment to enact change in their lives, and prepared action plans for this purpose.

A UN Women staff summarized the positive impact brought by the projects on beneficiaries’ lives by saying that “women now have a more meaningful life”. Data from the monitoring interviews using the Women’s economic empowerment monitoring of quality protection services, conducted with beneficiaries of services provided by KAFA, validated this, where most of the women interviewed (20 out of 22) described the life-changing role that KAFA played in their lives, allowing them to transform from weak, abused, dependent women to empowered, strong, independent women.

Finding 10: While most of the impact was positive, the programme brought to the surface the importance of employing a more holistic approach, wherein risks associated with such programming could be proactively identified and addressed. At the family level, the projects yielded a substantial improvement in the relationship of the beneficiaries with their children, but this was not the case with their spouses. This highlights the importance of using the socio-ecological model to devise interventions that look beyond the individual level and incorporate important elements such as family relationships.

The impact on beneficiaries’ families was not homogeneous. None of the beneficiaries reported an improvement of their relationship with their partner; on the contrary, a number of women talked about the worsening of their marital situation. On the other hand, the impact on the beneficiaries’ relationships with their children was highly positive. The evaluation data highlighted the substantial difference the project made on the relationship of beneficiaries with their children, and on their knowledge about and perception of child raising. The examples mostly illustrated women learning to listen to their children and to be more flexible with them.

For instance, one beneficiary said:

“I was able to listen to my daughter and her problems and give her advice and solutions. I learned from these sessions how to deal with my children.”

Another one added:

“Before I came here, and because of the stress I was living in, I used to hit my daughter sometimes, and was so strict. But now it is different because they taught me here how to handle my children and how to communicate with them.”

In discussing the changes adopted in their children’s raising, FGD participants indicated that they were trying to focus on their daughters and transmit the learning they were acquiring about women’s rights to their daughters, to build their knowledge and strength. Similarly, they also indicated that they were teaching gender equality to their sons as well, raising their awareness about women’s and girls’ rights and encouraging them to treat their mothers and sisters with respect.

These findings highlighted the importance of working on the gender socio-ecological model to devise interventions that investigate social norms and family relationships while offering services related to protection from gender-based violence. The socio-ecological model starts from the individual level, where girls and women’s skills are strengthened in the objective of giving them agency and empowering them. At the same time, to reach full empowerment, women need to be surrounded by a supportive family, community, and legal framework. The family is the most immediate circle and the first necessary supporting actor in the emancipation of women, but it also needs to be embedded in an environment where social norms and laws are favourable to women. For this purpose, working on the interpersonal (family) level and the community level are crucial in the empowerment journey. The involvement of men and boys is of particular importance as they are present and have a strong influence at all levels of the socio-ecological model. Consequently, protection interventions needed to consider the family dynamics and the prevailing social norms and act on them in their empowerment responses. This is discussed further in depth in other parts of the report.

“My children were abused outside the house, but after the awareness sessions I was able to know how to deal with this. I learned that there are different organizations that can help in those cases. We also learned about who to trust and not trust. We also learned that if a problem happened between the husband and wife, the children should be out of this.”

– Focus Group Participant

Another area reported by the beneficiaries that needed attention was related to their expectations of the legal process that did not correspond to the reality of their protection journey. Some of them expected the legal process to be quick and easy but, they were not. Therefore, according to them, preparing women for such challenges in advance would be helpful so that they are relatively prepared for the challenging journey. At the same time, some beneficiaries who accessed the legal counselling without considering other essential services like the psychosocial support reported that they ended not benefiting fully from the project because they did not focus on building their emotional regulation and decision-making abilities. The surveyed beneficiaries also requested to advocate for faster divorce procedures and to prepare the beneficiaries for the time needed for legal assistance. A few respondents also highlighted that mediation with family members after a divorce, additional sessions of psychotherapy and a more hands on legal support could be useful in their situations.

Some women also reported that the projects were not fully equipped to respond to the needs of women who needed immediate financial support besides the protection support (e.g., rent payment, medicine, etc.) as the projects were not devised to respond to such imminent financial needs. Few suggestions were shared regarding the improvement of the projects’ impact, in an indication that both staff and beneficiaries were prevalently satisfied with the outcomes. However, among the propositions for improvement, cash assistance – mainly under the form of unconditional cash, but also cash for work – ranked in the first place, mostly requested by beneficiaries but endorsed by implementing partners as well. The need for financial assistance stems from the situation of economic crisis, which the livelihood component does not always succeed at alleviating. Beneficiaries mentioned being in need of assistance for their children’s education and for rebuilding homes destroyed by the Beirut Blast, for instance.

Another area of improvement was regarding transportation. While partially connected to the financial question, given soaring transportation costs due to the economic crisis, the issue also related to distances, and to the absence of partner Centers in peripheral regions of the country. Some beneficiaries noted the logistical difficulty that commuting to Beirut poses to them and demanded having Centers in different locations in Lebanon.

Finally, some important elements of improvement although exogenous and beyond UN Women and partners’ control yet advocating for them would be essential for a better impact of protection projects in general. These were related to the need for gender-based violence-related data, currently lacking at the national level, and a gender responsive legal framework, which currently remains highly unfavourable for women.

## Sustainability

Finding 11 Although evidence of sustainability was limited due to the projects’ short-term, different elements suggested that sustainability principles and approaches were embedded in the project implementation. UN Women and its implementing partners devised a series of measures to enable sustainability post-projects. At the national level, the collaboration with government and funding were the two key steps to achieve sustainability in protection projects.

The projects had a short-term duration, therefore, evidence of the sustainability of results could not be directly detected; however, several points indicated that the sustainability principles and approaches were embedded in the project implementation and its results could be ensured beyond the end of the projects’ duration:

- The provision of knowledge in awareness sessions (e.g., about women’s legal rights): according to the stakeholders consulted, the informative activities were a powerful tool that guaranteed results’ sustainability because the knowledge gained remained with women and were also being transmitted to their children. Once women had acquired knowledge about their rights, they started to act upon it to access and improve their protection.

- Having women beneficiaries who volunteer in community-based groups established by the implementing partners: some implementing partners established community-based groups to spread awareness about protection to a bigger number of women. Beneficiaries from the project generally volunteered in these groups, which ensured the sustainability of projects results among the beneficiaries themselves, and by extending them to new groups of women.

- Putting into practice learned protection strategies: during the projects, many beneficiaries succeeded at implementing strategies they learned during psychosocial support sessions, especially the ones concerning emotional regulation, like coping with stress and anxiety. This transition from theory to practice can be seen as a proof that the acquired skills and habits can continue to be sustainable in the long term, after the end of the project.

In addition, UN Women and its implementing partners devised various measures and strategies to help their beneficiaries on this journey and to ensure sustainability after the end of the projects. The following measures were cited by UN Women staff and implementing partners:

- Establishing referral systems and help lines to ensure that beneficiaries are informed of and can resort to in case of any emerging needs after the end of the projects.

- Building the capacity of MoSA and local entities, such as security forces, municipalities, to play an active role in the protection of women, e.g., through training on referrals and referral modalities, mediation skills, etc.

For UN Women specifically, an important strategy that was employed, consisted of being flexible with project partners in such a way that allowed them to shape their own sustainability. This was generally done by engage in a brainstorming exercise with the implementing partners, at the design phase, about ways to render the project sustainable after the end of the funding from UN Women. At times is also involved allocating a part of budget to the implementing partners to use after the end of the project to continue or conclude essential activities.

Beyond the specific projects under study, the evaluation recorded a series of advice around building sustainability of protection projects in general. The most suggested measure was the collaboration with the government to bring sustainability to a national level, as previously outlined in Section 6.1. In that optic, an interviewed expert talked about the necessity of “shifting from a humanitarian response to a development portfolio”, which also includes a need to focus on rural areas.

As covered under Section 6.1, inclusion of men in protection projects, having men as partners rather than opponents had a potential to sustain the results of the programme.

Finally, one of the stakeholders argued that sustainability required having a multitude of national providers such as small CSOs working on local levels, rather than larger international NGOs, which do not have the same deep reach. This will ensure the spread of sustainability across the national territory and to all communities. However, for the suggestion itself to be sustainable, the CSOs should have access to a variety of donors that can guarantee a continuous stream of funds, as opposed to be competing over a restricted number of funds.

Funding is indeed a crucial element for sustainability. The funding issue was also present in the talks about the sustainability of the teams of UN Women’s implementing partners. Indeed, for most projects, the teams were contracted for are short-term, and the work continuity was often tied to a continuous search for new funding opportunities. Even UN Women Ending Violence Against Women staff were not allocated full-time for the projects. Sustaining project results was connected to the retention of the staff expertise in the organizations offering the services, thus a debate about the sustainability of funding lies at the heart of the overall sustainability question.

## Human Rights & Gender Equality

Finding 12: In all phases of the projects, UN Women and its implementing partners made sure to properly capture and address beneficiaries’ needs, through feedback, discussions, and referrals.  However, the interventions were limited in gender transformation since their scope did not include direct work on addressing the root causes of gender-based violence.

The project design was carried out by UN Women internal experts and implementing partners, given their expertise on gender equality issues and their in-depth knowledge about UN Women’s economic empowerment ToC. However, the interventions were limited in gender transformation since their scope did not include direct work on addressing the root causes of gender-based violence. This said, the projects did not follow a particular set of policies and procedures to bring forth gender transformative changes and protect human rights, apart from the SOPs designed jointly by Care International Lebanon and ABAAD to help ensure the consistency and quality of their project.

In 2022 UN Women started training its partners on prevention of sexual exploitation and abuse (PSEA) and encouraged them to adopt PSEA minimum requirements. UN Women also worked on developing a capacity building action plan for each implementing partner based on the capacity assessment done for the partner at the start of every project.

Respondents from UN Women expressed that the protection interventions itself contributed to making women feel safer, which catalysed a set of gender transformative changes, such as increased mental health, wellbeing and an ability to work and be economically empowered.

“Protection interventions make women safer, and when women are safe, they are better able to participate in society, care for their families, and more likely to have better mental health. That is how we are contributing to gender equality. We keep women safe and we improve their wellbeing, then they are able to be better participants in society.” – UN Women Staff

During both the design and implementation phases, UN Women and its implementing partners worked to make sure that the needs of the different beneficiary groups were captured and properly addressed in the intervention. In the design period, UN Women team performed an evaluation of its implementing partners to ensure the presence of a diversified team that would be able to connect with beneficiaries from different backgrounds, and the commitment of the team to principles of gender equality and human rights.

Moving to the implementation, evaluation data included examples of modalities in which beneficiaries’ needs were captured:

- Through discussion: during awareness or support sessions, the implementing partners’ staff acted as facilitators, without imposing ideas. The objective was to allow the beneficiaries to understand the key message themselves, in a way that that the message would reflect the beneficiaries’ own priorities and needs.

- Through referrals: during the implementation of activities, the implementing partners’ staff at times noticed the presence of other urgent needs for beneficiaries. Often, these needs regarded basic assistance, shelter or WASH. Referrals were then performed by implementing partners’ staff to other relevant organizations to help the beneficiaries with urgent cases.

Overall, the evaluation noted that the projects were gender responsive, addressing the rights of women to a safe and dignified life but were limited in gender transformation since its scope did not include direct work on addressing the root causes of gender-based violence.

Finding 13: The project, especially from the implementing partners’ side, did not succeed well at extending protection services to people with disability, because they were not well equipped to deal with disability cases.

For certain women, the gender-based violence they face is aggravated by their disability status which renders access to protection services harder. Most of the stakeholders consulted (implementing partner organizations and staff from external NGOs alike) confirmed that they lacked the needed resources to deal with disability cases. First, few organizations had equipped premises that could receive people with disabilities. Those who did, had to deal with the electricity cut-out problem (caused by the economic crisis) that hinders the use of elevators, essential for the mobility of some people with disabilities. In general, transportation itself was hard for people with disabilities in Lebanon and remained challenging even if the organizations tried to manage it, because of a lack of financial means. Second, the gap in human resources constituted another major obstacle to offering an appropriate service to people with disabilities. Few organizations had personnel in their teams that were equipped to deal with specific cases like disabilities, and the teams in general did not receive trainings to prepare them for this task. Finally, funding also represented an issue in this regard, as organizations did not have access to specific funds allocated to adequately equip premises or train their staff.

# Conclusions, Lessons Learned and Recommendations

The conclusions, lessons learned, and recommendations build on the findings of the evaluation, and take into account stakeholders’ perspectives on the improvement of the different project components. Recommendations are divided by level of priority to advise on the most urgent actions to take to tackle protection needs and improve protection projects.

## Conclusions

- The projects were highly relevant to beneficiaries’ needs and had responded adequately to their protection and psychosocial needs. The evaluated projects were successful because the implementing partners had expertise in gender equality and were able to ensure that gender equality and human rights principles were upheld during the project. The implementing partners also had a deep knowledge of the field – in the case of this project, they captured the importance of considering the emerging financial and basic needs imposed by the current multi-faceted crisis context in Lebanon and to include them in the project response. The projects underwent some adaptations following the COVID-19 pandemic and the Beirut port explosion including a shift to an online delivery modality approach.

[Finding 1 and 12]

- The projects’ way of dealing with the COVID-19 pandemic showed that it is always preferable for protection interventions to be conducted face-to-face, when possible, as visual contact and body language are important elements in the interactions with beneficiaries. Nevertheless, the remote delivery modality could also present certain advantages for protection projects, mainly by allowing to connect with “harder-to-reach" women (e.g., women who live far away from Centers or women who are unable to leave the house).

[Finding 5]

- While having achieved the desired results, the projects’ design missed out on the potential to engage men. Engaging men in protection initiatives can improve projects’ results and sustainability. Men are often the other party in gender-based violence cases, therefore, their level of cooperation with – or opposition to – the woman’s empowerment journey can have a substantial effect on protection projects’ short-term and long-term outcomes. On a similar axis, protection projects can generate positive effects that can extend to women’s children – such as increased awareness, character building and an improved relationship with the mothers. These effects can materialize better if taken into account in the design of the projects.

[Findings 3, 9, 10 and 12]

- The psychosocial support interventions and the legal counselling came across as the most effective components of the projects as the victims of domestic violence not only needed psychosocial support, but also legal assistance to end the cycle of violence. However, the context of limited involvement of the Lebanese government, and a weak national coordination arrangement for gender-based violence response, did not support an optimal use of the projects models and successes.

[Findings 2 and 7]

- The psychosocial support and legal counselling activities appear to be cornerstones of the evaluated UN Women’s projects and of protection projects in general, as they contribute the most to providing women with a positive mindset and solutions to their situations. These activities yield the best results if implemented in parallel, as beneficiaries need to be emotionally and psychologically prepared to face the long and challenging legal journey out of gender-based violence.

[Findings 2 & 9]

- Significant efforts were made towards sustainability of the evaluated interventions. The projects however missed on the inclusion of men and on having clearer exit plans, in addition to being short-term, which does not allow for a thorough observation and evaluation of the projects’ sustainability – women’s recovery process included. At the national level, sustainability requires parallel work at the macro and micro levels. At the macro level, a shift to a development perspective, with the involvement of the government, is needed. From a micro perspective, ensuring sustainability demands an intensified work at the local level, having access to diverse funding sources and the inclusion of different components such as mental health and Psychosocial Support Service sessions, awareness sessions, and the complementarity with the livelihood components, all of which have long-term results

[Findings 3, 4, 11]

- The provision of protection services to people with disabilities is still weak, suffering from both infrastructure and skills/expertise difficulties. Substantial efforts and access to funding are needed to render protection services more inclusive in general and for people with disabilities in particular.

[Based on Finding 13]

## Lessons Learned

- While tackling a specific component that is the gender-based violence, protection projects cannot be dissociated from the context they operate in and need to take into account other potential needs such as financial needs that might be emerging under the project’s circumstances. Fulfilling, or contributing to fulfil the external needs is important to keep protection at the forefront, otherwise beneficiaries' risk to relegate it to secondary places in their attempt to secure their other needs.

[ Finding 1 and Conclusion 1]

- Protection projects are adaptable. Depending on the desired objective – whether it is to reach more “hard to reach” beneficiaries, expand the project’s activities or reach women under movement restrictions – the projects can broaden their set of tools by including digital platforms that allow them to conduct part of their activities virtually. The decisions though should be based on an evaluation of the real impact on the beneficiary, and whether it can replace the benefit drawn from a face-to-face implementation.

[Finding 5 and Conclusion 2]

- The extension of protection projects’ duration increases the effectiveness of their results and improves their outcomes. Having longer-term projects allows to better monitor and work on beneficiaries’ recovery and on the project’s sustainability of results in which exit plans, the involvement of men and the psychosocial follow-up of beneficiaries are important elements.

[Findings 3, 4, 9, 11 and Conclusions 3, 5 & 6]

- When designing protection projects, consideration of the positive spill over effects on beneficiaries’ children or direct family is important to use those to build a prevention component within the intervention modalities.

[ Finding 10 and Conclusion 3]

- Collective work through building synergies between NGOs working in the protection domain, and of advocacy campaigns for the change of the legal national framework, and for pressuring the government to increase its contribution to the protection sector are essential to address the protection needs effectively. Collective action is all the more important in the current context where protection needs are growing and cannot be addressed effectively and efficiently through individual work.

[Findings 7, 11 and Conclusions 4, 7]

- The protection sector needs to constantly review its performance and seek to enlarge and improve its services to include all categories in need, especially women with disability.

[Finding 14 and Conclusion 8]

## Recommendations

The recommendations were drafted following a participatory approach wherein the evaluation recommendations were drafted based on a discussion with the project stakeholders considering their experience in the protection sector.  In addition, a validation workshop and inputs from the Evaluation Reference Group (ERG), were also taken to develop more meaningful and actionable recommendations.

| High-Priority Recommendations | Recommendation | Relevant Stakeholders | Referenced Findings, Conclusions & Lessons Learned |
| --- | --- | --- | --- |
|  | - The projects should address the urgent financial needs of the beneficiaries. It should therefore include a cash component – unconditional cash or cash for work – in all current and near-future protection projects, to accommodate beneficiaries’ urgent financial needs. The cash component can last as long as the economic crisis persists or until UN Women might deem appropriate. | UN Women, partner organizations and NGOs working on protection in general | Finding 1 Conclusion 1 Lesson Learned 1 |
|  | - The project should integrate psychiatrists in protection projects and/or in the staff of organizations working on gender-based violence in general to respond to the needs of beneficiaries having dire mental health problems. | UN Women, partner organizations and NGOs working on protection in general | Finding 1 Conclusion 1 Lesson Learned 1 |
|  | - The project should work on the interpersonal level of the gender socio-ecological model, by raising the awareness of and empowering the beneficiaries’ direct environment. This applies to the beneficiaries’ children, but especially to the male figures in their family – husband, brother, etc. The work on the interpersonal level can happen by devising specific activities for members of women’s direct environment in the protection projects – i.e., for men, stress management sessions or awareness sessions about women’s rights – to be implemented in parallel to the activities targeting women. | UN Women, partner organizations and NGOs working on protection in general | Findings 3, 9, 10 Conclusions 3 & 6 Lessons Learned 3 & 4 |
|  | - The project should continue to advocate for changing the legal framework to render it in line with gender equality principles and push for the application or reinforcement of laws and policies that protect women and girls from gender-based violence. | UN Women, government? partner organizations and NGOs working on protection in general. | Findings 7 & 10 Conclusions 4 & 7 Lesson Learned 5 |
| Medium-Priority Recommendations | Recommendation | Relevant Stakeholders |  |
|  | - Design longer-term projects to allow for more time to fully respond to beneficiaries’ protection needs, and better shape the recovery and sustainability aspects. Develop a sustainability/exit strategy as a part of the programme design, implement and monitor. | UN Women, Donors | Findings 1, 3, 4, 9, 10 Conclusions 1, 3 & 6 Lesson learned 3 |
|  | - Use advocacy to mainstream gender-based violence aspects into the projects of partners working in the livelihood sector. UN Women is in a strong position to use the advocacy tool, given that it is chairing the Gender Working Group and the LGBTIQ+ Task Force, and co-chairing the Child Protection and Sexual and gender-based violence sector under the Emergency Response Plan (ERP). | UN Women, partner organizations, NGOs working on protection in general and governmental entities | Findings 2, 3, 7, 10 & 11 Conclusions 3, 4 & 7 Lessons Learned 4 & 5 |
| Low-Priority Recommendations | Recommendation | Relevant Stakeholders |  |
|  | - Include beneficiaries in the design of the project, through consultations with women from the targeted communities, to include community perspectives and increase community ownership of the projects. The community involvement can be extended for the duration of the project by having volunteers or remunerated women form a community-based steering committee whose task would be to meet at regular intervals for the duration of the project, monitor its status and give advice from the community perspective to include in the implementation. | UN Women and partner organizations | Finding 1 Conclusion 1 Lesson Learned 1 |
|  | - Following the experience acquired from the implementation of remote delivery due to the COVID-19 pandemic, use online interventions in parallel to face-to-face interventions to extend protection projects to harder-to-reach categories, such as women living in remote areas or adolescent girls confined at home and in need of awareness sessions. | UN Women, partner organizations and NGOs working on protection in general | Finding 5 Conclusion 2 Lesson Learned 2 |

In addition to the above recommendations, UN Women staff and implementing partners staff also presented recommendations geared specifically towards the inclusiveness of individuals with disabilities in protection programmes.

| General Recommendations | Inclusiveness of Individual with Disabilities | Relevant Stakeholders |  |
| --- | --- | --- | --- |
|  | Mainstream disability into protection projects. This can be done by: - visiting people with disability in their place of living, if feasible, or in the centers that host them, and implementing protection activities such as awareness sessions or case management in these locations. - Equipping SDCs for people with disabilities and using these spaces for protection activities. - Reaching people with disabilities through online platforms. - Instituting partnerships with NGOs that specifically work with people with disabilities and implementing a mutual coaching: organizations working on gender-based violence receive coaching on how to be more disability-sensitive, and organizations working with people with disabilities receive a coaching on how to integrate protection or case management in their services. | UN Women, its partner organizations and NGOs working on protection in general | Finding 13, Conclusion 8 and Lesson Learned 6. |

# Annex 1: Evaluation TOR

| EVAW Evaluation Consultant - Lebanese Nationality ONLY |  |
| --- | --- |
| Advertised on behalf of : |  |
| Location : | Beirut, LEBANON |
| Application Deadline : | 26-Oct-21 (Midnight New York, USA) |
| Type of Contract : | Individual Contract |
| Post Level : | National Consultant |
| Languages Required : | Arabic English |
| Starting Date : (date when the selected candidate is expected to start) | 01-Nov-2021 |
| Duration of Initial Contract : | 40 days within 5 months |
| Expected Duration of Assignment : | 5 months |
| UNDP is committed to achieving workforce diversity in terms of gender, nationality and culture. Individuals from minority groups, indigenous groups and persons with disabilities are equally encouraged to apply. All applications will be treated with the strictest confidence. UNDP does not tolerate sexual exploitation and abuse, any kind of harassment, including sexual harassment, and discrimination. All selected candidates will, therefore, undergo rigorous reference and background checks. |  |

Background

Background: UN Women, grounded in the vision of equality enshrined in the Charter of the United Nations, works for the elimination of discrimination against women and girls; the empowerment of women; and the achievement of equality between women and men as partners and beneficiaries of development, human rights, humanitarian action and peace and security. Placing women’s rights at the center of all its efforts, UN Women leads and coordinates United Nations system in Lebanon efforts to ensure that commitments on gender equality and gender mainstreaming translate into action throughout the world. It provides strong and coherent leadership in support of Member States’ priorities and efforts, building effective partnerships with civil society and other relevant actors. Lebanon’s current financial and political crises, the impact of the global COVID-19 pandemic, and the harrowing Beirut Port explosion (4 August 2020), has made for a challenging operational environment. These overwhelming and devastating conditions across the country have made Lebanese and Syrian women as well as women from different nationalities living in the country to negative coping strategies affecting their ability to negotiate equal treatment, rights and protections from violence. UN Women works to empower diverse women and girls in Lebanon, at micro, meso, and macro levels. Since 2016, UN Women established its office presence in Lebanon, the Women’s Economic Empowerment (WEE) programme has predominantly focused on increasing the resilience of vulnerable women and girls in Lebanon through the provision of the economic opportunities and improving their access to protection services from violence. UN Women, in partnership with local actors providing protection services, has been supporting vulnerable women and women at increased risk of sexual and gender-based violence . The protection pillar focuses on enhancing women’s safe access to critical protection related services for their full and effective participation in public life, including civil registration, essential services for the survivors of violence against women (VAW), self-defense training. Due to a rise in the rate of abuse and an increase in the cases of domestic violence as well as an increase in the need for protection of vulnerable women, UN Women is planning to offer multi-pronged approach to strengthening Lebanon’s protection response through scaling up direct services, increasing the capacity of government social development Centers (SDCs) and protection actors across the humanitarian sector, and scaling-up information and outreach to women, with a focus in hard-to-reach areas. Scaling-up protection services is urgently needed to meet the growing protection needs in the country. Women and girls will be targeted with different types of protection services, such as gender-based violence case management, legal counseling and legal representation, mental health services and psychological assistance services. Over the last decade, there has been significant investment in studying and improving protection services for women and girls. However, there remains an information gap on protection and gender-based violence trends of women and girls with disabilities and how to best meet their needs; particularly in response to the recent crisis: pandemic, Beirut explosion and economic crisis. UN Women is looking for a consultant to conduct an evaluation to assess the extent to which the protection services have achieved (or lack thereof) intended results and/or unintended results regarding improved response to violence against women and an increased sense of safety. Financial portfolio of the programme: The project to be evaluated is funded by the government of Japan, the overall project amount is 786,909 USD, out of which 154,000 USD are dedicated to the protection services in 2021/2022 and are to be evaluated under this ToR, along with a past intervention on protection conducted in 2020/2021 for an amount of 400,000 USD. The protection component of 2021/2022 is implemented with KAFA (a women led/ women’s rights organization specialist in protection), and last year protection component was implemented with CARE international (an INGO) in partnership with ABAAD (a women led/ women’s rights organization specialist in protection). Donor profile: Since 2011 the Government of Japan has been championing UN Women’s resilience and recovery response project, ‘Women’s Leadership, Empowerment, Access and Protection in Crisis Response’ (LEAP) to support women’s resilience as a strategy for community resilience in a crisis context. In Lebanon, UN Women has been receiving funding from the Government of Japan since 2015. The projects aimed at responding to the impact of the Syria crisis through the empowerment of vulnerable women and girls. Theory of Change: In all its livelihood programming, UN Women links its livelihoods interventions with the provision of proper protection information, awareness and referrals when needed to the targeted women. The overall theory of change of the WEE programme at UN Women in Lebanon is as follow: “If women are well equipped with market-based skills and resources, If women are supported in accessing the local labour market If women are provided with information and access to protection services and practical skills on self-protection Then there will be a more protective and enabling environment for women’s economic participation Then women will be more resilient amidst the economic crisis and protected refugee crisis because women will be more engaged in public life and better able to access decent work.” Logical framework and alignment to UN Women’s AWP and SN: The below project output is to be evaluated and the full logical framework can be found in Annex A. Output 1.4: Women and girls are more protected and more aware of different types of possible protection interventions (including PSS, PSEA, GENDER-BASED VIOLENCE case management, legal aid, gender-based violence awareness, first aid, and referral services through government SDC spaces and women’s centers) Activities: 1.4.1. Provide protection services and awareness raising for women and girls affected by the Blast and the economic crisis including case management, mental health, PSEA and psychosocial support (MHPSS) services, gender-based violence, and comprehensive legal assistance, including legal representation 1.4.2. Rehabilitate two social development centers to become safe spaces Indicators: # of women and girls reached through protection services and awareness raising. Baseline: 0. Target: 500 beneficiaries # of SDCs rehabilitated. Baseline: 0. Target: 2 The programme’s contribution towards UN Women CO Strategic note, UN Women Strategic Plan as well as its contribution towards (or alignment with) the international, regional and national treaties or conventions The project component we are looking to evaluate is directly linked to the theory of change that was developed in support of the development results of UNW strategic plan (2018-2021), outcome 4 that states the following: “Outcome 4: All women and girls live a life free from all forms of violence”. This project also aligns with the below output from UN Women Lebanon’s 2021 Annual Work Plan: Impact 2: SP Outcome 3: Women have income security, decent work, and economic autonomy Outcome 2.3: National authorities, private sector and CSOs are engaged in and actively support gender equality and women’s economic empowerment and protection Output 2.3.5: Women and girls are supported with essential protection services, including to respond to increased needs as a result of the Covid-19 epidemic. Partners: NGO partners: CARE International Lebanon is an international humanitarian and development agency with a strong technical expertise in gender and gender-based violence. UN Women partnered with them to deliver protection services in Lebanon under the Japan project 2020/2021. ABAAD is a nation women’s rights organization with a mandate to achieve gender equality and women’s empowerment. Under the project (2020/2021), CARE and UN Women are building the capacity of ABAAD in order to strengthen national ownership of the protection response and service delivery. KAFA (enough) Violence & Exploitation is a Lebanese civil, non-governmental, non-profit, feminist, and secular organization seeking to create a society that is free of social, economic, and legal patriarchal structures that discriminate against women. UN Women partnered with them to deliver protection services in Lebanon under the Japan project 2021/2022. Government partners: Ministry of Social Affairs (MOSA) is the leading governmental agency to oversee the implementation of the Lebanon Crisis Response Plan. UN Women is working to support the delivery of protection services through MOSA-managed Social Development Centers across the country.

Duties and Responsibilities

Purpose of the Evaluation The evaluation aims to support UN Women Lebanon’s strategic learning, and decision-making and positioning for future work and programming on the protection intervention of the WEE programme in Lebanon. The evaluation will follow a participatory approach that will include consultations with beneficiaries and key stakeholders, including the Ministry of Social Affairs and key NGO partners. The evaluation will draw lessons learned and recommendations for future work and programming on the protection component of the WEE programming in Lebanon. The evaluation will also have a forward looking or formative focus and will aim to provide key recommendations for the implementation and scaling up opportunities of future work, based on the lessons learned identified through this evaluation and will also provide forward looking recommendation on the roles of all key stakeholders to ensure linkages and mutual synergies of the different stakeholders. The main users of the evaluation are UN Women Lebanon Country Office and project stakeholders, who will use the finding of the evaluation to feed into the new planning cycle for the next period and in formulating new WEE programming in Lebanon. The evaluation has the following specific objectives: - Provide a detailed assessment of the extent to which the protection services achieved their intended results in line with the past and ongoing project’s results indicators - Identify and validate lessons learned, promising practices and innovations of protection work supported by WEE Programme within the context of the aid effectiveness agenda. - Provide actionable recommendations with respect to the development of the protection component of the next WEE’s programme. - Support the UN Women CO to improve its strategic positioning to better support the achievement of sustained gender equality and EVAW. Scope of the Evaluation: The selected consultant will evaluate the protection components of two UN Women projects funded by Japan (2020/2021 and 2021/2022), with focus on lessons and evidence of the achieved outputs and activities. The geographical scope of the evaluation will focus on the project three implementation areas (Beirut, Akkar and Tripoli). The evaluation will reach out to all principal stakeholders, i.e. the NGOs implementing the protection intervention (KAFA, Care International and ABAAD), the Ministry of Social Affairs, and other stakeholders working on protection in Lebanon, including international and national NGO’s. The evaluation will reach out to women, girls, benefiting from the services provided under this component. The evaluation will include a stakeholder analysis map. The evaluation should specifically look at how the project adapted its activities to the COVID-19 pandemic and evaluate the online awareness raising session and services provision. Limitations: The COVID-19 pandemic as well as the current fuel crisis might restrict travel and in-person interviews and focus group discussions. Therefore, some of the meetings will need to be hold online. However, if meeting will be organized online, the evaluator will need to take into consideration the lack of stable internet connection. Furthermore, in case beneficiaries need to join online meetings, they will need to be supported with internet bundles. The evaluation needs to take this into account and plan for a methodology that uses innovative tools for engaging with the different stakeholders. Evaluation criteria and Key Questions: Questions under OCDE/DAC evaluation criteria, including relevance, effectiveness, efficiency, coherence as well as sustainability will be answered by the evaluation. Considering the mandates to incorporate human rights and gender equality in all its work and the UN Women Evaluation Policy, which promotes the integration of women’s rights and gender equality principles, one of the key criteria and related questions will be around the Gender Equality and Human Rights perspectives At inception stage, the evaluation expert is expected to develop an evaluation matrix summarizing key questions, indicators, sources of information and methodology to guide the analysis and triangulation. Final evaluation matrix will be validated by the evaluation management group. The below questions will be refined by the consultant in the evaluation matrix. Relevance: - To what extent did the projects reach out and respond to the needs and priorities of the beneficiaries? - To what extent was the design and implementation strategy and approaches relevant to the needs and priorities in Lebanon? Effectiveness - To what extent did the project increase the protection and awareness of the targeted women? - What were the main successes of the project interventions? - What are the limiting factors that might hinder the achievement of the intended results and what needs to be done to overcome these limiting factors? - How effective was the online interventions that replaced the face-to-face interventions during COVID? Efficiency - To what extent did UN Women’s allocated resources (human and financial) enable the effective implementation of the project interventions? - What is UN Women’s comparative advantage for the implementation of protection services in Lebanon? - What improvement in resources, institutional setup and arrangements is required for the efficient implementation and the achievement of results? Coherence - To what extent were the project interventions coherent with UN Women’s Theory of Change? - To what extent were the project interventions coherent with interventions with similar objectives of other stakeholders? Sustainability - To what extent did the project interventions contribute to the creation of sustainable results (both on the individual and the institutional level) Human rights & Gender Equality - To what extent was the human rights-based approach and gender equality incorporated in the design and implementation? - To what extent has UN Women been able to address the challenges in addressing gender equality within the framework of the project? Evaluation Ethics and Norms: The evaluation is to be conducted in line with UNEG Norms and Standards for evaluation, the UNEG Code of Conduct for Evaluations in the UN System, UN Women evaluation guidelines including Evaluation Policy[1], GERAAS evaluation report quality checklist[2], and the UN Women “How To Manage Gender-Responsive Evaluation” handbook[3]. The evaluation shall also be guided by the UN Women Pocket tool for managing gender responsive evaluation during Covid 19. [1] https://www.unwomen.org/en/digital-library/publications/2012/10/evaluation-policy-of-the-united-nations-entity-for-gender-equality-and-the-empowerment-of-women [2] https://www.unwomen.org/-/media/headquarters/attachments/sections/about%20us/evaluation/evaluation-geraas-guidance-en.pdf?la=en&vs=408 [3] https://www.unwomen.org/en/digital-library/publications/2015/4/un-women-evaluation-handbook-how-to-manage-gender-responsive-evaluation Evaluation Methodology: This will be a utilization focused evaluation and the evaluation methodology will deploy mixed methods. This should include quantitative and qualitative data collection methods and gender and human rights based analytical approaches to ensure participatory, inclusiveness processes as described below: A theory-based approach and contribution analysis methodology will be followed for the evaluation. Thus, the existing Theory of Change (ToC) will be examined to gain an understanding of the conditions that affect results, to identify those strategies that are effective and to collect information that helped adaptation or lack thereof. In case the desired results did not materialize, the evaluation should ascertain whether this was because of programme design, implementation or external factors beyond the control of the programme. The ToC may be reconstructed to elaborate on the objectives and articulation of the assumptions that stakeholders use to explain the change process represented by the change framework that the Action Plan considered. Document reviews, content analysis, online or onsite Interviews and focus group discussions with all key stakeholders involved in the project implementation, including but not limited to UN Women team, local and international NGO partners, target beneficiaries, government partners, etc. will also take place. Interested bidders are requested to include in their proposal the best possible approach from a methodological standpoint. Evaluation Management and Phases: The evaluation will be a consultative, inclusive, and participatory process and will include a twofold management structure consists of an Evaluation Steering Committee, an Evaluation Management Group and Evaluation Reference Group. UN Women will form an Evaluation Management Group (EMG) to support the Evaluation Task Manager (ETM) who will lead the day-to-day management of the process. The management group is constituted to oversee the evaluation management, make key decisions and quality assure the different deliverables. Under the overall guidance of the EMG and the Evaluation Task Manager (ETM), the evaluation will be carried out by an external consultant recruited by UN women for this specific evaluation. The planning and coordination analyst at UN Women Lebanon office, will be the ETM and the evaluation consultant will report directly to the ETM. The consultant will be responsible for all logistics (office space, administrative and secretarial support, telecommunications, printing documentation, travel. etc) and the development and dissemination of methodological tools. ERG - In order to facilitate a comprehensive review of the evaluation products and to ensure the participation of key stakeholders in the evaluation, UN Women will establish an Evaluation Reference Group comprising of UN Women Staff, key humanitarian stakeholders in Lebanon, duty bearers and right holders. The reference group is an integral part of the evaluation management structure and is constituted to facilitate the participation of relevant stakeholders in the design and scope of the evaluation, raising awareness of the different information needs, quality assurance throughout the process and in disseminating the evaluation results. An evaluation Steering Committee, ESC, will be established as the key accountable body that will ultimately endorse the evaluation report and will be responsible for the development of an evaluation Management Response (MR) to address the recommendations included in the report. The specific functions of the ESC will include the following: - Be informed by EMG during the entire evaluation process. - Revise and endorse the different evaluation deliverables: inception report and final evaluation report. - Lead in the development of the evaluation Management Response (MR) in coordination with relevant staff. Endorse the MR, which will be made publicly available in the UN Women Global Accountability and Tracking of Evaluation (GATE) system. The phases of the evaluation will be as follow: - Inception phase: Develop the methodology in consultation with WEE team. - Data collection and analysis: Desk review of relevant documents. Interviews with the stakeholders, including UN Women staff and partners (government, UN, civil society, academic), beneficiaries and donors. Learning sessions for the UN Women office. - Reporting phase: Analyze data, draft evaluation and learning report, host closing learning session (open to externals outside of UN Women, as identified by UN Women). Deliverables: Deliverables; Timelines (expected overlapping deliverables). Draft Inception Report; November 31, 2021. Final Inception Report; December 15, 2021. Provide a stakeholder analysis map; January 15, 2022. Preliminary findings presentation and validation workshop; February 28, 2022. Draft Evaluation Report; March 15, 2022. Final Evaluation Report[1], Evaluation brief and a final evaluation PPT; March 30, 2022. [1] The Evaluation Report shall follow the structure detailed in the UN Women Evaluation Handbook (Box 18 Outline of Evaluation Report)

Competencies

Core Values - Respect for Diversity. - Integrity. - Professionalism. Core Competencies - Awareness and Sensitivity Regarding Gender Issues. - Accountability. - Creative Problem Solving. - Effective Communication. - Inclusive Collaboration. - Stakeholder Engagement. - Leading by Example. Functional Competencies - Proven ability to monitor and document GENDER-BASED VIOLENCE/SGENDER-BASED VIOLENCE, with an understanding of gender-specific protection concerns, and experience interviewing vulnerable witnesses; - Experience undertaking corporate learning exercises and evaluations; - Strong communication and negotiation skills; - Excellent analytical capacity; - Strong Knowledge in witness and victim protection and data protection; - Ability to speak and write in a clear and gender-sensitive language; - Ability to lead development of clear strategies and to provide strategic advice to senior management; - Ability to communicate effectively both in written and oral.

Required Skills and Experience

Education: - Master’s degree in International Affairs/Development, Sociology, Law, Gender and Women’s Studies, and/or with strong knowledge of gender issues, or related discipline. - A first-level university degree in combination with two additional years of qualifying experience may be accepted in lieu of the advanced university degree. - PHD is an asset. Experience: - Minimum 7 years of experience working in human rights, in particularly in the area of gender-based violence. - At least five years of prior experience of working on programs evaluations, preferably in the thematic area of gender-based violence. - Past experience of conducting gender responsive evaluations is an asset. - Track record of expertise on issues of women’s rights is an asset. - Strong expertise on organizational learning and development processes is an asset. - Solid understanding of the Lebanese context is an asset. - Exposure to country situations of political risk, crisis, or change is an asset. - Computer skills, Qualitative and quantitative software analysis skills, - Internet communication and command of MS Office. Language: - Proficiency in written and oral English and Arabic is a must. Evaluation Criteria: Consultants will be evaluated based on the following methodology: Only candidates obtaining a minimum of 49 points in the technical evaluation would be considered for the financial evaluation. Criteria Weight Technical: 70% (70 points) Criteria 1: Education: (20 points) Criteria 2: Minimum 7 years of experience working in human rights, in particularly in the area of gender-based violence: (30 points) Criteria 3: Prior experience working on programs evaluations (20 points) Financial: Lowest Financial Proposal: 30% (30 points) The points for the Financial Proposal will be allocated as per the following formula: - Contract will be awarded to the technically qualified consultant who obtains the highest combined score (financial and technical). - The points for the Financial Proposal will be allocated as per the following formula: (Lowest Bid Offered*)/ (Bid of the Consultant) x 30. - 'Lowest Bid Offered' refers to the lowest price offered by Offerors scoring at least 49 points in the technical evaluation. Application: Interested individuals must submit the following documents/information to demonstrate their qualifications: - A cover letter explaining your suitability for the work and previous work portfolio, and ability to meet the requirements, method of engagement based on but not mutually exclusive to the above recommended methodology and tools and other relevant information. - UN Women Personal History form (P-11) which can be downloaded from http://www.unwomen.org/about-us/employment; - Personal CV; and financial proposal; Proposed inclusive daily and lump-sum rate, which should include all costs associated with data collection and analysis. The above-mentioned documents should be submitted together, incomplete submission can be a ground for disqualification. At UN Women, we are committed to creating a diverse and inclusive environment of mutual respect. UN Women recruits, employs, trains, compensates, and promotes regardless of race, religion, color, sex, gender identity, sexual orientation, age, ability, national origin, or any other basis covered by appropriate law. All employment is decided on the basis of qualifications, competence, integrity and organizational need. If you need any reasonable accommodation to support your participation in the recruitment and selection process, please include this information in your application. UN Women has a zero-tolerance policy on conduct that is incompatible with the aims and objectives of the United Nations and UN Women, including sexual exploitation and abuse, sexual harassment, abuse of authority and discrimination. All selected candidates will be expected to adhere to UN Women’s policies and procedures and the standards of conduct expected of UN Women personnel and will therefore undergo rigorous reference and background checks. (Background checks will include the verification of academic credential(s) and employment history. Selected candidates may be required to provide additional information to conduct a background check.) Annex 1 Statement; Indicator; Means of Verification; Frequency; Baseline; Target. Goal: To provide and support to women affected by Lebanon's crisis (economic crisis, those impacted by COVID-19 and the Syria crisis), and their families to recover and to contribute to broader economig growth. - Reduced economic vulnerability of women, particularly for those in unstable employment - Improved response to violence against women and an increased sense of safety; Gender-sensitive resilience Index; UN Women team will lead the survey; Twice (Baseline and Endline surveys); TBD; (20% increase calculated from the 120 benificiaries). Outcome I; Economically vulnerable women - Lebanese and Syrian refugees - urgently access, livelihood opportunities and essential protection services to support them in recovering from the impact of the Beirut blast, COVID-19, the Syria crisis and Lebanon's economic crisis. Output 1.1; Areas of interventions of the project are assessed on the level of the markets needs to better inform the implementation.. Activity 1.1.1; In coordination with the Ministry of Social Affairs, hire a consultant or consulting firm to conduct a market assessment on the job markets in the target areas with specific focus on potential opportunities for women; # of market studies completed; Assessment/Analysis Report; Annual; 0; 1. Output 1.2; vulnerable women are capacitated and Provided with skills development and cash for work opportunities.; % of women who completed the skill development training with UN Women improve their self-confidence; pre/post training assessments; Annual; 0; 85%. % of women who completed the skill development training with UN Women increase their skills and knowledge; pre/post training assessments; Annual; 0; 80%. % of women who completed the job placement programme with UN Women continue earning income after the end of the programme; pre/post training assessments; Annual; 0; 20%. Activity 1.2.1; Provide women with training for jobs in priority sectors identified in the market analysis; likely focus on health and care economy sectors (elderly & childcare); # of women who have acquired new technical skills (60% Lebanese: 40% Syrians); RP quarterly report; Quarterly; 0; 120. Activity 1.2.2; Support women to generate income through 3 months cash for work and/or job placement opportunities for the production of social goods and commodities in support of local communities; # of women who enrolled in cash for work and/or job placement project for income generation (60% Lebanese: 40% Syrians); RP quarterly report; Quarterly; 0; 120. Output 1.3; 2 women led cooperatives are supported to revive and expand their business. Activity 1.3.1; Provide business development services and networking to two female-led cooperatives to support them in expanding their businesses; # of female led cooperatives supported to retain or expand their business; RP quarterly report; Quarterly; 0; 2. Output 1.4; women and girls are more protected and more aware of different types of possible protection interventions (including PSS, PSEA, GENDER-BASED VIOLENCE case management, legal aid, GENDER-BASED VIOLENCE awareness, first aid, and referral services through government SDC spaces and women’s centers); % of women who received the protection services or awareness raising feel safer; Assessment/Analysis Report; Annual; 0; 75%. Activity 1.4.1; Provide protection services and awareness raising for women and girls affected by the Blast and the economic crisis including case management, mental health, PSEA and psychosocial support (MHPSS) services, GENDER-BASED VIOLENCE, and comprehensive legal assistance, including legal representation.; # of women and girls reached through protection and awareness raising services (60% Lebanese: 40% Syrians); RP quarterly report; Quarterly; 0; 500. Activity 1.4.2; Rehabilitate two social development centers to become safe spaces; # of SDCs rehabilitated; Monitoring visit report; Annual; 0; 2. Outcome II; National economic actors developing recovery-focused macroeconomic policies, as well as the private sector, prioritize women’s engagement in Lebanon’s economic recovery.. Output 2.1; stimulus and recovery efforts are supported to address the needs of women and girls, through conducting gender sensitive assessment of recovery economic packages and policies.. Activity 2.1.1; Provide technical assistance and analysis to national economic actors (e.g. government, UN, World Bank) on the Blast response recovery and reconstruction package; # of joint reports generated recovery and reconstruction; Reports; Biannual; 0; 2. Activity 2.1.2; Advocate for gender sensitive recovery of the business environment; # of gender-responsive changes integrated into recovery and reconstructions plans and policies; Assessment/Analysis Report; Annual; 0; 2. Output 2.2; Engage the private sector to enact family friendly policies and to establish and strengthen gender-sensitive policies through utilizing the Women’s Empowerment Principles (WEPs).. Activity 2.2.1; Approach new enterprises to help them assess gender gaps within their enterprises and join the WEPs; # of new enterprises that join WEPS as signatories for gender equality.; Quarterly report; Quarterly; 0; 5. Activity 2.2.2; Support the enterprises that become signatories of WEPs to develop/revise their policies to be more family friendly and responsive to women’s needs for economic participation and gender equality; # of WEPS signatories that adopt new/revised gender sensitive policies/regulations; Assessment/Analysis Report; Annual; 0; 2.

# Annex 2: List of documents consulted

Project Related Documents:

- Documents of CARE (project partner from the 2020-2021 Japan project)

- Documents of KAFA (project partner from the 2021-2022 Japan project)

- ProDoc and Narrative Reports of the Japan project 2020-2021

- ProDoc and Narrative Report of the Japan project 2021-2022

Guidance and tools on gender-responsive evaluations:

- GERAAS - UN Women Global Evaluation Report Assessment and Analysis System (GERAAS)

- Pocket Tool for managing evaluation during COVID-19– based on the COVID-19 situation (with travel vs. without travel / remote data collection)- https://www.unwomen.org/en/digital-library/publications/2020/05/pocket-tool-for-managing-evaluation-during-the-covid-19-pandemic

- The UN Women Evaluation Handbook: How to manage gender-responsive evaluation

- UN Women branding guidelines for evaluation

# Annex 3: List of Key Informant Interviews

|  | Category | Name of Organization/Entity | Title |
| --- | --- | --- | --- |
| 1 | UN Women Staff | UN Women | Programme Manager |
| 2 | UN Women Staff | UN Women | Gender and Humanitarian Specialist |
| 3 | UN Women Staff | UN Women | Project Coordinator |
| 4 | UN Women Partners | Care International Lebanon | Director of Programme Implementation |
| 5 | UN Women Partners | Care International Lebanon | Project Officer |
| 6 | UN Women Partners | ABAAD | Deputy Director |
| 7 | UN Women Partners | ABAAD | Senior Complementation Coordinator |
| 8 | UN Women Partners | KAFA | Project Coordinator |
| 9 | UN Women Partners | KAFA | Support Center Supervisor |
| 10 | INGOs/NGOs/ Experts | Plan International | Programme Director |
| 11 | INGOs/NGOs/ Experts | Heartland Alliance | Programme Coordinator |
| 12 | INGOs/NGOs/ Experts | RDFL | President |
| 13 | INGOs/NGOs/ Experts | LECORVAW | Project Manager |
| 14 | INGOs/NGOs/ Experts | UNICEF | Child Protection Officer (GENDER-BASED VIOLENCE) |
| 15 | INGOs/NGOs/ Experts | MOSA/ LCRP Protection | National protection coordinator |

# Annex 4: Research Tools

Key Informant Interviews

Discussion Guide – UN Women Staff

Introduction:

Thank you very much for setting aside time to talk with me today.

Project Introduction: My name is ________ and I work as an evaluation expert who has been contracted by UN Women. I will be asking you some questions regarding your reflections, feedback and recommendations for the protection services provided under the WEE programme and funded by Japan (Interventions 2020/2021 and 2021/2022), in addition to the relevance, efficiency, effectiveness, impact and sustainability of the project. You were selected for this interview because you were involved in the project as a key stakeholder. However, it is not mandatory to answer all the questions in the discussion guide.

Interview Timeframe and Procedure: The conversation will take up to 1 hour.

Permission to Record: If you don’t mind, I would like to record our conversation. This allows us at a later stage to listen to the conversation and transcribe the information you provided us with during the meeting. I would like to assure you that no one outside of our team will have access to these recordings. Once the study is finalized, we will delete them.

Your answers will be used for data analysis purposes only and will be kept strictly confidential. No interview respondents will be identified by name in the report.

BEGIN RECORDING, if consent was explicitly granted: Before we begin, do you have any questions?

Background

- Please tell me briefly how long have you been working with UN Women, and what is your current role?

- In what ways have you been involved in these interventions? With whom were you in contact and for what? (Note to interviewer: please probe by entities: Governmental, donors, public-oriented institutions, implementing partners, etc.)

Relevance

- How were the needs/gaps of women and girls affected by the Blast and the economic crisis identified at first (sources of data used, assessment conducted, etc.)? How did they feed into the design of this project? What measures were taken to ensure alignment with objectives and needs?

- Given the timing of this project – emergence of COVID-19 worldwide and succession of crises in Lebanon - were there any major changes in the needs throughout the course of the project interventions from 2020 till date? Has the project design remained relevant to those needs despite changes?

- Were any adaptations to project or activity design made to respond to any changes? What were they and why?

- Do you think that these changes were able to respond to changing needs?

Effectiveness

- Did the project achievements increase the protection and awareness of the targeted women? How? From your experience, which of the following components was perceived as most needed: case management, mental health, PSEA and psychosocial support (MHPSS) services, GENDER-BASED VIOLENCE, and comprehensive legal assistance, including legal representation

- How effectively did the achievement of the results address women’s urgent protection needs? How effectively will they be able to recover as a result of these interventions?

- What were the specific needs met through each service/ activity provided? Please give concrete examples

- What was the result of each service/ activity provided? Please give concrete examples

- What kind of changes you noticed/ or foresee in the lives of beneficiaries as a result of those services?

- To what extent do you believe the services provided were the "right thing to do”? What was the MOST and LEAST effective in each and why?

- Were there any activities that you struggled to implement throughout the course of the project? What were the reasons for these difficulties? And how were you able to overcome them?

- How effective was the online interventions that replaced the face-to-face interventions during COVID?

- How has the relationship been between UN Women and all the other stakeholders involved in the project?

- Who are the stakeholders you engaged with and how?

- Did you face any challenges when working with any of these stakeholders?

- How frequent were your interactions with each of these stakeholders?

- Were there any delays in the planning and implementation of the project caused by any of these stakeholders?

- How clear was the understanding of roles and responsibilities and division of labour between project’s staff and implementing partners/ contractors? If you were to change any detail for better results, what would that be and why?

Efficiency

- Was the project managed in a cost-efficient manner (in terms of human, financial and other resources versus the results)?

- How did you track your spending?

- Were initial financial forecasts accurate? Did they have to be adapted?

- Did you have enough people and time to complete all activities as planned?

- Were resources and expertise shared among involved parties?

- What were the external constraints to achieving better efficiency and how well were they mitigated?

- How could the efficiency of the project be improved?

Coherence

- Are the project strategies and structures/ framework followed coherent and logical?

- What are the logical correlations between the overall objective, outcomes and outputs vis-a-vis the UN Women WEE programme Theory of Change (ToC)?

- To what extent were the project’s intended outcomes realistic?

- From a design perspective, how well does the project complement and build on other previous projects? Which projects you examined and what kind of info you took from them?

Impact

- In your opinion, what are the positive and negative changes in the beneficiaries’ lives caused by the project? Can you give examples

- Who were the most impacted (positively and negatively) by the interventions? And why do you say so? Note to interviewer: please prove into different profiling backgrounds of beneficiaries: marital status, having children, religious affiliations, level of vulnerability, place of residence, females with disabilities, educational background, etc.)

- Is there any evidence of the changes before and after the interventions?

- Who were the least impacted (positively and negatively) by the interventions? Why? Note to interviewer: please prove into different profiling backgrounds of beneficiaries: marital status, having children, religious affiliations, level of vulnerability, place of residence, females with disabilities, educational background, etc.)

- How could the impact of the interventions be improved?

Sustainability

- What evidence is there to suggest the project’s interventions and/or results will be sustained after the project end? What measures were taken to guarantee the sustainability of the project?

- What were the main concerns of the different beneficiaries in terms of sustainability?

- What were the main concerns of the different team members (individuals and institutions including governmental entities) in terms of sustainability?

Human Rights & Gender Equality

- When the project was first designed, was there any consultation with gender and human rights experts? Please explain how these aspects were included in project design and procedures?

a. How the needs and priorities of different groups, particularly women and those from the most marginalized groups were captured and addressed through the different phases of the project cycle?

- How did outputs and outcomes contribute to UN Women’s mainstreamed strategies including gender equality, and human rights?

a. Did you follow any set of policies and practices to bring forth gender transformative changes and protect human rights? Please provide concrete examples.

b. How effective were those accountability systems in addressing the underlying structural gender inequalities? Note to interviewer: Please ask what kind of structural issues they are referring to and probe into details (example of issues: law and regulations, patriarchal society, social and gender norms in society, lack of proper assistance, etc.)

c. What were the challenges you faced and how were you able to overcome those challenges? Please give examples

Recommendations

- What are your recommendations regarding the interventions? What should be done differently in future projects? What are the activities that can be improved?

- What kind of actions should take place to fulfil the needs of women and girls with disabilities under similar projects?

- Based on the needs and challenges you’ve mentioned, those identified during project implementation, and those generated by the crises within the country, what are the lessons learnt? Please elaborate

Discussion Guide – Partners Staff

Introduction:

Thank you very much for setting aside time to talk with me today.

Project Introduction: My name is ________ and I work as an evaluation expert who has been contracted by UN Women. I will be asking you some questions regarding your reflections, feedback and recommendations for the protection services provided under the WEE programme and funded by Japan (Interventions 2020/2021 and 2021/2022), in addition to the relevance, efficiency, effectiveness, impact and sustainability of the project. You were selected for this interview because you were involved in the project as a key stakeholder. However, it is not mandatory to answer all the questions in the discussion guide.

Interview Timeframe and Procedure: The conversation will take up to 1 hour.

Permission to Record: If you don’t mind, I would like to record our conversation. This allows us at a later stage to listen to the conversation and transcribe the information you provided us with during the meeting. I would like to assure you that no one outside of our team will have access to these recordings. Once the study is finalized, we will delete them.

Your answers will be used for data analysis purposes only and will be kept strictly confidential. No interview respondents will be identified by name in the report.

BEGIN RECORDING, if consent was explicitly granted: Before we begin, do you have any questions?

Background

- Please tell me briefly how long have you been working with [your organization], and what is your current role?

- In what ways have you been involved in these interventions? With whom were you in contact and for what? (Note to interviewer: please probe by entities: UN Women, donor, other implementing partners, beneficiaries directly etc.)

Relevance

- In your opinion, was the project designed to properly reach out and respond to the needs of women and girls affected by the Blast and the economic crisis identified at first (sources of data used, assessment conducted, etc.)? Why do you say so?

- Given the timing of this project – emergence of COVID-19 worldwide and succession of crises in Lebanon - were there any major changes in the needs throughout the course of the project interventions from 2020 till date? Has the project design remained relevant to those needs despite changes? How? Note to interviewer: For KAFA, since their intervention started after emergence of COVID-19 and the Blast, please ask whether the project design from the beginning took into consideration those needs

- Were any adaptations to project or activity design made to respond to any changes? What were they and why?

- Do you think that these changes were able to respond to changing needs?

Effectiveness

- From your experience, did the project increase the protection and awareness of the targeted women? How? Note to interviewer: please ask to enlist the different protection services and awareness sessions provided and give a good example of achievement

- In your opinion, which project activity was the MOST and LEAST effective in fulfilling the needs of the targeted women? Why?

- How were you able to track the effectiveness of each service?

- How were you able to see the difference each service made? Did you follow any impact indicator before and after the intervention? Please give details of the different measurement, monitoring and evaluation tools you’ve utilized

- In your opinion, how could the effectiveness of the tools be improved?

- How could the effectiveness of each service be improved?

- In your opinion, will the targeted women be able to socially recover as a result of these interventions?

- Were there any activities that you struggled to implement throughout the course of the project? What were the reasons for these difficulties? And how were you able to overcome them?

- How effective was the online interventions that replaced the face-to-face interventions during COVID? Please explain

- How has the relationship been between you and UN Women? You and other stakeholders involved in the project?

- Who are the stakeholders you engaged with and how?

- Did you face any challenges when working with any of these stakeholders?

- How frequent were your interactions with each of these stakeholders?

- Were there any delays in the planning and implementation of the project caused by any of these stakeholders?

- How clear was the understanding of roles and responsibilities and division of labour between project’s staff? If you were to change any detail for better results, what would that be and why?

Efficiency

- Was the project managed in a cost-efficient manner (in terms of human, financial and other resources versus the results)? Why or why not?

- What were the external constraints to achieving better efficiency and how well were they mitigated?

- How could the efficiency of the project be improved?

Coherence

- In your opinion, are the project strategies and structures/ framework followed coherent and logical? To what extent were the project’s intended outcomes realistic?

Impact

- In your opinion, what are the positive and negative changes in the beneficiaries’ lives caused by the project? Can you give examples

- Who were the most impacted (positively and negatively) by the interventions? And why do you say so? Note to interviewer: please prove into different profiling backgrounds of beneficiaries: marital status, having children, religious affiliations, level of vulnerability, place of residence, females with disabilities, educational background, etc.)

- Is there any evidence of the changes before and after the interventions?

- Who were the least impacted (positively and negatively) by the interventions? Why? Note to interviewer: please prove into different profiling backgrounds of beneficiaries: marital status, having children, religious affiliations, level of vulnerability, place of residence, females with disabilities, educational background, etc.)

- How could the impact of the interventions be improved?

Sustainability

- What evidence is there to suggest the project’s interventions and/or results will be sustained after the project end? What measures were taken to guarantee the sustainability of the project?

- What were the main concerns of the different beneficiaries in terms of sustainability?

- What were the main concerns of your team members terms of sustainability?

- Are there any other relevant interventions conducted by UN Women from outside this project?

Human Rights & Gender Equality

- When the project was first designed, was there any consultation with gender and human rights experts? Please explain how these aspects were included in project design and procedures?

a. How the needs and priorities of different groups, particularly women and those from the most marginalized groups were captured and addressed through the different phases of the project cycle?

- How did outputs and outcomes contribute to UN Women’s mainstreamed strategies including gender equality, and human rights?

a. Did you follow any set of policies and practices to bring forth gender transformative changes and protect human rights? Please provide concrete examples.

b. How effective were those accountability systems in addressing the underlying structural gender inequalities?  Note to interviewer: Please ask what kind of structural issues they are referring to and probe into details (example of issues: law and regulations, patriarchal society, social and gender norms in society, lack of proper assistance, etc.)

c. What were the challenges you faced and how were you able to overcome those challenges? Please give examples

Recommendations

- What are your recommendations and lessons learnt regarding the interventions? What should be done differently in future projects? What are the activities that can be improved?

- What kind of actions should take place to fulfil the needs of women and girls with disabilities under similar projects?

Discussion Guide – NGOs/ INGOs/ Experts

Introduction:

Thank you very much for setting aside time to talk with me today.

Project Introduction: My name is ________ and I work as an evaluation expert who has been contracted by UN Women. I will be asking you some questions regarding protection services in Lebanon including those provided under the WEE programme. You were selected for this interview because you are involved in this sector as one of the key stakeholders. However, it is not mandatory to answer all the questions in the discussion guide.

Interview Timeframe and Procedure: The conversation will take up to 30 minutes.

Permission to Record: If you don’t mind, I would like to record our conversation. This allows us at a later stage to listen to the conversation and transcribe the information you provided us with during the meeting. I would like to assure you that no one outside of our team will have access to these recordings. Once the study is finalized, we will delete them.

Your answers will be used for data analysis purposes only and will be kept strictly confidential. No interview respondents will be identified by name in the report.

BEGIN RECORDING, if consent was explicitly granted: Before we begin, do you have any questions?

Questions

- Please tell me briefly how long have you been working with your institution, and what is your current role?

- What is the overall strategy of the institution’ protection programmes? Please briefly describe the latest protection projects/ initiatives that you carried out or currently carrying out? Please Explain details…

- In your opinion, how did the different crises in Lebanon impact women’s protection? Please explain

- What kind of protection services are currently available in the country? Please give examples

- Who are mostly targeted by those services? Why?

- Are there services specifically targeting women and girls with disabilities? If no, why not? If yes, what kind of services? Please give examples

- How would you describe the access to those services? From your experience, how easy is the access and what are the challenges?

- Are you aware of UN Women’s efforts to increase the resilience of vulnerable women and girls in Lebanon through the provision of the economic opportunities and improving their access to protection services from violence- under the Women Economic Empowerment WEE programme?

- If so, have you been directly engaged in either designing or implementing any of the activities that were related to these efforts? Please explain.

- What do you see as the major results of these efforts?

- In your opinion, do these efforts sufficiently respond to the needs and priorities you see when it comes to gender equality and responsiveness in humanitarian action?

- Going back to the different services available in the country, the ones provided by UN Women, and by other entities, do you think there are there synergies built between different stakeholders when it comes to protection services? Is there enough and clear coordination? Do you build on others’ donor-supported projects? What can be improved in this term?

- From your point of view, what are the major weaknesses and limitations of protection services previously and currently undertaken? What is the reason for limitations?

- Has the onset of COVID-19 affected these efforts? In what way and with what consequence?

- Are the results of these efforts sustainable? What needs to happen for the positive results to be sustained? What needs to happen differently.

Focus Group Discussions

Discussion Guide – Beneficiaries

Introduction + informed consent, etc. (5 minutes)

Introduction and Consent:

My name is _______, I work as a research expert specialized in conducting evaluation assessments. UN Women has currently commissioned me to conduct a study to evaluate the protection services provided under the WEE programme.

You have been asked to take part in this research study to have your feedback on the services you have received.  This will help UN Women to improve its interventions and to design programmes the most adapted to the needs of women in the community.

During the next hour, I will be asking questions. I am interested in listening to all opinions in this room, but I won’t participate personally in this discussion.

Note to moderator: Please explain the role of the person taking notes.

Benefits to the participants:

Your participation in this session will not entitle you or any woman personally to receive any aid- rather; the opinions that we will be gathering will be collectively used to develop programmes for all.

Risks:

participation is voluntary. We do not want anyone to be uncomfortable during our conversation, so if there is any question you do not wish to answer, you do not need to answer that question. You can choose to stop the discussion at any moment you wish without any problem or consequences.

Confidentiality and Privacy:

- Your privacy will be protected.

- Your name will not be used in any report that is published.

- The discussion will be kept strictly confidential. We ask you all to respect the principles of maintaining the confidentiality of each other, not to mention who said what when leaving this room. If you want to tell us about a relevant story from your community, please do not disclose the names of the persons concerned, or any details that might reveal their identities.

- Please respect each other opinions.

- The discussion will be tape recorded only if all participants agree. The recording will only be used to remind staff what you said.

- No one aside from the main researchers will have access to this data

Discussion Timeframe: The discussion will take maximum 60 minutes.

Before we begin, do you agree to take part of this study?

Questions

- Please describe the protection services you have received? From what did you exactly benefit and by whom?

Note to moderator: please ask details of each programme and try to split attendance between those who received awareness sessions and those who received the actual protection services

- How did you first know about this service? How were you able to access it?

- How effective was this service in meeting your needs? Please elaborate

  - What kind of needs you had and you expected to fulfill from this programme?

  - Was the programme successful in fulfilling those needs? Why or why not?

  - Do you think such programme is able to meet the needs of all women in your community? If no, who are the women you are thinking of and why is this service unable to meet their needs?

- Did you receive all the information you needed about this service? What about information you needed from this service?

  - If yes, can you give examples

  - If no, what kind of information you are in need and this service was lacking?

- How important was this service to you? To your family? Why do you say so?

  - What are the positive and negative changes you noticed in yourself as a result of this service? Please give examples

  - What are the positive and negative changes you noticed in the family as a result of this service? Please give examples

  - What are the positive and negative changes you noticed in the male family members in specific as a result of this service? Please give examples

- Did the services you received take into consideration the COVID-19 issues? How please explain

- Did the services you received take into consideration the economic crises the whole country is passing through? How please explain

- Do you receive any follow up from the services providers? If yes, what kind of follow up and how beneficial is that?

- Are you in need/ still in need of any specific follow up or support? Of what kind?

- What do you think of such programmes in general as a way to socially support women? Why do you say so?

- In your opinion, what can be further done to enhance the services? Please elaborate

- In your opinion, what can be further done to support you and women in your community in recovering from the impact of the Beirut blast, COVID-19, the Syria crisis and Lebanon's economic crisis?

CATI SURVEY

Profiling Information

| P1. Name |  |
| --- | --- |
| P2. Age |  |
| P3. Gender | - Female - Male |
| P4. Nationality | - Lebanese - Syrian - Palestinian - Other, specify:____ |
| P5. Place of residence |  |
| P6. Marital Status | - Single - Married with children, # children:___ - Married without children - Divorced/Separated/Widowed with children, # children:___ - Divorced/Separated/Widowed without children |
| P7. Employment Status | - Outside the labour market OR never employed - Currently unemployed - Part-time worker - Full-time worker - Retired - Other, specify____ |
| P8. Do you have any of the following difficulties? (select all that apply) | - Difficulty interacting with others - Talking - Learning - Walking - Self-care (eating, clothing…) - Seeing - Hearing - Other, specify:___ |

Assistance Evaluation:

| Q1. Which of the following services did you receive? (select all that apply) |  |
| --- | --- |
| 01 | Training for jobs (i.e. elderly and childcare) |
| 02 | Three months cash assistance for job support/ production of goods |
| 03 | Protection services (including case management, mental health, PSEA and psychosocial support (MHPSS) services, GENDER-BASED VIOLENCE, legal assistance, including legal representation) |
| 04 | Protection awareness sessions if selected: what was the topic: _______ |
| 98 | Other, please specify |

| Q2. By whom? (select all that apply) |  |
| --- | --- |
| 01 | Care International |
| 02 | ABAAD |
| 03 | KAFA |
| 04 | MOSA SDCs |
| 98 | Other, please specify |

| Q3. How did you first know about the services (select all that apply) |  |
| --- | --- |
| 01 | I received a home visit |
| 02 | I knew about the services through word of mouth |
| 03 | I usually visit the center/ I keep asking about available services |
| 98 | Other, please specify |

| Q4a. On a scale from 1 (very bad) to 5 (very good), how would you describe the contact and communications you had with project staff? Note: question repeated for each selected assistance in Q1 |  |
| --- | --- |
| 01 | Very bad |
| 02 | Bad |
| 03 | Neutral |
| 04 | Good |
| 05 | Very Good |

| Q4b. On a scale from 1 (not at all) to 5 (extremely), how professional were the staff who provided you with the service? Note: question repeated for each selected assistance in Q1 |  |
| --- | --- |
| 01 | Not at all |
| 02 | Not professional |
| 03 | Neutral |
| 04 | Professional |
| 05 | Extremely professional |

| Q4c. On a scale from 1 (not beneficial at all) to 5 (extremely beneficial), how would you describe the topics discussed in the awareness sessions? Note: question asked to those who received awareness sessions |  |
| --- | --- |
| 01 | Not at all |
| 02 | Not beneficial |
| 03 | Neutral |
| 04 | Beneficial |
| 05 | Extremely beneficial |

| Q4d. Do you know any woman in your community who was in need of this service but couldn’t access it? |  |
| --- | --- |
| 01 | Yes. If yes, who and why she/they did not access? _____________________ |
| 02 | No |

| Q5. While receiving the assistance, did you face any particular issues? |  |  |
| --- | --- | --- |
| 01 | Yes | Continue |
| 02 | No | Skip to Q6 |

| Q5a. If yes, what kind of issues? (select all that apply) |  |
| --- | --- |
| 01 | Disrespectful behaviour from staff |
| 02 | Complaints about service which were not addressed |
| 03 | Discrimination |
| 04 | Corruption |
| 98 | Other, please specify |

| Q6. Looking back at the assistance and its impact on you, is there anything that you would enhance in it? |  |  |
| --- | --- | --- |
| 01 | Yes | Continue |
| 02 | No | Skip to Q7 |

Q6a. If yes, what would that be?

| Q7. On a scale from 1 (not at all) to 5 (extremely), how satisfied are you with the relevance of the service to your needs Note: question repeated for each selected assistance in Q1 |  |
| --- | --- |
| 01 | Not at all |
| 02 | Not satisfied |
| 03 | Neutral |
| 04 | Satisfied |
| 05 | Extremely satisfied |

Q7a. Please mention one need you had prior to this service and was met when you received the service:

Need 1:

Q7b. Please mention one need you had prior to this service but was not met when you received the service:

Need 2:

| Q8a. What are the most significant changes you had in your life as a result of this service? (select all that apply) |  |
| --- | --- |
| 01 | Safety/ feeling safer |
| 02 | Improved knowledge of my rights |
| 03 | Reduced violence in my life |
| 04 | Increased financial independence |
| 05 | Increased social support networks/ feeling increasingly supported by people around me/ building trusted support networks |
| 98 | Other, please specify:________ |

| Q8b. What are the most significant changes your family had in your life as a result of this service? |  |
| --- | --- |
| 01 | Improved relationship with family members |
| 02 | Improved wellbeing of children |
| 03 | Increased safety of other family members/ or children |
| 98 | Other, please specify:_______ |

| Q9. Are you receiving any kind of follow up from the service provider? |  |
| --- | --- |
| 01 | Yes |
| 02 | No |

Q9a. What kind of follow up you are/ might be in need of?

________

Thank Respondent and End Interview

# Annex 5: Evaluation Matrix

| Question | Sub Questions | Measure(s) or Indicator(s) | Data Sources | Data Collection Method | Stakeholder/Informant | Data Analysis |
| --- | --- | --- | --- | --- | --- | --- |
| Relevance |  |  |  |  |  |  |
| the extent to which the objectives are aligned with the countries' priorities and needs, and those of beneficiaries | ∙ How were countries' needs and priorities first identified? ∙ How were beneficiaries' needs and priorities first identified? ∙ What are the sources of data used and how did they feed into the project design? ∙ Did the project design take into consideration the emerging needs amid COVID-19 and Lebanese economic crises? | •Objectives and strategy of the project support national priorities and needs | •Key Project Documents | •Desk Research | •UN Women Staff | •Qualitative analysis of strategies and reports |
|  |  | •Project activities respond to the needs and priorities of the beneficiaries | •Other pertinent documentations (statistics, previous research pieces, reports, context analyses… ) •Stakeholders | •In depth Interviews | •Partners Staff | •Qualitative data analysis of KIIs |
|  |  | •Project activities respond to the emerging needs and priorities amid COVID19 and the economic crisis |  |  | •INGOs, NGOs and Experts |  |
| Effectiveness |  |  |  |  |  |  |
| the extent to which the two interventions of the project can be said to have contributed to their overall objectives and more concretely whether the stated outputs have been produced satisfactorily | ∙ How well did the interventions meet the intended results? ∙ How effectively will project beneficiaries be able to recover as a result of the interventions? ∙ What are the women’s perceptions and satisfaction with the overall package of services/ support received? ∙ What are the challenges faced during project implementation and how did implementing partners overcome these challenges? ∙ How effective were the alternative modalities followed due to COVID-19 restrictions? ∙ How effective were the implementing partners’ monitoring evaluation tools? | •Project achievements | •Key Project Documents | •Desk Research | •UN Women Staff | •Qualitative analysis of strategies and reports |
|  |  | •Hindering factors and response to emerging needs | •Stakeholders | •In depth Interviews | •Partners Staff | •Qualitative data analysis of KIIs and FGDs |
|  |  | •Effectiveness of online modality amid COVID-19 •Effectiveness of implementing partners’ M&E tools |  | • FGDs • Surveys | •Beneficiaries | •Quantitative data analysis of surveys |
| effectiveness of management arrangements | • How effective was the communication between project stakeholders? • What were the challenges faced? • To what extent the distribution of roles and responsibilities was clear and properly followed? | •Interaction between stakeholders | •Stakeholders | •In depth Interviews | •UN Women Staff | •Qualitative data analysis of KIIs |
|  |  |  |  |  | •Partners Staff |  |
| Coherence |  |  |  |  |  |  |
| the extent to which the project design, logic, strategy and elements are/remain valid vis-à-vis problems and needs of beneficiaries | • To what extent were the project intended results realistic and valid vis-à-vis problems and needs of beneficiaries? • To what extent the project strategies and intended outcomes are coherent with UN Women WEE programme Theory of Change (ToC)? | •Strategies and structures considered coherent with UN Women ToC | •Key Project Documents | •Desk Research | •UN Women Staff | •Qualitative analysis of strategies and reports |
|  |  | •Intended outcomes are realistic and inclusive | •Stakeholders | •In depth Interviews | •Partners Staff | •Qualitative data analysis of KIIs |
| the extent to which synergies have been built with national initiatives, with other donor-supported projects as well as other thematic areas of work | • How well does the project complement and build on other previous projects? | •The project complements other UN Women and non-UN WOMEN protection projects | •Key Project Documents | •Desk Research | •UN Women Staff | •Qualitative analysis of strategies and reports |
|  |  |  | •Other pertinent documentations (statistics, previous research pieces, reports, context analyses… ) •Stakeholders | •In depth Interviews | •INGOs, NGOs and Experts | •Qualitative data analysis of KIIs |
| Efficiency |  |  |  |  |  |  |
| the extent to which the outputs achieved are derived from an efficient use of financial and human resources | ∙ How well was the project managed in a cost-efficient manner (in terms of human, financial and other resources) ∙ What were the main constraints to achieve results effectively? | •Efficiency of resources allocated to project interventions | •Key Project Documents | •Desk Research | •UN Women Staff | •Qualitative analysis of strategies and reports |
|  |  | •Needed improvements in resources, institutional setup and arrangements for higher efficiency | •Stakeholders | •In depth Interviews | •Partners Staff | •Qualitative data analysis of KIIs |
|  |  |  |  |  | •Government & Public Entities |  |

| Impact |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| the extent to which the outputs achieved have contributed to changes (positive and negative) in beneficiaries' lives as a result of the intervention | • What is the likely contribution of the project interventions to the lives of beneficiaries? What are the positive and negative changes and effects caused by the interventions? • What is the impact of services/ support received on beneficiaries and their families? • What are the propositions for increased projects impact? | •Intended outcomes are impactful | •Stakeholders | •In depth Interviews •FGDs •Surveys | •Partners Staff | •Qualitative data analysis of KIIs and FGDs |
|  |  |  |  |  | •Beneficiaries | •Quantitaitve data analysis of surveys |
| Sustainability |  |  |  |  |  |  |
| the extent to which the existing results are likely to be maintained beyond project completion | • What evidence is there that the results of interventions will be sustained after the end of the projects? • What measures were taken to guarantee the sustainability of the interventions? | •Project results at the individual and institutional level are considered sustainability potential | •Stakeholders | •In depth Interviews | •UN Women Staff | •Qualitative data analysis of KIIs |
|  |  |  |  |  | •Partners Staff |  |

| Human Rights & Gender Equality |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| the extent to which the design and project framework considered human rights and gender equality | • What is the evidence of consultation with the right holders for the programme design and procedures? • to what extent the project design considered age, gender, and ability? Whose voices are heard and whose priorities are represented or met? • How effective are the accountability systems and processes towards the affected population? • What is the evidence that the programme planned and contributed to bring forth gender transformative changes by identifying and challenging the underlying structural power imbalances and inequalities? | •Alignment with UN Women’s mainstreamed strategies including human rights-based approach and gender equality | •Stakeholders | •In depth Interviews | •UN Women Staff | •Qualitative data analysis of KIIs |

# Annex 6:  GRES Scale

| Evaluation Findings | Gender Results Effectiveness Scale |
| --- | --- |
| Finding 1: EVAW interventions responded adequately to protection and psycho-social needs amidst COVID-19 and Lebanese economic crisis, and fairly well to economic and financial needs, while being at the same time relevant to UN Women’s WEE Programme ToC | Gender Transformative |
| Finding 2: The projects fulfilled their intended objectives, with psychosocial support and legal counselling as the two most effective components | Gender Transformative |
| Finding 3: While the projects’ results were valid and realistic, the exclusion of men constituted an important limitation, in addition to the short life span of the projects. | Gender Targeted |
| Finding 4: The projects put beneficiaries on the path of recovery, but full recovery is a long-term process that depends on a multitude of factors. | Gender Responsive |
| Finding 5: Implementation challenges encountered by the projects were mostly exogenous, and mitigation strategies were employed to overcome them. The major mitigation strategy consisted of a shift to online modality due to the COVID-19 pandemic. While having brought good results, its level of effectiveness could not be equated with face-to-face implementation. | Gender Targeted |
| Finding 6: The projects were characterized by smooth communication and effective coordination between all stakeholders, with no major challenges noted, but there is scope for improvement. | Not Applicable |
| Finding 7: The projects build on UN Women’s previous initiatives and their lessons learned, which result in constant improvements. At the national level, though, the initiatives in the protection domain suffer from a lack of coordination due to a weak role of the government. Moreover, competition over funding represents a major issue. | Gender Transformative |
| Finding 8: Despite some constraints in resources and restrictions caused by the health and economic situation, the projects were managed in a cost-efficient manner. | Not Applicable |
| Finding 9: The projects had an overwhelmingly positive impact on beneficiaries’ lives, which manifested at the psychological, emotional and social levels. | Gender Transformative |
| Finding 10: At the family level, the projects yielded a substantial improvement in the relationship of the beneficiaries with their children, but this was not the case with their spouses. | Gender Transformative |
| Finding 11: Apart from exogenous improvements needed in the gender equality context in Lebanon, few improvements, mostly of financial nature, were suggested by beneficiaries. | Gender Responsive |
| Finding 12: Although evidence of sustainability is limited by the projects’ short-term, different elements suggest that it is achievable. | Gender Transformative |
| Finding 13: UN Women and its partners devised a series of measures to enable sustainability post-projects. At the national level, the collaboration with government and funding are the two key steps to achieve sustainability in protection projects. | Gender Transformative |
| Finding 14: In all phases of the projects, UN Women and its partners made sure to properly capture and address beneficiaries’ needs, through evaluations, discussions and referrals. | Gender Responsive |
| Finding 15: Disability aggravates women’s access to protection, as NGOs are generally not well equipped to deal with disability cases. | Gender Transformative |

# Annex 7:  Partners Monitoring Tools

KAFA Satisfaction Tool

استمارة تقييم الخدمات المقدمة من منظمة كفى عنف وإستغلال

يرجى البدء بقراءة الموافقة أدناه للمستفيدات ومن ثم يمكنك الحصول على موافقتهن الخطية/الشفوية قبل الشروع بالأسئلة.

مرحبا، اسمي .......... وانا أعمل في منظمة كفى عنف واستغلال. نلتقي اليوم بعد حوالي ستة أشهر منذ قدومك الى مركز الدعم. الهدف من هذه المقابلة هو تقييم خدماتنا ومعرفة المزيد عن تأثيرها على النساء المستفيدات من خدمات مركز الدعم.

قبل أن نبدأ، أريد التوضيح أن المشاركة في المقابلة طوعية. يمكنك اختيار عدم الاجابة عن كل الاسئلة أو ايقاف المقابلة اذا كنت تريدين ذلك.

سوف أطرح عليك مجموعة من الأسئلة، ليس هناك إجابة صحيحة أو خاطئة وكل ما تقولينه خلال المقابلة هو سري ولن يطلع عليه أحد خارج فريق المشروع. عندما نقوم بالابلاغ عن نتائج المقابلات، فان ما أخبرتنا به النساء لن يتم تقديمه الا بطريقة تجعل من المستحيل تحديد هوية النساء المشاركات.  لذا يرجى الإجابة بحرية وبأقصى قدر من الصدق. سوف تستغرق المقابلة ما بين 15و20 دقيقة. اذا لم يكن الوقت كافيا سوف نقوم بحجز وقت لمقابلة ثانية.

هل لديك أي أسئلة قبل أن نبدأ؟ يمكنك أيضا أن تسألي موظفينا اذا كان لديك أي أسئلة في وقت لاحق.

- يرجى ملء الجدول التالي بالمعلومات المطلوبة:

|  | الجنسية |  | العمر |
| --- | --- | --- | --- |
| - عزباء - متزوجة - مطلقة - أرملة اذا كان وضعك العائلي متزوجة أو مطلقة أو أرملة، الرجاء ذكر عمرك عند الزواج(الأول): | الوضع العائلي | - لا تجيدين القراءة والكتابة - تجيدين القراءة والكتابة - ابتدائي - متوسط/اعدادي - ثانوي - جامعي | المستوى التعليمي |
| - نعم - كلا | هل تعملين | - نعم - كلا | هل لديك أولاد |
| - نعم - كلا | هل ما زلت تستفيدين من الخدمات التي تقدمها منظمة كفى؟ |  | تاريخ بداية الحصول على الخدمات |
|  |  |  | تاريخ ملء الاستمارة |

- الرجاء وضع دائرة حول الخدمات التي حصلت/تحصلين عليها من منظمة كفى:

- ادارة حالة/ملف

- متابعة قانونية

- متابعة نفسية من معالج نفسي

- الرجاء وضع دائرة حول الانشطة التي حصلت/تحصلين عليها من منظمة كفى:

- نشاط دعم نفسي-اجتماعي (علاج درامي....)

- الانشطة التي تهدف الى التمكين الاقتصادي ( دورات لغة انكليزية، مشاغل...)

- جلسات توعية

- دورات لتعزيز المهارات الحياتية

- احالة الى خدمات أخرى، الرجاء التحديد:

- هل كان لك مشاركة تفاعلية مع مديرة الحالة في وضع خطة عمل تلبي احتياجاتك؟

- نعم،الى حد كبير          2. نعم، الى حد ما             3. قليل جدا              4. ابدا، ليس على الاطلاق

.IVa ما هي النقاط الاساسية ضمن خطة العمل؟

- هل المشاركة مدركة لخطة العمل الخاصة بها؟ (الاجابة على هذا السؤال من قبل مديرة الحالة)

- نعم،الى حد كبير        2. نعم، الى حد ما          3. قليل جدا           4. ابدا، ليس على الاطلاق

أي ملاحظات اضافية (لمديرة الحالة):  Va.

- الى اي مدى خطة العمل قد استوفت/لبت احتياجاتك؟

- الى حد كبير           2. الى حد ما            3. محايدة             4. قليل جدا                5. ليس على الاطلاق

- بشكل عام، ما مدى رضاك عن الخدمات التي تلقيتها من منظمة كفى؟

- راضية جدا            2.الى حد ما          3. محايدة         4. غير راضية بعض الشيء      5. غير راضية ابدا

VIIa. لماذا انت راضية أو غير راضية؟

- اذا كنت قد حصلت على احدى الخدمات التالية: المتابعة الاجتماعية، القانونية، أو النفسية ، الرجاء الاجابة عن الأسئلة:

| مفيدة جدا | مفيدة الى حد ما | غير مفيدة | غير مفيدة أبدا | ما هو تقييمك لخدمة المتابعة الاجتماعية (ادارة حالة/ملف) التي تلقيتها من منظمة كفى؟ |
| --- | --- | --- | --- | --- |
| مفيدة جدا | مفيدة الى حد ما | غير مفيدة | غير مفيدة أبدا | ما هو تقييمك لخدمة المتابعة القانونية التي تلقيتها من منظمة كفى؟ |
| مفيدة جدا | مفيدة الى حد ما | غير مفيدة | غير مفيدة أبدا | ما هو تقييمك لخدمة المتابعة النفسية التي تلقيتها من منظمة كفى؟ |

- هل سبق لك أن شعرت بالخوف من أن يعرف أحد معلومات عن ملفك الشخصي؟

- نعم كثيرا                         2. نعم الى حد ما                         3. كلا

| - من بين الخدمات التي حصلت عليها من منظمة كفى، ما هي الخدمة التي وجدتها الأكثر افادة؟ | - متابعة اجتماعية (ادارة حالة/ملف) - متابعة قانونية - متابعة نفسية من معالج نفسي لماذا وجدت هذه الخدمة الاكثر افادة؟ |
| --- | --- |
| - من بين الخدمات التي حصلت عليها من منظمة كفى، ما هي الخدمة التي وجدتها الأقل افادة؟ | - متابعة اجتماعية (ادارة حالة/ملف) - متابعة قانونية - متابعة نفسية من معالج نفسي لماذا وجدت هذه الخدمة الاقل افادة؟ |
| - من بين الانشطة التي حصلت عليها من منظمة كفى، ما هو النشاط الذي وجدته الأكثر افادة؟ | - نشاط دعم نفسي-اجتماعي - الانشطة والمشاغل - جلسات توعية - دورات لتعزيز المهارات الحياتية - احالة الى خدمات أخرى |

- هل انت راضية عن النتيجة التي حققتها حتى الآن؟

- راضية جدا            2.الى حد ما          3. محايدة         4. غير راضية بعض الشيء      5. غير راضية ابدا

هذا القسم مخصص للشخص المسؤول عن المقابلة من منظمة كفى:

- ملاحظات (اذا وجدت):

- عبارات مقتبسة من المشارِكة خلال المقابلة:

Pre-Post Wellbeing Survey

Wellbeing Survey

| QUESTIONS |  |  | ANSWERS |  | TECHNICAL INSTRUCTIONS |
| --- | --- | --- | --- | --- | --- |
| English |  | Arabic | English | Arabic |  |
| Hi My name is___, and I am working with ____. This survey explores a 'snapshot' of your feelings, roles in the community and SGENDER-BASED VIOLENCE related attitudes and practices, and it will be taken at the beginning and end of your participation in our project. You should feel comfortable to answer honestly according to what response is most true for you. Any information that you provide will be kept confidential. It will be used by our team to develop a greater understanding on how our intervention has impacted you. This is voluntary, and you can choose not to answer any or all of the questions. However, we hope that you will participate since the information is important for us to develop a greater understanding of women’s situation on several levels and to better support them. The survey usually takes about 10 minutes to complete. If you have any questions, please let us know. Do you accept to continue? مرحبًا ، اسمي ___ ، وأنا أعمل مع ____. يستكشف هذا الاستطلاع "لمحة" عن مشاعرك وأدوارك في المجتمع والمواقف والممارسات المتعلقة بالعنف الجنسي والجنساني ، وسيتم أخذ هذه المعلومات في بداية ونهاية مشاركتك في هذا المشروع. يجب أن تشعري بالراحة للإجابة بصدق وفقًا لنوع الاستجابة الأكثر صحة بالنسبة لك. سيتم الاحتفاظ بسرية أي معلومة تقدميها. سيتم استخدام المعلومات من قبل فريقنا فقط لتطوير فهم أكبر لكيفية تأثير هذا المشروع عليك. هذه المشاركة تطوعية ، ويمكنك اختيار عدم الإجابة على أي من الأسئلة أو كلها. ومع ذلك ، نأمل أن تشاركي بهذه الاستمارة لأن المعلومات مهمة بالنسبة لنا لتطوير فهم أكبر لحالة المرأة على عدة مستويات ودعمها بشكل أفضل. يستغرق الاستطلاع عادةً حوالي 10 دقائق لإكماله. إذا كان لديك أي أسئلة ، فيرجى إخبارنا بذلك. هل تقبلين المشاركة؟ |  |  |  |  |  |
| A. General Information |  |  |  |  |  |
| A1 | Date | التاريخ |  |  |  |
| A2 | Name (optional) / Code | الاسم أو الكود |  |  |  |
| A3 | Age | العمر |  |  |  |
| A4 | Sex | الجنس | €Male €Female | ذكر€ €أنثى |  |
| A5 | Nationality | الجنسية | €Lebanese €Syrian €PRS €PRL €Other | لبناني€ €سوري فلسطيني سوري€ €فلسطيني لبناني €غيره |  |
| A6 | Marital Status | الوضع الاجتماعي | €Single €Married €Widowed €Divorced €Separated | €أعزب/عزباء €متزوج/ة €أرملة/ة €مطلق/ة €منفصلة |  |
| A8 | Are you the head of the household? | هل أنت رب الاسرة | €Yes €No | €نعم €كلا |  |
| A9 | Educational level | المستوى التعليمي | €illiterate €Primary school €Secondary school €High school €University degree €other | €غير متعلم/ة €مستوى ابتدائي €مستوى متوسط €مستوى ثانوي €مستوى جامعي €غيره |  |
| A10 | Employment Status | الحالة الوظيفية | €Employed €Unemployed |  يعمل/تعمل عاطل عن العمل |  |
| A11 | How many times have you attended activities provided by our organization? | كم مرة حضرت الأنشطة التي قدمتها منظمتنا؟ | €Less than 2 times € 3 to 4 times € More than 5 times |  أقل من مرتين  حوالي 3 إلى 4 مرات  أكثر من 5 مرات |  |
| B. Human Insecurity Index Questions |  |  |  |  |  |
| B1 | To what extent do you fear for yourself in your daily life? | إلى أي مدى تشعرين بالخوف على حالك في حياتك اليومية | €Always €Sometimes €Never €I don’t know |  دائما  أحيانا  أبدا  لا أعرف |  |
| B2 | To what extent do you fear for your family in your daily life? | إلى أي مدى تشعرين بالخوف على عائلتك في حياتك اليومية | €Always €Sometimes €Never €I don’t know |  دائما  أحيانا  أبدا  لا أعرف |  |
| B3 | To what extent does your family feel fear for your safety? | إلى أي مدى تخشى عائلتك على أمنك الشخصي | €Always €Sometimes €Never €I don’t know €Not applicable |  دائما  أحيانا  أبدا  لا أعرف  لا ينطبق |  |
| B4 | To what extent do you worry/fear for your future and your family’s future? | إلى أي مدى تخشين على و مستقبلك و مستقبل عائلتك ؟ | €Always €Sometimes €Never €I don’t know |  دائما  أحيانا  أبدا  لا أعرف |  |
| C. Mental Health Questions |  |  |  |  |  |
| C1 | During the last week I burst into tears several times | خلال الأسبوع الماضي انفجرت في البكاء عدة مرات | €Always €Sometimes €Rarely €Never |  دائما  أحيانا  نادرًا  أبدا |  |
| C2 | During the last week I was tense and nervous | خلال الاسبوع الماضي كنت متوتر/ة | €Always €Sometimes €Rarely €Never |  دائما  أحيانا  نادرًا  أبدا |  |
| C3 | During the last week I felt lonely, sad or worried | خلال الأسبوع الماضي شعرت بالوحدة أو الحزن أو القلق | €Always €Sometimes €Rarely €Never |  دائما  أحيانا  نادرًا  أبدا |  |
| C4 | During the last week I didn’t feel like talking | خلال الأسبوع الماضي لم أشعر بالرغبة في التحدث | €Always €Sometimes €Rarely €Never |  دائما  أحيانا  نادرًا  أبدا |  |
| C5 | During the last week I was fighting for no particular reason | خلال الأسبوع الماضي كنت اتخانق من دون سبب معين | €Always €Sometimes €Rarely €Never |  دائما  أحيانا  نادرًا  أبدا |  |
| C6 | During the last week I didn’t have any hope for the future | خلال الاسبوع الماضي ما كان عندي أي أمل بالمستقبل | €Always €Sometimes €Rarely €Never |  دائما  أحيانا  نادرًا  أبدا |  |
| C7 | During the last week my sleep was interrupted because I was thinking of so many things | خلال الاسبوع الماضي كان نومي مقطش لأني عم فكّر بكتير إشيا | €Always €Sometimes €Rarely €Never |  دائما  أحيانا  نادرًا  أبدا |  |
| C8 | During the last week I was having difficulties concentrating on what I was doing | خلال الاسبوع الماضي كان عندي صعوبة ركز على الشي يللي عم أعملو | €Always €Sometimes €Rarely €Never |  دائما  أحيانا  نادرًا  أبدا |  |
| D. Community Integration Questions |  |  |  |  |  |
| D1 | My family and friends stand by me in difficult times | اصدقائي يقفون معي في الاوقات الصعبة | € A lot € Quite a bit € Somewhat € A little € Not at all |  كثيرا  الى حد ما  نوعا ما/ وسط  قليلا  أبدا |  |
| D2 | I make new friends and I spend more time socializing outside my home | أقوم بتكوين صداقات جديدة وأقضي المزيد من الوقت في التواصل الاجتماعي خارج المنزل | € A lot € Quite a bit € Somewhat € A little € Not at all |  كثيرا  الى حد ما  نوعا ما/ وسط  قليلا  أبدا |  |
| D3 | I know where to go to ask for support or help | أنا بعرف أين أذهب من أجل طلب المساعدة | € A lot € Quite a bit € Somewhat € A little € Not at all |  كثيرا  الى حد ما  نوعا ما/ وسط  قليلا  أبدا |  |
| D4 | I enjoy participating in the customs and traditions of the community in which I am living now | أستمتع بالمشاركة في عادات وتقاليد المجتمع الذي أعيش فيه الآن | € A lot € Quite a bit € Somewhat € A little € Not at all |  كثيرا  الى حد ما  نوعا ما/ وسط  قليلا  أبدا |  |
| D5 | I participate in communal events (e.g., group prayer, attending communal grouping, events, etc.) | أشارك في الأحداث المجتمعية (على سبيل المثال ، الزيارات والأحداث المجتمعية ، وحضور التجمعات المجتمعية ، والأحداث ، وما إلى ذلك) | € A lot € Quite a bit € Somewhat € A little € Not at all |  كثيرا  الى حد ما  نوعا ما/ وسط  قليلا  أبدا |  |
| D6 | I have opportunities to improve my relationship with spouse, family members, friend and others | لدي فرص لتحسين علاقتي مع الزوج وأفراد الأسرة والأصدقاء وغيرهم | € A lot € Quite a bit € Somewhat € A little € Not at all |  كثيرا  الى حد ما  نوعا ما/ وسط  قليلا  أبدا |  |
| D7 | I feel safe when I am with family/ household etc.. | أشعر بالأمان عندما أكون مع العائلة | € A lot € Quite a bit € Somewhat € A little € Not at all |  كثيرا  الى حد ما  نوعا ما/ وسط  قليلا  أبدا | KAFA intervention doesn’t target the family |
| D8 | I am aware of my own points of strength and I feel confident speaking up in community events/dialogues | أنا على دراية بنقاط قوتي الخاصة وأشعر بالثقة في التحدث في الامور اليومية / الحوارات المجتمعية | € A lot € Quite a bit € Somewhat € A little € Not at all |  كثيرا  الى حد ما  نوعا ما/ وسط  قليلا  أبدا |  |
| E. Roles in family, decision making and Support questions |  |  |  |  |  |
| E1 | Do you feel that you are allowed to have a job outside the house (employed in agriculture, private business, with government, NGOs etc.)? | هل تشعرين أنه يُسمح لك بالحصول على وظيفة خارج المنزل (موظفة في الأعمال الخاصة ، أو مع الحكومة ، أو المنظمات غير الحكومية ، إلخ) ، أو في الأنشطة التعليمية وأنشطة المهارات الحياتية؟ | € Always € Sometimes € Never € I don’t know |  دائما  أحيانا  أبدًا  لا أعرف |  |
| E2 | Do you feel you have control over your life? | هل تشعرين أنك تتحكمين في حياتك؟ | € Always € Sometimes € Never € I don’t know |  دائما  أحيانا  أبدًا  لا أعرف |  |
| E3 | Do you usually make decisions in your household? (decisions about visits to your relatives, money, education, work, voting, family disagreements etc.). | هل تتخذين قراراتك عادة في منزلك؟ (القرارات المتعلقة بزيارة أقاربك ، ادارة المال ، التعليم ، العمل ، التصويت ، الاحتلافات الأسرية ، إلخ). | € Always € Sometimes € Never € I don’t know |  دائما  أحيانا  أبدًا  لا أعرف |  |
| E4 | Do you feel supported by your family members to participate in activities such as psychosocial (life skills, counselling, activities at a women’s or a community center) | هل تشعرين بدعم من أفراد أسرتك للمشاركة في أنشطة مثل أنشطة الدعم النفسي والاجتماعي (المهارات الحياتية ، الاستشارات ، والأنشطة في مركز نسائي أو مركز مجتمعي) | € Always € Sometimes € Never € I don’t know |  دائما  أحيانا  أبدًا  لا أعرف |  |
| E5 | To what extent does your family support you to participate in economic activities (have job), or in educational and life skills activities? | إلى أي مدى تدعمك أسرتك للمشاركة في الأنشطة الاقتصادية ( مثل أن يكون لديك وظيفة) ، أو في الأنشطة التعليمية وأنشطة المهارات الحياتية؟ | € Always € Sometimes € Never € I don’t know |  دائما  أحيانا  أبدًا  لا أعرف |  |
| E6 | To what extent do you feel supported by your family members to participate in family decision making processes and in community decision making processes? | إلى أي مدى تشعرين بالدعم من قبل أفراد عائلتك للمشاركة في عمليات صنع القرار في الاسرة وفي عمليات صنع القرار في المجتمع ؟ | € Always € Sometimes € Never € I don’t know |  دائما  أحيانا  أبدًا  لا أعرف |  |
| E7 | To what extent do you feel that your family listen to your needs and your feelings are taken into consideration? | إلى أي مدى تشعرين أن عائلتك تستمع لاحتياجاتك ومشاعرك تؤخذ في الاعتبار؟ | € Always € Sometimes € Never € I don’t know |  دائما  أحيانا  أبدًا  لا أعرف |  |
| F. Comment / Feedback |  |  |  |  |  |
| F1 | Are there any thoughts or comments that you would like to share? Anything that can make the process better? هل هناك أي أفكار أو تعليقات تودين مشاركتها؟ أي شيء يمكن أن يجعل عملية التدخل أفضل؟ |  |  |  |  |
| Thank you! |  |  |  |  |  |

# Annex 8:  Project Progress Report

# Annex 9:  Project Expenditures Face forms

Kafa

Care International

World Health Organization. Global Programme on Evidence for Health Policy. (‎2001)‎. Putting women first: ethical and safety recommendations for research on domestic violence against women. World Health Organization. https://apps.who.int/iris/handle/10665/65893

Gender Alert on Covid 19 Lebanon: Access to Justice and Gender-based Violence, June 3, 2020. Issue No. 3.

Gender Alert on Covid 19 Lebanon: Women, Gender, and the Economy, May 15, 2020. Issue No. 2

European Union, UN Women. 2021. European Union Sector Specific Gender Analysis: An In-Depth Sectoral Examination of Feminist and Women’s Rights in Lebanon.

Interagency Coordination Lebanon, 2020 (https://reliefweb.int/sites/reliefweb.int/files/resources/SGENDER-BASED VIOLENCE%20TF%20Lebanon_Survey_Impact%20od%20Covid-19%20on%20GENDER-BASED VIOLENCE%20Programming.pdf), UNFPA and UN Women. 2020. (https://arabstates.unwomen.org/sites/default/files/Field%20Office%20Arab%20States/Attachments/Publications/2021/03/En_VAW%20in%20the%20Time%20of%20COVID-19_Lebanon.pdf).

Violence Against Women in the time of COVID-19. Country Brief. 2020

Impact of COVID-19 on violence against women and girls and service provision: UN Women rapid assessment and findings: https://www.unwomen.org/-/media/headquarters/attachments/sections/library/publications/2020/impact-of-covid-19-on

KAFA received 186,744 USD for protection services, (154,000 USD from Japan SB 2021/2022 and 32,744 USD from the National Committee fund), ABAAD received 43,980.64 USD from UNW HQ as a response to the Beirut blast, CARE international in partnership with ABAAD received a total of 405,838.12 USD (200,000 USD from Japan SB 2020/2021, 150,000 USD from Japan regional COVID project 2020/2021, 50,000 USD from Japan Legal reform project 2020/2021, and 5,838.12 USD from UN Women’s National Committee funds).

Resource Center for Gender Equality is a UN ECOSOC accredited organization that aims to achieve gender equality as an essential condition to sustainable social and economic development in the MENA region.

The evaluation did not look at the impact criteria holistically as this was not an impact evaluation. However, it examined and assessed the emerging impact (planned as well as unplanned, positive, and negative) that could be potentially measured through an impact evaluation.

http://www.unevaluation.org/document/detail/1616

http://www.unevaluation.org/document/detail/2866

https://www.unwomen.org/sites/default/files/Headquarters/Attachments/Sections/Library/Publications/2015/UN-Women-Evaluation-Handbook-en.pdf

http://web.undp.org/evaluation/documents/guidance/gender/GRES_English.pdf

http://www.unevaluation.org/document/detail/100

https://www.who.int/publications-detail-redirect/9789241510189

KIs with UN Women staff and implementing partners

Arab News (February 11, 2021), https://www.arabnews.com/node/1807246/middle-east

KI with an external organization’s staff

KI with an implementing partner staff

UN Women, CARE, UN ESCWA, ABAAD, UNFPA (October 28, 2020), https://reliefweb.int/sites/reliefweb.int/files/resources/Rapid%20Gender%20Analysis_August%202020%20Beirut%20Port%20Explosion_October2020.pdf

UN Women field visits, June, August, October, December

Gender-based violence in numbers – KAFA Monthly reports and data. https://kafa.org.lb/en/taxonomy/term/166

FGDs with beneficiaries

According to responses in the FGD conducted with KAFA beneficiaries, in answer to the question “How much (in %) did you benefit from KAFA services?”.

KIIs with UN and partners staff

A distribution of resources between the two components accounts to 35,900 USD for psycho-social support vs. 30,000 USD for legal representation

KII with implementing partner staff

KIs with all key stakeholders

KIs with implementing partners’ staff

KIs with UN Women and implementing partners’ staff

Ibid

WEE Monitoring of Quality Protection Service tool

KI with external organization’s staff

UN Women staff involved in the project included programme manager, programme specialist, field coordinator and programme assistant

Project Expenditures Face forms added as annexes

FGDs with beneficiaries

FGDs with beneficiaries and KIs with implementing partners’ staff

UNFPA, UNICEF, UN Women. 2020. https://www.unfpa.org/sites/default/files/resource-pdf/Technical_Note_on_Gender-Transformative_Approaches_in_the_GPECM_Phase_II_A_Summary_for_Practitioners-January-2020.pdf

KIs with UN Women and implementing partners’ staff

KIs with implementing partners’ staff

KIs with experts

KI with an external organization’s staff

Ibid

KIs with implementing partners’ staff

Currently implemented under UN Women Lebanon’s projects with LUPD and KAFA - 2022