Annex 1: Template MERP UN-Women Jordan 2013

| Title & Type of MER activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome | Relevant Country/ SRO AWP Output | Office to manage the MER activity | Country | Joint MER activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-completion) | Budget (US$) for MER activity/ Sources of Funding | Status (pending - initiated – ongoing - completed) |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1) MONITORING activities undertaken by the Country Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual Work Plans for all ongoing projects updated. | Y | UNDAF (2013-2017): Outcome 1: Jordan has undertaken political and institutional reform at national and subnational levels in a participatory, transparent and accountable manner. Outcome 2: Jordan has institutionalized improved social protection and poverty alleviation mechanisms for vulnerable people at national and sub-national levels. Outcome 4: Jordan has institutionalized necessary policies and mechanisms for effective and inclusive participation of young people in social, cultural, economic and political life. UN-Women SP MRF cluster 2: to institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation. | UN-Women Strategic Note Jordan and Syria 2012-2013: MRF2: 2.A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women Output 2.1: UN-Women programming practices reflect SMART and systematic results orientation | Jordan & Syria Country Office | Jordan | N | Jordanian universities, inta@j, Ministry of ICT and UN agencies, ZENID, UNV, Ministry of Tourism, Ministry of Information & Telecommunications, INT@J, King Abdulla II Award & 10 Private Sector participating companies.GBD (General Budget Department), JNCW(Jordan national commission for women), National Center for Human Rights (NCHR), Jordanian National Commission for Women (JNCW), Family Protection Department (FPD), Intersos, Jordanian Women Union. | First quarter. | N/A | Completed |  |  |
|  |  |  |  |  |  | N | - “Increasing Women Economic Participation in Poverty Pockets in Jordan”: UNESCO, ZENID, FDA, Friends of Environment. | 1st-31st of July 2013. | N/A | Pending | The project is expected to go through a LPAC in June 2013. |  |
|  |  |  |  |  |  | Y (with UNDP) | -“Women’s political participation” project: JNCW JWF, NFW, National Coalition, Ministry of Political Development. | 1st-30th of June 2013 | N/A | Pending | The project is part of the EU programme (Spring Forward) and there will be joint activities with UNDP. Activities are supposed to start in July 2013. |  |
| Field visits and interviews. | Y | UNDAF (2013-2017) Outcome 1: Jordan has undertaken political and institutional reform at national and subnational levels in a participatory, transparent and accountable manner. Outcome 2: Jordan has institutionalized improved social protection and poverty alleviation mechanisms for vulnerable people at national and sub-national levels. Outcome 4: Jordan has institutionalized necessary policies and mechanisms for effective and inclusive participation of young people in social, cultural, economic and political life. UN-Women SP MRF cluster 2: to institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation. | UN-Women Strategic Note Jordan and Syria 2012-2013: MRF2: 2.A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women Output 2.2: UN-Women country programme support evidence-based knowledge generation on gender equality and women’s empowerment | Jordan & Syria Country Office | Jordan | N | Universities of Jordan, ZENID, UNV, private sector (tourism/ICT), Ministry of Planning, Ministry of Finance,NCHR, JNCW, FPD, Intersos, JWU, JWF, NFW, National Coalition, Ministry of Political Development, Ministry of Tourism, GBD (General Budget Department), UNESCO, ZENID, FDA, Friends of Environment. | All year. | N/A | Ongoing | For all projects, regular meetings and field visits. |  |
| Project boards meetings for all ongoing projects. | Y | UNDAF (2013-2017) Outcome 1: Jordan has undertaken political and institutional reform at national and subnational levels in a participatory, transparent and accountable manner. Outcome 2: Jordan has institutionalized improved social protection and poverty alleviation mechanisms for vulnerable people at national and sub-national levels. Outcome 4: Jordan has institutionalized necessary policies and mechanisms for effective and inclusive participation of young people in social, cultural, economic and political life. UN-Women SP MRF cluster 2: to institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation. | UN-Women Strategic Note Jordan and Syria 2012-2013 MRF2: 2.A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women Output 2.2: UN-Women country programme support evidence-based knowledge generation on gender equality and women’s empowerment | Jordan & Syria Country Office | Jordan | N | Ministry of Education, Ministry of ITC, Jordanian universities, Jordanian universities, inta@j, Ministry of ICT and UN Agencies, Ministry of Planning, Ministry of Finance, ZENID, UNV, JNCW,GBD, programme management in HQ, NCHRH, JNCW, Intersos, Jordanian Women Union, UNESCO, ZENID, FDA, Friends of Environment, Ministry of Tourism, Ministry of Education, Jordanian universities, JNCW JWF, NFW, National Coalition, Ministry of Political Development. | 2nd quarter. | N/A | Completed | As two projects (“ Increasing Women Economic Participation in Poverty Pockets in Jordan” and “Increasing women’s political participation in Jordan” (Spring Forward)) will start their implementation in July 2013, their project board meetings are scheduled for 2014. |  |
| Reports: internal progress reports (every six months) | Y | UNDAF (2013-2017) Outcome 1: Jordan has undertaken political and institutional reform at national and subnational levels in a participatory, transparent and accountable manner. Outcome 2: Jordan has institutionalized improved social protection and poverty alleviation mechanisms for vulnerable people at national and sub-national levels. Outcome 4: Jordan has institutionalized necessary policies and mechanisms for effective and inclusive participation of young people in social, cultural, economic and political life. UN-Women SP MRF cluster 2: to institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation. | UN-Women Strategic Note Jordan and Syria 2012-2013: MRF4: Mobilization and management of Financial resources Output 4.1: Improved stewardship of resources under UN Women management at country levels | Jordan & Syria Country office | Jordan | N | Jordanian Universities, MoICT, ZENID, UNV, Ministry of Tourism, 10 private companies, GBD (General Budget Department), JNCW(Jordan national commission for women), NCHR, JNCW, FPD, Intersos, Zenid, Jordanian Women Union, UNESCO, ZENID, FDA, Friends of Environment, JNCW JWF, NFW, National Coalition, Ministry of Political Development, UNV. | 2nd quarter. | N/A | Pending |  |  |
| Financial reports for all projects on quarterly basis. | Y | UNDAF (2013-2017) Outcome 1: Jordan has undertaken political and institutional reform at national and subnational levels in a participatory, transparent and accountable manner. Outcome 2: Jordan has institutionalized improved social protection and poverty alleviation mechanisms for vulnerable people at national and sub-national levels. Outcome 4: Jordan has institutionalized necessary policies and mechanisms for effective and inclusive participation of young people in social, cultural, economic and political life. UN-Women SP MRF cluster 2: to institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation. | UN-Women Strategic Note Jordan and Syria 2012-2013: MRF4: Mobilization and management of Financial resources Output 4.1: Improved stewardship of resources under UN Women management at country levels | Jordan & Syria Country Office | Jordan | N | Jordanian Universities, MoICT, ZENID, UNV, Ministry of Tourism, 10 private companies, GBD (General Budget Department), JNCW(Jordan national commission for women), NCHR, JNCW, FPD, Intersos, Zenid, Jordanian Women Union, UNESCO, ZENID, FDA, Friends of Environment, JNCW JWF, NFW, National Coalition, Ministry of Political Development, UNV, UN-Women HQ finance unit. | Quarterly basis. | N/A | Ongoing |  |  |
| Annual reports of all projects. | Y | UNDAF (2013-2017) Outcome 1: Jordan has undertaken political and institutional reform at national and subnational levels in a participatory, transparent and accountable manner. Outcome 2: Jordan has institutionalized improved social protection and poverty alleviation mechanisms for vulnerable people at national and sub-national levels. Outcome 4: Jordan has institutionalized necessary policies and mechanisms for effective and inclusive participation of young people in social, cultural, economic and political life. UN-Women SP MRF cluster 2: to institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation. | UN-Women Strategic Note Jordan and Syria 2012-2013 MRF4: Mobilization and management of Financial resources Output 4.1: Improved stewardship of resources under UN Women management at country levels | Jordan & Syria Country Office | Jordan | N | NCHR, JNCW, FPD, Ministry of Tourism, Ministry of Political Development, ZENID, Ministry of ICT, Ministry of Education, Jordanian universities, GBD (General Budget Department), JNCW(Jordan national commission for women), Friends of the environment, UNESCO, UNV. | 4th quarter. | N/A | Pending |  |  |
| Updating Atlas management tool with risks and issue logs (all projects). | Y | UNDAF (2013-2017) Outcome 1: Jordan has undertaken political and institutional reform at national and subnational levels in a participatory, transparent and accountable manner. Outcome 2: Jordan has institutionalized improved social protection and poverty alleviation mechanisms for vulnerable people at national and sub-national levels. Outcome 4: Jordan has institutionalized necessary policies and mechanisms for effective and inclusive participation of young people in social, cultural, economic and political life. UN-Women SP MRF cluster 2: to institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation. | UN-Women Strategic Note 2012-2013 Jordan and Syria: MRF 3:Improved organizational effectiveness with a focus on a robust capacity and efficient Output 3.2:Operations reflect a culture of risk management , oversight and accountability | Jordan & Syria Country Office | Jordan | N | N/A | Throughout the year. | N/A | Ongoing |  |  |
| Data collection for all projects to establish further baselines. | N | UNDAF (2013-2017) Outcome 4: Jordan has institutionalized necessary policies and mechanisms for effective and inclusive participation of young people in social, cultural, economic and political life. UN-Women SP MRF cluster 2: to institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation. | UN-Women Strategic Note Jordan and Syria 2012-2013: MRF2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women. Output 2.1: UN-Women programming practices reflect SMART and systematic results orientation | Jordan & Syria Country Office | Jordan | Y | Jordanian Universities, MoICT, ZENID, UNV, Ministry of Tourism, 10 private companies, GBD (General Budget Department), JNCW(Jordan national commission for women), NCHR, JNCW, FPD, Intersos, Zenid, Jordanian Women Union, UNESCO, ZENID, FDA, Friends of Environment, JNCW JWF, NFW, National Coalition, Ministry of Political Development, UNV, Research Center – ICT partners. | Throughout the year | N/A | Ongoing |  |  |
| Lessons learned log updated for all projects. | Y | UNDAF (2013-2017) Outcome 1: Jordan has undertaken political and institutional reform at national and subnational levels in a participatory, transparent and accountable manner. Outcome 2: Jordan has institutionalized improved social protection and poverty alleviation mechanisms for vulnerable people at national and sub-national levels. Outcome 4: Jordan has institutionalized necessary policies and mechanisms for effective and inclusive participation of young people in social, cultural, economic and political life. UN-Women SP MRF cluster 2: to institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation. | UN-Women Strategic Note 2012-2013 Jordan and Syria: MRF 3:Improved organizational effectiveness with a focus on a robust capacity and efficient Output 3.2:Operations reflect a culture of risk management , oversight and accountability | Jordan & Syria Country Office | Jordan | N | N/A | Throughout the year. | N/A | Ongoing | The log will be included in the annual reports. |  |
| Performance Monitoring Framework (PMF) updated for all projects. | Y | UNDAF (2013-2017) Outcome 1: Jordan has undertaken political and institutional reform at national and subnational levels in a participatory, transparent and accountable manner. Outcome 2: Jordan has institutionalized improved social protection and poverty alleviation mechanisms for vulnerable people at national and sub-national levels. Outcome 4: Jordan has institutionalized necessary policies and mechanisms for effective and inclusive participation of young people in social, cultural, economic and political life. UN-Women SP MRF cluster 2: to institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation. | UN-Women Strategic Note 2012-2013 Jordan and Syria: MRF 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women Output 2.1: UN-Women programming practices reflect SMART and systematic results orientation | Jordan/Syria Country Office | Jordan | N | N/A | Throughout the year. | N/A | Ongoing |  |  |
| 2a) EVALUATIONS managed by the Country Office e.g. outcome, thematic, programme evaluations etc. Since the Country Office became operational in early 2013, all evaluations of UN-Women’s projects in Jordan and Syria will be conducted in 2014. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2b) Other EVALUATIONS in which Country Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors etc. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3) RESEARCH Activities undertaken by the Country Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |  |

# Annex 2: Evaluation Justification Matrix

N/A.

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |