UN-Women Brazil Country Office

Monitoring and Research Plan 2014-2016

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Collect baseline data for Strategic Note | UN-Women CO staff | January 2014 | Core | 5,000 |
| Monthly programme monitoring meetings | UN-Women CO staff | Every last Friday of the month until 2016 | --- | --- |
| Monthly operational reports | UN-Women ACRO | Every 5th day of the month until 2016 | --- | --- |
| Quarterly programme reports | UN-Women ACRO | Every 5th day of April, July, October and January until 2016 | --- | --- |
| Six-monthly update of the Indicator Tracking Tool | UN-Women ACRO | Every January and July until 2016 | --- | --- |
| UN-Women CO annual reports | UN-Women ACRO | Every December until 2016 | --- | --- |
| UNDAF Mid-term review | UNCT | October-December 2014 | --- | --- |
| Final report to Avon Institute | UN-Women ACRO | December 2014 | Avon | 2,500 |
| Annual and final reports to TCCC | UN-Women ACRO | Every January until 2016 | --- | --- |
| Annual and final reports to the Brazilian Cooperation Agency | UN-Women ACRO and Secretariat for Policies for Women | Every January until 2016 | --- | --- |
| Bi-monthly national steering committee meeting | Coca-Cola Institute | Every two months until end of 2015 | TCCC | 30,000 |
| Collection of baseline data | Coca-Cola Institute | First semester of 2014 | TCCC | 40,000 |
| Monthly monitoring meetings | Secretariat for Policies for Women | Every month until end of 2015 | --- | --- |
| RESEARCH |  |  |  |  |
| Feminicide | TBD | TBD (2014) | Core | 40,000 |

Evaluation Plan 2014-2016

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Officer in charge | Region/ country |  | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1: Final evaluation of Programme “Education for women’s rights: disseminating knowledge about the Maria da Penha Act and how to use it” | Y | UNDAF Outcomes 1.1, 1.2, 3.1 and 3.2 SP Impact 3, Outcomes 3.1 and 3.2 | Brazil AWP Output 3.2.1 and 3.2.3 | Brazil CO | Brazil |  | N | Avon Institute, Fundo Elas, CEDAPS | June-September 2014 | US$30,000, non- core funds (Avon Institute) | Planned |  |
| Evaluation 3: Final evaluation of Programme “WEE and Integration into the Value Chain of TCCC in Brazil” | Y | UNDAF Outcomes 1.1, 1.2 and 2.3 SP Impact: 2 Outcomes: 2.1 and 2.2 | Brazil AWP Output: 2.1.1 and 2.2.2 | Brazil CO | Brazil |  | N | ICCB, IBAM, IPSOS | October-December 2015 | US$40,000, non-core funds (TCCC) | Planned |  |
| Evaluation 3: Final Evaluation of Programme “Strengthening Public Policies for Women” | Y | UNDAF Outcomes 1.1, 1.2, 1.3, 2.3, 3.1, 3.2, 3.3 SP Impact: all Outcomes: 1.1, 1.2, 1.3, 2.1, 2.2, 2.3, 3.1, 3.2, 4.2, 5.1, 5.2 and 6.1 | Brazil AWP Output: all | Brazil CO | Brazil |  | N | Secretariat for Policies for Women, Brazilian Agency for Cooperation | July-September 2017 | TBD | Planned |  |
| Evaluation 4: Meta Evaluation of evaluation managed or with the participation of Brazil CO in the period 2012-2016 | N | UNDAF Outcomes 1.1, 1.2, 1.3, 2.3, 3.1, 3.2, 3.3 SP Impact: all Outcomes: 1.1, 1.2, 1.3, 2.1, 2.2, 2.3, 3.1, 3.2, 4.2, 5.1, 5.2 and 6.1 | Brazil AWP Output: all | Brazil CO | Brazil |  | N | All partners in SN | April-June 2016 | US$10,000, core funds | Initiated | Additional funds will be sought. |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1: Mid-term evaluation of Programme “Domestic Workers: Building Equality in Brazil” | Y | UNDAF Outcomes 1.1, 1.2 and 2.3 SP Impact 2, Outcome 2.2 | Brazil AWP Output 2.3.1 | Focal point in Brazil CO in close cooperation with FGE | Brazil |  | Y (Fundo Elas, Themis) | ILO, FENATRAD, SPM and SEPPIR | March-June 2014 | US$30,000, non- core funds (FGE) | Planned |  |
| Evaluation 2: Final evaluation of Programme “Domestic Workers: Building Equality in Brazil” | Y | UNDAF Outcomes 1.1, 1.2 and 2.3 SP Impact 2, Outcome 2.2 | Brazil AWP Output 2.3.1 | Focal point in Brazil CO in close cooperation with FGE | Brazil |  | Y (Fundo Elas, Themis) | ILO, FENATRAD, SPM and SEPPIR | October-December 2014 | US$30,000, non- core funds (FGE) | Planned |  |
| Evaluation 3: Mid-term evaluation of Programme “Engaging women and men with gender transformative CCT programming” | Y | UNDAF Outcomes 1.1, 1.2 and 2.3 SP Impact 2, Outcome 2.2 | Brazil AWP Output 2.3.1 | Focal point in Brazil CO in close cooperation with FGE | Brazil |  | Y (Instituto promundo, Instituto Papai) | MDS | June-September 2014 | US$22,500, non- core funds (FGE) | Planned |  |
| Evaluation 4: Final evaluation of Programme “Engaging women and men with gender transformative CCT programming” | Y | UNDAF Outcomes 1.1, 1.2 and 2.3 SP Impact 2, Outcome 2.2 | Brazil AWP Output 2.3.1 | Focal point in Brazil CO in close cooperation with FGE | Brazil |  | Y (Instituto promundo, Instituto Papai) | MDS | TBD | TBD | Planned |  |
| Evaluation 5: Final evaluation of Programme “More Rights More Power for Brazilian Women” | Y | UNDAF Outcomes 1.1, 1.2, 1.3 and 2.3 SP Impact 1, 2, and 5; Outcomes 1.1, 2.3, 5.1 and 5.2 | Brazil AWP Output 1.1.1, 1.1.2, 2.3.1, 5.1.1 and 5.2.2 | Focal point in Brazil CO in close cooperation with FGE | Brazil |  | Y (FGE consortium and SPM) | TBD | July-October 2014 | US$72,000, non- core funds (FGE) | Planned |  |
| Evaluation 6: UNDAF Final evaluation | Y | UNDAF Outcomes all SP Impact all Outcomes all | Brazil AWP Output all | Brazil CO | Brazil |  | Y (UNCT) | TBD | October-December 2016 | n/a | Planned |  |
| Evaluation 3: Final evaluation of Programme “WEE and Integration into the Value Chain of TCCC in Brazil” | Y | UNDAF Outcomes 1.1, 1.2 and 2.3 SP Impact: 2 Outcomes: 2.1 and 2.2 | Brazil AWP Output: 2.1.1 and 2.2.2 | Programme Division | HQ | N |  | ICCB, IBAM, IPSOS | May-August 2016 | US$50,000, non-core funds (TCCC) | Planned |  |

# Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Final evaluation of Programme “Education for women’s rights: disseminating knowledge about the Maria da Penha Act and how to use it” | Mandatory evaluation per request of donor. | TBD | To support the formulation of new programmatic activities and to generate accountability. |
| Final evaluation of Programme “WEE and Integration into the Value Chain of TCCC in Brazil” | Mandatory evaluation per request of donor. Potential of program to identify innovations. | TBD | To support the formulation of new programmatic activities and to generate accountability. |
| Final Evaluation of Programme “Strengthening Public Policies for Women” | Mandatory evaluation per evaluation policy. | TBD | To support the formulation of new programmatic activities and to generate accountability. |
| Final Evaluation of the Strategic Note | TBD | TBD | To support the formulation of new programmatic activities and to generate accountability. |

Please fill out a separate row for each evaluation.