1. **Planning duration** – the evaluation plan is for 2010. What about 2011? Which ones will be conducted in 2010 and which ones in 2011?

**2.     Template** – as you can find in Annex 3 of the Guidance Note on Biannual Decentralized Evaluation Planning (No.2A) (Please visit the intranet), the template requires to include the below information:

**Evaluations to be conducted in 2010:**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation title and type | Mandatory evaluation | Relevant regional SP/SRS/thematic outcome and theme | Relevant MRF | Office to manage the evaluation | Joint evaluation | Key evaluation stakeholders | Dates for the evaluation | Budget for evaluation | Status | Remarks |
| **Managed by North Africa Office** | | | | | | | | | | |
| Evaluation of “Supporting family courts for implementing the family law" project 54557 :**Final** | Yes | GPS  DRF 3.1 and 7.1 |  | UNIFEM North Africa SRO | Yes  UNIFEM  UNICEF  PNUD | - Ministry of Justice | Nov. 2010 | 13 000 USD | Project in implementation |  |
| Evaluation of the “Multisectoral Programme for the fight against gender-based violence through the empowerment of women and girls in Morocco" project 58215: **Midterm** | Yes | VAW  DRF 2.1, DRF4.1  DRF 5.3, DRF5.4  DRF 7.3, DRF8.2 |  | MDG-F Secretariat | Yes  UNIFEM  UNFPA  UNICEF  UNESCO  UNHCR  UNAIDS  FAO  BIT | 13 national Entities and 50 NGOs (Ministry of foreign Affairs, Justice, Interior, (DGCL/ Sûreté Nationale), Gendarmerie Royale, Economy and Finance, Employment, Health, Agriculture, Youth and Sports, Social Development Family & Solidarity, High Commission of Planning, Communication, and Religious Affairs | Mid term evaluation : June 2010 | NA | Project in implementation | This programme duration may be extended |
| Evaluation of the "Cultural Heritage and the Creative Industries as Vehicles for Development in Morocco" project 63003: **Midterm** | Yes | ESR  DRF 5.3  DRF 6.2  DRF 7.3 |  | MDG-F Secretariat | Yes  UNESCO  UNIFEM  UNDP  UNIDO | Ministry of Culture;  The Agency for the Socioeconomic Development of the Southern Provinces(Programme Oasis South) ;  NGOs and women’s cooperatives of Guelmim, Tata and Assa Zag ;  The communes of Assrir, Ifrane, Foum el hisn, Akka,Tamanart, and Foum Zguid. | Mid term evaluation : June 2010 | NA | Project in implementation | This programme duration may be extended |

A review of the SP for 2008-2010 conducted by the Institutional Development Team (IDT) with the cooperation of UNIFEM North Africa SRO in 2010

**Evaluations to be conducted in 2011:**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation title and type | Mandatory evaluation | Relevant regional SP/SRS/thematic outcome and theme | Relevant MRF | Office to manage the evaluation | Joint evaluation | Key evaluation stakeholders | Dates for the evaluation | Budget for evaluation | Status | Remarks |
| Managed by North Africa Office | | | | | | | | | | |
| Evaluation of the “Multisectoral Programme for the fight against gender-based violence through the empowerment of women and girls in Morocco" project 58215: **Final** | Yes | VAW  DRF 2.1, DRF 4.1  DRF 5.3, DRF 5.4  DRF 7.3, DRF 8.2 |  | MDG-F Secretariat | Yes  UNIFEM  UNFPA  UNICEF  UNESCO  UNHCR  UNAIDS  FAO  BIT | 13 national Entities and 50 NGOs (Ministry of foreign Affairs, Justice, Interior, (DGCL/ Sûreté Nationale), Gendarmerie Royale, Economy and Finance, Employment, Health, Agriculture, Youth and Sports, Social Development Family & Solidarity, High Commission of Planning, Communication, and Religious Affairs | Final evaluation:  end of 2011 | NA | Project in implementation | This programme duration may be extended |
| Evaluation of the "Cultural Heritage and the Creative Industries as Vehicles for Development in Morocco" project 63003: **Final** | Yes | ESR  DRF 5.3  DRF 6.2  DRF 7.3 |  | MDG-F Secretariat | Yes  UNESCO  UNIFEM  UNDP  UNIDO | Ministry of Culture;  The Agency for the Socioeconomic Development of the Southern Provinces(Programme Oasis South) ;  NGOs and women’s cooperatives of Guelmim, Tata and Assa Zag ;  The communes of Assrir, Ifrane, Foum el hisn, Akka,Tamanart, and Foum Zguid. | Final evaluation:  end of 2011 | NA | Project in implementation | This programme duration may be extended |
| Evaluation of the “Upscaling GRB for accelerated action toward GE-Morocco- Phase III” Project 72690  **Midterm** | Yes | ESR  DRF 4.1  DRF4.2  DRF 7.2 | MRF 1.1  MRF 1.5  MRF 4.3 | UNIFEM North Africa SRO | No | Ministry of Economy and Finance;  DGCL;  Ministry of Social Development Family & Solidarity; High Commission of planning, 6 other sectoral departments TBD, NGOs | 2011 | 8 500 USD | Project in implementation |  |

**3.       Evaluation budget** – What is the evaluation budgets for the last two evaluations? (Multisectoral programme for the fight against gender based violence through the empowerment of women and girls in Morocco” and “Cultural heritage and the creative industries as vehicle for development in Morocco) According to the draft plan, the evaluation budget against project budget will be :

|  |  |
| --- | --- |
| Evaluation title | Evaluation budget against project budget |
| Supporting family courts | 1.33 %\* |
| Multisectoral programme for the fight against gender-based violence | The MDG-F Secretariat has not informed us about these evaluations budgets |
| Cultural heritage and the creative industries |
| Upscaling GRB for accelerated action toward GE-Morocco- Phase III | 1.10 % |

 \*Please note that :

* The funds for the implementation of this programme have been mobilized progressively. Therefore, as we did not have an overall visibility of the total budget, from the beginning, we could not plan the appropriate budget. However, we believe that the budget of $ 13 000 would enable us to ensure a sound evaluation, emphasizing the programmes’ strategic aspects.
* The evaluations of the “Support of the implementation of existing laws” and “Trust Fund to end violence” projects will be managed by our national partners (i.e. CIDDEF and INSAF).

**4.       Mid-Term Review** – The Institutional Development Team (IDT) at HQ is planning to conduct a review of the SP for 2008-2010. The SROs will be asked to cooperate in the review in this year. You may include this information at the bottom of the plan, for instance, “other type of assessment – A review of the SP for 2008-2010”. This will be managed by the IDT team and I am asking the role of the SROs to them. I will let you know when I receive their answer.

**5.       Next Step** – After reviewing the draft, please send it to GEO section focal point and related thematic sections at HQ. They may have their own comments too. Please copy it to myself and Shravanti Reddy, focal point at EU. Then, after their approval, I will upload it on the Evaluation Resource Centre (ERC) and will inform you of the upload.