**KYRGYZSTAN CO – MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2018-2022**

*NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities. Remember that MERP has to be linked with many of the outputs and activities planned for in the OEEF.*

**Monitoring 2018-2022**

| **SN Impact/Outcome** | **Activity** | **Responsible staff member** | **Partners and stakeholders** | **Planned Dates (Month and year of start and end)** | **Budget** | |
| --- | --- | --- | --- | --- | --- | --- |
| *Source* | *Amount* |
| **MONITORING** | | | | | | |
| *Quarterly monitoring of activities* | *Update RMS* | *Focal point per Output in RMS* | *Internal staff* | *1/2018-12-2022* | *n/a* | *n/a* |
| *Outcome 1. Women and men, especially youth, value social norms supporting gender equality and women’s empowerment at individual and community levels* | *Omnibus survey on perception indicators* | *M&E focal point* | *Internal staff* | *1/2018-12-2022* | *Core* | *$1000* |
| *Mid-term review of SN* | *Survey, Desk review, Workshop* | *Representative & M&E focal point (support from RO Planning & Coordination Specialist)* | *Office staff, beneficiaries, government and other state institutions, civil society, UN system, key donors and development partners* | *8/2019-11/2019* | *Core* | *$30,000* |
| *UNCT-SWAP Gender Scorecard* | *Survey, Desk review, Workshop* | *Representative & National Programme Officer* | *Un system* | *TBC* | *Core* | *TBC* |
| *FGE project monitoring* | *Update RMS* | *Focal point for the project* | *Internal staff, partners* | *TBC* | *n/a* | *n/a* |

**Research Plan 2018-2022**

| **Activity** | **Partners and stakeholders** | **Planned Dates (Month and year of start and end)** | **Budget** | |
| --- | --- | --- | --- | --- |
| *Source* | *Amount* |
| **RESEARCH** | | | | |
| *Research on women’s roles in preventing, promotion and participation in violent extremism* | *UN System, Academia* | *1/2018-12/2018* | *Non-core* | *$80,000* |
| *Audience research for BCC strategy* | *UNCG, academia, media development NGOs and media outlets* | *2/2018, 2/2019, 2/2020, 2/2021* | *TBC* | *TBC* |

**Evaluation Plan 2018-2022[[1]](#footnote-1) [[2]](#footnote-2)**

| **Evaluation name** | **Mandatory?**  **(Y/N)** | **UNDAF Outcome/ UN Women SP Goal, Outcome** | **Country/ MCO/ RO AWP Output** | **Office in charge** | **Region/ country** | **Joint activity**  **(Y/ N, indicate partners)** | **Key Stakeholders** | **Planned Dates**  **(start-end)** | **Budget (US$) / Sources of Funding** | **Status (pending/ initiated/ ongoing/ completed)** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ***Evaluations managed by the office*** | | | | | | | | | | |  |
| *Evaluation 1 Final evaluation of the ‘Livelihoods through participation and equal access to water’* | *Y* | *UNDAF Outcome 2 / UN Women SP Output 11 / SN Outcome 1* | *TBC* | *Kyrgyzstan CO* | *Kyrgyzstan* | *N* | *Ministry of Labour and Social Development, district administrations, partner*  *municipalities, water users associations* | *January – March 2018* | *US$20,000, non-core funds* | *Pending* |  |
| *Evaluation 2*  *Country Portfolio Evaluation* | *Y* | *UNDAF Outcome 2 / UN Women SP Outputs 11 and 5 / SN Outcomes 1 and 2* | *TBC* | *Kyrgyzstan CO* | *Kyrgyzstan* | *N* | *Civil society partners, Government and State Agencies, Parliament, Beneficiaries, UN system, Donors and Development Partners* | *November 2021-April 2022* | *TBC* | *Pending* |  |
|  |  |  |  |  |  |  |  |  |  |  |  |
| ***Evaluations in which the office participates*** | | | | | | | | | | |  |
| *Evaluation 1*  *Evaluation of the Joint UN Programme on Prevention of Violent Extremism* | *Y* | *UNDAF Outcome 2 / UN Women SP Outputs 11 and 5 / SN Outcomes 1 and 2* | *TBC* | *UNDP and UNICEF CO* | *Kyrgyzstan* | *Y* | *UN System, Government, Civil society, Development partners and Media* | *January 2020-April 2020* | *TBC* | *Pending* |  |
| *Evaluation 2 UNDAF Final evaluation* | *Y* | *UNDAF Outcomes 1-4 / UN Women SP Outputs 11 and 5 / SN Outcomes 1 and 2* | *TBC* | *RCO* | *Kyrgyzstan* | *Y* | *UN System, UN System, Government, Civil society and Development partners* | *December 2020-June 2021* | *TBC* | *Pending* |  |

1. Please see Guidance on Decentralized Evaluations, [link](https://unwomen.sharepoint.com/Policy-Programming/instdev/Annual%20WorkPlan/Forms/AllItems.aspx?RootFolder=%2FPolicy%2DProgramming%2Finstdev%2FAnnual%20WorkPlan%2F2016%20SN%2DAWP%20Internal%20Documents%2F1%2E%20Guidance&FolderCTID=0x01200013346CFF745A88469EF40CF29382BA1C&View=%7BA52F1024%2D6728%2D4C59%2D97AB%2D9974726DF3F9%7D). [↑](#footnote-ref-1)
2. Please fill out a separate row for each evaluation. [↑](#footnote-ref-2)