**HAITI MONITORING, EVALUATION AND RESEARCH PLAN – MERP, 2016**

**Monitoring and Research Plan 2016**

| **Activity**  | **Partners and stakeholders**  | **Planned Dates (Month and year of start and end)** | **Budget** |
| --- | --- | --- | --- |
| Source | Amount |
| **MONITORING** |
| Monthly monitoring of core and non-core projects (programmatic activities & delivery) | Internal exercise with LAC RO | Monthly  |  |  |
| Quarterly progress programme and operations report  | Internal exercise with LAC RO | Quarterly |  |  |
| Annual report  | Internal exercise with LAC RO | Annually |  |  |
| Muskoka Final narrative and financial report (donor report) | Ministère des affaires étrangères de la France | January 2016 |  |  |
| F4GE Final narrative and financial report (donor report) | European Union | January 2016 |  |  |
| Elections Project Final narrative and Financial report (donor report) | UNDP | January 2016 |  |  |
| RVC Final narrative and Financial report (donor report)\* | Community Reduction Violence – RVC Unit /MINUSTAH  | July 2016 |  |  |
| UNTFHS narrative and Financial report (donor report)\* | UNTFHS, UNDP, UNESCO  | Annually |  |  |
| Indicators Tracking Tool to monitor AWP implementation | Internal exercise with LAC RO | Annually  |  |  |
| Completion of Results Management System  | Internal exercise with LAC RO | Quarterly |  |  |
| Mid-term review of the Country Office Strategic Note (SN) 2014-2016 | Internal exercise with LAC RO | September 2016 | Core  | 1,700 |
| **RESEARCH** |
| Conduct a study on the impact of drawdown of Minustah for UN Women | External Exercise | In 2016 | Core | 8,000 |
| Assess and dissemination of all laws adopted by Haiti promoting women’s rights and pending law including those in discussion at the Government in relation with women’s rights | External exercise | January- July 2016  | Core Non-Core TBM | 10,00027,650 |
| Diagnosis analysis of the legal, regulatory and administrative barriers for development of women's capacities in climate-resilient agriculture | External exercise | March – September 2016 | Core Non-core TBM | 9,00025,000  |
| Conduct a study on the perception of human insecurities related to disasters at community level – with a special focus on women, youth and disabled | External exercise | January-June 2016 | XBNon-core TBM  | 10,00045,666 |

**\***The report will be produced if the funds are received

**Evaluation Plan 2016**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Evaluation name** | **Mandatory?****(Y/N)** | **UN Women SP Goal, Outcome**  | **Country AWP Output** | **Office in charge** | **Region/ country** | **Joint activity** **(Y/ N, indicate partners)** | **Key Stakeholders** | **Planned Dates** **(start-end)** | **Budget (US$) / Sources of Funding** | **Status (pending/ initiated/ ongoing/ completed)** | **Remarks** |
| ***Evaluations managed by the office*** |  |
| Evaluation of root causes and barriers to women’s access to opportunities and productive resources for Climate-Resilient Agriculture  | *No* | *Goal/Impact 2* *OC 2.1.*  | *OP 2.1.1.* | Haiti Country Office | Haiti | No | All partners involved on the field  | February- July 2016 | US$ 20,000 core 38,800Non-core TBM | Planned  |  |

**Evaluation Justification Matrix\*\***

|  |  |  |  |
| --- | --- | --- | --- |
| **List of selected evaluation** | **Criteria used for the selection** | **Potential evaluability** | **Intended use of evaluation findings** |
| Evaluation of root causes and barriers to women’s access to opportunities and productive resources for Climate-Resilient Agriculture. | This area is a priority for Haiti Office in 2016. Second, they may be opportunities to empowering women’s through income generating activities for Climate-Resilient Agriculture. | The potential impact of this evaluation is high. There are not many studies or evaluations on this field and many stakeholders are interesting to collaborate in this process.  | The assessment findings will provided key elements to design projects and programs and then mobilize resources.   |

**\*\*Evaluation Plan 2016: As the ISF (UNDAF) was extended for a year to 2017, Haiti Office will request extension of its SN to align it with ISF, and so the final evaluation will be conducted in 2017.**