MONITORING, EVALUATION AND RESEARCH PLAN (MERP) – Pakistan – 2016-2017

NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities. Remember that MERP has to be linked with many of the outputs and activities planned for in the OEEF.

Monitoring 2016-2017

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| SN Impact area 4 Outcome 4.2 | Monitoring missions of the implementing partners | Programme Officer | NDMA, PDMAs (Balochistan and KP), SDMA, PAK, CERD | Quarterly 2016-2017 | Non-Core Available $26,000 through WLSR and $24,000 to be raised | $50,000 |
| SN Impact area 2 Outcome 2.1 & 2.2 | Monitoring missions of the implementing partners | Programme Officer | Labour and Human Resource Departments (Punjab and Sindh), HomeNet Pakistan (HNP), Baidarie, Baanhn Beli, Gorakh Foundation (UNTFHS), FAO, ILO, UN Women | Quarterly 2016 | Non-Core available RNE $1,500 UNTFHS $1,000 | $2,500 |
| SN Impact area 2 Outcome 2.2 | Monitoring missions of the implementing partner | Programme Officer | Baidarie | Quarterly 2016-2017 | Non-Core Benetton to be raised | $3,000 |
| SN Impact area 1 Outcome 1.1 SN Impact area 3 Outcome 3.1 | Monitoring missions of the implementing partner | Programme Officer | UN women, Government Partners identified/selected for the implementation for VAW and Governance Program | Quarterly 2016-2017 | Non-Core To be raised | $20,000 |
| SN Impact area 3 Outcome 3.1 | Monitoring missions of the implementing partner | Programme Officer | SCF | Quarterly 2016-2017 | To be received from RO | 6,000 |
| SN Impact area - All Outcomes - All | Review the existing monitoring matrices and its institutionalization across all programmes to measure implementing partners’ progress | Strategic Management and Partnerships Officer | N/A | First Quarter 2016 | Core | No funds required |
| SN Impact area - All Outcomes - All | Capacity strengthening of implementing partners especially on the gaps identifies during the capacity assessment | Strategic Management and Partnerships Officer | N/A | 6 monthly | Non-Core to be raised Non-Core available | $5000 $5000 |

Research Plan 2016-2017

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |
| --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Research Study on “Status of women’s economic participation and empowerment in humanitarian and development context” | CGaPS | September 2015 – January 2016 | Non-Core Available RNE $20,000 WLSR $13,000 | $33,000 |
| Punjab Economic Report 2014-15 | LUMS | August 2015 – June 2016 | RNE available | $62,500 |
| Gender profile for KP and PAK in partnership with Government entities | PBS | July 2015 to Dec 2017 | Core available | $60,000 |
| Support NCSW on conducting National Level Baseline on VAW "Generating Data for Women’s Social and Economic Wellbeing" and its dissemination through provision of national and international Technical Assistance. | NCSW, CSOs, UNFPA,UNDP, UNICEF | January 2016 – September 2017 | Core available | $20,000 |
| Briefing/research papers based on National VAW Baseline Study by the NCSW highlighting prevalence, trends/issues related to VAW. | NCSW, Academia, CSOs, Network of Women Living with HIV/AIDs, UNAIDS, UNFPA, UNDP, UNICEF | 2016-2017 | To be raised Core | $20,000 $20,000 |
| Conduct and disseminate findings of the Study on Scaling up HIV/AIDs services for most marginalized women transgender, disable, Women Sex Workers) and build capacities of advocates to advocate on the issue. | NCSW, Academia, CSOs, Network of Women Living with HIV/AIDs, UNAIDS, UNFPA,UNDP, UNICEF | 2016 | Core | $10,000 |
| Prepare position paper with key recommendations for ECP and the Electoral Reform Committee Review/Assessment Paper of Local Government Elections Laws Document Case Studies of Women Candidates and Voters from DIR, KP, Punjab and Sindh. Lessons Learnt based on Local Government Elections Printed. | UNDP, ECP, WPC, IFES, FAFEN, Academia, Political Parties, NCSW,PCSW, WDDs | 2016-2017 | To be raised | $20,000 |
| Baseline development for DRF Impact area 2 | Labour and Human Resource Department, Planning and Development, Women Development Department, HNP, HBWWCA, APLWHIV | 2nd Quarter of 2016 | To be raised | $ 45,000 |
| Baseline development for DRF Impact area 2 | Baidarie | 1st Quarter of 2016 | Hard pipeline (Benetton) | $10,000 |

Evaluation Plan 2016-2017

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation1: 03 End of Project Evaluations/Reviews for WEE Programme | Y | Goal 2, Outcome 2.1, 2.2 and 2.3 | Pakistan AWP Output 2.1.1 2.1.2 2.2.1 2.2.2 2.3.1 | Pakistan CO | Pakistan | N | Labour and Human Resource Departments (Punjab and Sindh), HomeNet Pakistan (HNP), Baidarie, Baanhn Beli, Gorakh Foundation (UNTFHS), Thardeep Rural Development Programme (TRDP/FGE), FAO, ILO, UN Women | January – June 2016 | $25,000 (Norway available for 2016, remaining will be utilized in 2015) $15,000 (UNTFHS available) $20,000 from Benetton committed for 2017 25,000 for UNTF end term evaluation | 01 initiated, 01 due in 2016, 1 end term review due in end 2017 | End of project evaluation, company is selected and contract under process. Evaluation will help the programme determine whether the project has achieved its project outputs and outcomes |
| Evaluation | Y | Goal 4 Outcome 4.1 |  | Pakistan CO | Pakistan | N | NDMA, PDMAs (Balochistan, KP), SDMA, PAK, CERD | March-June 2016 | $29,277 | Will be due next year | End of project evaluation of one year project to assess whether the planned outputs and outcomes were achieved in the project course |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.