BCO – MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2017-2020

Monitoring 2017-2020

| Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source | Amount |
| DRF2/3: Women’s economic empowerment enhanced through removing structural barriers, including violence against women |  |  |  |  |  |
| Baseline study for Combating Gender-based Violence in Bangladesh project | Programme Coordinator EVAW | Community participants, IPs | 06/2017-08/2017 | Non-core TBM | $30000 |
| DRF 4: Women’s and girls’ resilience to climate change and disasters enhanced. |  |  |  |  |  |
| Baseline study for joint National Resilience Programme | Programme Coordinator G & CC/ M&C Officer | Govt, IPs, participants from target communities | 03/2017-05/2017 | Non-core TBM | $ 30000 |
| Mid-term review of joint National Resilience Programme | Programme Coordinator G & CC/ M&C Officer | Govt, UNDP, UNOPS, IPs, DPs | 06/2019-09/2019 | Non-core TBM | $30000 |
| Pilot community led participatory monitoring system under the National Resilience Programme | Programme Coordinator G& CC /M&C Officer | Community women, local IPs | Yearly | Core | TBD |
| DRF 5: Institutional capacity to implement gender equality commitments and priorities enhanced |  |  |  |  |  |
| Monitoring of GRB project implemented jointly by MoWCA and BCO | Programme Coordinator GRB | Ministry of Women and Children’s Affairs (MoWCA), Ministry of Finance, Ministry of Planning | Yearly | Funded by MoWCA | TBD |
| Cross Cutting |  |  |  |  |  |
| Monitoring of the progress of development and operation targets of DRF/AWP and OEEF (2017-2020 Strategic Note) on quarterly basis | Country Representative/Operations Manager | BCO | Quarterly (16) | Core | TBD |
| Monitoring of individual performance plan as they contribute to AWP results | Country Representative /Operations Manager | n/a | Yearly | Core | TBD |
| Technical support to UNDAF M & E group | UNDAF M & E Focal point | UN agencies in Bangladesh, Government partners | 01/2017-12/2020 | Core | TBD |
| Mid Term Review of BCO Strategic Note 2017-2020 | Country Representative/ M & E Focal | BCO | 07/2018-09/2018 | Core | TBD |
| Annual CO workplace satisfaction survey | Country Representative /Human Resource Associate | BCO | 10/2017-10/2019 | Core | TBD |
| Monitoring of Internal and external audit preparedness. | Operations Manager | BCO | Ongoing | Core | No cost implication |
| Monitor implementation and effectiveness of Resource Mobilization Strategy | Country Representative | BCO | Quarterly | Core | No cost implication |

Research Plan 2017-2020

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| DRF2/3: Women’s economic empowerment enhanced through removing structural barriers, including violence against women |  |  |  |  |
| Assessment of required and desired skills- financial, commercial, life- by female Ready Made Garment workers | National skill development Board, Ministry of labour and Employment, ILO | 02/2017-06/2017 | Non-Core TBM | $25,000 |
| Research to fill knowledge gaps and develop evidence for policy advocacy related to economic empowerment of women; Exact topics to be determined based on research ongoing in 2016. | UNDP (2016 research is in partnership), women’s organizations, civil society think tanks, marginalized women groups | 04/2017-12/2017 | Core | $25000 |
| Formative research to develop curriculum for promoting gender equitable roles and respectful relationships in households | NGO partner to be selected | 09/2017-08/2018 | Non-core TBM | $ 40,000 |
| DRF 4: Women’s and girls’ resilience to climate change and disasters enhanced |  |  |  |  |
| Effectiveness of Early warning ON DRR system for women | Bangladesh Meteorological Department, Flood Forecasting System, Cyclone Preparedness Programme, Ministry of Disaster Management and Relief, Ministry of Women and Child Affairs, IPs | 06/2017-10/2017 | Non-Core TBM | $ 30,000 |
| Research study on market opportunities and formal waged employment opportunities for green livelihoods for women in climate affected areas | Ministry of Disaster Management and Relief, Ministry of Women and Child Affairs, Ministry of Environment and Forests, Bangladesh Institute of Development Studies ,IPs | 01/2018-04/2018 | Non-Core TBM | $ 30,000 |
| Longitudinal research on intra-household decision making and responsibilities to inform how the increase in women’s empowerment and resilience influences gender equality | Ministry of Disaster Management and Relief, Ministry of Women and Child Affairs, Ministry of Environment and Forests, IPs | 06/2018-10/2018 | Non-Core TBM | $ 25,000 |
| Impacts of climate change on poor urban women | Ministry of Disaster Management and Relief, Ministry of Women and Child Affairs, Ministry of Environment and Forests, IPs | 08/2019-12/2019 | Non-Core TBM | $ 25,000 |
| Mapping of GBV during and post natural disaster situation at and off shelters/camps | Ministry of Disaster Management and Relief, Ministry of Women and Child Affairs, IPs | 03/2020-07/2020 | Non-Core TBM | $ 25,000 |

Evaluation Plan 2017-2020

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| DRF2/3: Women’s economic empowerment enhanced through removing structural barriers, including violence against women |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation of Career, Capital and Confidence | Y | UNDAF Outcome 3, UN Women SP Goal 2, Outcome 2.1 | BCO output: 2.1.1, 2.2.1, 2.2.2 | BCO | BCO | Y | NGO partners (to be selected); project participants, Partnering employers; partner financial institutions | 06/2018-10/2018 | $ 20000 (Non-core - Benetton) |  |  |
| Final project evaluation for Combating Gender-based violence in Bangladesh project | Y | UNDAF Outcome 3, UN Women SP Outcome 3 | BCO Output 2.5.2 | BCO | ROAP/BCO | N | NGO partners, project participants, MoWCA, University Grants Commission, University partners, Local government partners | 07/2020-10/2020 | $ 40000 (Non core TBM) |  |  |
| DRF 4: Women’s and girls’ resilience to climate change and disasters enhanced |  |  |  |  |  |  |  |  |  |  |  |
| Final Project evaluation for Joint National Resilience Programme | Y |  | BCO | BCO | ROAP/ Bangladesh | N | Govt, UNDP, UNOPS, IPs, DPs | 08/2020-12/2020 | Non-Core (TBM) |  |  |
| Cross Cutting |  |  |  |  |  |  |  |  |  |  |  |
| BCO Strategic Note Final Evaluation | N |  | BCO | BCO | ROAP/ Bangladesh | N | Govts, IPs, DPs and UN | 06/2020-08/2020 | $30000 (Core) |  |  |
| UNDAF Evaluation | Y |  | BCO | BCO | ROAP/ Bangladesh | Y (UNCT) | UNCT, GoB, civil society partners, DPs, intended beneficiaries | 09/2019-12/2019 | TBD |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| DRF 5: Institutional capacity to implement gender equality commitments and priorities enhanced |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation of GRB project jointly implemented by MoWCA and BCO | Y | UNDAF Outcome 1, Un Women SP Goal 5, Outcome 5.1 | BCO Output 5.1.3 | BCO | ROAP/ Bangladesh | Y | Ministry of Women and Child Affairs, Ministries of Finance and Planning and line ministry participants (TBD), GE civil society advocates | 06/2020-10/2020 | $ 20000 (Funded by MoWCA) |  |  |

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.