**MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2018**

**Monitoring 2018**

| **SN Impact/Outcome** | **Activity** | **Responsible staff member** | **Partners and stakeholders**  | **Planned Dates (Month and year of start and end)** | **Budget** |
| --- | --- | --- | --- | --- | --- |
| *Source* | *Amount* |
| **MONITORING** |
| *2018 AWP* | *Routine monitoring of programme portfolio; core and non-core projects (programmatic activities & delivery)* | *Programme Manager and/or thematic responsible*  | *Internal staff, implementing partners/responsible parties* | *1/2018-12/2018* | *n/a* | *n/a* |
| *CO 2017 Annual Report* | *Update RMS* | *Programme Analyst* | *Focal point per Output in RMS* | *01/2018* | *n/a* | *n/a* |
| *Quarterly monitoring of activities* | *Update RMS* | *Programme Analyst* | *Focal point per Output in RMS* | *3/2018**6/2018**9/2018**12/2018* | *n/a* | *n/a* |
| *Donor reporting* | *Prepare and present narrative and financial reports to donor and update the information in DAMS* | *Programme Analyst* | *Internal Staff: Programme staff assigned to the projects and Programme and Finance Associate**Donors: Itaipú Binational and EU* | *05/06/2018 (Final Narrative & Provisional Reports) – DAMS ID: 11615 - Itaipú**21/08/2018 (Interim Narrative and Financial Reports) DAMS ID: 12171 – EU* | *n/a* | *n/a* |

**Research Plan 2018**

| **Activity** | **Partners and stakeholders**  | **Planned Dates (Month and year of start and end)** | **Budget** |
| --- | --- | --- | --- |
| *Source* | *Amount* |
| **RESEARCH** |
| *Publication of the Economic empowerment of women in vulnerability situations through gender mainstreaming in projects and flagship programs of the Secretariat of Social Action (SAS)* | *UN Women* | *3/2018-10/2018* | *Core* | *$2,000*  |
| *Systematization of the pilot planning experience with gender indicators with the Ministry of Public Works* | *UN Women* | *6/2018-11/2018* | *Core* | *$4,000*  |
| *Research on the representation of women´s political participation in the media in the electoral process toward the 2018 national elections.* | *UN Women* | *01/2018-07/2018* | *Non-core* | *7.500* |
| *Research on political violence against women in Paraguay.* | *UN Women* | *01/2018-07/2018* | *Non-core* | *7.500* |
| *Research on the electoral results of women in 2018, compared to the previous elections.* | *UN Women* | *01/2018-07/2018* | *Non-core* | *7.500* |
| *Qualitative study on persistent forms and new forms of violence against women and girls.* | *UN Women* | *01/2018-03/2018* | *Non-core* | *5.000* |
| *Publication of the Equal Pay Day update* | *UN Women* | *01/2019-05/2019* | *Core* | *3.500* |
| *Roadmap of the Interinstitutional Committee to implement the Comprehensive Law on VAW.* | *UN Women* | *04/2019-11/2019* | *Core* | *7.700* |

**Evaluation Plan 2018**

| **Evaluation name** | **Mandatory?****(Y/N)** | **UNDAF Outcome/ UN Women SP Goal, Outcome**  | **Country/ MCO/ RO AWP Output** | **Office in charge** | **Region/ country** | **Joint activity** **(Y/ N, indicate partners)** | **Key Stake holders** | **Planned Dates** **(start-end)** | **Budget (US$) / Sources of Funding** | **Status (pending/ initiated/ ongoing/ completed)** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ***Evaluations managed by the office*** |  |
| *Country portfolio evaluation* | *Y* | *UNDAF Impact 1 and 2* *UNDAF Outcomes:**1.1.* *1.3.**2.1.**SP Goals* *1, 2, 3, 6* | PY Strategic Note 2015-2019 | *Paraguay CO* | *LAC**Paraguay* | *N, \*Ministry of Women**\*Secretariat of Planning**\*Secretariat of Social Action**\*Ministry of Labor**\*Gender Secretariat of the Supreme Court of Justice**\*National Statistics Office**\*Congressional Commissions on Gender Equality**\*SDGs Implementation National Commission* | *\*Ministry of Women**\*Secretariat of Planning* | *March to September 2018* | *$20.000* | *Pending* |  |
| ***Evaluations in which the office participates*** |  |
| *Gender-responsive evaluation of the III National Plan for Equal Opportunities between Women and Men (2008-2017), implemented by the Ministry of Women.* |