**MONITORING, EVALUATION AND RESEARCH PLAN 2019-2021**

**UN Women Regional Office for Asia and the Pacific**

**I. Monitoring and Reporting**

| **SN Impact/ Outcome** | **Subject/Topic** | **Responsible staff member** | **Partners and stakeholders** | **Planned Dates (Month and year of start and end)** | **Budget** | | **Note/Updates** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Source | Amount |
| **Impact Area 1. "An enabling environment is in place to advance GEWE, in line with international norms and standards"**  **(Responsible persons: Hanny Cueva Beteta and Alison Davidian)** | | | | | | | |
| ROAP DR Outcome 1.2. to 1.3.  (Aligned with SP output 6) | Monitoring of Gender statistics programme | Sara Duerto Valero |  | Jan 2019 – Dec 2020 | MEWGC FPI -- DFAT | (TBD) | All activities in the project refer to data, thus monitoring, research and knowledge. The Prodoc does not provide sufficient cost breakdown to determine exact monitoring costs. PMF is in development.  Mid-year review to be conducted 2019. |
| ROAP DR Outcome 1.5  (Aligned to SP output 7) | Monitoring of Access to Justice Project | Gaelle Demolis | TBC (Nepal and Philippines in particular) | Quarterly 2019-2021 | A2J project | 35,000 USD | Duration of the project is June 2018-June 2023  From ProDoc “Monitoring is done by respective organization for their work. UN Women will consolidate the information for monitoring for reporting. Evaluation will rest with UN Women.” Monitoring will be conducted quarterly and through site visits, collections of stories of change and strengthen the capacity of the responsible parties. There will also be a mapping in the Access to Justice. |
| ROAP DR  Outcome 1.6  (Aligned to SP Output 13) | Monitoring of the Preventing Violent Extremism Project | ROAP PVE Team | BNPS, BRAC, BRAC University, WAHID Foundation, INFEST, Habibie Centre, ECOWEB, Moropreneur | 4 monitoring missions to Bangladesh and to Indonesia to take place over the years covering 2019-2021 (Precise dates TBC) | Japan Sup F | USD 175,447 | Extract from ProDoc: All reporting, monitoring and evaluation will be undertaken in accordance with UN Women corporate standards as defined in the Programme and Operations Manual (POM).  Field visits will be conducted quarterly to monitor, document and adequately manage and draw from progress, challenges, risks and opportunities. Technical support will be provided to partners to ensure that they implement a monitoring plan and report to UN Women on a regular basis. |
| ROAP DR Outcome 1.7.  (Aligned with SP output 13) | Monitoring of the Trafficking UNODC- UN Women Joint Project | ROAP WPS team | Htoi in Myanmar and CWCC in Cambodia | 4 monitoring missions  (Exact date TBC) | Japan Sup F | To be mobilized $450,000 ($150,000 USD per Year) | From ProDoc “All reporting, monitoring and evaluation will be undertaken in accordance with UN Women and UNODC corporate standards. Field visits will be conducted quarterly to monitor, document and adequately manage and draw from progress, challenges, risks and opportunities. The Responsible Parties’ report will feed the progress report and final report to be submitted to the Donor. Technical support will be provided to partners to ensure that they implement a monitoring plan and report to UN Women according to the quality standard that is expected” |

| **SN Impact/ Outcome** | **Subject/Topic** | **Responsible staff member** | **Partners and stakeholders** | **Planned Dates (Month and year of start and end)** | | | **Budget** | | **Note/Updates** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I**mpact area 2. "More women have increased economic opportunities"**  **(Responsible person: Sally Barber)** | | | | | | | | | |
| ROAP DR  Outcome 2.1  (Aligned with SP output 8) | Monitoring of the Poverty Reduction through Safe Migration, Skills Development and Enhanced Job Placement in Cambodia, Lao People’s Democratic Republic, Myanmar and Thailand  IOM-PROMISE project | Regional Migration PM | TBC | | | Dec 2018 - Sep. 2021 | SDC (through IOM) | Staff time | Duration of the project is December 2018 - September 2021  PMF and monitoring plan are being developed. |
| ROAP DR Outcome 2.3  (Aligned with SP output 10) | Annual review meetings by the Project steering committee to consider the Annual progress reports and interim and certified financial reports of the project on Strengthening human rights and gender equality through climate change action and disaster risk reduction | Inkar Kadyrzhanova | The project covers Bangladesh, Vietnam and Cambodia COs; they will contribute to the progress report to the donor (SIDA) on an annual basis. The review of the annual report will be conducted by the Project Steering Committee at the Annual review meeting to be held once a year in May of each year (2019-2022). The regional results will also be included in the same way. | | | May 2019, May 2020, May 2021 | EmPower project | 30,000 USD | The project will organize annual review meetings with participation of the Project steering committee members (about 15 people).  UNEP takes about 40% of budget. It will have its own M&E system and will report to the UNW according to the agreement on the financing and on the progress in implementation. The monitoring schedule is as follows: Annual Progress Narrative reporting around 15 March 2019-2022, 6 Month Progress reporting annually around 30 July 2019-2023 and Annual Certified financial reporting annually around 30 July 2019-2023. |
| **Impact area 3. "All women and girls live a life free from all forms of violence"**  **(Responsible person:** **Melissa Alvarado)** | | | | | | | | | |
| ROAP DR  Outcome 3.1  (activity 3.1.1.36)  (Aligned with SP output 11) | Project monitoring, baseline and end line survey - Safe and Fair programme | Melissa Alvarado | EVAW Team, ILO | | May 2018-May 2019 | | EU | USD 70,000 | A consultant to coordinate monitoring among COs is hired. |
| **Impact area 4 / OEE. "AP RO and COs are centres of excellence, connecting partners, creating and sharing evidence and knowledge, and inspiring actions for gender equality"** | | | | | | | | | |
| ROAP OEE Output 3.1 (Advice and support to CO for programme) | Management oversight visits and skype calls coordinating with RO managers and POs. | RD, DRD, OM | COs and selected POs | | As needed | |  | TBC |  |
| ROAP OEE Output 3.4 (RO SN management) | Mid-year management review of RO AWP | Mgmt. and M&R | ROAP | | Around June annually | |  | Staff-time |  |
| ROAP OEE Output 3.4 (RO SN management) | Mid-term review of Strategic Note | Mgmt., M&R, and Planning | ROAP | | Mid 2020 | |  | $15,000 |  |

| **SN Impact/ Outcome** | **Subject/Topic** | **Responsible staff member** | **Partners and stakeholders** | **Planned Dates (Month and year of start and end)** | | **Budget** | | **Note/Updates** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ROAP OEE Output 3.4 (RO SN management) and  Output 3.5 (Support to CO for PMR&E) | Monitoring through RMS quarterly and annual reports | M&R | ROAP, CO, POs | | Quarterly |  | Staff-time |  |
| ROAP OEE Output 3.5 (Support to CO for PMR&E) | TA for collecting missing baselines, targets and sources for new SN/AWP of Cos. | M&R | ROAP | | 2019-2021 |  | Staff-time |  |
| Trust Fund /FGE  (Migration) | Monitoring project progress and conduct a monitoring mission | Nuntana Tangwinit | Athika (FGE Trust Fund) | | Mar 2016 – Dec 2019 | FGE Trust Fund | No budget implication |  |
| Trust Fund | Monitoring project progress and conduct a monitoring mission | Nuntana Tangwinit | Asia Pacific Sex Workers Network  (EVAW Trust Fund) | | Apr 2017 – May 2020 | EVAW Trust Fund | USD 2,000 | Duration of the project is Mar 2017 – Feb 2020 |
| Trust Fund  . | Monitoring project progress and conduct a monitoring mission | Nuntana Tangwinit | Persatuan Kesedaran Komuniti Selangor ( EMPOWER)  (EVAW Trust Fund) | | Sep 2018 – Dec 2021 | EVAW Trust Fund | USD 4,000 | Duration of the project is Sep 2018 – Sep 2021  There will be 1 on-site monitoring mission, 2 progress and annual reports and feedback. |

**II. Knowledge generation and research (ROAP OEE Output 3.2)**

| **SN Impact/ Outcome** | **Subject/Topic** | **Responsible staff member** | **Partners and stakeholders** | **Planned Dates (Month and year of start and end)** | **Budget** | | **Note/Updates** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact Area 1. "An enabling environment is in place to advance GEWE, in line with international norms and standards"** | | | | | | | |
| ROAP DR Outcome 1.5  (Aligned to SP output 7) | Mapping on women’s access to justice in Asia and the Pacific: bridging the gap between formal and informal systems through women’s empowerment | Gaelle Demolis | TBD | Q1 2019 | SIDA | USD 80,000 |  |
| ROAP DR  Outcome 1.6  (Aligned to SP Output 13) | Research on  “Building a  Stronger Evidence  Base: A Gender  Sensitive  Approach to  Preventing Violent  Extremism in Asia  and the Pacific” | Alison Davidian | Monash University | Q3 2018 Q1 2019 | Japan Sup Fund | $160,000 |  |
| ROAP DR Outcome 1.7.  (Aligned with SP output 13) | Research on the Gender Dynamics of Trafficking in the Greater Mekong Sub-region | Alison Davidian | TBD | Q3 2018 Q1 2019 | Japan Sup Fund | $80,000 |  |
| N/A | Leadership and Participation of Women’s Organizations in Humanitarian Response in Asia and the Pacific | Smriti Aryal | TBD | Q1 2019 | TBD | USD 60,000 |  |

| **SN Impact/ Outcome** | **Subject/Topic** | **Responsible staff member** | **Partners and stakeholders** | | **Planned Dates (Month and year of start and end)** | | | **Budget** | | **Note/Updates** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I**mpact area 2. "More women have increased economic opportunities"** | | | | | | | | | | |
| ROAP DR  Outcome 2.1  (Aligned with SP output 8) | Gender-responsive research on Skills Development and Employment Opportunities for Women Migrant Workers? (IOM - PROMISE) | Regional Migration PM | TBC | | 2nd Quarter 2019 | | | IOM | USD 35,000 |  |
| ROAP DR Outcome 2.3  (Aligned with SP output 10) | Research paper on best practices on mainstreaming gender and climate change prepared under the project on Strengthening human rights and gender equality through climate change action and disaster risk reduction | Inkar Kadyrzhanova | Bangladesh, Vietnam and Cambodia COs | | June – December 2019 | | | EmPower project | 50,000 USD |  |
| **Impact area 3. "All women and girls live a life free from all forms of violence"** | | | | | | | | | | |
| ROAP DR  Outcome 3.1  and 3.2.  (Aligned with SP output 11) | Scoping Studies and Baseline Study for VAW Women Migrant Workers in ASEAN Region for ‘Safe and Fair’ Project | Melissa Alvarado | | ILO, ASEAN Member States | | Quarter 4 2018-Quarter 1 2019 | EU | | $230,000 Scoping Studies and $70,000 Baseline Study |  |

| **SN Impact/ Outcome** | **Subject/Topic** | **Responsible staff member** | **Partners and stakeholders** | **Planned Dates (Month and year of start and end)** | **Budget** | | **Note/Updates** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Impact area 4 / OEE. "AP RO and COs are centres of excellence, connecting partners, creating and sharing evidence and knowledge, and inspiring actions for gender equality"** | | | | | | | |
| ROAP OEE Output 3.2 (Knowledge generation and dissemination) | Prepare a synthesis of the lessons learned mainly from project implementation | M&R | ROAP, CO/PO’s | 3rd -4th Quarters 2019 |  | Staff time |  |
| ROAP OEE Output 3.2 (Knowledge generation and dissemination) | Brief on Emerging Issues in AP | M&R, Planning and Advisors | ROAP, CO/PO’s | 2020 |  | $15,000 | If funding is not available, then the activity may not be possible. |

**III. Evaluation**

| **Evaluation name** | **Mandatory**  **(Y/N)** | | **UNDAF Outcome/ UN Women SP Outcome and relevant SDGs[[1]](#footnote-2)** | **SN Output/ Relevant flagship program** | **Office in charge (managing the evaluation)** | **Region/ country** | **Joint activity**  **(Y/ N, indicate partners)** | **Planned Dates**  **(start-end)** | **Budget (US$) / Sources of Funding** | **Status (pending/ initiated/ ongoing/ completed)** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Section A. Evaluations managed by ROAP** | | | | | | | | | | | |
| Midterm Evaluation of “Enhancing Access to Justice for Women in Asia and the Pacific: Bridging the Gap between Formal and Information Systems Through Women’s Empowerment” | | Y | SP Impact area  2. Governance | Access to Justice  ROAP DR Outcome 1.5 | RO-AP | AP | ICJ, OHCHR | Q4 2020-  Q1 2021 | $50,000/ SIDA | Pending | Gaelle Demolis |
| Mid-term project evaluation Strengthening human rights and gender equality through climate change action and disaster risk reduction | | Y | SP Impact Area  3. WEE | WEE, Gender and Climate Change  ROAP DRF Outcome 2.3 | ROAP | AP | No | End of 2019 | EmPower project  50,000 USD / non-core | Planned | Inkar Kadyrzhanova |
| Thematic Evaluation of Gender in Humanitarian Action and DRR in Asia and the Pacific | | Y (one thematic per SN cycle) | SP Impact Area  3 WEE; | Humanitarian/DRR, LEAP flagship programme  ROAP DR Outcome 2.3 [DRR]  and  OEE 3.1 [humanitarian action] | ROAP | AP | No | 2019 | 100,000 / core | Pending confirmation | Smriti Aryal / Sabrina Evangelista |
| Midterm and final evaluation, evaluability assessment "Safe and Fair" project | | ? | SP Impact Area  4. EVAW | Ending Violence Against Women  ROAP DR Outcomes 3.1 and 3.2 | ROAP | AP | ? | TBD | TBD | Pending confirmation |  |
| Private Sector Partnerships Development in Asia and the Pacific | | N | SP OEE cluster 2 | ROAP OEE Output 2.2: AP-strengthened private sector engagement | ROAP (RES) | AP | ? | 2021 | 60,000 / core | Pending confirmation | Sabrina Evangelista / Maria Guimaeres |

| **Evaluation name** | **Mandatory**  **(Y/N)** | **UNDAF Outcome/ UN Women SP Outcome and relevant SDGs[[2]](#footnote-3)** | **SN Output/ Relevant flagship program** | **Office in charge (managing the evaluation)** | **Region/ country** | **Joint activity**  **(Y/ N, indicate partners)** | **Planned Dates**  **(start-end)** | **Budget (US$) / Sources of Funding** | **Status (pending/ initiated/ ongoing/ completed)** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Section B. Evaluations in which the office participates (other office managing)** | | | | | | | | | | |
| Final Evaluation of the 3-year “Coming Home Reintegration Programme” | Y | SP DRF 3 WEE | Women’s Economic Empowerment  ROAP DR  Outcome 2.1 | Led by external partner with RO | AP | ATIKHA | Q4 2019 | N/A | Pending | Carolyn Horekens and Nuntana Tangwinit- Co-managed by NGO and UN Women Fund for Gender Equality; implemented in Philippines, Hong Kong, and Singapore |
| Evaluation of the Poverty Reduction through Safe Migration, Skills Development and Enhanced Job Placement in Cambodia, Lao PDR, Myanmar and Thailand (PROMISE Project) | N | SP DRF 3 WEE | Women’s Economic Empowerment  ROAP DR  Outcome 2.1 | IOM | AP | Yes – IOM, ILO | Q3-Q4 2021 | Not Applicable | Pending | Sally Barber / Sukanya Thongthumrong |
| Final Evaluation “Ending violence against sex workers in Myanmar” Project | Y | SP DRF 4 | Ending Violence Against Women  ROAP DR  Outcomes 3.1 and 3.2 | Led by external partner with RO | AP | Asia Pacific Sex Workers Network | Q1-2 2020 | N/A | Pending | Nuntana Tangwinit |
| Final Evaluation  “Countering the Role and Impact of Sexual and Gender-Based Violence on Women’s Freedom of Expression and Decision-Making in Public and Political Spaces” Project | Y | SP DRF 4 | Ending Violence Against Women  ROAP DR Outcomes 3.1 and 3.2 | Led by external partner with RO | AP | Persatuan Kesedaran Komuniti Selangor ( EMPOWERPersatuan Kesedaran Komuniti Selangor ( EMPOWER) | Q3-4 2021 | N/A | Pending | Nuntana Tangwinit |
| Country Portfolio Evaluation: Papua New Guinea | Y | ALL |  | RES & CO | PNG | N | 2019 | 50-60k CO  core | Planned | Co- managed by RES and CO |
| Country Portfolio Evaluation: Bangladesh | Y | ALL |  | RES & CO | Bangladesh | N | 2019 | 50-60k CO  core | Planned | Co- managed by RES and CO |
| Country Portfolio Evaluation:  Nepal | Y | ALL |  | RES & CO | Nepal | N | 2020 | 50-60k CO  core | Planned | Co- managed by RES and CO |
| Country Portfolio Evaluation: Viet Nam | Y | ALL |  | RES & CO | Viet Nam | N | 2020 | 50k core CO  core | Planned | Co- managed by RES and CO |
| Country Portfolio Evaluation: Cambodia |  | ALL |  | RES & CO | Cambodia | N | 2020 | 50k CO core | Pending Confirmation | Co- managed by RES and CO |

1. Outcomes contributing to the SDGs as per the Strategic Plan [↑](#footnote-ref-2)
2. Outcomes contributing to the SDGs as per the Strategic Plan [↑](#footnote-ref-3)