**CO MEXICO**

**MONITORING, EVALUATION AND RESEARCH PLAN 2020-2025**

**UPDATED: 29th January 2020**

| **Activity** | **Partners and stakeholders** | **Planned Dates (Month and year of start and end)** | **Budget** | |
| --- | --- | --- | --- | --- |
| Source | Amount |
| **MONITORING** | | | | |
| Monthly monitoring of core and non-core projects (programmatic activities & delivery) | Internal exercise | January- December  of each year | Core | Covered by CO Human Resources |
| CO Quarterly progress report | RMS based exercise | April/ June/ September/ December of each year | Core | Covered by CO Human Resources |
| CO Annual Progress Report | RMS based exercise | Annual basis- November-December of each year | Core | Covered by CO Human Resources |
| Annual UNSDCF Logframe Monitoring System | RC Office, UNCT through UN INFO Platform (TBD first Quarter 2020) | TBD after UNSDCF group results confirmation | UNCT | TBD after UNSDCF group results confirmation |
| Strategic Note Mid-Term Review | HQs Programmatic Division and LAC-Centre / Internal exercise | July-November 2023 | Core | $ 5,000 USD |
| **RESEARCH** | | | | |
| Thematic publication “Progress of the world's women” in the framework of global publication | COLMEX | Biannual basis  2021, 2023, 2025 | Core | $ 18,400 USD |
| Evidence based knowledge products on women's time use and unpaid work to carry national care strategy forward and contribute to position care in public debate. | SDG Fund, INMUJERES and academia | Annual basis  2020 | Core/  Non-core SDG Fund | $10,000USD |
| Country Gender Profile | INEGI and academia | First semester 2020 | Core | $15,000 USD |
| Knowledge products on Public Policies and SDG’s | COLMEX | Third quarter 2020 | Core | $10,000 USD |
| Research study on Women, Peace and Security to strengthen state and civil society organizations capacities to construct sustainable peace.   * Gender peace analysis | INMUJERES | Third quarter 2020 | Non-core INMUJERES | $10,000 USD |
| Knowledge products on gender statistics, geospatial analysis and innovation:   * Revista Académica Edición Especial: Coyuntura Demográfica sobre familias | COLMEX, SOMEDE, INMUJERES | First semester 2020 | Non-core- INMUJERES | $8,587 USD |
| Knowledge products of Safe Cities and Public Spaces for Women and Girls to generate evidence as part of one of the four strategies that are implemented in Mexico   * Diagnóstico sobre la violencia contra las mujeres y las niñas en Coahuila. * Diagnóstico sobre participación económica de las mujeres en Coahuila. * Publicación sobre buenas prácticas de trabajo con hombres y niños sobre masculinidades positivas. * Estudio diagnóstico sobre el acoso sexual en el Tec de Monterrey, campus Monterrey. * Diagnóstico de acoso sexual en una alcaldía en Ciudad de México. | Coahuila Government, Monterrey Institute of Technology and Higher Education, Municipality of Guadalajara, GIN Group. | 2020-2021 | Non-core Government of Coahuila, Guadalajara  Non Core- Tec de Monterrey | $30,000USD |
| In the framework of the Project “Alliance UN Women – Danone to promote equal opportunities for women and men and women´s economic empowerment”:   * Sistematización de experiencia “Avancemos por la igualdad” * Business case * Fact Sheets | Danone-Bonafont, CREA, Instituto de Liderazgo Simone de Beauvoir | First semester 2020  Second semester 2021 | Non-core- France National Committee | $30,000USD |
| In the framework of the Programme “Second Chance Education”   * Sistematización de los cursos implementados en el marco del programa. * Manual de implementación del programa a nivel global. * Análisis de buenas prácticas que han tenido impacto en el empoderamiento económico de las mujeres a través de la educación de segunda oportunidad. | BHP, Implementing Partners (Convivencia Joven, Servicio de Promoción Integral Comunitario Juvenil), Ibero Puebla, CEGS and academia | First semester 2020 Second semester 2021 | Non-core  BHP Billiton Foundation | $50,000USD |
| In the framework of the “Spotlight Initiative”   * Diagnóstico y propuesta de reforma al marco legislativo a nivel federal, estatal y municipal. * Guía para legislar con perspectiva de género. * Diagnóstico y armonización de datos y estadísticas de violencia contra las mujeres y niñas. * Análisis sobre los cambios normativos en materia de violencia contra las mujeres y las niñas hechos a nivel federal, estatal y municipal en el año 4 del programa | European Union | Second semester 2020  First semester 2021 | Non-core- Spotlight | $43,000USD |
| Knowledge products on Beijing +25 and Political participation (parity) | Academia | 2020 | Core  Core RO for Beijing+25 | 3500 |
| Knowledge products on Political Participation to drive women´s advancement into highest-level politic, promote the exercise of women´s political rights and leadership at local level.   * Studies * Diagnosis | Academia | Annual  2020 | Core | 3500 |
| Knowledge products on “Gender and climate change”   * Studies * Fact sheets | Academia | Annual  2022 | Core | 5000 |

**Evaluation Plan 2020-2025**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Evaluation name** | **Mandatory?**  **(Y/N)** | **UNDAF Outcome/ UN Women SP Goal, Outcome** | **Country/ MCO/ RO AWP Output** | **Office in charge** | **Region/ country** | **Joint activity**  **(Y/ N, indicate partners)** | **Key Stakeholders** | **Planned Dates**  **(start-end)** | **Budget (US$) / Sources of Funding** | **Status (pending/ initiated/ ongoing/ completed)** | **Remarks** |
| **Evaluations managed by the office** | | | | | | | | | | |  |
| Final evaluation of communication campaigns | N | TBD | TBD | Mexico | Americas | N | According to non-core projects | 2020, 2021, 2022, 2023, 2024, 2025 last quarter of the year | Minimum $20,000 USD per evaluation funded by Non- Core and  Core | Not initiated | UNW CO is planning to continue innovating on evaluations of its communications campaigns that are used as programmatic tools of Non-Core projects such as Safe Cities, SCE and Moving Forward for equality. |
| Moving Forward for Equality Final Evaluation | Y | Women have income security, decent work and economic autonomy | 3.3.1: Women affected by humanitarian situations and in areas of greater vulnerability to disasters develop capacities to design and manage innovative and sustainable businesses.  3.3.2: Local institutions generate economic empowerment and entrepreneurship policies based on evidence on the impact of climate change and human mobility on women. | Mexico CO | Americas | Yes  CREA, ILSB | TBC | 2020 | Non Core  $30,000 USD | Not initiated |  |
| CEEG Mid-Term Evaluation | Y | Women lead, participate and benefit equally from governance | Output 2.1.3: National Statistics Offices drive analysis, research and innovation in gender statistics through the exchange of best practices at global, regional and national level to track progress of gender equality and women’s empowerment. | Mexico CO | Americas | Yes,  INEGI | TBC | 2020 | Non Core  $15,000 USD | Not initiated |  |
| Final Evaluation of Mexico Strategic Note 2020-2025 | Y | OEEF Outcome 3: A strengthened knowledge based and innovative organization for high quality of programmes | Output 3.3. Results based management and evaluation capacities are strengthen for improved effectiveness in programme implementation. | Mexico CO | Americas | No | Government parties | Q1 2025 | Core/Non-core  $ 20,000 USD | Not initiated |  |
| **Evaluations in which the office participates** | | | | | | | | | | |  |
| Spotlight Mid-Term Review | Y | All women and girls live a life free from all forms of violence | 4.1.1: Institutions improve the generation of knowledge, statistics and access to quality data on feminicidal violence and other forms of violence against women and girls to encourage evidence-based policies, programs and decision making. | Mexico CO | Americas | Yes  UNDP  UN Women  UNFPA  HCHR  UNODC  UNICEF | Implementing partners and local government | 2020 | Non Core  $58,879 USD | Not initiated | TBC which RUNO will oversee coordinate this evaluation |
| Second Chance Education Final evaluation (TBC) | Y | Women have income security, decent work and economic autonomy (former Frontier Issues) | 3.2.4: Private companies implement gender equality policies and are committed to economic development, access to the labor market and the autonomy of women and girls. | Mexico | Americas | No | National Government, BHP Billiton Foundation | 2021 | Non Core  TBC | Not initiated | This evaluation will be coordinated by UNW Geneve Office |