## Annex 6: Monitoring, Evaluation & Research Plan

| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget in USD |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |  |  |  |  |
| Biennial Work Plan review of the progress against BWP & SN towards intended results, identify lessons learnt and key issues and challenges that require addressing, and revisit organizational priorities for the following year | All | All | All | This will be a review with data already collected as part of regular monitoring processes listed below | Planning & Monitoring Officer – Full time | n/a | Dec 2024 and Dec 2026 | n/a | n/a | n/a |
| SN Output 1.1 - Normative Frameworks & Data |  |  |  |  |  |  |  |  |  |  |
| Half-yearly monitoring review | UNSDCF Outcome 2/SP Outcome 1 & 6 | SN Output 1.1 - NCSW & NGDP | 1.1 A & 1.1 B | Yes - through NGDP data and monitoring reports | Project Monitoring Focal Points – Full time | NCSW, NGDP, National and Provincial Statistics Departments | Semi-annual 2023-27 | n/a | Core | TBD |
| SN Output 1.2 - Innovative Gender Financing |  |  |  |  |  |  |  |  |  |  |
| Quarterly monitoring review | UNSDCF Outcome 2/SP Outcome 2 | SN Output 1.2 - Enhancing Women's Access to Finance | 1.2 A & 1.2 B | Yes - through project monitoring reports | Project Monitoring Focal Points – Full time | Commercial banks, Government stakeholders, implementing partners | Quarterly 2024-25 | JICA | Non-core | $34,000 per year |
| Quarterly monitoring review | UNSDCF Outcome 2/SP Outcome 2 | SN Output 1.2 - Innovative Financing Solutions for Women | 1.2 A | Yes - through project monitoring reports | Project Monitoring Focal Points – Full time | Commercial banks, financial regulators, implementing partners | Quarterly 2023-24 | ADB | Non-core | $34,000 per year |
| SN Output 1.3 - Protection Against Harmful Practices |  |  |  |  |  |  |  |  |  |  |
| Quarterly monitoring review | UNSDCF Outcome 2/SP Outcome 3 & 4 | SN Output 1.3, Rule of Law | 1.3 A & 1.3 B | Yes - through project monitoring reports | Project Monitoring Focal Points – Full time | Government, Implementing partners | Quarterly 2023-25 | EU | Non-core | TBD |
| Quarterly monitoring review | UNSDCF Outcome 2/SP Outcome 3 & 4 | SN Output 1.3, Prevention and Protection of Women from Violence through Enhanced Access to Justice and Services | 1.3 A & 1.3 B | Yes - through project monitoring reports | Project Monitoring Focal Points | Government, Implementing partners | Quarterly 2023-24 | INL | Non-core | TBD |
| Quarterly monitoring review | UNSDCF Outcome 2/SP Outcome 3 & 4 | SN Output 1.3, Women’s access to quality and survivor-centered justice | 1.3 A & 1.3 B | Yes - through project monitoring reports | Project Monitoring Focal Points – Full time | Government, Implementing partners | Quarterly 2023-24 | Germany | Non-core | $34,000 per year |
| Quarterly monitoring review | UNSDCF Outcome 2/SP Outcome 3 & 4 | SN Output 1.3, Essential Services Package | 1.3 A & 1.3 B | Yes - through project monitoring reports | Project Monitoring Focal Points – Full time | Government, Implementing partners | Quarterly 2023-25 | Australia | Non-core | $34,000 per year |
| SN Output 1.4 - Awareness, Voice, Agency & Leadership |  |  |  |  |  |  |  |  |  |  |
| Quarterly monitoring review | UNSDCF Outcome 2/SP Outcome 5 & 7 | SN Output 1.4, Japan DRR | 1.4 B | Yes - through project monitoring reports | Project Monitoring Focal Points – Full time | Government, Implementing partners | Quarterly 2023-25 | Japan | Non-core | $34,000 per year |
| Quarterly monitoring review | UNSDCF Outcome 2/SP Outcome 5 & 7 | SN Output 1.4, Indus | 1.4 B & 1.4 C | Yes - through project monitoring reports | Project Monitoring Focal Points – Full time | Government, Implementing partners, partnering UN agencies | Quarterly 2023-27 |  | Non-core | $34,000 per year |
| Quarterly monitoring review | UNSDCF Outcome 2/SP Outcome 5 & 7 | SN Output 1.4, Women Political Participation | 1.4 A & 1.4 C | Yes - through project monitoring reports | Project Monitoring Focal Points – Full time | Government, Implementing partners, UN partner agencies | Quarterly 2023-27 | EU | Non-core | $34,000 per year |
| Quarterly monitoring review | UNSDCF Outcome 2/SP Outcome 5 & 7 | SN Output 1.4, WPHF | 1.4 D | Yes - through project monitoring reports | Project Monitoring Focal Points – Full time | Responsible Parties | Quarterly 2023-27 | WPHF - TF | Non-core | $10,000 |
| SN Output 1.5 - Women Economic Empowerment |  |  |  |  |  |  |  |  |  |  |
| Quarterly monitoring review | UNSDF Outcome 2/SP Outcome 4 | SN Output 1.5, Economic Empowerment of Women and Women with Disabilities | 1.5 A | Yes - through project monitoring reports | Project Monitoring Focal Points | Government, Implementing partners | Quarterly 2023-24 | Royal Norwegian Embassy | Non-core | TBD |
| Quarterly monitoring review | UNSDF Outcome 2/SP Outcome 4 | SN Output 1.5, Women in Agriculture | 1.5 A | Yes - through project monitoring reports | Project Monitoring Focal Points | Government, Implementing partners | Quarterly 2023-24 | USAID | Non-core | TBD |
| Quarterly monitoring review | UNSDF Outcome 2/SP Outcome 4 | SN Output 1.5, Women in Technology | 1.5 B | Yes - through project monitoring reports | Project Monitoring Focal Points– Full time | Government, Implementing partners | Quarterly 2023-26 | KOICA | Non-core | $34,000 per year |
| SN OEEF |  |  |  |  |  |  |  |  |  |  |
| Annual monitoring review | SP OEE Output Clusters 1 to 5 | SN OEE Output Clusters | All OEE indicators |  | Operations Manager/Planning & Monitoring Officer |  | Yearly 2023-27 | n/a | Core | TBD |
| RESEARCH |  |  |  |  |  |  |  |  |  |  |
| 2 knowledge products per year developed using data from NGDP | UNSDCF Outcome 2/SP Outcome 1 & 6 | SN Output 1.1 - NCSW & NGDP | - | No - through NGDP data | PCO/Implementing partner | NCSW, NGDP, National and Provincial Statistics Departments | Yearly 2023-27 | n/a | Core | $25,000 |
| Baseline study | UNSDCF Outcome 2/SP Outcome 3 & 4 | SN Output 1.3, Prevention and Protection of Women from Violence through Enhanced Access to Justice and Services | - | Yes | PCO/Implementing partner | - | Q1 2023 | INL | Non-core | $25,000 |
| Baseline study | UNSDCF Outcome 2/SP Outcome 3 & 4 | SN Output 1.3, Women’s access to quality and survivor-centered justice | - | Yes | PCO/Implementing partner | - | Q2 2023 | Germany | Non-core | $25,000 |
| 1 Knowledge product on gender and climate, peace and security – women stories of climate change impacts on human security (qualitative data) | UNSDCF Outcome 2&3/SP Outcome 5 | SN output 1.4, gender and climate, peace and security pilot in Pakistan | 1.4 D | No | PCO / consultant | MoCC, NCSW, NUST | Jan 2024 | DFAT (regional) | Non-core | $10,000 |
| Perceptions survey | UNSDCF Outcome 2/SP Outcome 5 & 7 | SN Output 1.4, Women Political Participation | - | Yes | PCO/Implementing partner | - | Quarterly 2023-27 | EU | Non-core | $20,000 |
| Perceptions survey | UNSDF Outcome 2/SP Outcome 4 | SN Output 1.5, Women in Agriculture | - | Yes | M&E Focal Points | FAO | Q1 2023 | USAID | Non-core | $10,000 |
| Baseline study | UNSDF Outcome 2/SP Outcome 4 | SN Output 1.5, Women in Technology | - | Yes | PCO/Implementing partner | - | Q2 2023 | KOICA | Non-core | $25,000 |
| CGEP | UNSDCF Outcome 2/All SP Outcomes | All SN Outcomes | - | Yes | PCO | - | Q1 2025 | TBD | TBD | $25,000 |

## Evaluation Plan

| Evaluation name | Mandatory | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity | Planned Dates | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (Y/N) |  |  |  |  | (Y/N, indicate partners) | (Start-end) |  |  |  |  |
| End-line evaluation of Womens access to quality and survivor-centered justice | Y | UNSDCF Outcome 2/SP Outcome 3 & 4 | SN Output 1.3, Women’s access to quality and survivor-centered justice | PCO through Implementing Partner/Third Party | Pakistan | No | 2024 | Germany | TBC | Pending |  |
| Mid-term project evaluation survey | Y |  |  | PCO through Implementing Partner/Third Party | Pakistan | Y (UNDP) | 2023-24 | EU | NC | Ongoing |  |
| End-line evaluation of Women's Political Participation | TBC | UNSDCF Outcome 2/SP Outcome 5 & 7 | SN Output 1.4, Women Political Participation | PCO through Implementing Partner/Third Party | Pakistan | No | 2027 | EU | TBC | Pending |  |
| End-line evaluation of Economic Empowerment of Women and Women with Disabilities | N | UNSDF Outcome 2/SP Outcome 4 | SN Output 1.5, Economic Empowerment of Women and Women with Disabilities | PCO through Implementing Partner/Third Party | Pakistan | No | 2024 | Royal Norwegian Embassy | TBC | Pending |  |
| End-line evaluation of Women in Technology | Y | UNSDF Outcome 2/SP Outcome 4 | SN Output 1.5, Women in Technology | PCO through Implementing Partner/Third Party | Pakistan | No | 2026 | KOICA | TBC | Pending |  |