# Monitoring, Evaluation and Research Plan 2018-2022

| Activity | Partners and Stakeholders | Planned Dates (month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount (US $) |
| MONITORING |  |  |  |  |
| Projects Tracking and Monitoring activities | All partners (governmental, non-governmental, NGOs) that are part of the implementation of each programme | Ongoing over years of SN 2018-2022 | Core Non-Core | NA |
| Quarterly monitoring in RMS | Staff (Focal point per activity in RMS) | January, April, July, October every year | Staff Time | NA |
| Quarterly Regional Director Report | Monitoring, Evaluation and Reporting Analyst | 4th of Month Following End of Quarter | Staff Time | $0 |
| Develop and contribute to the corporate Annual Report | Monitoring, Evaluation and Reporting Analyst | January every year | Staff Time | $0 |
| Rapid Monitoring/Assessment Exercise | Project governmental and non-governmental partners | 2019 | Non-Core | TBD |
| Building Blocks System (End line monitoring exercise) | WFP | 2019 | Non-Core And staff time | TBC |
| Mid Term Review of the SN 2018-2022 | All partners and stakeholders that are involved in the implementation of the programmes during the SN period | 2020 | Core | 20,000 (TBC) |
| RESEARCH |  |  |  |  |
| Produce and update a national gender profile biannually, including a report on the status of women, men, girls and boys in Jordan. | DoS, JNCW, MOPIC | 2019-2021 | Non-core (EU) | 150,000 |
| Survey of Jordanian and Syrian women engaged in economic activities in Jordan – MADAD programme | REACH, UNHCR, MOSD, MOL, ILO | 2019 | Non-Core | 50,000 |
| IMAGES Research | PROMUNDO, Research Institutions, DOS, MOSD | 2019 - 2020 | Non-Core | 300,000 USD (TBC) |
| Tax incentives for childcare and transport | Sadaqa, MoL, ILO, MoSD, MoF | 2019 | Non-Core | 50,000 USD |
| Patriarchy and Social Norms | IRCKHF, JNCW | 2019 | Non-Core | 30,000 USD |
| Provision of gender sensitive Financial Services (Briefing Note) | TBD | 2019 | Non-Core | 30,000 USD |

Evaluation Plan 2018-2022

| Evaluation name | Mandatory? (Y/N) |  | UNSDF Outcome/ UN Women SP Goal, Outcome | Country/ Output |  | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of the National Strategy for Women and A Situational Analysis of Women’s Rights and Gender Equality in Jordan (2013 – 2017) |  | Y | UN Women SP Outcome 5 |  | DRF/ output 4.1.2 | Jordan Co | Arab States/Regional Office | N | Government, JNCW | 2018-2019 | Non-Core 100,000 |  | initiated |  |
| From Principle to Practice: understanding stereotypes that discriminate against women and pave the way for policy reform – Impact Evaluation (gamification platform) |  | Y | UN Women SP Outcome 6 |  | DRF/ Output 6.1.1 | Jordan Co | Arab States/Regional Office | N | All stakeholders involved in the implementation of the project | Q4 2019 | Non-Core 12,772 |  | Pending |  |

| Projects Tracking (internally) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tracking and monitoring of all AWPs to update them regularly | Y | All related UNDAF outcomes related to UN Women SN 2018-2022 | Jordan SN AWPs for all components as stated in the SN 2018-2022 | Jordan CO | Arab States | N |  | JEFE, AWLN, Reach, Sadaqa, JWU, ARDD-Legal Aid, JNCW, IFH, ASK, Generation for Peace, IRCKHF, MOWGLI, AWO, JNFW, FCPS, JPBFW, MoSD, MoL, JAF, Police , Civil Defense, Gendarmerie | 2019 |  | N/A |  | pending | This will be followed up and implemented by the M&E Analyst and each Unit Head |
| Field Visits & observation | Y | All related UNDAF outcomes related to UN Women SN 2018-2022 | Jordan SN AWPs for all components as stated in the SN 2018-2022 | Jordan CO | Arab States | N |  | JEFE, AWLN, Reach, Sadaqa, JWU, ARDD-Legal Aid, JNCW, IFH, ASK, Generation for Peace, IRCKHF, MOWGLI, AWO, JNFW, FCPS, JPBFW, MoSD, MoL, JAF, Police , Civil Defense, Gendarmerie | At regular basis over each year, |  | N/A |  | Pending | According to projects schedule and plan |
| Projects Boards and Steering Committees meetings for all ongoing projects | Y | All related UNDAF outcomes related to UN Women SN 2018-2022 | Jordan SN AWPs for all components as stated in the SN 2018-2022 | Jordan CO | Arab States | N |  | JEFE, AWLN, Reach, Sadaqa, JWU, ARDD-Legal Aid, JNCW, IFH, ASK, Generation for Peace, IRCKHF, MOWGLI, AWO, JNFW, FCPS, JPBFW, MoSD, MoL, JAF, Police , Civil Defense, Gendarmerie | Over all the year( s) at regular basis according to each project management & planning |  | N/A |  | pending | According to projects plans and management arrangements |
| Reporting: internal progress reports | Y | All related UNDAF outcomes related to UN Women SN 2018-2022 | Jordan SN AWPs for all components as stated in the SN 2018-2022 | Jordan CO | Arab States | N | JEFE, AWLN, Reach, Sadaqa, JWU, ARDD-Legal Aid, JNCW, IFH, ASK, Generation for Peace, IRCKHF, MOWGLI, AWO, JNFW, FCPS, JPBFW, MoSD, MoL, JAF, Police , Civil Defense, Gendarmerie |  |  | Over all the year(s) at quarterly basis | N/A |  | Pending |  |
| Financial Reports at quarterly basis | Y | All related UNDAF outcomes related to UN Women SN 2018-2022 | Jordan SN AWPs for all components as stated in the SN 2018-2022 | Jordan CO | Arab States | N | JEFE, AWLN, Reach, Sadaqa, JWU, ARDD-Legal Aid, JNCW, IFH, ASK, Generation for Peace, IRCKHF, MOWGLI, AWO, JNFW, FCPS, JPBFW, MoSD, MoL, JAF, Police , Civil Defense, Gendarmerie |  |  | Over all the year(s) at quarterly basis | N/A |  | Pending |  |
| Projects Annual reports | Y | All related UNDAF outcomes | Jordan SN AWPs for all components as stated in the SN 2018-2022 | Jordan CO | Arab States | N | JEFE, AWLN, Reach, Sadaqa, JWU, ARDD-Legal Aid, JNCW, IFH, ASK, Generation for Peace, IRCKHF, MOWGLI, AWO, JNFW, FCPS, JPBFW, MoSD, MoL, JAF, Police , Civil Defense, Gendarmerie |  |  | Over all the year(s) at quarterly basis | N/A |  | Ongoing at some projects Pending at other ones |  |
| ATLAS Project Management Tools | Y | All related UNDAF outcomes | Jordan SN AWPs for all components as stated in the SN 2018-2022 | Jordan CO | Arab States/ Jordan | N |  | JEFE, AWLN, Reach, Sadaqa, JWU, ARDD-Legal Aid, JNCW, IFH, ASK, Generation for Peace, IRCKHF, MOWGLI, AWO, JNFW, FCPS, JPBFW, MoSD, MoL, JAF, Police, Civil Defense, Gendarmerie |  | Over all the year(s) at quarterly basis |  | N/A | Ongoing at some projects Pending at other ones | This is a mandatory for programme personnel |