MERP Serbia 
Serbia: Monitoring and Research Plan 2019-2021
	Activity 
	Partners and stakeholders 
	Planned Dates (Month and year of start and end)
	Budget

	
	
	
	Source
	Amount

	MONITORING 2019-2021

	Monthly monitoring of status of AWP
	Coordination Body for Gender Equality, Ministry of Finance, Ministry of European Integration, Ministry of Interior, Provincial Secretariat for Demography, Social Welfare and Gender Equality, Provincial Secretariat for Finance, State Audit Institution, Ministry of Justice, selected NGOs, LSGs
	Monthly  
	N/A
	N/A

	Annual review of implementation of AWP
	Coordination Body for Gender Equality, Ministry of Finance, Ministry of European Integration, Ministry of Interior, Provincial Secretariat for Demography, Social Welfare and Gender Equality, Provincial Secretariat for Finance, State Audit Institution, Ministry of Justice, selected NGOs, LSGs
	Annually
	N/A
	N/A

	Monitoring of delivery as per AWP and Project Plans
	Coordination Body for Gender Equality, Ministry of Finance, Ministry of European Integration, Ministry of Interior, Provincial Secretariat for Demography, Social Welfare and Gender Equality, Provincial Secretariat for Finance, State Audit Institution, Ministry of Justice, selected NGOs, LSGs
	Monthly
	N/A
	N/A

	Regular update in the online RBM system
	
	Quarterly
	N/A
	N/A

	Review and response to RO feedback to country quarterly progress reports to ensure the comments are incorporated
	
	Quarterly
	N/A
	N/A

	Preparation and submission of annual narrative and financial report for the project Support to Priority Actions for Gender Equality
	Coordination Body for Gender Equality, Ministry of European Integration, selected NGOs
	Annually
	N/A
	N/A

	Preparation and submission of annual narrative and financial report for the UN Joint Project on Integrated response to violence against women and girls in Serbia II (Completed)
	Coordination Body for Gender Equality, Provincial Secretariat for Demography, Social Welfare and Gender Equality, selected NGOs
	Annually (Completed)
	N/A
	N/A

	Preparation and submission of annual narrative and financial report for the UN Joint Project on Integrated response to violence against women and girls in Serbia III
	Coordination Body for Gender Equality, Ministry of Interior, Ministry of Justice, Ministry of Labor, Employment, Veteran and Social Affairs, Ministry of Health, Ministry of Education, Science and Technological Development, Ministry of Youth and Sports, Commissioner for Protection of Equality, Provincial Secretariat for Social Protection, Demography and Gender Equality, civil society organizations and media.
	Annually
	N/A
	N/A

	Preparation and submission of quarterly (Q5) and the final narrative and financial report for the Gender Responsive Governance-Redistribution of Unpaid Care Work
	Coordination Body for Gender Equality
the Ministry of Labour, Employment, Veterans and Social Affairs, Women CSOs, gender equality mechanism and local self-governments
	Quarterly (Q5) and Final 
	N/A
	N/A

	Preparation and submission of annual narrative and financial report for the UN Joint Project on the rights of persons with disabilities 
	Selected DPOs, OHCHR, ILO, UNFPA, UNDP, Ministry of Labor
	Annually (Completed)
	N/A
	N/A

	Preparation and submission of inputs for annual narrative and financial report for the Serbia component of the Regional EVAW Project
	Coordination Body for Gender Equality, selected NGOs
	Annually
	N/A
	N/A

	Preparation and submission of inputs for annual narrative and financial report for the project Improved Safety of Women in Serbia
	Ministry of Interior (formal partner), Ministry of Justice, Local Self-Governments, Women Parliamentary Network, media houses and associations, Women CSOs
	Annually
	
	

	Preparation and submission of inputs for annual narrative and financial report for the Serbia component of the Regional Gender Responsive Budgeting Project
	Ministry of Finance, Provincial Secretariat of Finance, State Audit Institution, LSGs, direct budget users
	Annually
	N/A
	N/A

	Preparation and submission of inputs for annual narrative and financial report for the Gender Responsive Budgeting at Local Level
	10 municipalities/LSGs, GIZ, 10 local CSOs
	Annually
	
	

	Review of quarterly narrative and financial reports of UNTF Grantees
	selected NGOs
	Quarterly
	N/A
	N/A

	Review of the annual narrative and financial reports of UNTF Grantees
	selected NGOs
	Annually
	N/A
	N/A

	Monitoring of all responsible parties as per LoA and PCA and their activities, outputs and output comes 
	Provincial Secretariat for Demography, Social Welfare and Gender Equality, municipalities, UNTF to EVAW grantees, selected NGOs
	Monthly
	N/A
	N/A

	Conduct monitoring missions to RP and partners
	Provincial Secretariat for Demography, Social Welfare and Gender Equality, municipalities, UNTF to EVAW grantees, selected NGOs
	Quarterly
	N/A
	N/A

	Collect/analyze monitoring data per indicator of outputs and outcomes
	Coordination Body for Gender Equality and selected government institutions, selected NGOs
	Quarterly
	N/A
	N/A

	Monitoring of Consultants and Contactors as per contracts and deliverables timelines
	
	Monthly
	N/A
	N/A

	Monitoring of capacity development efforts by Serbia PP Office
	Selected NGOs and government institution
	Monthly
	N/A
	N/A

	Monitoring of delivery rates
	
	Monthly
	N/A
	N/A

	Monitoring of DPF Outcome on Gender
	UNCT and OGG
	Quarterly
	N/A
	N/A

	Preparation of the Outcome Group on Gender Annual Report
	OGG
	Annually
	N/A
	N/A

	Monitoring of the implementation of the recommendations of the Gender Scorecard
	OGG
	Annually
	N/A
	N/A

	RESEARCH 2019-2021

	Completed:

	Gender Analysis of the economic programs and measures 


	National Alliance for Local Development NALED, EU, Innovation Fund, Ministry of Economy
	January 2019 – June 2019

Completed
	GEF project budget

Donor: EU
	40.000 USD

	Gender Analysis of employment measures
	Ministry of Labour, Employment, Social and Veterans Affairs
	Jan-Dec 2019 
Completed
	Core
	3,000

	Baseline mapping of women and girls with disabilities in top management positions within disabled people’s organizations and women’s civil society organizations in the republic of Serbia
	UNPRPD, Centre for Independent Living
	January 2019
Completed
	Project
	10,000

	Impact of the COVID-19 pandemic on specialist services for victims and survivors of violence in Serbia: A proposal for addressing the needs
	Women CSOs
	April – May 2020
Completed
	
	N/A

	Impact of the COVID-19 pandemic on specialist services for victims and survivors of violence in the Western Balkans and Turkey Report
	UN Serbia, Women CSOs
	June 2020
Completed
	
	

	Assessing the influence of COVID 19 on position of women in different areas: labor, rural women, entrepreneurs, and economy of care. 


	CBGE, MEI, SeCons
	July 2020
Completed
	GEF project budget

Donor: EU
	10,000 USD

	Analysis of Unpaid Care Work
	Coordination Body for Gender Equality
	July 2020
Completed
	Project
Donor DFID
	10,000.00 USD

	Covid-19 Socio Economic Impact Assessment
	UNCT
	July-September 2020
Completed
	
	N/A

	Ongoing:

	Media Reporting on VAWG through the Analysis of their Social Media Accounts during the State of Emergency 2020
	Media
	August – December 2020
Ongoing
	Non-core
	5000 USD

	Gender analysis on energy poverty and 

Gender sensitive inventory on emissions
	EU, Ministry of Energy, RES, SIPRU, MEI
	October – December 2020
Ongoing
	GEF project budget

Donor: EU
	15,000 USD 

	Analysis of urban planning with a focus on public spaces
	EU, Ministry of Infrastructure, ZAD, MEI
	October – December 2020
Ongoing
	
	20.000 USD

	Gender Analysis of legal practices/regulations in the economy of care
	Coordination Body for Gender Equality
	December 2020
Ongoing
	Project donor: DFID
	17,000.00 USD

	Gender analysis of budget reallocations as response to COVID-19 outbreak
	Ministry of Culture and Information, Ministry of Finance, Ministry of Economy and more budget holders TBC
	Ongoing
	Regional GRB Project
	20,000 USD

	Childcare/Early Childhood Education, Women’s Employment and Covid19 in Serbia
	UNECE
	Ongoing
	N/A
	N/A

	Women, Girls, and ICT in the Context of Covid-19 and Post-Covid Recovery: A Study of Select Balkans and European Partnership Countries 


	Regional ECA Office
	September 2020-Ongoing
	N/A
	N/A

	Gender Equality Index
	Republic Statistical Office, CBGE, SIPRU
	November 2020 – January 2021
Ongoing
	GEF project budget

Donor: EU 
	17,500 USD

	Ex-post analysis of National Strategy for Gender Equality 2016-2020
	GEF
	November 2020 – February 2021
Ongoing
	GEF project budget

Donor: EU
	10,000 USD

	Gender analysis of the participation of rural women in the political and decision-making positions
	TBC
	TBC 2021
	Project donor: SDC
	TBC

	Country GE Profile/Brief
	TBC
	TBC 2021
	TBC
	TBC


Serbia: Evaluation Plan 2019-2021
	Evaluation name
	Mandatory

(Y/N)
	UNDAF Outcome/ UN Women SP Goal, Outcome  
	Country/ MCO/ RO AWP Output
	Office in charge
	Region/ country
	Joint activity 
(Y/ N, indicate partners)
	Key Stakeholders
	Planned Dates 

(start-end)
	Budget (US$) / Sources of Funding
	Status (pending/initiated/ongoing/completed)
	Remarks

	Evaluations managed by the office
	

	Final Evaluation of the Gender Equality Facility Project (IPA 2016)
	Yes
	DPF 2016-2020, Pillar 1: Governance and Rule of Law;  

Outcome: 3. By 2020, state institutions and other relevant actors enhance gender equality and enable

UN Women SP Outcome 2: Women lead, participate in, and benefit equally from governance systems.
	Output 1.1.1 Gender equality mechanisms, key national institutions and women' NGOs have knowledge and skills to fulfill their mandates and advance gender
	UN Women Serbia
	Serbia
	No
	Coordination Body for Gender Equality, Ministry for European Integration, women CSOs
	October 2020 –  January 2021
	 USD 20,000/Part of the project budget, donor: EU Commission
	Pending
	N/A

	Evaluations in which the office participates (ex. UNDAF evaluation)
	

	Evaluation of UNDAF/DPF Results Framework
	Yes
	UNDAF Monitoring and Evaluation - An evaluation in the penultimate year of the programme cycle will be conducted to support the formulation of the next DPF. The evaluation will assess the relevance of the DPF outcomes, the effectiveness and efficiency of implementation by partners, and their sustainability and contribution to country priorities.
	/
	Office of the UN Resident Coordinator in Serbia
	Serbia
	Yes
	Government, CSOs
	July 2019 - December 2019
	/
	Completed
	N/A

	Evaluation of the Serbian Component of the “Ending VAW: Implementing Norms, Changing Minds”
	Yes
	Development Partnership Framework 2016-2020, Pillar 1: Governance and Rule of Law;  

Outcome 3: By 2020, state institutions and other relevant actors enhance gender equality and enable women and girls, especially those from vulnerable groups, to live lives free from discrimination and violence.  

UN Women SP Outcome 4: All women and girls live a life free from all forms of violence
	Women’s NGO have knowledge and skills to provide services to women and girls victims of violence
	ECA Regional Office  


	Western Balkans and Turkey 


	No 


	Women CSO

Women’s CSOs


	October 14-18 2019 for the field mission in Serbia; Sept– Nov 2019 for entire evaluation exercise
	N/A
	Field mission in Serbia completed 

Evaluation process completed
	N/A

	Final Evaluation of the UN Joint Project on the rights of persons with disabilities
	Yes
	DPF 2016-2020, Pillar 1: Governance and Rule of Law;  

Outcome: 3. By 2020, state institutions and other relevant actors enhance gender equality and enable

women and girls, especially those from vulnerable groups, to live lives free from discrimination and violence.  
UN Women SP Outcome 4: All women and girls live a life free from all forms of violence
	3.1.4. Increase the capacities of women CSOs, i.e. of women and girls with disabilities to promote the importance of their political, economic, social and health related rights. (Joint PRPD)
	OHCHR
	Serbia
	Yes
OHCHR

UNFPA

UNDP
ILO


	Women CSOs and Disability Persons Organizations, CPE
	August 2020-
Evaluation process was initiated by OHCHR and undertaken by an external consultant
	N/A
	Ongoing
	N/A

	Final Evaluation of the Gender Responsive Governance-Unpaid Care Work Project
	Yes.

Details TBC. 

The Evaluation will be undertaken by the donor, UK DFID.
	DPF 2016-2020, Pillar 1: Governance and Rule of Law;  

Outcome: 3. By 2020, state institutions and other relevant actors enhance gender equality and enable

UN Women SP Outcome 2: Women lead, participate in, and benefit equally from governance systems
	Output 1.1.1 Gender equality mechanisms, key national institutions and women' NGOs have knowledge and skills to fulfill their mandates and advance gender
	TBC
	Serbia
	No
	Coordination Body for Gender Equality, women CSOs
	
	
	Pending
	


3

