## Sheet1
Annex - MONITORING, EVALUATION AND RESEARCH PLAN 2023-2025
Argentina Office - Strategic Note 2023-2025
i. Monitoring and Research Plan 2023-2025
Activity | UN Women SN Outcome | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget
[9 empty] | Source | Amount
MONITORING
Monitoring gender mainstreaming in the implementation of the UNSDCF and wide accountability (UNCT SWAP Gender scorecard and Gender Marker System). | Impact 3. Outcome 3.2 | Output 3.2.2 | Indicator 0.7.b | Y | UN Women Argentina María Luz Vegas | UN System Coordination | 1/2023-12/2025 |  | Staff time | N/A
Submission of corporate mid term and annual progress reports in RMS, preparation of inputs for the UN Women ACRO Annual Report and other required inputs. | OEE Output 5 | Output 5.1 | TBC | Y | UN Women Argentina María Luz Vegas |  | 1/2022-12/2025 |  | Staff time | N/A
Technical assistance and reviews on gender mainstreaming for joint programmes and UN agencies' strategic plans. | Impact 3. Outcome 3.2 | Output 3.2.2 | Indicator 0.7.b | Y | UN Women Argentina María Luz Vegas | UN System Coordination | 1/2022-12/2025 |  | Staff time | N/A
Conduct regular reviews of the work plan, e.g. weekly staff meetings, operations meetings and quarterly/bi-annual reviews, and to ensure implementation of follow up actions | OEE Output 5 | Output 5.1 | TBC | Y | UN Women Argentina María Luz Vegas |  | 1/2022-12/2025 |  | Staff time | N/A
Midterm Review of the Argentina CO Strategic Note | OEE Output 5 | Output 5.1 | TBC | Y | UN Women Argentina María Luz Vegas |  | 3/2024-5/2024 |  | Non-core | USD 15000
Final assesment Technical Assistance to the Argentine Government | OEE Output 5 | Output 5.1 | TBC | Y | UN Women Argentina María Luz Vegas |  | 2023 | Government of Argentina | Staff time | N/A
Final assessment Girls with future | Impact 1- Outcome 1.1 | Output 1.1.2 | Indicator 0.1.e | Y | UN Women Argentina Sabrina Landoni |  | 2024 | Merck Family Foundation | Non-core | USD 2400
Final assessment Technical Assistance to theMinistry of Public Works | Impact 1- Outcome 1.2 | Output 1.2.2 | Indicator 0.4.a | Y | UN Women Argentina Lisa Solmirano |  | 2023 | UNOPS | Non core | USD 2800
RESEARCH
GENDER MAINSTREAMING
Common Country Assessment | Impact 3 - Outcome 3.2 | Output 3.2.2 | Indicator 0.7.b | Y | Argentina María Luz Vegas | UN System | 2023/2024/2025 |  | TBC | TBC
Perfil de País según Igualdad de Género Argentina (PPIG) | Impact 3 - Outcome 3.2 | Output 3.2.2 | Indicator 0.7.b | Y | Argentina María Luz Vegas |  | 2024 |  | TBC | TBC
Analysis of 2020 Census data from a gender and intersectional perspective | Impact 3. Outcome 2 | Output 3.2.1 | Indicator 0.7.b; 0.7.c | Y | Argentina María Luz Vegas |  | 2023 |  | TBC | TBC
WEE
Customize policy interventions according to national priorities to promote Gender Responsive Fiscal Stimulus Packages in Argentina | Impact 1 Outcome 1.2. | Output 1.2.2 | Indicator O.4.a; O.2.c | Y | UN Women Argentina Gimena de León | CIEPP | 01/2022-03/2023 | OSF | Non-Core | USD 10000
Expanding existing costing exercise of Care Policies in Argentina. | Impact 1 Outcome 1.2. | Output 1.2.2 | Indicator O.4.a; O.2.c | Y | UN Women Argentina Gimena de León | CIEPP | 03/2022-03/2023 | OSF | Non-Core | USD 20000
Document identifying viability conditions of businesses to women and LBTI+ as contractors of public infrastructure. | Impact 1 Outcome 1.2 | Output 1.2.1 | Indicator O.4.a; O.7.c | Y | UN Women Argentina Lisa Solmirano | CISCSA | 01/2022-10/2022 | MOP | Non-Core | USD 10000
Set of 4 Manuals to include gender perspective in the cycle of public infrastructure | Impact 1 Outcome 1.2. | Output 1.2.2 | Indicator O.4.a | Y | UN Women Argentina Lisa Solmirano | UNW UNOPS | 11/2021 -06/2023 | MOP | Non-Core | USD 49900
Survey on care needs and strategies in rural areas (to be applied in provinces of Gran Chaco Region) including a care-related mapping of programs, infrastructure and interventions available to rural women, with recommendations for improving the care situation of rural women. | Impact 1 Outcome 1.1 | Output 1.1.2 | Indicator 0.1.e | Y | UN Women Argentina Sabrina Landoni | Lola Mora Foundation | 01/2023-12/2024 | Community care programme | Non-Core | USD 57000
Qualitative study that systematizes the community care services provided by women and other social organizations in the city of Rosario and two municipalities of the GBA and contains a mapping of care programs to address the needs of disadvantaged communities, with recommendations for the strengthening of community care systems. | Impact 1 Outcome 1.1 | Output 1.1.2 | Indicator 0.1.e | Y | UN Women Argentina Sabrina Landoni | Lola Mora Foundation | 01/2023-12/2024 | Community care programme | Non-Core | USD 96000
Analysis of subnational architecture and alternatives for promotion of formal and paid work with social protection for community caregiving workers | Impact 1 Outcome 1.1 | Output 1.1.2 | Indicator 0.1.e | Y | UN Women Argentina Sabrina Landoni | Lola Mora Foundation | 01/2023-12/2024 | Community care programme | Non-Core | USD 29000
EVAW
Study on sexual violence against indigenous women based on "traditional practices" (chineo/rameo) | Impact 2 Outcome 2.1 (SDG 5.2.1) | Output 2.1.2 | Indicator 0.33 | Y Qualitative data on cases of sexual violence | UN Women Argentina Carla Majdalani | Amnistia Argentina TBC | 2/2023-8/2023 | TBC | TBC | USD 15000 TBC
Economic Costs of VAWG - costing excercise on the impact of GBV | Impact 2 Outcome 2.1 (SDG 5.2.1) | Output 2.1.2 | Indicator 0.33 | Y Quantitative data on costs of violence | UN Women Argentina Carla Majdalani | TBC | TBC | TBC | TBC | USD 30000 TBC
GWPS
Study to analyze the pathways in competitive examinations for access to positions in the justice system in Argentina from a gender perspective. | Impact 3 Outcome 3.1 | Output 3.1.1 | Indicator 0.1.e | Y | UN Women Argentina Delfina García Hamilton | Women's Office of the Supreme Court of Justice of the Nation | 2022-2023 |  | Non-Core | USD 6000
Qualitative and quantitative study for the integration of the gender perspective in the planning and implementation of forest and climate change management policies, plans, programs and projects within the REDD+ Payment for Results Project. | Impact 3 Outcome 3.2 | Output 3.2.2 | Indicator 0.7.b | Y | UN Women Argentina Delfina García Hamilton |  | 2023/2024 | FAO | TBC | TBC
Quantitative evaluation of the integration of women in the Armed Forces. | Impact 3 Outcome 3.1 | Output 3.1.1 | Indicator 0.1.e | Y | UN Women Argentina Delfina García Hamilton | Ministry of Defense | 2023 | Government of Argentina | Non-Core | USD 5000
Systematization of impacts and recommendations for improvements for scaling-up strategies and possible replications in the areas of violence, women's participation in public life, human trafficking and migrant smuggling, peace and security, economic empowerment and environmental protection. | Impact 3 Outcome 3.2 | Output 3.2.2 | Indicator 0.7.b | Y | UN Women Argentina Delfina García Hamilton |  | 2023 | ACNUR | Non-Core | USD 2000
Lessons learned from School of Leadership | Impact 3 Outcome 3.1 | Output 3.1.1 | Indicator 0.1.e | Y | UN Women Argentina Dalia Virgil Pino |  | 2023 | Government of Neuquén | Non-Core | USD 20000
ii. Evaluation Plan 2023-2025
Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks
Evaluations managed by the office
Country Portfolio Evaluation of UN Women Argentina Strategic Note 2023-2025 | Y | SP1-4 Cross-cutting | Cross-cutting | UN Women Independent Evaluation Service, IEAS | LAC Argentina |  | 1/2025-6/2025 |  | USD 30000 / Non core
Final evaluation Community Care Programme | Y | SP2- Outcome 4- Women’s equitable access to services, goods & resources | Argentina SN Impact 1- Output 1.1.2 | UN Women Argentina Sabrina Landoni | LAC Argentina | Lola Mora Foundation | 2024 | Community Care Programme | USD 12000 / Non core
Evaluations in wich the office participates
Final Evaluation Spotlight Initiative | Y | DG 5, Outcome 4: All women and girls live a life free from all forms of violence | Argentina SN Impact 2- Output 2.2.2 | UNW Argentina Carla Majdalani | LAC Argentina | Y Spotlight Team Argentina | 1/2023 - 4/2023 (TBC) | MPTF- Spotlight Initiative | USD 21629 Non-Core Donor MPTF Spotlight Initiative EU | Pending | This process is led by HQ. UN Women Argentina has shared the COA for evaluation in August 2022
Final Evaluation of the UNSDCF 2022-2025 | Y | SP1-4 Cross-cutting | Argentina SN Impact 3 - Output 3.2.2 | UN Women Argentina María Luz Vegas | Argentina | UN System Coordination | 2024/2025