NEPAL Country Office

EVALUATION PLAN 2015

Evaluation Plan 2015

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1: Evaluation of Gender Responsive Budget (GRB) Programme of the Government of Nepal | N | UNDAF Outcome 5: Institutions, systems and processes of democratic governance are more accountable, effective, efficient and inclusive | Output 2.3 A clear evidence base generated from high quality evaluations of AWP implementation for learning, decision-making and accountability | Nepal CO | Nepal | N | Ministry of Finance, Ministry of Federal Affairs and Local Development | March 2015 | USD 60,000 (Denmark and GoN) | Ongoing | Evaluation carried over from 2014. |
| Evaluation 2: Mid-term evaluation of Strengthening Implementation of Women, Peace and Security Agenda in Nepal (SIWPSAN) project | Y | UNDAF Outcome 9: National actors and institutions have managed conflict risk and are progressively consolidating the peace UN Women Nepal AWP Development Results Goal 4: Women’s leadership in peace, security and humanitarian response | Output 4.1.1 Government officials [MOPR, MOWCSW and DCC] able to implement and monitor NAP on UNSCRs 1325 and 1820 commitments at the national and local level in collaboration with CSOs Output 4.2.1 Conflict affected women in select districts have voice and agency to influence local decision making processes to sustain peace and demand accountability | Nepal CO | Nepal | N | Ministry of Peace and Reconstruction and Women, Children and Social Welfare, DCCs, Women and Children Office, Civil Society Organizations, Interparty women’s alliance, service provider | February 2015 | 24,000 Noncore | Initiated | Evaluation carried over from 2014. TOR advertised in December 2014. |
| Evaluation 3: Final evaluation of Gender Responsive Recovery for Sustainable Peace (GRRSP) project | Y | UNDAF Outcome 9: National actors and institutions have managed conflict risk and are progressively consolidating the peace | Output 4.1.1 Government officials (MOPR, MOWCSW and DCC) able to implement and monitor NAP on UNSCRs 1325 and 1820 commitments at the national and local level in collaboration with CSOs Output 4.2.1 Conflict affected women in select districts have voice and agency to influence local decision making processes to sustain peace and demand accountability | Nepal CO | Nepal | Y [UN Women, FAO and ILO (UN Women as lead agency) | Ministry of Peace and Reconstruction, Ministry of Women, Children and Social Welfare, and other relevant ministries, local bodies, line ministries, DCCs, conflict affected women, and Civil Society Organizations | February 2015 | 15,000 Noncore | Ongoing | ToR advertised in December 2014 |
| 5. Review Mid-term review of the Country Office SN and related framework (DRF and OEEF) | N |  | Output 2.3 A clear evidence base generated from high quality evaluations of AWP implementation for learning, decision-making and accountability | Nepal CO | Nepal | N |  | Last quarter of 2015 | 10,000 Core |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation 1: Final evaluation of Building Peace in Nepal: Ensuring a Participatory and Secure Transition (EPST) project | Y | UNDAF Outcome 9: National actors and institutions have managed conflict risk and are progressively consolidating the peace | Output 4.1.1 Government officials (MOPR, MOWCSW and DCC) able to implement and monitor NAP on UNSCRs 1325 and 1820 commitments at the national and local level in collaboration with CSOs Output 4.2.1 Conflict affected women in select districts have voice and agency to influence local decision making processes to sustain peace and demand accountability | UNDP and UN Women in Nepal (led by UNDP) | Nepal | Y [UNDP and UN Women] | Ministry of Peace and Reconstructio, Ministry of Women, Children and Social Welfare, and other relevant ministries, local bodies, line ministries, District Coordination Committees, conflict affected women and civil society organizations | Third quarter of 2015 |  |  | To be led by UNDP |
| Evaluation 2: Final evaluation of Rule of Law and Human Rights Programme (RoLHR) | Y | UNDAF Outcome 8: National institutions have addressed conflict-related violations of human rights and international humanitarian law and the post-conflict needs of victims | Output 5.1.7 Supreme and district court judges in (UN Women project areas) have a better understanding of and commitment to gender equality and knowledge on eliminating gender biases in court structures and practices Output 5.1.8 Legal aid centres and referral networks are gender sensitive and implement programmes to promote women’s access to justice in UN Women project districts | Nepal CO | Nepal | UNDP and UN Women (UNDP as lead) | Ministry of Law Justice and Parliamentary Affairs, and other relevant ministries, Courts including district courts, conflict affected women and civil society organizations | Third quarter of 2015 | 49,000 Noncore |  | To be led by UNDP |

Please fill out a separate row for each evaluation.