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NEPAL Country Office
	EVALUATION PLAN 2015	

Evaluation Plan 2015[footnoteRef:1] [1:  Please fill out a separate row for each evaluation.  ] 

	Evaluation name
	Mandatory?
(Y/N)
	UNDAF Outcome/ UN Women SP Goal, Outcome  
	Country/ MCO/ RO AWP Output
	Office in charge
	Region/ country
	Joint activity 
(Y/ N, indicate partners)
	Key Stakeholders
	Planned Dates 
(start-end)
	Budget (US$) / Sources of Funding
	Status (pending/ initiated/ ongoing/ completed)
	Remarks

	Evaluations managed by the office
	

	Evaluation 1: Evaluation of Gender Responsive Budget  (GRB) Programme of the Government of Nepal 
	N
	UNDAF Outcome 
5: Institutions, systems and processes of democratic governance are more accountable, effective, efficient and inclusive 
	Output 2.3
A clear evidence base generated from high quality evaluations of AWP implementation for learning, decision-making and accountability
	Nepal CO
	Nepal
	N
	Ministry of Finance,
Ministry of Federal Affairs and Local Development

	March 2015
	USD 60,000 (Denmark and GoN)
	Ongoing
	Evaluation carried over from 2014.


	Evaluation 2: Mid-term evaluation of  Strengthening Implementation of Women, Peace and Security Agenda in Nepal (SIWPSAN) project
	Y
	UNDAF Outcome 9: National actors and institutions have managed conflict risk and are progressively consolidating the peace 

UN Women Nepal AWP Development Results Goal 4: Women’s leadership in peace, security and humanitarian response
 
	Output 4.1.1 
Government officials [MOPR, MOWCSW and DCC] able to implement and monitor NAP on UNSCRs 1325 and 1820 commitments at the national and local level in collaboration with CSOs

Output 4.2.1 Conflict affected women in select districts have voice and agency to influence  local decision making processes  to sustain peace and demand accountability
	Nepal CO
	Nepal
	N
	Ministry of Peace and Reconstruction and Women, Children and Social Welfare, DCCs, Women and Children Office, Civil Society Organizations, Interparty women’s alliance, service provider
	February 2015
	24,000
Noncore



	Initiated

	Evaluation carried over from 2014. TOR advertised in December 2014.

	Evaluation 3: Final evaluation of Gender Responsive Recovery for Sustainable Peace (GRRSP) project
	Y
	UNDAF Outcome 9: National actors and institutions have managed conflict risk and are progressively consolidating the peace
	 Output 4.1.1 
Government officials (MOPR, MOWCSW and DCC) able to implement and monitor NAP on UNSCRs 1325 and 1820 commitments at the national and local level in collaboration with CSOs

Output 4.2.1 Conflict affected women in select districts have voice and agency to influence  local decision making processes  to sustain peace and demand accountability

	Nepal CO
	Nepal
	Y [UN Women, FAO and ILO (UN Women as lead agency)
	Ministry of Peace and Reconstruction, Ministry of Women, Children and Social Welfare, and other relevant ministries, local bodies, line ministries, DCCs, conflict affected women, and Civil Society Organizations
	February 2015
	15,000
Noncore
	Ongoing
	ToR advertised in December 2014

	5. Review 
Mid-term review of the Country Office SN and related framework (DRF and OEEF)
	N
	
	Output 2.3
A clear evidence base generated from high quality evaluations of AWP implementation for learning, decision-making and accountability
	Nepal CO
	Nepal 
	N
	
	Last quarter of 2015
	10,000
Core
	
	

	Evaluations in which the office participates

	

	Evaluation 1: Final evaluation of Building Peace in Nepal: Ensuring a Participatory and Secure Transition (EPST) project

	Y
	UNDAF Outcome 9: National actors and institutions have managed conflict risk and are progressively consolidating the peace
	Output 4.1.1 
Government officials (MOPR, MOWCSW and DCC) able to implement and monitor NAP on UNSCRs 1325 and 1820 commitments at the national and local level in collaboration with CSOs

Output 4.2.1 Conflict affected women in select districts have voice and agency to influence  local decision making processes  to sustain peace and demand accountability

	UNDP and UN Women in Nepal 
(led by UNDP)
	Nepal
	Y [UNDP and UN Women]
	Ministry of Peace and Reconstructio, Ministry of Women, Children and Social Welfare, and other relevant ministries, local bodies, line ministries, District Coordination Committees, conflict affected women and civil society organizations
	Third quarter of 2015
	
	[bookmark: _GoBack]
	To be led by UNDP

	Evaluation 2: Final evaluation of Rule of Law and Human Rights  Programme (RoLHR)



	Y
	UNDAF Outcome 8: National institutions have addressed conflict-related violations of human rights and international humanitarian law and the post-conflict needs of victims
	Output 5.1.7 
Supreme and district court judges in (UN Women project areas) have a better understanding of and commitment to gender equality and knowledge on eliminating gender biases in court structures and practices 

Output 5.1.8
Legal aid centres and referral networks are gender sensitive and implement programmes  to promote  women’s access to justice in UN Women project districts
	Nepal CO
	Nepal
	UNDP and UN Women (UNDP as lead)
	Ministry of Law Justice and Parliamentary Affairs, and other relevant ministries, Courts including district courts, conflict affected women and civil society organizations
	Third quarter of 2015
	49,000
Noncore
	


	To be led by UNDP




1

image1.wmf

