## 2013 Indi&MCO
MONITORING, EVALUATION AND RESEARCH PLAN 2013
INDIA MULTI COUNTRY OFFICE, NEW DELHI
Title & Type of MER activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome | Relevant Country/ SRO AWP Output | Office to manage the MER activity | Region, Sub Region or Country | Joint MER activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-completion) | Budget (US$) for MER activity/ Sources of Funding | Status (pending - initiated – ongoing - completed) | Remarks
2013
1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc.
DRF Goal 1: Women’s increased leadership and participation in the decisions that affect their lives
Training assessment of the training workshops with government officials at the district level by NIRD and 5 state SIRDs for 15 districts | N | India AWP DRF Outcome 1.1: Enabling environment created to promote women’s political participation in select states. | India AWP DRF Output 1.1.3: National and state training institutions have enhanced capacity to strengthen knowledge of Government officials at State, District and Block levels on gender equality obligations of local governments and PRIs | India | MCO | N | Lal Bahadur Shastri National Academy of Administration (LBSNAA) National Institute of Rural Development (NIRD) State Institute of Rural Development (SIRD) | March 2013 | NIL | Ongoing | Governance
Compilation of Monthly progress report received from District Project Officers | N |  | Output 1.1.2: Elected women representatives in local government have the knowledge and capacity to influence policies, programmes and resource allocation for gender sensitive governance in 2 states in India, by 2013 | India | MCO | N |  | Jan- Dec 2013 | NIL | Ongoing | M&E
DRF Goal 2: Increased economic empowerment of women, especially of those who are most excluded
Baseline Survey of the SEWA Bharat Project | N | India AWP MRF Goal 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women | India AWP MRF Output 2.3 A clear evidence base generated from high quality evaluations on SP implementation for learning, decision making and accountability | India | MCO | N | Individual Consultant | Jan - Mar 2013 | 9000 | Initiated | M&E and WEE
Baseline Survey of the Home Net India Project | N |  |  | India | MCO | N |  |  |  | Initiated | M&E and WEE
Training assessment of NRLM and MKSP | N |  | India AWP Output 2.2.2: Civil society organizations (in Bihar and Madhya Pradesh) selected by Ministry of Rural Development, GOI have enhanced capacity to incorporate gender responsive approaches in the implementation of Mahila Kisan Sashaktikaran Pariyojna (MKSP)– a major component of National Rural Livelihood Mission for women farmers by 2013 | SASRO | India | N | Ministry of Rural Development & partner NGO | April - June 2013 | 8000 | Pending | WEE
Quarterly progress report from all the partners (SEWA Bharat, Home Net India) | N |  |  | SASRO | India | N | SEWA Bharat | Jan - Dec 2013 | NIL | pending | WEE
Annual progress reports from SEWA Bharat and Home Net India | N |  |  | SASRO | India | N | Home Net India | Oct - Dec 2013 | NIL | pending | WEE
DRF Goal 3: Prevent violence against women and girls and expand access to victim/survivor services
Annual Progress Report from the project partners of "Empowerment of Widows and their Coalitions" and Anti Human Trafficking | N | Outcome 3.1 Policies, strategies and programmes on preventing gender-biased sex selection and violence against women and girls are adopted/implemented | India AWP DRF Output 3.1.1 UN Women partners in 2 project areas have enhanced knowledge on developing multi-sectoral strategies to address trafficking in women and girls India AWP DRF Output 3.1.5 Capacity of widows enhanced to access VAW services (free legal and counseling) in the project areas | India | MCO | N | ASTHA, GfS, SANLAAP, FXB, CBATN, AID India, CECODECON | July 2013 | Nil | pending | EVAW
Quarterly Progress Report from the project partners of "Empowerment of Widows and their Coalitions" and Anti Human Trafficking | N |  |  | India | MCO | N | ASTHA, GfS, SANLAAP, FXB, CBATN, AID India, CECODECON | Jan - Dec 2013 | Nil | initiated | EVAW
DRF Goal 5: Government and civil society institutions are responsive and accountable for improving women’s position, advancing their social, political, economic rights and preventing gender discrimination
Annual Donor Report prepared for FORD Funded project | N | Outcome 5.2 Processes/Mechanisms for monitoring implementation of gender equality commitments regularly generate analysis and evidence on gaps and performance at the national level and in select states. | Output 5.2.1 Select government agencies (Ministry of Women and Child Development, Reserve Bank of India), women’s rights organizations and budget groups have enhanced knowledge and skills on gender analysis in planning and budgeting. | India | MCO | N |  | March 2013 |  | Completed | GRB, M&E
Quarterly Progress Report from the project implementing partners Swadhikar, North East Network, NFI and Social Watch | N |  |  | India | MCO | N | Swadhikar, North East Network, NFI and Social Watch | Jan-Dec 2013 |  | Ongoing | GRB, M&E
MRF Goal 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women
Assessment of the M&E capacity building trainings for the UN WOMEN staff members | N | MRF Goal 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women | SASRO AWP Output 2.1.1 Improved monitoring and reporting on AWP and joint UNDAF outputs | India | MCO | N | TBD | July-Aug 2013 | 10000 | Initiated | M&E
18 Monitoring visits to the project areas to monitor the progress of the project implementation | N |  |  | India | MCO | N | TBD | Jan-Dec 2013 | 14000 | ongoing | M&E
Web based Project Monitoring and Reporting System for monitoring and reporting of all the projects in India Multi Country office | N |  |  | India | MCO | N | Velocity | Jan-Dec 2013 | 15000 | ongoing | M&E
2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc.
MRF Goal 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women
Mid Term Evaluation of the Anti Human Traffiking programme | N | India AWP MRF Goal 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women | India AWP MRF Output 2.3 A clear evidence base generated from high quality evaluations on SP implementation for learning, decision making and accountability | India | MCO | N | Ernst & Young Pvt. Ltd. | May - July 2013 | 31000 | Ongoing | M&E EVAW
Baseline evaluation of the Safe Cities programme | N |  |  | India | MCO | N | ICRW | Jan - May 2013 | 50000 | Completed | M&E and Safe Cities
Impact Assessment of the RBI-CAB training under the Gender Responsive Budgeting programme in India | N |  |  | India | MCO | Y | RBI-CAB | March 2013 | NIL | Completed | M&E and GRB
2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors etc.
MRF Goal 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women
Corporate Evaluation of the EVAWG | N | India AWP MRF Goal 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women | India AWP MRF Output 2.3 A clear evidence base generated from high quality evaluations on SP implementation for learning, decision making and accountability | India | MCO | N | Universalia | Jan 2013 | TBD | Completed | M&E and EVAW
Mid Term Review of the FGE-PRADAN programme | N | India AWP MRF Goal 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women | India AWP MRF Output 2.3 A clear evidence base generated from high quality evaluations on SP implementation for learning, decision making and accountability | India | MCO | N | Sadhbhawana Trust | April - May 2013 | 18000 | Ongoing | M&E and FGE
3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans
DRF Goal 2: Increased economic empowerment of women, especially of those who are most excluded
Research report on social-cultural barriers that prevent implementation of the Hindu Succession (Amendment Act) 2005 in context of women agricultural producers | N | India AWP DRF Outcome 2.1 – Relevant Government Agencies, Policy Makers and CSOs have increased access to and are able to use the study on socio-cultural barriers that prevent the implementation of Hindu Succession (Amendment Act) 2005, in context of women agricultural producers | India AWP DRF Output 2.1.1 Evidence based research and advocacy on social-cultural barriers that prevent implementation of the Hindu Succession (Amendment Act) 2005 in context of women agricultural producers completed by 2012 | MCO | INDIA | N | LANDESA | March - April 2013 | USD 46,000 | Ongoing | WEE
Research Study on Women’s Rights to Social Protection | N |  |  | MCO | INDIA | N | TBD | TBD | TBD | initiated | WEE
DRF Goal 3: Prevent violence against women and girls and expand access to victim/survivor services
Research study on Gaps in programme and policies for widows | N | Outcome 3.1 Policies, strategies and programmes on preventing gender-biased sex selection and violence against women and girls are adopted/implemented | India AWP DRF Output 3.1.5 Capacity of widows enhanced to access VAW services (free legal and counseling) in the project areas | India | MCO | N |  | Jan-June 2013 | 13000 | Completed | EVAW/Anju
Research study on Preventing trafficking in women & girls ; community based models of prevention | N |  | India AWP DRF Output 3.1.1 UN Women partners in 2 project areas have enhanced knowledge on developing multi-sectoral strategies to address trafficking in women and girls | India | MCO | N | TBD | TBD | 40000 | pending | EVAW/Anju
MRF Goal 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women
Individual and Organizational capacity assessment ; A Guidance Note | N | India AWP MRF Goal 2: A culture of results-based programming, reporting, knowledge-management and evaluation comprehensively institutionalized across UN-Women | India AWP MRF Output 2.3 A clear evidence base generated from high quality evaluations on SP implementation for learning, decision making and accountability | India | MCO | N | TBD | TBD | 1500 | Initiated | M&E
Publication on Gender and Evaluation | N |  |  | India | MCO | N | TBD | TBD | 1500 | Initiated | M&E

## Sheet1
5