MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2018

| MONITORING |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
|  |  |  |  |  | Source | Amount |
| All areas | Field visits | Program Specialist Project Coordinator | UNW Partners | Quarterly | Core Non-core | N/A |
| All Areas | Monitoring of the Strategic Note | Program Specialist | UNW CO Staff | Quarterly RMS | Core | N/A |
| All Areas | Elaboration of CO annual report | Program Specialist | UNW CO Staff | Annually RMS | Core | N/A |
| All Areas | Prepare quarterly update procurement and recruitment plans | Procurement Associate and Program Team | UNW CO Staff | Quarterly | Core | N/A |
| All areas | Donor reports delivered | Program Team/donor focal point | UNW CO Staff | Yearly | Core | NA |
| All areas | Asset verification | Assets Focal Point | UNW CO Staff | Yearly | Core | N/A |
| All areas | Monthly Financial Monitoring | Representative, Program and Finance Team | Regional Office | Monthly | Core | N/A |
| All areas | Mid Term Review of the UNDAFF | OCR | UNW CO , UN SYSTEM | Mid 2018 | Core | NA |
| All areas | Mid Term Review of the Strategic Note | CO | UNW CO | Mid 2018 | Core | NA |
| OEEF | Implementation of UNDSS Security Standards | Representative and Security focal point | UNW CO | Yearly | Core | N/A |

| RESEARCH |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |  |
|  |  |  | Source | Amount |  |
| National report on parity democracy in El Salvador. | UN Women and GPM, UIM, ANDRYSAS, PDDH. | 2018 | Core | 7,000 |  |
| Comprehensive National Policy for Indigenous, Rural and Peasant Women | Policy Driving Group | 2018 | CORE | 5,000 |  |
| CEDAW report, CWS report and SDG´s report. | UN Women and partners | 2018 | Core | 8,000 |  |
| Learning Curriculum for politician women | UN Women and Civil Society | 2018 | Basque Government | 14,000 |  |
| Opinion pool on the quality of service of UNIMUJER | Civil National Police, PNC | 2018 | Core and Non Core Basque Government | 20,395 |  |
| Pilot experience to identify obstacles to access to specialized justice. | Justice sector | 201 | Core and Basque Government | 25,000 |  |
| Analysis of cases and resolutions issued within the framework of specialized jurisdiction | Justice sector | 2018 | Core | 15,000 |  |
| Updating of Guidelines and Profile of UNIMUJER | PNC | 2018 | Non Core | 15,072 |  |

| EVALUATION |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ Country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |

# Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Final evaluation of the Strategic Note |  | High: necessary conditions in place to assess key aspects of the SN |  |